## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER | REVISION TYPE
1010000002 | SDG&E | 2026-05-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment |  | WMP.0473 | Project | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | 08.02.02 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition | Quantitative | Miles | No | WMP.0473-Strategic Undergrounding |  | 2026 | 1 | 1.38 |  | Completed |  | Addition of Strategic Undergrounding completed miles due to data lag in source system. Columns changed: QUANT YTD VALUE | 2026-07-31 | 1 | MODIFY
1010000014 | SDG&E | 2026-05-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Overhead Patrol Inspections |  | WMP.0488 | Program | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0488-Distribution Overhead Patrol Inspections |  | 2026 | 1 | 28315 |  | In Progress |  | Addition of 49 inspections to the Distribution Overhead Patrol Inspections Program (WMP.0488) due to completion lag in source system. Columns changed: QUANT YTD VALUE | 2026-07-31 | 1 | MODIFY
1010000025 | SDG&E | 2026-05-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Corrective Maintenance Program |  | WMP.1434 | Program | Ensure SDG&E repair procedures are being adhered to | Ensure SDG&E repair procedures are being adhered to | 08.05 | Equipment ignition likelihood | Quantitative | OH Fire or Safety Related Corrective Actions | No | WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program |  | 2026 | 1 | 3.7% |  | In Progress |  | Removed non-HFTD records within QA/QC of Corrective Maintenance Program (WMP.1434) to align with the WMP scope for this initiative. Columns changed: QUANT YTD VALUE | 2026-07-31 | 1 | MODIFY
1010000029 | SDG&E | 2026-05-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of Strategic Undergrounding Program |  | WMP.1497 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program |  | 2026 | 1 | 7.8% |  | In Progress |  | Addition of QA/QA of Strategic Undergrounding records due to data lag in source system. Columns changed: QUANT YTD VALUE, STATUS | 2026-07-31 | 1 | MODIFY
1010000054 | SDG&E | 2026-05-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality assurance/quality control of Pole Clearing |  | WMP.1507 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Poles Cleared | No | WMP.1507-Quality assurance/quality control of Pole Clearing |  | 2026 | 1 | 294 |  | In Progress |  | Removal of records associated with pre-inspection audits. Columns changed: QUANT YTD VALUE | 2026-07-31 | 1 | MODIFY
1010000053 | SDG&E | 2026-05-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality assurance/quality control of Pole Clearing |  | WMP.1495 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1495-Quality assurance/quality control of Pole Clearing |  | 2026 | 1 | 31.18 |  | In Progress |  | Removal of records associated with pre-inspection audits. Columns changed: QUANT YTD VALUE | 2026-07-31 | 1 | MODIFY

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SDG&E | 2026 | 1 | 1396 |  |  | Not applicable | Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SDG&E | 2026 | 1 | 13692 |  | 15088 |  | Addition of 49 inspections to the Distribution Overhead Patrol Inspections Program (WMP.0488) due to completion lag and Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SDG&E | 2026 | 1 | 62 |  |  | Not applicable | Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SDG&E | 2026 | 1 | 13116 |  | 13227 |  | Addition of 49 inspections to the Distribution Overhead Patrol Inspections Program (WMP.0488) due to completion lag and Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SDG&E | 2026 | 1 | 0 |  |  | Not applicable | Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility | SDG&E | 2026 | 1 | 61.9879 |  |  | Not applicable | Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility | SDG&E | 2026 | 1 | 538.072 |  | 600.0598 |  | Addition of 49 inspections to the Distribution Overhead Patrol Inspections Program (WMP.0488) due to completion lag and Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility | SDG&E | 2026 | 1 | 2.8583 |  |  | Not applicable | Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility | SDG&E | 2026 | 1 | 506.421 |  | 511.2508 |  | Addition of 49 inspections to the Distribution Overhead Patrol Inspections Program (WMP.0488) due to completion lag. | 2026-07-31 | 1
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility | SDG&E | 2026 | 1 | 0 |  |  | Not applicable | Updated inspection method labeling to “Ground Inspection” for all records in Distribution Overhead Patrol Inspection Program (WMP.0488), to align with WMP descriptions. | 2026-07-31 | 1
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 3 |  | 5 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 14 |  | 15 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 107 |  | 135 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 30 |  | 36 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 287 |  | 471 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 26 |  | 32 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 30 |  | 32 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 124 |  | 134 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 625 |  | 1150 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 174 |  | 205 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 881 |  | 1100 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections | SDG&E | 2026 | 1 | 8 |  | 9 |  | Updated to include the telecom (CIP) related findings | 2026-07-31 | 1

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | ACTUAL VALUE | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER | REVISION TYPE

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 11
METRIC NUMBER | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY (IF BLANK THIS REFERS TO ALL ACTIVITIES UNDER THE INITIATIVE) | EXPENSE TYPE | HFTD TIER | UNIT(S) | UTILITY MITIGATION ACTIVITY TRACKING IDS | PRIMARY DRIVER TARGETED | SECONDARY DRIVERS TARGETED | YEAR INITIATED | MOST RECENT PROCEEDING | MEMORANDUM ACCOUNT | CURRENT COMPLIANCE STATUS | ASSOCIATED RULES | OTHER SPEND CATEGORY | COMMENTS | UTILITY ID | ORIGINAL REPORTING YEAR | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER | REVISION TYPE