## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER | REVISION TYPE
1010000030 | PC | 2026-05-01 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of cFCI |  | SA-07 | Program | Line Sensors: cFCI Distribution | Conductor mounted sensors with embedded communications modules that monitor conductor current, electric field intensity, and alarm on the detection of fault currents and loss of electric field associated system outages | 10.3.1 | Equipment ignition likelihood | Quantitative | Devices | No |  |  | 2026 | 1 | 13 |  | In Progress |  | As reflected in the Q1 Spatial filing for the Other Initiative Point feature class, the number of units represented in column M for the 5 entries is 13, necessitating the change in QUANT YTD VALUE from 5 to 13 | 2026-11-02 | 2 | MODIFY
1010000031 | PC | 2026-05-01 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of SCAN |  | SA-08 | Program | Circuit Breaker/Recloser Monitoring: SCAN | Substation control advanced network (SCAN) automatically retrieves and archives enriched event data from protective relays; the data collected includes sequence of event (SOE) logs and COMTRADE event files associated with breaker operations, overcurrent faults and high-impedance faults | 10.3.1 | Equipment ignition likelihood | Quantitative | Locations | No |  |  | 2026 | 1 | 9 |  | In Progress |  | Upon identifying an incorrect number of entries in the Other Initiative Point spatial feature class for Q1 it was determined that the QUANT YTD VALUE would need to be changed from 7 to 9, with the necessary supporting spatial data | 2026-11-02 | 2 | MODIFY
1010000032 | PC | 2026-05-01 | Situational Awareness and Forecasting | Grid Monitoring Systems | Distribution Protective Settings Review |  | SA-09 | Program | Distribution Protective Settings Review | Replace old electromechanical protection devices, like reclosers and relays, with new microprocessor-based devices | 10.3.1 | Equipment ignition likelihood | Quantitative | N/A | No |  |  | 2026 | 1 | 17 |  | In Progress |  | After reviewing the number of activities completed in Q1, it was determined that the QUANT YTD VALUE would need to be changed from 13 to 17 | 2026-11-02 | 2 | MODIFY
1010000022 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission Pole Replacement and reinforcements |  | GH-03 | Program | Transmission Pole Replacement and reinforcements | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | 8.2.4 | Contact by object ignition | Quantitative | Transmission Poles | No |  |  | 2026 | 2 | 116 |  | In Progress |  | Upon identifying an incorrect number of entries in the Grid Hardening Point spatial feature class for Q2 it was determined that the QUANT YTD VALUE would need to be changed from 127 to 116, with the necessary supporting spatial data | 2026-11-02 | 2 | MODIFY
1010000024 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Expulsion fuse replacement |  | GH-05 | Project | Expulsion fuse replacement | Install new and CAL FIRE-approved non-expulsion fuses including power fuses and current limiting fuses to replace existing expulsion fuse equipment | 8.2.12 | Equipment ignition likelihood | Quantitative | Fuse locations | No |  |  | 2026 | 2 | 948 |  | In Progress |  | Upon identifying that one of the spatial data entries in Q2 will have had an isolation bank with solid blades on the load side, it was confirmed that activity would not count towards the initiative target and the QUANT YTD VALUE would need to be decreased from 949 to 948, with the necessary supporting spatial data | 2026-11-02 | 2 | MODIFY
1010000030 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of cFCI |  | SA-07 | Program | Line Sensors: cFCI Distribution | Conductor mounted sensors with embedded communications modules that monitor conductor current, electric field intensity, and alarm on the detection of fault currents and loss of electric field associated system outages | 10.3.1 | Equipment ignition likelihood | Quantitative | Devices | No |  |  | 2026 | 2 | 13 |  | In Progress |  | As reflected in the Q1 Spatial filing for the Other Initiative Point feature class, the number of units represented in column M for the 5 entries is 13, necessitating the change in QUANT YTD VALUE from 5 to 13 | 2026-11-02 | 2 | MODIFY
1010000031 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of SCAN |  | SA-08 | Program | Circuit Breaker/Recloser Monitoring: SCAN | Substation control advanced network (SCAN) automatically retrieves and archives enriched event data from protective relays; the data collected includes sequence of event (SOE) logs and COMTRADE event files associated with breaker operations, overcurrent faults and high-impedance faults | 10.3.1 | Equipment ignition likelihood | Quantitative | Locations | No |  |  | 2026 | 2 | 10 |  | In Progress |  | Upon identifying an incorrect number of entries in the Other Initiative Point spatial feature class for Q2 it was determined that the QUANT YTD VALUE would need to be changed from 7 to 10, with the necessary supporting spatial data | 2026-11-02 | 2 | MODIFY
1010000032 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Distribution Protective Settings Review |  | SA-09 | Program | Distribution Protective Settings Review | Replace old electromechanical protection devices, like reclosers and relays, with new microprocessor-based devices | 10.3.1 | Equipment ignition likelihood | Quantitative | N/A | No |  |  | 2026 | 2 | 33 |  | In Progress |  | After reviewing the number of activities completed in Q2, it was determined that the QUANT YTD VALUE would need to be changed from 30 to 33 | 2026-11-02 | 2 | MODIFY
Note on Y6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Schiedler, Kevin (PacifiCorp) confirm this change description matches your intent and details the technical language accurately.

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | ACTUAL VALUE | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER | REVISION TYPE

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | UTILITY ID | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 11
METRIC NUMBER | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY (IF BLANK THIS REFERS TO ALL ACTIVITIES UNDER THE INITIATIVE) | EXPENSE TYPE | HFTD TIER | UNIT(S) | UTILITY MITIGATION ACTIVITY TRACKING IDS | PRIMARY DRIVER TARGETED | SECONDARY DRIVERS TARGETED | YEAR INITIATED | MOST RECENT PROCEEDING | MEMORANDUM ACCOUNT | CURRENT COMPLIANCE STATUS | ASSOCIATED RULES | OTHER SPEND CATEGORY | COMMENTS | UTILITY ID | ORIGINAL REPORTING YEAR | PRIOR REPORTED VALUE | PRIOR REPORTED BLANK MEANING | UPDATED VALUE | UPDATED BLANK MEANING | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | ORIGINAL REPORTING YEAR | ORIGINAL REPORTING QUARTER | CHANGE DESCRIPTION | REVISION SUBMISSION DATE | REVISION SUBMISSION NUMBER | REVISION TYPE