## Subparts 1, 2
| Mitigation | Projected Average Project Duration per Circuit Mile of Projects Expected to be Completed in 2025* | Average Project Duration per Circuit Mile of Projects Completed from January 1, 2021 to June 30, 2024* | Notes
i | Covered Conductor Installation; | Fire Rebuild: 3486 days/mile Base SH: 540 days/mile | Fire Rebuild: 221 days/mile Base SH: 242 days/mile | The reported values are an average of duration per mitigated mile installed and does not reflect actual project durations. The data used to calculate days/mile for Forecasted work is based on estimated data that is currently available. Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs Some ordersdo not currently have the necessary data in our system of record to calculate the project duration, those orders have been omitted from the calculation of the reported average.
ii | Undergrounding; | Fire Rebuild: 332 days/mile Base SH: 247 days/mile | Fire Rebuild: 310 days/mile Base SH: 296 days/mile | The reported values are an average of duration per mitigated mile installed and does not reflect actual project durations. The data used to calculate days/mile for Forecasted work is based on estimated data that is currently available. Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs Some ordersdo not currently have the necessary data in our system of record to calculate the project duration, those orders have been omitted from the calculation of the reported average.
iii | Distribution Pole Replacements and Reinforcements; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
iv | Distribution Traditional Hardening; | N/A | N/A | We do not have a separate program for overhead system component hardening that aligns with the updated OEIS definition of traditional overhead hardening. Please see Section 8.1.2.5.2 of our 2023-2025 WMP.
v | Transmission Pole/Tower Protections and Reinforcements; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
vi | Transmission Traditional Hardening; | 52 | 52 | Please note that we do not have a projected average project duration per circuit mile beyond historical average.
vii | Transmission Shunt Splices; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
viii | Distribution Protective Devices; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
ix | Breakaway Connector; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
x | Surge Arrestor Removal/Replacement; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xi | Distribution Motorized Switch Operator (MSO) Replacements; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xii | Non-Exempt Expulsion Fuse Removal/Replacement; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xiii | Microgrids, including remote grids; | Fire Rebuild: N/A Base SH: 298 days/mile | Fire Rebuild: N/A Base SH: 221 days/mile | Please note, data is included for Remote Grid work only. The reported values are an average of duration per mitigated mile installed and does not reflect actual project durations. Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs Some ordersdo not currently have the necessary data in our system of record to calculate the project duration, those orders have been omitted from the calculation of the reported average.
xiv | Avian/animal protection plan; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xv | Enhanced Powerline Safety Settings (EPSS); |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xvi | Distribution, Transmission, and Substation: Fire Action Schemes and Technology (DTS-FAST); |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xvii | Downed Conductor Detection (DCD); |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xviii | Rapid Earth Fault Current Limiter (REFCL); |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xix | Pole Mounted Sensors; |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xx | Early Fault Detection (EFD); |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xxi | Distribution Fault Anticipation (DFA); |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xxii | Smart Tape |  |  | N/A - NOT MEASURED BY CIRCUIT MILE

## Subparts 3, 4
| Mitigation | Factors resulting in projects completed from January 1, 2021 to June 30, 2024, with duration unit 20% more than the average. | Discussion of how factors impact duration | Factors resulting in projects completed from January 1, 2021 to June 30, 2024, with duration per unit 20% less than the average. | Discussion of how factors impact duration | Notes
i | Covered Conductor Installation; | Estimating: -agency permit requests (CalTrans, FERC, BLM, etc.) -access (easements, private property) -environmental concerns/considerations (biological, cultural) -encroachment permits, restricted work windows -iterations and revisions of design -learning curve in incorporating design standards Construction: -weather that limits safe work (ex: snow) -challenging terrain (ex: steep grade, hard rock) -geographically restricted areas (ex: narrow roads that have restrictive traffic controls and limited space for crews) -crew availability -permissible work hours (limited to specific hours and days of week) -environmental concerns/considerations (biological, cultural) -material procurement (ex: specialized tranformers) -sequencing; jobs have to be completed in a particular order, certain sections may be dependent on the completion of a preceding section -restricted safe access to construction site -location of work (work time includes travel to/from site) Portfolio Planning: A project may have started estimating, but may have been put on hold (ex: 2023 GRC decision to decrease undergrounding miles and increase overhead hardening miles). Duration would reflect the original design/estimating start date through completion of construction with no breaks in between. | These factors entail additional time that could contribute to a higher than average project duration. | Estimating: -no agency permits needed -limited land rights required Construction: -no work restrictions (days/hours) -good soil conditions for trenching -no environmental restrictions -workable environment (weather, access) -multiple access points to site | These factors could contribute to lower than average project duration because there are less dependencies or restrictions on the work.
ii | Undergrounding; | Estimating: -agency permit requests (CalTrans, FERC, BLM, etc.) -access (easements, private property) -environmental concerns/considerations (biological, cultural) -encroachment permits, restricted work windows -iterations and revisions of design -learning curve in incorporating design standards Construction: -weather that limits safe work (ex: snow) -challenging terrain (ex: steep grade, hard rock) -geographically restricted areas (ex: narrow roads that have restrictive traffic controls and limited space for crews) -crew availability -permissible work hours (limited to specific hours and days of week) -environmental concerns/considerations (biological, cultural) -material procurement (ex: specialized tranformers) -sequencing; jobs have to be completed in a particular order, certain sections may be dependent on the completion of a preceding section -restricted safe access to construction site -location of work (work time includes travel to/from site) Portfolio Planning: A project may have started estimating, but may have been put on hold (ex: 2023 GRC decision to decrease undergrounding miles and increase overhead hardening miles). Duration would reflect the original design/estimating start date through completion of construction with no breaks in between. | These factors entail additional time that could contribute to a higher than average project duration. | Estimating: -no agency permits needed -limited land rights required Construction: -no work restrictions (days/hours) -good soil conditions -no environmental restrictions -workable environment (weather, access) -multiple access points to site Fire Rebuild projects typically entail less permiting, dependencies, and work restrictions in comparison to Base System Hardening projects | These factors could contribute to lower than average project duration because there are less dependencies or restrictions on the work.
iii | Distribution Pole Replacements and Reinforcements; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
iv | Distribution Traditional Hardening; | N/A | N/A | N/A | N/A | We do not have a separate program for overhead system component hardening that aligns with the updated OEIS definition of traditional overhead hardening. Please see Section 8.1.2.5.2 of our 2023-2025 WMP.
v | Transmission Pole/Tower Protections and Reinforcements; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
vi | Transmission Traditional Hardening; | Weather, Extensive use of Helicopters, Access, Improve or repair access roads, Clearance availability, extensive Crane Use | Weather, heavy rain, heavy snow, high winds all can increase the duration of the porject, improving or repairing access roads increases the cost, | Good weather, limited use of helicopters, easy access, roads in good condition, short Clearance | All of the factors mentioned reduce the number of days it takes to complete work | Please note that we do not have a projected average project duration per circuit mile beyond historical average.
vii | Transmission Shunt Splices; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
viii | Distribution Protective Devices; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
ix | Breakaway Connector; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
x | Surge Arrestor Removal/Replacement; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xi | Distribution Motorized Switch Operator (MSO) Replacements; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xii | Non-Exempt Expulsion Fuse Removal/Replacement; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xiii | Microgrids, including remote grids; | Estimating: -agency permit requests (CalTrans, FERC, BLM, etc.) -access (easements, private property) -environmental concerns/considerations (biological, cultural) -encroachment permits, restricted work windows -iterations and revisions of design -learning curve in incorporating design standards Construction: -weather that limits safe work (ex: snow) -challenging terrain (ex: steep grade, hard rock) -geographically restricted areas (ex: narrow roads that have restrictive traffic controls and limited space for crews) -crew availability -permissible work hours (limited to specific hours and days of week) -environmental concerns/considerations (biological, cultural) -material procurement (ex: specialized tranformers) -sequencing; jobs have to be completed in a particular order, certain sections may be dependent on the completion of a preceding section -restricted safe access to construction site -location of work (work time includes travel to/from site) Portfolio Planning: A project may have started estimating, but may have been put on hold (ex: 2023 GRC decision to decrease undergrounding miles and increase overhead hardening miles). Duration would reflect the original design/estimating start date through completion of construction with no breaks in between. |  | Estimating: -no agency permits needed -limited land rights required Construction: -no work restrictions (days/hours) -good soil conditions -no environmental restrictions -workable environment (weather, access) -multiple access points to site | These factors could contribute to lower than average project duration because there are less dependencies or restrictions on the work. | Please note, data is included for Remote Grid work only.
xiv | Avian/animal protection plan; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xv | Enhanced Powerline Safety Settings (EPSS); |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xvi | Distribution, Transmission, and Substation: Fire Action Schemes and Technology (DTS-FAST); |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xvii | Downed Conductor Detection (DCD); |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xviii | Rapid Earth Fault Current Limiter (REFCL); |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xix | Pole Mounted Sensors; |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xx | Early Fault Detection (EFD); |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xxi | Distribution Fault Anticipation (DFA); |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE
xxii | Smart Tape |  |  |  |  | N/A - NOT MEASURED BY CIRCUIT MILE

## Subpart 5
| Covered Conductor - Base SH (Completed in 2023) | [5 empty] | Undergrounding - Base SH | [5 empty] | Remote Grid | [5 empty] | Transmission Traditional Hardening
| Project ID | Location (City) | Project length (circuit miles) | Project Capital Cost | Project Duration (days) | Duration per circuit mile | Project ID | Location (City) | Project length (circuit miles) | Project Capital Cost | Project Duration (days) | Duration per circuit mile | Project ID | Location | Project length (circuit miles) | Project Capital Cost | Project Duration (days) | Duration per circuit mile | Project ID | Location | Project length (circuit miles) | Project Capital Cost | Project Duration(a) (days) | Capital Cost per circuit mile
Highest 1 | 35279626 | Paso Robles | 0.16364 | 195840.6 | 399 | 2438.3333 | 35259512 | Bella Vista | 0.10739 | 747574.69 | 569 | 5298.6243 | 35246501 | Santa Rosa | 0.70227 | 1636192.87 | 304 | 432.8803 | 74032944 | CRAGVIEW-CASCADE 115KV | 8.6 | 17436202.25 | 974 days | 2027465.3779
Highest 2 | 35279121 | Murphys | 0.14905 | 537109.02 | 327 | 2193.8501 | 35342151 | Fairfield | 0.077841 | 311514.58 | 390 | 5010.219 | [6 empty] | 74030726 | Drum-Rio Oso 115 kV | 16 | 28987823.3 | 2821 days | 1811738.9563
Highest 3 | 35026643 | Placerville | 1.0733 | 1086480.66 | 1846 | 1719.9365 | 35226799 | Platina | 0.19792 | 525055.91 | 843 | 4259.3684 | [6 empty] | 74046318 | STANISLAUS-NEWARK #2 IDLE REMOVAL | 4 | 5920231.76 | 368 days | 1480057.94
Highest 4 | 35299133 | Lakeport | 0.28163 | 385277.2 | 365 | 1296.0323 | 35390288 | Grass Valley | 0.10549 | 763559 | 387 | 3668.5099 | [6 empty] | 74033653 | Fulton-Calistoga 60 kV Line | 12.4 | 16385366.69 | 809 days | 1321400.5395
Highest 5 | 35362685 | Murphys | 0.42727 | 817280.85 | 519 | 1214.6809 | 35342145 | Fairfield | 0.18068 | 1187736.3 | 429 | 2374.3396 | [6 empty] | 74046520 | PORT COSTA BRICKYARD TAP REMOVAL | 1.9 | 1827138.97 | 233 days | 961652.0895
Highest 6 | 35254266 | Winters | 0.15814 | 243300.1 | 181 | 1144.5269 | 35326790 | Auburn | 0.1322 | 375028.39 | 285 | 2155.8739 | [6 empty] | 74046382 | NEWARK LAWRENCE LAB 115KV COND. REMOVAL | 3 | 2464137.28 | 258 days | 821379.0933
Highest 7 | 35250575 | Lakeport | 0.30133 | 399801.54 | 326 | 1081.8856 | 35277924 | Tollhouse | 0.12633 | 410230.19 | 248 | 1963.1784 | [6 empty] | 74046293 | Kilarc-Deschutes 60 kV Removal | 2.5 | 1001651.46 | 227 days | 400660.584
Highest 8 | 35240166 | Manton | 0.4786 | 2470539.01 | 505 | 1055.1642 | 35290808 | Potter Valley | 0.20587 | 1433317.16 | 383 | 1860.3864 | [6 empty] | 74046341 | BRIGHTON-CLAYTON REMOVAL | 3 | 946732.33 | 359 days | 315577.4433
Highest 9 | 35227868 | Middletown | 0.57727 | 468853.41 | 531 | 919.8425 | 35330245 | Clearlake Oaks | 0.077273 | 661881.44 | 126 | 1630.5882 | [6 empty] | 74046298 | MENDOCINO # 1 60KV CONDUCTOR REMOVAL | 5 | 1180189.59 | 518 days | 236037.918
Highest 10 | 35114040 | Pioneer | 1.4932 | 3480667.65 | 1185 | 793.6073 | 35277938 | Tollhouse | 0.45492 | 1539313.53 | 706 | 1551.9067
Lowest 10 | 35228188 | Middletown | 3.403 | 944411.74 | 442 | 129.8842 | 35311897 | Corning | 4.1133 | 7083823.71 | 417 | 101.3795
Lowest 9 | 35234395 | Redding | 2.6911 | 2645197.33 | 331 | 122.9981 | 35339288 | Anderson | 2.5063 | 6063053.8 | 239 | 95.3616
Lowest 8 | 35225829 | Redding | 2.1792 | 2083128.38 | 263 | 120.6883 | 35421339 | Potter Valley | 0.37178 | 385868.22 | 33 | 88.7621
Lowest 7 | 35264182 | Santa Ynez | 2.6348 | 1850557.64 | 276 | 104.7499 | 35337012 | Anderson | 4.1544 | 7358868.1 | 350 | 84.2489
Lowest 6 | 35234398 | Redding | 2.7417 | 3102558.15 | 263 | 95.9271 | 35332215 | Anderson | 2.1809 | 3545163.96 | 174 | 79.7846
Lowest 5 | 35234381 | Redding | 1.5324 | 1790122.89 | 142 | 92.6659 | 35311895 | Anderson | 2.4659 | 5532869.81 | 196 | 79.4839
Lowest 4 | 35329474 | Clearlake Oaks | 1.4695 | 1307343.46 | 135 | 91.8675 | 35330812 | Elk Creek | 2.3237 | 4526367.48 | 179 | 77.0332
Lowest 3 | 35234400 | Redding | 1.2771 | 1144742.43 | 116 | 90.832 | 35332214 | Cottonwood | 4.307 | 8460941.03 | 310 | 71.9757
Lowest 2 | 35219287 | Redding | 2.31 | 2621729.94 | 191 | 82.6826 | 35316569 | Cottonwood | 4.4525 | 7755400.88 | 291 | 65.3571
Lowest 1 | 35237370 | Vacaville | 3.6491 | 2939269.6 | 297 | 81.391 | 35274593 | Mariposa | 2.9869 | 7161349.3 | 194 | 64.9496
| Note: Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs | [5 empty] | Note: Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs | [5 empty] | Note: there are fewer projects listed here for System Hardening Remote Grid compared to the System Hardening Remote Grid table in response to Q1 subpart 6 because orders that do not currently have the necessary data in our system of record to calculate the project duration are omitted in this response
| Covered Conductor - FRRB (Completed in 2023) | [5 empty] | Undergrounding - FRRB
| Project ID | Location (City) | Project length (circuit miles) | Project Capital Cost | Project Duration (days) | Duration per circuit mile | Project ID | Location (City) | Project length (circuit miles) | Project Capital Cost | Project Duration (days) | Duration per circuit mile
Highest 1 | 35368118 | Berry Creek | 0.030303 | 119126.37 | 231 | 7623 | 35292791 | Greenville | 0.11932 | 438381.7 | 350 | 2933.3333
Highest 2 | 35280498 | Greenville | 0.15019 | 219514.31 | 274 | 1824.3632 | 35334541 | Boulder Creek | 0.13617 | 1109248.06 | 359 | 2636.3282
Highest 3 | 35281816 | Burnt Ranch | 0.086174 | 329401.94 | 99 | 1148.8352 | 35318072 | Boulder Creek | 0.19413 | 1223735.95 | 507 | 2611.6683
Highest 4 | 35396073 | Oroville | 0.16951 | 119797.48 | 136 | 802.324 | 35342339 | Boulder Creek | 0.14489 | 414483.86 | 343 | 2367.3725
Highest 5 | 35342460 | Boulder Creek | 0.54129 | 773978.81 | 213 | 393.5059 | 35334407 | Burnt Ranch | 0.22538 | 765094.23 | 499 | 2214.0504
Highest 6 | 35398090 | Greenville | 0.46042 | 465300.76 | 159 | 345.3394 | 35350039 | Berry Creek | 0.096212 | 258264.99 | 190 | 1974.8031
Highest 7 | [6 empty] | 35318074 | Davenport | 0.3 | 813652.38 | 588 | 1960
Highest 8 | [6 empty] | 35292780 | Greenville | 0.24318 | 2525074.63 | 465 | 1912.1495
Highest 9 | [6 empty] | 35241077 | Berry Creek | 0.33807 | 1311675.83 | 587 | 1736.3361
Highest 10 | [6 empty] | 35404061 | Greenville | 0.071591 | 176692.28 | 123 | 1718.0952
Lowest 10 | [6 empty] | 35279985 | Chester | 2.7989 | 8650247.37 | 463 | 165.4243
Lowest 9 | [6 empty] | 35292754 | Greenville | 4.0852 | 32780357.79 | 560 | 137.0793
Lowest 8 | [6 empty] | 35297694 | Burnt Ranch | 0.93371 | 4435344.38 | 121 | 129.5903
Lowest 7 | [6 empty] | 35292755 | Greenville | 2.6481 | 24960547.85 | 338 | 127.6384
Lowest 6 | [6 empty] | 35297693 | Burnt Ranch | 0.95928 | 4757421.87 | 116 | 120.924
Lowest 5 | [6 empty] | 35374686 | Mariposa | 2.5994 | 5735859.53 | 267 | 102.7148
Lowest 4 | [6 empty] | 35297699 | Burnt Ranch | 1.0606 | 4909264.84 | 106 | 99.9429
Lowest 3 | [6 empty] | 35374559 | Mariposa | 3.9581 | 11794951.26 | 323 | 81.6039
Lowest 2 | [6 empty] | 35374681 | Mariposa | 5.0826 | 14087778.18 | 404 | 79.4873
Lowest 1 | [6 empty] | 35297692 | Burnt Ranch | 4.5938 | 21769150.74 | 116 | 25.2517
| Note: Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs | [5 empty] | Note: Base System Hardening (Base SH) and Fire Rebuild (FRRB) are separated to provide visibility to the differences between the two programs