## Liberty Q1 2022 QIU
WMP Initiative Category | WMP Initiative Category# | WMP Initiative Activity | 2021 WMP Page Number | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 80 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Situational Awareness & Forecasting | 7.3.2.1 | Advanced weather monitoring and weather stations | 81 | Weather Stations Installed | 10 | 0 | 2 | 8 | 10 | 0 | - | - | - | - | - | - | - | - | In progress
Situational Awareness & Forecasting | 7.3.2.2 | Continuous monitoring sensors | 82 | DFA Units Installed | 10 | 0 | 5 | 5 | 10 | 0 | - | - | - | - | - | - | - | - | In progress
Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment | 83 | Fault Indicators Installed | 2 | 0 | 0 | 0 | 2 | 0 | - | - | - | - | - | - | - | - | In progress
Situational Awareness & Forecasting | 7.3.2.4 | Forecast of a fire risk index, fire potential index, or similar | 84 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Complete
Situational Awareness & Forecasting | 7.3.2.5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 85 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | 86 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Grid Design & System Hardening | 7.3.3.3 | Covered conductor installation | 87 | Circuit miles | 10.29 | 0.5 | 0 | 5 | 10.29 | 0.5 | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles | 90 | Poles | 231 | 23 | 75 | 150 | 231 | 29 | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement | 91 | Expulsion Fuses Replaced | 1500 | 0 | 300 | 900 | 1500 | 117 | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.8 | Grid topology improvements to mitigate or reduce PSPS events | 93 | Line Miles | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.9 | Installation of system automation equipment | 93 | Automatic Reclosers Installed | 4 | 0 | 1 | 1 | 4 | 0 | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.12 | Other corrective action | 94 | Tree Attachment Removals | 45 | 0 | 15 | 30 | 45 | 0 | - | - | - | - | - | - | - | - | In progress
Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment | 96 | Line Miles | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment | 81 | Line Miles Inspected | 307.8 | 50 | 175 | 250 | 307.8 | 134.86 | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.3 | Improvement of inspections | 82 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment | 82 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.6 | Intrusive pole inspections | 83 | Poles Inspected | 2598 | 0 | 0 | 1299 | 2598 | 0 | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment | 85 | Line Miles Inspected | 706.28 | 100 | 250 | 400 | 706.3 | 152.3 | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections | 86 | % of detailed inspections | 0.5% | 0% | 0.5% | 0.5% | 0.5% | 0% | - | - | - | - | - | - | - | - | In progress
Asset Management & Inspections | 7.3.4.15 | Substation inspections | 88 | Substations Inspected | 42 | 10 | 20 | 32 | 42 | 10 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts | 104 | Line Miles Treated | 6 | 0 | 2 | 4 | 6 | 0 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections of vegetation around distribution electric lines and equipment | 107 | Line Miles Inspected | 222 | 53 | 109 | 170 | 222 | 53.5 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.5 | Fuel management and reduction of “slash” from vegetation management activities | 109 | Acres | 280 | 0 | 95 | 190 | 280 | 0 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.7 | LiDAR inspections of vegetation around distribution electric lines and equipment | 112 | Line Miles Inspected | 701 | 0 | 0 | 701 | 701 | 0 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspections of vegetation around transmission electric lines and equipment | 113 | Line Miles Inspected | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment | 113 | Line Miles Inspected | 171 | 43 | 88 | 130 | 171 | 43.4 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation inspections | 114 | Line Miles Inspected | 221 | 22 | 92 | 162 | 228 | 22.4 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel | 116 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | 7.3.5.15 | Remediation of at-risk species | 117 | Line Miles Treated | 238 | 30 | 110 | 190 | 238 | 30.4 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.16 | Removal and remediation of trees with strike potential to electric lines and equipment | 118 | Line Miles Treated | 171 | 8 | 63 | 120 | 171 | 8.6 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment | 119 | Line Miles Treated | 701 | 400 | 600 | 701 | 701 | 404.9 | - | - | - | - | - | - | - | - | In progress
Vegetation Management & Inspections | 7.3.5.21 | Vegetation management activities post-fire | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Grid Operations & Operating Protocols | 7.3.6.1 | Automatic recloser operations | 120 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Grid Operations & Operating Protocols | 7.3.6.3 | Personnel work procedures and training in conditions of elevated fire risk | 121 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Grid Operations & Operating Protocols | 7.3.6.4 | Protocols for PSPS re-energization | 124 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Data Governance | 7.3.7.1 | Centralized repository for data | 98 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire | 126 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Emergency Planning & Preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration | 128 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Emergency Planning & Preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts | 130 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies | 132 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Stakeholder Cooperation & Community Engagement | 7.3.10.1 | Community engagement | 135 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA | 141 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 5.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 5.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 5.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 5.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 5.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 5.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 5.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 5.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 5.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Remediation of at-risk species
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation inventory system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other