## Cover Sheet Tables 1-12
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines Appendix D, Section 1.2
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | Liberty
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2022
Reporting Period quarter |  | Q4
Date Modified |  | 2023-02-01

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitativieObjecvtive | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
LU | 2023-02-01 | Project |  |  | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  |  | Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | 1 |  | LU_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment _Risk_01_2022 | 80 |  |  | N/A | - | - | - | - | - | - | - | - | - | Enhance wildfire risk model and update data | Participating in RMWG meetings. | Participating in RMWG meetings. | Participating in RMWG meetings. | Updating components of Liberty's wildfire risk analysis and scoping out risk analysis activities for the 2023-2025 WMP cycle. Participating in RMWG meetings. | In progress
LU | 2023-02-01 | Project |  |  | Advanced weather monitoring and weather stations |  |  | Situational Awareness & Forecasting | 7.3.2.1 | Advanced weather monitoring and weather stations |  | 1 |  | LU_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _SAF_01_2022 | 81 |  |  | Weather Stations Installed | 10 | 0 | 2 | 8 | 10 | 0 | 0 | 0 | 5 | - | - | - | - | - | In progress
LU | 2023-02-01 | Pilot |  |  | Continuous monitoring sensors |  |  | Situational Awareness & Forecasting | 7.3.2.2 | Continuous monitoring sensors |  | 2 |  | LU_Situational Awareness & Forecasting_Continuous monitoring sensors _SAF_02_2022 | 82 |  |  | DFA Units Installed | 10 | 0 | 5 | 5 | 10 | 0 | 0 | 0 | 10 | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Fault indicators for detecting faults on electric lines and equipment |  |  | Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment |  | 3 |  | LU_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _SAF_03_2022 | 83 |  |  | Fault Indicators Installed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Forecast of a fire risk index, fire potential index, or similar |  |  | Situational Awareness & Forecasting | 7.3.2.4 | Forecast of a fire risk index, fire potential index, or similar |  | 4 |  | LU_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SAF_04_2022 | 84 |  |  | N/A | - | - | - | - | - | - | - | - | - | Continue to integrate FPI into operational decision-making to mitigate wildfire potential | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  |  | Situational Awareness & Forecasting | 7.3.2.5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | 5 |  | LU_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions _SAF_05_2022 | 85 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  |  | Grid Design & System Hardening | 7.3.3.2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 |  | LU_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _GDSH_02_2022 | 86 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Covered conductor installation |  |  | Grid Design & System Hardening | 7.3.3.3 | Covered conductor installation |  | 3 |  | LU_Grid Design & System Hardening_Covered conductor installation _GDSH_03_2022 | 87 |  |  | Circuit miles | 9.55 | 0.5 | 0.5 | 5 | 9.55 | 0.47 | 1.88 | 4.96 | 9.6 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Distribution pole replacement and reinforcement, including with composite poles |  |  | Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles |  | 6 |  | LU_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _GDSH_06_2022 | 90 |  |  | Poles | 231 | 23 | 75 | 150 | 231 | 29 | 88 | 152 | 226 | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Expulsion fuse replacement |  |  | Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement |  | 7 |  | LU_Grid Design & System Hardening_Expulsion fuse replacement _GDSH_07_2022 | 91 |  |  | Expulsion Fuses Replaced | 1500 | 0 | 300 | 900 | 1500 | 124 | 755 | 1858 | 1858 | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Grid topology improvements to mitigate or reduce PSPS events |  |  | Grid Design & System Hardening | 7.3.3.8 | Grid topology improvements to mitigate or reduce PSPS events |  | 8 |  | LU_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _GDSH_08_2022 | 93 |  |  | Line Miles | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Installation of system automation equipment |  |  | Grid Design & System Hardening | 7.3.3.9 | Installation of system automation equipment |  | 9 |  | LU_Grid Design & System Hardening_Installation of system automation equipment _GDSH_09_2022 | 93 |  |  | Automatic Reclosers Installed | 4 | 0 | 1 | 1 | 4 | 0 | 1 | 1 | 2 | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Other corrective action |  |  | Grid Design & System Hardening | 7.3.3.12 | Other corrective action |  | 12 |  | LU_Grid Design & System Hardening_Other corrective action _GDSH_12_2022 | 94 |  |  | Tree Attachment Removals | 45 | 0 | 15 | 30 | 45 | 25 | 55 | 93 | 145 | - | - | - | - | - | In progress
LU | 2023-02-01 | Project |  |  | Undergrounding of electric lines and/or equipment |  |  | Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment |  | 16 |  | LU_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _GDSH_16_2022 | 96 |  |  | Line Miles | 0.36 | - | - | - | 0.4 | 0.24 | 0.24 | 0.24 | 0.24 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Detailed inspections of distribution electric lines and equipment |  |  | Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment |  | 1 |  | LU_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _AMI_01_2022 | 81 |  |  | Line Miles Inspected | 307.8 | 50 | 175 | 250 | 307.8 | 117.67 | 246.41 | 301.21 | 328.6 | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Improvement of inspections |  |  | Asset Management & Inspections | 7.3.4.3 | Improvement of inspections |  | 3 |  | LU_Asset Management & Inspections_Improvement of inspections _AMI_03_2022 | 82 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Infrared inspections of distribution electric lines and equipment |  |  | Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment |  | 4 |  | LU_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _AMI_04_2022 | 82 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Intrusive pole inspections |  |  | Asset Management & Inspections | 7.3.4.6 | Intrusive pole inspections |  | 6 |  | LU_Asset Management & Inspections_Intrusive pole inspections _AMI_06_2022 | 83 |  |  | Poles Inspected | 2598 | 0 | 0 | 1299 | 2598 | 0 | 0 | 2735 | 2735 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Patrol inspections of distribution electric lines and equipment |  |  | Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment |  | 11 |  | LU_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _AMI_11_2022 | 85 |  |  | Line Miles Inspected | 706.28 | 100 | 250 | 400 | 706.3 | 152.3 | 466.7 | 503 | 503 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Quality assurance / quality control of inspections |  |  | Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections |  | 14 |  | LU_Asset Management & Inspections_Quality assurance / quality control of inspections _AMI_14_2022 | 86 |  |  | % of detailed inspections | 0.005 | 0 | 0.005 | 0.005 | 0.005 | 0 | 0 | 0 | 0.0044 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Substation inspections |  |  | Asset Management & Inspections | 7.3.4.15 | Substation inspections |  | 15 |  | LU_Asset Management & Inspections_Substation inspections _AMI_15_2022 | 88 |  |  | Substations Inspected | 42 | 10 | 20 | 32 | 42 | 11 | 22 | 34 | 45 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Additional efforts to manage community and environmental impacts |  |  | Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts |  | 1 |  | LU_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts _VMI_01_2022 | 104 |  |  | Line Miles Treated | 6 | 0 | 2 | 4 | 6 | 0 | 0 | 0 | 6.33 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Detailed inspections of vegetation around distribution electric lines and equipment |  |  | Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 |  | LU_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _VMI_02_2022 | 107 |  |  | Line Miles Inspected | 222 | 53 | 109 | 170 | 222 | 53.5 | 149.3 | 210.59 | 210.6 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Fuel management and reduction of “slash” from vegetation management activities |  |  | Vegetation Management & Inspections | 7.3.5.5 | Fuel management and reduction of “slash” from vegetation management activities |  | 5 |  | LU_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _VMI_05_2022 | 109 |  |  | Acres | 280 | 0 | 95 | 190 | 280 | 0 | 56.7 | 393.6 | 515 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | LiDAR inspections of vegetation around distribution electric lines and equipment |  |  | Vegetation Management & Inspections | 7.3.5.7 | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 |  | LU_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment _VMI_07_2022 | 112 |  |  | Line Miles Inspected | 701 | 0 | 0 | 701 | 701 | 0 | 0 | 701 | 701 | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Other discretionary inspections of vegetation around transmission electric lines and equipment |  |  | Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspections of vegetation around transmission electric lines and equipment |  | 10 |  | LU_Vegetation Management & Inspections_Other discretionary inspections of vegetation around transmission electric lines and equipment _VMI_10_2022 | 113 |  |  | Line Miles Inspected | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2023-02-01 | Program |  |  | Patrol inspections of vegetation around distribution electric lines and equipment |  |  | Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 |  | LU_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _VMI_11_2022 | 113 |  |  | Line Miles Inspected | 171 | 43 | 88 | 130 | 171 | 26.1 | 92.9 | 170.46 | 235 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Quality assurance / quality control of vegetation inspections |  |  | Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation inspections |  | 13 |  | LU_Vegetation Management & Inspections_Quality assurance / quality control of vegetation inspections _VMI_13_2022 | 114 |  |  | Line Miles Inspected | 221 | 22 | 92 | 162 | 228 | 22.4 | 184.1 | 249.9 | 271.7 | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Recruiting and training of vegetation management personnel |  |  | Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel |  | 14 |  | LU_Vegetation Management & Inspections_Recruiting and training of vegetation management personnel _VMI_14_2022 | 116 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2023-02-01 | Program |  |  | Remediation of at-risk species |  |  | Vegetation Management & Inspections | 7.3.5.15 | Remediation of at-risk species |  | 15 |  | LU_Vegetation Management & Inspections_Remediation of at-risk species _VMI_15_2022 | 117 |  |  | Line Miles Treated | 238 | 30 | 110 | 190 | 238 | 30.4 | 30.4 | 104.85 | 223 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Removal and remediation of trees with strike potential to electric lines and equipment |  |  | Vegetation Management & Inspections | 7.3.5.16 | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 |  | LU_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _VMI_16_2022 | 118 |  |  | Line Miles Treated | 171 | 8 | 63 | 120 | 171 | 8.6 | 8.6 | 101.85 | 203 | - | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Vegetation management to achieve clearances around electric lines and equipment |  |  | Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment |  | 20 |  | LU_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _VMI_20_2022 | 119 |  |  | Line Miles Treated | 701 | 400 | 600 | 701 | 701 | 404.9 | 697 | 701 | 701 | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Vegetation management activities post-fire |  |  | Vegetation Management & Inspections | 7.3.5.21 | Vegetation management activities post-fire |  | 21 |  | LU_Vegetation Management & Inspections_Vegetation management activities post-fire _VMI_21_2022 | N/A |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2023-02-01 |  |  |  | Automatic recloser operations |  |  | Grid Operations & Operating Protocols | 7.3.6.1 | Automatic recloser operations |  | 1 |  | LU_Grid Operations & Operating Protocols_Automatic recloser operations _GOOP_01_2022 | 120 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Personnel work procedures and training in conditions of elevated fire risk |  |  | Grid Operations & Operating Protocols | 7.3.6.3 | Personnel work procedures and training in conditions of elevated fire risk |  | 3 |  | LU_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk _GOOP_03_2022 | 121 |  |  | N/A | - | - | - | - | - | - | - | - | - | Annual training; update procedures and incorporate feedback from training | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Protocols for PSPS re-energization |  |  | Grid Operations & Operating Protocols | 7.3.6.4 | Protocols for PSPS re-energization |  | 4 |  | LU_Grid Operations & Operating Protocols_Protocols for PSPS re-energization _GOOP_04_2022 | 124 |  |  | N/A | - | - | - | - | - | - | - | - | - | Continue refining activities associated with reducing PSPS impacts on customers | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Centralized repository for data |  |  | Data Governance | 7.3.7.1 | Centralized repository for data |  | 1 |  | LU_Data Governance_Centralized repository for data _DG_01_2022 | 98 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Collaborative research on utility ignition and/or wildfire |  |  | Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire |  | 2 |  | LU_Data Governance_Collaborative research on utility ignition and/or wildfire _DG_02_2022 | 126 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2023-02-01 |  |  |  | Adequate and trained workforce for service restoration |  |  | Emergency Planning & Preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration |  | 1 |  | LU_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration _EPP_01_2022 | 128 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2023-02-01 | Program |  |  | Community outreach, public awareness, and communications efforts |  |  | Emergency Planning & Preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts |  | 2 |  | LU_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _EPP_02_2022 | 130 |  |  | N/A | - | - | - | - | - | - | - | - | - | Continued engagement with local stakeholders to prepare for and respond to fire-related event; Meet with Community Advisory Boards | - | - | - | - | In progress
LU | 2023-02-01 | Program |  |  | Customer support in emergencies |  |  | Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies |  | 3 |  | LU_Emergency Planning & Preparedness_Customer support in emergencies _EPP_03_2022 | 132 |  |  | N/A | - | - | - | - | - | - | - | - | - | Conduct Incident Command Training for all identified IC members and hold a Virtual PSPS Tabletop exercise; Continued implementation of Liberty’s 2022 AFN Plan; Continued maintenance of emergency response plans; Enhanced documentation and use of lessons learned to update plans. | - | ICS Training and PSPS Table Top Exercise held on June 15, 2022; PSPS Full Scale Exercise with Public Safety Partners held on June 23, 2022 | - | Liberty ICS Course, including FEMA ICS 100 and ICS 200, assigned to all Liberty Incident Management Team personnel. | In progress
LU | 2023-02-01 | Program |  |  | Community engagement |  |  | Stakeholder Cooperation & Community Engagement | 7.3.10.1 | Community engagement |  | 1 |  | LU_Stakeholder Cooperation & Community Engagement_Community engagement _SCCE_01_2022 | 135 |  |  | N/A | - | - | - | - | - | - | - | - | - | Continue to survey customers, CBOs, community partners and stakeholders to understand wildfire and PSPS awareness and the needs of customers. Strengthen and expand AFN CBO partnerships. Identify emerging channels and technologies to better communicate with customers, community and stakeholders. | - | 15 in-person events, 12 virtual events, and two rounds of social media posts focused on PSPS education and wildfire awareness, AFN outreach, and CBO colalboration and one phone call meeting with elected official. | 14 in-person events, 7 virtual events, 21 social media posts, 9 emails, 2 rounds of bill inserts, 3 website posts, and print /digital advertising. Focused on PSPS education, wildfire awareness, AFN outreach, and CBO collaboration. | 10 In-person events, 24 round of social media posts, 3 posts to Liberty websites, 19 sets of Emails distributed, 2 rounds of bill inserts distributed, 1 round of direct mail, and 1 digital ad. Focused on PSPS education, wildfire awareness, vegetation management, Low Income / AFN outreach, and CBO collaboration. | In progress
LU | 2023-02-01 |  |  |  | Cooperation and best practice sharing with agencies outside CA |  |  | Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA |  | 2 |  | LU_Stakeholder Cooperation & Community Engagement_Cooperation and best practice sharing with agencies outside CA _SCCE_02_2022 | 141 |  |  | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | Liberty | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2023-02-01 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | [15 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
| Table 2: Performance Metrics | [8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 2; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 6; Actuals 1: 3; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 13; Actuals 2: 2; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 18; Actuals 2: 8; Actuals 3: 9; Actuals 4: 13; Actuals 1: 18; Actuals 2: 11; Actuals 3: 5; Actuals 4: 79; Actuals 1: 4; Actuals 2: 33; Actuals 3: 9; Actuals 4: 147 |  |  |  | Number of events | 104 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 1; Actuals 3: 2; Actuals 4: 2; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 15; Actuals 1: 0; Actuals 2: 4; Actuals 3: 1; Actuals 4: 13 |  |  |  | Number of events | 12 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 4; Actuals 2: 2; Actuals 3: 2; Actuals 4: 2; Actuals 1: 3; Actuals 2: 1; Actuals 3: 2; Actuals 4: 3; Actuals 1: 2; Actuals 2: 1; Actuals 3: 1; Actuals 4: 10 |  |  |  | Number of events | 8 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 3; Actuals 2: 2; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 9; Actuals 2: 1; Actuals 3: 0; Actuals 4: 2; Actuals 1: 5; Actuals 2: 3; Actuals 3: 1; Actuals 4: 30; Actuals 1: 0; Actuals 2: 6; Actuals 3: 1; Actuals 4: 36 |  |  |  | Number of events | 22 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 5; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 6 |  |  |  | Number of events | 5 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 3 |  |  |  | Number of events | 2 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 3; Actuals 3: 7; Actuals 4: 1; Actuals 1: 0; Actuals 2: 1; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 3; Actuals 2: 0; Actuals 3: 0; Actuals 4: 10; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 19; Actuals 1: 6; Actuals 2: 3; Actuals 3: 0; Actuals 4: 1 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 40; Actuals 2: 27; Actuals 3: 45; Actuals 4: 48; Actuals 1: 39; Actuals 2: 34; Actuals 3: 33; Actuals 4: 257; Actuals 1: 44; Actuals 2: 50; Actuals 3: 45; Actuals 4: 120 |  |  |  | Number of events | 76 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 2; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 2; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 1; Actuals 3: 4; Actuals 4: 4; Actuals 1: 2; Actuals 2: 1; Actuals 3: 3; Actuals 4: 28; Actuals 1: 1; Actuals 2: 8; Actuals 3: 6; Actuals 4: 8 |  |  |  | Number of events | 7 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 2; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 6; Actuals 2: 5; Actuals 3: 6; Actuals 4: 11; Actuals 1: 7; Actuals 2: 2; Actuals 3: 6; Actuals 4: 18; Actuals 1: 4; Actuals 2: 8; Actuals 3: 5; Actuals 4: 10 |  |  |  | Number of events | 7 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 2; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 2; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 8; Actuals 2: 2; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 3; Actuals 2: 3; Actuals 3: 1; Actuals 4: 3; Actuals 1: 6; Actuals 2: 4; Actuals 3: 3; Actuals 4: 0; Actuals 1: 1; Actuals 2: 19; Actuals 3: 2; Actuals 4: 59 |  |  |  | Number of events | 36 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 2; Actuals 3: 0; Actuals 4: 8 |  |  |  | Number of events | 7 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 2; Actuals 2: 1; Actuals 3: 0; Actuals 4: 3 |  |  |  | Number of events | 2 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 5 | 1.5 | 1.5 | 1.5 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0 | 0.25 | 0.25 | 0.25 | Number of events
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 492; Actuals 2: 1008; Actuals 3: 3864; Actuals 4: 3648; Actuals 1: 3480; Actuals 2: 5496; Actuals 3: 8400; Actuals 4: 3384; Actuals 1: 2304; Actuals 2: 1224; Actuals 3: 1704; Actuals 4: 1584 |  |  |  | hours
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 1752; Actuals 2: 3672; Actuals 3: 5592; Actuals 4: 6408; Actuals 1: 9997; Actuals 2: 10632; Actuals 3: 9744; Actuals 4: 8832; Actuals 1: 4536; Actuals 2: 5832; Actuals 3: 7344; Actuals 4: 5112 |  |  |  | hours
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 384; Actuals 2: 3432; Actuals 3: 1752; Actuals 4: 2472; Actuals 1: 528; Actuals 2: 1656; Actuals 3: 2712; Actuals 4: 2472; Actuals 1: 4800; Actuals 2: 144; Actuals 3: 2532; Actuals 4: 2880 |  |  |  | hours
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 456; Actuals 2: 4008; Actuals 3: 5376; Actuals 4: 3302; Actuals 1: 2668; Actuals 2: 5239; Actuals 3: 8976; Actuals 4: 2856; Actuals 1: 5592; Actuals 2: 2491; Actuals 3: 8448; Actuals 4: 4164 |  |  |  | hours
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 144; Actuals 2: 984; Actuals 3: 1512; Actuals 4: 1368; Actuals 1: 8436; Actuals 2: 4584; Actuals 3: 8472; Actuals 4: 2976; Actuals 1: 84; Actuals 2: 192; Actuals 3: 2472; Actuals 4: 2484 |  |  |  | hours
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 144; Actuals 2: 3062; Actuals 3: 4274; Actuals 4: 4221; Actuals 1: 9792; Actuals 2: 10152; Actuals 3: 10272; Actuals 4: 4691; Actuals 1: 6728; Actuals 2: 7008; Actuals 3: 4968; Actuals 4: 10602 |  |  |  | hours
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 168; Actuals 2: 0; Actuals 3: 876; Actuals 4: 1104; Actuals 1: 2304; Actuals 2: 5280; Actuals 3: 6068; Actuals 4: 3540; Actuals 1: 144; Actuals 2: 288; Actuals 3: 3696; Actuals 4: 2160 |  |  |  | hours
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 168; Actuals 2: 0; Actuals 3: 1224; Actuals 4: 1794; Actuals 1: 3081; Actuals 2: 6168; Actuals 3: 6537; Actuals 4: 4089; Actuals 1: 5661; Actuals 2: 312; Actuals 3: 5112; Actuals 4: 4056 |  |  |  | hours
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2160; Actuals 1: 0; Actuals 2: 5112; Actuals 3: 2448; Actuals 4: 0; Actuals 1: 0; Actuals 2: 144; Actuals 3: 48; Actuals 4: 1944 |  |  |  | hours
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2856; Actuals 1: 0; Actuals 2: 5112; Actuals 3: 5169; Actuals 4: 0; Actuals 1: 0; Actuals 2: 2784; Actuals 3: 48; Actuals 4: 3192 |  |  |  | hours
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 1248; Actuals 3: 840; Actuals 4: 6648; Actuals 1: 0; Actuals 2: 0; Actuals 3: 6240; Actuals 4: 5040; Actuals 1: 144; Actuals 2: 504; Actuals 3: 2952; Actuals 4: 3936 |  |  |  | hours
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 3518; Actuals 3: 1440; Actuals 4: 7440; Actuals 1: 0; Actuals 2: 0; Actuals 3: 6528; Actuals 4: 5112; Actuals 1: 192; Actuals 2: 926; Actuals 3: 4080; Actuals 4: 4099 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 192; Actuals 3: 60; Actuals 4: 2208; Actuals 1: 6168; Actuals 2: 7200; Actuals 3: 10464; Actuals 4: 12048; Actuals 1: 13896; Actuals 2: 16728; Actuals 3: 17040; Actuals 4: 0 |  |  |  | hours
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 1485.6; Actuals 3: 648; Actuals 4: 2229; Actuals 1: 6168; Actuals 2: 7200; Actuals 3: 10488; Actuals 4: 12112.8; Actuals 1: 13896; Actuals 2: 16728; Actuals 3: 19070; Actuals 4: 0 |  |  |  | hours
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 18288; Actuals 4: 0 |  |  |  | hours
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 18288; Actuals 4: 0 |  |  |  | hours
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 432; Actuals 3: 888; Actuals 4: 0; Actuals 1: 0; Actuals 2: 7104; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 1248; Actuals 3: 888; Actuals 4: 0; Actuals 1: 0; Actuals 2: 7104; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 384; Actuals 3: 504; Actuals 4: 2232; Actuals 1: 5832; Actuals 2: 7224; Actuals 3: 9336; Actuals 4: 11244; Actuals 1: 13548; Actuals 2: 15936; Actuals 3: 17340; Actuals 4: 18840 |  |  |  | hours
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 384; Actuals 3: 1128; Actuals 4: 4920; Actuals 1: 8112; Actuals 2: 9338.4; Actuals 3: 10822.8; Actuals 4: 12096; Actuals 1: 14383.2; Actuals 2: 17176.8; Actuals 3: 18777.6; Actuals 4: 20112 |  |  |  | hours
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 936; Actuals 4: 2832; Actuals 1: 4380; Actuals 2: 7836; Actuals 3: 10524; Actuals 4: 12432; Actuals 1: 14340; Actuals 2: 15264; Actuals 3: 18528; Actuals 4: 0 |  |  |  | hours
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 936; Actuals 4: 4296; Actuals 1: 6362.4; Actuals 2: 8214; Actuals 3: 11082; Actuals 4: 12432; Actuals 1: 14437.2; Actuals 2: 15264; Actuals 3: 18981.6; Actuals 4: 0 |  |  |  | hours
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 96; Actuals 4: 3768; Actuals 1: 5412; Actuals 2: 8112; Actuals 3: 10656; Actuals 4: 0; Actuals 1: 14136; Actuals 2: 16620; Actuals 3: 20448; Actuals 4: 0 |  |  |  | hours
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 3081.6; Actuals 4: 3768; Actuals 1: 6336; Actuals 2: 9072; Actuals 3: 10677.6; Actuals 4: 0; Actuals 1: 14136; Actuals 2: 17127.6; Actuals 3: 21126; Actuals 4: 0 |  |  |  | hours
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20016 |  |  |  | hours
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20016 |  |  |  | hours
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20016 |  |  |  | hours
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20016 |  |  |  | hours
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 360; Actuals 4: 3168; Actuals 1: 3024; Actuals 2: 7560; Actuals 3: 10512; Actuals 4: 12024; Actuals 1: 13752; Actuals 2: 14832; Actuals 3: 18336; Actuals 4: 20004 |  |  |  | hours
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 20.4; Actuals 3: 810; Actuals 4: 3168; Actuals 1: 6216; Actuals 2: 9206.4; Actuals 3: 11028; Actuals 4: 12552; Actuals 1: 15321.6; Actuals 2: 17966.4; Actuals 3: 18672; Actuals 4: 21336 |  |  |  | hours
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1128; Actuals 4: 1740; Actuals 1: 6144; Actuals 2: 6912; Actuals 3: 9912; Actuals 4: 12264; Actuals 1: 13968; Actuals 2: 15168; Actuals 3: 18264; Actuals 4: 19944 |  |  |  | hours
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1171.2; Actuals 4: 2178; Actuals 1: 6144; Actuals 2: 6912; Actuals 3: 9912; Actuals 4: 12432; Actuals 1: 14304; Actuals 2: 17732.4; Actuals 3: 18859.2; Actuals 4: 20112 |  |  |  | hours
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 3792; Actuals 1: 0; Actuals 2: 7944; Actuals 3: 0; Actuals 4: 12048; Actuals 1: 13680; Actuals 2: 16440; Actuals 3: 17880; Actuals 4: 0 |  |  |  | hours
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 3792; Actuals 1: 0; Actuals 2: 7944; Actuals 3: 0; Actuals 4: 12063.6; Actuals 1: 13704; Actuals 2: 16440; Actuals 3: 17880; Actuals 4: 0 |  |  |  | hours
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20016 |  |  |  | hours
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20016 |  |  |  | hours
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20112 |  |  |  | hours
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 20112 |  |  |  | hours |  | No data relevent to requested intersections
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | hours |  | No data relevent to requested intersections
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 2; Actuals 2: 3; Actuals 3: 8; Actuals 4: 11; Actuals 1: 56; Actuals 2: 265; Actuals 3: 404; Actuals 4: 910 | 414.75 | 414.75 | 414.75 | Number of orders
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of orders |  | No data relevent to requested intersections
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 2050; Actuals 3: 7210; Actuals 4: 7365; Actuals 1: 7370; Actuals 2: 7437; Actuals 3: 7446; Actuals 4: 7809; Actuals 1: 8916; Actuals 2: 10284; Actuals 3: 10526; Actuals 4: 10547 | 8500 | 6700 | 5960 | Number of orders
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 71; Actuals 3: 332; Actuals 4: 340; Actuals 1: 340; Actuals 2: 346; Actuals 3: 346; Actuals 4: 405; Actuals 1: 431; Actuals 2: 431; Actuals 3: 431; Actuals 4: 431 | 107.75 | 25 | 25 | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Hours
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 71; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 3; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 6122; Actuals 3: 12229; Actuals 4: 686; Actuals 1: 68; Actuals 2: 324; Actuals 3: 32; Actuals 4: 663; Actuals 1: 2230; Actuals 2: 3037; Actuals 3: 642; Actuals 4: 78 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 188.73; Actuals 3: 257.83; Actuals 4: 19.84; Actuals 1: 1.62; Actuals 2: 6.12; Actuals 3: 0.85; Actuals 4: 75.7; Actuals 1: 87.51; Actuals 2: 125.11; Actuals 3: 58.42; Actuals 4: 3.6 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 57; Actuals 3: 29; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 1; Actuals 3: 1; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 193; Actuals 3: 863; Actuals 4: 6; Actuals 1: 0; Actuals 2: 7; Actuals 3: 1; Actuals 4: 57; Actuals 1: 156; Actuals 2: 352; Actuals 3: 64; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 1896; Actuals 3: 5302; Actuals 4: 127; Actuals 1: 5; Actuals 2: 79; Actuals 3: 9; Actuals 4: 291; Actuals 1: 704; Actuals 2: 1015; Actuals 3: 158; Actuals 4: 21 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 904; Actuals 3: 725; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 6; Actuals 1: 84; Actuals 2: 17; Actuals 3: 14; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 22.71; Actuals 3: 17.8; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0.56; Actuals 1: 2.14; Actuals 2: 0.44; Actuals 3: 1.2; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 36; Actuals 3: 54; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 25; Actuals 3: 1; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 339; Actuals 3: 288; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 34; Actuals 2: 12; Actuals 3: 4; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 324; Actuals 2: 22; Actuals 3: 74; Actuals 4: 2 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 22.39; Actuals 3: 13.43; Actuals 4: 2.06; Actuals 1: 0; Actuals 2: 0.22; Actuals 3: 0.03; Actuals 4: 10.19; Actuals 1: 12.64; Actuals 2: 1.22; Actuals 3: 4.82; Actuals 4: 0.09 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 4; Actuals 3: 2; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 53; Actuals 3: 24; Actuals 4: 2; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 31; Actuals 2: 1; Actuals 3: 5; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 234; Actuals 3: 229; Actuals 4: 34; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 14; Actuals 1: 110; Actuals 2: 6; Actuals 3: 15; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 100; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 171; Actuals 2: 4; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 4.4; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 12.43; Actuals 2: 0.29; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 19; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 5; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 79; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 54; Actuals 2: 3; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 53; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 2.23; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 26; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 26; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 2; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 2; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0.17; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0.15; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of findings from these asset inspections |  | No data relevent to requested intersections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 7; Actuals 3: 26; Actuals 4: 2; Actuals 1: 1; Actuals 2: 1; Actuals 3: 44; Actuals 4: 1; Actuals 1: 1; Actuals 2: 1; Actuals 3: 3; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 1; Actuals 3: 21; Actuals 4: 29; Actuals 1: 46; Actuals 2: 130; Actuals 3: 78; Actuals 4: 158; Actuals 1: 194; Actuals 2: 68; Actuals 3: 67; Actuals 4: 34 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 5; Actuals 3: 7; Actuals 4: 1; Actuals 1: 30; Actuals 2: 52; Actuals 3: 71; Actuals 4: 243; Actuals 1: 478; Actuals 2: 253; Actuals 3: 132; Actuals 4: 51 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 40; Actuals 1: 19; Actuals 2: 5; Actuals 3: 6; Actuals 4: 4; Actuals 1: 2; Actuals 2: 1; Actuals 3: 3; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 2; Actuals 4: 6; Actuals 1: 1; Actuals 2: 1; Actuals 3: 1; Actuals 4: 183; Actuals 1: 49; Actuals 2: 20; Actuals 3: 6; Actuals 4: 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 4; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 5; Actuals 4: 1; Actuals 1: 3; Actuals 2: 20; Actuals 3: 3; Actuals 4: 0; Actuals 1: 1; Actuals 2: 2; Actuals 3: 6; Actuals 4: 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 8; Actuals 1: 18; Actuals 2: 4; Actuals 3: 1; Actuals 4: 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 13 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 9 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of asset inspection findings which have been fixed |  | No data relevent to requested intersections
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 22147; Actuals 1: 0; Actuals 2: 0; Actuals 3: 178649; Actuals 4: 32904; Actuals 1: 0; Actuals 2: 0; Actuals 3: 209322; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | Actuals 1: 2554; Actuals 2: 2189; Actuals 3: 2421; Actuals 4: 1750; Actuals 1: 795; Actuals 2: 1744; Actuals 3: 2488; Actuals 4: 1962; Actuals 1: 1109; Actuals 2: 1021; Actuals 3: 2998; Actuals 4: 715 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | Actuals 1: 179; Actuals 2: 252; Actuals 3: 453; Actuals 4: 792; Actuals 1: 656; Actuals 2: 378; Actuals 3: 383; Actuals 4: 173; Actuals 1: 330; Actuals 2: 346; Actuals 3: 578; Actuals 4: 243 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | Actuals 1: 103; Actuals 2: 158; Actuals 3: 344; Actuals 4: 357; Actuals 1: 253; Actuals 2: 123; Actuals 3: 192; Actuals 4: 126; Actuals 1: 156; Actuals 2: 166; Actuals 3: 204; Actuals 4: 156 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 886; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1226; Actuals 4: 93; Actuals 1: 0; Actuals 2: 0; Actuals 3: 640; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | Actuals 1: 1514; Actuals 2: 852; Actuals 3: 934; Actuals 4: 604; Actuals 1: 415; Actuals 2: 853; Actuals 3: 1322; Actuals 4: 1261; Actuals 1: 757; Actuals 2: 775; Actuals 3: 2153; Actuals 4: 687 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 4392; Actuals 1: 0; Actuals 2: 0; Actuals 3: 24343; Actuals 4: 1244; Actuals 1: 0; Actuals 2: 0; Actuals 3: 25126; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | Actuals 1: 92; Actuals 2: 66; Actuals 3: 37; Actuals 4: 10; Actuals 1: 6; Actuals 2: 83; Actuals 3: 90; Actuals 4: 12; Actuals 1: 61; Actuals 2: 150; Actuals 3: 24; Actuals 4: 6 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | Actuals 1: 19; Actuals 2: 14; Actuals 3: 0; Actuals 4: 28; Actuals 1: 4; Actuals 2: 4; Actuals 3: 42; Actuals 4: 1; Actuals 1: 16; Actuals 2: 18; Actuals 3: 0; Actuals 4: 20 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | Actuals 1: 11; Actuals 2: 1; Actuals 3: 0; Actuals 4: 25; Actuals 1: 3; Actuals 2: 3; Actuals 3: 22; Actuals 4: 1; Actuals 1: 16; Actuals 2: 7; Actuals 3: 0; Actuals 4: 19 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 54; Actuals 1: 0; Actuals 2: 0; Actuals 3: 33; Actuals 4: 5; Actuals 1: 0; Actuals 2: 0; Actuals 3: 24; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | Actuals 1: 60; Actuals 2: 22; Actuals 3: 23; Actuals 4: 10; Actuals 1: 6; Actuals 2: 60; Actuals 3: 64; Actuals 4: 6; Actuals 1: 28; Actuals 2: 87; Actuals 3: 22; Actuals 4: 3 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 617; Actuals 1: 0; Actuals 2: 0; Actuals 3: 13306; Actuals 4: 174; Actuals 1: 0; Actuals 2: 0; Actuals 3: 9903; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | Actuals 1: 228; Actuals 2: 684; Actuals 3: 666; Actuals 4: 438; Actuals 1: 425; Actuals 2: 301; Actuals 3: 163; Actuals 4: 55; Actuals 1: 64; Actuals 2: 10; Actuals 3: 5; Actuals 4: 5 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | Actuals 1: 16; Actuals 2: 32; Actuals 3: 663; Actuals 4: 55; Actuals 1: 77; Actuals 2: 35; Actuals 3: 26; Actuals 4: 46; Actuals 1: 17; Actuals 2: 1; Actuals 3: 14; Actuals 4: 1 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | Actuals 1: 14; Actuals 2: 7; Actuals 3: 494; Actuals 4: 45; Actuals 1: 36; Actuals 2: 23; Actuals 3: 13; Actuals 4: 33; Actuals 1: 12; Actuals 2: 1; Actuals 3: 1; Actuals 4: 1 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 31; Actuals 1: 0; Actuals 2: 0; Actuals 3: 183; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 44; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | Actuals 1: 99; Actuals 2: 247; Actuals 3: 226; Actuals 4: 187; Actuals 1: 135; Actuals 2: 165; Actuals 3: 48; Actuals 4: 15; Actuals 1: 25; Actuals 2: 8; Actuals 3: 4; Actuals 4: 5 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 0; Actuals 2: 0; Actuals 3: 5085; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 5963; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | Actuals 1: 0; Actuals 2: 41; Actuals 3: 214; Actuals 4: 63; Actuals 1: 0; Actuals 2: 23; Actuals 3: 66; Actuals 4: 189; Actuals 1: 171; Actuals 2: 137; Actuals 3: 286; Actuals 4: 65 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | Actuals 1: 21; Actuals 2: 4; Actuals 3: 36; Actuals 4: 3; Actuals 1: 5; Actuals 2: 0; Actuals 3: 0; Actuals 4: 11; Actuals 1: 4; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | Actuals 1: 5; Actuals 2: 4; Actuals 3: 34; Actuals 4: 3; Actuals 1: 5; Actuals 2: 0; Actuals 3: 0; Actuals 4: 10; Actuals 1: 4; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 3; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | Actuals 1: 0; Actuals 2: 40; Actuals 3: 210; Actuals 4: 46; Actuals 1: 0; Actuals 2: 8; Actuals 3: 22; Actuals 4: 189; Actuals 1: 125; Actuals 2: 123; Actuals 3: 188; Actuals 4: 135 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 6; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1217; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1276; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 6; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 10; Actuals 4: 151 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 6; Actuals 1: 5; Actuals 2: 5; Actuals 3: 0; Actuals 4: 0; Actuals 1: 6; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 3; Actuals 1: 2; Actuals 2: 2; Actuals 3: 0; Actuals 4: 0; Actuals 1: 6; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 2; Actuals 1: 0; Actuals 2: 0; Actuals 3: 2; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 5; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 10; Actuals 4: 129 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 366; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 444; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | Actuals 1: 66; Actuals 2: 14; Actuals 3: 16; Actuals 4: 37; Actuals 1: 3; Actuals 2: 22; Actuals 3: 9; Actuals 4: 0; Actuals 1: 52; Actuals 2: 15; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | Actuals 1: 1; Actuals 2: 0; Actuals 3: 61; Actuals 4: 1; Actuals 1: 0; Actuals 2: 99; Actuals 3: 5; Actuals 4: 1; Actuals 1: 6; Actuals 2: 1; Actuals 3: 4; Actuals 4: 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | Actuals 1: 1; Actuals 2: 0; Actuals 3: 39; Actuals 4: 0; Actuals 1: 0; Actuals 2: 9; Actuals 3: 2; Actuals 4: 1; Actuals 1: 6; Actuals 2: 1; Actuals 3: 4; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | No data relevent to requested intersections
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | Actuals 1: 49; Actuals 2: 9; Actuals 3: 15; Actuals 4: 29; Actuals 1: 2; Actuals 2: 6; Actuals 3: 7; Actuals 4: 0; Actuals 1: 9; Actuals 2: 49; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Percentage of customers notified of evacuation

## Table 3
Utility | Liberty
Table No. | 3
Date Modified
[5 empty] | Actual | [7 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
Table 3: List and description of additional metrics |  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning

## Table 4
Utility | Liberty
Table No. | 4
Date Modified | 2023-02-01
Note: These columns are placeholders for future QR submissions.
Table 4: Weather patterns |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric type | # | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 2.62; 4: 0 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 0; 4: 0 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 4.15; 4: 0 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 1: 539.104; 2: 28.035; 3: 0; 4: 263.648 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 1: 66.112; 2: 0; 3: 0; 4: 31.316 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 1: 17.926; 2: 5.223; 3: 0; 4: 8.255 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 0; 4: 0 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 0; 4: 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 0; 4: 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 1: 0; 2: 8024.05; 3: 49707.66; 4: 858.57 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 1: 0; 2: 507.43; 3: 4313.12; 4: 0 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 1: 0; 2: 510.26; 3: 3987.09; 4: 81.19 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)

## Table 5
| Utility | Liberty | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2023-02-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[8 empty] | Actual number of risk events | [15 empty] | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 2 | 2 | 2 | # risk events (excluding ignitions) | 1 in NWS Winter Storms in Q4 2022
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 2; Actual number of risk events Q2: 8; Actual number of risk events Q3: 1; Actual number of risk events Q4: 18 | 29 | 29 | 29 | # risk events (excluding ignitions) | 8 in NWS Winter Storms in Q4 2022
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4 | 4 | 4 | 4 | # risk events (excluding ignitions) | 3 in NWS Winter Storms in Q4 2022
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 10 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | 0 in NWS Winter Storms in Q4 2022
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) | 1 in NWS Winter Storms in Q4 2022
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) | 1 in NWS Winter Storms in Q4 2022
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 2; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3 | 6 | 6 | 6 | # risk events (excluding ignitions) | 2 in NWS Winter Storms in Q4 2022
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 9; Actual number of risk events Q2: 21; Actual number of risk events Q3: 3; Actual number of risk events Q4: 59 | 92 | 92 | 92 | # risk events (excluding ignitions) | 36 in NWS Winter Storms in Q4 2022
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 8 | 11 | 11 | 11 | # risk events (excluding ignitions) | 7 in NWS Winter Storms in Q4 2022
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 3; Actual number of risk events Q2: 7; Actual number of risk events Q3: 9; Actual number of risk events Q4: 7 | 26 | 26 | 26 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 2 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 12; Actual number of risk events Q4: 1 | 15 | 15 | 15 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 2 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 3; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrestor | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrestor | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 4; Actual number of risk events Q4: 1 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 10 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 5 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 5 | 5 | 5 | 5 | # risk events (excluding ignitions) | 5 in NWS Winter Storm in Q4 2022
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 7; Actual number of risk events Q2: 6; Actual number of risk events Q3: 2; Actual number of risk events Q4: 66 | 81 | 81 | 81 | # risk events (excluding ignitions) | 52 in NWS Winter Storm in Q4 2022
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 4 | 5 | 5 | 5 | # risk events (excluding ignitions) | 4 in NWS Winter Storm in Q4 2022
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 3; Actual number of risk events Q4: 2 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 4; Actual number of risk events Q2: 7; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 13 | 13 | 13 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 36; Actual number of risk events Q2: 21; Actual number of risk events Q3: 9; Actual number of risk events Q4: 10 | 76 | 76 | 76 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 3; Actual number of risk events Q3: 3; Actual number of risk events Q4: 0 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions)

## Table 6
| Utility | Liberty | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2023-02-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[7 empty] | Actual number of ignitions | [15 empty] | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.66667 | 0.66667 | 0.66667 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment/facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and brushing | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and brushing | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and brushing | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and brushing | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and brushing | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and brushing | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrestor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrestor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions

## Table 7
| Utility | Liberty
| Table No. | 7
| Date Modified | 2023-02-01
[7 empty] | Actual | [15 empty] | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 5.32; Actual Q2: 4.77; Actual Q3: 4.79; Actual Q4: 4.79 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 1.15; Actual Q2: 1.03; Actual Q3: 1.04; Actual Q4: 1..04 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 12.98; Actual Q2: 12.51; Actual Q3: 12.53; Actual Q4: 12.53 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 5.8; Actual Q2: 5.81; Actual Q3: 5.79; Actual Q4: 5.82 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 52.4; Actual Q2: 52.82; Actual Q3: 52.82; Actual Q4: 52.55 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 16.06; Actual Q2: 16.06; Actual Q3: 16.06; Actual Q4: 16.16 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 305.52; Actual Q2: 305.89; Actual Q3: 305.68; Actual Q4: 305.47 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 17.7; Actual Q2: 17.69; Actual Q3: 17.81; Actual Q4: 17.78 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 580.59; Actual Q2: 578.86; Actual Q3: 579.03; Actual Q4: 577.52 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 170.05; Actual Q2: 166.65; Actual Q3: 165.85; Actual Q4: 160.99 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 112.39; Actual Q2: 112.76; Actual Q3: 112.49; Actual Q4: 112.37 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 71.76; Actual Q2: 72.55; Actual Q3: 72.04; Actual Q4: 71.87 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0.02; Actual Q2: 0.02; Actual Q3: 0.02; Actual Q4: 0.02 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 107.44; Actual Q2: 107.86; Actual Q3: 107.9; Actual Q4: 107.9 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 15.62; Actual Q2: 15.62; Actual Q3: 15.62; Actual Q4: 15.62 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0.49; Actual Q2: 1.43; Actual Q3: 1.43; Actual Q4: 1.43 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0.12; Actual Q2: 0.39; Actual Q3: 0.39; Actual Q4: 0.39 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0.18; Actual Q2: 0.08; Actual Q3: 0.08; Actual Q4: 0.08 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0.11; Actual Q2: 0.17; Actual Q3: 0.17; Actual Q4: 0.17 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0.84; Actual Q2: 1.59; Actual Q3: 1.53; Actual Q4: 1.58 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0.08; Actual Q2: 0.18; Actual Q3: 0.18; Actual Q4: 0.18 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 2.98; Actual Q2: 5.48; Actual Q3: 4.49; Actual Q4: 5.69 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 11.96; Actual Q2: 15.73; Actual Q3: 15.58; Actual Q4: 20.67 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0.23; Actual Q2: 0.25; Actual Q3: 0.25; Actual Q4: 0.25 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0.03; Actual Q2: 0.03; Actual Q3: 0.03; Actual Q4: 0.03 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 2.32; Actual Q2: 2.32; Actual Q3: 2.32; Actual Q4: 2.32 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 21.44; Actual Q2: 21.44; Actual Q3: 21.45; Actual Q4: 21.45 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 1.15; Actual Q2: 1.15; Actual Q3: 1.15; Actual Q4: 1.15 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 3.35; Actual Q2: 3.35; Actual Q3: 3.35; Actual Q4: 3.35 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 1.97; Actual Q2: 1.97; Actual Q3: 1.97; Actual Q4: 1.97 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 8.68; Actual Q2: 8.68; Actual Q3: 8.68; Actual Q4: 8.68 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 1.84; Actual Q2: 1.84; Actual Q3: 1.84; Actual Q4: 1.84 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 98.17; Actual Q2: 98.17; Actual Q3: 98.17; Actual Q4: 98.4 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 11.32; Actual Q2: 11.32; Actual Q3: 11.46; Actual Q4: 11.53 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 291.71; Actual Q2: 291.71; Actual Q3: 292.37; Actual Q4: 293.31 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 76.57; Actual Q2: 76.57; Actual Q3: 76.75; Actual Q4: 76.82 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 33.74; Actual Q2: 33.74; Actual Q3: 33.71; Actual Q4: 33.76 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 9.85; Actual Q2: 9.85; Actual Q3: 10.28; Actual Q4: 10.28 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 8.73; Actual Q2: 8.73; Actual Q3: 8.73; Actual Q4: 8.73 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 1.46; Actual Q2: 1.46; Actual Q3: 1.46; Actual Q4: 1.46 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.05; Actual Q4: 0.05 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.98; Actual Q4: 1.08 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.15; Actual Q4: 0.15 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 12; Actual Q3: 18; Actual Q4: 19 |  |  |  | Number of critical facilities
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 1; Actual Q2: 10; Actual Q3: 14; Actual Q4: 14 |  |  |  | Number of critical facilities
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 2; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2 |  |  |  | Number of critical facilities
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 12; Actual Q2: 42; Actual Q3: 88; Actual Q4: 71 |  |  |  | Number of critical facilities
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 3; Actual Q2: 13; Actual Q3: 14; Actual Q4: 14 |  |  |  | Number of critical facilities
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 17; Actual Q2: 239; Actual Q3: 364; Actual Q4: 361 |  |  |  | Number of critical facilities
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 4; Actual Q2: 49; Actual Q3: 49; Actual Q4: 49 |  |  |  | Number of critical facilities
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 29; Actual Q2: 217; Actual Q3: 258; Actual Q4: 253 |  |  |  | Number of critical facilities
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 9; Actual Q2: 54; Actual Q3: 59; Actual Q4: 58 |  |  |  | Number of critical facilities
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 11; Actual Q2: 23; Actual Q3: 53; Actual Q4: 46 |  |  |  | Number of critical facilities
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 10; Actual Q2: 24; Actual Q3: 25; Actual Q4: 25 |  |  |  | Number of critical facilities
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 3; Actual Q2: 42; Actual Q3: 60; Actual Q4: 61 |  |  |  | Number of critical facilities
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 3; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of critical facilities
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 1002; Actual Q2: 1002; Actual Q3: 1001; Actual Q4: 1013 |  |  |  | Number of residential customers
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 17; Actual Q2: 17; Actual Q3: 17; Actual Q4: 17 |  |  |  | Number of residential customers
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 366; Actual Q2: 366; Actual Q3: 363; Actual Q4: 367 |  |  |  | Number of residential customers
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 18; Actual Q2: 18; Actual Q3: 18; Actual Q4: 18 |  |  |  | Number of residential customers
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 1477; Actual Q2: 1477; Actual Q3: 1474; Actual Q4: 1473 |  |  |  | Number of residential customers
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 37; Actual Q2: 37; Actual Q3: 37; Actual Q4: 37 |  |  |  | Number of residential customers
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 13946; Actual Q2: 13946; Actual Q3: 13917; Actual Q4: 14043 |  |  |  | Number of residential customers
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 40; Actual Q2: 40; Actual Q3: 40; Actual Q4: 40 |  |  |  | Number of residential customers
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 19514; Actual Q2: 19514; Actual Q3: 19490; Actual Q4: 19752 |  |  |  | Number of residential customers
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 972; Actual Q2: 972; Actual Q3: 971; Actual Q4: 990 |  |  |  | Number of residential customers
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 1717; Actual Q2: 1717; Actual Q3: 1713; Actual Q4: 1718 |  |  |  | Number of residential customers
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 205; Actual Q2: 205; Actual Q3: 205; Actual Q4: 205 |  |  |  | Number of residential customers
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | [19 empty] | Number of residential customers | bar: Actual Q1 to Actual Q4
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 2758; Actual Q2: 2758; Actual Q3: 2758; Actual Q4: 2774 |  |  |  | Number of residential customers
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 142; Actual Q2: 142; Actual Q3: 142; Actual Q4: 142 |  |  |  | Number of residential customers
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 92; Actual Q2: 92; Actual Q3: 91; Actual Q4: 110 |  |  |  | Number of commercial customers
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 14; Actual Q2: 14; Actual Q3: 14; Actual Q4: 14 |  |  |  | Number of commercial customers
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 75; Actual Q2: 75; Actual Q3: 74; Actual Q4: 77 |  |  |  | Number of commercial customers
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 96; Actual Q2: 96; Actual Q3: 94; Actual Q4: 95 |  |  |  | Number of commercial customers
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 216; Actual Q2: 216; Actual Q3: 216; Actual Q4: 216 |  |  |  | Number of commercial customers
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 85; Actual Q2: 85; Actual Q3: 84; Actual Q4: 85 |  |  |  | Number of commercial customers
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 1934; Actual Q2: 1934; Actual Q3: 1917; Actual Q4: 1989 |  |  |  | Number of commercial customers
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 252; Actual Q2: 252; Actual Q3: 249; Actual Q4: 253 |  |  |  | Number of commercial customers
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 1410; Actual Q2: 1410; Actual Q3: 1408; Actual Q4: 1524 |  |  |  | Number of commercial customers
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 319; Actual Q2: 319; Actual Q3: 320; Actual Q4: 343 |  |  |  | Number of commercial customers
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 146; Actual Q2: 146; Actual Q3: 146; Actual Q4: 146 |  |  |  | Number of commercial customers
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 89; Actual Q2: 89; Actual Q3: 89; Actual Q4: 89 |  |  |  | Number of commercial customers
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 49; Actual Q2: 49; Actual Q3: 49; Actual Q4: 52 |  |  |  | Number of commercial customers
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of commercial customers
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 5; Actual Q2: 6; Actual Q3: 109; Actual Q4: 124 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 4; Actual Q4: 5 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 4; Actual Q2: 4; Actual Q3: 57; Actual Q4: 59 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 9; Actual Q4: 9 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 40; Actual Q2: 50; Actual Q3: 505; Actual Q4: 525 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 2; Actual Q2: 1; Actual Q3: 20; Actual Q4: 18 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 124; Actual Q2: 127; Actual Q3: 2722; Actual Q4: 2900 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 8; Actual Q4: 7 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 35; Actual Q2: 39; Actual Q3: 1905; Actual Q4: 2084 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 3; Actual Q2: 3; Actual Q3: 110; Actual Q4: 119 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 23; Actual Q2: 31; Actual Q3: 398; Actual Q4: 423 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 44; Actual Q4: 60 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 21; Actual Q2: 18; Actual Q3: 334; Actual Q4: 362 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 2; Actual Q2: 2; Actual Q3: 18; Actual Q4: 20 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | [19 empty] | Number of substations | bar: Actual Q1 to Actual Q4
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 1; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2 |  |  |  | Number of substations
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 3; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4 |  |  |  | Number of substations
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 3; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Number of substations | bar: Actual Q1 to Actual Q4
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Number of substations | bar: Actual Q1 to Actual Q4
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3 |  |  |  | Number of weather stations
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Number of weather stations | bar: Actual Q1 to Actual Q4
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of weather stations
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 15; Actual Q2: 10; Actual Q3: 10; Actual Q4: 10 |  |  |  | Number of weather stations
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of weather stations
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 4; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4 |  |  |  | Number of weather stations
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Number of weather stations | bar: Actual Q1 to Actual Q4
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 8
| Utility | Liberty |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2023-02-01 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | [15 empty] | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: -0.54; Actual Q3: 0.02; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: -0.12; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: -0.47; Actual Q3: 0.02; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: -0.02; Actual Q4: 0.03 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0.42; Actual Q3: 0; Actual Q4: -0.27 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0.1 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: -0.3; Actual Q2: -0.13; Actual Q3: -0.21; Actual Q4: -0.21 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: -0.03; Actual Q3: 0.12; Actual Q4: -0.03 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: -1.95; Actual Q3: 0.17; Actual Q4: -1.51 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: -0.35; Actual Q2: -3.46; Actual Q3: -0.8; Actual Q4: -4.86 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0.29; Actual Q3: -0.27; Actual Q4: -0.12 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.79; Actual Q3: -0.51; Actual Q4: -0.17 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0.42; Actual Q3: 0.04; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0.94; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0.28; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: -0.1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: -0.36; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0.75; Actual Q3: -0.06; Actual Q4: 0.05 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0.1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 2.5; Actual Q3: -0.99; Actual Q4: 1.2 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 3.77; Actual Q3: -0.15; Actual Q4: 5.09 |  |  |  | Circuit miles
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.02; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: -0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.23 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.14; Actual Q4: 0.07 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.66; Actual Q4: 0.94 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.18; Actual Q4: 0.07 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: -0.03; Actual Q4: 0.05 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.43; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.05; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.98; Actual Q4: 0.1 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.15; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: -1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: -1; Actual Q2: -2; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: -1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 5; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: -5; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 9
| Utility | Liberty
| Table No. | 9
| Date Modified | 2023-02-01
[7 empty] | Actual | [15 empty] | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 1.26 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.41 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0.47; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0.02; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0.09; Actual Q3: 0; Actual Q4: 0.12 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 1.27; Actual Q3: 3.08; Actual Q4: 3 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 1; Actual Q2: 2; Actual Q3: 0; Actual Q4: 2 |  |  |  | Number of substations
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 10
Utility | Liberty |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2023-02-01 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | [15 empty] | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric type | # | Wind Warning Status | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW & RFW | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | None | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.b. | RFW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW & RFW | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | None | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| 1.c. | RFW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Customer hours per year
|  | HWW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Customer hours per year
|  | HWW & RFW | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Customer hours per year
|  | None | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Customer hours per year
| 1.d. | RFW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of events
|  | HWW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of events
|  | HWW & RFW | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of events
|  | None | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 5 | Number of events
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Circuit mile days
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 45.8; Actual Q3: 0; Actual Q4: 0 | Circuit mile days
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Circuit mile days
|  | None | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 997.8; Actual Q3: 459.2; Actual Q4: 616.5 | Circuit mile days
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | Actual Q1: 8405.5; Actual Q2: 22184.2333; Actual Q3: 5963.4333; Actual Q4: 16965.4333 | Total customer hours of planned outages per year
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | Actual Q1: 34153.7833; Actual Q2: 71388.3333; Actual Q3: 62850.3667; Actual Q4: 198165.4 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | Actual Q1: 0; Actual Q2: 989.8; Actual Q3: 0; Actual Q4: 7680.8 | Total customer hours of outages due to fast-trip per year
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | Actual Q1: 40.8611; Actual Q2: 86.5923; Actual Q3: 75.1934; Actual Q4: 246.2717 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | Actual Q1: 40.8611; Actual Q2: 86.5923; Actual Q3: 75.1934; Actual Q4: 246.2717 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | Actual Q1: 0.38655; Actual Q2: 0.5946; Actual Q3: 0.73289; Actual Q4: 0.70316 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | Actual Q1: 0.38655; Actual Q2: 0.5946; Actual Q3: 0.73289; Actual Q4: 0.70316 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.b. | N/A | # of medical baseline customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.c. | N/A | # of customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of customers
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of risk events

## Table 11
Utility | Liberty | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2023-02-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actual | [15 empty] | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Grid Design, Operations, and Maintenance | Covered conductor installation | WMP-GDOM-GH-01 | Other contact with object | Equipment failure | 2019 | 2021 WMP | NA | In compliance | NA | NA | [5 empty] | 7820 | 7820 |  |  | 10550 | 10550
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP-GDOM-GH-02 | Other contact with object | Equipment failure |  | 2020 WMP | NA | Exceeds | NA | NA | [5 empty] | 522 | 522 |  |  | 903 | 903
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP-GDOM-GH-03
Grid Design, Operations, and Maintenance | Line removal (in HFTD) | WMP-GDOM-GH-04
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | WMP-GDOM-GH-05 | Equipment failure |  | 2011 | 2021 WMP | NA | In compliance | GO 165 | NA | [5 empty] | 3652 | 3652 |  |  | 5003 | 5003
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | WMP-GDOM-GH-06
Grid Design, Operations, and Maintenance | Microgrids | WMP-GDOM-GH-07 | PSPS - for sectionalization, etc. | Resiliency | 2020 | 2021 WMP | NA | In compliance | R20A | NA | [5 empty] | 672 | 672 |  |  | 107 | 107 | 38 | 38
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP-GDOM-GH-08
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP-GDOM-GH-09 | PSPS - for sectionalization, etc. |  | 2020 | 2021 WMP | NA | In compliance | R20A | NA
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP-GDOM-GH-10 | PSPS - for sectionalization, etc. |  | 2011 | 2021 WMP | NA | Exceeds | NA | NA | [5 empty] | 454 | 454 |  |  | 339 | 339
Grid Design, Operations, and Maintenance | Other grid hardening technology installations and pilot progress | WMP-GDOM-GH-11 | [15 empty] | 1 | 1 |  |  | 101 | 101
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above: | WMP-GDOM-GH-12
Grid Design, Operations, and Maintenance | Tree attachment removals | WMP-GDOM-GH-12a | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 1358 | 1358 |  |  | 597 | 597 | 33 | 33
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | WMP-GDOM-GH-12b | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 738 | 738 |  |  | 600 | 600
Grid Design, Operations, and Maintenance | Animal guards / Avian Protection | WMP-GDOM-GH-12c | Equipment failure | Animal contact | 2020 | 2021 WMP | NA | NA | NA | NA | [7 empty] | 15 | 15 | 719 | 719 | 31 | 31
Grid Design, Operations, and Maintenance | CalFIRE exempt hardware | WMP-GDOM-GH-12d | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [9 empty] | 31 | 31
Grid Design, Operations, and Maintenance | Open wire/grey wire | WMP-GDOM-GH-12e | Equipment failure |  | 2021 | 2021 WMP | NA | NA | NA | NA | [9 empty] | 604 | 604
Grid Design, Operations, and Maintenance | Substation Equipment Replacement | WMP-GDOM-GH-12f | Equipment failure |  |  |  | NA | NA | NA | NA | [9 empty] | 88 | 88
Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment | WMP-GDOM-AI-01 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO128; GO165 | NA | [7 empty] | 838 | 838 |  |  | 409 | 409
Grid Design, Operations, and Maintenance | Intrusive pole inspections | WMP-GDOM-AI-02 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO165 | NA | [7 empty] | 10 | 10 |  |  | 158 | 158
Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment | WMP-GDOM-AI-03 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO165 | NA
Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment | WMP-GDOM-AI-04 | Equipment failure | Other contact with object | 2020 | 2021 WMP | NA | Exceeds | GO95; GO128; GO165 | NA | [5 empty] | 2994.2665 | 2994.2665 |  |  | 19.897 | 19.897 | 1055.9277 | 1055.9277
Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections | WMP-GDOM-AI-05 | Equipment failure | Other contact with object | 2021 | NA | NA | In Compliance | GO95; GO128; GO165 | NA
Grid Design, Operations, and Maintenance | Substation inspections | WMP-GDOM-AI-06 | Equipment failure | Other contact with object | 2016 | 2019 GRC | NA | In Compliance | GO174 | NA
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | WMP-GDOM-MR-01 | Equipment failure |  |  | 2019 GRC | NA | NA | NA | NA
Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk | WMP-GDOM-GO-01 | PSPS - for sectionalization, etc. |  | 2021 | NA | NA | NA | NA | NA
Grid Design, Operations, and Maintenance | Grid response procedures and notifications | WMP-GDOM-GO-02 | PSPS - for sectionalization, etc. |  | 2021 | NA | NA | In compliance | CPUC D.21-06-034 | NA | [5 empty] | 93 | 93 |  |  | 46 | 46
Grid Design, Operations, and Maintenance | Personnel work procedures and training in conditions of elevated fire risk | WMP-GDOM-GO-03 | Equipment failure | Other contact with object | 2019 | 2021 WMP | WMPMA | In compliance | NA | NA | [7 empty] | 279 | 279 |  |  | 250 | 250
Grid Design, Operations, and Maintenance | Automatic recloser operations | WMP-GDOM-GO-04 | Contact with vegetation | Equipment failure | 2011 | NA | WMPMA | In compliance | NA | NA
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System | WMP-GDOM-GO-05 | [17 empty] | 10 | 10
Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed | WMP-VM-INSP-01 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 556 | 556 |  |  | 701 | 701
Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol | WMP-VM-INSP-02 | Contact with vegetation |  | 2018 | 2019 GRC | NA | NA | NA | NA | [7 empty] | 420.8004 | 420.8004 |  |  | 337.8295 | 337.8295
Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDAR | WMP-VM-INSP-03 | Contact with vegetation |  | 2020 | NA | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [5 empty] | 369.2978 | 369.2978 |  |  | 350.4282 | 350.4282 | 303 | 303
Vegetation Management & Inspections | Pole Clearing | WMP-VM-VFM-01 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 0 | 0 |  |  | 984.6756 | 984.6756
Vegetation Management & Inspections | Wood and Slash Management | WMP-VM-VFM-02 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | PRC 4291; PRC 4292 | NA | [5 empty] | 89 | 89 | 360 | 360 | 0 | 0 | 1196 | 1196
Vegetation Management & Inspections | Substation Defensible Space | WMP-VM-VFM-03 | [15 empty] | 0 | 0 |  |  | 0 | 0
Vegetation Management & Inspections | Fire-Resilient Right-of-Ways | WMP-VM-VFM-04 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 771 | 771 | 317 | 317 | 333 | 333
Vegetation Management & Inspections | Clearance | WMP-VM-VFM-05 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 0 | 0 |  |  | 0 | 0
Vegetation Management & Inspections | Fall-In Mitigation | WMP-VM-VFM-06 | Contact with vegetation |  | 2018 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 2722.5304 | 2722.5304 |  |  | 1222.1736 | 1222.1736
Vegetation Management & Inspections | High-Risk Species | WMP-VM-VFM-07 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 7338.3232 | 7338.3232 |  |  | 4677.999 | 4677.999
Vegetation Management & Inspections | Emergency Response Vegetation Management | WMP-VM-VFM-08 | Contact with vegetation |  | 2021 | NA | NA | NA | NA | NA | [7 empty] | 0 | 0 |  |  | 0 | 0
Vegetation Management & Inspections | Vegetation Management Enterprise System | WMP-VM-ESG-01 | [15 empty] | 0 | 0 |  |  | 0 | 0
Vegetation Management & Inspections | Quality Assurance and Quality Control | WMP-VM-QAQC-01 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | NA | NA | NA | [7 empty] | 67.0328 | 67.0328 |  |  | 141.1176 | 141.1176
Vegetation Management & Inspections | Vegetation Management - Discretionary Inspections | N/A | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 85.1387 | 85.1387 |  |  | 2 | 2
Situational Awareness & Forecasting | Environmental monitoring systems | WMP-SA-01 | PSPS - for sectionalization, etc. |  | 2019 | 2021 WMP | WFMMA | Exceeds | NA | NA | [5 empty] | 243 | 243 |  |  | 12 | 12 | 319 | 319
Situational Awareness & Forecasting | Grid monitoring systems | WMP-SA-02 | Equipment failure |  | 2020 | 2021 WMP | WFMMA | NA | NA | NA | [5 empty] | 158 | 158 |  |  | 18 | 18 | 229 | 229
Situational Awareness & Forecasting | Fire detection and alarm systems | WMP-SA-03 | Equipment failure |  | 2022 | NA | NA | NA | NA | NA
Situational Awareness & Forecasting | Weather forecasting | WMP-SA-04
Situational Awareness & Forecasting | Fire Potential Index | WMP-SA-05 | PSPS - for sectionalization, etc. |  | 2020 | 2021 WMP | WFMMA | Exceeds | NA | NA | [7 empty] | 44 | 44 |  |  | 14 | 14
Situational Awareness & Forecasting | Ignition likelihood calculation | WMP-SA-06 | Contact with vegetation | Equipment failure | 2020 | 2021 WMP | WMPMA | NA | NA | NA | [7 empty] | 67 | 67 |  |  | 53 | 53
Situational Awareness & Forecasting | Ignition consequence calculation | WMP-SA-07 | Contact with vegetation | Equipment failure | 2020 | 2021 WMP | WMPMA | NA | NA | NA
Emergency Preparedness | Wildfire and PSPS emergency preparedness plan | WMP-EP-01 |  |  | 2011 | GO 166 | NA | In compliance | GO 166 | NA
Emergency Preparedness | Collaboration and coordination with public safety partners | WMP-EP-02 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Emergency Preparedness | Public notification and communication strategy | WMP-EP-03 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Emergency Preparedness | Preparedness and planning for service restoration | WMP-EP-04 | PSPS - for sectionalization, etc. | Equipment failure | 2011 | GO 166 | NA | In compliance | GO 166 | NA | [7 empty] | 502 | 502 |  |  | 460 | 460
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | WMP-EP-05 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA | [11 empty] | 101 | 101
Emergency Preparedness | Learning after wildfire and PSPS events | WMP-EP-03 |  |  | 2011 | GO 166 | NA | In compliance | GO 166 | NA
Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | WMP-CO-01 |  |  | 2019 | 2021 WMP | WMPMA | Exceeds | P.U. Code § 451 | NA | [7 empty] | 92 | 92 |  |  | 102 | 102
Community Outreach and Engagement | Public engagement in WMP decision-making process | WMP-CO-02
Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities | WMP-CO-03 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Community Outreach and Engagement | Collaboration on local wildfire mitigation and planning | WMP-CO-04 |  |  |  | 2021 WMP | NA | NA | NA | NA
Community Outreach and Engagement | Best practice sharing with other electrical corporations | WMP-CO-05

## Table 12
Utility | Liberty | Notes:
Table No. | 12
Date Modified | 2023-02-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | Method of Verification | Comments
Grid Design, Operations, and Maintenance | Covered conductor installation | WMP-GDOM-GH-01 | Quantitative | Circuit Miles | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP-GDOM-GH-02 | Quantitative | Circuit Miles | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | WMP-GDOM-GH-03 | Quantitative | Poles | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | WMP-GDOM-GH-04 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP-GDOM-GH-05 | Quantitative | Circuit Miles | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilot progress | WMP-GDOM-GH-06 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Microgrids | WMP-GDOM-GH-07 | Quantitative | Microgrids | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP-GDOM-GH-08 | Quantitative | Automatic Reclosers | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Line removal (in HFTD) | WMP-GDOM-GH-09 | Quantitative | Circuit Miles | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP-GDOM-GH-10 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP-GDOM-GH-11 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above: | WMP-GDOM-GH-12 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Tree attachment removals | WMP-GDOM-GH-12a | Quantitative | Tree Attachments | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | WMP-GDOM-GH-12b | Quantitative | Expulsion Fuses | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Animal guards | WMP-GDOM-GH-12c | Quantitative | Animal Guards | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | CalFIRE exempt hardware | WMP-GDOM-GH-12d | Quantitative | CalFIRE Exempt Hardware | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Open wire/grey wire | WMP-GDOM-GH-12e | Quantitative | Circuit Miles | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Substation Equipment Replacement | WMP-GDOM-GH-12f | Quantitative | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Liberty will provide Grid Hardening targets for 2023-2025 in its March 6, 2023 WMP submission.
Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment | WMP-GDOM-AI-01 | Quantitative | Circuit Miles | TBD | TBD | 156.4 | - | - | 264.2 | 260.9
Grid Design, Operations, and Maintenance | Intrusive pole inspections | WMP-GDOM-AI-02 | Quantitative | Poles | TBD | TBD | 3046 | - | - | 2302 | 2411
Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment | WMP-GDOM-AI-03 | Quantitative | Circuit Miles | TBD | TBD | 592.1 | - | - | 589 | 540.9
Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment | WMP-GDOM-AI-04 | Quantitative | Circuit Miles | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections | WMP-GDOM-AI-05 | Quantitative | % of Detailed Inspections | TBD | TBD | 1% | - | - | 2% | 3%
Grid Design, Operations, and Maintenance | Substation inspections | WMP-GDOM-AI-06 | Quantitative | Substations | TBD | TBD | 42 | - | - | 42 | 42
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | WMP-GDOM-MR-01 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk | WMP-GDOM-GO-01 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Grid response procedures and notifications | WMP-GDOM-GO-02 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Personnel work procedures and training in conditions of elevated fire risk | WMP-GDOM-GO-03 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Automatic recloser operations | WMP-GDOM-GO-04 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System | WMP-GDOM-GO-05 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed | WMP-VM-INSP-01 | Quantitative | Line Miles | TBD | TBD | 220 | TBD | TBD | 220 | 220
Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol | WMP-VM-INSP-02 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDar | WMP-VM-INSP-03 | Quantitative | Line Miles | TBD | TBD | 700 | TBD | TBD | 700 | 700
Vegetation Management & Inspections | Pole Clearing | WMP-VM-VFM-01 | Quantitative | Line Miles | TBD | TBD | 4960 | TBD | TBD | 4960 | 4960
Vegetation Management & Inspections | Wood and Slash Management | WMP-VM-VFM-02 | Quantitative | Acres | TBD | TBD | 280 | TBD | TBD | 280 | 280
Vegetation Management & Inspections | Substation Defensible Space | WMP-VM-VFM-03 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Fire-Resilient Right-of-Ways | WMP-VM-VFM-04 | Quantitative | Line Miles | TBD | TBD | - | TBD | TBD | - | -
Vegetation Management & Inspections | Clearance | WMP-VM-VFM-05 | Quantitative | Line Miles | TBD | TBD | - | TBD | TBD | - | -
Vegetation Management & Inspections | Fall-In Mitigation | WMP-VM-VFM-06 | Quantitative | Line Miles | TBD | TBD | 220 | TBD | TBD | 220 | 220
Vegetation Management & Inspections | High-Risk Species | WMP-VM-VFM-07 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Emergency Response Vegetation Management | WMP-VM-VFM-08 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Vegetation Management Enterprise System | WMP-VM-ESG-01 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Quality Assurance and Quality Control | WMP-VM-QAQC-01 | Quantitative | Line Miles | TBD | TBD | 229 | TBD | TBD | 229 | 229
Situational Awareness & Forecasting | Environmental monitoring systems | WMP-SA-01 | Quantitative | Weather Stations | TBD | TBD | 5 | TBD | TBD | 0 | 0
Situational Awareness & Forecasting | Grid monitoring systems | WMP-SA-02 | Quantitative | Fault Indicators | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Situational Awareness & Forecasting | Fire detection and alarm systems | WMP-SA-03 | Quantitative | DFA Units | TBD | TBD | 0 | TBD | TBD | 0 | 0
Situational Awareness & Forecasting | Weather forecasting | WMP-SA-04 |  | - | - | - | - | - | - | - | -
Situational Awareness & Forecasting | Fire Potential Index | WMP-SA-05 | Qualitative | - | - | - | - | - | - | - | -
Situational Awareness & Forecasting | Ignition likelihood calculation | WMP-SA-06 | Qualitative | - | - | - | - | - | - | - | -
Situational Awareness & Forecasting | Ignition consequence calculation | WMP-SA-07 | Qualitative | - | - | - | - | - | - | - | -
Emergency Preparedness | Wildfire and PSPS emergency preparedness plan | WMP-EP-01 |  | - | - | - | - | - | - | - | -
Emergency Preparedness | Collaboration and coordination with public safety partners | WMP-EP-02 | Qualitative | - | TBD | TBD | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards | TBD | TBD | TBD | TBD
Emergency Preparedness | Public notification and communication strategy | WMP-EP-03 |  | - | - | - | - | - | - | - | -
Emergency Preparedness | Preparedness and planning for service restoration | WMP-EP-04 |  | - | - | - | - | - | - | - | -
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | WMP-EP-05 | Qualitative | - | TBD | TBD | Conduct Incident Command Training for all identified IC members and hold a Virtual PSPS Tabletop exercise; Continued implementation of Liberty’s 2022 AFN Plan; Continued maintenance of emergency response plans; Enhanced documentation and use of lessons learned to update plans. | TBD | TBD | TBD | TBD
Emergency Preparedness | Learning after wildfire and PSPS events | WMP-EP-03 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | WMP-CO-01 | Qualitative | - | TBD | TBD | Continue to survey customers, CBOs, community partners and stakeholders to understand wildfire and PSPS awareness and the needs of customers. Strengthen and expand AFN CBO partnerships. Identify emerging channels and technologies to better communicate with customers, community and stakeholders. | TBD | TBD | TBD | TBD
Community Outreach and Engagement | Public engagement in WMP decision-making process | WMP-CO-02 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities | WMP-CO-03 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Collaboration on local wildfire mitigation and planning | WMP-CO-04 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Best practice sharing with other electrical corporations | WMP-CO-05 |  | - | - | - | - | - | - | - | -

## Table 13
Utility | X |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2023-02-01
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
4647a002-0af0-4b07-8c9f-c98ed5bb1faa | Pole | 2 | Distribution | 2020-04-09 | 2025-04-08 | Level 3
6ef80bad-a949-4aaa-93a4-ce252d210ff9 | Pole | 2 | Distribution | 2020-04-10 | 2025-04-09 | Level 3
062e61ae-866b-4c65-a751-787bd12ba3bd | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3
0b83e500-030d-4ded-a4db-62533d2ece14 | Pole | 2 | Distribution | 2020-04-13 | 2021-04-13 | Level 2 |  | 2021-04-02 | 2022-04-02 |  | Required to Re-inspect a subset of assets
408a13b3-eb60-4a2f-91c4-79ab1ced3f91 | Pole | 2 | Distribution | 2020-04-13 | 2021-04-13 | Level 2 |  | 2021-05-27 | 2022-05-27 |  | Required to Re-inspect a subset of assets
4632b479-2b43-4530-a9f3-00539ecead09 | Pole | 2 | Distribution | 2020-04-13 | 2021-04-13 | Level 2 |  | 2021-05-27 | 2022-05-27 |  | Required to Re-inspect a subset of assets
5e183598-a539-4706-beaf-ee1a2c8a13d0 | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3 |  | 2021-05-27 | 2026-05-26 |  | Required to Re-inspect a subset of assets
ab7d95b8-417a-4a70-840f-e6c409a19c16 | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3
0285bc85-5e14-4320-9904-1823aa2376a3 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
0afe3999-0f69-4626-a966-c0ceaa8b79c7 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
0df54f4d-f917-4074-80a7-4da7e13d0a8e | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
14e549d8-7961-4a7b-9094-1f8e3fcfe401 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
186ec59a-27b4-4a1f-8ee5-e2dcbc4a1842 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
27f273a9-f0c9-40a4-b1f5-7e56beb88eda | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
621cd443-057c-44a9-986d-8f806b7066ef | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
77b1ed33-c2ab-4598-91cb-4058d358df04 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
93655288-925f-4af3-9414-7c432241a9b6 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
99d93125-b62b-4341-a833-2c920d888a83 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
be24cfc1-08ac-4c05-9d6f-9ef610d15aab | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
c8131cc2-3a08-42bf-b7d8-1708276012ea | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
e04d5835-06c4-4f71-a0bc-6ba9b71ed739 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
e2ea30de-0167-4acf-824d-93858c3813b0 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
e4959f03-aef9-4718-a6c3-cc1e1ab788a8 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
f612475f-7fa3-4094-8d19-1f42cc4f7a5a | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
fd1f5200-6859-4d8e-bea4-ed4554ecbb5a | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
01d6c74b-e359-459d-b47f-c66fe2225669 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
047f3f3e-6600-42a1-8dda-fca0b5418a66 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
04b22eaa-9f6a-4001-b5dc-dc2d078007bf | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
0883ebcb-778e-44b3-b8b4-6c1767d019ef | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
08c02c81-3d3e-4674-8fac-2048684dea52 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
09e9fa0f-ac47-4a92-8f47-a4bcebc5db54 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
0ea06e49-19a9-4e6e-9453-2efc22b69a8c | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Required to Re-inspect a subset of assets
1afb34f5-1250-4ae9-908e-30b3de598bc4 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
21f6294c-a614-43cb-853c-c50f5feb2c30 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
22073d1f-54d1-4363-9d87-5f5e4bb7bc4a | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Required to Re-inspect a subset of assets
361c1760-777c-4760-8c31-b9be704d3d81 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
3a463e14-a140-4649-930a-e01b509326a5 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
3d8f4f08-f0e6-4a49-8880-c43fa308a8e0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
3f8e7a84-5a1c-4b8c-be93-c7602a4dc1d0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
4096061f-9a87-49a1-b8c9-65867bb5d62c | Pole | 2 | Distribution | 2020-04-15 | 2021-04-15 | Level 2
4183c821-6f73-42eb-975a-c452917f9789 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
44cf1cbd-820f-4a0c-9384-95d505a31638 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
52395920-5878-4b42-b049-a1aad481cfee | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
52e11b26-71f8-410a-a5d5-a729a27f0813 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
56e11b57-691a-4697-b525-2cc9925c9d0b | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
6400e8f5-4426-4f53-96de-d236cbb046e4 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
651f1799-2533-4911-ade8-9ce983af9bf2 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
6bc92c9d-c72d-445a-a763-d3cc4a1f589d | Pole | 2 | Distribution | 2020-04-15 | 2021-04-15 | Level 2
701c1854-9b5d-4972-bca6-55e4a6ad409a | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
8f98695b-4903-459f-8c78-176d3a834c64 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
9e962665-bc94-4dd2-9062-556c722c2b2c | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
a17b8d85-c010-434f-b6ff-a6ee5981aab0 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
a93b3153-7b43-44f4-9458-62df2eaed7cf | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
ad618fb7-6e8e-4ed1-bcf1-d07152b9feb1 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
ba9b80e0-fd27-4a50-b92b-8b9fc34dad35 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
bcb0f141-d8b6-4ed2-a4ab-d0ef12527dd5 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
c3f13bc3-e395-4f25-ba97-44eb49f3e65e | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
c9c4fa62-81b0-4bdb-a049-43ab274bcbc1 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
d74dbdce-fd34-4113-9f24-df16414b3790 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
da5e00d6-8f44-4bae-a11e-844d5d1f1f64 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
efbc38ed-2ccd-4eb4-ba72-58c241ef9ce0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
f403f7f3-2caa-4773-bc8e-bb19cbcf21fa | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
02691da4-35fb-4a11-8ab3-ec566dc61c4b | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
07977cbc-9149-40e5-8bb6-4c9c151303db | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
0b9c0fe9-444f-4135-aeef-d0a9972b32bb | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
1412eba2-827a-4857-94b1-f2d0421d01c4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
151f16cc-ca70-468f-b6fd-75d085ef2813 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
1bdc8b4b-2b00-4962-90d6-94803586f065 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
29507e3e-4130-4f9a-979a-fd16a2e7b536 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
30427d6b-0509-4c36-a68d-c9111f609c98 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
38f7296d-4930-49e1-9510-3637bf8e0be5 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
392be24c-9cc5-4951-81fb-c037186123e8 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
3bd638bd-0190-4cb0-a3f1-7de71610b198 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
4203a1f1-8128-4901-a86e-57a0bf730038 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
457c586b-b7c7-4316-997b-efa9afe8c124 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
5b7237ce-396a-41c3-ae5e-29c7dc6ab153 | Pole | 2 | Distribution | 2020-04-16 | 2021-04-16 | Level 2 |  | 2021-06-02 | 2022-06-02 |  | Required to Re-inspect a subset of assets
64a178e6-fa47-4970-b56e-0b49b0d1028e | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
675eeff6-eabf-408b-b4ed-e399c3acd6ec | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
704f4cf0-4c90-444c-a9f8-fa3349b3dc48 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
7730be94-43b7-45fe-9656-3466337cfb17 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 2021-02-10 | 2026-02-09 |  | Required to Re-inspect a subset of assets
7cb55b62-90bc-4884-95a2-717037cc85b3 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
806a56a7-59b8-4349-bfbd-66be64e04793 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
8cbf0acb-8fcb-4e4d-8525-68799c14afa4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
8f93aa1f-caa1-4ad6-b861-67acb766ebea | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
92609d42-3a00-42d8-900a-c6f62ad88f9c | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
954be54a-ad19-4a80-b24e-930271435ae8 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
9cbf0d85-7f21-4879-9dfd-fd9910a14be4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
a902c5a5-04f6-467d-b67f-015295133382 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
b213d07d-650d-4f91-b92d-27aafe1db071 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
b2841180-667a-400c-b6b2-363f2826e918 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
babbf408-caae-4fbb-9ba5-3609e58c43ec | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
bfe8b61c-6d2a-41cb-a337-8c60da0ca7ac | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
c1a92c54-9344-4296-94dc-9a4ee053aa85 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
c681123b-4b20-473d-bb7c-f7aabb18cf6f | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
c8eae61e-9f20-4bb2-b691-160e78626c9a | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Required to Re-inspect a subset of assets
d0383438-6416-47a5-8811-fa20f6aa4877 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
d50e5640-b3e5-4ab4-8fdf-7302c89dfb3e | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Required to Re-inspect a subset of assets
d8964c17-b5f4-485c-b481-1c8848876cce | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
e1b50f00-b34d-4353-9f26-91404543833f | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
ed3fe5c1-1ee2-4792-a1cf-e667c191531a | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
fdcfeaab-dcdf-45be-9d3c-8ef2add63147 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
012e6b14-40f9-40ee-8b0b-129121bbe713 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
0179ca7d-c005-4946-8475-d588b6401759 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
0768ebec-fc3b-4135-aa8b-7f5b7db41a6d | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
07ad58b3-fc44-4081-9527-611ef3bbea00 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | 2022-01-18 | 2027-01-17 |  | Required to Re-inspect a subset of assets
29aa509c-d0d5-470d-a4eb-bdef0fc7603a | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
424f1ca0-d53d-4289-a3fb-94a762bf16ad | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
5009dcc9-f8c7-4b1b-8499-04d3947f2d23 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
51b29948-21e5-4747-a454-690d9129d040 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
58912729-0b81-45ae-8534-5733ae947555 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
6445f9f7-a93f-4d69-ba02-057c304c9d93 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
a9275406-a444-4867-b8be-c680679fb079 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
d2f771b4-1fd1-416c-930e-35eab0a3cbe0 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
ed429bd8-3666-413b-a956-b6a4abd3c957 | Pole | 0 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
f39a5c5a-a70d-4e74-9e85-b442019dd0e7 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
f726b5d5-5780-4ec3-964c-9b9c75395b64 | Pole | 2 | Distribution | 2020-04-17 | 2021-04-17 | Level 2 |  | 2021-04-23 | 2022-04-23 |  | Required to Re-inspect a subset of assets
0a3b271b-1ae3-4423-92cb-0a6551313004 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
45c8f5a8-5244-496e-a503-1d2fee48c9ac | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
4c23040e-31e4-45c2-8037-3a0726091cbc | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
53ad3a5b-5149-4e22-9eb1-6a7efbc43ee6 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
65fe869f-1899-4d68-99de-af301e37f52a | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
6a64ce17-1a36-4066-939f-33ddd4490f32 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
bccc86f7-f67a-40bf-b089-cef29c9c942e | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
011fdb3d-c951-4a32-9f79-0bf6e20719ef | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
0a76f961-1187-4364-b614-f4136c4e5c62 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
0ec8cd5a-be6b-49c6-9d20-f3dd494bb069 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
10dff315-fec7-4327-88c1-332a4ed87c1e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
190bc995-7a47-4d8b-8bc0-c7ef82381248 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
1bb9f3bf-0ec3-44e6-bd52-5de556f2f7a8 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
2395bd13-6049-4d62-9371-f6a71ae5eb56 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
2958caf4-a91a-46ab-a32e-a78524fe6015 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
29d73382-fd62-4c61-bb6a-f17dc156c53e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
3314cf32-c8c7-4de0-be50-59f893bc4378 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
3e00bbd3-243b-4eb1-a313-4e12640a95ca | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
3f40d5f9-e980-47a2-b8dc-46a84b3c4d17 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
5180aa14-ba35-4006-bbd6-adec82841833 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | 2021-02-10 | 2026-02-09 |  | Required to Re-inspect a subset of assets
51eb688a-6040-43ca-8f5c-9e1d0f152402 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
561f8a7d-1085-49eb-9450-fdb1299f0f4a | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
56521823-2149-49ac-9d56-dc1d9cd34dfc | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
745b7f2e-ec59-44fc-b136-f0642b600204 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
767496c9-70bd-4f0d-8a26-ad435ffe667f | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
7777d14f-f6da-4385-a437-e56f8241a554 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
7a15f696-2919-4fc7-802a-00a25ea0b941 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
85bb94f8-a5c3-466e-a765-7d91b7ab68cd | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
85ea555a-b7ce-488b-96df-24a243705569 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
92f0442e-a417-4958-9667-8c877e5d7921 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
9b81b43f-ac48-47a5-bb9e-484cc9840f9c | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
a9a3b0e2-7266-428f-b4b5-5a18d8cae88b | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
acbf2db0-d5ea-4df1-b4cb-78d4950758df | Pole | 0 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
afbfc2ba-03f4-42df-8ad2-1ba84be87062 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
affbb68e-abfd-4cd0-8311-847b0474a597 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
bdb06a02-45e9-4a9c-9f9a-6f2d6b471542 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
c23594dd-16aa-43a8-afbc-c6cbccc8a83a | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
c4079f18-1e1a-40df-b140-3adcbf8a3cd4 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
cd18cfd1-b975-435c-b97a-26df11cddb7e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
cd271600-5414-4423-ac95-425a27d58550 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
cfdf8038-78e4-4b94-a381-140a991fb875 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
d7c82787-3415-4296-a1f7-c6ea3d73180f | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
d9d62337-45f1-4842-9e75-2828497afee0 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
e0fc6f4d-910b-401a-b303-6fc49c380c85 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
e987f4f9-db2e-4b0e-bc85-dfc9d1490c04 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
ea8b7c5f-6bd5-40a7-a81b-6d4995b974c6 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
ee90950b-48af-46a6-9428-8f169b5d5c8e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
ef289629-0095-4247-90a8-e676f74b8c35 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
f6f1cf70-f8c3-4f98-849a-ebac0797fd16 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
fc442c7a-2fbf-4697-baa0-40f4428d2ef4 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
1038cf65-c946-40b7-a2f4-77e5ec3305d7 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
1680450c-0582-432b-aeac-a5827ee1a94f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
1a5094ac-da30-40d9-b916-ccd79e47d854 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
1ddd7e6c-aa1e-4851-8111-dd3d765503b8 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
289ffda9-97f2-4b2a-abe8-e678e6f084ca | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2a7d5cd6-c887-4f4a-80fe-2f789e1a9ef6 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2c7d5038-f946-42fd-b48d-7f28c4bc4498 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2dc6ab5f-32b8-4a7e-a16e-04a265f731c0 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2f95c48e-3d8b-426a-adc2-ea226366f938 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
33a69be3-0d81-4e88-98c0-f23783f398cc | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
3664cd3f-59ba-4d71-98e3-a13c02708d03 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
44a42916-abdf-4565-acb7-c47e84e88d4a | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
477d4921-d355-44e9-8127-73e2abfb0840 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
491763eb-a112-4dc5-b552-a84fe7eddf9a | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Required to Re-inspect a subset of assets
58b929de-5247-448b-a68c-fe41b5e3b24d | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
5f31c132-6f0a-4a98-aa94-78ba041ee760 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
6b301545-6b00-4341-a430-7dfeabac34b4 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
747b45b6-2e59-4d73-8b7a-17455a66a67e | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
9f5194d7-7ef2-45ce-8f61-268b60afca3f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
9fc0ffa7-335e-433e-8a95-79934889322c | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
a73f63e2-0bdf-4362-84b7-f2aebcb3eef7 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
b4272723-6a32-4de2-b80a-58127ad84b42 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
c8a688cd-78c4-4ad8-ba41-4b228806923b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
d191e4b2-3e69-416d-b7e4-1701b534e01b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
d3b55c3b-f849-460a-b00c-d876394ffe3f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
d8f5c361-8ec4-4580-806f-0696447b723b | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Required to Re-inspect a subset of assets
e2ca8f63-ca7c-4267-a107-589ca5e1b013 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
e7bb481d-ee41-49d4-b55b-1a1146764970 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
e87f2462-9024-4202-bef6-a8216a7b316b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
f2cba526-375e-4a99-aaa9-432169446cea | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
fe1b98fa-0479-4aa7-bde5-fcd6b95614b0 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
09d5ec18-7ed2-44ae-898e-43cd5a2e90c7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
0b975f68-e109-4084-a542-6936e358ba21 | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
1315b189-4810-4252-9e96-1832f27bfc2d | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
2edfd5a7-dee6-411b-a024-e586c7b72d1a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
2fdda43e-a414-49d1-a797-bf9f5f1f6923 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
348ead00-07ed-4307-b735-50cec0e2f971 | Pole | 2 | Distribution | 2020-04-22 | 2021-04-22 | Level 2
3916edfb-7b0d-4177-a0a9-d1a12fcdc21f | Pole | 0 | Distribution | 2020-04-22 | 2021-04-22 | Level 2
3c61f6bb-f2f4-41c5-b74b-1c9757a85d76 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
41373813-f3a1-40f3-8b6a-51620bcb51ad | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
414e240c-64ac-4243-adfa-6f3e5b2033ff | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
464b3f46-a131-4ac8-9c48-0bf0b6d9717b | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
53745b1e-7593-41e3-adcc-5dbf85383dbf | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
5555bfe4-aa94-4180-aea8-4c63dbc19bf7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
593da27a-be52-430e-864c-4f96bbfa6500 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
67e7d1c0-4255-450b-ae74-720a1c6d3ee9 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
6a06e581-4e98-442a-ab47-24dc57f0b533 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
6ca4fe7b-0bbf-4585-aace-3726f01d34d7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
78e905ec-0006-490c-94eb-bd55dc617a0a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
79a5ff48-4ab8-49ed-8b27-179c5a018434 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
7d90a458-b5d8-4e50-b1e1-e8902f317992 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
82ae6940-357e-4f1e-8760-489024f96910 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
8df3e928-0f3d-47cf-af43-1ec84f821bdd | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
930af33b-56d4-411c-8946-dadb7fca5b96 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
968ca7e4-8732-4a66-827e-a1f034d16d78 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
9b520188-af2f-4ba4-b57d-9d3191ca4711 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
9b690f08-76b7-4fae-bd57-13d2474b0ae1 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
9ed46254-7134-419e-adf7-387fe6096557 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
aeae9bb5-9123-4117-af70-cb9341ba2f26 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
b337e368-3ec4-4953-9033-4691e8ee7b45 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
ba84d0e9-ca7c-4734-94d9-53e3ff4dc065 | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
bab31805-c363-4d70-abb9-663a5ee51044 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
c4c9e8c5-1849-47be-be0b-c29ef324f226 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
c83c26f0-2b58-4a77-88dc-7cbb227e131a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
c8e84706-14a2-4021-af40-2ea2dcae664c | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
cd44ea95-389d-42d4-9258-541932298835 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
ce8baa4c-bdf0-4539-b3f4-ea531d8c0858 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
d2f2e459-deb6-469a-bfb6-688ad81186a7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
d78e72e2-1767-4299-a45b-1f2caff5907b | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
e02c0192-81e3-4a0f-b8c3-8d4066e6fc48 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
e86dc3ef-e925-45c9-ab5d-40a022a01820 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
f7c3560e-1e28-4228-9b91-b32216ee6422 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
fea88618-8b64-4a43-8887-09db6fceb5d6 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
ffcbe9f2-5a40-4740-9ead-27f63142b2f8 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
0463cde6-9418-413b-b755-390ed34aa677 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
0aaf83fd-8545-4826-85d0-71e05450a684 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
0e895f7d-aa31-4248-a239-54b5ba0bf69f | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
1189e360-cf6c-441a-b1b2-7181b6b3f818 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
14a8e0e7-64a6-4d57-b6fc-60fbb6db1198 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
1728d1d8-5718-477e-ac21-40d1f50dd7c5 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
17be4394-07a7-4e09-bbd5-b7757f645743 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
1b171de5-2db1-416a-891c-4f7fba14fa64 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
2c126c3b-35b3-4b09-866c-ad350d97661b | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
2d616e43-f43a-4608-97bd-40131d8fe579 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
30e3df49-05d2-40e3-8337-67a1f890dcd9 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
34febe28-5276-477f-8cba-9171b96fee69 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
3a9c8c7f-7d31-4f66-a114-a8335401f4f9 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
3c571e2b-540d-4e9a-b23c-941815925a0c | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
4fb90ed1-9a09-427d-9f06-4ad972bf6ec2 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
57af0bba-d81c-4959-9fa2-0f9fc45486ee | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
594207b9-1c2b-4223-aa8a-373fb19e1cc5 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
5ff8551b-994d-4812-9976-1197f80619ff | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
65ea9b8e-ebd7-468f-8e2b-a1e84a2bddb6 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
6770e7a6-9df6-491d-bb4a-6c73ed51106a | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
693ad4fb-5e89-4305-8f19-febad96819e4 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
6d7638a1-cfe7-4341-aa28-62b098dbf121 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
74689919-abb5-43eb-a049-2cbe15941fc7 | Pole | 0 | Distribution | 2020-04-23 | 2021-04-23 | Level 2
76c823e1-20c7-476c-ad3f-082f1f2f5312 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
78705628-d02c-48cc-aa99-f45ce803a379 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
79fcdf9c-1b78-47bf-a59f-09843066c16d | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
7c3f9750-2aa0-4eab-8269-bcf940f3d658 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
83df61ef-a37e-4127-bc92-40be66c53d09 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
8f0fb592-05a5-453c-9458-79743e63281e | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
90cf3f03-79ed-4b75-87d0-18f727d55766 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
9f444a68-d568-40dc-ba3b-7148679b6b6e | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
c38ab4c8-f8ff-4694-a012-43c8cad96184 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
c9b78ab8-6064-4095-a9f9-c124c6865c5f | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
cc0880ad-3986-41af-8002-c42769af9bfb | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
cf1a3e34-e802-443d-bcae-87a5fa9c495c | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
d80f7409-45e9-4730-911c-b1cdc702ad8e | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
e393b4f1-6870-4767-8bfc-6fa2017dab2d | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
eaabc6a5-7887-4001-b7ab-b68af62b6af0 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
f7496b4d-e984-4905-8964-65b60f15eb6c | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
fc00541f-050e-4859-bd85-2d37d2dd7880 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
031e5e33-430b-4ee5-b3f1-ff553e8ef611 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
1d6f13cd-73c8-4c6c-81fc-982919547f5a | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
22263dcf-3c6a-415b-b628-cb3020a24d21 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
23553030-1c93-45d3-9af4-1146770fb33d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
2658bee1-2912-4307-a1a2-e8bc0c8a9b22 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
35312874-6588-4fc3-8d43-acd6cff9a3e4 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
4362f727-1e3b-45d8-ac26-34f497563152 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
468f77b4-aeba-4c1f-b80e-465c1d3e4e2e | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
4dbec616-d185-4342-ae3c-bda82bd2db1f | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
5158e0ec-2e62-42e8-b1be-b42a12f50141 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
5374348c-ea11-471f-a2b7-d4e7f8582713 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
56e6d26e-f56b-488f-aebe-ae32f72cae50 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
5a638305-51ad-47e4-ad07-128107163607 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
5b2dcaa5-ce5c-4b28-87e8-91db4577ff84 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
636a0edc-2a68-457d-8ac5-0132755ff629 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
63a27cc3-61be-4796-8fc1-cd5e2f7cdaf1 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
6f9617ef-ed2d-4446-b4d1-e95cf99e2027 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
70b70a5e-143e-4355-bff6-e4a5ca6bdf77 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
72b9b52f-e8e0-46f9-8cf4-513e53c93d36 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
7df47d11-625b-4dd1-82b9-69cc53395b36 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
7f05b1b6-5d6b-4ed1-a974-a1e86e2a1172 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
85284b29-db3f-421d-b71a-5018416bcd77 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
8b339ae1-63b2-42b9-879f-1369b547f46d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
8c6222be-80ae-4c20-8175-fd6e02588f74 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
942969cb-ec34-4d44-adce-69cbf526994f | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
95fbca92-9796-4746-b5b4-b91729f6e394 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
9c2e15c3-431f-41a4-b0a4-df2e0ab9bc84 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
9eebbe5f-1348-4749-ad9f-2d3c7e2457e0 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
af059ab7-70f8-42ed-8863-864a800daac7 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
b3aa5ff1-2e11-4fcd-8bd5-d3b365476aef | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
b535aa4b-763e-4e94-996e-2e4b218884e8 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
b709b02d-da27-4353-bf28-9efa2a4fd5b6 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
baaf1d43-7540-46d0-936d-7b2c82ec2dba | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
bf5d3535-526b-4568-bd0d-77488ef77e96 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
c8cf8b0e-7317-4659-9692-aea4ef275e33 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
cbfc257b-df92-47a7-a29c-a7212f4e354f | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | 2022-01-17 | 2027-01-16 |  | Required to Re-inspect a subset of assets
cdc89234-0185-4242-942f-12f4bb17161d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
ce14771e-9686-4d33-90ce-30fdb3b084d6 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
cfaa8f2a-487e-4d02-9df5-51db1e27e45c | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
d6ccb6ed-5d8e-43c3-9369-95f01c2d5fa0 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
dc429a9a-de94-4609-aa9d-e399944f899b | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
e6b2c619-0a72-4f3f-a4e3-087c1279c92b | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
f438a777-b494-4635-a6c7-209a0a40d197 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
32b9b9a1-4096-4b4d-9b79-0b77845dc752 | Pole | 2 | Distribution | 2020-04-25 | 2025-04-24 | Level 3
052d2dca-85a3-441f-bd7b-1c872bed5b31 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
0b20744c-7ce5-46c0-8662-d6ced55ce383 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
0cb86daa-8b95-44c7-8511-eed3b1ff75df | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
11106336-8d8f-468d-b652-e5eb268d707c | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
14e64303-7777-4f98-a2cd-11d4d0b78db0 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
1513cbde-9513-4a2d-b368-c118048e6255 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
15e04300-3efe-4048-b1f4-8dd65b10999b | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
172614e1-501b-434c-b4b5-38095ee5c956 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
18471bd1-4e36-469d-9510-377de789fdb6 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
1906ceb7-2181-43ea-bb68-72b0f275c8b5 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
193ecc48-f145-46f7-afb6-d7323365fdf9 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
19f52d03-65ae-47fb-968b-8a6af7f6974b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
1add986b-aa20-4c3d-868d-fa81f86c3876 | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
2002442e-e364-4238-a189-ee3662ac8661 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
20b078f5-16e1-41e6-82d1-906a27abb805 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
278b44e5-1673-4864-9931-6f93bca43f7f | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | 2022-01-17 | 2027-01-16 |  | Required to Re-inspect a subset of assets
305760d3-ae78-40be-9883-9813964cc033 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
35231c4f-2d82-4ed9-8941-f3d334697e52 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
358dbb48-3405-48d7-a534-aa2998c50fb5 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
47a7d44b-9b90-4b65-b4e5-f893dd2f2e8d | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
4d87377c-721b-4d68-8e25-42c016158f1c | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
58115f5d-f7bb-4d15-aeed-96d7913e71da | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
58be6e1d-4c82-4459-9369-350933d98e5a | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
62140000-74be-412f-a13c-323014773a5f | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
64630b3c-53f9-497f-8e2c-459d02c7ab55 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
6af294aa-abb9-4aa8-a9cd-0c5bcd2d6921 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
78bd680e-0b2c-47b1-b275-f41547a0c3a2 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
79f6e532-bb09-49b2-ad4e-f2c948273036 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
7c79b616-4c5b-4716-9599-e3a03edee57f | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
827da063-638a-41d0-abc4-a4c3e807f4d1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
85e97c2c-4a72-448a-9f6c-05ac725c2882 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
86ad855b-a238-408a-91c7-0cfa0f2641ee | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
8781a40d-2fa2-4ca4-9073-7d05247afe3b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
893968a9-f7d2-4c0f-b312-20e4d5d4a1a1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
896e8a26-5c9f-42d7-820f-060d929235d3 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
96d95561-583f-49d0-bdc1-6f4b9b60c165 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
9e5fab15-37da-415f-8f67-0d4e209faaf1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
a58e9d74-fc1a-4044-9f60-0dc239b4422b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
b210a6a1-345c-44a9-bf7e-80683aed5177 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
b5ef5c4f-9165-496a-bd80-f8f3312b493b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
bfcb00fc-2568-4adc-88b5-7163e41a6ce6 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
c1163052-4bef-4cb5-9b09-7e4bc1ba5820 | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
c6b6951d-8a6a-405e-8943-338675b992eb | Pole | 0 | Distribution | 2020-04-27 | 2021-04-27 | Level 2
d0ac0ba1-f028-4950-9fd6-fe26ff9e43f1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d0e1568f-be1d-47a5-9f85-749f2e35056c | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d25291aa-f01a-4bf2-aff3-b3d8388fab22 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d3bd90b5-ec10-49a6-a840-1dae9da3dfe0 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d7a5be38-5c2e-4e16-98df-e31ad6467bed | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
e09d463f-2b2d-4cde-83c3-31f82e066b68 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
e5408b23-06a0-4889-9cfe-1459aa63425d | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
e6f5fedc-e6bc-4424-ae7b-690392737d38 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
ebc04b78-716d-4f65-abc8-f6a8510b86e1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
f346c9e4-0241-454f-8168-f46c74cae8c3 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
f947711f-32df-4c92-b4d0-ddb1d2ee18b9 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
fdf225e1-57bd-4723-bd69-b9442cedb160 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
003532a5-f874-4897-86e2-01d263236200 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
08da7db0-5556-45c8-bbaa-9e6b1c70a52d | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
0d056eb0-3bf1-4fa6-b47c-01880a10fb9f | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
15171492-6852-4719-a1aa-18c406ae8fd8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
1569a903-0015-46c3-b11d-f88e6b9b0587 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
2110b418-c40c-44c4-87f5-1019f222072b | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
2e895b5c-d700-4386-9ff1-635f4b0e2494 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
4069606d-04ed-497e-a25e-884ebd7bfbe5 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
47eff5b4-e383-417d-87c8-2ae90b78daf6 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
520771fc-2c29-42a4-a70e-0145754135a3 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
62c3fda6-08bc-45e5-8acf-64d416454ffa | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
6f0242ae-d2eb-445f-ae81-1551879392ae | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
83160693-5a95-4aa8-93c1-fcf36d4afa60 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | 2021-03-03 | 2026-03-02
87965bb3-6c6d-4ccc-bb48-fa2a349c8484 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
89e32e9e-34d5-46ad-93f5-5c81514796f7 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
9321a826-8036-451a-aef9-c8dd8b9ea4a4 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
a331fcfa-a745-4e38-9ff8-696690322020 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
a589524d-986f-4ccc-8eb2-221838a26ba8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
aa752864-76a1-4ecd-82ce-20979837f59d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
aac3b5d7-4eec-4939-8f72-97303baa8232 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
abdccf8b-0d55-4fce-a61e-5237525935d1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
ad4a636e-ea02-4786-b635-53eb41b28eba | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
adcd4bef-d719-4c53-a2a7-642f425852f6 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
af3ba445-3fc1-4727-8471-2d77b11eb2d3 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
b1a2b2dd-776c-484f-a18e-0c1c8aee0c98 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
b57528d2-d09c-4c83-89c9-a21717aee097 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
bbe541da-1c00-450b-b3ef-39beee439c05 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
bee7947b-f1ff-43ce-8cee-9063fc018f83 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c33c1b73-5222-437f-9258-b4814fc9cab9 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c44b7643-4161-40df-b44e-54de45c0f367 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c886beca-9c20-4a89-b578-8a6e93e503a8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c8dd21e1-80c7-4423-b8b6-bce86b47a8f1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c9fb3f22-fb50-45b5-a1f6-7341c660bdfa | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
ccf879c4-ba71-46c3-8695-b171ee936317 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
ce2f3699-c7f4-4fcc-ac90-d21d2f3d8861 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
db916691-1634-4971-b061-0f57059d73b5 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
dc6bf244-0db6-466f-ac19-edb2bc2ceaf1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
ea53d1ec-7868-4080-8364-2ca69227cc1d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
f3e2b1a3-4f3f-41eb-bb2c-a3ad182d847b | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
f67f8181-c62e-4d90-89b3-65fd89d4c45e | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
f9bff972-e071-44b8-b006-3aa7695e8c1d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
fc186ee5-1475-4748-ba65-5b858cce0ce2 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
fea01f17-a03d-4af4-a45b-7a4782fb1f10 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
03dcfee3-d802-40a0-be05-f7dd7c71178f | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
07a2375d-9dcb-40e8-a10b-31e70a435d1c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
1806df61-b3f3-4666-944e-b641ca59790a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
1f5e92bb-7e8c-4628-93f0-4678b01822fb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
1fb22a72-3638-412d-8b1d-7e382dbe9a28 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
20d7ad77-0388-405d-8b5a-2047e3da4021 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
24412a7b-5a12-446f-8848-e27ea68f9484 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
27e7ed88-e29b-442d-9c11-4cddbcb21692 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
28f857f3-5c8a-4801-b154-fa774e3decf5 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
29eed51a-ba84-4ddb-8289-0b29278dff0b | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
30a775ed-e367-48a6-ab67-49d03fe62ae9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
320528c9-fca6-40e5-a382-e4b1b72a9153 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | 2022-03-02 | 2027-03-01 |  | Required to Re-inspect a subset of assets
367b47f6-7fa2-41b0-8c16-1a805ff73e4e | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
3ac8d79d-460b-4338-baa5-b737b9046982 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
3e2d2782-924e-4205-b96b-7fb6ba72ea27 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
41be9fe7-698c-4043-8c26-d6ef61797c6a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
4273e01d-0147-43fe-9b71-7bacce3b1b42 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
443f664b-94f3-4d72-a10e-3a2e41625171 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
46e1c6a3-9e32-4d82-bf99-baf27da9ddb4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
4fcfe9b5-fe35-4105-bc41-d71a14ce63aa | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
53b8cadc-146d-402b-935f-e9e4be740132 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
58fdb083-cfe6-4863-a8e0-88360b46afc0 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
5fa4c865-7aaa-4b4f-b09c-20ca4631ce09 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
67b63552-7993-482a-9bc1-9073f7e725cb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
69ba84c3-d0c8-4e7b-a128-9aa06fb1f2b6 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
71e63628-3826-4a58-ba05-33ca9f62e68c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
73142592-8a24-48f4-8b63-05a188786539 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7357b60f-422e-4073-986c-0c2dc80001e5 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7bbeda37-855e-4278-a5f7-15d0f8e2ff1b | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7cc032f3-dfd4-4616-ba8e-78652c921b5c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7eb651e8-6f7d-4e6a-abfa-1348b20eae85 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
827da7d2-0924-4539-9b8e-31e444c917ca | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
837080ef-05b3-4ad7-a623-e84c4ceee013 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
83add555-73b2-4af8-b989-23ad42284190 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
86f08ca7-abe7-44e0-a32d-dea0992f7b33 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
92a0b3d8-e180-4d0b-9528-42d1e72823cb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
944d05ba-9b7d-4e5c-9090-991101a3371c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
95463f9c-29a2-4ee6-9c7d-37f6e02ea9ed | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
9a6b2120-3d3f-4281-aa73-9881e38340e9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
9d2004b4-40db-4e87-822a-a2851681477a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
a3b597eb-ecbd-4f8f-94b0-a4b8df3fecdf | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
a46c2b89-7ea9-4b63-9794-fa3ffab9f0f0 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
a7552d2f-c6c4-47a3-82be-fa035cc237c4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
b13ab5fa-4cbb-4511-8bdb-6dc7afe376fe | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
b1cdd578-fb2d-4458-9b88-2349c7ed84e7 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
b2ae5313-f964-4b18-bef5-90fac7ec4c62 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
bb8c8909-dc08-4575-8623-52e0e6f80a15 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
bf701bbb-1174-4420-96a9-9f16db9bbc16 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
c44052bf-7b9f-493e-9f4d-b4f7d047d1fc | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
c54e1d26-1669-439a-94a3-c85444c46491 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
c77635b3-e156-48d4-9908-34bc7f1d966c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
d46e24dc-ae37-42ad-9298-c97d30e642ee | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
d5cf375d-7ca2-470d-a1ad-6c35294240e4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
dab140af-faa1-4f0c-83c8-3ef77cafb1f9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e1189a41-19f3-418f-9c86-972192cf258a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e42264e3-2e11-48c9-92b4-9a17ee70bc83 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e50d8b8c-b58e-4a77-a4dc-618468c9d4dd | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e55c30c6-d89a-48f4-b58e-81f9225c325f | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e5ef72ba-a80a-49e6-8809-5298f6f42351 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e6511318-6b17-42df-bb6c-2af709525f8a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
eccc256e-e031-4584-a793-5a2cc85592dd | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
f1cbd30d-3940-49f2-9075-ca92d646ff04 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
f8531135-6865-4a21-8838-5e5df384c415 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
06be03f7-fc00-4f37-8efb-a1030d1622a5 | Pole | 2 | Distribution | 2020-04-30 | 2021-04-30 | Level 2
0e74556c-089a-4d47-bba2-be11f351b6b0 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
13381093-4e8b-4428-87d7-f02868751e23 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
20e3a89e-fcac-406e-b0a0-daeec355ce16 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
30c90825-1c2d-4664-a008-e7a370d3e8b4 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
30dbb492-2a83-4816-be14-3e8a88609e48 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
36d7857e-bc37-48ac-bdc4-e57b16ed6922 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
430f64f7-a95e-4e5a-8aec-2352fde5a289 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
5b043478-833c-49a2-be8a-e0c76ff83b7b | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
5be6da19-ee26-4bd5-ba31-722099741d01 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
5c85ae6b-66c6-4f0c-980c-0144f7bd9244 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
67c19923-31a3-4cdc-a311-9a2b71708c74 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
6ad6aa60-8d22-4530-b319-499b4d2d77f7 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
6bf162b6-cbd1-40c0-b617-b4cda4bddf27 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
7155a2df-d460-427e-8609-99c4e0340b1c | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
91a1d565-acdd-421d-bf4d-96abb48027b0 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
a23b456a-f53d-46d6-9e66-600e6da1e621 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
a8da8dc1-bce9-41d6-9440-80d4cca5270e | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
ab516081-6c3a-4456-ab89-7faee59e4a20 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
b8f492aa-3012-4bc1-af1f-7ac38a63bd3c | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
c1136a3a-4945-4892-b3d2-0d15e5fb6b24 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
c79ef9ab-12b8-4505-b97b-d7b8e6264fcb | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
d4e7342a-ab96-4da6-b6ed-a462f7ac45d1 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
e1fcfbbf-ab62-4551-b11d-64da8c02e07f | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
034330e6-01a4-4ade-8b29-81ca2c12b8da | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
047675a4-a871-49bf-9bf5-fc37ab0f0ca9 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
0c68c2b7-45e9-4333-aa11-72e744a70032 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
143cb5b9-da5a-4e87-a81a-cbe730b6d4fa | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
147cf57c-8f56-4434-b71d-f9bb704f4172 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | 2022-03-02 | 2027-03-01 |  | Required to Re-inspect a subset of assets
16207858-1752-42da-837b-31ad7a1f2f1a | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
1d548ab6-014a-4ffb-b7ce-e383eac221e4 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
2228cfd3-67ea-4ffe-ad9e-5f3a135245b7 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
24fddb5a-a968-4fd4-b3bc-8d1ed7904623 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
285ad527-b8dc-4409-a27e-69eca8ac2226 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
2bbaa7ec-298d-442c-8c3f-5bc35c6e67d6 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
37719945-a1e5-49f7-87ca-e97b592edb57 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
3c182798-e4eb-44fa-91f1-443892bc1d1e | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
47be917b-4c54-491b-9e18-489cbe463cf8 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
4b331ad5-c147-4e64-9c00-27819a26d591 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
4ba22137-01d5-4a2b-8979-ebb21eb9c33b | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
513b111c-abdd-4e56-9431-bda8b50ed367 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
52d63da3-dd2d-428f-b1b3-a1c31d503460 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
57d32883-1cc5-479f-b42a-e3dcf3cd5f06 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
61415a59-7478-4fe2-9f3f-d1fb116fba57 | Pole | 2 | Distribution | 2020-05-01 | 2021-05-01 | Level 2 |  | 2021-09-30 | 2022-09-30 |  | Required to Re-inspect a subset of assets
687f1f59-784c-4c6b-aad2-69383d376485 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
7723a75a-a650-4e13-8be3-aebb59923399 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
7e1b6587-91ed-40ae-8493-245f60b3df1c | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
85f33013-b1d3-4803-9332-ce5dc79a9ae3 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
8680a7bc-3b07-4c69-838d-929539cc1b92 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
8e2c75f9-0cc2-4c3b-aec3-11e79c446ec0 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
90799aa6-b524-498d-a18f-795c5aa77db0 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
94005a4e-fa1e-42aa-9830-1fba54ca1a7c | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
974587bd-7b6f-4df2-99c1-a0cef4025a94 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
a0bb8a9f-32e4-493a-8c77-f19ae5978940 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
b2b80681-d4a5-4f00-87d1-0bfffac7825a | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
bbb934ec-fe27-4061-ba82-6b77deebab01 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
c165a378-e034-47c4-a56c-a8793eac1a90 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
c2666885-a343-4e7c-a36d-3e83292767b5 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
d5720fbf-c827-4d09-9abe-8ee9fcbeeaf9 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
d9f903f5-d11f-4dca-a9e0-63cb69f961fb | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
db182d75-dbba-4957-adf0-58c264fc654b | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
dfc58e31-9027-46ca-a6d0-2d8c48378d19 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
e0be06f9-e0c3-4c95-9268-cc3d71afcaf4 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
f070a96b-22a1-4b29-beb5-3b18ed3fb7cf | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
f90f1c1a-0987-4f94-98d1-bcb671d04e0c | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
f99f9a2e-8115-44d5-9ed5-d9e8dc00feb5 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
1ab641ac-174c-4edd-9ccb-23e3e8922632 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
4ea5eb9a-da6b-46c5-953c-5c49c0ac543f | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
53fd8d9e-308d-48c8-be1d-c649388d2f19 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
8b08687e-5a25-47c0-9739-cf881f303a81 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
99488eec-fbde-4a5c-bc28-a0f48dcf60ef | Pole | 0 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
aad29f10-8a17-4176-b81f-8f3132b93043 | Pole | 0 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
b6f9b765-443c-49b0-a3e9-393b024e99af | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
c5b926bf-86fe-44a2-8625-7488281a4644 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
d934a254-bca8-4aee-bb4c-769dc670e1fd | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
084175f2-7bd3-40aa-96d2-b8366849f297 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0ac8c25e-5b2d-4874-83cd-b21898375815 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0ba5aa72-29e9-4786-9d89-e3bf6d83b5f2 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0d4c92a6-fd01-435d-8809-8f09b7fb9f12 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0f76feaa-1666-42df-b7bb-d36a97fed275 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
11c3ec88-c92b-4b75-8c48-e16a5ef250de | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
1478225c-52a6-4954-87c1-e1bfb2507b9a | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
17d25510-a18d-4cd2-a779-0f43ee01bf88 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
2042c71d-3113-48b1-910d-3a5598d405f3 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
2d21897f-fcec-4149-b276-f3cb466dbb27 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3236af3e-3890-4b2b-9600-be3d5382f5a7 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
37c9345a-298b-4db9-936b-4f3678d68780 | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3a473451-21c9-4248-9874-445e3a453a20 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3dce80fd-6022-4f55-a4da-911a2b56475d | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3f9489a6-3a02-4738-9db1-fa247d4ac3fb | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
448cce3d-1853-46cf-8069-927d459198f5 | Pole | 2 | Distribution | 2020-05-04 | 2021-05-04 | Level 2
46580a1d-244b-4ee5-8c52-7aac3429ca87 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
54a954dc-4fa3-4bbc-9a0d-254206958f78 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
576ee34c-4d43-4718-b9ec-0b9a586205c8 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
58e646eb-e8a4-4c0e-8c6f-b6c31c791770 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
5dc8dcbd-7e28-47cb-a413-682c7b17d8c1 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
5dd658a5-7315-445e-8e33-a68d54a67628 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
6af804f4-52b2-41c8-987c-a6671b0c560b | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
6cb8822c-adea-4d81-aaa8-4ad0207d5e1c | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
7b8aed0e-13ef-43d9-a225-bb48e767e556 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
837204a4-0758-4fd1-85da-326293832aae | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
8f515682-dd02-4e89-bf77-494cf254e3a3 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
94cb8661-cd32-4726-a160-a3963fe2ada5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
9ebe9fb2-4c28-4c29-be37-4f6d213f1649 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a1985791-bec5-475e-ace0-f2c81d22227b | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a3693937-3182-46ec-8110-dd9917ca1cc5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a41c06be-6e87-40e1-a6eb-23e988908819 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a770bdc8-dc0f-42a5-ab6b-0b9dc3e282ae | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a7960325-9bc8-4dc9-84ba-44d10be9929f | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
b1e89fc9-719f-4b42-b1c9-9e208ea1b667 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
bae7fb8f-229e-41b3-8fc6-aa9fe3416dee | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
bb4cff05-4607-4c67-b0ff-28be0df77de7 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
c069f8a0-a04d-458f-8563-97a792681d37 | Pole | 2 | Distribution | 2020-05-04 | 2021-05-04 | Level 2
c6c2f97e-06e3-4d1b-bac0-9f3ef30d48ff | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
ca9ce774-70d4-46dd-89e2-352d84fd9c0e | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
d4641a33-7d4c-4016-be19-80a2a185d123 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
d9683e52-99cc-442b-b18e-dedba6870a25 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
e60892f0-eea6-4860-bba2-816c5df82afa | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
eb254225-642b-455c-965b-6b1b80619fd4 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
f57052c8-6f90-454c-9868-f4c49bc18d23 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
f9561d80-21bd-4e39-9ce8-9300e37035c5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
ff17b4b5-af21-4aea-88f1-59479d8b8c34 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
016f8834-03ee-4296-bd93-bab2873a2ac0 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
08b20688-f7a4-4a51-a737-20485ef672eb | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
1382cff2-6bb7-491e-9d09-a26797963d83 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | 2021-05-27 | 2026-05-26 |  | Required to Re-inspect a subset of assets
1ba0d940-bd62-472e-920b-b86b0616188c | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
27057fc5-7000-4238-a2d4-deee3a84d34b | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
34bf1fba-52ef-492a-80be-7fc17f024c97 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
428b1e74-9274-44ef-b7d0-12775d24fa8d | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
4585c037-2973-4523-8cb7-fa0223ab3c47 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
46007178-651f-4d05-bf20-03d23bf0fc74 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
463ddb6a-0edc-445d-b4c7-4f4a9085aec4 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
46fd5cd0-e01c-4422-95fa-729a9b59c745 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | 2021-05-27 | 2026-05-26 |  | Required to Re-inspect a subset of assets
4cd2fd2d-7805-4640-9f59-b3de4e2bc24a | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
4e59c8e6-ed46-45f6-ae8f-f05927fce800 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
51ec18bf-944e-4fc3-8582-b49bbfcdcc5c | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | 2021-05-27 | 2026-05-26 |  | Required to Re-inspect a subset of assets
608c69d6-a5df-426b-b1f6-08687a993aa1 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
650ad662-ef52-40b4-80c0-34220680f3e0 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
6919f6a0-3538-481e-9dfd-2950dec89825 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
69502a28-0b3c-4b77-aa16-995658698812 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
6c4ca4c1-4ba3-49a8-b9ae-4cefeecbf104 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
6eae9dde-cce3-4f19-8c5b-d070f21b9e57 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
72f0ffcc-3818-4fae-9535-bf69428a7b9b | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
81459025-1b79-476f-adc7-af20e9d8c7f9 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
82536ea8-9d81-4e03-9db3-b8f8b7071001 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
8c7b0d52-f92f-406c-ac3a-2fc49d3b9a29 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
a11ff7ab-6c0c-4b67-9dc7-1832bd85d5b8 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
a508d8f5-360f-4f3f-88ee-0b508571a16e | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
b3bf3a06-0d89-4249-b068-1245be3570c3 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
b4175150-c61a-4755-8afe-19749612f1b6 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
be273a27-9dc7-49aa-aad0-8e2d917f8d3d | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
d0a15478-7d42-4960-9218-8238351d78fb | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
d5eded60-f9c3-4f14-b8ef-08a5fc5ad9cd | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
e0db280b-4ef0-446e-8968-717043b763a5 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
e6483c6a-5b35-4605-83cb-047fa5b5dd2d | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
ede2f44a-5ef7-4a40-8348-2aec92768940 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
f12288d0-9c06-44ac-8566-382e79697be0 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
1064b926-749a-4270-be28-9f405174c5d8 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
13adcb50-6609-4fc7-a7fe-023be363cee4 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
17728c14-68ab-46f6-9495-8176955dffbc | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
18b77001-1728-4d75-ba2b-c916a2f57d0c | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
1a8c4fcc-6520-4df7-9c6d-5f5eca9b4f19 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
1fe5f67a-d7cd-4576-8c80-907b24a887d2 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
235a2e58-1007-42c9-ac95-a928de663551 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
2418d01c-9971-40dd-b125-c30a27636ba5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
2bc226b6-c2d5-49ee-92cc-13962a72823b | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
2fac3e3e-54b6-4494-94e6-dc128cfe3764 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
4b0b0d75-3f5d-4893-81d7-65b13c29a2ea | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
4e5d0946-f2e4-44da-ad33-60dace530731 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
53d02af3-4e02-4842-91dc-9305a04d10e5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
596d24a2-5432-4420-804b-8c57614f391a | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
5ade0272-f64b-47c5-b636-1fa7babdf9bb | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
65456cc0-25b1-4dab-9ee1-298f7c3c12bd | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
6882385d-2fe0-4ad7-a688-c2e715474b76 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
6efa98bd-2c4d-46e9-bb45-897e5fd2772e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
74588346-5a86-4929-bbba-e2b44332404a | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
7bd01956-df26-458d-b9a3-278c53710e97 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
7f7f356f-1707-4f47-bfc6-749ab2a3c90f | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
820e8a3c-6065-48e7-a24b-5c4ad6a3c509 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
874bfd68-e89f-4621-a4ac-d8d59b2200f8 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
94606a0d-c0db-48a7-96db-7bbebc17da4e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
9727fe7d-767b-4390-a517-c0c5d42d918c | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
a0648ac7-a2e2-4823-995a-0c8ab148da39 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
a2d850d9-f0fd-4552-936b-94f695fe6863 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
af71dd16-627c-4ef3-a0b3-9823cc80c60d | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
b38179b8-df64-45fc-b9af-4cb462bbb102 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
b582f4f4-4876-4c91-9903-d2c609a393b6 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
b64138d5-b8b9-4075-9d3f-301cc58cd6e6 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
b64ad184-956c-4f59-a1e6-cc9ad199f1f7 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
b7d572c3-f401-4c97-b557-e4960e9f13c7 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
c16bdf71-9f8a-46c5-85fe-b7950642b52a | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
c2eac45c-c931-4c45-81f2-803d7bc6c51d | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
cb721eb4-3536-4225-a2a7-c99249a8a59e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
d988cf77-27da-49f0-b8f3-acaa4ab7f216 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
e0f3279e-e97d-4e6a-9bf9-d79700f70a45 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
e97989c3-0227-425b-b15d-4280c14cb383 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
e9b6ec95-b731-479c-897a-f7d556dd0740 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
ed3eb46d-2e0a-46ea-89ea-f0d599033206 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
eea829a2-e560-48c4-8d8b-32f40074ac26 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
f614e3d2-f5a2-45e7-9d2b-e3c6db5d6e94 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
f6cb001a-9f44-424f-97ca-3827f23aa9de | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
f9c7b66b-de01-470b-a6b0-539f32715790 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
fb899cf2-302a-4494-90aa-492ce0cc10c5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
fe3576e4-0013-4cc1-ac7f-382ffa9892b6 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
087a548c-b2ca-4812-996c-539d0ac2951f | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
0a472885-8ce2-4131-92ed-98c0b602e0e7 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
0b593546-fb59-452b-8f51-bda6849fa20b | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
0f734ede-ab67-4b08-ac4b-238ea8069931 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
12b3159a-273a-43a8-bb97-fac8654984a7 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
29ae7109-7c6c-4ab1-876f-7873be1d9ee9 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
3c7a1e4f-e996-47e0-8dc5-4cab9bfda021 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
43b2ff6f-676f-4578-9be1-a4784f1e40b9 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
4878e6c2-ac6b-4129-a566-11ca4cd42eff | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
4cf81b5d-9aa1-4a6f-9e7f-1f3635736e13 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
555a190c-bd42-4df8-9165-cd361688883f | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
5c216429-df09-4067-9dd8-3ecfbc8a321d | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
5fade760-903f-4870-b54a-460a26bf56a7 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
62d9f053-507e-4d52-8f8d-296812263303 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
67773787-c127-40e1-95f7-ff2a3963740c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
6b4ac851-152a-4cd7-b22e-bdeb42d6910c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
77a6c29a-7286-4357-88c5-e88abb2fffdb | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
7fe7c6ff-a2bb-4618-b592-1a04ab96f255 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
84c1808f-ed0a-4640-b834-0fd864939323 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
8b87102c-b3fb-42e3-9e64-e8eb3f7cbd98 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
8c8a46c1-4859-47b5-89e8-3168a506c806 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
985d56a2-9c1e-4f7e-8da6-2a24091dedc8 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
99c63bba-56e9-4a1c-9a93-311f7a2be91d | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
9a5a27bb-174f-479d-ab21-c2071e6ab5f3 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
a1d31faf-ccfb-4ab6-b7b7-a6e3659bb1bc | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
a8f75d36-2c12-4c56-93d7-d7e26fb9c30e | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
acdaa6df-cd0a-446d-9025-0c999c961c0d | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
ad432d86-1a01-48aa-9f8e-3ed66ed6f288 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
adcd22a3-3967-4abe-9342-fd24d10b4b5c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b2c785e2-a23c-41a9-830d-fee4069d5e90 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b676793a-7515-465e-8bc1-88ff76a3773a | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b94a7a26-6cdd-4cd7-97af-900b7adcaffa | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
bc2de546-577d-4c70-bcbd-3982b2ae1516 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
bc6a8e15-dfcc-43ce-b08a-b48e58c5b56a | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
bc768dc7-bbf2-4ca1-9233-d56341a7cd7f | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
be037e3a-a305-4193-ab92-b35574ffef49 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
be231c80-8b59-47fc-a53f-1f98fee837db | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
c71fa9af-fd28-49b7-8daa-c5b3185298c6 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
cc49f07d-2d41-4da9-ad81-e654ff424a96 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
d28b39ac-900f-42ba-b1ea-60c1fe512d62 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
d3f9e964-f3a2-47ba-b8d1-8617b4394edc | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
d753be93-1ec5-44b8-b922-75e5c7dbe0b6 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
db01bd40-1567-4592-8c13-37a694287334 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
dba44d10-376d-4f82-a49d-c1bdaea8caf5 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
e238a508-8b01-4e23-9bf9-71d315ebf9f2 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
e359ac23-0467-452b-931a-34255c5fdd06 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
e76b04a0-1549-4437-a020-cac09ec3f737 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
ed23497d-b31e-4081-a1e5-23088818abce | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
efa65308-da7d-46db-86d1-e86745ec4014 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
f2aa4ac3-5776-4e77-83d7-1c60a9c655b9 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
f3d542ff-86e3-46b3-9317-60df2c91ccdd | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
f6f5f18c-4a61-4141-870b-38e2e95651d6 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
fd267ec2-1b23-4346-b8a5-9d866f5be262 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
049709fb-e9c7-4064-8c73-ffb6b0c10fcb | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
1b185877-7b36-4480-bc86-c5c202de6492 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
1b356147-041a-4f4c-8746-d356fe3f94bd | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
25ae29be-4599-42e4-8d3e-5068934c3a24 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
3103430c-6289-47f9-9763-f83bbd411174 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
33559564-5257-4c65-bc57-d6b2e7cd39ce | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
494b5a07-b74d-4cb9-97fd-d9f6a8e6074d | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
51c0f373-154d-4214-9405-a977744dbb0f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
63ae0f58-192a-4e45-beac-a4c45b78f7ca | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
6d5824ba-7dd7-4361-b612-39ecf4c43161 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
743266c2-5a3e-43b6-9eaa-3a7e2d84499a | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
7b7ad3bc-6ee8-4da3-8ba1-39bcaee2ff33 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
854a7c06-8c13-4385-bab0-1dc63c5de6f4 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
8696c674-f9d8-421b-8a2d-5532d8e1fefa | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
86e0983a-7b3a-4457-a319-a061265aae09 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
86fb0fa0-ced6-4c72-99d7-af0e126b4bec | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
8b861111-56a7-4d6f-af31-978d2a1a8be2 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
8c045216-06d7-4459-9b52-cc43d3176fc9 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
924873f7-8324-4c88-87d0-56ae1b541427 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
93e262df-8418-460e-a1f5-6c19ea22a16b | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
974f76a9-a150-495f-b6b7-a5563defb33e | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
9ce10e49-3c4b-4e7c-8f46-4df48a42d12f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
a3941a41-fcd9-4bc5-9366-143afd5a4766 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
a5bdce12-8234-4147-aa95-76aff7277f20 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
ab5603f9-761a-46d9-9507-6f0026706245 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
b28ef08d-df94-4e58-b883-314161d25093 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
b82124c1-708a-4f0a-bb54-392ece6e05ad | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
b8585375-ab22-48cf-aa87-aaeab22f316f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
bdf9e004-1570-4586-9707-e5b4b61449aa | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
c3c94409-f784-410a-9679-b141c109d0ae | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
c90447eb-aa47-4c74-9fc0-66bd65536d3c | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
caa57011-9cf4-4fe6-9971-a5d394aa7353 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
cab9b05e-dc1d-4803-9b71-dccfb5f12d23 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
cd115a8a-b0af-48de-a7ee-55af3c97f726 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
ce8f30f3-6da7-4ce4-b5b6-cb174cab6f5f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
d886245f-8351-4ec9-ba7b-0a41e5cb6e4e | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | 2022-03-01 | 2027-02-28 |  | Required to Re-inspect a subset of assets
d8fb5c1a-36b4-45f0-8fee-7b23c51089f7 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
e439c010-30d2-4f2c-9e2c-df2c4bccf5d6 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
eeb87e1a-a320-4c65-9b95-42224a8c1486 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
f9b1c9c3-bb3b-486f-96f4-19b930b9e6a0 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
fb4a757e-148f-4087-8683-6b0a354f583c | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
9b064557-13ca-4b78-964c-fc661059d18d | Pole | 0 | Distribution | 2020-05-09 | 2025-05-08 | Level 3
b5cab04c-9fd3-4a11-8662-3a8de9c45116 | Pole | 0 | Distribution | 2020-05-09 | 2025-05-08 | Level 3
02372a50-674f-44d2-9e99-37fff71ebb91 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
05ec52b4-c01f-461f-b8a7-9b267707b0ed | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
21a8bde7-97c9-41f3-aff2-78c6a0ed0431 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
5845bf12-b2f5-49a8-9991-b61e94c174ad | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
69e3eadc-54cf-4204-b5cd-28aef412dde8 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
7f961c1a-6c7c-4797-9760-4dc9a329062c | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
8aff4f5f-b01a-4796-8569-a0615ed0e3d7 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
a8a670f6-3efb-47a8-afb8-07313639c21e | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
cb8665d2-7ee5-4682-bf3b-15a5c505b0cc | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
d3fa00ee-bb8d-4159-bce4-c69e392a3504 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
0992cabc-7a62-4250-a4ef-04dbfb8d483a | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
0e13fb79-1f4a-42cc-a4f2-f95ff17d35b6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
1030a471-f0ea-41f2-b297-df47aeaf84c9 | Pole | 0 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
1b6164e0-69ec-4d84-8a13-49f4469860d7 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
1e442a4c-6904-47b8-adf6-0df1ad10b047 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
2d7bffda-1adb-4972-9742-569fc916e561 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
379b5736-0e77-4891-9545-3cc3a20739a2 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
3b4cfe3b-401a-4956-b4ab-9b80bcf1c13e | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
3cfd170a-4c79-4154-af57-a9d818e9eebb | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
4a358beb-6d90-4744-9e31-a1b6a212ecea | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
4fd236c0-7fe1-4b44-9d65-344d7c936ba6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
64936060-0067-482a-822b-2d137dcb1867 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
73849316-6ee3-49ff-a442-56599d17825c | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
753180d6-ec1f-4684-a1af-50050a72cb3d | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
77161aa9-b9c7-4a74-8dfe-7809c72fd552 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
7dc9546e-d28b-4466-a1e2-675f54cc2483 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
826500b2-8f56-4c60-a10a-13498b8ebabb | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8bac5bc3-a5ac-4c48-af13-76fa21690590 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8d80af29-cee7-42db-b2ed-17324163acf6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8ed2adb7-dfb9-4581-8d9a-012d27f92d36 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8f82629c-9eaf-4e4d-a648-31e6ef66e984 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
91d48b43-a333-435f-b2f3-a99d328df695 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
a71864ea-0516-44f6-b339-6f40e46af0ea | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
aa1af4eb-7b46-4d45-92a1-2693d1bbe70b | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
afa326d3-bc78-48ed-8322-394624533157 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
b326dc47-51ae-4702-95e8-84a9f1607487 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
bc290678-eed0-4999-ac82-496fd9598186 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
c7c316c7-69a0-44c9-a178-34d0c93ce210 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
ccc09d29-fee6-4267-bc86-cece4a79f36a | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
d56cdd82-11ee-437f-8158-c22ca24cbd91 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
e32fed23-ed08-47b2-bd4a-75d6d27c7068 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
e6cc5012-fa93-4dc8-a9b9-ef98a63d4db5 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
ec437e35-96ab-43b0-85ab-7a8d139be597 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
fd5d8217-62d8-452c-963d-8dc312761640 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
04ec7d19-0ad4-441b-84ba-190c4c7faefe | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
04ec83aa-2194-457b-bcc0-14614f6dac2a | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
1ee3e300-64fc-4cd1-b456-cb3c0ae67cde | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
2797543e-f9e1-4cfc-8b11-8cc8ab73fd56 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
326caf54-c51c-4d5a-bb0c-46bd95233ff2 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
32b1bfd8-4d3b-43c8-a65a-baed2746be8d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
354b21eb-6cc7-4319-b900-271bbd3866f8 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
3d23236f-de9d-48e0-90be-22227b8b5c34 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
42085b67-ac70-48c4-a2c6-3674cd057f4d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
462d1add-2cfb-4921-aa82-cb92b5cae146 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
58366037-dd05-4d4c-92d3-198b62bece27 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
5a95ecec-6dfb-4614-85e1-4e9951d1f204 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
5cd839ad-1438-4d0f-8b92-e3e2bb13c97b | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
717b53af-39a5-4381-b375-522f8d77b247 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
7230e860-8934-4cc9-b4b1-f96301b3cbed | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
73a15269-816f-4f55-bf47-6e928af39348 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
751614a4-f25e-47b3-8891-3c0d20e6afe6 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
7869b44d-4be5-4876-b651-4bb059d61a39 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
78a5e659-62eb-4d2c-8c0b-625169730523 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
7cb31505-1234-453f-b761-1ba8c245b067 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
91f98341-06ea-437b-94e3-6389c5b82a2d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
94eb235b-9bd1-4dec-80fb-cfbeba6d6e2e | Pole | 2 | Distribution | 2020-05-13 | 2021-05-13 | Level 2
9be6cfb4-6006-4c13-99c5-971d5f1c31e2 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
9ca3a0ff-6b2d-4cbd-83dd-c7fdad2b6bd6 | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
a5c833b2-094d-4951-a7fe-e4ec3b9e005d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
a61c9711-dd4e-48cb-92f3-4fbae07448ff | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
b49fc804-557e-41c2-9ec2-03a0204a3e6b | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
b91850f9-27f5-4632-b7de-7a4bc61adb7d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | 2021-07-18 | 2026-07-17 |  | Required to Re-inspect a subset of assets
bcfd018a-bf84-4ed6-983b-968680de54de | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
e0eed9ca-a8e0-413b-97e5-dca44df97395 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
f209ccbf-5469-483b-9a5e-3c813f456fbc | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
05b6dca4-4d19-46c6-8462-bc0fdecc75d1 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
12cfdf20-60d6-408e-8ba9-910d6601612e | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
1b1a4e68-8650-4314-9b30-d2810dbbae26 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 2021-05-28 | 2026-05-27 |  | Required to Re-inspect a subset of assets
1f23bf72-744c-40e8-a47f-d60ff72e09ad | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
3c682f74-f0dd-45d3-ab10-d4bef9d79364 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
5f3a8a65-21e8-4f9f-b1ee-96b36d69e761 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
625095f5-d6cb-4fd4-8f8f-f63192a5d05f | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
7b4e004e-5e0e-4cee-a456-09ab935df573 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
8c584c16-9bc0-4f23-89d2-4a4eda5ef036 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
92827999-fa1f-4e4c-93d2-b93e5453f065 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
a7b9ac68-544e-49f3-8ea2-a6f522cf73b6 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 2021-05-28 | 2026-05-27 |  | Required to Re-inspect a subset of assets
b1b1ded1-02a6-4af2-984b-68c7627e15a7 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
c7a86051-62f5-47b9-bbde-77adf7c75979 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
d46971f5-bd54-4962-bedd-af1b7e5cdfa4 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
e13149d4-fde4-4285-a12b-dfca8e9e9096 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 2021-05-28 | 2026-05-27 |  | Required to Re-inspect a subset of assets
06e9d14b-d287-4818-b8d3-3397c8e89060 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
8f3369c2-dba0-44b0-afe3-7a77978017b7 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
91549a1d-4b9f-485f-9953-ddfddcbe51ad | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
ad010ba3-457c-4624-a5a3-b173a5995b91 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
d80e0c4b-16c5-4d4b-9fdf-6db86c2d1426 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
ec18621e-b025-4de9-af07-db20384faab7 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | 2021-07-18 | 2026-07-17 |  | Required to Re-inspect a subset of assets
444c6720-5675-4c55-b791-401109d52add | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
692dd435-25cc-4076-b5e5-4a927b917dff | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
8a75bdaf-ca8a-4f49-9fc6-5dc687f0d0e6 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
aeb55969-9193-4974-a095-a94c53e77055 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
b776650a-75a5-43eb-8b8c-13c5ebea3559 | Pole | 0 | Distribution | 2020-05-16 | 2021-05-16 | Level 2
b9b04197-e504-4279-8841-2b744d655e0d | Pole | 0 | Distribution | 2020-05-16 | 2021-05-16 | Level 2
e3a70d1f-79be-4932-a296-a55f84df0ed3 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
eb175d0a-80d9-48bf-a4c0-6a515e2f7e61 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
40d1a9b7-1c47-4695-ae96-653b6eafdde1 | Pole | 2 | Distribution | 2020-05-18 | 2021-05-18 | Level 2
452d3435-5fd0-43f6-9bab-dd0972a41569 | Pole | 0 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
53a03697-8ccd-4acc-aca5-ddbb1ab86fc2 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
5f1d6604-7895-434c-8d0b-5f750f554b44 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
6b8f67ff-67ff-4dbf-b318-3b5688c09ea6 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
7bf63fb7-fa7c-483a-903c-71d3ec2561ba | Pole | 2 | Distribution | 2020-05-18 | 2021-05-18 | Level 2
7da46341-5f73-45cb-acc6-1a6c0435bb9b | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
8354e197-8683-48b2-b1ca-30d0da015944 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
89fa3ebf-b907-4136-8ebb-eb32238cb44a | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
8fba3f55-a097-4e38-a568-12695c576fe7 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
b0f2e7b0-d562-4748-a999-eb882909c3cb | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
caa5dbff-bb0b-46c0-aee0-7874ce150542 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
e012bca1-98dd-4843-b9c6-248c74cdcfed | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
e12b4bc6-6979-4e92-8358-e528f5c7afc4 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
e3260076-6771-4e2a-8db9-861410264652 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
ed501187-5bc2-48ed-8531-735ffaf9158d | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
fb4048fc-2030-47e2-b626-8570022422de | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
fb639ec5-b61f-44e2-bdba-796b5490571b | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
2077998d-ef0a-4297-8507-8e309988f4f9 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
24219567-b721-4569-9039-9d8da67cdb26 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
2605b400-a971-44d6-97d2-a2ca89d43692 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
44a5ef5a-0990-4c87-8642-ac9f22725b38 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
490fd03f-77c9-4638-9934-e4b730186781 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
528e9bec-0021-4f48-babe-a29ab6077c3a | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
560f12e2-fa49-4cac-96bf-f27c1762b310 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
56d519fc-ae75-4b1c-a0cb-f1090bff662e | Pole | 0 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
5f8d96f8-5dde-4237-822c-ddfa88d1853f | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
64bc557d-69ee-411d-80b9-965c38e24d50 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
6cd22fb0-050b-4df8-ac7f-d45c3520d2bb | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
891678a7-8fce-4958-b836-933d5d8cfc67 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
8b60f815-127a-4b58-8173-31d5f69776ef | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
92303dab-032d-492d-a17c-65cb6a12ed5f | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
9480f630-f5fd-4e8f-80b9-fa41724cb2af | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
b05a5515-a2e6-4cf2-bbe3-2d377331ee8a | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
b46dba50-17d6-4dee-980c-dd9a641e14b5 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
fe96cde6-e725-465f-964c-1a786efce1ed | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
0c3f0dd3-d915-4711-98f5-9aa2f85d9a5e | Pole | 0 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
103a2c4a-aee1-4426-ab73-09a71bca340d | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
11b7d65d-18a2-4f0d-a52d-461f57aa1bd9 | Pole | 2 | Distribution | 2020-05-20 | 2021-05-20 | Level 2
184c655a-92c8-4dc8-b226-312c257e04ed | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
1cd56026-cf6f-4635-8c06-619ba0a8bf1e | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
2ad3184f-0463-41f0-867f-3c35d4554df7 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
356d44fa-917c-457d-a750-8a8b262cb524 | Pole | 2 | Distribution | 2020-05-20 | 2021-05-20 | Level 2
3cce51f8-c166-4b73-9241-5ad47aeff75a | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
449bb1e0-dcc4-4272-97b0-d30af4358381 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
525b710f-baea-474b-8934-1985c33f23d0 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
53740f0d-89b9-4dd6-ae23-992515a555c0 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
5f3bf0ae-b733-4c75-92b8-893f46c87422 | Pole | 2 | Distribution | 2020-05-20 | 2021-05-20 | Level 2
6623bc81-7e48-44ed-8491-57a5da03f14a | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
732b30cf-9323-4987-a1fd-018c45039dd9 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
afcd25ed-80f3-4710-9d92-a76f02827438 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
ca71e25d-7d1b-418c-a477-bd74289a955c | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
d16b9235-9ae0-464e-b612-347d8523446f | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
d23f063a-e12b-4380-983b-c145bdda3649 | Pole | 2 | Distribution | 2020-05-20 | 2021-05-20 | Level 2
d398af7e-ecfb-4696-b860-fe7984364c7c | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
d3f5059f-cae7-4d78-b636-7678457cb825 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
d7c3ff93-6fc9-4627-9bff-10a3b5f86ca5 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
e09cc3cd-02f6-4596-b535-28b222f50d30 | Pole | 0 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
e6545e42-4c3e-460f-a0ec-9f8dac1385e7 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
f48894b3-a87b-440c-82f7-6f5cf21f06b2 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
0632a920-2a62-40ae-aa85-15ec85366e91 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
0c24aeff-585d-4375-8681-774c9aa2bddc | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
25eb587d-aef6-46de-90ec-bc3b6d77561f | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
2689f454-78f6-4081-93ff-3484f3fb6734 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
26fb4f58-2bc3-4f0e-b1fb-c5df65973f37 | Pole | 2 | Distribution | 2020-05-21 | 2021-05-21 | Level 2
3e557c0a-350e-46f6-8bef-bd2bcf38f977 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
3f7927d0-9219-4bbf-9aa2-f6b6fbd01bcb | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
405c8c41-a320-490f-9005-54f2ce1c3703 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
6c4fc33d-43eb-459d-8745-433d7e9736ea | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
807d6421-8d5a-4a74-963f-5617adc14843 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
85f83f5e-333b-4872-a9f4-ef08146944b0 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
89731e94-3ccb-4444-8977-8a58f9972d82 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
8b6c4337-b05d-42e9-84d6-eb01d86290fd | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
93a87237-4adb-4950-b813-ce78af6c3b0e | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
9e72b6f5-6bb3-42f1-91b9-7ab969be613d | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
a06f65a6-61a0-4f81-bc4a-9b8d9f68b552 | Pole | 2 | Distribution | 2020-05-21 | 2021-05-21 | Level 2
a157516b-2448-4e33-a311-25461c432b68 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
adfc56f5-dc1e-440e-a912-403ab1a41044 | Pole | 2 | Distribution | 2020-05-21 | 2021-05-21 | Level 2
c25ff366-77f7-4542-8447-43d911bcbf14 | Pole | 2 | Distribution | 2020-05-21 | 2021-05-21 | Level 2
c80da304-2e3a-4222-8362-7ead710c8a57 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
cac24de9-4b75-43d5-8d7f-c723e2ccc2e1 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
cce1ca62-c8a7-4fdb-b6cd-5828a46916ac | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
ce42fda2-e39f-43b8-ad09-b7da29f3b2f0 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
da1f6bf9-35ca-4768-bf5c-4850b7495668 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
eb4e1951-4361-47fb-b521-d3f33255ed47 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
f737b8b3-7a66-41af-a337-a88449691132 | Pole | 2 | Distribution | 2020-05-21 | 2021-05-21 | Level 2
042ab82f-0c8d-489b-a416-94c06e104e4b | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
0575f101-4702-4ca8-9bfd-27590b7be815 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
12a9421f-0754-4f9d-95c6-3532d97a8e1a | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
1cceee29-6fae-41a9-b64a-a4edaa5a4a59 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
227572b7-f111-42a7-83e6-19a059229dc7 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
3cf44692-62de-4a0b-bb8a-6e27d4f83e6e | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
84322372-bb4c-4a89-b66c-df6c180fa8bf | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
8863c212-da34-4eee-a1d1-2bf7ae2c1d60 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
c02852c9-0704-4665-94ed-3ab62e39d823 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
11580ae0-cb40-4182-a21e-e5ec4fe34a0e | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
4896c309-9b2e-469a-93d1-5b217adec5d2 | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
49d54eaa-837e-481e-bf5e-d27b94ef4dff | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
4b10ec1b-3951-4404-a016-8aa5092b7c1f | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
639d7211-e341-4be8-97df-820cc41c815c | Pole | 0 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
9f2e4742-b754-482d-9972-272df9affd73 | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
a88c8d31-ed45-4fb7-ab49-c528605d2443 | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
b9291bd1-8bbe-436b-a59c-429b62418cb0 | Pole | 2 | Distribution | 2020-05-23 | 2021-05-23 | Level 2
c2d81c65-4484-4227-b2a9-6d4431dd3f54 | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
cd3500f4-73d9-46a4-9aa2-040157984bc0 | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
d654289e-3fe4-46ce-9c5f-52066f5f0ce8 | Pole | 2 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
030bfdad-0d50-4d55-be6b-a6f334e94667 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
096fe5c1-f086-49c7-b8da-955b0c02ee5b | Pole | 2 | Distribution | 2020-05-26 | 2021-05-26 | Level 2
15b027a4-45d1-48fa-a6f7-ee9afae5fe13 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
22d87353-89d0-40aa-87a2-209c6e49f722 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
2d0cfe50-0752-4b49-a30b-a1199d014453 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
2f994569-5e4a-4386-8b74-966e3441d997 | Pole | 2 | Distribution | 2020-05-26 | 2021-05-26 | Level 2
3119bf3e-beb7-4138-95f2-9de93ce61d70 | Pole | 2 | Distribution | 2020-05-26 | 2021-05-26 | Level 2
3f86ffb7-12d3-4551-b5e1-e24db4b930c0 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
3fb5d623-1e1c-4717-8fa7-72dca553dae2 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
43934c93-b6da-4597-8e45-a8f7915c3cdf | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
56019431-6ed3-487d-8338-e116d210dbd2 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
58b0355e-0c9c-46a7-a0bd-e9275f924c24 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
743c8247-e057-4df7-b952-21d6732f0b40 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
79c43639-b5b7-43ea-a622-ad6ec1155609 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
7d69b8a9-2c7a-47eb-aab8-3da6c2a5d175 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
8509e229-981f-4b69-86f6-cf19b8bedcc8 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
8619fd70-b12c-41ef-8b54-7dcf5c4788c9 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
8de069b8-11f3-4010-81f9-5d5f7c68ac76 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
8ee9b02e-7d14-4992-9708-1dd748ddb05d | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
959bc14d-9d18-40d9-b530-7fea3b3dae7e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
95bac7a8-6efb-4be0-bf58-9e51d85d79ad | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
a51d1920-1706-4103-b220-fff42644f53c | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
aa2afc70-11b3-4453-a8ba-c475c13f3373 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
aaf293f6-f244-4e31-b52e-b5820a9527b2 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
ae4833bf-1fda-4e03-8994-6900c6f63ad6 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
ae77c100-a665-4699-82f4-b85bc94ee86e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
b445c7a9-27df-44f3-904a-da661b95d27e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
b7efc259-ca0c-4158-8d1d-19e19039dfbe | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
bf6fa54a-f59d-4cf0-8da1-8d7988b0e429 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
bf9d2f32-faab-43b3-84a2-b18dbb39e559 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
bfcdc883-a456-40da-bb63-bd1e9d510d9f | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
c05e472b-bb27-40c6-83d5-4e9e9ebe8938 | Pole | 2 | Distribution | 2020-05-26 | 2021-05-26 | Level 2
c374e464-70a4-4a0d-a325-d0bc55efab34 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
cbca5b3a-458c-4101-99b8-524b13c48d8b | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
d5971376-5bdf-4766-ba58-2a2e23e648c5 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
d771a840-433e-4553-90e5-f3d3239cdf4b | Pole | 2 | Distribution | 2020-05-26 | 2021-05-26 | Level 2
d9656d1c-f0d1-4115-a01a-b249ab231187 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
df2766f2-786b-4a40-a8b9-3fa5ab5b73e6 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
e2625e98-ad3b-4ba3-a1e2-85ed0a6db25c | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
e7856048-dfee-476e-bc51-87785f15041c | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
ec1fb059-cd11-4d13-84bc-31a81ee2ddb6 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
f20ae222-1d51-481c-a752-8ca01c452f23 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
f45f5cde-ec6e-475e-b0b0-7b7e550c8551 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
018e4b0f-ca00-4e01-a19e-e7775d5a400d | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
0d240c27-4e08-442c-9ddf-74bcbf582ff7 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
0da8d208-acf7-4b4c-bc30-263e5c53ab80 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
0dbdc91b-9683-49fb-acec-ab34daee8c16 | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
0fbf518d-e1cc-4d8f-b1d2-535960d40d3a | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
13059a39-a6e8-4090-8e3a-1d1f8f576a48 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
13dfe693-2fb9-4182-bbdd-e3afe8cc6e1a | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
214831a9-4aba-4426-b220-f3b820217598 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
21b1f616-4d28-4c2d-b874-26e235b3fdc5 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
29810324-acc4-45f7-91dd-d3cecc49279c | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
3a8a957a-b137-4391-a23a-21210ff1ea9e | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
3c90a2f1-1308-49b5-8f1b-428362f90e7d | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
4106e4ac-ff5b-456d-b75d-73e770e2180c | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
4d50b8e6-6a30-4b2c-85c6-7cd07655cb87 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
5db4f4b7-e454-40fc-ba11-227f09e3a1ec | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
5de4086e-6c38-437c-b65b-91a6bdbdba37 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
5f04fcb3-3a94-4b29-b845-7bae3def21e9 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
60c3fe70-ddcc-49a7-a4b4-c5982109932f | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
65f98f9a-d14f-4482-8db9-bee65028fe6d | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
6630beee-d84d-46ec-832e-d12eb6403efd | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
665d8460-9e08-4b16-8562-66f3cd871077 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
6ff2debe-4365-4913-b15d-b63f5e6797ca | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
74c36a7f-b5c8-4e4d-8ca1-16a5f5bd29dc | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
77e1e2db-23fe-4104-809f-0849d7aaef1e | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
784cee99-1e90-4161-94d0-e2550919cd1d | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
7dd1aee8-c613-4c56-8de8-895fcfcb4aa9 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
8080089c-e01f-4828-b742-6070831a2e41 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
80c21f99-d4ff-4301-b9bb-69b8b7163da5 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
82b2e567-7bf4-4565-b4e8-226ca959a8f5 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
850b7afa-9277-475f-a899-7aa9938481ed | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
85c8bdce-6f04-41e0-ae6f-e4a5772e71c3 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
88141770-6c80-42c4-96d8-281974bef033 | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
8920b6fb-0216-4cf5-990c-fdadc8a37950 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
8d2d86b3-ef49-4e9c-a762-b433a843cf81 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
8ffbaac3-ce10-4e75-a300-9940e0c4f2ac | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
91a28a7c-fe2d-4986-ab86-f27417a7a491 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
987dd7ed-9392-4357-a439-da547801dacf | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
9b911c71-95b7-4d18-8dc8-898ef9a00069 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
9c8cd574-58af-440b-bec1-9ff58a1f9d98 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
a060a722-0fa2-4b3d-89fb-423393f3d5a4 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
a557eb2f-2b17-484a-a235-cbba6576dbe2 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
a6b9607d-2138-4d2c-81b3-f460bd0ba83a | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
afad2a10-97d1-4ea5-98df-244f981f2e81 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
b2104f7f-a06a-4312-8773-3c1d6e7a2689 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
b5140f8e-0469-4531-9620-4fb11c8149e4 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
c2abd9d0-48cc-4044-840b-0e2a7cc468b0 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
ca543bf9-0a6f-46c2-8e4f-e97cc71113d2 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
ce39f80b-c4f1-4f47-9e07-25c974f23d5b | Pole | 0 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
cf98855d-1521-4744-b3eb-c6d3144508f4 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
d1362e5f-f700-4fcb-8614-62d0092f867a | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
d552be87-7d15-45cd-8130-677e8b0fdbf1 | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
da498df5-c6d5-4ca0-bb75-305f91177c46 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
f3a5db9f-2b6a-4da5-afc1-c38d3b2bbbaa | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
f7040ee4-65a6-4615-b3f0-0324e0a56e53 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
f96c24fa-0c62-416b-a6a7-c54eb64d6b7b | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
fc8fccd2-5e86-487a-ade1-16dd156e6ab5 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
fcf726c4-e72c-4916-abda-f56f1e3c05ac | Pole | 2 | Distribution | 2020-05-27 | 2021-05-27 | Level 2
131875ae-3128-4e84-bf4c-efdfc56713a3 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
1eb85c4a-c509-449b-bb9b-5c858dca494b | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
2316d524-7862-4524-bdaf-73e924bc2646 | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
2b7dfbea-8f22-42ad-8857-08e15d1a75b8 | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
30ebeb2f-1863-4267-8939-4f7bfe41b46b | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
37c0b2dc-545f-477b-b952-f065afefe1f5 | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
5bea67b5-ce92-4730-b823-dc1924c09fac | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
5fa80595-d6d4-48d2-9c06-e8d41b1ad2fc | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
61f6ddf2-94e6-40d1-84b4-630fc2a19a8c | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
65731c48-c096-4368-ab15-82f7a9d10b12 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
6b27f451-f0dc-4269-a840-d75e5b34b566 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
71491fe0-7d6f-4e83-8af1-d79095464810 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
73d2e087-2a03-45cc-839d-81b22bc48807 | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
742b4e58-e555-450f-848c-f855b48ae0c3 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
7cc07760-49c2-4c68-87ad-74783753b6f5 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
8847256b-025d-455f-ba07-099b871ddf47 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
8ff877dc-3153-4e5e-b860-600fd4f744cf | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
9535265a-04ca-4a09-b71c-f2a6b1ee6336 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
98bd8654-f5bb-44bd-87f7-0480159c6a29 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
9aa22f0c-03de-4aed-ab61-8d005899e06e | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
b2d97f5f-72a6-4734-ab99-9033dcf17adb | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
bf8b8222-f331-4ea8-93e6-3249da62d084 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
da3a887d-609a-4f74-9ef0-bb091646bb53 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
ddee5057-698f-42a7-8cdd-1adbdd72fa29 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
e04ad1c6-838c-4fe1-8bdf-46c81d255082 | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
e9877be7-d0ff-4236-98c2-f0c2372624a6 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
f9d78d16-bcab-48c3-8f6a-5cbb9ae8013a | Pole | 0 | Distribution | 2020-05-28 | 2021-05-28 | Level 2
fd8b8786-faf8-47f5-8792-5e667966c606 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
fe3eb3b3-be70-49ab-ab18-01f9bd8b504e | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
0612c414-af3a-4c55-b1b3-de65e27559bd | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
3843097c-090b-45cf-a84a-0eccbae83213 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
47fdb50e-08bc-49b1-b030-a1708b0d993b | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
c8ea586a-a2a0-4d25-bba7-ece86ef09e19 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
c9aa8721-2594-478d-90ea-a3cc79e75ae9 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
d3024389-ab7e-438f-ba4d-933ef69e9d0a | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
d856167f-d747-4861-b040-ce9d1b4259c3 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
04d42b15-f7c7-4887-be1d-39eedb6b041a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
1e1837b0-bd7b-43f0-b1c4-cc2ca91b6dab | Pole | 0 | Distribution | 2020-05-30 | 2021-05-30 | Level 2
2b0c58f3-f9be-4447-884c-1d88c8333df8 | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
2fdf2a14-0af0-4f35-b5e7-3d906b5de7f2 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
3f117007-e7bb-4065-bf39-9358ce376e3a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
584a2ad4-6616-4e53-a150-fd7da3df079b | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
58b9b3cc-6110-4661-b21d-e7aae29f8c3b | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
5a3f69c9-cd0b-4b2b-8547-e2c9c7154cea | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
6a481b6e-6597-42e2-b26f-388d05b0b6e7 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
6ded2091-9992-4ae7-953c-8d31b37f7c96 | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
8b0594e5-4299-407c-bb93-3fb60d478bae | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
af1ae1ed-ae5d-49dd-b804-8c0511e19c91 | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
b0475d8e-21db-46ff-be02-44d63d9d98d8 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
df87d92b-f131-417e-af4f-f30641efa50b | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
e80b276d-e60f-4816-848b-9b3fa22c5c92 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
e891a2cf-274f-4f82-a8d3-ce36bb376abe | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
eb8ea6ed-a522-4ff3-af56-edcfc06879da | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
ebfa42cb-ce02-4436-b12c-81348cdb782a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
0b7d1737-4577-426b-b129-c5b15b3b7d4a | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
0f9cb270-fb35-4788-a9c1-a46ff9aa712c | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
1ca119eb-337d-43b3-a385-476e595df367 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
212a8d75-764e-40bd-a7d5-384f98ffba3c | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
250e00df-d4d4-4c89-ae53-a9ca3157d619 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
26d15447-3948-4bb4-a35f-1b2f0683e2bc | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
2b540719-fc7e-4b37-8568-85fdd48fb504 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
783733ec-4a1c-4608-bd56-3a0ff25bad90 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
78c9e454-e959-4bd8-9e34-b4ae56f9e16d | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
8ace8f23-17a2-4fbf-b272-d6ffe3a13601 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
8bcd60a9-b8fe-4ffc-b48a-0bc5655b2b52 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
9e4a87ee-5f08-4575-9378-715c9f8a12b0 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
a3b6a4b2-7c65-4c80-a09b-ccba8dc652a3 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
adcdfe91-858d-436f-a41b-b179a0922201 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
e39681e0-e930-4533-a8f4-a31e02e167cb | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
e97574c7-efd1-44a2-9684-b3d4c8ab40d8 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
080d00f3-5fba-477b-aef9-f6c3578c563a | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
30ce9bcd-9edb-4a38-9332-0219dbb0439c | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
3f5eb7fb-8771-4b98-a5ef-0246da117111 | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
44e3bf61-a54b-4b80-a2f1-8d09a671a2f3 | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
4c4e9433-fa75-46d5-9b3c-3adf8300c6f3 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
4f97aa0c-5a3d-4872-a859-fa4b0bf884cb | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
51245b95-6ffe-40c6-9279-b97ecef0da7f | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
6c3241ef-ccde-484c-a350-c79f6e612ad5 | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
7c0d85a2-2b45-46f2-bc55-51b7281eb017 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
83df01b0-7a1a-415f-9fbc-b0243d62411d | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
93c1acd1-18a8-4137-bfa4-aab9046cb191 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
a3b57de3-ded7-45e0-883f-accf4f09d62f | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
a8896dd5-c2e7-4923-a9ec-4a27f7b43588 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
c63b6980-13e9-468f-aa9b-1dfc9decac87 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
cb32183b-ed20-4f04-a034-b443de2422b4 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
d4d5f75d-805f-4601-a788-04242bd5fc4b | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
ddbaf6a1-ec0d-4093-887d-fb134c173d74 | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
ee4c3576-9d7f-4643-940b-e7db0ddf1dbd | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
000d6554-53fd-4fd2-ba83-2102f1df719c | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
001b28b1-a788-460d-9767-d6b7fc992dcd | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
15251438-a773-41c6-9771-cb1f1f28e3fa | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
166595b4-e30c-477e-b2e0-ce3e384aa416 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
20a13a3a-095b-4343-8521-b05a83bc4990 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
3d1d9cda-042a-442d-9321-3904889025b4 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
52af7a26-e7f2-4236-ad4d-f94de591db22 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
73ffd829-0c88-4016-8c7b-70ff955a1c3a | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
7452e2cc-3fd5-424f-a42b-11b56c9b9090 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
8ad3f694-741a-45d0-b6d4-0618fbf19756 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
8e845c8f-03fa-4c64-9a47-101b9a8ffb8e | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
a16662dc-7d00-4b29-9f5b-c7b468958946 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
a247f381-b491-417e-95f1-eecdbadc34ff | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
b3ccb286-e26d-4f97-891a-f4375a0745e5 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
b52837b1-fa26-4f34-9c8a-68e018e7b568 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
be1398a6-2afa-4363-95b5-a5b27b182f3a | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
ec1c11c9-1579-424a-baa6-ab098de6be81 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
04b45561-b615-4f05-ad50-ffd9e7fe8e8c | Pole | 0 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
2edf8c73-3987-4940-8580-163d1ed339b1 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
32045473-f769-4a36-8b2c-e1a18a2f7619 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
44af95e5-d9f5-48c2-913c-6cb72fc5fc9a | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
6c2b1a47-994b-43a9-834d-e072e7f77577 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
837e4b18-02ab-4739-b434-a15c44b6a8b6 | Pole | 0 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
863e8635-0cd5-45f7-addc-541cf3c825a1 | Pole | 2 | Distribution | 2020-06-04 | 2021-06-04 | Level 2
9f75cf17-9786-4870-9373-9f11f11d91fb | Pole | 2 | Distribution | 2020-06-04 | 2021-06-04 | Level 2
aeb3343c-5028-4b3e-8073-ecc29fcc4678 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
af1498ea-418c-4c11-a01e-b215a222f67b | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
b9799cea-7739-4e44-a908-208f32bdb8e8 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
bace2217-446f-4bad-b2a5-94400909b866 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
d6bddd38-89b0-4ba6-803d-d1ff74c6db1e | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
f412ca0a-7e4f-4e15-8756-10d97494d6ad | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
02344e6d-83e7-49f8-9d84-ff2e35b3a6f6 | Pole | 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3
c93df8b3-40aa-4669-9f40-067e31dbba44 | Pole | 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3
0fd08cfe-1081-481e-942c-4f9f45cfa17b | Pole | 0 | Distribution | 2020-06-08 | 2021-06-08 | Level 2
21b47173-9eff-45c7-8b94-863a9f119792 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
2d72eb9e-2c3e-47e3-b598-f967379303fd | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
385011b6-e124-4200-b979-a6cceaaafe20 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
545b9cde-99d3-4a44-847f-cb4f2ebcbbb0 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
5f3d33ee-c093-4c0e-9141-38e119b7f936 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
6daefa31-e5a8-4c4c-9790-cb7563625ef0 | Pole | 0 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
7e1e834e-550a-4d34-b758-89eb071558ee | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
9a604bf3-419a-4dae-ad3f-96161468c058 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
9ab0e5fc-be17-4b27-9b13-b6c5cf6ff9ff | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
acbf3bf0-9be1-4635-a9b1-1824ddb72572 | Pole | 0 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
b19aabc9-ac01-4482-807a-b8b83d44d184 | Pole | 0 | Distribution | 2020-06-08 | 2021-06-08 | Level 2
d03c6be3-6cb5-495e-aa2d-1443451c09ad | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
e8c321d7-ef6c-4c75-84b8-e4f6a20240bc | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
f331ed81-87b3-4963-8bfe-c33ee6f51ca2 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
ff2f1fc6-ffc0-4dce-913d-9b952a34a384 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
02dfe44e-70a4-4ac4-b452-a6b19d4da52d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
06e4038d-c548-4310-bda4-3813c1460585 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
080401cf-608d-4320-839f-236e9050f19e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
0967767a-ae26-42da-9af2-f828eb3a33bd | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
1422c26c-bef3-402d-a3ba-17bf458470e3 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
170789aa-88d3-4501-a556-8f74a5aa40c7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
176e05d5-c420-41e1-997e-23940a2c0cbf | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
1b1d833e-4a57-45b0-aa3f-2137df008f6b | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
1b5681ae-7351-4d77-a623-900390def3ec | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
215ff7e3-c507-4041-97f6-a9a277dde2e0 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
2548c863-b045-48c7-a426-a4ad9bea30b5 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
34d88b01-6c39-4059-b5a7-699ae79b9d5e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
37841d19-9db8-4e23-bd88-3535b4ba739f | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
3bab1843-2b41-460b-9e88-f2f1633828d3 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
46fc78ec-48c7-4000-8109-e6769d8a5386 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
5484733b-c97d-4873-8d9a-0fde7043f4f7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
60214aef-2742-4cc5-a78f-0603ebd8e13f | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
6291db56-a064-4aba-b92a-7e2156cba41e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
671f2925-2aae-4aee-a177-a5a1661638af | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
685e4d35-f687-4d42-807f-d1daa6e999a8 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
6bc56f87-9b1c-4f86-9eb8-845b4e5c62ed | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
6fb8be98-3328-4c21-9de9-58c62dce53ba | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
730291ff-fd0a-441c-9355-56f0fb97999d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
76b4f43e-9720-4b57-a917-3b9b58aef381 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
76bd49f3-4101-45b5-8642-dd7bfd90ce0c | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
7c540a44-82f0-4e33-9597-c00f12d6dfd9 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
7c800ae2-0c50-4f6c-ae14-8930671bbd65 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
999a9a37-e93e-47a5-8e78-d100204d1dd7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
b0eda230-26c5-48ba-8929-1e469db1553a | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
b48b4c59-2c96-4eba-ad86-6662e445bf50 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
bb220be7-8f0a-4ccf-9383-1666ad64e609 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
c6217fcb-1654-4cd0-9b63-a60d0c7f99c6 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
c81d314e-f947-4c1d-b4c8-94f8c78c991b | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
db09e8a7-ce2e-48cd-802b-2335114cc856 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
db67f771-1c69-4fca-9857-1a02fd97d909 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
e496fda0-9d29-4a84-a5dc-b0fcdb06f835 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
eb139688-455f-48c3-8684-e56a0b600a8d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
f1ea5576-3363-4244-a989-f809b777f346 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
f4574e02-cfa4-4fb5-9a52-a395ce2863ba | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
f7b05064-67bb-4860-869c-92da0fa42fa5 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
004cc409-6767-4f47-922e-70a181b3111c | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
0599d14a-ff5f-46fc-9842-8026c3dbe721 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
0b9b5d91-6545-410b-8a5d-180fbdec8584 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
0f8d7fb0-459f-4606-bc8c-edf30432c8db | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
19ae7396-66de-49a5-ac06-abd4fee47054 | Pole | 2 | Distribution | 2020-06-10 | 2021-06-10 | Level 2
2a69ee6f-0001-4da2-9451-0e86a2c1baed | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
2b167978-5f9b-43b3-a44e-888e986516f8 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
2b78c450-4ae6-4a52-9a7c-7d1b460a800f | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
33894339-aea8-4535-b979-2ad380646a01 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
4116cfc5-4215-41c5-a6e1-850c32a5ec54 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
6ff21d50-881a-42b6-adca-1c6b573e7570 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
73a96c50-d579-4516-ae91-fd5d8950e3bf | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
8b2796f9-8091-4815-9bbb-cb765a2d2a1e | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
b9ab27a1-b4d9-4f4b-a303-ccebc36945a5 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
d43ec500-5f73-4518-97f2-675408b934cf | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
e646d019-6aa8-4487-b200-28079532c5d0 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
f8834862-2132-4dd2-9862-6ec011e234dd | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
f9813daf-7509-41ee-ad7b-fb9cc7afba5c | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
ff453540-dd5c-44b9-818e-e76993a5ef01 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
60f5e1d4-bfca-41b6-81ef-6112ec31ac01 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
6e3e8a50-794f-4210-a1a0-24c7b4feee32 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
8129d2e4-8709-4d35-902c-93ce87740e5f | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
8ac8393d-f445-45ef-a316-954503eceda5 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
927a0a7d-7c51-4d82-ab78-e8b632ffdb82 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
9760bf70-9b7d-497f-a4e2-edb0753d230c | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
a5feccf3-cfe4-4bb1-87d9-a168e6ed80cb | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
cfe2ccd5-422a-400c-80a6-92875bfed708 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
ecf79453-46aa-4172-affe-23f89b20b9ae | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
f290599e-7bc1-45ef-bd7d-03007011e779 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
293b9178-b9e4-44f5-b557-6d233a3de302 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
59e4e5f6-18f7-43d0-bcef-b155802e98d4 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
d1811666-9286-46a2-8061-20744598e308 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
d8bf584c-7a8c-4d25-9d4b-b3fcfb3efc43 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
ed8b752a-a673-4962-9c22-df4d82be806a | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
01f6a2e1-e684-4cb9-b5f1-266195647e42 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
0380c174-29e1-42db-a46c-2bf591038ef3 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
11658340-a951-426c-bc97-aef0d57266b3 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
1d90da52-a463-4e77-9d00-12af57abf2d6 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
1ec593a7-4f68-4903-982a-0c8ee6dd9ec9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
2ace12f2-9784-4ffa-8c4f-597075c9c8c4 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
4c6750d6-1d06-4e02-b6aa-74a6a405019f | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
4da76b41-d120-40a0-a95a-f8fe2d396c0e | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
6f1a0b58-bf7f-4f9a-85ab-998425147884 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
79b10188-8397-4b97-af36-4f8e82fb4bf3 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
8550362b-1f26-4be8-a3d1-8fd8e75a871d | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
942e4bd1-9fd6-4fa4-a47c-4765099b899b | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
9807aead-c4a8-4673-8768-cb1e1fcb79b0 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
98c62ce5-fdd6-462f-a119-8b62387e241e | Pole | 0 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
aca4ece7-5ace-402e-8cf7-2154b11186d9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
af502321-71ef-4d71-ab98-421f0dbabb99 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
bee7bcdc-d2fd-4b28-8ef9-945f5765540d | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
c4fd6e64-f008-425d-b6a4-085797fbb0ae | Pole | 0 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
d28d08da-8a9a-4a83-a251-2fed91f2436b | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
d7fe47f9-c662-486c-b60f-3a561ddb9737 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
dbdc1909-681e-4867-b01b-fd2e312c7738 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
e6893d0f-e805-4d12-b81a-ff3230f48099 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
fb5e081a-0154-47c7-aa31-2ee4aa6ab4e9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
08c26722-d4fb-4d38-9041-320e42f64114 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
100b23f3-30ce-4070-a831-aebf821e5467 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
12588efb-58d3-4dd5-9415-3e45ef959629 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
130c29a3-f68c-4a3b-9f3a-7d8d58cfb9aa | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
14e4d08b-32e9-464c-859c-206557919546 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
20ee09cb-1117-455e-bb2f-8addc0d19913 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
23e03bcd-46a3-4169-9aa2-ebb46e3b7988 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
25fe7bf1-8a6a-4df0-ae24-fe9a006c4127 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
26b5b789-d548-4873-9130-3d2f0486d8a9 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
284f8efc-14b8-458c-8915-797b5eec9de9 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
2fac2070-83e2-49dd-8375-65f1ac739517 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
42de0a8e-f463-431c-84f9-74b432827e48 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
43e8f4a9-00cb-4995-8799-b07472ced851 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4b3d8b42-ec61-493a-b497-8c246586e6a2 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4b561221-623c-494a-97f5-7c3e2ad1eb5c | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4d38c9a2-e0ea-4e68-9983-3ec0d32dc3d7 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4d75f31c-dc00-4a8f-b2e3-77f5e1ebe810 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
514e9951-e5d7-41b4-98aa-640379f07582 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
5385694c-b7ea-4e2a-9856-aba709463f69 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
59c23560-39c6-48d5-8f20-7fe7f08b0440 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
5f32cd9b-9f9f-481a-b079-8cb0f75997d3 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
62958aed-5be4-4e80-941b-315f2de15eaf | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
6333f9dc-0767-4582-b3dc-950c3691f634 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
71a92032-cc44-4019-b3ef-03a16dea9727 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
7a751178-337b-4718-93d3-cfbec13ef339 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
85725ea5-5553-4e30-b74c-27b04540523e | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
86ad8a46-4820-4b1d-9a25-e32af08e161f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
905504d0-9e30-43ce-910f-372bafa149cf | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
95958bba-fc1b-4c56-b82f-7dd30736e687 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
97e9be74-c376-4f9a-a07e-5e5eab6d2a00 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
9b36a91e-77c4-43fc-8b5f-20479df48e18 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
a4b24059-d2ca-4db9-b7d9-7792cbaa8415 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
a57bde98-bd3e-4ed3-9b2c-c132720e5b05 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
a5af7af0-5b37-4865-9215-0c695f56f32d | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
b47da945-fbca-4c81-9e70-bc3a4b2b42e1 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
b74d8cd0-e943-4604-9678-6af45864fcc8 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
be827ee8-6726-4ac3-958b-ea21d218938f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
c2b82296-ec75-4393-b36d-05866c88691f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
c2bbf35f-4771-4eb6-a941-c12afc6b3c78 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
c2d60c9c-3ccc-437d-a313-29344358e42f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
c3e77797-3f5d-4bfb-bc9b-1d6ee05b3d7b | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
dd961bcb-c36c-40c4-b2ad-c672534e5f52 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
ddb274d6-023c-45b8-a868-5e452090d704 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
deb17079-db5c-4795-913b-f0a64c54569b | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
02139e47-cca6-4f2c-ab8a-141b5f1c2871 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
0355fc19-656f-471e-8625-9d649f1f9c8f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
042cd7f9-01c1-4c97-b3a3-2de190df6602 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
0ddd8d42-7ac0-470c-8cea-5c787fc9fb04 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
121b0a16-9f60-4cd0-81ec-de8f90975d6f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
13b2b12c-4694-494b-bf0f-4949db7aa4c8 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
1849050b-a2be-4d37-9671-dbc35474c58f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
23ac153c-a11e-4cc0-a74d-5ae3f4dc6f2e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
274cbf33-8770-4627-9dcf-95c261373c7a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
2854f145-7758-4242-932b-40d9bf7c1f98 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
2a0644c2-8c32-4c71-a2c1-f824647851f4 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
2d92a3ea-bd47-495a-943d-00aa49140d26 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
2de7e0c5-ada8-418e-b09f-2019c81b5b12 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3052e4e1-fe15-44e7-9a40-d4e4a0f67619 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
363aa800-8034-4a9a-9647-4da1b7e8321d | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3a7a2532-caae-4be5-bef2-3e7c196b622e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3b7a4f42-efa3-4191-85e2-047e738de316 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3f660050-96ea-4eff-a87c-21b42e2a2770 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
460366f8-75fb-4dfa-a44f-52869b92191e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
4635e742-4d54-4575-9831-da2124ec2103 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
47620d6b-5844-42aa-a240-480623dd2a10 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
4fd2be34-3dad-42da-85bc-325a1bff6851 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
51997adb-6f49-4917-a3d7-0d3c65947d65 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
5543403c-cd01-4d57-bd23-d62d524d4e03 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
58eeeba5-cc3a-4625-94e0-dac6000e66bb | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
602c59c6-4284-466d-b49c-287b8b50a721 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
61e28d29-fb4b-4bd5-a644-a4445d70d0d9 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
65ada0c6-02f2-4dc3-acb4-029efbd9acbb | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
6730804d-20b5-477a-b781-0bee3fa1d324 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
67abe50f-763d-4505-90a1-5c21df6f0b00 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
69eb1326-21b2-4ed7-bd5a-3950afb0a371 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
6d26aa8a-9d06-49aa-afbb-4ec80d9c3975 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
6f0f98f0-b3ad-4932-88db-869aad680f2c | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
71d67d3e-818b-406e-aaae-c7d36582c368 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
7252cb95-08ad-4ba8-9f0c-93deaf06e8dd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
72a5e09d-451f-43de-a3c9-142a2221e2ca | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
74385126-e8ff-4b62-9239-6fab093db6de | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | 2021-04-05 | 2026-04-04
75c6c19c-23e0-4a2f-9093-fbfd6b2c82aa | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
76ca1961-26bd-4a53-8ddb-679109929708 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
80b89359-e257-4176-a191-fa0fde99f6d1 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
842abad8-528c-47a7-87f6-755abbbf9ba5 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
882db907-2e16-4705-8b13-fef0cd1d9fdd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
8f5a474e-b911-40b8-9956-1a73928a83f0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
8fb4f431-bee0-4aa0-92b8-b43b7adbfde5 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
9513cc73-4467-4c54-a26e-4e5b011c1bf6 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
9608f8d3-1741-44ad-9ee6-d7ba260ee4c4 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
9eb0fc45-6338-4aaa-b51b-ff514bb7f5dd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
a24b195b-74bb-4b27-af7e-5713d7d1f144 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
a7951fc7-f848-4f22-afc9-2a6ffc3a4ed9 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
a93d94ef-5c3e-4e55-9aef-0d5cfd6f060f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
b7516126-c0ef-4d18-97e2-f4347694221a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ba8e8ee3-723b-4739-b039-eb771634110a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
bb98d7fa-2c72-4172-97b0-cb9abe553aae | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
bc73a106-27f2-453e-8017-c9de226194a0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
bd5f70f0-e7b1-43c4-959e-1ca538087e52 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
c014fa42-d1d4-48b9-898e-0b1885ce8878 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | 2021-04-05 | 2026-04-04 |  | Required to Re-inspect a subset of assets
c1599ab9-7266-41da-8c23-e9beadb09126 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ca861f23-5524-4c2f-8d3a-c9750e5d47a0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ccafc5d3-4780-48a7-92f0-4e3b77312a66 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
cd740d2f-4fb6-4d72-b109-b5af9413fc0f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ce653643-a75e-47e3-a4f3-44fa8b82ea95 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
dafffccc-49ae-4098-b8ea-97f3d339b228 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
dcd2ac25-9eaf-44a8-9117-cd8540ec101d | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
dce68f65-4f23-4363-93a6-d36f8c80fe9e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
e009a6fd-a426-4242-b8b3-4aefdbf018c4 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
e3642a38-128b-489a-9cae-ac41ea9f7cc1 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ebe854e2-10ca-4c69-bde3-d31f5894addc | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
f6412b1c-ad86-418c-9232-dd1ff8b7e045 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
f64acb2e-c98f-4038-98ae-5752f7650b31 | Pole | 2 | Distribution | 2020-06-17 | 2021-06-17 | Level 2 |  | 2022-02-14 | 2023-02-14 |  | Required to Re-inspect a subset of assets
ffb2a3f8-8314-43e9-b532-805792ad60f4 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
00cd6034-90ae-4c92-ab96-ec4797187743 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
016bd0b4-ab54-4578-bebd-54201027436c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
024f1dfa-f5cf-47b7-8c39-bacda515e7ad | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
02db2998-be85-4cd7-b008-30ed1fc15005 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
0b01c3f8-5563-4fa9-be0d-ef8cee63ab86 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
0ba37e80-2aaf-4a13-877f-5ef357f58c41 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
0e4fff38-eca0-4ea6-9047-e7949160e310 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
111e8b90-16cb-4a16-be1c-5a78cd98bb84 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
14eab584-ca74-449b-8b28-95e18ace810f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1965971b-946b-4fe3-95a6-c24a2dc5b319 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1a5cab52-5491-4ecc-ada6-38ac1ecf5a75 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1f86e085-6bc6-4058-b916-bd7d81948fdc | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1fedba06-3edc-4961-9265-f421931c2425 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
20bf6001-78af-4a0d-afc5-40110335257f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
2186f6d4-80f9-457d-a4ec-b0ecad324911 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
24f11f4a-c7ce-4fd8-90e2-61a5ce2cf505 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
295e741b-0444-42cc-b9d4-a278db89ba1e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3360d1c9-02e2-4969-8c84-88e8fb2a69c7 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
35247a14-7218-4971-8115-f2fbaeae2580 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
35f2afc2-3de1-44bc-8137-d564d098ee27 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3923537c-b2dc-42a5-ab41-2b6683866076 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3b41cf8b-8918-4512-bc2f-e96e4d9975d1 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3d5f3b0e-76e3-49a3-9ea3-45a25874adb3 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3ec938b7-fb1e-4d77-bd02-c1c6d191c956 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3fbb4c23-222c-4754-83f9-c06024bc26e4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
43c1b9f4-605d-43c2-af51-403c220536f7 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4639ab5e-ff57-4d4b-b238-41d347b528fd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
471cafaf-ed83-4570-a7a7-a483791da6f5 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
496409a8-957d-48ed-b939-11e31b43278e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4a40846c-d6f3-4ba9-a0d4-4f6c1783bcee | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4a4375c7-46a5-471f-a8b0-2d5b9ca9f42f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4a76a857-e0db-427b-b038-1bebfdd1c073 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4b7756cb-6805-4a21-b8d3-48d4f39e154e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4d08eb59-41a9-4271-b73b-fa021f7cf60b | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
52257f2f-699b-42ac-85bc-a8c0cba0ab37 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
5e9e06b6-0807-4bf8-b61c-616fcf2b1ced | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
5ea0e2a3-f49f-4d72-a98d-ba8f1bb89e60 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6187ee35-27d0-408c-b25f-685c6f4cff86 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
64e79839-6b05-460e-b6aa-b146de34cd21 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6759a367-0d01-47af-9fe9-ccfedd1ec6fc | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6da1e94a-4500-43a6-b1ea-99040f7fa44a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6ddf18bd-5522-4b4e-a0a5-fc21bcd2a77a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
733c4f3d-8676-404b-9d13-00014b5fcc47 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
74681f93-546c-4476-8fe2-281bb9c8f0a4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
7bf86b3d-b7b0-4006-a4b9-3970426a1edf | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | 2021-11-17 | 2026-11-16 |  | Required to Re-inspect a subset of assets
7f4c1647-2eb1-4ff3-bf35-658ac45ba797 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
80f16822-2810-4cf4-8ecd-308281edc9ee | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
85e56b3d-80fc-4584-922c-5d8a0b97b814 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
8a813efc-1f90-4ddb-81f4-a94aae52ce28 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
8adc09ad-da17-4d56-906e-77bc4e1da3c2 | Pole | 2 | Distribution | 2020-06-18 | 2021-06-18 | Level 2 |  | 2021-04-05 | 2022-04-05
92db5668-0323-4947-8344-ef1cace2864d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
96848c03-cd9f-4f8b-b9c7-da7510cf6f0d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
973242ce-6831-40b2-afb2-2ddfaea2e86c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
9af747f0-dcc9-42fc-b9ad-6bbd91be0427 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a06f9b29-5bfc-4782-bfba-eeaf2b9cb502 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a1995b28-ab54-4271-8c21-865137b1185e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a870008a-7a56-4e4b-9081-62c247b984f8 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
ac1e9bb3-2479-4d4f-a516-ace320ba0248 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
ae79c957-85d8-4126-93bb-48cfe524ac0e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b1046a26-9670-4553-84d7-0244821568b2 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b2d455e3-153f-4f08-8755-9ed80767664f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b58c4337-fe71-470a-bf88-a860c1441de3 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b7751c2c-6be5-43db-88c6-ec1edde17080 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
bb37b487-2926-4b8e-998e-a5122a4b6aca | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
bc082cc7-9d27-44f0-a03f-af80323e9115 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
be89cbed-f794-4a3e-928f-9f1dc484a109 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
bffd744b-6f18-4239-bec0-0c1c39ab9b3c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
c66e7fc9-3e30-44dc-9748-f365d63aa59d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
c7100f98-1b10-456e-a32e-364fff9b2ae0 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
ceefe8f8-5fe1-48c9-8ba9-14f0a6acf560 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d1d7bcd7-6e85-4bcb-80e4-babf3c4eb51f | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d1ddf84c-9ac3-4f8e-baec-29fb1c328e59 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d587e5bf-ee41-4e4f-8f09-5fa7de5fc5e4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d7ec684e-5593-49b5-87cc-962d05b13cdc | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d92edfbd-2989-499d-8710-3ef92315e503 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
dc7f9438-4285-4007-bb4b-c52e6a345abd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
dd7eef1d-9efa-4dac-a7ea-01caea9cf7a0 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
df600a4d-b67d-4b6e-a6b8-ad77c019379f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
e31f7385-bb7d-4f01-a21e-7649c585b75a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
f3400bd4-188d-4c92-982b-132bd4f1e955 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
f63ec69d-6c6e-4b3b-8db0-5fb57453e9fd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
f86f93b7-c168-4c85-ae7e-8f251e43242a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
fdc52b0c-8fd5-403a-ae54-5986169802de | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
02a56653-2675-4392-a067-541417a97438 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
03114452-4eee-4113-aa19-a7899349f90b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
04c32d67-3204-42d6-b362-6e999247868a | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
09e207ae-d85d-4bc6-82b1-ee3c6cb93945 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
0ac0c8e2-e5dd-4d65-a629-28048831e00e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
0c384509-d31d-4f33-bc00-eee02296eb58 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
0e5b9d25-4fb1-42fb-8e8c-1cede50f1535 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
11155b4e-d8a1-41de-80d1-721a10a46e01 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
11307c9a-348a-4634-a842-17b2bc617e8e | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
14b1b9bb-6399-4855-b711-9434da84ef08 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
173567e0-cb2f-48ba-b379-95c413e4bbc5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
1d53278b-4333-40b2-a690-baf75dcbc5d5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
1f5076f0-909c-41b7-a5fc-b526edcd0171 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
239a01e1-ba2f-4513-9604-c58cca19516e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
265debab-6d68-4896-b119-01dc4f5fd30b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
2ca32e57-453d-4d14-aa06-2e98922bee0f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
2dc10e8c-43ce-4889-9c0b-9571509d83c1 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
2f43e28c-aea0-4720-9649-7d20005f0a30 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | 2022-11-09 | 2027-11-08 |  | Required to Re-inspect a subset of assets
32087715-86ce-45bd-b5c2-aaa2532014c5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
3f0aede7-2193-439a-ab5e-275d34e83af7 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
432b48f7-9e15-4c09-ac0e-d4f774afe696 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
4c853d16-73b0-4d07-99e1-fef395e67089 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
4e6090fa-a289-4b6b-a426-e57eb3a47ad8 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
5397419f-3760-4435-9aa1-7259d14586ba | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
5bb25fb2-1301-4486-87f1-2fb0d6aff127 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
5cc87c91-672f-46a4-8132-e2abbb4528de | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
62b1cda1-254c-4bc1-bf8d-ca12df9f39d2 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
65434239-eea9-4e86-a307-a17439aabf30 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
67f6543b-74f4-481b-aa6a-437c2813189f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
6a0101cc-b040-4785-a94d-6dfead3e4d35 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
6a295a6f-8ec5-41ed-9701-206dbca0f5f1 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
6adc4edd-898a-448d-8d43-a0809f46a690 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
6d518dbc-f960-41c5-abfa-3df4c4b5ba04 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
716d1db7-c1d9-4515-a5c8-078a8db45898 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
764f469b-600e-45d6-bcfd-ae10452393c8 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
7b093877-434e-4afe-82a3-0634ff7c2009 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
8938d985-fd76-4bdb-b2ce-7203c56ca3e7 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
8bb238d1-572b-4fad-b9b7-1cff48affabe | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
8dd92974-28ab-4178-b432-222e3bf66269 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
945e5153-e460-4407-a38e-134b5a338b22 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9763e357-b051-4e7d-93d5-fd7dafd2e2a0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9a3c901c-ec77-4714-9858-197191b3277e | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9b52c8f2-ad8f-4689-bb38-ff05775d6ca3 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9b54d2b3-f79e-4b3e-93bf-4e02f4c577de | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9d3b6db5-f354-40d4-9b6f-15e2178b313b | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9dcda6d2-9adf-4968-bf8f-98defc9706d6 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9eb03c0d-d84d-4c47-ba5b-4dd9e449f92e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
a20cec94-5e73-4bb6-8753-d9fbe4874595 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
a416bccc-e385-43bd-901f-6ef2f22a7f6f | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
a4738ee0-32a1-46b0-92e3-8d9bfe6cf5ad | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
adb95c06-6aa5-467b-9fd4-e4ccad54ab5f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
b13797b8-66e9-4e91-b80d-3084fd7ff124 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
b31f34d6-9193-41ab-b916-7fa45954ce51 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
b3978a2d-c517-41ee-b407-11a585bf96eb | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
b6b9f2f7-32db-4318-8a50-7a3f108379d7 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
bacbba9d-24cc-47d8-be54-5e0f4ac4db19 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
c11f75fd-d5cc-4832-a573-24d7abe136c0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
c39e7137-89e4-489f-8d12-a9473229ac32 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
c8445fe5-6159-4042-82e0-d30b275daf4c | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
cc0228fe-e26a-4054-a313-061cd138fe82 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
cd6e785c-855d-4582-b955-f6b5517e27fa | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d0b98047-b4f2-4bd7-a235-ece05abb368d | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d0de4e3c-46a7-4fb9-a487-ee0052dca351 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d2b0813d-d7c9-41ee-9100-aaeab7ef8491 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d430f272-84fd-4ff0-ad47-1c2f8790e608 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d5fac83e-6961-43be-b824-6c76f4005b4b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d691ca28-27b1-4ec1-bc1c-a711cd2c027b | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d70e2f5c-58de-4fdc-9c81-09adebd5a8c6 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
daf5c354-220f-4576-8c48-8d406f16f5a6 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
db3a2ec9-db5d-4664-990e-acee3e624953 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
dccbe7c4-9821-4c3f-b137-59ea1b4c1a82 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
e5b1e486-53bb-4adf-918f-e0864c6da55b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
e77bdbf4-a4f2-48ac-a141-9522595cccc2 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
eaf8744e-cc6a-4f13-8c3d-ea4a88b0e40b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
eb15c717-e93e-47a6-9367-9daa1ace59e0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
ec7ab5d0-11c9-40f0-bfa0-ad5e59c02b6a | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
efc2d95c-e966-46b4-8cad-b1a9a0327fd3 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
f42dd436-4f49-43e4-846d-f473d1497df0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
f6a88c60-ba9a-468d-b550-240f277ba0f5 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
039d7ab9-5c89-4a2b-9302-08d477fabea0 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
05856d6f-64e6-4102-9c88-f6809c0e9015 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
089d1e32-36b3-4a4b-94ad-04ca87094bfa | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
0c1b9592-e898-4a7a-aa77-b2582f94fa04 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
0efefbf3-d8d0-4537-a85c-61fa0d1e1764 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
12abae04-4c2a-4f18-84ed-89e038e285e9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
17ff1c88-8438-4a22-a3bb-f81a46a9b9e9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
1a28444f-0187-4d71-b066-4d637bf88df9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
21dd1f4e-acec-4c91-bb6c-541016106b53 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
222bbb8a-673d-4da3-bf03-a3deb4d82f95 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | 2021-04-29 | 2026-04-28 |  | Required to Re-inspect a subset of assets
2476a927-6cc2-419c-a714-ac75e5e74f41 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
2890dd64-3e13-44b3-8eac-04e3a524a415 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
2dd2777a-7acf-4116-985b-7dc3f777bc3c | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
34bd9831-dd25-45ae-9a5a-8505b1a230bd | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
44a3ef4b-98db-44d4-8a4a-eb043aa2ce8f | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
45060af8-637b-4b2d-b4f0-f8054ae16143 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
485fccae-0846-4c6b-bcbd-841bee744d31 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
50db1b7a-1ed4-4718-b780-72df76efad2d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
5591e8ed-22be-45d7-96ec-1d89c99e28f2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
585b901f-58be-4440-aa8b-2af87f2c3f40 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
5a3b9384-33f6-4c84-bc81-9de47f7f43f8 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
671568b6-3d67-4abd-b075-b73a46ae9be1 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
6a3cc61f-514f-4585-809a-ef0783b4978d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
79a50eac-083b-4180-8ccc-2a0cf1718fc5 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
79b23a67-d2e3-4ca3-9516-d9a10f2b7a40 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
7dc399fc-6b05-4983-9192-bb113b582d0d | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
8361087a-9c3e-4fa0-aeff-af3355203f1b | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
8f887f03-f5a7-40b3-9eb8-89626a5bee4a | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
912e00e4-d44f-4eba-a324-3c6cf9f58ab4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
9538d2ab-ff7a-4ed7-a41a-6cd6697535f8 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
98724d3d-0e04-4127-a63d-89ced6dff3ad | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
9b003c92-caee-4c4d-b18a-16533f830aa5 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
a925c989-d261-4fdb-b7a5-7d5faa313422 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ab2065fe-89ab-4f01-827f-acfbd2da91b2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ad226c8a-0447-4453-ac74-ecc11dc58ac4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
aed855f3-a0f4-441a-bd87-f53090f00454 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
af7b102c-1df6-4036-9a8e-9440b839bb0b | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
b88f5c63-1dd2-42be-8e24-594eb0d77642 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
bcf04c9f-c76e-4d6f-90b2-5c88e4449b1a | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
c54dce48-3e74-4ee0-a61f-7b830e051e52 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ca6b90d4-2d4c-4056-ba6b-17f5b42947a4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
caad1ad2-21a1-4f6f-a931-7007a1c44fd2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
d0673a44-eec4-4dbb-a44e-98fd9f20a746 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
de4b462d-ce0a-4f59-8d16-a1cab842d645 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
deea4bc9-9ef1-45e2-8793-8c515cfc3031 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
e030bb8a-cd30-475f-8e01-f23227c4d985 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
e5ed5acf-f90e-4443-b65b-49640baf5228 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ee4aa1a6-ecbc-4a80-9018-bc7d3c2faf98 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ef92b9c6-19de-4e27-83ee-12d8e99d778d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
f1bae1e0-c81d-47c7-9a49-b853bbaa8ea7 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
f95f0dd5-af79-4ba5-99cc-27f8bc189ff0 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
fcf268d1-f589-46a1-84e2-a71f5db1edce | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
04bebec8-8a5a-499e-839d-5f3635adebc3 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
0b7c5dae-9b47-4f96-a4d2-7b64a75f7eb7 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
10994a1c-e862-499d-99aa-5c0d1d1a5721 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
10a25420-c12b-4fab-8fe0-7785fc4f162e | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
1483d12b-e665-4576-aa1b-b010a6f21d74 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
188631a6-d5fb-44ed-a41b-97f83baea314 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
19ae9250-ec80-4d6a-bc85-28213d7eca13 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
21b3ce85-cbee-422d-81a7-f284bd4b63a8 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
29956b7f-ec0f-43f6-8fe9-f97990686847 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
2b49e4a5-3127-4498-93d7-aa782274da55 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
2f0b72e6-d724-475b-9e03-cb6f84b4a15a | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
3e82aae9-a5ca-4755-bda8-016105f231ba | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
4b8791d8-ceb1-4a03-903e-a072c1a957fb | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
4cab09c3-8c60-4b58-b7ca-15f48cd94d07 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
54d42a26-1e38-4522-b8d8-fee85db89470 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
5570b5d7-33d6-4d2f-b389-06ed8022b1c3 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
58ceeba8-b08b-421f-bfac-2035247e9a88 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
5db68c03-8c0d-48a2-9d06-426ea341e73c | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
61b6aff5-e6f3-4937-9cba-acb41beffd60 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
698d282f-292d-4df2-bf40-834e8800b482 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
6ecd1eca-1fce-45b2-abda-82b5e17cea38 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
70339f64-6fd3-423f-91c0-197b9122e000 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
7e608a48-b485-4d0f-be98-265f06fec672 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
7e6db917-14a3-4b7c-aef0-bbab648ddfd3 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
85a53496-1108-465a-b44a-132f81ac585b | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
874e2e05-029c-447c-b6fe-9f4b8c57c95f | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
8c5882e1-dac8-4d1d-b0c5-192a405036bd | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
98ffcd3a-418b-4b1a-b964-c67028f62714 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
a7cec7a9-9054-4fb7-8450-8b2d6283c877 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
aaf091ac-d100-4aa7-9d32-ce8d06ff1d19 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
ab11dd14-a0e5-4887-86ac-2c345dadd443 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
aefde86c-4809-42a8-becf-90f693166ee2 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
b0a7f69a-37e8-4f80-94bb-32d35df8528d | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
b49ba89a-e2f3-43d4-a762-1b64c9673c63 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
b88edc8f-0dc6-4266-9baa-254862dcfb32 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
bfe55a0f-3a28-441a-bdc5-d2e672bd5494 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
c1db789b-2672-45e7-8b51-6223e1e69bee | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
c2e783e7-5a64-4ff9-9540-94a8c883fe33 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
c3f2cbd6-ac4b-4ef0-aded-0cb7172a17e8 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
d2682e02-7aba-4199-998e-69243c831842 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
d291f631-a08c-459c-8d52-c03a33b9a713 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
d3b88be7-2c4d-4dcd-8965-8961cb73e174 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e7b77432-b78e-476f-9b9c-3c0c11045415 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e80a4238-bee0-42f3-b4e2-a34b34278291 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e8218af6-7717-4d4a-a6b2-b1ba075e47b4 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e92672c3-9361-4f78-a8c8-cee176a34721 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
edf83bfa-6151-4eac-b63e-33abc518b217 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
f1834de7-8c0f-4f89-925b-8aa0436bc679 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
002fe135-38ea-4cf3-a441-6a06ae4fa972 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
008db2a9-8957-4af7-9481-f3c54c5a8900 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
02e58939-3c4d-4c0c-8aa6-205e085404ab | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
06afd339-c8d3-43f6-8464-7542998c4fc6 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
1ac8b35a-f9cf-42f0-b562-9980c4ba079d | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | 2022-02-08 | 2027-02-07 |  | Required to Re-inspect a subset of assets
1bbe68b0-f9e9-4a50-b031-acec1e83c2ae | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
26339124-825e-40ec-915a-fffa7052bdac | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
2bc59a40-d6a5-45fe-aad7-ccce00411051 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
2e2ecc4b-9379-4450-879f-feea210b48e6 | Pole | 3 | Distribution | 2020-06-23 | 2020-12-20 | Level 2 |  | 2021-11-16 | 2022-05-15 |  | Required to Re-inspect a subset of assets
304c05c2-f7fc-4e57-8632-a783db09837c | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
371f0990-793a-4128-bb68-65be4fe67121 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
44b178ae-c3ba-4f53-b211-e946903f463a | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | 2021-04-06 | 2026-04-05 |  | Required to Re-inspect a subset of assets
49191429-dff4-4d4f-a0d5-763c6a9305a3 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
49b74be3-0168-4d1e-952c-4450c7981ef9 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
4ad15acd-9f41-48c6-ab23-d0b534fed5a9 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
4b532bdf-88a2-4bb9-818c-d9127e2df87f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
4c864429-e355-4b71-afdd-21c5ebec5d02 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
507edeba-5cb4-49ae-876f-e4b19d86d29f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
52987523-dfe3-4bb6-aedc-c09e5df517e2 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
56455d3f-cae2-4fdd-914e-46f91b0be54f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
716caf31-a3a5-4db2-bcef-9d175a8c12e4 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
71af0cbc-2934-4f81-97af-86d4407feb7e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
77125cdd-8bad-464d-a039-daff3efda020 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
79396c85-28dc-41b7-97c0-10fd468e20ae | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
7b3c9249-0d46-44ef-ac36-704fcc146571 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
7b858153-914b-421c-98bf-79e93c373e0a | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
7b899d9f-eec2-4024-9b71-2ece1dcb79b3 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
7cba5a89-d7bf-4934-8bea-36aac7c87da1 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
8090ad40-5ccd-4208-9f0b-120434b674db | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
87d3f39c-c1f2-4dce-834e-341f0bec52da | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
8c3df28b-caed-4749-a636-9b10cd12e431 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
9155ce3e-0816-434b-ac6d-bf79d1a9c117 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
917abdc6-e03f-44b2-a578-8c6b474ddd46 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
999a6497-c49c-46f1-bbf2-d6ec19793e4c | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
a4ff24a2-2757-43c8-ab0d-f9472decfbd1 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
a929ad9d-d48e-44dc-a3b2-bf54d8d7b99f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
ab1ef444-5aae-475a-b7cb-e0eb421901f6 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
b0aceb20-1ff8-4fe3-bb30-314f7b6d3db9 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
b1c14276-328a-486e-a4e7-6a67621b65a9 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
bf323f11-80d1-48ec-bb42-5e28d0779737 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
c2866058-dd9a-42d4-8f90-cfc688e0cd46 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
c4a45a4c-57ae-4334-a2c7-311ae6cfcf82 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
d0228653-c7f8-4087-b513-ff1b4c937371 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
d8a89991-219d-49a6-9a63-6febcf5a043d | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
dd64b478-1578-4906-9424-a6f78b7ecd71 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
e3088ea0-f521-4bef-87fb-39cdc23e2bc5 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
e4429fe8-ede8-472f-b03e-00757d01375e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
ecfd0d6b-7206-4394-a2e3-e023ee5f0ce5 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
f3023e49-3142-4d97-bfd3-dddaaafafca9 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
f7147810-e152-4c85-b25d-d97e83ffd02e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
02fee0a8-e4c7-4832-8bf3-8bc953161c59 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
0a086e1f-eaa5-40dc-8bc4-465aac93a5ef | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
104366a6-69a6-4bc2-b570-c221d630521f | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
1c92117b-e16d-43aa-b434-e6b436a885f2 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
1f727005-d03d-4c80-b788-8b9f61afd3c2 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
1fffa40f-168c-4c5a-96f3-7ace5c433a87 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
271dbae6-d155-4640-a474-23b6db1d9ab7 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2a52fa8c-19ee-4d84-9cea-c0a1001fac16 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2b43afe4-ffc3-4b43-9ccf-dba75c65bcdb | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2cba7531-2b01-4ad6-a51b-c13d65176e13 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2ed05423-321b-4ad3-a8b2-caa4c423738b | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
4da846b7-2d95-4710-8a88-0e60645e55b8 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
51c12225-f0a7-4bde-bdcf-9be7fb3184b5 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
5cf7502e-b68f-4b18-be04-b0f14b66f219 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
5daecbd6-9c6e-4e9f-804d-18adb8c977b6 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
5fa3078a-7dc4-40d3-9faf-a585269cf9da | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
604a6e0e-139c-4af5-b245-787bc610885a | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
6117b049-b1b7-4db0-97de-9b4d446a95d0 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
61f3292b-6d38-4605-8fdb-f272c6b85b37 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
66b7aece-37ef-4265-ba46-3b7c9374de88 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
7d031917-c268-45e9-99ce-9c1c631ae30e | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
90edf98c-3ea8-4aec-952d-32387489bb11 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
9e07b871-8577-4097-9c72-79efca0bd079 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
a3c0c5f7-c4e0-4669-90b5-4b324db82ee0 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
a76bcf26-87cb-4275-955b-582f6152e6ae | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
adc3f614-a6b0-4668-a12c-dc6f6c16d47c | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
b04c6fff-951c-4d53-ae63-a00d2ba076c9 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
bab2724b-f600-43ce-b63e-3c69af96fc57 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
bac569a7-20e2-45a5-832f-7e6665904430 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
bbbbacdd-82ac-4f75-a7e8-a7f6b3973088 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
c192c0d3-89c1-4ada-8475-774403aec93f | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
cd71a568-2c4b-4ad2-a7dc-40768159962d | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
d3efbae6-5a18-46b2-a87b-c0cc3b2dd8b4 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
d5253ffb-2d0f-4d58-8ade-62e43808e029 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
e057a47f-8dab-445c-b650-91f8f5296eaf | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
e13a886f-4473-4389-829f-b8786a4c08ef | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
121083f7-cab6-402e-a038-b8b0d40729ed | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3
17cc363b-bb3a-48fe-a6f7-ab19fc71200e | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3
aa4a4f89-550c-434b-a987-2d285f6f57a5 | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3
010dea4b-5723-4c4e-b547-0f071701cd6c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
037f1e9c-2fa5-4b2f-89d7-94b71533a86e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
07687a79-7302-4301-92fb-c135bd031df8 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
10929716-ffdb-4809-8965-18dca0f94032 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
14635e22-68db-492e-9390-bbb0b42f63eb | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
153a8b97-1037-42e1-a826-3e07d0398f0a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
26e73e10-bdbb-4ed8-b5eb-80b148f524cf | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
28228cbc-9c8c-4a42-acaa-8b5e532176bd | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
2ced75f1-65d1-446c-8ecc-6544027cf994 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
3616faf2-70ac-49be-9038-f43a55d4a132 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
395f242e-314e-4d0a-846a-19d238330d92 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
3f81c4c5-4e27-44c0-b0f3-8133c8a04c53 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
410c85d8-c60b-4a47-8a2f-f518a34aa65a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
43919adc-265d-49dd-a1fc-2a5fd0964197 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
44f132df-06a2-4366-997f-abe300570334 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
452cbb64-dfec-48ff-9473-dc919fa56f2c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
45b9385a-ff0d-46c3-a387-e629de452425 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
4761d2bd-df55-40bc-8b3f-685d08c65b50 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
4a1ba934-7f4d-45fa-ae17-00b0aab98e7d | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
5d8e0cb4-a54a-4b14-9d5a-06f07a5076d0 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
676309f5-4399-462d-bbe5-56f3eba2a109 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
6b168566-c458-48d1-b847-59ad2901ff32 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
6f49de98-44b8-42bd-9d32-cb230f76f77f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
74b35813-f04c-42a6-a9e4-786970a9f75c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
7ab4984f-0e02-429a-a669-a28fbacb10a1 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
7d6d4e47-cfcd-4bf2-8b92-3dfde0dd8885 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
85951483-a278-464f-9fa7-0b3ba767d66c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
877d78d8-e068-4865-8742-ddefe6db6afd | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
879fc600-f387-4175-9403-4cdb61f7df70 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
953cc4e6-0b1e-4304-a325-f3c9edfd8e52 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
9ef8814d-191b-438b-bfcf-85d36dce3c7c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
a4619a5b-c701-48b9-a3b5-2c718136ab6e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
aac4a932-fc7f-4c4e-9b8c-08537c9388be | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
ad7985d4-cd46-4f6e-84ab-61f86cc488a9 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
afb77e87-6c87-467c-845c-6729d5c06cdb | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
b35cce3f-cbdc-4d0e-b6e0-c61993ec5317 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
b957b650-276d-451b-8bdd-699c7dfba05c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
bb7900e9-22fd-4f03-9f50-549f3dac6d84 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
be2c8d00-3ede-4f6c-9f34-fcc520ce8885 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
c0be4ef2-e3e4-4fa7-8f5c-8f103c7e9b5b | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
c431e01f-357d-4c27-9fb7-8c411e9087f7 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
c5fde696-cd36-4330-bb33-acaf1dbe07ba | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
d6f704c0-14ab-4f61-a005-98c1035b286f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
e4951624-5c90-4133-a059-7ccd435c250a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
ec8a747f-f7d6-4143-a01e-2d4a6d7712d8 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
efd2da55-493f-4673-b4f1-2229c14b75d6 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
eff1de65-23eb-4c3b-86f1-2fde2d995091 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
f43b4113-1e8b-4972-b255-6e7de666817c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
f71a341e-40c2-40dc-adcf-f7dda7623a1e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
fc4b0c68-1e8f-4ab5-9f5f-7f0481f8e37f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
fe200f70-1456-453e-a343-aab9690db571 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
fec1f6e4-ecf1-4d58-9992-7e4ec1c7ae43 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
02ef93b2-f9e4-4147-88b8-94e6bca6ce8d | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
06d73a8e-c88d-430b-952e-c4e7c2adce99 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
09986968-41e9-4962-b795-6364930f9a48 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
0d8fc9e4-2c57-4b70-b443-90cd0204c2f6 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | 2021-02-20 | 2026-02-19 |  | Required to Re-inspect a subset of assets
0eea7117-0804-4eb3-8dcb-7b4b51b1bd60 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
107e3cb4-987e-4158-a158-c35f49ea3595 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
1284b4d1-d833-429e-b933-a357e900a647 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
128f8944-5bab-442d-8600-79c423186d0f | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
147fb4d5-07ca-48c7-a541-91de53d4cd38 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
163eaf18-4e56-4cca-b007-9044c750fd6e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
187a3b78-cd7f-46b2-af5a-3b67deb63aba | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
1f118a43-0e56-49fb-a5a2-1ae5c07c9d61 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
2b6fa4f7-0190-4d83-a802-6722a2886a76 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
36de26e1-3f94-41d5-9cda-19889db7dc32 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
37a47cf5-337d-4417-83c7-9b9e7b2d5d0a | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3969bf77-0256-4c83-b6a1-e5b79a9885ae | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3b821410-34b9-408e-ac3c-e0fe85a9607a | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3ca0b151-623f-4e70-8f50-4250096f3517 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3d588a01-bbcb-494a-a689-113ef6616ad2 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
4148eb72-d1f1-448e-a4ee-f37ed6088bbc | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
433a0535-2570-4e23-80d4-12c2fc438f06 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
43802c10-c840-42c0-8b9b-9cf9137bb581 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
4d05546f-ac5d-4e85-991e-63f82fbccf81 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
5333a12c-2e6e-4519-8b85-1a1564e03492 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
54efb175-1c61-4a82-a4b4-5b5558d8709e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
556905b2-b911-4435-bcc2-364dc56bf95f | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
5c5638f9-db42-40c4-9f7d-edf5ea0bf692 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
603d293b-69d3-42a2-bd67-cc8b06f420c9 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
642a93f6-411a-4897-8772-5eda69304c2e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
68415d3f-52bc-4364-9332-12143462bcd2 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
69d727d2-eedc-4298-9e8f-d3d62cd4e230 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
6eabcfea-503c-49ff-b0fb-37889e91c08d | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
712d8bff-7077-48ef-8ed5-a30cc9ce6fd3 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
72696d1f-1fda-4026-9d7b-0d38893f9287 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
72bc0fba-0e18-4f06-9b8f-91ba2213beab | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
78b36adc-1733-4dfa-87a7-4a106a55ca90 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
78c4f330-c948-4a00-9b79-08b9a7e57326 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
85ef6292-47ab-47cc-b945-fc2cdb60db9e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
8806c422-b2ce-46dd-94ac-80ab4e19fd4e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
884975fc-2cb4-486f-8832-f749224689fe | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
8d0fbcf8-a48d-437a-b2ae-1620829e3d9b | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
91e4e388-dd32-440e-9ad5-3664cf8e6f48 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
94a3d1c1-3e80-4713-abc1-bf44fcb58201 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
94d58262-0436-4c54-9bad-7125a07b2dc6 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
9a1d3ded-fe52-4a59-a37d-6f97683426bf | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
9bff3554-1abf-414c-9afc-0783bab946f0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
a0b71633-ddd2-46c1-a6e8-e9a4b830df0c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
aee1cf12-4f8e-4f1c-9320-9dd2caad70e0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
b0acd8a7-018b-4433-981a-0bdcfba8283c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
b69a0afe-0601-468f-929f-e6dc571b3be7 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
c3faa75c-5ee7-4d1d-900d-926287bef9c0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
ce9c74b8-5406-4376-b450-30224704c272 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
db6319a8-3ed7-4120-8190-df2e8154e676 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e242ea4e-dd01-494d-9d35-b9cd1c397f61 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e35752c3-be1f-40d4-ab58-98b3e3af8ba5 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e442d116-3c58-4eee-a889-3832325663cd | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e7c7ceef-6e7f-4598-a673-b144b1c37c20 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
edfcb782-ead5-43fa-968d-e0c59fdcdfd9 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
f28f6101-8cd5-4d7d-b260-cd6aa9b2bfe5 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
f3cba543-55e0-40d2-b7dc-ae28bf2faa3c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
f751f785-c464-4c2f-8814-5594c759f51c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
ff925cc0-bbbb-47c9-b9c7-e4c1fc29e346 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
0166f3ac-b1a4-4f30-930a-68ffbb6ef502 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
0508e5c9-9634-4fb2-bd93-42beef939288 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
05a5439e-d149-4511-b22d-6b3ceb7a1086 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
1425b2a4-e013-49a2-9817-2556d9be8c71 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
14e377a1-e093-4ce3-ab63-bcf42dd61975 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
17204ebb-ada2-4803-b50a-cb89600c83b1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
1b3f49e0-be8e-4a4f-a594-d888d7896d06 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
1e1e89d4-14b7-4fc7-8322-8afd029686a1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
1ebdb519-0473-4aa1-bf78-ebdf167d06bd | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2107f36e-a842-424b-b58b-a6556228af91 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
21a861eb-0df7-466a-ae53-7c35c80d8164 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2878ce35-c745-4643-aca3-e5e1e41e46de | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2e6afe47-8b4d-4b91-b05d-ea09faae6ebe | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2f7dbab1-ec02-41ae-b2a8-519b1b4d6704 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
3a67bf18-b460-4590-8631-4f4296711e77 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
408f776d-c353-41d9-a29d-d729cfaa03d1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
41df014b-0d11-4cc5-ae86-0c99a9360e9b | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
42b739f2-26ee-484c-ba18-02685a5eb480 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
442ce52a-3ccf-4667-8b12-ab57d047ee6f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
44962482-c053-4446-9e43-8ff3c0b98109 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
46bc20fb-d1c2-4361-b372-b198f23f4737 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
4816836e-d108-4928-95ff-bd9d22bd442b | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
504c40b7-cd0d-4f19-b30d-2e869850c6c7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
60dfdfda-a4ae-4727-9f85-95ad4a6dad51 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
61c10519-e229-4b28-91ca-2a5beac6bfc4 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
621f1f70-d18a-4baf-a929-88724179afcc | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
667dd612-ac84-42d9-b97f-8c04b6c2e2b1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
680bccd7-c650-48bb-a443-4dc0671c5854 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
6b714a30-3bd4-4a5b-beb7-4aa4e85b633c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
6ce013c0-8231-4929-b0ca-ad121c5b5cb2 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
6ee4fa0d-2562-4aae-9f07-00203a52bb61 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
715c593d-701e-4002-8281-cbd554deba35 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
80169dad-3e79-49fa-8733-3ba1a0554c11 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
8227b54b-f57f-4ef7-84b9-d18391b0512d | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
874179e7-2c84-454d-b39f-13c9aa9521fb | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
8bbf06fc-02e3-463e-8ee8-a298bd105e3a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
94f93e8f-bfc5-4d7f-8645-6d4d3784b6f7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
9a2ba4de-4644-47cb-bcb5-0c40f6c910a1 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
9a4f98e2-d52e-4218-bc0a-1d6590f91a83 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a00cb210-06e3-421f-b87b-35b22bebf91a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a411ab9b-0f0d-4435-b35a-a75bffb7548e | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a46fa2d5-4ad8-4f18-964a-f6c47856ce0a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a5346598-f0a2-454a-bd58-c8c4484cc9cc | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a691948e-9a3e-4464-abc1-edf2a248e796 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a6d73656-12e9-4681-abe8-0ad1733ddda0 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a75c6235-372d-4ef5-acd8-9402b38bc7d8 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a77e166c-2152-47b1-93c8-d7a97c47bd2a | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a92e6097-1c91-4ce6-b54d-1f3f65a8e68b | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
ae900de9-ff22-4fd3-9141-a073c1bceaf0 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
b0cdb9cb-4328-4681-80f3-6fd185bb8a64 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
b464cdf1-9d79-4cd5-b151-6d6debdba853 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
c2e995c9-327e-4eb4-888e-bc448091041d | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
c3c103ab-d0b7-4694-a228-0d6ec858cf3c | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
c7f42114-e5f2-4636-9471-f99a17b12e6d | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
cde3e0db-8c7c-4f2b-9c75-071ce0e72f3c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
dbfe41a3-d717-4099-a2bb-5a0f0aa28eb0 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
dddaf571-a30b-48dd-9bfc-345a72ac7d1f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
dec80bf3-ee49-4446-a0e4-a62785713791 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e1fdfed8-d81a-4ac2-850c-4c8748bb721c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e366110a-a17d-4d19-b020-4ac22956f496 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e6ac2342-d4dc-4566-9c27-d3aa33a94054 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e8f7ddfa-2f6f-4dd8-9724-073800ecbd1f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
ea81115b-ec4f-49b0-8b79-cc584391367d | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
ecd71f45-465a-4c15-b45c-ab328900bdd2 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f12c1364-2924-44d6-bbff-fdf8c70de16c | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f136a2cb-4126-4ff4-97e9-be365ddb5961 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f569e62f-b536-4656-93c3-4a049b03836a | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f7d6a012-fd71-4055-b6ab-7f5de486e797 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
fac8e6d2-6fd7-4a4d-8eb7-cecbaea24ab7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
fce803bc-6260-47af-ab5b-892e4a32e46f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
0398fe52-2ba3-40f5-baaf-591472bce0de | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0399be6e-35f2-410b-9925-5c644135282f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0d50f5e0-6b86-42ff-a529-0b77f181e8ac | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0f0c18fa-ed86-4758-89c0-d19a7d095d38 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1128dbda-f585-46b5-8643-76ac2cf0d407 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
17999798-87f1-4f99-b1ed-db74f51fb5b0 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
18fa11d8-ab79-45ac-af0e-8283b9222377 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
19739efe-7be1-41e6-8857-11adaea29c4d | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
197fb920-d9b8-4af6-8d44-359d8f30a0f2 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1a8aec85-62d6-49c5-a333-dfd5cad287d3 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1b117939-4685-40c1-b61a-cd9204e4d92a | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1ed6e8bc-7d30-46f3-934e-e8870c76e87b | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
24363318-3afe-4cd7-a5b0-a1b36ae7ffcb | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
26456949-a6fb-4af8-a1ce-169b430c9b9d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
2a8bfdc5-d62d-4526-b19c-c02b5f546988 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
2ac99714-d148-46da-a112-472f40263d5b | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
2d919b1c-9aa7-4490-af40-125efcce7874 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
2e6f2758-0e45-4176-be96-32695d39ce57 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
2ef3a1e6-f89a-4085-a528-da30acc62da6 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
3140b80e-652b-4b93-b08a-302508803a00 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
34266f70-0340-441a-bcf8-10f3994662b4 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
3886ddc4-978e-4636-a374-20e7f080066b | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
415f4615-39a8-4bec-b443-0e8ac73c1bfb | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
4706b5f9-4362-4f9e-a161-72fda9ad1a0d | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
47963164-c2d7-4ad3-93c2-8b2ea740310e | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
52d25e4d-c469-4fec-8fe1-80762dc82227 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
5311c8c5-d4d3-4f79-ab1f-481dcf41bd9c | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
570edb85-f989-48e8-bafb-4c77e474953d | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
57e36233-b8f8-4085-984e-111b358905d7 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
5c4fc335-c8bd-47df-9d9a-25372f9f5c98 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | 2021-11-11 | 2026-11-10 |  | Required to Re-inspect a subset of assets
63f09cb1-6076-48af-9870-5bd5ea1b07ff | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
672dc76e-dc2d-4424-89fb-d5a6de907be7 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
6adfa1cb-43a6-45dc-9c0e-9721bd8447d1 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
6af1ef9b-7f23-401a-bbb3-ffabaf0c6919 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
713a99d7-169c-4c4c-ae37-fa558a197479 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
74bac55c-1eb6-47d5-83c4-0b00cda2400c | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
8c09ced1-900b-40fb-9b43-5153732e8573 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
8fc5ec2a-52e9-4619-af19-55dd0653257d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
97dd48f2-936e-4f67-9290-ffd66636993f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
9935d440-1b9e-4127-8ddc-832fcf6930a3 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
9dd71ebf-c328-45f5-b058-277917ca4169 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
a3a11b38-57c9-4488-963d-2f6f4feafc73 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
a3f0da5f-84a0-4fc2-a292-4250e81f7aab | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
a7d342db-42cf-4886-ad47-460c07bd2e22 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
ae8471ba-1f7d-45e9-a92b-4e72ead8bd7d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | 2021-02-27 | 2026-02-26 |  | Required to Re-inspect a subset of assets
b10a44e0-31e3-4afb-a6e7-be0e9156b789 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
b1b0133d-9113-4b04-9e0f-ee227cab8d04 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
b514cd60-bb09-45c3-8ff1-588f8b6d8191 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
b569d043-9aa1-47ae-a254-853040276277 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
bea4a1a8-d14b-4ac1-9c7c-6610cd1db4a5 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c2a14c40-f9af-4f1f-a412-0f929e414227 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c2e1e764-0581-4996-8e98-cf83d256f982 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c36cb937-9237-4e3a-ad29-fe2dfe0cf2c8 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c481f239-aaff-40f7-8c5c-6095135ede3e | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cb573dd7-8f3e-4b6e-bedd-30c65e707dd9 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cc3a0dda-5157-403e-807a-70550dfd90f9 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cdbe3ec8-7811-4481-aa48-bf62569eb7a8 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cf2407c0-3a11-479d-9dd8-e9c11ecf9df7 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cf7186fb-1763-44a6-9ee6-988cc6ae9297 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
d4ccab76-7a51-49e2-bda4-48d9181e111e | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
d566079e-d3f5-4e65-b35a-e17117275520 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
d63d4bd6-b428-4821-b9c2-fbb11f658695 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
db969c8e-a91d-48ec-b3a6-c1c6e2f20d77 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
e2511eba-b569-4490-b977-fa36b942c62f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | 2021-02-27 | 2026-02-26 |  | Required to Re-inspect a subset of assets
e288d7fa-d33e-4092-91b3-8946db4fd85f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
e30d40b6-98b8-46fc-acc0-8219177903fe | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
e6c5804a-585e-4dbc-94d8-71c18cbaea2f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
f6790f3c-ebf1-419a-9b75-2649d9037cd5 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
f73768b7-aef2-4297-a9b1-ac19bc9dcefc | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
f9d98c21-da5a-481d-9141-b5b3e241c58f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
fba4dd40-87ff-4f89-a805-697d00e74e47 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
ff5b4440-3c62-4ee7-81c4-6da30ff0a8f2 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0020020f-d97d-460d-b0c0-ea27e71dd023 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
016abd50-6525-46c0-b106-a9320b06e650 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
1380528d-05e1-44be-8659-b6c2ac92ebad | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2460bf6f-7b26-4c28-86e5-3fbd858d4616 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
28f87e48-9739-47b5-9f09-9c986492b20b | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
29e0707c-f938-46ce-8de7-b2d115555323 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2a71a7c7-6c6e-4648-aedb-cdf565a1464a | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2b2ec846-041a-4c0a-9223-51c4339e5a04 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2da97822-8553-414d-b81a-e68123316f96 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2e40657b-2672-497e-a88c-7443e289dc0f | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
307454cb-4429-422c-be44-4ecadaad7bdc | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
30fc1958-f9ab-4051-8a32-f2068c2fa5a7 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
359c62bb-0d12-43b0-817c-067e390a1563 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
3c965987-9d9d-473c-87b5-86af61f86806 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
41269246-0aba-4fd3-8c17-8f3e1ccace21 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
41d5985d-c9d5-4adf-84ce-432a63725292 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
45afab05-5428-4de6-ab39-0bccb0fcc0a1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
47064fc4-cf1e-4e77-8e4d-66d79537a47d | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
48736301-da5a-4f47-a2fc-950dfe47430b | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
4ba583d3-8d0b-43d6-80e1-8345f3e1192c | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
4e92bd42-3149-4c89-8703-ceab0a955c16 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
5e72993d-a097-463e-a3e4-a3d321931105 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
681edcbb-e8c2-4781-97b8-a2fb9828edbd | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
6e8aa700-b83b-4699-93b9-ba4444c935ec | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
78247f7a-0352-44d0-8c6a-1c6698d9514c | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
7ea1828b-8371-4ca1-9615-7b1a6ba4325e | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
7ec94654-ca3f-410e-9ac5-13236eaa97d3 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
83b4395d-0dbb-4ee9-9587-fb6a0b0c70f1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
89f1c51f-7d6e-4087-a816-835d893885d8 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
8c17a871-df9c-4003-a610-f7d914dacca0 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
95df34f4-d327-40a4-87e5-72d2c9787603 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
96952dc0-5280-4fb2-b099-f802f86ad70a | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
9e248863-0a53-4a85-b1e4-0c7f4ad8adfc | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
9e8f5b3f-ed38-4423-8365-150d27ce4372 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
a7ed9c43-4d68-484b-a789-82fadfdeb433 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
a9621bf2-8437-4ea5-910f-6db8fd57ef01 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
ab3fa375-8bfc-49c2-87a1-3197fb2f69f7 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
af23feef-c4b6-4a8f-ad12-492cf6b94286 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
b1fe51d8-68e2-4ac2-863e-f9a5efb7affc | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
b3e8d100-9c01-4fca-9e47-25f0395d137b | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
ba110dea-13aa-459d-bb0e-2fd554c8eeb4 | Pole | 2 | Distribution | 2020-07-01 | 2021-07-01 | Level 2 |  | 2021-05-20 | 2022-05-20 |  | Required to Re-inspect a subset of assets
bab110b8-bd28-4fe1-baa5-0777ef860235 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
d0610ec3-31f9-4530-a86b-c0fea594a305 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
d1d8edb0-1c90-4077-9a6d-4f43b53508e1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
d64acf27-22a5-489f-879d-0a59098e6e79 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
d7f3dd59-55b7-4b79-b01f-5bb79e7e22eb | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
dc8303f0-d0a3-429a-9640-eafcec41f31b | Pole | 3 | Distribution | 2020-07-01 | 2020-12-28 | Level 2 |  | 2021-11-12 | 2022-05-11 |  | Required to Re-inspect a subset of assets
e5406709-d765-4f8d-a5aa-478fb8a5ab2e | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
e8f028ec-4cd6-446f-9d9b-0b539cbe100a | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
eef0e9fc-022b-4e13-8f05-c8e31e691174 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
ef19901f-5fdf-41ff-b807-184d9608259d | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
fa3b859b-3769-4728-bb23-1eebf6638dd8 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
fdcbcd51-68a7-4b25-9514-23d414a696b3 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
0345cf23-32d1-456a-bb57-e73e8875776e | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
06cea37c-a8ea-4c08-8951-532495f3a242 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
21ed4afa-bad8-4973-9bff-ed07b02e4c17 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
2c0ac079-7793-43a0-a9bd-77394058e1d8 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
3df0d63c-ef17-4ac3-9e30-2aa2a228b9b1 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
3f22c5e2-1393-4b4d-b6ea-33865ab3fd15 | Pole | 3 | Distribution | 2020-07-02 | 2020-12-29 | Level 2 |  | 2022-02-04 | 2022-08-03 |  | Required to Re-inspect a subset of assets
491889b6-8361-46c7-a2dc-b64ada3a139c | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
53e03fe3-b13f-432e-8e2f-829932937707 | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
60792779-8186-4882-96a1-6ee78756a7df | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
6aa8948b-54fb-4b7e-81f1-74aca9385ea7 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
6ddd0ecc-ba20-43c9-8d2d-b6c6e5b05203 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
7a576c19-8f81-43c4-81b2-777826586b9e | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
809e6db5-a91e-4d4b-ab4b-076127e93aad | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
b73c318c-c739-45dc-95a4-efc087d84edb | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
d9d8b4be-d8eb-456c-802c-f3f3fdce077c | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
e5719e0d-066c-4f55-a501-295b111763c5 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
eb4745b8-05e5-448c-bc9d-9e91520469be | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
002386a8-997d-4cf9-8a5e-75a26e8dcd4e | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
03ab292c-8efe-4c24-9926-42674d382785 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0a720879-1a68-4922-8d53-4eb8cdb25b0a | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0cdcfefa-585e-4411-8005-f3ba4439e79b | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0e83fa6f-3f1b-4a2f-99a5-3e56c06de4d6 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
156216d1-767d-4048-b862-a87db522f3ab | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
24008e5f-3f22-499b-839f-240dc1400bb1 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
476233b1-e400-4667-a56a-b7280ac65ff8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
4f67f863-89b3-4091-9c94-a6cf88fef633 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
50043214-c47a-4379-96dd-ad23350081ce | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
524820f5-7ecc-408c-919d-9f258db1a82c | Pole | 3 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
52ebe1db-c269-4f7a-8371-f92894b3dd9f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
5ac9bf74-6775-4596-b6d1-ece0b5ce2f87 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
5c74527e-37c9-4ad4-88ce-ee7d6f8e3d16 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
6ae4b32a-a0e2-481b-8576-4937f9045bf5 | Pole | 3 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
7023fec6-cd05-40e2-9c67-1cd2548a17e9 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
7047572e-f938-4c47-85ee-7322ab3e06a9 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
7a6d0cea-b451-4549-9cc0-fff0ab5b58e8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
7c68b51a-688a-4057-b5b4-ffdcbfe6deb8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
87c437d6-7418-4019-8f61-abd750ff5749 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
9314ebea-407c-452d-97ed-5a114b37a1cb | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
99b92bed-6a4f-416f-b2d4-aee21c9d603b | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
99fd3dfd-bf33-4ee2-b5b1-17e83bc7d4aa | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
9c1097c4-2bb2-4a10-ae54-f0e97bff5aca | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
a6d53c28-5e67-4a6d-9ccb-dfa957ae13d4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
aaf4fa1b-7adb-4a32-9234-1e7ff0d4c097 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
b444c3a0-9813-40c5-9758-a964b10e1a79 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
bc20f272-e776-4b4c-bfb2-93717e684dc5 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
c5ba3167-d4c5-41a9-8754-240301a8f6fb | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
c68ce4bf-3f28-493f-88be-6786c8af3768 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
c7f95d63-a6ff-40ca-8a07-c9ccdeeb32ed | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
ccf0ec6c-9f33-4d08-a33d-e4ee9ae9e966 | Pole | 3 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
d6d6d4f4-67ca-42b6-b350-c51207a0ab3b | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
d750fa3b-40ca-464b-8b9d-8768d5fc19d7 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | 2021-03-25 | 2026-03-24 |  | Required to Re-inspect a subset of assets
de0b9fb4-8a11-4d17-914b-6d3e0968208f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
e4766b0d-b291-440e-8fdf-2addc537b6f4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
ed52b673-d866-41f9-89bb-847012e7230c | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
eef8868d-258d-4d04-97b1-e24f7ba35ba0 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
ef91043d-64ed-4241-90f7-eb7a661ad63f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
f4cb338e-d902-4a52-bd88-9a84c6f21ff4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
f8d52daa-332b-4eeb-8507-862ab852c93d | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
feab19df-c64f-4911-8a30-58e1f19f5f5d | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0195ff25-8060-4ddc-b000-45da67fe1c56 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
04eaeadf-3804-4277-9e99-99e0e161763c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
0a3729df-a831-48fb-bd8f-5c1f262b5f99 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
1b88f05f-27e8-4cc2-b6fb-c46d46c4d736 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
1d690f02-beea-4463-a7e9-1f5c27367b61 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
23ca360d-b7c9-4408-b14e-abbd08fd7549 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
28f0a912-fa6c-4218-8c24-77bcdb8f5265 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
36fb4d22-997b-4bc5-ada7-87e1b16dce58 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
3b0fdb20-4d4e-4d6a-b4d4-e109a71ccad7 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
4cf14ed9-5d22-4c5d-a9ec-4e0a75642859 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
4e500be7-6821-47ae-9461-9e83af5a70d7 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
4fe3bb93-2e69-4402-bcca-99cc5538064e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
4ff1158b-4d31-4e2b-b2ad-77a685b556c1 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
52f9d909-51f6-4b25-98b8-11a18c482951 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
531eb34b-c6f2-4193-a33f-dbed5a53118e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 2021-03-17 | 2026-03-16 |  | Required to Re-inspect a subset of assets
56a1c32c-4e86-4583-abeb-af61764d2424 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
6059279f-5a46-4e2d-904e-1e86690766ba | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
60f56ba1-b348-4043-ada4-3678fb08c8d0 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
6337d787-14a8-4e05-9eb8-0988212e4c8d | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
663ec697-531d-4437-86ed-8608796a2b73 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
71cb4785-14a8-49ab-af12-e89cd1d9676e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
77b39cd6-fc8a-4702-bd83-e4daa89d1493 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
789b3c8d-05a3-44d1-86e5-648898a061f9 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
78b06658-fec5-4708-b8e9-7834dfda691c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
8aa384e1-ce17-4915-8ac8-1ec9dba17cbc | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
92764730-a935-47cf-8c26-20852a5a66cb | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 2021-02-27 | 2026-02-26 |  | Required to Re-inspect a subset of assets
9bd3f677-d4d9-4d76-94b1-7d2a1574364a | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
9c0abb0b-a348-4999-9343-0b6686df6525 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
a00d5fea-e2a4-42d6-b24a-bd0321b04678 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
ad16868b-a539-40a0-bcb9-c25cfaf67c8f | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
b08acdce-6f5f-4e3d-be94-8f2d8f58a957 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
bb5a472b-ab23-401e-8866-6039d3babc30 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
bc724c11-dfb5-48cd-90d4-c5cfa93d6928 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
c162ec37-2c3d-4639-a0c3-5353b1b667ad | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
c2bb9fc1-7e44-4f8f-9b32-9dd150871ed7 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
c7b625df-ed6b-4b1d-94e8-7c1df3df6d8c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
cd1cc82d-1106-477d-9ce1-d2415fedc10b | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
db584575-0efa-46d9-9fa4-9fd064a1999c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
dd0eee9d-91e3-4089-a583-8bcdca49f43f | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
dd386778-2810-43ef-960c-3afcd4f7e669 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 2021-04-27 | 2026-04-26 |  | Required to Re-inspect a subset of assets
e0d700c0-2d91-47bf-89cc-fddd6f43f41e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
e0e94b8b-ef90-4e09-9e60-89c793e9eaca | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
e94082b3-e375-46da-9330-b270df7ad367 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
f3b7928c-0162-4cec-b886-63e3f8c80c78 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
f558ae7d-6ef1-4d45-96db-a2511b5d0893 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
fff4b774-407a-49dc-985f-1654642809e6 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
040e3070-3fa5-40a0-9b90-33f0581e2852 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
05d73453-5a32-4012-a77c-de379b54be8b | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
104f1808-1b0e-49b6-bcee-b5c028286831 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
21e0c81b-36e8-40d2-b1d0-d8e616cb36d9 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
2fc7720e-2f0b-4f96-9034-b907565be749 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
46d9f392-54e0-4d5a-83ee-ec099a7f0881 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
562335b2-7a72-4bf2-b31b-490945698c89 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | 2021-11-08 | 2026-11-07
62e557c2-ef6e-41d1-bbec-eb0e9f0b96a2 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
728285a9-0039-4f09-bd8f-b5e3baf66d8b | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
79c8bb23-b503-455c-80f0-98d18656e233 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
822dfe7b-feb7-473c-9eb7-ec461bc3f311 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
881e3307-12a1-446a-8f36-2a90f4ef483d | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
885ee9b8-7720-4690-803b-fedda2eb4135 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
97cf3a0a-27aa-4ce5-8970-9818295f806f | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
a3b24d15-6bad-461d-809b-8b4e55389976 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
ad0de100-52a0-45b0-b4c6-ce8968ad0963 | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
b8d9cb64-ffee-48fc-8bd7-394178ff9187 | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
bc0f4971-62e5-453d-8419-1feea26b57a0 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
bd165113-6276-483e-957b-211cda272fec | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
d2399d3f-32bf-4414-a7dd-c34456fe124b | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
dcbbc348-d239-4e74-8eb9-d289498f0d50 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
e64c5aa6-9b57-4be9-ae07-e4734e79edbd | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
ed21d40c-e8e1-477a-b8cd-17538399044e | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
09789e8b-a0a4-451b-ae99-4fdc82a78836 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
0998404c-c5a6-40a5-8f52-f3557ce6b9c6 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
0d59c623-85e0-4a88-81f5-75c003a6efa1 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
136b0b14-4d49-4fb6-b283-9a41eecc867c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
1561b033-ead8-4a21-9f24-2169e8c0ca9c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
162252b0-ea0e-4964-ae08-628bc0d93fd2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
20b61a44-5209-4ce0-b705-5067d2780bfc | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
2e08d494-cec7-4cfd-a681-33309fe959d2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
2fbaf27d-5e82-405f-a1ba-850e6bbe4949 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3099c0f9-3ace-4cae-8478-f4ddd8ff247c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
34ad1da3-c96a-4572-9c54-3c55905940a9 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
350fd8f0-f559-4afe-80d0-8716e19defa5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3785822e-c4e1-454e-8414-9b5bdace0334 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3c0eb500-e11c-493a-9f08-4bb1c84b3562 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3ddffcd8-94a0-4e47-a242-90993eb7afae | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3e12d27f-881f-4efd-8707-42bc669ba974 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
40e4332a-0b32-4532-8018-db31e8239325 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
4537edcf-8a01-4c8c-808d-9e201d34e5e5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
490d302b-80fa-4c9c-9c35-2c8584ef34bf | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
509f1361-6031-43b4-923d-ff8b75fa87ba | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
558e6d42-d66a-41cb-8202-ab9f23615401 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
57c7666d-c431-497a-b51d-a1c9ecacf456 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
5995cc07-d3c3-42d2-9493-28fc9097cf98 | Pole | 2 | Distribution | 2020-07-07 | 2021-07-07 | Level 2
5c3f7a04-ad4c-4dd7-aaf3-c2d0d86848da | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
60dfa80a-ac4e-4da3-ba7d-8fb2f84f4022 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
638f8a87-2f23-4abb-8016-c16a2d31875c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
6590c18c-c624-4014-9a69-6fde521c7d20 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
6650820a-acf2-4374-b578-87596ef5a20f | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
70652582-6429-4343-a700-20d2f65b4cf1 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
75c12d75-f7ab-4d3f-956a-5e83cc171ea6 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
76f68161-f6f7-47e7-b6c4-4b1314042030 | Pole | 2 | Distribution | 2020-07-07 | 2021-07-07 | Level 2 |  | 2021-04-01 | 2022-04-01 |  | Required to Re-inspect a subset of assets
79849a4f-5952-410e-a048-f983b757ed7c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
7a755d73-b3aa-4eef-a717-16664cbf4b66 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
7cf535e8-dbef-45e6-af3d-fb0a4d376f67 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
86d5d62e-0cea-4f00-af76-15aca8c6052e | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
88d655b9-11c2-469d-aa38-a877bf790a8d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
8c2019d3-49f8-4e34-8a5e-43d8f50cf9a5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
8cd19431-121a-4233-9960-dbb3ce26f551 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
90633db6-b0e9-48e9-a451-44a0c0820f6d | Pole | 2 | Distribution | 2020-07-07 | 2021-07-07 | Level 2
945791ae-ff42-4bd2-acd0-a9f043292e06 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
96d8d3f2-57a8-4a90-a89b-5e198f305d84 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
98b76161-a05b-43ed-bd97-60b48975eb76 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
9ab8386b-4f4f-4424-bf6e-201172d3b1a4 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
9b649708-b3de-4368-b345-a4f4571ff944 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
9beab15a-3606-4b07-adde-a707ae3600d3 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
9e17c0a4-319d-48e9-b786-6d85ce7282a5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
a21e92d0-717d-4583-b3ed-6a534a94ccf0 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
a9ab6ab7-ee25-471c-abc0-3cd04d547907 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
ad8cd10f-c662-4538-81bb-56e8bafc3da2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
afdec874-724a-41f5-9749-aa4cbbeca2c0 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b08d2a06-6a63-4186-9662-f3be9d6e0f0d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b4a13217-5857-4480-997a-a7fa3a142f31 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b50dfc88-e6d6-4861-9730-67feea529433 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b8b29138-2ce1-4ce6-b1df-d2c4cdf4b0e8 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b983ea63-2431-4771-a381-96a53ce83e86 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
bb43f43b-84fe-433d-aef7-325e4f26608a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
be79c0fa-1065-4be5-ab0d-09bbf3bcfad4 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
c3adf9c8-7e1e-4719-a2fd-2a452800f245 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
c3eedc2d-ce18-4912-a4ed-56c23a29bbe7 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
c5affcf9-f7d4-4d53-8365-4554100de38d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
cac04a0c-751b-485f-bb86-bec8b74ced2a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
d051843b-0edf-417b-a57c-babceefbdd8a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
d6e6c551-ff75-49d6-bb4b-53adc8f0ee9d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
d8189565-6f54-47a3-96af-37d0e0c8cb1e | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
da631c49-4888-4401-ac49-60e1561e8279 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
db9f0799-2bb9-4f61-a4f8-901221e66b31 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
eeb3e4f7-db32-4187-8127-fba22c230109 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
f5680546-7a1d-479a-bf7e-ee89a155881c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
f900cbb5-a9a3-491d-950d-c438424e3497 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
fb0fd933-8f31-4395-b381-7f9cfd812add | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
01a565ce-279b-4893-804d-ecfdd68e35d9 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
039dab48-7ab6-424e-bd35-878ccccbc01c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
07b47977-02ab-41a6-bab0-a2f5302dccdc | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
07da275e-3375-410f-ad44-e8cf3cf67037 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
0f9b104a-fbf8-45a5-a750-c150da9b58fb | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
183e1851-4f1d-4fad-98ca-65a576de818f | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
20e6df17-1947-495b-bfe9-d46c40724699 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
215da2ca-07b0-4207-a9e4-0633540eda8c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
23a0855f-120f-4e32-9afe-f66bd242b4fe | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
367eb169-e2da-450c-b405-e9da58bd38e3 | Pole | 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
3a4e678a-d238-489b-b7e1-69491d03a693 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
3b33b767-d154-4729-a074-794e34aae61e | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
3d8e0bc9-362f-42f9-8b65-801458a5fa23 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
44402463-686c-49d2-9db5-3750d3c03ac9 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
542f598c-1130-4422-af20-c041b8159ac7 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
5a48fcd4-4e98-48cf-8686-f49a80c17e5a | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
5df62bd9-4ad4-489f-8427-5134de5a3b66 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
625479c4-9bc4-483c-b3c6-675a7c5ccb60 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
62a85437-6942-408c-af20-a47ff7985bbf | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
6aacb92f-84a4-4e71-b7a6-41208188f31f | Pole | 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
72028981-a4fb-4d92-a513-50d4248076cc | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
76aa33cb-ebb5-4819-807d-fdfa3a68363d | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
78a22abb-4ec5-4736-bb66-0014495f0c32 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
84ce554d-2b99-4049-9e09-0a4b8d13d550 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
8658dc2e-4f45-40d4-a6b7-77ab6cb67a16 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
88599f80-4282-4c60-8dfd-b74de6ab0141 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
8d3a2d38-10d6-4d82-94fc-69287e8fcd1b | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
932a79dd-1490-416c-bc1f-322b3541d400 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
a4515193-5a42-4a24-a5d7-6e865d9c9121 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
a510252a-8b76-4c18-8595-89194a2d5827 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
a724e85e-8c36-400d-8c46-6676d5332f1c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
aab536c2-e237-4961-a3d7-12a9b2a3c86b | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
abfed62a-1467-4931-98c1-d1e9bacfdd26 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
b7e626c7-1448-4dd2-8ed3-7465dca1f582 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
bc60ddeb-759e-42a2-9253-3f3f9a8f7ae2 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
be819848-1845-41fe-abda-9795370756e3 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
c316323c-9e77-4d16-bf15-88c3fd626276 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
d0b24701-9db7-483f-ae69-1e34cff4bf30 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
d668026e-9848-4177-a727-0e0b987f8b15 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
eb2ba522-29b7-4ebf-b8d2-4fa162eea7fb | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
0b8a8bcb-4c87-4690-9a2a-ecab003e418b | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
102b8a1c-fbcb-4a53-8060-49b706605ef7 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
1f590e13-c214-437c-af18-0313d881a3e2 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
210ab97b-c5cc-4324-b224-dabf31dcb559 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
28de7189-4749-474b-8420-97a96eeee4ce | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
2de6ca7e-6430-4ac5-95fa-5be86dcb2638 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
2ff9bc63-f610-46a0-b6cb-b210e7c39541 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
330abb75-52a5-46f5-b482-f40c265d7dda | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
3c163a0e-b9cd-42aa-874d-c5fba4680d26 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
4448cb1a-4cb9-4159-9d03-9ec494115634 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
4a8b18bf-13ce-45e8-ae56-e7419af93bca | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
5cfaead7-7dd5-4c16-80b7-58955c44706e | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
67997b7c-f999-4a66-aec3-97263f7d05c8 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
6bdd12d0-4208-4243-ae05-fb08bf9e012e | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
7a46c49a-876f-4b95-aee0-75419a7da8ac | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
7c24b7b7-0d82-4161-82a3-74e7313ea976 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
8d792b1d-3fb7-471a-aecd-0f6ad0190807 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
96f06149-da11-4570-b19d-7c92371687fb | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
98bd97d3-30cd-4b4c-83ea-9e5169b023d8 | Pole | 3 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
a4208c9c-14f8-4057-965c-0432a4afeb94 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
acb4af6f-8d13-4347-bafd-acd60cb4fdc7 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
af560922-81b0-4386-b6c5-6612e85a1565 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
b7f99e6e-1beb-4fa2-b4c8-4538d26fc979 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
ce1e99ef-c521-4194-84ca-b41443e71a7f | Pole | 3 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
d6231e56-5a46-4fe6-95f9-b4fdf518b92f | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
d73736c1-9f8d-4655-bb72-509b6cffc1d3 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
db4bed87-98e1-43fb-ad7e-b9b884c25fdf | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
efc89a8c-3e4f-4a97-9981-3e749ef5f250 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
f797c6d5-623f-420d-bae9-530502569f82 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
029131b4-0785-4c56-a449-d29a9f038cc0 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
13f6c40c-55ff-49a9-8412-c5c1b0b5285f | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
2340128f-e9f6-484f-a290-75a46f458ec5 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
284aba57-8f5a-406e-a1c2-8a5249514420 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
389e10e8-a939-4438-9e46-f5911de6b854 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
4bf086a1-ed82-4503-a500-ce8d481176a2 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
5563500e-5163-41b0-839b-7c3205a5ee2c | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
61980001-95ca-4ff5-90b0-60e39fd588a2 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
65d126ec-8de4-4cdb-82a3-2256b95e3272 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
6fc92763-275d-4223-b5f8-d6dc1fdf00af | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
72aca320-85d9-4a46-85a9-4b5ead644d56 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7a933010-5609-4515-ab08-3a982ae744df | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7c8dc814-d882-4c81-8df4-372dd3c350ef | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7f6c9254-b686-4c48-9886-03ae426df60b | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7fe208ac-aca7-476f-851c-423b6eb09d2d | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
8a6c3ca8-5100-4f28-8bba-87845bec960d | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
94670d55-bb6c-4b2b-90a9-60cfa5b4fa0f | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a0abe18e-3705-47df-bf18-b480954c0e2d | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a1cce40d-56c2-42eb-8d3b-3f2bab0ef617 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a1f9a0a2-e669-4fb4-a817-a2d105e65044 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a5013f09-cb48-4714-a19b-6f644ec84c6a | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ac4820ca-6f3e-40ae-9e17-a637c7718ee8 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ae881877-ae5b-4df7-be28-3b08c4886ce6 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
af3fb385-e147-4899-804c-024c8a1f6832 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
b3a1be52-e478-45c8-be12-5601f631de34 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
bbd149d4-15a8-47c6-b462-40fa38bfd062 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
c1d52933-9662-4b22-b58f-10bd7053c57d | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
c98f5eb4-afcd-4b07-919d-5ea45dfd8fd4 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ce0a14a5-f0d3-4ee5-899b-d6b48a1e7b67 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
d3d3d447-9263-4666-ba09-cb8f765113c4 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ec82d171-f80f-4c41-9fd5-3e15894b2942 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
f193becc-25b2-4289-a18a-17e6aaa3eff7 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
fb871fe2-feb6-4397-a61b-be3cd4ff418b | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ffeeca76-70f8-491f-add1-5b6698252e01 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
00be15b4-c2e4-490f-b960-2750ddc77373 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
02ab1997-8c82-4fb2-b9a9-5a60b1cacb34 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
115df9f9-1924-4a29-863e-6f73d130edfc | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
1d92fff8-9a0e-4add-a7b8-4a3d8cbef31c | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
217869cb-f684-418c-9654-6378bf3dbddd | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
2e684ee6-cb95-4c8e-87f9-6d9ae3c5f8ba | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
2f06ca57-5ba2-437e-a1a7-843137e805ca | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
35bb34a8-195d-4769-8f1c-5482c2cc5f93 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | 2021-03-23 | 2026-03-22
56873713-bee0-42aa-bdd0-67301e8755f6 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
62d22d83-e2c3-4cf6-bf1a-714d8711b0e8 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
63c5c14f-7b73-4783-9033-a0d6afd485c7 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
64d91c91-f726-45c3-998e-ca9c2ecdc5dd | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
68dbe3cf-51a5-4a8b-a69b-1470441af42f | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
749c4458-f0ef-4a06-a7fc-a81f415b9e72 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
74ad17b2-94fa-484a-a23e-10219704ab89 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
75253ccb-161f-4d9e-9845-9208899056a5 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
759d26e9-b485-45ea-8923-4ba5baf16e4d | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
77b88be4-3b3b-49a5-badf-ad716029b010 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | 2021-03-23 | 2026-03-22
957def5e-9283-4ab8-92eb-474b7d9ae653 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
9a69eced-85c0-4013-98bf-0c1090de5121 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
a73d38f1-8039-4ec7-9abd-0697fd19651d | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
b0ceec1e-d446-42bc-96f1-b6eadaf6378e | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
cbaa88d1-e54f-4660-8061-3ef6e179edca | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
cd1090b9-c0f3-47a0-9d79-3f4123ffa402 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
d250ea03-9601-41ad-98d7-2d284e3247f2 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | 2021-04-02 | 2026-04-01
e0940932-bb69-4de1-8219-5c8516485cc9 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
e4defeb2-fd3c-462d-be4f-e1e992aa0946 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
06cc3d5d-da4f-4a70-b401-3333bdf816b9 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
06e44772-34cf-4fd9-989e-464b1e9159cd | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
076acbaa-b9cb-4d2a-9226-fee4160a29a3 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
0a814c71-7063-4711-a211-909eac49f263 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
0d91ef75-398b-4670-9fa1-3d7f4981fd1a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
0f9bce5d-8ce8-4055-8a8d-6d20c3d800fb | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
1be2113f-541a-4e01-ac94-5a027d03f037 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
21682c7a-6c77-4a8f-8a4b-9e78f891f8e7 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
218753f8-caa7-484b-a94f-0529f31e3cbc | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
25ac6250-68ad-4763-bf9b-560bf3fc0fe0 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
2655e768-b7c7-41ee-80a4-8027c0034c89 | Pole | 2 | Distribution | 2020-07-13 | 2021-07-13 | Level 2
2862d31c-06ee-4836-a127-d2069447bb12 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
2b86baea-671c-4918-8e06-82f91568a851 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
2c2a02b8-76da-41af-90e7-3fb1e881a826 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
2d8c8f16-a95a-4956-ba3e-6f8fedc6772a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
3741baac-aab6-4a7f-b033-a669bfe35805 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
4af32f74-290c-4e46-bfc7-38f1d2506652 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
58b564cb-8b9c-465d-8381-4d22feae2362 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
5951d750-6a4b-4c83-8e42-b087ce5dfffd | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
60d7a4b0-309c-4959-97a8-c8f8eee53299 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
61726dab-05cf-4d18-a83c-63985a3a274f | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
6b255edd-ed25-4211-a360-fd29bb6523a9 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
6de9c915-8e96-4ca8-a40c-8c1e4ae75b86 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
7946d755-6bec-41f1-a796-e5241094fd57 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
81c50eca-4bb0-49a7-9aff-c40b70a659f5 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
85e50f89-6285-492b-aa29-10b3640a6c70 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
8a9cb10a-a529-483f-bb27-5ba21e1b394e | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
8e8b354f-a8c1-4f66-be8d-84a0f54eacec | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
975dd9b4-3e59-45f3-896e-f2caee795652 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
a2cadece-c727-442b-b8e9-b3c83b0d7ad5 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
a383d047-e090-4873-99a5-63f9e264dbfd | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
a7647d6e-bd39-456a-8992-4e46ef6ad01c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
a7f17cd6-37ec-41fc-bf48-3a8d1714e72a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
aa09c30e-0565-46e3-aa35-6aaadf6c5a36 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
ab7e51a4-7b28-4a86-9bcc-c2907a0371fc | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
ad1b880b-50eb-4073-8e89-34c2f78a37c6 | Pole | 2 | Distribution | 2020-07-13 | 2021-07-13 | Level 2
aebbad7c-8d73-4286-bab2-fe126e229fa2 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
b0fb093e-b5aa-4bcf-b75a-1856e6b6ff28 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
ba1f1c0c-10cd-4dc2-bf79-f952bb78cc2b | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bad09e72-aaf4-45ef-bea1-5c1458b3e263 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bc6aea75-f002-4862-9b31-a57090c5114a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bca15910-3fe2-4a81-bb56-904406319f9d | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bdf395ad-2726-4c91-b341-2023c4ddafa7 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bfe33634-60fd-429b-bc08-9962ff00094a | Pole | 0 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c348571e-90f1-4b22-84ca-21f5a0de7980 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c63a44b0-0588-4c9b-adaf-b97da5b8f899 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c931e7b2-c5c8-4423-9a35-3da57752328c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c9bd8a48-26e8-4cf1-a77d-86a00dcbd801 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
cecb391b-1bf1-4c0c-a3f4-7ae03cbcde9f | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
cef367a7-b2c9-4ad5-8f80-121802ecda91 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
d769ea51-2771-420b-97e4-c7ce399a863c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
d972de19-acee-4ab8-bd1f-fbde550d9a65 | Pole | 0 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
daac018e-61ae-483a-9de5-7cfbc9df89da | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
e2a9d5d3-bbcc-4546-851d-9bc70f285421 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
eb1b8ca4-e2e9-41f7-a91f-7881a47d0272 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
f668d65b-a29d-400b-b075-24f26c06c982 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
fc7b7975-62c7-4fe9-b9ff-dd6296f2f82a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
fc9db498-54ea-4e27-8b4f-20df72a77a84 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
02deb27f-16e7-426a-af51-5574090f54c2 | Pole | 2 | Distribution | 2020-07-14 | 2021-07-14 | Level 2
03db0ec4-4589-4769-b418-ab0ad6033bfd | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
05fd0b6a-3773-4770-8f92-87418593f985 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
0951fe77-6d9d-435d-8a92-a65818b547ac | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
0b2408bb-c402-4e00-b0e3-1e87406bedc1 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
1e238023-4bb0-4b50-b19d-b866493a9284 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
2045bdbe-cfce-4c5b-a2e4-d6c5e6a15783 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
23888309-b7e8-4172-a3fc-bc879153c6a5 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
24645ac8-7a67-40c7-b07f-e2beacfdcf85 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
278b1280-99c0-4d0d-b5a0-20d34567cc9f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
3102b1bc-61ea-43df-b1ee-d56aabdcaad4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
34e061cc-4e21-4fae-a89d-42b58814c0c7 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
35e8f7a6-252b-4da9-8882-c6b0a97da0b8 | Pole | 0 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
38e20666-31a2-41fe-a59c-e59f1bcf4710 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
39b54d10-77d6-42d1-84e3-a7e0975182d3 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | 2021-03-23 | 2026-03-22
3a663fab-ccab-43b3-9855-436f204b5456 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
41b6bbbe-86fd-4427-82e1-3ee795c0b829 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
43f29f6f-cad7-4402-b015-65a3bd2faf7f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
4418ad78-a931-4a91-81b6-5edf804a7ad7 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
443e5d5e-531d-42b0-8d74-f81076661a30 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
4fe94855-cfc3-4de5-a3f5-83c032f3a44f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
51baa0a9-1e17-4c2c-a161-3b4cf2fea538 | Pole | 3 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
5b3e361a-4d62-498c-bc8c-56c9572b50e6 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
5cf8556c-efac-4258-b13a-d3c8290edd88 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
5de3af97-792e-4441-9d67-ed157497ce0f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
6c51d5cd-e64d-4d3e-a967-e5f3d2209bfb | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
6dbbedd8-1c60-4d41-a215-3dfeedc1bc7a | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
6f16aa83-0e34-496a-b063-5d5de5da5dd4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
8b2b26ef-401e-4cca-a480-d7680e9e38b8 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
956c84f9-db01-4958-a608-fe93cb8dfdba | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
95971189-7f86-45ac-8418-103c47255113 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
983178a7-959a-4356-8a2e-889ffc491e28 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
9afb25a7-8e56-4334-911d-d028ee55accf | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
9c57eafa-c083-4bb7-a16d-a4c1a67f3ed5 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
9fc52370-645f-4da4-b583-0fd490f89469 | Pole | 3 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
a03bbac5-6bfc-438c-b8c2-31c0c054bed2 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
a9c25284-649c-44e3-90a6-eaae94b995e4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
aa3e63b0-40f6-432b-82c8-42e7e25d9926 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
ab3c81f6-75d3-4b0c-9229-3fd4528ef3de | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
afdf6967-245c-4d1d-b770-6592348bf19d | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
b6ba2138-f206-4422-9413-18969e71f6cc | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
b7be3051-26f3-4e9a-8ccb-2fa19c685529 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
bd1dcf2c-1154-4361-9706-667c0f14e630 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
c78c1a41-acd4-4896-b17c-e13250784c85 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
c880847e-38b9-4790-9b1d-d71d6c16cc5f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
cf3a3473-814f-4f90-b63e-61d09e46ab87 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
d0765955-c15c-47ac-807e-d6b9b3402339 | Pole | 0 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
d39c399e-753b-437b-9d0e-d3dc6be72dfd | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
dc8e934e-8a61-4ed1-8af5-71176eb2398a | Pole | 2 | Distribution | 2020-07-14 | 2021-07-14 | Level 2
dd0e9a46-385c-4eea-b150-e168f221abb1 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
dea1d9ad-92bf-4f30-9cd5-add90bf97b9f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
e22a1881-757c-469f-8094-15e41ebf0ec5 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
e369b04e-76dd-42fc-adf6-4973cd112cbf | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
e9e1902b-54ad-4740-9b7a-bd4ea61141e0 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
ea5e7a63-0ef1-4bfd-ba9f-02db6bfc5e19 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
ed6155ca-65c4-449a-a7f5-0d9fe180de37 | Pole | 3 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
ee45b538-1334-4604-8735-08f265c50232 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | 2022-02-24 | 2027-02-23 |  | Required to Re-inspect a subset of assets
f32a3838-ac6f-4d72-b52e-0d27cb592ee6 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
f6c6ac34-65f3-49f7-9e10-7b7fcba18f2b | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
fdec1f1b-9296-465d-b4ba-c755a8a41b2c | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
003a1b8e-3dd1-4fd5-b7e1-9d1aad092aca | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
056e4ce3-5902-4996-a68d-6f7306ec5bd6 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
168daa7d-74eb-416e-b6b9-e22d5380404b | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
18577d8c-2af4-4625-97c8-c80a2b7bf16f | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
1f4b6be9-8e76-47f0-9b37-1893b79a5061 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
21913b3f-17c6-4042-b66d-43882c9c7356 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
21e3840b-9bd3-4923-a030-adb3201fcd70 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
25c8ab34-c4d1-4906-a0bc-7c28476aa6c8 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
2ecd2313-5ce0-4fb1-8d43-7a55265fb8f4 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
379fa490-e978-4700-8702-6e31261175c2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
38da69a1-062c-406d-92d1-a4bac2960717 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3a12d4cf-64f5-4eb4-8288-b822bc786964 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3a460b97-8a06-48f0-ac28-901d3920a027 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3d87b62e-86b6-4e3f-a187-ee47eb6046e5 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3f56cc60-3519-486a-80ea-feda0f55f465 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
4a3d8b56-c88a-40fd-a4fb-0d1fc8fef922 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | 2021-11-19 | 2026-11-18 |  | Required to Re-inspect a subset of assets
4f789622-6ee9-4c56-b18f-207894de2d0c | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
57afcd7d-acd1-4dbd-b108-a8362e2028b2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
591c2e28-1e91-49c3-b8bc-b46ccecb7668 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
5b2459c9-0c84-490f-98be-a72b3270cd73 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
5c9af004-5123-43b5-8fd4-e18472a598d3 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
5d9497f4-6d9d-491a-9b5a-91345640269a | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
5e925c60-5d1f-4d6b-8867-1a0547c0b353 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
5f7f8958-1b3e-4305-9a49-0e5e567cea1d | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
619319f3-bfa7-405b-a275-f754ef915169 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6202d35c-54e3-412f-aa65-03d4cfb85cca | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
63cca026-dbba-4693-a621-e9677737699f | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
64f88342-f190-42eb-9149-603605a5a436 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
66bdfca1-8808-4a2c-a7ba-5b2832c5b813 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6adefe5e-cae0-4f41-9fb3-9adb0c64eced | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6bcc5a1d-2d2d-4637-b413-681f433cd6b2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6d511096-17b0-4c19-b602-da8243c37e94 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
714ea2a0-d411-4222-921d-4e8d615a1bc1 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
806381ee-a00c-47aa-8268-1f1026f06f87 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
859f4d1c-a87f-4bee-be47-aa2788edf1a8 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
863d578d-efb3-46da-b376-6cfa0fd284af | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
88255f82-12a8-4308-88c5-d7b40ccc7629 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
9011ec9a-91ef-45cb-9b94-350e82bee796 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
920727ca-5b4d-4f80-a623-35b6620ede24 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
940a890a-48db-4f3f-943f-e12b46eb80ee | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
96b6413c-ce2f-45c6-b43d-6535e75f6ebe | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
96ec2302-57bf-43c6-a0e3-2637aa48559e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
99cb0f3b-95e7-4fa7-a3ef-f7c9eb39d343 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
9a1d1c93-c4cb-4951-9c76-c07af4d969d2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
9ab184e5-3702-456d-ad97-f433c74128fc | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
a1486fe0-ace6-46a2-8db2-de8c1509f023 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
a6fe9675-0109-4adc-b758-352813f7f606 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
aba16b00-80bd-4bf6-92de-81f429fd6ca3 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
ada5501c-d455-4a1c-950f-78e9ded26120 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
ae59537b-6c67-470f-91f7-87587e9c8065 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
af388937-88e5-4648-9cb5-e9d7e8da5bfc | Pole | 2 | Distribution | 2020-07-15 | 2021-07-15 | Level 2 |  | 2022-02-22 | 2023-02-22 |  | Required to Re-inspect a subset of assets
b257a734-e34b-4568-aee1-4d762fbe0c91 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
b358ef18-8ea2-4482-a3ca-cdcea0fd882e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
b434b3ee-14f5-40ff-84e9-aa0ea7bda7df | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
b69fabbf-d4aa-4064-ac78-f83b67e90db4 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
bab58fd8-ab16-4c02-8259-c05aca64b1a1 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
bce8c412-fd43-4933-8ed1-69d05ead5094 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
c0ccf71b-10b0-4434-bfc1-82e1caf7778f | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
c1ef1f28-9135-4034-9d09-063294a5483b | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
c2fe30d7-b47a-49f7-b525-52124b92718e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
cbddcb84-76b8-4d83-a423-78700957370a | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
d59c5e89-d456-4dbf-856f-95f32b046148 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
d636004f-0896-40e0-9c91-6f2d649c38e6 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
e023329f-8498-4245-93b0-afa35662413a | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
e3accea2-23a8-4845-a1c7-d1b985f344a7 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
e6db48f8-888b-4340-b755-d814f47fa8f5 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
f1d7c57e-9957-423e-bee7-de69da3877bd | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
f6201cc8-5008-4a14-a9f2-9dce3da63b33 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | 2021-12-03 | 2026-12-02 |  | Required to Re-inspect a subset of assets
f9df9a55-39c9-4d6c-bd88-503f1d4b58c2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
fdd79a73-2537-4e9c-a915-7d156c10b1da | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
0237034f-f68f-4caa-b5b5-1b3d4449a72e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
02b28d78-14c2-4ba0-984b-b018d0dd3e38 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
0334c31c-299a-4b5f-b805-f2326f4f7220 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
0a5845ba-2ff6-4e75-b4a7-ffd5dd6e5d38 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
0b04a3e1-67d8-4e0c-a93e-fc5f43765948 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
15fdde60-0a4f-42b8-b934-489d6e8121af | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
168eceb0-93c6-45dc-b560-0396c5ff2b6f | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
18c3fff6-a0bd-4099-9727-456d63de6e14 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
1b40114b-b171-432d-876f-01a4c20913ab | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
1f114070-f894-42c6-8b01-a5d4632aaccb | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
23114e8c-c780-4e99-a633-f9061d27afb2 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
24f5fbb3-61bd-4333-8080-e95ee5828b6c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
2928656e-8f23-47e3-82d7-bc5f867d6533 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
3a9dc097-e4f2-4859-9c9a-8814593ccb8a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
3d872ec7-743e-44ab-93f6-d71036cff90a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
3e22ec8e-395a-4e2e-a805-aaa0623c242a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
3ffe566c-7959-4d01-b6fe-08dd49586921 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | 2021-04-01 | 2026-03-31 |  | Required to Re-inspect a subset of assets
44eed2ea-b533-472a-8dd1-e88390340573 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
4567128c-ff18-472d-89d4-92d0d7721df0 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
456a1083-52b3-4d34-96d0-6a9809ddcc15 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
482d19a2-4a63-4692-b1ea-b97df1d84a20 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
4ca456d0-8d09-4503-abcf-671eee9c3bfc | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
4d3fe422-2c5f-47c1-99db-8aa5c1f0d789 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
5207ad74-f452-427b-840c-4076253231fa | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
55a2bbd2-728d-4e0c-8dc0-1de2f7ff7e6c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
5d4c9934-081a-4483-a6d5-7c2c0b2bae25 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
5e1d043f-b4ad-427b-beff-aa7026b36ff7 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
61c93b86-24f7-46ea-be52-b2a36942afef | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
6504e2ae-260e-4814-af61-51052ed75d76 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
6ba35320-b539-45dd-8812-51f43f0c4703 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
7008094e-d8c1-4a57-9d98-9a1da282cd0b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
7146218f-7a7f-4717-9125-16d634eb6ad9 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
74629c3c-9de9-42ef-9865-9e1e4cbccb7d | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
74f5eac6-b938-47de-9331-74315f348238 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
77bff4ba-7e52-4065-8efe-3139cd48cb3e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
78f38334-8eb0-4a05-954e-34bf4f9c2d5b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
80207ad2-8e9a-4226-8076-c0529428f921 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
8b402724-3a2e-4d75-9544-a537ed05743e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
90038b2c-00fb-4447-9f8c-adf4bf7f333a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
a6cbd979-8acd-40b8-b26d-154669f8795c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
a6d4657f-4e1e-4fe7-96d8-619b5959aa0a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
a9f50b8c-543b-4c11-85bb-f384c1f33024 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
aa3bc441-8508-422e-adac-46469523cc1e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
b7eac2fd-45fd-4e75-9b14-086353456a7b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
c06d3336-ea87-4d00-b924-c66bdc5c197e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
c4eb0b91-8342-42d1-be16-99922593ccc3 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | 2021-03-31 | 2026-03-30
ce2a0f74-0a4f-403a-b434-cf8b74ffa268 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
cf8753c5-d61c-4d35-a7f8-ff6b4ece8324 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
d0bb3155-c65b-4a5a-a2e3-62b8af6e2f9e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
d3d24e91-b9a0-4161-b809-bb708c53b175 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
e5a1c66f-16f4-4644-aac5-fc2f6a0f0fdf | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
e9118d0a-4962-4e52-b34e-f1261fe6ffba | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
ec8f1c88-ca51-4c18-b26b-b985a8ea9e09 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
efe1b942-82e5-408f-bfb3-a4852dbe45e3 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
fc87c65f-3146-4f17-beaa-5f90a8cffd09 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
ff6dd662-2437-447d-9110-4595bc3fe6ad | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
01f717d1-7308-41ee-86a4-940501af91f9 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
03140f0e-abad-43f5-a397-984bc2f990be | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
05ed8aa0-414b-4e85-a91e-6f499ebc13c5 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
0dc9c97f-7a17-4bad-a8e8-5f452181e982 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
0f5a4247-7f07-4c99-9ba4-4813ae448809 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
128f3638-a54b-434c-901c-a4e3e037e621 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
12b002c6-86c3-46e5-ae29-fb22f34d2f94 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
167b91ed-1f3c-4519-95de-ee4a519c2963 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
1c3e7cff-0c2a-47b4-8f03-7556f7ca60bb | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
241ba7fa-c720-4591-986c-d3b18dc938f9 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
24783cfb-5044-4bff-9a6b-281582e9c1e4 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
295657c2-f3dd-48e6-9077-2b409e2394a7 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
344583d1-f707-4ff7-b50c-db6c291a323e | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
3f538d4a-ec5a-469d-9ef0-fa0a6260a2f9 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
4665acdc-3bcb-4e89-82ab-e9d7709c9b9d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
47575fa9-54ad-429b-9d93-235cc2d8c578 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | 2021-04-05 | 2022-04-05 |  | Required to Re-inspect a subset of assets
4815b3e9-76d4-40cd-b715-ab9e63a62be4 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
4dff9202-a97c-48da-9870-9744cbe7b268 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | 2022-06-22 | 2023-06-22 |  | Required to Re-inspect a subset of assets
59c11797-c686-4198-98a8-360f1a092c54 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
5ca68509-e990-44c1-bf0a-09ff47d10245 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
62db877e-3f07-4980-b74b-2bcb506a199d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
6afd861e-c4e9-4b30-a99a-c568fdcf5997 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
6c7b3c46-b353-41af-aa73-64681216f6ca | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
6db3f49a-4e61-405e-adda-5826b5597f62 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
6f2802bb-c03f-460c-8737-2d1e1d2e70f5 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
6f8b5209-cdcb-4711-8a9e-7d62f74c6144 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
70a0627f-ab7c-453f-8fcb-484b435c3452 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
7b29683b-3f7f-4d96-9805-fcedfbc0cb0d | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
7c4db3d1-1106-4899-a4eb-5377de5241e0 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
837120c3-17f1-402a-9592-8997d15f9461 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | 2021-04-24 | 2026-04-23 |  | Required to Re-inspect a subset of assets
8e5e0aff-b933-4d89-a1db-64254aa84619 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
926a72c5-58d0-4523-938a-7eb5f1b78a8d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
92b50663-df2b-4ade-83f9-e6e8e754ec97 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
93609343-806f-4598-b67f-1eaa9784a017 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
93b03910-1519-4d79-bcd9-a5a6578a8a12 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
96dee2f0-7179-49de-bb4c-d9be812d50f3 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
9737481e-398a-4ed9-9e07-0416dd74317b | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
a05a06e1-9d4f-44f8-a4da-d7975a901ec0 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
a347afaa-7807-49d3-aeb6-95c2ba75fa90 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
aa630e89-aa2c-4391-84f1-97c61e7d3d82 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
abf4326a-1ccd-4eea-9968-3990dfe656ac | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
aed19e99-b51b-4af6-8e53-2cdf13a5a609 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
b71347e2-5250-4981-bbcb-38ae685dc42d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
b79e1b2a-2968-451d-9f3a-7027f977d4b6 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
b95397ff-1bff-4008-b171-68cb2bd58e68 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
bad4e9da-5b75-43a8-95aa-b2c82050c272 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
c2fcf20b-4971-409e-8131-dd32cc5b82c7 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
d752e5ab-64bf-4cd9-8e3a-fd4624510d79 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | 2022-03-08 | 2027-03-07 |  | Required to Re-inspect a subset of assets
db932bb5-8bb9-4d90-80b3-855174819c6a | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
e1754114-6a89-46c9-a307-b47eab8306f4 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
e6a7a95b-313c-468b-93dc-fa7042ace9ff | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
ec65114b-27f6-4e39-b7f9-03bb08b23d8f | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
ed6a1a2d-12dc-4e89-9616-aa77478753de | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
f833f559-06cd-4272-821e-21572ce4406e | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
f9220b3c-33c9-4657-b286-389740b83b9b | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
fc7e833c-1e71-41dc-a1b8-b03bbefe6699 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
fcf3f390-39f3-435e-ab90-25c3ca725889 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
ff8c77ad-a4b7-4cca-a85b-0e341bde2859 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
11908b5f-0fde-4dba-bfd3-92ed8e4a3545 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
178e76ca-3f65-4172-92bc-c62336d7bcb6 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
24006ed8-116a-44d0-abcf-0ab4199f42f3 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
55f7fcbc-abba-4161-878b-35b0ebefbbdf | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
60bcc842-a224-43e2-9dd6-e1ce849175b7 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
6a2e5370-0f7a-4fe7-9e57-b33c403d3ef3 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
6bc63adf-03d4-4b31-a0a9-bb5f638750bc | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
812efdb0-06a6-4eea-8a0f-0e2c563a504d | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
84c1ff77-3191-471a-a3a8-57f29fd2a95f | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
87aa3d4c-0fb2-4fba-9072-6727f95cc351 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
8e116f2c-86dc-495b-b264-eb6b074fd4c0 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
9c401bfb-2322-4c76-833a-fa11e6204837 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
bc093c8c-ecf9-4a3a-9bf3-b45cd6bea5c5 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
ceafb374-b59e-4595-91c6-2de7a8ee74de | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
e1f35570-51cc-4f8e-97a9-f0a32d73d765 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
e7c16dd1-9c91-4812-972f-7c1bcb5708e5 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
e7ef003c-d2f5-4286-b943-78fb99c2f935 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
f6e09d6b-a53a-4261-a4a3-d46456c8e254 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
02c80ff2-581b-413c-9853-cf1af17a98ff | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
057a7f4d-a73a-48a6-85a0-aade082bc31d | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2021-04-17 | 2026-04-16 |  | Required to Re-inspect a subset of assets
144f0b17-79cf-477a-9f3f-afcd972a364d | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
19268f5c-dfbf-437c-b14d-e8ca4d8d5a2b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
2311241d-3d0d-459b-ba7b-c8de086d8219 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
2804356c-9fe4-4a49-bc1f-17583af14fef | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2022-06-25 | 2027-06-24 |  | Required to Re-inspect a subset of assets
30866adf-2311-4c6c-9ce0-050f651409cc | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
391df015-7321-4906-ac5b-eebc15f4ecb9 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
4787aa03-530b-4213-beba-bafc340fa18e | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
5161549c-315a-4bd9-8be8-667f5aed786b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2021-03-23 | 2026-03-22
5add4b6d-f3ee-414c-b0e3-422de2afdb23 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
6417255d-899b-4456-b3c6-fa37231f5386 | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
753f3bd2-af43-43fb-bf0b-b6c8b8fd5148 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
77e45e00-1ce0-4099-a518-3547de7d62e3 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
79fa3002-b692-404f-9b00-461e4fcdfeee | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
7d015a14-edcc-4358-bfdf-d436eeebfc64 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
81f2ec27-6401-4940-8c63-63105b64f621 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2021-03-23 | 2026-03-22
821cc4d9-f38f-4df0-b367-b22134e51c1e | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
8509fa78-d222-4e74-aa72-1846f285b24d | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
89b0920d-cab1-4c19-8cc6-7ae03e043bc5 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
8a484f29-fff7-4857-9089-2654b7eba806 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a3098122-297e-492c-8b3f-4ec78db277f4 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a3e0fae0-27bc-4339-b082-c43b5de9e03f | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a8f3d770-dbeb-4f5d-b8ca-73c13e909c0c | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a92bbaf3-b018-434b-9c0c-3a57327715d9 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a962400c-fd23-4609-a5a7-4ae59a61c4e1 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
ac043725-2f27-47fa-99d9-f1ca294dfdf1 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
b21923de-223f-49b6-8122-51a19ce0791f | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
b8152516-07b1-4a49-824d-f581edeb537c | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
b816f01f-cdb6-47bb-af95-1d24dfa3e796 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
c451203f-0202-4240-af51-175eba5a674b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2022-03-07 | 2027-03-06 |  | Required to Re-inspect a subset of assets
c4c63535-fa10-4603-9374-be4065b1f623 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
c8d66303-c9f2-4072-b3d7-e34ec79cb1fa | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
cda540b7-d8d5-4951-afb6-c6946828ff96 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
d00805be-e237-4d7d-b3a4-b11fe00f07ba | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
d8179e93-de5f-413b-b66a-5b2a5f6461fa | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
d8a8f95a-5387-4e46-b565-124a697f9272 | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
efbb483a-158f-49bb-85bf-29a970c0febe | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
eff81703-4ca8-40a2-b1b7-eb2e937d8a58 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
f4593b9f-06de-4c7b-afd0-6b9df836ec22 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
f464f476-f015-4750-b8d9-a98dd5b6c26f | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
fb2ccd4c-2017-44d2-87e7-ae25026ec653 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
0196a5f7-0d34-4377-80fb-e8e04e65c909 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
04669731-239f-46c8-8fa5-f487c461a6f1 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
06ae4613-be32-4a1e-b034-6e1b01532978 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
06e02a1a-8240-44e0-a277-b80eac4c6ff4 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
09c4463e-b973-4922-96e1-23d50a3320a8 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
17ed0436-cc43-45c9-bc37-3459a1b590b4 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
196bc163-a8b6-4590-b677-4f85b86ff3a6 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
28ddd9e1-2095-4504-a177-83922d788c04 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
290bf067-f873-4001-aa45-bc06dee2ade8 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
29647e95-75cb-4184-a4cc-882ed1f91a5d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
2a28e0ca-8af6-4972-a0e6-028beafc7f84 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
2ca30f9c-44c2-4b1f-819b-f0331d5f1d5e | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
30b87931-03c0-4850-b683-2f30d7609a4f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
33d9875a-60a1-4e58-a02b-31f940c356d8 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
35fe3b8a-8969-4d06-8b13-bd1f63a3781f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
3a5f7a23-7bc9-450a-a5f6-d8537cec5340 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
4305418b-d31a-4981-875c-5c025b4e9657 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
46936969-c8fb-4c15-b6e8-470a48a7e18d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
4759da8a-a9c9-4e93-b291-39abf7b5dd55 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
4b217c92-9fd5-4cf8-b6c7-3a1606ff6dd1 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
596c30ac-3828-40db-a384-247fc8298fca | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
5ad2e8a0-37a4-49aa-aecc-3e80de2e686f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
611090df-9c8a-41d2-ae6f-82029f640a35 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
626ebcdd-4704-4010-a8f2-076f04d2b05a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
6455412b-1182-4628-a028-ef272e21018a | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
66104dae-0add-4d33-859b-fe7274c390f7 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
69fd2fe0-51d9-4fbe-ba2c-ba81f969327f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
6b3c1700-406a-4410-9d58-bf50e1e2e85a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
6c92aeeb-ea13-475d-b2dd-56b4dcceff1e | Pole | 2 | Distribution | 2020-07-20 | 2021-07-20 | Level 2 |  | 2022-03-31 | 2023-03-31 |  | Required to Re-inspect a subset of assets
6e98f160-b555-446a-a0e7-f574f5107c40 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | 2022-02-19 | 2027-02-18 |  | Required to Re-inspect a subset of assets
71c1ee50-32ad-4cad-814c-ae3fc82b0b89 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | 2022-01-12 | 2027-01-11 |  | Required to Re-inspect a subset of assets
7229fb24-2a3b-4ec6-a7ae-292bb838bea2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
73a73861-daa7-4c3f-a14c-58fbfb56a8b4 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
7931707b-99c7-4120-8ed0-e097149de49d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
816cb613-0007-4008-b5cf-dbd15e40c22c | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
821c8440-dacc-4240-bd53-fd8c6b6d24cd | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
85b474a4-0499-48ba-ab38-ffcfd2a4dfe2 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
85db31c4-72df-4cf5-ad74-8cb2c82e946b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
94464cff-e062-4d8f-9307-fe4397e055aa | Pole | 2 | Distribution | 2020-07-20 | 2021-07-20 | Level 2 |  | 2021-04-17 | 2022-04-17 |  | Required to Re-inspect a subset of assets
9564ef0a-02a7-4c72-9c69-ed3d50f1ac4b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9612ab60-195d-4464-87fa-f77f2c8ff299 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9cb15299-16b9-4f1b-90bf-330239be398b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9e52205a-a613-47de-a1e7-5457af2c7402 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
a14c43db-e9ff-4934-aa72-3c03c7c3482a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
a86888b6-6692-4aca-9343-84360627b78e | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
ab2da9cb-b40a-47b1-a72e-ef95d3c05cb7 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
ac64b5fa-a91f-4da2-9e16-925145b53b16 | Pole | 2 | Distribution | 2020-07-20 | 2021-07-20 | Level 2
acca18db-8abe-4714-bded-b25f27d791b1 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
b2f48594-f25a-46be-b4d9-2d3e50b21e20 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
b470117f-58dc-45e0-8e30-5081e1aa779b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
bad97488-645d-433f-bccb-e862c482aef7 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
bb13b521-2d96-473c-aec9-7d21f83b770d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
c4551ab1-5a6f-4b02-9abf-7e1a8258ca49 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
c5dd986e-495d-48f7-be1c-a78e0835a290 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
c89ace32-c18d-488b-9f5b-93b54aad0903 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
cc3eaf5b-8fe8-402d-876e-746bf55e7f85 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d0986280-a573-44b3-a36f-e142da9b98a6 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d0aecece-4e54-491c-a62a-125922771b26 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d1de1219-f68c-4ccc-9255-498c2c1832cd | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d2bc092e-634e-4ca0-be39-d42640e3999c | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d37a2e2f-a0da-4a96-81e2-11b193ae1fb2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d6528172-7ee0-4858-971b-2e0d6f19aaf2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d7ba98cc-ca07-449b-a1f9-2da90e14d491 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
dbc765fd-5adf-420e-b00d-1544dbfcc9e2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
e1aba768-76bb-4c00-8353-56688c2b1df2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
e3976782-8580-4c31-9870-32e8c144e65b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
e6d06425-ead1-475f-bf9e-f3d3c7e5c790 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
ed6c140e-6852-4af9-b107-8dd865db3103 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
efdede95-9920-4017-b8bb-5a86b3615374 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
f8648ac4-9c88-441c-8e95-0dc27c7723d6 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
fa420072-be74-4196-9c4b-2558018eb189 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
fa899a0a-a631-4c9d-b535-356b862087a4 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
fb197b09-e22a-4951-9ebe-b623ddfff9ca | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
fb90dda1-d78d-4e90-b330-62d27e10a10b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
ff6992f4-747b-44c9-af52-294742064d1c | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
07620583-adf3-43cc-9a91-f6834a0b0554 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
0d58507e-d237-40e3-8429-8d73903b20c2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
1258e9e6-143b-4ff1-913e-86cccc0089e4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
12b57d87-721d-4b2b-96dc-aeb535649d5d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
275c3a42-3c2e-4a82-83df-8f8cc7b3f614 | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
2e0e1288-e41a-4bf0-b99a-cdff29dceb66 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
3253b362-4bba-4929-beb9-1c2410e24140 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
362d7092-0399-4d99-861e-03d354a068ca | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
36dbf361-c960-4a34-931c-5a8f2374766d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
38358e00-bd4e-4880-8a0d-c4b02e134be4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
39c5ae64-5b55-4885-b551-64b2d7301716 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
401be3d4-0f47-4c5e-87cf-8ee92da99623 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
5004b9d2-4f24-4b09-aca9-8c663f4a2a89 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
52abae4d-633f-4648-80e4-f87a66fdfcde | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
5950aa63-af98-4174-b1c8-beaba46ffb0b | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2022-02-19 | 2027-02-18 |  | Required to Re-inspect a subset of assets
64b88181-53d1-4653-8691-2faf0d2e5b99 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
694ccc4e-d5b4-4526-9b6a-2ea31f8cf2b2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
6ed0ac91-9311-4139-9280-68f3823b8899 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2022-03-25 | 2027-03-24 |  | Required to Re-inspect a subset of assets
6f07b5a5-14ee-48ae-9bf4-628f252686ea | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
6ff3febb-d5f9-4fea-af9d-121db7f0cd8f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
72b6394e-f2f9-4513-ab79-2dbb0ec26093 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
72f98bc5-e352-4f42-9d9d-edc4089c6c16 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
7d9baa52-a96d-44bb-b624-8c8f386fe720 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
85c68410-ff3a-440c-bbcd-b64ef788ce01 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
86da2d27-8311-4406-af97-98d249e4fb1c | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
8bb19de2-7608-47d3-8038-6e63998f79e4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
8e0aab8d-ca63-42c8-9d7c-981a9fcf5c4f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | Required to Re-inspect a subset of assets
8e34fb4f-63b5-4512-be3b-bfc452499ee4 | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
92d9ce94-74b2-4d6c-829e-41e7e46e7d08 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9409c75d-7c30-49b3-8146-fad952b09d54 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9801541c-05ba-4cf7-82a9-245067ce9fba | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9cd705f6-8d6d-48f8-ab56-7a7bde2acd07 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9cf17f0f-503c-466c-bf8e-c01d7e35039f | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9f2aef04-6651-4b87-b68e-7b1a5cb5a35e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
a349e40b-0ddc-49ac-9e78-72a187d965bb | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
a4c7d7a8-396c-4809-93e8-77154a7a0f9d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
a8671fb9-bd3a-457c-9461-e19062726f0d | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
aca471ff-7d2e-4d82-9042-afea6052942d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
b5e13980-29b8-45e8-88e8-41f8d337ae76 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
b6d853d6-f71e-430c-b623-547e88375d43 | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
ba08c030-cefb-4d9b-bfbe-5a994ecf831e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
bda08f9b-eeb1-4fd5-88a8-3a0bd64601f9 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
bfd98b08-5ae0-49d4-bbdd-64d0287c1319 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
c21f4584-7d63-4012-a386-39d322e656ae | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
c5865cee-90a0-4085-8cc1-13936170ee9e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | Required to Re-inspect a subset of assets
c70b88aa-de9c-46e8-86f6-c4b633986114 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
c8e01d8e-79a3-44d6-88d9-3129e1f51ca6 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
ced979d4-fa4d-4d59-96bc-57639d2353f8 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
d05dc5d6-4cf3-4784-aec9-e12eb0fdeb96 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
d5108369-35a7-4d36-bb0d-80259427fbd2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
da7599b7-749c-4b43-8474-2c4e8a0c3bad | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2022-03-10 | 2027-03-09 |  | Required to Re-inspect a subset of assets
dc0837f1-e8bc-4868-aa00-9d32837d377c | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
e216a338-68f5-496f-a471-9909e3b3becb | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
e5392381-9f70-43d8-ad9e-a1c9298bee5f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
e7cac274-98c8-44c9-b6bb-9feb6ff071ee | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
eef4ff04-00bb-45ad-9689-8f4fd4217983 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f387ad30-1bd0-459f-8e75-32c891644940 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f4aa5d71-2f63-4e72-b1d3-933e25c3c387 | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f68f4919-e060-40fa-80b9-832faaaaf89b | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f7dc410d-8814-4910-bc35-62597dfda333 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
fbc61eb1-b8c0-41c0-a335-9fbd4d1b5658 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
fe617fe5-7c30-41f8-a77a-16bf41ce9204 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
04febacc-9966-4a43-87eb-69a86f1e24f0 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
05fdbc9d-d937-4701-8f4f-f6f4465a8a6b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
0786dad8-bca3-499d-bc57-785b98ae8d2f | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
086230cc-ad48-40a1-ad2a-91ca12507cde | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
0977edae-210a-4b8e-8772-75b00f924e93 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
098c164f-7e9d-4633-a5b4-88153739b5a5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
0de55f19-e2f8-44be-9f62-df9912c0d1d7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
11120c99-a2ad-475d-8dbe-b54e7075998c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
13238533-7fd0-4523-8632-306f1ae57a06 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
132456e1-0066-4fe2-b241-25a488e5a680 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2021-03-15 | 2026-03-14
1485de5a-768e-494b-9b30-b7e19b7704d5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
14bec3c6-5198-4db8-bd04-acffa0afd202 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
155762f0-4785-463c-8856-95f0551ef22d | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
16f4b1cf-f0f6-4e81-94a2-2595d9f7dd64 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
190b03f7-b251-4993-8382-15af1568e858 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1963cb4c-b18a-4ebd-b74d-0182939b6df9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1a799a6a-5541-4ab2-82b8-3e5ed80819eb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1d9584ef-ebf1-4864-b4f3-5789b70bf57a | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1decbb6e-d070-4657-ba79-8f82b881b00e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
24b987f4-5597-40e5-af46-782b541fa24b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
26e77652-6876-4728-a567-0a7925d3e879 | Pole | 2 | Distribution | 2020-07-22 | 2021-07-22 | Level 2 |  | 2021-03-11 | 2022-03-11 |  | Required to Re-inspect a subset of assets
27f48abd-d9b7-41d9-ab36-03c19a340945 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
2c1e2353-5443-42bf-8179-7dda6dfaa082 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
2e17ac99-11ae-45b8-a9f1-273d58ef5eb9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2022-03-24 | 2027-03-23 |  | Required to Re-inspect a subset of assets
2f8bbe77-7d8a-4947-9965-59d6b882a9c3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
35802a8c-3856-4a9d-8eb8-03a9413009fb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
372da38b-0726-4963-84f8-75a3077167a2 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2021-03-23 | 2026-03-22
37445053-45b0-4628-8f12-a95cec3d2571 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
3b491c78-00c3-4bed-87ff-aa54ab556aaf | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
3c39e64d-f70e-4e1f-8251-021fe85f1fd1 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
3d7ba87d-8b13-4e08-bbcf-24c034797c1c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
405b052e-6889-4be7-8d1f-06b5d22ccca6 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
423a33bc-cf14-4548-bd86-81d15e32ea57 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
50b568f2-695a-466a-b98d-2997535f785c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
516fbe02-4ef3-4d88-b6a6-0c4108dae548 | Pole | 0 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
598c74c6-8ea9-4d3a-a02f-b83d41f8dc50 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
60a9223b-21ef-455b-aa5b-5b6ff35fb81b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
61fad609-a547-4a6c-a6ad-bc8ce0eae09e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
66646f9d-524b-424c-a5f8-4cb771e41843 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
690883b7-c36b-470e-b002-9e20cb13309c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
69208e43-3a14-48d5-99bf-1d3b0ae68c14 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
73b3a429-219d-4dd1-bf1d-10fce518c971 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
780fb113-4ded-4ce8-b6c9-bfba421c0616 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
7914e5df-8243-4f12-874d-6f2b9c738878 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8004e28c-2a38-460b-8e21-887038ef0251 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
84d37068-9341-44d8-964b-07ad838c664b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8599be8d-04d5-4204-a310-4a87496ea316 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8ad250f5-f519-40c0-b058-4b8fcbbba1b7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8b65fdf4-59bb-416e-9ee8-be0b341c8b5e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8dab747a-3709-498d-bcf7-506777190769 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
90e7665a-99e5-4b5f-a861-8a0b51307251 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
987cbcaa-0dec-4e03-ae21-d444b2ae6d6e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9b2847ed-2921-4ad7-bf63-9dd326765631 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9b716f3a-2c0f-412f-a570-ce444abc5983 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9d2cf61f-5a50-41c4-98b6-e174e1d019d6 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9f1eafbe-ed7b-4906-acc1-7b1076608be3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
a08fb303-85d7-49de-8aec-e0829ad05dd3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
a22d6ed9-e6ca-4e29-9171-6c0caceeef9a | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
a56e15bf-0aff-4dd9-aebb-39923016d9f4 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | Required to Re-inspect a subset of assets
b2bdc967-b469-467d-8186-02b7f0ae0029 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b7942559-3236-4f98-9a47-f6db44a637d7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b90b3981-0f02-466e-9dc4-c93a2237f1bb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b9463073-4e7b-4e41-8295-c1a0a13f00b5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b9b0f04e-5231-4bd3-8e18-fdaf3eef5798 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c042e979-570b-4978-b783-689160cf81cb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c32ab9ab-649d-459f-84f6-8ec644e9e737 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c40364cc-d21e-4f86-ad44-46eee8975965 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c678b42d-01f6-468f-b181-ced58d55b8ea | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c9c8db20-aab1-48da-b1c7-1bd83eefbc2d | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
cac63fa1-8a82-491d-92f8-e1330f14a5f9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
ce40b536-e69b-4029-b28a-c833c18157fe | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
ce47d1ae-af91-4ebd-b247-ca19071bbcbe | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
d53a06b9-9c2d-4e7c-a637-ec8a8f9a59a9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
d85f85ff-5cbe-43a2-9ec1-20846a6e0d00 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
da0e6c72-9e2d-4933-ba8e-ada24d403f75 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
da133657-de75-4ac4-9604-1690dbe4c606 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e00c735c-a286-43a1-a31a-00fb36379f4e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e0cc2876-9cd0-4a8f-bb2f-c03d14cd63c5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e24506d0-e73f-4c09-a7b0-33b74c5bcb57 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e3591db5-e43b-426d-8b9d-e24f214dada1 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
eaa444f2-f440-43ea-9b1a-5c1b9a903cde | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f05dcb78-2778-4503-ac04-9177a07287ff | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f13e9beb-6897-4157-9214-e0c672b568cc | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f45cfb59-ba99-4a2b-b1c3-cd66d4fb930b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f77c1508-8f47-4721-9e1b-92e915f963cf | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f9e9047c-b34a-4ed8-b73c-daf01b292062 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
00ce0865-0dd5-4d91-aa90-01561d97be37 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
01eb1ea1-6e43-482b-a94c-86bb150d8d06 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
02e83783-eb3a-42c2-ac06-48bca42cf6cb | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
04475d42-57e2-4981-941e-2b3de281b128 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
05a3f811-7a19-4417-a272-2f63df0e7920 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
085c2c25-5898-4f0a-bc5f-9385d146de45 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
09e1428c-50f8-437a-8161-cc1b73a13626 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
0c550d44-d299-4fb1-96d9-23ea59c258b8 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-10 | 2026-03-09
0d8ee1c4-f016-48f5-be8e-32869cd24322 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
194f9314-1b3c-42b3-87cd-b832d8b436b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
1ad2d8df-a69e-473a-935e-3aaea16136ae | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
1b06439d-9ad4-4df0-a7ba-1fc62015f25f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
1ed3847d-f7fc-4074-89f9-7a6b653869e1 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
21565dca-9bcc-48c2-b026-e547c5d98e44 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
25d9e6ee-5ea9-48ce-9fc5-e447f997294b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
27404532-3408-48ad-9a47-7a7cfcece515 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
281ad005-0bc1-4cb4-abcf-954eb1268cb9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
2c0100ac-11c8-437d-bdf9-717f38ec384a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
3021d73c-a8be-44f2-b25a-46b72896598e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
354d9ceb-7af8-425e-881d-9e6dab935a0f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
35b52963-b8fb-443d-a8b6-336ec47518f2 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
363e3f99-74c0-4428-b074-bdba35b4b9b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
37198e6e-e7ec-4d4d-af04-1ab1359c4c2c | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
3d8f480e-8dd3-4e2b-b81b-15e7ac32dcd7 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4191b4ab-fd68-48ce-b5d7-65bdf62ddb9d | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
419942b2-93f7-4f7b-93de-bbb8b9b2ee18 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4398aa7d-1a63-4f83-924a-a414910ad33f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4478bc29-cce3-4387-a2cd-c32a3e1f3acf | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4596ab5e-60cf-4551-8d2e-7041da80abc3 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
47fafa8c-cb3d-4110-9eb8-d8ecc0b3cf26 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4a39d4a5-6c73-4261-b391-da50cf40d701 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4d7435e7-f3b7-439e-bca6-5981e48ce258 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4fb53c55-9013-4906-8b56-88055308983f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
53e74fcf-a45b-4b18-847f-098712d8972a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
54cebd87-2719-4443-a224-8b692043b06f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
5972564a-69b3-47ab-8170-913e61e0276c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-15 | 2026-03-14
5afc87d0-b0bf-4b19-b1ef-f703318f95ea | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
5cb2ac38-d26c-404c-a8c9-f0d77e0c3be9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
60cd121f-d795-4c5f-917a-24e91332c073 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
69e6d010-a164-4dee-a8d8-66368f15470c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
6ce6c076-5091-4dd0-83fb-b93cbd937e95 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-17 | 2026-03-16 |  | Required to Re-inspect a subset of assets
7040eaef-d496-4f0b-8448-a8adad58fa11 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
78ce8d24-c839-4120-9cd0-b7a964b374b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
7acfc8db-4e08-45de-986e-ac95fde0dc49 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
7f0f5e71-0310-4024-b0f3-edd3626c52e2 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
841db771-85ce-40f5-8c95-498545060e61 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
863aa4f2-b747-4f64-ae9b-8879f0fabd8b | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
885704c2-940f-4d6c-834d-76a9dad1fc16 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
8c1bffe1-406b-49a2-a442-c4f1c963a90e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
8d0108e2-b46d-42ca-b25b-1fa2ae5502be | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
8f09317d-dd5e-4588-a0db-2f9f2a0fef78 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-15 | 2026-03-14
8f577979-a23c-4d3e-88ac-c169a0d7597b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
92c622fe-9ed7-4249-9005-3899c4084d2e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
944e1cd3-f96f-4d26-999e-1fd2623aff73 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
96246768-1dfd-4096-8eda-e87f8e3bfc95 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
9b6a594c-0c09-43cb-b4e3-b62302ba649e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
9c8222f1-a13b-4444-9c30-e8e4d6adc330 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
a71d4161-dc15-4cbd-8cf2-1ca301cd624f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
b4d30087-ca3b-48d1-aeb1-e6960034c54c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
b74efb70-68cd-4e49-9bd3-0b7ec7f81f63 | Pole | 2 | Distribution | 2020-07-23 | 2021-07-23 | Level 2 |  | 2021-03-23 | 2022-03-23
bd13d8ad-9fae-40d2-b038-92498ae8218a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
bd407c35-55c8-4b8e-8678-1f5bfcae0a03 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
c18314cf-3263-425e-9c53-749e7b2afad4 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
c9054571-2de8-48a8-9608-155a5a2ad3f8 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
c92ae763-7071-404f-9f90-fc83c0fd6867 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-10 | 2026-03-09 |  | Required to Re-inspect a subset of assets
cfbf8eef-c768-44eb-a9d7-3cdae9a51818 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d1511522-6eb3-45d0-b641-0cf7be29b490 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d1f04ea7-6d73-410d-86ec-e34a73e428f7 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d398e978-0e99-487c-9605-e8fbd109843b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d54a66e7-fb70-4ed9-bf6b-732d8ce29998 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d7ffe809-1b0a-46e2-ad0d-6ab7239e3f48 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
df78451d-0c2f-4b78-98bf-6bd6865c03b4 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
e0776c6d-73f9-46e2-8f4b-28cf2d1d77a6 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
e0b0897e-31dd-40d4-ae27-ffd3521dc5c6 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
e3fd1a61-8c49-4ba8-9074-d018b8c85d2c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
ee7ac0e6-b9c2-4193-b7b9-aa9910a7fcb8 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
f28dc49c-cc67-4dfc-b9b6-f6662dd41d18 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
f3ba4a46-4a87-47cc-ace2-f58d6d1c64ff | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
f4719c35-e1e5-40f0-ae0d-44e4d223b884 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
f850e003-14ed-47c5-b712-81e45bc83a2e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
fb95a9e8-1af2-4c28-871b-9d0e00e3142a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
fc8ccefe-4834-44ba-965f-5d558bd527d8 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
003c59eb-40dc-484b-9640-1c5e37db9b33 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
00559924-e13a-4bc0-9386-72583f56a0bf | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
0b47ebd7-c425-421d-86b4-5d53573a560f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
0dec6fd3-fbc1-42b2-874a-442625cfc636 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
101e2290-eba0-4055-9fdf-4553d6e80c43 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
115994ac-439f-44cb-9ab8-f0de01013b7e | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1852553a-bc1d-42a2-96ec-d9e400661cb0 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
19baf206-5c26-4d6b-bbe5-8a2c704aa694 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1ac5ab46-f1b7-4aa0-8f25-f12dec34e942 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1be22bab-8575-442b-a0aa-7055fae11650 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1c12eec7-5ebf-424c-83a8-fd5f478a608a | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1d0983f2-c338-4fbe-bf9f-27907390bd05 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1d9c3aeb-79e0-4723-afcd-85eed64ca037 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
20f4af41-75d2-460d-a866-7a0db49de817 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
21ad4fb8-c1dc-41dd-8dad-3689f15e9eb1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
22722ca6-9403-4e60-8d0a-387975c1afa4 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
232aee0d-dce8-47c8-b68d-9b4a7dab88ac | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
29d2f6d7-3daf-4129-bc07-87f3fdfefee8 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
30b5a9b8-73d8-42ac-a8f8-7ff26c1e2374 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
31565d9a-23d1-4c5a-99bd-1e0daa103a15 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
38687e2a-2c98-48e6-a05b-8ad2ab78fc64 | Pole | 3 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
3d1aaf44-3d1a-4792-a657-a853978901a2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
3d28c191-d444-4a96-9e89-299617c57217 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
3f122b74-2fcd-4b81-8222-f7b747ed461c | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
435c05e2-3a99-45b1-a41d-0c3b4b9cd321 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
4a2b5025-4710-4276-a145-569f0cddbdb9 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
52e8104a-6e84-4f5b-87a5-fdb12a133772 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
59909e58-1b08-4e5e-a859-5afc39079d77 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
5d8387f4-0713-46a7-ac75-d1df6ab20258 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
604b2ee5-40f5-4a54-94a5-9dab81a9ae2e | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
62241ba0-b7e0-4af8-84bc-f9ce14c3a198 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | 2022-07-12 | 2027-07-11 |  | Required to Re-inspect a subset of assets
6256e6b8-0b28-4b6d-8ba1-177c99110aad | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
67c741f7-94f8-4b96-93ad-2254e0562ea8 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
68275e3c-66f1-49c2-bb85-4f36cee8c165 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
6df356bf-63eb-4276-9bd9-0dd80497962b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
708a52bb-062e-4997-98ef-022033b3c3bb | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
7661cf2e-3116-4f35-976e-9a6cea7a067b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | 2022-07-12 | 2027-07-11 |  | Required to Re-inspect a subset of assets
7b1ec036-0af7-424d-8e94-f8043da784cc | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
802b8fc1-c6a7-4869-be3f-eadcd1ae393b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
867074a8-218a-4ae1-8e29-d22832ed1860 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
89d6031e-8edf-49f6-91ee-9422099803c0 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
8b45902a-9b3c-40cb-9a9a-082f630a9803 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
8e3b2240-349b-4b1f-ab41-cf386ff7b65a | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
9b7645aa-eeca-44db-8014-121a4bf2709b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
9ffaade1-d5d1-4757-9d4d-79ffe28599d3 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
a4ecd39c-24b4-4281-b510-1bcb6322f98b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
a61eea3e-4d56-494b-b7ce-f440da7f71a4 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
aa64dc5b-aeee-4deb-9619-1f354a3e7fb3 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
ad3d56a0-1031-4e6c-b671-fa7f41777979 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
aed073ee-3047-4e68-9716-9053c86c2125 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
b2aaaf91-eb36-4830-acec-b1c004751f78 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
b405f9e1-4769-4bcc-b9a1-0728c496b813 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
b85376ac-63cd-4d67-8099-dbce7e56db51 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
c0778902-b75b-4846-8def-337b8b43e207 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
c1bcb287-caf5-4c11-b488-949119005e95 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
ca0ac1eb-a55a-46cb-b485-c1687c2585f2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
d25e5082-eece-4711-a22b-cfc8ba2f7553 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
d545220d-91d9-4cba-81b2-77722478e04f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
d8d1998d-1b94-413e-a6de-bdcf004a3e16 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
dc06a5c0-f1aa-4005-9939-9871fbab1b83 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
e0ba35fe-cb16-42cb-b192-aa5612a1b339 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e0f896da-cf58-4b2c-a52e-6720c90a28d1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e369c0ab-7a00-4cb0-84e4-a8040b994409 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e4a0c59a-b115-466a-9505-8ce23b616aa1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e677af6b-a06c-40ee-94c3-7b25e6f97f7f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e6f77305-c823-4467-90b6-6c054a208c3c | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
eb6cb0cd-04db-4cfa-afde-6d40409cb012 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
ecb5faf9-6e0b-4b35-b555-a75dcebae774 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
ed74877b-39e8-49c4-b8de-83c18d35d045 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f4ea0341-a1dc-4a31-b067-1e1e4240b9db | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f57b86e8-a119-4adf-9f83-408cde6cfcc2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f6c3a41e-6d34-434a-8bfd-644f9b1fa854 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f86cdc8b-1efb-440b-9f4c-e27753315103 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f8aadcd7-fe4f-41dd-a410-46b90a3b1888 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f91fee5e-7ef2-4260-8d16-bf1434bfc7d5 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
fa0fd212-d8f8-4ad9-856d-5c08c4395da2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
fdbfcc1b-3376-4b23-a829-1caa3373725d | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
06a23d92-f9bc-4f00-96a2-68e1dc99da64 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
09405994-5841-43ba-a61b-c74efaa3df84 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | 2022-05-06 | 2027-05-05 |  | Required to Re-inspect a subset of assets
0a5ad9e8-a099-4ef3-ac31-516073b01406 | Pole | 2 | Distribution | 2020-07-25 | 2021-07-25 | Level 2 |  | 2021-03-29 | 2022-03-29 |  | Required to Re-inspect a subset of assets
101dcd84-167d-434a-8da1-1c8d8e9d37a9 | Pole | 2 | Distribution | 2020-07-25 | 2021-07-25 | Level 2 |  | 2022-02-17 | 2023-02-17 |  | Required to Re-inspect a subset of assets
1cbce5f6-c8c5-4558-95e1-588168863eb9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
2414fa95-46c4-4c84-a207-61d4018eb31d | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
24498ce0-e1fc-4109-808b-1d4071da1e88 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
2fce35c2-08fd-4336-97f7-70d8457934b3 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
31463294-66e3-4dfc-ad24-6c43d7ac1a8b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
40a9a224-231e-46eb-b345-129ff80d00bb | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
40d16bb1-c5fd-4485-80db-25436f30aeaf | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
46053864-22bb-47cd-9772-65731f1be5c7 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
48fe73ee-9948-4386-a7e2-2420b1d71f42 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
5844b28b-517b-4aff-8135-ddec0ec80b54 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
5be44354-cfce-4926-af84-11da50b211fa | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
5d4892a3-546d-426d-bd2b-27b4016a7b7b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
63fde725-0265-484a-ad00-735d90899cec | Pole | 2 | Distribution | 2020-07-25 | 2021-07-25 | Level 2 |  | 2022-08-25 | 2023-08-25
653b50fa-bec5-4939-885d-46121f5cdcd9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
6af7a202-7a76-47b2-843d-d3405b8def54 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
6baccda1-c019-4152-ae02-ae434d414722 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
70d895e1-9c29-4ec0-99e8-6dfe55d310cc | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
76e58a45-cb14-4453-92fd-dffae4d9172f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
79cea3dc-6837-4cbf-a132-5dc114de007f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
84e45149-8df7-4e47-a329-a48f10c56730 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
894bcc58-a829-418f-acd8-2ab8d55438f4 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
8a06853d-dcc7-4258-917d-37d0cccd6351 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
8ac96b96-71e9-47bf-952d-0212e8762f58 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
93470e73-94f4-4968-842d-e9637dda68ed | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
95f90b1a-5519-4198-b78a-83e85d26ae7b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
97c20486-f5a2-4919-8736-112cdcce4773 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9aca6f71-8a97-4292-91c5-9d1754f19d43 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9ba9c733-6653-46a6-a735-ea2c9baade51 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9dd7c588-3bf2-45de-ac05-4010301dd772 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9e72f818-3d7c-4d12-b55b-1ad6f5f80ba3 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a0ff8995-3177-47a1-8e4a-a49e3eb61fa0 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a2d42460-8559-47cc-b617-62c7bfb82140 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a4ddd710-4d7e-460e-afd7-ba537d5f0c12 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a58ffd25-d7a5-473c-9c53-133b954cd1b9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
b36d75d8-bad5-4eb4-8c7a-91c33be09c40 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
b3708441-83ea-4bdf-b5bd-350e20511b75 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
bc0d92df-f8e9-4213-a4b8-651c5f98d9bd | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
bfb2b51f-0065-480f-b240-6d6d417138ef | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
ca10b871-ce23-47f2-b7b4-be42e0b3f1f1 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
cf986275-b8c9-4115-a8ba-1246522517b1 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
d3eca088-7967-49a9-a5c8-249a90501212 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
d5af6537-e686-40ca-a17d-e24a9b91a5e5 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
d66c665f-046d-4544-8ca1-2cb89af14429 | Pole | 2 | Distribution | 2020-07-25 | 2021-07-25 | Level 2
d8506054-6f8b-4ade-b5e7-b3f2679603fc | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
d9f78edc-0f18-442d-8310-b2cbde6a724b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
da0f11d5-e2ac-47ae-9d6b-8cec2b0e68c0 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
ef11487d-6f1a-4269-91ce-e2205c6a2e7f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
faa804ab-0c23-4062-bbc9-394aa6f74b7d | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
04fb1bc2-11a2-4207-8216-58d6856f9f21 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
08e2ddbe-4b33-4712-8478-218a6fb1bd26 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0aafad34-42ac-476e-ac8c-54c862e16cbb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0bd6d83f-f021-48d2-8311-6db32cfd9ce3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0c402419-f5b2-474c-bb9e-12bf4911a428 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0c6f4905-9adb-4968-a170-0fa92f583682 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
0d197760-31e2-4ce6-82c4-fba2c6e80a5d | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0f0ce153-8b60-42c0-8a7b-0eca192bff50 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
10e93fd5-bd9e-4242-8e94-f2eebe66a2c2 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
16071641-3702-4977-bf43-a54664ef80cb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
16079d29-deaf-425a-be8a-2245f5bf19af | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
19ce54f8-126f-41d6-bce6-55edc5d1add3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
1f983b94-d24d-45d5-b246-da45b6367fc7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
240f5504-42f5-45bb-85e1-f8371f776cc0 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
24ede8d3-94c6-4693-9295-63130864f5a5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
256c610f-a22d-47da-88eb-212cc5eb9987 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
266e7653-1c98-4d63-82be-8ba4a3f0236e | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
26cc9f27-6d88-4c56-84a3-79d74c0f16ea | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
310df8b7-9f82-4ef0-ae95-11ae77d8c001 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
325fdf71-c816-44db-85ea-3843ce618bcc | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
3285d520-02f9-4803-aacc-8ace9e2d3875 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
377ea0e0-3b5a-49c2-bc35-e62fc260b8f9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
3b858829-f0ea-47cf-bf52-08920721d70e | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
3c627af7-95ed-4b15-a3a2-433641af31f9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
3e253b70-8ed3-4288-84b6-d241933fd525 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
3e4bf7d8-fe74-450d-a3f8-fb5655734b4d | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
410758f3-b72c-439b-af9e-fb1771285d7f | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
4498c0e0-4771-4f08-b24c-c2bf5b087968 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
4a298c8e-8224-4cab-8a43-1ed67b76ffa6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
4a5579b2-7175-4948-9702-016a4d552df3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
4f8220a9-eccd-4ede-b7f0-130f909fdb5b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
5040948d-cecf-4677-a2de-3f9eaab147b9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
52a7be7e-b1fb-42b4-8801-a7f34327bde7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
536eeab0-bf6a-443b-ac5a-22f2b888f0f7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
53d741cb-fbc4-4755-bd69-2151dfb7c6e3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
5626322e-0487-4f57-9373-d0ad1ad1c27d | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
58b70cef-f34e-42d1-8c3d-5f668e86b8d5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
5be6c9fd-a3cf-4cfe-ae02-2b617434f07f | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
5fa544cd-2c65-4415-9d9a-43fcd2f78cd9 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
6052ce87-bd3f-4ead-9833-c40e5fcbd947 | Pole | 3 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
6509f087-f157-4b0a-afeb-61a7bad2ae19 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
684c194d-6eb4-4651-a99c-b26b7687282e | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
7157b679-c570-49ff-a846-a6f08b4ff464 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
7221de15-46e0-4765-b4ba-4f00db901a85 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
7b08ec98-eacb-42a2-b0e9-4614dee5cfb9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
802a7fd7-ed36-446c-83ed-e631c056bce6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
81180f46-e739-4a22-8676-936e05f70a26 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
8534da5d-a8dc-4b42-8119-d0bd06e2f0e9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
859602a5-0c5b-4ba9-9856-0375b091dbb4 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
88c264f9-e4a0-4a5b-b8df-4720c9ed66b4 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
8dc0c9db-6268-4b04-9b72-8c795e33b2d7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
8e19c206-a8c4-48d7-aff7-28c85797a3e2 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
90449a01-0b54-412d-a266-58b3fb1c403a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
9128ff74-11b0-4116-be85-91e6ab93ec38 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
97ef9a56-58d6-47f0-b54e-5adba61d01dc | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
9ad72806-0e0a-4d42-8d2a-0bad5c92f8ba | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a0c77977-a560-4a76-a444-7c7316b0995b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a2e84a4a-54a6-4ab1-ba9e-f94b68ebe30a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a63ebe2d-d7a5-42cf-9f66-e6d45152d6e1 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a9bf8b0b-9cef-44d2-b61f-b2ac60b9320b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
b9516bdd-c9e5-4ec2-9ea7-ca8c8b7cc0bf | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bac3de06-73bc-4427-bcb3-f9a181b0042c | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bbb71932-fefe-47b1-83d0-5b92e63c3c98 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bc9ed3f5-d2a1-416d-9e0a-1c7738dd7c37 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bed56ddb-e3de-40ff-8d1d-bd6db74ab876 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c1708261-48fa-4aca-b30b-a327cc7ae9c5 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
c5bdc97f-e027-4039-8ec8-d3421ea340e3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c5eade21-f3b4-41d7-9e41-90b2f6e046d2 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c984bb3d-c177-4894-8d44-24d6feab679a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ca8196b6-beb6-4c75-82ba-61cc33c78fdb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
caca63a5-c510-4cef-9de8-ddfdc645f616 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
cd0f9b49-edcd-44f5-af7e-082c4fc8b828 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ce51b1b2-4597-4f79-a22f-87a947b51394 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d0f14781-16ae-4395-acb6-bdc59bc37df6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d1de505c-6b60-4c06-a3e8-5ec1da9cb29b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d6f48278-49b5-4c0d-9acd-d7d9bb6413c3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d85e5374-c715-4a59-8e9a-21ece63cf463 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
de919eac-3f9d-40c7-97aa-77c6aadc9a48 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | 2022-05-06 | 2027-05-05 |  | Required to Re-inspect a subset of assets
e07056a8-fe97-4a0c-aa40-5667a7f90580 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e3290529-4221-4bb0-a06a-1c29dabe4bfa | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e3f47c04-c64c-47fe-aac7-7d357fe1a0e0 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e4a6e208-a721-4c91-af40-5065b5850b8b | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
e4d9c159-06ab-4a20-809e-1193d09d3872 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
e75ffa6a-b9bf-45aa-a6ff-f1535dcc73cf | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e77d9ce5-76b2-4e8b-9f0c-1a425b5961c7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e81cd987-ec11-40d2-acf4-67599cf5c5b9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ea256105-3863-408d-b389-0130db4f9896 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ea2ee312-b599-48aa-a510-2375b951488a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ee2bad73-8101-4480-a5ff-1ec3567132c5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
f1f3a918-1ca1-4190-bd29-f4633a548a9e | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
f8bdaee7-ffe8-4db0-a7a5-2b42d2eaaf19 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
f97e627e-7e39-4f41-98c0-61ba9b377a09 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
fef96e72-d1b6-4eb2-ac35-1dee0a2594dc | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
ff5a7239-9e20-4286-81e7-2849f71c7719 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ff7b28d7-eaf9-4d02-b3cf-f9adb7f99c22 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0549899d-67b7-4e22-a7b4-70f665d21b6f | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
219e3b39-e6a2-472a-be13-b919a4dc1b96 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
48ff97ee-f096-40e2-80c6-79ad6e0f1010 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
57b9bdcc-ad8c-48d2-acdb-13697751ba2b | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
5cbc8dfb-85d1-4533-bad3-75ba5e67bd63 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
6041a586-d4c9-41ae-9d11-9800457e7b13 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
62d91f4e-7d90-4de3-93ea-cbb2d4086e17 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
88bac969-6de0-4066-84fa-f923d58dd592 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
9339479d-15e6-4b4e-a74c-63d32f9742f4 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
aacebaa4-e2c7-4490-b0d2-6ad7bba36c17 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
ac1aecc7-68ea-4cd0-b10d-3ff53099a01a | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
ae5168cc-9f3e-4869-9dc2-a275595d773c | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
b6a2eebc-b732-4904-b7b3-2a91b74435e8 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
b791c4ff-1208-4a4e-ac5d-02706af92bf8 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
c26ed660-6679-4137-85dd-d702ec2bc333 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
cf3366d4-2f94-4442-8694-a54ed5dbd9b1 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
d199acb0-ea31-482c-8b76-11e0687ce3c5 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
e0aea6cb-3892-41a2-a92c-c10ae6d50647 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
e0e41d57-2316-4497-be09-37f8403ddfd4 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
e629c9ca-056c-4d80-bc7f-9d16509fe557 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
f60243da-cac6-47bd-8017-909973a4a54f | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
0ab79c47-1aee-490d-9cfa-74ce0f6d2067 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
193e3815-f98e-4087-ab8c-a98e2ec355ff | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
1b308029-a7a1-48cd-962d-4c49080299c3 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
1f2c40fe-c02e-43cc-87c4-5bea377fa0d2 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
1f916061-aaf9-4807-abe7-7d6191f0de6c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
248f7ed7-2e31-466d-9fc7-0b5c8af7eae9 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
3111d693-dfda-4ec7-9f2d-e2a45e58f8ee | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
3495b74b-f180-441f-8bc1-0e87be8ef2e4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
36bcfa88-b9b0-49a5-826c-93a8fdee5f59 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
462da5e9-722e-4afc-9b21-5f5af6ef5b02 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
49005197-5dee-43c4-b03f-0c715e5e0c61 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
49b1aab9-da8c-4e05-a481-43e6c6b751ba | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
4a9f5b49-79d2-4fbc-8854-78931865ba37 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
5b37d8a4-3fd3-401b-8a92-ee6324dc52c4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
5f4d106f-440f-41ca-95d2-b76e20e7514b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
693709ed-c576-4234-af7c-41068ab22b0d | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
6d58c532-f052-416a-951e-232b73d5ea98 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
7007ce8e-ee20-4f47-baa1-9e7661759f97 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
74285a22-5e06-46e1-a1c1-63eb5b833fc0 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
7c69f66a-76c3-44f1-8297-8179bf540365 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
8a064dec-25f2-40c4-bb8a-f4d4250bb05a | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
8dfc44b1-bf2e-4274-8197-6af57753517b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
9784cba4-c0ce-4787-bdad-482aff9567a9 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
9ee2413c-d189-4b77-8edf-7431864abfa5 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a586fa3a-5e0d-49a8-9f9e-a9b8e9cce037 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a631df52-39fc-4fea-8d46-4cf22257a836 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a6c86b8c-da3b-49ac-8efe-d12df7df666b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a7c5597c-c0fc-479f-b218-937e3b1321bc | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
b9806141-fb96-4e68-b25e-26f51f37b01c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
b9ed212d-c65b-4da8-95a6-f9e331b51600 | Pole | 2 | Distribution | 2020-07-29 | 2021-07-29 | Level 2 |  | 2022-02-14 | 2023-02-14 |  | Required to Re-inspect a subset of assets
bbdf13b0-7cf4-448f-a4bf-3b5f07b0172c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
c0abcb83-c54c-4502-ae34-f8a6b4272d59 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
c876d12c-2b23-46b0-884c-a1de489372c4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
cc63cf0b-6844-4d5e-b954-53d1f8ef0e80 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
d0bb76fd-5dca-481c-8b9e-8678aeaeaa8d | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
d78ca063-ac73-4aa5-a0fb-978b23f7d073 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
def6190c-7f00-49f0-8768-90b185cd3a80 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
dfc9c00f-4892-46db-a67b-6729c6027b55 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
e433fabb-6d6e-4786-85be-7151856ba7fa | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
e4cbb4b7-6344-44d1-9040-8190f557bddc | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
e8d4af19-f666-4eff-a174-877bac0e1fa7 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
eb6df2a8-0e23-4afa-8d55-a632337336c0 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
edce0504-399c-4c3b-a2cb-8ed6ab0ba374 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
f22dd979-5340-48fd-abca-7d9ba7801da3 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
fdb40fdd-130a-4d12-8cac-410e008a66d2 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
fe276f13-e176-4342-a789-6f96623eb761 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
0528c46b-0b91-444f-9c2d-2d24ab4dea1a | Pole | 2 | Distribution | 2020-07-30 | 2021-07-30 | Level 2
053fcbaa-39a7-439d-9b27-d422ee857742 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
06b847b3-fec7-403a-aef5-743294ba574f | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
070b2a1b-f77e-4034-a458-e1265f8c9478 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
09ec1139-c336-44eb-b661-90fcb003a10c | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
0b82095c-23db-4106-a52b-1aa08b274c02 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
163fd724-f184-4fa5-ad4c-87c14616ceac | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
1757c1b2-1b45-41a8-974d-6afe1e2a0c55 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
23b43a59-3d7f-41db-b121-1a6079b10cca | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
23d5be88-bb3b-429f-b665-1038cac42329 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
23e58721-722f-4dd5-a1e6-a5ba53f2d8a9 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
2c28b806-2e23-414a-b770-db946a9555ed | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
2ed490fb-80c8-4625-83f6-0ac3618de835 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
375910c6-0019-4e80-9520-5f799de4956a | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
39ab9892-5a96-47ee-9591-cce751d9ebce | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
3bd02773-faf8-4a90-b71b-61909c00069f | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
4190bffe-e431-4f1a-93e0-295ae2cdeff5 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
450e27bc-6bfe-480d-bac4-872a37c7d2ed | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2022-03-24 | 2027-03-23 |  | Required to Re-inspect a subset of assets
467e2744-01dc-45b1-8cc4-09a5ed171bee | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
475107e5-1daa-43bb-84eb-d90b55b8729a | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2022-03-24 | 2027-03-23 |  | Required to Re-inspect a subset of assets
4b6da47c-fe68-4bbd-99b5-86d81e7c4d14 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
4db217ec-acb2-4333-a444-fe91a09a2c29 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
51ef1542-bafa-40db-b16d-bb7cded61a20 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2022-03-24 | 2027-03-23 |  | Required to Re-inspect a subset of assets
56b5d1c3-0811-4df6-96f4-ea94411eec24 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
56c25b00-1b97-4e8b-a119-6b2885c2aa25 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
5fbd73d2-389e-49dd-b3de-9d8ead41b493 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
611e4c51-9c89-4f26-b295-40efdf367339 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
621f490a-019b-4906-8a66-c9c8709137df | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
67506e5e-7bd8-48ae-9efd-84cdd7f284d8 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
74dfafd9-7fcb-418b-92f8-65c3e4a9cba6 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
77b1a0e1-2c75-4372-a3b7-5b9c8b53e645 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
7df02f3d-fc07-4472-b9d0-d330e9b786c6 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
848051fa-fb95-415f-a8df-1d4f439fdf51 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8a3dcaff-5c1e-4a0d-897d-ee2b6e084304 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8a95f0dc-3de1-4647-a7be-e65e6605ffe9 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8d8d8458-3a22-45b1-ae86-bbc984a36f85 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8f07b11d-0467-4b2b-8b88-bd2251c54a23 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
98a3f311-9d56-4693-8e97-bcd26455e683 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
a8744aac-51d6-42bc-af8a-b1261e58cb5d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
ab225ffb-46ce-4cd2-b5da-7efe58fbbb8c | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
adea6fd4-30e3-4863-ad07-8a0e3b1c559d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
ae0e17f1-05b3-44ba-bfe5-8d7b07a1ddab | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
b41fba4f-3a53-41bc-ab37-26ab8e59a45a | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
b9b73726-0207-4b26-bc56-4ebdea9c8379 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
c6ca1f8d-1f1f-4b7a-9ef4-fb6f5aca9dd1 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
c703fc86-af30-48f2-a543-02218fd1832e | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
cff6b214-5ccd-4972-9dce-2ed3393d64d8 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
d214ab3e-f07e-4944-a756-49e18f674bff | Pole | 2 | Distribution | 2020-07-30 | 2021-07-30 | Level 2 |  | 2021-07-16 | 2022-07-16
d53bbb7b-4ef8-4252-a579-5e39eef82efe | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
d9465eaf-8d55-44d3-9b16-d98d058ca84c | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
d99a9ea9-dfb4-4e10-a395-fb86f8ebb618 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
dbe3d212-618f-48d1-b1c0-40858e895c62 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
dc85d9e8-fcc4-4350-a14c-db8f1d853ca3 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
dfd7a173-f86e-4b4e-b5c4-febea764c9bd | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
e84d9cfe-88b5-4eaa-8b9b-25ccca25c024 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
e9f00fcb-48a4-4941-86ee-f9967f4b118d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
eb960ef1-6022-44c4-ac45-76ee623e3e26 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
ed646468-627f-499a-8668-a69bc7774ac7 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
f21d7579-0fe1-4539-885f-fd8e9a067410 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
fb45652f-bb6a-4972-a4f3-0fc3aa63669b | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
0a3582ac-30be-4318-a20e-b370c5b950b2 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
0f600af8-e21d-4f48-a075-eaf85ac02ec8 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
126fd123-11a6-4211-91a8-e3a25ad0a677 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
1622dcb3-4770-4139-932a-926a8334e95c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
171cf388-e301-40cd-a45e-645246fa6494 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
1a100b9e-1185-41a1-bd2a-bdd3cb22140a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
1a551ffc-3f4e-4014-b22b-9808a3705729 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2021-04-21 | 2026-04-20 |  | Required to Re-inspect a subset of assets
1cc64aac-3612-4b75-95dc-1f3a7e674aa3 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
224341ad-2cc7-4fe5-9e3b-d64159e5c262 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
25ae3197-9a65-46d4-a082-19ea63f8ba73 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
2c6a54aa-4837-43d0-9123-b98373e88c1e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
3252dd4f-fc85-43fd-ac07-54e0bd73cec6 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
37fc1b02-059d-4954-8823-2897756d437b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
3f9ca84c-ed45-4a74-a1c2-30b1d847890f | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
4992da7c-5d6b-406e-a560-46267d3355e9 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
4ce1d739-0e10-4e61-ac8f-80b2d063391a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
4e5ddaff-d9ee-4aa7-b198-e914156e3f9b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
56640363-305b-4796-8fe4-b6a3a4edb1e0 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
5a441163-533b-45b0-9f6e-8b68f9d988dc | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
5d02d0ed-383c-4006-95bc-02c4de96f23c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
635888d4-19f9-4422-9cd3-40159f92eaf4 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
696f6861-cb91-4370-af66-0d7ed5758dd7 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
6eb8aeb1-93af-496c-a586-d2285f446c83 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
78d4a2b9-8bad-41af-9a78-08ea968e0b3b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
7c13e852-312a-461c-bb1c-43edb052e81c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
7cb9636b-fd28-489e-a13d-ea0273d0ab8e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
7fd72772-4251-4e41-9ab5-4b8eb355eb4c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
87452c8a-2cb3-4d27-985e-79f8b0281f06 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
889bff9f-a31d-4850-b111-451f0e2ddf96 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
952f498e-07e1-4040-be46-13afc3f2a7b6 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2 |  | 2021-04-16 | 2022-04-16 |  | Required to Re-inspect a subset of assets
96abef3b-ec1f-47fb-a988-f7c29c394695 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
97d57daf-34d2-408b-9d7d-b7854ea01e12 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
99ab8b9e-c923-4ce0-b46c-8e9890dd9355 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9a38cb32-db3f-4718-ad8c-14d0301a8464 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9b6e34f3-c54b-4c12-a78f-46301bceee21 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9bc6a260-8b08-4388-b606-cf0be95967fe | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9e1cc321-18c6-4c0f-a7da-55392c1ab5d9 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9e904ef8-ca92-4a6b-aceb-99903fd38385 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
a10efa60-7aaf-4d57-bd5d-3d98a3643c33 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
a2c570fa-56be-4b0f-8341-14a6346dc187 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
a32e8679-ade5-4414-b7b0-ea711c924fbf | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
ad404b88-053e-49ce-a0da-36e73fa27308 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
b2af9c76-9e3b-402c-a7ae-a6bf145fb1b9 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2
b5c61d2b-7aa4-4f81-962c-04c1a5322f9a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
b9459af1-e01c-4ac5-97d4-f9c730bae24c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
bbeaad8d-7068-47d4-9943-344369aaef27 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2 |  | 2021-04-16 | 2022-04-16 |  | Required to Re-inspect a subset of assets
c05c5e37-46f8-4884-a4a1-02e55cf07d01 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
c3adab76-6039-4b0f-b9a3-8b0cc8615c87 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
cb455cfb-e71c-49d4-bc3a-8e03a989c126 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
ccd2c51e-0b96-404f-a200-df16ef8e251d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
d4ad8854-dd45-42e2-99b2-4372fd81d10f | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
daccbe3a-1622-49f0-926d-70728282aeae | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
dc6844a5-dee1-4014-8e5e-f838a2050c65 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
e2f77868-b496-4e70-b56e-3abff794696e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
ef021309-ef28-42e4-a38b-f52b39a3be3d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
f5adcc77-8cea-4953-9be8-42183961fb0d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
001795d8-d8d7-47e5-ae00-a0f0a750b103 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
188852bf-7e31-4b74-a4c4-ab573fc2c8da | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
1cceb03c-0abd-464c-a263-ba99d2f8f8a9 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
3ec305a7-aaae-4075-9af0-f3363bf414be | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
3edb2e98-a5ea-4b36-b962-97e7297549c9 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
455d47fb-d0fe-488d-ad1f-66270ae21528 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
4a77bfff-337e-457c-a8d5-db6a23d03727 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
4dcd2a82-68dc-4042-814d-a94ea8fdbefa | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
5ea04825-81db-43de-b679-1a8403c36582 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
60d25ec9-0428-4b06-8fda-a2c588cbb12f | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
73070146-f2d2-4e7b-8283-23b2f9780d9e | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
8e4e0149-8380-45bf-8b88-c4e89585699f | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
9d28af65-1aae-4c86-b959-1da10c160023 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
c4fccad2-0f9a-46a5-bf54-406f1f4bf58e | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
d6d4af7e-2867-4f1b-b381-d8e649626bd8 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
e8f9bdf8-b321-43d3-9de9-d98143e3eed3 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
018e380a-947c-4810-9bbd-0c50e0e4f599 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
09f6d240-905a-461b-8bf8-d77ed594f31d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0af8fe6c-f7bd-49a3-b783-58724a11abce | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0b6c1320-fd8e-4acc-a649-1460e84bde4f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0c2a266b-6b1c-44e1-8939-d6e9d4526f41 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0dfe9e62-034e-4e88-8e99-f9eb51cc13d1 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0ffc3f4c-b098-4c17-b57f-1cea71085925 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1107750b-4798-4e6f-bfe0-10f4c75a568f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
130d4e00-1d0b-45db-8b0e-496b631714d4 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
136f9d67-de17-43ab-ac44-412b12d45e4b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
15d39de6-8a7c-492e-b609-485393d48f25 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
19d04e4a-0d37-47c3-b5fb-11be61ced039 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1a2fc922-0e03-4f4f-bc51-7a0c5ff0a0af | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1a5b203e-0bc2-4383-8309-bd1906cdf55f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1e6fb41e-5421-4e77-b774-9513d2dfeab2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1e930df5-fef5-48bc-b718-c7c50f6d4e5b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1fa5b571-4852-4f94-9695-7aacccd59534 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
224410c4-a0b1-40cb-bc33-1e20cd2ec6e7 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2325bf99-6f22-4c88-b432-566d72d80ad5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2638f325-4898-471f-b39d-64d934e31970 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2cb6e554-25b3-4ec2-948b-5e678c0acf70 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2df2ef07-ab06-4722-9193-34e78bf1b7f4 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2ebd9721-acaf-4a78-a137-6c52114f1ea1 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2f266d5f-de7a-407f-b136-73d3655c7278 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
304c4817-9e28-4f87-9f16-135ade81fdfe | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
36a22349-8c00-4aae-b1ab-13480c1db606 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
38311ffc-3747-40c7-a198-201a7674bd44 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
39a2f2d5-d782-434a-b82d-340e528ee5ac | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3c532d41-4e11-4ff7-a6f0-fa5fa2755ad0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3c6943ff-27fa-40b1-9c6e-a014d71fa691 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3d4d78dd-42d1-4d3b-a50b-46859f1376a8 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3f92e769-2ca6-4559-9cec-124d6c66410a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4126f051-f83a-495b-b0e8-0badba462f0e | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
488f9a81-77b7-4613-80da-f523e1254c92 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
489df34d-717f-4ac2-a712-1770661dddbf | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4b8a30f6-302c-4b76-8519-c472c4d7f8d3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4cfbd08c-11bd-4d9f-8869-8c7cca6cc794 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4dfae9a6-30e1-471a-8045-b9a99c196d8d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
52ab1469-0867-4595-9493-2eb36542a309 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
55501b28-ef41-46c4-bece-bf35aee83548 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
57bf5e4d-f016-4d6b-a6c7-0940cc00c167 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
5a597158-95ef-4c9b-8142-400bd172e179 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
5caae9f5-c314-4bad-bebd-5abad13f0a0d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
5dfd2579-bc42-435b-b102-9aec8fe0f2c0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
67d2c9ff-bd9b-426f-93c4-ff16e405c140 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
6b661b0a-36a7-442c-b66d-3181bb9e6580 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
6ea8b47c-7563-4659-850d-d0342618be7f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
709f3b95-8e3e-4bd0-9839-59f72ed8ba65 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
721a006f-09c1-4752-a4e1-493d95098d0c | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
72209d37-2179-4077-98cd-c290167c1b57 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
7bb558df-bd0a-4d42-ad2d-0eadf733395d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
81891eb4-0285-4b00-b3dd-11e17543c1c2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8304f19b-186a-46f6-bffe-b3a05bafd516 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
85d49349-3372-4df2-81b7-cddd8249a552 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
85db1d0e-fa0f-481a-97e2-412e55aad0f3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
87068f74-60ad-4336-86a6-860dd8b55f42 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
885217dd-8276-4bae-ac68-0ccee650d88b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8b81e8ce-de14-4e50-8b91-daee4836eae3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8b84ea1c-8793-48bd-9f46-3ce4aaf26963 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8bdaf38b-c989-4c03-b4e1-936772e85375 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
93ef954f-75a8-4751-bc2b-8ee73be93e61 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
940a2b00-fccb-4f4c-8a56-2bc8c598dba0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9498c9ab-e901-42e2-9b13-41bd1e0eb7ab | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
974ed518-130e-49a4-b47a-95d2b85901a5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9980b6f7-5641-47fe-8c2a-9baf7c4d7f63 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9b17161f-8c3f-4418-a8ca-bea4ef08e78a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9daaf1e5-89a2-4959-bf88-1dcf9a80ac27 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
a0e042cb-4458-4e5a-888d-46f2868fd6e2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
a2391e1c-451c-4256-9bff-b39d388eb895 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
a4e2e557-f66f-40d3-8ef6-0967856bb59d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
aa50cf13-be7c-4403-a954-0631041ae19a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
aa8b3c73-cb52-4308-9434-cc1cf2addde7 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
b1436b1c-8bcf-4a80-a466-9863da5a9aad | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
baec7f17-1d8d-4600-b986-4b813ce2beaa | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
bc0f2cc9-1474-4950-ac8b-6e6913b5e679 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
bfe436a5-a729-4ecb-8e2c-51e71db67b09 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c7f4c31a-bf49-42dd-a7eb-d8f3099fcc8b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c80d64e7-80f9-4c8c-97fe-d4a93e6ca127 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c8542491-e865-43e0-9a4f-67535513bdcb | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c907274e-1b71-46b4-b27c-fca780cbcbb0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
caf4fd7d-271b-46d1-9397-e04d18e3f5b6 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
cc0bd53b-fa69-46de-ae60-616818616496 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ce7c1fb0-7d96-4c48-899d-b02d32e8521b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d05e2b24-da5d-448a-ba90-0babb4cddf0f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d0bf7dad-6410-408c-adb1-cda2ef9b8bfe | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d25628c9-a142-46d4-a40f-4dfa083cc8d2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d7990b3b-b7fd-46e0-a899-26bce4bf9687 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
db43b801-97eb-41eb-bf09-85908d5d355d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
dc133c13-1dd4-4d88-a78b-aa847c1dc480 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
df4fc912-ba3a-4c9e-a1db-761b3e0d19bf | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
dfeafac8-b4fb-45b8-8136-032b2c9e23aa | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e2e2787e-ab37-43d4-a8bd-6bb36f8c4cf5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e356b4a7-a764-4a4a-b250-ad8182334898 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e67594c6-80fc-4e14-9192-5021f583407e | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e6a0f759-b684-40ca-9085-19665bd4fc0d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e9dba797-a711-46e3-9e8a-6e53b7504b84 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ea4358c6-86c1-436e-954e-e4d293d61fd9 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ea4db674-6372-4338-a213-1ba2c914aabd | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ebf595ee-2fc5-44e1-87d2-ab94f7c0ff64 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f0364de3-38b6-4579-a31a-87e341e14ae3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f10b59f1-d25e-477f-b843-5f13747e4fc0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f1335eb3-1fbd-4245-b8e8-692cb8406e6f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f2bede69-3eb9-477e-872a-f8621fd8fad8 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f4133813-d90d-4b8d-af40-55e5ea892bd0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f78438a9-eb3d-4086-8839-40c985cbdb99 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
fb907482-ebcc-45e9-bdb7-7bb4c7325669 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
fcbf3fd4-b0cd-4760-b7f9-b2af1c0f0ccd | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
fe634fba-7186-4898-a13b-626e52f7418d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ff13701b-d8ed-40b1-a94b-400d0e2efe4a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ffbfb881-ae1b-4ba2-9e3b-c7d6cc7d423f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
016de47e-ac16-4ae9-974c-85cb069a0068 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
01e17ebc-bdf4-4a1c-9a4e-a4053a4b0a4c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2021-04-15 | 2026-04-14 |  | Required to Re-inspect a subset of assets
092f20eb-d98b-4121-b115-56890e9c3a25 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
0aa31781-2582-4845-962c-8cdd2631662d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
0c666485-386c-4b59-900d-1efda3b4f1ce | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
0e3ea69b-4419-4f6b-8cd0-36be8afde6a9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
1130cbaf-ca1f-4143-82fa-dc54f3c73e93 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
12bd148b-ddbc-4f02-bc02-35d66aa798a6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
150a290a-fa44-431d-831a-0d45c6536cb9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
155a9102-ce41-4525-96bb-4e9e218116d8 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
1c1ad66d-52b3-4521-b5d0-1e86a18117d3 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
27db1a60-7eb3-41b3-bc90-36839b815a66 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
291692dd-fa0a-45b1-ab1d-7817cea70e53 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2a208ec8-3785-4200-81cf-7b99c6bd636d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2ded5301-cdcd-4744-9dcb-b1ac19c707f2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2f5ffcfd-0698-465c-a3bf-2fe14e4ecde7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2fc6b427-fc8d-4480-91dd-6e814be52699 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
338cbd3a-4c85-405e-8b8f-bf4e678d6d11 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
33b09294-571f-4543-81f8-de4eef4a698d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
364233ba-48a9-4630-8bab-77ddb66c71e4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
37441fdc-6a2b-4f0c-925a-fc14cdd0fe2d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
384e7e46-9b7c-428e-a620-258d6f42a838 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
385ac7fe-3ee9-489e-a3ec-c6ebc4b09bde | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
39a94e2e-9455-437d-8111-959907cc1919 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
3b77ffb5-ce56-453b-bf22-8cba81c67564 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
3fc797ee-0868-4a15-aea4-103adc2ad54d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
410d9361-8f75-40a8-a42e-46e8861c02bd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
456d3608-9550-4e96-9efc-3472a392ebd5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
4593022f-da59-4d37-a1ba-2c861ea2c86c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
55e5a746-db68-460f-95f4-5e49528826fa | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5909e2c8-2bc2-4b0e-b24d-fe8bbaaa0213 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
59638746-062d-43d1-b52a-7a41723fe40c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
59935878-a084-456d-9ecf-4bbf76be0387 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5b3d9ee6-6933-403d-8222-47592c421b9c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5eb88ab9-b27b-425c-917e-f94463d97d77 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5ed22696-98cf-4d9b-91a0-7c4a728af6e9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5f56bb5f-9cd6-4fb1-8a3c-a04c976b34dd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2021-05-24 | 2026-05-23 |  | Required to Re-inspect a subset of assets
63cad37a-749f-4094-aba0-47481db4c772 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6642fc8c-3637-4f3d-938c-3bb2c92e70d7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
685a536c-c659-47fc-a9a1-413ab21c5d38 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
68ede30f-4e51-4571-bfb7-3425113c7667 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
69bf8ad4-c344-4782-8606-a006492712e4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6a035814-8aac-432d-b0a9-3ae643effc8f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6a2604ac-328b-4e68-8fe4-e3cf9ae985f3 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6aad7281-c469-44b7-8bf0-c61d80443e2e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6c399e4b-69e0-4410-80c5-7bd3109a4bd6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6fe5b755-9c35-4afa-99d3-7390003f0382 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
70509ffb-06f1-4f99-bc1b-924bd4a2fe25 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
71fcd5da-68f3-43ce-a2fa-85b365d8e59f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
726137b2-25fa-4d46-8530-4701ba8a5542 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
76697788-29fe-40a6-9345-64aeec456774 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
77435444-98e3-4c7e-a8e5-dcf56a5fb792 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
77a87cf6-9909-46bb-83ff-d596eeeb422b | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
79005cb1-9a4d-4559-8664-97238b311bd0 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
7a26ca39-760d-4032-a468-1f38ffcdb0bd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
7dc95049-cce7-4bab-b1a8-a879afffc607 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
7dd236f7-5255-403e-b2c6-60efeb44f5b6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
82ba9dd8-8c34-48c7-93ff-3dff212e01eb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
84d5b6e1-0965-4885-97ba-8b26177dac88 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
863f4b77-9867-48bf-8863-d416d79d74d2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2021-06-29 | 2026-06-28 |  | Required to Re-inspect a subset of assets
88338fbc-b0c9-46b8-9e36-fd0e0105b74d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
8d733888-c52a-406a-8a05-c3876ea94763 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
8ffe057a-b4e6-44b6-b085-6e94ba1eea1c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
909d9418-0f50-4293-945d-e0318b0175d9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
92f3df32-83ba-489b-a899-0f29afe5c95e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
932cc9ac-8528-4217-9936-e44a3bd76fa4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
96e53035-709a-4439-9434-a986590e2dfa | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
997021d0-b955-4107-a0c3-ad96636ad6f1 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
9e7c5562-1003-4660-8343-df5753778e7e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
9f62e863-7b9e-40f4-97d6-570ef8aef2a0 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
9fe0a798-e1cd-402f-91bb-d4ab9718fc7c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
a77ff628-6127-4bd8-9b4d-1b05e7540605 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ab285fb4-6940-4489-ad35-103d1972c094 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ab54816a-a029-42c8-a71d-d6ca1d603a7e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ab7400f7-bf2e-4b36-bd8c-4dc8f433a08f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
b114f1d0-0e21-4b9c-9155-d245a0563289 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
b3c8123c-8fa1-4a3b-a81a-dc33d7ecb83e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
b73c7276-6cb9-4da3-a489-87c3dcce1f37 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
bb6494c2-3cd1-4286-a88e-552f7da99374 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
bfd55422-aa1d-4c08-ae75-a4efd9a7f51d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c21cf2fd-9ee5-4721-a0bc-2c3906d80d5e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c368069e-ab63-42e3-9d2d-acb03d404d1a | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c3c3981e-fbda-4e9d-9400-801dce639daf | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c6e2e9e6-3af1-4670-b774-95928ffc94b7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c94e826c-39a1-4559-8070-57d317f0c003 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c9acc18f-bd41-4539-b9ef-d3b4e3be4363 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ca15506c-e4b0-4ba2-bf8e-4ab83ab4c38b | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ceb57227-dd31-4ad7-9090-151b25e4f856 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
cf0bdde3-9846-4959-bc29-f3d3957bdb01 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
cf4df3f3-b5b8-465d-8dda-d02feb2c1058 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d18a9d65-36a9-4723-9bbe-2626220b0667 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d21e9052-05af-4895-912a-4b87437d2abb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d39a0d31-2b91-4f10-b5f8-90195a5ccb8c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d8c02533-cde1-4616-bcc4-764edfca56f2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
db5e2e0c-f22d-482a-9ed5-eac4f6e1e987 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
dec26b87-b825-4210-aea5-ac46932ea715 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
df8ab364-0589-4645-809a-dcf2aef9d528 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
dfbb6664-0216-49d1-802f-55a86a33ee09 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
e00d3961-74a0-4de0-b612-b3287720a3eb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e0923553-285a-4aca-8f7a-e9d4c54b3aa5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e13cdb5b-f8c6-4f15-8949-1f3f68280fa5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e22be44a-1efa-4075-abfa-d0a2efa4b2d6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e3f816c8-d3ba-4b80-a92d-a318ec5a8d58 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e4c08b8f-339d-4eab-8ec3-9f9833d47261 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e619b660-f1ea-4678-9fff-5c45931b6a7f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e7ed035e-3882-4647-9f92-34f5b1b39e10 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e89d5933-a6c8-4c35-a3a6-c8dae02a3c41 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ec0e4c9e-7796-4b2f-904e-b8ae1c8560f7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ee40f41c-e415-4389-ad21-dd368a8dd9d2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
eeb1defd-1415-4b79-9af7-ce79922ae44c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
efb05e35-63c0-4d65-a961-5cf07756494f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
f18fa482-e68f-4d93-9c77-59365cc3c7bc | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
f515ffe5-fa3b-44c4-a54e-a214003da4b9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
fa71151c-810d-415f-86d0-54c733efcefc | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
fc20c68f-8a02-4d1c-8816-196bec0ebb3d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
00784bfc-aa4e-401d-8cb3-5ea57aa86b66 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
00ec779c-eb12-48d4-804f-c13cb846c68c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
01a1e930-8bfd-462a-9ff8-28c5ca3bcbd3 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
049e3cdb-38a5-461d-8e69-7a855821562f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0680f2c1-8054-4e8d-a60b-4d3b2331932d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0989dc6e-ae07-4eda-8b9a-7947360344b6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0a6911e5-3ecb-499d-8519-23f292e2ee2a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0ab08512-65f3-404f-b99f-6f4110b1907d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0af5cae6-5c55-43b8-bfe7-0e8e127c9cc2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0b449792-eb3a-46c6-8f30-d04c1a4275a9 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0d1aeec7-c8ae-4d0e-890e-e418534f6367 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0db40024-2eb8-443a-82d3-44c306be3b46 | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2
0ee9daa5-cd0a-433e-a41b-ab2f09e097d1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
14765d57-5199-4faf-8067-754407c46ec8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
16e854ad-3e9c-4559-8c18-4138240fd24e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
177ac5a9-cd72-4674-93be-03e0b26071a2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1c49a69d-3c87-437d-99ae-9913f423aa6b | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e399946-4e29-446a-ada9-87a6f56a4436 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e3cc06f-87cf-48f5-ba76-37fbf86dd601 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e47fb8a-633b-4db9-abfe-01d127932c0b | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e6c7d78-b821-4305-bb63-665abbb459d2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1f55b1f0-e131-4dd8-a30f-9e0638fa8636 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
20355b09-f97b-49df-8aaa-181965450382 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
21814b91-fdf5-42f5-bd64-63d8de4714e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2235dfe3-7c8c-47b5-9bb3-bd5398c06db6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2257e7dc-45b9-4f4b-917e-fe1db5251496 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2732e135-2118-40df-a459-a1351ff942e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
287a91da-c557-46ac-975b-684d2d417462 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | Required to Re-inspect a subset of assets
28c6732b-7ce4-46c0-ae01-07714309cf4f | pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
28e94845-96fb-4387-a992-0d43789dbb43 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2a886aa9-6ebd-4fe0-953c-ec90f93aa0a0 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2a9cb56e-db86-4e1d-82fc-a3e544af255f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2afe0aa0-29a4-4492-98e2-ba8d35e7c57d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2dce39a7-222e-4aea-8163-92d5c7de4644 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3531e3c6-68d3-4687-b5fe-a70e10e7c773 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
36719411-5eb0-44cf-93bb-5f2a3381bae1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3bc8d9bc-10f2-4183-acf3-fdbeb7fbaeef | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | Required to Re-inspect a subset of assets
3d951ac9-4003-49c1-9d35-9ba373c41067 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3de89cfa-4381-46d0-8356-6444256d0c60 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3fbcfa36-5e57-4280-9b0c-b3eceb5e1303 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
459f694b-8792-4467-ac68-cf8f98030fd1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
460f2025-530b-4c60-b4f4-22343d8eea7c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
4a99594b-e709-4232-85ed-f2f830356b6a | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | 2021-11-10 | 2022-11-10 |  | Required to Re-inspect a subset of assets
4d168164-34f7-4d5b-a4e6-42ca58b013fa | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5303fd3b-93bf-449e-a899-b0cbc43a43d4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5934d853-9693-4572-9eee-2f39c7cba159 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
59ccace7-f6fb-4def-b050-181734132481 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5f76f859-8d4c-41e6-af95-a34a107a73ac | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5fc9948a-a322-402b-8a36-c511e264de74 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
65605fe1-44cf-4653-857f-bfc088019f8c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
656cd643-361c-4c01-8138-e727a53db9ff | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | Required to Re-inspect a subset of assets
662a1fa6-a019-4578-86e2-e4d9e82bb285 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
66e88ea4-2b44-4628-96fd-37f36ace2cf6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
6ab39443-84d3-4b43-9d17-9347d1511f5e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
6b7bc8f4-f818-4114-accc-0ba4383e9104 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | Required to Re-inspect a subset of assets
70ec3213-18de-483f-93b3-f521470d788c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
7511b759-3986-49b9-8a46-92fc3f4daaf9 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
7bec93b9-3acf-43fe-af3d-4bd326ff1cca | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
7d381d25-7b50-49ba-921c-dcd194958e55 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
85591d6f-5225-401a-8421-1aa41d5e44e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
8a927bb1-878b-42bc-b8c5-fbabdb4834e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
8b2830f1-2494-4494-9581-97041f0d8d82 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
8b399519-6373-4863-9ab5-b17050739f97 | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2
940ce92b-4bd0-4000-808a-814be67cbaf1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
948a7c6d-6da5-423f-b48d-7dd5785c6052 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
94b0cee8-ecfd-40fa-a49e-c72042900252 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9a48666b-5954-4e17-8e2e-13c0c2af7ecd | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9cffeb8c-cdb5-48de-ba82-41b5b3f2024e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9d7ecb32-74e6-4b45-877d-45f01c9bb3c4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9dbf5f10-0543-4aca-b696-74a03a69a732 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
a5aa7bb1-6234-42d3-b7df-147264f95079 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
a8a8ccb3-3444-4e3a-8b6a-ab99a23e81fe | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
a8db26bb-c05f-47e0-a589-2bf2a05276c7 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
b1990580-29f9-4f5b-9f4e-aecc429e9a05 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
b5bec8e3-8013-448c-9cd6-fd0017f81029 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ba4a9d4c-d19a-46bc-bba9-bbaa89a36618 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bb1c0598-e0b7-469c-8e05-a5127d1d028a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bd906c22-52c1-4e53-855d-048666ebf3aa | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bf65479c-d7fc-4dab-be80-f42c588c48eb | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bf979a9a-e453-4e87-bd38-930a475e62d4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
c6bda757-da5c-416e-a0d2-5f8b88c234e7 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
c8917a6e-7690-4fd9-bf9b-6a5ad105f978 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
cc10387c-8083-4a11-8741-08174f7ce52e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ce5de478-9be1-413f-bd57-290980287b40 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ce9f8d44-26bb-4841-a8c8-d43966759fdd | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | 2021-11-08 | 2022-11-08 |  | Required to Re-inspect a subset of assets
cf53685f-6bca-45d0-9c7c-b6ca796910e8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d285b588-71ca-4067-9f56-d9d53cdebf18 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d523fe1f-f25b-4c80-abe0-90ef889f6d17 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d6ae9d52-065b-40fc-aba4-fea0f364199d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d7444693-fb4b-4bb8-8487-2c240599d7b2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d7cfd504-78f0-4148-8f07-a8bfc885fccd | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e00e6ee7-915b-4846-bd3d-d3467e3f9a97 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e4425c75-4c89-4ba2-a83a-726fd5ceb60a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e731d4cd-5abd-43fa-9d39-0f3fe21fb5e8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e7b3191f-e0aa-4b2f-a962-db5e98e91018 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e8163cfe-dc38-44d4-9150-284e9a83f924 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e98947ef-2596-4287-af6c-fca455145239 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ea560e12-6bbe-4a21-8697-6ed8c3bd69d6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ea8243de-0f7d-4e75-af5e-521bdb3f2b0a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
f1caca33-bc9b-4326-ac62-14e643a2208a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ff5a0709-52a6-403f-bfea-580d05329914 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
04614e75-11ae-419d-a151-f8962ee01168 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
0798a37c-6e73-43be-a6af-9d527de937ce | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
0aae8441-c6b5-4752-99d7-5319d558b075 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
0d64303a-aab3-4e26-a2a2-f1687291831a | Pole | 3 | Transmission | 2020-08-06 | 2021-02-02 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
152f7142-95eb-443d-bf16-4adb53721e55 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
1be441be-fd15-424a-b32e-08f638bdfdbd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
1cb4e5d9-7f76-4ae3-b4bb-492ee919388c | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
1f812904-ae9e-4ee8-8eea-ce4e4fbb3535 | Pole | 2 | Transmission | 2020-08-06 | 2021-08-06 | Level 2
1fbb3618-1ef4-42ba-8d11-45589f9cb6fd | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
21277841-1680-42dd-860b-7e81da34e133 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
21493901-e1ad-4891-bd75-8aef6c61586b | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2167a372-0b16-489d-a25c-813e2199c73e | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
22b04be1-4ccb-449f-9929-b94d8b5bc871 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
23702c38-4150-40ce-aff3-5a032fee91cb | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
273dd98e-be57-48fa-960f-23575d9ace86 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
27c7108d-946a-4542-a3fa-44291b8fc6e5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2ac5f31b-18a1-430f-b01f-244b6f330998 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2bb14fb0-8ed5-42b7-a13d-0dac281e73b5 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
2c67edb4-a078-4b7c-87b2-a7c8d7c17bfa | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2ed522c4-2c00-4c45-be3d-477a6e35e73e | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
306a8452-4d4c-43e2-9429-343854a70dd1 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
31ff1148-68cd-4375-a5a4-52f6159da0b5 | Pole | 3 | Transmission | 2020-08-06 | 2021-02-02 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
336992f0-33d9-472b-a198-9a7f70d73ea6 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
339260b7-56da-481b-812b-b5060715ecc9 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
34a41090-2455-4a09-9d58-0018a6e1436e | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
3b142276-1b53-4ab6-b782-dcee543537f0 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
3e844e3d-4274-4b58-b89f-4d9b01e6d81f | Pole | 3 | Transmission | 2020-08-06 | 2021-02-02 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
431d602f-04cd-40aa-9cd6-0a867182e4ed | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
4e1f38f0-b338-438a-9ceb-cf48f0d62f02 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
4f7c55ca-9bcc-4851-89e9-be2df314aa65 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
50d2d93c-64c0-448c-a8f6-a90585d6f9d2 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
51b846b8-f1e6-461a-81d9-06bd4346b6fd | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
53c19b41-c407-4d31-ac65-922b982df8c5 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
5baf9f7e-b80a-433a-a64d-d24ef462aedd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
5cd7e909-36a5-4dbf-87c6-5a96c28a285d | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
5eff9fa5-ae71-4c6b-b9a1-24d8d5ef5f03 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
66492662-7246-4545-9615-9486a83bd365 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
6780215e-6d92-4338-8380-50603cd9effb | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
749ce49c-ce96-4cf7-8548-9ceb7c928c31 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
797ecf81-1a20-469a-bfa5-2aec7609fbec | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
79b2a4dd-6511-42d1-868f-5322cd1d6370 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7b16aab1-5b31-4e76-994f-81f0155f3c40 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7b1a224c-d871-447b-b280-e65de7e8b020 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
7c893b1d-e7ec-42f7-bccc-7b55f40aa1dd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
7d14871a-915c-42a5-8bd5-5a395461f090 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7e0bf980-d8bc-4529-adbc-996b7aa5aa93 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7f63c267-dc36-473b-b8b8-1892b68830c6 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
8038b02f-2539-485a-8f60-1cb29129256a | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
822112db-b37f-4904-8c6d-e54ee88b8d62 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
86b60daf-887b-4caf-ab67-e30d06efd9de | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
89562b8d-c9f5-4dbc-9ab1-b3c708b740ba | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
8b23763b-e982-41fe-8d50-ea375b106be3 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
8b27b12a-e1d8-4b29-843d-143c552a6787 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2021-06-30 | 2026-06-29 |  | Required to Re-inspect a subset of assets
8c673f87-a295-4fc9-b77d-9201603ef82a | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
8f591d33-5cb6-4257-825f-d8fae9d60b0c | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2021-06-01 | 2026-05-31 |  | Required to Re-inspect a subset of assets
8fa28f4b-faa9-425a-bb4f-3d10fbc02d78 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
90bf984b-2b8e-4ca4-98fb-561c49819037 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
93e5284d-7508-4b1a-a31c-3a63489558cc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
94a0f837-7a7f-4e5b-a606-433ae1e2d179 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
9803feef-11e3-41c1-8fca-ee8702f1b767 | Pole | 2 | Transmission | 2020-08-06 | 2021-08-06 | Level 2
99a04e76-b79c-4bca-a78b-469ba67619b0 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
9c60ff2c-058b-4549-bada-efba859c7ffc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
a060a7e6-f8ec-4845-9abf-b1bb5ce5a2df | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
a0c24945-a699-48c2-af2a-07715f737b44 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
a5bb8fab-4d50-4a13-91ac-8d83520dd434 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
a5c7bef8-b9b7-4317-9206-20d6fc73fd21 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
a8a66c1f-1872-407f-a13e-3074a1c2e581 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
b092926a-4f95-4926-b0a6-8000ffc7f819 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
b20ef1aa-a86a-455b-b280-8532554c1277 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
b797b66f-0f10-4012-91b0-216ae24bad62 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
b7c5e067-fcd8-419b-8a8c-58f1ece0cdc5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
b81a658e-396a-48b4-b9aa-35564ff30269 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
b86c43a0-ff8c-4e98-afea-44fd7fe37b3d | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
bd51a076-16fd-452a-b2fc-fd5437ed8bc1 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
bd84bb2e-1ce8-418b-a7ba-5857da0cecc7 | Pole | 3 | Transmission | 2020-08-06 | 2021-02-02 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
bed3caaa-573f-450d-943a-ea560626a283 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
bf2ed20a-b677-454d-af48-a3a8b4f1ad2c | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
c08ef8ff-b904-4b2c-9b7a-f5ec4d02185e | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
c0a18295-55fe-4762-b589-76d5d83b3d82 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
c1717a43-c82f-428d-93d4-cccfc5f33e77 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
c3a00615-bd6f-480f-9a1b-ef9d536e0c56 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
c5262d63-f7a7-4b6e-b548-009234183927 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
d035dba8-17b6-49c1-8bd7-914b4f6e1bcc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d4883218-9e77-450a-a09c-ae2529abe71c | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d6ebea98-2c75-4b76-88ba-e756ba58f37a | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d7997488-3ea8-4478-a492-b2b88e69131e | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d9dc8d8c-cb3b-4dc7-a651-b46e88169341 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
e12f340d-b8e5-4437-a0dc-552558de9ebc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
e21d1c4b-40bc-4e24-a1ec-ce545d9874a9 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
eb488266-1193-40a7-887f-6f4ff76d29e5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
ed28f450-96cf-4737-93ad-f9cdbf23fd67 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
ede784ad-c97d-4b07-ada1-e9e942370bd8 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
f1f65302-a38c-4800-bcda-ebbbf44788be | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
f21b2d06-6edd-433c-98dd-c78c9d99d776 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
fdc0f9b1-3315-40be-980b-beafe5bd0791 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
fdee82da-cda0-4304-a5e4-a35bac3771b7 | Pole | 3 | Transmission | 2020-08-06 | 2021-02-02 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
fee556ad-f08c-4ab7-8dfc-5f6b7b765e34 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
0033f633-775a-42a1-8d8b-5a5f681d458e | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
0223d736-bf71-4c13-8be7-40cfd5051cd4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
02246cbe-3a83-455a-b774-5911ef51b30f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
094f0ba7-79b7-4d9d-9cd1-8a4d310e5650 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
0988a21c-1ae9-433e-8a3c-48e39d169683 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
0ba60eab-d404-495f-aa44-cf6d1fc14b99 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
0d1e452e-eb78-4476-bbe5-4dfc7cfe0881 | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2
0d4077f1-04db-495f-b1ff-97570487daac | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
1029d0ee-ccb1-4168-aa4b-cdc166633f86 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
1216475a-12c9-471b-af5c-104eb774e9f0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
144134f3-759d-481f-a7ef-602c3cc8b989 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
15570870-31e7-40fc-bb11-b47a8031a01f | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
1a1496b2-c0c0-4a27-a30a-8ee41d4092a9 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
1b6c5f96-1900-4cdd-ac81-f61ac23a20e4 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
21aeb734-edba-4b2e-91b5-d718b296cd1b | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
22fe7f11-5d91-4941-8645-a81f949cfe9c | Pole | 3 | Transmission | 2020-08-07 | 2021-02-03 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
28ab91d9-51f5-45cb-80c0-aa60b4230ae4 | Pole | 3 | Distribution | 2020-08-07 | 2021-02-03 | Level 2 |  | 2021-03-31 | 2021-09-27 |  | Required to Re-inspect a subset of assets
2b7e82c2-5850-4e5e-8b28-00093f17b058 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
2cdefd32-ab80-4864-8b80-80dc20b3d859 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
2e7a1a36-0959-4f56-9a54-b103d5b34f6f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
3207da94-8793-4188-b5fe-971ac3ead86d | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
374f97d3-3153-477d-b45c-87c49be15760 | Pole | 3 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | 2021-05-17 | 2026-05-16 |  | Required to Re-inspect a subset of assets
3dfe287f-2078-422a-b56c-8ea1e47efac4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
3e958964-2e7d-457b-97b3-590fed72085c | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
43990ec4-c3e9-4fee-bbba-626312ca730d | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2
441c15d8-87bb-4617-9b9e-834d29b1a0d9 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
4bcd46ac-01d5-4b3a-875f-5d09d6a9f691 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
4f2b7a14-8989-4ae0-b19f-4f5c97080968 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
4f31a43e-46a8-4604-b908-be1042ed4c51 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
504d0ab9-e61e-4108-a817-4721caba8e2f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
5391c9a3-4564-420c-9504-23637ecc6973 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
53ec9e31-08e1-43eb-b958-60ece6e6e657 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
54d6b2fd-d106-46b8-9913-881257d831fa | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
57357c9c-4260-46d6-91e6-ee618d65e684 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
58ceca54-a69b-4265-beae-10bcdb14967c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
62054625-3946-455b-98ee-8afbab0f20d7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
631b9428-9efd-466b-833e-f73802a748a6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
6384113b-954c-4046-8962-86b2f630d0f6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
64725eca-f689-41d0-8925-050fe44435e8 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
670f770c-2367-49c9-aa26-3134c8f0a2cf | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
6883a39b-cd22-43ff-b74d-38de1e837e60 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
6a1a7c52-a491-41e1-b2bf-4bd62b7abb37 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
6d2c645d-b53e-4655-bad5-5d56d72b64ef | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
7091401a-2cf8-44ff-91ef-8e5651c58f78 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
71b3b1c8-2433-43c1-84d3-721ddea6c241 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
75aa3e2d-133f-424c-8700-c1a9216172c9 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
7633d2c6-12c4-4f55-a8f2-63aa8d59b96e | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
7637161e-21ee-44a7-80b6-f7b4d37eed11 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
77910078-a650-4efe-ad18-4bf4d053be01 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
78338716-93a0-4bb6-8fbe-dcfaf66d0376 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
78c5593a-2ba5-436b-93ff-b66dda796582 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
7969d91b-d734-4237-8c96-a44b4be48c1e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
79a520d2-0a98-4212-8254-fc4f8bf73b94 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
79e9deca-358b-457a-b0de-968b6ee90b06 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
7d838af6-e97d-44a2-8ff7-7dd12a0c243c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
832e4cd2-2244-4f37-ad5f-75b3b83231b6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
83c0920f-a3ea-488d-a74b-4bb14a3444c0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2021-06-01 | 2026-05-31 |  | Required to Re-inspect a subset of assets
898fb4e4-2a41-4d44-97e9-9e41d64bf08c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
89b76d8a-6f80-4695-98ca-de37aac708e8 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
8f11bc46-f3c2-4be1-9811-d23156f8ef5e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
900b2a71-16cb-4cff-ab05-b775bf0fad3a | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
93aa8a56-96f7-480f-b605-68aff92bfc92 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | 2021-05-17 | 2022-05-17 |  | Required to Re-inspect a subset of assets
93b164b3-f9ef-4b13-9734-422b08aef464 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
949cf6f0-584d-44ab-8202-79dd1f5cfcdf | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
952397e1-3130-49a7-8084-6dfaeb0da75e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
95307ad0-66fa-47d0-8150-7beb6e60c230 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
95d5b573-c3eb-44d5-b1dd-50aa9de901de | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2021-06-01 | 2026-05-31 |  | Required to Re-inspect a subset of assets
96a1e0a9-c7aa-4293-bfe2-348cfbe5850b | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
975d52ec-8dc9-48cc-b90d-d1e43cc89a0f | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2
987f479b-8039-440a-b286-fcac2b2a7a09 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
988ca0e3-1467-49c8-b36d-bef4c9ab222b | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
9bce5e35-3fd9-4dca-80f3-c1ad98b231cd | Pole | 0 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
9cc4f567-2d93-4b55-8d49-86cda292dcb4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
9e85afe4-727c-46c6-a5fe-547454adeda6 | Pole | 3 | Transmission | 2020-08-07 | 2021-02-03 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
9eb4d24c-e04c-4494-9b2e-c86ee8d2deb2 | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2
a0091864-a088-4820-846f-850e54b4c4dc | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
a0c744c0-8453-427b-934a-0d27604ea11a | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
a603589d-404a-4163-a1de-9309aabe10e0 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
abcc1f25-862a-4655-8237-5f54c8adf17a | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
acdde7ec-7dd9-4c89-915f-5a09470831b7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
ae7b9670-b59f-4cfb-9c42-5b0ae48ffede | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
af96a897-1d36-4bd5-9434-6a28ba0fbb74 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
b5be4d08-7f9b-4d72-b2c3-6f875059f1b4 | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2
b7f500bc-cff1-4176-9ce7-330219743bec | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
ba80bbf8-ce69-412b-95e2-ca531209a50e | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
bfeddf90-70b1-4f83-9fc6-e297d3df690a | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
c28b6284-6d21-4baf-906a-af4bd038798f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
c4e595e0-242a-499e-9d63-29cd2294e329 | Pole | 3 | Transmission | 2020-08-07 | 2021-02-03 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
c56830f5-4972-4233-9d88-2812d201d127 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
c7347d5b-8e51-455f-a754-0aae2c6da479 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
cae9bbb5-e019-46dc-b780-31c6d71512f7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
cd6ee233-a8ff-4a4a-8880-bb43e9bad7a7 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
cee3372f-f1c0-46f7-a194-9d7fa634f59a | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
d42b0df8-9bf9-46ab-88ec-457838d09f9d | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
d799e9ac-d124-4713-9a7c-c0d589d378d4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
d8513130-8605-4eb3-b92a-821d21c1614f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
da86f739-68db-471b-878c-c43d5c67e176 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
db98aabd-62dc-4bfe-beb9-e58c9734a5f0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
db9e3513-c175-4a57-a482-e5e8f6282133 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e3284f93-d64e-44ac-80b5-38be06ad72bd | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e38ade05-f812-4b3b-8351-e27efda55cc4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e4c4d3cb-c410-460c-aee3-947a3c96d051 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e95092dd-5f86-4f4d-9b14-e2faa64316d5 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
ecbdd67b-529e-44b6-bbfb-e05edbc80dd1 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
eff14bc2-9cbb-410f-bea9-35dd0a4ee602 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
f34e57ca-c632-4e55-b81e-9175f53c5a45 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
f4cedd95-44a0-4ce2-b023-410875eb848f | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
fd99e5b5-7ebc-4baa-a229-2e91211a0a60 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
ff686600-44d8-454b-bb77-c03308af28e2 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
0771a3fd-b22b-488a-bfea-ccb93d9025bc | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
09d38a63-2124-4bfe-a326-4a89b64d92a4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
09dfe4ef-a759-4b86-9016-2c895c06a713 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0a163401-b722-4f99-a8ce-fd38fa842878 | Pole | 3 | Distribution | 2020-08-08 | 2021-02-04 | Level 2
0a62a4fc-08a0-4811-aad9-1b0d73fd17c4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0b168aec-76d1-48ec-9d86-6777d1afb3a6 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0b8ce194-b19c-4595-b2c8-95e5cc7a7415 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0d04d559-6add-494f-b154-163ddd155afc | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0f39039f-7552-41e2-9292-8a858bb32cf4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
114f1cc8-b4a5-434c-bcbe-d05606eb152f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
12451f30-7775-46bf-90e4-e5679e5678cb | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
1bebb68c-d6cc-4638-8dd7-e0af5c46e470 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
24d8636d-d2ad-448c-b203-cb55973ef767 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
262790ad-73d1-4107-acda-5f78efff53c9 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
354e0b99-e20d-412f-bead-bee2b7ef7cb0 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
376d17c0-bcc5-4a4f-a959-401440a0937c | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
3795a344-c14e-4004-a738-a09aa39db785 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
381a9021-335e-4d31-8753-f4b5b3c3c402 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
384030ba-2fd3-40ce-8218-262c10ff1bb9 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
4615da5e-caff-4528-92a2-3c84b03b294c | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
48c67562-3f9e-42fc-925c-e91777125ac4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
49c141bd-86fd-4d37-94f5-2ee2479ab9fe | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
4e768e82-a505-4442-b95d-0c69977ebcee | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
52bea135-6342-49c4-b224-96a154c6fdec | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
556ef512-1961-49f4-a841-f5032e796ebb | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
5df46407-b24d-4bd0-9a6b-52d6364d25b4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
61146b59-2f58-4c33-83ac-a6892b4a75c4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
6333adf6-3f33-44ba-bd44-0f5a0a6e1f85 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
66711678-afd0-4a1e-829d-75dcdc438fa3 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
67347856-db2e-4591-b79c-37ce9016f4f8 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
6cd0a2e7-a269-4fda-aab6-0c9f54b5bdb0 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
6d34b0ea-e4e8-4d78-a276-f3dd283ef829 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
71ef0733-318a-4aaf-b2e2-ce5df17c64b7 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
76631a4f-4d31-4b6c-9853-09a5d1af81eb | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
76c48ad8-f71f-45a0-8c55-e86007388f7f | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
79aac699-d5fc-4aff-91b7-77075ead77d1 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
7e6acdf8-2059-41d4-bbbb-c8c0490b7a6c | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
7f2afca6-7bd3-4b31-9e5b-91991cb25e05 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
7f48c2cd-6592-4f00-85ba-093f316fc9dc | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
88b05b64-e38e-4f30-9ab5-ea3da6b979bd | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
8ed209a0-9924-4d32-a293-fd2c452feef2 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9154720c-f78e-4969-a4da-a2d63af6b8c1 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9557d04e-7e05-4905-8839-90a6778671f2 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9570cb38-1dc7-4630-815a-840d66c6d2fe | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
96b8c7ca-f31a-484d-8570-396c38d818aa | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
980f09f8-9921-4048-825f-99afcb5d9c7c | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9c137735-85a6-4d22-8473-2aaac15d119f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
a9873b68-eac2-4780-9b11-3d2a7967842d | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
ab9841af-1aa9-4bbf-9d47-5c7e461e4c2d | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
af21bcd9-e913-49a9-9d60-d91e0175062a | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b25d2d8c-4dca-40ac-a79f-7090a5638a54 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b4208164-897b-4fa0-81a8-16ecd0ff19ab | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b5b7eaa5-a391-49e3-9b2c-d01e9e86f1d0 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b94ed509-ec1f-4dc3-898b-b4b12f1f9dc4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b9ba4abf-b5a5-4766-a983-f6b105826f9f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
bb500cd1-4278-4b62-97f5-fd714f0c1778 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
bbe6edfa-e325-47e1-843e-fa758a3a32cf | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
c0651488-7b56-43f9-bd19-f8c1df98af19 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
c160f3e8-6e96-4131-b409-7fcb66cc2237 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
c846bcea-9f1c-4acf-8d31-f9c28e55a50e | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
cc602c02-c923-4901-b516-a3ca9a30498e | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
cddb1b7b-d8a0-4f05-82ac-70f66e4095f4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
ce1fdb9c-d8ae-4185-ab97-3a3c61f60f32 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d2146ed7-947c-4121-b85b-d983dfd9fd55 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d293ce12-3567-4dcf-9817-528cc753b2d9 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d2a9964d-2593-4591-8db1-5b95c98e4c8d | Pole | 3 | Distribution | 2020-08-08 | 2021-02-04 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
d6b027b0-79c8-4973-907a-080eb0c68013 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d94fe4fa-22a2-421b-b8ac-bce559f0ee3e | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
de5ac015-6037-4fa5-8802-cf5c951b6b4d | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
ded8bbee-d4a2-4034-8588-ff9738d3721b | Pole | 2 | Distribution | 2020-08-08 | 2021-08-08 | Level 2
e262779a-7db1-4491-a6d8-086e748f6081 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e484adaa-c8d7-43d5-acb9-f93f4adc6695 | Pole | 2 | Distribution | 2020-08-08 | 2021-08-08 | Level 2
e5fee9dc-b689-44d6-9157-f130b868ce51 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e8ad5662-8c0f-4209-9a0a-7bf58ce843a4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e8ed8f4f-b11b-4888-85c7-64f818e6754f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e9228c32-2489-481b-af57-491a11847902 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
f31620c4-3cc4-450d-bbfd-a5ff3870e74a | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
f9dba5a7-7aa4-4822-b00a-f896dd24f44e | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0021fc77-89bd-428c-8869-006b584bec4e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
03c319fb-8baf-4b34-ae6b-4062f03464e3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
04fb9588-5210-4f12-9594-7a584ad9a3ee | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
058a6018-0adf-441f-98d4-700424598959 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
0846c154-c3fb-429a-b0ef-0c4a15a265d9 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
0cc66d0d-b590-46b6-a33d-70d8b2e6bcc3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
0da049a3-ad51-409b-979f-08da6c2f9e03 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
0ebcbba0-01ea-4b94-9d1e-f66ed002f129 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
13fdc2a0-0af6-4114-bb88-2223c46c8f56 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
144fe3d9-06cc-42d6-aa6e-ef1285809bd7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
1c041453-c3ee-40da-a0d9-f6120ab35595 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
1c701eef-2410-47d2-b44f-84843338f3b6 | Pole | 3 | Transmission | 2020-08-10 | 2021-02-06 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
21be9825-f584-494f-b1ec-5e777ea1caef | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
25a1499d-73b7-4d37-823e-5ba4571711a2 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
27fbeef5-7241-4a5c-a0d7-947c2298347b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
28d9fc91-ea07-46e6-929f-da4296d8024c | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
2996ddf8-389e-43d2-99f9-c3234e9a1cf9 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
2f378d56-0883-4d52-8602-1f73fcaa44de | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2
312564e7-7af6-4612-9d9a-200747f7c84e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
31a10354-8cb5-44db-b3d0-1cc82f2b5971 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
3314f109-ef76-4222-87a0-ce35dbc9cd85 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | 2021-05-10 | 2026-05-09 |  | Required to Re-inspect a subset of assets
344e7ce4-34cc-48a0-b396-4ebdda41cd7a | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
38217f5a-fd7d-4faf-994c-8b3a0c86ba9d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
3e1644dd-fa31-4155-830c-28a9db266c12 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
3f18ce0d-a86d-4518-a486-a74fe1d4c001 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
40ab11a5-779a-4454-aa04-8b481458511f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
4305e7cb-770c-4e32-a2ef-f981ea180cc7 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
4be147d2-adee-4e89-988d-99ddd736afe4 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
4d82cfc1-b1c4-40bf-aaba-3ab3cc252481 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
5084c38a-7ff3-4f68-a164-b1135835b633 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
50c1ca9e-2ef3-473d-995a-e1906b0e2f6b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
544b6797-3133-4f1a-adf3-de312306f3bf | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
55cf549a-ff24-44a4-ab8d-c49bc1d902c4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
57db1d8a-50fc-42c9-8105-39ddaaf25e48 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
5c82b238-5f98-458a-956a-9c3545cdd839 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
61cf29bb-87cb-4380-b25a-907f2655c439 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
676acd28-4dda-4019-a5d0-1f18a3771d98 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
6840d229-2c61-4b56-b767-50d2a9ba57be | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
6d34c4f4-418e-443a-8e05-fd1208133649 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
6e9211bb-2b2f-41b9-9fc7-c9f9dce4317e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
71f62ba5-20b9-413c-a158-b43c912507a3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
73c4a8cc-c28a-4133-adf5-f637528fc4eb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
7c36f091-643d-436f-ac02-72472b8b16c9 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
7dd5160d-be73-4133-bd97-b755def7547d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
7ec4a4b0-2347-4191-8718-65a3f7f16ec0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8032e7d3-27aa-4e0d-8b05-623edea9d822 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
829ea974-07c2-455f-a205-271d72e99bf7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
838fb907-b3a0-406a-9072-1e399d78eefa | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
83f69566-1b33-43b7-b18d-921305b57c0b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8acfa16a-29ac-4bd7-9d9d-df7c3965c57f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8cf50f29-a20f-47c2-8a96-fb48aeb7f68f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8e2824f2-b72e-489f-9ecd-9d75b31455e1 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8ee43334-1b02-4a45-a3c7-fdea37e6bfb2 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
8efbfe7e-51f5-4ae3-9891-e1721e725657 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
94af3719-8cdb-46f6-9550-7e1ce66b02df | Pole | 3 | Transmission | 2020-08-10 | 2021-02-06 | Level 2 |  |  |  |  | Required to Re-inspect a subset of assets
96a0cfa9-903b-4fde-ac99-3d4afe2a256f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
9a818497-6161-49c5-bc29-7d07af6968d1 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
9b6215a1-4bf0-43b9-a13b-4ac495b728e8 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
9b86b828-25d3-42bc-864c-15a3a1fbaf41 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
a45cbec3-f522-4a49-8d35-d5415c76ce83 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
a69946de-8393-4559-91e1-7863b21258f2 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
a934af7a-17a0-4921-a828-0ec603b01485 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ae2785c1-8b25-4425-9245-e228b8cb5357 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
af30944a-91df-4d34-ad3e-786e177bc4ae | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
b2fe75f5-eb18-4b84-a7c3-77c92168e1d3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
b839500b-6047-4905-b9c6-df7d9e1e532e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
b8e46f50-140e-4116-b0e1-461c915c0ed5 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ba95fe97-7d4e-4fad-994a-e9e6716550fb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
bb32c5ff-216b-47e6-bff6-8db03de960f0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
be7608e9-79b7-43e4-942a-a7736ce6c78c | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
c20929f2-2453-4652-8b67-1cdd3e4547f6 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
c51ee81f-4cec-4651-921d-e4603b37b1ea | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
c91acdcc-896f-492b-9147-0a505aabbc5e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
cc074b91-ff7e-48c8-8b22-ead2209cd850 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  |  |  |  | Required to Re-inspect a subset of assets
cf3a9cd7-70de-4e90-8a99-349651712814 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d2617a62-240b-406a-87ae-305d1ed393e3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
d3185ad4-06db-4160-9f73-f5063a92d089 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d32fa763-e735-4d5b-96bd-a0d8304609cb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
d34ba74b-f523-4074-9af3-0a0db0f88529 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
d48df17a-3d47-4e88-90de-b5f0cb1627b4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d8287010-cae8-488e-898a-5ef93e2a83a0 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
d9b33f7e-82d5-4cab-a5eb-f3792a4ce0c8 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
da757bf2-cf77-47a3-a2d6-96416db0d4b5 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
db8632ca-7985-4d0c-839a-e20a7b20063b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
dc25532d-7634-433d-8268-bf0e8b64da12 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ddb6354a-d174-419e-a816-b5df65056a5f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
dfc0a50a-757e-4245-bb9e-0712f29de56b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
e199ce05-e286-407b-903e-98f516b3ed9c | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2021-03-17 | 2026-03-16 |  | Required to Re-inspect a subset of assets
e1ab2e8a-62f0-40f2-a400-41138028ba8d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2021-03-15 | 2026-03-14 |  | Required to Re-inspect a subset of assets
e4f1c3fa-1186-4d4a-a968-74da57d744a6 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
e6ae605c-f65c-4bc4-be0e-99a0a263fac7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
e6f5ce70-efaf-4778-a0b0-27c2d8711c09 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
e7dc4542-65f8-4fe9-8032-7318a6a81059 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ec4891e0-82c4-49f5-aa0e-af537bf7ead4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ee0e9526-dce6-43af-ac23-0935a028973c | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2
ef27f034-6f79-4de5-819f-c68ba9cf9bc2 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ef6f0b72-be91-498e-9930-1eb6026ddc8a | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
f1e5a4f5-4127-40a9-8a93-8b5e32abeef3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
f24169b3-2c51-4482-a4ca-7269b0367f22 | Pole | 3 | Transmission | 2020-08-10 | 2021-02-06 | Level 2 |  | 2021-06-03 | 2021-11-30 |  | Required to Re-inspect a subset of assets
f66910c8-8ab7-4037-a14a-6107b39e388f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fa0a4eca-a786-442d-9a28-446dceefd54e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fc0a968b-6754-48e5-8fab-990a67545535 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fd413ece-688f-4af9-ae39-b329fc71feb0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fe5f647f-afac-43d3-8dec-1dd946271f67 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ff42a9a2-01e6-4fba-8c9f-fad3174eef84 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
0033dc4f-c9fa-4faa-b3c9-08c64394c60b | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | 2021-03-24 | 2022-03-24 |  | Required to Re-inspect a subset of assets
006bfd1d-bc17-44d5-8738-a5c00bbb089e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
00b9fd77-89d5-44dc-af68-b394b3bcb59b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0115e288-2bb1-43ff-b04b-1e4df012a0c0 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
01b43a7d-067d-4130-a078-809aba570e62 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
02bfd782-dcfb-44df-97e3-4b624b0f7a90 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
04e9ae6e-89fa-47da-9029-fc298ddc7393 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
075f2da0-2cc9-4c78-b741-83d30a00646a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0b877b59-c620-4def-8f73-d418140aff7f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0cf155d7-27fd-41b9-a1d0-4dc060be6bcc | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0dc3862c-a831-4abf-999d-889af2d988b2 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0efd3256-decd-4030-83b8-2dd08fa277ff | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
11237a51-1789-4e9b-ad4c-25c91e699457 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
157bb57b-6160-4ad3-b33d-938a04cc3141 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
19ce6b24-5e85-426b-957d-23b4a8ec34b9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
19f47a32-83f2-4882-a6ee-3c53c9467873 | Pole | 3 | Distribution | 2020-08-11 | 2021-02-07 | Level 2 |  | 2021-04-02 | 2021-09-29 |  | Required to Re-inspect a subset of assets
1d7bcd56-23be-4e6f-ba43-f6409db8d3e6 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
232fd5a5-85e0-4d13-94f2-75c6d28c6e6b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
294a28b1-8042-4318-bd27-cf9f2bcaf2cf | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
2a525730-764c-4233-9035-62bfe76f68e8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
2b4afd08-e386-4417-bb5d-c42a9906f8d1 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
2bc3fc72-e7bd-4e7d-973e-20f8c7648c08 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
31cab056-13dc-4efb-b5fe-0979fd87e6a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
35372b90-34f2-4d79-8fd5-85440191235b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
35566c08-5d3d-419d-ae6a-90c12d56a86b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
381e4d13-0ee9-4bff-ae65-af96b01cf12a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
38c48d19-ff5b-49d0-a69b-dff760465eee | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3d7f74df-c904-4d91-85d4-2f337bd32aed | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3e5fa1fa-12cb-446c-8a5a-9b65206fe7b8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3e95def7-3fb4-4148-9e8c-7a41a080dd95 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3f1730e1-8fb6-486b-a06a-9b385a6780ab | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3f246742-297e-4197-82a4-038d21972036 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
40343078-60d8-4c22-9592-1ce3ebfdc203 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
46a075e5-4d51-44de-89d0-65f1654a7678 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
4b1f6b6f-ceda-41e0-813d-5e106b5832ec | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
4d3f9d2f-da3f-4bc8-a847-525eb2f0a355 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
4fb66361-1bdd-4b4d-9e00-35ba4094317a | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
51cbfc7e-9349-43ec-aa40-691a27a897ed | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
526ffd37-262c-4205-9eea-e5be282e2d83 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5401313d-1f35-42fa-bf29-105eab38d294 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
547d5850-1bcc-49bc-8e15-cdad790e3961 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5514772e-9065-4f53-9551-f1974eeb9a11 | Pole | 3 | Distribution | 2020-08-11 | 2021-02-07 | Level 2 |  | 2021-04-01 | 2021-09-28 |  | Required to Re-inspect a subset of assets
564d01bb-89a8-4140-87d9-63acc07994de | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
56679041-8d59-4dd7-9c4f-1669ae7b6f5b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5d72eebf-dc35-4ce8-b155-2f023a7b789b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5f1d12d6-a743-4ce5-8562-e716b8f12997 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6013c15f-bb99-46e9-850e-4647a71c14d9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
61908aa3-9b59-448a-ad92-021315eeff23 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6205d9a2-2469-4b3f-ad52-042161682d67 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
6596c158-2bc3-4dca-9797-cd51ea69f4cd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
682866e8-88a9-4cf2-9f01-3b3028168d22 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6bd38cf8-5cbf-43c6-9050-8ecb9932eee8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6e09334c-2ea1-43b5-b31e-fa4c10074ecd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
70d208eb-40bf-4003-8def-f3973169e86c | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
73109797-ac64-46e8-ae0c-b908f41072dd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
75118536-2cbc-4dbc-8668-24172c2a4751 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
75390c82-54f8-492e-b7d2-6dd9b53043d7 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
755a998c-b2d6-4607-95b0-74e78b5aa1b6 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
76f1e667-e5b8-4001-828c-253512d3ef32 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7b745c87-d2a8-4fad-a21b-817edefb5bb5 | Pole | 3 | Distribution | 2020-08-11 | 2021-02-07 | Level 2
7d9da2b0-9b08-4441-9e66-d9b9e22ddc40 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7db52768-7e70-4580-894d-084f51a8c2a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7dd32696-157b-4907-a075-93889b3aea74 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7e78ff96-e4a6-4d70-8a63-15580687498a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
812c6d77-3d5e-4b4d-ab74-f87db9607451 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
83749815-9cbb-457e-b748-09983f982346 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
837f2a58-5707-4160-b3d6-2645bc20efc8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
83be8f23-476f-4f63-8e17-e9d48fbe1e88 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | 2021-03-24 | 2022-03-24 |  | Required to Re-inspect a subset of assets
84c01308-3a30-4c7d-b891-4cf7978f9c0c | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
8550e1e9-b102-430e-a668-9e236f44565a | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
8c33ff4a-24e7-4011-aec1-cb27983fe88f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
8df984a7-7a56-44d7-8f17-ed20bf4f9967 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
90e578ca-ed6b-4d1c-a108-c3fd9b5f3619 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
93950de4-201a-408f-8a6e-7c6acd39e430 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
97431d8c-ede0-4f6b-a296-038a5bda8bbe | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
985c20df-ae78-4612-bec9-4d1d89a69440 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
986a7178-cadc-40e4-bd35-0db93472953f | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2021-02-11 | 2026-02-10 |  | Required to Re-inspect a subset of assets
99f38695-dde6-42db-946e-1b30230db0c5 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
9c785737-6de2-42fa-8b37-9e8c94180b33 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
9fd32fd6-56e5-4971-994e-530e138bb4f9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a0e56827-87e1-4427-8715-2aa99ce2c9db | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a19ce921-79fa-4de1-85ff-e32b3808c4a7 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a1e4527f-4e9c-4311-a375-48b43d1f8c1b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a84dbf8c-f31f-45e6-acaa-f8ae05bc7432 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a96bb538-7baf-4806-b79c-8d254e55a3c9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ad886d2a-3bc3-4716-bab3-2b88cab9809f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ade3a6c4-99d2-43fb-aaa2-bf5a74f6ca22 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ae907f3d-6a31-4c90-a77e-fd41d05d0cae | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b15487ce-fe4e-4241-bf58-50ac4c3ac7dd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b366bd8e-ee08-48da-bd35-a2a7925a62fc | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b5e5cf86-bd42-4ab7-a9e6-1e2656725532 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b705139c-25e8-4a75-a7bc-e7ff0e38e1bf | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
b79fc751-e5f4-45dd-a9bb-49f2d37aeca1 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b845ee1f-9879-4778-ba4f-da52c528f605 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b87c0910-ac42-4c1a-b720-74a05842bab5 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ba748093-3ea4-4e04-b742-6b0e777143eb | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
bafada88-8846-44d8-b260-8137cb4e898e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
c4127e7d-8eba-4059-8dc3-0b3cb3f78b99 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
c7ed9cd8-0fa1-4edc-ba92-0117dd529295 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
c8dd343d-d7ec-4b3f-b6f4-19b2a75df113 | Pole | 3 | Distribution | 2020-08-11 | 2021-02-07 | Level 2
cafd9538-2f84-4115-be4b-f05d84559eac | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
d2dfd70f-c13d-411a-9bf2-a3f7200ee5ce | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
d814d3cf-5a3d-4819-8709-c06ff4799632 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
db79698b-1db4-463b-a26e-5d6c05e9bf9e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
dbd4b02f-f6ee-4eca-94bd-477026884420 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
dc4b7b1d-a604-4354-a5a4-0b84f1d6976b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
dd9aa1ef-64e2-4d00-9bd1-22c57afaed0d | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e02a8c5a-c207-45ec-a9c9-c7e3ce25b97d | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e1c755d9-3507-4bc9-9dba-b9d636ab4f0d | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e6bddca9-9ae9-49e5-a5e8-843636da981f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e70c8f33-d22f-4bdd-9795-ad89a080f7a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ebbb8f7c-7c78-4345-add0-74535e2cc0d6 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ed0b9dbe-db40-496c-9601-e52c55514115 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ee54b362-5fa9-4de7-a0c0-0ae338c7f04f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
f6dd73bd-431b-493a-91ac-0c2f940d93eb | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
f7411306-3cc2-4a63-b444-a90ae1eb35aa | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
f8700744-ccdb-4253-850a-bd057f73c9d0 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
fc8b3e11-3958-4591-9b02-41beba8fbdc7 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
fed91080-aed7-4383-8cc1-4caba1818c73 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
fee37963-6c31-4923-8cee-f839e20d3903 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
01c4f125-4a07-4d39-ba73-b36005081ed9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
02ceb0c5-9c55-4bae-8743-1f002290c8af | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0475b47e-4b35-4548-946e-126a6d8530a7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0563280c-a8f1-4a91-bfb3-3d31002c2dab | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
062a10d4-0ad1-4b24-ae97-4ce6acd9b06b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0abff65f-ffc5-4a5a-922b-7e0487ac1cbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0b5564e3-e707-4425-8b96-2efcfaf76433 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
102a4ac4-9bc5-4da9-bd67-297582af2a91 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
15c6a04e-c5cd-46e3-ac51-8511bf45ef03 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
166214a8-63d0-45c2-99f6-7b7c768e04ff | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1aff95be-7f01-45d1-96e4-8a282c990974 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1c8a0104-57fa-4757-87ff-7204c7128ea5 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1d4c5e9d-6f2c-401c-8741-1b03d4455716 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1d900489-246c-49ae-aca1-fd1c881bfff7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1dbd14da-8dd6-4c21-ad69-ee62d193e122 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1dc17a5b-5fa2-48e9-9c93-0d5a9cda3c70 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1ef6a2c4-325d-4852-ab96-9204729e35d3 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1fd5a071-4782-40fb-8103-2383846142bd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
20dfe33b-ccce-41bf-9f60-a04f09221578 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
22ccc302-5f2c-4519-9e35-c569fdd1b59d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
290a2e00-67ef-4e7e-bcfb-5a58f387f714 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
29c70cb0-66fe-42e2-9fcc-80bfe9e35963 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
2a755204-0c03-44e8-b0bc-d6f4c4883d86 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
2e5352df-3597-40e3-8c21-229edced4bfe | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3110ea1c-5bd1-457f-b99a-15d5e39200e2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3198ca17-2857-4eca-83f3-f4d990bd6e69 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
31b3ec69-01a1-4773-8def-094fddf0113d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
348d0cd8-bdcf-4350-8b50-9b17e6015d4d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
34bd7f36-21ef-4a46-b460-399432e0849d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
391b6155-61f4-4c87-ac4a-913739009a25 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3994dc19-ccb5-4889-a436-8cd2e8a90b9e | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3b22f3e7-f573-4537-97d6-bfae8209b083 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3c75e3bc-a35f-43ea-8937-7c1cf618d08f | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
3d45753b-7543-46eb-9e97-59c724149314 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
41019575-aed0-4603-8227-02f21ca13391 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
44f307ff-2870-495b-90f9-b0c0363f41c5 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | 2022-09-01 | 2023-09-01
46b74e23-c1ed-4b1a-b2df-3d019ec001b9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
485dd898-327e-4d73-92b2-fd071ccb2c13 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
488a93a6-640b-4d58-8782-45cc2e8fe4b8 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
495c9d31-b037-4d23-8d6a-62b7ea696bbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
4f526001-1185-4acd-a3e3-60ddce305dde | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
4fc70023-0783-468a-9f20-b2d4849c3046 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
520ca10b-7b06-4c05-95ad-83a3aa260a73 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2022-09-16 | 2027-09-15 |  | Required to Re-inspect a subset of assets
54973d07-a59a-4eee-abfb-74bd97e1d9e8 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
5644e16a-bcab-4ca2-970c-151153bb536a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
58667738-cd0b-4e77-9c30-56d15717d138 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | 2022-02-02 | 2023-02-02 |  | Required to Re-inspect a subset of assets
591e4568-81ee-4b27-9730-20c49031e646 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
5c4ccbe4-8c31-40a8-8222-7620c29065eb | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
5e4d35b4-9d47-45b9-ba0a-5cb3ebfc7c83 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
5f3e222c-84fa-4206-b606-9477a0ae6c92 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
66ed57dd-4f41-48a5-9515-c46c6bd8832a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
687a2a25-df42-4f4c-adbd-e537759e5154 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
68a810e2-8dde-4b7f-8d92-0ba1ddb37f2a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
69807d73-1c22-4d6f-9b92-bfab57e31c06 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6c87e8ba-2deb-4a68-82af-9846a0c87df2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6db4ce95-3ecc-40ff-a7a4-e1d38fe36392 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6e2e0070-4cba-4bdf-a681-a775a6d47d16 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6e4eca6f-784a-422c-827f-2f2c48f752ee | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
713c4c87-4b62-407d-9568-1936fdd36062 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
73d94ea0-b88f-407b-b54e-0e7fc593475a | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
7848c8f4-db12-42d8-b69b-34670cbd891e | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7a3541b1-889e-4a6d-b340-564b584c4e06 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7bdba4b8-b2a7-4a04-8aef-fee4078b2f93 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7ce6f6f2-b5bc-4694-a166-ab17b07afcce | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7d4202ad-95e5-4a71-93f1-310e925e4c79 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
808e5343-03b2-45e7-ace0-ebda45409701 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
86a77624-595f-4d0b-b720-3c0289cb3762 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
898a41ed-20be-4ec5-963c-69f04a1378fc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
8ef8d7ae-40b6-46b5-8382-b5d8039c7dd0 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
8fdcb8f4-6664-48f7-9d21-67c6ddd6a9cf | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
91a5c92f-e227-4365-8b07-fe02f190015f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
956e35e2-7a53-47ca-b7e6-c7367d8da01d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
97191a49-590d-4e3e-bd8c-2aec9ca6b0ef | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | Required to Re-inspect a subset of assets
9c716cea-353d-40a1-9ec5-ce5f191c4d3c | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
9f5365f7-b542-4a6f-a2ff-ed82ae082bdc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
a6c10575-5828-49e3-983c-f0bd5fb7300b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
a6c6a5ce-055d-4ed0-b594-1d0bbb9b4b27 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aaa4e655-a1e2-4c75-8b2f-e43d1bcf638b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aaa89b44-3a31-44b1-a766-aae067cb74fd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aacf146a-42a3-4109-ac98-33d80b5e8f82 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aba25529-66af-4f4b-a588-37db8b05b647 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
acd58bd4-fd0f-4884-8143-6e2288e4e7b1 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
ad006007-38d6-493e-893b-ea8d1fef783a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
b195fce0-5199-4a1b-8bd2-05bc2a915fae | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
b40af3fe-918c-40a1-9123-9487ba1808d9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
b968f4da-c5e9-44ce-ad50-349b008e5504 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
bae6aecc-9e41-4aa6-aba9-98c01139ff1a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
c1c5b4bc-0617-460c-95d1-9245d5e3789f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
cdd62acb-4b9d-41e6-bf85-3409a1cf0683 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d00bc188-d698-433c-9534-1cb37aeb1b34 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d392dcdd-700f-4565-8e05-732f57e64dbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d49a8cad-d360-44bf-9505-9e71c449e7ce | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d49c7247-c0fd-420c-b685-e841c29f4220 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d554d4b8-0a2b-438d-b512-c819333654d7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d8069c6a-1394-4a06-9af3-e65bf837d125 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d888170b-00e9-44fa-96d9-e5e4d9ac1296 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d8afc4d0-96cb-4f8e-ad46-f144fecaa543 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
d8efe912-1f0c-4e76-b582-024667a4f7b2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
dcaa42ba-9515-4d6e-aee3-4c0aa0546ef3 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
dd42ac7a-70eb-4ae6-a220-401ffe8e2add | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
ddcb61a9-cd8e-4026-8f84-a3cdbba63208 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
df53b8c1-aca3-43e2-bcbc-1f46e621a914 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e0948f39-4546-4dae-935a-73b449e2d3b4 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e59f7617-02c2-4c0e-9eb7-bc597227bba0 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e65968f5-7e18-49b0-b78f-24e86351a72b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e69ace64-164d-45b6-8455-2ec519773e4d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e75afbaa-988a-49b7-829f-34e66362cd25 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e75e0ef3-2fb6-49ef-9d05-22ac64fa2702 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
ea472a04-0ce6-437c-85ff-7bf44bc30848 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
ef6f1ff6-311e-4627-8108-c055103a940d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
faa99ad4-c658-4666-b88c-3afb5c8f8d3a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
fafad9e8-5ed6-4569-a6a7-b0b7d0b0e9bc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
fd30dacd-455a-4da7-9961-07ba7fea4e6f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
084c6fbf-b655-4c63-9ec0-848f235c8a5f | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2022-04-28 | 2023-04-28 |  | Required to Re-inspect a subset of assets
0987eb82-2978-44d0-b7dd-206f5e9d4d47 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0abe8ff5-8384-43c3-9f23-047d4feddf6f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0b68a451-7788-4a8e-b2f6-22963332269a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0bd215ab-5e21-48cc-8770-8902b6d57ad9 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0cb84489-4dea-4c60-b1e6-bbda3cdb677b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0e895429-6c95-4181-afc2-aa7772f04cc5 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
15300369-90f5-4123-8f9e-a01ff2fe25c7 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
16055c60-98fa-4f7a-a5de-94d6ea4d85ab | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
1651e3d4-1dc0-4225-92f1-72f11ec1776b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
1bdc4cdb-ebb6-4fc1-a07b-4f54862572b3 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
21abeddc-f80c-4a61-bfe5-8534997917af | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
25826d66-01d8-47f4-b153-90b1f4321e02 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
259f17ef-ae74-4b75-a494-b74bd2b14169 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2a17f094-ddf9-42ab-8c8b-bbbc100136bf | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2d0ff6d1-73bb-44f9-bdc0-35a427a5eeb8 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2f10f4fd-3dfb-4327-a5f5-8a5937e213cb | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2fd1858b-a392-4140-8238-e41b1c936db7 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2ffbb6ff-c91d-47b7-b5b5-7e2fe0033357 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
35eabd22-f0ba-48a0-82b9-d5c0824ba6bd | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
3832ffc3-0b2e-4f35-99a9-07c81315971c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
391ef15f-25e3-4ab0-a834-d5bdc7b4ba78 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2022-09-16 | 2023-09-16 |  | Required to Re-inspect a subset of assets
3a1f98c4-1404-4e8a-939c-242c6c19fb4f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2022-10-18 | 2027-10-17 |  | Required to Re-inspect a subset of assets
3f29dd34-b394-40bc-a23c-fd0822e757c6 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
4e8bef8e-2743-4080-afae-86c519fd1614 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
4ea64335-cf60-4813-91af-71802974dcd2 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
51f4b82e-c7d9-469f-82d6-abd100f15a7b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
583ae9ad-9adf-4156-8917-af0092ae617b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
5d1173d0-097f-4ccd-82b1-ee73f52109ee | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
5d2a72e3-8216-4bca-8ec0-14fe4a0eeb29 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
5d67f1eb-e5cc-4c50-8fed-144807184d44 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
60e3173a-965b-4318-9238-e3b7f0b93670 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
61cbd3d2-64a2-4fa5-b64d-11106447c187 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
61d768d2-4b69-489a-aee2-8bb8c4011422 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6361960a-0db5-4173-9d15-348ba5a9f336 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
65e9d501-aef8-489d-872b-ff59bcab4d54 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
66def900-7600-469b-9faa-a900856c8057 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6742c3d7-5014-4e77-89f7-f4dd00e36b2e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6891b239-c848-45c5-a415-81309ed07811 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
697169ed-7b13-465a-b903-3ccc0b399a61 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6bc203fc-a5bc-4c9e-8d48-49fa7686d540 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6ccf1c9f-1a3e-49d9-99c2-6c5b9e6a7eca | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2022-09-16 | 2023-09-16 |  | Required to Re-inspect a subset of assets
6d7481cd-f589-4cd0-b1de-02046b7367df | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
701fb98a-9bcd-4ebf-8292-7ce080a7d127 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
70f916c6-9efa-433b-971d-73c8f98228de | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
77377869-009b-45f5-9a6f-9ff1fb1b9245 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
792e710a-4a81-4ac8-a018-451aa41700f9 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
822f6a92-8e50-405d-a46b-85d0e9042c7c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
835fa24a-4fea-4055-ae6e-c1e69ed2cb69 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
85bc66bf-7687-4391-8bae-dfe9591a32bf | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
8da9a20c-176c-4b39-96a0-57304f18cf37 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
8f5f0054-1f46-4772-83f9-8dd4799107fe | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
912b9fe7-67df-43ea-a42d-aac7b52cf35d | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
933f8ec1-0cbe-4407-b4dc-31448210676a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
9636fd8d-8d86-4506-a690-0bf7744b2b66 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
978d0485-3a87-47ef-89f2-4b917128c02a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
98017901-7984-43a0-93fa-36d3fb9df275 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
99e54a94-e9c5-4199-8644-420be1579690 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
9af49be3-c04f-4d03-8e26-0ce756b8d94f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a054ba27-f49d-4d8c-9b15-37b8990d174e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a42a1a2d-6bc7-4f90-ae84-278747f82a67 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
a8ef3ff7-fe49-4a2f-a780-4a1e09c6a143 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a9eeaef3-a442-4961-8028-a646554e990b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
ab71b13d-5f8f-46e3-bc54-e128437b681b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
abf02d38-2319-469d-8797-bbc3891146c6 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
affad873-f0f4-43db-8a53-198fd472fe7f | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | Required to Re-inspect a subset of assets
b7088299-9c9a-4b05-8572-02b81c71cba0 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
bd3a9134-f914-4056-aee1-43c622513394 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
bdc915b2-a1db-4ec7-8168-55c97915d24a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
c07be6dd-70fd-46e8-b60d-b1efe6c8aace | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
c1d82274-dfc5-46ad-958e-ba9234483a4e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
c2704209-38af-4944-9cb7-c02752a67019 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
c49e23c9-b579-4bed-9a7a-30f0ddddd831 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cb3e3a32-9690-4b29-afb7-4eb7d3009591 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cb9ee7ef-be23-4461-982c-460181a3741c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cc490623-3855-4887-8da3-a719f481840e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cd4f05de-8abe-446a-afdd-4ded7fc6f609 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
d355c38d-c720-455a-88a2-474753e17391 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
d3884099-007a-441f-9aed-cb2f0325a23e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2022-09-16 | 2027-09-15 |  | Required to Re-inspect a subset of assets
d69c52d7-283c-4a45-b673-0af2dbdc1454 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
e426e70c-83f0-4d97-b9d5-a489163aa24c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
e91a6999-153c-4f2a-a9ff-d77fcf7a87fb | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
ec7930f0-7f62-42ab-94a8-67802bfa1f5d | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
eedbf0fc-8bef-4e17-a50b-77e1bf3cf520 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
f28774ad-b0ca-412d-af86-2404bbb924ef | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
f478c9d4-800d-41d5-a4b9-d609414a4d2c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
fa21e8b1-a328-4e21-a4ad-8745a8356b5e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
fb59c5da-9d0a-4da4-bf22-de2ebc621d54 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2021-06-29 | 2026-06-28 |  | Required to Re-inspect a subset of assets
fc2a9cc0-b145-4d7e-82b2-581f5e3dae9f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
00319bbe-a52c-476e-b92f-8d67cdf9d297 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
050067e0-6d79-4f65-bdb4-63af528f4cde | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
09cbf493-2005-4a68-b940-e61155dfb64c | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
0c6e0603-2876-40b3-8edb-02adc4b6a0d7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
12212548-c09c-4714-bbeb-3bb6160da972 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
1e6d628a-6c56-445f-910e-ddd39aad3653 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2b2c9ece-414e-4010-bda5-1b1853947f6a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2d3df91d-46fa-4f41-b735-532d21dd4620 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2d9c2da4-f42d-4073-a244-09d973798eb6 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2ec6b880-ab4c-4c7d-bab9-acef35d11f55 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
36ad5913-8cd7-42c7-828e-773a1888feda | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
38195f22-dff8-432d-a9aa-aa4f964d8417 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
43c865df-3edd-4779-8ab9-a6d019d91180 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4482735b-d051-420c-b600-760171a56049 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4718a946-4fa3-4680-9206-dd33e8b2362b | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4a1eb129-0dfa-43e3-a3a5-660a31b01deb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4a8a7b63-cd99-40de-a477-f7d6bb21a378 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4bd83973-63e5-45ed-b637-947215fed7ad | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
51d6d732-0f90-4609-b7db-509332696458 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
535619d8-01bd-4ca8-bbbf-c2d65559bef2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
55d4678c-2a60-4a46-b272-5357b0afd4df | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 2022-05-02 | 2023-05-02 |  | Required to Re-inspect a subset of assets
595085a2-838d-4df9-9371-e890f10e5b05 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
5997646b-b80e-44c2-9263-36338731aa4a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
5c5bcf67-be2a-4afd-a874-d7038f1d4ae7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
60df7a83-e2b7-41de-899a-89af255ae74d | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Required to Re-inspect a subset of assets
61f32093-3370-4fe6-a39f-bf511de8c9c8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
637bed12-26e7-4561-8741-64f2eb372892 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
6ad4a601-476d-4bd6-b3ea-8bfb599b5d1d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
6b02b67e-2e4d-4745-b5b9-311f0e5e1df2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
6b233bca-6b80-4348-b1f8-c6c3b262269d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
71ed9e41-996b-43c0-a0da-87e5e5794a7f | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
7a87e7a4-aed1-4461-9030-04ec47814c10 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
7d1fde50-8e5f-40dd-a9df-d7f1231b335a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
7de91a19-9b7c-4271-8135-01f57ebd2ffd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
80555dda-580e-4c6b-87aa-5d5cc6382a4b | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2
80c91bed-22d6-4e22-a6e5-a44435624cd7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
813f1274-0381-4685-8794-0c66d8792b4f | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
81845573-b07d-441a-ac12-90653a46c47b | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
81b1a7bc-60f5-476e-a969-4cf9c68186ab | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
84fad399-0aff-4cf7-8f39-292466aa5455 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
8b4649c4-c71d-460d-9116-d412ea6f609c | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9143321b-6851-49f5-916d-36c158a2eda4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
916dda97-dded-4eaa-ab95-6abd17098b08 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9b71307c-dfdb-4711-ab2b-e8a20fda2dfd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9bf5754d-a001-4fde-be2c-31e52e3d5eac | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9c9e4b93-3de4-4b0e-aa47-8de5833f9240 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2
a8e69d42-444a-414c-b6b7-5ecd7bcdcbc8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
acc70cb6-b822-4522-bd21-77a603905cf1 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2
af0f6cf6-8a59-4e8f-9a6d-f31231274621 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b12f5e9c-ac18-4f59-a37d-23c4f73437f2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b22e7a3e-f920-4e74-83e7-699d76adb9d7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b3577643-12b2-4928-93db-ea4baf3358dd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b510c45f-c689-4756-a5f0-85bcdfb9fd50 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b8b81add-0d53-499d-804c-a9aac3129e4d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
c5992e72-d5f6-457b-a13e-0a23aae26ae6 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
c9243a75-de5f-4a88-a89c-a2bb48669383 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
cb687a34-fc7f-4367-909a-801ba3a2f0db | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d29b1171-3281-4930-a1bc-d58cd937c498 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d87f2178-c65a-4df4-a850-af77b89e9907 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d8a0f4e8-e9e9-4120-9f5e-72e19a1e6697 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d9265647-f7e7-4826-9bba-6aa620dbb0b4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
dbc64b55-54d2-467c-b22d-bedfa8d9bbdb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
df364ea1-a48a-451f-9d09-93d13c19b9c5 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
dfcfe4cb-a756-4869-8793-ed9f52bef5a4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
e9e9599b-774e-4d96-9e90-95bfce79e380 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
eedee0d2-7dfb-4736-9154-5cb4b357e8f9 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Required to Re-inspect a subset of assets
f13e46fc-9b8d-42d0-9661-2b0df51d8ddd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f441916c-100f-45ef-8be8-ae11692e3706 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f5d233e0-974b-4eb2-b89c-97752c3ecdd8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f5f1b57f-b77f-41b2-8658-ef6b33321f46 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f87581c4-6579-4365-ac11-9e767761d3bb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
fd48d4f7-bbed-4371-8804-6bf3397382e4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
fe4ee3a0-bb3f-4d86-9fab-f2a147fadab5 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
0211e8f8-b6ff-4830-876a-48b93cbd08b3 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
05800e39-c7d1-4b5b-a76e-c1c836d516bf | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
0b60272c-ae68-49f2-aa5d-1b8365f5c87e | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
1152a63a-2a0e-4a25-a0eb-47f97a651d89 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
1f8b0832-4db5-4553-87ff-77ad4bba8b8b | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
2364902d-1953-4578-8d28-5bfd964f7f29 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
236604c4-9294-4cb2-b998-4538b47637bb | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
2fd3d56b-fe1f-4ded-bcb2-2cc3d2d4b39e | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
31b80abc-d615-4816-9e40-40405a6bb6b5 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
325e224d-b5ed-4082-bebf-a6a9123295ba | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
35248dbe-1c85-4786-bbb9-a56975879bb1 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
3617d431-76a1-4fb2-90d6-8ccca747ba20 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
37c174c5-ddc5-4789-ae06-578e8fc9b9ac | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-04-13 | 2027-04-12 |  | Required to Re-inspect a subset of assets
388da06a-d796-4401-b0c4-f0cd0f4f2d88 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
3b5d666d-34e6-4f28-a604-061ce9813249 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
46eeaf0e-dc62-4353-b605-a110e7b7fd8d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
47e4c2c5-1cfd-4d90-ace4-2ef59464733e | Pole | 2 | Distribution | 2020-08-15 | 2021-08-15 | Level 2
4836bf34-9269-4123-913f-a0d04f2507c3 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Required to Re-inspect a subset of assets
490506b0-59ae-4dfe-bfd9-035280b95623 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
4e5266dc-8573-4028-8b70-07e5a49a2076 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
4f06e832-849d-449d-90b5-0407f1d96e58 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-01-17 | 2027-01-16 |  | Required to Re-inspect a subset of assets
54d9c368-af37-4469-96f2-0939976416d8 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
5a4bd463-45dd-4f9b-8430-6ab6cc5d383f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
5a78c1b9-2070-470d-bdde-e2224132a44f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
651987c7-7b3d-4845-8225-0d3f6e7545c2 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
6db03cfe-d3c9-4a60-bf9a-6a3a06467bad | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
74b9822c-ae6e-430b-b5fd-f1e22ec3d23f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
7562d2cf-2ae6-40f3-b2e3-b6bd5d1d3eb5 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
7a92742c-4d5a-4c14-99a0-425bdefdef94 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
8157bf08-64f7-4a4b-bfbf-6327d5b1c540 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
84dfda52-8222-4551-b993-ea82dc159805 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
864418c7-5d3b-4f8f-abc0-4368cf03e0ad | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
87c9e503-e571-4bac-8aa7-fcd7e8bf852f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
89ce9c8d-6786-49e6-9aa1-7f340250f257 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
91488720-29f3-45dd-b103-f3532d961515 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
917ce863-0fe6-4434-9de4-9a2c0da7560d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
95f95bff-3d70-4da6-81ed-04f0d659589d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
989286d1-8539-4f15-98cc-8c47ef735132 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
9fcde381-bc44-4000-8ba4-81d05f6e1a21 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a00f4933-b1dd-490e-bbc0-55da1ce2c64a | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a1508a0e-8f74-4b2a-a416-b04d2dc3bc78 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a5866153-51df-47a2-93bf-3e873729c1f4 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a755a4c7-4357-441c-9e36-528414d4e700 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Required to Re-inspect a subset of assets
ad650805-040b-4934-bb05-b83e22cbb3cf | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b12ca565-c372-42cb-877d-59db9e82567c | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b348bcf3-f28f-47ac-89b4-e3176fb40321 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b5041df4-aa6b-4bc2-8fe5-3481ed039ffa | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b8078155-979e-4aba-bb46-95049ffb048d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
c0089e0e-773a-4bf5-812b-46dcb14260a0 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
c327e379-d2a0-4dc2-ab9e-39d5cf7772d6 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-04-13 | 2027-04-12 |  | Required to Re-inspect a subset of assets
c73fc4d0-68a3-4701-8347-6c465de8f3f9 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
d3a0fe46-3ed2-431b-9a21-512f8fafd5dc | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
d3aa8a2b-a2e0-45f2-b265-3e250c51223c | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
d85f947c-4a9c-4601-bd86-bdc3f739bc44 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
d9696caa-4404-4b8b-a194-cfa39ac5ca60 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Required to Re-inspect a subset of assets
da66590b-acbb-458e-bbf7-1a6ea54ae44d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
dc6c0124-508c-4376-9344-e45e9a81c989 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
e5a0be90-e1c2-4b80-bb6e-442635ce73d0 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
e6f40188-8ccd-42dc-b207-172408ca5641 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
eaff128f-0a14-40a6-9208-ffa70e24cf01 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
ebdd8ec2-c8f5-4449-913a-6a4716585bb9 | Pole | 2 | Distribution | 2020-08-15 | 2021-08-15 | Level 2
f4e36da8-0b4c-41b7-ac66-aa197514d18a | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
fd668582-c75b-4e92-85c9-31d0f5ff75f7 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
fdede023-b3e1-457a-af88-47fa1f6bc977 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
015c2480-1383-4725-8533-0ab38fea2293 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
08c5f11b-ad44-4173-b76c-b2af354dd03a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
08ff3a2a-40ad-498f-b462-f6eb83c963f2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
117a341d-5365-441c-84c7-940a097f0c4e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
161875ca-cdbd-4985-acce-7cbd1bb65e03 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
16943990-539d-42c8-a9bd-3f047fc6e42e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
1cbc349e-79b0-47be-a206-08701acd7cbe | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
1e4367f4-2c9d-42d0-844a-303194872c6c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
1ff030bf-fa8e-4dd4-94f8-4ac95f42960a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
228db20d-9b6d-4847-9d06-ce75dcc32870 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
251a0bb4-83f3-4b78-b4a1-ff8bbb9bd5d2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
2569924e-25dd-4879-8a83-33ccb91bae84 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
272bf117-5927-4e5b-b382-2d6ac69e0760 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
28146eac-d943-411f-8889-deb211631540 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
29c82222-293b-4a32-95f8-151f3ab7e81b | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
2c114db1-886f-437c-b12c-1fb65ec0526e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
2f8b5669-282b-4c29-902d-dfce109c59be | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
307d8277-ef02-442b-8ab6-fd169e6ca394 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
32c57763-aefe-415f-bf04-69341fe31c28 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
3660f45a-20f7-4ce3-8114-0875951c52a3 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
39b9e663-9ced-4562-b1f5-1c480aa6437c | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
411ed8e8-44b6-4879-84ce-aba8c2921428 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
42dac4db-8e0d-437c-bd90-a7b328ae40d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
45864e66-f483-4cc7-b32b-c96d77bdbc94 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
48030b4f-b861-452c-9a92-4d2ac63cb503 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
4bff3a0c-b7d4-4331-98d9-79d737515a9c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Required to Re-inspect a subset of assets
51bfe483-4817-42c8-acbf-272e6b90525f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
52de37d7-ab7f-4b7c-a2de-48c6320659a1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
53a5f6f2-079b-42f1-996e-4219f6bbdad2 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
55ba0fec-d19e-4fcd-888a-c18a6a2dacd6 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
56667e94-ec85-4255-96f4-c0de81248b9a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
576ee34f-d0ae-480e-a976-b8a92aaa4971 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
58a009cc-6878-4e63-8c78-b7de977c6cb2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
592560bd-5d4a-4272-898f-6c71a1ec7e8a | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
62a5cb90-d3b1-413b-be86-8b8d736caa62 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Required to Re-inspect a subset of assets
64246506-5d8d-4682-8ec3-846c5c787df9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
674722df-ed2e-4c30-9007-ec44c3488dbe | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
69c44e45-3f6b-4aae-9c6e-2fdbf69a7ea3 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
6c2c97c0-5e55-4339-8638-93b95ed5fb96 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
6c54efa0-21fc-492f-98bd-b74d6e4e2454 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
6de3bd9c-aecb-4059-a602-2de95260446a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
744d1497-f8e6-444e-ab2d-f2d73c919b1d | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
7a19c449-2489-4962-81d0-a9af56ddac00 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
7c78dff6-e125-4a0a-982d-a006e9900bce | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
7f4f1a4a-e575-404b-9e28-e92223e83328 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
831c2938-fd76-45f8-a96c-d200701cf205 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
84ebc02e-44a8-4f14-b714-69c304893e6a | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
89184d9c-8092-4880-8664-008afdf3310e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
911c9549-651c-4991-88f1-fddeffb2239d | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
9605d1d6-55c8-44ad-b1ac-612445ea4b72 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
9a79125a-0329-4a6f-b019-f9aaf71bc318 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
9c9043f2-2844-4085-b533-1fc2c13d8251 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
9ccd0455-f1dc-4168-9bd6-d878bf39bfec | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
9d310ff6-a880-4d39-806b-4b1436070d18 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a0d19bc4-bdd0-4abd-a768-7db12450895d | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
a1fb95c3-ca88-473f-a284-331bfaa60309 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a28035f5-b9fc-4552-a383-28122d72a803 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a5edbeca-083b-47da-9a1c-4da37cef2b88 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a64ba217-551f-4721-8ee5-0aba3c66d87d | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a9e4be83-4527-4c70-9391-944f0ddd012b | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
aa78fa36-7666-4e67-986d-4320d1e1367a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
ab4083ac-8340-4d40-a7f1-f0e60e08b1bd | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
af6d4ddf-7a25-4c52-b979-d7f12bec1ce1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
af718e4e-7ae4-4c6d-9257-92113c342ee9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
b4031d0a-bf36-4ad6-85ac-bdd9db8d462b | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
b45fece8-d42d-467b-a9bf-e4345b362c31 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
b9e9e230-6219-4fa4-8658-65c23f0e48f4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
bc12aa80-156e-41f0-abfb-7d66d9ca6fad | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
c4ffec8e-09cb-4b96-9de1-e0052129e00e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
c870e2d3-6d0c-4a62-a313-96eac2328b7c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
cbb6c1e3-b9e3-4d73-b866-0d23ff8da89f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
ccc31837-b691-4fef-8cfb-420a9c986f6e | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
ced65230-8ce3-435d-b3cd-049e512f70f1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
cf20e5ab-7994-491d-8c48-f71752e2f9da | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d13ddcea-d37e-4bdc-8e15-bdd0df4b7f7c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Required to Re-inspect a subset of assets
d29561a7-8405-4a5e-b5b0-b3878fd954d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d794126c-74ad-4908-8120-3f7f9e5ddc95 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d7c21f9f-9c8c-4152-8c10-516a78c9d365 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d9772245-ef52-40b1-ac10-7eb5f1fd87b9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
debf420f-9b73-46ea-b497-ece854a4cf1c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e1202c72-2e24-46e8-953d-f9f4ba387f33 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e4be35d7-263d-42df-9492-8650436f5c1f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e6fd3be4-9c85-4051-a8d0-4eafb561c95a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e753e589-d39b-4991-86b0-3828f5360e5f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e9e234a5-7427-4cae-aed4-b29a306e42a7 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
f1ce3b9f-2443-4abb-a2a3-7c38ba45c3de | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
f5f39dc4-94a1-49da-a567-f006b67ac6d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
f959cab9-f391-4340-b0cd-0d11d74b9c1e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
fde7fb71-5b5a-43a2-9e49-cae2df0dfdbd | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
037f4bb6-ff16-42da-b708-14e877054505 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0789bcda-fabb-40fd-b0e1-8c4a342cc89a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0874076c-938d-4888-9586-ba6f7d508656 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0ac890f6-d830-4aba-afe8-e8cb2f2cbe2a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0e057503-38a7-46ae-aa73-161e8e7ef00b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0eeda815-0a11-43e4-9c58-0c449ad2f3d5 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
10ff2d43-ca85-472d-b3f9-89a9e90f8ed5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
1485262f-ca19-4be9-a707-c50541d554a7 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
14e9bde6-b391-4cef-b64f-54fc50ac9ae0 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
184d0a28-a8bd-4c03-8f99-a834837b6407 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
18c35cdd-0462-4221-b7c8-aa3c5f36de69 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
1c5a017b-5683-4c5a-a9dc-c9a8bc2a8c84 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
1ca66a6a-b843-45b7-8176-ddd870e21726 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
21c1ee9c-aa5b-4755-b5a2-549878cc4158 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
224c7fa6-2ef0-482d-86c0-b5ffd950b6d5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
26219c65-5417-4716-a7ff-8be83d87fc8b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2699c35c-8f25-4595-8b5a-24986bdef181 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
29eb491b-8bce-4460-80bc-44a9c96b625f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2ae4a931-d30c-4f3f-89da-a031b868cc2a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2ca83bdb-bd87-4fe0-acb7-bf91f62b1ac6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2f55ab03-6f57-4749-8aa2-98d5b1b65d85 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
325673a1-1d31-4513-bb68-1edff9a97ef5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3548192a-ce1e-4a38-8955-52f57a6f4b0a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
38a44b26-7dce-4e61-aa8f-6e11d11e11f8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3b562847-952f-4668-8d90-f27aa9d9b91f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3bafffc9-76f5-46ee-a490-d1d6aa2dbcdd | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3bdcc904-3039-4424-9d36-549b44cb56a5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3c71a6af-e6ec-43af-9769-781499060547 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
3d2f3246-cf5b-46b0-b0df-359820ccc940 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3e1a716d-83c3-41d9-842b-7f83dabd3755 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3e8e3315-076c-4172-b85c-a110b3fe42f6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
451033b0-1758-4568-969d-3e6279118a92 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
453f9748-a296-48d3-bc0c-75f3653f60dc | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
4c2d2957-4fd0-4dbd-ac63-7e0dea3a1e58 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
4e1a04cf-15f9-410d-85f2-6aecb95a8daf | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
50aee005-d410-4074-841d-9dd018e4d149 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
50e8adf4-2e8c-4ffa-85f9-fb1e5b90b288 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
510b3214-99a2-4be7-bfcb-87f99570eff9 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5339741f-0c7a-4201-a3b2-18e80f377f46 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5455ee15-0018-4cd2-a5d9-13c1d34dd292 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
55031869-6936-4e29-9700-a254e3170282 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5b66073f-3706-4bf2-ac6d-8c79ccb83394 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5c93a722-7f9b-4af5-9dd5-92d18edd7c26 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5d3b9254-7f11-4f5f-8862-a67c30ecaf43 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6188d1ff-0ee3-40da-ad4f-5d1365767bc8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6747e479-5c67-4a4d-ad25-116e68147e6d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6945c72c-9976-4651-906e-5bee6e6fa0b7 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6eb674d0-4723-45cf-808c-a6510fce7c67 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
71be8d32-9e4f-4ba8-9a75-0a15e922a5ef | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
723a389d-ac75-41d5-b5d8-4f27cc245836 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
7c185836-647b-4458-a807-7d73341df16d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
7fc858fb-3310-453c-baf7-a569db6ebc6c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
807f6987-52b6-44eb-a6ae-a1bbc3705f0d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
811b999d-c62d-44de-8362-ac538008ba82 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
876d703e-467b-4f13-8bf1-09bcf9af4b0c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
88c2707f-b121-4dfe-ba0d-789fdc2ad72e | Pole | 0 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
88dc3f26-449d-4b7a-a4d6-7cb485ff3f5f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
8c36461c-d479-4f66-8004-085b96e9e8f9 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
8dc2f7d5-a641-445d-954e-03cfddbc812b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
92c8b363-e6f3-479f-b643-2fab4f152750 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
94cab6d5-9e34-4e37-8330-ababbf11eafd | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9918e2d6-29a7-4611-8937-99fd60659765 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
99a23be1-a46e-4f88-a1f7-5923c07a7385 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9c430c21-d296-450c-85c6-7a156c9579ed | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9cf01289-ab07-4f46-a4cb-49479fd9534e | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9d8c5c96-3dec-452b-8fd7-06d7412a2ce2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9f3147e5-5128-4243-84df-eaccad993da6 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
a214e533-0789-4696-b2a9-2ece6e343bb2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
a4e88dda-84b1-4171-a033-afebea131e5a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
a877e69f-5cc3-42a3-b5b0-a702e90b470c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ab4369bc-bf7b-4d8c-adc1-b875d68c72c2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ab444256-8dc6-43fb-8978-e839456af26a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ab54b250-806c-4168-9e03-52650d47f7fe | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
afc78ec9-a571-452b-ba2f-e79af29f8ed4 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
afeb76ca-aa75-4cdb-8b3a-b8808df05d7c | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b3f06a93-8ca7-4681-bde3-fdd11bf86898 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b5c34493-c737-4286-b045-6d7fd8db6f70 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b707e4ea-b55f-4b59-9a73-22f5f85fb903 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b70a66b1-d15a-456f-aed5-d477aeca7050 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b98ff61c-6834-46f1-8b40-a043d0ed0251 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c5106f44-b5b7-4ebf-af75-cfdf2e5db260 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c9295586-d953-48be-b98c-d4c5aa968576 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c96067ff-f30a-44be-8894-ae47b1c897cb | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
cab6999d-b6b5-48bd-8d28-dd7cfd260ea6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
cc8ff79a-1a27-4cba-a419-a08822ad3c63 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
d3372f1c-4378-4ab0-b729-13c787dc499f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
db5738d8-5ac3-4429-9c39-386354d2b0c6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
dbc9e480-1418-493e-8314-302d2f3b7778 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
dbef4d57-e519-4a39-bbac-b0006b42557e | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ddac9ace-d50c-4064-a84a-cae86ceb6a90 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
e02bb811-23f5-4894-93dd-95d83d0c2e11 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
e43255f8-b40a-4e16-a338-755868481c97 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ee2b3e8f-93ef-47df-99fc-a7b002203614 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
eee074ca-3b9a-4ef0-bace-a361bcb9bafb | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
f651612d-e0f7-4ad3-b916-652e318ff48a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
f9379adc-61d5-4744-975e-09ec8614da3a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fc031a9f-3809-4d57-9c2c-fb6c3df2012c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fe49a6bf-4d67-4632-b08d-43d24b4066b8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fe5ade2b-d90f-4d54-aa14-feb27297b4bc | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fe9d2d69-7444-4b6f-b96e-185ea21440b3 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
01c4f200-327a-482e-9420-a4b74a4a5075 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
01edf49b-3de4-47ab-982d-47a4243edbcc | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
09808cdd-b7ef-42fc-a490-904b7dd1a99c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
0f0aee21-1d63-490f-aa79-ab3c2850a307 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
0fce14c2-b555-4cb2-85c5-4778229405c9 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
1095a1f7-41d8-41b3-9c4e-9a910624b565 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
13b15da0-a934-482c-8aea-a35a358d0040 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
175f1662-ec38-44ef-a219-48a74210c46f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
25c7c50e-099c-48f9-985a-8d9503285c1f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
2663d61e-a9ea-4e55-9800-dc9d5647d33c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
29ef90b9-2ea8-4d25-81c1-b69b50a2a0f5 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
2d30ac7f-4f81-4118-9d5a-3ad711d7ea80 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
2ff4b31f-402d-4b9a-847f-a93209956482 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
327120d5-ab67-4602-b121-4b63dbea0812 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
33cd40fd-68d5-49e7-b28e-e770d27a3c00 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
38ae9491-c1c2-4fe1-9970-b14b5754915e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
39cfc813-49dd-4991-91f4-e8cbf7365957 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
3aac25cd-18d4-42f6-8c11-945552fadc82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
3d5fbd3d-7774-4969-89ec-0980349482fe | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
40564c82-c3c5-42f5-b53c-f0cf24544ff2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4369a697-45f6-4f7b-9df9-f4f7b462c5a1 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
443da5f5-40ff-4a48-9f8a-327cd6c62f82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
44650334-5131-4870-9b56-a54802ed159f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
44c3317f-eef0-4f98-be55-2fb244b082bd | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4546ef99-0c98-4b26-947d-dccdf90e223e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
462f680c-8c4d-4283-a9cb-c051c3deec25 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
46ee302a-de1d-48f4-9c81-235337c7ce5a | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
470755a4-efdf-4ab5-858e-073bf26e177c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4a42eff8-044f-4311-bf8f-00f6465692a4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4b5f1c21-5255-482f-bda5-62bd6be6a9b4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
50790657-e212-43b6-b0eb-0dfa19a1ef78 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
517133dc-441f-41ae-ae6b-f6d1c433af9b | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5709ba8f-816b-43cc-a89f-343c48fb2433 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
59c8fc01-639e-4a13-8721-b44943e46e04 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5baf3b98-ea75-4c18-807c-ca39ebbce0e6 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5c5719c5-37ef-4b2f-b782-42795374cb57 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5cd5616c-6f7b-4efe-bc95-970d3669ce69 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6089591b-f976-451d-964d-673d2418874e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
60ccd8e9-edda-4b5c-b244-68f461cdf38d | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6373f150-fffd-49c8-9097-937ea25a8796 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
66466e1b-525a-4fef-91c5-975c99eb4cfb | Pole | 0 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6a47356a-c822-4bdd-8074-be17c440c57e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6ce62036-f92c-4482-9a4e-7534971edc88 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
72663578-72f0-4579-a218-40d4ffbcb42c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
73fc4211-e067-4eb0-b436-3fb0d00b87c5 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
760f5dc9-240b-4373-9fd2-bd08f08ffbac | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
7a138981-8606-4d31-a4d4-a8c6a97c102c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
7c01e3ad-66b4-41b2-b0de-539308e0a955 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
7dd2857a-bc0c-412f-8aa5-d3dab831e510 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
83ecbd07-9907-4007-b566-21b3b11a86d4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
86cff8e1-2989-4640-887d-a7ebab1535d7 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
8873423d-378a-4af6-8175-12a054520c81 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
8aa38f18-e81d-45fa-a12d-856edbb8a495 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
911e85b5-ab1a-4e89-9ef3-c3e6760fd084 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
93e27638-5729-44b6-b534-6dd6a741a88c | Pole | 0 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
9bb9420d-a7db-4ba1-8e1a-90986940145e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
9e8598f9-4271-4af8-8da0-1b32cbc19519 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a15867d6-bc7a-4471-93a7-6b786534f678 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a4c41253-5265-412b-8590-07f4f07df7d4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a74eadf3-e41b-41f7-89d8-5deab2996789 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a7672d38-3c76-493c-ad3a-59f329e45cd8 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a8b5fe50-2c39-4c8a-b16f-793e6f10556a | Pole | 2 | Distribution | 2020-08-19 | 2021-08-19 | Level 2
af802fac-1402-41e8-83f8-cc888a43f354 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b138b43e-3a72-4d7e-9bec-fe0735ea3a7d | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b2316b78-20b9-437b-81e0-045b39f6d125 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b45f0373-1ad9-4cfc-9278-7dd1ef3fc6ec | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b5e5a689-b304-48b7-95c4-8966b0c2c421 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b64f6e58-abcc-4bf5-bddb-1644a64c1fdb | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b9188a3e-207c-4189-ae54-2358ce7e1e40 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
bcf8b45a-8487-4bc7-a8e0-d7b363680fdd | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
be93ec67-49c5-4db6-8fa6-0246a9f2b08a | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
c68bf7be-9539-4f76-9a6c-7efed0a94a35 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
c749493f-04f9-4087-a555-ddafafe7fbb2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d23e8e37-7c92-4ce9-a670-4da00fff9de4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d47facfb-c829-4102-9d60-886dbb6f4db6 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d6f421a1-cce8-461d-84cb-3ba32bf766ea | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d7f8e1eb-e163-4890-ac62-6a7fe6dd5a02 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
df5462c4-331b-426f-a4e3-8d572bd288e7 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
e2b7dd9a-1898-4c4d-9607-98687ba39676 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
e6698b4a-c239-4dea-95ed-1e676c83091f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
ef678ddb-5991-483e-ad56-c631c85f8f82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
f188fab2-03c6-44bf-bd2a-9054c657b3bf | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
f273512b-7a48-4b91-8957-7ec60a965b61 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
f4949f60-25a4-412f-87fd-b0a786be3b29 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
fd24a9a4-ef63-4840-bf6f-6a64480f8e27 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
fe2f857e-3972-40cd-b6d3-f614903a91a2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
02c955f1-c0ea-43fc-b9df-a55734a8a077 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
046ce6c8-929e-41ad-9d43-7239d315b280 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
04929957-94a1-43c6-94b2-8be6b2b3a8cb | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
0784caf9-122e-43c8-8c37-be7a23f9a8c1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
080420c0-d108-4057-976b-0baf9dd9aeae | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
080bdac0-5181-43a2-bd24-ccb91e925547 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
0caca01c-db4d-483d-981f-f6230422b8d3 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
11423224-828e-4e7b-a7b4-e6a7f4f3c75b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
1cfea449-468e-44f3-b0f7-b7ad4ff6b767 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
1d83f641-e17e-4a91-8a61-e8bdfd5a64f6 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
20037d15-fed1-4a24-b0fc-6db8a39955be | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
20701f49-a4ca-499e-a442-2596fd6990fc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
30f1e271-0964-40fa-a120-75f53679680e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
31b4b520-499d-4290-beaf-7175e7afe03e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
36ef9d67-8998-401c-99db-330696393cd6 | Pole | 2 | Distribution | 2020-08-20 | 2021-08-20 | Level 2 |  | 2021-03-24 | 2022-03-24 |  | Required to Re-inspect a subset of assets
3d0b51af-a482-44c5-ad77-e2beacdaacdc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
3ecf158b-3797-493d-81d5-fd83ff9946dc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
413a6a09-624c-4dd4-af88-7e92a1069c2c | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
434e1e55-a04f-4756-a7c0-817ad9f97aa9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
49ad1175-8d66-4c68-8b57-22fad176056d | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
4f27343e-ad92-457e-aac7-df14b975fe9e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
4f406a31-3d44-4b89-a8f6-8409844660f9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
4fd93608-f794-4726-98ec-6ebae4779bda | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5a5b48ef-833f-433c-8525-bbb26d81e678 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5a6a2a72-367a-4962-800b-11cdcc428e29 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5c4017fb-fb9f-4167-8ffa-ff9fa7db18f7 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5d030dcd-6912-485a-8ca6-26e1afd3f51a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
6b70e287-fac6-479f-ac15-3776e01d5080 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
6d0a4a2f-a8ae-46d7-b318-eaca4913fdc5 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
721d35a2-de0f-427b-b61f-7f643b0aa11f | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
72bc2a09-3345-4d19-ab1c-3b9cdc3896e5 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
7bde8c50-9400-4f08-89c3-a50632f44772 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
848f5619-1dc7-4ae0-8906-23ed199b5d6c | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
85cb32f2-1c77-4b97-a761-57b880250339 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
886216f1-afd0-4ead-aea1-e3c173754212 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
8a075a2c-d5c0-4b5e-bbe0-50c2bb91e706 | Pole | 2 | Distribution | 2020-08-20 | 2021-08-20 | Level 2 |  | 2022-06-16 | 2023-06-16
96a498b7-c844-4958-bb33-ff0cd3a453e1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
98e69d14-a840-4608-a01a-e405bad3fe08 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
9d25cf18-91a0-4471-b7dd-d6edf9c26d37 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
9dbc7287-6aa6-4a14-a5a1-7a16aef3d578 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
9ef66c75-aebe-4eb1-a36b-4093959608e2 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
9f9e0c23-5447-42f9-a68d-a3fc19c4bb56 | Pole | 2 | Distribution | 2020-08-20 | 2021-08-20 | Level 2
a2c94345-e9a4-4cb8-8844-a62af37f2111 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
a72476b1-1614-4a7f-a97a-c9dece18d7f1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
b199ce3f-8cd9-45cb-b9c0-53378891b31f | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
b56321e8-08a1-4803-b2cb-5b0812b55ade | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
b648586b-3fc7-45f8-acda-058f3a15894a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
c129ca7d-ed0c-4254-b9c5-641333619ca9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
c7c2562b-fae5-4fe0-b7bc-89253ca5dd1b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
c900045f-f318-49ab-a830-a32f27695c96 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
ccd478d1-b4a5-4c0d-bfaa-7a1a1e03360b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
ccdbe39e-5ed6-4209-ad84-c42c01c0e7d9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d3c62967-cdf2-4341-8c88-536b7a30af00 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d7e811b2-3721-4feb-8b2f-48d8f27ba946 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d8d9b280-4a8d-4609-a737-dab6528bc1a4 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d9cfb9d4-94f0-4570-b691-1d71d00d4460 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
ddbff38c-084d-414c-be5c-478240ed2285 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
defbe8fc-f958-412a-81a4-402a0bd1ef2b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
e4d07fa4-9cfe-4bf1-b285-49503dfb244a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
e760087c-bb48-4c00-807c-29427a41bb11 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
e7a8049b-d174-4b61-891a-9918452f9b24 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
f442b77e-cb66-422e-a8ea-e0596c67fe0d | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
07e77001-3fc7-4b34-9659-0d48e2bcab85 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
120a58a8-b0c3-41d3-bb84-da1f25905a69 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
16a43eae-fc46-4dca-bdfa-371eb00bda01 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
17a99d36-eed9-40ad-9aa3-ec8d689230d7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
181416d8-5923-4b0c-8cf5-091451d27d45 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
18e3e729-8144-43cb-a98b-e6b18d99a77b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
19b5d6be-7b33-440b-bfae-1db15d626e24 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
1b164444-d1c5-437a-90b4-67936087b88d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
1c0d7534-e690-4c0f-8e81-210c9bcee5c8 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
1f4cdf85-591a-4ffc-ba96-bd0cf71a06fb | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
206dcf61-946e-4705-80f0-0bee6cfc2253 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
208899fb-877b-430e-a144-89ec87c5d537 | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Required to Re-inspect a subset of assets
2256753b-572f-461e-87d3-1fbfae08fe5b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2404b8fe-084e-46d3-bb1d-b3f5a56f3794 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
26359e5c-65fb-4759-b965-3ea13715fdf1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
290bfdc5-072e-46f9-8c7c-2ae3816280ca | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2911651e-0244-4029-9114-11c08591aafa | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
296e128c-6c61-446e-ad5b-afd9fea966f2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2acb6da7-16de-41b2-9381-8595a4426468 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2b35dfb7-d39d-48bd-b6b8-b278f1df137b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2e56e6ed-6bf7-47b7-a989-fd412931f776 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
381e8af2-1000-4949-9235-6040da3568ef | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
38b3744c-8a90-4ebe-87f6-f8014a1f0e82 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
3f0bd24e-ceb5-4c24-a68e-c51b13344ab7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
3f9a6f37-595a-4641-af67-8a8e3faba5d1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
423b9eaa-1d6e-4bcb-b984-8aa9c584c967 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
460515e4-f6fc-4904-bab4-ee97dea0cd9d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
4d33210b-47ca-4af3-912c-4b60024ea558 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
503edd13-1405-4654-a70d-285465a4416c | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
50eba439-7ded-4181-8816-c02f442f6339 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
5749e759-008b-420d-a6d0-a185be758918 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
578bccc9-a71a-48e9-ba9b-019c616783d4 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
62c99459-aafb-4b54-9943-e4225ca1d3cb | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Required to Re-inspect a subset of assets
648f480a-ca28-4729-b215-58ce1b046b25 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
65ee9b37-0b7f-44c4-8af2-d2b13933f0f7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
6788174a-cc61-4c97-ba38-c500cf43cfd3 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
69a730e0-23fe-49be-991d-2d0509a6f407 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
70170b6c-6ae3-4efc-9e25-bcfa526b0102 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7046a946-aa1c-4421-8be2-7dd426be470d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
708b9374-1d03-487e-9584-ffc790998eb3 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
724b8804-5e98-40e5-bfce-24e62c9b9745 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7254d6e7-1cbc-47ee-965f-dfc73cb7012b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7464383b-60bf-474d-aa59-bac45025e8b1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
74a9ec57-97db-4ead-8bac-a45b658a4724 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7bc4e703-2ef2-41ef-9c46-7c85d08bd49b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
82fc94cc-c2af-4a25-bf7a-7f044b54971b | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2 |  | 2021-06-09 | 2022-06-09 |  | Required to Re-inspect a subset of assets
8b195a16-3acf-4455-b579-1d75f8cac2bf | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
8ddd82c4-023f-4354-96e9-10b74739127e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
9262dfdf-fdfe-4fd9-99ba-98a108480f9c | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2
94149a5b-8f4a-4555-8f20-a0e5104bd592 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
95dc0d80-5869-468f-b4aa-b34c8819e8fb | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a0fc2ac0-9e91-43d1-b7a4-6889bfaf3f09 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a1f9bab8-3242-403f-8cf9-5a87f6f5b867 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a243caf2-ed7b-4888-a349-634bd5d851c9 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a4b560e6-1d75-40cb-a115-e7764c2bf7e1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a6d14036-12fd-4c1b-8ee3-65fbc530b644 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2021-05-10 | 2026-05-09 |  | Required to Re-inspect a subset of assets
a9428bfe-0632-43bb-b908-445120f3e936 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ac165c9b-15a1-49e8-965f-1769af3fd06e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ac4dd433-43cf-46b9-b6b6-568aeaa7c929 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b02a0c2d-4dc9-4cf3-b256-40d1ff9ef270 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b046d6b5-9f41-4f25-a3bd-d4b59c7628af | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b3a1ef30-ccbd-486b-9c9a-92e252dc3985 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b4bd537e-8cb4-4d68-9778-a2fdddf7aad5 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b536a166-6092-4f29-9fd5-2143c80ce1e8 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b83e0265-85be-4f55-badd-a27c37b6edf2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
bbed361c-7952-4b23-a0f6-1f576c0fbcf2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
c615d57c-94a5-409e-845f-f88c848eef43 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
c72408f7-cd4b-4530-a85f-8d9f97ef8ef0 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
c7bbf099-b30e-4738-b921-90db42b3aa68 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d065a93c-2b76-4ddb-a651-a0c8b1fec846 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d32d0d18-c709-426c-b914-db34bd194039 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d377aaf3-701d-4eff-ade6-67ccf33aab48 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d424608e-b920-4abd-8677-75990a249ece | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d4a7cb65-7f1c-4982-8440-273be46d92ba | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d6c67903-58a8-4beb-8c54-31632b0ba073 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d8f09f6b-032a-4324-8d1b-23324449e63f | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
dd1a9414-6087-40f5-bfcd-a04017f99b0d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
dd7db983-9c8b-466e-9335-6082c40a9b30 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
dfde9fdb-3f97-4c82-b1b2-c879ab736ccf | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e0db0126-a525-4fba-b218-0e4187c4e56a | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e41a0e8d-d0b9-48f0-a74c-4433a5b2fe7c | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e9d88dc0-89c1-4ea9-93c6-5ecbad6c72a9 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e9e09793-9636-4526-a13b-cb424e4e6672 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ec57f022-d105-4971-a0a2-a20855e356ba | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
edb3418c-512f-46d7-8443-d9a508cc7672 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
eff1f07a-da92-4609-adfd-ff1fd725c85d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
f27d39e6-a57e-442d-bdb2-98c165f32a0e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
fcf8168d-30e0-42ab-adb2-36e4655389f1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ff4ddf1d-a766-48e0-9172-3a52af9f0191 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ff711c0b-540c-4490-8846-4c33771bf483 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
03a54ad9-5348-4f0a-a037-bac73be6983f | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
07a1549d-1957-4e74-89af-9e98faa8f0ea | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
138b0dad-0a7f-4e38-b381-4be4ee9a2f49 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
13c979b0-53df-42ea-b29a-161e807952fb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
1804d141-8abb-40f5-a34c-c4b127b9abf5 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
1beb9eed-ba0f-4dda-9d47-f2dee27912a5 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
1d911a6c-d51f-4dae-958e-1f864a1b066a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
25dde5d3-9c0e-4a3a-bb29-c29926f5cc49 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
291ff5a2-1c7d-4228-b267-69eca0d406df | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
2a2c61a2-e97b-45ed-8a12-51f2093f176b | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
2a42f3b5-3927-4be6-b9ac-1605b38dd52c | Pole | 0 | Distribution | 2020-08-22 | 2021-08-22 | Level 2
2ea60b47-c3cb-4980-86b1-a7d86aef722a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
2fd3bf45-f566-4dc8-bbd2-6241c11a7da4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
3138744d-7da7-48b4-8646-cbdcfe52ddc6 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
33ffa39e-6a2e-4bb2-93c7-e0386b771881 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
36ae1088-f3a9-4747-9692-adb8d2bebbe7 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
38b0a9f4-2f81-4691-9e88-0f0f66e84a2c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
3ac3a03b-081c-4bc1-87f6-fe6661367242 | Pole | 2 | Distribution | 2020-08-22 | 2021-08-22 | Level 2
3d5f2a2b-7035-4c83-ac98-ec0504d618c9 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
43f9115b-9101-40f2-b41a-9f811941ddec | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
455bf8ee-ce56-4cd4-afbc-b1fff98db057 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
455f6c3d-6030-40e9-91e3-05c0ee958885 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
4857f2bb-d3cf-4fd2-808a-8f0e3a6c27ff | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
4a2b7159-6a1c-4f46-b9e3-35f3cb7ea8fb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
4bd97999-6744-437d-a5d4-c513db99e08a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
5047d9df-483e-463d-8cff-9352daba5a91 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
52c5b391-9858-4285-a4a9-b8dee6260a2a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
55aa453d-d19a-44da-98b8-ae57d0a16e5f | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
574110f9-6a32-4710-a86c-8915792b1042 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
58d41ea1-78aa-489f-a9d3-1626a21827a4 | Pole | 2 | Distribution | 2020-08-22 | 2021-08-22 | Level 2 |  | 2022-08-01 | 2023-08-01
5fcab607-b49a-44b8-a4d6-2e826096f695 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
6fed99d9-a3a0-4e88-ba36-a623728d58cf | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
714cace7-bdee-4b10-a429-dbf01f0d8817 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
7205845a-d190-4a6e-b656-f2d75b1c0ce1 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
73c20c2c-9d87-4e8c-b04e-8cf38c58b9b2 | Pole | 0 | Distribution | 2020-08-22 | 2021-08-22 | Level 2
798006f7-b816-421d-a0e1-2119e0cc3dda | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
7bb1765f-48ef-4464-897a-ad1ece8d4edb | Pole | 2 | Distribution | 2020-08-22 | 2021-08-22 | Level 2 |  | 2022-08-01 | 2023-08-01
7dffac05-9b4b-41f5-bcc5-71667cd534e7 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8384026b-79ae-469c-b380-0e95714f70ce | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
83ca67f8-eb62-4096-819e-6dd136034245 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8a735ec5-2713-47c2-91f0-271596c41001 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8b3703a8-8b2a-4429-99e5-3ff8c9ff6d37 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8ce2769d-c402-41bc-a24f-6d47b4a2d5c4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8df58217-fabd-4d04-994e-a0b3d66b49cb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8f0be831-2257-4c68-899f-c8901df70abe | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
93e1ea25-ed79-4b46-9119-1df8a838654a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
95344de2-059e-44da-87fe-eff7f0340c40 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
993bc072-b69d-4438-9527-14e3430aff12 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | 2022-01-17 | 2027-01-16 |  | Required to Re-inspect a subset of assets
9b6379f0-956a-4034-91c9-6ba5f91802f3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
9f85ee01-9a5b-40f6-ab78-a3341136817a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
a09e5d65-3ee8-438f-a62d-1b04fd7abca0 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
a26ae3f6-57d8-4769-ba5a-d115a73f924c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
a38d2c32-3b85-4f7c-be15-ba0c32fec1ca | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
a4062a4d-8e86-4645-a051-5fc867a0e355 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
af4c6123-df01-4cc8-9fdb-593b7b3e4e65 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b1b3fce1-6e7e-41a6-b32a-45ae0b6a2b65 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b6a87fb3-e863-43df-bbe3-65a8b7323bd0 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b6bb7f89-b211-415a-83b5-89fca471306e | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b6d072b7-22fb-42f6-97f0-6d10a2d1a6cb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c2284def-ce66-405d-96a6-e4b8f0699bcf | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c2cbda82-13e6-4bbd-9b75-c594b88cfac8 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c8f0f0b4-6bfd-40eb-b187-3e6bd285d61c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c9ce0c68-3e3c-400f-8a61-f541e4c13666 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
cab9fdfc-acb6-4fc7-8a95-0b0221c4725a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
caf10615-6298-43a4-83e3-6b71b9675914 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
cb7df45d-150d-4d00-a026-402a1e1107bc | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
cd0f189c-5904-4f67-9b8f-c99be5fa5130 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ce3f6533-b1db-4ecb-9b0b-109b863824b3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
d188cb32-1117-4adb-a63f-afe3184569d2 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
d3d58892-96e0-47a0-841c-47234b991750 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
dadb22c0-33eb-4413-97e1-11d2f1da3d99 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
de3aba20-9ef5-40fe-a095-ac3e0dfa3f52 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e0474074-20a1-4fb9-b3af-d7641d8cdcad | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e1b3ae38-18c4-491c-8fdd-e6c120a8b73c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e29abc5c-7cab-42e3-b81a-a9af7413d7c1 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e53b9ff8-377c-4624-8d57-fa8ae40e9fae | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e9254aff-9023-4222-8427-0642bb90b0f8 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ebc7b5a6-e101-4da7-b444-003b4cf170f3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ec3dcdd7-9c3f-41f4-97a2-a325d4153c1c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ed1c1b49-16bd-451b-9582-827f27784724 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
f15c5192-2dc4-4e5a-8dbc-e47821b82018 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
f9655750-ee7a-44a0-8f04-80135fcdcf77 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
f9fd398b-bc2c-458f-981e-80f73a36c463 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
fa9c2cd1-dd55-4c6f-a638-084f2a81fe81 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
fb35cad8-18b7-4afa-95fe-70cfb50e7f54 | Pole | 2 | Distribution | 2020-08-22 | 2021-08-22 | Level 2
fe7a8dd8-8790-45a2-b39e-812edd1361eb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ffe96216-db00-4a09-840d-c79543dffda4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
03959e41-5712-45e9-8064-9d0cd087740a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
03c332b7-ab23-4d04-835f-83ed423c16fe | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0509118a-5be4-4204-895d-5d9ca101510e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0533f8d9-f359-4131-ad25-7aafad4fb232 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
05be7bde-3810-48ff-bb53-0364b44a91e5 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | 2022-09-01 | 2023-09-01
07159db7-db1b-4b8f-82d8-27cea174a573 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
07bcb6db-ebf1-451e-b2b0-cbac7c0752fd | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
093cfc04-1c50-4834-a64e-a20747f7cb23 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | Required to Re-inspect a subset of assets
0a34fe5f-7f51-4afd-8527-9dbf5b62a98d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0c576fa3-328a-4596-b4a3-93a10eecf676 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0dfa2a0d-43aa-4e39-ac2f-a6e18bf117a3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0ed56227-999a-4b37-af68-fdc8b0ea4438 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
0f277fe5-d973-4160-9ef4-936e0bf5473f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0f8278c0-5d4c-46ea-8eeb-0dcaae21c278 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0f9baf43-159e-4d43-b950-dfda2d8b8b7a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0fe8598f-55a5-43a1-b1b0-c8eedfbc5eeb | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
10e52de0-8ad8-47fd-ad88-4cc811f53231 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1531b749-4268-450b-9d0f-fff2cce2c90c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
15cea97c-174c-4a49-a4a7-d4af04b3b229 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
17c89b67-9c69-43d1-851a-cdbd04caad12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
194783d2-4339-4b29-aa4a-c5c6350ff681 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1a6bc9eb-b33f-4881-9b83-bd83882dc9d6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1a86563e-f6fa-4bb1-bb29-907fe461d184 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1c69312c-875f-4482-9837-cb21ef73029f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1c8199c6-504a-4cd7-824c-9589720bfa24 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
1e030840-5d4e-4de4-a1fb-22270c81a486 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
20494439-07b4-4765-bb9b-9a10b9919d39 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2157e450-8c93-4cf2-91f6-d09d301af560 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
21d20f80-bd9d-4cf1-912d-28a5e25118d3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
23c8095e-175c-424a-b73e-fa1e25bcb57a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
255fc0f2-f0f1-4434-893f-38c5529608b8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
25a10e5e-b5b6-459b-a7e0-d85acf4759b7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
26b159dd-11e2-4cfc-874e-442d8894933e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
29e8f289-377c-4710-9e73-25e90601395b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2a0d97f3-0303-4f8c-a13f-de23903c8c12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2a9f4372-774d-4cfb-934a-4266e5ceb8d8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2ad9e6bb-cd42-4107-b85d-713c55e549a1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2bad306e-f2bb-4655-9e60-3200b56187e8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2bf9a9cf-0f27-45b9-b079-82b5fc528394 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2c2653c5-5a40-4b2e-bd53-100e06ad2691 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2c780323-ea7c-4568-a9a7-ff4d04d74b05 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2d72985e-be3c-4906-8b4a-289b9060b7bb | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
30e20acc-170c-4051-a7f2-9b9c3cfe3ed5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
322d579e-b470-434b-9fb9-617cebcf406e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
37811f8c-b4fd-4615-86f7-c7938a590e7f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
3bc9967a-d0aa-4488-a474-f51e867c36e5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
3bcb8731-93b6-4792-8428-c5206e100620 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4002d2ce-9bf0-4bf4-8688-f5857beca803 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4083875d-9460-4504-89c3-7fe0e4b6405c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
40e9c7ab-7d5f-4847-9b65-22cf83312526 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | 2022-09-01 | 2023-09-01 |  | Required to Re-inspect a subset of assets
41002bd6-f76f-4d7e-a8ef-911facb83c85 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
422d8a55-b179-4a29-ac5d-69f8235f292d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
43a07d3d-b42f-44ec-bae9-02b23d36b2d1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
46f1eecb-5681-420e-b167-9567e773d5c8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4a4f11ce-fc5b-49e3-8e5c-9e6c3a4944f1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4bb4eb82-e238-4578-bb15-809d0e3feec5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
50389f54-5bdc-4015-8318-a3b44dd125a9 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
53d78c6e-5722-4446-9f01-09481e51ff20 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
5bc97d7f-e75e-464b-966c-8eaa206a0d12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
5c33c5eb-fed5-4029-b3b5-61a78f2d647d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
5f3870d1-710b-4bc3-a3f9-672b0bdbd90c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6459fb92-ba38-4e6a-9457-5d82fc8dca52 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
653e39c2-86c5-420a-93bd-823a9b33cd47 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
65cffca3-84ca-47bf-b564-d75dac5cdc08 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6635d941-e229-4b81-bbe0-ab452de061f8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6b2bbb73-3f82-4f9c-a0e8-927f38bcc7dc | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6db749a1-1a5d-4c39-a1bd-7a12f61de856 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
715570d0-7fee-454d-af52-64d6692fb73c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
71d11db3-e944-414c-bfaa-ce24d212da3e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
737e8da1-2771-41f6-9524-ef0d3f6d00fe | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
73bd8e10-363d-4ae8-96c2-68505d266d8c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
73d5aba5-3d28-4a5f-bc47-6e9decaafcbd | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
74229587-c37a-4884-ad39-1b24a79243d3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
77517874-dd3b-46ab-af63-71f1e66afa06 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
78e55c04-9191-4af6-9b78-29a17131859c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7c2634b8-6da8-4192-8f1d-fbadfd13b428 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7d43d86e-07fb-4fa3-ae2f-bd32605b066a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7d4eb686-fda6-43e4-945b-326a3b89e5be | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7f7e2670-8d9b-4e1c-85d4-d16716bffc07 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
82f87c6f-e524-4581-919d-c438606b880f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
83e35432-4064-4aae-afda-55c42783f64a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
86d73140-d9c2-40dd-a974-9f80754c880d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8746834e-548b-4ea1-8698-f62cdda2d08c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
88308dbb-4ab0-46f3-bc5b-b11f0dbe02a1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8bc662ce-450f-4725-8101-d0acc4878a3a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8bf43cfb-1590-4a26-8d4d-d33057e1545e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8d90996b-d904-47c1-a474-ddf27517edf7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9417c7c2-27a3-4444-929d-99550aee1a7a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
95ee95a7-d907-4b38-a868-7d3c30aaa927 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
961222b1-4a34-4c6b-b4bf-b38aa160118d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
96e51c32-f160-417b-8e13-8a4c8b25a3b4 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9c910675-6a06-492e-9ea8-b2026b6232ba | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9cb92896-3a35-4ec1-abd6-a0d3a2353e61 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | 2021-05-10 | 2026-05-09 |  | Required to Re-inspect a subset of assets
9db055d7-2483-45fb-b97c-470efc2fc826 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a45f56a7-54f0-4832-a465-50e732eb111f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a510717f-51cf-4a30-b879-a62b0bd6ef6b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a6f82906-da08-45ee-85f4-7cae9d535516 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a8c68e71-550f-4dd0-b3f4-8a768fe8728a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
aa45a9d2-4e27-4911-9157-4dd9ddad9397 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ac887a93-6032-495d-9319-29a17c154294 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ad6bf67b-b398-49fd-8fd7-97736345f7b3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
afb61237-75a8-487c-a036-783048f8dcc6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b1b4e4d7-b056-4319-9efa-242c22516399 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b24ac6c8-e066-45ff-b166-d6ff54da78f8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b351a7f2-224d-4cd4-aca5-22122e479ac6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b399f829-020a-4886-9382-685feb32e14b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b4a4247f-7853-43ff-bdf5-b9ee9e8be258 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b70951ed-fb8f-4576-ba69-5605aa6bf76a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b76bfd6a-40e2-4079-a87e-b850886417ae | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b85d380c-57cf-4c64-9aad-1b995413088a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
bc4f3a85-7192-43eb-9f56-26bc260cb3e8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c0b3e5af-87c0-40da-8175-68dfe2b2cf8a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c646a5b5-fc57-4f5d-be09-9db12d1cc650 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c71cbab4-722b-4b47-a86b-33136ea63b77 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c750e280-511c-43f3-8729-73715423dd5c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
cc0e2af0-179c-49f2-9df0-54ac69d1af88 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ccd99c5b-9b21-40f6-837f-4c788ec7d461 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
cde96f37-e445-4374-ba98-c3b43593b3a7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ce47a680-b0b4-4448-825a-92bd03b2acd6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d34d85d1-ce18-4be3-8290-f469ee2d5f4f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d39287cc-a79e-4099-932f-c76fbac2db39 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d4751484-6b66-46bb-a175-1e5165e64c05 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d505db20-efbd-4d35-aafb-f5a08947d83b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d9bf2872-c676-4c0e-9f77-33f997728f81 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ddf3ecab-d5c3-4b29-92f2-91b766903775 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
de0a915b-ead8-4c51-abbd-81b09d336567 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e0deefa4-7549-4abd-b562-43394f0bc88c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e26e8dc8-b761-4c38-85a8-272adcf8f5c3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e2ddcbad-e02d-41f6-896a-2ccece9bbd56 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e41dde77-3a78-4ad0-a169-2815a08ec305 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e643d1dd-2f70-495a-84d0-352005bcafe8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e8c7318b-28de-406c-9fa9-6a5bdb753794 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
eaa75bc6-f620-4fb9-9d8e-eada2a070958 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
eac3aa17-2c63-4359-91cc-5152023cdc1f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
edfef705-72de-46be-b3f4-850b9d95c468 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
efa95dfa-f8de-40bf-a995-227fe933aba5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
f34f2a8f-96c7-4570-9d8e-2de9f097cca7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
f3cce9bc-b5f8-479f-be7a-07dd22f5c398 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
f3dcbfd8-0e2e-420c-847d-81f844cffd16 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
fd829f2b-ce2b-4922-97bd-589472d85208 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
feb7c63c-674a-4f50-bf0b-b62233d13bd4 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ffe7de67-0575-40da-ae6a-dbd636c5a3b9 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
04240fbe-8615-4a27-9b7d-38f9c513796e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
045d07b0-95a0-42dc-a023-d0d23a813c5b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
05735387-2b6f-47f4-aa1b-ed79fed23364 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0642d086-0be9-426b-b9ac-9a801b57a878 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0689b605-fecd-4319-be07-2bdf5d64ae8d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
08208c8b-bc39-4294-af3e-51e6ea1fb3bf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0832fd9f-32ff-4381-9159-a4301b83620e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
091ac45c-1b4b-45e4-a73e-5e1b04c88ce6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0bd47bb2-1245-43c1-b024-a004cbeda03b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0d52d201-79dd-40e7-a479-9a4d412d3fe3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0d80d7dc-eb08-4e31-8596-91016621b234 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1201c7d1-dad6-456a-976c-22e94956bdf3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
158fc6d4-50af-45fe-b5f8-bc7132288d17 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1713e222-b452-4ff9-b79f-befb05579412 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2
18e5d7d2-a28e-4db8-89fa-5d50abd3457a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1a437a76-6ca1-443f-a2e7-344b91852719 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1b6701c9-3d2f-4ceb-b814-53f3396b833f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1cbbe529-3a0c-4c33-9565-d00c119d1b4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1cfb9c8c-e949-4acc-b0d6-4a339c712a6d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
21d5df52-4e67-445d-ac9c-725275a44f0e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
28b41204-6e2a-48ac-a8cd-775283fda1ba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
290650ee-3e72-48ee-9fc6-a0c054289240 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
2b5a7faf-e1b4-497a-83f7-5b9788bef450 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
2c8ed2ac-b841-49a0-811e-814adf031065 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
2f68e0fd-edf7-409d-a930-564e5e540938 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
31890bb4-24f5-4e2a-acb1-1a0b516b8fca | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3205ee93-d368-4642-91e6-c88ee4d6ca54 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2
356c03e0-a104-4da7-8cc6-0bac1ac8e8d4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
35a966f3-027e-4a5d-bd6e-49dfbd6d8232 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
369067ac-d08b-43a7-a9de-afebe9bd2606 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3787a36b-b6c8-4ad2-bbd1-957fb132a548 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3a1eb240-3e97-4ea1-9eda-66939614ab67 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3c007cde-26f1-428e-bc0b-f0653aa957db | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3db2b8ec-f03f-4428-8c6c-29036754afe0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3ec8fbff-93a8-4042-8e0e-69bdb5d8cc91 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
4639c896-33ba-4496-8a7f-7f79b405920a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
471a5d38-e10d-4c5f-865e-c9911ce99d4b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
4bfebac9-2560-4f0c-a90e-91c671b8048e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
508c141b-125d-4ba6-8992-7ad79f3ae5a6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
51634ef9-6b28-4308-a0ae-e33bf474a973 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5330c84f-9b80-495c-b861-aaf8ac0fb7c6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
53479864-ed55-4c5c-9aa8-5d6d490e13fa | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5775b823-3452-45e4-9aac-6665444284ba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
591890f5-503c-4d4f-89e7-57bbf4109907 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5b36e71b-745e-459d-b7a9-3f095b896ce4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5c7eb72a-e97b-4b09-aabf-984b8fc9b0ed | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5eb99e4b-7408-4098-a89e-4f6e2401656f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5ec95d73-3fa9-4f7e-b013-15dc90e532b7 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5ef33cea-2239-4aea-9dc3-0f0e36e42d49 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5ff5527d-4d84-4af6-a6f9-28f25451bd7c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
611acafe-5c5d-4f1f-bdac-b6df3554ad75 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
63af1910-deea-4bc6-85da-9a84b0d40ecc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
64d293f7-bc29-49bf-b88f-087ab25c52d8 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
69a7761f-4081-4dfe-b411-874b7a3f925d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6bac055d-196b-4d53-8f2e-cf18665e5ba6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6d1665d6-c454-4ddd-81f1-aefd3a96579b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6d8b2cf5-7dfd-466e-840a-4ce363c319a0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6e70763a-c65d-428c-846d-f43e4c0bd236 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6fba6b99-d8ef-499f-82b0-bd7e50630f65 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
72c073f8-70af-4d8f-8e05-1f186a8bf22e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
73cc2647-e5df-4549-b79d-1c4c63f0d7e3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
767d3999-9b67-49b7-846f-b276f2ed11bb | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
79edce01-d09b-4375-bf3e-f7596c38ed13 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
7bfa8f18-4b4d-4e46-b2a9-9704e3009c4a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
7c02d2f9-1c8f-4cb2-81ce-70833d3c0d23 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
7c4721e4-5abd-443f-ad8b-1440a91fa3ad | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2
7cd7f51b-ae5a-43a0-bb83-dec7c55b1665 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8189db7b-78fc-49c1-822e-edc1d7fc8aac | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8376508e-1e64-4bf8-a050-2603dce0999d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
86b1e3cf-37a4-4aa5-b67b-090768153103 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
876ec2b5-1023-412a-b8f1-258f5763c847 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2
881aac50-c5ec-4d3b-880e-5d45778a6ba4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
898a9cae-21a5-4dfb-a943-0b88b56bd2ef | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8ae398fe-aa12-461e-b480-6aa1975fd365 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8dced52f-467e-4903-b7b7-0dc9c8f286c7 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8e1d1a36-483e-4ccc-967d-8fab40e487f5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8f46bb38-599f-400c-ac58-15d64dcc60b0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9028919b-c486-4a59-8250-909e35736c4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
91e29412-5c62-48a1-abad-8ec5da3020d4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
924b6453-1ba2-4430-9b56-ee7133ea44e2 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
96a224d1-7736-4cb7-bb4a-762385ab3a89 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
974d755e-6c14-40a8-ac35-7f210a4b2b62 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
976892ad-4b3a-4468-943b-f56b5bb6d73c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
97e49778-1eee-4438-81ae-7040ea1f2905 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9979df8c-c3f8-4472-97a8-231e91ff0e6a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9a7a7b73-82a9-49fe-ae6b-2f2ca24d9437 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9acc4129-1b85-4117-b0cf-508654e0bfb5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9e15aaf0-92f3-46e6-b145-a670d9c44397 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9fae1d3d-4f03-44b4-8af0-6f867fb9a838 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9fcd68a0-7631-456c-9a09-053129464caf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a0c62f60-bb66-4ba2-9d29-60ded7e52771 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a0c8acef-2327-4529-a12c-0c556ee890d6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a6b117d3-dd97-4fec-8095-8c70969cffda | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a7a57a60-4bb4-4295-955d-80307362806e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a8b870fe-fe2c-4a73-8b64-1d177e7f9bf4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a9468f7c-0233-4c00-ad49-6b3c0d72f9a2 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a94e18ce-e4a2-43e7-b4c4-f086c045997f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a9fcd34b-63d1-4e67-a632-bde997c30517 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ab3fe644-3280-4509-a0cd-1ce9fe622fa5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ae0e8e50-910d-472e-9c14-ed5c90828881 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
af5a584c-12ce-4b47-8f8d-32dd295a4b8d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
b1a97f1c-ffda-4c76-9ffd-0b2b7bf246c5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
b22f93bd-b5e6-41f8-91d1-d0f974aed8dd | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
b97a270e-f6cd-4842-8213-9cfac3080aba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
bb270697-4253-4626-92da-a3daf117455e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c00bbb7b-7e1e-4b98-9f01-f0c187deb66e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c0bd06ff-25d5-4232-ac6c-646d5c7a30f6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c2d5ac84-42e3-44ff-831a-07e366207228 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c4928fa6-2792-4b9b-a09a-517dcd2d6ec4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
cd197258-db6c-4f2a-a989-758162450ca9 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
cf89e813-f253-4bab-8379-7659167d2626 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d1af7df4-4c9c-4288-a5ad-7bd9e91bad88 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d2c000c7-e232-490a-bf7d-939c6e93f729 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d480a95b-8835-4a16-8963-49cb101fb3a1 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d5dc456b-2d99-46ed-82bc-fd0788a1edff | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d7d0c8bc-56a1-4ced-90a6-cfa8b42e83bc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d849511a-d182-4d41-b0e4-3dcf052a76bc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
dcc78147-14d8-4b7a-a995-456814b60d95 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2 |  | 2022-08-01 | 2023-08-01
e1eb8ed2-847e-4b3e-8bae-a61b99063acf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e5d333d2-d180-4deb-9e61-69d19076863f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e6503596-9981-41ce-9bd2-2b398f47161a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e769cda8-1713-42cb-8820-35f39edf7782 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e7ffc440-e131-4120-a669-f5981d147d4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e84ff4e1-767a-48c3-bce3-e7ae339c907a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ea35d793-e5cd-4dc2-a152-599e7c234d9b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ed826ba9-0ab5-49e7-8845-63cc5f73c967 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ef024a55-ce9d-4dd0-bb79-3fa86937f5a4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f02875d6-5cad-4e73-b6ae-5148e25ee977 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f045205c-8ebb-4859-baee-63ab05173ec9 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f2a0a66a-d58a-42dc-b1c4-a0981c57e4a1 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f3ccbce3-9af8-43f2-b636-c929063fb658 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f58c4eee-d8ec-4250-96e3-17cc55ae72f5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f99159a9-291e-4c1a-9c09-802b0256a515 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
fb572cbf-9238-4c0f-9848-3b85914bc353 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2 |  | 2022-08-01 | 2023-08-01
fbd31e49-2636-4be7-a69f-cb34531cf26d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
fe2a45e3-0af5-4a9a-b946-826f08320464 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ffe3cc2a-5f07-4aa9-a1be-7a193e39762c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0098089f-a7ec-4fd4-83f6-bb88a9802a76 | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2 |  | 2022-08-01 | 2023-08-01
00d60a2f-06a0-42cc-b9a1-1f60d02c75ce | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
01cb9da3-0b8f-432c-9307-4a7db2c733fe | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
071c7c18-3be8-44d7-a6b2-964c51c68a3e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
0f297c49-8f54-42c2-92c7-47c82d023893 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
0feedbca-ee5a-4e27-a3aa-faf791e52295 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
1d14d146-58de-4807-b155-55bf84040336 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
1d7c21e1-e5c1-4a80-a34c-e2da39a18e4f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
1dd0bae7-34c0-40d7-a0b3-535102a03610 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
22e4f44b-a759-490c-b839-445240cebcc1 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
26c1af08-e315-465c-ac33-01d1d34b3e5f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
27a13a0c-95ee-4d45-85af-f2a41fead3b4 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
29c2b704-f16f-4878-9132-7232a1bf211b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3225f821-7503-4c43-a498-7a49db9521ca | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3397b717-6a1d-468f-a1f7-92d0ce515f6b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
33b0fef5-ade0-4330-a97a-740ba45b9e72 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
347f310b-54b5-4f72-bb95-e9a5c1d71b62 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3a2d51a7-dfde-4c6f-bf0d-3fa928e81646 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3f0ee385-257a-47cc-b2e0-195ed1ec7db0 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3f8dc028-e635-48af-85cd-f543515bf917 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
446d81be-8cbb-404e-bc7f-b56e9aed4f2b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
45bfebba-bb22-422f-bea3-3ad3a143a596 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
4f3a3287-3c04-4963-b179-080fd499da54 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
52c02616-77d7-4ad9-9bc4-b384471c32e9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
52fbbcf5-e938-464e-8da5-69fa5c9914bc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5380d8b2-64cb-4e84-a136-2220df73533b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5bc13482-3f2b-477d-983d-3dab41bc0945 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5ca9f5f0-d72d-473e-ac11-a09b29592f8b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5ff4555d-16d5-442b-b2cf-2e107f2a3d0a | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
60159ab7-113c-4f91-aa29-a932814e27cc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
6a72f514-d73d-4f44-ad7d-4cc89870b633 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
6bd4377d-42dc-458e-8566-837751f2e86c | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
71584111-5bb8-41ec-907a-0adf51d3a01a | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2
77770603-c699-451e-9cd2-c89bee6fe724 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
7f6da5e2-be12-42fd-a778-f115bd52f6f3 | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2
8022089c-b52b-4bca-a77a-ac035e042199 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
82ebaf66-a15e-427e-bc90-709990efd9ff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
86707e61-9fb6-4489-8c3f-5b1ace96c221 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
8974f9cb-96a8-4a6b-b9d4-44b1b9b10de8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
8f2d893a-bc21-4301-9eb7-d6c9fe2c0f18 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
91886048-4ca0-4d03-a1e9-2dc2a82e1b66 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
93401b71-f7c5-4f02-9b22-8cbc2ce288ab | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
973b227a-22f7-471c-b5e4-7b3ba06c0238 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
9a88eaf9-1343-4e00-bdad-d69bb6dff177 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
9f35a2cf-b449-4feb-9d2e-9295a1ae24cd | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2
a4f7f48f-db2c-42c9-9cdf-d1df945e981b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
a6794192-54d4-42fd-823c-b47efdb794bd | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
a99ec8cb-7f02-4209-bc41-4ce76aef82ca | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
aa6d6ad3-b879-4e51-87c8-9aa7134b5902 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
ad0d7e84-3be9-4f6c-8889-d44cbd05f9dc | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2
ae9fbdc6-7ac2-4ca2-afe6-da00053e77bc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
b637846d-8322-420a-8540-53ee8aa180cf | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
baa7346d-0ea7-48a0-aba1-dfe196417946 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
bf2218e3-0c44-4382-9254-b0622e8b71ff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c3d61466-d21f-4e92-9d0d-26b77aba4abe | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c573c9ae-8745-4fc8-ac84-5c3f9aa7abff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c60d00a5-e438-45e0-b550-aaad016bcaeb | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c72fb72e-9b56-4a1c-b1d1-ca179a14dc4a | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
cac7c7cd-34d8-424b-b54f-eb4a431fe292 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
cdd97878-adf4-4e4a-93ac-1d0f5b37dc0c | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2
cf7c8f33-bdf1-4785-b5ef-eaa8042e9a1e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
cfed5938-97e1-446d-84f4-b9a5f27ba7ce | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d02aa2b8-aaef-45b2-9443-64365ae13e13 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d10d1ae8-fed7-4b57-95ad-26e705e8bd9d | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d18053e7-499f-4a62-ace9-81888de0cdc6 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d2a1168d-3186-4da5-92d9-d7938ed6ed71 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d355a7f6-c74d-457f-92ef-524cf8b9f733 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d8deaadd-34d8-4a0b-9a29-d18a32500fdb | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
de085876-38a6-4ead-9c01-6002befaa8e9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
e6826095-e636-45b1-b778-9b4bb7f769a8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
e72751a5-9167-47aa-ba5a-edc24c3df84f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
e939a423-0475-4cbe-8888-8c9647736f19 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
ec6c28d2-8fa2-40ef-aaee-fef93f43df06 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | 2021-06-05 | 2026-06-04 |  | Required to Re-inspect a subset of assets
ef411a7f-9675-4d79-99ba-fc84c5628345 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
efa13b06-e773-4d0e-a26e-3891dac2cbf8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f481de80-e9f0-4f28-9963-f82822e1d28e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f543e580-9cd5-4e30-b2ea-2181ce187df9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f5b1afa2-64a6-4e5b-a9af-358a8543650c | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f9f29c55-d913-48c6-8637-d5c1f49368e6 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
fd1904d9-72be-4cfb-8870-5c97cc031ef5 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
007413c7-508c-4a71-ba33-6b12a56b51c3 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
032ad3ab-2b61-4217-a907-57e46d336d85 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
091bb153-f365-4d07-8c27-ae892724630c | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
09f2f087-cf5b-4d0c-8bc1-97e6d8fb4080 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
0e35b734-55aa-4a24-9a4e-5c948587a09b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
129abf4c-d429-4522-8b80-7014ad9394b2 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
13dbe904-9f5b-4758-b16d-5607247b3960 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1798505f-54cb-4398-86cb-08a8a90d930e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1a2246bc-10a1-4c41-bb6d-38332502daa6 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1bb41ec6-65f0-458c-aa6c-7f2aa4551f7f | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1cc492b6-ff0d-4d5f-aade-e5e6759b404c | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2
1defc274-243b-4a96-978f-78ceade39019 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
226fe9dd-8318-4d44-9bed-6367747b2001 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
2a267537-d43e-4cdd-b40f-c701b15aa9a7 | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2
301f12b0-12e2-45e3-b254-9346adb5bc2d | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
3fffadb8-90e3-4632-9c56-2b2cac05442a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
41eb12d9-ef04-427a-a0d2-026e70b1d76b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
45946db1-b2e0-4a65-a817-35d3f6213f5a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
45a927ba-06e5-48c3-bfe5-e5d8cee38537 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
4b7f6609-6852-4b9f-8105-eb749f349cca | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2
50756823-7823-4f55-b0b8-5a8033ab8e38 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
569fe4fc-9978-4184-94f2-1933ca6e4da3 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
5f51c0e1-2ca6-4cc5-aa74-65e76ad5affd | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
60747b85-18e5-4fcd-b6d1-a79930b5345e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
6ec94a68-fbd2-4c0c-99e6-7ccce0c7e657 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
732e56f6-c64f-4310-8ff0-24b8e597fe0b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
75f3c549-2d91-415f-89c3-174b73b49232 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
772df434-5a0d-4af2-8d5d-431014c2377a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
77707561-199f-4093-83f8-2f3292e6f2b7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
7a5bdbfc-3f90-40a5-a7d0-611c441cb00f | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
848106d3-1601-4cfe-8e4c-8abdd31b94a5 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
856ec955-a16c-48a4-a9a2-aacd3beb4c2a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
86e58aad-fe5d-4ca7-bd54-285b3d2d8f42 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
87d519ef-56fe-4c58-880a-a699047ad4a7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
8d38071c-b43f-43af-87f4-67878ec71e22 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
9a1b273e-9121-4994-a3dd-1eb8e9b6701e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
9ab77f4d-12b0-45f3-9c01-b927f0ed0d58 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
a3ba4301-dbea-4151-9156-eb730cd0dff1 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
a3e1f557-fefa-4874-979f-a2a78f9ff93a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
a3e8ba56-eb8a-4d93-80be-b63100922844 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
ac7056c7-ca49-4e12-b6f7-d417889a9fb6 | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2
ad73227a-33c3-4196-8bfb-bf5d41f3468f | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2 |  | 2022-09-01 | 2023-09-01 |  | Required to Re-inspect a subset of assets
b4544187-8b3f-46aa-bd11-bab0baceabe4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
bc67f35e-201a-4351-8a95-e26e4f36b615 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c4c48f43-911d-4df8-a64c-9892edfffc89 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c72c9726-c8c3-45ca-87ec-e9a5835b60c9 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c82b07d3-b13e-4d04-8214-b56b9979f87e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c84207f2-f38f-455c-8c9a-8eff55723067 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
cd2d3d8e-f489-4a64-8cda-22b1590e7e68 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
cd81b8ae-90d2-4718-b515-09ab018943d3 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
cf127098-b692-4a8c-9e41-e97bc9e78c0a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
d2e236e2-77f9-4e2d-9a21-0cfd1c4340c7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
d3ba9d5f-cfce-406b-ac3d-3bb283103ce4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
dacb6a61-3405-44e1-a29b-9305bcdc953c | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
db55c75d-cac3-40c6-bb17-bcd6cb16d793 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
dc22ddff-c170-46e0-a217-a0569d0bd5b8 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
e70ebbfa-2d54-4f6a-badb-f50ccfcb108a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
e91d29bd-402e-423a-a3d8-17040d9353ad | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
ea95dd19-80aa-4041-8326-1a683225d1fc | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
f2e81ad8-0d9e-4049-b150-976ad17adbc4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
f34a9b28-5cd7-4a7d-88a2-d13c138c5076 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
0053d106-4cf9-473e-8490-f2e8bb45556f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
018c1ed2-a704-4cac-975c-6c447cde1844 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
098295a0-3194-4d6e-b0f0-00f6d410de41 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
0ae6c236-98da-4c1f-ad53-e30ae104f337 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
0cdfff1f-d7b9-4da5-bf24-eb3fa7e9d5be | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
19650172-b43b-4681-9819-4b227a0fe108 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
1bbc9d4e-5f98-4d3c-a8d5-ae1b6736e67f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
1ecf6d8f-35cd-44ba-bfad-8f8bc8a2908c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
22aaad18-0f1d-4be8-9fd3-43ccae48d198 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
22d21458-98a9-46fc-885b-bfc1aadfcbee | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
22f3cd7b-18f9-4273-bc58-592d3a172d7c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2c0d3320-e06e-415f-82bf-950b82787cb3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2c43fd7f-0a5d-47f9-84f0-42f5cee1653c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2cd4964f-54f9-4a2f-9030-a92d08681453 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
2d39bc14-75dc-4ac0-b4a1-31d46948b1e7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2e00d42c-a0ee-4987-968f-6eee4215b4b9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2f83882d-da96-4a9e-b5c6-a1306ac8134c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2faabb7c-eebb-4d7a-984f-167b91a13785 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
36be8bf8-b35e-4b96-9bbe-47086a979a54 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
383b00ed-fd9c-431a-9a50-7fd5a9e59e09 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
3857a653-55e7-46c1-b39c-29a8c9df7b72 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
38e60757-40cc-4b7b-8ffe-b3134ca026e9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
39264b2d-b9a4-4659-8d76-7cf8b26b0946 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
3b77507c-1f0b-43b5-8020-024453af8ba2 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
3c1fe5cb-0cf2-4624-8b3f-c3d20a5bceea | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
3efbc659-b90f-4e1f-a4e8-354c5950515e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
403b9f9d-e67e-4e25-85bb-da558b04b438 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
45ad98a6-b982-40ce-91ee-b5baef752587 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
465bd75e-3014-42e6-958b-b3b2565bd2c4 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
47676695-7d3f-428b-a6ca-23950b1f09b4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
4b2fa13c-8a1e-4435-a751-6eed12f6ee4b | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | 2022-08-12 | 2023-08-12
4c000ed9-825b-4e61-a788-a78f17f43b8d | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
54ca7898-fb64-4326-a881-659240d53e8f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
57b80639-bada-4ac9-9f99-646a5209da48 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
58ee8569-2d99-4124-9bd4-32301f5e328f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
5b0306e9-c656-4f5a-b553-5add00bc9e9b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
62220ddc-6c49-46b0-90ed-8fa4db530f5a | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
649596bb-7442-4225-baad-cdeee3342fac | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
65119417-d2bb-4d72-8255-643fed97dfd8 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
656a3474-e118-402c-b4b4-a1b934d97c14 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
658d77a9-52c3-49d5-8fd1-cd4cd55db7a9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
6792ca8b-be41-45e6-baeb-d8e89f109549 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
6858d1a4-def4-43ca-a253-16cdf1fc5cd8 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | 2022-09-01 | 2023-09-01 |  | Required to Re-inspect a subset of assets
70792428-2eeb-4adc-a55f-598bd4bd23cd | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
717b07e8-4e05-43d4-9ac9-9f2d47ce7ad5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
7462d635-af71-40fe-aafb-2428c71b078c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
785a118b-7a35-42f6-bd25-95a44ca649c1 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
7b8df639-6602-432c-8f3c-6ad8449e5a7e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
7e69918a-900c-4839-badc-f389b42b74b3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
80f1c292-d8ad-44ab-b8aa-3e5c19bb6bf5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
8629dd4f-bb13-4e13-aa38-72edc96ee2d4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
86abc42d-2766-419c-bdcd-c171faad51ae | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
8828ad41-f56d-4175-967d-c391f39a0996 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
89e8ed6a-1056-43c4-8822-efc4a2923a3b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
8a8effeb-a935-4f39-bb84-c64c27d63c32 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
91489629-77af-472b-a704-e811758dfeaa | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
9210f170-5482-459a-b767-1ed0f6447dc8 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
9514ed02-f5f8-4ab3-a42b-792a3664635b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
97478a66-a5e0-4e67-9956-d0a2c9cb25d7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
989a3ae9-4376-4bed-ad43-7e95ed17d559 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
9f492354-d461-4fab-8ce3-2d27b07c4077 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
a512b0a5-726e-4e41-9291-da8874724915 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
a55a437f-4d29-4531-b24b-bd172c4305b0 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
a889cad6-3f97-4eda-bf6d-489040f1c037 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ac39aed1-7f6c-4a55-ba5c-84a88ac1e179 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ae10270c-8ca5-47a7-8518-7eabdb0b5910 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
aed0bfb8-4a5b-4b4b-9365-cd52214b81f3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b0add2fe-8626-4508-9f61-558fc344dff0 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b33ac467-9a25-4186-95fb-718498acf0ba | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b868d7b2-751f-4da4-8bb6-66dd65202301 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b8e566e1-4e8e-46ae-ae92-94221113717f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ba683b89-189c-42bd-bd55-a771492b0d0f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
bc0ad7e6-6117-4558-9eab-bf631a6b7ac7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
bc4bb32c-1e90-43b8-aadc-fe71bdd162a4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c1a1f810-a23e-4212-ba94-9a7e1ae2f4ce | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c74f1c9e-e8c1-48de-a8db-a70736d33a9e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c849c4d0-58e2-4291-a6a0-05e92d59f9b4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c8760a75-1537-4b14-8d24-784498b6d1b5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
cbdcb2d0-cf1b-433f-8fad-f2f8a3d4f2df | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
cccd913c-1083-4f12-9e76-7a9b1b3e17a7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ce00173d-bbda-467f-ac37-eb917d38e7c2 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d0198959-7a5a-4d2d-b716-47f229529bc9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d252b023-84a9-475e-9b35-54887aa00539 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d2b6c5f2-2e68-4538-8baf-8fb8a6507517 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d2dbf5ad-abbe-47ab-8703-243a822bd2dc | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d330751e-8cdf-4091-aeea-e690002ea98b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d3bfec49-5350-4530-a016-216aa13e0c1c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d4479c95-ddd1-435a-af96-aa47f6900c49 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d594fa99-79a9-4cfe-9b6f-ddaa584f2fac | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
dc82649a-5909-4957-b11f-b73a0743a2b8 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | 2022-09-01 | 2023-09-01 |  | Required to Re-inspect a subset of assets
dd1c355e-7928-45bf-8379-044e6fff89fb | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
dfbe3a8b-e685-400f-bac7-73f361466900 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e0bfa77e-b701-4216-b869-46b70a824265 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e18ae2aa-2441-4dc4-a3ee-a42230fb04cd | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e7e1fc8d-b959-406b-a0f0-8bf09bc89ca6 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e7e9076b-b97a-453a-a794-298d157389f7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ed867287-bddd-4287-9512-5ab9a3aa4ccd | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
efbb6374-935e-406f-93b4-f98e80901107 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
efecc28c-697a-4edc-be1a-fabf946f9b55 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
f04a10be-6ca2-4c17-97e0-23be546faade | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
f36fb126-0344-4d6a-b8d5-a972a9b898df | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fa290195-eb15-409d-86f3-43149eafba13 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fa549dd8-c467-4879-8f5c-6745fc543021 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fadeeb00-f555-4535-ac21-5644dcfd06ec | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fe027072-d689-4cfd-925f-0d0b57ea48ad | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
02154b5c-5733-475e-875d-70f6576fcc8a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1370bfcb-0f40-4109-8523-e6b71d9eaf99 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1ba90aeb-83d7-4dcc-9ae2-e54b5da8e025 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1e1a7f7e-aa1e-4263-8194-6dc8993e25ea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1f8a62ae-5655-4024-a415-325d13602523 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
20725891-8460-4ad7-a407-514b072b7795 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
24af0108-e145-4fb7-ae99-f5a40dc152bc | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
252e052c-f447-4585-9f27-ff6d6e2339a9 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
27bb5e92-20b5-4e52-a586-94f1912beaf9 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
285a40f3-9da7-469e-96f2-f1a8c89f426f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
2c439689-77aa-4f6f-814c-fb349df3b6ea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
2ea31130-dd9f-4633-9ff7-7d21c0b76b64 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
32802c40-6d99-4836-97d3-4270f76e3dcd | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
37dfb10c-98b5-41cb-a7ea-6080dbad0b7a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
40f21d64-0531-48ab-bd98-6879d65034bf | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
419d5566-43b2-4339-89d4-abf786f432ec | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4bae78ef-a3d8-46db-bb32-f8f1961b1542 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4c8d0cc6-f680-4d10-8de1-135fa285b48c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4cf237a1-02f1-4fd6-b6a8-39eae00c7771 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4e07c79a-398e-4ad5-8164-9cb68a487c5a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4fc7c861-6692-452b-bdac-1640d3f59d94 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
575de996-da99-412d-a558-2cf7110578fd | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
5842ce0d-a641-48c7-a73a-11fece367d83 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
58a291b9-e925-40e9-aaa0-43ff0d862112 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
59e77797-a3ac-4efb-96dc-4a1615400290 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
623b0174-3328-49c8-a68a-0209f35258b7 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
634aed90-05e6-4991-bed5-f16ed193d804 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
649360f8-d65b-41a9-8b14-0a26a83052ce | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
65f7eeb1-f45b-4f7a-96f6-52e85a2e38bd | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
67f7b467-dfff-4428-8f4c-12d22df72a95 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
6db70c71-2f1c-42df-9183-6f6b6a7b5ad4 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
6eee28bd-69ce-4015-987b-f5af6f8608f3 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
77106a3a-903b-46e9-8791-ba85e33dd47c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
78a8d2c6-8337-4397-a4d7-27042f54ba92 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
78b1e580-37f0-45c5-8508-2ad06b9476e0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
79acb193-3355-46bb-a41a-75f656adf4be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
7c5cd56b-b536-4a10-8795-cec4fd40226f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
849dad03-256e-433d-ab1f-793ad7b63aea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
8541b4bb-f24d-466b-b02b-44873d091669 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
87dc14f8-f0dc-4deb-8f7c-7a1ed269e219 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
8a94738b-4706-4581-805a-d7508ddaa86f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
8a99b69e-6246-427e-a390-c9e44aa20e85 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
9101ec35-8ae9-49e9-a4c8-d57fe2f99a7d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
910b841d-ca3d-4e94-954a-7e3f4f32f836 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
9116c256-c4dc-4cf8-ba9b-d39dc25ff7af | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
91763030-325d-489f-9d19-412d9ea90357 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
93cbebe4-2038-4374-85d8-a9f38f38e7d1 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
958d6208-957b-4c19-b64f-1366d39e83be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
96ad6dd8-e019-43a9-bdd9-349c15e2dd6a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
9d1ac5b8-87b4-406f-a331-4cd47be1fc6d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a1646d65-ab36-4087-96cd-b05087cc6f8d | Pole | 2 | Distribution | 2020-08-29 | 2021-08-29 | Level 2
a2b9158a-980c-4bb0-bed4-691466c63a15 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a5ba7098-af8f-446f-b6f0-0db9c2190e0d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a67244a2-99dc-4ed5-bfd8-c1bd2ef2f6be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
aac16faa-286d-4438-8e85-59a574f86a0a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
afc49c8d-c96e-4371-8b01-2c61cdcb337a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b2473eb6-80f6-4e44-b4a7-664a0a0ab89e | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b3dda626-3f26-46bf-8441-4e20fab6bd0c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b91daa42-5b8a-4937-96cc-214d1d91d12d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b92c4ebf-d938-4441-bd02-d24cee72bf1b | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b95794e2-4d0a-4b81-87f2-13831c057df5 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
be6d0c99-898b-4327-bea2-ee9854cd983f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
c0549cc1-32df-4aef-a0bb-82dfbb4f44f0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
c7426c0c-2f36-4540-a879-9365a174d7af | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
cf15e6fe-975f-49d7-a55b-8f729d5208f3 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
cfd2919a-372d-45b0-b103-c425fc173eb0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d0656d07-e935-452a-8214-2fc076b0b432 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d1b7adea-2503-4dfb-948b-d562f3d4aa82 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d2122a85-6c29-4e2b-93c5-142f68cb2fcb | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d6e9f31f-803d-43cb-aebb-0d017b5f3b59 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e233563f-1b50-420b-aefc-810d6cf91930 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e4869d67-af42-40af-ad79-30f3e004cc56 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e5d3feb1-5ca9-45ee-a949-cfbdea0358ab | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e8d4726b-6658-4616-a51d-631eb3ac122d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
eaf2b7bf-d29b-4912-8ea4-494fe2d13d3f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
f4af0ee8-60cb-4f1c-972e-f51c4ea9db87 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
f9ba4a13-894c-46ec-adf1-ec131be8da44 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
fe7277c5-c631-4eb9-9e36-a71d6000790b | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
020fd888-a02e-4dff-ac8f-888762d08506 | Pole | 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2
02c0e15c-b416-4dbe-ada3-1e7c60fea209 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
046dd7f6-f250-44ae-a93a-c471a0003ae3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0488d860-8e13-4301-b664-3755ac68f5e0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
062c2f04-7f46-48d0-99f1-44d9c6fb5188 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0747833b-7cc6-463a-b1b4-55d34f7f5e6a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0b1116ba-d827-4249-94ac-d4119160e231 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0d31ab71-ff97-4a68-a3e6-8278fe133e62 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
15eae9f4-1d60-4e82-a6c4-1e4f64ac0b42 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
160d63fe-1595-4fe3-8ea4-be158c40c27c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
17b46e6f-b804-46e7-aef0-5c7533f8824b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
1d16959b-37ce-405f-b3f9-32c129e77915 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
239ef321-6ebd-424e-b8bd-2461094f5392 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
23c853f9-00c4-4b86-88e6-55f55127cdf7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
240db039-f27b-4a44-a5ca-8968d2e4e581 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
25a748a8-a1d0-41c1-9722-b3f50ac2e647 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
27c24d24-0b53-4fe0-a923-e7df32ce2b7f | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2a3f068c-197a-411b-9db5-a959dcb804e2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2afb1480-243c-4bba-8e57-61d0019984e2 | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2d44d5c1-c15e-4408-8ab3-7dff52602d7c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2eb3f226-ddf8-4ab8-b5a3-b1349b5126fe | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3404e748-dec9-457d-895c-d21ecdd77e54 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3576262b-4b01-4543-93a0-522ea5aba78e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
357c69d8-cdc5-4058-8a23-d3e5e5cb98dc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
35c243a7-6cba-424c-bea9-943d130d74e2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3c500bac-f68e-4ec3-9062-5161bca625fd | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3fa3b635-1bb3-4829-9667-3cc4b4066e8e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
40df8c8d-034a-4fec-98bb-ef97da437b93 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
419ce2ba-d75e-405e-a61c-6cf2334f18ba | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
43db67da-deff-41c6-aa3c-b1bbeb12a316 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
45755dcc-9c43-4a30-bbcf-f598fa1c5c22 | Pole | 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2
4b3fd7a3-f5f3-4c8a-a75d-02718e0a3ab4 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
4ba08f66-d3d8-4bf1-8e88-cbd1e72f389f | Pole | 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2
51f67e93-04e1-4a0d-a2c7-8d664519d290 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
52c93669-db64-4b56-9272-c6159f297f96 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
5419ed02-11a9-4ccc-88ca-ce8eb98e509f | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
59988cdd-c539-4a9e-a9ef-4c5d7aa4cd7e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
5d09086a-2e2f-4ebd-9091-de50065ea0f7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6118cef0-2623-4972-b1f9-434eec962a7d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6161ae5c-41af-4746-8240-7011b4c37fa3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6c336089-7169-456e-80f1-c7736ca75aaf | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6c63fcfd-6d66-4f0f-8097-da502f1d6929 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
71a2b5e6-6936-4a9f-b326-994511fafe69 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
741d6642-5be6-4219-9783-4948204d0833 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
74f0ad61-dd7d-4a59-a5ed-51eaa371fefc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
77897dde-06a4-466f-b792-15fd3254a2ce | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
79bfb517-adda-4dd6-a8ea-a2dc07e85f55 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
7c479afd-a0a4-48fe-aa0b-a59f482471c2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
7e116651-da1b-4b64-ada3-06458605b742 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
800ada78-e40b-4af1-aedc-505aa75a5968 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
80f63447-0533-4ada-b654-b9631e0347a3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
810e4b85-bdee-42ac-bf15-fb6c1844c687 | Pole | 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2 |  | 2022-09-01 | 2023-09-01 |  | Required to Re-inspect a subset of assets
83325ef1-434c-4d60-909f-267d766f7403 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
84755190-9622-402c-9776-541b9d281016 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
84e1196b-0153-4b13-ad7f-e99e0b0852ef | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
875d130f-b150-4cf3-88bd-41320835ac86 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
87dac9fe-851d-4e22-b737-28b58fc487d1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
886b88ee-a8e3-47fa-bd29-d00df34e9069 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
89147cdd-15cc-41fe-abb1-3bb43f3ef51c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
8a669dc2-aa45-4129-b35f-92d3a2dca667 | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
8b8ab350-37c2-49ea-9121-51d78a21db27 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
8d1225ab-0eab-4a8c-8e27-db536b3a1003 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
8f57a2c9-31bd-4179-8ec0-b93ed8b1642e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
929bed08-2f14-4b60-be02-700ab3355c60 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
92c114b3-fdae-4eaf-8f3f-3c6afdf1ddbe | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
940b0d13-1312-4f18-8427-e8fc56481ec4 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
954a49cd-fe81-4ae5-aefe-a238b4f12814 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
95e3c09a-7baa-4037-a878-f9fd4f94af2a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
97307ef0-0ad2-42b2-bf8c-6571261d36ba | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
9d5b6d10-6ac0-452c-956b-dcb6b88867c3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
9d63f519-46a4-441b-8a78-eefc34590d2a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
9e05c523-b7f4-46cd-a687-d0d682684298 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
a53ad0a7-b18d-487b-aa0a-70a5023394d0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
a7a377b5-f6ce-4f4f-ace4-b8cee00359b3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
a7bda126-e3f2-43f5-a0cd-8d540dd75049 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b1c745f4-5083-4796-a1c4-c7b641705168 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b4617974-1982-47cb-8672-13a5f005fece | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b5cd0e67-c0bf-4698-b3e2-625165f658d1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b86717c7-beb6-495e-92aa-2cb90869310c | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b86fa922-6699-4783-8d9f-4e50e54009c1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b944276b-e247-456a-a95e-32db3f079b08 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
bc12987d-59d7-49b1-b536-b51bc23cd288 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
bd47fbd7-abee-459c-a648-481f979d985a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
bf438a78-0353-4109-a0a6-8f4a49f4ace2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
c4f224b7-c0a6-41d3-b214-37ad5049330c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
c6c67015-c860-4b6b-8bb9-91902f2bce86 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
c80d6530-165e-43df-a89e-0a8b2a734fc6 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
cef986ba-2381-45dd-887c-dc7ba4435a13 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d137aa0a-c075-4b91-842e-14ebb0dfe363 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d2c99502-e285-4806-8cbe-815a720a4a89 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d539be7b-0e66-4011-9555-2d4dd5573359 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d64855d8-8843-4cfd-b0a1-cc0e45b9d810 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
dbeea258-a912-4ec6-aca1-384355ded232 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
dc4738c1-e6b0-423a-a362-8ba85b6f88da | Pole | 0 | Distribution | 2020-08-31 | 2021-08-31 | Level 2
dc7688e3-764c-4518-97e3-803a2ff79980 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e11f3af3-6270-40e1-bfc4-d178f510132b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e199d637-2e3f-41c4-abb3-3b385ba62c47 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e4e3e716-8050-4205-a8ac-fae2c4107156 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e684fce7-e87f-4a47-9a9a-f646ae16aff9 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e6d16844-8407-41a3-ae63-b152792f9f8c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e90d2002-95ce-4f5d-aadf-70b08778a2f3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
eae5ecf3-20c4-4bce-a8a2-fda3576491e0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
ecb2de1f-4edb-4d7a-9801-0deab7f37c3a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
ecee9244-d93f-497b-877a-e525f2ae0b8d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f1a4d153-fb12-40a2-bfea-e50f6abe6ebc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f35cedbd-3d77-4094-b5e2-80ea631e78c0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f60a4b47-fab6-46a0-afc9-178ac64f8a1b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f694ce95-f22d-4b53-958e-52cef46b9c83 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f7f405d4-8923-4c38-8bb9-1b6fbd95df48 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f9664bae-2d45-46dd-93da-eff1e1a80b84 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
fb20e2ac-0903-4be3-8f4c-6fa80ece123d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
fb61b037-8890-471e-acac-f042c5b9adb7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
fd57d334-e485-41e4-ace0-3a6e5709a24c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
00ea67b3-d014-4f72-8a56-1eec72dac360 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
01eeb00e-9c7b-49d2-838f-9582360f1c3a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
02cf0692-0c5c-404d-9e77-c8c59dcd1e26 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0452c33f-6125-4ed5-bec4-ed3b8a65b199 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
04b2b7c6-09cd-43bf-af84-e69f59035c1f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0542e537-4b5a-417d-86e0-3039c14a5dd4 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0748dd77-f736-4127-a1c7-4597a86d5c5e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
094e8042-ad7c-4b45-9ac0-92f60ebb085b | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
09d10548-d343-4feb-89b5-aeef8494d6dc | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
0b1a28ad-51a6-4e5c-8c05-7e1a04f884d9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0cd2f3fd-3c6c-4520-b5c6-70effe16c1bb | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0fd6c225-61a9-407e-bfc3-dafb7ba9ca3a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
108ac909-658d-45db-819e-1807f2aa0960 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
13cb38af-c27c-4246-9024-ed6375b925f5 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1745efce-9b32-4abc-9b17-855636a605c7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1d7ffae3-6ebf-4158-8c4f-b85f03cf581d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1f430726-98d0-43d5-9ba1-978a9a60c34c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1f9fdb01-6ff5-4190-aafa-f6015a30eeda | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
1febe576-cd49-4c54-b733-cb53e2826dcf | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
241fa420-b339-4a73-a778-7cecbd4cf154 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
246e7159-d1fd-4cb8-85cc-42a1a885e44d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
2540eb6a-ee4c-4927-8ce8-d8c47140014d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
28a1450d-3823-4925-b769-f2abc45ac855 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
296dbc28-e97b-4fc6-88de-0830c0c866e8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
29a1421b-d404-427e-b99b-61dfc91c3c56 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
2bf0adde-0e08-46de-92c7-a3163bfdf5c7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
2d4c6ff4-4348-4546-b247-18a591d570e4 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
300d4d28-de23-460e-ab98-c7a5345ee175 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
338c0afb-45ac-4e4c-9c9d-632970961463 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
3809c851-ae48-48fa-94b8-e63cac41abc3 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
38689df5-ed3a-4972-a768-a30870e2458c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
3cdebe1b-383c-4a18-a748-1482c78bd7a9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
3f02a38a-f265-4bd5-a1e9-7d3f31b1a410 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
40ca0c67-2eb0-4821-bdbb-9dad7fe6c6f9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
424b7ab3-beca-4966-9fdb-ccf133aa1279 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
42a4c11f-be39-4720-b107-e78c23c73ac5 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
42c4b99c-903b-4f0f-9189-d34173c9d46d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
45beb6d5-679a-44bc-855e-bfbc11896340 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
45c9ec24-b788-4594-9024-ee3ca5fa0444 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
48d37046-a22f-4285-85ba-ea171c29b02f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
4e54a16d-e9b3-4353-87fc-f120013a38e6 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
4f81ed6c-143f-43d5-a56e-cf9d22866d8f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
4ff2e1e9-3ff3-4dce-b435-7265a02b8a59 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
58f9fbe3-6e1a-493f-9c09-980197e63350 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
64ebcbf4-2e78-4dbe-ab72-a7fb5da8dc1d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
6598de81-29fb-444c-a292-7c462f6fa622 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
6675f7fe-66e1-42d8-802d-e07e9fc5c7c8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
67abe691-35fb-4d6c-8251-a4930192d069 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
69de7782-3e45-422b-aa80-0f036d3c6633 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
6af542a5-6a41-431a-b3e9-aa79140d3380 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
71425b1d-dc09-43c6-a239-b2fde62f8e57 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
729afbae-f6b3-4e3f-ac15-60baf56026ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7386fbb0-4cea-49e4-b493-95e94bd119ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
79c89fec-cf61-4fe4-a3fe-e23ccd0222df | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7b419c2d-34a4-4423-87c6-d6d937673b43 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7c1a5ce5-a610-49f6-afa4-05ca3188b95c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7e0a3f3e-3101-4967-9843-29656b0658d3 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7eb2c6b3-f8fd-4cef-b728-e04c7a10f61e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7fdaca81-d2c1-42b6-a2f8-1482fa2809ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
81148ac1-dd0f-4a8f-bae2-86d37b95eaa1 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
820202a5-1469-4bbd-a65d-4040b42e812b | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
87be9d3b-5bc6-458b-9500-006d9bfab959 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
8c39bf06-f0a8-416b-88d7-b06f29272800 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9021155c-d406-4db8-9a3e-68dc02c56483 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9593c5bb-8859-4d0a-b89d-579a93190b97 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
99e5ce0d-a2e3-4967-99cf-486898fd6ac9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9cb83f2e-272e-434d-a99a-c2725ef521df | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9f76e8b3-6fb6-4bfa-be87-b983fb0d6ea2 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
a2e6fce6-c524-49e7-8e77-99f166a04b38 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
af4d92ed-4707-4dcd-937d-718b006dbf78 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
b1021bc5-c137-4b76-885e-97d7eabe840a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
b144cc85-6181-43d6-a3ba-9b8935c5ded5 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
b30b1874-07d1-4920-a76c-ba623eb13794 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 |  | 2022-09-06 | 2023-09-06
bb64e499-75bd-4afb-9122-afbbc0e62239 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
be42a931-e725-48f5-870e-908d52782b4c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
c2c48094-8a2b-422f-abbb-fe19740ef911 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
c493cdc8-1f5b-4e88-b75e-42d613be479c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
cd1fb2f9-721f-4594-8fcb-c92d7cada6e7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ce06f667-11fc-4299-8e9a-46d1a986fb8c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ce36b1da-8f29-4946-8802-e0958bedf189 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ce4b319a-5f73-48bb-8291-6378792d4f2c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
cf0a15a1-73cc-4921-9e7e-bebccb0c4a6a | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d09b8b6f-2ab8-43da-a8a9-e91774f6655e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d55162ba-c472-433c-adf7-518ef7186212 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d7103d61-3aab-4e98-a1ee-68f52282bc2e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d95fe712-ff6a-4a25-98f9-d8a8ac6e40c8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dabdb48b-6ef7-4f76-b4d3-d417ea1282ab | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dac227bb-8a69-492f-9c47-70b24a146074 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dbf77031-3d77-41f6-a0ca-6594a216e747 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dc7568cd-6059-4b39-af9c-748517347e14 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dd154be7-6396-47d6-ad5c-5b17a52e2012 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dd3f4ef2-aba8-4c98-91dd-e82cd8521feb | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dd62f31f-5529-4d25-aaa0-fe3c17fdabd9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e0997e6c-cca2-497b-b835-90d92aed5f6b | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e2ceb37a-cef6-4cad-8c6b-1496e1b1215f | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e3df9bfb-393f-4551-88b5-f58d8f2317de | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
e617cb04-b05d-4fa8-9b41-296590d76e99 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e95b8b01-ee94-4af2-9ad6-d4b7d0178ddb | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e9753b4c-a67c-4829-8629-674a2fe942d9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
eb6920ce-79a4-466f-ae37-87fc5dbb44de | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ecb93fbf-51c2-4fb4-96f5-d630752a56b2 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
ed1ec319-8364-47e6-8a79-91132087eb31 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
efb84d4b-64f5-4ed6-b6c9-e8aec7df8cc1 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
f0bab855-33d6-4d15-8d7c-142df5e52731 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
f33666c9-d97d-45a1-b05f-29f40affb989 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
f8a9b4aa-8c29-4e54-a583-cb68d849f0b0 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
fbaea623-918b-491c-aa89-4f5454ee1360 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
fdcaeee7-fdfe-4fde-815e-8382fd31821d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
028bba8c-b1f4-4b64-8dd5-f2a76f3d706c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
02d04093-143b-4f68-a648-2ca57cd362d6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
0ceb36db-0fb4-40e5-899b-d8555958f19a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
15ac1b4b-aa67-43f5-8c09-912543d2ab64 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
19ce6161-2a94-41b7-bb83-fd8e507e286f | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1b2750ce-dd1d-4157-a1c1-82c9ce5902d2 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1bdcaf32-54cc-4b8e-8027-8c8f82afc9a0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1da421fc-c7c8-4de7-934e-869945778fd8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1f10ed99-3f21-4bec-a67b-d0361a453726 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
20d00224-fc97-456b-8e5e-3375e1bb6cb8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
22a72e49-514c-4e0f-9804-afc0fb684127 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
264f6777-292d-418d-8c2e-955f5f42d444 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
2aca75ac-e5b2-48cf-9918-ef81c8b6eff1 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
30c82d42-2490-493b-9298-38f340310fc0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
30f30b1e-da12-4b28-8673-597916f0fd55 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
3671a876-f064-4e36-b861-d75f1c2349f8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
40ec9a3f-0bfc-45a2-b076-f415683ba247 | Pole | 2 | Distribution | 2020-09-02 | 2021-09-02 | Level 2
4289eb5e-9202-465a-8a64-a5835eec2231 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
43accaba-0103-4976-b84f-ade8668a9958 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
441c0487-52f2-4b01-a27f-1087429efb6c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
450cf542-041d-4199-b502-74cf55cac66b | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4afbf1a3-7284-4b92-ba5e-a590ac715f10 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4bb75326-d7e4-4591-a838-240a5ebdf11b | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4bda4677-dcae-4dcd-9a3c-6266c738f2a5 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4ca9d859-fd9c-4ea1-b0d3-9bb871a98fa4 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
565ee028-49fd-4509-9874-9accc5122955 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
59c77c7f-d073-49a5-a5ef-b67f91b08aa0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
59e8d255-b4aa-4c17-bc15-739a56cc2794 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
5ecc8eaf-db7f-4dc3-9bd5-31dea1878395 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
60bb171b-0d91-49cc-91a5-41d3778a5441 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
63bd84d5-f025-4cee-84e9-6378fbbeee27 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
66c9877b-0b55-417d-b957-59ce26913e30 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6983ef13-e457-4102-a978-20114d4f1878 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6ad850d4-7b6a-42d4-be9b-d2f23f4be085 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6d0a4f46-f766-4226-9cc6-5065b4a1fed6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6dc4aec9-5e86-4bbd-b989-8098faae7389 | Pole | 2 | Distribution | 2020-09-02 | 2021-09-02 | Level 2
6f32cb28-8681-4ff8-bcfc-30e14ef7d7d2 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
719f7546-2ed1-4e9c-9093-d6b56abb4df0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
720ff74d-c782-4a18-a0f9-01e8cd87bf8a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
795baf10-946f-482d-882b-8d48c7250918 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
805c65f5-220d-4d96-a07f-0ed60f48e9db | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
81f66b9f-bf0d-4df8-bb58-58316f9aabbc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
84ad98db-b50f-45c8-93db-1d5014266fc6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
85b45d95-927e-42e9-96bc-32ab87026aaf | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
8673e38d-6d6e-4d40-ae6b-a1517c53f50d | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
8d2ed11a-e266-4d3a-b968-e4de2b10703c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
8ee5b509-ba9c-4fe8-a9d7-59d9ec9fe80a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9030198a-d4bb-47d9-b44f-05b835798f83 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9099b8aa-6e93-4498-855a-05d35d914d04 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
93a9fd03-49b9-45fb-bdd6-33a86d0cee24 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
943348fb-3449-45c9-8ee4-f0a88d9d7e66 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
94a56a3b-fec0-4a42-9056-10ed26262c8d | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
94e72f92-4961-4903-8097-99fda1b6b0c5 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
96f21226-74b2-49fb-a8e6-04ab98866d82 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9bb3c732-38c9-49c2-be62-6fd71f3fa4dc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9d70c4a2-7b2c-40db-a9ce-7d1e05b5629c | Pole | 2 | Distribution | 2020-09-02 | 2021-09-02 | Level 2
a3b368e6-6baf-4913-8684-ba72e72c0c53 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
a8d0f2a6-b09d-45b0-ab51-c2415c6b6e32 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ac2b75a3-7f9b-4b1b-a188-2420a6ef26bc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
b1d1e627-b7ed-4a8e-b93e-902ef5962987 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
b25c2317-b76c-4b2e-baf9-08196d89a979 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
b790f402-aafb-46a1-82d7-652046d26886 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
b7c0ceb6-811d-440e-a34f-7c8a0c8015fc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c25d9c3f-7191-425b-9ed9-a40a4fd5a201 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c28ed16a-ec4c-48ba-b13b-cf0520b4de16 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c31566fe-07e5-4295-a95f-065b8ef2b747 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c877b346-ab51-4811-b848-e518db1f365c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c9369554-feaa-46a5-abc9-82f66272762a | Pole | 2 | Distribution | 2020-09-02 | 2021-09-02 | Level 2
ca0f3982-9948-4978-9c5a-68da3c4388cb | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d09ba523-b3db-4310-8479-7eaeac594469 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d359d0dc-37a4-471b-90e1-86dee87e79b7 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d60536e3-4ae3-443f-b159-a8b533d22979 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d8b1a01b-6d84-4a14-8417-27129ac077d7 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e20a5379-e703-4e9b-abf8-6899487dc03c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e26e8bb6-3661-4c63-bbaa-6c3cc6984930 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e5cd6b9e-331f-4cca-bc9b-a937b82f7a76 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e75fb859-7317-4d86-a540-2c83e9fcc96f | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e89c3b20-4411-43fe-a6cd-b64e434c1ae6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
eaf3d09d-7d45-4808-b0f9-f7ea90ec5673 | Pole | 2 | Distribution | 2020-09-02 | 2021-09-02 | Level 2
ecf7f048-e36a-477d-9aac-f03e39882b50 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ef867c46-ca44-4738-8ff0-51be94d3b248 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
f49e9555-e823-457b-aadc-abbf1f234d02 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
f53bf024-7ef8-4afd-b1ea-ca5b6f2f625e | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fa77a539-6489-4abd-8d45-4ce110d069cd | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fe38089c-aa00-4512-9842-39a293bd7ed4 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fea02365-3dec-4a27-bd4b-c94340890528 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fed972e8-64f0-4526-9c95-5fb988785d82 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ffe156cc-8509-4114-854b-089bf03f9cb9 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
026eed93-a63f-487e-9762-9514fc61aa88 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
0e866a93-bfa2-4330-b155-ca7e6d295290 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
0e8a5916-9667-44f3-b805-289f3f7c5598 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
0f67fafc-bf6b-4578-9e13-e91edd72022e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1792740e-39a2-4aa3-9909-2bb24b95c328 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1821f34d-3e92-44ab-8a9f-fc76e4363942 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1876de59-37d2-4888-a040-c80203093175 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1abc30e8-fd13-4041-b0f5-89406ac22b0f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1d4d8048-9041-4d02-b767-246583ccdbf2 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
22192ba3-1c1f-46a5-a6df-d5f7e038f414 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
241a3ae9-d3a7-4a77-b10e-4c012f6b3bf1 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
25841d4e-d5a0-47ba-9d1e-1cb9133e32e7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
28dec882-be69-4b0d-898c-8226bb188e21 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
2bd4b273-a600-4a5e-a6c4-9b6135c11bf7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
2cff5f4a-2437-4440-9ade-5592907f087b | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
32917b75-fa84-46c6-936f-b257d8ae43c5 | Pole | 0 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
32c5e4a5-9ff1-4583-a848-61b592b3c704 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
362ccb32-91ee-4642-947f-d2a58a56d47e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
377d6ab5-d931-40c4-8a2b-b77469799d8e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
3e25d63d-4117-4aa8-b091-7970e8178931 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
40042331-70b4-47a7-ba96-d5ac8a91216e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
40457e96-3d71-43b6-9645-28c65b9a7d93 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
42af15cf-e466-4908-8db0-71e72dc1590c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
42de51ae-2f3c-481e-843b-6fe39b4edeb4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
45bc74f6-1240-4d96-ae1a-817faddc4129 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
47cd5c0a-9d2d-4e6c-b0ed-15931ffac538 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2
4b2730b9-1661-448f-b5ef-138721f0df29 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
4c61cb8b-fca6-41ea-8191-b67c7bbda8cd | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
4e2c152d-48f5-4274-8564-e2160cfdce48 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
50c2db88-5df4-472a-b1f1-5447b0163033 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
51213f38-9a94-4183-8c0e-ab1e8587dcd0 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
53d6e92f-b9b2-4d22-afa4-89d7fbc87490 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
5908cb06-5cae-47f4-9330-4d66a5cb09ca | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
59bcd9f1-8d47-432f-b030-1c50ccd6a341 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
5c004a10-967c-486b-93d3-3662bc6d0a18 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2
5c39527f-40d5-4b47-a41a-52aaed79e30d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
60a0e830-569b-4bc6-b760-272d102ac75d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
64bd2ecd-5c2e-4a77-bb4a-e308e3b590fa | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
6f696f76-7ff9-49a4-accc-9ad1bd8059cf | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
74752e6e-b206-42ea-ae09-3f41d38f0439 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
78e81f6d-1bd1-406b-8548-412d7e2c353a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
793ee3f0-4ba2-4fff-84ea-78591fdea2e9 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7bd75769-9809-4333-86df-7001cb7e8e54 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7c1c83b4-0e4c-4f4a-824e-428a7ceeca4a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7c827a66-cdd9-4045-baa7-0c07096e7aa4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7d3ed886-79d0-4e0e-94e1-92456a8147bd | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7dcd709c-7a36-4b59-b760-9554231998ad | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
859e89c7-bc68-41dd-8bdd-17ed9bb5e533 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
88952e0b-115c-4252-a2b8-1977d941ce9a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8c0d2acd-fd47-410f-985b-9fff62dee6c7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8dee2d31-6e16-439c-9afe-8fc9332d6d7f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8e9cb34d-8f3f-4f5e-b0e5-09ea686f46d5 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2
8ff1bc52-0726-4352-b0b3-d831262c3a6c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
9001bb70-723a-4903-8848-888a2fb5af4f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
91ac1360-78a2-4775-babc-ed1ea48cc12a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
93a67e1c-d8ba-4426-99b8-d3c37aa5dab6 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
a3997a6a-46ee-4788-8cfe-540f41f7fe94 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
a6ecf43c-7e1b-4d0a-875f-bc0a168ce775 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
a99bd2e8-35cb-42b5-8c3f-9ba750389135 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ab5a839b-d9d1-49bc-957b-1556dbecfd4d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
aba9bf91-affb-4196-b128-8faab3ce837b | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
b11e74be-b298-4cf1-9fff-8a32eabcf047 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
bee7f411-d34b-4f10-9e31-44f694ebd1f7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c331422e-23c9-4e96-a6db-d4b80e116488 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c4434b52-578d-4a41-a575-204a218abf0a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c779e182-c441-4de8-b6fd-b3b81fb0d70a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c937511b-a453-4fd9-a638-daa60d69aea4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c997713d-0e5f-405d-b451-ab03b96270ed | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ccdf8de7-fa66-4912-b143-98fa6b727181 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
cdf75ea9-fd3c-4178-a016-f0b75dfec632 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ce6c2722-65f2-46b1-9a96-fd416b16eb61 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
d0fc5976-1529-416e-84c7-0ea6f9ebec77 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e07f3cef-361e-4278-ba0f-5648cc6ddbf8 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e716486c-85a7-48b1-a136-0e43efa7958a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e7d139ee-40c5-4715-991f-976c48c684ae | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e8d5fc16-ccc6-46cf-aa4a-bfcbfc2ec23e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ee5fe661-3c6b-4707-8e5f-ff0886e60c5d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
eed2b923-49b4-4d34-b30c-8878b699ca62 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f0ae48de-a529-42c5-9da5-d03e3404fe2d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f0ca0045-f786-4618-8664-3cecb1df301c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f449fc2a-d4bf-44d0-b996-c5b4efa1801e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f599e0ca-c8e7-4ee0-99cd-6ff51b213105 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f699168e-68c2-4c6d-88b6-fe57f0e63629 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f870d706-5d5b-42cf-a78e-5df2c6358e5d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
fd115b23-38fe-43a7-9098-0892debe1571 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
fdac2927-5b74-42a7-9d46-3de1ff53c3c8 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
feb31db9-739c-4246-b217-67c4d3479010 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ff161ed3-af56-4e06-93be-d635fe5f7b0c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ffd402e8-8849-4e5f-ada2-4667ae6e3c07 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ffec84eb-881b-49d5-9eaa-a96e003a4509 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
0144a31f-f308-4520-82e2-885c76ec70ed | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
019f5c2a-ad86-42f7-b014-8bf30cace2df | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
04e3e2fe-194f-48af-8dc1-3622f6a40b74 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
0aebd7e9-f056-40be-816d-5961c129c4b2 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
111d99d2-0abf-436c-9c59-b28c6e0a8a34 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
17fc2f85-43fb-4c54-86ea-b8a2b3f2c788 | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2
188e4e64-b8d5-4ad4-94e8-efddc3801ea8 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1a4e3f50-670f-4944-8c8f-3126d3cf4108 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1b5e87cb-9e6b-4225-8725-582dcad776fd | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1bc6be04-5cd4-4a10-acc7-94b09b27699c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1da0c206-20ca-4b4d-a5c9-5bde1909b10a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1fc88df2-c68c-4200-9db2-f4a7e98e3de3 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
20f1b388-4757-4b77-b8c8-a89e117761af | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
23322787-dee5-4e83-bd8c-ba5a35a7ac0a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
29d29366-b49a-4217-b14a-58f8a04f7ffe | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2b100b8e-37cd-41bc-a6e7-cf7b2c630ca6 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2b3d117e-70cf-4eba-a855-96bb895608fd | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2c1d4635-8652-438d-8ee3-69b9d4796bb9 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2ed8418c-495c-425a-8157-267f7a16bc3c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2fe5873d-68a3-4a36-85bc-6166cd9f3480 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
326f9c67-dd0e-46fa-ba69-df3b0521600e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
3761f46a-35b8-49b6-946f-63528659eee5 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
3c73a0b7-ab99-4927-a417-92474c552f09 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
3ec8c3f4-9955-4c1a-a33f-5e730b7f9da1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
43d35486-ca0a-4731-8b39-0acfae6744fe | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
4da17a15-1c32-40b8-8b6b-34c8a83edf07 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
5333c5f7-dc2a-42c8-b0a1-7d51a85b4330 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
552a5ca1-8004-4832-bc93-a8dc4572480d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
58af91a2-9173-4891-bd46-f22d3af4f8d1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
599e071f-b927-4f9d-a839-7d6bb427e94c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
59d8f02f-daa6-4005-aa82-b5201b40101a | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
5e9d3dbe-83e3-4031-a451-f7607487bed4 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
6118d409-b573-4433-b074-ebcc40146fca | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
62a2a326-04f4-477f-a4b4-ffae717d4338 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
6625a1b7-4aa3-4839-9560-d1b4c2c798de | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
675beea7-8022-43c6-83d3-c552ef04193d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
70c4f184-c4f8-4fcc-a79c-6364867aa3c0 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7249ee2b-ae13-4167-90a9-113c0db50b72 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7379d2af-e4b6-40ef-afd2-556b87769b0d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7622ffd3-0e55-435f-ad87-4c5fa95f9905 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
78b1020d-9295-4c28-9563-687964cd6f24 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7b9dd334-23b4-4f0c-96ac-37f6f9effd9e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
824dedac-1926-4bf2-96db-ff7dc4422ff3 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
8846969b-ab27-4cd8-944c-a20f37ce3b6b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
94792054-16a1-4450-a03d-597b173e1fcf | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
98653a36-9249-4f40-9ecf-adb4654c618b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
986ce322-8b30-40f7-baf3-b98e99bef4e6 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
9dee83c4-429e-40f7-afee-7b5469bf8317 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
a38335c1-5bf0-47c0-a335-611b5acc4e48 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
a616811b-b3e8-4c0c-bbdf-e485917b6187 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
a64a72ae-3ed7-4f07-a01b-00eea1c36dbb | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b17dbbaf-b321-4a53-943b-d6cff3d0037b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b18575dc-378f-4777-9b13-5314624f0fed | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b8d9b0b0-c808-4ef5-a886-1a1e8c452c27 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b988b884-c0b8-488e-a11d-19bad8120d7f | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
bb2b8e75-a6ab-4739-b5d1-5dfe0038b779 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
bde5e2d0-5723-4d0e-a62a-a654bbc4d037 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c18b1e71-0bdd-4573-917c-1e6a1dbee7f2 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c37fe6bb-a873-401d-ad46-73900c514564 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c64e44f1-de3b-46ad-9e36-bbff6f68c36e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c78149bb-e550-4284-b0d1-b445fe292b27 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c9bd42c0-1988-446f-9dd8-dc4800b40448 | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2 |  | 2022-05-03 | 2023-05-03 |  | Required to Re-inspect a subset of assets
cc329c5b-0a01-46cf-9ed1-0aafa9d40597 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
ce733115-7d3e-4afa-955b-4bcd0e10fa76 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
d30ec098-6943-4e28-a1c7-ae2fd67c8381 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
d62827ec-7323-4015-b7f9-29a92c85428c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
d74ab664-8fba-4068-8250-1a339149868a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
de1aeec2-d397-469a-8539-f275bfebd894 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
de8f1549-549d-4ca4-9f93-b3e94ec87361 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
e3eeaac4-5add-475a-98a1-cc17c032dce4 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
e78aa2d6-ce03-4b5b-b20a-f8f7d4038f87 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
ea88181f-b8ad-4a90-bde5-69b975ab296b | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2
f01c0809-a76e-4e7b-b101-445d0b805549 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f0c4d872-f970-4941-9bde-bfaad45c7af0 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f0c532bd-1a74-4597-bbd4-60907b480179 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f136769b-cb1a-4cba-bfa3-e0d7d74cbf41 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f6d4d2e6-cebb-421d-ab71-3ce4021bb699 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
ffe83f37-d44b-4b5a-ba2c-6f193843c5d1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
00b12d0f-273b-46f5-af10-0d8c19cfa9c2 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
01e07b73-c11b-4788-8934-0a883d539e0a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
052f5e46-e610-4fe7-b9c4-29b9fbb0c033 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
0a1bbb28-fed4-4e68-bdd1-b7513814c362 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
0c44dffd-c944-409d-9bab-04bdfda5ff54 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
0ced76c3-4d7b-48ae-abfb-1ad255951dc9 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
10d96d76-610a-4198-bd15-e2982b8464ce | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
14667c72-39fa-4889-bb72-e5fafcc0c209 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
14ebf574-7f8e-41a2-b968-8e8da245e45b | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
1a8a7bfe-561b-4cf2-a0dc-99cf45d8d98f | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
1fbfdcd5-613e-4f50-93ff-9f88a90018a1 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
2718216a-c861-4388-99c0-8b523fe719d9 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
2747e8ad-0167-406d-92b3-b10059bfa622 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
30a71c3c-efbe-4569-b745-24354b8b0729 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
37c14969-153a-41f0-8be2-4137adf34384 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
37d49d91-f96b-4f10-acac-42a82cf76338 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
406a7372-3a54-4637-9f03-7a745b469b3c | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
41b49b5f-9621-4809-b095-7288ac22ff6b | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
498947c7-4d35-4419-a553-7c1c34293f97 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
4f86c94d-dae8-4a0e-99e6-081c8391feb0 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
5105c557-1c73-4f7c-8c66-56a22fc92eff | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
53863e53-64a0-4226-8642-34cb2169d364 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
609169e2-a165-4a27-a080-e51de78251fe | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
687591f2-36b9-44a0-b23a-77303cb79d5a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
6c663b78-1fb6-4eff-95e7-4a75d6cb8193 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
76df2894-b548-44f2-9b3d-1fbf65014e5a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
79a1e265-b6b5-4999-8b77-2616694d8e28 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
7d1ad1bc-454c-47bd-8999-752f376c7faa | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
7e6c4788-64a7-480e-b1aa-eb45fca11bd5 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
83d11714-ab4d-4cd7-9c7d-2366b418a7c1 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
85d298f7-98ca-4fe4-a82e-b09b78e42448 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
8ffd1c2e-9442-4098-83dd-25f3c734fb28 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
96a41b9c-09d4-4427-850d-d1f0d48f9c1e | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
9e72ff63-ec9f-4430-ac3a-16f5b9ec1b94 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
9e74ba59-50ee-427f-9aa5-1500b50d3f58 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
a24763e9-8525-411a-acf0-4a28c82220fe | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
afc68393-d89a-4a9a-8ea2-1c63fe8eb06a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
aff8bc86-68e0-453b-a5f9-93840bda7eca | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b3869d9e-d9b9-4cc2-99ca-6bca4151a640 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b3ece2c7-72a2-4b46-8f3e-af35ba1b5d04 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b43d9cde-796b-4e6b-be6c-6e05343becec | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b84f5f6d-b861-4f42-817d-693d2c26e82f | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
be284cae-e84a-48bd-ba5e-fcac4c0a0d67 | Pole | 2 | Distribution | 2020-09-05 | 2021-09-05 | Level 2 |  | 2022-02-25 | 2023-02-25 |  | Required to Re-inspect a subset of assets
c9c479a8-4418-43bb-84d0-e2eeb10e8ae5 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
d9884afb-8c3d-4684-9791-ea8c23cfb7c4 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
da7071ca-cacd-47eb-aa47-c6cfc507a48d | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
db20c81d-1af0-457b-84ab-cec08f4b3084 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
e1c82cf6-28b6-4ab7-81c1-e6693d661764 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
e954f118-a930-4b47-9c0b-1a0be0aaf170 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
f16ed127-1528-491a-84ef-70caea43017c | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
f5edade8-b947-4c0f-afd4-9b2cf4c1aea7 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
f8b161fc-0e9a-404c-99b2-ed5fd018c308 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
fa5af747-33de-484d-819e-31df176de49d | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
024f6c60-ff02-40d1-b69d-b487007175da | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
06899ca1-e5fd-4d5b-b862-39f6a8447a13 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
12e2834e-f88c-4032-9995-c22e9d0da1da | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
1550e977-0de2-4d0a-a225-01c40b406483 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
15f24734-9e7f-4162-a821-b16df038fe73 | Pole | 2 | Distribution | 2020-09-08 | 2021-09-08 | Level 2
19a5b9fc-749c-40a4-948e-101072e56771 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
240b50d4-c7eb-4bc0-a676-8a16bf2ea521 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
24f4f769-7fcf-4180-9457-6bdf22e5f427 | Pole | 2 | Distribution | 2020-09-08 | 2021-09-08 | Level 2 |  | 2022-02-24 | 2023-02-24 |  | Required to Re-inspect a subset of assets
2abf4712-2189-4708-8a18-51848df4112a | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2b4a46c4-f79c-41df-8856-36bf667578d5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2c94f8e6-2da7-4ece-8f84-b8bfd465d47b | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2ea550ad-8ef0-49cb-9761-fdc48d5bfb8e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2f67e228-d591-42cb-b671-114ff8e39214 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2fbda864-7b21-40d3-8a25-6992afe2fb9c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
375ab800-c410-4131-b9c9-8fc3fabafa40 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
393d7c17-7e53-4b80-90c7-9e855dff80bf | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
41e953e2-fc58-41c8-83a4-045ef44bab7e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
42ae9b87-a6c6-43fc-9952-ce84e5559e6d | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
48d3ec55-feeb-49d7-9a30-1a37c2e95bd2 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
4d07c03b-e33f-4224-b4cb-43d894302b47 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
4db87775-266c-4b75-9591-9079baa6d8a5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
54c59ffb-9223-4b48-983d-2196acdc90fa | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
55a7ecde-57c4-4e64-91f9-102c42ac961e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
636a27a1-b387-4d00-9ad3-5a1228759afc | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
66120f86-56c2-4bfd-9430-bc20357231c1 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
69cc017a-5d89-464d-ac5b-4ec33c1ddbed | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
6c6529b5-f6c4-41b9-bc8e-ffcbbc9a2725 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
6fbe44da-810e-43c3-ba9c-19560823a653 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
73490d40-4936-4a87-b5f1-77ab16ee65e2 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
76e896a7-6e8d-4b5d-91b2-b0fe5140136c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
78f5ca16-6f8b-4ae5-96dd-843cb92aac15 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
7a4ace39-6521-4a1d-8c08-40f0a0d9918e | Pole | 2 | Distribution | 2020-09-08 | 2021-09-08 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | Required to Re-inspect a subset of assets
7c48afce-1b06-475b-a8d0-0698b0715c84 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
7db0c57e-01bb-4c51-94ed-692b15bfe739 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
806a044a-1e7e-4440-b9cf-3c946f102d01 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8102d5dc-0f2b-4c0b-a698-e9ad86f47ad8 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
831c3b93-ae13-41fe-b708-6070f92de206 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8e03a218-82fe-40e8-bb85-f79b9abca62e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8f042e4a-6974-41d1-a522-8237c4793bac | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8fc0ecc6-5811-4fc1-8b13-4d4bc637f719 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
92955c0d-8f91-44ab-84f5-dd61971d297c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
9f5ad1c9-d402-4da8-9f11-43dcdfb81d1f | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
a566bea4-f8cc-4c9d-ad0e-52f458024ac6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
a92fdd03-e53f-4461-98d2-fda5083039e7 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
aad3c9ec-80ee-4d6b-ba65-99a040d897b6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
abf0df36-36dd-4d10-a1be-dbe52a03f3d4 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
bb854659-af6f-4a5e-ae8d-775c1b200a91 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
bf414139-c891-4a38-8a27-c96b547b8ff6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d041f2d5-d22d-47e2-be2a-89c5239369f1 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d3085b44-6db7-4998-8f42-e7aa173344a5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d3ebeb17-7ded-45c1-9864-239f5465c1d6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d6ca7524-6261-4ced-aa07-dbd39ab49a16 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
dcae8831-43fb-4edc-8eef-f44370eef726 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
ec3c1a11-b2df-4799-b307-573414a69b3e | Pole | 2 | Distribution | 2020-09-08 | 2021-09-08 | Level 2
eda784c0-6fe5-44e1-835e-f3a702b2e559 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f35668be-83fa-4190-9161-8da3e5ede8fd | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f44fb34b-0e6e-4c9e-afc8-13c2ef973133 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f535d0c9-2c43-4f48-802c-066fbe4676d0 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f68e546a-3040-428c-a93e-415b53c11cb5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
fa520d51-473e-43a2-b9c8-c48dd37674fe | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
fa9f6063-133d-495c-8d5b-dfe8a4f89622 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
007fdac0-cb4e-4e37-90d9-3a3349f9ebd5 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
07488f54-5c5a-4e2c-b67a-7742566d3ead | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
07f6d1d4-a745-4314-bc68-39428f89bd87 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
0b3484ec-82c1-4898-b34b-c221ee045f70 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
0c2447ef-cfac-45b2-8932-60652242ff2d | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
10b04f77-b488-47e9-b35c-4b311c07eff7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
1129d575-5c54-4d51-b247-6762944ed7fa | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
11ec67f5-9c1e-45a5-9686-2e5d750bf4bd | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
15f5a249-a566-43ff-bac3-d50aaa28aaa2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
19fba032-bcc1-45cf-b87f-eb4ba2c174e7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
1c655b60-d492-40cb-9257-6c92d764b412 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
24e4529f-9728-4a4d-9714-8f81c6853de3 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
2bad7dd0-0984-4602-9ffb-7fbecbb194dd | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
2e445db0-1cbe-4d68-82a2-313c8ae56c86 | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2 |  | 2022-03-01 | 2023-03-01 |  | Required to Re-inspect a subset of assets
353bc8c9-147e-41e8-851b-d03064a5c56e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3789f0d9-5a8a-4ce8-9e9b-c0218362de42 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
385a498a-f6ca-459a-9057-e294cf77139b | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3a05872e-ab72-4941-b98f-0ab8e17e087a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3af34345-9d0e-48cd-a463-4f774261f162 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3b971442-07c6-49ee-a7a9-a9f1e1349e29 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3d386e16-9cf7-4545-a597-58fcfca2fcdb | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3ed00688-1808-4529-b0d3-b2da0d03f5b9 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
476fec00-2b69-4167-a662-f4f309809ea9 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
54b5d292-9787-4c8a-bace-241cfa6831b7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
58841f2d-54fe-4296-a20c-cbe15fcd1b56 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
5a2c25df-c168-43f8-a9dd-bc41d7455e19 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
637bb15f-f1bd-4ba8-9f7a-4f132d02f0ff | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2
66a86bde-102e-4e0f-9ee0-0de3d662e805 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
6d30dc64-a57f-4fa5-a18c-87172319c6fb | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
71e6de20-9815-48c1-ba65-939bb5bc05e2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
73270fdb-d3b1-44f9-ac89-01721fc49d3a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
77196ef7-113b-49a4-a25c-5c97513578df | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
79818e87-1936-4878-8dae-4019320e079a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
7bedcf8c-be74-4f77-a8b9-8050fe29473e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
7c187c63-4ac1-40e4-bfe0-2f31ba9ba143 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
8735d8b5-3937-4730-94aa-e7f489ce9e84 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
879fb521-a0f6-4a66-815b-12940472578f | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
8a97c09f-9abe-44b9-8176-6a685dc41e1c | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2 |  | 2022-08-01 | 2023-08-01
9325734d-7db3-47aa-a039-385bd47c9ecc | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
96ec0dd6-0c31-4ace-8a66-8d06853c2d85 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
99f8a735-991d-4534-a5e2-bf46e44e9bdc | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
9bced209-5a6a-414b-821e-fc1df9483d55 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
a494f653-fba6-4b1b-bffa-568c25c45f58 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ad4610f3-cdc8-48bb-b50d-f1036c8ace75 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ad86ba97-47ad-40a9-a66b-401cf8a70f89 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
aefee700-0616-40c7-8795-c0b7a625f74e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b14978a1-ae9d-4b9a-871c-22de517726e2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b27889c0-ddb6-47a8-848d-93b56dbf8ec5 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b50780e8-0311-4a48-b639-02a7f817676c | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b6678cd0-091e-4dab-8177-3772efc3cd9a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b723812c-70f2-44a0-9c8b-e9c4dc0cd642 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b88b9f25-860e-4866-9055-904312608291 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
bb4f430d-0792-4719-939e-2f40c5dc0d94 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
bfc4e19a-ec42-4224-9b83-9793801b6ce0 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
c351f124-b84c-4420-bf5f-1e11a6ee13f7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
c85d5613-8f6e-4bc6-87e5-a1c7252f5bd6 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ca5b430b-720c-45a8-87b8-72a944b0ec2c | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
cdc01b4d-b15b-4e32-8681-7eb967089f58 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
d2b7160e-789f-4a4a-a680-001b77ca3dcc | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2
d9337983-775a-4461-beb0-697ac09c5a05 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
dc2bcdc5-f3e3-42c0-9847-b44bf745bde1 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
dda1f78f-6c90-4366-abb5-ab36e6526399 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
e1c723df-5942-452e-a8e4-5441e4ee90fa | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
e48c593f-e666-448e-9885-7b5160303671 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ef605571-9146-4f2a-9b92-9a5ecdbef07a | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2
f1c8bf7d-aad6-463c-9df5-6e7a7efe2ec7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
f97bc0ae-eb42-45e1-845b-8e22214459ea | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
fbb628c3-0e1a-4128-937d-d315aae2ebd0 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
fcc9ee67-7cba-471b-ab96-8d89f84a73f8 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
06094732-0d28-41d2-af3a-7302be409143 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
08cc3064-e8d3-4142-a001-61100fa7252e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
0c3dbf29-5c48-4190-9f13-246d14cb1e4d | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
0f2ebcad-ecab-4290-bb06-750f1bd97f51 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
10c84829-41c9-4047-9d4a-16636a3128b5 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
138ef56b-089d-4183-9589-89dfc105e5e3 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
19e12a14-1a05-45af-b0e6-954e28c9ea70 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
1dcb4be3-30cb-4828-9ae5-14b8ce742746 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
24a52811-eb26-48a2-8e7f-238867955863 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
26a5a473-a5f6-4562-b8c4-1f35128adf8c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
28e65c12-9e2e-474a-be83-454ac367bf56 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
2dd013d8-8f60-46a8-a298-a040d821d64d | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
30b094fe-0d15-42f7-9e3c-f26374988b93 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
314a3045-cffa-417b-a0d6-2b48ea9f1767 | Pole | 2 | Distribution | 2020-09-10 | 2021-09-10 | Level 2 |  | 2022-02-28 | 2023-02-28 |  | Required to Re-inspect a subset of assets
3b2f696c-1736-4687-b6f2-4192915f631c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
3ddd2f2c-3e80-400d-b3b1-dd632ace2c40 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
3eba58dd-57a9-44cd-b792-ea6d6ec2a51f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
4010651b-9a16-4090-8425-5a10fab00e12 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
407bf218-0e81-4691-abed-136d398a3e35 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
435fc398-26bf-4571-9a80-f68662556def | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
445468da-5be3-436a-9ef1-8a8b34522f3e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
4e187afd-1e5f-4a37-bb02-3e41b5dcff5c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
5a2f144b-7621-42a0-8ea2-574ab12133cd | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
69c6a510-4a23-4767-b433-56414a4a8f55 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
6f71e2c7-ce89-40f6-bd18-e67d501c6dec | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
70903d03-db04-46f8-b114-b595047587b8 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
71d5542e-7e9c-42cb-826e-3db4bfa9bfdd | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
71f40119-bc71-4064-8e99-7f18a6a2484c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
82f158c8-a3a2-47f3-a057-1cf7cc7f5983 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
864c79c2-b840-436b-b20d-132d0d4c14b9 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
8bbaea22-21c4-4ad2-b7c1-c4df7f28f134 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
8c52d151-6226-48f9-be80-b4d18df7b4f1 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
96d21b30-8e4d-4aef-b099-2cf7ddac941c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
a8916749-cc5f-479c-8804-e50c7dcc4268 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
b3787423-b15e-42a0-8144-eed040a1464a | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
b4b7ef74-f0f1-4e35-8f7f-25f368e188b2 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
bba20c57-5a90-4bc9-85ac-9f1c5d3e7f1e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
bd468c6c-8b08-4d34-aaec-f540c1bd96af | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
c3f88970-c8ac-4350-9225-a98bb8ba1c5f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
ca71c0e6-a241-4191-8318-d4a2ac793cb7 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
cb2a11f2-d208-4ee7-8dc6-dafde46aface | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
cf928c1e-e5fb-45d2-adb9-787f81497bb6 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d0cfdcf9-12d6-45d8-9dbb-79f957841f13 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d5fd6047-4915-45f6-b2d5-9636c87fe220 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d6bb383a-d6c5-4757-ac41-cefb820d7c56 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d7674af9-0fc9-429f-8564-bab04a1bd0ba | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
dffcc6e1-3005-4831-86a9-1b5d07ece2c6 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e19acc34-e06c-406b-b384-c461968b757f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e30174c1-5673-4617-8c30-481419c386ea | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e52524d3-0a65-42fd-a7c0-f408d6232394 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e5700baf-b167-4c98-a52f-a47271069622 | Pole | 2 | Distribution | 2020-09-10 | 2021-09-10 | Level 2 |  | 2022-02-28 | 2023-02-28 |  | Required to Re-inspect a subset of assets
e8df1698-f47e-42c7-9331-be67c8b7ef86 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
ea7ab73d-60d4-401e-9d00-f3f032b0965a | Pole | 2 | Distribution | 2020-09-10 | 2021-09-10 | Level 2 |  | 2022-02-28 | 2023-02-28 |  | Required to Re-inspect a subset of assets
ef093c28-1799-456b-afde-e8118635aeba | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
ef2f3830-8bdc-473b-bc6c-5d5e3c0a2257 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
f02c74c5-8a2f-4576-aa8b-732220f7defe | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
f881a56e-ac93-4cc4-97a4-3d2cf6f933e7 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
00be9e54-14e0-40b4-963f-783681085ee5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
046fcf7f-3e1e-4a86-9129-9ff828622dac | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
05de68df-cb14-47e4-b564-32e1008d89b9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
07069fb2-5304-4444-99d6-5b165010b9cd | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0ae4385d-8987-4a51-89d9-220c22a9d2cf | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0bc962f4-7e68-4ead-a677-b7910bf77c62 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0cebb518-40d5-402a-8f70-0778e1139389 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0dfc1b39-c2b9-49e3-a640-e18a4609bba6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
136576f3-067c-4c70-bc58-c3ed1d828cee | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
17c155f4-c258-40b0-a588-41e830848475 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
17c1b3ed-698c-446e-b6a8-b17b92eaf191 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
1ee99fdc-4900-48ac-93c9-1998500ae93d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
1fc849dd-2451-41a6-abdb-fb1049b05b14 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
201df0c3-44ad-4f03-b2a7-6fd703227a4b | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
2036f882-4de9-4ad1-ab93-cff7634e5d35 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
227076e0-3522-4396-a1fc-fd3126607bd9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
246e587c-ee06-4d07-9bb8-17e62a8b9e48 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
2fedb42e-f08d-41c7-bff4-b6cc6791b7ec | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
312028b5-da46-43de-b246-beaa87f8a2a2 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
32320a52-aabf-4be4-be8f-7ca01287a010 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
38d52519-20ab-4359-8758-f701609e7a82 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
39ffb9a0-9517-488b-bbb5-9261d40114ae | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
4dffa63e-5d70-4c83-90cd-aba0e3a08a43 | Pole | 2 | Distribution | 2020-09-11 | 2021-09-11 | Level 2 |  | 2022-02-28 | 2023-02-28 |  | Required to Re-inspect a subset of assets
50a00ead-c7a9-4a04-92ed-ac72fd7b4b30 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
53b83bc1-c945-4103-810f-e103e07c8880 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
632a2553-610b-48e4-8022-8a1d554914f1 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
66efadb2-d4e5-403d-8927-29a942926aad | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
69b36e18-d30e-444c-9569-d89ae132554c | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
7a2f9074-de47-48b2-a9c5-a81414e10b19 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8601578b-c58f-46e3-a0ca-0398c6bd2fa5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
88530dd5-6868-4f87-81dc-fd0022eea835 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8ae3071a-7787-452d-8866-325ddd8b4d2b | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8b23e39c-cc65-451e-9eea-f2d1baebedba | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8e2d50e2-fe17-496c-ab82-7e0cfc9925d7 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
9020629a-ccf4-4a82-a5f7-87fd81f23d2d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
94b9512c-28e8-4d4b-85f1-f86a654b30e7 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
98a5d338-02aa-435a-be64-3b77bcfdf4eb | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
994f5a5c-4f3f-4179-8c5c-7bda58b75483 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
9ca62d32-b106-408b-860a-11bbfaf6a79d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
9d979115-e9fd-4210-b01f-9dae17b6aef6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
a6bb3f46-0dee-4029-b1e1-915f491d80b3 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
a87b6f9c-b48b-4f20-8c6a-d5d56bc572f6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
abb8cd0e-9b02-4d20-93ff-7d95cb1af307 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ac2c3a92-5048-4329-8111-746b82aac626 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ac70b546-3509-47d4-a30d-da199e16d0eb | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ad0dc710-e286-4ca2-b190-7c54279903e9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ae8fccf5-3142-4a3c-bb42-11af8844d968 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
b777cdb4-363f-42a4-828b-28109ffa5bef | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ba9b8ffe-4c61-482d-a9ad-d2f19342f84e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
bbedcc58-d59e-40b4-b5e8-e690f94981ff | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
bcb3a97f-456f-4489-8141-276490866959 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c01d86e4-cd0e-473f-ba4b-7ad4812a5047 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c0331e2c-fbf5-4cd3-b147-618faa155e33 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c16cdcca-a65b-4095-b319-104474959fd2 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c20fba24-b1c0-4eee-b816-d239cf852423 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c211d9c7-f71c-4c80-8ec6-a6c53286dd0d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c976e090-d0b9-4e22-b331-d72dd6d7e01f | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c9c01a04-41b6-46ba-b733-675fdca5698e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
d153fc80-566f-4787-b331-8f300c39f0bc | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
d62b3434-70fe-47da-a47a-1a462d9826a4 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
d8b2a13f-b851-4dbe-b751-090c379670b5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
dbc0d419-3c41-4821-849e-7c0247f230e6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
dd7186c9-f289-460e-9a8c-04af99402f0e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
dda6dcdb-915a-44b6-b01f-b4335150818d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
eaabc698-88c3-4daa-9155-d77e053d1d86 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ead94f8c-f29f-4fb0-840e-10878e1ecd49 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ee54049b-aeba-4f2a-9c13-67ecaf4a25bf | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
f51985c8-cb0e-4b2e-9da5-308ffa27e25a | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
f8459cd4-a447-461a-9738-f47a8fc3b581 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
01e6c5ed-156c-4b4e-8de8-8681f881f24e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
06604983-fa04-4aaf-be86-ef07b43fc7b0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
06755211-ab07-441e-9981-3b4edef33865 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
06b0d8f4-a9d1-49fa-91bc-74efe51457ae | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0712ed3c-753c-4061-b5f8-2836f1c77cef | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0a111d2e-daac-4306-9eca-304e5e6ee31a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0c319c12-23a2-45d7-be58-283f2dcb12f4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0f07545b-e55f-4d04-82fe-3cda2c6ae59b | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
15cf07a7-56d7-497b-bab4-84660d8b852a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
163e8a9e-3a5a-43f6-9d4e-1ccfba73aacd | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
1691c318-562f-43d3-b54f-4030205c64ff | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
1ac7413e-69d1-4edb-9091-6cc19eef7c55 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
1ca7a044-c332-463d-a98c-6b36b1fc90b6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
202a03b5-8d1d-48a9-84b0-52bd56114772 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
21654e92-310e-4a09-b165-ee32b6bf795d | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
257aedf9-3c0e-46f8-beda-b1beddbaacbd | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
25f5c736-d551-4930-8e41-51a1cda4fbfa | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
38946370-0838-4111-be8b-cf241ddf1c33 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
3f4d3ec9-2c51-4acb-bb84-d4e115e1ff84 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4055c402-0c8b-4bcf-a47a-21cd851fbd60 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4b06414f-8076-4c60-a1a2-e8805922d95e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4d1cf6c4-cdb6-417d-9dbe-b90a5efeb6d6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4e939279-f832-489f-948a-41ca884bc7e4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
51621dc7-9ad6-4a76-be9c-84c1c4f7599b | Pole | 2 | Distribution | 2020-09-12 | 2021-09-12 | Level 2 |  | 2022-03-01 | 2023-03-01 |  | Required to Re-inspect a subset of assets
594502b7-18b1-4f3a-9d74-f35218e7790b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
61f41eca-2114-4dcf-8232-a3559f12b6ae | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
66e156d8-e695-4d11-816e-f899d950c393 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6774d447-f696-4a90-8325-f3ce1be506ab | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6c4a54ba-d370-4451-9756-d9a3f5a7c0f3 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6d7067c2-441e-4dcb-a3fc-4a005c825408 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6f00bbce-6bac-49c7-8616-27d9b0703203 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
70b0829f-74ad-4468-aa52-12cdfa06d7c8 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
7220c249-f551-4bf2-ab9f-fe4038e72af9 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
734c6e77-d2eb-4181-a3f6-35dac2b83043 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
7553da92-b5a5-4e3a-8e40-acb6726eda82 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
872a3935-9cd2-44bd-b21c-5d4738959eb4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
88fe2232-245d-4538-a6ce-4b34275cf0c1 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
8b542ee7-b9d3-44f3-ad3b-f5eeda3cc86b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
8c723f58-9e70-4747-a577-58237763f6f1 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9155ac75-ca35-4712-b5ab-146830acb411 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9254e558-b0bc-4f80-a46a-d487b061c3a0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9990b478-c4e4-4ecd-849e-ebe907e73454 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9a02260b-2a44-40ce-a817-7a4384261c63 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9f9043e8-b8c5-48e3-bf62-6239c569e427 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
a269ead0-de83-4d7a-9aa7-0ae62cf741e9 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
aadae53c-71d4-4b7f-a582-a31bbd79c427 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
aeff464c-7fee-443d-9091-78b67a79b8c0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b0de87ba-e3b0-4f4f-8d06-76a3d8c60f6b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b47a14d1-105d-4c69-8952-a08f3262052a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b4beaee6-2627-423f-90de-1e1e9d57a0d7 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b5e91be1-bd32-47e1-841a-32dd2ce308aa | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2022-03-01 | 2027-02-28 |  | Required to Re-inspect a subset of assets
baf4cd56-dff3-49f1-9400-138a09cb5fb5 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
bb76c009-be7a-4bba-a483-da41b3743b91 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
bbf42bcd-4b8f-42d8-9150-efe9588986ab | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
bdd50219-1284-4e0f-83ad-b392d16734d8 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
be1a67ff-9ee5-424e-9c65-032689bdcca4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
c761525f-43b3-4af9-b611-a4512688f535 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
c8f462f4-91d6-45eb-9a2d-153a801bf53b | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cab342d0-2bef-4463-8368-1aa5d5ccb4df | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cb2f24ec-e6ac-4421-8f0f-4ad4e7006691 | Pole | 2 | Distribution | 2020-09-12 | 2021-09-12 | Level 2 |  | 2022-03-01 | 2023-03-01 |  | Required to Re-inspect a subset of assets
cdf0ecfb-1a7f-414b-9639-22d8cb3167db | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cdfba419-7c3e-49db-8f2d-88f8b2238cd0 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cf10adcf-7179-41eb-985c-19f1af5d42bc | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d08c887b-7e80-4488-979f-3e6014235aa6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d208860b-fc78-4c95-8ccc-2a8d4178954e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d3df4e29-eb1b-4e76-8f19-8744e29f940f | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d49a18d4-bfd1-4509-9a62-daf135a843ad | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d8f1a664-5636-4020-995b-4479eb02dc7c | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
da72b4fd-0ad9-4747-a5b4-6911d648762b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
db063571-bea5-4468-bce5-2f3c382a3158 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
dc297714-4f0f-42c9-9348-412898baadcd | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e27a9e6a-264e-4d80-bb44-f0f3e4ec453c | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e2c01527-c896-48f2-b8f0-9f4e41aaecee | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e3e35637-ec93-4ea9-a3ce-851c60d10b8c | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e78bc320-9752-4aa7-9564-47813cd6fb87 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e8505b70-dcf4-4dd6-922c-2ccaa4bb6d79 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e9c96776-7433-41eb-a7a3-4f5fab9fef0a | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
ec16c3c8-b03f-4f11-a3fb-a1d201e28a62 | Pole | 0 | Distribution | 2020-09-12 | 2021-09-12 | Level 2
edad180d-af49-4d38-9971-4391a9ce1299 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
ef23e86c-4acf-463e-a10e-e3f74c580c3d | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
f924a1a0-15ac-423a-a941-724e10b92eb0 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
fb3e4972-d35d-4610-a425-83779eaf94aa | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
fc88c135-f63c-4ca6-94f4-d22989f0e019 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
fcd9b46c-3491-4c49-b1c3-aeec9f576b91 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
ff3c09cd-251d-4306-a517-6d9082c544b3 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
00eaccc4-4087-4125-ba38-91a7ed63a24b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
017c8504-a7a4-46dd-b292-22465835c9a3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
0a579afc-14ce-4f44-b2f2-23d2c169d3b3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
10054db1-627f-4676-9177-bcb9cd077701 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
142f4922-2844-4143-931a-25157e0c6c99 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
16404d5d-b241-4eac-8015-cc30df8852bf | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
1ae76144-8199-475a-a238-9c5c36d35793 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
1c669c99-126c-4efc-862f-91480eea31c5 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
1f01ee3c-8b7e-4501-9d96-6e8a76ee9633 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
201a9dc9-63b6-45e9-ae6c-9534f67456b3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
21c27a95-45c8-4ae3-8cba-8a5ce930180c | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
236987f1-51e5-4077-aa3f-567e317677f4 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
239ac3a8-1ac8-483a-ab08-bc48b883da89 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
289c49f7-0840-4bc0-a318-af0365dbc828 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2ccd4649-4bd2-4208-ab69-7024a37c3a7e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2e8b6799-1d7f-4dbc-90c5-e1a2916a9c67 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2ec02df7-19f7-410b-bfd0-9af776299377 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2f940277-22be-42a7-8834-28da9b620be7 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
30ea35ba-82a2-4395-b5ca-23767c9f4cff | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3268f684-b4c0-4caa-bb35-a6f7a291a021 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
37b626c9-790c-4620-8ff6-503f9536079e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3a7a4299-3220-414f-859f-6d963ab6b87c | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3d9319f3-88c4-422c-901b-4cd2e2dbc9c0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3db4a227-beba-4a17-bdd9-e48ca6425e88 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3ed28385-0648-4977-87a6-65a7d7a1fe66 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3f26fa99-0f48-494c-885e-9a95a886e0c8 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
43e21dca-aab9-4819-81c9-33bbda26f39e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
46a0c114-b7d3-4a0a-a855-772da5c09609 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
4a08e08d-85bb-4562-88c5-937f0c2a8ae0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
526588aa-256b-4741-90e7-3b88094bcbe0 | Pole | 2 | Distribution | 2020-09-14 | 2021-09-14 | Level 2 |  | 2022-03-02 | 2023-03-02 |  | Required to Re-inspect a subset of assets
666fb3ed-e20d-40f0-8b03-913de4682d4d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
679c7247-166d-4cda-8f68-754f0b779935 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
6b5a8c21-5912-495d-a809-0cdd73a5ade3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
6e743dcd-99a5-4a3c-8223-2ee7bd1c376e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
714d193b-5ad9-44a9-9ec8-1bd95146278f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
72783e60-b2da-468a-b64f-240f165d90a8 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
746d3295-42cc-44e6-9475-a5b550153674 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
78fc88c5-a130-4294-8c06-631a641c9794 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
79ff81be-c137-4ef6-b8fa-88490cc87c68 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
7c387807-4864-49b9-9be7-eaf0a5c3dc11 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
7f98a276-aaef-4e4e-8020-a5a6b515e965 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
818f8593-eea8-4d65-95e4-707b548ab5e2 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
83a8c1c4-e015-4089-865e-e4daacbcaf66 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
8aa0934e-539c-4e34-866c-5c80f44deece | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
8aed9894-cd25-4c07-a7db-76de1b4ae368 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9234af58-456c-49d4-ad61-d21a411a6694 | Pole | 2 | Distribution | 2020-09-14 | 2021-09-14 | Level 2
96ea5888-fbb6-424b-a049-5adf718be119 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
983f8ae9-03e1-49a3-b856-45d5f93c6135 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
984de1fa-faed-4291-919b-7e77f6b01246 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9b827a8d-2e06-4358-9460-25ffbb47fa92 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9f774194-b8d7-4a48-9767-09e3fdfafa1a | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9f883c68-681e-4422-a6b7-139e5c86449d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a094e5f0-2dda-46f4-87b9-68b3aea4666e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a3493de1-a56d-4952-8ae9-b8383a85242d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a51abbcd-cb0f-49ec-9cd1-db12da4b3f32 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a574af9f-d02a-4e64-8ea5-08e12ccdde3b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a81f8630-108e-4a47-ade7-080ef714b268 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
b16340ae-5162-4c85-9f77-789d657abc06 | Pole | 2 | Distribution | 2020-09-14 | 2021-09-14 | Level 2 |  | 2022-03-02 | 2023-03-02 |  | Required to Re-inspect a subset of assets
ba4c3707-710f-40c8-b5f4-9bdab567945e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
be8b262a-684c-4e47-9bdd-f065634ae952 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
be90295b-349a-4878-98bf-33a2a2d7ec67 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
c55a2456-6b93-4050-911b-48f71a4c3e8d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
c55a605a-ed89-47a6-b36d-2c75c05fac98 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
c67d3a4d-f21e-4d7b-a899-bc6aad27a9be | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
cdec7f9b-9445-4227-b217-c1691deef7fb | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d02ad81d-c36c-4f03-8446-63f38b87a1a0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d0e4dcb4-f883-4a7b-b998-7e882a986b74 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d2a9aa10-7714-47f7-8cfc-652b51da1d80 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d3753484-90c2-40c6-aa44-3ca624190873 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d722d7ca-d9bb-422a-a8f2-6ae5321c69c3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d8d3ef4d-b13a-4c14-bf38-864feed58533 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
daef9cc9-1a31-4b38-b101-652e946f8b70 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
dc21539b-4d1f-4990-8084-407e0b5d592b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
df9bfc8b-c32a-4240-b8de-64a94b1edba1 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e159490b-60f8-42ca-badb-3f026dd704ee | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e4fd0d7f-e763-44ab-9e26-9fc35bf3a22b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e6cacc72-dfbb-40c1-a08e-472b82fe849e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e827226c-a359-471e-b274-de887a36c47e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
eadc47fb-a021-4234-a4e4-6b277b3a7e2f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
ec50b6a9-9fe4-45f2-a5bc-45b6b71b6477 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
f86a644c-9338-40d8-92d2-a1f3b75e6a8f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fa0f8be2-9eb2-4510-b8d1-8f2f636f6167 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fc43f010-3bfd-4a9f-88cf-e50d24db8908 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fdb3aa6e-3ea3-44f6-b303-5f01c602ff79 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fe7a4988-1ccb-464e-814c-a7a524d0fb56 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
067e4ac0-886f-4ac1-af54-32a63eab9b42 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
07fca404-4dc4-44f7-a404-09d8523b587c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
107ba6d0-e1b6-4f10-9919-f37f2e208575 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
10c9ccd2-308e-485c-a558-0008371562a9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
14b98f8f-0c48-45db-8853-4a7482454431 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
1a6ba33c-00cf-49b9-9043-41b91d4bc8e8 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
27be5e51-b051-440d-af43-b3cb806b36c1 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
3075c30e-85cc-4db1-8118-945536b7b927 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
3cb5e2a6-a19a-455c-bb52-4f0aecf94ff8 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
43a896f4-c675-4bf8-9b67-dd69d08d987a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
43d17037-cffa-4d8b-9374-3b091af9a85e | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
477ae48d-10f0-4d68-98ab-8fa0bb030f8a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
498bdfc7-bad8-46cf-a701-ea01bdf5a587 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
4b295f21-fdec-497b-a08e-780627ed1cb6 | Pole | 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2 |  | 2022-03-02 | 2023-03-02 |  | Required to Re-inspect a subset of assets
599ccb56-6f87-46da-9250-b2c7aaa4ba8f | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
5e644c34-f461-4598-a822-2f8d4f2319b9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
65e3b1da-37ee-4ec3-9bd3-4bc859c5a9b5 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
664e2e7a-b144-464d-af7c-d1132438b573 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
69790a6f-42f7-41ea-86dd-965fae409c41 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
756ee04b-8cc6-402d-a244-88780a075a63 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
7606eb99-8600-4603-aaac-200e22ef804d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
78972a0d-4932-4116-bc8b-092d55069718 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
7eaa1565-1ad5-40dc-ab59-a8217d453bef | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
802c6196-7321-4988-a5a4-70c294cc4944 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8122da08-bc53-4fd5-a516-05fbf08d7e43 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
862f2dd9-360a-4444-8aef-b2870a42807f | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
89686f07-b95c-4cd6-91fc-00d97765fa55 | Pole | 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2
8ae19aae-0071-4595-81dc-43884931423a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8d92b1e6-efd4-4596-a0b8-518b9710e5e0 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8eb5ff86-91b6-440c-89ec-7c4dbdb06fcb | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8f90750d-0075-43ee-8c62-dccc27d04d6c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
90624ba7-6762-4402-9406-0b3d8e20251c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
9cb6165e-f9d4-4165-a703-cfd2b5194f41 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
9df6dcd8-3dcc-4589-8ab5-7c5e81e01996 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
af301db1-2b3e-4ce0-a440-7d1ed256217f | Pole | 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2 |  | 2022-03-02 | 2023-03-02 |  | Required to Re-inspect a subset of assets
b5028673-0f01-4209-88bc-77c2e275cb10 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
b886b911-20b3-4066-92e3-e8cc20675f44 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
bcb375d3-66d5-4288-9aa7-41776c6ca9e7 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
bdc962b1-fa7f-4ca7-bfe5-8d6774347587 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
c1720bef-4566-4d2f-8a1f-91269baad7f3 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
c6acd3f6-4e6b-481e-a83e-87993c838de1 | Pole | 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2 |  | 2022-03-02 | 2023-03-02 |  | Required to Re-inspect a subset of assets
ce59f6cf-4f6b-403e-8916-8d871077ed7d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d138fc4d-6fd1-49d0-8f13-6968a31b9586 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d13f7b66-b894-4757-8c5d-087da3ad415c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d1796ca6-f922-452d-890c-5dcf6bca29a6 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d32c1bfb-84a2-43ff-a577-b81e9940f5c0 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d4a22035-e959-4264-9207-3c09be3820f9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d737cfbc-e4cf-40aa-be91-063577e7f4a1 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d7dbcda5-3b07-4167-a103-e2395c77a380 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d8ecff38-59cd-442a-84a1-36f2be89cb4d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
df909596-d684-4343-b007-72b96d93e505 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
e506a92a-c8cc-485e-81e8-79a8a9c1cc32 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
e561d49f-34b7-4e88-ac3d-bb9024d46f51 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
ec7d63bf-2694-48cb-b862-a7141a854db5 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f15f43c3-5a0c-4503-a204-6a5612dd845b | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f1b8fcf7-c299-4f9b-84f1-75bf884592bd | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f7141845-a515-4116-a3de-da48789f83c9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f7cbe413-6fd2-43c6-8a6f-d6e1ea7b3266 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
00e53c6d-3ff6-452f-bf1c-fd95b05f1d8b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
057b3070-2577-4fba-95dd-e98df1b371ac | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
06c91f96-2882-44df-a127-d9d7edb056e3 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2
16f16a53-c628-498c-add5-2cde6af5614f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
1920283a-ab84-4304-ba1c-b2b7e81a407b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
1c2a2c16-6b47-4cef-8ee5-59cc4bd1a4c6 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
1e3f2bfe-64cc-4941-86cc-3099b3b01ff6 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
2236abdc-8fd8-4d42-bb68-7aa14a9dfc37 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
25d3161f-6f1c-453b-be04-853f01ed7245 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
2faa00f9-2964-4f78-bdfe-0de414ea9a6a | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
37b978b8-efa6-4d26-95e7-f322863fdacc | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
3bff1469-04ef-4476-9a42-679d9ebb1360 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
3e69c394-2d6a-49f9-bf43-05ee6b6ffd72 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
582ff41a-00ee-4ba6-90a3-f21790ab6d84 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
591f3239-7835-4764-8b38-ddc7ed924b35 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
6bbfefc2-a654-41bb-97f0-821f1dce37db | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
6e3025f3-316c-4dd5-9a86-76dd587a1607 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
6fd0ea63-d3ed-4f83-aad4-f6ae44c01438 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
72fd69f9-5bd4-428e-90b4-a7b4b42f0630 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
7c1075e7-6c0c-43c7-a567-eebe29dc10fd | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
81df3ead-c173-42c8-92ae-29a5cd1a91f6 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2 |  | 2022-03-07 | 2023-03-07 |  | Required to Re-inspect a subset of assets
908b1516-b4d2-4365-8a8c-d8fe544c1598 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
911c6faf-0b65-47ec-b1bd-9a34161166c1 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
9128dc83-f3a8-4507-9eff-afd05f5e9abb | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
92dd6c1f-e942-41c8-ac60-b0b426f174ba | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
970ed103-bd33-4f27-b406-6f87814c3a7f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
991bcaf2-38de-41df-b1a2-44e5a6225af9 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
a1367e0f-1f7a-455b-9696-278ddb5bab36 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
a1e65cd2-52d2-4e57-8400-2591b1046bac | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
aac668a0-e890-48b8-a57e-20028e3bc185 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
afe872f4-e448-4231-ab4d-b3fd5ba0f220 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
b1ae1934-7f2a-4c0e-af59-5e3547a7bd1f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
b63d98e9-25ac-4df6-91ba-2a5e0883425f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
b7785d70-15a8-4224-961e-d2173cb94f85 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
bd6e233c-0f91-4150-9600-9b03016c7374 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
c9317a3e-a7f2-43c4-9b07-c51f6793da44 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2
cc216c78-a960-45ec-b0a8-7f4ae515c58b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
ccfe3f15-bc48-48cb-8bfb-f355f95bd249 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
d572c4ee-6734-4c64-9c51-c990f525caf2 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
d6af5aa4-2a0b-4996-a592-8d88ccf16a85 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
e2719427-d0b9-4433-b28e-d9237ed649ad | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
e6e6e4b0-56dc-4017-9280-a0cfa7a65284 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
ef08833b-4fa6-4df6-bfb0-10e45e6a8bfb | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
f79fa4df-f779-49ee-8bc9-0b1948b9a3a9 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
ffcf7ca7-62a9-4256-a8b9-f71301012fff | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
04fa2192-dabe-4039-bed9-b9b233de68fe | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
07f7bef7-e317-4cae-a372-0bb3492bed6a | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
10feacd5-3688-46d5-9059-38989ace3fa3 | Pole | 2 | Distribution | 2020-09-17 | 2021-09-17 | Level 2 |  | 2022-03-08 | 2023-03-08 |  | Required to Re-inspect a subset of assets
260619ef-6aad-4159-a461-1062dbb9ed12 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
291d924f-3c56-457a-a893-383b82738b33 | Pole | 2 | Distribution | 2020-09-17 | 2021-09-17 | Level 2 |  | 2022-03-02 | 2023-03-02 |  | Required to Re-inspect a subset of assets
2a73b142-fce7-459b-b03c-3cc306567b45 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
3e557f15-23e8-4816-b3f2-f356404b4866 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
408f30e8-6d9e-4f0d-88f6-f11a9f89dbc6 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
4998c980-b7fb-497c-a656-e76fe594a783 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
4a93adc1-e7f3-4f81-9808-16b9b62a52ca | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
518b01b3-f0d1-412c-8fe8-597620965eb0 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
552207e6-75b8-457e-bd52-b416f5780f45 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
72c8b212-8d5b-4925-b63f-88ab55c0a1bc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
79d02709-cf05-4575-a30f-190b4f420571 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
84826027-e0e4-4e4e-86dd-e09c269dfb50 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
8db86714-7cd0-45a4-8838-b01231ed8491 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
9bd6ea73-c0f0-4846-9bdd-7f9c326bc4da | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
a349cab4-f321-487f-ae80-4e56731d67ab | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
bfe9da00-69bc-4548-8219-ad57ae7eba4c | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
c500eb9a-3614-42cb-a1e6-1f63f4815c4d | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
c6a77b7f-e804-4183-8913-475ea4635186 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
cfea1c17-4508-4643-8ec0-58414025fba4 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
d66fe9e6-429e-4b7f-a14c-50d763735cbc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
f56d600a-0a69-4468-aa43-2511b6ecd3fa | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
f65c39d7-b294-41d6-8e96-30413e9716bc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
0169efcb-2ed4-46a6-938c-9355f405f29a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
02dd2efa-4a82-40e8-b0dc-a9bac672145c | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
08823e46-166d-44e8-a68d-2efcccf6635d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
0af720ed-a0ee-422b-8ee4-5b43c9d33bc7 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
0f6d8585-c96b-4b2a-8505-2ae85c885aed | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
1481e906-fc04-42e5-950f-5c1bdd2515f1 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
161a6279-0e70-4b64-84c2-ae4db8cde788 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
1a22c63e-20cf-4e46-b500-b518ba555114 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
20cb28f7-61d3-4784-a45b-710a7678a36f | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
2434adee-efde-4f45-ac86-9758cca5205b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
38c95a71-08e4-4b9e-81ec-db4c6fb63593 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
3fd0bfd6-afa6-41b5-9c84-60dc6a75914d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
42a95ff2-89a0-4cd9-9e15-e1938b7eded3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
45eb5350-c97a-4f5a-a3b5-9ad2ab5dcd8b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
4612ac93-3159-4bbc-aa74-44e409c85742 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
4be75378-5f4a-459e-b458-0f1d1bbc600a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
51dc9f81-f4da-4c03-a1b4-289c80803f41 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
55b091e8-0373-4266-ae34-a990caf18c71 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
563682f3-9b98-4d5c-8687-5e85323f1ea3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
5a135d5e-5a13-4681-b7d7-0c68a78c303b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
5c9472de-c4ea-409b-8b56-c7cefb2b086d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
63167f0c-f143-4fb9-a8f2-a780200c68ba | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
67c5f9ce-acb4-40ba-96f8-8e481ec2ba6f | Pole | 2 | Distribution | 2020-09-18 | 2021-09-18 | Level 2 |  | 2022-03-07 | 2023-03-07 |  | Required to Re-inspect a subset of assets
788f5ea1-9623-487a-9665-fd79e78b3c75 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
7f1e6e8f-b861-45e8-b507-f2f42b9aeac0 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
84740b3a-385b-4615-b2fd-0b49f99c79c9 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
87a69f7b-e368-4bb8-a01b-bb63429d8fff | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
8a22207f-5436-46b6-9d74-fcfa85b29d56 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
963c12c9-7b0f-467d-9c58-cbf6e88b5f04 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
97c6bb25-ce15-4cff-b3f1-b485ea909282 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
9c0f69e4-5fc0-4a37-88c0-52f7e74af755 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a29d1750-c86c-418f-a254-44d62cd85908 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a4c4ca2a-cc13-4985-91b1-0f395446db77 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a7a0b342-c6ed-4b27-8685-0438b78c4833 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a87a505c-9c20-4cdf-8222-b72d9dcf5755 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
aa2380d3-8eba-403f-b0c1-3f45abe71f18 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2021-04-16 | 2026-04-15 |  | Required to Re-inspect a subset of assets
abc60e15-37a6-47f9-8211-e278b3351738 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
ad0a2c1c-4861-4356-97f4-cb11c9d6134a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
af40d29d-b24f-444d-a48c-12bf5593a315 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b01c07ed-d120-4b35-97ed-2bb63026fc1a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b0d549f3-b255-42b5-a79e-09a0f619f941 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b3b74663-4b02-4240-9a7e-879cbff5357d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b762f9ee-8b1f-493d-93ba-a5b1a423e7f7 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
bbcb524b-b380-4a3d-922d-3975149be33f | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
c62b4dd9-4343-4492-83c1-667c5b157d80 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
ce972377-fbf7-4a68-86b4-1ce8cd23b1b1 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d507778b-7f2b-43ac-a5ba-548a999bb32a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d5385b7e-bf12-4cfd-944c-8ccc97c81c38 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d76a10eb-13f4-4cfb-9a22-6aaa31a618a3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
db8dda95-89d8-4d44-9c22-577164cd8c0d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
dc24ed84-4be8-492f-95c4-c286e84eba22 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
e465f5d5-0d4e-45e7-8b49-d11c88f1c759 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
e5dc5cbb-8b70-4326-826e-a23fb01cba97 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
e98f4df7-9ef2-402b-9bb1-ca2eea3e3701 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
eb13cd7a-4931-4ad0-8ff2-8fc8ba005ec0 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
eb4eb104-f56c-4363-98a0-528a4b632402 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
f25dc6da-ad0f-4012-9e9d-617087ec7230 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
f3b94888-8879-4bf2-8d5a-f37987967b66 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
f3ede1de-0f44-4b95-8563-c50ffb570473 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
faa36a05-6d01-427b-9b99-8c640ca26358 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
fb889244-cd8c-4dcc-bab0-7447d2f073dd | Pole | 2 | Distribution | 2020-09-18 | 2021-09-18 | Level 2 |  | 2022-03-07 | 2023-03-07 |  | Required to Re-inspect a subset of assets
02478bd8-57a8-4d1a-b6d8-c31b522adab2 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
064f086c-54e6-4007-944b-398f79d3713b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
0c0994aa-3444-494a-a211-fca5f27b60a9 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
0d230900-2629-4e0b-8ef3-951fd826b2d1 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
131e8968-d1fa-4c1c-b968-a7793e30c812 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
144964b2-28c4-4443-abdb-1fd432bc0ed2 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
16e75a48-71d7-446b-be1f-c011067d8713 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
18f6926d-bf28-4073-82ca-dcf1e0a03969 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2
1b238d06-2938-44e0-a1f9-ae909ee178ff | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
1d549433-8f37-42e9-9f9d-1ba386aa5086 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
26964d70-51c6-4e86-a41c-f71119ecbe04 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
280e46b9-6bb1-4010-9091-ffb217b83c58 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
282e9eb5-ae62-4c61-81e0-8b54c6631b9e | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
2c7e8da3-493a-4221-a267-1f7825506d8a | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2022-05-27 | 2027-05-26 |  | Required to Re-inspect a subset of assets
38081f83-c28e-4b24-ac25-3d45d8cbd2ae | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
381d8814-d3a6-49ac-9848-8e76e63b0524 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
3a3ac121-d4d6-4b9a-bc67-e354d823fd1d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
4e298a92-46c3-49d7-97ce-f85b1c05dc29 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
4eda5d1e-d599-4a7a-a3ec-b02133a038d4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
53f96c07-8016-463d-b808-94c49787328b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
5a73eae3-7d0d-47e7-9c8d-d659b69f867d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2022-05-27 | 2027-05-26 |  | Required to Re-inspect a subset of assets
5eddef51-62f3-4b95-92f4-fd582d3511d4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
5f49e29a-51f0-45cc-9982-fb7d9fd98c68 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
5f641f14-f3dc-4074-8cfc-f0a209295355 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
67a26434-ecb7-41db-a708-04f4a2e0154f | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
71349818-7580-455a-91d0-048fd826e4c0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
72407f6f-3629-41ce-a150-e1fccc9ee5cf | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
725f8b5f-df3b-4b22-8c10-0a7eba33af26 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
75d1fc85-7755-4b72-bb93-b309d8ea3930 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
7b282242-ebcf-4dfa-891a-b3538d922efc | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
7cd6118b-1e86-41d3-908b-0a96bc4378d6 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2 |  | 2022-03-08 | 2023-03-08 |  | Required to Re-inspect a subset of assets
7f413600-9fea-49c3-b532-925067d40b87 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
7f718100-8722-49bc-a879-4a95d7106ba5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
870336d2-780c-4d45-8f3a-9417175fa2c0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
8c37726f-b365-498a-9805-ea90dee7df35 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
9016a7d6-27b4-406e-81b9-94a86f6761d0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
93082e1b-e7e9-4ce1-89a3-2a9b1944771c | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
a7fccfc1-f161-452b-a740-090fe2e0d5c5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
aaab666b-c2d6-4b26-ad9e-771fcb5536bb | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
abf03dad-8707-4f48-a0fd-cc6eb84890a0 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2 |  | 2022-03-08 | 2023-03-08 |  | Required to Re-inspect a subset of assets
ad34d8c0-ec8e-43a9-9725-e49b19bfc103 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
af3e8268-2e81-48be-8ea7-bb83170a2faf | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
b0e14802-6165-4f88-8981-1bf04ed23404 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
b6a78978-5ce7-42d9-9491-5b25b95bcbbd | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
b7fcfa87-ee6a-4340-be13-2d87c63df87b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
ba24abe6-05db-42c8-ac89-e73092c60d76 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2
bdae4cf3-59c7-4b0d-b646-d87e3150b3b8 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
c1555915-83f2-4cd7-a767-425ab9a0e932 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
c3696ce8-4cc0-44db-a49a-6d1d31802eb4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
c811748c-f3ed-4bca-8035-d2a263064ae5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
cd3c3e79-6e00-455a-b805-7faa5e05d82e | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d0552240-ad2d-41aa-99f2-ebc66d5e9463 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d3609e1b-52f4-4f31-8fbe-b3ffbeb041c8 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d3a05c5c-8937-4030-a809-4a34d80200e4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d4740d9c-b482-466c-b338-3e22518f4a89 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
dce02cab-2f64-464c-8787-ca752d541d8d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
e20d97f5-d335-4f0f-a319-b09e13407e07 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
e39e9540-d75b-42a3-8022-d79d6285dc98 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
eb8b3260-d6a5-4952-8cca-4c2a71e0f260 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
ebd4b750-cf76-43b6-a3eb-4b31c0f8a773 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
ec5dc4ac-6a07-41b9-b61e-dad2c5c9e780 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
f22e9fb5-b5d8-443c-ae18-be0d32f6fef7 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
f349b4b2-af6f-4d17-b93c-013a76e9ac07 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
fb46d411-5cc4-4e79-804f-728d4650d58b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
0e740a7b-7d29-43cf-a0cc-eaa21602b720 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
1117d1f1-fe70-409c-83e0-ec926de681d3 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
14532269-d714-4010-bbcd-652cd9ae26d6 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
15e24b26-d177-4193-94ee-ad0e83155867 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
1cefd6ff-8a39-4ba8-8f0d-813c43084c99 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
1ea289ed-b6a2-4f3e-88f4-b140ea1499fe | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
22b8e8d0-a4de-462f-a08f-6e54f5c46c1f | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
25e1cf66-bd0b-4bbb-b68e-24d3353cca6f | Pole | 2 | Distribution | 2020-09-20 | 2021-09-20 | Level 2 |  | 2022-03-08 | 2023-03-08 |  | Required to Re-inspect a subset of assets
2c99cbf7-7d26-411c-8af6-23b9e1158ebd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
3453d0d2-a655-49fb-9ad8-1810b75432ea | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
387cc8e2-2d3d-49f9-8841-99d9abb071d9 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
46101885-50f2-45f8-b1e7-a692a1a9b0f8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
4ba63b2f-5b79-4c38-8a14-fc6435dce7bd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
545fd7fd-e788-4d67-8c3c-2ef4dce14e1f | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
54c8cf7f-92b9-4e44-b7e8-f70dd7ccce8b | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
5a114bab-ad6e-40c0-a4ea-80e597da421e | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
64760a9a-780e-4e14-a944-fc8fb47f47b7 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
6503d9fa-63fb-4afe-a3f4-9495d5be7de3 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
693a1f56-5104-42de-a179-77cfc44456fd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
71e617a2-e939-4499-85f5-9e7210963caf | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
73a70c41-d838-428c-b6b9-538bbf7b931c | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
82174148-0a5f-4b46-9191-5bb750438556 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2022-04-15 | 2027-04-14 |  | Required to Re-inspect a subset of assets
a24eb6f6-4d2e-4703-9556-06a97fa67214 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
aa8edd9c-7ee6-4212-9687-9bd38fabceea | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
ab03f6ad-35b0-4485-8bf0-efd1aca3b486 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
b932e7be-4127-4738-b0a8-d3d1f11b1af2 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
b9f92c26-c72f-4180-ad0a-89742a7969e8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
c2c9d79b-7d35-4742-939b-0373d22e0fc9 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
c41c3d44-552f-4c17-970e-39011f68caba | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
d17f322d-79ca-484e-92d4-de702ba0fdc6 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
d8a60def-06c9-4b60-8bc7-28f66a835e5d | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
de17cbb0-da00-46f3-9f93-90d2d5c86ed8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
e04b4164-2aba-44a5-ae76-1a7a99b0ca8e | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
e09a7e9d-ac55-4c4e-a5bd-0e14245c4336 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
e15d998b-37fe-4e12-9cd7-70b3452e2117 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
fc9763da-5feb-4619-8e0a-5bbef2f0a77c | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
09e2028b-dd39-45e8-bb14-beeb43dba495 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
145c0dc1-f6aa-46db-ba66-1ea1a6742fd4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
1549aa84-9ee2-4fd9-9959-ade7a3058c93 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
2bd3bd95-1be1-4b54-a30b-5d48625870a4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
5c7bb953-d9c2-49e9-b1ea-ede13ebc527e | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
62b08ee9-a921-4a59-b178-59b0f9970b6f | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
6d8a5646-6a38-4ee9-b4d8-ffce1f8eeabf | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
8baf0207-8837-4fb0-8337-ef289fd5eba4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
967b71e5-a348-4d23-b76c-7ff17325523b | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
ab061379-8e68-42ff-89e2-09a998aab300 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
b00122b0-d174-4c6a-96ff-347b2d312b57 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
c00852cf-094a-4399-8968-2ff75599306a | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
c1a0303f-de68-4cca-b4fe-a1950f6f6cb8 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
c34be656-3015-4e8a-b974-b59edbd8ce1e | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
c7965465-c705-46ff-9cf2-ca6000a6f705 | Pole | 2 | Distribution | 2020-09-21 | 2021-09-21 | Level 2 |  | 2022-03-01 | 2023-03-01 |  | Required to Re-inspect a subset of assets
d2e96ea3-ab61-40ac-acdd-a06e0b5a4be5 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
0372d406-43ea-4d8b-916e-baa6b619a8d9 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
0b1fc06e-bb35-4fa0-94a6-407136e6821d | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
16cb6f18-110e-47bf-bb21-2b49c863a980 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
315893bc-8bf0-4169-9044-290fd14510ce | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
6d15505f-1c03-4442-87c5-e139ca184132 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
6e91be45-74f8-4cee-a80d-b729442d818f | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
83c76b50-c5e2-4c44-bc14-26eae6d45f25 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
d9b8e866-edc7-4fcf-8651-68ded02b80f2 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
f4622cbb-471d-4d00-9b02-87afe135a3e3 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
05dad096-127c-4b2d-b6eb-d4d799332779 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
183f7684-fa6d-4cee-bbfe-0815333cf09f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
19e3ca7b-42df-445f-ad31-1cd727a30780 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
1dae268c-2c82-4f9d-b775-e99d9d9981df | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
26985cbf-f6df-47d7-bd12-5a9ced24f730 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
286b3b1e-002b-4299-9b00-12b89fae14ed | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
2a6febca-9650-4a16-b64c-981622ad12b3 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
310c89e6-3d96-4994-9742-19fd1f80d49d | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
40540f1a-ba90-415b-b62d-db6f03f4bcce | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
48c688de-4ac3-44e0-8eae-2028eaed4c5f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
50ecd8b8-a11e-46d1-969c-127156a96abe | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
6008c623-14f8-411f-baba-30f99e57e83f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
69a6b781-5323-4678-8dce-296e4b8990a7 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
6a208164-8b29-4834-ba67-66f354dc6b2f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
725fcadf-d587-4187-8419-613508848c3e | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
75ac842b-131f-41aa-ac05-362e5fcb22e6 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
7b879260-8240-42ff-a819-d8237f735781 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
88bf9e5b-712f-45d1-a757-18de6e8a9333 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
899b4e46-63ff-4e11-8240-3528774fa842 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
8eac32a1-3e4f-448a-8c52-9391a0b96aa7 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
90f9aff7-b2ef-404b-9b07-99a10d537107 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
9bde3b8e-b7a3-4337-82fe-645cfb8fdd7d | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
9cd04e7c-24b0-4d52-b0da-4de823c37a05 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
b336bae1-4de4-42f8-8342-a75ac26107bd | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
c9b77d53-1992-4902-b026-1fa5f36365c1 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
cac0e953-93eb-4e2b-b842-b7beb4e7fe30 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
d3e2c850-037d-4970-8e4e-2b76531ce32c | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
d466c7a7-3f54-423c-82f3-e7e454879774 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
f1dfba25-bb98-4aaa-bafa-22ab77ddf652 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
fcca4c0c-971f-4d03-a6af-d299317a3ba2 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
0113187d-969a-487c-8333-f82ec1ab6ae9 | Pole | 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
0904baa1-e4c8-4efd-bab8-68769a47e986 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
09d68a3f-e4ac-4b24-b4c6-b224611c70f8 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
11b6d47c-3ee6-4cda-8a23-64c1336cacf3 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
1832dc12-5ef5-49b7-a70f-a4e2725c6458 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
1d280027-04f6-47e4-80ac-48afe986e84f | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
1d4d29e3-ca10-4501-8219-0ce24e712dae | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
26c29f7a-590f-44ca-8869-c2c4b7b333e5 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
2959c08b-2d61-4dd4-b84a-c430ced94c0e | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
396105ff-5c6f-4ff2-b723-4c0aa1a2be6b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
408da581-b792-48ab-a4f3-51d0de8a106b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
4470a632-25d9-4396-a577-3a6886bf6ff0 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
45718d8b-01e1-4314-8080-fe3183110c39 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
494375ba-3253-4c92-b4ce-4f13bfa61d7a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
4b87c4eb-d3d3-4a08-a3f3-001395047364 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
660d0384-5198-4e6a-8736-390cfff3e0ed | Pole | 0 | Distribution | 2020-09-24 | 2021-09-24 | Level 2
6f2509b5-adf1-4d7d-b0c2-135b63ff7362 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
704185da-3454-4160-989e-9fd85c65cac9 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
71ee2e78-4e14-4a2c-9dfb-96c1442394f5 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
7b2ef357-f3a4-483f-8008-1cd84f5b3a0a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
863ee853-cd25-431c-8853-a1cd779a38d8 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
8ed4feb7-2f41-40d8-9025-568fb267ac03 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
963ea595-4ef4-4972-8113-5d0fe3facd00 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
97b4e740-f17f-48db-ba20-487b5984f0a6 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
a67a9c0a-fb0b-4c9f-ba60-057dfbe2e558 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
a68f1ce3-f612-4e9b-adca-504d667a1a3d | Pole | 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
a7317bc6-9766-4721-9b7f-28780f5efcb7 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
ab23d578-c5c6-4120-bb19-f10d6db7071a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
ada8989f-4023-4937-bc58-09c6f4260e01 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
b2569ea7-8267-40f5-bca5-841c9c6ddb77 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
b415ca9a-f0eb-4100-b34e-163e1f51c9c9 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
b84f22a9-7b01-4b60-aabe-4774a6724136 | Pole | 0 | Distribution | 2020-09-24 | 2021-09-24 | Level 2
b957c8dc-03aa-4a21-9c89-65b3c3948462 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
cb5a1e7f-bd7f-4f71-a2bd-c0f2d2b84c54 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
d6e906d6-5694-4e6c-9401-5ff6bd6bda82 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
d84483d6-f80e-41b4-be8b-d718c0956194 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
dc170a4d-fb8b-42fd-9283-5f9b4fe35c83 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
edc52a12-a097-4c4f-8b40-d08bbf974a6b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
f03bc64f-e118-4f33-9bc8-1d5c5ae7eb65 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
f56bacf5-2d6b-44c5-a39a-7da8d192985e | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
f86916e6-3703-48d9-93fe-f3aa0b357368 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
fbea8a5c-92f2-4a5d-a3d7-97eaaa819d7b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
12b3c0a0-1434-4a0d-9f64-f79b23cad13b | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
234b87d0-7609-4032-856c-432078f2e060 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
3048addc-d28a-48b6-991a-5eadd5fd03b7 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
33026ba8-873d-4ec1-b7dd-00a50d49fbd8 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
453ac828-a001-4bc5-992b-d2e535489cfd | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
583a377f-3d93-472c-84c0-1727816b6837 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
5e6bbac8-4251-4cf8-878f-4938327be4b0 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
63b2eaf6-1c5f-4c86-9fb1-9a2007e4565d | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
63e3eaf1-827b-4499-853f-a9ec0b84e3c8 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
7ee6f158-f093-45e7-897c-28564e0592ce | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
855e5ef6-5b9f-4cbc-a685-611445b321bb | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
88c49d40-5d5e-4730-b4bb-92b017e0d0a4 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
8bbaf5b8-eed4-473c-a4c2-9c4a38c62059 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
97c109dc-80ed-4efc-ae8f-a930752a2d2c | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
adf493ae-9310-4bee-8bc3-6c1ad88258ba | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
b2d8ee65-83c9-41f0-998a-316d649842bf | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
bb10f092-94a3-4482-84bc-724b83061830 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
da2ad61b-7116-4fe9-bf8d-16631e499f5d | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
e8198807-4624-4b13-b2c9-18813a90ea6f | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
ec92a2d0-7117-4ea8-88c3-58125ed00aee | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
f312b6d3-ca7a-49d4-bc2d-b0972f9bd4a5 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
f8e5a2e5-27dc-41eb-81e0-ed47b9664c2b | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
ffa34a39-ef1f-4524-a636-595b49248c0f | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
089f6d02-0269-470b-bf54-6f4f55bd4c69 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
09028e99-5d02-4bed-96a5-90b246972158 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
0f09dd73-6162-4d90-b6e5-e5379e8855dd | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
121c6538-9c22-44d6-8b38-635f4ee35bbe | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
18b49776-fd89-48e8-8c0b-6d1fdc129e18 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
2bec4f63-d4ec-4992-af66-98c7d088240e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
30e72115-8f73-424d-8ecc-79214094cae4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
397b73ca-e508-46eb-9465-7884249d5653 | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2
421dd21d-9307-4272-8c7c-d3e1f73b7d52 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
54516942-f08c-433f-9f28-5c853b4f85d9 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
5cb8d148-fe45-4f79-a200-d18f987aa9da | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
6102cc02-baf7-4511-a4e8-285ac03b9361 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
62f13b10-e755-4c35-b337-ef6026af9916 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
69a415e2-f048-4f07-a80e-7730dba5bc34 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
74f4da9b-1906-4ee1-b31d-42ac1bb04bf4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
919e5b7a-6e5c-4fce-abbc-8338266a90f4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
991e79e1-42d0-461c-ab21-cbff43d1e652 | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
9ef6f2d4-befd-4d2f-bc4e-315154660a62 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
a036e711-0315-4a54-bac3-9b0a629c5e16 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
a7cc73c5-eecd-452d-a877-cedbcd85a55d | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2
c29e85c3-a3bf-477e-8dac-224c4cb3445a | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
c4744b04-54c0-4252-8746-e113b5ec3142 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
c599ca11-c9cc-4b3b-9b0e-3ec7b84ea11e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
d554ed87-db18-43b8-9ac1-02d309f18a41 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
d991737a-6733-4501-8099-57a932b0cfbc | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2
db981d8d-c628-4b01-85db-00da6c133ed1 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
de629e6e-b40b-43d5-9a7a-1f02c116e82e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
df2a27f9-0f81-4a41-9b07-ab59748877ca | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
ea722252-db7e-404e-a49a-3cd4e1da035d | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
ee4096df-31ee-4d06-9a61-f0be8e6b9bf4 | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2
ef5b64ba-f200-43da-8d7b-cfb8d4d0d8d2 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
f18689de-38b8-4474-a6c5-3f927b0e0cff | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
f44551c7-83ae-4559-8f67-ea8339cc5246 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
0822043e-147c-4566-9214-9ab66abbbe1f | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
171dae0b-a1e1-4c1c-9930-83cbf65851a3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
279f3360-6ee1-4438-9260-b6dea217540b | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
2ba2bcfc-60e3-455a-bdd3-3051b79fd991 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
2f5c0bb0-1200-406e-a1cb-3bcef4c7a133 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
3a5b00d9-84c5-408a-b2d2-176951d3dee3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
3bb8cfcf-1147-47a1-bb53-747e552dcbca | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
480c2983-675a-41c6-8f4d-7a6e449464a2 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
49d3a1ce-fb6b-4e95-b78a-cabeda51a5f0 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
4fbe3f1c-1637-4f9d-8445-4b54b34c90db | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
59accfff-a725-4fe4-873e-d1b51220c0fa | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
5c6ab85f-c7d6-488f-bbf0-fa2a7d6aa742 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
6752692a-257c-4fb8-8c24-82ec0b574362 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
70823a40-febe-4108-8ad9-70d057ce54d9 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
71446ff4-9909-4f67-b0d9-d8865feba4a9 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
78122c3c-e98d-4114-8391-152c3079ccea | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
8a6fdd68-4c2e-4d42-9a43-1f56bde74c66 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
8dcef529-717f-4101-afb2-09d6a7cfcb27 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
aa8e7ff1-c981-49e2-97eb-4e2577832c45 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
aad5284f-cf48-4794-a4da-2592de82e896 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
ac42d891-175e-4b53-824b-afdc9ba92ff7 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
b4467d20-79ec-4adf-a2b9-7766baa4b143 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
be28be52-f91f-4fea-b065-be3ae65a7ba3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
c8b7d356-301c-43dd-aa43-95ef651f88d6 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
cd19da15-d082-4204-9b1d-35b3a4d24fc6 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
eef020f1-e468-4325-a884-d2586f2c1dc3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
f8316d8a-d2de-4fed-82cc-31ced95672a1 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
05c645a9-cd34-4c5f-b0bb-a00358e1f839 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
08112856-2b9d-4f15-a1c0-8b39d1bb64ee | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
08fe1380-7898-442a-8092-0642125d5e61 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
24b66aa1-e886-4701-bd93-f52c2188c94e | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
36ec1802-a5b0-4fcc-a0cc-e7ac3781cf33 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
3bf898ac-e17e-4a42-a0de-6dd4c2b373f2 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
3f357e24-71d9-4c8c-a25b-09b8b09f7499 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
409a1c2b-44ab-4c49-a6dc-08e5305f3b50 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
464a53fb-0379-4377-a9ba-2124d4b51c1c | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
6a01a572-5309-4914-93d6-db110c29b828 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
70a02f91-77e8-416b-90c8-37f28f13f796 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
783d18df-429c-42cf-bfda-60aa13b6455a | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
8bea36d5-da4e-42a0-8afc-4ff8dd8dd1f0 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
8ed7a970-5ab6-47e2-bce3-59bf35b8c592 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
9111d2f5-b08b-410b-8aa2-fbf3068e7107 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
937bceaa-08e0-47a3-9008-73ec1e532314 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
a6e72fd3-7687-4b37-88fd-607cf2eb3de2 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
aff9bcb2-33fc-4acd-8893-e768bb1398dc | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
b240550f-360f-47c9-bcfa-7c6639d619e4 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
c4794c18-ff10-4f09-8903-663680283b1c | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
ce44f22d-89fb-452c-b5e3-4cdae58eb01a | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
d15114f8-3dfd-4ad3-bcdf-d93f58ab86ca | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
d48e861f-26bf-48ee-a4b5-e77f74542ca6 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
ff3ce20a-11c1-493c-9066-67568265e51c | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
0c05e7be-3d32-4e62-bfb2-a81a1d2c3991 | Pole | 0 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
2db263e1-28d3-4ecb-8bd7-780d6408c6d2 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
a78d19da-acfd-4a33-b7c6-dc81e657c7c4 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
de3247ce-f59a-4b1d-ac4f-2b9c288080fc | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
e36a2c59-9285-4e5b-9b41-916363ade87f | Pole | 0 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
0202af24-c134-487b-93f8-d56b5b5dff89 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
0e8605ca-cf6e-4082-9e78-dc3b6ed24db3 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
0f469cfe-371a-4e0f-b808-0eaae1d8f827 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
1700ede0-151f-4658-a34e-6e643442fb50 | Pole | 0 | Distribution | 2020-10-24 | 2021-10-24 | Level 2
23624916-6017-4757-8054-d2a71d0d1e7d | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
23921928-dd79-4922-828e-4525249c2020 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
24897567-a0a8-4937-89c1-3016690d14b2 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
30c51d66-49c2-4dd9-9151-8f4764f4ac25 | Pole | 2 | Distribution | 2020-10-24 | 2021-10-24 | Level 2
576da134-1eab-4915-905d-2ee96edcd332 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
5c28d58c-64ff-457b-a3af-be2a874f5acc | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
7d75c011-f9e8-460f-b2dd-782b7ab47cb7 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
7d8c80a0-cf74-4ab2-8108-1fbd84f60766 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
8b3644d2-6861-496a-8cc9-c17c552e9baf | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
ab75932b-2c78-43d1-902b-3cbf6c81e4a7 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
b75ad0ca-e0a0-469f-b3d5-f729f419cee1 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
bc5e5133-99a4-4e44-b7c4-6223673422eb | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
c66cebb7-58b5-460b-86ad-1da8d1f743c7 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
f4685233-5388-4328-8e88-53d5e2f87c01 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
045821c8-1666-49a5-a4bf-e757974e75ae | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
0fd03e2b-6cfc-4c28-82b7-04dafb7755fb | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
259f747d-cab9-450d-a73c-bc97decc887f | Pole | 2 | Distribution | 2020-10-31 | 2021-10-31 | Level 2
2d05026f-d6f7-424e-be09-0a53a38b5fbe | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
31efd5c0-35aa-432b-ba18-725735bb42af | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
35da62bb-89f0-4555-8c23-d6e82a91cd79 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
3b8c4552-f17b-417f-8b5e-b5134f299bd7 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
4a22d034-af5a-484a-80d0-d56cab2fc52a | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
6328891d-e2d5-47e8-9fce-5ad49d6939a9 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
68b79d80-623b-415a-bb8f-e39003edfc9e | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
7451306b-464f-451e-a308-b8a879e2f521 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
95ddb1f1-d32d-4242-8aa4-4fe7898c177e | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
97da06a5-91c6-4200-99a3-80429c15eb49 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
2ac66b2f-e929-4ae6-a6ae-2fcdb3a43704 | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
4cbd9b67-e042-4eb6-acad-60eebb0ff06d | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
72f060b6-aee7-4276-97e9-17a602834e7d | Pole | 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
7f2ff55a-d4b4-467c-8390-8cde4f3d9ad9 | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
b58728be-315c-4702-b333-4650a1252bd1 | Pole | 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
fa3a6a3f-da62-49f4-8cb0-b8cffda0ee3e | Pole | 0 | Distribution | 2020-11-02 | 2021-11-02 | Level 2
fa93d64e-e449-40b9-a04c-47c9e3a5d44a | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
13e66b18-4646-4c68-ba09-2ecfbeea5295 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
16c4fbfc-1b2d-4e48-9411-33aa38fd24fe | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
18b83043-c444-4081-92e3-17f2e0fcc1ce | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
242938d9-ea14-48f9-a871-4b0fe2c56ce1 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
30188ccc-6c02-42a6-9593-d4bfab541819 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
3f0821eb-0661-41e1-beb0-ab8f2328c4b3 | Pole | 2 | Distribution | 2020-11-03 | 2021-11-03 | Level 2
5aa1f991-42e3-49f9-a448-314cacfe0558 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
6fa3379f-28d8-47f3-9075-5dcee0021350 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
70d06477-1cdf-4e60-a521-7aaa6ae06aa6 | Pole | 2 | Distribution | 2020-11-03 | 2021-11-03 | Level 2 |  | 2021-06-02 | 2022-06-02 |  | Required to Re-inspect a subset of assets
73c7aa1d-f3d3-4858-b5a4-7a30e63398cf | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
857011e7-17e7-4989-b5f7-d8855b094072 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
8a7c6375-a2f8-47f1-b34e-fbf98195de7d | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
9e1c0331-0913-481a-b7f0-c3e55090b069 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
fc508bcb-835e-47fb-98fd-b217a0253225 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
fd7a2ddb-6dbe-478a-bfbe-09e4977c6baa | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
10a46bdc-ff45-4cfb-b382-d32b53018fa3 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
36c24442-95a7-46d7-b483-e43348955130 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
37e13b96-c9a0-4a56-b9cd-ca210701994d | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
3fa3edb9-0223-4c2f-bf5c-93a4d1912192 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
4006a461-8e7b-436a-9f94-3b80ffb7368d | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
41c301ca-f8da-4262-a899-f0e928c5c567 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
52a264de-d18c-4886-b22e-9e9bdbb46bf3 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
6cdb0dd6-58bb-4a1b-879e-c8c92d1f03b9 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
74da15fb-1dd5-4e5a-b57b-6230b4e7212b | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
8203fb0f-5e11-48ba-959b-050786096a80 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
89706162-b9c4-4b79-b1b8-3a5769d6ca25 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
a2870148-6a38-491c-a2b3-c69849e44dfd | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
af45b8e6-2d8b-420a-ac23-d86959b0f453 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
c67c4188-1292-440e-bd6a-91d3a40eeeb1 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
c83f277d-75e3-47af-b27c-1a482079727d | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
d2a06795-a4b5-4e0e-99e1-f6ba8276f609 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
05abd4a0-3ad4-4c26-9ab6-96c44e02f66d | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
2a012593-ddf7-4030-b998-885c1dea755d | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
30714bc3-8a87-4d0e-914a-6efa49c4adc0 | Pole | 2 | Distribution | 2020-12-14 | 2021-12-14 | Level 2
51ed5513-539c-43e4-978d-a60c01ada391 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
6f2768e7-417e-436d-a182-1bede09d23b1 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
a6f42990-a933-4e30-93da-5bbe8b784519 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
a757e3f2-eeab-4dd3-b4d1-975da11a09a9 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
c8213d31-66e3-4e5e-9621-c7d7695d96e2 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
cd5019ab-cb16-4734-bbdd-2b9627301993 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
ce355eb1-8741-4b1e-aa45-4559704fbef4 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
f05649f1-0061-4aa5-a97f-37b282cfe320 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
cc79afd9-4068-483f-b32b-60ca551e2070 | Pole | 2 | Distribution | 2020-12-16 | 2025-12-15 | Level 3
d311405d-07ff-4d02-a01a-9aeafdd5e2ee | Pole | 2 | Distribution | 2020-12-16 | 2025-12-15 | Level 3
059cd3f8-3f05-4f08-8ac0-2007b0349c85 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
1dfba368-0f8b-4bc7-9ea6-13bef4ed3455 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
3d7daa0b-97c7-4848-b2f3-7c1161854d38 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
42beeeb4-6d9f-45a3-8787-c8088dbace9d | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
7177f772-c256-47e3-be0c-f0e099f1facb | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
dcd9d11c-fca7-4ebc-b570-4d34ef118141 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
e01786a2-1cbf-4fe9-a8a6-882b6f59dba2 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
1132b68c-088b-41ba-a207-4b380e802cbd | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
153031d3-51ca-4179-afb8-f4e0c2377643 | Pole | 2 | Distribution | 2020-12-18 | 2021-12-18 | Level 2
31e90cb5-ce05-431d-92da-dce023a6746f | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
330852cd-9aae-48df-943e-96a15c57a544 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
638d596e-8576-4ba0-876d-6c5e126ca05b | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
6bbfbf2e-0990-432c-9763-3453ed37c7ed | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
9deeeaf6-b96b-42bb-ad8d-0556629dcd01 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
a21b8b30-d55d-471e-9127-7b6faed0a8f8 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
d01164f6-447f-4225-b969-e271db983325 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
d0de9407-1752-4628-a809-8de834351d41 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
21cf93c0-8456-4c78-8f2f-da402b654f02 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
8cf29a3a-1bcb-45d2-80e1-b792ad8fc960 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
a73fee10-0e9d-47ba-937a-3f9687900e87 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
be3a6610-8ad3-4ae2-9c39-2372d418b8eb | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
e7620f4c-5dde-4833-9dc3-0f86ba11b22d | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
3a34d26c-1b83-488e-b0db-cf3fcdcec3bf | Pole | 2 | Distribution | 2021-04-28 | 2026-04-27 | Level 3
0c88dec1-27d0-44a2-9cac-edc4127bf2d1 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
18df15b7-dbcb-4eca-84d1-2be331080052 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
1e9d1d0a-bb27-469e-b595-5ff300ff273a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
22f64a95-b562-44aa-9537-65f936ce9654 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
2a07577f-b3f4-4ce8-ae72-5d1ad47185d9 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
35ce2f0d-a464-4c34-b1e8-086b90711db3 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
3ffb3f8e-f0c3-4551-907e-66e478986f1a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
7809daac-a066-4b4c-80a6-50fef4685c4f | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
af57562b-db22-48aa-9b36-d89583ac5f7e | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
bec5e9e1-c8c5-46a8-96b7-ca73a130722b | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
e30160df-4c83-49c6-9980-367734f7c1fe | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
e7bafe57-13cd-45e5-aba3-70bc50025290 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
f5292a05-5d6f-4fd4-b118-08a7fc08a5ac | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
fb58cdeb-97b8-478c-9abd-e449ac77695a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
0061582a-773f-43b5-8863-245bc0d08fa2 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
18b08b8c-1201-4f08-a90c-d91cab8251f1 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
46c6109a-3376-435a-85fb-202def1b4017 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
5129bbb2-6cf7-4d34-aa5a-3b3795c0b3ce | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
8e6b4499-3622-4999-a502-77eb608cd385 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
94a68f8e-9954-4fea-a59d-acb8a0b712fb | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
a829abaf-bbb8-4fe5-9c0e-f80fe4af51b6 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
a91e7fd3-36a4-4083-857a-ad2a76aad36f | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
b2b532f3-0553-447e-a66d-3b730849b277 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
ba3c37c4-5184-4bab-8106-de6da6799464 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
bb7d72a0-99f9-4841-b25c-90e8fd0e33f2 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
bf71822f-1fe7-4f1c-beb4-3cd0f71b0a31 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
01367fc4-8fc5-47d1-9109-edf3e1a5e4e4 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
0f52bc9a-dedb-480d-9a2f-8be6e92238d4 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
2921d876-d683-4510-ae5b-fbab0913a353 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
c06e0d38-1814-494a-b657-b2e5dfaf63db | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
7ebd0501-4c69-46c3-a9b3-fc7c3005632f | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3
b32a9137-cbb3-44ff-a45e-560182f9885a | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3
fb47b541-12d0-41ad-a428-5f7fc375958b | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3
296bef50-d0da-4c12-b265-17e221248a61 | Pole | 2 | Distribution | 2021-05-05 | 2026-05-04 | Level 3
37056221-fe6c-4de8-b617-a94feca8a471 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
4f1e2adf-520a-47ab-91f4-ed1235d65e0f | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
b36ffc38-4d5e-4250-a769-c9e388fec444 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
c2c4fba6-8be8-4156-9ceb-38c84210ac45 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
18a40d05-90fd-445f-819c-db748d984211 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
49ab3288-7640-48fe-a3ca-b178f23ac28b | Pole | 2 | Distribution | 2021-06-03 | 2022-06-03 | Level 2
5ab2c315-aff3-4fc1-af2b-b6ebd77be984 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
7c56fffb-b9fe-4224-9fbf-f1c6a93c2bb8 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
d92a770c-1c52-415f-b5f0-faca8fc6011f | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
126788a7-aa86-4ec6-95a8-5380489b1b7c | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
7e65d6e0-8672-4b10-a030-e0a0a6740819 | Pole | 2 | Distribution | 2021-06-04 | 2022-06-04 | Level 2
8c3a30b8-c7e5-4e1f-b099-b21d51181055 | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
8fdc8965-49d7-4753-bc91-051ed7b7cd59 | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
b3fe46b7-8243-43b2-83f8-8c761aeb50d3 | Pole | 2 | Distribution | 2021-06-04 | 2022-06-04 | Level 2
cc953013-ddf2-4b47-b420-359eb93f1ffc | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
63975c28-5e39-4be5-9e5a-366944612499 | Pole | 2 | Distribution | 2021-06-14 | 2026-06-13 | Level 3
05fa339a-1700-4f68-87e0-aab5efa1b46f | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
ba196846-799d-4408-ad22-d2bbc1452d0a | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
c5a76494-d8de-4329-b5fc-812a5fd7d9dc | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
d779e54a-a832-447f-b43e-c84d7b64f4aa | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
e6df7adf-b39b-4a70-a115-5e85cea4503d | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
2ed40ae8-7ecb-4bc3-af77-9ab8c0527856 | Pole | 2 | Distribution | 2021-06-21 | 2022-06-21 | Level 2
b8b41498-3a32-45a6-acea-dab119d13be2 | Pole | 2 | Distribution | 2021-06-21 | 2022-06-21 | Level 2
5ea583c9-58b8-4b65-84c7-4592c200aa38 | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
839e7ee8-7c40-4c80-9f50-87d0160630ea | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
8c12109f-5e1c-4929-83ef-0326996a47d5 | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
cb078fce-4181-4170-97d2-3d28a6c8a8ef | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
2d0d5ff1-e53c-49b7-91a6-fa1a7d1a07cd | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
6ce82829-710b-4ec7-813d-a72254e2fd3a | Pole | 2 | Distribution | 2021-06-24 | 2022-06-24 | Level 2
7618aadf-07d7-4222-a267-f7f7d9285122 | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
88170c15-148b-49b1-9483-32f69fb49d71 | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
fc642943-4c43-4530-9e1c-3507c790d03b | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
0e4e6094-7cc0-4cd4-8c93-c623e394cfd3 | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3
14ee7c33-3957-46b1-8042-10df52c595c2 | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3
5b7c59f5-2241-4d5a-a61f-44619dc28cea | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3
1c3d0e1c-ba90-461d-b685-dce35d0cef47 | Pole | 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3
af972b85-ef7e-4fab-b62d-63e311958fa5 | Pole | 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3
14219f68-abc9-47d6-9c31-f787b6450796 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3
fcf297d2-10a7-4bb0-977e-a28aa527aa50 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3
34e3cfc8-e4d8-4bb8-8f9b-d73583d99c8d | Pole | 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3
c124d0af-8ed4-47b6-a135-dcf5e92c1360 | Pole | 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3
38b45260-c054-41ff-b95a-4f5841ef6436 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
3c09ec68-ea4f-405a-a972-25afcdd34695 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
5193025a-5b67-4cc4-8604-8e93fc8e2d81 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
9ad01a60-27ea-4f2d-9b84-f99bc5076aca | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2022-10-19 | Level 2
af7fac7a-e34e-4471-94e0-851510639e15 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
c3e666c3-5df2-4e96-b060-6774d1cd4019 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
c7590ca7-0f57-463e-8661-044b781c6280 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
ecb03a07-2432-4e2c-a9f8-30195c936947 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
0f48869a-73cd-4dd0-a399-20e4da546ec1 | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
18e79d39-bc5c-4ba1-96d7-51eac8aff3d4 | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
700098f9-95c1-4d46-bb5b-a0441f4ab144 | Subsurface Transformer | 2 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
c8f7c641-dc69-428d-aa03-7d10624ad54d | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
042e8926-2c53-44bd-b440-5088822e1078 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
16d604cb-d4b6-4555-97a7-f540f28222e2 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
178690c6-20b4-4625-b0d2-ad7bb32b23f3 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
208033da-57b1-4f97-8a6d-4f91d396e108 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
282a7f03-51f0-4639-b6a4-fb5f21735e46 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
34d38710-c291-423f-bc5a-053b2f4338a4 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
3510d1f5-b55c-4026-a699-48009589fd8c | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
3607a411-9506-4dd9-bde5-6d417a28f4a0 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
3a9dcaf6-0d0f-4631-849c-6da5b3fd2ad4 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
4ae352cf-3849-433b-850d-bf137ac3614f | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
5419f188-597b-4f87-ac2a-f85ca3a0088e | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
54c833be-8619-4ee5-9db7-b0d17d2b5134 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2022-10-21 | Level 2
59c289e0-f8e6-4231-94cf-a84fb953f7d4 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
69b5b637-59f6-482d-944e-2f451b5b0397 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
75ea10ca-c63c-4e90-8a6b-97d7fb348fab | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
7ed4bb36-60ba-423d-995c-cea3c157ab56 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
813bcc20-84da-4843-b1fc-2a810be994ec | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
a09553e3-7e4a-480e-837a-0161a44610c7 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
b7b8c16d-993d-44d6-85ca-5786b2d08d54 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
dfbf6508-3bc0-42d2-8ae7-1bcdab2f7041 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e144c5c7-892b-4b33-94db-1c202faaefee | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e3a8ee9e-1e0f-4bfe-b2e3-4587330ca0d2 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e6ec1743-2d0c-4896-92ab-9b58d88d6b77 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e9026147-f9d7-44a6-910e-71e0489624aa | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
f6f76c88-b3ea-48e9-9aba-271fdbdd66b4 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
067e54ae-6f41-4593-8219-f4b6caefbc14 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
168468f5-1a76-4702-a32c-68e40c8d4997 | Padmount Transformer | 2 | Distribution | 2021-10-22 | 2022-10-22 | Level 2
26ee2dea-6b75-4afe-8159-a40882cf5d0b | Vault/Box | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
2f502134-ee12-46db-b322-bd84040b8394 | Subsurface Transformer | 0 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
59dcf11c-5afa-4e0f-b760-1f9f74e4ee29 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
64125ed6-bf79-4bd5-b24b-cfae85f50f67 | Vault/Box | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
6f28aa38-21b4-4d1c-8e29-1f09c4daf840 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
7da367c6-0a7d-4273-975f-8fd3299f27b3 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
948a5d2d-164b-4e9b-85a9-87574ea00e73 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
c03ddda7-3e08-4c55-b886-6f6d4d377ee5 | Padmount Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
ec44ca4f-a2ad-4dd4-83b0-03f3766314aa | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
f3243f21-b472-48aa-b895-5759dc0954e3 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
f9c08220-3b95-456c-8660-2b98d8ac2897 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
0223c440-79de-4cc1-b6f3-3b99fbb4e611 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2
15eed4d2-cd9d-482d-98db-6f45194f200a | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2
698e8fb3-e5b1-42f4-95fc-055bb01c1e24 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
896c3455-6340-4bea-ba2c-3a2ebd063f10 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
9593a78c-fcaa-4dfd-be17-45943eb14fb0 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
baab2a27-c835-42bf-a131-b0013222f5cb | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2
f833ecdf-bd46-4695-82f5-8a499459153b | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
09525167-8322-4e8a-88b5-ad0c01ed99a7 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
1226f38f-6372-4b38-8ebf-db2acc652f06 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
173bbc1f-e2dd-49a0-9434-f4ff8d4befc5 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
257cace0-d5f5-4006-9363-9058a66e4ceb | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
2a653d8b-0cb8-4cc2-a9d0-0b7e137608ce | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
37aa2543-c5a9-4355-94de-15de40e25801 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
4edde5ec-f06a-4d0d-a9e3-2ad0a2a16f9f | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
5ea41cff-1efb-4996-827b-ec22ec35b5ec | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
6dd0c98a-e008-4d06-96b7-10ccc7cd1f82 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
6df7862d-1a18-4493-8d17-5070bbd3807a | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
731c9e68-6eaf-4025-83ec-c99eea7335fe | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
8dc31024-acc9-43c3-be5a-581331739be3 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
9d9bcdd6-28f2-43a1-a9ed-07e9161713d6 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
a28afb3c-6a47-4909-8bcb-d96e2a66fba6 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
b557800e-b205-4891-92b2-d173ce3c1667 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
b97cc0c4-568a-4b1b-83cb-681dffc0ccc6 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
d0335cd1-ed87-4caf-b00a-b8edbb0f7ce5 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
d186e017-9afb-4ddb-8520-c7cbcdf14db2 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
d2b24d0b-51f5-4e33-ab76-5c8916cda60f | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
f3f04387-269e-4300-8002-5ab516fc4df7 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
fecd6ad9-8d2a-45fc-9d21-1e135817ab51 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
2daa0614-4553-43b3-9a31-051a0e16b041 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
67eacf97-c032-4b3d-a1bd-be19fb824b78 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
791e201f-de2a-4d61-9a7c-8117d626cef5 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
7cfdedad-72e3-449c-8de1-0af0106c75e2 | Padmount Switch | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
a9ae1d94-323b-4985-b0a8-208d43683390 | Padmount Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
a9cbf5a1-fb57-4c92-8e76-664dcb70e241 | Padmount Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
b8c207f0-341f-45b2-a5dc-2f565c61c815 | Padmount Switch | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
b9ea6852-7497-44da-8f8b-d77c1b943033 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
1662a1cd-5ceb-49b1-93fc-a780bc658dbf | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
289c8014-190f-47e9-ac2d-755d631fc1a4 | Padmount Switch | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
3a9e766f-4355-48a6-a98c-26413c184e08 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
516d4ecf-2e7f-47ec-8b9e-cb0e6172279a | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
60e1dc24-1694-476a-8035-f63d08c7a5de | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
6c746ba8-da7e-4ad8-8790-70a1250c36d4 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
705954ad-496e-4cc0-b6c7-10e0d1e5534f | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
b95c5c5b-4dfb-4aa2-8956-8bcabdd6a8b5 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
c76a61c9-f3f7-47dd-9a91-409abc408bb0 | Padmount Transformer | 3 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
cae5cd38-c6c4-455d-8ecf-babbbe45d76b | Padmount Switch | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
d3de8ebe-423f-4820-9355-20ab83160314 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
d9bd5f86-2789-47d1-95f2-8ef4e7546ecd | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
ddcb61f1-817e-4f30-a5eb-1399cdeb7f15 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
def94314-7bf1-4d50-a301-c1377311a40a | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
ea278f9c-df96-4c88-90ab-79fd5f703f23 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
1f47a02a-b72a-4272-8e35-70c46eca8481 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
2194b38e-ecc9-42e7-ba81-98882a6802c5 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
222913d1-64b2-4570-b54a-c92d197894b9 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
263d957b-b8ec-4459-99d4-708c8f4cb8e5 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
30e9ec4f-8a1b-4d9e-8532-c854b4e6b4bd | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
3759326a-470d-4c7d-8311-25a0e44e0f4e | Million riser with bridge switches | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
576f7b80-f2d2-4731-be05-70a5d29b13e9 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
667e43bc-507a-4413-8557-353f4a4898d3 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
687bf21f-b12c-48bf-9870-c8de1c197818 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
69d7491f-b958-4eb5-9cd1-5435458de94c | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
6f123e8a-3cb2-41b9-aa62-e23a93ef5b19 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
6f28b315-0e58-4612-ad5a-2a3853b04416 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
85d4614a-6d61-41e3-a7a5-21efa3c79c16 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
860516a4-f107-40dc-8538-e90fa6a756de | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
899bc20c-4cb4-4be1-bf60-bc086ba5793b | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
8a336278-04fd-44fa-9ed4-c5d71dde4123 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
8eb42b9e-511f-4868-89ae-9d12db9fe120 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
9f691f93-53a5-43e5-b44b-baf83c2ef448 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
a06a1ad2-9562-4b09-8f02-4a154d17f877 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
aaf28071-aeea-4c96-99df-6eab44cc2337 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
aeeb16c4-7b48-4227-8f43-0d4eee62ea2c | Other (Describe) | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
b50b99a7-fb00-4311-a1d9-a3f89d7864d6 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | 2021-11-01 | 2026-10-31
b96f3921-513c-4b08-b81b-0f1f58e34371 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
c8cc97f7-4d0f-448c-aebc-cebb7276f32b | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
cc851e0e-8d95-479b-a5a9-3d77768ae1be | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
d6b82dd1-a08b-4b83-82a5-d2bd032df7d2 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
dda5488c-0c0e-422f-bdb9-d392e60854ca | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
df7688d4-8313-4168-b7bf-a87b95666571 | Padmount Transformer | 0 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
e03311d5-420b-422e-a9ab-3d0fc1e77fda | Million dip pole with bridge switches | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
f618206c-89b0-4fc8-8f65-2a1b027669dc | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
f752fed6-7947-407b-aaf2-bdd3a0357ef5 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
08424585-7ba5-4cff-b92e-801dd5235785 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
0d9ba3c0-2cbc-4ac0-888c-67a632acd0e0 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2022-11-02 | Level 2
0fbb8efd-795b-47a9-844a-41c33711be26 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
202306af-3d29-4b76-9fc9-c92977c5c6fc | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
282a8782-68b3-44a6-9c9d-414e0afebc11 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
2a17d956-d1d9-4688-8a05-e6366d70043f | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
2bcfa3c7-e207-4b2a-9fdb-162a328ebb25 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
31326bed-e107-419c-b734-6d38965d99fe | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
34c4977c-6c47-4c0a-98a3-d647a63042a9 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
40754894-3c03-4575-bdae-b16e8eda3e1d | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
49820070-79e5-40a8-bf91-1519dd8ce439 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
64680c52-9914-4c73-b3ee-f6e5768242cb | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
72f9fdde-8e04-415d-aa16-9e37a42065a0 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2022-11-02 | Level 2
7d7a2c81-2e1f-444f-b157-e14dfcb1a344 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
95c44381-ef2c-435b-97ae-f9c7e26f0fd9 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
a01c768e-377a-42fd-9b04-e254799656e7 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
a16e8f1a-4a74-44d7-aac1-cd8b0e3e9a9f | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
a226c54b-8224-45f2-a698-f0c54751d210 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
b355d795-79e3-442c-8cf8-b69dfafbe192 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
bc562ff2-9873-4067-beb1-2f2520203035 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
c118f64b-6213-4764-8ef3-05098fe360cf | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2022-11-02 | Level 2
ea54d99a-af5a-4ee7-b2af-fb88850a308c | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
f2622b7e-b390-479a-ba41-1f805c66265f | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
0889c0ab-af53-4b52-966b-c7966de6c95e | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
23cfefa2-b7ac-4d1d-a846-ea7217718faa | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
2764ddfa-0b63-4c37-8cc2-a6629c2dd847 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
2aac781f-1042-4840-8cf2-cece4975881b | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
2c2b9acc-bc63-4d8c-a8eb-5612c880af46 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
3034fb3c-80d5-46f5-b837-b356ff07d96a | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
3f89810f-aec4-4c11-9464-bba99e81c671 | REGULATOR | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
4cf051ed-03c2-4b86-93ad-d36824c5d1b7 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
62520226-2d13-44b5-98c4-39e513502843 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
627e2ed8-2b7b-4ad5-9592-b2b9b1da2e03 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
64d0c6e2-4180-4485-b091-665f21f54a1d | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
663be561-e47d-4a4a-a947-9a6ed3226a13 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
706064f3-6b86-46b4-a599-35b72f63b403 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
70b2142d-8af5-4574-91a6-0d128404f305 | Regulator | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
93d7140b-c38d-4544-8943-d6f10f81c0d1 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
a0667eed-d8c1-4c75-b815-1d3ec28802f6 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
bebc84c7-06b8-40db-bbe1-f514f12a8092 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
ebfa4c12-246b-49b1-9f0f-3763bc8403ec | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
f7a05631-3d06-42f7-886d-22c6ce62d088 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
f7fb82af-30e1-4070-aced-8e7e8b00fabd | Regulator | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
fb3f036c-8876-42ba-ba67-aed8dbd22c2f | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
1f9260c7-52f3-4899-bb23-d50f0f10e731 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
2dd3e7a8-fdf4-4d1e-8536-f017c5ceb505 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
341f0cc8-8c7f-4c87-8032-1f3a48f11e10 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
4c547298-e4bd-485b-917b-51011cfbd4a1 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
73b7c453-abd5-4af7-9ffc-7b8156c492be | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
8a7c0559-9c60-453e-9fc8-7530b67dce88 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
a0ea73a0-5f94-49b8-a85c-31731e089641 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
a5386803-b15c-4a6f-bf05-638df8393114 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
a75e9ea7-3731-4bac-b931-04e78db08cf7 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
c0f1ca20-bbdf-4aa0-b0c9-1cb02cf1ed0a | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
c3a8e1af-bae3-4e0b-a94a-a90a8b1f5883 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
c5b9339d-41e8-44b3-80bc-90d403e4634c | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
e23e8807-3a89-4db3-8790-9130562e7746 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
e2bb6d47-6f79-4d3c-ab96-0820c511eb40 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
e51f68ea-cec8-4452-a21a-c62a1982412f | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
f889f99b-8348-4eae-9e52-0725d6ac6b52 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
fd0b4574-5ba1-4562-b59f-68fb630ea61c | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
fe41d1c6-0e56-47e9-a73c-3040e69b2502 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
1875650d-24c7-4293-8782-8c6e3824b99f | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
18fcb6ea-fd22-445b-b0b4-e1c64f157c4d | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
227908c1-f50d-4759-8774-8ba2d213e060 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
2792c957-ee85-4f28-bab0-56c2e206c72b | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
27c06025-52ce-4196-b682-3a241787ae85 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
2dd09a9c-c660-4e43-8e11-029d8ae9e48b | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
3fd61d92-6f63-4b37-ba9a-b1b09c5ce596 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
46d022c9-680e-4e20-8f99-55002d0e7284 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
577437d5-0a47-4e9c-a242-6670b40b3cfc | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
66e0e874-4e13-4d2f-a3ec-f2e723fc496e | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
69241977-9715-4fec-ad36-d67f66b5f906 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
6c3a4663-78f2-4816-81b3-95a91e27fb16 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
74c0b6b5-b8d2-40a1-85f9-4c74c64bbdd4 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
7ad44b3b-d63c-4695-a1ef-4f86f9eadee0 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
9affb1e5-9dbb-418c-920a-daeb0018f39e | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
9f401988-789d-4f66-80a9-765293f412af | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
b5057e47-e617-43af-a3cf-91b4802b90e5 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
b9004984-ec78-4876-8754-7a73adee4943 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2021-11-08 | Level 1
bba9a32a-bb17-416c-aa4a-9af80ebfac5f | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
bc0b3005-2782-4a47-92c8-f54a6f26cdb5 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
bed65d66-1f64-4025-9500-e2f2ba549cc3 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
cb93ed30-9033-443e-93f2-3bb708c9b8ea | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
e974d547-3d45-4077-a1ef-ecea5dcef47d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
f36d7db6-0938-472d-b286-e7d76932d14d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
f6c9f6e3-df6c-4084-8b5e-a695bebdf92a | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
f9784fb5-d97f-44e6-aea9-2072689fe04d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
00dc6f15-9045-4a19-93be-ce9de0c68255 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
25f7629f-7d89-48d8-8852-a15c4657cc3f | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
319c29e1-03ea-4d14-8610-01d22d6f36a5 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
38b11b5e-29c8-4185-a777-a39b40fb6229 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2022-11-07 | Level 2
4dbc31d0-dfa0-4bb1-a42f-9f9462341297 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2022-11-07 | Level 2
56359f14-9ac2-4f85-9075-d22b8ecaab76 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
719dbd3b-d751-45e9-87ab-af0d9109e15b | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
90c8650f-41e4-41aa-822c-fcf8ee06143a | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
97e9c61d-d22e-4545-9191-e249545e43e4 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
9a921048-7e6f-4db6-9494-62177420aec9 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
b19740c6-82b3-4456-bc27-4dbc429cd91e | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
bd07ebc9-d428-4687-95c6-9e045b4fadb3 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
c2889f05-4510-4bf6-ab9b-3a4b66be74a3 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
cdf62963-81f4-44bf-a343-2c37b56b2d86 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2022-11-07 | Level 2
d33e239c-4582-4f45-bf1c-f22a3f9c29b5 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
d664a045-7015-4ed1-b912-f92646a4c65b | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
d9d5b7f0-c1a6-493e-b2c6-e022dec25fd8 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
f3353016-ac9f-4637-a0bc-487684cb63de | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
fd2d7187-2411-42ed-81b8-58a4d3d71abb | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
fd37a7ff-ec5c-49d6-b940-190d7817b22f | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
95541ad0-168f-41ca-bcb2-d0b547cfbacc | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3
99265580-7cd9-4c07-b772-80aea4f639d1 | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3
d56b7971-beb4-49a9-8dfc-cc670246da33 | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3
2b8283b7-a2c3-4cfe-8eee-12277827d33c | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2
51788ff7-bb37-4122-a2d6-7e4d6b7e172c | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2
a8ea1ae8-5656-4ce1-8b6f-08c89190871f | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2
06e4862b-57b0-4ee6-9c99-899fc65af24b | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
161128f5-5beb-464e-b4ed-b0cfb4d63550 | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
2c1a70d9-e6ae-4d34-a193-e6787d5cd9d8 | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
3ca8fda8-fcab-4e9c-8950-7876261c927f | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
4abace26-9b92-462c-a909-ec21b40f503a | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
6098b3a4-42c1-45d9-a318-c394bae91b4f | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
6ff67d57-ab95-4cbc-883b-367c9e4cfc15 | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
e361cf1e-7e14-4baf-a0b8-3b432485a2cd | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
231e273a-300e-43d7-8334-e3eb71a03bf1 | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2022-11-15 | Level 2
51ec8f6b-3653-493e-962e-330279c4d004 | Junction Enclosure | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3
9f80bca3-d103-477c-9ec5-a389993ccd73 | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3
c556ac8e-a705-4d00-9b78-97b085f2af0f | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3
154ab2c1-ae69-4121-a8de-166eaa9b3a14 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
48698bf5-585c-4c57-b8de-ec5aa34a7970 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
70058380-feae-409b-b1e3-47d2ad9e6e77 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
8edd9b0d-26e7-48a1-b66e-fac80750d58b | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
b822fca3-fd4c-47ea-9ddc-9167b560ad51 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
21bc4f74-b34f-45f6-b29e-a2dd5aecd76e | Padmount Switch | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
70c962d7-6162-4a7f-94d4-ad9df67d6c07 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
85a73d53-800a-4c43-8f87-82d825a579b0 | Padmount Switch | 2 | Distribution | 2021-11-17 | 2022-11-17 | Level 2
c094b4dd-1902-47ff-a385-e48c5e994a19 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
cb1e5547-d2dd-4b55-8a09-be2dc3b60a6a | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
d00c121c-2471-4af9-8c17-3a79b2777da5 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
6618f0f8-ebb0-4295-a4c0-6bfc3488c21e | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3
c7b2ac54-938e-4cf5-a26d-cd52ae3b1b42 | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3
d9340227-da6e-4f44-bacb-51dceb365b6e | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3
241ab08b-d97b-42a8-a97e-99c77a7d6f79 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2
304d7afb-bbed-456e-9ae8-f48dcb2304a2 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
69a59481-aed4-4173-9712-9f08c91585fe | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
95ede16f-c88d-46c4-b310-16cf8354ec48 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
9b024ff7-2807-44b3-9991-494a15a76622 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2
a040db75-035a-43d4-bec6-c13c38f64046 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
a12c31c3-9ac8-4131-b5ea-77233fe0b020 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
c4928fcc-5509-493e-9b9a-2742942b5c46 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
e20eaa67-1091-4ce1-b285-a0e3f1931e75 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
f48ff40f-4ce2-4846-b1ed-ac068f6235e2 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
f8615808-3fd3-40bc-9370-4ea665f9e3f3 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
36c17e5c-1cc8-421a-a50c-f67bb2d7ec7b | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
4435fc26-76b4-4a0e-a46c-8dcbfbc84136 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
6b3a6260-7875-48dc-a1fd-33bbbb986312 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
8d2fe2d9-43de-4491-a056-9a97584d3eb4 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
8d4a8de5-304f-4643-a28a-05dc0f673e86 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
c370e1cd-6580-40e7-91f9-db0eeca2b9ae | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
cc61fa4b-8928-4590-a4d1-bd72247967e8 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
e5295df6-40db-4f53-89ce-ac6e73646e07 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
4da60e94-641b-423a-9dad-5c5c95c6de2f | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3
5e3ee522-f59b-4ec1-958b-ff9fa6efcf5a | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2022-11-23 | Level 2
71ee4b91-2ebf-4985-8928-57e543073197 | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2022-11-23 | Level 2
ad6ccf3d-4c5b-4448-806b-dbf8e81acd71 | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2022-11-23 | Level 2
b36ebc00-f57f-414f-afef-b60fdadd8779 | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3
f2859908-b0c1-49df-921c-ce5a60d0cbad | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3
0b1f391b-32c2-4f14-92ab-711db48a41b7 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
1b253976-9c2d-4270-a34f-813ab66503a0 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
221e44c1-ec1c-4133-bbcf-e64ba2c4ffd8 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2022-11-24 | Level 2
4e8ef4c2-2c5e-4f71-bcfa-4845bc57d7da | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
777df967-9a5c-4ca3-87b5-db6426ebd4a1 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
97a720ee-e51b-46e1-88ab-58b6bfd08bc3 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
cc1f8089-8663-4abf-afb9-cb4b43c68fdb | Junction Enclosure | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
4c2c4142-a874-4d10-9da9-ab9ebc138bcc | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2022-11-29 | Level 2
8edfd2d7-e57e-4fe8-90ee-604aa24ac4a4 | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3
c4ece5b2-7e7c-44d0-9cea-67796624633b | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3
ff964d7f-6d24-449c-b315-071cc9b78f34 | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3
00fb24bf-98fe-4101-8238-883b65fe9137 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
26202d26-2064-4a79-b960-26f8b2dc6496 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2022-11-30 | Level 2
7e1a7735-c75b-45e0-b5f7-42de67dcb4ad | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
855a23c1-8179-4082-8ca9-d7faeca7a793 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
f8f2dd25-e607-49f7-bc2a-a2d8ae51067e | Padmount Switch | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
28ae7b8f-a7fb-44e9-9bdf-bbe9ed769bf2 | Junction Enclosure | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
3431efa3-da78-4ad6-a734-9f8b13f762d9 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
3d4bdd58-28cb-4bc1-8ab5-24a2b45ebda5 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
59dc15a0-980c-47bd-b5be-6d0074d4c738 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2022-12-01 | Level 2
9e52e1e2-97ec-4ddd-94f0-6eecd1d46ef0 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
a628d59a-f18b-4ad5-a2de-7b8ef81e545b | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
d1bc89fd-6369-4743-97c7-3ec1c295fc98 | Junction Enclosure | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
da876f43-5eca-4b84-b449-92617ba3821e | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
134b6581-1656-426b-8159-10bae2b929db | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
1a563d83-44ee-4c3b-b10b-5e3e65d1debf | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2022-12-08 | Level 2
3950a961-3b8d-4152-be84-faf11e57a222 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2022-12-08 | Level 2
78f4a10a-4ad7-403d-85aa-6e1c501f5833 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
858ac9f1-67ea-4d93-b090-1448d44e0922 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
89dc8e3e-bbc0-46d8-93ef-8e076dbceb41 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
c28aee0a-ceff-4572-bc48-2e5cb0a84e83 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
f79316fc-f799-462c-aa1b-9da0ca30754a | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
36be12e2-15f6-4ae7-8887-2f6823f3012c | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
3fc33f72-480f-4986-b4d7-245969deafb7 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
5094ee40-d750-4e30-acc0-72c09561e678 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
6f081616-2a6d-4b22-9142-b6696dcea656 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
c589af83-02ef-467f-aeee-7d217f1e8f13 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
ca4cb178-f6a7-4484-816e-59b7c67fe56a | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
dc0f5871-0131-4f09-9527-17d704e73a1e | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
f17ccf5b-a1c4-4a0a-9532-3522a4767fcc | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
0eb637ab-60cf-4b3b-b8ae-840ddb8b5cf1 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
14d6eb9f-89f0-4b12-9036-a3f7b388f9fa | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
243d7ee1-f943-4ef4-ba74-67b07dabec33 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
26b0dcfa-de42-40df-9903-179e832b48d8 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
2c97498b-cd6e-4150-b31d-c40916a8e36e | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
80aa210b-37b6-4f13-a74e-2710845afc9e | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
caba6f74-2b89-45f8-a32c-90a52d5d8b28 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
cb869d06-bdaf-4ba4-a091-e77f580294ec | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
e3a29ce1-e303-4930-a89d-e0a322d3acc9 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
25ff2b77-ef21-4496-b38e-9a8111541a44 | Padmount Switch | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
895d798b-1930-4b36-b5b9-b4c7289a2128 | Padmount Switch | 2 | Distribution | 2021-12-13 | 2022-12-13 | Level 2
97368413-706a-447f-9b5a-dd0750305bed | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2022-12-13 | Level 2
9ae2ab3f-b422-4680-8c42-2921922e1c1f | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
a719487e-a750-441b-b85f-04a822e554bd | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
e70af0a7-2aa0-41cf-8c43-6486ee763173 | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
11f778af-d1c3-469f-a294-ebb58f0efb19 | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
3d3a05a7-c603-4c90-bad2-0dcebecd2e53 | Junction Enclosure | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
43ab3ef7-b7d2-45a5-8fda-42eb651834c2 | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
5ee1b427-c329-4379-8db0-a2052d7642cc | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
7f028d2a-90c8-44d1-b2c5-70c6d9c66a4e | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
de7edbd5-f702-4c28-a3ca-d686c7e9311a | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2022-12-20 | Level 2
2d968f2b-c0c2-48ac-a981-41d4c4c06d4d | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3
96df2510-834a-4c56-975f-7faa124c0065 | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2022-12-21 | Level 2
9bb99be4-599e-48de-a5a8-3adeb285894e | Junction Enclosure | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3
c32b12be-062f-4209-acce-3b56afc9ff2c | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3
eba29318-c221-4eaf-b989-0ba7d80e26ab | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2022-12-21 | Level 2
259e0f78-ef03-4bec-b5d0-52870c54dd63 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
2d440729-aaad-4cbe-b9cf-29f1a2671023 | Padmount Transformer | 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
2f431f96-ba99-48fb-b4ed-144018357c85 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
4006d224-a3cd-41e1-bbf4-2f8e33663527 | Junction Enclosure | 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
6fdfe8d9-f1d1-4987-afa5-100642f24f8f | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
9815eb27-a84d-4d74-90f4-48b89dbd5194 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
98880d10-31ab-4fd3-bd11-918b54d50281 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
9b2b4f00-bf87-450b-b218-4bd61980c528 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
b043c885-86d2-4708-a4a8-d4c523c38710 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
ceae8a3c-ebaa-48c5-96eb-3820c7acfeca | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
edc285b9-13e1-4d0b-b27b-8ac71239b037 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
00ae7a6e-21ce-43f3-8e6a-e9c5360de7fd | Padmount Switch | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
0277508f-0c50-4703-9be7-9125d4268361 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
08d547e8-a5c2-473a-a6be-84f511b6d5fb | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
1104ef60-88ca-43c9-bdf6-97494ad8fda6 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
1e9a1327-0c87-46d3-bf4e-f7d4a57910f0 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
1eb15c5c-161b-4a25-b21c-3dba971c1f6f | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
1f24d5d0-8418-47f1-897d-4683b8869b3c | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
3cf79ed8-740f-4afc-abb6-af5a8d24cf81 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
433df26e-b9fe-46b3-ac84-8f2d3d679ced | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
4a12f514-e185-4ea2-9ffc-50bb9db60e56 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
6a00524e-e4bb-48f7-ab2c-8930f7cddceb | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
7362db7c-3418-46b1-b363-050ebc6befd6 | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
85876347-5fe2-4ec0-a549-8c3ebe25f0a8 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
86c714dc-ffa8-4b1a-848f-e5d8b0e30c5e | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
a5eee544-b786-4e61-a196-4bd701207d97 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
b9d0b771-b60d-40b9-bdb6-3f6e28f4a8d0 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
bf15e60a-78ab-448d-b152-b3a0481513e7 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
d9cf66c2-337d-4eb0-b597-6165a1a0e021 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
dfcfdca6-6336-43ba-b883-e93be03864cf | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
e0d50655-43ff-40fb-bb34-dd1edbc37ac3 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
ebbebcd8-d748-458d-b72b-0b3cb3a8a81d | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
ed1651d5-b910-41dc-a308-9c61a77f537e | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
f3182b1d-31f0-4c76-97f6-63e1d518d9ec | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
f902e167-88d6-4d72-8c22-ef535b6daa78 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
00baae16-87f8-4ef0-a371-677f6b3fc9d0 | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
01bebe7d-d676-4e4d-878b-d83a0d6dc154 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
0dbd06bf-73c9-47f4-b82c-fd93a575e3a5 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
1afa07df-5652-4731-a553-837aea85f6ef | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
29bce270-d482-4724-924d-613e6e3fb41a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
2db31abf-c0c9-4fa2-9a85-9c046769046a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
31a84e3a-8718-4206-8d68-4eb3f1824895 | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
4734d0db-d69d-442d-9329-a72bd49e6426 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
4bf630e0-88f5-4909-bdc3-531419564305 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
7c8bfe0b-609c-4ba6-a3c1-85b5d2ef29ba | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
7ecacf7e-521e-45bf-bb42-2b4274086fde | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
aea6ccf9-6fad-4278-87f5-ba0510d99b5f | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
c5d55497-e65c-4f7d-ab84-8e9cdf4e869a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
c6690925-fa90-43e6-ba6d-049b1e0e9c3f | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
d266625c-43c3-4c3c-94e3-23d778ea75a3 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
dbc3e3b3-ae05-4c5a-9963-18c961f030ea | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
dfd24fd6-91b4-4bb8-8839-a82c1dc935e2 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
f2a2a997-eeb8-4c09-877b-e9fdcb6035c0 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
07721d5a-ad9b-47f9-8819-d39cf45b9d5c | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
103f1ea9-8a8e-42f9-a2b3-3525f31e499a | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2023-01-21 | Level 2
1aaa5c1f-bcb6-4cce-9787-100a211eb9e5 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
1f99e0f4-136f-406a-8262-107ae1a80f08 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
472eb80e-191d-40fd-ade0-ae3e51c4e6d1 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
6cc1fc5a-97c5-4a06-a0a6-da51d2293a39 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | 2022-10-26 | 2027-10-25 |  | Required to Re-inspect a subset of assets
d267c7e5-4ceb-4199-97f7-bf2048740895 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
da6dacc1-4a6a-4394-957c-924cb73056d8 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
01350a7c-1f7b-4751-802e-9697146fb570 | Pole | 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
2b5846ce-5add-4fb6-b30e-110f0be2516c | Pole | 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
32eac4d9-d7a9-4d84-afbd-d62f0f2bc1fa | Pole | 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
4e3aef07-4474-4037-a686-2466f72e74ff | Pole | 0 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
7c2e1f94-8362-4587-b84e-fb1b613b0fcf | Pole | 2 | Distribution | 2022-01-24 | 2023-01-24 | Level 2
b65d9914-75b7-42d7-87c2-3a1b5618bdb9 | Pole | 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
c870861d-c3e4-4606-a8d6-8f4a09bc13f2 | Pole | 0 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
d26fd316-98a4-484a-b296-4ab7bd2d1fd5 | Pole | 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
df04d907-f050-4e06-9ae5-67856b74cbd9 | Pole | 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3
fc498a09-326d-4d63-9f85-0e58a10d54c1 | Pole | 2 | Distribution | 2022-01-24 | 2023-01-24 | Level 2
08977244-361d-49a6-a11d-b7ea84885b95 | Pole | 0 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
099b610b-3d59-4b76-957e-d75e3f85534a | Pole | 0 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
0b34aa8a-df27-4ba6-90a9-f48d3b31634e | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
1aa56628-a981-4cc2-9c27-8f81f0b0010e | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
222bee85-4956-4636-87b3-8d20690dc12e | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
22873d5e-6e3a-4964-b783-0ea455498356 | Pole | 2 | Distribution | 2022-01-25 | 2023-01-25 | Level 2
4d986c89-524b-49a6-9c18-2c77865ba0b1 | Pole | 0 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
6c046136-2827-4373-8563-bd0891df2e3a | Pole | 2 | Distribution | 2022-01-25 | 2023-01-25 | Level 2
79f94430-f7dd-4e43-b791-ac44b00b66bf | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
7a8cc998-e2c9-46f8-acc3-c1ce1ebd65ce | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
864a8c34-b3c3-4c27-900a-35e20d23b1e7 | Pole | 0 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
89cff108-88f9-4315-9b45-e516a53c9b5f | Pole | 0 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
8dd8777f-cf04-4be3-b637-99cdbbccd3a6 | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
8f54a0c1-d79e-4053-adb3-8dbe11fabb40 | Pole | 2 | Distribution | 2022-01-25 | 2023-01-25 | Level 2
900092a9-0d82-4ba2-8e68-2a871ec76873 | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
a37fd697-b7a6-476c-8937-f670b58d050d | Pole | 2 | Distribution | 2022-01-25 | 2023-01-25 | Level 2 |  | 2022-12-28 | 2023-12-28 |  | Required to Re-inspect a subset of assets
b646a044-212a-4883-b835-05df3135e9be | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
c6449c3e-a68c-4ec4-958d-e4d29fdbb840 | Pole | 2 | Distribution | 2022-01-25 | 2023-01-25 | Level 2
dd4c6a5b-6280-461a-9307-7810ce4d656a | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
ede85024-0ed1-4881-a165-cae441895ca2 | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
ffdb08e1-3cda-4d70-b378-a29db53c941b | Pole | 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3
228af172-de20-4126-8c9b-17f1104625e8 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
28a651f7-bf68-40a7-a7d4-87e2666f933b | Pole | 2 | Distribution | 2022-01-26 | 2023-01-26 | Level 2
2de29661-84fd-42b7-9355-fdb668ede5d7 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
3069902d-837b-464b-938f-ae44fd0ea3a0 | Pole | 2 | Distribution | 2022-01-26 | 2023-01-26 | Level 2
3b13e89d-65a8-4270-8810-28f708bfc6ea | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
468f2fdd-e8ea-4ee5-8a89-d9111ae6c9ea | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
5f2162e3-67aa-44a3-9117-68f66bec77ca | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
6eed2db0-a166-431d-8bd6-c30d56d18c7c | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
71859952-679d-4912-8265-60faa7e2ef99 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
7c487575-2644-4b52-8e54-d79f29303859 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
8065a6ec-eb02-46ad-9c65-7b69f012a9b1 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
8bf623ee-ebef-4f63-a753-3af34c5f53f2 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
99eb7146-2303-4774-b479-2df14edf0fea | Pole | 0 | Distribution | 2022-01-26 | 2023-01-26 | Level 2
b07a6841-ec72-4547-80db-57b6fb1ba967 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
de0312a9-32dd-4e37-b7ea-5450062d4b14 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
df490ce5-67b8-4c04-b025-9f75b0f3f4d6 | Pole | 2 | Distribution | 2022-01-26 | 2023-01-26 | Level 2
ed1f4cfe-c268-4216-abc5-e013378d3fef | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
f9153708-9fe5-45de-a0c5-5772290817c2 | Pole | 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3
043fae98-ccc9-44de-a7c0-fa93e21c647c | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
159e1a8c-1def-4adf-85dc-753639c85d4e | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
191884e9-eb33-4f6f-bf76-653a77eeefa4 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
36db653b-49fa-4fff-a66e-f48cda801d8c | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
4170f2d8-a3b3-4fd9-892d-02c99aeff2c0 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
55163faa-a6bf-4846-a22a-43f45272dba0 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
5957e772-71c6-475b-a7b0-6c0c4f54115e | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
6e1d1192-67d8-43df-8937-bd582eeac2d0 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
78e1a696-704a-4c47-bcee-1338dd0737c4 | Pole | 0 | Distribution | 2022-01-27 | 2023-01-27 | Level 2
854ae423-8952-4f95-b779-391c374b506b | Pole | 0 | Distribution | 2022-01-27 | 2023-01-27 | Level 2
8bfd5005-be1f-41ac-8a4e-f257533a2c7e | Pole | 2 | Distribution | 2022-01-27 | 2023-01-27 | Level 2
8c70cf5e-777d-4e6a-a0e3-216ed425c4a3 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
8d86757a-3c9b-42af-adc7-06796d9d7a29 | Pole | 0 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
af3c60aa-0c35-43c4-b18b-54a6a678f88d | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
b816cc8d-e397-44c2-b931-b1693beffc76 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
c55ae154-c776-4d22-8c01-d3618e007b92 | Pole | 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3
19034374-606f-44f0-bbca-bbc9c8e6c6d5 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
240dd5b0-bf4b-4d2b-9958-dd0349c52e71 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
30e9314b-3fc7-4ef3-8a8f-8672f6471c83 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
310df571-c1f2-4150-b7d9-9590cc000ce0 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
32ecb370-1fe2-4223-9aa3-b3b344016ad4 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
38ea6374-a530-4a97-8051-02e116fa36d8 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
3e5aa20b-287f-4e65-8d89-20f2b57510ef | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
64de3135-7326-462c-b984-7f93c432fe62 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
6dd8d446-3ba3-4675-81d8-13aadcafe105 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
7b161d3f-c818-4639-a2bb-a97f1b8dc49e | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
80b3a676-69ca-4447-8044-503c203f9f54 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
93ee02b8-6f36-4c48-a150-07ca5b99df53 | Padmount Transformer | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
9db076d1-85ab-4f7b-8fe6-cebe9e9e4372 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
bf41e8c1-f20b-4868-bd31-488ffc926480 | Pole | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
bfbc3d9d-99ea-4edd-91aa-d26abf3aec1e | Padmount Transformer | 0 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
c2494965-76d3-4f24-9c76-06d620e419d3 | Padmount Transformer | 2 | Distribution | 2022-01-28 | 2023-01-28 | Level 2
0f04e37b-11c4-4417-839e-18c95bb58812 | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
14a55c3d-7228-478b-9c15-e17f4b3f3dcc | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
3863d8ff-96e3-4363-8e01-44bd64f1e23d | Pole | 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2
45272cd3-3f95-4a7b-bae8-62c8842024cf | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
453370c9-9491-4498-89a4-34d078f014b2 | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
4683e080-f392-4e3b-95c2-a95e274ac53a | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
5cfd89ec-b5bf-4403-a62b-7de5a991b46e | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
697dd3f0-21f1-48f0-bf87-f8c7b3d3a00a | Pole | 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2
74d3df68-d906-4449-be83-d39385d41faf | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
79258e62-ee91-4690-9408-c165c6761acc | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
79500704-6812-4c62-823b-ede8492e679d | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
89554432-36cf-4421-a905-75d794760a16 | Pole | 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2
a945fddb-f3c3-44de-a109-e0d56866c621 | Pole | 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2
b2ae0f31-3cfd-41dc-9a14-e0695e2c3162 | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
c4e018ac-38c8-4b21-a021-3434ef36aed7 | Pole | 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2
d53e934e-5450-43ab-981c-1a4c39321b26 | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
e7f8b7f3-8c67-4c62-a2d3-25de36bddacb | Pole | 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2
ec0ae177-610f-40dd-8840-854efb5ca0fc | Pole | 0 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
ee8b96bf-0235-4a6d-b410-3adc36b03f94 | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
fee644bf-d820-47ff-84ef-ed0a8f4c90fe | Pole | 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3
1804e337-8682-4fa3-90af-ab5a106c71e5 | Pole | 0 | Distribution | 2022-02-01 | 2023-02-01 | Level 2
40ed4c65-72dc-40e1-bb31-024a4eaeb42f | Pole | 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3
47a98e2f-f112-4294-9698-44510b7ddfe7 | Pole | 2 | Distribution | 2022-02-01 | 2023-02-01 | Level 2
673b2574-95cf-4487-b75a-9bd29aeba34f | Pole | 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3
8c24bf14-2eb8-4e22-888a-6337abc1cc7e | Pole | 0 | Distribution | 2022-02-01 | 2023-02-01 | Level 2
8e910bc3-7b15-4540-9482-fe25885e484c | Pole | 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3
b5a819ee-8a32-44bd-9ab3-4557bc103c3d | Pole | 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3
b66c6340-5f3a-4341-ac49-6bfce30c3977 | Pole | 2 | Distribution | 2022-02-01 | 2023-02-01 | Level 2
bb6f0d85-ecd7-4884-a166-b09df0130823 | Pole | 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3
c683f763-e432-4ba1-9825-fd7bf223df28 | Pole | 2 | Distribution | 2022-02-01 | 2023-02-01 | Level 2
cd06f12c-7067-4332-93c2-1bf2de1e0fac | Pole | 0 | Distribution | 2022-02-01 | 2023-02-01 | Level 2
f9f147e9-2310-4fd9-8566-3b168ad678f2 | Pole | 0 | Distribution | 2022-02-01 | 2027-01-31 | Level 3
0616218b-bb19-4d87-99e1-0e825bcd16ea | Pole | 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3
0c86298f-f809-4f3b-9ddf-da345c0ffdc8 | Pole | 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3 |  | 2022-12-28 | 2027-12-27 |  | Required to Re-inspect a subset of assets
181f236c-f525-4d85-acb5-0905fd151847 | Pole | 2 | Distribution | 2022-02-02 | 2023-02-02 | Level 2
7a202396-2fa4-4d61-aba4-2c26ca013098 | Pole | 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3
e044ce00-f559-4a8f-b3ce-01599b55f35d | Pole | 2 | Distribution | 2022-02-02 | 2023-02-02 | Level 2
e0a1751c-bdfa-4331-8979-9128fd95f145 | Pole | 2 | Distribution | 2022-02-02 | 2023-02-02 | Level 2
eef9f8e3-0d94-48c5-8767-e524d5a51daf | Pole | 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3
0a5f34bb-89c6-4d6f-88e6-975684f2b44d | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
1b830366-a6c7-4b26-ae93-86da0e17ae57 | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
2ae45b42-6bdc-45a4-8c14-68dc424b9375 | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
3ac8c862-c5a2-4a45-bee1-3464038d3d1d | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
3b411f7d-7f84-4058-aeeb-38aeb8b9ae3e | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
4a7144a5-f9f3-4ff2-a4c9-94df8b05ec85 | Pole | 2 | Distribution | 2022-02-03 | 2023-02-03 | Level 2
8e8cc5cf-35da-4c8b-8bba-06cfc398c5a3 | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
aaffcd1b-a947-42c5-b502-27c72cdab91b | Pole | 2 | Distribution | 2022-02-03 | 2023-02-03 | Level 2
ccfc32d6-007e-4975-aaf2-5b54592213bd | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
db955333-1b48-44ff-a86f-eb29f060cb2d | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
eb0ee75f-54e1-4190-bbfc-c675345a4506 | Pole | 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3
4caed8d0-3562-4ccf-8268-1666563489a4 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3
5557cf6e-722e-449a-b1c9-9d5b57bf62ed | Pole | 2 | Distribution | 2022-02-04 | 2027-02-03 | Level 3
6f851d3c-aed8-43cb-83c7-ed251a712fb0 | Pole | 2 | Distribution | 2022-02-04 | 2027-02-03 | Level 3
863da285-edbf-4295-b8c2-fe56458d6273 | Pole | 2 | Distribution | 2022-02-04 | 2027-02-03 | Level 3
d91d5763-eb98-45d2-b25d-14175af96863 | Pole | 2 | Distribution | 2022-02-04 | 2023-02-04 | Level 2
f00f17de-b84b-4d40-bccf-c6688a380e85 | Pole | 2 | Distribution | 2022-02-04 | 2023-02-04 | Level 2
0f5d4677-fbd6-4d80-881f-e1aced3e76ba | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
2ef13931-0df6-425f-baae-b99d67aa692b | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
3246d659-6d77-4831-90b6-cea9af7d79c8 | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
3cd8779a-dd4f-4a80-bd0f-da912a22a440 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
50eec48a-d4d0-451b-8f8d-7bf69be83d88 | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
59814633-5d78-46c3-98a6-d6a793ea0993 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
5a44b1f9-daf3-47d2-9906-da650f080764 | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
73c23c0f-66aa-4389-a9e0-3c4e21a9372d | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
7ae3c14f-2dbc-4e6d-bd76-be4e2ded08fb | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
9b504635-8529-47ad-987c-e9c222dfaf87 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
c14a4737-fc67-4d8c-87b1-69c7a475277b | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
ca052ec3-6474-4b71-9760-46f14f99c04b | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
e491bab9-5918-49d5-910a-d85306c65fe7 | Pole | 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3
024a504a-a708-47ea-a6e1-6aea8430b429 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
26733d3c-41e1-4939-b0c9-974e9b7aed94 | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
2ba86207-016f-4a6c-8374-f575e54bc4d0 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
40731215-a42f-447e-8e09-2a70e393c3f5 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
45d8b59e-b40d-437d-9a7c-2b9b922f4f0e | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
47d9ac1c-3101-444c-a723-f6b156677068 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
48876cbb-c205-4317-900c-8b1b899ffb53 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
4fee4d82-ce54-4497-92cd-bef5e1a98bcd | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
5e8d7c1c-19a9-4c15-bd56-e3877901be45 | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
689a9694-35c7-4e5d-8fd6-76093054c955 | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
6fe1e808-51f9-4bbb-b36b-38c49894d5df | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
74d3db50-2958-4ea3-aae7-6ec687c6f7f3 | Pole | 0 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
829bc174-98ef-4def-b02c-c28427280eb9 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
93088519-5600-44c8-b679-2de6d10b40fb | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
94c1c1f8-c648-4047-ab7b-42658c6e8c22 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
96ed71cd-d30a-4844-86b5-88e009d4f810 | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
9d4aeb38-6c02-4d0d-9d96-ecf2b02be560 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
a9b7700f-f1be-4f14-ab18-ff0d9cfdc9c1 | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
ababbc44-1c9d-4cda-883d-5c0705266f70 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2 |  | 2022-12-28 | 2023-12-28 |  | Required to Re-inspect a subset of assets
ba6e7d0f-d2c6-4b19-a729-2cf4fa5b6aba | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
bd2ecedf-a2b4-4298-b714-ea376549d553 | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
c60090d2-1d60-416a-a60d-d31e4a6797b9 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
c8948eb2-ee8e-4a7a-b39d-4d0fb33f4b2b | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
c8b0d519-5ed0-4d04-ad75-c9644ff6b414 | Pole | 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2
e755036b-b4b9-46e2-9efe-88413bcaceed | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
fdb754c7-0348-4e32-8e09-bf70bf37e73c | Pole | 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3
0d4d8486-686b-4e59-9502-cf8d8dec856d | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
24567a0a-842b-4466-8e30-ec5914884b87 | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
262258f9-4b4a-4482-ab78-5c5d251ff5d4 | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
27a4e67d-0b6f-45b8-bda6-d421370b0101 | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
2f8b7c0e-9f64-40b0-9e06-c2e61b46ab5f | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
361ad578-c9d1-44d6-83fd-a6171688612e | Pole | 2 | Distribution | 2022-02-08 | 2023-02-08 | Level 2
3a508812-be8d-4175-855e-66a8a93c1e9f | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
6541e1ef-582c-4724-abc1-27c4a5ff6ff1 | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
6e920e41-7726-4669-b859-7885e6e5d4ff | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
7867d964-1f89-4b8c-9e83-e87cc761370e | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
7b48c7b5-e511-40cf-9c07-908d5a0fcc4f | Pole | 2 | Distribution | 2022-02-08 | 2023-02-08 | Level 2
8fd2d194-0cc3-4236-b131-692a3f7afe6e | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
a5cdc95e-52b2-4bbf-a91a-46e8ac3e68eb | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
aab229c0-4d78-4d7d-ae92-e8778adf11b9 | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
b1d99005-1e7a-4463-9842-bcd00c91afeb | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
b5aa8e4f-995f-4832-8c9d-a0f0382225c0 | Pole | 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
c5a11c96-f73a-4aa4-a8e8-9b0f66fc6d10 | Pole | 0 | Distribution | 2022-02-08 | 2027-02-07 | Level 3
c897e307-c5e7-4f21-b76c-66ebb1c7c7b0 | Pole | 2 | Distribution | 2022-02-08 | 2023-02-08 | Level 2
04d57a4f-0ec3-42b6-914f-a3469fd5f3a2 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
0d19c7ec-c428-45af-9d00-249b7b29c16e | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
11b9b340-0f94-43dd-b4e7-f59a375faf5e | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
1418d789-7bc6-4a55-93a4-632676a3455d | Pole | 0 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
3377288b-7821-4177-8bf7-5452691c702b | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
356f558b-9c56-411b-bf2d-785329b89139 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
3a211bc7-0824-48e7-ab31-826154608772 | Pole | 0 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
3ecc3630-65b8-4cfa-b026-5aea84a78cc9 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
409e354b-5e35-4b21-9f26-c5349fcaf695 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
4c4a84be-2c92-4176-b64c-03051d78995d | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
65d2bf68-d300-4cd4-b5b8-897247934d06 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
685c2e3b-7e3a-4f84-afcb-a540db1bd42b | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
7838ca3b-97d3-41ed-864e-90337de4d2cb | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
8b77616c-e838-4a9d-9d19-43e258cce374 | Pole | 0 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
8ebbf735-2967-43ce-a524-164f20cfb254 | Pole | 0 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
9c8a0198-fe64-4ece-a649-80e87f783fdd | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
9e1bba3a-8133-4bcd-90e4-4a1ad40a0f54 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
ad3fb623-0e83-4c5e-9c25-c81f37faa957 | Pole | 0 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
aee47510-2510-4c8a-866a-dfc1851e7622 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
b164fc35-2500-44d9-9ece-ebfeb6b00cdf | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
b4aff6f8-b0f6-4950-a3c5-64249790acc4 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
b82ee00e-e10b-462c-b893-fd1c6cf6c836 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
bbb0feb7-c394-4e1f-b724-67b7a5aa828d | Pole | 0 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
dc0dde83-37dc-46dc-abf8-e909708acf89 | Pole | 2 | Distribution | 2022-02-09 | 2023-02-09 | Level 2
e28837f0-09b3-4e71-a818-70bd5fb9c6fd | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
e491c326-4ddc-480c-af9e-5cf024b89dd5 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
e62a2953-aa96-437a-adc0-6eca5113006a | Pole | 2 | Distribution | 2022-02-09 | 2023-02-09 | Level 2
e94c659b-4d85-4b88-9972-6d2f0fc95a7b | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
f5e435d2-8dcb-4ab3-8d2b-874bf6cfbc58 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
f5f3a27d-0f28-41e2-b904-041b5222c77f | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
f9deba75-bfe9-44f9-8b9b-6a996ee65564 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
fed718bd-832f-4373-ba15-962f652ee5ea | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 |  | 2022-12-29 | 2027-12-28 |  | Required to Re-inspect a subset of assets
336ffc13-c07a-4ce2-908b-b94223b4b313 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
347a3df6-003d-4e15-a10e-c538cc3aa9c2 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
373081f1-43f4-43b3-9ac0-ac3005b9bc1c | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
4ba7a9c4-396a-4e83-b196-597dc613f730 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
4e714cfe-6bfc-47c4-9d1d-9c79c9631560 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
641c09cd-7df8-49c1-89fd-0c28e7ab180e | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
72180a74-92d1-4ee8-af48-47fe23503a02 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
7ca72158-fca3-4608-963a-606b7090802f | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
84f38b4c-878d-4aab-8e63-f0fca525ea00 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
8577e9c9-d067-43e7-b353-dabea63707cd | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
92273650-5c8c-4b31-80fb-371286773c33 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
98e997d0-bb60-416e-9d8d-00e00d072fc6 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
afc2c3c2-8cc4-4f9a-bf8b-acf9f7e7afec | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
b5369aa0-9d84-4889-8a25-ba2d224cabd7 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
e1bc3482-f8dd-45b3-9c5c-02021907d297 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
ea3ffd3d-76d1-472b-962c-05a5f788a14a | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
ef2c5216-f05c-4c86-aa97-c358aa5d4da3 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
f4ed4a8c-c4a4-4a20-979c-921a00c4a32f | Pole | 2 | Distribution | 2022-02-10 | 2023-02-10 | Level 2 |  | 2022-03-01 | 2023-03-01 |  | Required to Re-inspect a subset of assets
f8b26909-0c63-4bb4-a557-61764d582af3 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
fd25aefc-5092-45e8-8b3f-41191c2b6338 | Pole | 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3
0096ef7a-d300-41bb-894d-8731d7d42a20 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
07e75018-b091-4cc4-857d-f76a024cce8f | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 |  | 2022-12-29 | 2027-12-28 |  | Required to Re-inspect a subset of assets
0ed4b466-e953-4ed0-a059-eec179a89ccd | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
1048a037-c19e-4410-a822-f54a33a094e2 | Pole | 2 | Distribution | 2022-02-11 | 2023-02-11 | Level 2
2203535d-0869-461c-ab49-ed472ad0a845 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
27271a79-83ee-4590-bc95-201c162d2d62 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
3255b111-9ee4-4ea9-9911-131e79871f89 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
48cde3d7-c26e-4fee-b6f5-36d1b31c6894 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
5027ec82-9617-45c1-b457-2c865828a8a4 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
5b5d578b-5cc4-49f1-909c-43d1aa697d7e | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
5f3dff51-319e-46b0-98b6-e3656b60e743 | Pole | 2 | Distribution | 2022-02-11 | 2023-02-11 | Level 2
640e56e0-8c5b-421e-ae26-999b8e6b038d | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
6eafa25b-0379-4a53-a155-a00da1809bdf | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
7889ba89-05dd-4b28-98b5-2c780633160b | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
7975eba6-4ada-453f-9f75-5f0e06d525a9 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
7fd32072-5cc8-40b7-87e8-a7b5b9a3db60 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
854a7074-a592-4f1a-8b28-994790628182 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
85cf0826-67ef-469b-953f-fff1489e8e07 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
86064895-eec6-4003-b4bf-25c639008185 | Pole | 2 | Distribution | 2022-02-11 | 2023-02-11 | Level 2
8fdd7ca0-48ee-48e5-8706-1e05f3dc29a1 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
90dbe23a-5b6a-4fe4-847e-069aa09a1b87 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
98797cd6-beba-4dd1-a582-96adbd90c85a | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
9a7e0f58-d901-472f-9d39-46d84a1deb44 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
9eadc902-960d-462b-ae6a-85a890a2b9ed | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
a778c250-eeeb-44bb-81b9-94f18cf50bc8 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
a91bcfcf-9eed-4f03-bb0b-5e5807b9a478 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
e8ea4709-8a1f-41fc-bd5e-022f9f4e755b | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
ef0f6d13-2f30-42cf-a839-16c3b8bd0f84 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
f93c7ddc-36bf-4e1f-aab6-bcc9ca37f7b9 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
f98781ca-7f80-4d10-9921-e9f3e33dfecf | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
01f2f755-36c3-4cd8-85cb-6c5d1280b754 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
0b4dbea0-9aa1-4c2d-98af-0e14ef947e5b | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
17407ecf-d6ae-4333-a45f-c72e0dd2f76f | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
1cf59be6-c5e4-4755-aefd-924f11e06867 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
29680063-05b2-4883-ae3e-bd1e250dd46c | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
35475c42-c6bb-4c3b-8f31-ecc9fafb1fc2 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
36f334c7-a190-4f99-b45d-1e740329be2d | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
3bfdd5a6-e333-4da7-a375-20004b5d6fc7 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
52bf416b-bc47-43d0-8ad9-ac88cbe69068 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
5aff8b59-a6c4-4e8a-b3c1-87ab7457b5aa | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
74624c63-4d4d-485d-821d-65a1725e9c91 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
90b0a8f3-97ea-48a5-b83b-b41ce2aba6e0 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
94d69d5e-b9c9-43e8-b57c-6b5f4214c313 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
9bfca67a-0300-4dbe-b484-7e9513d71de2 | Pole | 2 | Distribution | 2022-02-14 | 2023-02-14 | Level 2
a44c9641-1ef0-4d78-a32a-2fe5306a978e | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
b8daa9ae-7ca3-4e7b-b9d5-7b92c08e954c | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
d6b20f75-a2c2-431e-86ff-7afeed876eb2 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
d9e040c1-b18f-4b27-a4a8-b2008765546b | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
daeaf391-654d-4291-aa01-3ff6de002d49 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
02796879-2d8e-48f0-8d61-19999923fd7b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
039d6d2a-b43d-49d4-9bb3-875ca5452b3d | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
18bd9e4c-5b55-47fb-801d-d163bfd77b96 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
248d43da-8321-4808-a946-7cabdb32c13b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
383aa520-ca8f-4e32-9b16-df1d4a27ed0d | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
38853420-36b3-4547-8e53-0b4f46fe2305 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
3a89e89a-dd36-4b9e-a5ca-d48f3ac4ef29 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
3c6b65c4-c447-44ba-8b8d-39cb1b955f06 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
3f6dd675-87dc-4253-ab19-28b711bb2c96 | Pole | 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2
438f01c7-4e93-4fed-899b-db83aa2f520b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
45ecfcbc-2389-4242-a5ce-de7064b1d746 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
487ad8dc-134c-47ab-9b38-4b7772b7d179 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
4e8d9aa4-a7e1-4e57-b12d-d3da98fc7707 | Pole | 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2
553f2862-4976-4606-b812-4a351c550645 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
55899d15-7725-4a37-b2ac-a02ae705d0ee | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
65be6773-48df-42d0-8a6c-69c015e3152d | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
69f3fdb5-fc6c-4016-a37a-1c5b3981f9e1 | Pole | 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2
6bffbf8f-5193-4989-9d4d-868158074cb2 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
761e0631-9e18-4c18-b91d-11607bb6c248 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
7931be79-59c6-4093-8bf0-f35fff6cfba1 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
7da9e69c-245a-42ae-af6b-417204b8571d | Pole | 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2
7e07d202-73f1-4563-a420-00fb3f5d7ffa | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
87462660-e568-41cb-b54b-9a9c864adca1 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
947bc1d4-4b8f-4b81-a2f2-63d56c37edbe | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
a69f610f-2ce0-453c-bf6e-188cddc9421c | Pole | 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2
a78cc53e-7923-4c2b-bb1e-6cf59d8a332e | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
b22ee7ef-2188-4ff5-b4b3-c54bea5237be | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
b94ff1b6-54e0-4804-a8bd-29e125163ec3 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
c062b670-c241-4a35-b934-06669267a140 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
d890ee9a-0f14-4296-9bcb-cac84e5cb56a | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
da83ef42-52ad-42b2-b8c1-ec12b7d3294e | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
df0e6db0-e95b-47ff-8728-3bae6646c39b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
e090602f-3ae0-4894-8b91-6c55cfcc870d | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
e3f6bb7e-bd0b-4d80-950a-097a99a868bb | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
ee4f3c52-702f-462c-8a6a-505e7d518d4b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
f7deaf33-5ee4-4c6b-a334-ec6c4138a5e6 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
f80faefa-f6a3-4b7d-a0da-2c08a49e03df | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
077c66c6-f44d-4523-b9e8-69a3c7cfa7b9 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
0b995957-56d6-443c-8bca-8201f2e469d0 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
0d0bbe7f-c4fc-4976-9fab-e6f5da0c688c | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
0ed6137f-68ab-468e-9627-772310bca331 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
20304509-bc34-492b-a313-18c2622fefdb | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
22d303dd-6f3f-4495-869f-f550c3c1c990 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
271138f7-5681-485c-a4ad-f1121977cc3a | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
2dafe234-c350-4a22-b05a-4618d50078c3 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
2ec9f44d-2040-42a7-a15d-e49edf39d141 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
400aa66b-215c-4181-95ec-7b0e831f1bf7 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
44fe6654-06be-439c-887c-70312b9f1c44 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
47ce586a-09a3-4662-99a2-8fff6187df98 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
49cc4cbe-ae3a-4e43-9dc4-6547476d1c7c | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
4cffcaa4-5daf-41a9-8b4c-2a7062fe2ea1 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
5865ac4e-a73c-4af6-ad1b-2855f0e051fd | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
5c4f95d1-d523-425e-9963-647e5a53c5fe | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
691e566d-b98f-4afc-8531-bb44156b2843 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
701d94bc-9812-47e0-8ac8-132e8531acae | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
708ce6c9-1517-4ddc-a7be-264312b1ac38 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
70d32056-7851-4462-aa51-fa56955ad38a | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
724923f7-f34c-451b-9e8c-fe74dd568deb | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
74866de0-16c5-4b62-9d23-2b95b0ad037a | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
7f8b7030-ef5a-4aa9-a69b-48627e76fb78 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
8621246a-ca6c-4f4d-9c76-f902012c90a3 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
8d8d136e-295f-4bd5-a39e-370d80b33820 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
9443dcbc-54a3-49f4-bd68-6a4199c6044e | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
9785ba76-1aba-41f1-864d-849a201fd1e3 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
99e20059-b9cc-4a3a-9f4b-b2912bf19144 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
9b33a883-46e6-4e44-a5fb-cb23af6f1daf | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
9d022b08-baf9-4dc3-851c-5f875c872ae3 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
9dbdf0c5-a323-4342-af6d-5dad03f7cd5b | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
9f3d9b3b-c7c8-4231-b897-17f0e3dcb676 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
ae116213-af5f-42cc-b484-d2d33bee6dee | Pole | 2 | Distribution | 2022-02-17 | 2023-02-17 | Level 2
b0b78394-d538-4c74-bd45-fa3c8b5519d8 | Pole | 2 | Distribution | 2022-02-17 | 2023-02-17 | Level 2
b0f2f717-f4ab-499f-8053-20af695ded7c | Pole | 2 | Distribution | 2022-02-17 | 2023-02-17 | Level 2
ba1957ca-b71b-44d6-928c-e08a6c85191c | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
c0382428-dc2b-4b99-8042-c74090e94096 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
c05eda3a-6618-4736-94c5-3774feb112ff | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
c1b5acd2-946f-4d5f-a591-52b40de913ff | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
c65a2464-72d2-4e03-b050-aa50e1bec388 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
c759a3a6-d3ce-4df8-9543-3c2a63ed597b | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
d73ac0c0-0bce-472f-b676-a3d01dae965d | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
e6a04be2-e75f-415e-825a-bd372c0d6d15 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 |  | 2022-12-29 | 2027-12-28 |  | Required to Re-inspect a subset of assets
ea1fb652-0fd8-429d-80d0-084ea93c2976 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
eeda8052-0c8c-45c1-b98f-525241ff9abd | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
efbee5aa-3981-42f1-92b4-a6e75952b7bf | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
f9e503a2-28d1-4614-9105-80b064f10829 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
0f36032e-a34f-4754-91dc-47ff2a73a780 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
10ed8733-af37-4da6-92c8-9fd2f663e4d9 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
10f20064-542b-4830-af34-68bb174c67d5 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
1b3ce024-4b1d-422d-a0c3-3f9b51d9ee13 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
20ebfdd9-851a-4144-ba77-0625426e7d2f | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
244f07ff-8cae-43b4-9289-1cc2efb2b7c4 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
283a6378-1bd6-4d04-9e97-f397374239cb | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
37bc1523-6a11-4ff1-86d9-7279f88c8d46 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
4e389dee-70ea-4356-81fb-848fef83676e | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
4fcae5b4-076c-4606-90eb-7451fcc61311 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
54f4a338-1b7a-4e1f-a3df-9f70fe166300 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
552f0a00-eef7-4833-8a3a-4c29ddbf7b79 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
5bebe5ff-2c01-4b56-a77f-80dcc59928a2 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
5ce7533d-3ee9-41e1-b22f-ae9f635c88b4 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
5e59230f-37cd-4b9b-9a74-00da4dfc6c55 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
65a309c1-cf6b-4bed-bcae-32cb6208d3b2 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
66d67cb7-0a5e-4f49-92b2-dfcc25c0c996 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
67d30b97-97b0-4a62-84cd-7797cbc7b27a | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
6a4a1c51-02a6-4b74-b82f-3fcac6619351 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
73417c36-a5fa-42e7-b7fa-016da35491c3 | Pole | 2 | Distribution | 2022-02-18 | 2023-02-18 | Level 2
76bc5507-d5b8-4391-b358-fd12cb4faa44 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
78061a04-4fec-4305-93a4-7cfd7a4b02ae | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
7ae8bcc0-ff28-43ad-821f-34df53e64856 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
877f8b4c-dc66-4311-908d-bbcea4e4d9be | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
8bd616ac-809a-4ef6-8ae4-aebb96ae6c54 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
91550388-5b24-4a68-a5b7-6af2371b9823 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
96ac7bc1-1d28-4af4-8a56-4082430c47f2 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
96ee963a-a3aa-4fe7-8aba-3a3c507240dd | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
9d0b1f07-aeca-4179-9c61-d5c19e29d82e | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
9ebdfd81-25dc-409d-8f99-287299a905da | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
a1244c25-99ee-4524-b910-82767ebe789e | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
a4b3aed5-09f3-42d6-9182-f9fe12c38c47 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
ac5e64b7-acb8-4a6c-bb1e-19af91331589 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
b5061134-142f-4342-8014-0a2d767e3bbc | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
b574719a-7966-4dfb-b4f3-c52cc84fb70f | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
be5507f0-60d3-47e0-9691-1b65485e38c7 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
c41a0ffa-8e5a-4fc4-8324-75301f9b0219 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
c46eeda5-e1b1-4d5b-b74f-77cffee8366d | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
ce444bd1-7843-4a24-97ce-db8d482edaf0 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
d422ad98-a166-4f00-b5c3-d0ffb783b6ff | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
d8e7a254-8a3a-4de6-be80-3ae534416fe2 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
d969d457-fe53-4ba4-b9e9-b87c641c08a8 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
e3510e28-1307-4d46-9454-ec5d1a1ec04c | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
e9c86fb0-6313-4803-b85e-72184bea0efe | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
f063a576-c2b0-4457-b0f0-97e0cb588a4e | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
f271782d-5511-4e1d-bdf3-28767b2d367d | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
f3cd9c1f-4c46-439e-8a76-2812b3465187 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
fb9048f9-5624-4264-9d5b-e8011ad6c8c7 | Pole | 2 | Distribution | 2022-02-18 | 2023-02-18 | Level 2
fca214a1-d141-44ab-bb2f-c84e9fc310bd | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
ffd4779b-c0d9-4725-9b42-351f37b59c47 | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
10e876c6-2a1b-4a9c-bf84-44016aeb1892 | Pole | 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3
264b5ab0-413d-448c-8116-10d1869718da | Pole | 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3
5187767b-3cdd-4cdb-8f9f-10e4aa4480da | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
52c0de77-d992-4514-9d56-36c61b61bff1 | Pole | 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2
859ba831-d0d3-4c11-84f3-8617d3494973 | Pole | 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3
bbfbd9e5-2a43-4cf9-8d63-384354e6193b | Pole | 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3
bc29ee4b-f7a0-4828-968d-3e0639b738ec | Pole | 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2
d6f3c386-d7a5-4808-b5dd-fd681b500b73 | Pole | 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3
e97f345a-3839-4f3d-b1f6-c654779fe4a3 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
ff865cf6-cf44-45b0-861c-7d275610101b | Pole | 2 | Distribution | 2022-02-19 | 2023-02-19 | Level 2
02e2ef56-f561-4295-acac-ac41e9847395 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
1d7adb21-0340-4c49-bdee-7f24895a2ca2 | Pole | 0 | Distribution | 2022-02-21 | 2023-02-21 | Level 2
27bf932c-cdd0-42fa-bae3-ffae46450035 | Pole | 0 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
37fa9bba-bcbd-412a-95af-4e2d9e84c822 | Pole | 2 | Distribution | 2022-02-21 | 2023-02-21 | Level 2
39633e0d-56ab-497f-8238-3a8df6bf0422 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
3987970c-c1ce-46c6-b15e-53928aa69149 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
4b4c7bc1-cefd-4e62-be59-d42b422ceb0b | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
77826756-5e17-4d26-b134-e37ade697d3d | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
89f49812-93ae-46ff-962f-b7b67ea85506 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
935fcf7b-57f0-4309-b78f-19e5b8f9afb3 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
c8f056ac-db16-40d8-8fa4-89a632372d17 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
d0679a56-a508-4998-a368-beb8db0243c0 | Pole | 2 | Distribution | 2022-02-21 | 2023-02-21 | Level 2
dd434e8d-f495-42ae-8a3c-fbc483fa85a6 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
e234c2b7-5a0f-487f-a649-9d28f00d1a91 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
e729f543-36a5-413d-b31c-4375990c69fc | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
fadd5227-6d6f-4ef4-87be-8f1aba1ae6e6 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
fe07a373-030c-4e43-91d6-e4896f5a4256 | Pole | 2 | Distribution | 2022-02-21 | 2022-02-23 | Level 1
ffbaf2c6-7462-4317-a18b-a21a6807b544 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
0cd63da1-526d-4da0-ac70-547f15f64ce0 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
6b61782c-fec9-4fae-bcdb-f8a67d3504f8 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
7504ee01-d24f-47c7-9e2a-53653be8e7d0 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
88843017-9c65-45d8-93d1-b860d32ae628 | Pole | 2 | Distribution | 2022-02-22 | 2023-02-22 | Level 2
ba12ac90-f81c-4d8d-9070-2cff1aceae74 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
bb4bd015-9872-40db-8d37-12119ad44acf | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
c6096db7-aa5a-4245-a2c2-a96b032299cf | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
ecb58d8d-80f7-4f95-896b-ce7a0b23d10f | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
0140a406-6179-42b2-b2a0-71b36891e433 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
0379701f-b44e-43d0-9341-899221cc2669 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
07c28662-ceac-4cd0-90ce-8232d672aabc | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
0f7a0ee3-6487-43b9-904b-33fc1a81d8d6 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
124dea7d-f27f-4eaf-b349-c1c7a50111de | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
17c56006-77aa-4bad-9700-66ab807ea020 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
1c5378ec-3677-4013-b0b2-c329fd782dec | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
20450006-f432-4668-b702-b8e36c5bfddd | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
2e6fb196-3097-45e6-a10e-27664619e9e3 | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
36069986-be44-4faa-8aa2-6eda045b2330 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
372548d8-5d80-4e58-8835-e36b0f7f89e0 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
3caf99d2-0abb-439c-9769-a4ff298a68f5 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
3f64f689-52cc-4c2b-94f0-4ebce548d03a | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
4909c102-847e-4b1b-b3b8-96117b2f076e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
4b6d1296-b85e-48e6-a916-2b30cb4661b6 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
531a22fa-866b-4e53-ad53-89fd92e25d63 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
5a4c2575-d784-4717-a5b9-5b04aecb63fb | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
5afd6502-8f0f-4a16-bf57-2f2f56ceb31e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
6173cb7a-c893-47af-a28a-4a74f1e27324 | Pole | 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
630fd4ac-7b24-4af2-8518-c56c321a5816 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
7494c47b-292c-48e2-88e2-df9f87ce0379 | Pole | 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
78875fd4-13a8-495b-85ed-64b32539bffa | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
7b4ed4b5-987c-4178-8126-47e8fc35ae06 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
7f527968-df73-49cc-9f05-cee645222c12 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
8214c438-9985-4466-ae83-4df0a16e2e41 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
8623e559-0d0a-4e71-a711-b09f3f779f4f | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
86cef1eb-f4ff-406d-a915-fa230d2b4ce1 | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
8ea93489-bcfe-4f13-b958-deafc56beff1 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
b7bc3996-5f98-4d41-9f81-962473fb8e46 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
b9628861-bc4b-4148-b1fd-949f998b1025 | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
bd5384c7-4bd1-4745-97a1-ac54117d1068 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
be02f36a-9b3d-4e56-b48c-c3225cb948d4 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
c187a387-0679-4feb-ba14-1b09635120f3 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
cac1df23-bf75-4e0c-b092-534cadd6ed8e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
efbcf980-3eb9-4358-b4b4-fab2c7cbd84a | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
f064449a-ebf4-4c12-8b30-c523861c16b0 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
f43ef478-f816-4534-807e-30a5f1e2b999 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
f4b7252d-7706-4bb6-9124-504b40c9892b | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
f785a383-b8c7-4949-92c5-a96f19b711ea | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
ffe7051f-b693-481e-85a8-15ddc753f00a | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
0c1fa858-08cd-4b10-b081-f06df53fe855 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
0d0ce0e9-ab78-4daf-89f7-b341bd58b579 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
16d8cd56-e13d-4341-9277-3a576765b208 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
2241ac4b-d0c8-4428-b8d5-dcc663a03eca | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
2da0467b-65de-4db7-83aa-5af6beedda0f | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
41d6a7ff-eb55-4d3b-adc1-f1ad1336eb34 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
4707987d-5239-43ec-a193-afa0d31cd8d0 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
4f6414e8-2baf-48f5-b9d8-7b32a0de8f13 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
50ec66bd-cf4a-43bd-86e2-f06446bbfb0e | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
592a28d7-5d44-4ec4-9df9-d4a543d9502b | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
5a6e904a-a5e0-4884-b599-84158bb3e8a0 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
5f74188c-7d0f-4654-903f-dd07b1ff2938 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
617233fe-4179-44f6-8e64-2079d1e94090 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
653e1c9d-7ae1-4705-8755-43c539383418 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
684a79c0-7eee-4735-8346-84c7d8926b0c | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
688af7c8-9566-4874-b32b-950521a06c76 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
6ba47bd8-a400-42ee-b779-bb1cc7941ed6 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
7c3e3bb4-6a83-4dad-b9f8-7f3ed34fde94 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
7ee0fdbf-ca7f-40d7-8618-b74ec406a621 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
8020fb5f-2f00-4302-af7a-fef6bc43c26a | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
8be489ac-8429-4a28-87ab-64885de3e9df | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
a0dd75d0-b4df-4f0f-b125-6856ded774d3 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
a8b4ab2a-eb29-4e16-9782-63034f4d0465 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
bbef76b2-3d90-4a6b-b2a4-4a9c7b9a4934 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
c19e6e65-7d10-4a44-a241-18982b285b54 | Pole | 2 | Distribution | 2022-02-24 | 2023-02-24 | Level 2
c8847889-53be-40b1-af9d-59ce98bc74ea | Pole | 2 | Distribution | 2022-02-24 | 2023-02-24 | Level 2
d089bd9c-b2d7-4026-9d59-f64fc9a6ec5a | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
d5049150-9b22-48c4-a7a7-a8b1ec4eb6b7 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
d5f16ab2-8a29-40b1-85ed-73ee67224e08 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
de35ac6e-74d0-42c4-bbe0-ce163b65e1c7 | Pole | 0 | Distribution | 2022-02-24 | 2023-02-24 | Level 2
e7a4df91-179a-4d39-b3ea-90d33d5661a7 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
e7f729ce-ace2-4cd7-b676-9d4d161b25bd | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
ea66c5b7-9c80-4ad8-8e4f-c788116c06bd | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
eae58e54-52f9-4ea4-995c-125da0f0f215 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
eb996fe9-c479-441a-9a73-d88a38ca7f49 | Pole | 0 | Distribution | 2022-02-24 | 2023-02-24 | Level 2
ee11176b-3a19-4089-8484-06d7561fa353 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
f1e8c6c2-4de8-412c-aa2b-e4963cdf9c0c | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
fa420291-7268-418d-a286-ffc4591be4a5 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
ff36785d-4895-4b39-bcfd-64f13737584a | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
007adb36-353c-4d60-9351-f01847004a89 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
02287107-b5c9-47ad-a076-6b4080f37575 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
193082a7-e68b-4ce4-8a3b-9b364ebc950c | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
19e6c6d5-3a10-431c-bd3b-6269206237cd | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
1e4290a2-bf89-4ca7-b567-b0f90682ac45 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
2b6404e0-300e-4568-b19d-daeb5f1312ff | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
2bf7b5bb-b699-4a78-a386-b22cc4a00aa8 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
34b536ef-9926-4a28-979d-9ea00ff0c04a | Pole | 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2 |  | 2022-12-28 | 2023-12-28 |  | Required to Re-inspect a subset of assets
356e602a-f24f-4c41-b98a-1b0be6e758a3 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
5608cf3e-092d-4b1f-ae9a-541d43d2f86a | Pole | 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2
698955df-c161-4a9c-967c-36ac6dba11ba | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
7c10a9ac-4ea9-498f-b730-4b1065e51329 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
809af1d9-399a-47c9-8fb6-8efba13a0af5 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
81eaa342-3487-479a-ba94-4d620a038329 | Pole | 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2
87acbce1-183e-469f-89bb-f3aafed8179e | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
9e1f1fbd-075e-437b-96ed-f2611da9d845 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
aaecfa6c-cfa5-43f6-8b5c-d38d2a748b99 | Pole | 0 | Distribution | 2022-02-25 | 2023-02-25 | Level 2
ab3c6590-a4df-42c2-8121-9cf7647b2562 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
bb82f9b8-e802-473f-8a06-6d61c026f351 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
d25bf3c3-6e57-4a85-99ec-e293ed6810b7 | Pole | 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2
d3b213f5-43c0-4075-84c3-bd43f7297c41 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
e3aff06e-22a7-4b19-9110-190114a77c6d | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
e7b213d0-3779-4907-b2d9-3f148b7206f4 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
fac502ae-f6d8-4080-92ee-301b5930cafb | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
fcde8853-3f14-4a30-91b9-6e7d7e542ef6 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
0b6fa2a9-15c2-4fb5-a732-95b67d772a09 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
0d772885-a904-4855-a0e0-707a9fa963aa | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
16402208-3df6-430e-8b4e-ee80422b2254 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
35e5c18b-0dec-4bfc-bf48-1f60948ebfaa | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
42f85533-e863-4a93-87e7-99415f5e27e5 | Pole | 0 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
4de6ce0f-cb74-44fa-be5c-062afe46e7be | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
528d45cb-0f42-4079-b4b8-49fa9b7b5315 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
62489f1b-d54a-41e2-a264-b7bafe0d0157 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
6c09af98-be98-4462-881f-f1d78def1e5c | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
766c83e0-a3aa-4e77-b637-e8ecaf1b61ed | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
83f5d058-7808-425a-b206-12cfdbffbee9 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
9231d6f7-6fa9-45e8-aec7-b40fecdc7368 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
a265bb57-349a-40eb-9932-c92587748cde | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
a6107ee3-4637-4ff1-89f5-6e474a425c0a | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
abecd5f2-eb6e-415a-9c75-aba7decef107 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
b44346f8-e0ac-49ec-b4b8-4b41fbd05c58 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
c455f87c-68f4-4a74-8c62-9f34c883b9ab | Pole | 0 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
cbee412b-ea08-4e2e-8dd3-d840df3f1c60 | Pole | 0 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
e13607fb-4ea9-4e5a-914b-bb659cba38c7 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
fd91963e-a2cc-43a3-a68b-18168ae3086a | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
0986680f-8214-4c22-94b3-8c32954200cb | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
122eb7be-1c77-4245-a809-e09c54b2adfa | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
16d48e85-5980-4fb0-80e5-af92cd8c0c12 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
1aca49f4-c0cc-4aef-a70e-09b25742eab9 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
1b9986ea-83fb-4867-b847-047d3ba37992 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
1e45b898-c7f2-435e-8349-fc7809bc9f55 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
24618b52-1670-4e55-a09c-e2d1fb43c8cd | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
25f2e63b-c85c-4234-9ffc-04de760a6776 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
2b9f9207-d3aa-442d-b07f-39d280f770b2 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
2fa0521b-e61b-416a-8f2f-3c0c17fe21fc | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
4a28b787-6012-416f-8b40-7721bc6fcedf | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
4aa52295-2248-4da6-b326-9dd4b4f35a9b | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
51034a0e-ea9c-43b2-8941-50c489670c8f | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
6d074cf4-a17a-4fe5-bfe0-6de6cb56cce8 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
727405c8-18bb-47d6-b2d6-6f98a423c685 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
78d36f79-29de-4990-b920-353692b06c85 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
a40c9abe-5c76-4fd4-a070-8f009638f197 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
a4347ef1-435d-48df-96da-8f1ed3f0eb54 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
abc16615-7808-45bd-8c70-2b5542d2bcc1 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
cb9757c8-d8a8-4991-8515-a062a28b9290 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
d117c99e-354c-49ac-b4d8-105333acd364 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
d62fa4d2-caab-490d-af6d-57a57fc0cfb0 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
e0db64da-2c9d-4cdc-b766-f48469b85041 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
e55eebf1-bf37-4a9a-bd12-b1932e810128 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
e62875a8-dbae-4925-a593-342f2b8aa66e | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2022-12-28 | 2027-12-27 |  | Required to Re-inspect a subset of assets
ea17fc89-d740-4a5a-8096-ede5873481dc | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
f31d21e5-944e-48ac-bcee-c29074c92159 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
fc784963-eeb2-4201-822b-6048a528620f | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
fe559a22-c1bd-4951-804f-41f2a2e465dd | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
0ae7b352-2068-4074-8fab-d548e5c6c68b | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
0d16fe95-8650-4231-a428-68409e9a8f3a | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
18973631-330a-44d1-9202-597c7ad5e5d4 | Pole | 2 | Distribution | 2022-03-01 | 2023-03-01 | Level 2
1dcabb81-1f56-4fea-bca5-f7f19f9bf01f | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
2c55fe27-4cd1-4e2a-ae51-18a99ba78830 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
2ceee83f-745a-4463-ab2d-78d3abdec0a1 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
3bbcdad2-e1dc-4fef-810a-019ee6ab95b1 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
54c80c86-bda6-4faa-b364-0de74817354f | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
62bce5c0-f588-45f9-8106-4ba0db955ef6 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
630e4df7-3669-4d57-87d2-cdffd369ea1c | Pole | 2 | Distribution | 2022-03-01 | 2023-03-01 | Level 2
68b18736-b7b4-4bca-8d46-59248f476a1c | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
72c4c84c-87b0-455e-851d-825e40159edb | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
7ca3e4fb-fb83-489d-98aa-772562220747 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
859fd0c2-8fa4-4bf2-9659-587b4e5732ba | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
86d91ef0-bb98-44e9-941b-17e6c4447ff3 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
91136101-af1b-46e6-b620-206deae7a9a8 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
950a67c5-1730-4be5-b8f7-2437a7ad8fb3 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
964f3cce-fe69-45c0-8bf0-5f65bfa42529 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
9c4203c1-b39b-4541-b373-fa82aaacf2bd | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
9eb1cdb7-024f-4897-ba8d-65150cefb10c | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
ab4e4237-c38a-4bb3-9480-54759f5a47ed | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
d68284bd-a701-4957-a1b3-f3cb139f7a64 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
d73636b1-e8b1-4abb-ba62-27cbdf69c45b | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
dc5d2b55-535a-4145-9186-3c2a0aa11515 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
dfc8b817-3d10-4b7b-9a0d-2c4a12f2d3e6 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
000345bd-beab-4323-b047-7f58ba23bfbe | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
0748d31d-9a0e-4785-9110-e2548baf68bf | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
0e86a72c-b6bf-4b5b-8af1-ae60b9358040 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
118db6f3-3972-4377-b6ff-70f0658a1503 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
122a807f-c7ec-4aed-928e-6b3d4f503e18 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
14b43334-4892-43f3-a1a6-aa38552380b5 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
18e5b3be-284d-4902-a1ee-d6bb5ce2f183 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
19f71cb1-dbcd-4170-8ae6-25e7ed818a99 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
1c2f1ab1-2d58-4c48-bb42-ecbfefa48e04 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
27c9ae21-8533-4ae8-9740-3318625968de | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
2f111a29-6b32-457a-9820-681f39c0f7d4 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
2faa0286-4d2d-4802-a602-1c0e8b995b19 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
33061a2a-6d36-4520-96b4-52f28f78dce1 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
3659639d-9882-44da-bdbf-68aa293c1ee7 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
3df0bec5-a624-49bb-bd69-1c3c07bc2706 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
3ef96de5-6e55-455d-9012-0c5a3bc12f1c | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
43ffd650-ff5c-466c-b1d9-bd4eae98c628 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
468e7a72-aac9-4875-b6c6-7ca17a809add | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
474acbbf-1f6b-40c5-ab4b-c83d0bf93411 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
51708ac0-d11e-4bd3-8f62-d39b0431acc9 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
5e33c42e-4c59-401e-9915-88db56c0ed59 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
680f696a-d323-4268-9363-35638b749d85 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
693d6d3f-43b6-483f-b596-02f3e434f733 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
6c215b98-b1b7-497e-8a66-3970d8a5494a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
70944a0d-756d-494f-b125-25dabe12863d | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
724d5e19-ee2c-46e8-b91e-82c5961309eb | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
72bb551f-6b47-4005-adea-85a9e259208e | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
75ecbeb3-bf64-4fa9-ae16-d7357816e3e0 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
7adc2332-94ef-496d-a96a-f6ec2947f265 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
7d018483-bba2-4200-9adc-8c381cc929e3 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
8146167e-d080-4c28-8fe0-198b6e8a9165 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
89657559-0bcb-4d5f-b8e3-84122ca68424 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
8a979b76-6ec7-41fc-8585-4eefc8cf724d | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
8bb2c126-9068-4690-ab94-4f64edd7f3ec | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
8d118ee1-dd6c-495d-b2cd-52df3a96953a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
990158fa-e96c-4f0a-aa6e-c1664130a62b | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
a36c39a2-d592-40bf-bb22-32899f3d83ba | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
af8dfd74-8f2c-4b62-9813-3fcb014ba1e9 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
b2336ecc-a1d2-43f8-b9b6-427b9730dd83 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
b6260d5a-1901-4166-a6c1-b260bbeb57b6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
b772229f-97fe-48d9-b003-e5f11e0eb8dd | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
b8834e72-d29b-4778-b42f-e2b80f7f191a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
bac01e77-1f47-4cf2-8f25-54a526864b6e | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
c7863bf5-26e3-4ffb-8f1b-71b33ed22fc6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
cba75e47-6f96-4558-9d85-e6d55a79ff4a | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
d1b72a86-f7be-4903-9054-deb205701c4f | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
dfcf8a9d-eb91-4253-8590-a160c4caadd0 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
e7f4af8e-02c8-44ad-a67e-14d3f4c94fbe | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
f13f03b0-6587-4546-a4d0-864efa88dc57 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
f88c8f7c-92a9-43f3-bb9f-b123e322da59 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
fa6c7baa-32de-4b98-ab22-a0e03ab650da | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
fcc1597a-45de-4181-b63d-34996c6ce1ff | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
fd775da9-8175-45c0-8c64-c18753d96dbf | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
fff10f7c-ed25-49bc-96de-64b2a069d9d6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
06206f9d-eda9-4c5c-96ed-3f59c4327e0d | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
06aabdef-f5bc-44f6-a49d-3eb35336f7a2 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
1da73f04-c984-40a2-b8e6-9f9366d0df20 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
33f59594-0c27-45ee-b5ab-3493515073f6 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
4ac35a51-82d1-4533-9529-2c6634d7ceb8 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
510b574b-7121-46fd-9f6d-6a84ce90a9e4 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
620954ff-355a-49c5-ab33-e6a060c052cd | Pole | 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3
758290f2-01dd-4589-b57a-e87f0f5f5633 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
7c1d2fd2-d98e-46eb-81a6-748860f7b50d | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
9d132614-0aa3-494d-aac5-3e3d460483ed | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
aba0429d-c04c-49af-99a8-cea2d2e7aff6 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
b413799e-05fd-45c5-802e-338b566158e2 | Pole | 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3
d99fc235-3238-444d-9910-8b9558db73fa | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
dbd1372c-c638-40b0-a3db-cd5693d7c804 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
025e007c-06ce-4b46-bbc8-5cabb0bd4861 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
0df5b45a-6aee-4b6a-9dd8-4b22c3ebcaa5 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
0f662efc-3ac0-4aa7-8a02-0ccfc133df98 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
2024979d-c021-487a-a2fa-a2e6d07a09c6 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
24d2edde-aeb0-4236-bc19-ba4362ad2f40 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
2ded8066-d4b4-40f2-bd54-ddb7872365cd | Pole | 2 | Distribution | 2022-03-04 | 2023-03-04 | Level 2
2e409d41-287c-43f3-ac53-499d40a97fef | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
32f9d99d-e77c-4545-b2fd-f5ebb3e666f4 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
335cdb12-6083-4253-a219-067cc0fdfad4 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
34aa068f-eae2-42f2-a339-f27e7fc0244b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
353766f1-44e7-4178-94c1-8ac40f110f3c | Pole | 2 | Distribution | 2022-03-04 | 2023-03-04 | Level 2
35b4d4d0-2fc3-436e-96ad-81964433385a | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
43a65242-1c7c-4286-9d19-7d97648a390f | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
45db216a-e14e-45c7-a114-8075f729ddad | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
5c8cd669-43da-4290-bf9e-f9ac7d21bee8 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
6d4e04e6-91fd-44ad-922e-62012c0d31a8 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
7e19f252-101e-4b08-b6e8-824cb7ed7eb6 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
7e3b28cd-1d10-47c2-84e4-8c62190a6099 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
819a3168-cac9-4bcd-a941-a3954609b813 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
890ce002-3f41-4eb1-b37d-b6be1048d91b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
9117be77-b5a9-4744-ac55-c52b5de5f09e | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
928bbc33-bdbe-438e-99a4-bea302d0435d | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
96708bff-8bc3-4550-a2fb-20e3b30d5e52 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
bf515492-9cd1-4193-90d2-9bf157917115 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
c06e8002-8e70-4553-8c1b-822d3e181b18 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
c182d3be-fafd-4868-9269-acef9b47712b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
d500bc58-e23c-45c1-accd-4d30e52bc300 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
ec42faca-dcdb-498a-8bf6-a60434c3b19a | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
eff1c26a-66c2-4481-9297-519c502653d5 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
131a2118-e6cd-4620-b5f6-97f79bd425d6 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
194af122-7ba8-452d-92b4-2e945ff7b1bb | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
47dd40eb-38a8-4772-aa88-a283ddcf0597 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
4b093598-5e42-4a39-9233-e1fa149ee236 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
7ed130d7-1186-4547-9330-9eaeda9697ad | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
99fc7cda-66cb-4d16-9062-7493c69c22ed | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
9e2e4c11-0309-44e4-895a-2def76648e70 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
e0b22470-e823-4b0a-94e5-b34563b87d3a | Pole | 2 | Transmission | 2022-03-06 | 2023-03-06 | Level 2
fac6a3a0-75c0-4c0e-ad42-252501c6f847 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
0e8625a3-c494-412e-836c-1be5916e8639 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
2372f5c2-cc0a-49e6-ab1c-2dd7fcfc068f | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
26765015-9d89-4141-800e-c39046580bad | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
5e0722d8-69a2-407c-a314-57a8661cffea | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
61ca8aa9-9f93-4772-b94a-3ed5add449ce | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
6e286861-2fe2-450a-8b00-e5f6fe613bf6 | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
8eddc616-56e7-495f-bb7d-c5fe14e9b934 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
9de101a5-29f0-4ef5-8b1d-7282e3de919a | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
c00c60ce-8573-4a4d-ba19-025391d89fbe | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
c791507e-d6cd-4eab-8f9b-d1af5e25a67a | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
dba0de0b-e910-4ad9-b9e6-2f78914fc9ae | Pole | 2 | Transmission | 2022-03-07 | 2023-03-07 | Level 2
f0e1f223-0124-4ccf-bb14-f3bb9f41e348 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
061c8eba-3bb4-4ae2-b7f1-8549334a02f6 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
17c4164c-08cf-44c6-8260-4c22c1d562a8 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
2f2523e0-7813-45e4-8a58-ef81b4ccec88 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
3f0c9acf-3bdb-4b70-b93b-c4aa35120ab6 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
464b835f-a798-4131-8016-4c214f0e213c | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
52b3bb82-a148-4fe7-9809-3d3e3af5559a | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
68836db5-75d8-4aad-a2be-cdcb197bb3e2 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
846e663b-edf0-44f5-a7c8-537674ae3985 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
8c01093e-fe1e-4abd-af6a-3558a3e369c8 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
96fda099-61e5-4a65-854a-88b07f5157d5 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
a9167ffc-b364-4904-a8f5-90858cd97fe3 | Pole | 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2
a97070f0-5eb5-4298-9b6c-ebac96bd5688 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
b11d56e4-ee07-4482-bac6-a5e36516ec30 | Pole | 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2
c35d1544-aa74-4417-8cdc-e81f255d8238 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
c7fca155-0652-4ee4-aafd-7503a09ce007 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
d397777e-e891-43c0-a84e-2a74a7c45f8b | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
d6cb10d1-d7dc-4e0b-ac90-b2b353c48f06 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
e6c1721f-beb8-44ec-b219-19a1059a8b6d | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
ed0f6aea-7165-4fff-88d8-f9867587887d | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
f789fc99-b2a4-4bb9-bac7-c403caed68ae | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
f835e242-4b66-4e7c-aca2-3697a3f0e3a4 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
fa230d1b-f768-44e5-83c6-09183d8e629f | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
1df7f79b-a981-42fb-9ac5-455e1dd4b0b0 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
23537b86-62b8-4250-b35d-034eaa1c1141 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
605e7139-bc15-4384-80a0-e9de124b5015 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
af0375a9-c7d2-4a90-8acc-34d85a7f13a4 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
b4476d03-25d1-4434-8c0c-a7902095b7d2 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
e3246536-3dcf-44ef-86b3-5c19328aaaac | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
025c4b62-5b4b-41ee-9419-e27acc7063a6 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
13971505-5365-4f01-b581-24e6769325a5 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
16798d74-022e-4437-b25f-649b59081b37 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
1a7643da-9618-40e6-946a-8c2c2d56714b | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
1d33503c-9bc0-47e7-be14-b1b53691a757 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
2372015e-64c0-44b8-82b4-73056cdde97f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
3762d4c0-5d25-4785-a9e3-5393c12cbe86 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
44633787-88e7-4af9-8ec1-e9972e059db8 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
4c46185f-0b39-402b-9e8e-0151e4082e2f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
52b8496e-426a-4ded-a03e-132ef352601e | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
676714d5-68aa-4c9c-976e-ef813cfdd699 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
70ddc3ca-18fc-4e3d-bd71-0c7c693f97e4 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
7d05c622-4a5e-4882-a671-a9fd262946b0 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
84ae0376-9280-444b-acb0-b7842b97933d | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
a7b864e5-96ad-4fcb-8fe0-2a97a37e631c | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
a9b2b03a-df52-4c65-9dfb-9318ccfb7f88 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
c20c1f1f-7462-4211-b5fe-e4148c16ef12 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
c6234b52-1401-4d86-a5bf-0b4e08381ece | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
d113c1ba-623b-49e3-94e8-7bb9c3f45b3f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
d517e014-173a-4cb2-9a87-c627e1ed8a30 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
d58cfff1-e5cb-4ca6-941c-109affcbddef | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
d97f7481-1c54-4655-9e44-51522b00fd8f | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
dbcbd99c-ce34-4b5b-9d40-0c33de97ba90 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
e4e59f0a-d1a0-4a64-a2dd-b5ea44bacfe2 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
e7def9e7-d7af-4c6e-ad1d-d26eb717d698 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
033d17e9-55ab-4c53-818a-49b90ddc6cd6 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
141c7577-c329-4591-a877-0a7d83bbdeca | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
279d1e14-2627-43da-8c7e-af99443f339f | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
3715d1fb-91fd-423d-afab-7c8bcae80623 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
4ffc6e7e-0a2e-467f-9c1d-9cf72424c2b4 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
5960d81e-af50-48d2-809b-ae69fa14be13 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
5bd81093-f232-47fd-af7e-68e5c0bf90d3 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
b53bf995-0386-4ab5-b6b0-79cd85d17735 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
b5c03242-7eaa-49c0-ae4e-6d9717f62e71 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
bb356c05-3af4-4b7b-bf4d-0d0ac2b45127 | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2023-03-11 | Level 2
c22e7131-2579-48a3-ab97-aeb489c57316 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
eb530aad-7b18-4fac-b711-865eb071c1b3 | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
eee6c825-8770-4f13-9298-273ba7da5e09 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
f13d4655-f3b0-47bb-82d5-09c840a3b9a3 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
17d3c5ae-1a61-499b-85db-e0afebfb141a | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
4603d0bb-e271-4150-ac04-2241b42f860f | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
5a6ed601-50b4-406f-923c-17ec889eb8d1 | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
7075171a-6818-43d2-84b0-f7c093960da3 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
7153b268-c1cf-40b4-aa2d-f4b3f25affbb | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
7db679cf-c015-42ea-b516-0a4403ccf871 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
94ace622-8c1a-4609-8a33-472cd42734ce | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
bb7567a0-885b-4452-86d5-374a14e2e18e | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
c4cec9d4-5ec6-4229-b888-cebdfe9d179c | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
d45e9353-79be-4969-9c66-566d481027a5 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
e0259b07-0c21-497c-b08a-7ed5e2506f97 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
e59ccf2e-acb0-4adf-a134-86a8d15c4b63 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
ecffc587-cbd4-4a44-b6bd-d80c02e982a7 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
f4cc5c29-7835-4f72-9951-9bdf8a231d8b | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
f5b65d56-f626-44d4-8be2-369d271c7370 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
fbe3fd4e-af09-422e-a17e-1a62ea52de69 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
ff1e9233-01b3-495b-a602-4c463825dc1c | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
0478cc94-0f0e-48fb-9852-d500dc8bcf42 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
058b3238-f344-4a1c-bcec-4b27eb6f203c | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
1c6a1ff4-0a94-49aa-8583-8f3abe9d7f26 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
2ef72a3e-2478-4340-bbcc-a488360d832c | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
482bc288-e8b7-4f39-88be-0a7740247e14 | Pole | 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3
5c3a802c-4785-4db0-94c5-f154d611ed32 | Pole | 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3
6aeebeca-82a7-4a2d-b9bb-6abc2d989058 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
7c24e023-b231-4b8f-91c5-0ec59d66f256 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
8d79dd12-3bf3-4cf4-ba22-431cffa0d543 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
974c6e73-1861-4b99-90e5-856952a7e3bd | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
eb82dac6-5d55-4953-86db-1f69a16c99db | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
2956fbb8-2b4d-4f3d-8950-2386873a3c59 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
42b8af2d-2292-4e20-84f6-bd12843b48a1 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
5ea6f806-94d2-45f8-afee-bfc21a9cbf00 | Pole | 0 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
95e725ab-d539-4898-959c-e9efb0a6c79b | Pole | 0 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
ba8d0a27-5b02-48eb-9c07-b4b7aec6d00e | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
dc5068f0-666d-4743-98c9-19c05a143aa5 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
1ed9d52f-bb57-4ad9-87a7-c23c4b844308 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
38ca824a-2abc-4ad6-975f-4110e77e4fd9 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
3b57e49f-aed7-4e4a-88e2-06675e5e4418 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
42e3d468-2f5f-40f2-951f-286f35f35b1c | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
5360e95d-af7a-49ef-8025-dfea3146d5ce | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
5600602a-e0b6-402b-9576-b8c528e3a1fb | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
68d65041-18be-47ff-a2d8-0f37eb7854f0 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
79096de5-208d-4f60-a25b-925873503991 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
811602ef-6022-41d4-99e1-d86307e3e657 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
81a9eefa-5d2e-4fc6-b919-d84d93a2f74c | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
84ef54bc-3380-4333-a157-497a39da266e | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
9743601d-a563-49a9-b989-53394adbcef1 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
9932d08c-9950-4b33-a9ee-87efe222a449 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
a4681f11-8df9-4cab-9864-b15c560da8b8 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
a5644755-c84f-4047-b25a-a818fd232486 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
af7de0d1-50fd-4fcd-a12a-e7c4a4a54ad7 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
bc49c0ff-57c7-471f-92da-29a03735adc2 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
c4f945aa-aab0-4a0f-bc6f-4f279b5f19a3 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
ca843b56-99c9-4151-9145-7bd4b7645870 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
cba3d22f-5dcf-41c5-a4b8-2e838459ff38 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
d5ea176f-2f85-43dd-850b-9a70d0726a03 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
e56b0a19-d77c-434c-90c1-636d57a1142c | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
1763ee4b-8321-454e-8bfc-b13cc1e079b6 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
30a5ebd3-baba-41ee-926c-6ac341664752 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
373bf0b7-ba44-4850-b54c-41ea75be2660 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
48dd83f8-80a8-4950-aeee-27004f83fddb | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
6b4ae72c-2ea7-4e35-8810-0ffaf2bb1ea1 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
828b8419-e97d-445f-a054-db36bc5cfdbe | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
9f148b51-c9aa-4630-bb30-0c5c88046c5e | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
af4e0761-fae5-457c-b4f1-9ec961b0f9ad | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
b02104c0-7b96-4c69-91a8-309110eb8cb3 | Pole | 2 | Distribution | 2022-03-22 | 2023-03-22 | Level 2
e3db88c7-f89c-4738-8cdb-81fe55a72999 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
e90f28cd-d6e7-4851-a7df-b91785c877e9 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
140aa5fb-4683-4775-a87d-35ca405d2236 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
1aac4d42-464b-4da0-b231-20b6f6a06b97 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
23774c31-0797-47d4-b0e9-8bdd8bd27e94 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
3ff87b0b-e34b-457f-be4a-8695265fc19c | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
447ed10d-58ee-48d8-89a5-867fb454245c | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
499cb009-44c9-4dc0-bbc1-b6963ee863a8 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
4acbd570-1d2d-4ffc-8438-a62d218c4ac4 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
560db93d-3c89-4f60-a167-677f58802def | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
56166386-a26e-44c9-a6eb-d4262ef2a8d7 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
5ca58bf3-0258-484b-bdc3-30ad06f4fdb7 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
67b5eb10-2680-4429-9b60-994e45a85302 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
6dd3bb92-e7e5-4228-93a7-002478038549 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
7b5dee18-6d15-4e99-a3ae-8dfdabc965c4 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
7e043f09-b91b-4d40-8029-d46cb83e6b84 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
8e20a9d7-45fe-468e-9f69-e23d7ce2e508 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
a6bfd5ee-865a-4814-9e0e-1df0e7600bf9 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
c1baf5f6-97fa-4434-977c-b1e1136be72b | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
dddb4116-46de-4952-a2c4-738668f1ea8a | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
ea9b8a76-f067-45f2-b25c-685d63c98253 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
f89b896e-07a6-488f-96a5-543230fac341 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
ff778ed3-80c1-4d7f-951a-48916ff6a921 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
02f1711d-c3ca-4a27-9542-6712e192c178 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
0a7892d0-e1cc-49fb-88f8-147c3111999c | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
16c7a8ca-d294-4077-8444-0473df29aca3 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
38b8cda4-4c09-4873-abd9-113c145665bb | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
53373121-98de-448e-8c85-35b9576a6869 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
5d79c467-6219-4db9-ba36-b0a8a8d0431c | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
635f9fa8-3766-4c4c-9dbb-8ccf5eb329b5 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
7140be2b-e3df-458b-bbfd-117749007274 | Pole | 2 | Distribution | 2022-03-24 | 2023-03-24 | Level 2
a27afb20-a99c-45f5-aa39-f36d29624e88 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
a2fb0a9c-6906-4fb9-900a-4fac4be7bb0a | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
b175498a-a063-4229-9b97-d27f8d7cfed1 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
d36fc3d6-2f3c-403f-9526-d1749b72f8a2 | Pole | 2 | Distribution | 2022-03-24 | 2023-03-24 | Level 2
e1c6831c-fabc-464b-a2af-a95acc347472 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
11243b97-53ab-4744-a034-24451762a977 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
513fd5a0-de8c-41da-9d72-1424d6b94193 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
6699147a-6673-431d-830b-225a8877bb19 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
69aaa11c-e5c6-419c-9c55-729a62cd0f23 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
6aadc235-7fa4-4d37-aa2e-1fb1c9f33c10 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
74e58603-8cfd-4988-bcd5-e30bcef68217 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
b4884129-3fd9-4d6f-b444-1c305127ca1f | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
bc74636c-5151-4683-b755-1a6d7a31847b | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
d7e5092a-f441-446a-a6ff-2aca2538685c | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
088d6e8b-8dfc-4af1-8424-a7b20328ee6b | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
0a09f7b4-a52b-4f94-ad95-54c10d0e50f1 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
1a93eb3f-f827-489c-a224-2a114bfcc464 | Pole | 2 | Distribution | 2022-03-28 | 2023-03-28 | Level 2
200ff739-41c9-4c5c-b5a6-d450709308b9 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
2f7fe449-2991-4db1-9ed4-233caefc8f61 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
30ebaf39-0ece-440a-9dda-b9718906fa0c | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
33765a7c-2407-42da-af75-23c078fcc578 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
3eba6a40-cc51-4e45-9881-f709b53de4cb | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
4c7c8abc-f686-40b3-bd47-59270d8226ca | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
4e889c56-a03f-4a27-b96d-b61e7750e2e0 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
56b7984e-4a35-4040-b664-d056fd093793 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
572334fe-7128-4c46-aafa-e15fde3d0406 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
576433c1-00d5-4142-ab60-574f73f8b481 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
587ebae3-8915-46d9-9018-31dc45226ac5 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
5a74840a-f070-47be-b881-55be4791cae5 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2
630ee49b-cf2a-4f03-a499-9e6fb80d8444 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | 2022-12-28 | 2027-12-27 |  | Required to Re-inspect a subset of assets
64329c5c-0eac-4146-993f-db6c62c47c6f | Pole | 2 | Distribution | 2022-03-28 | 2023-03-28 | Level 2
7113c053-0d5e-4b37-ac1a-e0d5289233dd | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
7e9a6086-1a1e-4600-b621-64b022f371b6 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
8ee6f7c2-e248-4b75-813a-f29ff833a560 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
9caefccc-45ee-4908-b9b4-6bb22162fda4 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
a9e1c32c-16e2-4bf6-870f-594a27c27380 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
ad30b0b4-deb0-4522-8234-f90c5af20818 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
b2efeb4d-1763-4ae4-b9dc-f8deff9b794a | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
be47bb45-9307-4fe5-a58d-b5404dcd5477 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2
cfe47165-b819-443c-bf13-89f001d9a641 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
e4faa2da-69fc-40ad-8f2e-a51b483f43d0 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2
eb64b061-18b7-4d35-8d61-aa1c863c4a85 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
ee0688f6-7625-4b66-8f99-be251eb47300 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
f1796a26-08d3-4992-8b1d-64e4efe52a50 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
f1eab8ff-b0b7-42cd-a2df-61ca5e145a62 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
f9d49df4-00fb-497f-bfbf-417c02838a38 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
054d5142-3c61-417b-93ed-a94b7bdfd801 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
0dbf0317-a7a8-4698-a4ca-3971775080b0 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
2ef54a15-4c10-49e5-b567-5e59d0700826 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
31a23009-f25d-49b6-a3fd-d5cc12cd7295 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
3680f66d-8301-4e4c-8077-ed8fe78e3c7d | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
3e4d9860-54bc-4284-b86d-482d1087a4cf | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
41241f71-55e4-488a-b5a8-6343683eef57 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
4cf2f11f-0be7-4345-811d-b4c6af47fae1 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
56dcb4a9-f149-4118-94a7-fb0ae769b8bb | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
69ee62c8-ae3c-4c3f-9e09-4154c499eb66 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
82ee6174-3cb0-4c52-afa9-ebd956c2e838 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
843ea2ba-a32b-45e7-b2d4-f9055a18cb86 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
91361795-60df-4b1a-9321-0cfc53bf378c | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
99d7243f-5c8e-4660-a75e-fac5c6b459bd | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
a4eca477-882c-4782-8ea4-8de3006f2571 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
b697c0d1-222d-449d-a7bc-49617e4acdc7 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
b9cd256a-feb4-4d90-826d-9822a74540a3 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
bed53dd8-e7b2-4f94-a8fc-2fd562ab41b2 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
c2587685-8648-4dbb-8d1e-39f7c60a65c8 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
dae60379-6f06-412c-b840-9ea6044082c9 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
db47ef52-d8ab-4a74-8543-6e9adc9515b8 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
f09b139c-1fd8-44b1-b6f8-f3886641beaf | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
f60e8afb-b15b-42ea-bbd2-a02f3193f59b | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
f8100800-b33b-45ea-932e-630f87eb3779 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
09f1c01d-3812-4691-a333-c4f67703de98 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
158ff743-f443-4039-8f3b-147887272a04 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
2a75247d-d462-4a28-92d0-6ee95d5eab4f | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
2c212e12-c84b-44a5-bcbe-ecfc211beb0a | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
371f7c92-04ec-4d25-9929-44772f4a543d | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
3ebe0cbb-27eb-41e0-b609-e6202b6571b0 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
40129d3b-7c9a-4e64-8341-5b5bac0bfe11 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
467f7c03-befd-4a18-ba8f-0168f99f851d | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
5cdb3d41-9a5e-4fb9-bc38-4c99dc3e3a60 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
77da13f2-e51e-4343-84a8-8a2bbd21f480 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
80b7baf0-df49-479c-b1be-683135d89104 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
84b52372-589a-4d67-b45d-6df73a7fe2dd | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
9997ec9b-751e-4adf-9db4-16b7c38b2cef | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
a285c7f0-7141-4cab-b006-5ce892882fef | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
c54573f5-0856-4cf8-88f2-d2c71b3747b9 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
f3b5b8b5-252a-4bfc-9474-f51b9a84c246 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
011ec3be-637c-4c53-8455-19bd724131e2 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
0433e635-6459-45c2-a96f-dcb378c21e73 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
0d818849-b462-47b1-b64b-09034da53661 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
2526366c-7d72-463d-b87a-572826383f6c | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
31a70705-7cad-4c98-ad1b-346a1a5fa69c | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
3427a04e-af38-44c7-9dc0-03f25aea0c47 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
3bb02784-7dc2-4e8c-a3c6-e36fd5d31219 | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
449a3fd9-6a15-4edb-adef-37eecac70186 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
4c41728c-b3e3-48a1-9d54-839cac4e7513 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
4fab5f0d-3051-44dc-85a5-b019491ad3cc | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
53c60202-2fc4-4d0f-8eb0-64fad0838449 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
54ccdac7-65e7-46aa-8772-7ac31e642101 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
6c6ce9cf-af7a-4b5e-9a32-872c136f8d6e | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
6d1b0110-1392-456a-94f9-dcf6ff4171bf | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
78e82791-ec49-4494-9f03-0e875b4e68b1 | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
7ce90122-c092-4e49-bccb-85440ed0b30d | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
80ae8e82-c16f-4a96-9269-1ae027ba6cb8 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
83d5dd95-842e-4913-a37b-7420672690d9 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
88780bf0-6e73-41fe-9dff-845115867a46 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
8b443ca0-7851-4a81-8ab8-8d63a71b476a | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
8d4f6243-4f8c-42be-a198-dcbd678ae2c5 | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
8d54dcdf-1a6c-49db-afda-98e99130de1d | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
8fcbcae0-1ef0-4008-9785-8fef12aede6e | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
94b9925d-0c4c-4917-8b7a-3b98ee27b73d | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
a6325903-5690-4566-a643-a95167b5973d | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
a9bfb66b-f162-4b34-98b5-7dda4204c231 | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
b1aa0da5-f4a9-437c-90d0-ca0a246abe10 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
c4d29819-fed4-45ff-b7a7-ca68887233e9 | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
c8bdab78-0c5b-4209-871e-e9ea2e4e3118 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
ca4720c8-5ed2-4db6-a280-b55370cf589a | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
cd68c314-02ea-47f3-a18d-6f8eebcd2459 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
db67ef23-5606-4962-88af-aa13d23541ee | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
f18805e4-d2db-40f3-8e7f-36fa9d0231fd | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
f3007a7b-d884-4d87-9f70-33666733bf30 | Pole | 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2
fb204016-655a-44a1-9307-fb449a10c57e | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
fc83b659-098c-4bb4-81a2-adb559ab8f89 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
11951544-ac09-410e-9b67-787b49f3dfd5 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
230a7703-10ba-4f4f-810a-614f4f8df84c | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
3490a2ae-cf9d-443c-a876-3945b1a2ddd8 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
3d208c10-a999-4b35-9b2e-947f166c2fb1 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
3fbedee7-5a99-4aee-9a4e-471dc904f736 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
57298da4-085e-4a72-9192-b84b02d621eb | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
60b388e9-9190-4be4-844d-0f31aed95a7e | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
66a36bd6-ddf1-4343-8ded-318b84afcc04 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
6753f49f-78be-43e9-b0e1-7ad99d995a72 | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
70490651-8848-40de-b6b8-6db69485859e | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
771a1a54-c679-4232-8d62-bfebeeeba78c | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
77a734b1-f825-4a0d-bfde-f8fef4f64205 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
827c4128-d223-4814-9725-43e1ae045916 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
88a46452-182b-40e8-a311-561508acf7cc | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
9517ff8b-70eb-4a79-9c2c-13f5d37f6027 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
9d54261b-583d-4de6-9a34-5a3bc96ee7c8 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
9ddd52ad-27a2-4940-b3bc-9183c21d6be5 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
a64b714a-e86e-4c91-8616-7eaab0d4fde5 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
aeb3f051-68ce-4d17-b99c-3a30c040d614 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
b419a52d-bd16-45fa-92d9-24da7540126b | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
b749afa2-f60d-4b16-a6ab-c8c92391fb2b | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
c1d3a587-eb86-4aff-8eee-3859a1a8b293 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
ce7d0427-8658-41c9-9497-c0adce5ac409 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
d0ca56b8-d416-4434-ae5c-41f9b51005c2 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
e8803a8d-62e6-4fea-8538-962bde8504f9 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
3e4167d9-5472-4774-854a-6b53e05d62a5 | Pole | 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2
42416bc3-b0fb-42c1-9961-e231d17186db | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
536882ae-ee2d-4682-a30f-02f7efdd9622 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
588474a6-25a5-4a6b-b3e4-08a6f6898b19 | Pole | 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2
6490187f-9bae-4210-ace4-826a81fc03b8 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
65aea2c3-65de-49ea-8c7b-da0da71d7c4c | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
6ddc633d-747c-438e-9737-1ba3a0a6dc06 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
7bbccf90-29eb-417d-8e3f-62545c3ada82 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
891c7007-934c-4802-926b-c92f036b54f8 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
a514a183-210e-4d3d-9669-be29f8443e5a | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
bcd9aff4-460c-4c49-948b-31c213e9d26c | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
c51b68ce-3e6a-43db-9fe1-9ef47b103ca9 | Pole | 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2
cd81920c-5d4e-42de-b358-916abe611f0b | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
d34f4cf2-e8c8-456a-8526-104005306e15 | Pole | 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2
e707e466-721c-4732-9532-a9f6cc279846 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
0ca8a859-b5cb-4f82-b0c5-f891d553eb89 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
1357eced-8afd-4479-b82c-152944c3f572 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
17110f8b-c3ee-4ff3-a026-e51494e1cf8c | Pole | 2 | Distribution | 2022-04-05 | 2023-04-05 | Level 2
200d0718-05df-4d68-823c-1acba6231fd5 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
204dd1bc-82a9-4f3b-87d6-1c611d5c5d37 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
4b8543b4-81d4-43a2-b8c9-a9d1ba053787 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
51fcd251-20d2-4d11-8ff0-5e3c30eaad34 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
5c2db236-cb0b-49cf-801d-540bc544f344 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
5e98754d-8e65-4817-b4ee-f93d0f3b5073 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
82d11acd-3ad3-4f63-9d6b-46b184452ad4 | Pole | 2 | Distribution | 2022-04-05 | 2023-04-05 | Level 2
9644509f-ddb0-408c-aea3-d01dbd944b83 | Pole | 2 | Distribution | 2022-04-05 | 2023-04-05 | Level 2
a39dd90a-6368-42a5-8bdf-ff9f0348990f | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
c41d3b73-5ace-40ad-8145-f8563c8d2a53 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
c4998d00-7245-4eeb-bb67-208def1546f7 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
c8d0333c-1ab8-4836-9766-032e21e4742d | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
ef7fea55-987a-43d3-9f22-203f7c6236a6 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
fad86c80-6615-4b44-8b56-5f6200dcffc0 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
04f67fff-4a65-4373-bdf0-ff776df5fe0f | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
0dba6e19-acb0-4b5d-bff5-f55abb94f985 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
21da8d67-1551-411d-89c4-80fa9c5de0aa | Pole | 2 | Distribution | 2022-04-06 | 2023-04-06 | Level 2
31889cf0-d500-4f53-a3ae-768c8a99097e | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
406e13b0-2310-4f0e-93c3-465097c609c8 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
b456e1ce-be9f-47fa-b2f9-6637c376e266 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
06fbe163-02ab-4510-b071-ab68098ccbf1 | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
110e256e-ed09-42c0-977b-6ab387d4d360 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
3312cced-0c43-47c9-9268-33658a56b4ba | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
41ed7441-2394-478d-8c32-528aa9839a6a | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
453e5e4a-a4bf-4062-9c16-7154c57a7647 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
47ab9d43-bf03-4de6-9615-c79cd8e6f57e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
5c4e7dde-77b3-4613-a6e6-7e362b1c0e91 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
663b25fb-2e31-4bf2-8e46-eedb315e366f | Pole | 0 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
759dd31a-a29e-47a2-acbf-3117e4dd7a3e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
7f5d4317-8e59-4210-8d36-86f829a70cf2 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
7f7458a2-d63f-4f1f-af4b-ead310ce806b | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
93df7ac3-a101-49e7-a9a0-081db111c960 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
989d3a22-55d6-4d04-be3e-072a0db3b5ab | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
9dd4116d-078b-42f9-9b94-92ccf7f1ebd0 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ab44f8dc-89e3-4176-850f-793b3f19f46d | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
ad3b4396-71e8-4b29-b5bc-9954921e8a4d | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ba31ea8c-07c5-4600-a7e5-0892d7adaa56 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
bd236c1c-cf93-4583-9c18-f5e00a873ebc | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
bd59abc6-3dd7-4d8f-9199-94f9be846fb5 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
c3a29af3-8df4-4143-8864-b06a10d0f73e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ce61d46f-6e7f-4e8a-96ca-f5e12021aa28 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ec0e8d41-e7c9-428d-9be6-c293c45c8aa2 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
f073a40d-ec75-4bb8-bc0c-bd0bbf1fd031 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
f0a38a97-52b0-471b-ac55-f62e15c3613e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
1c918c01-a2cc-4e59-8a5d-7d05f9392d6a | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
2de84543-6ed9-41f3-bc97-3ed5812f8b5e | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
31144e21-548e-437a-96b7-e0e1a0ca98f3 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
4d2b8ecc-c3f7-41b2-8868-bda740cad8a8 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
50b30623-87c5-49eb-826b-7fe81ce79572 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
55843fbd-5904-4f14-a601-7845e4c47909 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
5f704f5b-9674-49fc-a084-041814e9145b | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
6a56aa29-5d24-4179-ab69-2d8a5118ae4e | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
7458865c-ccb2-4f54-82a2-011af5d3522b | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
752f7f4e-4f9c-4523-9d70-effcd4b9fae5 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
893d438e-38da-4a1c-8277-df8c921f331a | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
92ebab34-88d2-4e0e-af9f-1a54dee52310 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
94d4b915-97b1-4f86-831e-9194b52b6f18 | Pole | 2 | Distribution | 2022-04-08 | 2023-04-08 | Level 2
a9077e38-0a8a-4f05-bb09-d2e748847190 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
ae8a5b56-5f09-49c5-879f-39a52004dce2 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
b18ac578-5674-49dd-a472-13aa899aedef | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
cb3882a6-06d2-41ea-bad7-9ba7027598e6 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
dbde7c58-9f55-429b-8dd8-d36bb2fe4f06 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
e39e2aeb-ed41-46ae-a4e2-ff69b898c7db | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
f3c25928-8609-4651-a68b-3a65dcf43984 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
1544ccbe-fbcc-477a-b0e7-85f33f0a08cb | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
25ff992f-3184-4b34-9463-ea896bb6ce19 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
51520868-e8f7-4ba5-94c5-5cae244b6dd8 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
54b8461e-4806-4f58-bfa3-70ed626e1606 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
5b41def9-f8a7-4ace-a844-7ceb90ed3b0b | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
5da1ffe8-e13c-4e1b-8d84-4f24e9a59222 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
7f9f2bf2-b36a-4093-8a23-d04f9dc0d04d | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
a6a4386c-e04c-4192-ac0f-464059095588 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
ac825b42-2f9f-494f-8b6d-f2c0fbd2529e | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
afdbba1f-3561-46c6-885a-ce59a58a0cc4 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
b4b229c7-0dd0-4a81-ae1b-3a1b4db8ba28 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
cc00849c-8eb3-40fd-a6e7-ed38b13486ba | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
ccb378ae-b837-4738-8914-9a5503502d4a | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
e39b1d54-a22d-46ac-bce1-fc26a6794a4d | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
fb2d214e-b91d-435f-9f3b-e2b0845207e1 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
089da26f-0a22-4ca1-a226-62a94e2cc3a9 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
0a66d65a-3fa9-421a-a1f7-65d9dac49469 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
0f60ef12-9527-408a-a304-d1cd7f4d30b2 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
344dcb0b-06e1-412a-91e2-0174a804f168 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
3be52607-611d-403d-a3ac-ffacf6f69c22 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
4771aac8-e424-4297-a657-bb9d8165da26 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
497d4a24-b574-49c4-b47b-d04eb2b34f0c | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
51d941da-1ea2-4b06-b1cf-ec2c7b918d12 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
539206c6-785c-4360-a057-97571eb7e5e3 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
67c6b4e4-4d9c-456d-9889-c87907659f09 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
802ae38c-43be-4b1e-80ae-be0a03e89114 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
926910b6-22b4-4d03-8804-2453d9bf325e | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
9441e91c-7b1d-4fae-8a31-5204036dc095 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
969808e2-e63f-4c96-8cad-34e50ca2ecc0 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
a0e8e8b4-792d-481e-aff5-af88c1ab75b6 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
c335708a-9c1c-4f52-bf0a-372951cf6e28 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
c3e0a445-ba3d-4db1-a5b6-2b7f678cdbf5 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
ccbbf5d6-424a-4913-b12b-3ce684553850 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
e49fc700-183a-4e03-bbc5-1d93cdf59c53 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
f753bfa8-481c-4af4-b311-b608006f8799 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | 2022-04-12 | 2027-04-11
fcfb005b-5af5-44af-99dc-1f9859caa707 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
fd57bc9f-3544-4a49-b01f-6742774af9cf | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
fee81b88-0170-40b1-ac9a-c7c944a7aa14 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
0255c325-77ac-4d86-bd16-8bfcf45f9eef | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
04033804-b4c3-4d80-830b-a7a95b8a0527 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
14ce59cc-2383-4ff6-81ce-09997389c907 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
15a8510e-5caf-4f94-9c84-c23352144894 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
69c465b0-603c-49e9-9907-7b1bf9244dbb | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
6cc8fef2-8517-4e54-a02f-d6c447c29159 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
73784f6d-0fed-4606-8086-b489dd4a3696 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
85c234cd-3fb1-428f-9e56-78e3f210c822 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
8c5cb3bc-b7b1-47b7-9657-3e2f254bdcfe | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
91263e8a-96e5-4cef-a764-64a1dc400f17 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
9b7fa005-09f1-4e72-8f0e-2bb4c688d2a6 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
a05159f4-3bdb-4c11-a05d-1e6c4436e9f4 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
a1423266-f9b5-4b7d-8b63-98d7000c94dd | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
ab8fca95-315f-45d5-bacf-483be38d6aec | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
c3f2adc2-d576-4016-8bc1-42810deca7b3 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
c5fc0e98-f616-40d7-b78e-acd718d8ce1d | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
c691edd5-ae00-43f2-a5fe-e310b773e7eb | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
e3342162-d6f8-46bc-b0ba-219d23c2d252 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
ec7f82f8-4b5e-4598-9456-79c5cdfb747d | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
f435a7b8-06f2-4b6b-9fdf-8eb65f08c292 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
fc2c159a-ae49-4cb9-8688-dfea83f773a7 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
037de28d-f5aa-406c-bf65-922fca677062 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
1b946904-148b-4bdf-bc48-70d5ea50b3db | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
2303c569-23d0-4e2b-b11b-dc1230aac3f1 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
24a2500a-92e5-4d31-898a-ce2468c06c84 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
2e3e75b5-cb8e-44b1-8231-10e37d7be6c1 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
37ced4df-2357-4c0d-b9bd-ac2b485fd4df | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
38bfc3a2-e04e-48d1-86cc-97d661b1b849 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
407180b4-8080-4c0f-a1c5-5c48ee428a7f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
43605e97-3ece-477a-b27e-5858505b3b50 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
46d1fafb-47ef-4b24-be4d-2d611d53b42f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
543fd334-c0c7-4361-9569-153ef40dce9d | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
5d7d532b-9cac-49b0-85b7-43685b3ce849 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
6caa2c64-cc49-40f9-9e73-38d20bafa34f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
703ba5e6-5988-46a9-9e1f-78c2902721d8 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
74d9f9d2-5c33-48fc-98f1-f7de4db96d26 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
7bbd07cb-c488-4df5-aa04-48a1aff2bd68 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
95aadd0c-83fe-45a7-a906-9627397d36a0 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
95ade939-2538-4008-a08a-a823d6d34b66 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
a148c546-02ae-4f0c-9be8-3204d556ff2d | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
a7978a0b-a636-40ac-a42b-2b214aee9077 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
b8a3c1c3-60dc-49ee-8451-c633fa64a3a4 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
d6104597-b904-4237-93ea-5baf8c4e7b46 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
f7ec1070-6f3f-4d4a-82cd-fd760bd250c0 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
0cb11de0-c940-4107-85a0-a362719d60c1 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
22b5057e-3d76-4c55-8b83-048e78ea29a6 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
3272f139-72cd-4f0b-a678-c87a55274de5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
34188dce-9593-4da6-a8d3-a23c78bdd2e5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
3519c253-e12f-425c-9bd3-f0f540b08283 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
3b25ab8d-845a-4f13-823a-e24707d3e252 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
46fa10f8-a381-4ff6-bf27-65ad50a860fc | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
4daae178-c498-4952-973e-9e2ca33f41f5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
5149607e-d663-4d92-aeea-0b0e5e11edc0 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
53e22257-d863-45aa-be5a-4b9ffeb2db7c | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
58b1dc1a-2f93-45e5-a588-25d0000094be | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
5f9f2e8d-c191-46df-bda3-118d3523d4a2 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
63639052-7d8a-4148-ba18-da2636ec976a | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
7cb83437-f6e7-4e3b-9150-24b9dff21a2f | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
7de8a9a8-846b-4e38-96e9-a4952b78d819 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
8739f452-dbb5-4f7e-9b92-be33290ec8c0 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
8db2bfec-bdae-47d2-9e9e-ed19224acec2 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
98219143-1471-4aaa-a415-ba60d1b34d14 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
a1d4f08a-129a-452f-9c9a-9d8b7e8e747c | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
a696cbf6-2311-4295-bb81-6ca5690ad502 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
b0578be8-ff41-49f0-ba78-8b5266a06dee | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
b08889ee-cab6-4d1f-9820-0cbb0b6c1890 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
c117febe-713a-4a78-9ee8-5730bd8cd8ac | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
d118a864-2860-4ba7-ba06-8da6829be47f | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
d670ffb7-afd5-4a68-983c-14c8a5e8e42f | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
e51699d1-2083-41bf-969d-ab7f570dc789 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
eaf92ed2-82d7-4d73-926f-43b6498137f3 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
eccfd6d8-acf6-4758-a83c-65180e565fb4 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
0bd4c211-2fa0-4ffc-a3a3-bcded4f6b868 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
1b308e41-8eef-4f01-8695-2f778faf43f6 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
254b66a1-7352-4c51-9f61-8cac67d87333 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
403edcc2-01cd-4a41-a9c2-0bf707958cf2 | Pole | 2 | Distribution | 2022-04-18 | 2023-04-18 | Level 2
4d7fbda5-e43c-46a5-b778-4afc68793f4f | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
52403095-c006-4df4-bda1-0ef42303f754 | Pole | 2 | Distribution | 2022-04-18 | 2023-04-18 | Level 2
56cf1067-2051-4971-8821-6c9641dd1a41 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
84533a32-7b4d-4dc8-ae99-e970c426cddc | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
9406777b-4441-440a-9a39-08327bd49676 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
98a38247-b04c-4ac1-a41a-1562fd198823 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
b332e4f1-6cde-41b0-86f4-7d0b268d74ce | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
de8bd420-d768-4014-b51e-342e27fff9fe | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
e134d490-b857-4154-a754-1a2975fc9bd4 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
e327c1cb-1cd4-4877-b74e-782d514eb4b8 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
f1ef87a7-0809-470d-8808-18e141ff2619 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
180dddd5-3a08-4127-80af-d0a2337d7d6e | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
56868fd5-9ff0-4f89-82d4-7be7a56e6942 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
6cba7a52-ab89-45a4-94ad-9102f1a5e49e | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
820e463c-a80d-4696-9060-5c0e91baedf6 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
ab279528-8f1a-4ad8-b7c8-fea9d47704e1 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
d091772c-f9c9-4cef-894a-56c98ff09b58 | Pole | 2 | Distribution | 2022-04-19 | 2023-04-19 | Level 2
e05502a5-09c8-4f79-996c-f04ee625a61f | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
054e0e84-f654-4554-a525-9a5221a953bd | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
1642a1ef-59bf-4d0c-a7e7-055505be9cf3 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
1fe9393b-6eb4-44d9-9b41-3e575a170eda | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
273ba082-00f7-4349-a975-b4e9df59307e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
33c04f36-79c4-4646-b225-429b502f1886 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
3abac912-64b6-4103-aabb-354e2cb0dae2 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
4e1d73d7-3d14-4f6a-9218-bfd869079ee8 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
78d1ccd9-3911-4bd2-9c00-40f31eb4a38a | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
79a0ecdf-3fd3-4e45-8e16-323b372112cc | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
9772a723-2f64-42e1-8cc0-5f1f82b1178e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
97873176-0c76-4b9b-9c10-0f7645ee7bfb | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
9eb99346-4d3a-471c-aa00-1effa3959605 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
a3f53bdb-f2d9-4601-b323-0be53c48ab01 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
a73c2a3c-debb-483e-b3a2-a01985a052e9 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
ade23e57-cc83-4877-a4cc-45570765cc0a | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
bc9af2ee-8b89-4018-b278-d05b9f6c55db | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
d0b676d6-e95b-43b6-a8e3-39baddb92208 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
d60cfa2a-96cd-41c5-ad21-ae48698acc3e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
db9b0309-2e8b-42ab-86d3-196ba68add20 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
e0dc8417-b16e-4bff-b3d4-49214f604e2f | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
e7870a9e-d735-4842-a675-f0b52c9d1bc8 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
f1b338dd-4222-4fb4-917c-e7faec94a149 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
0d610b10-2f44-4fb3-934a-9472302bb773 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
1f30e40c-e8d0-4759-b5d3-68467e64ea48 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
21cc9ccd-84a4-4e94-b033-832ca5e79404 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
3e2ef773-be85-4b1e-990a-d0a9323c28f2 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
515f9e6a-b336-470c-a130-22c684af9fab | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
58bfd453-3669-4847-8464-c3906ea0539b | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
6dd093d7-4d98-417b-8966-989557e8e47a | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
a5ef761c-4fdf-43a0-95e4-cacbc7df56e4 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
af2931f1-1663-45ca-9442-79950f592897 | Pole | 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2
b41acc02-a3cb-4116-bbe4-ed092a439a81 | Pole | 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2
d5ec9669-37ab-439f-917f-9370f770d13a | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
ee281a7a-954e-4279-8d5f-e3d4cdd508b5 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
00938a31-b0ed-44b7-a7bd-22d6337aea43 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
044cc782-1ed1-4432-9585-6b85bb948fbf | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
06b139f3-8c89-458e-af64-dc6b1526a460 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
0cdaa5f0-aa98-4c2f-a7d5-d704aec50ed6 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
13a4db37-d8f3-47fa-bf71-dae3fbb871f5 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
23bd6e0d-7625-4a8e-a9f1-8b199e2a657c | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
29b603ab-ec6d-44a9-8b96-6b949b6492d5 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
2a27cfc0-721c-433a-9041-b5969624522f | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
2d2b64bd-4bb7-44f2-9e08-e25d7689d582 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
2e60ca46-b8d2-457a-b7b4-bded61dd0418 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
39247234-a6cf-497a-8401-46673d79b298 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
47d0da06-5c16-43cf-9ea9-e78485957c69 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
54c6c5c7-af47-4c91-92b2-813046992f50 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
59005d42-b17a-43c7-85e1-68f2ab5a48f8 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
645df035-6d32-4acc-9e66-2e458f1374a3 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
82ffac28-abac-4ca3-bd22-91c804c21fcf | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
8eb17872-59c3-4c74-865e-633371a9a064 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
a551285b-18dd-46b8-9be5-6324e3b5fb18 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
c48b42c7-d669-4c37-98ad-fe93558dfe71 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
e79d5f6f-bec2-4403-b983-9f2af8015a75 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
04a9d646-9efd-4061-a678-7db7600e449a | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
0abf462f-4a89-4ad1-93a1-5c809be35dfa | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
16a33b52-5c49-4a86-91c8-2c426afc256a | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
2406f9f3-e6fe-47e2-ae4a-d7416dd2b1c4 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
2d9c6b08-ed25-4e74-b690-97155fd70bc3 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
2f243988-2fa6-48d8-abe0-8492a97c81c5 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
31905159-7ab1-429b-8efc-06ae07dee55d | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
3dbebf98-ac14-4bee-9c02-e676adaf0872 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
502368bb-6d99-4105-bda3-8490f7be749e | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
51b1eadd-a6ed-4bb3-be36-c36e88e52843 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
5d1cdcf7-cf77-4d35-ae7c-f4eabca8e997 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
710d83bb-840c-4a36-86a3-5a843c89ee4d | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
777597b1-ae99-42ef-8558-8ba002ddc946 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
77b6f8ca-e4a6-4ef8-8e44-f9036fe953a1 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
7df8c0c0-5b6a-4bd5-80e8-b7f7a98175c1 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
8015a689-bd64-48c2-a191-5a0f687408d8 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
8bea342d-0196-48de-9f71-45cb08c431d5 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
9639183e-8204-41fb-88ed-13a524577e27 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
9e84ef53-20a3-4b45-a4c9-854d11c5eef7 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
a008d37d-0cbd-4ee2-97f5-2d20d394eafb | Pole | 2 | Distribution | 2022-04-25 | 2023-04-25 | Level 2
a7685d84-109d-4a27-b5ca-1deecf092af3 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
b54999a0-3cfd-4075-95d7-bc9c75a9d4f2 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
c65a0758-fb70-4012-8743-352dfe10f458 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
c6a44c2d-b649-4509-ac88-16dff9f42731 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
c84c01a0-f68b-4310-afc6-b512fd72e013 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
d3e0b15a-ce35-4a71-811f-da58dc85a696 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
eab6a9b3-f84e-46ef-9457-61187b254332 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
ef4075bd-e271-46ab-8913-3db49c6b78fb | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
01d92645-4777-4f1d-b242-0334b457dfb2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
0367aa0d-f46a-432e-959b-d3859b0a17bb | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
038f91bd-8454-46a2-ae8a-e4908d660e69 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
069ed871-507e-4c1e-846d-c92cc464c1c1 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
07bfed0e-c746-4c8f-917a-4248316c2af2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
07d834e7-8f2b-49bc-87d1-27a6fd4dc5a4 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
0833051c-b789-492d-9806-12e8358f4344 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
17de24c2-dfd4-4fd5-98c5-57ccb2182bb5 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
2fc4bc29-57bb-4649-a741-e1ca849c9dcf | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
40f404f7-dc72-4dc7-8d67-686cfe847e3c | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
41b66920-69dd-48f1-b4b4-98ddbc999562 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
50bec5c4-71e5-4185-bf79-5361312f15b8 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
52f857ac-6d0f-4ba0-8e97-19cc8588bb8d | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
53a37f78-8993-4739-af06-b616d3ae3e77 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
542329eb-42b7-4911-8f1c-a2e944d44258 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
589ef09d-4c69-46b4-bd8e-274ab38f46bb | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
5a417363-4ed5-4d92-8015-12be423cd2d2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
61e83759-0271-443d-abff-525b6fd7e48c | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
663f2b28-a649-46ef-ae1f-4bf5ae717110 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
6a43f961-bb20-4849-907f-14538694b5e4 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
72b0d48b-eb88-4c83-9be2-ae4576358aea | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
758e15ff-a633-4495-b376-8b9a44799092 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
7bfc2379-96f5-4571-8714-afb7ee873d07 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
834a7a1e-47f1-41e2-b4e1-40aacdb85f78 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
85bcb33d-0c35-4fa8-be16-8f4a22edd160 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
8ea913ab-45b6-42fb-afbe-cf977650b049 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
952b4002-2bb7-4402-8ae2-30eadd29b6bc | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
9d29eb7a-6ea7-44e4-8ed6-023beb64f8d9 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
a1fbe212-3bf1-4a34-9a17-263de4bf64fd | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
a3c3384d-c552-468d-b240-683ae8907f38 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
ae7f8db5-b9c1-414b-91ed-49c90a051ce9 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
b2606c75-08ed-491d-87b4-5d9f1cbfcce7 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
b573f33f-f255-4104-b024-e25af92008ac | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
bc8417b1-5599-4d1a-9225-0a2b1b119973 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
beb398ae-2ae3-4eca-9999-c9c5570f9792 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
cd37d0b4-ddbf-4d47-b6ad-43d58fdfce36 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
d60e3007-fc96-476a-9381-ad3643717c56 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
e4499eb4-909f-47c5-bc44-525058e7f990 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
ef23f2bd-81ca-4be9-8160-d13efa8306c7 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
f4a4f0d8-bb92-4f64-b3e3-79cd6479c452 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
fb283363-5592-4be7-9764-10b624714f82 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
fbe9d800-d621-4c95-9fb7-259abe4e07ea | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
0318d11f-2f87-450a-b603-43d888a89f72 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
0629db64-83d4-41d5-80fd-22719b138975 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
0a0bacef-9fc4-499e-8558-647fd2c0be1f | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
1fd43ccd-e5e4-4e3e-87df-4397fee6dc37 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
212cb912-e24e-4343-bd3e-bfc6145ffcb9 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
22bf9b5c-b001-4d92-902c-43c4733d2574 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
26768c99-8868-4ec8-b111-d76c648afdfb | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
3636c18b-c058-4485-8039-e34bec8cba11 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
54f86c39-892e-46d8-941c-f9ade22d4870 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
564a106d-0ae7-4e5d-aa4c-e1fb43ea2901 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
5e900486-9d8e-4610-811d-28aa4893de87 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
62f47145-3205-4731-b352-ed7396aa41a9 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
690e78ee-29c2-46a3-81d1-af6c4c5f1c79 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
6ebf55f6-3536-4e8f-8754-927eaad90ecc | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
75f2268b-a5a3-4695-b28a-23761b20fd3b | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8250d725-cc01-43cc-8f23-3254f0e72d0e | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8301bf99-a3a6-4415-82a0-5ad16bd85f1e | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8b9d1e14-ace4-4f85-aba7-b989505dd28c | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8eb424bf-e1e1-463f-9772-2cca597d3be0 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
93d14fda-c6d3-4457-bdd7-bc80db8389e6 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
a2d3c3ea-e3d7-4b30-8838-6aa3cabef393 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
a985b574-9cde-45f0-8a41-e914321f1b1c | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
b5780f2f-838e-4fdf-8b5d-df06ce8e5484 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
b5ca188e-f899-4b0a-96de-c11d5246f427 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
b6937104-4532-4756-93bf-b225d7135eb6 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
c2ed1905-61da-4bbf-a76b-d7d370c77a5a | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
cb5945f0-9be0-45d6-8bfe-5bd12f4dd4af | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
d33b8988-f6ba-48ac-8fdf-af6285764344 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
d366d640-46a0-4f93-9247-7c19cb93fcbf | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
0dda6f65-eb19-40b6-b945-4fd6ca182da7 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
16a39b9b-e032-4f6a-a032-aa2a246c387c | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
17a215a7-a6cb-425c-9e29-130efbaf6fe5 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
198dbe61-54ae-406a-ac56-24a2c8805765 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
2617f26d-02ce-4ab6-8fd0-91eff4d3c449 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
27e3db0d-9a6e-4c92-bdcb-60af8abe9e3d | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
3405dcee-99a7-426f-8fd8-bed4543525e9 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
3aa036e9-1a77-4653-aa81-42b481a56beb | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
3f2d58af-39fd-41f0-bc76-431a4b0f6fce | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
42d32473-1f99-4f39-af4c-34f7cbca946c | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
4898f1f9-ca92-4abd-a39a-56c31bca5fcd | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
4c7c2b9b-fbdd-4d52-a0b0-f840144407c7 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
5e5568b1-4fd2-4063-89bf-358efa693e7f | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
63cbeda4-a91f-407f-ab3a-6c08e5bae3b3 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
77e090c7-9e60-4cf1-a15d-ea403e60a9fd | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
7a7993fc-5cfe-4c56-8496-d721b321e80c | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
82f7a0e2-0728-42d9-a38c-f0b89ecbc160 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
89271cb7-de87-400b-b17a-4c0701d14603 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
929101b3-b50a-4d44-84be-00e737994858 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
a40b1cfd-b0af-4f5a-a559-507feb57f89a | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
b6ecde73-ce19-4b8e-8f61-e46186057791 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
bcb273e3-5757-4cc0-91d4-cacb4de778b0 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
cb8582af-f8c6-4bf3-a8a8-b3b0e2f41052 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
d2d1e4dd-0faa-42c7-a490-9f331f9fd649 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
daf56ca5-a16f-4ba9-b2ba-6b728127123b | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
e1c833bf-37ca-4e04-8d08-70a7ebee73b6 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
ec81eb58-86e6-4ebf-a94e-aa7e70ab80c8 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
f0d50760-95a9-4cc3-a86f-8c427405f517 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
f0d82822-32c0-4fb6-8dab-3838b94dd563 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
fb9b2ead-06e9-4098-bbdf-db0fc5061f8c | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
fd946841-35c6-41e7-a1f7-55e477a766da | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
fdb9518d-3c84-4bbc-b469-0f43993ffffd | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
0234498d-ad8e-4b40-8afe-c0b403f2ac8b | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
0ac9c8ce-e205-4f36-9543-c097923f7b75 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
1536684a-211c-40db-9af6-4199a916d950 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
1761b84e-f0c6-4206-ae56-3e9464a42f90 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
24146a7b-51ee-4e81-931f-e2fd66909a79 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
246b2e48-94f1-4411-8a1c-d06c04444f16 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
256e68a3-61b2-43e7-9b00-931e4e44e6f6 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
2f43edf0-cbf0-4367-a620-63b001033c51 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
33a55016-349e-41fc-a0c6-e49767add75e | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
341b548c-ae42-4302-9ae5-3897ce9f0680 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
3d8bd53d-c6b2-49ae-b822-850928f81956 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
594dd444-ca51-40d6-81a4-94385fd0dacf | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
5bcb458e-9e6d-408c-a2be-98e3b88b0ec9 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
5e027456-795e-4b81-a8d0-86d8c146ea5a | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
5f92a481-35f9-4857-b3f2-eb108755e8fc | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
6c17c2d0-0b09-4cd1-89a2-07207a2abbb1 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
72db2865-e80d-4dad-898b-f9c98b309b2f | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
74e24c6f-a103-4377-a148-8c301e8b7ad8 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
77474da8-7aa5-4e14-96dd-175836619c82 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
79f39a65-278d-4e1b-a55c-f94a5e5c736d | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
7aa47c82-9e5f-4760-8cf5-15e50e48708e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
8306185f-f18f-4c0f-af79-55a742d53a5e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
83fb296e-0460-45fa-92f2-45e0d036dcc5 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
8fa52884-10f0-4eb6-86ee-aa719caf9619 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
9349ea89-26e4-455b-9bd8-3d9f11f2317e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
a4fe59d9-672f-4c29-a3e8-738250b92127 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
bff92b25-2566-489f-a195-93767608bd67 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
d697fb5d-d03e-4abe-a250-5b462f533741 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
d6ab7c48-9bab-4fbe-9b4d-9d860a9c2e0c | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
da380639-a5b4-4d9d-a9c1-5cf6b88927ce | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
db42f7b0-6a61-4b83-9a30-77ac554fc1bf | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
e1bc60cd-916d-4277-a384-2de9ebc1cd81 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
e203f001-da55-4f5c-8a55-2da7a8b35868 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
e6494aea-47fa-482d-8648-15ab5747b169 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
0b695171-55e4-43fa-ad21-9b83eba6753b | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
0c8e7d8e-9899-4ba7-9984-e99feba3ad6f | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
2ea8cfcb-d4d0-449d-934b-dfd1aa8f6d8d | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
318c7b46-e673-4d1c-b4cd-7f033c31d376 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
36a9efd0-30ba-4b09-a4bc-1f213624f566 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
4e8d5dc1-856f-4046-805e-8a954648c489 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
50e9f4d0-7941-412f-9771-49b22ff8dc5e | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
68ebfe06-637e-4f88-896d-96645b530d1b | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
6b025a29-d9b0-45eb-8b6a-ceb7dc88b186 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
7c473661-9e38-41b1-abcc-a26a97e1d21d | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
a505d7a8-f7cd-4f25-a549-362868951d27 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
b32b855f-f7f0-411a-a961-4cfaa24f7d7c | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
c8e92259-9b4e-4997-adb7-6853d5256c95 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
c91a2c6a-3c62-4301-b620-8dcedcabea6a | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
ca695a36-c0f7-49e5-92eb-87e275d4e714 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
df68ef83-7e79-4448-be29-50a71572d360 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
e2095962-bdf5-4afe-8797-0233055b99e8 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
e9a4e53a-1782-471c-88ce-8c7e5f9b216d | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
f8da13c0-8255-4dd7-88d4-16e2a797c1b3 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
076d4ef7-a837-4601-946a-029bef5e14ba | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
0c6f7350-a4ea-45fa-ab22-370ebbee41e7 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
228d2cb7-d7a6-4a36-a73a-283efe271485 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
48518f1d-2595-40b5-8924-6b742fdcb17d | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
61173988-c7b1-48ad-b17a-2d1497dceaa6 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2
6c05f3e6-37bf-4168-b966-e1438fc2d73a | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
77182ab3-77f5-498f-beb5-85cc3deb90e0 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
89cf2416-36ec-48b1-bb4c-9052cb4369fd | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
8a7b2d40-9237-4655-a519-21efd6f22c7d | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
a203d871-6590-4aec-8e96-ef991e36f81c | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
a6e2881a-c1b9-4c1c-9f88-d1fdc54dd3b8 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2
bd894413-e933-4360-912d-a32f8fea01d7 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2
d7eb3ac1-6b18-4425-9cdd-373363321ecb | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
d8032f20-9dea-48b3-914d-27c54b7f6925 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
e52e8fe8-90d7-45f9-b80f-3df0403efeb3 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
eacb7d9c-4cba-425d-bed3-504356e99776 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
0f3a120b-7446-4255-8ec7-6c7f193af38e | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
1567677c-816f-40d7-987d-c602783becae | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
26e12f30-e2cf-4a51-ae6e-051856c267e4 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
2d0208ab-1bdd-4532-a626-e644f08d8c7e | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
2dcec391-80df-4f4f-ad23-090ea3738b4f | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
34f2c261-e464-4c56-be2f-3610ddae6394 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
48c01278-af28-44e5-a26b-dd1d010abdf0 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
615fd047-d964-433a-8ec1-a8cd5e0d4b29 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
7814f53c-c373-417c-a2d2-629c3ac77954 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
7b7573e8-06cf-4263-82dd-d16c9a597d39 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
92155074-1e9f-4f27-933a-53155c709102 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
a153e5b7-67ad-4956-af3f-21da2c6992aa | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
ad92c3c1-1c63-48c8-8684-e93fb0e004a2 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
b97f01d5-fa57-44cb-815b-daac957d9caf | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
bf380df4-2c23-4518-80c6-9a6a4fb159d6 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
eddc312f-48a3-4918-837c-2a59bb177e38 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
0d3a0903-4db9-4957-9ba4-337edfac3076 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
13336123-cfb2-4bd8-81e7-16fbb24084fa | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
500167d1-0ff0-4bba-bea2-7a5a742042af | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
5a163363-d9be-49d5-81cb-72b428b16110 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
723a343f-4e51-4bf7-a265-9242d90af7b1 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
77b533e1-a452-4cfb-bea1-2b613a035e42 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
838dce41-ca2d-4d97-a272-98ca91f47122 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
8c54cc1f-12be-43df-becf-bc441ce52540 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
c27b9310-f6c6-489d-94b8-45352e6fcffa | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
df73a8da-26a1-42cf-98f3-2ee96cc3c1e9 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
ea185c55-88be-4ea7-a3e9-af69dd064868 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
ec320cce-d1a4-414b-957f-415718a43756 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
026d47dc-553a-4ff9-a20f-23e44e64751b | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
087f0031-9527-4d59-aa00-0124cde74a51 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
0b1e0fe6-1291-41a8-9a1d-861417c02db4 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
2737454e-4260-49eb-8111-875df1cb3b21 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
352cd739-a6b4-4fb3-8e36-c3e93f22bb63 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
3ae6c5d3-c414-424d-a062-5333682d7029 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
3f23facb-5a3c-4b5c-a791-c27ac33e4fba | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
4392d768-0901-4ca6-9d77-2ed47f7efb4b | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
5a5a41fb-162a-435d-937e-1b032e906c4c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
6907b8b0-ca5f-48f2-9217-fc197c6c7437 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
7f8d2fde-1755-4d97-91f0-eeb4f092bf32 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
810f9668-2368-4863-98eb-093f7cf724fa | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
866b2edb-b250-4424-96b6-c3b86a0976b8 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
8a5a4df7-ccbc-4fe1-a564-d7c289f777c1 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
8b29ee0d-724e-40bb-ba29-ac0ebe8559a9 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
93ada3f8-e853-4787-a2ed-f0b7870cd766 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
ad25fa49-2bb6-4179-8eda-e9ac9f8493ff | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
b0e440c5-168e-4668-8c38-693f00bd2aa7 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
b0fd0a86-c1e5-4e32-aefc-571641fea711 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
b5f26494-e562-47e3-a3bc-d18e02851bef | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
b605ea32-f156-4465-8b97-a49162316d92 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
d9d32242-3e75-408d-8370-e16d01cfb6f7 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
e7e3c85a-f8db-45d5-8aec-09f48a3bb715 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
f13f49c2-aba6-4985-9435-eb679b8dad4a | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
f446b843-8afd-416b-821b-2148b5ec5c88 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
fb4849c6-46db-4f34-88e6-445f80f4be8c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
fe002313-099b-4a80-ac35-3a3fc9088b7c | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
fe2e481d-f037-4f69-82f4-c7a5c959308c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
1ccc9596-f125-47b2-ab94-951452106206 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
21c82dd3-ecfc-4309-b9b9-e46f2e901177 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
28b07699-de04-4b49-abdc-d86aa11382d9 | Pole | 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2
4a2fb610-8807-42aa-b38a-797a84ff8f0a | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
56b1a033-198d-4bc1-a07f-0eb32b0ed58b | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
5cfe1468-32ca-4e12-a0ab-55474e125c06 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
5ec0681e-e7f7-4a7b-b1a4-6765bee527d7 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
63057f2e-0863-47c1-8d75-4a0eebe620af | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
75ea52d9-1dfb-4a06-a563-67a1589eaa98 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
7ed2ee1c-b85d-40f2-8f38-851856d0c1db | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
900da43b-04a7-45ae-81d1-de5f0af9f3b6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
90783e95-7e39-4992-b4f8-71b3128a9482 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
9ea2fde5-4db6-4f90-a51b-174fcdb5e656 | Pole | 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2
a42f0493-0684-486d-8333-e2289e0c3161 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
a5003db8-217d-4336-9f3f-db97e213fea6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
a83d38b2-dac8-4a57-aaea-bce505a923d6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
ba76ed03-2511-401f-87eb-e09e5f80b75e | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
bf0aa8b5-a941-4939-a381-93910f7fc02e | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
ce8c1933-be50-4ed5-8f7c-2ff099e88ca3 | Pole | 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2
dabed6aa-f8f0-4745-9501-28e7e84dcf8f | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
e22f244a-0041-4546-b830-e561007ff366 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
ee2fd42a-3d23-4a9a-a0aa-58202834ac50 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
f5781dcd-e01d-40c4-b100-2d9f63e273a9 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
f70d9920-31e0-487a-81d1-9d74e638dfb4 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
04518567-e400-4a1a-a062-c4edde578017 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
0678f8a2-b3eb-4de3-8787-e17649350717 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
0a44173d-8c09-460e-91d0-74d41c134d65 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
108d34d8-4517-448c-be2a-1186078e302d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
16521153-0865-4b40-98be-a5c334b8a534 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
2c011b87-f707-4c13-b9dc-4bfc441020af | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
30ac2746-26bb-46c5-87c6-acf4c25fb429 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
3c0818f3-cb30-4b00-a7fa-1f5393e0e99e | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
3fec7da1-48ae-4ce1-883c-83dd0f972d9a | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
41947854-6932-4f22-b900-f1f6a97a7688 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
4c453254-238b-4546-802a-dc8ebee7a6c9 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
4dfd5545-7edf-4b19-9d31-458102a0974d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
547a0952-2197-4b32-9bbb-36d7249a625e | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
61bcc74d-e717-4103-883b-297b3173ed70 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
6ae0df42-bf1c-4842-83d3-fcb69c7acece | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
73c34230-7354-4775-8ee6-23a6e3fa1583 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
7e35ce2a-9bd4-47f5-8e97-f4fedfda30ab | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
99456af3-f563-4a5f-b6ae-8832e8654d17 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
a3b2fc8a-8493-41d0-b4d3-8e0d75d04f29 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
ab67e711-e865-4782-bd62-2d367eb475cb | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
b6dded03-7c16-42f9-a8b5-82641a92bef8 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
c451d87c-e164-4460-a49e-ebf2bbcc9b9c | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
c9ed9a33-8d0c-4744-af75-b64b3de81d1d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
cf578f20-f0ca-4f01-9ab9-0eb809da3c33 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
cf9c32c9-ead5-430c-a5b3-d98b54e04c52 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
dd6e61f7-a06b-466b-997a-a0a8649f4e58 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
dd7bb2d3-9c62-4276-9538-6732161d98b6 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
debbd0c3-df06-4755-9134-8256649ffee6 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
e112b9e4-7ebb-4fde-acbd-b79d3c58e69b | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
e517c7dc-17cf-4c9b-8014-32d596d7b441 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
ec391e67-c3be-43a3-aec4-a087563f7ff6 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
edc9c05c-0227-461b-8f01-842471a3381d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
f25e005f-877f-41f8-9d65-2131daafd4aa | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
f4506190-281a-465d-9d46-fd99a42d869f | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
13100467-81e8-4d66-aa0b-f423075276be | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
220a05b6-c830-4ef5-a6da-fa4170b7b94f | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
294674d8-d9f4-4e88-8461-86d97e46f4bb | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
32c6b6d6-cb5f-407c-878d-0985e5c5acc0 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
33b79351-792d-4d2d-835b-6d7d670c416d | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
33e35ae7-9404-4e56-8169-6951705a7ecd | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
3d9dac08-5e73-428a-9723-b3bcc0600b01 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
464fec34-0df9-4edb-af91-51643bc42449 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
49fb5ba0-64c5-4e38-b0f5-2a8c899d902f | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
505e633f-bce3-47aa-85fc-1234122e8ba7 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
55590990-53e5-4182-95ee-303d9408b888 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
6629aca7-8fd5-4d3e-a714-eee9437ad511 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
667e47bd-8e57-4407-b423-4a802e6a74ba | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
78d3cfd8-53ce-4ff8-bf20-fe77d7eae1e8 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
7dc01b1c-02f4-4d88-ac33-1e5c9abc506b | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
972e7dbc-c100-486b-8177-670cb2803156 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
9ed43638-b9d3-47f7-8d2b-087c225373ad | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
be154a97-5b53-4013-9a8e-4b8643bf52bf | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
d130fb4f-c85d-4ee6-a2d8-e42e79f0f899 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
e9ae9ee6-2fc5-4b44-9733-cd5cfb8bb0d9 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
ee346935-8cb1-444a-b68c-2085d64de721 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
faa2db55-b52b-42d6-be50-bd6aee42e3a9 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
0204041b-1a77-41c7-9247-42c3b34be7aa | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
194dc582-a29f-4dbc-a317-91b32acef012 | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3
256b66b1-2ddb-43cb-ad76-83810c9f160e | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3
38683f2a-5adb-440c-a1c2-81f1288d9be0 | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
8fd1d9c4-bf77-49e7-9abf-b1012c4672fb | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3
d5aae43c-3c1e-4043-88d8-def61824f9db | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
f724d32f-943c-4cdc-9711-87ce46c7939b | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
0680f341-6c1f-4e59-baf0-e1d4c69a21ae | Pole | 2 | Distribution | 2022-05-13 | 2023-05-13 | Level 2
4f2a3573-f2d9-4ff3-b2a5-afe6de78150a | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
637599e0-ec51-4add-9d1a-42663680cb5b | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
85ee3e80-4f20-42f4-a67d-38af9b9511d8 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
afaad66e-9a9a-4bf5-afc2-7ee64c669dbb | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
b3bf5bcd-09cb-418d-9e4b-aa111694b225 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
d833749e-0c56-48ca-a0fb-7beff27afedc | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
e84f7c0b-e5e0-41ac-891a-c728f3990d34 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
f60dc076-11b1-4df4-b652-af532aea360c | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
f822cdcd-3a99-40d0-ac18-af7d33c3af88 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
f934b33a-03d5-4802-913a-eb46eb639a7e | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
fa40f187-c389-41f5-9127-aa22ca5bfa94 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
06da5821-f246-4f7d-9c6f-752a68a848f1 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
0d8639ee-bdda-45d1-8ce2-28bc300bbc67 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
147e403f-2b91-45bc-98af-44d624b0c4ed | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
1ef8c973-b823-4a2f-a5d2-e06b849c4a90 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
396e1662-d2d0-4286-95fc-d376b2e62559 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
45a41680-03db-4f0e-b088-939bac66b0c0 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
47c89d3f-4265-4127-bae6-7ac6891e3a39 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
855fc86e-5d68-4ea9-8343-3ea3b6922a94 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
9d666eb6-1b72-4bbd-ad54-88d2094f5c34 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
9ed03e98-53ca-46a7-9617-77e5ed9ffb1f | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
d4ce3d9c-87c4-4ca5-8d17-dc551a99da55 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
d773336f-c1b1-4778-94e1-b32fa1bd9a10 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
db5f8dc4-33e8-41e9-bb0f-0ad577f75c62 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
e3244def-bfad-4992-82a1-6e265c43ee8d | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
1159c80e-4c3b-45d0-bba4-21f8f8f4d773 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
22589855-1772-4d68-85af-91b3e958f9df | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
237dad7d-48a8-460e-8c48-89b67321a2aa | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
329f42cf-70bc-4fa0-99f5-ca5b0a7411cd | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
41b78726-5139-4e9c-bacc-525098d42ca4 | Pole | 2 | Distribution | 2022-05-16 | 2023-05-16 | Level 2
519b67dd-89ac-4b6f-94f8-6e3f24d8e250 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
5a6e5bd4-88bd-441a-a0ce-17c749ae2ce3 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
6d6c1649-9610-420f-a93d-da286d9a99bc | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
6fc703a5-14ed-4041-9a27-04023a45becd | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
9557e282-8f9d-4a1c-9f17-3c7931ec364d | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
a27edec6-3d6c-4d71-98db-6e854ae4fe9c | Pole | 2 | Distribution | 2022-05-16 | 2023-05-16 | Level 2
a8b2be93-8052-4875-94f4-9e8cdfe429cd | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
ccf999ef-e5d5-4a6d-9874-66232e53efb9 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
e2c3e5e5-b4db-4e9b-b384-c3a5d7977276 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
078072b0-71f3-49ad-bbfe-bf824f9b3cbf | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
0f070b41-15c3-4d82-b992-9d73209fa178 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
1070bec3-2966-4e39-8354-b72b3d08757f | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
219e7cd2-12ca-4b13-a8b7-8621badafdeb | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
22e64c27-052d-4568-aac1-e660300cc1dd | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
2b8bd0da-72b9-4866-a727-2242c6f6e6e6 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
488caa30-ed3c-4f9b-9b11-c1e178d6b86e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
4b62cb6e-b2d5-4723-ab9d-a64436a57b43 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
56f7bc40-7eb0-4c6d-be56-820e9ec1d1b8 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
62a80d46-8938-4e92-90dc-5cf6e3998b80 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
6e168b59-7a0b-4bba-a899-81f7a92ad7f6 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
714a5bcf-804b-4038-a5d5-352eb694ab5e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
7167a6f6-c0b7-4bd9-9988-7a00ca842872 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
76feba2b-2651-4f98-8bb7-bd8a7faa8b1f | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
8346f35e-f234-47aa-9434-a2116b44bb26 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
876a7730-77be-4090-bc98-50db532e4141 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
8b93c3a2-edd4-44c4-bae6-07877af99f1e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
951ae3e7-9615-48b6-a908-39d21c5e4a36 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
97df6be5-a6ed-4314-abb9-e8e2e1270fa0 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
a48c0986-1d1b-4952-ad31-8a3df5b03e21 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
a6ce0b2e-ac23-4aaf-a34b-558ac239c1f7 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
b4d6e2c3-fe0b-410d-900e-d48d3e9f1fee | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
b6256077-3e85-4c23-a1dd-cc8ea809319a | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
bd45476d-a7c9-4199-b928-ea755031b0d4 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
c162c34b-39f3-4869-af08-224f7af9fee9 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
c4055f7e-19e9-401c-8d65-1c7cfca7f892 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
cf4b55c9-5aba-43ca-b132-d30426043996 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
eb36f181-a496-4a89-976d-cb0a48294277 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
f016d9cd-42e8-402d-9607-a374b1a1eacb | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
f2d4e6dc-2309-449c-b1a2-c556636c8fa4 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
f589bd31-b3c8-4344-ae97-b49df98d8913 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
ff1306d8-83f7-47fc-9cb4-68de7fa6a629 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
0486a58f-bdb6-45b7-ba7d-28240ba67d45 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
0640b799-8f6a-4f11-8d18-dabb435fe145 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
0707aaf2-c0ae-469f-88b0-3cb3981aa796 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
0ad3329d-1306-423e-90dd-7b311f7760cd | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
0d80419b-bf9f-4184-b4ae-4b27ae58c222 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
104950d2-0272-416f-8686-84215cf155b0 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
155e2ebf-1aae-4a6e-8c8d-2240923007d1 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
175f420f-e847-4184-9998-fd23d168f48e | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
1864c947-254f-430d-811c-db73e773ef64 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
2edafc4e-a5e2-4c3b-a0df-6a25975ca7b0 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
32333d13-64fa-47a1-9e56-dca8e3eef442 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
35d43c75-e3ef-41a7-b070-4c6eac7d844b | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
3b773101-870e-4a08-ae20-b02ab96a33c6 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
4147ebb7-d785-437d-94f1-c63e15439295 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
46fa30e2-97c6-4a32-840b-7b3e9f31d2d8 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
5903c963-16cb-4a0f-8e38-f800c9e244e8 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
5ce1a4c8-5c74-4e61-8b60-a253f34df4b9 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
662e0bfc-3131-4f47-8230-40fbc4fed84e | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
6b04fb6a-31df-48d0-9fc0-334cd1a12725 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
6b877e8d-8acc-4e10-b718-5eb75c248112 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
6bbf3f82-28f2-426e-9b71-1d50074026ce | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
74266696-695b-4964-b1dd-a2b63713e3c1 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
82a7526d-7a2f-4475-a870-68c09b9c835b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
8732133a-438e-4ded-ad8b-cec9ba855769 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
90b4f5e9-41c8-48c4-9322-70be8a13ca5a | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
92424739-e331-4e40-a749-7a329c235006 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
9d4e2a3b-ef78-4aac-becc-e33a60924c3b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
a1ea593c-b185-4196-b046-595f5ba05e97 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
a26810fc-68ac-457e-8ea7-9abaccd6588a | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
a43c9627-0d8d-43a5-bfc4-4cd8414b681c | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
a519ae2b-006b-4b3e-928d-864d5ef4f0bc | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
aa65076f-4933-4807-b073-434bc9591816 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
b3ac1287-4de5-49ba-a161-efe7e47413b8 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
c267a96e-9a05-4bd3-96de-095097d5e278 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
c311b3f2-bf1e-4e29-b177-17934cda0ece | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
c830a559-ab82-4815-92d3-c2386f52acad | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
d0283dad-cc53-4d92-a7fe-42be13e315ea | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
de823bc0-8d63-4926-a57d-7854fc53a55b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
e915edc4-9537-4dbc-9a78-47734a6ab98e | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
f8190310-fae6-4b2a-b517-ab1f4388407f | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
f89edeb2-c46a-49f4-8055-92bf361b8f29 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
123a9e06-62e8-4afd-ab56-247195019dbf | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
304f1e88-33f1-48e3-ba34-7bbe004eb742 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
3491b4d5-1c53-4b90-9947-3be1e233dfaa | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
3e4d08e2-1296-4bc4-b3bf-81756346a887 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
49e8d807-fce8-43c9-bceb-02bf5ed9d1f0 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
4e7fa2fa-8c1f-4f5f-bee2-8b6dbe927515 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
50abee65-818f-40b3-8141-6948c17c2d94 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
50d35370-528c-423c-bd11-8da4b094cd89 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
5220555d-530b-45d6-b4bd-ee50b223879a | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
52f93104-8448-4fef-ae59-88653391c9d6 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
5339201f-d0f2-462f-9eaf-f17476fd6d24 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
536d83ea-f364-426f-93a5-0a620ea9406e | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
571f0020-9591-4622-9474-2b8e91dfba03 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
5c21b966-f6db-41a9-bf62-b3d9d2f34c3a | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
6f2df028-03e9-4e56-b18a-2c4bfb112639 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
7af6d6df-0180-46dc-8b6a-28b949a5a3e2 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
7b89fcb4-3cd3-43fa-9592-c47b1ca957e4 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
7d8414b7-ff9a-4d69-8992-df55ac0cbc62 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
8460ce50-0b37-4933-ad25-95050f88c719 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
93a335ca-82cf-4835-a281-331b5e83b781 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
9c438d86-726c-4e65-a203-d2bcac9d287f | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
ade811e7-b55a-406e-bd85-e3cd30edb095 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
b76c6aaf-95ad-4b67-953d-4208b2b29c49 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
c8e5f9a6-ce7e-48f2-80b5-a5e0ba803450 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
d22dc964-e107-44f4-8144-8f0607530939 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
d4707f21-93ae-47d1-9ab6-cf194ccb33b1 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
d542c0d8-df17-4f29-9ec2-fc934ca050d7 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
db876965-5197-403b-aefe-95aad0258ce1 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
ea5785b1-bf8a-4b71-89f4-3af532006b39 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
ec196a38-98dd-4e08-8eea-7c971650741f | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
f3b1c574-0fc6-4e8b-898f-170248306465 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
010e0020-c8cd-48fa-a80b-834f2967770e | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
055dc2a9-be82-49c3-afb8-88fb39888a0c | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
05e35217-c3f4-441f-8455-310e178a63a4 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
09a260c3-77a5-4772-a258-5a1a5b66ea3a | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
148c6197-d403-4754-8baf-666de4873008 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
314e7b35-7ea7-4eae-9c90-e028ea06a985 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
36ef5a98-625b-4e64-9702-335a5c6b252d | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
449b87c6-5e53-40d2-8166-0665f7a1d879 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
4ad9da18-917b-4291-8884-271f04675abf | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
7459bda8-3abb-466e-b42f-3268ac203cb3 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
82ea73e2-0efa-45ac-a8f9-98bf59bf105e | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
9c0e2499-44d6-4e31-aff9-74f207158bdb | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
ac237f28-9555-4f50-b984-7528333fadbb | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
ae24e9d1-bdec-41a3-a8c2-89f32bbc48b5 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
17b25550-373d-4c9d-bbcd-882f32c45001 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
2e353a9f-445b-4240-8dbd-3236eb6e8d23 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
2f152e79-307e-41cf-a830-5f5389eec106 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
3a855c2b-1857-42c8-8850-c51d01e2f481 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
3c50df41-b1cd-4c2b-97be-80611e16cbaa | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
46fa1606-63bc-41e6-9f34-efad31c5f0b9 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
47c58d6f-9aee-45f0-ae9f-05b326bb32d6 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
5a41558a-d04e-4c48-b213-1a82a99d62b8 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
5cbb051d-accb-4524-af88-9343fe354823 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
6e368a25-af71-4924-bcbf-00c3c50baef5 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
71a4bc93-ed2c-485f-9823-2345f2cea45e | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
82ae470d-6afc-4e80-a861-5cf8835b671c | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
9155a036-ddce-4153-a0d0-44c851a12fca | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
a7dadf3b-07ed-4c98-85e4-f6c835836615 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
abe60f95-1731-414e-b847-a507c4ea0969 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
d3043195-c9c8-4020-b207-be73e2db89cc | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
d68215e5-e57e-4acc-8292-2600f6410c6a | Pole | 2 | Distribution | 2022-05-23 | 2023-05-23 | Level 2
dc7877b6-a9b0-4fe9-8240-9ef7cc1dbfc9 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
ea2b3db4-ecd5-4be2-b399-64e741ef75db | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
efc9b24c-0113-4f8d-8387-17679624b0db | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
f9633e89-d882-461b-86a7-dcdf10d2a0d4 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
0df625a4-db4e-4cee-a6cb-d4dadfd77d3a | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
13b0b3ca-53ee-43b9-923e-5b6356603705 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
174824fb-5595-41cb-a90d-93345c5cf435 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
26d25121-6218-4d60-945f-c9a9cde8f6dd | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
3c50456e-25b7-4a83-b669-353187ff64f4 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
5d553ff7-ee75-4cde-9563-0da84159e678 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
60183bb6-6bcf-472c-8413-081fd6aac91d | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
732c27b2-45de-4ed2-89e5-6e48a2bcfe04 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
76f37124-91df-4cbe-8964-13cf992f56b1 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
88fb5747-16b1-4f56-b066-ccb7fab27f4e | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
8aeb2d85-050e-477e-af90-c4ebaf7c42c2 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
961f2713-774c-471c-8f08-c3b9cf972127 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
9f99edc3-6bdf-40cf-910f-5f84dacab975 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
a8e64e4c-86ca-4958-9d0c-d947f9ff16c7 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
b5ab0eaa-c29c-4281-b77a-93d8b0114f33 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
ceea8410-f62f-416a-a7c4-b23e273cf619 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
d5bb20d8-2408-45e9-b957-d2f5e1eba677 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
ebb27f0e-7932-483f-81b3-afdc68154065 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
f4e22ffe-6b08-4517-85c6-75ca91aee3e9 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
fd340584-8b88-483b-bf90-26d3f8827736 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
22299901-0f59-4707-81b9-769ec8f650aa | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
5072ce8d-9834-4add-a63d-e52acb103917 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
59455992-9461-48e4-97ec-f5f9c665ccc5 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
66115500-4bf0-4d9f-bc1c-b7d06e4bce20 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
d7aff897-46aa-4afe-b1d1-dfa8685cb22d | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
de4f3f45-d0d4-4ba2-a3c6-bf3836c2d426 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
f160d08f-6a1e-46d9-ac66-d902a79b9ed2 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
1dc314d0-11c2-4f43-aa8a-a4131e7c003f | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
22b4cbd1-3d67-415c-a47a-50cbd2b022e6 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
3e92f47a-65e1-4e13-b072-7b1cb5e090e7 | Pole | 2 | Distribution | 2022-05-26 | 2023-05-26 | Level 2
7d2f1c1f-932e-488b-9765-49ad27882812 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
e526279b-ed7c-40eb-8099-3746fcdfec96 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
35209a0e-9b48-4506-87da-501a290bdbaf | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
63365578-58ff-46e9-8336-cf747e38cde3 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
a2473792-ef56-427d-a95d-423999bf95c1 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
ac07bd03-ce8a-44be-bd89-d24904f5f391 | Pole | 2 | Distribution | 2022-05-27 | 2023-05-27 | Level 2
e0c988d9-a902-49c3-9c95-34d6067e3fda | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
f449ab15-e9ff-45fd-bfae-cfcf326b07d7 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
0b41d155-659d-4ea7-beff-e0b010afa00b | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
3b30eb11-aec6-43f8-90e1-f0fdbfc1aafd | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
7493ed1a-00af-4355-a092-383cf7c0d111 | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
77332381-4f14-4eb1-b441-72c8b5b8e7b9 | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
80b85f3a-9117-41d0-9c76-d1e70b8f289f | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
877836b3-dd74-4bf5-9c6b-ff661710bbe3 | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
96efef68-d2ff-4ca3-a2fc-f0e3aeb407aa | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
983d9c01-c8d2-4623-aedf-8cb59c15b1a9 | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
9955d68a-5c5f-4d3f-ab30-f6c18feb4e1e | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
c2f59fab-62e9-450b-9c65-c109628b3cfe | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
e932c775-2032-4e9e-8f9e-15251c4b5b88 | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
25b2e274-6aaa-450a-aa2a-c3ceaf205b75 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
4a6c8b6f-c9fc-4d8e-bbe8-8009fb86bed1 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
69b45941-f0bf-487e-93ef-48fe135ee252 | Pole | 2 | Distribution | 2022-06-01 | 2023-06-01 | Level 2
69b929dd-0a64-4706-8c5e-02953ecba04d | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
9b5c75b5-ec13-4479-a57a-3d5eca35c05d | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
a75dc238-4b55-4230-80b5-c570377e8fb5 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
b177b828-9045-45b8-987e-ff209f5e04d8 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
344540d6-aa77-49c6-87b8-ee89545406f9 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
544ea706-289a-48f0-8384-c72a8b6ab557 | Pole | 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3
97ce9be9-a6f7-41bc-8b9e-0434c6963bcc | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
a0e91ea1-20e1-4eed-b5c3-5408145d40c5 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
ab349ebf-3f7b-4b3e-802a-1025bc172f19 | Pole | 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3
ba834cde-e3df-43f5-96d1-33b9be818e80 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
c2f00bf4-d74b-4975-bed9-12f53f52f774 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
d9b309e3-a9ca-443d-925f-931b8c31be80 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
0004ef32-55de-4796-a5d2-ef0815b5b4d5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
0257d981-50de-4016-92df-0a9a2290e96e | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
1105f55c-a02b-4f8c-a1ab-ec093302f416 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
1dcc91c3-6439-4a25-b616-c0c3163c8238 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
224eac4e-8b98-4b71-aca2-341ffa7d775b | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
28ff136d-8274-48a8-83ba-c3f34a0bf1e1 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
365ad973-8dea-4f3d-b539-c451969f6133 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
43d4a2d2-071a-46c9-bb90-b2749196bc9f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
44d3930f-fed5-4551-95da-28560ea80bed | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
49a929b8-5ab4-4298-a7cc-a354737d0d1f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
4d9149b2-558f-429f-8144-18a1e534ee34 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
52d86207-83cd-4904-8445-ae19bb1fed5d | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
568897e5-692f-4a67-9af5-1ba24d26a6bf | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
641c7bd6-7e31-4005-b8e0-0e00bc1a38b5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
65e906ad-2194-410b-b868-fc5af8b4c6f6 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
7c05d0e4-74aa-4701-8395-8f789e1b0e70 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
85bd66b4-9b62-4760-8d76-49d1113c42fd | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
8b6b3e00-ee3e-48e7-a445-fce9cc685653 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
8eb7d97e-fabf-429c-ac5f-4a8efc01a614 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
90fee683-d963-4d0e-9327-346e9f41b287 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
94db3358-ee6c-4411-9915-33ec28fbfdb7 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
9cc8ffdd-3042-4da1-a5d5-df835373ba25 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
a24df196-8d97-4a12-92e6-f5a8922fc6a0 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
a33a96c3-318b-4b31-bf8d-d1411499d534 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
a57bea5f-2613-4fad-926a-bd76af3440e8 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
a9408bc8-7d43-408e-8ce0-21b554a0fa6f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
b3916c20-c8e8-47fe-88ac-41405a4752e1 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
b868bc94-ec54-42d3-b68a-366a0c027b28 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
ba4ef147-96b6-4d55-9e4b-4fe01bf5a68f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
c72b6fa5-65cf-4ee6-b860-e9bbdd92d250 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
cc09cfdc-7ce1-4808-852a-f933e92f2e84 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
cd4a6116-442b-4d49-b794-8b71fd6785b8 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
f26571b0-3c04-43fa-acb6-13e24dad40b5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
0200fbf5-5e71-4d27-9bf2-1b0f89bf8a16 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
04d90c31-c6cf-40db-a291-c14c7c0d019b | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
0f3b29de-43a4-4019-a79d-eb0d26a27127 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
1091024c-4583-41af-ac5f-c8132f98a92d | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
143bbcb1-4bff-4433-84e3-d094e278d229 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
17a22e5b-8b3d-4a7b-b9ef-36576707d486 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
2628c265-f38d-47c8-91f4-c3b899afc407 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
2a83371c-6805-483e-b8fa-115e4efd9845 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
2b633708-0cef-4527-a8d4-9119b075dfd0 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
40f21ba7-c1ce-4efb-a977-590ff30a2695 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
43501e18-0e84-4ad2-ab2d-2a2b9e7df184 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
498bbc1e-87ed-402f-acaa-1e43184e88ef | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
5a115124-8908-49a9-94a8-4fde1c0b83ff | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
5c7abca4-93ab-415f-aae6-894390258a8b | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
5dbb384d-5ed2-4e9d-8243-c29615898e04 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
6024e71a-260b-4ac9-96dc-e8be5c7a322d | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
6164a3fd-2e5d-4854-a49c-e1ba315485f8 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
6f69bad8-f7b3-456c-8901-297866b3168a | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
75346032-5ffd-467a-a9dc-26765ebe63f9 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
79df62d4-4dd2-4508-ba7f-6016607cdb70 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
8347da64-97a9-4a07-816e-f71c74c97c51 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
89b7b56c-6ee6-4ea6-aa4f-c62b9e0b616c | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
a1e8170d-d7f9-4c71-ac3f-8e22425c7ecc | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
a462f44b-488e-45ff-a864-6352b6f8ee8e | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
a7e4c324-e7d0-49ed-a931-d2e0f25d95a1 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
b18384f7-d98d-4851-a203-1dd41237edff | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
bdfc1123-ca3e-424f-a172-c484daa01e15 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
be5ece9f-9866-4eac-9334-2a0111a72dbd | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
c2b386f3-ff5b-4dd6-8cfe-eaba46a5655f | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
c3b3a404-477c-439a-9ce5-65cd6e2437b8 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
d05e7b2e-80a6-4535-a5de-94064cea95bc | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
d6cd3eed-b6b8-4874-8349-92039cf7d9db | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
e4207e32-3e57-4e46-aff9-bef016f2e1e3 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
e5844cbe-fbbd-4078-a8a6-138725c488c5 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
ea5770a3-ff60-47eb-8279-807cb3b89135 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
ef5123cb-d246-4d14-ba64-fff8b68cf143 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
f0366e2f-3c13-4419-b8da-b0cb60dce6a2 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
fb367aff-2091-4b6b-b6dd-4b5368d95621 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
00c6c0df-7ba4-46e4-9ca0-f596c6566e99 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
033e80b5-8fdd-4101-826b-1b3dbb4c5003 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
0ed4cc9e-383b-4403-83f3-140be6a2aec1 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
10e75c0d-ef4b-4388-b340-0c723134601e | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
12c01b20-ec26-4be2-b598-24c2ed5b66ad | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
16957b7f-f983-4d49-889d-1c2c9b4c3e2a | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
1c1a3677-ba9b-49d0-a429-8e1417474d26 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
26b3dbfb-5a1c-4770-9a84-9d7bf1d9745d | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
2d8f792a-2f8c-4947-b3e3-dda69c820c66 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
39c9cae9-f732-4d6e-9ce3-4fb4e0ad0de8 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
3ae6e97f-1a00-4d9f-8268-2507845b8aab | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
46b3736e-d55a-4b84-86f5-89b1306ae357 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
47ba5de7-aeb7-4305-8607-a5a50d8d8b03 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
5e665a4a-1cfd-4b7c-b3c9-79ac17054773 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
610a11c5-d848-4ba5-a3e9-4b9f049202c2 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
6721eba9-26ee-4363-9e7d-f2baf93dfed9 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
6ff2103e-9b57-43e2-a8e2-6a016c8de0cb | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
7121153b-540e-48fb-8b8a-6cdf9f494a9a | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
7b4e4f45-4042-4bda-a3eb-93ddffa49b70 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
811c29aa-d1ab-4bc5-b0de-4dc6d53e7404 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
89243e80-21b9-4c81-abb0-ac874c6aef31 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
8fbf94ed-694f-4242-8a81-855c4aa7d402 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
94a0c8c5-2903-4047-bbea-5334412cd953 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
ad4bc031-31af-4954-a81a-dbadd5261944 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
b53ba4da-4c50-41d4-83cb-4664dd6fe869 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
c043bef2-8c25-4843-a6d7-4c57315b35ac | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
c7f5bc57-50e9-463a-8a0f-1e97063e5d37 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
d34c369e-0670-458f-9779-ec2eee716336 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
d4d0f64b-1b9a-466c-bab8-f5c5130ebc3f | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
d8a5981c-99a8-4882-bc7b-fe15da7e877c | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
d8ee79cc-cc3a-4afc-8186-0fc2c2faed27 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
e2af2c61-872f-43dd-ae6c-a1ffa0134aff | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
e99a5261-5b6c-451c-ad50-e048655028ee | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
eb6dc44a-b988-418a-a0ff-22d1cd79acdd | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
fd680597-8140-4f9e-afb9-d33fb48688eb | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
030516a7-37e7-476b-af86-799f23d757ba | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
0d1f616f-770b-420e-986d-f1fc7bd3a990 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
117e42ec-cb68-47e9-813e-43c6b94bb0b0 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
12964d6f-00cc-4837-ba67-e5b2f44fbfec | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
16736fa8-722d-4f1b-92db-821095e5fd60 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
2ae64c44-e90e-4ed1-81d0-6959f5fe1b3b | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
3894c5ad-c5ea-4bae-8275-5b100046b365 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
4d25a906-c4e2-4089-ab3d-4449c0fdc7b8 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
590cf76c-a89a-4e81-b739-d18a1642ac34 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
59369ff7-ec57-45e1-8bf9-c0577d184f35 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
639521ae-05f0-4abd-b6c5-82b96a55caa1 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
67afd26c-d3f6-4ce3-a851-501a1a857693 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
6df4c503-5cf4-42a5-b6e1-5e3ef8a09d21 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
6e80bc61-8c7a-44ad-88b3-c3641cebfe45 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
7360a078-0a86-439d-a7c0-196dbda5fecc | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
8131c11a-f9e8-488e-82f9-892003027963 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
955f7bad-e0de-4d11-966e-c08488217d6b | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
97b1d5a3-55bf-45a2-a736-b2ce11ec8ae5 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
992ded53-33dd-4611-af76-9f92d103cf7d | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
a48203eb-b6c2-4b4a-95f1-b19c22e55207 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
a706e177-cd63-4ef9-984c-e27242f5da03 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
b3382cfd-c86f-403d-bc3e-889a8fa63c5d | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
b97a498c-5c5f-48ec-8343-cfd2184200d6 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
bf012361-830d-45ef-a59e-602e4e18d229 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
ca74a331-e4cc-4f8e-ad42-8574c45660dc | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
d4ae4378-3070-4ca1-9009-183da73c76e0 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
d5daeaf8-1647-460c-9095-ec2bd3fd7fdd | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
dc248d8d-c700-4bc9-a3ba-d55f7e2fc200 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
dcac5f3e-4407-470e-be13-c09cf9a31e21 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
e1b9709a-344d-4b43-857c-0d6c316f2268 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
f584ea2f-6753-4c74-b111-fdeefc8847c2 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
f94afe8d-cb88-42db-b43b-d702af3a8d7f | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
fa02ba18-7868-4f64-87fd-aeb01f8e6926 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
00b8c0a6-c1a8-4e54-8c60-19669f2de0f3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
06b47d1d-c5fd-4fe8-b82d-dbd38ea8e0e2 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
19ec18cf-589b-4159-87e0-a0ce16964c5d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
2f652811-2797-42b2-ba8c-06cd614836f3 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
3ff53d29-9563-4f26-a93f-3de4ac86d9c3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
44ce2fcd-932b-443e-bd84-2dea92269b13 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
547df3a8-d8cf-402b-87f7-886f2b88ebd8 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
5793ec76-84b0-42d4-aadc-1ea80d13fb9a | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
59e80f05-3557-4c90-bcea-bc10df1be715 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
5f5b4618-7268-428c-b0b8-09d42b89103d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
6aa2eeac-a9a8-49ad-8e90-7c088d354d00 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
6e8efdb5-9225-4f0b-bdab-a9e86d23f028 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
6efafb16-b4b2-4eca-88a2-06a14c1ea4fa | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
70d4c2cc-1f9a-4d08-9f09-a20173deef77 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
72e2909f-3a6c-4947-ad12-a6e0a22ea95f | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
776ba426-b852-4b74-ad93-8b094a7a7bf7 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
7a1111ea-8917-4aad-bf78-02a3f7e22a8c | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
7fefae0a-266a-4014-8243-9d52caa0bced | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
8d8aa830-4e11-4ac9-a531-f31c1b7f7f8e | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
94e06f01-586d-4916-93b3-4858ba59a27d | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
9bdf1422-0a23-4167-ad66-f099a033ed88 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
9f5f4036-0b0c-4ae0-b953-e198ca5a87df | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
a093f7d3-98b4-45cd-9f44-5994f9f7e574 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
a3a973dc-676b-49d3-9567-b008c3465bdf | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
a91b776b-9d8b-4edc-9a12-b7c48ed066f6 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
acfb5d74-3bf9-4def-a2eb-f736b7063911 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
b299265e-8a9b-48bc-9175-750d57068db8 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
b90cadbc-a988-42b6-b032-ee25c611af61 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
bb7ae4ec-850a-4889-be7b-c7769b3cc726 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
bf041ecd-6b91-41f1-b71b-aceba9ac6631 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
c7ea0d7b-8c7e-420b-abe5-83e7ab9e7429 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
d0672f7a-c10b-4a24-be37-c98d5566b47c | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
d206aedf-c741-47e4-8256-a93cd5b71298 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
d8f0eaf7-a89c-447d-9b9a-ff7ffb3bdb28 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
e0909b68-8b8a-4028-9a48-75c5c0763c5d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
e2606b07-1c58-4746-9c85-884dac2ff3e3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
e4b32770-d16b-46aa-810f-2c8a57420c67 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
e5b1ad7b-2da5-41fa-aa38-290a6a17dff7 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
ee259df9-03fc-4a09-9126-d0b360ffb060 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
eec22a6c-64ac-407a-8e2d-9a47c73998c5 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
f6537276-f464-468b-986f-a4c35002caad | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
f8d706b8-cdcf-4f1f-b1de-7bf07145fa92 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
fbd60d91-6368-4256-9790-db5cfb0d8b5b | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
fc4b04ed-221c-4b43-8109-d0ec8d1e23eb | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
1bddce8b-51af-493f-8ff2-fac9ee93b34e | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
1cea45da-bc2d-42ed-abcd-f25cd56c82a3 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
249927ef-e0df-4e3d-8205-354d55f3fba0 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
290bbee0-6117-413b-9cdb-55914c561a8c | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
356cd0ba-d898-4e07-907c-f35f19af5018 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
35ed2a18-82a2-4ab2-b79d-171d24206f13 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
3b53f5a8-10b0-4db1-a667-40d33a431ed7 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
5182dca2-ef61-4303-b834-52684d6930ee | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
5b15de2f-4970-41de-8235-aaaa4a3b6961 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
6734fe9d-87f6-4247-99ea-7163f41dc9a2 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
6dbbf8fc-a6db-4565-8976-7174e4606826 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
7498583a-fd8a-499d-98db-67d2943192e0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
7b09cb7c-f6dc-4ba3-8aae-e83bf299e90d | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
7e618191-a9e9-40e3-b7e0-2f90d7ee8142 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
80e726dd-8693-4556-94ee-30918a08623d | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
81bdb8ce-56a5-4ea2-8ae5-de2957ebd00b | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
8823bcf2-5a8b-4e38-a025-12a11cfb0f69 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
8b8256dd-84d7-48a0-8da3-6a035abf43e0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
910c4810-263c-4616-93a4-af5bb4c194d5 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
9afc7767-cc86-497c-bb2e-b61316415c7b | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
9f62e665-54f0-4c44-b33b-53c80657a277 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
a16e4a84-84a7-4f5d-9c1b-f86cf42893fb | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
a34c196a-47ca-4983-bfaa-c8821936e298 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
a9cd4a66-b9b7-42ce-bc51-c7ced036d76f | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
b5f6ae45-7962-4d58-b38a-06dcc5a2cd15 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
bc7929a8-81eb-4f38-b040-4aab7bf60376 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
c2a855e3-f912-47da-a981-c5cb431607b0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
d21f36af-a788-41a6-a2f7-406f2ccf412a | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
d3d5c8c5-5f12-4ef5-aa51-97ea57ecbb41 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
de614919-df7d-490e-b6aa-3ba696d31a37 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
e302d77e-6ba1-4d69-b18d-5855cc1511ff | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
eec0317c-6a48-4eec-9716-7ce75e49df66 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
efab264e-d833-4984-8b68-4cffa4b0faa3 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
f2c2ad53-04ce-4783-a4d9-951e48be4994 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
00b3fd56-db6c-41ff-a851-5eff8b2cacdb | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
0f30e4bf-789f-44d9-a930-8727944076c1 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
1170992b-ed45-41ac-93a7-032a54eb0ebb | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
19cab8c8-0dfa-4322-8b4a-05320eb6f9fa | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
1c1504b5-446d-4ff1-82eb-28faf23d02af | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
1de2c696-a2b7-4b7a-ac6e-39f87a4dc1e5 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
24c63960-2949-42cf-903e-ff759109994b | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
261cabce-af69-41d1-a513-b03e51fed527 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
3314c839-49fd-4c84-94f0-ff403a2bdffc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
3873a587-5e53-49e7-9d4a-2f9f5a677351 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
39c1dac9-e06a-4b8c-bd8a-4c93aeac0196 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
3f9e0f34-cd83-4ba3-a1d2-bffcbd1108e2 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
408ead9d-8c47-452b-86ea-166c4a7d60fd | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
55c92808-b9d6-41c7-ace1-392949910923 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
5775a1e6-05d1-44b5-a543-7e4b7318f052 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
5b615b9c-ac4c-4d44-85a0-e409bb969a3c | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
5d124e0b-77b2-48e7-9313-3f3db4224a4c | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
699324da-bb0d-4487-a086-e86d128a785b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
73ca89fe-85b5-4b96-9621-8e91e4a65ca9 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
74c5dd60-f8d2-40d8-b606-4ac2f7096b0b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
7a096404-c6db-401b-9c0e-6d69e51f83fc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
804502ca-24d1-400f-a84d-0e9a9eb097cc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
8d0e55ff-e064-484e-8b42-b5e0c78a2695 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
8dfae59c-eed3-4df2-8281-c14d0df52f36 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
91da5b98-7af5-4a4f-ab56-6f8195f33720 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
a62bae72-306b-4eae-832a-2129fad5a76f | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
ab02603e-840a-43a7-9f4c-325968540c93 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
b1a7d64c-7a21-4cee-819f-df93dc2eedd5 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
b2f9c999-a4e5-4b34-aa30-10c7ac927129 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
b58bc783-32f4-4556-b786-ae361c9288c9 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
c21ec53c-ef54-444b-b8ce-623927a779a0 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
c7e8802c-d27b-4b94-baa7-e10f88157697 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
c952b1f1-1fdd-4c82-987b-9ae9b7fe7b9f | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
d03823a5-9742-4526-a977-5a7534b82a18 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
d1a0409e-8058-4121-bcdd-874595064e6b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
db6af8c7-5e20-4e33-b1d9-7cd021bf3786 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
dd57316a-83fc-4d6f-81a2-dbc163e2924b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
e3eedb98-60df-4408-b15c-d986e8827147 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
efd3f90f-9739-4c81-a469-48521dbe643d | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
f0166268-2464-4c2c-9702-7aa32f362b69 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
f41478ee-683b-478b-b430-6641d9c61b4b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
fc47e68d-ad6c-4e62-b3f2-e4668ed6ca13 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
fc9d603a-221f-4c0e-aec3-1aa90c798efe | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
190563a1-0644-4d08-b1e4-23489e44ff24 | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2
2a57d8cb-f0cc-4d12-be65-ad767a431439 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
34575d69-e68f-4379-9637-d26f15c8b743 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
65afe448-4e5d-4267-aead-b056db2139d3 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
6b6cdbbe-fcf8-460c-9a52-178b96039102 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
816258eb-cf1c-485b-b439-a8f618635d29 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
ce749701-3e23-4323-9ee0-3daeba73ca6d | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2
e63ee37c-9e77-4b4c-a390-1fe9daf492f7 | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2
f6162a34-a159-4591-bdd0-9495d27962b4 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
1285fe7a-41ca-4da2-bcc7-e9f28b4f25ee | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
32e267c8-84fa-43f5-ae4a-81246921927b | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
33ded1fd-e4c8-4757-942c-c3601f19c733 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
3c2024f3-3bfd-4964-985b-a8a6e4811a87 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
3f72c3c4-b139-4746-83be-66219e91b11c | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
43afcc3c-dc6b-40d9-b76d-b32e9627b339 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
45c74e7f-6f85-4b30-888b-4b7260c34cf6 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
49e7d3c1-4baa-481f-8b7a-99b53ecf6011 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
53dec5b3-faa7-4bfc-a0c6-48c5cc985149 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
55ff8a66-62f9-4125-90f7-3fd21f8c442c | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
7d98426a-1568-40cf-99fb-d528cc8a41cf | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
a57bfe1b-c179-46d0-b10e-ff93c631c020 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
a9b0bcdb-a1bf-4a10-a4ea-dd20a4ac0b5a | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
b142c4c5-82cc-4937-a8e4-2befc07d782c | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
b7809b28-bd3d-4e4f-85a8-8d71e13df508 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
bad390b3-c903-4be0-93e4-942920b6bb8d | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
d1753f35-63fa-464c-b705-daf1cf8ac8bf | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
d515860a-4f67-4079-80ea-216d2ed310eb | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
d5fa045c-98af-430e-b4e0-3ab4770edff2 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
d60e7213-0abf-4d68-a77e-c670919e64de | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
efcc95b5-2126-42ab-8708-b9881e78c60e | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
f7b87618-6ab5-4a0c-9cd2-257dc9c646ce | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
01d772fd-37b6-4c2b-ba60-74b5953dc58e | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
0ede8458-fe64-4fe8-aa1f-1001484e6c23 | Padmount Transformer | 0 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
2356a8df-bed8-4722-a538-a0e13afdd20f | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
31bd0687-5047-4776-aeec-5a0e59630cc2 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
4b047ca6-1b7e-4d8c-b79b-27fd2880956a | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
4cffdebe-6b28-4f95-8684-2ba580ee4cf0 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
4da1583a-09df-461d-98df-c52e9eef8c32 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2023-06-14 | Level 2
62f41e21-fd72-44c0-9e40-428dc67e40d7 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
6caa5d57-2859-42c4-b6a8-4aff7aea2a62 | Pole | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
80f3e900-83a3-403a-9e12-087e705925e1 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
8da15489-0c79-49d8-a2b5-d9657f001e25 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
9d931224-1b1d-4b0c-a10c-3146752be6b3 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
cbcdad00-52a9-44d9-9e6d-e222773baf0b | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
2d41216f-eb07-4d47-8ac4-d361b2cc6657 | Padmount Transformer | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3
41c771ad-a229-48d4-b6ce-833512e9406d | Pole | 2 | Distribution | 2022-06-15 | 2023-06-15 | Level 2
b7137f0b-e07e-4d6f-b28c-527d4970a1ed | Pole | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3
d5883e28-c8b9-4cfc-a5e6-3a6d407fd18c | Padmount Transformer | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3
0376c3be-b3c8-495b-957c-8b33413a41d1 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
12d50ad3-b4b0-4548-8a09-5df48a9c5cf4 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
13f53e72-f481-40ec-bc62-9184799269dc | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
18e8883c-5871-4d53-8b54-f822ff9b0bca | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
1b437797-e7da-4b7f-9f33-a2353b7a05cd | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
1cf96f06-cc51-48f4-af3b-69bb6b81b81d | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
1dd4e67f-1ba4-46ea-9458-dd6e5782db9f | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | 2022-12-28 | 2027-12-27 |  | Required to Re-inspect a subset of assets
298880e0-5326-4328-ab84-29d25d0c3509 | Padmount Transformer | 0 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
2ab9ebb6-a13e-455e-9d5d-eee2f3fc5415 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
3326eae9-8915-41ed-8c3a-ef82f50c8e29 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
36e9404f-b39d-459a-87b2-8a4451fc4f9d | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
3be1b787-56a8-460f-a934-283c82edd225 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
6a6dd65f-c51b-42a6-987d-6fee52bc0225 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
6ee10a26-a07e-405a-a205-dda0961b8089 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
98989c5f-65de-46e5-80dd-aa56cb001af5 | Padmount Transformer | 0 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
ac0a7736-89d2-4830-aca9-990ecbaee780 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
bf32fec6-968c-4837-af4d-610d3f242349 | Padmount Switch | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
c01f3c98-69d0-426f-8186-9d0255a281e0 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
c4c35c38-bb84-4a25-a2ba-8ae5cdb4c7e0 | Pole | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
c968c4f0-659f-4de5-a1e6-f4e6889ab438 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
cd1d59a7-4fc4-4b0d-86dc-4f87bcede5d4 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
e3c72cee-d094-433c-8f7d-e7b6adda54d7 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
eb6c4f93-fb4b-4290-a48c-cc4393fa51ca | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
ef2b6b89-31e4-41f2-b08d-62fe967cd958 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
1cd58a7a-4a44-41f2-b43c-71405fb4fe55 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
1e0436ed-acd5-4707-9e0d-4b9caf87169b | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
1f0ae53d-ed03-4fae-bad7-fed38ae00e9f | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
3bab858e-5e11-40a5-8a19-325a0fe605b9 | Padmount Transformer | 0 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
44bc7ca1-878e-4831-98ce-904617207a57 | Pole | 2 | Distribution | 2022-06-17 | 2023-06-17 | Level 2
4bcae9be-09ad-4b8e-9d80-4edc59cfa6a4 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
5130edae-bd79-4ba5-bb9a-0a3700ed4e69 | Padmount Switch | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
5a47bdef-e192-447a-908c-febf0d336eca | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
8469ab74-35be-445a-ac3d-969d7431d8f4 | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
850c4a3c-16db-41c0-bd1c-7e4235e41cde | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
8a69389e-42e4-4bf2-8fc6-3e0a7062ef4a | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
94ead8eb-5256-4eec-9e73-cc55975f3aac | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
9fa3fb16-783e-439f-a137-d189d85edde6 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
9fefda5a-c474-4c3b-b008-51ecf675b89b | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
a85af020-f1a8-4bb7-9b25-7d6ab1800b87 | Padmount Switch | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
b4c67ffb-8e1b-4316-a2cb-13655371deb1 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
b9dcc4c2-d986-4466-a298-b71daad4aed2 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
c19fde90-5337-4ab8-b411-2b6c4af6ba3a | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
c29af4d0-15bc-4a57-af8c-9349b7329734 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
d3c9cbf5-7f45-454c-b4b9-305dcb465d91 | Padmount Transformer | 0 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
daed959a-4d21-4774-b0e0-a6f3204eda5c | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
df52a1a8-0c31-44bf-8e75-6d7b9568ab17 | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
e28a3cf3-c43f-442b-afcf-caff845f3b3e | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
e47e950f-526a-4611-b10b-0276ebfc4323 | Pole | 2 | Distribution | 2022-06-17 | 2023-06-17 | Level 2
e4856038-cb1a-451c-8a7b-c4ca6595cdcb | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
03e35072-a4be-4ccc-913d-6eb56020644d | Padmount Switch | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
32741ceb-896d-452b-96ba-e07359dffa68 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
5c779567-9f7b-4a49-bbb5-e3a9b15ce3aa | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
7e212068-3acf-47f4-9214-d7170a58f009 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
9797b6a0-a6ce-484d-99ef-e7b1277772e3 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
9da46770-0fda-41c3-87c3-2dac72b9aedd | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
a13d0258-61f1-43b1-9228-dce5c58695ec | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
a183ea84-4574-42c4-83cf-160c72450850 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
af878fdd-e739-454c-b83c-0d3c8a3da074 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
b9158da8-200b-408a-b0b3-fb24709ef9fd | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
ba4cec74-5af4-4a41-acc4-e3333ffdfeea | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2023-06-18 | Level 2
c8b69eb6-aec6-48c1-9b49-bc58621544f4 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
cfa424be-1ade-43fa-b75e-5577b89676e5 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
d7c209e0-3cd6-45ce-a082-cb48abee240d | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
d9bf59df-21ac-4e4c-94d3-f737205c5a93 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
ed9fe677-fa14-4fc9-a972-79aa488a92e3 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
edf775bc-9d7b-4a7c-b533-cec7cc2aeb91 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
fcedc6ac-f0de-443e-832e-0f8cc65d9a00 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2023-06-18 | Level 2
4434c782-74d5-4f2c-a82c-96bddec5c6cf | Padmount Transformer | 2 | Distribution | 2022-06-20 | 2023-06-20 | Level 2
8e7c11bc-ab30-4a6a-bc20-03597152f93e | Padmount Switch | 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3
de95aa96-8b3f-478f-ac18-01663b7bb0a6 | Padmount Transformer | 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3
2625c5b4-fb0e-4ad3-93fd-09e3dde8fc73 | Padmount Switch | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
2a6fc61d-ec28-49a9-a828-ac07c755ebe4 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
6341d88c-4143-454a-8a88-a2c71eb74b70 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
73e61b9b-9c57-4cd1-b8a6-d973bd599f77 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
83cb1b94-fe53-4233-ba65-b57df4a5f29c | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
97f58b5d-8cef-4551-8b35-298f73685ad1 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
a40c2b47-a8bd-4acb-9f70-3d5f1488f2b9 | Pole | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
afbcdd41-9670-439b-9ffe-df89054667ae | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
b020aae7-2559-49d6-b69a-568c73d95411 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
c32741fe-cfac-41e6-8903-51d452f4222c | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
ecdaaf67-2f25-48e0-b1f1-17c861eee95e | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
0506b8a3-464f-4898-b97d-fbd1adc9cbef | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
0f552bba-6a98-4f3f-bf4c-e1e6b54a2889 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
1f3e2d0b-4465-4596-8775-db561b7ecb54 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
3b34f210-1300-4f76-97de-97cf73055ebe | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
5ff51a71-1123-4167-a8f1-9b8cdb1bc2e2 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
86d0243f-c291-40c5-ac7b-cb1dbe150bfd | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
99d66450-6366-41fd-9cbd-ec5fc98f170e | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
a6ea84c3-f617-4943-93b4-b20a57622cff | Pole | 0 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
b5ecf54b-8f71-492e-b9ef-5fd482eaddc5 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
c62a6fd3-3d2a-4738-83c5-9c116ff7d314 | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
cd54d625-24a3-4554-831c-b03562412bb2 | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
ee2203ea-1b73-48e9-b816-a57eaaf99754 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
f57249bb-e0c6-4e31-b952-966facf30c04 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
646e47e1-596b-4c18-9e99-e3b019554b14 | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
6b7360dd-d7ca-478d-a8f4-621faa5f32aa | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
6c9aca1e-de70-4304-802d-23aac78d08b3 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
7dea3583-8a76-4701-bbff-0d76c1d40381 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
873c3160-dc6f-4c6d-9cd5-907452cd4bab | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
9e31fbe7-495e-410e-be28-838fb43b055a | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
9fe80817-b76a-41b7-b99a-6e5982e7301c | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2023-06-23 | Level 2
b507717d-4fef-4b44-9fbf-7080fd933f3c | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
d13ec6ad-2fdf-41da-b0ea-8b8bcb119603 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
da61a454-3b12-4842-b23f-f8ce9a5d9375 | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
f2144e7c-b2f0-4a5b-b261-25ea32aa872d | Other (Describe) | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
f3a74b06-ca89-44fc-9aa2-970b8f01b5ab | Other (Describe) | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
fc00b21c-94d0-41e1-b78f-2da60c9f1c66 | Padmount Switch | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
25a66cf1-9f47-4ef4-bed0-376ebb3bf713 | Padmount Switch | 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2
281403c0-201b-41f6-89e0-f84abbe894c4 | Padmount Switch | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
2876af88-cb1a-4ae9-a211-7396568f0ce7 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
3a1d63a9-f5a9-4265-9384-6d0923a2d824 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2
3a916cab-3fa2-4352-8551-d7e195085c80 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
5bb253fb-2aba-44f5-b468-489eeeaba216 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2
6597ca3e-b449-4172-8b43-63a83360f954 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2
70c03c5e-c0eb-43b5-9304-5b4b58c14e51 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
983332d7-a2d7-4f4e-87fa-337b7aca6c24 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
b8daf1f6-1c7a-49ea-9f87-a5455520c5e2 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
c8a68e42-6db8-45f8-a73c-3b63e6a8d181 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
c9e6a4a4-6892-431c-9c6e-9bff7f782e69 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
fc293dd4-0504-4566-9e7f-0bc28705f971 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
0276fbd3-4b6d-4a0a-9b7d-f0d6a7d9d58a | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
17a54f4d-9f42-456b-a828-e2a16184a2e3 | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
328f773a-3bbb-48cf-acf6-11c9c4514842 | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
3ca1e1bb-6d6c-497f-9632-0c7bb1721885 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
4534ba9e-d547-427c-8c62-362a16f70e68 | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
768d7e09-a2b7-40d3-beae-e276910fb2fd | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
8eaa42d2-3c2a-43d8-868e-1c4607bea3cc | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
9ab7f456-a2d7-4bac-b9d6-a22a4ae06fce | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
9b8d2261-7f08-4787-a267-3a40676c302e | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
a16e64ef-2d77-4b8d-820f-0bedffe6c85d | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
e5da4dea-6576-4188-abb6-5c5b407d2daa | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
e88d3cef-d974-4f40-b969-eaed7156703a | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
ed42748d-cde4-4cea-8306-63913d379ec9 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
fea63757-cdc6-43a8-bb4d-f67cc2dcb752 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2023-06-25 | Level 2
158284ec-87b6-44ff-8d88-744610aef02c | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
1cdd61bb-40cc-4898-a072-83625893d433 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
250fb58a-d59f-4e30-acdf-da04a8325175 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
2e7582e2-17ba-40c1-b3f8-8230194c5720 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
417ba8ba-aff3-4c3c-a6ca-712c8d56501d | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
57132dbf-b2ac-4061-a0c9-85a59e17da31 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
8bb83fdc-cf25-4ed3-a1b4-aaec1d4d16a1 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
945759fd-7e64-461e-9003-579624b1b8a6 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
97333fea-8d0f-4cd7-b461-c7801cd23c3c | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
c7091109-e6cb-4bd3-aeda-bc71f46805d1 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
039b0d1b-f16b-44e8-9c30-bef197d876ce | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
326e49d2-6a70-4f9a-8bae-8f583c49acf8 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2
3aa680e5-bc9e-4303-8983-379d6a5bcc86 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
46b5491d-a643-4ea0-9d7c-d7a875934113 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
645c1cda-f8f3-4ffe-b798-c09f8a9db316 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2
652d85cd-7dca-4650-b09d-38be7c3593fa | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
65a9971a-6362-4e5d-9cb4-3eaf1725e19f | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
753cf3b4-90cc-4803-9c6f-993f901c1bd8 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
7c599f05-e0c5-4df6-b5bc-a71ab5c38a27 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2
9b5df6df-a7fa-43bc-b655-8d4b230c40bc | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2
a045f6a4-5a5f-4005-a009-1d3e74085d87 | Riser | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
a56054d6-e431-4b38-8102-c6340cd0a187 | Junction Enclosure | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
a7f44a4f-90ab-4f83-a5b9-d16942e0f474 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
a9131814-1970-45d0-bb41-9a14a4e9b581 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2
b33758ba-033b-4466-8860-d7ae9e85c794 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2
0687ca96-0d7d-499a-b133-6232b6a7a83a | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
3660f9c8-118f-4a67-a131-8be4912ccb05 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
3e50c77f-a7f2-4955-b0d0-5278041b75a2 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
46015e21-06bd-4a7a-a5ee-6f73f23c3df5 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2023-06-29 | Level 2
5ee63644-9e79-4756-a201-1bf59accbe53 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
5f0f0f98-d7a8-4f7b-8e1c-9eed7eab2f85 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
8b167cad-ced3-48d0-970e-6006b5a91556 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
aed6da2e-7936-4cc0-8dc2-b1c63023fd72 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2023-06-29 | Level 2
cb46753c-69b2-4b62-bfa8-fd6e22d45485 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
d0248b90-8bf6-4a68-bff8-0331537d2212 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
e6196d01-9922-43cd-81e6-ed765dfbaead | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
fd1f1b36-cae1-401f-beab-1a4c00ce6113 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2023-06-29 | Level 2
3c6e3906-5dbc-47c0-ab98-7c06e5d5b54d | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
4211b33e-172d-45bd-9697-8a989f875f1e | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
68d4db95-826e-4a41-99d6-adbacc591d9f | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
7142821b-0126-4800-b5ed-30fe0d80526b | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
932cef69-6251-41a0-9c2b-d4e9c18b70b3 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
a24192c7-d0e0-4b59-a80e-4c1dfa603c19 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2023-06-30 | Level 2
b6a202cc-e85c-4595-9e38-5237c44102d4 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
dc8b62e1-29cd-4951-9234-3c9c888e7a7b | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
ddf4c389-923c-467c-96b0-d0c119361cc2 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
ecad7c32-ba3f-452a-b4fc-8b8a34a72cfc | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
103cbd0e-4c81-4263-82f0-26673268ac69 | Junction Enclosure | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
51d31739-f023-4f0a-af6b-356f3f09467a | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
595d9a28-7679-428a-aac7-2a76ca0a922e | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
6a10e78d-e849-4d53-96ac-903f9d740ad9 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
6b7598d8-da77-4cf2-ac75-b73d0f9b87cf | Junction Enclosure | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
6b836ade-5562-4df0-8732-4fb259dcd55e | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
9b5f2d37-ff25-4842-8de1-153bd7b26a75 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
b05349ad-d090-42f6-b589-162c097954d0 | Junction Enclosure | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
ba067540-1d19-4f4c-b5d3-def1738a8c81 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
cf55623f-419e-4069-989c-94e0947422e3 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2
d5585683-acce-42de-9146-a24e9a28ec94 | Junction Enclosure | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
66e436c3-787b-4ac7-8cb0-2a5d9bc284d8 | Padmount Transformer | 2 | Distribution | 2022-07-02 | 2023-07-02 | Level 2
705da63e-2ba7-43f7-acd8-8bbb9dc75726 | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
737883d5-c881-49dd-a4ba-11d018923726 | Junction Enclosure | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
8408d0f0-77ea-4d51-ba6f-d091d93ee9ca | Junction Enclosure | 2 | Distribution | 2022-07-02 | 2023-07-02 | Level 2
8f1cfaa6-fa5c-4bcd-8cac-67fb4803ad76 | Padmount Transformer | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
9c1dd4ec-db04-49ac-8b38-729c84ad393f | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
a748300e-ff2d-42dc-89a4-eb1d9a4dbf57 | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
c51783c2-eb7f-43dc-9154-9e496a6f7e5a | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
027a2f58-1d17-4e0a-a4a9-c922cbfd3de7 | Junction Enclosure | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
1687162a-3a74-4fd2-a72d-8c2d60f44910 | Padmount Transformer | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
2faa30c4-d4da-4dce-8030-6837ad2ad8ba | Padmount Transformer | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
3493f8c0-f12a-47df-8eac-b81266e89564 | Padmount Transformer | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
5e010107-022c-4acd-8f69-609a66459566 | Padmount Switch | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
6e9caa46-31e9-41e3-b321-2f53f311d61a | Padmount Transformer | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
9a6b5a22-0fe3-49f5-b508-e69a20793bdf | Padmount Transformer | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
cb4353f3-e71b-4310-9627-b21fcefacf07 | Junction Enclosure | 2 | Distribution | 2022-07-05 | 2023-07-05 | Level 2
4c767dc1-5140-4492-9c75-4c402780a616 | Padmount Transformer | 2 | Distribution | 2022-07-06 | 2023-07-06 | Level 2
63af2876-f0e9-4056-afeb-877faba02380 | Padmount Transformer | 2 | Distribution | 2022-07-06 | 2023-07-06 | Level 2
6fda0957-0356-4325-a85d-95b80a10e0f5 | Padmount Transformer | 2 | Distribution | 2022-07-06 | 2023-07-06 | Level 2
80b6e39a-2b60-462f-8500-f8230ff8c88b | Padmount Transformer | 2 | Distribution | 2022-07-06 | 2023-07-06 | Level 2
0eaec015-d283-49a0-b937-bbdabba47018 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2
35c0a14f-e71e-4039-93ba-c1c0a0e077a3 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
39df8bba-e3ec-4586-a4f4-e88ea4e81a39 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
543bdd87-6ad5-4467-a96b-1817cdf1685c | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
68e1d5e5-eff0-424a-9140-d7a6c56d949c | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
7b81f885-698b-40f4-bf70-872bdb3a84c2 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2
7f1ff962-6326-4560-80e9-9bdc6059841a | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
866d4f8a-f536-4f2c-a15e-2fe3d47e28fe | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
9027305d-5ca5-4d5a-9787-94edef7f4c3d | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
96f35bd5-2d54-4ad3-887f-2982b4691c8c | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
af4a2120-e8a6-444a-8cf2-9f9173acc042 | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
cad96719-c1ad-4544-ba90-3d96d7c9daa5 | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
b79fbdf9-cd7d-4c21-b4da-2da62d78492e | Pole | 2 | Distribution | 2022-07-08 | 2027-07-07 | Level 3
239f138e-2956-4b73-a248-a45f866ef2ad | Padmount Switch | 2 | Distribution | 2022-07-09 | 2023-07-09 | Level 2
308a50e2-5367-4c61-a78f-37bfca1d8cf8 | Padmount Switch | 2 | Distribution | 2022-07-09 | 2023-07-09 | Level 2
92530485-8c67-4892-827b-293d16760fab | Riser | 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3
9567cc29-6689-4920-8645-488197aad59f | Padmount Switch | 2 | Distribution | 2022-07-09 | 2023-07-09 | Level 2
d132bcc9-cfc1-4714-a003-0444f573da93 | Padmount Switch | 2 | Distribution | 2022-07-09 | 2023-07-09 | Level 2
d651946a-1810-4220-bad9-ee37a1623a76 | Padmount Transformer | 2 | Distribution | 2022-07-09 | 2023-07-09 | Level 2
d661365c-f23a-4424-b3a5-1608c055c038 | Padmount Transformer | 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3
32a90151-c9ff-402a-8e34-3d86e01a9052 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
60d3794a-6e91-440e-b84e-7ed56015b922 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
6b23045f-95b2-4a67-ac9b-bbc5e6392a53 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
96a352ac-447b-4c8b-a75b-3f4c60b8ba38 | Padmount Switch | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
a7ff1dbf-b76c-4369-86c4-45a8164b6443 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2027-07-12 | Level 3
e018e5b0-b00a-4921-bcd5-f520ecfc857f | Padmount Switch | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
f32beb32-ddc9-4e38-b5bf-cb11af16f838 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2027-07-12 | Level 3
f5bef563-93a4-4e5c-8152-864e6dd8f6b1 | Junction Enclosure | 2 | Distribution | 2022-07-13 | 2027-07-12 | Level 3
2c46a6b7-8e04-4748-afbe-a3cda8019211 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
365bee8d-1b6a-42a1-b2fc-77d25bdadf62 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
49c0182d-a1f1-46de-9431-6770c058615d | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
68a02437-a256-419e-a9d3-f894f99ad010 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
69022e46-c851-4f51-9196-842c44563b72 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
7043c738-d041-43cf-9b14-2807c0406316 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
93f622d5-9481-4454-9711-a95cc62475c9 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
b36e2ca2-b169-4493-9b73-e845e21fd800 | Padmount Switch | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
b548237b-9408-400b-b565-8a28bf3d6739 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
df73377f-8e16-4be6-a8e8-a831c9668a3f | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
0eaa605b-90e2-4dbc-aa23-f842abb4441a | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2
14d3fbec-cdea-436a-b506-902b9b425279 | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2
179aeb7c-a58f-4c01-94bf-2733a6069c87 | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
1e5b4693-4012-4541-94cf-5a10b67cf02c | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2
572a067d-dbe9-492e-9d01-d8016fec4e2f | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
d6efa84d-31c2-4031-b7cb-6913f263534e | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
dc142e9c-5516-485e-8870-39690eb540fd | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
0dcdac62-15c1-4b4d-8bb5-ae602fbde396 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2023-07-16 | Level 2
39732bce-4537-47fc-a2a1-2444145d59fd | Padmount Transformer | 0 | Distribution | 2022-07-16 | 2023-07-16 | Level 2
436bff65-1e42-4cdf-b38d-9154e6ca75eb | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
615eb800-1974-438d-b5e5-b83e4e8b78d6 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
9123d66e-a97f-433c-ab1d-0232923dacb8 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
ba98a25d-f5f8-492a-abb7-8c54732f1ef8 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
cd408b5f-a09a-485f-8f27-e6803a712d42 | Padmount Transformer | 0 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
8a878202-fa41-4e6b-a4df-280c18ce7bd0 | Padmount Transformer | 2 | Distribution | 2022-07-18 | 2023-07-18 | Level 2
11deba5f-8923-4b68-b64f-fc0c83247e94 | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
4d85fbd3-0ecd-4729-be4a-8415b59a261a | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
503b2711-da55-4704-9f2a-7c2d6d4d528f | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
5e15942c-10a5-499d-bc5e-5cf00d088373 | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
ed9c0452-40c1-4795-88a2-77612647cc3f | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
0e1bf72d-2512-4448-ae30-bb458d249f82 | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
3cbd90aa-9655-4e4f-a4ec-802bedc5e9d5 | Riser | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
c97c87ec-f115-42a9-9eb6-7efcdc14342c | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
d2e5e96d-3ff7-4b40-ace8-d17a680cdc57 | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
0ab84f84-a932-43df-b47e-ce294d75037d | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2023-07-21 | Level 2
23dfef54-33e2-4de7-9ce1-208820fd6853 | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2023-07-21 | Level 2
5621a3df-f5c6-4921-9d74-96aaac526093 | Riser | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3
5f70c3c0-a585-4d1f-99c5-c2c97cdaddbe | Riser | 2 | Distribution | 2022-07-21 | 2023-07-21 | Level 2
916aae83-4ce8-466a-b377-bd1a2df74ada | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3
ffc6ab46-5799-4009-924b-309c0bf5c4b0 | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3
09b6a4c9-9d9a-4658-a262-ffae9d6a71f0 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
1921a16a-9eb2-4a74-bd75-b59ed792a8d0 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
7d1c1ce3-6f82-499d-9d0e-ac6a13a28378 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
87bf2d25-51f5-4eda-a819-3e4bc1b3e078 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
8f2cb139-da71-4796-b8eb-1c9491fd93d1 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2023-07-22 | Level 2
915c9f2e-77c3-4454-b5d4-0816e8586cdf | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
91853f5b-ebfa-4c2d-802c-6777e74acc44 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
9d1360b0-d78b-4956-b9a7-c3cff338b71e | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
b4c00fa9-e2d6-467d-9da7-1477bf4ad733 | Junction Enclosure | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
f020a51a-b5df-4f16-a610-6fc66e8217e3 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
1ce135df-0492-4f05-a54f-9bfd206d79cb | Padmount Switch | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
22e3dfd9-6227-46a9-9d10-78e4e0380395 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
2e3b666d-5a2a-4ebd-8ef5-c40eb21d0101 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
30dcd263-f462-417a-85ba-1ed216a3cb18 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
6972277e-1219-4402-98b1-47968c05a7e4 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
830b5119-e30f-421b-985d-cacfda17d10b | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
8778d3f4-313d-43a3-9601-be10799c26f9 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
8afed30d-af2a-41f4-82e2-096f0182e553 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
9124c0a8-8a90-4a28-8c44-4fa166a9667e | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
ba8c44eb-52e6-42b9-a08e-023e286df4d2 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
be65b7a9-0606-4a77-bc91-6909cacb4fe5 | Junction Enclosure | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
c4e084fa-63a2-4377-aa34-6aa94ee6b599 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2023-07-23 | Level 2
cdd81f99-0c1e-4117-bd49-8cc919fafbd3 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
d00f29c3-9cf1-469f-ac39-107417483492 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
e29ddcdd-dcdc-466d-86d7-4baed185d2d4 | Junction Enclosure | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
e3b24731-f94d-4b5e-8a1b-25cf57a7e5f1 | Padmount Switch | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
fdefdf95-fead-4925-b734-d1d13d0ac4ce | Padmount Transformer | 3 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
0362e6ab-ce17-47fe-956a-9f771f25f8c8 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
294e7f47-d95b-497c-864a-d7d66db88130 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
31332b21-931a-44b4-956e-6993ef7ed5b5 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
4886971a-3471-44ca-a661-16449a1380a4 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
5321383c-e6de-4fff-a775-611f046675fa | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
9075fa42-4c3d-487f-a422-210cffd4125d | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
956f4069-31b0-428d-8177-b463da41c82e | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
a911aff4-9c38-4ffe-965d-b093eb1a13f2 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
f503f765-03d2-4afe-8fb4-2de7d0fdb1d3 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
0b50282c-7fd6-49fa-8b00-1f1305cab7f0 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | 2022-07-26 | 2027-07-25
1a27a9cf-dc7f-4bc3-b2e6-fbfe68a30b2c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
31813f44-b57a-4296-85b6-fd66ae276c82 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
4f595da1-4354-4fb8-acba-fd9314f20b0c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2
5a0069b4-5bd0-4b71-bf50-c858e664f10c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
5a5bb1a4-1131-4fc2-8a5f-abb07ab05718 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
675e58bb-28dc-4e04-867a-1bd8b7207473 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2
69642a7e-84c4-4db3-90da-e2d9b776a952 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
77793559-5287-440e-8def-2d3f2ed3bd11 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
884194fe-1dee-4abe-9f39-1f907d53ada5 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
8dd3673d-4c38-4812-9032-9c7028bf5216 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2
95d79daf-b3b6-46a7-95cf-761c5a74859a | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
d2a27a69-d475-4feb-8400-300c992ea1d1 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
d87e3694-0fc7-48a5-8c45-b29c3679e33c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
0a06ac16-598c-424e-b4eb-233e72e13620 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
0b437a6f-992c-4b63-a4a0-8f63bd61e472 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
341d56ad-4a32-4bb0-b9a9-8d3614f11eb2 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
5ac12c6f-3ad7-463e-9239-feeed233a5f6 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2023-07-27 | Level 2
6afb2566-bd9a-4ff9-8468-a7468a5268d8 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
9e7ecdf4-4653-42ac-ad6d-850829b6f1d6 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
a8abaf8e-5bc4-4ba0-85c2-e9a5c7efdfae | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
a9397d43-0dcd-4c29-a948-40b7010d35e0 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
f55618a6-1f62-48fe-8bf2-1115e5f41d21 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
bb476adf-97b8-4815-a240-b138b51e2aa8 | Padmount Transformer | 2 | Distribution | 2022-07-28 | 2027-07-27 | Level 3
be1662c3-9bf6-48ed-aff0-4c87d3afe575 | Padmount Transformer | 2 | Distribution | 2022-07-28 | 2027-07-27 | Level 3
e3327c80-9d0c-4ef7-a5fe-f0536db487c8 | Padmount Transformer | 2 | Distribution | 2022-07-28 | 2027-07-27 | Level 3
1761d8aa-d8bd-4ac7-88c9-76835cd41838 | Pole | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
250c9c34-9c2e-45bd-af09-ab33a48ca98c | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2023-07-29 | Level 2
65d3714c-1df3-4741-b98b-07d6a384ccbe | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
6cb5f3c7-bd45-459b-b014-f082c2b0ebb4 | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
861b19f4-6d5c-4e9c-9ba3-2c6ccad098db | Riser | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
b0268673-e6c0-4cb0-ab9a-6609cf887d27 | Pole | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
e5687798-66d1-40cd-91a7-d3da0ce5a4b4 | Riser | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
ea9c69b8-d525-414d-8a95-f15e5cc68fc7 | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
2e744b36-b962-4744-8d66-c2e62ba5bb58 | Junction Enclosure | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
34676611-518b-4fea-ac97-e8d8543a0ac5 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
45730c84-655a-4bfc-a159-3a0c8f8b6408 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
69a96925-cc06-440c-9b2f-475fc55218d0 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
7410d3df-1fed-4cea-80d6-315c4022df64 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
8e4a5f9f-6632-4d4f-a9f5-1d80070e9d15 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
a6715506-e507-48ed-887e-83fadb3014a5 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
b50f0096-968c-48bf-9e26-a52003b046d3 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
b9a781ed-4ea7-4ce4-a8a3-f1a04afad7b8 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
c5e97d32-4cde-4060-9ba5-6b9dc2766f89 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
ce38b17f-da91-472c-9395-7d1e3d7722cc | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
db1089c1-261e-4831-81da-48dfce9f5005 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
f4343387-4bdd-4505-b3cf-a4b09f7a2010 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
0be8bcc9-67f5-4258-b3dd-a5ae8079bebc | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
551d7049-3680-4d3c-b86a-8ab3c0b39a03 | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
6b16815e-4292-4a3a-b91a-bf8f2bd436fa | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2023-01-28 | Level 2
8932cfee-afd9-4c3a-a74a-1356c81f1554 | Subsurface Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
b0d7d791-1408-4a03-997f-e76303f83691 | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
c12d6384-f464-4de5-95c3-64bddecf4c59 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
c61c9708-851f-4d07-b5e6-9688d560081a | Padmount Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
d5601299-ce56-48d1-a84b-0f66eca70bab | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
d5636e90-0e1a-44fd-8e2a-62427b08c5d7 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
f181aca2-9243-4210-b20b-f296f4d959a0 | Subsurface Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
f60c47f7-4dc0-485d-bd3e-bcf1fdf28e54 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
435f3543-bb37-4136-8ba8-731182324c01 | Padmount Transformer | 2 | Distribution | 2022-08-11 | 2023-08-11 | Level 2
97469f90-6197-4c07-b313-b1e18fa4a873 | Padmount Transformer | 2 | Distribution | 2022-08-11 | 2027-08-10 | Level 3
055d4a8a-a9f3-4084-98f4-33839fc50091 | Subsurface transformer in cabinet | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
090d0960-c0bf-4243-a70d-952b018015c5 | Padmount Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
9455b029-8445-47d2-ae09-d8435a7339a0 | Padmount Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
e8094d4f-dc0b-479d-a747-5b551348ddd3 | Subsurface Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
0184cb9e-1316-4350-8fdc-49ad401c0bc9 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
024331a3-be90-425c-973c-6606c5e02e06 | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
0c19aae1-d27c-4edc-985e-97c0dd54245a | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
22eb09b5-181a-41b7-878e-b93311d44e98 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
24468157-72e7-4e81-9a97-9131fea2a8aa | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
535c7cf6-0fe5-4998-b175-8c659de3f0e2 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
60c7352e-e2ca-41e4-b777-9c66b20e6f58 | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
68ff7442-50c4-42c1-957b-7353b5141e73 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
73b33a60-718e-45e1-be66-7665d45bbb94 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
82dddba8-3724-46af-b675-55fd3cbad637 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
a71ef824-c2bc-4acd-9d39-bf5326eac1e6 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
d627965b-18e3-46f3-80c8-a090d628dd4d | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
8ecb5ecd-7a8b-425d-938f-e04e52b56bc9 | Padmount Transformer | 2 | Distribution | 2022-08-18 | 2023-08-18 | Level 2
f07da56a-f3cc-43de-9464-849917314445 | Padmount Transformer | 2 | Distribution | 2022-08-18 | 2027-08-17 | Level 3
4e8a02b2-8dcc-41cc-a6c9-c15f59a5d881 | Padmount Transformer | 2 | Distribution | 2022-08-20 | 2027-08-19 | Level 3
7aec2cde-0c8b-4373-ae05-963e468e25d8 | Padmount Transformer | 2 | Distribution | 2022-08-20 | 2023-08-20 | Level 2
c68d948b-bfc6-4b81-bfc9-dde35345f055 | Padmount Transformer | 2 | Distribution | 2022-08-20 | 2027-08-19 | Level 3
3e4c6145-134c-4104-a579-0b4309f9c94f | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
41375cd6-eebc-43fd-b564-7cfbd63d5278 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
493f2e0d-d24c-493d-8e8f-1dc94a068fd1 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
4ef37639-9390-4614-9a4c-fb12f82e5f18 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
64e39d77-1867-4417-8e0c-e715fc4f932c | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2
87a165b5-ae73-4c59-bc68-0ac3fc94b44e | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
93e03673-6637-4894-913c-77f87a7eace4 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
a28d12ef-69ed-41df-a1e7-c79e0bfaf05e | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
a767130c-dba3-4952-917f-3ecbef23df55 | Padmount Switch | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
b9023123-e78a-4574-8077-001d9a4529ba | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
cc0a0498-0e59-4468-a87b-d5e286323e83 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2
cfbef4e5-cbf9-40f4-9444-585ce549423a | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2
e41871fe-103e-4997-94fd-40c37951a733 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
05424644-e141-48c3-b836-1e04f775c299 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
1183d39d-1dc9-4c4b-ad48-da44f6057a64 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
279b39fa-e1c9-4903-9c28-68043690652d | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
390e4d13-65ab-4011-90f0-4c9bfc1dbbe1 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
5a590a03-3348-42c7-a656-21ac9d10ae10 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
6b1ae1a4-428b-4dba-97f2-a493b71f6c90 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
7d8dd5db-5b95-4953-9214-71f4ea07b834 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
8029cc16-eaec-49cf-af10-4ec84ae103f1 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
9871f144-207f-445a-83d2-e70b618e35f5 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
af1cb5e4-d7c6-4250-ad1e-b0c8ba097f58 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
f5f7f618-595e-458b-9551-fc38426e872c | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
fa9a583e-e74f-4d93-9403-9463f183dc81 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
e639a6bc-d4c8-49ff-aa17-ea6ae6d6bcdf | Pole | 2 | Distribution | 2022-09-10 | 2023-09-10 | Level 2 |  | 2022-09-01 | 2023-09-01 |  | Required to Re-inspect a subset of assets
3c855010-4141-4bd1-8816-7c7dd8e3e396 | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
575f5753-2477-4b9b-a2e1-a7602258edfc | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
58942f1a-5036-44b2-91b6-f30a3ef7760f | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
5bdf31cc-12ba-40bd-945b-df6d16365a4b | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
6b552787-0918-4b6a-bd9f-97930d93230e | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
986ff4b7-5132-4b0d-9221-aff00fb9ed4e | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
bfde1b03-fd7c-428a-9801-45647e7f245d | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
13022bd5-a541-404d-b7ad-91aa761151c3 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
2439f181-39ee-431e-89e9-0e27b0b4fb44 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
4384139a-8914-4f69-898a-dcfc983d3606 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
889d3755-0ce9-4849-a53f-a410f3d60766 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
dc6d9ebd-a35d-4e38-a32f-380c68d11fb1 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
dd30c485-f732-48af-a419-c23e6af5be23 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
d689b31a-dfb8-45a3-84d8-941810274be7 | Pole | 2 | Distribution | 2022-11-23 | 2027-11-22 | Level 3
0e390fe4-c150-4bb1-bd86-8ee5d6a963ca | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
89926fbb-cae6-49c3-b81a-361100e2f151 | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
adef5ec6-94cb-4749-aa95-9a009b4f90c3 | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
e4d54697-90b4-4c0f-8054-564699302bad | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
1d870439-b07c-4d3b-bd87-e32e995d0f1d | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3
603c4036-e86a-4ab3-8508-2af5613496a9 | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3
6683fc71-8b48-4287-b7c9-05b6e14e884c | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3

## Table 14
Utility | Liberty
Table No. | 14
Date Modified
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution
HFTD 2 Distribution
HFTD 3 Distribution
Non-HFTD Transmission
HFTD 2 Transmission
HFTD 3 Transmission

## Table 15
Utility | Liberty
Table No. | 15
Date Modified | 2023-02-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS | Comments
MEY3300 |  | Primary | 52.59 |  | Tier 2/Tier 3 | Very High | [15 empty] | The overall circuit risk is based on the Circuit Risk Asessment presented in Liberty's 2021 WMP Update. Liberty plans to update its risk analysis and circuit risk scores to include additional components listed in Table 15 over the 2023-2025 WMP cycle.
MULLER1296 |  | Primary | 43.62 |  | Tier 2 | Very High | [15 empty] | The overall circuit risk is based on the Circuit Risk Asessment presented in Liberty's 2021 WMP Update. Liberty plans to update its risk analysis and circuit risk assessment over the 2023-2025 WMP cycle.
MEY3400 |  | Primary | 54.37 |  | Tier 2/Tier 3 | High | [15 empty] | The overall circuit risk is based on the Circuit Risk Asessment presented in Liberty's 2021 WMP Update. Liberty plans to update its risk analysis and circuit risk assessment over the 2023-2025 WMP cycle.