## Expense Summary
Expense - 2022 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
2022 WMP Initiative # | 2022 WMP Initiative Name | 2022 Fcst | 2022 Actual | Var. | Threshold for change (over $10M and greater than 20%) | Variance Driver
7.3.1.1 | 7.3.1.1 A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.1.2 | 7.3.1.2 Climate-driven risk map and modeling based on various relevant weather scenarios | 1572 | 2684.6688 | 1112.6688 | not meet | N/A - does not meet threshold
7.3.1.3 | 7.3.1.3 Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.1.4 | 7.3.1.4 Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 168.4643 | 168.4643 | 0 | not meet | N/A - does not meet threshold
7.3.1.5 | 7.3.1.5 Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 3200 | 3189.104 | -10.896 | not meet | N/A - does not meet threshold
7.3.2.1.1 | 7.3.2.1.1 Advanced weather monitoring and weather stations, Numerical Weather Prediction | 789.075 | 826.9644 | 37.8894 | not meet | N/A - does not meet threshold
7.3.2.1.2 | 7.3.2.1.2 Advanced weather monitoring and weather stations, Fuel Moisture Sampling and Modeling | 598.0965 | 551.7479 | -46.3485 | not meet | N/A - does not meet threshold
7.3.2.1.3 | 7.3.2.1.3 Advanced weather monitoring and weather stations, Weather Stations | 1595.2679 | 1934.2225 | 338.9546 | not meet | N/A - does not meet threshold
7.3.2.1.4 | 7.3.2.1.4 Advanced weather monitoring and weather stations, Wildfire Cameras | 11211.216 | 11878.3265 | 667.1105 | not meet | N/A - does not meet threshold
7.3.2.1.5 | 7.3.2.1.5 Advanced weather monitoring and weather stations, Fire Detection & Alerting | 341.3279 | 312.3866 | -28.9413 | not meet | N/A - does not meet threshold
7.3.2.1.6 | 7.3.2.1.6 Advanced weather monitoring and weather stations, Other Meteorology Tools and Upgrades | 1020 | 400.2572 | -619.7428 | not meet | N/A - does not meet threshold
7.3.2.2.1 | No 2022 Activity - 7.3.2.2.1 Continuous monitoring sensors, Electric Transmission SEL T400L | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.2.2 | No 2022 Activity - 7.3.2.2.2 Continuous monitoring sensors, SmartMeter™ Partial Voltage Detection (Formerly Known as Enhanced Wires Down Detection) | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.2.3 | 7.3.2.2.3 Continuous monitoring sensors, Distribution Fault Anticipation Technology and Early Fault Detection | 2573.4993 | 264.8238 | -2308.6756 | not meet | N/A - does not meet threshold
7.3.2.2.4 | 7.3.2.2.4 Continuous monitoring sensors, Sensor IQ | 0 | 26.5423 | 26.5423 | not meet | N/A - does not meet threshold
7.3.2.2.5 | 7.3.2.2.5 Continuous monitoring sensors, Line Sensor Devices | 0 | 1232.6982 | 1232.6982 | not meet | N/A - does not meet threshold
7.3.2.2.6 | 7.3.2.2.6 Continuous monitoring sensors, Distribution Arcing Fault Signature Library | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.2.7 | 7.3.2.2.6 Continuous monitoring sensors, DTS FAST | 600 | 596.007 | -3.993 | not meet | N/A - does not meet threshold
7.3.2.3 | 7.3.2.3 Fault indicators for detecting faults on electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.4 | 7.3.2.4 Forecast of a fire risk index, fire potential index, or similar | 1867.1707 | 1522.5826 | -344.5881 | not meet | N/A - does not meet threshold
7.3.2.5 | 7.3.2.5 Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 4841.3383 | 3956.9697 | -884.3686 | not meet | N/A - does not meet threshold
7.3.2.6 | 7.3.2.6 Weather forecasting and estimating impacts on electric lines and equipment | 1107.8211 | 746.0634 | -361.7577 | not meet | N/A - does not meet threshold
7.3.2.8 | No 2022 Activity - 7.3.2.8 Other, Meteorology Analytics/Operations Center | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.7 | 7.3.2.7 Other, Wildfire Safety Operations Center (WSOC) | 6981.0461 | 4269.2623 | -2711.7837 | not meet | N/A - does not meet threshold
7.3.3.1 | 7.3.3.1 Capacitor maintenance and replacement program | 2369.2363 | 2843.1651 | 473.9289 | not meet | N/A - does not meet threshold
7.3.3.2-D | 7.3.3.2-D Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Distribution | 2585.9803 | 3482.6426 | 896.6623 | not meet | N/A - does not meet threshold
7.3.3.2-T | 7.3.3.2-T Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Transmission | 2444.5316 | 2225.2238 | -219.3078 | not meet | N/A - does not meet threshold
7.3.3.3 | 7.3.3.3 Covered conductor installation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.4 | 7.3.3.4 Covered conductor maintenance | 9013.3054 | 11192.421 | 2179.1156 | not meet | N/A - does not meet threshold
7.3.3.5 | 7.3.3.5 Crossarm maintenance, repair, and replacement | 2567.1658 | 715.0768 | -1852.089 | not meet | N/A - does not meet threshold
7.3.3.6 | 7.3.3.6 Distribution pole replacement and reinforcement, including with composite poles | 3460.0221 | 3362.5204 | -97.5017 | not meet | N/A - does not meet threshold
7.3.3.7 | 7.3.3.7 Expulsion fuse replacement | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.8.1 | 7.3.3.8.1 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Sectionalizing | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.8.2 | 7.3.3.8.2 Grid topology improvements to mitigate or reduce PSPS events, Transmission Line Sectionalizing | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.8.3 | 7.3.3.8.3 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Motorized Switch Operator Pilot | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.9.1 | 7.3.3.9.1 Installation of system automation equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.9.2 | 7.3.3.9.2 Installation of system automation equipment, Single phase reclosers | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.10 | 7.3.3.10 Maintenance, repair, and replacement of connectors, including hotline clamps | 14596.8005 | 10251.0847 | -4345.7159 | not meet | N/A - does not meet threshold
7.3.3.11.1 | 7.3.3.11.1 Mitigation of impact on customers and other residents affected during PSPS event, Generation for PSPS Mitigation | 112689.5805 | 40589.8345 | -72099.746 | meet | Variance mainly driven by: 1) Temporary generation rental cost - lower due to 2021 over-accrual adjustment ($19M) and overall rental quantity (# of MWs) 2) Reduced operating costs incurred driven by minimal PSPS activity
7.3.3.11.2 | 7.3.3.11.2 Mitigation of impact on customers and other residents affected during PSPS event, Substation activities to enable reduction of PSPS impacts | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.11.3 | 7.3.3.11.3 Mitigation of impact on customers and other residents affected during PSPS event, Emergency Back-up Generation – PG&E Service Centers & Materials Distribution Centers | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.11.4 | 7.3.3.11.4 Fixed Power Solutions | 7800 | 2103.8663 | -5696.1337 | not meet | N/A - does not meet threshold
7.3.3.12.1 | 7.3.3.12.1 Other corrective action, Distribution Substation | 976.9113 | 836.596 | -140.3153 | not meet | N/A - does not meet threshold
7.3.3.12.2 | 7.3.3.12.2 Other corrective action, Transmission Substation | 504.1428 | 1136.351 | 632.2082 | not meet | N/A - does not meet threshold
7.3.3.12.3 | 7.3.3.12.3 Other corrective action, Maintenance, Transmission | 127975.5381 | 90649.114 | -37326.4241 | meet | Variance mainly driven by: - reclassification of Bay Towers costs to capital - Lower volume of work for wooden structure (MAT ICW) compared to plan; also unit cost was favorable due to efficiency/savings
7.3.3.12.4 | 7.3.3.12.4 Other corrective action, Maintenance, Distribution | 93704.4326 | 82510.2202 | -11194.2124 | not meet | N/A - does not meet threshold
7.3.3.12.5 | 7.3.3.12.5 Other corrective action, Generation Substation | 2839.3903 | 3353.6816 | 514.2913 | not meet | N/A - does not meet threshold
7.3.3.13 | 7.3.3.13 Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 154.455 | 0 | -154.455 | not meet | N/A - does not meet threshold
7.3.3.14 | 7.3.3.14 Transformers maintenance and replacement | 1335.0436 | 661.1994 | -673.8442 | not meet | N/A - does not meet threshold
7.3.3.15 | 7.3.3.15 Transmission tower maintenance and replacement | 50261.2325 | 68704.561 | 18443.3285 | meet | Variance mainly driven by: - Maintenance Program (MAT ICS) - higher units worked than planned - Tower Coating program (MAT ICX) - Paint Tag cost remained in expense to align actual costs and funding per capital accounting guidance
7.3.3.16 | 7.3.3.16 Undergrounding of electric lines and/or equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.17.1 | 7.3.3.17.1 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.17.2 | 7.3.3.17.2 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Transmission | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.17.3 | 7.3.3.17.3 Updates to grid topology to minimize risk of ignition in HFTDs, Surge Arrestor | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.17.4 | No 2022 financial data - 7.3.3.17.4 Updates to grid topology to minimize risk of ignition in HFTDs, Rapid Earth Current Fault Limiter | 0 | 818.9029 | 818.9029 | not meet | N/A - does not meet threshold
7.3.3.17.5 | 7.3.3.17.5 Updates to grid topology to minimize risk of ignition in HFTDs, Remote Grid | 14824.2289 | 2028.8633 | -12795.3656 | meet | Variance mainly driven by: - PG&E did not complete any Line Elimination Incentive Program (LEIP) projects. This was due to fewer than expected new opportunities for the LEIP and to opportunities pursued where PG&E could not reach mutual agreement to discontinue electric service.
7.3.3.17.6 | 7.3.3.17.6 Updates to grid topology to minimize risk of ignition in HFTDs, Butte County Rebuild | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.1 | 7.3.4.1 Detailed inspections of distribution electric lines and equipment | 100378.9799 | 98300.3642 | -2078.6157 | not meet | N/A - does not meet threshold
7.3.4.2 | 7.3.4.2 Detailed inspections of transmission electric lines and equipment | 86707.253 | 68327.2321 | -18380.0209 | meet | Variance mainly driven by: - Favorable unit cost - Aerial Inspection (BF2) desktop review contract updated with favorable rates.
7.3.4.3 | 7.3.4.3 Improvement of inspections | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.4 | 7.3.4.4 Infrared inspections of distribution electric lines and equipment | 2225.8927 | 1987.8783 | -238.0144 | not meet | N/A - does not meet threshold
7.3.4.5 | 7.3.4.5 Infrared inspections of transmission electric lines and equipment | 2220 | 3659.6682 | 1439.6682 | not meet | N/A - does not meet threshold
7.3.4.6.1 | 7.3.4.6.1 Intrusive pole inspections, Distribution | 21239.442 | 20553.6291 | -685.8129 | not meet | N/A - does not meet threshold
7.3.4.6.2 | 7.3.4.6.2 Intrusive pole inspections, Transmission | 2150 | 1694.2239 | -455.7761 | not meet | N/A - does not meet threshold
7.3.4.7 | 7.3.4.7 LiDAR Inspections of Distribution Electric Lines and Equipment | 10500 | 8457.3615 | -2042.6385 | not meet | N/A - does not meet threshold
7.3.4.8 | 7.3.4.8 LiDAR Inspections of Transmission Electric Lines and Equipment | 5030 | 3741.7738 | -1288.2262 | not meet | N/A - does not meet threshold
7.3.4.9 | 7.3.4.9 Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 3257.6179 | 4029.9256 | 772.3078 | not meet | N/A - does not meet threshold
7.3.4.10 | 7.3.4.10 Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 4300 | 0 | -4300 | not meet | N/A - does not meet threshold
7.3.4.11 | 7.3.4.11 Patrol inspections of distribution electric lines and equipment | 6062.9179 | 8394.2028 | 2331.2848 | not meet | N/A - does not meet threshold
7.3.4.12 | 7.3.4.12 Patrol inspections of transmission electric lines and equipment | 83.6831 | 49.4885 | -34.1946 | not meet | N/A - does not meet threshold
7.3.4.13 | 7.3.4.13 Pole loading assessment program to determine safety factor | 9122.83 | 8952.2548 | -170.5752 | not meet | N/A - does not meet threshold
7.3.4.14 | 7.3.4.14 Quality assurance / quality control of inspections | 6015.9077 | 6415.1061 | 399.1984 | not meet | N/A - does not meet threshold
7.3.4.15-T | 7.3.4.15-T Substation inspections, Enhanced Transmission, Substation | 1757.465 | 1740.387 | -17.078 | not meet | N/A - does not meet threshold
7.3.4.15-D | 7.3.4.15-D Substation inspections, Enhanced Distribution, Substation | 4397.3044 | 2956.126 | -1441.1784 | not meet | N/A - does not meet threshold
7.3.4.16 | 7.3.4.16, Other, Substation inspections, Generation | 1141.3333 | 1036.0696 | -105.2638 | not meet | N/A - does not meet threshold
7.3.5.1 | 7.3.5.1 Additional efforts to manage community and environmental impacts | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.2 | 7.3.5.2 Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment | 1370788.1352 | 1338158.56 | -32629.5752 | not meet | N/A - does not meet threshold
7.3.5.3 | 7.3.5.3 Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment | 111609.484 | 118608.391 | 6998.907 | not meet | N/A - does not meet threshold
7.3.5.4 | 7.3.5.4 Emergency response vegetation management due to red flag warning or other urgent climate conditions | 3126.977 | 3126.977 | 0 | not meet | N/A - does not meet threshold
7.3.5.5 | 7.3.5.5 Fuel management (including all wood management) and reduction of “slash” from vegetation management activities | 92609.6675 | 160447.05 | 67837.3825 | meet | Variance mainly driven by: - Significantly more units completed than initial forecast, at a higher unit cost. All wood management is based on customer opt-in’s which can vary by region or any given year. Further, disposal fees and T&M rates for R-4 and difficult to access units contributed to a higher unit cost relative to plan. - Partially offset by wood management roll out into the routine program did not come to fruition. As such, funding requested for incremental headcount and work execution did not materialize as forecasted.
7.3.5.6 | 7.3.5.6 Improvement of inspections | 143138.4921 | 68799.88 | -74338.6121 | meet | Variance mainly driven by: - Due to change in QC commitment, funding was reprioritized for higher risk work. Team finished 2021 commitment in 2022 (’21 VM Tree work was completed in the following year), did QC sampling, field quality assessments and quality assurance work. - Staffing levels for both internal and external work verifications were lower than forecasted combined with contractor conversions and efficiencies leading to reduced spend.
7.3.5.7 | 7.3.5.7 Remote sensing inspections of vegetation around distribution electric lines and equipment | 37090.1758 | 3641.45 | -33448.7258 | meet | Variance mainly driven by: - Significant reduction in Ground based LiDAR scope due to the WMP commitment of 2k miles vs. potential opportunity to collect ~49% of HFTD spans. Re-flight/ aerial collection of data was de-scoped. WMP forecasted spend followed a 6AOI allocation based on an anticipate level of programmatic support.
7.3.5.8 | 7.3.5.8 Remote sensing inspections of vegetation around transmission electric lines and equipment | 13000 | 7769.761 | -5230.239 | not meet | N/A - does not meet threshold
7.3.5.9 | 7.3.5.9 Other discretionary inspections of vegetation around distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.10 | 7.3.5.10 Other discretionary inspections of vegetation around transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.11 | 7.3.5.11 Patrol inspections of vegetation around distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.12 | 7.3.5.12 Patrol inspections of vegetation around transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.13 | 7.3.5.13 Quality assurance / quality control of vegetation inspections | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.14 | 7.3.5.14 Recruiting and training of vegetation management personnel | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.15 | 7.3.5.15 Identification and remediation of "at-risk species" | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.16 | 7.3.5.16 Removal and remediation of trees with strike potential to electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.17.1 | 7.3.5.17.1 Substation inspection , Distribution substation | 552.779 | 848.705 | 295.926 | not meet | N/A - does not meet threshold
7.3.5.17.2 | 7.3.5.17.2 Substation inspection, Transmission substation | 232.938 | 740.153 | 507.215 | not meet | N/A - does not meet threshold
7.3.5.17.3 | 7.3.5.17.3 Substation inspection, Generation substation | 1766.3333 | 1806.9861 | 40.6527 | not meet | N/A - does not meet threshold
7.3.5.18.1 | 7.3.5.18.1 Substation vegetation management, Maintenance substation distribution | 1265.501 | 2458.129 | 1192.628 | not meet | N/A - does not meet threshold
7.3.5.18.2 | 7.3.5.18.2 Substation vegetation management, Maintenance substation transmission | 1252.9987 | 863.876 | -389.1227 | not meet | N/A - does not meet threshold
7.3.5.18.3 | 7.3.5.18.3 Substation vegetation management, Maintenance substation Generation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.19 | 7.3.5.19 Vegetation management system | 92516.1157 | 21379.14 | -71136.9757 | meet | VM team provide update on 3/29 pm: - ~$75M of the forecast was earmarked to help with a transition away from EVM at the beginning of 2022. This was intended to revisit procedures, update trainings and work on lessons learned. However, the EVM program continued on through 2022, so these money was reallocated back to the EVM program.
7.3.5.20 | 7.3.5.20 Additional vegetation management practices beyond regulatory requirements and recommendations | 32353.9608 | 28913.99 | -3439.9708 | not meet | N/A - does not meet threshold
7.3.5.21 | 7.3.5.21 Vegetation management activities post-fire | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.1 | 7.3.6.1 Automatic recloser operations | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.2 | 7.3.6.2 Crew-accompanying ignition prevention and suppression resources and services | 14524.0149 | 11870.909 | -2653.1059 | not meet | N/A - does not meet threshold
7.3.6.3 | 7.3.6.3 Personnel work procedures and training in conditions of elevated fire risk | 1000 | 808.4113 | -191.5887 | not meet | N/A - does not meet threshold
7.3.6.4-D | 7.3.6.4-D Protocols for PSPS re-energization, Distribution | 10093.2135 | 9272.4519 | -820.7616 | not meet | N/A - does not meet threshold
7.3.6.4-T | 7.3.6.4-T Protocols for PSPS re-energization, Transmission | 2000 | 440.3739 | -1559.6261 | not meet | N/A - does not meet threshold
7.3.6.5-D | 7.3.6.5-D PSPS events and mitigation of PSPS impacts , Distribution | 68814.333 | 2.6499 | -68811.6831 | meet | Variance mainly driven by: - PSPS events did not happen as weather conditions was more favorable in 2022
7.3.6.5-T | 7.3.6.5-T PSPS events and mitigation of PSPS impacts , Transmission | 1807.925 | 7.882 | -1800.043 | not meet | N/A - does not meet threshold
7.3.6.6 | 7.3.6.6 Stationed and on-call ignition prevention and suppression resources and services | 4841.3383 | 791.3939 | -4049.9444 | not meet | N/A - does not meet threshold
7.3.6.7 | 7.3.6.7 Other, Aviation Support | 6142 | 2569.2103 | -3572.7897 | not meet | N/A - does not meet threshold
7.3.6.8 | 7.3.6.8 Protective equipment and device settings | 142592.2 | 82889.3885 | -59702.8115 | meet | Variance mainly driven by: - EPSS Patrol lower than planned primarily due to improvements/efficiencies made by the EPSS program (e.g., daily EPSS enablement/disablement based on wildfire risk and installing fault indicators to narrow down circuit area for outage patrol)
7.3.7.1 | 7.3.7.1 Centralized repository for data | 857.7958 | 857.7958 | 0 | not meet | N/A - does not meet threshold
7.3.7.2 | 7.3.7.2 Collaborative research on utility ignition and/or wildfire | 866 | 295.7302 | -570.2698 | not meet | N/A - does not meet threshold
7.3.7.3 | 7.3.7.3 Documentation and disclosure of wildfire-related data and algorithms | 1047.3536 | 1047.3536 | 0 | not meet | N/A - does not meet threshold
7.3.7.4 | 7.3.7.4 Tracking and analysis of near miss data | 650.6529 | 650.6529 | 0 | not meet | N/A - does not meet threshold
7.3.7.5 | 7.3.7.5 Other, IT projects to support wildfire mitigation work | 45100.0056 | 44059.6774 | -1040.3281 | not meet | N/A - does not meet threshold
7.3.8.1 | 7.3.8.1 Allocation methodology development and application | 3485.7611 | 1262.3355 | -2223.4256 | not meet | N/A - does not meet threshold
7.3.8.2 | 7.3.8.2 Risk reduction scenario development and analysis | 62.1916 | 62.1916 | 0 | not meet | N/A - does not meet threshold
7.3.8.3 | 7.3.8.3 Risk spend efficiency analysis (RSE) | 933.7633 | 933.7633 | 0 | not meet | N/A - does not meet threshold
7.3.9.1 | 7.3.9.1 Adequate and trained workforce for service restoration | 7666.0593 | 7277.4476 | -388.6116 | not meet | N/A - does not meet threshold
7.3.9.2 | 7.3.9.2 Community outreach, public awareness, and communications efforts | 21739.4284 | 17157.3547 | -4582.0737 | not meet | N/A - does not meet threshold
7.3.9.3 | 7.3.9.3 Customer support in emergencies | 3413.3412 | 2287.7805 | -1125.5607 | not meet | N/A - does not meet threshold
7.3.9.4 | 7.3.9.4 Disaster and emergency preparedness plan | 6843.4437 | 4712.2493 | -2131.1944 | not meet | N/A - does not meet threshold
7.3.9.5 | 7.3.9.5 Preparedness and planning for service restoration | 15794.469 | 10351.3177 | -5443.1513 | not meet | N/A - does not meet threshold
7.3.9.6 | 7.3.9.6 Protocols in place to learn from wildfire events | 1235.8906 | 1235.8906 | 0 | not meet | N/A - does not meet threshold
7.3.10.1 | 7.3.10.1 Community engagement | 20615.9564 | 16347.4358 | -4268.5207 | not meet | N/A - does not meet threshold
7.3.10.2 | 7.3.10.2 Cooperation and best practice sharing with agencies outside CA | 193.2407 | 179.661 | -13.5797 | not meet | N/A - does not meet threshold
7.3.10.3 | 7.3.10.3 Cooperation with suppression agencies | 4532.2125 | 4788.3371 | 256.1246 | not meet | N/A - does not meet threshold
7.3.10.4 | 7.3.10.4 Forest service and fuel reduction cooperation and joint roadmap | 5132.6675 | 3098.99 | -2033.6775 | not meet | N/A - does not meet threshold
7.3.10.5 | 7.3.10.5 Other, PMO and General Wildfire Support | 24192.6411 | 27419.6599 | 3227.0188 | not meet | N/A - does not meet threshold
| Total | 3072640.4048 | 2612563.4511 | -460076.9537

## Capital Summary
Capital - 2022 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
2022 WMP Initiative # | 2022 WMP Initiative Name | 2022 Fcst | 2022 Actual | Var. | Threshold for change (over $10M and greater than 20%) | Variance Driver
7.3.1.1 | 7.3.1.1 A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 909.8101 | 510.5451 | -399.265 | not meet | N/A - does not meet threshold
7.3.1.2 | 7.3.1.2 Climate-driven risk map and modeling based on various relevant weather scenarios | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.1.3 | 7.3.1.3 Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 909.8101 | 510.5451 | -399.265 | not meet | N/A - does not meet threshold
7.3.1.4 | 7.3.1.4 Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.1.5 | 7.3.1.5 Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 1194 | 1170.0543 | -23.9457 | not meet | N/A - does not meet threshold
7.3.2.1.1 | 7.3.2.1.1 Advanced weather monitoring and weather stations, Numerical Weather Prediction | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.1.2 | 7.3.2.1.2 Advanced weather monitoring and weather stations, Fuel Moisture Sampling and Modeling | 0 | 0.35106 | 0.35106 | not meet | N/A - does not meet threshold
7.3.2.1.3 | 7.3.2.1.3 Advanced weather monitoring and weather stations, Weather Stations | 6181.3442 | 5625.0762 | -556.268 | not meet | N/A - does not meet threshold
7.3.2.1.4 | 7.3.2.1.4 Advanced weather monitoring and weather stations, Wildfire Cameras | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.1.5 | 7.3.2.1.5 Advanced weather monitoring and weather stations, Fire Detection & Alerting | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.1.6 | 7.3.2.1.6 Advanced weather monitoring and weather stations, Other Meteorology Tools and Upgrades | 0 | 0.24574 | 0.24574 | not meet | N/A - does not meet threshold
7.3.2.2.1 | No 2022 Activity - 7.3.2.2.1 Continuous monitoring sensors, Electric Transmission SEL T400L | 0 | 134.9162 | 134.9162 | not meet | N/A - does not meet threshold
7.3.2.2.2 | No 2022 Activity - 7.3.2.2.2 Continuous monitoring sensors, SmartMeter™ Partial Voltage Detection (Formerly Known as Enhanced Wires Down Detection) | 0 | 7.4248 | 7.4248 | not meet | N/A - does not meet threshold
7.3.2.2.3 | 7.3.2.2.3 Continuous monitoring sensors, Distribution Fault Anticipation Technology and Early Fault Detection | 14579.4178 | 9942.4689 | -4636.9489 | not meet | N/A - does not meet threshold
7.3.2.2.4 | 7.3.2.2.4 Continuous monitoring sensors, Sensor IQ | 0 | 0.02615 | 0.02615 | not meet | N/A - does not meet threshold
7.3.2.2.5 | 7.3.2.2.5 Continuous monitoring sensors, Line Sensor Devices | 7812.786 | 2291.1971 | -5521.5889 | not meet | N/A - does not meet threshold
7.3.2.2.6 | 7.3.2.2.6 Continuous monitoring sensors, Distribution Arcing Fault Signature Library | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.2.7 | 7.3.2.2.6 Continuous monitoring sensors, DTS FAST | 19452 | 2957.8918 | -16494.1082 | meet | Variance mainly driven by: - Decreased program forecast due to budgetary reduction. Program paused transmission efforts in late 2021. In 2022, the program did not receive the required funding necessary to continue efforts to deploy DTS-FAST. In the interim, the program is looking to make the system more scalable and cost effective to deploy.
7.3.2.3 | 7.3.2.3 Fault indicators for detecting faults on electric lines and equipment | 0 | 79.3713 | 79.3713 | not meet | N/A - does not meet threshold
7.3.2.4 | 7.3.2.4 Forecast of a fire risk index, fire potential index, or similar | 0 | 2.9138 | 2.9138 | not meet | N/A - does not meet threshold
7.3.2.5 | 7.3.2.5 Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 230.0126 | 8.5697 | -221.4428 | not meet | N/A - does not meet threshold
7.3.2.6 | 7.3.2.6 Weather forecasting and estimating impacts on electric lines and equipment | 1022.9234 | 728.8202 | -294.1031 | not meet | N/A - does not meet threshold
7.3.2.8 | No 2022 Activity - 7.3.2.8 Other, Meteorology Analytics/Operations Center | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.2.7 | 7.3.2.7 Other, Wildfire Safety Operations Center (WSOC) | 124.6707 | 23.2503 | -101.4204 | not meet | N/A - does not meet threshold
7.3.3.1 | 7.3.3.1 Capacitor maintenance and replacement program | 10549.2358 | 11855.4282 | 1306.1925 | not meet | N/A - does not meet threshold
7.3.3.2-D | 7.3.3.2-D Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Distribution | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.2-T | 7.3.3.2-T Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Transmission | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.3 | 7.3.3.3 Covered conductor installation | 366000 | 285543.7965 | -80456.2035 | meet | Variance mainly driven by: - favorable unit cost performance from reduction of pre-construction vegetation clearing and implementation of unit price RFP contract strategy
7.3.3.4 | 7.3.3.4 Covered conductor maintenance | 44386.3098 | 39994.0152 | -4392.2946 | not meet | N/A - does not meet threshold
7.3.3.5 | 7.3.3.5 Crossarm maintenance, repair, and replacement | 71788.1646 | 76476.8907 | 4688.726 | not meet | N/A - does not meet threshold
7.3.3.6 | 7.3.3.6 Distribution pole replacement and reinforcement, including with composite poles | 419170.185 | 489698.8336 | 70528.6486 | not meet | N/A - does not meet threshold
7.3.3.7 | 7.3.3.7 Expulsion fuse replacement | 35000 | 23064.1995 | -11935.8005 | meet | Variance mainly driven by: - favorable unit cost performance
7.3.3.8.1 | 7.3.3.8.1 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Sectionalizing | 10452.1989 | 13217.0844 | 2764.8855 | not meet | N/A - does not meet threshold
7.3.3.8.2 | 7.3.3.8.2 Grid topology improvements to mitigate or reduce PSPS events, Transmission Line Sectionalizing | 54247.7608 | 28806.6888 | -25441.072 | meet | Variance mainly driven by: - 2022 forecast showed cost for entire MAT code 94A which includes non-WMP related work; while 2022 Actuals are selecting specific SCADA projects that mitigate PSPS impacts
7.3.3.8.3 | 7.3.3.8.3 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Motorized Switch Operator Pilot | 10452.1989 | 6608.5422 | -3843.6567 | not meet | N/A - does not meet threshold
7.3.3.9.1 | 7.3.3.9.1 Installation of system automation equipment | 15598.7243 | 17350.5519 | 1751.8276 | not meet | N/A - does not meet threshold
7.3.3.9.2 | 7.3.3.9.2 Installation of system automation equipment, Single phase reclosers | 4400 | 10596.8485 | 6196.8485 | not meet | N/A - does not meet threshold
7.3.3.10 | 7.3.3.10 Maintenance, repair, and replacement of connectors, including hotline clamps | 3134.7231 | 2406.058 | -728.6651 | not meet | N/A - does not meet threshold
7.3.3.11.1 | 7.3.3.11.1 Mitigation of impact on customers and other residents affected during PSPS event, Generation for PSPS Mitigation | 23324.9089 | 11360.2007 | -11964.7082 | meet | Variance mainly driven by: - Lower spend on CMEP capital projects due to long lead time for capital projects identification and development - Distribution Microgrids PIH: Actual costs lower due to much of work completed prior to 2022, also updated workplan for 4 locations, 3 improvement projects.
7.3.3.11.2 | 7.3.3.11.2 Mitigation of impact on customers and other residents affected during PSPS event, Substation activities to enable reduction of PSPS impacts | 681 | 863.6387 | 182.6387 | not meet | N/A - does not meet threshold
7.3.3.11.3 | 7.3.3.11.3 Mitigation of impact on customers and other residents affected during PSPS event, Emergency Back-up Generation – PG&E Service Centers & Materials Distribution Centers | 18000 | 16670.1087 | -1329.8913 | not meet | N/A - does not meet threshold
7.3.3.11.4 | 7.3.3.11.4 Fixed Power Solutions | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.12.1 | 7.3.3.12.1 Other corrective action, Distribution Substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.12.2 | 7.3.3.12.2 Other corrective action, Transmission Substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.12.3 | 7.3.3.12.3 Other corrective action, Maintenance, Transmission | 412054.6501 | 464593.8498 | 52539.1997 | not meet | N/A - does not meet threshold
7.3.3.12.4 | 7.3.3.12.4 Other corrective action, Maintenance, Distribution | 196540.8369 | 325803.9985 | 129263.1617 | meet | Variance mainly driven by: - higher cost of materials/equipment due to supply chain issues - higher usage of contract resources
7.3.3.12.5 | 7.3.3.12.5 Other corrective action, Generation Substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.3.13 | 7.3.3.13 Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 9236.196 | 16364.9624 | 7128.7664 | not meet | N/A - does not meet threshold
7.3.3.14 | 7.3.3.14 Transformers maintenance and replacement | 22485.2165 | 29051.8473 | 6566.6308 | not meet | N/A - does not meet threshold
7.3.3.15 | 7.3.3.15 Transmission tower maintenance and replacement | 154981 | 66780.4889 | -88200.5111 | meet | Variance mainly driven by: - anticipated delays in the work scheduled due to permitting and access constraints for multiple Ignacio-Mare Island (230kV) tower replacements. - Underrun driven due to favorability vs original job estimate from successful contract negotiations on Lammers-Kasson (115kV) and SF Martin (115kV) Projects. - Project deferrals due to funding constraints
7.3.3.16 | 7.3.3.16 Undergrounding of electric lines and/or equipment | 611250 | 406761.6401 | -204488.3599 | meet | Variance mainly driven by: - timing variance of readiness budget for our 2023 UG portfolio of projects. The forecast for scoping, estimating/design, permitting, and pre-construction of 2023 projects (costs which would be incurred in 2022) did not materialize as initially forecasted.
7.3.3.17.1 | 7.3.3.17.1 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution | 977250 | 703061.4165 | -274188.5835 | meet | Variance mainly driven by: - Covered conductor installation - favorable unit cost performance from reduction of pre-construction vegetation clearing and implementation of unit price RFP contract strategy - Undergrounding program - timing variance of readiness budget for our 2023 UG portfolio of projects. The forecast for scoping, estimating/design, permitting, and pre-construction of 2023 projects (costs which would be incurred in 2022) did not materialize as initially forecasted.
7.3.3.17.2 | 7.3.3.17.2 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Transmission | 19050.876 | 7855.7489 | -11195.127 | meet | Variance mainly driven by: - Actuals lower due to updated planned transmission system hardening projects to be completed in 2022; in addition forecast was reduced to exclude idle line removal costs which are disallowed for recovery.
7.3.3.17.3 | 7.3.3.17.3 Updates to grid topology to minimize risk of ignition in HFTDs, Surge Arrestor | 33172.1158 | 37367.9307 | 4195.815 | not meet | N/A - does not meet threshold
7.3.3.17.4 | No 2022 financial data - 7.3.3.17.4 Updates to grid topology to minimize risk of ignition in HFTDs, Rapid Earth Current Fault Limiter | 0 | 75.1732 | 75.1732 | not meet | N/A - does not meet threshold
7.3.3.17.5 | 7.3.3.17.5 Updates to grid topology to minimize risk of ignition in HFTDs, Remote Grid | 17000 | 2734.0194 | -14265.9806 | meet | Variance mainly driven by: - lower than forecasted number of remote grid capital projects completed
7.3.3.17.6 | 7.3.3.17.6 Updates to grid topology to minimize risk of ignition in HFTDs, Butte County Rebuild | 138750 | 151306.5983 | 12556.5983 | not meet | N/A - does not meet threshold
7.3.4.1 | 7.3.4.1 Detailed inspections of distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.2 | 7.3.4.2 Detailed inspections of transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.3 | 7.3.4.3 Improvement of inspections | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.4 | 7.3.4.4 Infrared inspections of distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.5 | 7.3.4.5 Infrared inspections of transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.6.1 | 7.3.4.6.1 Intrusive pole inspections, Distribution | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.6.2 | 7.3.4.6.2 Intrusive pole inspections, Transmission | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.7 | 7.3.4.7 LiDAR Inspections of Distribution Electric Lines and Equipment | 0 | 1138.5355 | 1138.5355 | not meet | N/A - does not meet threshold
7.3.4.8 | 7.3.4.8 LiDAR Inspections of Transmission Electric Lines and Equipment | 11003 | 4719.9569 | -6283.0431 | not meet | N/A - does not meet threshold
7.3.4.9 | 7.3.4.9 Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.10 | 7.3.4.10 Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 3700 | 1123.3906 | -2576.6094 | not meet | N/A - does not meet threshold
7.3.4.11 | 7.3.4.11 Patrol inspections of distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.12 | 7.3.4.12 Patrol inspections of transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.13 | 7.3.4.13 Pole loading assessment program to determine safety factor | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.14 | 7.3.4.14 Quality assurance / quality control of inspections | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.15-T | 7.3.4.15-T Substation inspections, Enhanced Transmission, Substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.15-D | 7.3.4.15-D Substation inspections, Enhanced Distribution, Substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.4.16 | 7.3.4.16, Other, Substation inspections, Generation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.1 | 7.3.5.1 Additional efforts to manage community and environmental impacts | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.2 | 7.3.5.2 Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.3 | 7.3.5.3 Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment | 78701 | 35363.687 | -43337.313 | meet | Variance mainly driven by: - Due to budget/financial constraints, some Right-of-Way work was deferred to 2023
7.3.5.4 | 7.3.5.4 Emergency response vegetation management due to red flag warning or other urgent climate conditions | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.5 | 7.3.5.5 Fuel management (including all wood management) and reduction of “slash” from vegetation management activities | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.6 | 7.3.5.6 Improvement of inspections | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.7 | 7.3.5.7 Remote sensing inspections of vegetation around distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.7 | 7.3.5.7 Remote sensing inspections of vegetation around distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.8 | 7.3.5.8 Remote sensing inspections of vegetation around transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.9 | 7.3.5.9 Other discretionary inspections of vegetation around distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.10 | 7.3.5.10 Other discretionary inspections of vegetation around transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.11 | 7.3.5.11 Patrol inspections of vegetation around distribution electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.12 | 7.3.5.12 Patrol inspections of vegetation around transmission electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.13 | 7.3.5.13 Quality assurance / quality control of vegetation inspections | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.14 | 7.3.5.14 Recruiting and training of vegetation management personnel | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.15 | 7.3.5.15 Identification and remediation of "at-risk species" | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.16 | 7.3.5.16 Removal and remediation of trees with strike potential to electric lines and equipment | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.17.1 | 7.3.5.17.1 Substation inspection , Distribution substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.17.2 | 7.3.5.17.2 Substation inspection, Transmission substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.17.3 | 7.3.5.17.3 Substation inspection, Generation substation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.18.1 | 7.3.5.18.1 Substation vegetation management, Maintenance substation distribution | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.18.2 | 7.3.5.18.2 Substation vegetation management, Maintenance substation transmission | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.18.3 | 7.3.5.18.3 Substation vegetation management, Maintenance substation Generation | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.19 | 7.3.5.19 Vegetation management system | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.20 | 7.3.5.20 Additional vegetation management practices beyond regulatory requirements and recommendations | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.5.21 | 7.3.5.21 Vegetation management activities post-fire | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.1 | 7.3.6.1 Automatic recloser operations | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.2 | 7.3.6.2 Crew-accompanying ignition prevention and suppression resources and services | 690.0377 | 25.7092 | -664.3285 | not meet | N/A - does not meet threshold
7.3.6.3 | 7.3.6.3 Personnel work procedures and training in conditions of elevated fire risk | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.4-D | 7.3.6.4-D Protocols for PSPS re-energization, Distribution | 4940.315 | 1294.469 | -3645.846 | not meet | N/A - does not meet threshold
7.3.6.4-T | 7.3.6.4-T Protocols for PSPS re-energization, Transmission | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.5-D | 7.3.6.5-D PSPS events and mitigation of PSPS impacts , Distribution | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.5-T | 7.3.6.5-T PSPS events and mitigation of PSPS impacts , Transmission | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.6.6 | 7.3.6.6 Stationed and on-call ignition prevention and suppression resources and services | 230.0126 | 1.7139 | -228.2986 | not meet | N/A - does not meet threshold
7.3.6.7 | 7.3.6.7 Other, Aviation Support | 325 | -36.5398 | -361.5398 | not meet | N/A - does not meet threshold
7.3.6.8 | 7.3.6.8 Protective equipment and device settings | 0 | 17974.7961 | 17974.7961 | meet | Variance mainly driven by: - Substation capital work done/started (e.g., IPAC cabinet and relay replacements and Circuit Breaker replacements) to allow for enabled EPSS settings
7.3.7.1 | 7.3.7.1 Centralized repository for data | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.7.2 | 7.3.7.2 Collaborative research on utility ignition and/or wildfire | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.7.3 | 7.3.7.3 Documentation and disclosure of wildfire-related data and algorithms | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.7.4 | 7.3.7.4 Tracking and analysis of near miss data | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.7.5 | 7.3.7.5 Other, IT projects to support wildfire mitigation work | 49300.0264 | 52496.1189 | 3196.0925 | not meet | N/A - does not meet threshold
7.3.8.1 | 7.3.8.1 Allocation methodology development and application | 4382.394 | 4701.744 | 319.35 | not meet | N/A - does not meet threshold
7.3.8.2 | 7.3.8.2 Risk reduction scenario development and analysis | 909.8101 | 510.5451 | -399.265 | not meet | N/A - does not meet threshold
7.3.8.3 | 7.3.8.3 Risk spend efficiency analysis (RSE) | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.9.1 | 7.3.9.1 Adequate and trained workforce for service restoration | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.9.2 | 7.3.9.2 Community outreach, public awareness, and communications efforts | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.9.3 | 7.3.9.3 Customer support in emergencies | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.9.4 | 7.3.9.4 Disaster and emergency preparedness plan | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.9.5 | 7.3.9.5 Preparedness and planning for service restoration | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.9.6 | 7.3.9.6 Protocols in place to learn from wildfire events | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.10.1 | 7.3.10.1 Community engagement | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.10.2 | 7.3.10.2 Cooperation and best practice sharing with agencies outside CA | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.10.3 | 7.3.10.3 Cooperation with suppression agencies | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.10.4 | 7.3.10.4 Forest service and fuel reduction cooperation and joint roadmap | 0 | 0 | 0 | not meet | N/A - does not meet threshold
7.3.10.5 | 7.3.10.5 Other, PMO and General Wildfire Support | 0 | 0 | 0 | not meet | N/A - does not meet threshold
Adjustments to remove double count toward Total (e.g., 7.3.3.3 Covered OH Conductor, 7.3.3.16 Underground program, 7.3.3.17.5 Remote Grid), as those costs are already embedded in 7.3.3.17.1 System Hardening initiative |  | -994250 | -695039.456
| Total | 2891304.6719 | 2694538.8983 | -196765.7736