## Sheet1
Order | Order Description | Circuit ID | Circuit Name | Circuit Protection Zone | Program | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH 2021 Complete | UG 2021 Complete | Removal 2021 Complete | 2021 Miles Complete | OH 2022 Complete | UG 2022 Complete | Removal 2022 Complete | 2022 Miles Complete | OH 2023 Forecast | UG 2023 Forecast | Removal 2023 Forecast | 2023 Total Miles Forecast
35199234 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0 | 0 | 1.9848 | 1.9848 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9848 | 1.9848 | 0 | 0 | 0 | 0
35239464 |  | 82841101 | BIG BASIN 1101 | Big Basin 110110720 | Fire Rebuild | 0.070265 | 0 | 0 | 0.070265 | 0 | 0 | 0 | 0 | 0.070265 | 0 | 0 | 0.070265 | 0 | 0 | 0 | 0
35334406 |  | 82841102 | BIG BASIN 1102 | BIG BASIN 11022253 | Fire Rebuild | 0.041477 | 0.44318 | 0 | 0.48466 | 0 | 0 | 0 | 0 | 0.041477 | 0.44318 | 0 | 0.48466 | 0 | 0 | 0 | 0
35263364 |  | 82841102 | BIG BASIN 1102 | Big Basin 11025066 | Fire Rebuild | 0.38788 | 0 | 0 | 0.38788 | 0 | 0 | 0 | 0 | 0.38788 | 0 | 0 | 0.38788 | 0 | 0 | 0 | 0
35239462 |  | 82841102 | BIG BASIN 1102 | Big Basin 11025066 | Fire Rebuild | 0.28788 | 0 | 0 | 0.28788 | 0.22879 | 0 | 0 | 0.22879 | 0.059091 | 0 | 0 | 0.059091 | 0 | 0 | 0 | 0
35311924 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0
35225821 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 1.1314 | 0 | 1.1314 | 0 | 1.0252 | 0 | 1.0252 | 0 | 0.10625 | 0 | 0.10625 | 0 | 0 | 0 | 0
35242422 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.85398 | 0 | 0.85398 | 0 | 0 | 0 | 0 | 0 | 0.85398 | 0 | 0.85398 | 0 | 0 | 0 | 0
35242423 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.88958 | 0 | 0.88958 | 0 | 0 | 0 | 0 | 0 | 0.88958 | 0 | 0.88958 | 0 | 0 | 0 | 0
35242424 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.69943 | 0 | 0.69943 | 0 | 0 | 0 | 0 | 0 | 0.69943 | 0 | 0.69943 | 0 | 0 | 0 | 0
35242425 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.66155 | 0 | 0.66155 | 0 | 0 | 0 | 0 | 0 | 0.66155 | 0 | 0.66155 | 0 | 0 | 0 | 0
35242426 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.58864 | 0 | 0.58864 | 0 | 0 | 0 | 0 | 0 | 0.58864 | 0 | 0.58864 | 0 | 0 | 0 | 0
35242427 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.82822 | 0 | 0.82822 | 0 | 0 | 0 | 0 | 0 | 0.82822 | 0 | 0.82822 | 0 | 0 | 0 | 0
35242428 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.73598 | 0 | 0.73598 | 0 | 0 | 0 | 0 | 0 | 0.73598 | 0 | 0.73598 | 0 | 0 | 0 | 0
35242429 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.59792 | 0 | 0.59792 | 0 | 0 | 0 | 0 | 0 | 0.59792 | 0 | 0.59792 | 0 | 0 | 0 | 0
35236983 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.31989 | 0 | 0.31989 | 0 | 0 | 0 | 0 | 0 | 0.31989 | 0 | 0.31989 | 0 | 0 | 0 | 0
35235139 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 1.5297 | 0 | 1.5297 | 0 | 1.2008 | 0 | 1.2008 | 0 | 0.32898 | 0 | 0.32898 | 0 | 0 | 0 | 0
35235676 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 2.6394 | 0 | 2.6394 | 0 | 0.11231 | 0 | 0.11231 | 0 | 2.5271 | 0 | 2.5271 | 0 | 0 | 0 | 0
35235679 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.72784 | 0 | 0.72784 | 0 | 0 | 0 | 0 | 0 | 0.72784 | 0 | 0.72784 | 0 | 0 | 0 | 0
35233166 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | Fire Rebuild | 0 | 0.88542 | 0 | 0.88542 | 0 | 0 | 0 | 0 | 0 | 0.88542 | 0 | 0.88542 | 0 | 0 | 0 | 0
35290946 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | Fire Rebuild | 0 | 0.19924 | 0 | 0.19924 | 0 | 0 | 0 | 0 | 0 | 0.19924 | 0 | 0.19924 | 0 | 0 | 0 | 0
35290948 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | Fire Rebuild | 0 | 0.10966 | 0 | 0.10966 | 0 | 0 | 0 | 0 | 0 | 0.10966 | 0 | 0.10966 | 0 | 0 | 0 | 0
35292782 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | Fire Rebuild | 0.077462 | 0.11288 | 0 | 0.19034 | 0 | 0 | 0 | 0 | 0.077462 | 0.11288 | 0 | 0.19034 | 0 | 0 | 0 | 0
35280495 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | Fire Rebuild | 0.52121 | 0 | 0 | 0.52121 | 0 | 0 | 0 | 0 | 0.52121 | 0 | 0 | 0.52121 | 0 | 0 | 0 | 0
35279512 |  | 152461106 | BRUNSWICK 1106 | BRUNSWICK 11062790 | Fire Rebuild | 0 | 0.17708 | 0 | 0.17708 | 0 | 0 | 0 | 0 | 0 | 0.17708 | 0 | 0.17708 | 0 | 0 | 0 | 0
35279604 |  | 152461106 | BRUNSWICK 1106 | BRUNSWICK 11062790 | Fire Rebuild | 1.5455 | 0 | 0 | 1.5455 | 1.3104 | 0 | 0 | 1.3104 | 0.23504 | 0 | 0 | 0.23504 | 0 | 0 | 0 | 0
35286724 |  | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012056 | Fire Rebuild | 1.0837 | 0 | 0 | 1.0837 | 1.0485 | 0 | 0 | 1.0485 | 0.035227 | 0 | 0 | 0.035227 | 0 | 0 | 0 | 0
35285589 |  | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101344250 | Fire Rebuild | 0 | 0.26326 | 0 | 0.26326 | 0 | 0 | 0 | 0 | 0 | 0.26326 | 0 | 0.26326 | 0 | 0 | 0 | 0
35295010 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.3608 | 0 | 0.3608 | 0 | 0 | 0 | 0 | 0 | 0.3608 | 0 | 0.3608 | 0 | 0 | 0 | 0
35295011 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.12765 | 0 | 0.12765 | 0 | 0 | 0 | 0 | 0 | 0.12765 | 0 | 0.12765 | 0 | 0 | 0 | 0
35295012 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.89792 | 0 | 0.89792 | 0 | 0 | 0 | 0 | 0 | 0.89792 | 0 | 0.89792 | 0 | 0 | 0 | 0
35295013 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.25814 | 0 | 0.25814 | 0 | 0 | 0 | 0 | 0 | 0.25814 | 0 | 0.25814 | 0 | 0 | 0 | 0
35295014 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.15758 | 0 | 0.15758 | 0 | 0 | 0 | 0 | 0 | 0.15758 | 0 | 0.15758 | 0 | 0 | 0 | 0
35295015 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.26155 | 0 | 0.26155 | 0 | 0 | 0 | 0 | 0 | 0.26155 | 0 | 0.26155 | 0 | 0 | 0 | 0
35295016 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.22481 | 0 | 0.22481 | 0 | 0 | 0 | 0 | 0 | 0.22481 | 0 | 0.22481 | 0 | 0 | 0 | 0
35295017 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0.086364 | 0.33352 | 0 | 0.41989 | 0 | 0 | 0 | 0 | 0.086364 | 0.33352 | 0 | 0.41989 | 0 | 0 | 0 | 0
35295018 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.37121 | 0 | 0.37121 | 0 | 0 | 0 | 0 | 0 | 0.37121 | 0 | 0.37121 | 0 | 0 | 0 | 0
35295019 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 1.0549 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 1.0549 | 0 | 0 | 0 | 0
35295184 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.54205 | 0 | 0.54205 | 0 | 0 | 0 | 0 | 0 | 0.54205 | 0 | 0.54205 | 0 | 0 | 0 | 0
35295185 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.050379 | 0 | 0.050379 | 0 | 0 | 0 | 0 | 0 | 0.050379 | 0 | 0.050379 | 0 | 0 | 0 | 0
35295186 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 1.0076 | 0 | 1.0076 | 0 | 0 | 0 | 0 | 0 | 1.0076 | 0 | 1.0076 | 0 | 0 | 0 | 0
35295187 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.50644 | 0 | 0.50644 | 0 | 0 | 0 | 0 | 0 | 0.50644 | 0 | 0.50644 | 0 | 0 | 0 | 0
35295188 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.4733 | 0 | 0.4733 | 0 | 0 | 0 | 0 | 0 | 0.4733 | 0 | 0.4733 | 0 | 0 | 0 | 0
35295189 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.17936 | 0 | 0.17936 | 0 | 0 | 0 | 0 | 0 | 0.17936 | 0 | 0.17936 | 0 | 0 | 0 | 0
35295190 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.083333 | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0 | 0.083333 | 0 | 0 | 0 | 0
35295191 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.22595 | 0 | 0.22595 | 0 | 0 | 0 | 0 | 0 | 0.22595 | 0 | 0.22595 | 0 | 0 | 0 | 0
35295192 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.05303 | 0 | 0.05303 | 0 | 0 | 0 | 0 | 0 | 0.05303 | 0 | 0.05303 | 0 | 0 | 0 | 0
35295193 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.18542 | 0 | 0.18542 | 0 | 0 | 0 | 0 | 0 | 0.18542 | 0 | 0.18542 | 0 | 0 | 0 | 0
35295194 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.17102 | 0 | 0.17102 | 0 | 0 | 0 | 0 | 0 | 0.17102 | 0 | 0.17102 | 0 | 0 | 0 | 0
35295195 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.78447 | 0 | 0.78447 | 0 | 0 | 0 | 0 | 0 | 0.78447 | 0 | 0.78447 | 0 | 0 | 0 | 0
35292145 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 2.1555 | 0 | 0 | 2.1555 | 1.625 | 0 | 0 | 1.625 | 0.53049 | 0 | 0 | 0.53049 | 0 | 0 | 0 | 0
35295182 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | Fire Rebuild | 0 | 0.2589 | 0 | 0.2589 | 0 | 0 | 0 | 0 | 0 | 0.2589 | 0 | 0.2589 | 0 | 0 | 0 | 0
35385897 |  | 152181101 | FORESTHILL 1101 | FORESTHILL 110137238 | Fire Rebuild | 0 | 0 | 0.30303 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30303 | 0.30303 | 0 | 0 | 0 | 0
35385898 |  | 152181101 | FORESTHILL 1101 | FORESTHILL 110137238 | Fire Rebuild | 0 | 0 | 0.13958 | 0.13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13958 | 0.13958 | 0 | 0 | 0 | 0
35385899 |  | 152181101 | FORESTHILL 1101 | FORESTHILL 110137238 | Fire Rebuild | 0 | 0 | 0.10076 | 0.10076 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10076 | 0.10076 | 0 | 0 | 0 | 0
31547582 |  | 103021101 | GANSNER 1101 | GANSNER 11012424 | Fire Rebuild | 0.97765 | 0 | 0 | 0.97765 | 0 | 0 | 0 | 0 | 0.97765 | 0 | 0 | 0.97765 | 0 | 0 | 0 | 0
35279313 |  | 103021101 | GANSNER 1101 | GANSNER 11012424 | Fire Rebuild | 0.10227 | 0.46345 | 0 | 0.56572 | 0 | 0 | 0 | 0 | 0.10227 | 0.46345 | 0 | 0.56572 | 0 | 0 | 0 | 0
35220936 |  | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | Fire Rebuild | 0 | 0.86269 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0.86269 | 0 | 0 | 0 | 0
35217274 |  | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | Fire Rebuild | 0 | 2.5239 | 0 | 2.5239 | 0 | 0 | 0 | 0 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0.88277 | 0 | 0.88277
35282131 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0 | 0.038447 | 0 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0.038447 | 0 | 0.038447 | 0 | 0 | 0 | 0
35250343 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0 | 0.29432 | 0 | 0.29432 | 0 | 0 | 0 | 0 | 0 | 0.29432 | 0 | 0.29432 | 0 | 0 | 0 | 0
35254695 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0 | 0.055303 | 0 | 0.055303 | 0 | 0 | 0 | 0 | 0 | 0.055303 | 0 | 0.055303 | 0 | 0 | 0 | 0
35236992 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0 | 0.70587 | 0 | 0.70587 | 0 | 0 | 0 | 0 | 0 | 0.70587 | 0 | 0.70587 | 0 | 0 | 0 | 0
35235702 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0 | 1.8371 | 0 | 1.8371 | 0 | 0 | 0 | 0 | 0 | 1.8371 | 0 | 1.8371 | 0 | 0 | 0 | 0
35245140 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0.27746 | 0 | 0 | 0.27746 | 0 | 0 | 0 | 0 | 0.27746 | 0 | 0 | 0.27746 | 0 | 0 | 0 | 0
35245146 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0.13731 | 0 | 0 | 0.13731 | 0 | 0 | 0 | 0 | 0.13731 | 0 | 0 | 0.13731 | 0 | 0 | 0 | 0
35245148 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0.20492 | 0 | 0 | 0.20492 | 0 | 0 | 0 | 0 | 0.20492 | 0 | 0 | 0.20492 | 0 | 0 | 0 | 0
35245149 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0.26837 | 0 | 0 | 0.26837 | 0 | 0 | 0 | 0 | 0.26837 | 0 | 0 | 0.26837 | 0 | 0 | 0 | 0
35245150 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0.15966 | 0 | 0 | 0.15966 | 0 | 0 | 0 | 0 | 0.15966 | 0 | 0 | 0.15966 | 0 | 0 | 0 | 0
35294385 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | Fire Rebuild | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | 0 | 0 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | 0 | 0
35238840 |  | 82931101 | POINT MORETTI 1101 | Point Moretti 110135874 | Fire Rebuild | 0.14962 | 0.46117 | 0 | 0.6108 | 0 | 0 | 0 | 0 | 0.14962 | 0.46117 | 0 | 0.6108 | 0 | 0 | 0 | 0
35245029 |  | 82931101 | POINT MORETTI 1101 | Point Moretti 110136516 | Fire Rebuild | 0.35682 | 0 | 0 | 0.35682 | 0 | 0 | 0 | 0 | 0.35682 | 0 | 0 | 0.35682 | 0 | 0 | 0 | 0
35385407 |  | 252521103 | SAN JOAQUIN #2 1103 | SAN JOAQUIN #2 1103CB | Fire Rebuild | 0.69432 | 0 | 0 | 0.69432 | 0 | 0 | 0 | 0 | 0.69432 | 0 | 0 | 0.69432 | 0 | 0 | 0 | 0
35284568 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110132726 | Fire Rebuild | 0 | 0.92045 | 0 | 0.92045 | 0 | 0 | 0 | 0 | 0 | 0.92045 | 0 | 0.92045 | 0 | 0 | 0 | 0
35284567 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 11012768 | Fire Rebuild | 0 | 0.60701 | 0 | 0.60701 | 0 | 0 | 0 | 0 | 0 | 0.60701 | 0 | 0.60701 | 0 | 0 | 0 | 0
35295009 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 11012768 | Fire Rebuild | 0 | 1.0794 | 0 | 1.0794 | 0 | 0 | 0 | 0 | 0 | 1.0794 | 0 | 1.0794 | 0 | 0 | 0 | 0
35284569 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110248894 | Fire Rebuild | 0 | 0.62311 | 0 | 0.62311 | 0 | 0 | 0 | 0 | 0 | 0.62311 | 0 | 0.62311 | 0 | 0 | 0 | 0
35281759 |  | 103104401 | SPANISH CREEK 4401 | SPANISH CREEK 4401CB | Fire Rebuild | 0 | 0 | 2.7297 | 2.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7297 | 2.7297 | 0 | 0 | 0 | 0
35291986 |  | 103561101 | STILLWATER 1101 | STILLWATER 110148950 | Fire Rebuild | 1.8223 | 0 | 0 | 1.8223 | 1.6958 | 0 | 0 | 1.6958 | 0.12652 | 0 | 0 | 0.12652 | 0 | 0 | 0 | 0
35295745 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | Fire Rebuild | 0 | 0.40038 | 0 | 0.40038 | 0 | 0 | 0 | 0 | 0 | 0.40038 | 0 | 0.40038 | 0 | 0 | 0 | 0
35236984 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | Fire Rebuild | 0 | 1.5852 | 0 | 1.5852 | 0 | 0 | 0 | 0 | 0 | 1.5852 | 0 | 1.5852 | 0 | 0 | 0 | 0
35341054 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031941 | Fire Rebuild | 0 | 0.18333 | 0 | 0.18333 | 0 | 0 | 0 | 0 | 0 | 0.18333 | 0 | 0.18333 | 0 | 0 | 0 | 0
35331458 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031941 | Fire Rebuild | 0 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0 | 0 | 0 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0 | 0
35335712 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.0087121 | 0 | 0.0087121 | 0 | 0 | 0 | 0 | 0 | 0.0087121 | 0 | 0.0087121 | 0 | 0 | 0 | 0
35320807 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.09375 | 0 | 0.09375 | 0 | 0 | 0 | 0 | 0 | 0.09375 | 0 | 0.09375 | 0 | 0 | 0 | 0
35302356 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.24962 | 0 | 0.24962 | 0 | 0 | 0 | 0 | 0 | 0.24962 | 0 | 0.24962 | 0 | 0 | 0 | 0
35233039 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.42216 | 0 | 0.42216 | 0 | 0 | 0 | 0 | 0 | 0.42216 | 0 | 0.42216 | 0 | 0 | 0 | 0
35235706 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.7108 | 0 | 0.7108 | 0 | 0 | 0 | 0 | 0 | 0.7108 | 0 | 0.7108 | 0 | 0 | 0 | 0
35235707 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.94451 | 0 | 0.94451 | 0 | 0 | 0 | 0 | 0 | 0.94451 | 0 | 0.94451 | 0 | 0 | 0 | 0
35233300 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.36117 | 0 | 0.36117 | 0 | 0 | 0 | 0 | 0 | 0.36117 | 0 | 0.36117 | 0 | 0 | 0 | 0
35233302 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.14205 | 0 | 0.14205 | 0 | 0 | 0 | 0 | 0 | 0.14205 | 0 | 0.14205 | 0 | 0 | 0 | 0
35233310 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.28617 | 0 | 0.28617 | 0 | 0 | 0 | 0 | 0 | 0.28617 | 0 | 0.28617 | 0 | 0 | 0 | 0
35233312 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.78371 | 0 | 0.78371 | 0 | 0 | 0 | 0 | 0 | 0.78371 | 0 | 0.78371 | 0 | 0 | 0 | 0
35233314 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 2.3701 | 0 | 2.3701 | 0 | 1.9703 | 0 | 1.9703 | 0 | 0.39981 | 0 | 0.39981 | 0 | 0 | 0 | 0
35233315 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.70758 | 0 | 0.70758 | 0 | 0 | 0 | 0 | 0 | 0.70758 | 0 | 0.70758 | 0 | 0 | 0 | 0
35239522 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.24564 | 0 | 0.24564 | 0 | 0 | 0 | 0 | 0 | 0.24564 | 0 | 0.24564 | 0 | 0 | 0 | 0
35240546 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0
35283874 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Fire Rebuild | 0 | 0.40284 | 0.15057 | 0.55341 | 0 | 0 | 0 | 0 | 0 | 0.40284 | 0.15057 | 0.55341 | 0 | 0 | 0 | 0
35239095 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.5373 | 0 | 1.5373 | 0 | 0 | 0 | 0 | 0 | 1.5373 | 0 | 1.5373 | 0 | 0 | 0 | 0
35239096 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.78504 | 0 | 0.78504 | 0 | 0 | 0 | 0 | 0 | 0.78504 | 0 | 0.78504 | 0 | 0 | 0 | 0
35239097 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.2205 | 0 | 1.2205 | 0 | 0 | 0 | 0 | 0 | 1.2205 | 0 | 1.2205 | 0 | 0 | 0 | 0
35239098 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 2.1644 | 0 | 2.1644 | 0 | 0 | 0 | 0 | 0 | 2.1644 | 0 | 2.1644 | 0 | 0 | 0 | 0
35239099 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.41042 | 0 | 0.41042 | 0 | 0 | 0 | 0 | 0 | 0.41042 | 0 | 0.41042 | 0 | 0 | 0 | 0
35235700 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.96761 | 0 | 0.96761 | 0 | 0 | 0 | 0 | 0 | 0.96761 | 0 | 0.96761 | 0 | 0 | 0 | 0
35235320 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.2267 | 0 | 0.2267 | 0 | 0 | 0 | 0 | 0 | 0.2267 | 0 | 0.2267 | 0 | 0 | 0 | 0
35235670 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0.1178 | 0 | 0 | 0.1178 | 0 | 0 | 0 | 0 | 0.1178 | 0 | 0 | 0.1178 | 0 | 0 | 0 | 0
35236990 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.85303 | 0 | 0.85303 | 0 | 0 | 0 | 0 | 0 | 0.85303 | 0 | 0.85303 | 0 | 0 | 0 | 0
35236991 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.0731 | 0 | 1.0731 | 0 | 0 | 0 | 0 | 0 | 1.0731 | 0 | 1.0731 | 0 | 0 | 0 | 0
35237021 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.17386 | 0 | 0.17386 | 0 | 0 | 0 | 0 | 0 | 0.17386 | 0 | 0.17386 | 0 | 0 | 0 | 0
35236993 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.36837 | 0 | 0.36837 | 0 | 0 | 0 | 0 | 0 | 0.36837 | 0 | 0.36837 | 0 | 0 | 0 | 0
35236995 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 2.2905 | 0 | 2.2905 | 0 | 0 | 0 | 0 | 0 | 2.2905 | 0 | 2.2905 | 0 | 0 | 0 | 0
35237896 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.3059 | 0 | 1.3059 | 0 | 0 | 0 | 0 | 0 | 1.3059 | 0 | 1.3059 | 0 | 0 | 0 | 0
35237889 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.8193 | 0 | 1.8193 | 0 | 0 | 0 | 0 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0 | 0 | 0
35237890 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.2174 | 0 | 1.2174 | 0 | 0 | 0 | 0 | 0 | 1.2174 | 0 | 1.2174 | 0 | 0 | 0 | 0
35237891 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.43352 | 0 | 0.43352 | 0 | 0 | 0 | 0 | 0 | 0.43352 | 0 | 0.43352 | 0 | 0 | 0 | 0
35237893 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 0.74811 | 0 | 0.74811 | 0 | 0 | 0 | 0 | 0 | 0.74811 | 0 | 0.74811 | 0 | 0 | 0 | 0
35237894 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | Fire Rebuild | 0 | 1.1083 | 0 | 1.1083 | 0 | 0 | 0 | 0 | 0 | 1.1083 | 0 | 1.1083 | 0 | 0 | 0 | 0
35078735 |  | 102911107 | WYANDOTTE 1107 | WYANDOTTE 11071510 | Idle Facilities | 0 | 0 | 0.045833 | 0.045833 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045833 | 0.045833 | 0 | 0 | 0 | 0
35132570 |  | 42661104 | WILLITS 1104 | WILLITS 11044650 | Idle Facilities | 0 | 0 | 0.038068 | 0.038068 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038068 | 0.038068 | 0 | 0 | 0 | 0
35211657 |  | 152491101 | WEIMAR 1101 | WEIMAR 11012058 | Idle Facilities | 0 | 0 | 0.098106 | 0.098106 | 0 | 0 | 0 | 0 | 0 | 0 | 0.098106 | 0.098106 | 0 | 0 | 0 | 0
35205037 |  | 152491101 | WEIMAR 1101 | WEIMAR 11012058 | Idle Facilities | 0 | 0 | 0.028788 | 0.028788 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028788 | 0.028788 | 0 | 0 | 0 | 0
35221809 |  | 163201102 | WEST POINT 1102 | WEST POINT 11024788 | Idle Facilities | 0 | 0 | 0.029735 | 0.029735 | 0 | 0 | 0 | 0 | 0 | 0 | 0.029735 | 0.029735 | 0 | 0 | 0 | 0
35221807 |  | 163201102 | WEST POINT 1102 | WEST POINT 11024790 | Idle Facilities | 0 | 0 | 0.1214 | 0.1214 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1214 | 0.1214 | 0 | 0 | 0 | 0
35246806 |  | 163201102 | WEST POINT 1102 | WEST POINT 110293116 | Idle Facilities | 0 | 0 | 0.31534 | 0.31534 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31534 | 0.31534 | 0 | 0 | 0 | 0
35275960 |  | 103601101 | WHITMORE 1101 | WHITMORE 11011598 | Idle Facilities | 0 | 0 | 0.035606 | 0.035606 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035606 | 0.035606 | 0 | 0 | 0 | 0
35217667 |  | 103601101 | WHITMORE 1101 | WHITMORE 110145262 | Idle Facilities | 0 | 0 | 0.098864 | 0.098864 | 0 | 0 | 0 | 0 | 0 | 0 | 0.098864 | 0.098864 | 0 | 0 | 0 | 0
35294732 |  | 103601101 | WHITMORE 1101 | WHITMORE 110145262 | Idle Facilities | 0 | 0 | 0.039205 | 0.039205 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039205 | 0.039205 | 0 | 0 | 0 | 0
35204830 |  | 103561102 | STILLWATER 1102 | STILLWATER 11021466 | Idle Facilities | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0
35211694 |  | 103561102 | STILLWATER 1102 | STILLWATER 11021466 | Idle Facilities | 0 | 0 | 0.047348 | 0.047348 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047348 | 0.047348 | 0 | 0 | 0 | 0
35211743 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 2109CB | Idle Facilities | 0 | 0 | 0.031818 | 0.031818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031818 | 0.031818 | 0 | 0 | 0 | 0
35211237 |  | 43432102 | SILVERADO 2102 | SILVERADO 210234959 | Idle Facilities | 0 | 0 | 0.022159 | 0.022159 | 0 | 0 | 0 | 0 | 0 | 0 | 0.022159 | 0.022159 | 0 | 0 | 0 | 0
35207810 |  | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112014 | Idle Facilities | 0 | 0 | 0.072538 | 0.072538 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072538 | 0.072538 | 0 | 0 | 0 | 0
35083773 |  | 163240401 | TAR FLAT 0401 | TAR FLAT 0401CB | Idle Facilities | 0 | 0 | 0.09678 | 0.09678 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09678 | 0.09678 | 0 | 0 | 0 | 0
35083733 |  | 252931102 | TEJON 1102 | TEJON 1102732836 | Idle Facilities | 0 | 0 | 0.10644 | 0.10644 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10644 | 0.10644 | 0 | 0 | 0 | 0
35204877 |  | 42771113 | UKIAH 1113 | UKIAH 1113548420 | Idle Facilities | 0 | 0 | 0.092803 | 0.092803 | 0 | 0 | 0 | 0 | 0 | 0 | 0.092803 | 0.092803 | 0 | 0 | 0 | 0
35038557 |  | 42771115 | UKIAH 1115 | UKIAH 11151216 | Idle Facilities | 0 | 0 | 0.081439 | 0.081439 | 0 | 0 | 0 | 0 | 0 | 0 | 0.081439 | 0.081439 | 0 | 0 | 0 | 0
35205038 |  | 152431102 | SHADY GLEN 1102 | SHADY GLEN 1102CB | Idle Facilities | 0 | 0 | 0.052083 | 0.052083 | 0 | 0 | 0 | 0 | 0 | 0 | 0.052083 | 0.052083 | 0 | 0 | 0 | 0
35217683 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110132726 | Idle Facilities | 0 | 0 | 0.022917 | 0.022917 | 0 | 0 | 0 | 0 | 0 | 0 | 0.022917 | 0.022917 | 0 | 0 | 0 | 0
35273069 |  | 152431102 | SHADY GLEN 1102 | SHADY GLEN 11022232 | Idle Facilities | 0 | 0 | 0.20379 | 0.20379 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20379 | 0.20379 | 0 | 0 | 0 | 0
35208079 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210911092 | Idle Facilities | 0 | 0 | 0.13977 | 0.13977 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13977 | 0.13977 | 0 | 0 | 0 | 0
35224939 |  | 182631103 | SAN LUIS OBISPO 1103 | SAN LUIS OBISPO 1103V82 | Idle Facilities | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0
35225436 |  | 182661106 | SAN MIGUEL 1106 | SAN MIGUEL 1106428314 | Idle Facilities | 0 | 0 | 0.040909 | 0.040909 | 0 | 0 | 0 | 0 | 0 | 0 | 0.040909 | 0.040909 | 0 | 0 | 0 | 0
35221770 |  | 83371107 | SARATOGA 1107 | SARATOGA 1107LC12 | Idle Facilities | 0 | 0 | 0.043561 | 0.043561 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043561 | 0.043561 | 0 | 0 | 0 | 0
35225464 |  | 83692104 | ROY ROY 2104 | ROY ROY 210412596 | Idle Facilities | 0 | 0 | 0.21117 | 0.21117 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21117 | 0.21117 | 0 | 0 | 0 | 0
35211243 |  | 43291105 | PUEBLO 1105 | PUEBLO 1105637242 | Idle Facilities | 0 | 0 | 0.27386 | 0.27386 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27386 | 0.27386 | 0 | 0 | 0 | 0
35205119 |  | 103541104 | RED BLUFF 1104 | Red Bluff 11041630 | Idle Facilities | 0 | 0 | 0.18428 | 0.18428 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18428 | 0.18428 | 0 | 0 | 0 | 0
35244163 |  | 43191101 | Redbud 1101 | Redbud 1101323962 | Idle Facilities | 0 | 0 | 0.025758 | 0.025758 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025758 | 0.025758 | 0 | 0 | 0 | 0
35224421 |  | 253642103 | Poso Mountain 2103 | Poso Mountain 2103CB | Idle Facilities | 0 | 0 | 0.17254 | 0.17254 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17254 | 0.17254 | 0 | 0 | 0 | 0
35264102 |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | Idle Facilities | 0 | 0 | 0.10606 | 0.10606 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10606 | 0.10606 | 0 | 0 | 0 | 0
35114039 |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | Idle Facilities | 0 | 0 | 0.15549 | 0.15549 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15549 | 0.15549 | 0 | 0 | 0 | 0
35149631 |  | 43292103 | PUEBLO 2103 | Pueblo 2103678 | Idle Facilities | 0 | 0 | 0.23693 | 0.23693 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23693 | 0.23693 | 0 | 0 | 0 | 0
35204902 |  | 103461101 | PANORAMA 1101 | PANORAMA 1101CB | Idle Facilities | 0 | 0 | 0.017614 | 0.017614 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017614 | 0.017614 | 0 | 0 | 0 | 0
35176816 |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | Idle Facilities | 0 | 0 | 0.14299 | 0.14299 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14299 | 0.14299 | 0 | 0 | 0 | 0
35225254 |  | 83252105 | PAUL SWEET 2105 | PAUL SWEET 2105CB | Idle Facilities | 0 | 0 | 0.05303 | 0.05303 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05303 | 0.05303 | 0 | 0 | 0 | 0
35298200 |  | 153081109 | PLACERVILLE 1109 | PLACERVILLE 1109CB | Idle Facilities | 0 | 0 | 0.096591 | 0.096591 | 0 | 0 | 0 | 0 | 0 | 0 | 0.096591 | 0.096591 | 0 | 0 | 0 | 0
35225441 |  | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N48 | Idle Facilities | 0 | 0 | 0.49091 | 0.49091 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49091 | 0.49091 | 0 | 0 | 0 | 0
35204811 |  | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 11021584 | Idle Facilities | 0 | 0 | 0.082197 | 0.082197 | 0 | 0 | 0 | 0 | 0 | 0 | 0.082197 | 0.082197 | 0 | 0 | 0 | 0
35211263 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | Idle Facilities | 0 | 0 | 0.032765 | 0.032765 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032765 | 0.032765 | 0 | 0 | 0 | 0
35009378 |  | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | Idle Facilities | 0 | 0 | 0.60379 | 0.60379 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60379 | 0.60379 | 0 | 0 | 0 | 0
35211225 |  | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 110249144 | Idle Facilities | 0 | 0 | 0.048864 | 0.048864 | 0 | 0 | 0 | 0 | 0 | 0 | 0.048864 | 0.048864 | 0 | 0 | 0 | 0
35262346 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 11031500 | Idle Facilities | 0 | 0 | 0.13996 | 0.13996 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13996 | 0.13996 | 0 | 0 | 0 | 0
35262343 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | Idle Facilities | 0 | 0 | 0.063258 | 0.063258 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063258 | 0.063258 | 0 | 0 | 0 | 0
35262344 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | Idle Facilities | 0 | 0 | 0.043561 | 0.043561 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043561 | 0.043561 | 0 | 0 | 0 | 0
35243374 |  | 43051101 | MONTICELLO 1101 | MONTICELLO 11014360 | Idle Facilities | 0 | 0 | 0.61837 | 0.61837 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61837 | 0.61837 | 0 | 0 | 0 | 0
35244179 |  | 153132102 | NARROWS 2102 | Narrows 210248484 | Idle Facilities | 0 | 0 | 0.059659 | 0.059659 | 0 | 0 | 0 | 0 | 0 | 0 | 0.059659 | 0.059659 | 0 | 0 | 0 | 0
35211618 |  | 153132105 | NARROWS 2105 | NARROWS 210551582 | Idle Facilities | 0 | 0 | 0.060417 | 0.060417 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060417 | 0.060417 | 0 | 0 | 0 | 0
35294736 |  | 103521104 | OREGON TRAIL 1104 | OREGON TRAIL 11041574 | Idle Facilities | 0 | 0 | 0.050568 | 0.050568 | 0 | 0 | 0 | 0 | 0 | 0 | 0.050568 | 0.050568 | 0 | 0 | 0 | 0
35204806 |  | 103521104 | OREGON TRAIL 1104 | OREGON TRAIL 1104CB | Idle Facilities | 0 | 0 | 0.048485 | 0.048485 | 0 | 0 | 0 | 0 | 0 | 0 | 0.048485 | 0.048485 | 0 | 0 | 0 | 0
35241886 |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011130 | Idle Facilities | 0 | 0 | 0.023106 | 0.023106 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023106 | 0.023106 | 0 | 0 | 0 | 0
35260214 |  | 254452101 | MARIPOSA 2101 | MARIPOSA 21014410 | Idle Facilities | 0 | 0 | 0.095644 | 0.095644 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095644 | 0.095644 | 0 | 0 | 0 | 0
35083888 |  | 163011102 | MARTELL 1102 | MARTELL 110292172 | Idle Facilities | 0 | 0 | 0.072348 | 0.072348 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072348 | 0.072348 | 0 | 0 | 0 | 0
35211249 |  | 103491101 | MC ARTHUR 1101 | MC ARTHUR 11011490 | Idle Facilities | 0 | 0 | 0.032197 | 0.032197 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032197 | 0.032197 | 0 | 0 | 0 | 0
35038562 |  | 42951101 | MENDOCINO 1101 | MENDOCINO 110148750 | Idle Facilities | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0 | 0 | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0 | 0
35155226 |  | 24131102 | MENLO 1102 | MENLO 1102W80 | Idle Facilities | 0 | 0 | 0.042045 | 0.042045 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042045 | 0.042045 | 0 | 0 | 0 | 0
35277148 |  | 254452101 | MARIPOSA 2101 | MARIPOSA 2101309438 | Idle Facilities | 0 | 0 | 0.12652 | 0.12652 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12652 | 0.12652 | 0 | 0 | 0 | 0
35211785 |  | 153701104 | LINCOLN 1104 | LINCOLN 11042070 | Idle Facilities | 0 | 0 | 0.048485 | 0.048485 | 0 | 0 | 0 | 0 | 0 | 0 | 0.048485 | 0.048485 | 0 | 0 | 0 | 0
35244172 |  | 153701104 | LINCOLN 1104 | LINCOLN 11042070 | Idle Facilities | 0 | 0 | 0.17424 | 0.17424 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17424 | 0.17424 | 0 | 0 | 0 | 0
35211630 |  | 103221101 | KANAKA 1101 | KANAKA 110165606 | Idle Facilities | 0 | 0 | 0.060038 | 0.060038 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0.060038 | 0 | 0 | 0 | 0
35275961 |  | 103441101 | JESSUP 1101 | JESSUP 110141356 | Idle Facilities | 0 | 0 | 0.13068 | 0.13068 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13068 | 0.13068 | 0 | 0 | 0 | 0
35294739 |  | 103441102 | JESSUP 1102 | Jessup 110276068 | Idle Facilities | 0 | 0 | 0.057008 | 0.057008 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 0.057008 | 0 | 0 | 0 | 0
35037896 |  | 43311102 | KONOCTI 1102 | KONOCTI 1102965078 | Idle Facilities | 0 | 0 | 0.42443 | 0.42443 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42443 | 0.42443 | 0 | 0 | 0 | 0
35255493 |  | 14402108 | LAS POSITAS 2108 | LAS POSITAS 2108MR182 | Idle Facilities | 0 | 0 | 0.13447 | 0.13447 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13447 | 0.13447 | 0 | 0 | 0 | 0
35132573 |  | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 1102CB | Idle Facilities | 0 | 0 | 0.068182 | 0.068182 | 0 | 0 | 0 | 0 | 0 | 0 | 0.068182 | 0.068182 | 0 | 0 | 0 | 0
35208072 |  | 153701101 | LINCOLN 1101 | LINCOLN 11012310 | Idle Facilities | 0 | 0 | 0.11193 | 0.11193 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11193 | 0.11193 | 0 | 0 | 0 | 0
35224947 |  | 182581105 | GOLDTREE 1105 | GOLDTREE 1105CB | Idle Facilities | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0
35255487 |  | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102274 | Idle Facilities | 0 | 0 | 0.21818 | 0.21818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21818 | 0.21818 | 0 | 0 | 0 | 0
35037563 |  | 192431108 | HARRIS 1108 | HARRIS 11082062 | Idle Facilities | 0 | 0 | 0.040152 | 0.040152 | 0 | 0 | 0 | 0 | 0 | 0 | 0.040152 | 0.040152 | 0 | 0 | 0 | 0
35205102 |  | 192431109 | HARRIS 1109 | HARRIS 1109355914 | Idle Facilities | 0 | 0 | 0.10985 | 0.10985 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10985 | 0.10985 | 0 | 0 | 0 | 0
35151026 |  | 43211101 | HARTLEY 1101 | HARTLEY 1101658 | Idle Facilities | 0 | 0 | 0.10152 | 0.10152 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10152 | 0.10152 | 0 | 0 | 0 | 0
35037377 |  | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103CB | Idle Facilities | 0 | 0 | 0.0375 | 0.0375 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0375 | 0.0375 | 0 | 0 | 0 | 0
35037707 |  | 192221101 | GARBERVILLE 1101 | GARBERVILLE 110139524 | Idle Facilities | 0 | 0 | 0.21837 | 0.21837 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21837 | 0.21837 | 0 | 0 | 0 | 0
35150103 |  | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11021510 | Idle Facilities | 0 | 0 | 0.038447 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038447 | 0.038447 | 0 | 0 | 0 | 0
35037706 |  | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11022500 | Idle Facilities | 0 | 0 | 0.024811 | 0.024811 | 0 | 0 | 0 | 0 | 0 | 0 | 0.024811 | 0.024811 | 0 | 0 | 0 | 0
35208076 |  | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11026084 | Idle Facilities | 0 | 0 | 0.092235 | 0.092235 | 0 | 0 | 0 | 0 | 0 | 0 | 0.092235 | 0.092235 | 0 | 0 | 0 | 0
35149328 |  | 192321121 | FORT SEWARD 1121 | FORT SEWARD 1121CB | Idle Facilities | 0 | 0 | 0.16193 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16193 | 0.16193 | 0 | 0 | 0 | 0
35221637 |  | 254061103 | DUNLAP 1103 | DUNLAP 11037220 | Idle Facilities | 0 | 0 | 0.13636 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0 | 0 | 0 | 0
35208069 |  | 152762102 | EL DORADO PH 2102 | EL DORADO PH 21026645 | Idle Facilities | 0 | 0 | 0.041667 | 0.041667 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667 | 0.041667 | 0 | 0 | 0 | 0
35238953 |  | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012562 | Idle Facilities | 0 | 0 | 4.2356 | 4.2356 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2356 | 4.2356 | 0 | 0 | 0 | 0
35274991 |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | Idle Facilities | 0 | 0 | 0.072538 | 0.072538 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072538 | 0.072538 | 0 | 0 | 0 | 0
35275963 |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011654 | Idle Facilities | 0 | 0 | 0.18523 | 0.18523 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18523 | 0.18523 | 0 | 0 | 0 | 0
35144989 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | Idle Facilities | 0 | 0 | 0.073485 | 0.073485 | 0 | 0 | 0 | 0 | 0 | 0 | 0.073485 | 0.073485 | 0 | 0 | 0 | 0
35211280 |  | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | Idle Facilities | 0 | 0 | 0.029167 | 0.029167 | 0 | 0 | 0 | 0 | 0 | 0 | 0.029167 | 0.029167 | 0 | 0 | 0 | 0
35244155 |  | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 110610587 | Idle Facilities | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0 | 0
35211241 |  | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 11062100 | Idle Facilities | 0 | 0 | 0.074811 | 0.074811 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074811 | 0.074811 | 0 | 0 | 0 | 0
35237026 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | Idle Facilities | 0 | 0 | 0.19223 | 0.19223 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19223 | 0.19223 | 0 | 0 | 0 | 0
35208066 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | Idle Facilities | 0 | 0 | 0.14205 | 0.14205 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14205 | 0.14205 | 0 | 0 | 0 | 0
35207842 |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | Idle Facilities | 0 | 0 | 0.056439 | 0.056439 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056439 | 0.056439 | 0 | 0 | 0 | 0
35244159 |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | Idle Facilities | 0 | 0 | 0.038826 | 0.038826 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038826 | 0.038826 | 0 | 0 | 0 | 0
35208012 |  | 153741101 | DOBBINS 1101 | DOBBINS 11011264 | Idle Facilities | 0 | 0 | 0.075379 | 0.075379 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075379 | 0.075379 | 0 | 0 | 0 | 0
35208031 |  | 153741101 | DOBBINS 1101 | DOBBINS 11011808 | Idle Facilities | 0 | 0 | 0.051136 | 0.051136 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051136 | 0.051136 | 0 | 0 | 0 | 0
35208047 |  | 153741101 | DOBBINS 1101 | DOBBINS 11011808 | Idle Facilities | 0 | 0 | 0.02178 | 0.02178 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02178 | 0.02178 | 0 | 0 | 0 | 0
35244117 |  | 152321101 | DRUM 1101 | DRUM 11011602 | Idle Facilities | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0
35208019 |  | 102931101 | COTTONWOOD 1101 | COTTONWOOD 11011610 | Idle Facilities | 0 | 0 | 0.037121 | 0.037121 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037121 | 0.037121 | 0 | 0 | 0 | 0
35204803 |  | 102931101 | COTTONWOOD 1101 | COTTONWOOD 11011610 | Idle Facilities | 0 | 0 | 0.10606 | 0.10606 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10606 | 0.10606 | 0 | 0 | 0 | 0
35205032 |  | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 210413352 | Idle Facilities | 0 | 0 | 0.050189 | 0.050189 | 0 | 0 | 0 | 0 | 0 | 0 | 0.050189 | 0.050189 | 0 | 0 | 0 | 0
35252853 |  | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | Idle Facilities | 0 | 0 | 0.12557 | 0.12557 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12557 | 0.12557 | 0 | 0 | 0 | 0
35037880 |  | 42141101 | CLEAR LAKE 1101 | CLEAR LAKE 11011302 | Idle Facilities | 0 | 0 | 0.70549 | 0.70549 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70549 | 0.70549 | 0 | 0 | 0 | 0
35092175 |  | 83622105 | Camp Evers 2105 | Camp Evers 2105 | Idle Facilities | 0 | 0 | 0.032197 | 0.032197 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032197 | 0.032197 | 0 | 0 | 0 | 0
35150875 |  | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510294 | Idle Facilities | 0 | 0 | 0.027841 | 0.027841 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027841 | 0.027841 | 0 | 0 | 0 | 0
35206236 |  | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510294 | Idle Facilities | 0 | 0 | 0.056061 | 0.056061 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056061 | 0.056061 | 0 | 0 | 0 | 0
35038547 |  | 43411101 | CALPELLA 1101 | CALPELLA 1101542 | Idle Facilities | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0
35211655 |  | 43411101 | CALPELLA 1101 | CALPELLA 1101619542 | Idle Facilities | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0 | 0
35207971 |  | 43411101 | CALPELLA 1101 | CALPELLA 1101619542 | Idle Facilities | 0 | 0 | 0.072917 | 0.072917 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072917 | 0.072917 | 0 | 0 | 0 | 0
35037588 |  | 192291121 | CARLOTTA 1121 | CARLOTTA 112142896 | Idle Facilities | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0 | 0
35122386 |  | 103201102 | CHALLENGE 1102 | CHALLENGE 11021064 | Idle Facilities | 0 | 0 | 0.025379 | 0.025379 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025379 | 0.025379 | 0 | 0 | 0 | 0
35126796 |  | 102211103 | BUCKS CREEK 1103 | BUCKS CREEK 1103CB | Idle Facilities | 0 | 0 | 0.089583 | 0.089583 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089583 | 0.089583 | 0 | 0 | 0 | 0
35264103 |  | 42711101 | CALISTOGA 1101 | CALISTOGA 110189150 | Idle Facilities | 0 | 0 | 0.23277 | 0.23277 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23277 | 0.23277 | 0 | 0 | 0 | 0
35122244 |  | 183101103 | CABRILLO 1103 | CABRILLO 1103Y46 | Idle Facilities | 0 | 0 | 0.014205 | 0.014205 | 0 | 0 | 0 | 0 | 0 | 0 | 0.014205 | 0.014205 | 0 | 0 | 0 | 0
35246811 |  | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110111188 | Idle Facilities | 0 | 0 | 0.011364 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011364 | 0.011364 | 0 | 0 | 0 | 0
35221824 |  | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 11012646 | Idle Facilities | 0 | 0 | 0.033712 | 0.033712 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033712 | 0.033712 | 0 | 0 | 0 | 0
35079383 |  | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110147968 | Idle Facilities | 0 | 0 | 0.060606 | 0.060606 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.060606 | 0 | 0 | 0 | 0
35247006 |  | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 1101502 | Idle Facilities | 0 | 0 | 0.34943 | 0.34943 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34943 | 0.34943 | 0 | 0 | 0 | 0
35221818 |  | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110180930 | Idle Facilities | 0 | 0 | 0.071591 | 0.071591 | 0 | 0 | 0 | 0 | 0 | 0 | 0.071591 | 0.071591 | 0 | 0 | 0 | 0
35244185 |  | 152481106 | BRUNSWICK 1106 | BRUNSWICK 1106CB | Idle Facilities | 0 | 0 | 0.12178 | 0.12178 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12178 | 0.12178 | 0 | 0 | 0 | 0
35037613 |  | 192461102 | BRIDGEVILLE 1102 | BRIDGEVILLE 110237486 | Idle Facilities | 0 | 0 | 0.055114 | 0.055114 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055114 | 0.055114 | 0 | 0 | 0 | 0
35211755 |  | 103191101 | BANGOR 1101 | BANGOR 11011958 | Idle Facilities | 0 | 0 | 0.094318 | 0.094318 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094318 | 0.094318 | 0 | 0 | 0 | 0
35148039 |  | 153662102 | APPLE HILL 2102 | APPLE HILL 21028372 | Idle Facilities | 0 | 0 | 0.1089 | 0.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1089 | 0.1089 | 0 | 0 | 0 | 0
35294737 |  | 103261101 | ANDERSON 1101 | ANDERSON 1101CB | Idle Facilities | 0 | 0 | 0.088636 | 0.088636 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088636 | 0.088636 | 0 | 0 | 0 | 0
35208064 |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101806 | Idle Facilities | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0
74013926 |  | 152481103 | Brunswick 1103 | Brunswick 1103CB | Other | 0 | 0.14583 | 0 | 0.14583 | 0 | 0 | 0 | 0 | 0 | 0.14583 | 0 | 0.14583 | 0 | 0 | 0 | 0
35080162 |  | 43411101 | CALPELLA 1101 | Calpella 1101CB | Other | 1.4413 | 0 | 0 | 1.4413 | 1.2462 | 0 | 0 | 1.2462 | 0.19508 | 0 | 0 | 0.19508 | 0 | 0 | 0 | 0
31066255 |  | 152261106 | Diamond Springs 1106 | Diamond Springs 1106930190 | Other | 0.11269 | 1.3144 | 0 | 1.4271 | 0 | 0 | 0 | 0 | 0.11269 | 1.3144 | 0 | 1.4271 | 0 | 0 | 0 | 0
35112572 |  | 192221102 | GARBERVILLE 1102 | GARBERVILLE 1102CB | Other | 0.59527 | 0.57311 | 0 | 1.1684 | 0 | 0 | 0 | 0 | 0.59527 | 0.57311 | 0 | 1.1684 | 0 | 0 | 0 | 0
31546316 |  | 152691109 | Higgins 1109 | Higgins 110950072 | Other | 0 | 0.13049 | 0 | 0.13049 | 0 | 0 | 0 | 0 | 0 | 0.13049 | 0 | 0.13049 | 0 | 0 | 0 | 0
35206538 |  | 42091101 | MIRABEL 1101 | MIRABEL 1101CB | Other | 0.054735 | 0 | 0 | 0.054735 | 0 | 0 | 0 | 0 | 0.054735 | 0 | 0 | 0.054735 | 0 | 0 | 0 | 0
35236002 |  | 42091102 | Mirabel 1102 | Mirabel 11021139 | Other | 0 | 0.18163 | 0 | 0.18163 | 0 | 0 | 0 | 0 | 0 | 0.18163 | 0 | 0.18163 | 0 | 0 | 0 | 0
31383326 |  | 43321103 | RINCON 1103 | RINCON 1103472 | Other | 0.40133 | 0 | 0 | 0.40133 | 0 | 0 | 0 | 0 | 0.29867 | 0 | 0 | 0.29867 | 0.10265 | 0 | 0 | 0.10265
35384430 |  | 102541101 | VOLTA 1101 | VOLTA 11011596 | Other | 0 | 0.012879 | 0 | 0.012879 | 0 | 0 | 0 | 0 | 0 | 0.012879 | 0 | 0.012879 | 0 | 0 | 0 | 0
35226700 |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | SH | 0 | 0.4214 | 0 | 0.4214 | 0 | 0 | 0 | 0 | 0 | 0.41477 | 0 | 0.41477 | 0 | 0.0066288 | 0 | 0.0066288
35223039 |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | SH | 0.062879 | 0.50265 | 0 | 0.56553 | 0 | 0 | 0 | 0 | 0.062879 | 0.40985 | 0 | 0.47273 | 0 | 0.092803 | 0 | 0.092803
35254640 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 1.0326 | 0 | 0 | 1.0326 | 0 | 0 | 0 | 0 | 1.0326 | 0 | 0 | 1.0326 | 0 | 0 | 0 | 0
35254641 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.088068 | 0.33598 | 0.72008 | 1.1441 | 0 | 0 | 0 | 0 | 0.088068 | 0.33598 | 0.72008 | 1.1441 | 0 | 0 | 0 | 0
35254642 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.81042 | 0 | 0 | 0.81042 | 0 | 0 | 0 | 0 | 0.81042 | 0 | 0 | 0.81042 | 0 | 0 | 0 | 0
35254643 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0 | 1.2705 | 1.0356 | 2.3061 | 0 | 0 | 0 | 0 | 0 | 1.2705 | 1.0356 | 2.3061 | 0 | 0 | 0 | 0
35254644 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.42879 | 0 | 0 | 0.42879 | 0 | 0 | 0 | 0 | 0.42879 | 0 | 0 | 0.42879 | 0 | 0 | 0 | 0
35254645 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.7233 | 0 | 0 | 0.7233 | 0 | 0 | 0 | 0 | 0.7233 | 0 | 0 | 0.7233 | 0 | 0 | 0 | 0
35254646 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0 | 0 | 0.33996 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0.33996 | 0 | 0 | 0 | 0
35254647 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0 | 0.50928 | 0 | 0.50928 | 0 | 0 | 0 | 0 | 0 | 0.50928 | 0 | 0.50928 | 0 | 0 | 0 | 0
35254648 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.44375 | 0 | 0 | 0.44375 | 0 | 0 | 0 | 0 | 0.44375 | 0 | 0 | 0.44375 | 0 | 0 | 0 | 0
35240166 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.46326 | 0.015341 | 0 | 0.4786 | 0 | 0 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341
35240167 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 0.02803 | 0.40909 | 0 | 0.43712 | 0 | 0 | 0 | 0 | 0.02803 | 0.40909 | 0 | 0.43712 | 0 | 0 | 0 | 0
31633176 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | SH | 2.135 | 0 | 0 | 2.135 | 0 | 0 | 0 | 0 | 2.135 | 0 | 0 | 2.135 | 0 | 0 | 0 | 0
35219589 |  | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | SH | 2.7631 | 0 | 0 | 2.7631 | 0 | 0 | 0 | 0 | 2.7631 | 0 | 0 | 2.7631 | 0 | 0 | 0 | 0
35226900 |  | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | SH | 0.60871 | 0 | 0 | 0.60871 | 0 | 0 | 0 | 0 | 0.60871 | 0 | 0 | 0.60871 | 0 | 0 | 0 | 0
35094513 |  | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | SH | 1.7242 | 0.053977 | 0.048485 | 1.8267 | 0 | 0 | 0 | 0 | 1.483 | 0.053977 | 0 | 1.5369 | 0.24129 | 0 | 0.048485 | 0.28977
35192284 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | SH | 0 | 1.9475 | 0 | 1.9475 | 0 | 0 | 0 | 0 | 0 | 1.9475 | 0 | 1.9475 | 0 | 0 | 0 | 0
35223024 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | SH | 0 | 2.0195 | 0 | 2.0195 | 0 | 0 | 0 | 0 | 0 | 2.0195 | 0 | 2.0195 | 0 | 0 | 0 | 0
35223026 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | SH | 0.079545 | 1.329 | 0 | 1.4085 | 0 | 0 | 0 | 0 | 0.079545 | 1.329 | 0 | 1.4085 | 0 | 0 | 0 | 0
35223027 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | SH | 1.7458 | 0 | 0 | 1.7458 | 0.35909 | 0 | 0 | 0.35909 | 1.3867 | 0 | 0 | 1.3867 | 0 | 0 | 0 | 0
35238098 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | SH | 0.47936 | 0 | 0 | 0.47936 | 0 | 0 | 0 | 0 | 0.47936 | 0 | 0 | 0.47936 | 0 | 0 | 0 | 0
35129944 |  | 43432105 | Siverado 2105 | Siverado 2105167360 | SH | 0.68504 | 0 | 0 | 0.68504 | 0 | 0 | 0 | 0 | 0.68504 | 0 | 0 | 0.68504 | 0 | 0 | 0 | 0
35144944 |  | 22721107 | SNEATH LANE 1107 | SNEATH LANE 110748338 | SH | 0 | 0.20398 | 0 | 0.20398 | 0 | 0 | 0 | 0 | 0 | 0.20398 | 0 | 0.20398 | 0 | 0 | 0 | 0
35191318 |  | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | SH | 2.2331 | 0 | 0 | 2.2331 | 0 | 0 | 0 | 0 | 2.2331 | 0 | 0 | 2.2331 | 0 | 0 | 0 | 0
35226846 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 1.4795 | 0 | 0 | 1.4795 | 0 | 0 | 0 | 0 | 1.4795 | 0 | 0 | 1.4795 | 0 | 0 | 0 | 0
35226847 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 1.2947 | 0 | 0.22462 | 1.5193 | 0 | 0 | 0 | 0 | 1.2947 | 0 | 0.22462 | 1.5193 | 0 | 0 | 0 | 0
35226848 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 2.8729 | 0 | 0 | 2.8729 | 0 | 0 | 0 | 0 | 2.8729 | 0 | 0 | 2.8729 | 0 | 0 | 0 | 0
35226849 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 0 | 2.0458 | 0 | 2.0458 | 0 | 0 | 0 | 0 | 0 | 2.0458 | 0 | 2.0458 | 0 | 0 | 0 | 0
35226850 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 1.4674 | 0 | 0 | 1.4674 | 0.18542 | 0 | 0 | 0.18542 | 1.282 | 0 | 0 | 1.282 | 0 | 0 | 0 | 0
35226851 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 2.047 | 0 | 0 | 2.047 | 0 | 0 | 0 | 0 | 2.047 | 0 | 0 | 2.047 | 0 | 0 | 0 | 0
35231607 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 1.3644 | 0 | 0 | 1.3644 | 0 | 0 | 0 | 0 | 1.3644 | 0 | 0 | 1.3644 | 0 | 0 | 0 | 0
35231608 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 0.36742 | 0 | 0 | 0.36742 | 0 | 0 | 0 | 0 | 0.36742 | 0 | 0 | 0.36742 | 0 | 0 | 0 | 0
35231609 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 1.7044 | 0 | 0.15758 | 1.8619 | 0 | 0 | 0 | 0 | 1.7044 | 0 | 0.15758 | 1.8619 | 0 | 0 | 0 | 0
35062374 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 0.037311 | 2.0536 | 0 | 2.0909 | 0 | 0 | 0 | 0 | 0.037311 | 2.0536 | 0 | 2.0909 | 0 | 0 | 0 | 0
35062375 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | SH | 0 | 1.4892 | 0 | 1.4892 | 0 | 0 | 0 | 0 | 0 | 1.4892 | 0 | 1.4892 | 0 | 0 | 0 | 0
35219273 |  | 102541101 | VOLTA 1101 | VOLTA 110149742 | SH | 3.4322 | 0 | 0 | 3.4322 | 0 | 0 | 0 | 0 | 3.4322 | 0 | 0 | 3.4322 | 0 | 0 | 0 | 0
35240168 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 1.478 | 0 | 0 | 1.478 | 0 | 0 | 0 | 0 | 1.478 | 0 | 0 | 1.478 | 0 | 0 | 0 | 0
35254649 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 0.14773 | 0.46686 | 0 | 0.61458 | 0 | 0 | 0 | 0 | 0.14773 | 0.46686 | 0 | 0.61458 | 0 | 0 | 0 | 0
35254650 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 0.0056818 | 0.30436 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0.30436 | 0 | 0.30436 | 0 | 0.0056818 | 0 | 0.0056818
35254651 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 2.4038 | 0 | 0 | 2.4038 | 0 | 0 | 0 | 0 | 2.3117 | 0 | 0 | 2.3117 | 0.092045 | 0 | 0 | 0.092045
35254652 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 1.9714 | 0 | 0 | 1.9714 | 0 | 0 | 0 | 0 | 1.9714 | 0 | 0 | 1.9714 | 0 | 0 | 0 | 0
35254653 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 1.9822 | 0 | 0 | 1.9822 | 0 | 0 | 0 | 0 | 1.9822 | 0 | 0 | 1.9822 | 0 | 0 | 0 | 0
35254654 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 0.15511 | 0 | 0 | 0.15511 | 0 | 0 | 0 | 0 | 0.15511 | 0 | 0 | 0.15511 | 0 | 0 | 0 | 0
35254655 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | SH | 0.5517 | 0 | 0 | 0.5517 | 0 | 0 | 0 | 0 | 0.5517 | 0 | 0 | 0.5517 | 0 | 0 | 0 | 0
35231543 |  | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | SH | 0.13371 | 1.2386 | 0 | 1.3723 | 0 | 0 | 0 | 0 | 0.13371 | 1.2386 | 0 | 1.3723 | 0 | 0 | 0 | 0
35240169 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 1.9038 | 0 | 0 | 1.9038 | 0 | 0 | 0 | 0 | 1.9038 | 0 | 0 | 1.9038 | 0 | 0 | 0 | 0
35240170 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 0.83712 | 0 | 0 | 0.83712 | 0 | 0 | 0 | 0 | 0.83712 | 0 | 0 | 0.83712 | 0 | 0 | 0 | 0
35240171 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 1.4104 | 0 | 0 | 1.4104 | 0 | 0 | 0 | 0 | 1.4104 | 0 | 0 | 1.4104 | 0 | 0 | 0 | 0
35254720 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 1.4263 | 0 | 0 | 1.4263 | 0 | 0 | 0 | 0 | 1.4263 | 0 | 0 | 1.4263 | 0 | 0 | 0 | 0
35254721 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 1.7807 | 0 | 0 | 1.7807 | 0 | 0 | 0 | 0 | 1.7807 | 0 | 0 | 1.7807 | 0 | 0 | 0 | 0
35254941 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 2.0992 | 0 | 0 | 2.0992 | 0 | 0 | 0 | 0 | 2.0992 | 0 | 0 | 2.0992 | 0 | 0 | 0 | 0
35254942 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 1.4555 | 0 | 0 | 1.4555 | 0 | 0 | 0 | 0 | 1.4555 | 0 | 0 | 1.4555 | 0 | 0 | 0 | 0
35254943 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 2.2205 | 0 | 0 | 2.2205 | 0 | 0 | 0 | 0 | 2.2205 | 0 | 0 | 2.2205 | 0 | 0 | 0 | 0
35254656 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 0.0028409 | 0.44545 | 0 | 0.4483 | 0 | 0 | 0 | 0 | 0.0028409 | 0.44545 | 0 | 0.4483 | 0 | 0 | 0 | 0
35254657 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0
35254658 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 1.8225 | 0 | 0 | 1.8225 | 0 | 0 | 0 | 0 | 1.7841 | 0 | 0 | 1.7841 | 0.038447 | 0 | 0 | 0.038447
35254659 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | SH | 2.6057 | 0 | 0 | 2.6057 | 0 | 0 | 0 | 0 | 2.6057 | 0 | 0 | 2.6057 | 0 | 0 | 0 | 0
35254944 |  | 102541101 | VOLTA 1101 | VOLTA 11011596 | SH | 0.052841 | 0 | 0.083144 | 0.13598 | 0 | 0 | 0 | 0 | 0.052841 | 0 | 0.083144 | 0.13598 | 0 | 0 | 0 | 0
35243453 |  | 102541101 | VOLTA 1101 | VOLTA 11011596 | SH | 1.428 | 0 | 0 | 1.428 | 0 | 0 | 0 | 0 | 1.086 | 0 | 0 | 1.086 | 0.34205 | 0 | 0 | 0.34205
35217273 |  | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101CB | SH | 1.0777 | 0 | 0 | 1.0777 | 0 | 0 | 0 | 0 | 1.0777 | 0 | 0 | 1.0777 | 0 | 0 | 0 | 0
35219291 |  | 63591101 | VACA DIXON 1101 | VACA DIXON 1101126774 | SH | 0.36572 | 0 | 0 | 0.36572 | 0 | 0 | 0 | 0 | 0.36572 | 0 | 0 | 0.36572 | 0 | 0 | 0 | 0
35219269 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 2.1066 | 0 | 0 | 2.1066 | 0 | 0 | 0 | 0 | 2.1066 | 0 | 0 | 2.1066 | 0 | 0 | 0 | 0
35237258 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 2.1097 | 0 | 0 | 2.1097 | 0 | 0 | 0 | 0 | 2.1097 | 0 | 0 | 2.1097 | 0 | 0 | 0 | 0
35237259 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 3.5578 | 0 | 0 | 3.5578 | 0 | 0 | 0 | 0 | 3.5578 | 0 | 0 | 3.5578 | 0 | 0 | 0 | 0
35237360 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 3.0958 | 0 | 0 | 3.0958 | 0 | 0 | 0 | 0 | 3.0958 | 0 | 0 | 3.0958 | 0 | 0 | 0 | 0
35237361 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 2.7896 | 0 | 0 | 2.7896 | 0 | 0 | 0 | 0 | 2.7896 | 0 | 0 | 2.7896 | 0 | 0 | 0 | 0
35237364 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 3.0277 | 0 | 0 | 3.0277 | 0 | 0 | 0 | 0 | 3.0277 | 0 | 0 | 3.0277 | 0 | 0 | 0 | 0
35237365 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 2.803 | 0 | 0 | 2.803 | 0 | 0 | 0 | 0 | 2.803 | 0 | 0 | 2.803 | 0 | 0 | 0 | 0
35237366 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 2.2186 | 0 | 0 | 2.2186 | 0 | 0 | 0 | 0 | 2.2186 | 0 | 0 | 2.2186 | 0 | 0 | 0 | 0
35237368 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 2.8725 | 0 | 0.14129 | 3.0138 | 0 | 0 | 0 | 0 | 2.8725 | 0 | 0.14129 | 3.0138 | 0 | 0 | 0 | 0
35237369 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 3.2769 | 0 | 0 | 3.2769 | 0 | 0 | 0 | 0 | 3.2769 | 0 | 0 | 3.2769 | 0 | 0 | 0 | 0
35237370 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 3.6491 | 0 | 0 | 3.6491 | 0 | 0 | 0 | 0 | 3.5733 | 0 | 0 | 3.5733 | 0.075758 | 0 | 0 | 0.075758
35237371 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | SH | 0.3428 | 0 | 0 | 0.3428 | 0 | 0 | 0 | 0 | 0.3428 | 0 | 0 | 0.3428 | 0 | 0 | 0 | 0
35219590 |  | 63591105 | VACA DIXON 1105 | VACA DIXON 1105965390 | SH | 1.6172 | 0 | 0 | 1.6172 | 0 | 0 | 0 | 0 | 1.6172 | 0 | 0 | 1.6172 | 0 | 0 | 0 | 0
35224378 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 2.8888 | 0 | 0.075947 | 2.9648 | 1.0445 | 0 | 0.075947 | 1.1205 | 1.8443 | 0 | 0 | 1.8443 | 0 | 0 | 0 | 0
35227656 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 0.049432 | 1.0758 | 0 | 1.1252 | 0 | 0 | 0 | 0 | 0.049432 | 1.0758 | 0 | 1.1252 | 0 | 0 | 0 | 0
35227658 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 0.34489 | 0 | 0 | 0.34489 | 0 | 0 | 0 | 0 | 0.34489 | 0 | 0 | 0.34489 | 0 | 0 | 0 | 0
35227659 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 0.25568 | 0.056818 | 0 | 0.3125 | 0.25568 | 0 | 0 | 0.25568 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0
35227870 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 0 | 1.5928 | 0 | 1.5928 | 0 | 0 | 0 | 0 | 0 | 1.5928 | 0 | 1.5928 | 0 | 0 | 0 | 0
35227651 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 2.7343 | 0 | 0 | 2.7343 | 0 | 0 | 0 | 0 | 2.7343 | 0 | 0 | 2.7343 | 0 | 0 | 0 | 0
35227653 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 2.6422 | 0 | 0.064394 | 2.7066 | 0 | 0 | 0 | 0 | 2.6422 | 0 | 0.064394 | 2.7066 | 0 | 0 | 0 | 0
35271455 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SH | 0.54034 | 0 | 0 | 0.54034 | 0 | 0 | 0 | 0 | 0.54034 | 0 | 0 | 0.54034 | 0 | 0 | 0 | 0
35240178 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 1102710384 | SH | 3.4229 | 0 | 0 | 3.4229 | 0 | 0 | 0 | 0 | 3.4229 | 0 | 0 | 3.4229 | 0 | 0 | 0 | 0
35254263 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 1102710384 | SH | 1.2795 | 0 | 0 | 1.2795 | 0 | 0 | 0 | 0 | 1.2795 | 0 | 0 | 1.2795 | 0 | 0 | 0 | 0
35254264 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | SH | 1.26 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0
35254265 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | SH | 2.6678 | 0 | 0.054735 | 2.7225 | 0 | 0 | 0 | 0 | 2.6678 | 0 | 0.054735 | 2.7225 | 0 | 0 | 0 | 0
35240174 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | SH | 1.0494 | 0 | 0 | 1.0494 | 0 | 0 | 0 | 0 | 1.0494 | 0 | 0 | 1.0494 | 0 | 0 | 0 | 0
35145525 |  | 43321104 | RINCON 1104 | RINCON 1104CB | SH | 0.13598 | 1.283 | 0 | 1.4189 | 0 | 1.283 | 0 | 1.283 | 0.13598 | 0 | 0 | 0.13598 | 0 | 0 | 0 | 0
35145004 |  | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106CB | SH | 0 | 0.69489 | 0 | 0.69489 | 0 | 0 | 0 | 0 | 0 | 0.69489 | 0 | 0.69489 | 0 | 0 | 0 | 0
35324156 |  | 14161108 | ROSSMOOR 1108 | ROSSMOOR 1108CB | SH | 0.38864 | 0.55341 | 0.092614 | 1.0347 | 0 | 0 | 0 | 0 | 0.38864 | 0.55341 | 0.092614 | 1.0347 | 0 | 0 | 0 | 0
35264191 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | SH | 2.3604 | 0 | 0 | 2.3604 | 0 | 0 | 0 | 0 | 2.3604 | 0 | 0 | 2.3604 | 0 | 0 | 0 | 0
35264192 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | SH | 2.4191 | 0 | 0 | 2.4191 | 0 | 0 | 0 | 0 | 2.4191 | 0 | 0 | 2.4191 | 0 | 0 | 0 | 0
35264193 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | SH | 2.0784 | 0 | 0 | 2.0784 | 0 | 0 | 0 | 0 | 2.0784 | 0 | 0 | 2.0784 | 0 | 0 | 0 | 0
35264194 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | SH | 1.9746 | 0 | 0 | 1.9746 | 0 | 0 | 0 | 0 | 1.9746 | 0 | 0 | 1.9746 | 0 | 0 | 0 | 0
35271002 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | SH | 1.1235 | 0 | 0 | 1.1235 | 0 | 0 | 0 | 0 | 1.1235 | 0 | 0 | 1.1235 | 0 | 0 | 0 | 0
35240224 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | SH | 1.8794 | 0 | 0 | 1.8794 | 0 | 0 | 0 | 0 | 1.8794 | 0 | 0 | 1.8794 | 0 | 0 | 0 | 0
35240179 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104CB | SH | 0.31629 | 0 | 0 | 0.31629 | 0 | 0 | 0 | 0 | 0.31629 | 0 | 0 | 0.31629 | 0 | 0 | 0 | 0
35240220 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | SH | 2.7716 | 0 | 0 | 2.7716 | 0 | 0 | 0 | 0 | 2.7716 | 0 | 0 | 2.7716 | 0 | 0 | 0 | 0
35240221 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | SH | 2.9184 | 0 | 0 | 2.9184 | 0 | 0 | 0 | 0 | 2.9184 | 0 | 0 | 2.9184 | 0 | 0 | 0 | 0
35264181 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | SH | 2.7506 | 0 | 0 | 2.7506 | 0 | 0 | 0 | 0 | 0.89205 | 0 | 0 | 0.89205 | 1.8585 | 0 | 0 | 1.8585
35264182 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | SH | 2.6348 | 0 | 0 | 2.6348 | 0 | 0 | 0 | 0 | 2.4572 | 0 | 0 | 2.4572 | 0.17765 | 0 | 0 | 0.17765
35264183 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | SH | 2.436 | 0 | 0 | 2.436 | 0 | 0 | 0 | 0 | 2.436 | 0 | 0 | 2.436 | 0 | 0 | 0 | 0
35264184 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | SH | 2.0775 | 0 | 0 | 2.0775 | 0 | 0 | 0 | 0 | 2.0775 | 0 | 0 | 2.0775 | 0 | 0 | 0 | 0
35264186 |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | SH | 0.42822 | 0 | 0 | 0.42822 | 0 | 0 | 0 | 0 | 0.42822 | 0 | 0 | 0.42822 | 0 | 0 | 0 | 0
35062376 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | SH | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0.97178 | 0 | 4.2534 | 0 | 4.2534
35226853 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | SH | 2.6305 | 0 | 0 | 2.6305 | 0 | 0 | 0 | 0 | 2.6305 | 0 | 0 | 2.6305 | 0 | 0 | 0 | 0
35226854 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | SH | 2.1119 | 0 | 0.1572 | 2.2691 | 0 | 0 | 0 | 0 | 2.1119 | 0 | 0.1572 | 2.2691 | 0 | 0 | 0 | 0
35226856 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | SH | 1.093 | 0 | 0 | 1.093 | 0 | 0 | 0 | 0 | 1.093 | 0 | 0 | 1.093 | 0 | 0 | 0 | 0
35224377 |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | SH | 0 | 0.21799 | 0 | 0.21799 | 0 | 0 | 0 | 0 | 0 | 0.21799 | 0 | 0.21799 | 0 | 0 | 0 | 0
35226632 |  | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | SH | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0
35219280 |  | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | SH | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 1.6364 | 0 | 0 | 1.6364 | 0.063636 | 0 | 0 | 0.063636
35219275 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | SH | 1.0231 | 0 | 0 | 1.0231 | 0 | 0 | 0 | 0 | 1.0231 | 0 | 0 | 1.0231 | 0 | 0 | 0 | 0
35240176 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | SH | 2.3687 | 0 | 0 | 2.3687 | 0 | 0 | 0 | 0 | 2.3687 | 0 | 0 | 2.3687 | 0 | 0 | 0 | 0
35240177 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | SH | 2.3945 | 0 | 0 | 2.3945 | 0 | 0 | 0 | 0 | 2.3945 | 0 | 0 | 2.3945 | 0 | 0 | 0 | 0
35254177 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | SH | 0.29489 | 0 | 0 | 0.29489 | 0 | 0 | 0 | 0 | 0.29489 | 0 | 0 | 0.29489 | 0 | 0 | 0 | 0
35254178 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | SH | 1.2492 | 0 | 0 | 1.2492 | 0 | 0 | 0 | 0 | 1.2492 | 0 | 0 | 1.2492 | 0 | 0 | 0 | 0
35254560 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | SH | 1.2205 | 0 | 0 | 1.2205 | 0 | 0 | 0 | 0 | 1.2205 | 0 | 0 | 1.2205 | 0 | 0 | 0 | 0
35254260 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | SH | 0.1036 | 0.37822 | 0 | 0.48182 | 0 | 0 | 0 | 0 | 0.1036 | 0.37822 | 0 | 0.48182 | 0 | 0 | 0 | 0
35254261 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | SH | 2.829 | 0 | 0 | 2.829 | 0 | 0 | 0 | 0 | 2.829 | 0 | 0 | 2.829 | 0 | 0 | 0 | 0
35254262 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | SH | 2.0928 | 0 | 0 | 2.0928 | 0 | 0 | 0 | 0 | 2.0928 | 0 | 0 | 2.0928 | 0 | 0 | 0 | 0
35240175 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | SH | 3.3032 | 0 | 0.12879 | 3.432 | 0 | 0 | 0 | 0 | 3.3032 | 0 | 0.12879 | 3.432 | 0 | 0 | 0 | 0
35243440 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 1103CB | SH | 0 | 1.0214 | 0 | 1.0214 | 0 | 0 | 0 | 0 | 0 | 1.0214 | 0 | 1.0214 | 0 | 0 | 0 | 0
35225826 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 2.5006 | 0 | 0 | 2.5006 | 0 | 0 | 0 | 0 | 2.5006 | 0 | 0 | 2.5006 | 0 | 0 | 0 | 0
35225827 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0 | 1.1182 | 0 | 1.1182 | 0 | 0 | 0 | 0 | 0 | 1.1182 | 0 | 1.1182 | 0 | 0 | 0 | 0
35225828 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0 | 2.7928 | 0 | 2.7928 | 0 | 0 | 0 | 0 | 0 | 2.7928 | 0 | 2.7928 | 0 | 0 | 0 | 0
35233947 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.8646 | 0 | 0 | 1.8646 | 0 | 0 | 0 | 0 | 1.8646 | 0 | 0 | 1.8646 | 0 | 0 | 0 | 0
35233949 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.7706 | 0 | 0 | 1.7706 | 0 | 0 | 0 | 0 | 0.12955 | 0 | 0 | 0.12955 | 1.6411 | 0 | 0 | 1.6411
35233952 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 2.1816 | 0 | 0 | 2.1816 | 0 | 0 | 0 | 0 | 2.1816 | 0 | 0 | 2.1816 | 0 | 0 | 0 | 0
35233953 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0 | 0.81761 | 0 | 0.81761 | 0 | 0 | 0 | 0 | 0 | 0.81761 | 0 | 0.81761 | 0 | 0 | 0 | 0
35233954 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.19451 | 0 | 0 | 0.19451 | 0 | 0 | 0 | 0 | 0.19451 | 0 | 0 | 0.19451 | 0 | 0 | 0 | 0
35233955 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0 | 0.55928 | 0 | 0.55928 | 0 | 0 | 0 | 0 | 0 | 0.55928 | 0 | 0.55928 | 0 | 0 | 0 | 0
35233956 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.26098 | 0 | 0 | 0.26098 | 0 | 0 | 0 | 0 | 0.26098 | 0 | 0 | 0.26098 | 0 | 0 | 0 | 0
35233957 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0 | 0.10436 | 0 | 0.10436 | 0 | 0 | 0 | 0 | 0 | 0.10436 | 0 | 0.10436 | 0 | 0 | 0 | 0
35233958 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.18845 | 0 | 0 | 0.18845 | 0 | 0 | 0 | 0 | 0.18845 | 0 | 0 | 0.18845 | 0 | 0 | 0 | 0
35233959 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.3358 | 0 | 0 | 0.3358 | 0 | 0 | 0 | 0 | 0.3358 | 0 | 0 | 0.3358 | 0 | 0 | 0 | 0
35234380 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 2.1807 | 0 | 0 | 2.1807 | 0 | 0 | 0 | 0 | 2.1807 | 0 | 0 | 2.1807 | 0 | 0 | 0 | 0
35234383 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0 | 1.2502 | 0 | 1.2502 | 0 | 0 | 0 | 0 | 0 | 1.2502 | 0 | 1.2502 | 0 | 0 | 0 | 0
35234384 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.050568 | 0 | 0 | 0.050568 | 0 | 0 | 0 | 0 | 0.050568 | 0 | 0 | 0.050568 | 0 | 0 | 0 | 0
35234385 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.64545 | 0 | 0 | 0.64545 | 0 | 0 | 0 | 0 | 0.64545 | 0 | 0 | 0.64545 | 0 | 0 | 0 | 0
35234386 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.93239 | 0 | 0 | 0.93239 | 0 | 0 | 0 | 0 | 0.93239 | 0 | 0 | 0.93239 | 0 | 0 | 0 | 0
35234387 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.81534 | 0 | 0 | 0.81534 | 0 | 0 | 0 | 0 | 0.81534 | 0 | 0 | 0.81534 | 0 | 0 | 0 | 0
35234388 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.9795 | 0 | 0 | 1.9795 | 0 | 0 | 0 | 0 | 1.9795 | 0 | 0 | 1.9795 | 0 | 0 | 0 | 0
35234389 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.88731 | 0 | 0 | 0.88731 | 0 | 0 | 0 | 0 | 0.88731 | 0 | 0 | 0.88731 | 0 | 0 | 0 | 0
35234390 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.41439 | 0 | 0 | 0.41439 | 0 | 0 | 0 | 0 | 0.41439 | 0 | 0 | 0.41439 | 0 | 0 | 0 | 0
35234391 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.229 | 0 | 0 | 1.229 | 0 | 0 | 0 | 0 | 1.229 | 0 | 0 | 1.229 | 0 | 0 | 0 | 0
35234392 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.6227 | 0 | 0 | 1.6227 | 0 | 0 | 0 | 0 | 1.6227 | 0 | 0 | 1.6227 | 0 | 0 | 0 | 0
35234397 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 0.71345 | 0 | 0 | 0.71345 | 0 | 0 | 0 | 0 | 0.56856 | 0 | 0 | 0.56856 | 0.14489 | 0 | 0 | 0.14489
35234400 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.2771 | 0 | 0 | 1.2771 | 0 | 0 | 0 | 0 | 1.2277 | 0 | 0 | 1.2277 | 0.049432 | 0 | 0 | 0.049432
35234401 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SH | 1.846 | 0 | 0 | 1.846 | 0 | 0 | 0 | 0 | 1.846 | 0 | 0 | 1.846 | 0 | 0 | 0 | 0
35114040 |  | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | SH | 1.3718 | 0.093561 | 0 | 1.4653 | 0 | 0 | 0 | 0 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.058523 | 0.093561 | 0 | 0.15208
35254249 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | SH | 2.6725 | 0 | 0 | 2.6725 | 0 | 0 | 0 | 0 | 2.5458 | 0 | 0 | 2.5458 | 0.1267 | 0 | 0 | 0.1267
35254250 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | SH | 1.0428 | 0 | 0 | 1.0428 | 0 | 0 | 0 | 0 | 1.0428 | 0 | 0 | 1.0428 | 0 | 0 | 0 | 0
35278880 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | SH | 2.7083 | 0 | 0 | 2.7083 | 0 | 0 | 0 | 0 | 2.7083 | 0 | 0 | 2.7083 | 0 | 0 | 0 | 0
35278882 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | SH | 2.6322 | 0 | 0 | 2.6322 | 0 | 0 | 0 | 0 | 1.7252 | 0 | 0 | 1.7252 | 0.90701 | 0 | 0 | 0.90701
35278885 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | SH | 1.3748 | 0 | 0 | 1.3748 | 0 | 0 | 0 | 0 | 1.3748 | 0 | 0 | 1.3748 | 0 | 0 | 0 | 0
35278886 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | SH | 1.379 | 0.024621 | 0 | 1.4036 | 0 | 0 | 0 | 0 | 1.379 | 0.024621 | 0 | 1.4036 | 0 | 0 | 0 | 0
35279631 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N58 | SH | 3.064 | 0 | 0 | 3.064 | 0 | 0 | 0 | 0 | 1.4223 | 0 | 0 | 1.4223 | 1.6417 | 0 | 0 | 1.6417
35219542 |  | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | SH | 0 | 0.12879 | 0 | 0.12879 | 0 | 0 | 0 | 0 | 0 | 0.12879 | 0 | 0.12879 | 0 | 0 | 0 | 0
35279630 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 110359763 | SH | 1.6623 | 0 | 0 | 1.6623 | 0 | 0 | 0 | 0 | 1.6623 | 0 | 0 | 1.6623 | 0 | 0 | 0 | 0
35254251 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 110359763 | SH | 1.1744 | 0 | 0 | 1.1744 | 0 | 0 | 0 | 0 | 1.1744 | 0 | 0 | 1.1744 | 0 | 0 | 0 | 0
35145003 |  | 13801103 | MORAGA 1103 | MORAGA 1103CB | SH | 0.11742 | 0.12178 | 0.24356 | 0.48277 | 0 | 0 | 0 | 0 | 0.11742 | 0.12178 | 0.24356 | 0.48277 | 0 | 0 | 0 | 0
35223037 |  | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | SH | 0 | 0.0079545 | 0 | 0.0079545 | 0 | 0 | 0 | 0 | 0 | 0.0079545 | 0 | 0.0079545 | 0 | 0 | 0 | 0
35116444 |  | 163661702 | MIWUK 1702 | MIWUK 170238218 | SH | 2.1023 | 0 | 0 | 2.1023 | 0.38883 | 0 | 0 | 0.38883 | 1.7134 | 0 | 0 | 1.7134 | 0 | 0 | 0 | 0
35236439 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.17614 | 1.2508 | 0 | 1.4269 | 0 | 0 | 0 | 0 | 0.088068 | 1.2034 | 0 | 1.2915 | 0.088068 | 0.047348 | 0 | 0.13542
35236660 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0 | 0.42557 | 0 | 0.42557 | 0 | 0 | 0 | 0 | 0 | 0.42557 | 0 | 0.42557 | 0 | 0 | 0 | 0
35137590 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | SH | 0.39299 | 0 | 0 | 0.39299 | 0 | 0 | 0 | 0 | 0.39299 | 0 | 0 | 0.39299 | 0 | 0 | 0 | 0
35137593 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | SH | 1.3786 | 0 | 0 | 1.3786 | 0 | 0 | 0 | 0 | 1.3786 | 0 | 0 | 1.3786 | 0 | 0 | 0 | 0
35137596 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | SH | 1.0116 | 0 | 0 | 1.0116 | 0 | 0 | 0 | 0 | 1.0116 | 0 | 0 | 1.0116 | 0 | 0 | 0 | 0
35227162 |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | SH | 0.10227 | 0.22064 | 0 | 0.32292 | 0 | 0 | 0 | 0 | 0.10227 | 0.22064 | 0 | 0.32292 | 0 | 0 | 0 | 0
35227163 |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | SH | 0.33769 | 0 | 0 | 0.33769 | 0 | 0 | 0 | 0 | 0.33769 | 0 | 0 | 0.33769 | 0 | 0 | 0 | 0
35227164 |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | SH | 0.52481 | 0 | 0 | 0.52481 | 0 | 0 | 0 | 0 | 0.52481 | 0 | 0 | 0.52481 | 0 | 0 | 0 | 0
35217269 |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | SH | 0.15587 | 0.34261 | 0 | 0.49848 | 0 | 0 | 0 | 0 | 0.15587 | 0.34261 | 0 | 0.49848 | 0 | 0 | 0 | 0
35217271 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0 | 2.3784 | 0 | 2.3784 | 0 | 0 | 0 | 0 | 0 | 2.3784 | 0 | 2.3784 | 0 | 0 | 0 | 0
35227165 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0 | 0.89394 | 0 | 0.89394 | 0 | 0 | 0 | 0 | 0 | 0.89394 | 0 | 0.89394 | 0 | 0 | 0 | 0
35227167 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0 | 1.653 | 0 | 1.653 | 0 | 0 | 0 | 0 | 0 | 1.653 | 0 | 1.653 | 0 | 0 | 0 | 0
35227168 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0 | 1.2121 | 0 | 1.2121 | 0 | 0 | 0 | 0 | 0 | 1.2121 | 0 | 1.2121 | 0 | 0 | 0 | 0
35227861 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 1.4517 | 0 | 0 | 1.4517 | 0 | 0 | 0 | 0 | 1.4517 | 0 | 0 | 1.4517 | 0 | 0 | 0 | 0
35227862 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 1.2335 | 0 | 0 | 1.2335 | 0 | 0 | 0 | 0 | 1.2335 | 0 | 0 | 1.2335 | 0 | 0 | 0 | 0
35227863 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0.7947 | 0 | 0 | 0.7947 | 0 | 0 | 0 | 0 | 0.7947 | 0 | 0 | 0.7947 | 0 | 0 | 0 | 0
35227864 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0 | 1.3212 | 0 | 1.3212 | 0 | 0 | 0 | 0 | 0 | 0.36136 | 0 | 0.36136 | 0 | 0.95985 | 0 | 0.95985
35227867 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0.96932 | 0 | 0 | 0.96932 | 0.052652 | 0 | 0 | 0.052652 | 0.91667 | 0 | 0 | 0.91667 | 0 | 0 | 0 | 0
35227868 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0.57727 | 0 | 0 | 0.57727 | 0 | 0 | 0 | 0 | 0.13788 | 0 | 0 | 0.13788 | 0.43939 | 0 | 0 | 0.43939
35222045 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0.91648 | 0 | 0 | 0.91648 | 0 | 0 | 0 | 0 | 0.91648 | 0 | 0 | 0.91648 | 0 | 0 | 0 | 0
35220896 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0 | 0.31686 | 0 | 0.31686 | 0 | 0 | 0 | 0 | 0 | 0.31686 | 0 | 0.31686 | 0 | 0 | 0 | 0
35236661 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | SH | 0.20208 | 0 | 0 | 0.20208 | 0 | 0 | 0 | 0 | 0.20208 | 0 | 0 | 0.20208 | 0 | 0 | 0 | 0
35227003 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0 | 0.53864 | 0 | 0.53864 | 0 | 0 | 0 | 0 | 0 | 0.53864 | 0 | 0.53864 | 0 | 0 | 0 | 0
35227004 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0 | 0.35758 | 0 | 0.35758 | 0 | 0 | 0 | 0 | 0 | 0.35758 | 0 | 0.35758 | 0 | 0 | 0 | 0
35227010 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.091477 | 0 | 0 | 0.091477 | 0 | 0 | 0 | 0 | 0.091477 | 0 | 0 | 0.091477 | 0 | 0 | 0 | 0
35227013 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.041856 | 0 | 0 | 0.041856 | 0 | 0 | 0 | 0 | 0.041856 | 0 | 0 | 0.041856 | 0 | 0 | 0 | 0
35227018 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 1.1657 | 0 | 0 | 1.1657 | 0 | 0 | 0 | 0 | 1.1657 | 0 | 0 | 1.1657 | 0 | 0 | 0 | 0
35227021 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.35947 | 0 | 0 | 0.35947 | 0 | 0 | 0 | 0 | 0.35947 | 0 | 0 | 0.35947 | 0 | 0 | 0 | 0
35226861 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.8161 | 0 | 0 | 0.8161 | 0 | 0 | 0 | 0 | 0.8161 | 0 | 0 | 0.8161 | 0 | 0 | 0 | 0
35226862 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.71326 | 0 | 0 | 0.71326 | 0 | 0 | 0 | 0 | 0.5358 | 0 | 0 | 0.5358 | 0.17746 | 0 | 0 | 0.17746
35226863 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.52822 | 0 | 0 | 0.52822 | 0 | 0 | 0 | 0 | 0.52822 | 0 | 0 | 0.52822 | 0 | 0 | 0 | 0
35226864 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.36477 | 0 | 0 | 0.36477 | 0 | 0 | 0 | 0 | 0.36477 | 0 | 0 | 0.36477 | 0 | 0 | 0 | 0
35226865 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.23447 | 0 | 0 | 0.23447 | 0 | 0 | 0 | 0 | 0.23447 | 0 | 0 | 0.23447 | 0 | 0 | 0 | 0
35226866 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.56439 | 0 | 0 | 0.56439 | 0 | 0 | 0 | 0 | 0.56439 | 0 | 0 | 0.56439 | 0 | 0 | 0 | 0
35226870 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.35568 | 0 | 0 | 0.35568 | 0 | 0 | 0 | 0 | 0.35568 | 0 | 0 | 0.35568 | 0 | 0 | 0 | 0
35226872 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | SH | 0.21117 | 0 | 0 | 0.21117 | 0 | 0 | 0 | 0 | 0.21117 | 0 | 0 | 0.21117 | 0 | 0 | 0 | 0
35219272 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | SH | 0.88977 | 0 | 0 | 0.88977 | 0 | 0 | 0 | 0 | 0.88977 | 0 | 0 | 0.88977 | 0 | 0 | 0 | 0
35227028 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | SH | 0.65322 | 0 | 0 | 0.65322 | 0 | 0 | 0 | 0 | 0.65322 | 0 | 0 | 0.65322 | 0 | 0 | 0 | 0
35227029 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | SH | 1.1886 | 0 | 0 | 1.1886 | 0 | 0 | 0 | 0 | 1.1886 | 0 | 0 | 1.1886 | 0 | 0 | 0 | 0
35226624 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | SH | 0.70587 | 0 | 0 | 0.70587 | 0 | 0 | 0 | 0 | 0.70587 | 0 | 0 | 0.70587 | 0 | 0 | 0 | 0
35236437 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | SH | 0.3803 | 0 | 0 | 0.3803 | 0 | 0 | 0 | 0 | 0.3803 | 0 | 0 | 0.3803 | 0 | 0 | 0 | 0
35236438 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | SH | 0.5197 | 0 | 0 | 0.5197 | 0 | 0 | 0 | 0 | 0.5197 | 0 | 0 | 0.5197 | 0 | 0 | 0 | 0
35192281 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | SH | 0.5125 | 0 | 0 | 0.5125 | 0 | 0 | 0 | 0 | 0.5125 | 0 | 0 | 0.5125 | 0 | 0 | 0 | 0
35052737 |  | 163661701 | MIWUK 1701 | MIWUK 1701953336 | SH | 1.3907 | 0 | 0 | 1.3907 | 0 | 0 | 0 | 0 | 1.3907 | 0 | 0 | 1.3907 | 0 | 0 | 0 | 0
35116383 |  | 163661701 | MIWUK 1701 | MIWUK 1701953336 | SH | 1.3919 | 0 | 0 | 1.3919 | 1.042 | 0 | 0 | 1.042 | 0.34981 | 0 | 0 | 0.34981 | 0 | 0 | 0 | 0
35116385 |  | 163661701 | MIWUK 1701 | MIWUK 1701953336 | SH | 1.397 | 0 | 0 | 1.397 | 0 | 0 | 0 | 0 | 1.397 | 0 | 0 | 1.397 | 0 | 0 | 0 | 0
35232650 |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | SH | 0 | 1.3269 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 1.3269 | 0 | 0 | 0 | 0
35219281 |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | SH | 0.0083333 | 1.8222 | 0 | 1.8305 | 0 | 0 | 0 | 0 | 0.0083333 | 1.8222 | 0 | 1.8305 | 0 | 0 | 0 | 0
35119965 |  | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | SH | 0.84905 | 0 | 0 | 0.84905 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0 | 0.84905 | 0 | 0 | 0 | 0
35238567 |  | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | SH | 0.11723 | 0 | 0.28826 | 0.40549 | 0 | 0 | 0 | 0 | 0.11723 | 0 | 0.28826 | 0.40549 | 0 | 0 | 0 | 0
35219098 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | SH | 0.62424 | 0 | 0.063826 | 0.68807 | 0 | 0 | 0 | 0 | 0.62424 | 0 | 0.063826 | 0.68807 | 0 | 0 | 0 | 0
35229119 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | SH | 0.0054924 | 0.64167 | 0.28333 | 0.93049 | 0 | 0 | 0 | 0 | 0.0054924 | 0.64167 | 0.28333 | 0.93049 | 0 | 0 | 0 | 0
35219267 |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | SH | 1.8269 | 0 | 0 | 1.8269 | 0 | 0 | 0 | 0 | 1.8269 | 0 | 0 | 1.8269 | 0 | 0 | 0 | 0
35219587 |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | SH | 1.8813 | 0 | 0 | 1.8813 | 0 | 0 | 0 | 0 | 1.8813 | 0 | 0 | 1.8813 | 0 | 0 | 0 | 0
35219588 |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | SH | 0.88182 | 0 | 0.27973 | 1.1616 | 0 | 0 | 0 | 0 | 0.87045 | 0 | 0.27973 | 1.1502 | 0.011364 | 0 | 0 | 0.011364
35219266 |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | SH | 2.9455 | 0 | 0 | 2.9455 | 0 | 0 | 0 | 0 | 2.9455 | 0 | 0 | 2.9455 | 0 | 0 | 0 | 0
35223038 |  | 163541101 | MARTELL 1101 | MARTELL 1101CB | SH | 0 | 0.51155 | 0 | 0.51155 | 0 | 0 | 0 | 0 | 0 | 0.51155 | 0 | 0.51155 | 0 | 0 | 0 | 0
35225589 |  | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | SH | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0
35225591 |  | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | SH | 0.8464 | 0 | 0.63258 | 1.479 | 0 | 0 | 0 | 0 | 0.8464 | 0 | 0.63258 | 1.479 | 0 | 0 | 0 | 0
35219096 |  | 14452104 | KIRKER 2104 | KIRKER 2104442850 | SH | 0.11288 | 1.8303 | 0.028409 | 1.9716 | 0 | 0 | 0 | 0 | 0.11288 | 1.8019 | 0 | 1.9148 | 0 | 0.056818 | 0 | 0.056818
35191319 |  | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | SH | 0 | 1.1354 | 0 | 1.1354 | 0 | 0 | 0 | 0 | 0 | 1.1354 | 0 | 1.1354 | 0 | 0 | 0 | 0
35217272 |  | 103451101 | KESWICK 1101 | KESWICK 11011586 | SH | 0.014773 | 0.28466 | 0 | 0.29943 | 0 | 0 | 0 | 0 | 0.014773 | 0.28466 | 0 | 0.29943 | 0 | 0 | 0 | 0
35226630 |  | 103451101 | KESWICK 1101 | KESWICK 11011586 | SH | 1.4138 | 0 | 0.033523 | 1.4473 | 0 | 0 | 0 | 0 | 1.4138 | 0 | 0.033523 | 1.4473 | 0 | 0 | 0 | 0
35225595 |  | 42561107 | FULTON 1107 | FULTON 1107604 | SH | 0.8375 | 0 | 0 | 0.8375 | 0.11629 | 0 | 0 | 0.11629 | 0.72121 | 0 | 0 | 0.72121 | 0 | 0 | 0 | 0
35225597 |  | 42561107 | FULTON 1107 | FULTON 1107604 | SH | 0.79356 | 0 | 0 | 0.79356 | 0 | 0 | 0 | 0 | 0.79356 | 0 | 0 | 0.79356 | 0 | 0 | 0 | 0
35225598 |  | 42561107 | FULTON 1107 | FULTON 1107604 | SH | 0.9053 | 0 | 0 | 0.9053 | 0 | 0 | 0 | 0 | 0.9053 | 0 | 0 | 0.9053 | 0 | 0 | 0 | 0
35192292 |  | 42561107 | FULTON 1107 | FULTON 1107604 | SH | 0.19489 | 1.7848 | 0 | 1.9797 | 0 | 0 | 0 | 0 | 0.19489 | 1.7848 | 0 | 1.9797 | 0 | 0 | 0 | 0
31334291 |  | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | SH | 0.51326 | 0 | 0.13598 | 0.64924 | 0 | 0 | 0 | 0 | 0.51326 | 0 | 0.13598 | 0.64924 | 0 | 0 | 0 | 0
35231626 |  | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | SH | 0.78295 | 0 | 0.64962 | 1.4326 | 0 | 0 | 0 | 0 | 0.78295 | 0 | 0.60417 | 1.3871 | 0.045455 | 0 | 0 | 0.045455
35231630 |  | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | SH | 0.35663 | 0 | 0 | 0.35663 | 0 | 0 | 0 | 0 | 0.35663 | 0 | 0 | 0.35663 | 0 | 0 | 0 | 0
35231631 |  | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | SH | 0.44867 | 0 | 0 | 0.44867 | 0 | 0 | 0 | 0 | 0.36439 | 0 | 0 | 0.36439 | 0.08428 | 0 | 0 | 0.08428
35057018 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | SH | 0.22367 | 4.1256 | 0 | 4.3492 | 0 | 0 | 0 | 0 | 0.22367 | 4.1256 | 0 | 4.3492 | 0 | 0 | 0 | 0
35056733 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | SH | 1.7455 | 0.57576 | 0 | 2.3212 | 0 | 0 | 0 | 0 | 1.6231 | 0 | 0 | 1.6231 | 0.12235 | 0.57576 | 0 | 0.69811
35109541 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | SH | 2.8136 | 0.37955 | 0 | 3.1932 | 0 | 0 | 0 | 0 | 2.2008 | 0.04072 | 0 | 2.2415 | 0.57216 | 0.37955 | 0 | 0.9517
35109546 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | SH | 2.3513 | 0.44621 | 0 | 2.7975 | 0 | 0 | 0 | 0 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973
35192290 |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | SH | 5.0519 | 0 | 0 | 5.0519 | 2.8996 | 0 | 0 | 2.8996 | 2.1523 | 0 | 0 | 2.1523 | 0 | 0 | 0 | 0
35192291 |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | SH | 0.029167 | 1.0148 | 0 | 1.0439 | 0 | 0 | 0 | 0 | 0.029167 | 1.0148 | 0 | 1.0439 | 0 | 0 | 0 | 0
35026643 |  | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | SH | 1.0733 | 0 | 0 | 1.0733 | 0 | 0 | 0 | 0 | 0.2928 | 0 | 0 | 0.2928 | 0.78049 | 0 | 0 | 0.78049
35219286 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | SH | 3.4386 | 0 | 0 | 3.4386 | 0 | 0 | 0 | 0 | 3.4386 | 0 | 0 | 3.4386 | 0 | 0 | 0 | 0
35241072 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | SH | 3.4682 | 0 | 0.15985 | 3.628 | 0 | 0 | 0 | 0 | 3.4682 | 0 | 0.15985 | 3.628 | 0 | 0 | 0 | 0
35259511 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | SH | 2.667 | 0 | 0 | 2.667 | 0 | 0 | 0 | 0 | 2.667 | 0 | 0 | 2.667 | 0 | 0 | 0 | 0
35259515 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | SH | 2.517 | 0 | 0 | 2.517 | 0 | 0 | 0 | 0 | 2.517 | 0 | 0 | 2.517 | 0 | 0 | 0 | 0
35259516 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | SH | 0 | 0.19489 | 0 | 0.19489 | 0 | 0 | 0 | 0 | 0 | 0.19489 | 0 | 0.19489 | 0 | 0 | 0 | 0
35241071 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041582 | SH | 2.0297 | 0 | 0.21042 | 2.2402 | 0 | 0 | 0 | 0 | 2.0297 | 0 | 0.21042 | 2.2402 | 0 | 0 | 0 | 0
35241073 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 110449024 | SH | 3.8303 | 0 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 0 | 3.8303 | 0 | 0 | 0 | 0
35259517 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 110449024 | SH | 4.847 | 0 | 0 | 4.847 | 0 | 0 | 0 | 0 | 4.847 | 0 | 0 | 4.847 | 0 | 0 | 0 | 0
35232442 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | SH | 3.1608 | 0 | 0 | 3.1608 | 0 | 0 | 0 | 0 | 3.1608 | 0 | 0 | 3.1608 | 0 | 0 | 0 | 0
35232444 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | SH | 3.3822 | 0 | 0 | 3.3822 | 1.2443 | 0 | 0 | 1.2443 | 2.1379 | 0 | 0 | 2.1379 | 0 | 0 | 0 | 0
35232445 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | SH | 2.6036 | 0 | 0 | 2.6036 | 0.45246 | 0 | 0 | 0.45246 | 2.1511 | 0 | 0 | 2.1511 | 0 | 0 | 0 | 0
35232960 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | SH | 2.8663 | 0 | 0 | 2.8663 | 0 | 0 | 0 | 0 | 2.8663 | 0 | 0 | 2.8663 | 0 | 0 | 0 | 0
35240160 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045310 | SH | 3.9845 | 0 | 0.041288 | 4.0258 | 0 | 0 | 0 | 0 | 3.9845 | 0 | 0.041288 | 4.0258 | 0 | 0 | 0 | 0
35249871 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045310 | SH | 1.9297 | 0 | 0 | 1.9297 | 0 | 0 | 0 | 0 | 1.9297 | 0 | 0 | 1.9297 | 0 | 0 | 0 | 0
35249872 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045310 | SH | 2.7057 | 0 | 0 | 2.7057 | 0 | 0 | 0 | 0 | 2.7057 | 0 | 0 | 2.7057 | 0 | 0 | 0 | 0
35249876 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21046210 | SH | 3.7142 | 0 | 0 | 3.7142 | 0 | 0 | 0 | 0 | 0.94489 | 0 | 0 | 0.94489 | 2.7693 | 0 | 0 | 2.7693
35219097 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | SH | 2.4733 | 0 | 0 | 2.4733 | 0 | 0 | 0 | 0 | 2.4733 | 0 | 0 | 2.4733 | 0 | 0 | 0 | 0
35249996 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410030 | SH | 1.8127 | 0 | 0 | 1.8127 | 0 | 0 | 0 | 0 | 1.8127 | 0 | 0 | 1.8127 | 0 | 0 | 0 | 0
35249997 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410030 | SH | 1.9303 | 0 | 0 | 1.9303 | 0 | 0 | 0 | 0 | 1.9303 | 0 | 0 | 1.9303 | 0 | 0 | 0 | 0
35249998 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410030 | SH | 3.4638 | 0 | 0 | 3.4638 | 0 | 0 | 0 | 0 | 3.3981 | 0 | 0 | 3.3981 | 0.06572 | 0 | 0 | 0.06572
35243452 |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410030 | SH | 3.3856 | 0 | 0 | 3.3856 | 0 | 0 | 0 | 0 | 3.3856 | 0 | 0 | 3.3856 | 0 | 0 | 0 | 0
35145522 |  | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | SH | 0 | 2.7455 | 0 | 2.7455 | 0 | 0 | 0 | 0 | 0 | 2.7455 | 0 | 2.7455 | 0 | 0 | 0 | 0
35223062 |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | SH | 0.11402 | 0 | 0 | 0.11402 | 0 | 0 | 0 | 0 | 0.11402 | 0 | 0 | 0.11402 | 0 | 0 | 0 | 0
35115152 |  | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | SH | 1.6023 | 0 | 0 | 1.6023 | 0.83201 | 0 | 0 | 0.83201 | 0.77027 | 0 | 0 | 0.77027 | 0 | 0 | 0 | 0
35223036 |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | SH | 0 | 0.027841 | 0.018371 | 0.046212 | 0 | 0 | 0 | 0 | 0 | 0.027841 | 0.018371 | 0.046212 | 0 | 0 | 0 | 0
35223030 |  | 103191101 | BANGOR 1101 | BANGOR 1101CB | SH | 0.28352 | 1.2661 | 0 | 1.5496 | 0 | 0 | 0 | 0 | 0.28352 | 1.1364 | 0 | 1.4199 | 0 | 0.12973 | 0 | 0.12973
35052731 |  | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | SH | 1.3826 | 0 | 0 | 1.3826 | 0.57917 | 0 | 0 | 0.57917 | 0.80341 | 0 | 0 | 0.80341 | 0 | 0 | 0 | 0
35113950 |  | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | SH | 3.4441 | 0 | 0 | 3.4441 | 0 | 0 | 0 | 0 | 3.3188 | 0 | 0 | 3.3188 | 0.12538 | 0 | 0 | 0.12538
35113951 |  | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | SH | 2.3515 | 0 | 0 | 2.3515 | 0 | 0 | 0 | 0 | 2.3515 | 0 | 0 | 2.3515 | 0 | 0 | 0 | 0
35254078 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101CB | SH | 2.0998 | 0 | 0 | 2.0998 | 0 | 0 | 0 | 0 | 2.0998 | 0 | 0 | 2.0998 | 0 | 0 | 0 | 0
35277926 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101CB | SH | 3.4381 | 0 | 0 | 3.4381 | 0 | 0 | 0 | 0 | 2.1538 | 0 | 0 | 2.1538 | 1.2843 | 0 | 0 | 1.2843
35277927 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101CB | SH | 2.6888 | 0 | 0 | 2.6888 | 0 | 0 | 0 | 0 | 2.6888 | 0 | 0 | 2.6888 | 0 | 0 | 0 | 0
35278096 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | SH | 1.2744 | 0 | 0 | 1.2744 | 0 | 0 | 0 | 0 | 1.2744 | 0 | 0 | 1.2744 | 0 | 0 | 0 | 0
35278097 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | SH | 1.286 | 0 | 0.20095 | 1.4869 | 0 | 0 | 0 | 0 | 0.66345 | 0 | 0 | 0.66345 | 0.82348 | 0 | 0 | 0.82348
35278098 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | SH | 1.5273 | 0 | 0 | 1.5273 | 0 | 0 | 0 | 0 | 1.5273 | 0 | 0 | 1.5273 | 0 | 0 | 0 | 0
35254246 |  | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | SH | 2.6712 | 0 | 0 | 2.6712 | 0 | 0 | 0 | 0 | 2.6712 | 0 | 0 | 2.6712 | 0 | 0 | 0 | 0