## Cover Sheet Tables 1-12
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines Appendix D, Section 1.2
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | Liberty
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2023
Reporting Period quarter |  | Q4
Date Modified |  | 2024-01-31

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail | Comments
Liberty | 2024-02-01 | Project |  |  | Covered conductor installation |  |  | Grid Design, Operations, and Maintenance | 8.1 | Covered conductor installation |  | 8.1.2.1 | WMP-GDOM-GH-01 |  | 144 |  |  | Circuit Miles | 5.72 | 0 | 0 | 0 | 5.72 | 0 | 0 | 0 | 5.65 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Undergrounding of electric lines and/or equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | WMP-GDOM-GH-02 |  | 149 |  |  | Circuit Miles | 1.37 | 0 | 0 | 0.12 | 1.37 | 0 | 0 | 0.12 | 0.12 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Distribution pole replacements and reinforcements |  |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution pole replacements and reinforcements |  | 8.1.2.3 | WMP-GDOM-GH-03 |  | 150 |  |  | Poles | 200 | 0 | 0 | 125 | 200 | 6 | 22 | 214 | 292 | - |  |  |  |  | In progress
Liberty | 2024-02-01 |  |  |  | Transmission pole/tower replacements and reinforcements |  |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission pole/tower replacements and reinforcements |  | 8.1.2.4 | WMP-GDOM-GH-04 |  | 151 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | -
Liberty | 2024-02-01 | Project |  |  | Traditional overhead hardening |  |  | Grid Design, Operations, and Maintenance | 8.1 | Traditional overhead hardening |  | 8.1.2.5 | WMP-GDOM-GH-05 |  | 151 |  |  | Circuit Miles | 4 | 0 | 0 | 2 | 4 | 0 | 9.2 | 9.2 | 9.2 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Pilot |  |  | Emerging grid hardening technology installations and pilot progress |  |  | Grid Design, Operations, and Maintenance | 8.1 | Emerging grid hardening technology installations and pilot progress |  | 8.1.2.6 | WMP-GDOM-GH-06 |  | 152 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Microgrids |  |  | Grid Design, Operations, and Maintenance | 8.1 | Microgrids |  | 8.1.2.7 | WMP-GDOM-GH-07 |  | 154 |  |  | Microgrids | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Installation of system automation equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Installation of system automation equipment |  | 8.1.2.8 | WMP-GDOM-GH-08 |  | 155 |  |  | Automatic Reclosers | 8 | 0 | 0 | 4 | 8 | 0 | 0 | 4 | 5 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Line removal (in HFTD) |  |  | Grid Design, Operations, and Maintenance | 8.1 | Line removal (in HFTD) |  | 8.1.2.9 | WMP-GDOM-GH-09 |  | 156 |  |  | Circuit Miles | - | - | - | - | - | - | - | 0.51 | 0.51 | - |  |  |  |  | In progress
Liberty | 2024-02-01 |  |  |  | Other grid topology improvements to minimize risk of ignitions |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | WMP-GDOM-GH-10 |  | 156 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | -
Liberty | 2024-02-01 |  |  |  | Other grid topology improvements to mitigate or reduce PSPS events |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | WMP-GDOM-GH-11 |  | 157 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | -
Liberty | 2024-02-01 |  |  |  | Other technologies and systems not listed above: |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other technologies and systems not listed above: |  | 8.1.2.12 | WMP-GDOM-GH-12 |  | 157 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | -
Liberty | 2024-02-01 | Project |  |  | Tree attachment removals |  |  | Grid Design, Operations, and Maintenance | 8.1 | Tree attachment removals |  | 8.1.2.12 | WMP-GDOM-GH-12a |  | 157 |  |  | Tree Attachments | 60 | 0 | 15 | 30 | 60 | 0 | 13 | 23 | 37 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Expulsion fuse replacement |  |  | Grid Design, Operations, and Maintenance | 8.1 | Expulsion fuse replacement |  | 8.1.2.12 | WMP-GDOM-GH-12b |  | 157 |  |  | Expulsion Fuses | 3800 | - | - | - | 3800 | - | - | 3052 | 4122 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Animal guards |  |  | Grid Design, Operations, and Maintenance | 8.1 | Animal guards |  | 8.1.2.12 | WMP-GDOM-GH-12c |  | 157 |  |  | Animal Guards | 4 | 0 | 1 | 3 | 4 | 0 | 4 | 4 | 4 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | CalFIRE exempt hardware |  |  | Grid Design, Operations, and Maintenance | 8.1 | CalFIRE exempt hardware |  | 8.1.2.12 | WMP-GDOM-GH-12d |  | 157 |  |  | CalFIRE Exempt Hardware | - | - | - | - | - |  | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Open wire/grey wire |  |  | Grid Design, Operations, and Maintenance | 8.1 | Open wire/grey wire |  | 8.1.2.12 | WMP-GDOM-GH-12e |  | 157 |  |  | Circuit Miles | 2.548 | 0 | 0 | 0 | 2.548 | 0 | 0 | 4.43 | 4.43 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Substation Equipment Replacement |  |  | Grid Design, Operations, and Maintenance | 8.1 | Substation Equipment Replacement |  | 8.1.2.12 | WMP-GDOM-GH-12f |  | 157 |  |  | TBD | TBD | - | - | - | - | - | 1 | 1 | 2 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Detailed inspections of distribution electric lines and equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Detailed inspections of distribution electric lines and equipment |  | 8.1.3.1 | WMP-GDOM-AI-01 |  | 164 |  |  | Circuit Miles | 40.3 | 0 | 0 | 0 | 40.3 | 0 | 0 | 167.65 | 181.4 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Intrusive pole inspections |  |  | Grid Design, Operations, and Maintenance | 8.1 | Intrusive pole inspections |  | 8.1.3.2 | WMP-GDOM-AI-02 |  | 164 |  |  | Poles | 2867 | 0 | 0 | 1500 | 2867 | 0 | 0 | 2859 | 2859 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Patrol inspections of distribution electric lines and equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Patrol inspections of distribution electric lines and equipment |  | 8.1.3.3 | WMP-GDOM-AI-03 |  | 165 |  |  | Circuit Miles | 701.5 | 0 | 0 | 701.5 | 701.5 | 0 | 87 | 87 | 702 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Other discretionary inspections of distribution electric lines and equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other discretionary inspections of distribution electric lines and equipment |  | 8.1.3.4 | WMP-GDOM-AI-04 |  | 165 |  |  | Circuit Miles | TBD | - | - | - | - | - | - |  | 0.1 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Quality assurance / quality control of inspections |  |  | Grid Design, Operations, and Maintenance | 8.1 | Quality assurance / quality control of inspections |  | 8.1.3.5 | WMP-GDOM-AI-05 |  | 166 |  |  | % of Detailed Inspections | 0.01 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 12 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Substation inspections |  |  | Grid Design, Operations, and Maintenance | 8.1 | Substation inspections |  | 8.1.3.6 | WMP-GDOM-AI-06 |  | 166 |  |  | Substations | 42 | 11 | 24 | 38 | 42 | 10 | 10 | 32 | 44 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Equipment maintenance and repair |  |  | Grid Design, Operations, and Maintenance | 8.1 | Equipment maintenance and repair |  | 8.1.4 | WMP-GDOM-MR-01 |  | 166 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Equipment settings to reduce wildfire risk |  |  | Grid Design, Operations, and Maintenance | 8.1 | Equipment settings to reduce wildfire risk |  | 8.1.8.1 | WMP-GDOM-GO-01 |  | 174 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Grid response procedures and notifications |  |  | Grid Design, Operations, and Maintenance | 8.1 | Grid response procedures and notifications |  | 8.1.8.2 | WMP-GDOM-GO-02 |  | 176 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Personnel work procedures and training in conditions of elevated fire risk |  |  | Grid Design, Operations, and Maintenance | 8.1 | Personnel work procedures and training in conditions of elevated fire risk |  | 8.1.8.3 | WMP-GDOM-GO-03 |  | 177 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Automatic recloser operations |  |  | Grid Design, Operations, and Maintenance | 8.1 | Automatic recloser operations |  | 8.1.8.1 | WMP-GDOM-GO-04 |  | 174 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | -
Liberty | 2024-02-01 | Project |  |  | Asset Management and Inspection Enterprise System |  |  | Grid Design, Operations, and Maintenance | 8.1 | Asset Management and Inspection Enterprise System |  | 8.1.5 | WMP-GDOM-GO-05 |  | 169 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Vegetation Management Inspection Program - Detailed |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Inspection Program - Detailed |  | 8.2.2.1 | WMP-VM-INSP-01 |  | 193 |  |  | Line Miles | 220 | 38.9 | 88 | 151 | 220 | 50.4 | 112.5 | 193.8 | 236 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Vegetation Management Inspection Program - Patrol |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Inspection Program - Patrol |  | 8.2.2.2 | WMP-VM-INSP-02 |  | 193 |  |  | Line Miles | - | - | - | - | - | 63.1 | 66.8 | 78 | 78 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Vegetation Management Inspection Program - LiDar |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Inspection Program - LiDar |  | 8.2.2.3 | WMP-VM-INSP-03 |  | 193 |  |  | Line Miles | 700 | 0 | 0 | 700 | 700 | 0 | 0 | 707 | 707 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Pole Clearing |  |  | Vegetation Management & Inspections | 8.2 | Pole Clearing |  | 8.2.3.1 | WMP-VM-VFM-01 |  | 205 |  |  | Subject Poles | 4900 | 0 | 900 | 4060 | 4960 | 0 | 0 | 2232 | 4957 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Wood and Slash Management |  |  | Vegetation Management & Inspections | 8.2 | Wood and Slash Management |  | 8.2.3.2 | WMP-VM-VFM-02 |  | 205 |  |  | Acres | 280 | 0 | 93 | 93 | 280 | 0 | 50 | 255.17 | 625.4 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Substation Defensible Space |  |  | Vegetation Management & Inspections | 8.2 | Substation Defensible Space |  | 8.2.3.5 | WMP-VM-VFM-03 |  | 213 |  |  | Substation Treatments | 12 | 0 | 0 | 0 | 12 | 0 | 10 | 12 | 22 | - |  |  |  |  | In progress | [7 empty] | Updated Unit from Substations to Substation Treatments in Q4 submission.
Liberty | 2024-02-01 | Program |  |  | Fire-Resilient Right-of-Ways |  |  | Vegetation Management & Inspections | 8.2 | Fire-Resilient Right-of-Ways |  | 8.2.3.7 | WMP-VM-VFM-04 |  | 214 |  |  | Line Miles | - | - | - | - | - | - | - |  | 13.7 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Clearance |  |  | Vegetation Management & Inspections | 8.2 | Clearance |  | 8.2.3.3 | WMP-VM-VFM-05 |  | 207 |  |  | Line Miles | 670.8 | - | - | - | 670.8 | 239 | 531.7 | 707 | 707 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Fall-In Mitigation |  |  | Vegetation Management & Inspections | 8.2 | Fall-In Mitigation |  | 8.2.3.4 | WMP-VM-VFM-06 |  | 209 |  |  | Line Miles | 220 | 0 | 70 | 150 | 220 | 0 | 0.8 | 176.8 | 313 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | High-Risk Species |  |  | Vegetation Management & Inspections | 8.2 | High-Risk Species |  | 8.2.3.6 | WMP-VM-VFM-07 |  | 214 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Emergency Response Vegetation Management |  |  | Vegetation Management & Inspections | 8.2 | Emergency Response Vegetation Management |  | 8.2.3.8 | WMP-VM-VFM-08 |  | 215 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Vegetation Management Enterprise System |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Enterprise System |  | 8.2.4 | WMP-VM-ESG-01 |  | 217 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Quality Assurance and Quality Control |  |  | Vegetation Management & Inspections | 8.2 | Quality Assurance and Quality Control |  | 8.2.5 | WMP-VM-QAQC-01 |  | 222 |  |  | Line Miles | 229 | 0 | 114 | 171 | 229 | 2.39 | 200.5 | 299.73 | 299.7 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Environmental monitoring systems |  |  | Situational Awareness & Forecasting | 8.3 | Environmental monitoring systems |  | 8.3.2 | WMP-SA-01 |  | 242 |  |  | Weather Stations | 5 | - | - | - | 5 | 0 | 1 | 2 | 5 | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Grid monitoring systems |  |  | Situational Awareness & Forecasting | 8.3 | Grid monitoring systems |  | 8.3.3 | WMP-SA-02 |  | 246 |  |  | Circuits with Fault Indicators | 10 | 0 | 3 | 6 | 10 | 0 | 0 | 0 | 0 | - |  |  |  |  | In progress | [7 empty] | Updated Unit from Circuits to Circuits with Fault Indicators in Q4 submission.
Liberty | 2024-02-01 | Pilot |  |  | Fire detection and alarm systems |  |  | Situational Awareness & Forecasting | 8.3 | Fire detection and alarm systems |  | 8.3.4 | WMP-SA-03 |  | 249 |  |  | DFA Units | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Weather forecasting |  |  | Situational Awareness & Forecasting | 8.3 | Weather forecasting |  | 8.3.5 | WMP-SA-04 |  | 253 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Fire Potential Index |  |  | Situational Awareness & Forecasting | 8.3 | Fire Potential Index |  | 8.3.6 | WMP-SA-05 |  | 258 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | Completed
Liberty | 2024-02-01 | Project |  |  | Ignition likelihood calculation |  |  | Situational Awareness & Forecasting | 6.2 | Ignition likelihood calculation |  | 6.2.2.1 | WMP-SA-06 |  | 73 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Project |  |  | Ignition consequence calculation |  |  | Situational Awareness & Forecasting | 6.2 | Ignition consequence calculation |  | 6.2.2.2 | WMP-SA-07 |  | 75 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Wildfire and PSPS emergency preparedness plan |  |  | Emergency Preparedness | 8.4 | Wildfire and PSPS emergency preparedness plan |  | 8.4.2 | WMP-EP-01 |  | 268 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | Completed
Liberty | 2024-02-01 | Program |  |  | Collaboration and coordination with public safety partners |  |  | Emergency Preparedness | 8.4 | Collaboration and coordination with public safety partners |  | 8.4.3 | WMP-EP-02 |  | 287 |  |  | - | - | - | - | - | - | - | - |  |  | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards | Held Tree Mortality Wildfire Stakeholder meeting. Met with Nevada County Wildfire Coordinator. Participated in an Eastern Sierra Access and Functional Needs Workgroup. Liberty's Business and Community Development Manager voted onto Community Action Council of El Dorado County. Participated in AFN Statewide Council and AFN Working Group meetings. | Held Public Safety Partner Workshop on 4/13/2023. |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Public notification and communication strategy |  |  | Emergency Preparedness | 8.4 | Public notification and communication strategy |  | 8.4.4 | WMP-EP-03 |  | 305 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | Completed
Liberty | 2024-02-01 | Program |  |  | Preparedness and planning for service restoration |  |  | Emergency Preparedness | 8.4 | Preparedness and planning for service restoration |  | 8.4.5 | WMP-EP-04 |  | 314 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | Completed
Liberty | 2024-02-01 | Program |  |  | Customer support in wildfire and PSPS emergencies |  |  | Emergency Preparedness | 8.4 | Customer support in wildfire and PSPS emergencies |  | 8.4.6 | WMP-EP-05 |  | 319 |  |  | - | - | - | - | - | - | - | - |  |  | Conduct Incident Command Training for all identified IC members and hold a Virtual PSPS Tabletop exercise; Continued implementation of Liberty’s 2022 AFN Plan; Continued maintenance of emergency response plans; Enhanced documentation and use of lessons learned to update plans. | Held Palisades Tahoe Cup Tabletop Exercise. | Held table-top exercise on 5/25/2023. Held full-scale exercise on 6/22/2023. |  |  | In progress
Liberty | 2024-02-01 |  |  |  | Learning after wildfire and PSPS events |  |  | Emergency Preparedness | 8.4 | Learning after wildfire and PSPS events |  |  | WMP-EP-06 |  | - |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  |  | Community Outreach and Engagement | 8.5 | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  | 8.5.2 | WMP-CO-01 |  | 329 |  |  | - | - | - | - | - | - | - | - |  |  | Continue to survey customers, CBOs, community partners and stakeholders to understand wildfire and PSPS awareness and the needs of customers. Strengthen and expand AFN CBO partnerships. Identify emerging channels and technologies to better communicate with customers, community and stakeholders. | Conducted planning for 2023 coordination with public safety partners, CBOs, and other stakeholders. Planned for 2023 community outreach events. | 20 in-person events, 19 Virtual events, 4 hybrid events, and 38 rounds of emails, website posts, and social media posts focused on PSPS education and wildfire awareness, AFN outreach and CBO collaboration. 6 sets of direct mail & bill inserts and 4 sets of print and digital ads focused on customer and stakeholder outreach | 16 in-person events, 9 Virtual events, 1 hybrid event, and 51 rounds of emails, website posts, and social media posts focused on PSPS education and wildfire awareness, AFN outreach and CBO collaboration. 12 sets of direct mail & bill inserts and 4 sets of print and digital ads focused on customer and stakeholder outreach |  | In progress
Liberty | 2024-02-01 |  |  |  | Public engagement in WMP decision-making process |  |  | Community Outreach and Engagement | 8.5 | Public engagement in WMP decision-making process |  |  | WMP-CO-02 |  | - |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Engagement with AFN populations, local governments, and tribal communities |  |  | Community Outreach and Engagement | 8.5 | Engagement with AFN populations, local governments, and tribal communities |  | 8.5.3 | WMP-CO-03 |  | 335 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 | Program |  |  | Collaboration on local wildfire mitigation and planning |  |  | Community Outreach and Engagement | 8.5 | Collaboration on local wildfire mitigation and planning |  | 8.5.4 | WMP-CO-04 |  | 337 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Liberty | 2024-02-01 |  |  |  | Best practice sharing with other electrical corporations |  |  | Community Outreach and Engagement | 8.5 | Best practice sharing with other electrical corporations |  | 8.5.5 | WMP-CO-05 |  | 341 |  |  | - | - | - | - | - | - | - | - |  |  | - |  |  |  |  | In progress
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | Liberty | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-01-31 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | [15 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
| Table 2: Performance Metrics | [8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1 | 0 | 0 | 6 | 3 | 0 | 0 | 2 | 13 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 18 | 8 | 9 | 13 | 18 | 11 | 5 | 79 | 4 | 33 | 9 | 147 | 54 | 8 | 14 | 9 | [11 empty] | Number of events | 104 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 | 1 | 2 | 2 | 1 | 0 | 0 | 15 | 0 | 4 | 1 | 13 | 4 | 1 | 3 | 1 | [11 empty] | Number of events | 12 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 4 | 2 | 2 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 10 | 5 | 3 | 1 | 0 | [11 empty] | Number of events | 8 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 9 | 1 | 0 | 2 | 5 | 3 | 1 | 30 | 0 | 6 | 1 | 36 | 32 | 2 | 1 | 2 | [11 empty] | Number of events | 22 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | [11 empty] | Number of events | 5 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | [11 empty] | Number of events | 2 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 3 | 7 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 3 | 0 | 0 | 10 | 1 | 0 | 0 | 19 | 6 | 3 | 0 | 1 | 3 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 40 | 27 | 45 | 48 | 39 | 34 | 33 | 257 | 44 | 50 | 45 | 120 | 110 | 21 | 23 | 34 | [11 empty] | Number of events | 76 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 | 1 | 4 | 4 | 2 | 1 | 3 | 28 | 1 | 8 | 6 | 8 | 5 | 2 | 5 | 2 | [11 empty] | Number of events | 7 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 6 | 5 | 6 | 11 | 7 | 2 | 6 | 18 | 4 | 8 | 5 | 10 | 6 | 4 | 6 | 0 | [11 empty] | Number of events | 7 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 3 | 3 | 1 | 3 | 6 | 4 | 3 | 0 | 1 | 19 | 2 | 59 | 41 | 1 | 1 | 6 | [11 empty] | Number of events | 36 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 8 | 4 | 0 | 0 | 1 | [11 empty] | Number of events | 7 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events | 0 in NWS Winter Storms in Q4 2022
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 3 | 2 | 0 | 0 | 0 | [11 empty] | Number of events | 2 in NWS Winter Storms in Q4 2022
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | [8 empty] | 1.5 | 1.5 | 1.5 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0.25 | 0.25 | 0.25 | Number of events
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 492 | 1008 | 3864 | 3648 | 3480 | 5496 | 8400 | 3384 | 2304 | 1224 | 1704 | 1584 | 504 | 816 | 3336 | 2712 | [11 empty] | hours
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 1752 | 3672 | 5592 | 6408 | 9997 | 10632 | 9744 | 8832 | 4536 | 5832 | 7344 | 5112 | 1560 | 2040 | 5530.8 | 6654 | [11 empty] | hours
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 384 | 3432 | 1752 | 2472 | 528 | 1656 | 2712 | 2472 | 4800 | 144 | 2532 | 2880 | 156 | 168 | 3348 | 1704 | [11 empty] | hours
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 456 | 4008 | 5376 | 3302 | 2668 | 5239 | 8976 | 2856 | 5592 | 2491 | 8448 | 4164 | 728.4 | 701 | 3514.8 | 6878 | [11 empty] | hours
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 144 | 984 | 1512 | 1368 | 8436 | 4584 | 8472 | 2976 | 84 | 192 | 2472 | 2484 | 312 | 504 | 3504 | 6528 | [11 empty] | hours
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 144 | 3062 | 4274 | 4221 | 9792 | 10152 | 10272 | 4691 | 6728 | 7008 | 4968 | 10602 | 369.6 | 1865 | 3957.6 | 6780 | [11 empty] | hours
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 168 | 0 | 876 | 1104 | 2304 | 5280 | 6068 | 3540 | 144 | 288 | 3696 | 2160 | 1608 | 1392 | 1908 | 1776 | [11 empty] | hours
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 168 | 0 | 1224 | 1794 | 3081 | 6168 | 6537 | 4089 | 5661 | 312 | 5112 | 4056 | 1837.2 | 1488 | 4512 | 3593 | [11 empty] | hours
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 2160 | 0 | 5112 | 2448 | 0 | 0 | 144 | 48 | 1944 | 0 | 2424 | 4488 | 5064 | [11 empty] | hours
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 2856 | 0 | 5112 | 5169 | 0 | 0 | 2784 | 48 | 3192 | 0 | 2544 | 4872 | 6350 | [11 empty] | hours
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 0 | 1248 | 840 | 6648 | 0 | 0 | 6240 | 5040 | 144 | 504 | 2952 | 3936 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 0 | 3518 | 1440 | 7440 | 0 | 0 | 6528 | 5112 | 192 | 926 | 4080 | 4099 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 192 | 60 | 2208 | 6168 | 7200 | 10464 | 12048 | 13896 | 16728 | 17040 | 0 | 0 | 0 | 26904 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 1485.6 | 648 | 2229 | 6168 | 7200 | 10488 | 12112.8 | 13896 | 16728 | 19070 | 0 | 0 | 0 | 26904 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18288 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18288 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 432 | 888 | 0 | 0 | 7104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | [11 empty] | hours
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 1248 | 888 | 0 | 0 | 7104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | [11 empty] | hours
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours |  | No data relevent to requested intersections
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 384 | 504 | 2232 | 5832 | 7224 | 9336 | 11244 | 13548 | 15936 | 17340 | 18840 | 0 | 24384 | 12384 | 12288 | [11 empty] | hours
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 384 | 1128 | 4920 | 8112 | 9338.4 | 10822.8 | 12096 | 14383.2 | 17176.8 | 18777.6 | 20112 | 0 | 26328 | 27728 | 20875 | [11 empty] | hours
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 936 | 2832 | 4380 | 7836 | 10524 | 12432 | 14340 | 15264 | 18528 | 0 | 0 | 0 | 13152 | 0 | [11 empty] | hours
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 936 | 4296 | 6362.4 | 8214 | 11082 | 12432 | 14437.2 | 15264 | 18981.6 | 0 | 0 | 0 | 13152 | 0 | [11 empty] | hours
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 0 | 96 | 3768 | 5412 | 8112 | 10656 | 0 | 14136 | 16620 | 20448 | 0 | 0 | 0 | 12216 | 48 | [11 empty] | hours
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 0 | 3081.6 | 3768 | 6336 | 9072 | 10677.6 | 0 | 14136 | 17127.6 | 21126 | 0 | 0 | 0 | 12216 | 91 | [11 empty] | hours
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20016 | 0 | 0 | 13512 | 0 | [11 empty] | hours
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20016 | 0 | 0 | 13795 | 0 | [11 empty] | hours
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20016 | 0 | 0 | 0 | 0 | [11 empty] | hours
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20016 | 0 | 0 | 0 | 0 | [11 empty] | hours
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 0 | 360 | 3168 | 3024 | 7560 | 10512 | 12024 | 13752 | 14832 | 18336 | 20004 | 22944 | 24708 | 26424 | 28368 | [11 empty] | hours
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 20.4 | 810 | 3168 | 6216 | 9206.4 | 11028 | 12552 | 15321.6 | 17966.4 | 18672 | 21336 | 23448 | 25176 | 28968 | 29376 | [11 empty] | hours
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 1128 | 1740 | 6144 | 6912 | 9912 | 12264 | 13968 | 15168 | 18264 | 19944 | 22416 | 0 | 27600 | 28704 | [11 empty] | hours
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 1171.2 | 2178 | 6144 | 6912 | 9912 | 12432 | 14304 | 17732.4 | 18859.2 | 20112 | 22416 | 0 | 28536 | 29299 | [11 empty] | hours
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 0 | 0 | 3792 | 0 | 7944 | 0 | 12048 | 13680 | 16440 | 17880 | 0 | 0 | 0 | 28296 | 28824 | [11 empty] | hours
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 0 | 0 | 3792 | 0 | 7944 | 0 | 12063.6 | 13704 | 16440 | 17880 | 0 | 0 | 0 | 28536 | 28845 | [11 empty] | hours
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20016 | 0 | 0 | 13752 | 0 | [11 empty] | hours
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20016 | 0 | 0 | 13790 | 0 | [11 empty] | hours
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20112 | 0 | 0 | 0 | 0 | [11 empty] | hours
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20112 | 0 | 0 | 0 | 0 | [11 empty] | hours
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | hours
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 2195 | 4390 | 5724 | 6789 | 7131 | 4656 | 4761 | 4839 | 5312 | 4332 | 5037 | 3407 | 3333 | 2425 | 2829 | 971 | [8 empty] | 4881 | 4881 | 4881 | Number of orders
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 56 | 7 | 4 | [11 empty] | Number of orders
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2050 | 7210 | 7365 | 7370 | 7437 | 7446 | 7809 | 8916 | 10284 | 10526 | 10547 | 10465 | 10409 | 10039 | 9318 | [8 empty] | 8500 | 6700 | 5960 | Number of orders | 534 work orders were found to fall under vegetation management and were found to be fixed previously as a part of the Vegetation Management work orders.
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 71 | 332 | 340 | 340 | 346 | 346 | 405 | 431 | 431 | 431 | 431 | 401 | 924 | 937 | 767 | [8 empty] | 107.75 | 25 | 25 | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Hours |  | No data available at time of submission
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 6122 | 12229 | 686 | 68 | 324 | 32 | 663 | 2230 | 3037 | 642 | 78 | 0 | 0 | 1113 | 140 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 589 | [11 empty] | # of circuit miles inspected by the utility | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 188.73 | 257.83 | 19.84 | 1.62 | 6.12 | 0.85 | 75.7 | 87.51 | 125.11 | 58.42 | 3.6 | 0 | 0 | 146.04 | 20.61 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [11 empty] | # of findings from these asset inspections | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 57 | 29 | 0 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | [11 empty] | # of findings from these asset inspections | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 193 | 863 | 6 | 0 | 7 | 1 | 57 | 156 | 352 | 64 | 0 | 0 | 0 | 188 | 32 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [11 empty] | # of findings from these asset inspections | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 1896 | 5302 | 127 | 5 | 79 | 9 | 291 | 704 | 1015 | 158 | 21 | 0 | 0 | 265 | 42 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 904 | 725 | 0 | 0 | 0 | 0 | 6 | 84 | 17 | 14 | 0 | 0 | 0 | 32 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 22.71 | 17.8 | 0 | 0 | 0 | 0 | 0.56 | 2.14 | 0.44 | 1.2 | 0 | 0 | 0 | 1.71 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 36 | 54 | 0 | 0 | 0 | 0 | 0 | 25 |  | 1 | 0 | 0 | 0 | 3 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 339 | 288 | 0 | 0 | 0 | 0 | 2 | 34 | 12 | 4 | 0 | 0 | 0 | 6 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 22 | 74 | 2 | 0 | 0 | 52 | 3 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 22.39 | 13.43 | 2.06 | 0 | 0.22 | 0.03 | 10.19 | 12.64 | 1.22 | 4.82 | 0.09 | 0 | 0 | 5.93 | 3.38 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 53 | 24 | 2 | 0 | 0 | 0 | 2 | 31 | 1 | 5 | 0 | 0 | 0 | 8 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 234 | 229 | 34 | 0 | 0 | 1 | 14 | 110 | 6 | 15 | 0 | 0 | 0 | 15 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 171 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.3 | [11 empty] | # of circuit miles inspected by the utility | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility | Currently we are not able to track patrol inspections by HFTD so we have bucketed all Patrol circuit miles into HFTD 2.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 12.43 | 0.29 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 54 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 7 | 26 | 2 | 1 | 1 | 44 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 1 | 21 | 29 | 46 | 130 | 78 | 158 | 194 | 68 | 67 | 34 | 0 | 8 | 47 | 12 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 | 5 | 7 | 1 | 30 | 52 | 71 | 243 | 478 | 253 | 132 | 51 | 21 | 53 | 631 | 109 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 0 | 1 | 40 | 19 | 5 | 6 | 4 | 2 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 0 | 2 | 6 | 1 | 1 | 1 | 183 | 49 | 20 | 6 | 1 | 1 | 0 | 53 | 16 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 0 | 5 | 1 | 3 | 20 | 3 | 0 | 1 | 2 | 6 | 1 | 0 | 0 | 1 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8 | 18 | 4 | 1 | 3 | 4 | 0 | 13 | 1 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 5 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 10 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 22147 | 0 | 0 | 178649 | 32904 | 0 | 0 | 209322 | 0 | 0 | 0 | 0 | 189491 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 2554 | 2189 | 2421 | 1750 | 795 | 1744 | 2488 | 1962 | 1109 | 1021 | 2998 | 715 | 1412 | 812 | 1857 | 301 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 179 | 252 | 453 | 792 | 656 | 378 | 383 | 173 | 330 | 346 | 578 | 243 | 101 | 528 | 529 | 265 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 103 | 158 | 344 | 357 | 253 | 123 | 192 | 126 | 156 | 166 | 204 | 156 | 10 | 17 | 56 | 22 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 886 | 0 | 0 | 1226 | 93 | 0 | 0 | 640 | 0 | 0 | 0 | 0 | 249 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 1514 | 852 | 934 | 604 | 415 | 853 | 1322 | 1261 | 757 | 775 | 2153 | 687 | 21 | 1 | 12 | 2 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 4392 | 0 | 0 | 24343 | 1244 | 0 | 0 | 25126 | 0 | 0 | 0 | 0 | 24439 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 92 | 66 | 37 | 10 | 6 | 83 | 90 | 12 | 61 | 150 | 24 | 6 | 94 | 9 | 82 | 65 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 19 | 14 | 0 | 28 | 4 | 4 | 42 | 1 | 16 | 18 | 0 | 20 | 1 | 11.25 | 5 | 6 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 11 | 1 | 0 | 25 | 3 | 3 | 22 | 1 | 16 | 7 | 0 | 19 | 0 | 2 | 5 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 54 | 0 | 0 | 33 | 5 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 22 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 60 | 22 | 23 | 10 | 6 | 60 | 64 | 6 | 28 | 87 | 22 | 3 | 0 | 0 | 3 | 4 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 | 0 | 0 | 617 | 0 | 0 | 13306 | 174 | 0 | 0 | 9903 | 0 | 0 | 0 | 0 | 4720 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | 228 | 684 | 666 | 438 | 425 | 301 | 163 | 55 | 64 | 10 | 5 | 5 | 5 | 0 | 1 | 8 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 16 | 32 | 663 | 55 | 77 | 35 | 26 | 46 | 17 | 1 | 14 | 1 | 3 | 0 | 0 | 1 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 14 | 7 | 494 | 45 | 36 | 23 | 13 | 33 | 12 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 | 0 | 0 | 31 | 0 | 0 | 183 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 6 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | 99 | 247 | 226 | 187 | 135 | 165 | 48 | 15 | 25 | 8 | 4 | 5 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 | 0 | 0 | 2 | 0 | 0 | 5085 | 0 | 0 | 0 | 5963 | 0 | 0 | 0 | 0 | 27910 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 0 | 41 | 214 | 63 | 0 | 23 | 66 | 189 | 171 | 137 | 286 | 65 | 14 | 86.5 | 530 | 2 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 21 | 4 | 36 | 3 | 5 | 0 | 0 | 11 | 4 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 5 | 4 | 34 | 3 | 5 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 0 | 40 | 210 | 46 | 0 | 8 | 22 | 189 | 125 | 123 | 188 | 135 | 0 | 0 | 3 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 | 0 | 0 | 6 | 0 | 0 | 1217 | 0 | 0 | 0 | 1276 | 0 | 0 | 0 | 0 | 2398 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 151 | 116.25 | 22 | 63 | 4 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 0 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 20.5 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 129 | 0 | 6 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 366 | 0 | 0 | 0 | 444 | 0 | 0 | 0 | 0 | 169 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | 66 | 14 | 16 | 37 | 3 | 22 | 9 | 0 | 52 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 1 | 0 | 61 | 1 | 0 | 99 | 5 | 1 | 6 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 1 | 0 | 39 | 0 | 0 | 9 | 2 | 1 | 6 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | 49 | 9 | 15 | 29 | 2 | 6 | 7 | 0 | 9 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Percentage of customers notified of evacuation |  | N/A
Note on A784: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: [Mention was removed] [Mention was removed] [Mention was removed] [Mention was removed] [Mention was removed] I believe I have updated Table 2 with all the VM data points. Please let me know if anything is missing. I also uploaded a new workbook to the files folder in Teams with the HFTD, Time Between inspection and completion, and the formulas used to calculate median and 95th percentile timing for inspection to work complete data. For the lidar inspection dates, I used the date the data was analyzed and the work order created and not the date the data was acquired or delivered to us. Let me know if you have any questions.

## Table 3
Utility | Liberty
Table No. | 3
Date Modified
[5 empty] | Actual | [7 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
Table 3: List and description of additional metrics |  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning

## Table 4
Utility | Liberty
Table No. | 4
Date Modified | 2024-01-31
Note: These columns are placeholders for future QR submissions.
Table 4: Weather patterns |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric type | # | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 2.62; 4: 0; 1: 0; 2: 0; 3: 0; 4: 0 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 0; 4: 0; 1: 0; 2: 0; 3: 0; 4: 0 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 4.15; 4: 0; 1: 0; 2: 0; 3: 0; 4: 0 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 1: 539.104; 2: 28.035; 3: 0; 4: 263.648; 1: 5.5; 2: 0; 3: 0; 4: 0 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 1: 66.112; 2: 0; 3: 0; 4: 31.316; 1: 0.182; 2: 0; 3: 0; 4: 0 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 1: 17.926; 2: 5.223; 3: 0; 4: 8.255; 1: 0; 2: 0; 3: 0; 4: 0 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 0; 4: 0; 1: 0; 2: 0; 3: 0; 4: 0 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 0; 4: 0; 1: 0; 2: 0; 3: 0; 4: 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 0; 4: 0; 1: 0; 2: 0; 3: 0; 4: 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 1: 0; 2: 8024.05; 3: 49707.66; 4: 858.57; 1: 0; 2: 0; 3: 16501.2; 4: 0 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 1: 0; 2: 507.43; 3: 4313.12; 4: 0; 1: 0; 2: 0; 3: 1522.3; 4: 0 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 1: 0; 2: 510.26; 3: 3987.09; 4: 81.19; 1: 0; 2: 0; 3: 1207.1; 4: 0 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)

## Table 5
| Utility | Liberty | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-01-31 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[8 empty] | Actual number of risk events | [15 empty] | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | 1 in NWS Winter Storms in Q4 2022
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 2; Actual number of risk events Q2: 8; Actual number of risk events Q3: 1; Actual number of risk events Q4: 18; Actual number of risk events Q1: 14; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 29 | 29 | 29 | # risk events (excluding ignitions) | 8 in NWS Winter Storms in Q4 2022
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions) | 3 in NWS Winter Storms in Q4 2022
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 10; Actual number of risk events Q1: 8; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | 0 in NWS Winter Storms in Q4 2022
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | 1 in NWS Winter Storms in Q4 2022
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | 1 in NWS Winter Storms in Q4 2022
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 7; Actual number of risk events Q4: 1 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 2; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 6 | 6 | 6 | # risk events (excluding ignitions) | 2 in NWS Winter Storms in Q4 2022
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 9; Actual number of risk events Q2: 21; Actual number of risk events Q3: 3; Actual number of risk events Q4: 59; Actual number of risk events Q1: 42; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 6 | 92 | 92 | 92 | # risk events (excluding ignitions) | 36 in NWS Winter Storms in Q4 2022
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 8; Actual number of risk events Q1: 4; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 11 | 11 | 11 | # risk events (excluding ignitions) | 7 in NWS Winter Storms in Q4 2022
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 3; Actual number of risk events Q2: 7; Actual number of risk events Q3: 9; Actual number of risk events Q4: 7; Actual number of risk events Q1: 11; Actual number of risk events Q2: 1; Actual number of risk events Q3: 2; Actual number of risk events Q4: 4 | 26 | 26 | 26 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 2; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 6 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4; Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 12; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 15 | 15 | 15 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 2; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 3; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4; Actual number of risk events Q1: 2; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3; Actual number of risk events Q1: 5; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 6; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 4; Actual number of risk events Q4: 1; Actual number of risk events Q1: 8; Actual number of risk events Q2: 1; Actual number of risk events Q3: 3; Actual number of risk events Q4: 5 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 10; Actual number of risk events Q1: 7; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 5; Actual number of risk events Q1: 4; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 5; Actual number of risk events Q1: 5; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions) | 5 in NWS Winter Storm in Q4 2022
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 7; Actual number of risk events Q2: 6; Actual number of risk events Q3: 2; Actual number of risk events Q4: 66; Actual number of risk events Q1: 62; Actual number of risk events Q2: 4; Actual number of risk events Q3: 5; Actual number of risk events Q4: 3 | 81 | 81 | 81 | # risk events (excluding ignitions) | 52 in NWS Winter Storm in Q4 2022
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 4; Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions) | 4 in NWS Winter Storm in Q4 2022
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 3; Actual number of risk events Q4: 2; Actual number of risk events Q1: 3; Actual number of risk events Q2: 5; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 4; Actual number of risk events Q2: 7; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 13 | 13 | 13 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 36; Actual number of risk events Q2: 21; Actual number of risk events Q3: 9; Actual number of risk events Q4: 10; Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 76 | 76 | 76 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 1; Actual number of risk events Q2: 3; Actual number of risk events Q3: 3; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes | [19 empty] | # risk events (excluding ignitions) |  | Liberty's outage data is captured at the distribution level (i.e., Liberty's outage management system receives records from the impacted distribution circuit)

## Table 6
| Utility | Liberty | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-01-31 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[7 empty] | Actual number of ignitions | [15 empty] | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.66667 | 0.66667 | 0.66667 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment/facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and brushing | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and brushing | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and brushing | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and brushing | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and brushing | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and brushing | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrestor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrestor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions

## Table 7
| Utility | Liberty
| Table No. | 7
| Date Modified | 2024-01-31
[7 empty] | Actual | [15 empty] | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 5.32; Actual Q2: 4.77; Actual Q3: 4.79; Actual Q4: 4.79; Actual Q1: 4.71; Actual Q2: 4.59; Actual Q3: 4.59; Actual Q4: 4.59 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 1.15; Actual Q2: 1.03; Actual Q3: 1.04; Actual Q4: 1.04; Actual Q1: 1.04; Actual Q2: 0.99; Actual Q3: 1.03; Actual Q4: 1.03 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 12.98; Actual Q2: 12.51; Actual Q3: 12.53; Actual Q4: 12.53; Actual Q1: 12.53; Actual Q2: 12.56; Actual Q3: 12.56; Actual Q4: 12.56 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 5.8; Actual Q2: 5.81; Actual Q3: 5.79; Actual Q4: 5.82; Actual Q1: 5.83; Actual Q2: 5.37; Actual Q3: 5.37; Actual Q4: 5.37 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 52.4; Actual Q2: 52.82; Actual Q3: 52.82; Actual Q4: 52.55; Actual Q1: 52.15; Actual Q2: 52.21; Actual Q3: 52.24; Actual Q4: 52.24 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 16.06; Actual Q2: 16.06; Actual Q3: 16.06; Actual Q4: 16.16; Actual Q1: 16.2; Actual Q2: 15.99; Actual Q3: 15.99; Actual Q4: 15.99 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 305.52; Actual Q2: 305.89; Actual Q3: 305.68; Actual Q4: 305.47; Actual Q1: 305.46; Actual Q2: 305.48; Actual Q3: 305.37; Actual Q4: 305.36 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 17.7; Actual Q2: 17.69; Actual Q3: 17.81; Actual Q4: 17.78; Actual Q1: 17.88; Actual Q2: 17.87; Actual Q3: 17.89; Actual Q4: 17.89 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 580.59; Actual Q2: 578.86; Actual Q3: 579.03; Actual Q4: 577.52; Actual Q1: 577.44; Actual Q2: 578.85; Actual Q3: 578.75; Actual Q4: 578.75 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 170.05; Actual Q2: 166.65; Actual Q3: 165.85; Actual Q4: 160.99; Actual Q1: 161.49; Actual Q2: 162.7; Actual Q3: 162.19; Actual Q4: 162.19 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 112.39; Actual Q2: 112.76; Actual Q3: 112.49; Actual Q4: 112.37; Actual Q1: 112.64; Actual Q2: 112.45; Actual Q3: 112.45; Actual Q4: 112.45 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 71.76; Actual Q2: 72.55; Actual Q3: 72.04; Actual Q4: 71.87; Actual Q1: 72.18; Actual Q2: 72.13; Actual Q3: 72.12; Actual Q4: 72.12 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0.02; Actual Q2: 0.02; Actual Q3: 0.02; Actual Q4: 0.02; Actual Q1: 0.02; Actual Q2: 0.02; Actual Q3: 0.02; Actual Q4: 0.02 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 107.44; Actual Q2: 107.86; Actual Q3: 107.9; Actual Q4: 107.9; Actual Q1: 108.04; Actual Q2: 108.04; Actual Q3: 108.04; Actual Q4: 108.04 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 15.62; Actual Q2: 15.62; Actual Q3: 15.62; Actual Q4: 15.62; Actual Q1: 15.62; Actual Q2: 15.62; Actual Q3: 15.62; Actual Q4: 15.62 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0.49; Actual Q2: 1.43; Actual Q3: 1.43; Actual Q4: 1.43; Actual Q1: 1.43; Actual Q2: 1.44; Actual Q3: 1.44; Actual Q4: 1.44 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0.12; Actual Q2: 0.39; Actual Q3: 0.39; Actual Q4: 0.39; Actual Q1: 0.39; Actual Q2: 0.39; Actual Q3: 0.39; Actual Q4: 0.39 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0.18; Actual Q2: 0.08; Actual Q3: 0.08; Actual Q4: 0.08; Actual Q1: 0.08; Actual Q2: 0.08; Actual Q3: 0.1; Actual Q4: 0.1 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0.11; Actual Q2: 0.17; Actual Q3: 0.17; Actual Q4: 0.17; Actual Q1: 0.17; Actual Q2: 0.17; Actual Q3: 0.16; Actual Q4: 0.16 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0.84; Actual Q2: 1.59; Actual Q3: 1.53; Actual Q4: 1.58; Actual Q1: 1.58; Actual Q2: 1.58; Actual Q3: 1.58; Actual Q4: 1.58 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0.08; Actual Q2: 0.18; Actual Q3: 0.18; Actual Q4: 0.18; Actual Q1: 0.18; Actual Q2: 0.18; Actual Q3: 0.18; Actual Q4: 0.18 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 2.98; Actual Q2: 5.48; Actual Q3: 4.49; Actual Q4: 5.69; Actual Q1: 5.69; Actual Q2: 5.69; Actual Q3: 5.69; Actual Q4: 5.69 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 11.96; Actual Q2: 15.73; Actual Q3: 15.58; Actual Q4: 20.67; Actual Q1: 20.67; Actual Q2: 20.67; Actual Q3: 20.67; Actual Q4: 20.67 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0.23; Actual Q2: 0.25; Actual Q3: 0.25; Actual Q4: 0.25; Actual Q1: 0.25; Actual Q2: 0.29; Actual Q3: 0.29; Actual Q4: 0.29 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0.03; Actual Q2: 0.03; Actual Q3: 0.03; Actual Q4: 0.03; Actual Q1: 0.03; Actual Q2: 0.03; Actual Q3: 0.03; Actual Q4: 0.03 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 2.32; Actual Q2: 2.32; Actual Q3: 2.32; Actual Q4: 2.32; Actual Q1: 2.32; Actual Q2: 2.32; Actual Q3: 2.32; Actual Q4: 2.32 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 21.44; Actual Q2: 21.44; Actual Q3: 21.45; Actual Q4: 21.45; Actual Q1: 21.48; Actual Q2: 21.72; Actual Q3: 21.73; Actual Q4: 21.73 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 1.15; Actual Q2: 1.15; Actual Q3: 1.15; Actual Q4: 1.15; Actual Q1: 1.15; Actual Q2: 1.08; Actual Q3: 1.05; Actual Q4: 1.05 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 3.35; Actual Q2: 3.35; Actual Q3: 3.35; Actual Q4: 3.35; Actual Q1: 3.35; Actual Q2: 3.35; Actual Q3: 3.36; Actual Q4: 3.36 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 1.97; Actual Q2: 1.97; Actual Q3: 1.97; Actual Q4: 1.97; Actual Q1: 1.97; Actual Q2: 1.52; Actual Q3: 1.52; Actual Q4: 1.52 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 8.68; Actual Q2: 8.68; Actual Q3: 8.68; Actual Q4: 8.68; Actual Q1: 8.69; Actual Q2: 8.7; Actual Q3: 8.7; Actual Q4: 8.7 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 1.84; Actual Q2: 1.84; Actual Q3: 1.84; Actual Q4: 1.84; Actual Q1: 1.84; Actual Q2: 1.84; Actual Q3: 1.85; Actual Q4: 1.85 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 98.17; Actual Q2: 98.17; Actual Q3: 98.17; Actual Q4: 98.4; Actual Q1: 98.61; Actual Q2: 103.1; Actual Q3: 103.1; Actual Q4: 103.1 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 11.32; Actual Q2: 11.32; Actual Q3: 11.46; Actual Q4: 11.53; Actual Q1: 11.48; Actual Q2: 11.52; Actual Q3: 11.52; Actual Q4: 11.52 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 291.71; Actual Q2: 291.71; Actual Q3: 292.37; Actual Q4: 293.31; Actual Q1: 294.15; Actual Q2: 294.41; Actual Q3: 294.73; Actual Q4: 294.73 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 76.57; Actual Q2: 76.57; Actual Q3: 76.75; Actual Q4: 76.82; Actual Q1: 76.78; Actual Q2: 76.82; Actual Q3: 76.84; Actual Q4: 76.84 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 33.74; Actual Q2: 33.74; Actual Q3: 33.71; Actual Q4: 33.76; Actual Q1: 33.77; Actual Q2: 34.44; Actual Q3: 34.44; Actual Q4: 34.44 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 9.85; Actual Q2: 9.85; Actual Q3: 10.28; Actual Q4: 10.28; Actual Q1: 10.33; Actual Q2: 10.39; Actual Q3: 10.4; Actual Q4: 10.4 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 8.73; Actual Q2: 8.73; Actual Q3: 8.73; Actual Q4: 8.73; Actual Q1: 8.75; Actual Q2: 8.75; Actual Q3: 8.76; Actual Q4: 8.76 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 1.46; Actual Q2: 1.46; Actual Q3: 1.46; Actual Q4: 1.46; Actual Q1: 1.46; Actual Q2: 1.46; Actual Q3: 1.46; Actual Q4: 1.46 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.05; Actual Q4: 0.05; Actual Q1: 0.05; Actual Q2: 0.05; Actual Q3: 0.06; Actual Q4: 0.06 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.98; Actual Q4: 1.08; Actual Q1: 1.08; Actual Q2: 1.08; Actual Q3: 1.08; Actual Q4: 1.09 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.15; Actual Q4: 0.15; Actual Q1: 0.15; Actual Q2: 0.15; Actual Q3: 0.15; Actual Q4: 0.15 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 12; Actual Q3: 18; Actual Q4: 19; Actual Q1: 17; Actual Q2: 17; Actual Q3: 17; Actual Q4: 16 |  |  |  | Number of critical facilities
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 1; Actual Q2: 10; Actual Q3: 14; Actual Q4: 14; Actual Q1: 12; Actual Q2: 12; Actual Q3: 13; Actual Q4: 13 |  |  |  | Number of critical facilities
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 2; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2; Actual Q1: 2; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2 |  |  |  | Number of critical facilities
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 12; Actual Q2: 42; Actual Q3: 88; Actual Q4: 71; Actual Q1: 71; Actual Q2: 71; Actual Q3: 74; Actual Q4: 74 |  |  |  | Number of critical facilities
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 3; Actual Q2: 13; Actual Q3: 14; Actual Q4: 14; Actual Q1: 14; Actual Q2: 14; Actual Q3: 14; Actual Q4: 14 |  |  |  | Number of critical facilities
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 17; Actual Q2: 239; Actual Q3: 364; Actual Q4: 361; Actual Q1: 326; Actual Q2: 326; Actual Q3: 347; Actual Q4: 347 |  |  |  | Number of critical facilities
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 4; Actual Q2: 49; Actual Q3: 49; Actual Q4: 49; Actual Q1: 49; Actual Q2: 49; Actual Q3: 54; Actual Q4: 54 |  |  |  | Number of critical facilities
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 29; Actual Q2: 217; Actual Q3: 258; Actual Q4: 253; Actual Q1: 243; Actual Q2: 243; Actual Q3: 260; Actual Q4: 260 |  |  |  | Number of critical facilities
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 9; Actual Q2: 54; Actual Q3: 59; Actual Q4: 58; Actual Q1: 56; Actual Q2: 56; Actual Q3: 59; Actual Q4: 59 |  |  |  | Number of critical facilities
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 11; Actual Q2: 23; Actual Q3: 53; Actual Q4: 46; Actual Q1: 46; Actual Q2: 46; Actual Q3: 49; Actual Q4: 49 |  |  |  | Number of critical facilities
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 10; Actual Q2: 24; Actual Q3: 25; Actual Q4: 25; Actual Q1: 26; Actual Q2: 26; Actual Q3: 27; Actual Q4: 27 |  |  |  | Number of critical facilities
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 3; Actual Q2: 42; Actual Q3: 60; Actual Q4: 61; Actual Q1: 60; Actual Q2: 60; Actual Q3: 60; Actual Q4: 60 |  |  |  | Number of critical facilities
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 3; Actual Q3: 5; Actual Q4: 5; Actual Q1: 4; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4 |  |  |  | Number of critical facilities
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 1002; Actual Q2: 1002; Actual Q3: 1001; Actual Q4: 1013; Actual Q1: 1013; Actual Q2: 1013; Actual Q3: 1010; Actual Q4: 1011 |  |  |  | Number of residential customers
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 17; Actual Q2: 17; Actual Q3: 17; Actual Q4: 17; Actual Q1: 17; Actual Q2: 17; Actual Q3: 17; Actual Q4: 17 |  |  |  | Number of residential customers
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 366; Actual Q2: 366; Actual Q3: 363; Actual Q4: 367; Actual Q1: 367; Actual Q2: 367; Actual Q3: 366; Actual Q4: 366 |  |  |  | Number of residential customers
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 18; Actual Q2: 18; Actual Q3: 18; Actual Q4: 18; Actual Q1: 17; Actual Q2: 17; Actual Q3: 19; Actual Q4: 19 |  |  |  | Number of residential customers
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 1477; Actual Q2: 1477; Actual Q3: 1474; Actual Q4: 1473; Actual Q1: 1487; Actual Q2: 1487; Actual Q3: 1488; Actual Q4: 1496 |  |  |  | Number of residential customers
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 37; Actual Q2: 37; Actual Q3: 37; Actual Q4: 37; Actual Q1: 38; Actual Q2: 38; Actual Q3: 38; Actual Q4: 38 |  |  |  | Number of residential customers
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 13946; Actual Q2: 13946; Actual Q3: 13917; Actual Q4: 14043; Actual Q1: 14084; Actual Q2: 14084; Actual Q3: 14265; Actual Q4: 14343 |  |  |  | Number of residential customers
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 40; Actual Q2: 40; Actual Q3: 40; Actual Q4: 40; Actual Q1: 39; Actual Q2: 39; Actual Q3: 39; Actual Q4: 39 |  |  |  | Number of residential customers
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 19514; Actual Q2: 19514; Actual Q3: 19490; Actual Q4: 19752; Actual Q1: 19825; Actual Q2: 19825; Actual Q3: 19842; Actual Q4: 19911 |  |  |  | Number of residential customers
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 972; Actual Q2: 972; Actual Q3: 971; Actual Q4: 990; Actual Q1: 999; Actual Q2: 999; Actual Q3: 1002; Actual Q4: 1026 |  |  |  | Number of residential customers
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 1717; Actual Q2: 1717; Actual Q3: 1713; Actual Q4: 1718; Actual Q1: 1720; Actual Q2: 1720; Actual Q3: 1729; Actual Q4: 1741 |  |  |  | Number of residential customers
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 205; Actual Q2: 205; Actual Q3: 205; Actual Q4: 205; Actual Q1: 207; Actual Q2: 207; Actual Q3: 207; Actual Q4: 211 |  |  |  | Number of residential customers
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | [19 empty] | Number of residential customers | bar: Actual Q1 to Actual Q4
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 2758; Actual Q2: 2758; Actual Q3: 2758; Actual Q4: 2774; Actual Q1: 2777; Actual Q2: 2777; Actual Q3: 2774; Actual Q4: 2775 |  |  |  | Number of residential customers
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 142; Actual Q2: 142; Actual Q3: 142; Actual Q4: 142; Actual Q1: 142; Actual Q2: 142; Actual Q3: 142; Actual Q4: 143 |  |  |  | Number of residential customers
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 92; Actual Q2: 92; Actual Q3: 91; Actual Q4: 110; Actual Q1: 110; Actual Q2: 110; Actual Q3: 109; Actual Q4: 109 |  |  |  | Number of commercial customers
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 14; Actual Q2: 14; Actual Q3: 14; Actual Q4: 14; Actual Q1: 13; Actual Q2: 13; Actual Q3: 13; Actual Q4: 13 |  |  |  | Number of commercial customers
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 75; Actual Q2: 75; Actual Q3: 74; Actual Q4: 77; Actual Q1: 77; Actual Q2: 77; Actual Q3: 77; Actual Q4: 79 |  |  |  | Number of commercial customers
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 96; Actual Q2: 96; Actual Q3: 94; Actual Q4: 95; Actual Q1: 95; Actual Q2: 95; Actual Q3: 96; Actual Q4: 98 |  |  |  | Number of commercial customers
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 216; Actual Q2: 216; Actual Q3: 216; Actual Q4: 216; Actual Q1: 230; Actual Q2: 230; Actual Q3: 230; Actual Q4: 236 |  |  |  | Number of commercial customers
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 85; Actual Q2: 85; Actual Q3: 84; Actual Q4: 85; Actual Q1: 85; Actual Q2: 85; Actual Q3: 85; Actual Q4: 88 |  |  |  | Number of commercial customers
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 1934; Actual Q2: 1934; Actual Q3: 1917; Actual Q4: 1989; Actual Q1: 1988; Actual Q2: 1988; Actual Q3: 2002; Actual Q4: 2031 |  |  |  | Number of commercial customers
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 252; Actual Q2: 252; Actual Q3: 249; Actual Q4: 253; Actual Q1: 255; Actual Q2: 255; Actual Q3: 261; Actual Q4: 266 |  |  |  | Number of commercial customers
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 1410; Actual Q2: 1410; Actual Q3: 1408; Actual Q4: 1524; Actual Q1: 1529; Actual Q2: 1529; Actual Q3: 1526; Actual Q4: 1592 |  |  |  | Number of commercial customers
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 319; Actual Q2: 319; Actual Q3: 320; Actual Q4: 343; Actual Q1: 354; Actual Q2: 354; Actual Q3: 354; Actual Q4: 358 |  |  |  | Number of commercial customers
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 146; Actual Q2: 146; Actual Q3: 146; Actual Q4: 146; Actual Q1: 146; Actual Q2: 146; Actual Q3: 149; Actual Q4: 157 |  |  |  | Number of commercial customers
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 89; Actual Q2: 89; Actual Q3: 89; Actual Q4: 89; Actual Q1: 88; Actual Q2: 88; Actual Q3: 90; Actual Q4: 92 |  |  |  | Number of commercial customers
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 49; Actual Q2: 49; Actual Q3: 49; Actual Q4: 52; Actual Q1: 52; Actual Q2: 52; Actual Q3: 53; Actual Q4: 54 |  |  |  | Number of commercial customers
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5; Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of commercial customers
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 5; Actual Q2: 6; Actual Q3: 109; Actual Q4: 124; Actual Q1: 138; Actual Q2: 137; Actual Q3: 166; Actual Q4: 164 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 4; Actual Q4: 5; Actual Q1: 6; Actual Q2: 6; Actual Q3: 6; Actual Q4: 6 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 4; Actual Q2: 4; Actual Q3: 57; Actual Q4: 59; Actual Q1: 71; Actual Q2: 69; Actual Q3: 49; Actual Q4: 78 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 9; Actual Q4: 9; Actual Q1: 10; Actual Q2: 10; Actual Q3: 12; Actual Q4: 12 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 40; Actual Q2: 50; Actual Q3: 505; Actual Q4: 525; Actual Q1: 550; Actual Q2: 528; Actual Q3: 594; Actual Q4: 604 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 2; Actual Q2: 1; Actual Q3: 20; Actual Q4: 18; Actual Q1: 19; Actual Q2: 18; Actual Q3: 22; Actual Q4: 22 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 124; Actual Q2: 127; Actual Q3: 2722; Actual Q4: 2900; Actual Q1: 3119; Actual Q2: 3049; Actual Q3: 3603; Actual Q4: 3664 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 8; Actual Q4: 7; Actual Q1: 9; Actual Q2: 9; Actual Q3: 8; Actual Q4: 8 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 35; Actual Q2: 39; Actual Q3: 1905; Actual Q4: 2084; Actual Q1: 2380; Actual Q2: 2360; Actual Q3: 2897; Actual Q4: 2928 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 3; Actual Q2: 3; Actual Q3: 110; Actual Q4: 119; Actual Q1: 138; Actual Q2: 136; Actual Q3: 166; Actual Q4: 170 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 23; Actual Q2: 31; Actual Q3: 398; Actual Q4: 423; Actual Q1: 464; Actual Q2: 449; Actual Q3: 508; Actual Q4: 520 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 44; Actual Q4: 60; Actual Q1: 62; Actual Q2: 62; Actual Q3: 72; Actual Q4: 77 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 21; Actual Q2: 18; Actual Q3: 334; Actual Q4: 362; Actual Q1: 407; Actual Q2: 394; Actual Q3: 469; Actual Q4: 471 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 2; Actual Q2: 2; Actual Q3: 18; Actual Q4: 20; Actual Q1: 26; Actual Q2: 25; Actual Q3: 26; Actual Q4: 26 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | [19 empty] | Number of substations | bar: Actual Q1 to Actual Q4
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1; Actual Q1: 1; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 1; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2; Actual Q1: 2; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2 |  |  |  | Number of substations
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 3; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4; Actual Q1: 4; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4 |  |  |  | Number of substations
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 3; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1; Actual Q1: 1; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Number of substations | bar: Actual Q1 to Actual Q4
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Number of substations | bar: Actual Q1 to Actual Q4
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1; Actual Q1: 1; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of weather stations
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3; Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3 |  |  |  | Number of weather stations
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1; Actual Q1: 1; Actual Q2: 2; Actual Q3: 2; Actual Q4: 2 |  |  |  | Number of weather stations
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5; Actual Q1: 5; Actual Q2: 7; Actual Q3: 7; Actual Q4: 8 |  |  |  | Number of weather stations
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 15; Actual Q2: 10; Actual Q3: 10; Actual Q4: 10; Actual Q1: 10; Actual Q2: 11; Actual Q3: 11; Actual Q4: 11 |  |  |  | Number of weather stations
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5; Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of weather stations
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 4; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4; Actual Q1: 4; Actual Q2: 4; Actual Q3: 5; Actual Q4: 7 |  |  |  | Number of weather stations
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Number of weather stations | bar: Actual Q1 to Actual Q4
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 8
| Utility | Liberty |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2024-01-31 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | [15 empty] | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: -0.54; Actual Q3: 0.02; Actual Q4: 0; Actual Q1: -0.08; Actual Q2: -0.12; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: -0.12; Actual Q3: 0.01; Actual Q4: 0; Actual Q1: 0; Actual Q2: -0.05; Actual Q3: 0.04; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: -0.47; Actual Q3: 0.02; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.03; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: -0.02; Actual Q4: 0.03; Actual Q1: 0.01; Actual Q2: -0.46; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0.42; Actual Q3: 0; Actual Q4: -0.27; Actual Q1: -0.4; Actual Q2: 0.06; Actual Q3: 0.03; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0.1; Actual Q1: 0.04; Actual Q2: -0.21; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: -0.3; Actual Q2: -0.13; Actual Q3: -0.21; Actual Q4: -0.21; Actual Q1: -0.01; Actual Q2: 0.02; Actual Q3: -0.11; Actual Q4: 0 |  | -0.39 |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: -0.03; Actual Q3: 0.12; Actual Q4: -0.03; Actual Q1: 0.1; Actual Q2: -0.01; Actual Q3: 0.02; Actual Q4: 0 |  | -0.02 |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: -1.95; Actual Q3: 0.17; Actual Q4: -1.51; Actual Q1: -0.08; Actual Q2: 1.41; Actual Q3: -0.1; Actual Q4: 0 | -2.88 |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: -0.35; Actual Q2: -3.46; Actual Q3: -0.8; Actual Q4: -4.86; Actual Q1: 0.5; Actual Q2: 1.21; Actual Q3: -0.51; Actual Q4: 0 | -0.01 |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0.29; Actual Q3: -0.27; Actual Q4: -0.12; Actual Q1: 0.27; Actual Q2: -0.19; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.79; Actual Q3: -0.51; Actual Q4: -0.17; Actual Q1: 0.31; Actual Q2: -0.05; Actual Q3: -0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0.42; Actual Q3: 0.04; Actual Q4: 0; Actual Q1: 0.14; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0.94; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0.28; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: -0.1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.02; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: -0.36; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: -0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0.75; Actual Q3: -0.06; Actual Q4: 0.05; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0.1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 2.5; Actual Q3: -0.99; Actual Q4: 1.2; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 3.77; Actual Q3: -0.15; Actual Q4: 5.09; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.02; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.04; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: -0.01; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0; Actual Q1: 0.03; Actual Q2: 0.24; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: -0.07; Actual Q3: -0.03; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: -0.45; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.01; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.23; Actual Q1: 0.21; Actual Q2: 4.49; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.14; Actual Q4: 0.07; Actual Q1: -0.05; Actual Q2: 0.04; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.66; Actual Q4: 0.94; Actual Q1: 0.84; Actual Q2: 0.26; Actual Q3: 0.32; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.18; Actual Q4: 0.07; Actual Q1: -0.04; Actual Q2: 0.04; Actual Q3: 0.02; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: -0.03; Actual Q4: 0.05; Actual Q1: 0.01; Actual Q2: 0.67; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.43; Actual Q4: 0; Actual Q1: 0.05; Actual Q2: 0.06; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.02; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.05; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.98; Actual Q4: 0.1; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.15; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: -1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: -1; Actual Q2: -2; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: -1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 5; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 2; Actual Q3: 0; Actual Q4: 1 |  |  |  | Number of weather stations
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: -5; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 1; Actual Q4: 2 |  |  |  | Number of weather stations
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 9
| Utility | Liberty
| Table No. | 9
| Date Modified | 2024-01-31
[7 empty] | Actual | [15 empty] | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 1.26; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.41; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0.47; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0.02; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  | 0.36 |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0.09; Actual Q3: 0; Actual Q4: 0.12; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 6.14 | 2.58 | 5.09 | 2.21 | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 1.27; Actual Q3: 3.08; Actual Q4: 3; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.09 | 0.03 | 0.09 | 1.81 | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 3.23; Actual Q3: 0; Actual Q4: 0 | 1.45 | 3.04 |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 6.22; Actual Q3: 0; Actual Q4: 0 | 6.27 | 0.26 |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 1 |  |  | Number of substations
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 1 |  |  | Number of substations
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 1; Actual Q2: 2; Actual Q3: 0; Actual Q4: 2; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 2 |  |  | Number of substations
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 1 |  |  |  | Number of substations
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 |  |  | Number of substations
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 1; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 10
Utility | Liberty |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2024-01-31 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | [15 empty] | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Metric type | # | Wind Warning Status | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW & RFW | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.b. | RFW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW & RFW | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| 1.c. | RFW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW & RFW | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
| 1.d. | RFW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of events
|  | HWW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of events
|  | HWW & RFW | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of events
|  | None | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 5; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of events
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit mile days
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 45.8; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit mile days
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit mile days
|  | None | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 997.8; Actual Q3: 459.2; Actual Q4: 616.5; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit mile days
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | Actual Q1: 8405.5; Actual Q2: 22184.2333; Actual Q3: 5963.4333; Actual Q4: 16965.4333; Actual Q1: 13873.42; Actual Q2: 17032.8; Actual Q3: 33954.4; Actual Q4: 42923.8 |  |  |  | Total customer hours of planned outages per year
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | Actual Q1: 34153.7833; Actual Q2: 71388.3333; Actual Q3: 62850.3667; Actual Q4: 198165.4; Actual Q1: 116905; Actual Q2: 24444.7; Actual Q3: 29472.8; Actual Q4: 34832.5 |  |  |  | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | Actual Q1: 0; Actual Q2: 989.8; Actual Q3: 0; Actual Q4: 7680.8; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Total customer hours of outages due to fast-trip per year
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | Actual Q1: 40.8611; Actual Q2: 86.5923; Actual Q3: 75.1934; Actual Q4: 246.2717; Actual Q1: 139.864; Actual Q2: 29.245; Actual Q3: 35.261; Actual Q4: 41.666 |  |  |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | Actual Q1: 40.8611; Actual Q2: 86.5923; Actual Q3: 75.1934; Actual Q4: 246.2717; Actual Q1: 139.864; Actual Q2: 29.245; Actual Q3: 35.261; Actual Q4: 41.666 |  |  |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | Actual Q1: 0.38655; Actual Q2: 0.5946; Actual Q3: 0.73289; Actual Q4: 0.70316; Actual Q1: 1.0304; Actual Q2: 0.231; Actual Q3: 0.486; Actual Q4: 0.22 |  |  |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | Actual Q1: 0.38655; Actual Q2: 0.5946; Actual Q3: 0.73289; Actual Q4: 0.70316; Actual Q1: 1.0304; Actual Q2: 0.231; Actual Q3: 0.486; Actual Q4: 0.22 |  |  |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.b. | N/A | # of medical baseline customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.c. | N/A | # of customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of risk events

## Table 11
Utility | Liberty | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2023-05-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actual | [15 empty] | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Grid Design, Operations, and Maintenance | Covered conductor installation | WMP-GDOM-GH-01 | Other contact with object | Equipment failure | 2019 | 2021 WMP | NA | In compliance | NA | NA | [5 empty] | 7820 | 7820 |  |  | 10550 | 10550 |  |  | 9609.7262 | 9609.7262 |  |  | 3284.76 | 3284.76 |  |  | 8627.427 | 8627.427 |  |  | 4534 | 4534
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP-GDOM-GH-02 | Other contact with object | Equipment failure |  | 2020 WMP | NA | Exceeds | NA | NA | [5 empty] | 522 | 522 |  |  | 903 | 903 |  |  | 474.9841 | 474.9841 |  |  | 7692.65 | 7692.65 |  |  | 8482.68 | 8482.68 |  |  | 7000 | 7000
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | WMP-GDOM-GH-03 | Equipment failure |  | 2011 | 2021 WMP | NA | In compliance | GO 165 | NA | [5 empty] | 3652 | 3652 |  |  | 5003 | 5003 |  |  | 6909.4487 | 6909.4487 |  |  | 10970.194 | 10970.194 |  |  | 7413 | 7413 |  |  | 5000 | 5000
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | WMP-GDOM-GH-04
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP-GDOM-GH-05 | [25 empty] | 4961.889 | 4961.889 |  |  | 2068.318 | 2068.318 |  |  | 2500 | 2500
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilot progress | WMP-GDOM-GH-06 | [15 empty] | 1 | 1 |  |  | 101 | 101 |  |  | 4.5861 | 4.5861 | 150 | 150 |  |  | 3050 | 3050 |  |  | 3050 | 3050
Grid Design, Operations, and Maintenance | Microgrids | WMP-GDOM-GH-07 | PSPS - for sectionalization, etc. | Resiliency | 2020 | 2021 WMP | NA | In compliance | R20A | NA | [5 empty] | 672 | 672 |  |  | 107 | 107 | 38 | 38 | 230.8745 | 230.8745 | 33.2175 | 33.2175 |  |  |  |  | 1500 | 1500
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP-GDOM-GH-08 | PSPS - for sectionalization, etc. |  | 2011 | 2021 WMP | NA | Exceeds | NA | NA | [5 empty] | 454 | 454 |  |  | 339 | 339 |  |  | 191.3329 | 191.3329 |  |  | 1200 | 1200 |  |  | 1200 | 1200 |  |  | 1200 | 1200
Grid Design, Operations, and Maintenance | Line removal (in HFTD) | WMP-GDOM-GH-09 | [29 empty] | 500 | 500
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP-GDOM-GH-10
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP-GDOM-GH-11 | PSPS - for sectionalization, etc. |  | 2020 | 2021 WMP | NA | In compliance | R20A | NA
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above: | WMP-GDOM-GH-12
Grid Design, Operations, and Maintenance | Tree attachment removals | WMP-GDOM-GH-12a | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 1358 | 1358 |  |  | 597 | 597 | 33 | 33 | 988.5276 | 988.5276 | 36 | 36 | 701.112 | 701.112 |  |  | 720.392 | 720.392 |  |  | 740.203 | 740.203
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | WMP-GDOM-GH-12b | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 738 | 738 |  |  | 600 | 600 |  |  | 3431.6893 | 3431.6893
Grid Design, Operations, and Maintenance | Animal guards / Avian Protection | WMP-GDOM-GH-12c | Equipment failure | Animal contact | 2020 | 2021 WMP | NA | NA | NA | NA | [7 empty] | 15 | 15 | 719 | 719 | 31 | 31 | 719.4256 | 719.4256 | 12.0543 | 12.0543 | 40 | 40 |  |  | 100 | 100
Grid Design, Operations, and Maintenance | CalFIRE exempt hardware | WMP-GDOM-GH-12d | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [9 empty] | 31 | 31 |  |  | 619.3436 | 619.3436
Grid Design, Operations, and Maintenance | Open wire/grey wire | WMP-GDOM-GH-12e | Equipment failure |  | 2021 | 2021 WMP | NA | NA | NA | NA | [9 empty] | 604 | 604 |  |  | 3977.7848 | 3977.7848 |  |  | 1000 | 1000 |  |  | 2000 | 2000 |  |  | 2055 | 2055
Grid Design, Operations, and Maintenance | Substation Equipment Replacement | WMP-GDOM-GH-12f | Equipment failure |  |  |  | NA | NA | NA | NA | [9 empty] | 88 | 88 |  |  | 305.11 | 305.11
Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment | WMP-GDOM-AI-01 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO128; GO165 | NA | [7 empty] | 838 | 838 |  |  | 409 | 409 |  |  | 919.3908 | 919.3908 |  |  | 20 | 20 |  |  | 125 | 125 |  |  | 75 | 75
Grid Design, Operations, and Maintenance | Intrusive pole inspections | WMP-GDOM-AI-02 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO165 | NA | [7 empty] | 10 | 10 |  |  | 158 | 158 |  |  | 99.0499 | 99.0499
Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment | WMP-GDOM-AI-03 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO165 | NA | [19 empty] | 15 | 15 |  |  | 15 | 15 |  |  | 15 | 15
Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment | WMP-GDOM-AI-04 | Equipment failure | Other contact with object | 2020 | 2021 WMP | NA | Exceeds | GO95; GO128; GO165 | NA | [5 empty] | 2994.2665 | 2994.2665 |  |  | 19.897 | 19.897 | 1055.9277 | 1055.9277 |  |  | 3578.5134 | 3578.5134 |  |  | 1000 | 1000 |  |  | 1000 | 1000 |  |  | 1000 | 1000
Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections | WMP-GDOM-AI-05 | Equipment failure | Other contact with object | 2021 | NA | NA | In Compliance | GO95; GO128; GO165 | NA | [19 empty] | 10 | 10 |  |  | 10 | 10 |  |  | 10 | 10
Grid Design, Operations, and Maintenance | Substation inspections | WMP-GDOM-AI-06 | Equipment failure | Other contact with object | 2016 | 2019 GRC | NA | In Compliance | GO174 | NA | [19 empty] | 10 | 10 |  |  | 10 | 10 |  |  | 10 | 10
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | WMP-GDOM-MR-01 | Equipment failure |  |  | 2019 GRC | NA | NA | NA | NA | [19 empty] | 500 | 500 |  |  | 500 | 500 |  |  | 500 | 500
Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk | WMP-GDOM-GO-01 | PSPS - for sectionalization, etc. |  | 2021 | NA | NA | NA | NA | NA | [13 empty] | 47.1828 | 47.1828 |  |  | 150 | 150 |  |  | 150 | 150 |  |  | 150 | 150
Grid Design, Operations, and Maintenance | Grid response procedures and notifications | WMP-GDOM-GO-02 | PSPS - for sectionalization, etc. |  | 2021 | NA | NA | In compliance | CPUC D.21-06-034 | NA | [5 empty] | 93 | 93 |  |  | 46 | 46
Grid Design, Operations, and Maintenance | Personnel work procedures and training in conditions of elevated fire risk | WMP-GDOM-GO-03 | Equipment failure | Other contact with object | 2019 | 2021 WMP | WMPMA | In compliance | NA | NA | [7 empty] | 279 | 279 |  |  | 250 | 250 |  |  | 293.2922 | 293.2922 |  |  | 283.8938 | 283.8938 |  |  | 298.0884 | 298.0884 |  |  | 312.9929 | 312.9929
Grid Design, Operations, and Maintenance | Automatic recloser operations | WMP-GDOM-GO-04 | Contact with vegetation | Equipment failure | 2011 | NA | WMPMA | In compliance | NA | NA
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System | WMP-GDOM-GO-05 | [17 empty] | 10 | 10
Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed | WMP-VM-INSP-01 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 556 | 556 |  |  | 701 | 701 |  |  | 872.0499 | 872.0499 |  |  | 789.82 | 789.82 |  |  | 813.5146 | 813.5146 |  |  | 837.92 | 837.92
Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol | WMP-VM-INSP-02 | Contact with vegetation |  | 2018 | 2019 GRC | NA | NA | NA | NA | [7 empty] | 420.8004 | 420.8004 |  |  | 337.8295 | 337.8295 |  |  | 638.341 | 638.341 |  |  | 250 | 250 |  |  | 257.5 | 257.5 |  |  | 265.225 | 265.225
Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDAR | WMP-VM-INSP-03 | Contact with vegetation |  | 2020 | NA | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [5 empty] | 369.2978 | 369.2978 |  |  | 350.4282 | 350.4282 | 303 | 303 |  |  | 754.1925 | 754.1925 |  |  | 700 | 700 |  |  | 721 | 721 |  |  | 742.63 | 742.63
Vegetation Management & Inspections | Pole Clearing | WMP-VM-VFM-01 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 0 | 0 |  |  | 984.6756 | 984.6756 |  |  | 2671.1103 | 2671.1103 |  |  | 480 | 480 |  |  | 494.4 | 494.4 |  |  | 509.232 | 509.232
Vegetation Management & Inspections | Wood and Slash Management | WMP-VM-VFM-02 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | PRC 4291; PRC 4292 | NA | [5 empty] | 89 | 89 | 360 | 360 | 0 | 0 | 1196 | 1196 |  |  | 1515.1239 | 1515.1239 |  |  | 1500 | 1500 |  |  | 1545 | 1545 |  |  | 1591.35 | 1591.35
Vegetation Management & Inspections | Substation Defensible Space | WMP-VM-VFM-03 | [15 empty] | 0 | 0 |  |  | 0 | 0 | [6 empty] | 20 | 20 |  |  | 20.6 | 20.6 |  |  | 21.218 | 21.218
Vegetation Management & Inspections | Fire-Resilient Right-of-Ways | WMP-VM-VFM-04 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 771 | 771 | 317 | 317 | 333 | 333 |  |  | 928.0681 | 928.0681 |  |  | 255 | 255 |  |  | 262.65 | 262.65 |  |  | 270.5295 | 270.5295
Vegetation Management & Inspections | Clearance | WMP-VM-VFM-05 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 0 | 0 |  |  | 0 | 0 | [6 empty] | 886.9 | 886.9 |  |  | 913.507 | 913.507 |  |  | 940.9122 | 940.9122
Vegetation Management & Inspections | Fall-In Mitigation | WMP-VM-VFM-06 | Contact with vegetation |  | 2018 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 2722.5304 | 2722.5304 |  |  | 1222.1736 | 1222.1736 |  |  | 5443.7297 | 5443.7297 |  |  | 7750 | 7750 |  |  | 7982.5 | 7982.5 |  |  | 8221.975 | 8221.975
Vegetation Management & Inspections | High-Risk Species | WMP-VM-VFM-07 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 7338.3232 | 7338.3232 |  |  | 4677.999 | 4677.999 |  |  | 3148.6111 | 3148.6111
Vegetation Management & Inspections | Emergency Response Vegetation Management | WMP-VM-VFM-08 | Contact with vegetation |  | 2021 | NA | NA | NA | NA | NA | [7 empty] | 0 | 0 |  |  | 0 | 0
Vegetation Management & Inspections | Vegetation Management Enterprise System | WMP-VM-ESG-01 | [15 empty] | 0 | 0 |  |  | 0 | 0 | [6 empty] | 406.005 | 406.005 |  |  | 418.1852 | 418.1852 |  |  | 430.7307 | 430.7307
Vegetation Management & Inspections | Quality Assurance and Quality Control | WMP-VM-QAQC-01 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | NA | NA | NA | [7 empty] | 67.0328 | 67.0328 |  |  | 141.1176 | 141.1176 |  |  | 447.3006 | 447.3006 |  |  | 500 | 500 |  |  | 515 | 515 |  |  | 530.45 | 530.45
Vegetation Management & Inspections | Vegetation Management - Discretionary Inspections | N/A | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 85.1387 | 85.1387 |  |  | 2 | 2
Situational Awareness & Forecasting | Environmental monitoring systems | WMP-SA-01 | PSPS - for sectionalization, etc. |  | 2019 | 2021 WMP | WFMMA | Exceeds | NA | NA | [5 empty] | 243 | 243 |  |  | 12 | 12 | 319 | 319 | 144.2567 | 144.2567 | 229.3424 | 229.3424
Situational Awareness & Forecasting | Grid monitoring systems | WMP-SA-02 | Equipment failure |  | 2020 | 2021 WMP | WFMMA | NA | NA | NA | [5 empty] | 158 | 158 |  |  | 18 | 18 | 229 | 229 | 47.6879 | 47.6879 |  |  | 150 | 150 |  |  | 150 | 150 |  |  | 150 | 150
Situational Awareness & Forecasting | Fire detection and alarm systems | WMP-SA-03 | Equipment failure |  | 2022 | NA | NA | NA | NA | NA
Situational Awareness & Forecasting | Weather forecasting | WMP-SA-04
Situational Awareness & Forecasting | Fire Potential Index | WMP-SA-05 | PSPS - for sectionalization, etc. |  | 2020 | 2021 WMP | WFMMA | Exceeds | NA | NA | [7 empty] | 44 | 44 |  |  | 14 | 14
Situational Awareness & Forecasting | Ignition likelihood calculation | WMP-SA-06 | Contact with vegetation | Equipment failure | 2020 | 2021 WMP | WMPMA | NA | NA | NA | [7 empty] | 67 | 67 |  |  | 53 | 53 | [6 empty] | 1154.34 | 1154.34 |  |  | 683.807 | 683.807 |  |  | 704.2473 | 704.2473
Situational Awareness & Forecasting | Ignition consequence calculation | WMP-SA-07 | Contact with vegetation | Equipment failure | 2020 | 2021 WMP | WMPMA | NA | NA | NA
Emergency Preparedness | Wildfire and PSPS emergency preparedness plan | WMP-EP-01 |  |  | 2011 | GO 166 | NA | In compliance | GO 166 | NA
Emergency Preparedness | Collaboration and coordination with public safety partners | WMP-EP-02 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Emergency Preparedness | Public notification and communication strategy | WMP-EP-03 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Emergency Preparedness | Preparedness and planning for service restoration | WMP-EP-04 | PSPS - for sectionalization, etc. | Equipment failure | 2011 | GO 166 | NA | In compliance | GO 166 | NA | [7 empty] | 502 | 502 |  |  | 460 | 460 | 3.5964 | 3.5964 | 658.8028 | 658.8028 |  |  | 1369.2709 | 1369.2709 |  |  | 1437.7345 | 1437.7345 |  |  | 1509.6212 | 1509.6212
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | WMP-EP-05 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA | [11 empty] | 101 | 101 |  |  | 64.5907 | 64.5907 |  |  | 100 | 100 |  |  | 105 | 105 |  |  | 110 | 110
Emergency Preparedness | Learning after wildfire and PSPS events | WMP-EP-06 |  |  | 2011 | GO 166 | NA | In compliance | GO 166 | NA
Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | WMP-CO-01 |  |  | 2019 | 2021 WMP | WMPMA | Exceeds | P.U. Code § 451 | NA | [7 empty] | 92 | 92 |  |  | 102 | 102 |  |  | 83.6375 | 83.6375 |  |  | 90 | 90 |  |  | 90 | 90 |  |  | 90 | 90
Community Outreach and Engagement | Public engagement in WMP decision-making process | WMP-CO-02
Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities | WMP-CO-03 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Community Outreach and Engagement | Collaboration on local wildfire mitigation and planning | WMP-CO-04 |  |  |  | 2021 WMP | NA | NA | NA | NA
Community Outreach and Engagement | Best practice sharing with other electrical corporations | WMP-CO-05

## Table 12
Utility | Liberty | Notes:
Table No. | 12
Date Modified | 2023-11-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | Method of Verification | Comments
Grid Design, Operations, and Maintenance | Covered conductor installation | WMP-GDOM-GH-01 | Quantitative | Circuit Miles | 0 | 0 | 5.72 | - | - | 5.61 | 2.68 |  | Liberty will assess additional covered conductor projects for 2025 in advance of its 2024 WMP Update, including two additional projects that are in the preliminary planning stages and total approximately 1.5 miles
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP-GDOM-GH-02 | Quantitative | Circuit Miles | 0 | 0.12 | 1.37 | - | - | 1.25 | 1.25
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | WMP-GDOM-GH-03 | Quantitative | Poles | 0 | 125 | 200 | 100 | 200 | 400 | 400
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | WMP-GDOM-GH-04 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP-GDOM-GH-05 | Quantitative | Circuit Miles | 0 | 2 | 4 | - | 1 | 2 | 2
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilot progress | WMP-GDOM-GH-06 |  | - | - | - | - | - | - | 1 | -
Grid Design, Operations, and Maintenance | Microgrids | WMP-GDOM-GH-07 | Quantitative | Microgrids | - | - | - | - | - | 1 | TBD
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP-GDOM-GH-08 | Quantitative | Automatic Reclosers | 0 | 4 | 8 | - | 4 | 8 | 4
Grid Design, Operations, and Maintenance | Line removal (in HFTD) | WMP-GDOM-GH-09 | Quantitative | Circuit Miles | - | - | - | - | - | 1.1 | TBD
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP-GDOM-GH-10 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP-GDOM-GH-11 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above: | WMP-GDOM-GH-12 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Tree attachment removals | WMP-GDOM-GH-12a | Quantitative | Tree Attachments | 15 | 30 | 60 | 15 | 30 | 60 | 60
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | WMP-GDOM-GH-12b | Quantitative | Expulsion Fuses | - | - | 3800 | 0 | 0 | TBD | TBD
Grid Design, Operations, and Maintenance | Animal guards | WMP-GDOM-GH-12c | Quantitative | Animal Guards | 1 | 3 | 4 | - | 1 | 2 | 0
Grid Design, Operations, and Maintenance | CalFIRE exempt hardware | WMP-GDOM-GH-12d | Quantitative | CalFIRE Exempt Hardware | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Open wire/grey wire | WMP-GDOM-GH-12e | Quantitative | Circuit Miles | 0 | 0 | 2.548 | - | - | 5.096 | 5.2362
Grid Design, Operations, and Maintenance | Substation Equipment Replacement | WMP-GDOM-GH-12f | Quantitative | TBD | - | - | TBD | TBD | TBD | TBD | TBD
Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment | WMP-GDOM-AI-01 | Quantitative | Circuit Miles | 0 | 0 | 40.3 | - | - | 264.2 | 260.9
Grid Design, Operations, and Maintenance | Intrusive pole inspections | WMP-GDOM-AI-02 | Quantitative | Poles | 0 | 1500 | 2867 | - | - | 2302 | 2411
Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment | WMP-GDOM-AI-03 | Quantitative | Circuit Miles | 0 | 701.5 | 701.5 | - | - | 589 | 540.9
Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment | WMP-GDOM-AI-04 | Quantitative | Circuit Miles | - | - | TBD | TBD | TBD | TBD | TBD
Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections | WMP-GDOM-AI-05 | Quantitative | % of Detailed Inspections | 0 | 0 | 0.01 | - | - | 0.02 | 0.03
Grid Design, Operations, and Maintenance | Substation inspections | WMP-GDOM-AI-06 | Quantitative | Substations | 24 | 38 | 42 | - | - | 42 | 42
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | WMP-GDOM-MR-01 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk | WMP-GDOM-GO-01 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Grid response procedures and notifications | WMP-GDOM-GO-02 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Personnel work procedures and training in conditions of elevated fire risk | WMP-GDOM-GO-03 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Automatic recloser operations | WMP-GDOM-GO-04 |  | - | - | - | - | - | - | - | -
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System | WMP-GDOM-GO-05 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed | WMP-VM-INSP-01 | Quantitative | Line Miles | 88 | 151 | 220 | TBD | TBD | 220 | 220
Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol | WMP-VM-INSP-02 | Quantitative | Line Miles | - | - | - | - | - | - | -
Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDar | WMP-VM-INSP-03 | Quantitative | Line Miles | 0 | 700 | 700 | TBD | TBD | 700 | 700
Vegetation Management & Inspections | Pole Clearing | WMP-VM-VFM-01 | Quantitative | Line Miles | 900 | 4060 | 4900 | TBD | TBD | 4960 | 4960
Vegetation Management & Inspections | Wood and Slash Management | WMP-VM-VFM-02 | Quantitative | Acres | 93 | 93 | 280 | TBD | TBD | 280 | 280
Vegetation Management & Inspections | Substation Defensible Space | WMP-VM-VFM-03 |  | - | 0 | 0 | 12 | - | - | - | -
Vegetation Management & Inspections | Fire-Resilient Right-of-Ways | WMP-VM-VFM-04 | Quantitative | Line Miles | - | - | - | TBD | TBD | - | -
Vegetation Management & Inspections | Clearance | WMP-VM-VFM-05 | Quantitative | Line Miles | - | - | 670.8 | TBD | TBD | - | -
Vegetation Management & Inspections | Fall-In Mitigation | WMP-VM-VFM-06 | Quantitative | Line Miles | 70 | 150 | 220 | TBD | TBD | 220 | 220
Vegetation Management & Inspections | High-Risk Species | WMP-VM-VFM-07 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Emergency Response Vegetation Management | WMP-VM-VFM-08 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Vegetation Management Enterprise System | WMP-VM-ESG-01 |  | - | - | - | - | - | - | - | -
Vegetation Management & Inspections | Quality Assurance and Quality Control | WMP-VM-QAQC-01 | Quantitative | Line Miles | 114 | 171 | 229 | TBD | TBD | 229 | 229
Situational Awareness & Forecasting | Environmental monitoring systems | WMP-SA-01 | Quantitative | Weather Stations | - | - | 5 | TBD | TBD | 0 | 0
Situational Awareness & Forecasting | Grid monitoring systems | WMP-SA-02 | Quantitative | Fault Indicators | 3 | 6 | 10 | 3 | 6 | 10 | 10
Situational Awareness & Forecasting | Fire detection and alarm systems | WMP-SA-03 | Quantitative | DFA Units | - | - | - | TBD | TBD | TBD | TBD
Situational Awareness & Forecasting | Weather forecasting | WMP-SA-04 |  | - | - | - | - | - | - | - | -
Situational Awareness & Forecasting | Fire Potential Index | WMP-SA-05 | Qualitative | - | - | - | - | - | - | - | -
Situational Awareness & Forecasting | Ignition likelihood calculation | WMP-SA-06 | Qualitative | - | - | - | - | - | - | - | -
Situational Awareness & Forecasting | Ignition consequence calculation | WMP-SA-07 | Qualitative | - | - | - | - | - | - | - | -
Emergency Preparedness | Wildfire and PSPS emergency preparedness plan | WMP-EP-01 |  | - | - | - | - | - | - | - | -
Emergency Preparedness | Collaboration and coordination with public safety partners | WMP-EP-02 | Qualitative | - | TBD | TBD | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards | TBD | TBD | TBD | TBD
Emergency Preparedness | Public notification and communication strategy | WMP-EP-03 |  | - | - | - | - | - | - | - | -
Emergency Preparedness | Preparedness and planning for service restoration | WMP-EP-04 |  | - | - | - | - | - | - | - | -
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | WMP-EP-05 | Qualitative | - | TBD | TBD | Conduct Incident Command Training for all identified IC members and hold a Virtual PSPS Tabletop exercise; Continued implementation of Liberty’s 2022 AFN Plan; Continued maintenance of emergency response plans; Enhanced documentation and use of lessons learned to update plans. | TBD | TBD | TBD | TBD
Emergency Preparedness | Learning after wildfire and PSPS events | WMP-EP-03 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | WMP-CO-01 | Qualitative | - | TBD | TBD | Continue to survey customers, CBOs, community partners and stakeholders to understand wildfire and PSPS awareness and the needs of customers. Strengthen and expand AFN CBO partnerships. Identify emerging channels and technologies to better communicate with customers, community and stakeholders. | TBD | TBD | TBD | TBD
Community Outreach and Engagement | Public engagement in WMP decision-making process | WMP-CO-02 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities | WMP-CO-03 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Collaboration on local wildfire mitigation and planning | WMP-CO-04 |  | - | - | - | - | - | - | - | -
Community Outreach and Engagement | Best practice sharing with other electrical corporations | WMP-CO-05 |  | - | - | - | - | - | - | - | -

## Table 13
Utility | Liberty |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2024-01-31
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
6ef80bad-a949-4aaa-93a4-ce252d210ff9 | Pole | 2 | Distribution | 2020-04-10 | 2025-04-09 | Level 3 |  | NULL | NULL |  | NULL
0b83e500-030d-4ded-a4db-62533d2ece14 | Pole | 2 | Distribution | 2020-04-13 | 2021-04-13 | Level 2 |  | 2021-04-02 | 2022-04-02 |  | Needs changed out
ab7d95b8-417a-4a70-840f-e6c409a19c16 | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3 |  | NULL | NULL |  | NULL
062e61ae-866b-4c65-a751-787bd12ba3bd | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3 |  | NULL | NULL |  | NULL
0285bc85-5e14-4320-9904-1823aa2376a3 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
14e549d8-7961-4a7b-9094-1f8e3fcfe401 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
621cd443-057c-44a9-986d-8f806b7066ef | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
fd1f5200-6859-4d8e-bea4-ed4554ecbb5a | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
0afe3999-0f69-4626-a966-c0ceaa8b79c7 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
0df54f4d-f917-4074-80a7-4da7e13d0a8e | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
77b1ed33-c2ab-4598-91cb-4058d358df04 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
93655288-925f-4af3-9414-7c432241a9b6 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
be24cfc1-08ac-4c05-9d6f-9ef610d15aab | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
c8131cc2-3a08-42bf-b7d8-1708276012ea | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
f612475f-7fa3-4094-8d19-1f42cc4f7a5a | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
e4959f03-aef9-4718-a6c3-cc1e1ab788a8 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
e2ea30de-0167-4acf-824d-93858c3813b0 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
e04d5835-06c4-4f71-a0bc-6ba9b71ed739 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
27f273a9-f0c9-40a4-b1f5-7e56beb88eda | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
186ec59a-27b4-4a1f-8ee5-e2dcbc4a1842 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 |  | NULL | NULL |  | NULL
047f3f3e-6600-42a1-8dda-fca0b5418a66 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
0ea06e49-19a9-4e6e-9453-2efc22b69a8c | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Loose down guy, needs to be brought to tension
09e9fa0f-ac47-4a92-8f47-a4bcebc5db54 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
08c02c81-3d3e-4674-8fac-2048684dea52 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
04b22eaa-9f6a-4001-b5dc-dc2d078007bf | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
3d8f4f08-f0e6-4a49-8880-c43fa308a8e0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
3f8e7a84-5a1c-4b8c-be93-c7602a4dc1d0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
6400e8f5-4426-4f53-96de-d236cbb046e4 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
d74dbdce-fd34-4113-9f24-df16414b3790 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
c3f13bc3-e395-4f25-ba97-44eb49f3e65e | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
bcb0f141-d8b6-4ed2-a4ab-d0ef12527dd5 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
ba9b80e0-fd27-4a50-b92b-8b9fc34dad35 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
ad618fb7-6e8e-4ed1-bcf1-d07152b9feb1 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
a17b8d85-c010-434f-b6ff-a6ee5981aab0 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
f403f7f3-2caa-4773-bc8e-bb19cbcf21fa | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
efbc38ed-2ccd-4eb4-ba72-58c241ef9ce0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
c9c4fa62-81b0-4bdb-a049-43ab274bcbc1 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
9e962665-bc94-4dd2-9062-556c722c2b2c | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
0883ebcb-778e-44b3-b8b4-6c1767d019ef | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
22073d1f-54d1-4363-9d87-5f5e4bb7bc4a | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Pole area is submerged in water
21f6294c-a614-43cb-853c-c50f5feb2c30 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
1afb34f5-1250-4ae9-908e-30b3de598bc4 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
701c1854-9b5d-4972-bca6-55e4a6ad409a | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
651f1799-2533-4911-ade8-9ce983af9bf2 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
56e11b57-691a-4697-b525-2cc9925c9d0b | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
52395920-5878-4b42-b049-a1aad481cfee | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
4183c821-6f73-42eb-975a-c452917f9789 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
3a463e14-a140-4649-930a-e01b509326a5 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | NULL | NULL |  | NULL
392be24c-9cc5-4951-81fb-c037186123e8 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
38f7296d-4930-49e1-9510-3637bf8e0be5 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
4203a1f1-8128-4901-a86e-57a0bf730038 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
457c586b-b7c7-4316-997b-efa9afe8c124 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
675eeff6-eabf-408b-b4ed-e399c3acd6ec | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
704f4cf0-4c90-444c-a9f8-fa3349b3dc48 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
7730be94-43b7-45fe-9656-3466337cfb17 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 2021-02-10 | 2026-02-09 |  | Change to level 3. Distribution should be reframed due to heavy angle.
7cb55b62-90bc-4884-95a2-717037cc85b3 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
29507e3e-4130-4f9a-979a-fd16a2e7b536 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
0b9c0fe9-444f-4135-aeef-d0a9972b32bb | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
1412eba2-827a-4857-94b1-f2d0421d01c4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
151f16cc-ca70-468f-b6fd-75d085ef2813 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
1bdc8b4b-2b00-4962-90d6-94803586f065 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
3bd638bd-0190-4cb0-a3f1-7de71610b198 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
02691da4-35fb-4a11-8ab3-ec566dc61c4b | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
b2841180-667a-400c-b6b2-363f2826e918 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
bfe8b61c-6d2a-41cb-a337-8c60da0ca7ac | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
babbf408-caae-4fbb-9ba5-3609e58c43ec | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
c8eae61e-9f20-4bb2-b691-160e78626c9a | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | XFMR DECAL
c681123b-4b20-473d-bb7c-f7aabb18cf6f | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
c1a92c54-9344-4296-94dc-9a4ee053aa85 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
a902c5a5-04f6-467d-b67f-015295133382 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
92609d42-3a00-42d8-900a-c6f62ad88f9c | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
8f93aa1f-caa1-4ad6-b861-67acb766ebea | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
ed3fe5c1-1ee2-4792-a1cf-e667c191531a | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
fdcfeaab-dcdf-45be-9d3c-8ef2add63147 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
d50e5640-b3e5-4ab4-8fdf-7302c89dfb3e | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Needs above condition
d0383438-6416-47a5-8811-fa20f6aa4877 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
8cbf0acb-8fcb-4e4d-8525-68799c14afa4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
64a178e6-fa47-4970-b56e-0b49b0d1028e | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
07977cbc-9149-40e5-8bb6-4c9c151303db | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | NULL | NULL |  | NULL
58912729-0b81-45ae-8534-5733ae947555 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
f39a5c5a-a70d-4e74-9e85-b442019dd0e7 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
ed429bd8-3666-413b-a956-b6a4abd3c957 | Pole | 0 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
07ad58b3-fc44-4081-9527-611ef3bbea00 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | 2022-01-18 | 2027-01-17 |  | Pole needs replaced will not meet clearances if topped
d2f771b4-1fd1-416c-930e-35eab0a3cbe0 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
a9275406-a444-4867-b8be-c680679fb079 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
012e6b14-40f9-40ee-8b0b-129121bbe713 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
0179ca7d-c005-4946-8475-d588b6401759 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
51b29948-21e5-4747-a454-690d9129d040 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
f726b5d5-5780-4ec3-964c-9b9c75395b64 | Pole | 2 | Distribution | 2020-04-17 | 2021-04-17 | Level 2 |  | 2021-04-23 | 2022-04-23 |  | Pole needs to be changed out due to pole being deteriorated and stubbed.
0768ebec-fc3b-4135-aa8b-7f5b7db41a6d | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
6445f9f7-a93f-4d69-ba02-057c304c9d93 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
5009dcc9-f8c7-4b1b-8499-04d3947f2d23 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
424f1ca0-d53d-4289-a3fb-94a762bf16ad | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | NULL | NULL |  | NULL
53ad3a5b-5149-4e22-9eb1-6a7efbc43ee6 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
45c8f5a8-5244-496e-a503-1d2fee48c9ac | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
4c23040e-31e4-45c2-8037-3a0726091cbc | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
6a64ce17-1a36-4066-939f-33ddd4490f32 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
65fe869f-1899-4d68-99de-af301e37f52a | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
0a3b271b-1ae3-4423-92cb-0a6551313004 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
bccc86f7-f67a-40bf-b089-cef29c9c942e | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 |  | NULL | NULL |  | NULL
bdb06a02-45e9-4a9c-9f9a-6f2d6b471542 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
c23594dd-16aa-43a8-afbc-c6cbccc8a83a | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
cd18cfd1-b975-435c-b97a-26df11cddb7e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
92f0442e-a417-4958-9667-8c877e5d7921 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
85bb94f8-a5c3-466e-a765-7d91b7ab68cd | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
d9d62337-45f1-4842-9e75-2828497afee0 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
d7c82787-3415-4296-a1f7-c6ea3d73180f | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
e0fc6f4d-910b-401a-b303-6fc49c380c85 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
fc442c7a-2fbf-4697-baa0-40f4428d2ef4 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
190bc995-7a47-4d8b-8bc0-c7ef82381248 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
ee90950b-48af-46a6-9428-8f169b5d5c8e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
ea8b7c5f-6bd5-40a7-a81b-6d4995b974c6 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
e987f4f9-db2e-4b0e-bc85-dfc9d1490c04 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
f6f1cf70-f8c3-4f98-849a-ebac0797fd16 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
ef289629-0095-4247-90a8-e676f74b8c35 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
cfdf8038-78e4-4b94-a381-140a991fb875 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
85ea555a-b7ce-488b-96df-24a243705569 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
acbf2db0-d5ea-4df1-b4cb-78d4950758df | Pole | 0 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
cd271600-5414-4423-ac95-425a27d58550 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
561f8a7d-1085-49eb-9450-fdb1299f0f4a | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
3e00bbd3-243b-4eb1-a313-4e12640a95ca | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
10dff315-fec7-4327-88c1-332a4ed87c1e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
011fdb3d-c951-4a32-9f79-0bf6e20719ef | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
51eb688a-6040-43ca-8f5c-9e1d0f152402 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
1bb9f3bf-0ec3-44e6-bd52-5de556f2f7a8 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
affbb68e-abfd-4cd0-8311-847b0474a597 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
c4079f18-1e1a-40df-b140-3adcbf8a3cd4 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
a9a3b0e2-7266-428f-b4b5-5a18d8cae88b | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
7777d14f-f6da-4385-a437-e56f8241a554 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
0a76f961-1187-4364-b614-f4136c4e5c62 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
2395bd13-6049-4d62-9371-f6a71ae5eb56 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
29d73382-fd62-4c61-bb6a-f17dc156c53e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
2958caf4-a91a-46ab-a32e-a78524fe6015 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
7a15f696-2919-4fc7-802a-00a25ea0b941 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
767496c9-70bd-4f0d-8a26-ad435ffe667f | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
745b7f2e-ec59-44fc-b136-f0642b600204 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
56521823-2149-49ac-9d56-dc1d9cd34dfc | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 |  | NULL | NULL |  | NULL
2dc6ab5f-32b8-4a7e-a16e-04a265f731c0 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
3664cd3f-59ba-4d71-98e3-a13c02708d03 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
33a69be3-0d81-4e88-98c0-f23783f398cc | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
747b45b6-2e59-4d73-8b7a-17455a66a67e | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
2a7d5cd6-c887-4f4a-80fe-2f789e1a9ef6 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
2c7d5038-f946-42fd-b48d-7f28c4bc4498 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
1a5094ac-da30-40d9-b916-ccd79e47d854 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
1ddd7e6c-aa1e-4851-8111-dd3d765503b8 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
e2ca8f63-ca7c-4267-a107-589ca5e1b013 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
6b301545-6b00-4341-a430-7dfeabac34b4 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
1038cf65-c946-40b7-a2f4-77e5ec3305d7 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
58b929de-5247-448b-a68c-fe41b5e3b24d | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
2f95c48e-3d8b-426a-adc2-ea226366f938 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
1680450c-0582-432b-aeac-a5827ee1a94f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
a73f63e2-0bdf-4362-84b7-f2aebcb3eef7 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
e87f2462-9024-4202-bef6-a8216a7b316b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
491763eb-a112-4dc5-b552-a84fe7eddf9a | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | Dead end pole
44a42916-abdf-4565-acb7-c47e84e88d4a | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
fe1b98fa-0479-4aa7-bde5-fcd6b95614b0 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
f2cba526-375e-4a99-aaa9-432169446cea | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
b4272723-6a32-4de2-b80a-58127ad84b42 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
d8f5c361-8ec4-4580-806f-0696447b723b | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | 2022-03-09 | 2027-03-08 |  | DDE
d191e4b2-3e69-416d-b7e4-1701b534e01b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
d3b55c3b-f849-460a-b00c-d876394ffe3f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
9fc0ffa7-335e-433e-8a95-79934889322c | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
9f5194d7-7ef2-45ce-8f61-268b60afca3f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | NULL | NULL |  | NULL
9ed46254-7134-419e-adf7-387fe6096557 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
aeae9bb5-9123-4117-af70-cb9341ba2f26 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
930af33b-56d4-411c-8946-dadb7fca5b96 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
9b520188-af2f-4ba4-b57d-9d3191ca4711 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
cd44ea95-389d-42d4-9258-541932298835 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
ce8baa4c-bdf0-4539-b3f4-ea531d8c0858 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
bab31805-c363-4d70-abb9-663a5ee51044 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
c83c26f0-2b58-4a77-88dc-7cbb227e131a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
d2f2e459-deb6-469a-bfb6-688ad81186a7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
e02c0192-81e3-4a0f-b8c3-8d4066e6fc48 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
f7c3560e-1e28-4228-9b91-b32216ee6422 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
e86dc3ef-e925-45c9-ab5d-40a022a01820 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
79a5ff48-4ab8-49ed-8b27-179c5a018434 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
7d90a458-b5d8-4e50-b1e1-e8902f317992 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
414e240c-64ac-4243-adfa-6f3e5b2033ff | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
968ca7e4-8732-4a66-827e-a1f034d16d78 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
9b690f08-76b7-4fae-bd57-13d2474b0ae1 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
fea88618-8b64-4a43-8887-09db6fceb5d6 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
ffcbe9f2-5a40-4740-9ead-27f63142b2f8 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
8df3e928-0f3d-47cf-af43-1ec84f821bdd | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
d78e72e2-1767-4299-a45b-1f2caff5907b | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
0b975f68-e109-4084-a542-6936e358ba21 | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
09d5ec18-7ed2-44ae-898e-43cd5a2e90c7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
1315b189-4810-4252-9e96-1832f27bfc2d | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
78e905ec-0006-490c-94eb-bd55dc617a0a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
67e7d1c0-4255-450b-ae74-720a1c6d3ee9 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
6ca4fe7b-0bbf-4585-aace-3726f01d34d7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
593da27a-be52-430e-864c-4f96bbfa6500 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
41373813-f3a1-40f3-8b6a-51620bcb51ad | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
3c61f6bb-f2f4-41c5-b74b-1c9757a85d76 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 |  | NULL | NULL |  | NULL
3a9c8c7f-7d31-4f66-a114-a8335401f4f9 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
594207b9-1c2b-4223-aa8a-373fb19e1cc5 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
5ff8551b-994d-4812-9976-1197f80619ff | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
6770e7a6-9df6-491d-bb4a-6c73ed51106a | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
693ad4fb-5e89-4305-8f19-febad96819e4 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
79fcdf9c-1b78-47bf-a59f-09843066c16d | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
7c3f9750-2aa0-4eab-8269-bcf940f3d658 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
76c823e1-20c7-476c-ad3f-082f1f2f5312 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
78705628-d02c-48cc-aa99-f45ce803a379 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
14a8e0e7-64a6-4d57-b6fc-60fbb6db1198 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
1189e360-cf6c-441a-b1b2-7181b6b3f818 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
1728d1d8-5718-477e-ac21-40d1f50dd7c5 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
17be4394-07a7-4e09-bbd5-b7757f645743 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
0e895f7d-aa31-4248-a239-54b5ba0bf69f | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
1b171de5-2db1-416a-891c-4f7fba14fa64 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
6d7638a1-cfe7-4341-aa28-62b098dbf121 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
cc0880ad-3986-41af-8002-c42769af9bfb | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
30e3df49-05d2-40e3-8337-67a1f890dcd9 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
34febe28-5276-477f-8cba-9171b96fee69 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
0aaf83fd-8545-4826-85d0-71e05450a684 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
2d616e43-f43a-4608-97bd-40131d8fe579 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
4fb90ed1-9a09-427d-9f06-4ad972bf6ec2 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
cf1a3e34-e802-443d-bcae-87a5fa9c495c | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
eaabc6a5-7887-4001-b7ab-b68af62b6af0 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
f7496b4d-e984-4905-8964-65b60f15eb6c | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
fc00541f-050e-4859-bd85-2d37d2dd7880 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
e393b4f1-6870-4767-8bfc-6fa2017dab2d | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
3c571e2b-540d-4e9a-b23c-941815925a0c | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
c9b78ab8-6064-4095-a9f9-c124c6865c5f | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
c38ab4c8-f8ff-4694-a012-43c8cad96184 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
65ea9b8e-ebd7-468f-8e2b-a1e84a2bddb6 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
90cf3f03-79ed-4b75-87d0-18f727d55766 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
83df61ef-a37e-4127-bc92-40be66c53d09 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
8f0fb592-05a5-453c-9458-79743e63281e | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 |  | NULL | NULL |  | NULL
8c6222be-80ae-4c20-8175-fd6e02588f74 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
8b339ae1-63b2-42b9-879f-1369b547f46d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
af059ab7-70f8-42ed-8863-864a800daac7 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
b535aa4b-763e-4e94-996e-2e4b218884e8 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
cdc89234-0185-4242-942f-12f4bb17161d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
b3aa5ff1-2e11-4fcd-8bd5-d3b365476aef | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
dc429a9a-de94-4609-aa9d-e399944f899b | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
d6ccb6ed-5d8e-43c3-9369-95f01c2d5fa0 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
f438a777-b494-4635-a6c7-209a0a40d197 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
7df47d11-625b-4dd1-82b9-69cc53395b36 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
22263dcf-3c6a-415b-b628-cb3020a24d21 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
4dbec616-d185-4342-ae3c-bda82bd2db1f | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
ce14771e-9686-4d33-90ce-30fdb3b084d6 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
70b70a5e-143e-4355-bff6-e4a5ca6bdf77 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
031e5e33-430b-4ee5-b3f1-ff553e8ef611 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
63a27cc3-61be-4796-8fc1-cd5e2f7cdaf1 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
636a0edc-2a68-457d-8ac5-0132755ff629 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
5b2dcaa5-ce5c-4b28-87e8-91db4577ff84 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
56e6d26e-f56b-488f-aebe-ae32f72cae50 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
468f77b4-aeba-4c1f-b80e-465c1d3e4e2e | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
4362f727-1e3b-45d8-ac26-34f497563152 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 |  | NULL | NULL |  | NULL
32b9b9a1-4096-4b4d-9b79-0b77845dc752 | Pole | 2 | Distribution | 2020-04-25 | 2025-04-24 | Level 3 |  | NULL | NULL |  | NULL
35231c4f-2d82-4ed9-8941-f3d334697e52 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
305760d3-ae78-40be-9883-9813964cc033 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
47a7d44b-9b90-4b65-b4e5-f893dd2f2e8d | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
4d87377c-721b-4d68-8e25-42c016158f1c | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
58be6e1d-4c82-4459-9369-350933d98e5a | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
64630b3c-53f9-497f-8e2c-459d02c7ab55 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
62140000-74be-412f-a13c-323014773a5f | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
78bd680e-0b2c-47b1-b275-f41547a0c3a2 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
052d2dca-85a3-441f-bd7b-1c872bed5b31 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
14e64303-7777-4f98-a2cd-11d4d0b78db0 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
1906ceb7-2181-43ea-bb68-72b0f275c8b5 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
19f52d03-65ae-47fb-968b-8a6af7f6974b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
20b078f5-16e1-41e6-82d1-906a27abb805 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
1513cbde-9513-4a2d-b368-c118048e6255 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
18471bd1-4e36-469d-9510-377de789fdb6 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
1add986b-aa20-4c3d-868d-fa81f86c3876 | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
0b20744c-7ce5-46c0-8662-d6ced55ce383 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
e09d463f-2b2d-4cde-83c3-31f82e066b68 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
b5ef5c4f-9165-496a-bd80-f8f3312b493b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
358dbb48-3405-48d7-a534-aa2998c50fb5 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
0cb86daa-8b95-44c7-8511-eed3b1ff75df | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
fdf225e1-57bd-4723-bd69-b9442cedb160 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
15e04300-3efe-4048-b1f4-8dd65b10999b | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
896e8a26-5c9f-42d7-820f-060d929235d3 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
f346c9e4-0241-454f-8168-f46c74cae8c3 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
f947711f-32df-4c92-b4d0-ddb1d2ee18b9 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
193ecc48-f145-46f7-afb6-d7323365fdf9 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
ebc04b78-716d-4f65-abc8-f6a8510b86e1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
d7a5be38-5c2e-4e16-98df-e31ad6467bed | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
d25291aa-f01a-4bf2-aff3-b3d8388fab22 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
d3bd90b5-ec10-49a6-a840-1dae9da3dfe0 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
e5408b23-06a0-4889-9cfe-1459aa63425d | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
e6f5fedc-e6bc-4424-ae7b-690392737d38 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
9e5fab15-37da-415f-8f67-0d4e209faaf1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
a58e9d74-fc1a-4044-9f60-0dc239b4422b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
893968a9-f7d2-4c0f-b312-20e4d5d4a1a1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
85e97c2c-4a72-448a-9f6c-05ac725c2882 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
86ad855b-a238-408a-91c7-0cfa0f2641ee | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
8781a40d-2fa2-4ca4-9073-7d05247afe3b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
96d95561-583f-49d0-bdc1-6f4b9b60c165 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 |  | NULL | NULL |  | NULL
87965bb3-6c6d-4ccc-bb48-fa2a349c8484 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
89e32e9e-34d5-46ad-93f5-5c81514796f7 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
a589524d-986f-4ccc-8eb2-221838a26ba8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
a331fcfa-a745-4e38-9ff8-696690322020 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
abdccf8b-0d55-4fce-a61e-5237525935d1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
aac3b5d7-4eec-4939-8f72-97303baa8232 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
aa752864-76a1-4ecd-82ce-20979837f59d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
af3ba445-3fc1-4727-8471-2d77b11eb2d3 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
b1a2b2dd-776c-484f-a18e-0c1c8aee0c98 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
bbe541da-1c00-450b-b3ef-39beee439c05 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
ce2f3699-c7f4-4fcc-ac90-d21d2f3d8861 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
c9fb3f22-fb50-45b5-a1f6-7341c660bdfa | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
83160693-5a95-4aa8-93c1-fcf36d4afa60 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | 2021-03-03 | 2026-03-02 |  | NULL
c44b7643-4161-40df-b44e-54de45c0f367 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
c886beca-9c20-4a89-b578-8a6e93e503a8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
ea53d1ec-7868-4080-8364-2ca69227cc1d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
fc186ee5-1475-4748-ba65-5b858cce0ce2 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
f67f8181-c62e-4d90-89b3-65fd89d4c45e | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
db916691-1634-4971-b061-0f57059d73b5 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
003532a5-f874-4897-86e2-01d263236200 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
f9bff972-e071-44b8-b006-3aa7695e8c1d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
c8dd21e1-80c7-4423-b8b6-bce86b47a8f1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
bee7947b-f1ff-43ce-8cee-9063fc018f83 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
adcd4bef-d719-4c53-a2a7-642f425852f6 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
520771fc-2c29-42a4-a70e-0145754135a3 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
9321a826-8036-451a-aef9-c8dd8b9ea4a4 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
4069606d-04ed-497e-a25e-884ebd7bfbe5 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
15171492-6852-4719-a1aa-18c406ae8fd8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
fea01f17-a03d-4af4-a45b-7a4782fb1f10 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
2110b418-c40c-44c4-87f5-1019f222072b | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
1569a903-0015-46c3-b11d-f88e6b9b0587 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
0d056eb0-3bf1-4fa6-b47c-01880a10fb9f | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
08da7db0-5556-45c8-bbaa-9e6b1c70a52d | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
47eff5b4-e383-417d-87c8-2ae90b78daf6 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
c33c1b73-5222-437f-9258-b4814fc9cab9 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
62c3fda6-08bc-45e5-8acf-64d416454ffa | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
2e895b5c-d700-4386-9ff1-635f4b0e2494 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | NULL | NULL |  | NULL
41be9fe7-698c-4043-8c26-d6ef61797c6a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
4fcfe9b5-fe35-4105-bc41-d71a14ce63aa | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
46e1c6a3-9e32-4d82-bf99-baf27da9ddb4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
4273e01d-0147-43fe-9b71-7bacce3b1b42 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
443f664b-94f3-4d72-a10e-3a2e41625171 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
58fdb083-cfe6-4863-a8e0-88360b46afc0 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
7bbeda37-855e-4278-a5f7-15d0f8e2ff1b | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
7cc032f3-dfd4-4616-ba8e-78652c921b5c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
83add555-73b2-4af8-b989-23ad42284190 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
dab140af-faa1-4f0c-83c8-3ef77cafb1f9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
20d7ad77-0388-405d-8b5a-2047e3da4021 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
1f5e92bb-7e8c-4628-93f0-4678b01822fb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
27e7ed88-e29b-442d-9c11-4cddbcb21692 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
28f857f3-5c8a-4801-b154-fa774e3decf5 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
e55c30c6-d89a-48f4-b58e-81f9225c325f | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
c54e1d26-1669-439a-94a3-c85444c46491 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
837080ef-05b3-4ad7-a623-e84c4ceee013 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
1fb22a72-3638-412d-8b1d-7e382dbe9a28 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
53b8cadc-146d-402b-935f-e9e4be740132 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
7eb651e8-6f7d-4e6a-abfa-1348b20eae85 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
a7552d2f-c6c4-47a3-82be-fa035cc237c4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
d5cf375d-7ca2-470d-a1ad-6c35294240e4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
92a0b3d8-e180-4d0b-9528-42d1e72823cb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
f8531135-6865-4a21-8838-5e5df384c415 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
eccc256e-e031-4584-a793-5a2cc85592dd | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
e50d8b8c-b58e-4a77-a4dc-618468c9d4dd | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
e6511318-6b17-42df-bb6c-2af709525f8a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
e5ef72ba-a80a-49e6-8809-5298f6f42351 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
c77635b3-e156-48d4-9908-34bc7f1d966c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
bf701bbb-1174-4420-96a9-9f16db9bbc16 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
b1cdd578-fb2d-4458-9b88-2349c7ed84e7 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
b13ab5fa-4cbb-4511-8bdb-6dc7afe376fe | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
9d2004b4-40db-4e87-822a-a2851681477a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
30a775ed-e367-48a6-ab67-49d03fe62ae9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
9a6b2120-3d3f-4281-aa73-9881e38340e9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 |  | NULL | NULL |  | NULL
a23b456a-f53d-46d6-9e66-600e6da1e621 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
ab516081-6c3a-4456-ab89-7faee59e4a20 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
c1136a3a-4945-4892-b3d2-0d15e5fb6b24 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
c79ef9ab-12b8-4505-b97b-d7b8e6264fcb | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
d4e7342a-ab96-4da6-b6ed-a462f7ac45d1 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
20e3a89e-fcac-406e-b0a0-daeec355ce16 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
91a1d565-acdd-421d-bf4d-96abb48027b0 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
30dbb492-2a83-4816-be14-3e8a88609e48 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
0e74556c-089a-4d47-bba2-be11f351b6b0 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
13381093-4e8b-4428-87d7-f02868751e23 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
30c90825-1c2d-4664-a008-e7a370d3e8b4 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
7155a2df-d460-427e-8609-99c4e0340b1c | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
5b043478-833c-49a2-be8a-e0c76ff83b7b | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
5be6da19-ee26-4bd5-ba31-722099741d01 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
67c19923-31a3-4cdc-a311-9a2b71708c74 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
6bf162b6-cbd1-40c0-b617-b4cda4bddf27 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
6ad6aa60-8d22-4530-b319-499b4d2d77f7 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
430f64f7-a95e-4e5a-8aec-2352fde5a289 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 |  | NULL | NULL |  | NULL
57d32883-1cc5-479f-b42a-e3dcf3cd5f06 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
52d63da3-dd2d-428f-b1b3-a1c31d503460 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
3c182798-e4eb-44fa-91f1-443892bc1d1e | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
2228cfd3-67ea-4ffe-ad9e-5f3a135245b7 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
bbb934ec-fe27-4061-ba82-6b77deebab01 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
147cf57c-8f56-4434-b71d-f9bb704f4172 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | 2022-03-02 | 2027-03-01 |  | Service to night guard light has been abandoned. Light not in use at this time.
143cb5b9-da5a-4e87-a81a-cbe730b6d4fa | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
0c68c2b7-45e9-4333-aa11-72e744a70032 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
f99f9a2e-8115-44d5-9ed5-d9e8dc00feb5 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
d5720fbf-c827-4d09-9abe-8ee9fcbeeaf9 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
90799aa6-b524-498d-a18f-795c5aa77db0 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
d9f903f5-d11f-4dca-a9e0-63cb69f961fb | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
db182d75-dbba-4957-adf0-58c264fc654b | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
c165a378-e034-47c4-a56c-a8793eac1a90 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
e0be06f9-e0c3-4c95-9268-cc3d71afcaf4 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
513b111c-abdd-4e56-9431-bda8b50ed367 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
1d548ab6-014a-4ffb-b7ce-e383eac221e4 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
7e1b6587-91ed-40ae-8493-245f60b3df1c | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
8e2c75f9-0cc2-4c3b-aec3-11e79c446ec0 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
8680a7bc-3b07-4c69-838d-929539cc1b92 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | NULL | NULL |  | NULL
aad29f10-8a17-4176-b81f-8f3132b93043 | Pole | 0 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
c5b926bf-86fe-44a2-8625-7488281a4644 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
8b08687e-5a25-47c0-9739-cf881f303a81 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
d934a254-bca8-4aee-bb4c-769dc670e1fd | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
b6f9b765-443c-49b0-a3e9-393b024e99af | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
99488eec-fbde-4a5c-bc28-a0f48dcf60ef | Pole | 0 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
1ab641ac-174c-4edd-9ccb-23e3e8922632 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 |  | NULL | NULL |  | NULL
2042c71d-3113-48b1-910d-3a5598d405f3 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
0ba5aa72-29e9-4786-9d89-e3bf6d83b5f2 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
0f76feaa-1666-42df-b7bb-d36a97fed275 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
084175f2-7bd3-40aa-96d2-b8366849f297 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
1478225c-52a6-4954-87c1-e1bfb2507b9a | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
17d25510-a18d-4cd2-a779-0f43ee01bf88 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
d9683e52-99cc-442b-b18e-dedba6870a25 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
94cb8661-cd32-4726-a160-a3963fe2ada5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
6cb8822c-adea-4d81-aaa8-4ad0207d5e1c | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
5dd658a5-7315-445e-8e33-a68d54a67628 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
2d21897f-fcec-4149-b276-f3cb466dbb27 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
3f9489a6-3a02-4738-9db1-fa247d4ac3fb | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
58e646eb-e8a4-4c0e-8c6f-b6c31c791770 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
54a954dc-4fa3-4bbc-9a0d-254206958f78 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
8f515682-dd02-4e89-bf77-494cf254e3a3 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
c069f8a0-a04d-458f-8563-97a792681d37 | Pole | 2 | Distribution | 2020-05-04 | 2021-05-04 | Level 2 |  | NULL | NULL |  | NULL
bae7fb8f-229e-41b3-8fc6-aa9fe3416dee | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
eb254225-642b-455c-965b-6b1b80619fd4 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
837204a4-0758-4fd1-85da-326293832aae | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
11c3ec88-c92b-4b75-8c48-e16a5ef250de | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
d4641a33-7d4c-4016-be19-80a2a185d123 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
a7960325-9bc8-4dc9-84ba-44d10be9929f | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
3a473451-21c9-4248-9874-445e3a453a20 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
46580a1d-244b-4ee5-8c52-7aac3429ca87 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
0ac8c25e-5b2d-4874-83cd-b21898375815 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
3dce80fd-6022-4f55-a4da-911a2b56475d | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
576ee34c-4d43-4718-b9ec-0b9a586205c8 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
5dc8dcbd-7e28-47cb-a413-682c7b17d8c1 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
ca9ce774-70d4-46dd-89e2-352d84fd9c0e | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
bb4cff05-4607-4c67-b0ff-28be0df77de7 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
9ebe9fb2-4c28-4c29-be37-4f6d213f1649 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
37c9345a-298b-4db9-936b-4f3678d68780 | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
a1985791-bec5-475e-ace0-f2c81d22227b | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
a3693937-3182-46ec-8110-dd9917ca1cc5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
a41c06be-6e87-40e1-a6eb-23e988908819 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
e60892f0-eea6-4860-bba2-816c5df82afa | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
f57052c8-6f90-454c-9868-f4c49bc18d23 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
ff17b4b5-af21-4aea-88f1-59479d8b8c34 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | NULL | NULL |  | NULL
e6483c6a-5b35-4605-83cb-047fa5b5dd2d | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
a11ff7ab-6c0c-4b67-9dc7-1832bd85d5b8 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
8c7b0d52-f92f-406c-ac3a-2fc49d3b9a29 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
be273a27-9dc7-49aa-aad0-8e2d917f8d3d | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
82536ea8-9d81-4e03-9db3-b8f8b7071001 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
b4175150-c61a-4755-8afe-19749612f1b6 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
428b1e74-9274-44ef-b7d0-12775d24fa8d | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
463ddb6a-0edc-445d-b4c7-4f4a9085aec4 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
4e59c8e6-ed46-45f6-ae8f-f05927fce800 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
6eae9dde-cce3-4f19-8c5b-d070f21b9e57 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
608c69d6-a5df-426b-b1f6-08687a993aa1 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
4cd2fd2d-7805-4640-9f59-b3de4e2bc24a | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
08b20688-f7a4-4a51-a737-20485ef672eb | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
016f8834-03ee-4296-bd93-bab2873a2ac0 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
ede2f44a-5ef7-4a40-8348-2aec92768940 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
81459025-1b79-476f-adc7-af20e9d8c7f9 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
46fd5cd0-e01c-4422-95fa-729a9b59c745 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | 2021-05-27 | 2026-05-26 |  | Need to remove thimble bolt
6c4ca4c1-4ba3-49a8-b9ae-4cefeecbf104 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
6919f6a0-3538-481e-9dfd-2950dec89825 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
650ad662-ef52-40b4-80c0-34220680f3e0 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
1ba0d940-bd62-472e-920b-b86b0616188c | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | NULL | NULL |  | NULL
235a2e58-1007-42c9-ac95-a928de663551 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
2418d01c-9971-40dd-b125-c30a27636ba5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
17728c14-68ab-46f6-9495-8176955dffbc | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
1064b926-749a-4270-be28-9f405174c5d8 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
7bd01956-df26-458d-b9a3-278c53710e97 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
820e8a3c-6065-48e7-a24b-5c4ad6a3c509 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
65456cc0-25b1-4dab-9ee1-298f7c3c12bd | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
f6cb001a-9f44-424f-97ca-3827f23aa9de | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
6efa98bd-2c4d-46e9-bb45-897e5fd2772e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
4b0b0d75-3f5d-4893-81d7-65b13c29a2ea | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
2fac3e3e-54b6-4494-94e6-dc128cfe3764 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
9727fe7d-767b-4390-a517-c0c5d42d918c | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
b7d572c3-f401-4c97-b557-e4960e9f13c7 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
94606a0d-c0db-48a7-96db-7bbebc17da4e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
1a8c4fcc-6520-4df7-9c6d-5f5eca9b4f19 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
e97989c3-0227-425b-b15d-4280c14cb383 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
f9c7b66b-de01-470b-a6b0-539f32715790 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
b38179b8-df64-45fc-b9af-4cb462bbb102 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
1fe5f67a-d7cd-4576-8c80-907b24a887d2 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
cb721eb4-3536-4225-a2a7-c99249a8a59e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
74588346-5a86-4929-bbba-e2b44332404a | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
7f7f356f-1707-4f47-bfc6-749ab2a3c90f | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
18b77001-1728-4d75-ba2b-c916a2f57d0c | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
874bfd68-e89f-4621-a4ac-d8d59b2200f8 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
a2d850d9-f0fd-4552-936b-94f695fe6863 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
e0f3279e-e97d-4e6a-9bf9-d79700f70a45 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
d988cf77-27da-49f0-b8f3-acaa4ab7f216 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
e9b6ec95-b731-479c-897a-f7d556dd0740 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
eea829a2-e560-48c4-8d8b-32f40074ac26 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
ed3eb46d-2e0a-46ea-89ea-f0d599033206 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
f614e3d2-f5a2-45e7-9d2b-e3c6db5d6e94 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
fb899cf2-302a-4494-90aa-492ce0cc10c5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
fe3576e4-0013-4cc1-ac7f-382ffa9892b6 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 |  | NULL | NULL |  | NULL
f3d542ff-86e3-46b3-9317-60df2c91ccdd | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
d3f9e964-f3a2-47ba-b8d1-8617b4394edc | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
dba44d10-376d-4f82-a49d-c1bdaea8caf5 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
d753be93-1ec5-44b8-b922-75e5c7dbe0b6 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
be037e3a-a305-4193-ab92-b35574ffef49 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
e76b04a0-1549-4437-a020-cac09ec3f737 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
a1d31faf-ccfb-4ab6-b7b7-a6e3659bb1bc | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
84c1808f-ed0a-4640-b834-0fd864939323 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
9a5a27bb-174f-479d-ab21-c2071e6ab5f3 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
99c63bba-56e9-4a1c-9a93-311f7a2be91d | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
77a6c29a-7286-4357-88c5-e88abb2fffdb | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
bc2de546-577d-4c70-bcbd-3982b2ae1516 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
0b593546-fb59-452b-8f51-bda6849fa20b | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
087a548c-b2ca-4812-996c-539d0ac2951f | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
b676793a-7515-465e-8bc1-88ff76a3773a | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
bc6a8e15-dfcc-43ce-b08a-b48e58c5b56a | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
d28b39ac-900f-42ba-b1ea-60c1fe512d62 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
f2aa4ac3-5776-4e77-83d7-1c60a9c655b9 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
c71fa9af-fd28-49b7-8daa-c5b3185298c6 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
ad432d86-1a01-48aa-9f8e-3ed66ed6f288 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
acdaa6df-cd0a-446d-9025-0c999c961c0d | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
fd267ec2-1b23-4346-b8a5-9d866f5be262 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
5fade760-903f-4870-b54a-460a26bf56a7 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
29ae7109-7c6c-4ab1-876f-7873be1d9ee9 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
e359ac23-0467-452b-931a-34255c5fdd06 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
ed23497d-b31e-4081-a1e5-23088818abce | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
db01bd40-1567-4592-8c13-37a694287334 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
f6f5f18c-4a61-4141-870b-38e2e95651d6 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
bc768dc7-bbf2-4ca1-9233-d56341a7cd7f | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
b2c785e2-a23c-41a9-830d-fee4069d5e90 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
cc49f07d-2d41-4da9-ad81-e654ff424a96 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
4878e6c2-ac6b-4129-a566-11ca4cd42eff | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
43b2ff6f-676f-4578-9be1-a4784f1e40b9 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
4cf81b5d-9aa1-4a6f-9e7f-1f3635736e13 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
6b4ac851-152a-4cd7-b22e-bdeb42d6910c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
5c216429-df09-4067-9dd8-3ecfbc8a321d | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
62d9f053-507e-4d52-8f8d-296812263303 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
7fe7c6ff-a2bb-4618-b592-1a04ab96f255 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
3c7a1e4f-e996-47e0-8dc5-4cab9bfda021 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
adcd22a3-3967-4abe-9342-fd24d10b4b5c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
0a472885-8ce2-4131-92ed-98c0b602e0e7 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
b94a7a26-6cdd-4cd7-97af-900b7adcaffa | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
0f734ede-ab67-4b08-ac4b-238ea8069931 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
12b3159a-273a-43a8-bb97-fac8654984a7 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 |  | NULL | NULL |  | NULL
1b356147-041a-4f4c-8746-d356fe3f94bd | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
8c045216-06d7-4459-9b52-cc43d3176fc9 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
bdf9e004-1570-4586-9707-e5b4b61449aa | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
86fb0fa0-ced6-4c72-99d7-af0e126b4bec | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
63ae0f58-192a-4e45-beac-a4c45b78f7ca | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
51c0f373-154d-4214-9405-a977744dbb0f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
33559564-5257-4c65-bc57-d6b2e7cd39ce | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
f9b1c9c3-bb3b-486f-96f4-19b930b9e6a0 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
9ce10e49-3c4b-4e7c-8f46-4df48a42d12f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
fb4a757e-148f-4087-8683-6b0a354f583c | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
974f76a9-a150-495f-b6b7-a5563defb33e | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
8b861111-56a7-4d6f-af31-978d2a1a8be2 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
8696c674-f9d8-421b-8a2d-5532d8e1fefa | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
ce8f30f3-6da7-4ce4-b5b6-cb174cab6f5f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
c90447eb-aa47-4c74-9fc0-66bd65536d3c | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
c3c94409-f784-410a-9679-b141c109d0ae | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
b28ef08d-df94-4e58-b883-314161d25093 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
3103430c-6289-47f9-9763-f83bbd411174 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
25ae29be-4599-42e4-8d3e-5068934c3a24 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
b8585375-ab22-48cf-aa87-aaeab22f316f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
494b5a07-b74d-4cb9-97fd-d9f6a8e6074d | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
b82124c1-708a-4f0a-bb54-392ece6e05ad | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
1b185877-7b36-4480-bc86-c5c202de6492 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
7b7ad3bc-6ee8-4da3-8ba1-39bcaee2ff33 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
cab9b05e-dc1d-4803-9b71-dccfb5f12d23 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
cd115a8a-b0af-48de-a7ee-55af3c97f726 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
6d5824ba-7dd7-4361-b612-39ecf4c43161 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
743266c2-5a3e-43b6-9eaa-3a7e2d84499a | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
924873f7-8324-4c88-87d0-56ae1b541427 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
93e262df-8418-460e-a1f5-6c19ea22a16b | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
854a7c06-8c13-4385-bab0-1dc63c5de6f4 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
86e0983a-7b3a-4457-a319-a061265aae09 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
a3941a41-fcd9-4bc5-9366-143afd5a4766 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
a5bdce12-8234-4147-aa95-76aff7277f20 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
e439c010-30d2-4f2c-9e2c-df2c4bccf5d6 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
d8fb5c1a-36b4-45f0-8fee-7b23c51089f7 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
caa57011-9cf4-4fe6-9971-a5d394aa7353 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
ab5603f9-761a-46d9-9507-6f0026706245 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
eeb87e1a-a320-4c65-9b95-42224a8c1486 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 |  | NULL | NULL |  | NULL
9b064557-13ca-4b78-964c-fc661059d18d | Pole | 0 | Distribution | 2020-05-09 | 2025-05-08 | Level 3 |  | NULL | NULL |  | NULL
b5cab04c-9fd3-4a11-8662-3a8de9c45116 | Pole | 0 | Distribution | 2020-05-09 | 2025-05-08 | Level 3 |  | NULL | NULL |  | NULL
a8a670f6-3efb-47a8-afb8-07313639c21e | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 |  | NULL | NULL |  | NULL
d3fa00ee-bb8d-4159-bce4-c69e392a3504 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 |  | NULL | NULL |  | NULL
cb8665d2-7ee5-4682-bf3b-15a5c505b0cc | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 |  | NULL | NULL |  | NULL
5845bf12-b2f5-49a8-9991-b61e94c174ad | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 |  | NULL | NULL |  | NULL
69e3eadc-54cf-4204-b5cd-28aef412dde8 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 |  | NULL | NULL |  | NULL
7f961c1a-6c7c-4797-9760-4dc9a329062c | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 |  | NULL | NULL |  | NULL
753180d6-ec1f-4684-a1af-50050a72cb3d | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
4fd236c0-7fe1-4b44-9d65-344d7c936ba6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
4a358beb-6d90-4744-9e31-a1b6a212ecea | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
379b5736-0e77-4891-9545-3cc3a20739a2 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
3b4cfe3b-401a-4956-b4ab-9b80bcf1c13e | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
afa326d3-bc78-48ed-8322-394624533157 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
1b6164e0-69ec-4d84-8a13-49f4469860d7 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
1e442a4c-6904-47b8-adf6-0df1ad10b047 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
2d7bffda-1adb-4972-9742-569fc916e561 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
0e13fb79-1f4a-42cc-a4f2-f95ff17d35b6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
c7c316c7-69a0-44c9-a178-34d0c93ce210 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
b326dc47-51ae-4702-95e8-84a9f1607487 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
a71864ea-0516-44f6-b339-6f40e46af0ea | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
8ed2adb7-dfb9-4581-8d9a-012d27f92d36 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
8f82629c-9eaf-4e4d-a648-31e6ef66e984 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
91d48b43-a333-435f-b2f3-a99d328df695 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
d56cdd82-11ee-437f-8158-c22ca24cbd91 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
e32fed23-ed08-47b2-bd4a-75d6d27c7068 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
e6cc5012-fa93-4dc8-a9b9-ef98a63d4db5 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
fd5d8217-62d8-452c-963d-8dc312761640 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
8d80af29-cee7-42db-b2ed-17324163acf6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
aa1af4eb-7b46-4d45-92a1-2693d1bbe70b | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
ccc09d29-fee6-4267-bc86-cece4a79f36a | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
bc290678-eed0-4999-ac82-496fd9598186 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
64936060-0067-482a-822b-2d137dcb1867 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
77161aa9-b9c7-4a74-8dfe-7809c72fd552 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
73849316-6ee3-49ff-a442-56599d17825c | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
8bac5bc3-a5ac-4c48-af13-76fa21690590 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 |  | NULL | NULL |  | NULL
9be6cfb4-6006-4c13-99c5-971d5f1c31e2 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
a61c9711-dd4e-48cb-92f3-4fbae07448ff | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
f209ccbf-5469-483b-9a5e-3c813f456fbc | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
e0eed9ca-a8e0-413b-97e5-dca44df97395 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
9ca3a0ff-6b2d-4cbd-83dd-c7fdad2b6bd6 | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
a5c833b2-094d-4951-a7fe-e4ec3b9e005d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
b91850f9-27f5-4632-b7de-7a4bc61adb7d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | 2021-07-18 | 2026-07-17 |  | Need HV sign and to inspect neutral Hendrix top to be melted
b49fc804-557e-41c2-9ec2-03a0204a3e6b | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
2797543e-f9e1-4cfc-8b11-8cc8ab73fd56 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
3d23236f-de9d-48e0-90be-22227b8b5c34 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
04ec83aa-2194-457b-bcc0-14614f6dac2a | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
04ec7d19-0ad4-441b-84ba-190c4c7faefe | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
354b21eb-6cc7-4319-b900-271bbd3866f8 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
326caf54-c51c-4d5a-bb0c-46bd95233ff2 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
32b1bfd8-4d3b-43c8-a65a-baed2746be8d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
462d1add-2cfb-4921-aa82-cb92b5cae146 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
7869b44d-4be5-4876-b651-4bb059d61a39 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | NULL | NULL |  | NULL
7b4e004e-5e0e-4cee-a456-09ab935df573 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | NULL | NULL |  | NULL
e13149d4-fde4-4285-a12b-dfca8e9e9096 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 2021-05-28 | 2026-05-27 |  | Need guy guard changed out and new HV Sign
1f23bf72-744c-40e8-a47f-d60ff72e09ad | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | NULL | NULL |  | NULL
d46971f5-bd54-4962-bedd-af1b7e5cdfa4 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | NULL | NULL |  | NULL
92827999-fa1f-4e4c-93d2-b93e5453f065 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | NULL | NULL |  | NULL
05b6dca4-4d19-46c6-8462-bc0fdecc75d1 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | NULL | NULL |  | NULL
1b1a4e68-8650-4314-9b30-d2810dbbae26 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 2021-05-28 | 2026-05-27 |  | X-Arm needs lowered with pole top topped and new split bolt installed.
c7a86051-62f5-47b9-bbde-77adf7c75979 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | NULL | NULL |  | NULL
a7b9ac68-544e-49f3-8ea2-a6f522cf73b6 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 2021-05-28 | 2026-05-27 |  | High Voltage sign installed. Crew to change out insulator
ad010ba3-457c-4624-a5a3-b173a5995b91 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | NULL | NULL |  | NULL
d80e0c4b-16c5-4d4b-9fdf-6db86c2d1426 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | NULL | NULL |  | NULL
ec18621e-b025-4de9-af07-db20384faab7 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | 2021-07-18 | 2026-07-17 |  | Pole good and intact, missing above itwms
8f3369c2-dba0-44b0-afe3-7a77978017b7 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | NULL | NULL |  | NULL
91549a1d-4b9f-485f-9953-ddfddcbe51ad | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | NULL | NULL |  | NULL
06e9d14b-d287-4818-b8d3-3397c8e89060 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | NULL | NULL |  | NULL
692dd435-25cc-4076-b5e5-4a927b917dff | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3 |  | NULL | NULL |  | NULL
444c6720-5675-4c55-b791-401109d52add | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3 |  | NULL | NULL |  | NULL
e3a70d1f-79be-4932-a296-a55f84df0ed3 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3 |  | NULL | NULL |  | NULL
eb175d0a-80d9-48bf-a4c0-6a515e2f7e61 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3 |  | NULL | NULL |  | NULL
aeb55969-9193-4974-a095-a94c53e77055 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3 |  | NULL | NULL |  | NULL
8a75bdaf-ca8a-4f49-9fc6-5dc687f0d0e6 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3 |  | NULL | NULL |  | NULL
89fa3ebf-b907-4136-8ebb-eb32238cb44a | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
fb639ec5-b61f-44e2-bdba-796b5490571b | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
fb4048fc-2030-47e2-b626-8570022422de | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
5f1d6604-7895-434c-8d0b-5f750f554b44 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
8fba3f55-a097-4e38-a568-12695c576fe7 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
452d3435-5fd0-43f6-9bab-dd0972a41569 | Pole | 0 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
53a03697-8ccd-4acc-aca5-ddbb1ab86fc2 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
6b8f67ff-67ff-4dbf-b318-3b5688c09ea6 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
8354e197-8683-48b2-b1ca-30d0da015944 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
e012bca1-98dd-4843-b9c6-248c74cdcfed | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 |  | NULL | NULL |  | NULL
24219567-b721-4569-9039-9d8da67cdb26 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
6cd22fb0-050b-4df8-ac7f-d45c3520d2bb | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
64bc557d-69ee-411d-80b9-965c38e24d50 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
560f12e2-fa49-4cac-96bf-f27c1762b310 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
44a5ef5a-0990-4c87-8642-ac9f22725b38 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
5f8d96f8-5dde-4237-822c-ddfa88d1853f | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
891678a7-8fce-4958-b836-933d5d8cfc67 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
9480f630-f5fd-4e8f-80b9-fa41724cb2af | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
fe96cde6-e725-465f-964c-1a786efce1ed | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
b05a5515-a2e6-4cf2-bbe3-2d377331ee8a | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
8b60f815-127a-4b58-8173-31d5f69776ef | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
92303dab-032d-492d-a17c-65cb6a12ed5f | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 |  | NULL | NULL |  | NULL
732b30cf-9323-4987-a1fd-018c45039dd9 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 |  | NULL | NULL |  | NULL
d7c3ff93-6fc9-4627-9bff-10a3b5f86ca5 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 |  | NULL | NULL |  | NULL
e6545e42-4c3e-460f-a0ec-9f8dac1385e7 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 |  | NULL | NULL |  | NULL
e09cc3cd-02f6-4596-b535-28b222f50d30 | Pole | 0 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 |  | NULL | NULL |  | NULL
d398af7e-ecfb-4696-b860-fe7984364c7c | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 |  | NULL | NULL |  | NULL
afcd25ed-80f3-4710-9d92-a76f02827438 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 |  | NULL | NULL |  | NULL
ce42fda2-e39f-43b8-ad09-b7da29f3b2f0 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3 |  | NULL | NULL |  | NULL
eb4e1951-4361-47fb-b521-d3f33255ed47 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3 |  | NULL | NULL |  | NULL
6c4fc33d-43eb-459d-8745-433d7e9736ea | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3 |  | NULL | NULL |  | NULL
3cf44692-62de-4a0b-bb8a-6e27d4f83e6e | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
227572b7-f111-42a7-83e6-19a059229dc7 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
0575f101-4702-4ca8-9bfd-27590b7be815 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
042ab82f-0c8d-489b-a416-94c06e104e4b | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
8863c212-da34-4eee-a1d1-2bf7ae2c1d60 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
c02852c9-0704-4665-94ed-3ab62e39d823 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
84322372-bb4c-4a89-b66c-df6c180fa8bf | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 |  | NULL | NULL |  | NULL
639d7211-e341-4be8-97df-820cc41c815c | Pole | 0 | Distribution | 2020-05-23 | 2025-05-22 | Level 3 |  | NULL | NULL |  | NULL
7d69b8a9-2c7a-47eb-aab8-3da6c2a5d175 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
56019431-6ed3-487d-8338-e116d210dbd2 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
8ee9b02e-7d14-4992-9708-1dd748ddb05d | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
22d87353-89d0-40aa-87a2-209c6e49f722 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
3fb5d623-1e1c-4717-8fa7-72dca553dae2 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
58b0355e-0c9c-46a7-a0bd-e9275f924c24 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
e7856048-dfee-476e-bc51-87785f15041c | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
c374e464-70a4-4a0d-a325-d0bc55efab34 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
bf9d2f32-faab-43b3-84a2-b18dbb39e559 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
ae4833bf-1fda-4e03-8994-6900c6f63ad6 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
aa2afc70-11b3-4453-a8ba-c475c13f3373 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
d9656d1c-f0d1-4115-a01a-b249ab231187 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
8619fd70-b12c-41ef-8b54-7dcf5c4788c9 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
15b027a4-45d1-48fa-a6f7-ee9afae5fe13 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
d5971376-5bdf-4766-ba58-2a2e23e648c5 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
f20ae222-1d51-481c-a752-8ca01c452f23 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
ec1fb059-cd11-4d13-84bc-31a81ee2ddb6 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
bfcdc883-a456-40da-bb63-bd1e9d510d9f | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
b7efc259-ca0c-4158-8d1d-19e19039dfbe | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
b445c7a9-27df-44f3-904a-da661b95d27e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
cbca5b3a-458c-4101-99b8-524b13c48d8b | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
8509e229-981f-4b69-86f6-cf19b8bedcc8 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
bf6fa54a-f59d-4cf0-8da1-8d7988b0e429 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
959bc14d-9d18-40d9-b530-7fea3b3dae7e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
aaf293f6-f244-4e31-b52e-b5820a9527b2 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
a51d1920-1706-4103-b220-fff42644f53c | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
f45f5cde-ec6e-475e-b0b0-7b7e550c8551 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
e2625e98-ad3b-4ba3-a1e2-85ed0a6db25c | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | NULL | NULL |  | NULL
d1362e5f-f700-4fcb-8614-62d0092f867a | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
a557eb2f-2b17-484a-a235-cbba6576dbe2 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
a6b9607d-2138-4d2c-81b3-f460bd0ba83a | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
8d2d86b3-ef49-4e9c-a762-b433a843cf81 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
9b911c71-95b7-4d18-8dc8-898ef9a00069 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
29810324-acc4-45f7-91dd-d3cecc49279c | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
91a28a7c-fe2d-4986-ab86-f27417a7a491 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
5db4f4b7-e454-40fc-ba11-227f09e3a1ec | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
784cee99-1e90-4161-94d0-e2550919cd1d | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
77e1e2db-23fe-4104-809f-0849d7aaef1e | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
0da8d208-acf7-4b4c-bc30-263e5c53ab80 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
0fbf518d-e1cc-4d8f-b1d2-535960d40d3a | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
13059a39-a6e8-4090-8e3a-1d1f8f576a48 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
80c21f99-d4ff-4301-b9bb-69b8b7163da5 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
6ff2debe-4365-4913-b15d-b63f5e6797ca | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | NULL | NULL |  | NULL
71491fe0-7d6f-4e83-8af1-d79095464810 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
6b27f451-f0dc-4269-a840-d75e5b34b566 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
131875ae-3128-4e84-bf4c-efdfc56713a3 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
61f6ddf2-94e6-40d1-84b4-630fc2a19a8c | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
9aa22f0c-03de-4aed-ab61-8d005899e06e | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
e9877be7-d0ff-4236-98c2-f0c2372624a6 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
8847256b-025d-455f-ba07-099b871ddf47 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
9535265a-04ca-4a09-b71c-f2a6b1ee6336 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
98bd8654-f5bb-44bd-87f7-0480159c6a29 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
bf8b8222-f331-4ea8-93e6-3249da62d084 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
ddee5057-698f-42a7-8cdd-1adbdd72fa29 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
fd8b8786-faf8-47f5-8792-5e667966c606 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 |  | NULL | NULL |  | NULL
d3024389-ab7e-438f-ba4d-933ef69e9d0a | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 |  | NULL | NULL |  | NULL
c9aa8721-2594-478d-90ea-a3cc79e75ae9 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 |  | NULL | NULL |  | NULL
3843097c-090b-45cf-a84a-0eccbae83213 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 |  | NULL | NULL |  | NULL
0612c414-af3a-4c55-b1b3-de65e27559bd | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 |  | NULL | NULL |  | NULL
c8ea586a-a2a0-4d25-bba7-ece86ef09e19 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 |  | NULL | NULL |  | NULL
47fdb50e-08bc-49b1-b030-a1708b0d993b | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 |  | NULL | NULL |  | NULL
584a2ad4-6616-4e53-a150-fd7da3df079b | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
eb8ea6ed-a522-4ff3-af56-edcfc06879da | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
04d42b15-f7c7-4887-be1d-39eedb6b041a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
6a481b6e-6597-42e2-b26f-388d05b0b6e7 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
2fdf2a14-0af0-4f35-b5e7-3d906b5de7f2 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
5a3f69c9-cd0b-4b2b-8547-e2c9c7154cea | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
3f117007-e7bb-4065-bf39-9358ce376e3a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
e891a2cf-274f-4f82-a8d3-ce36bb376abe | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
e80b276d-e60f-4816-848b-9b3fa22c5c92 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
b0475d8e-21db-46ff-be02-44d63d9d98d8 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
58b9b3cc-6110-4661-b21d-e7aae29f8c3b | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
ebfa42cb-ce02-4436-b12c-81348cdb782a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
2b0c58f3-f9be-4447-884c-1d88c8333df8 | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | NULL | NULL |  | NULL
0f9cb270-fb35-4788-a9c1-a46ff9aa712c | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
e97574c7-efd1-44a2-9684-b3d4c8ab40d8 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
adcdfe91-858d-436f-a41b-b179a0922201 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
a3b6a4b2-7c65-4c80-a09b-ccba8dc652a3 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
2b540719-fc7e-4b37-8568-85fdd48fb504 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
0b7d1737-4577-426b-b129-c5b15b3b7d4a | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
250e00df-d4d4-4c89-ae53-a9ca3157d619 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
212a8d75-764e-40bd-a7d5-384f98ffba3c | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
8ace8f23-17a2-4fbf-b272-d6ffe3a13601 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
9e4a87ee-5f08-4575-9378-715c9f8a12b0 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
1ca119eb-337d-43b3-a385-476e595df367 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
783733ec-4a1c-4608-bd56-3a0ff25bad90 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | NULL | NULL |  | NULL
7c0d85a2-2b45-46f2-bc55-51b7281eb017 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
6c3241ef-ccde-484c-a350-c79f6e612ad5 | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
30ce9bcd-9edb-4a38-9332-0219dbb0439c | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
4c4e9433-fa75-46d5-9b3c-3adf8300c6f3 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
a8896dd5-c2e7-4923-a9ec-4a27f7b43588 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
93c1acd1-18a8-4137-bfa4-aab9046cb191 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
cb32183b-ed20-4f04-a034-b443de2422b4 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3 |  | NULL | NULL |  | NULL
be1398a6-2afa-4363-95b5-a5b27b182f3a | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
b3ccb286-e26d-4f97-891a-f4375a0745e5 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
8e845c8f-03fa-4c64-9a47-101b9a8ffb8e | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
000d6554-53fd-4fd2-ba83-2102f1df719c | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
52af7a26-e7f2-4236-ad4d-f94de591db22 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
3d1d9cda-042a-442d-9321-3904889025b4 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
7452e2cc-3fd5-424f-a42b-11b56c9b9090 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
001b28b1-a788-460d-9767-d6b7fc992dcd | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
15251438-a773-41c6-9771-cb1f1f28e3fa | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
166595b4-e30c-477e-b2e0-ce3e384aa416 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
20a13a3a-095b-4343-8521-b05a83bc4990 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
8ad3f694-741a-45d0-b6d4-0618fbf19756 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
a16662dc-7d00-4b29-9f5b-c7b468958946 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3 |  | NULL | NULL |  | NULL
d6bddd38-89b0-4ba6-803d-d1ff74c6db1e | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3 |  | NULL | NULL |  | NULL
04b45561-b615-4f05-ad50-ffd9e7fe8e8c | Pole | 0 | Distribution | 2020-06-04 | 2025-06-03 | Level 3 |  | NULL | NULL |  | NULL
6c2b1a47-994b-43a9-834d-e072e7f77577 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3 |  | NULL | NULL |  | NULL
837e4b18-02ab-4739-b434-a15c44b6a8b6 | Pole | 0 | Distribution | 2020-06-04 | 2025-06-03 | Level 3 |  | NULL | NULL |  | NULL
aeb3343c-5028-4b3e-8073-ecc29fcc4678 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3 |  | NULL | NULL |  | NULL
c93df8b3-40aa-4669-9f40-067e31dbba44 | Pole | 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3 |  | NULL | NULL |  | NULL
02344e6d-83e7-49f8-9d84-ff2e35b3a6f6 | Pole | 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3 |  | NULL | NULL |  | NULL
21b47173-9eff-45c7-8b94-863a9f119792 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
2d72eb9e-2c3e-47e3-b598-f967379303fd | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
5f3d33ee-c093-4c0e-9141-38e119b7f936 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
7e1e834e-550a-4d34-b758-89eb071558ee | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
545b9cde-99d3-4a44-847f-cb4f2ebcbbb0 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
385011b6-e124-4200-b979-a6cceaaafe20 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
9ab0e5fc-be17-4b27-9b13-b6c5cf6ff9ff | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
d03c6be3-6cb5-495e-aa2d-1443451c09ad | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
e8c321d7-ef6c-4c75-84b8-e4f6a20240bc | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
acbf3bf0-9be1-4635-a9b1-1824ddb72572 | Pole | 0 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
ff2f1fc6-ffc0-4dce-913d-9b952a34a384 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
9a604bf3-419a-4dae-ad3f-96161468c058 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
f331ed81-87b3-4963-8bfe-c33ee6f51ca2 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3 |  | NULL | NULL |  | NULL
eb139688-455f-48c3-8684-e56a0b600a8d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
730291ff-fd0a-441c-9355-56f0fb97999d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
f4574e02-cfa4-4fb5-9a52-a395ce2863ba | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
f1ea5576-3363-4244-a989-f809b777f346 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
f7b05064-67bb-4860-869c-92da0fa42fa5 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
db67f771-1c69-4fca-9857-1a02fd97d909 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
db09e8a7-ce2e-48cd-802b-2335114cc856 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
e496fda0-9d29-4a84-a5dc-b0fcdb06f835 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
999a9a37-e93e-47a5-8e78-d100204d1dd7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
c81d314e-f947-4c1d-b4c8-94f8c78c991b | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
c6217fcb-1654-4cd0-9b63-a60d0c7f99c6 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
bb220be7-8f0a-4ccf-9383-1666ad64e609 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
b0eda230-26c5-48ba-8929-1e469db1553a | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
b48b4c59-2c96-4eba-ad86-6662e445bf50 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
3bab1843-2b41-460b-9e88-f2f1633828d3 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
34d88b01-6c39-4059-b5a7-699ae79b9d5e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
37841d19-9db8-4e23-bd88-3535b4ba739f | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
5484733b-c97d-4873-8d9a-0fde7043f4f7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
46fc78ec-48c7-4000-8109-e6769d8a5386 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
7c540a44-82f0-4e33-9597-c00f12d6dfd9 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
7c800ae2-0c50-4f6c-ae14-8930671bbd65 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
76bd49f3-4101-45b5-8642-dd7bfd90ce0c | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
76b4f43e-9720-4b57-a917-3b9b58aef381 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
6fb8be98-3328-4c21-9de9-58c62dce53ba | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
60214aef-2742-4cc5-a78f-0603ebd8e13f | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
6bc56f87-9b1c-4f86-9eb8-845b4e5c62ed | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
671f2925-2aae-4aee-a177-a5a1661638af | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
685e4d35-f687-4d42-807f-d1daa6e999a8 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
2548c863-b045-48c7-a426-a4ad9bea30b5 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
215ff7e3-c507-4041-97f6-a9a277dde2e0 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
1b5681ae-7351-4d77-a623-900390def3ec | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
1b1d833e-4a57-45b0-aa3f-2137df008f6b | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
06e4038d-c548-4310-bda4-3813c1460585 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
080401cf-608d-4320-839f-236e9050f19e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
0967767a-ae26-42da-9af2-f828eb3a33bd | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
1422c26c-bef3-402d-a3ba-17bf458470e3 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
170789aa-88d3-4501-a556-8f74a5aa40c7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
176e05d5-c420-41e1-997e-23940a2c0cbf | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
02dfe44e-70a4-4ac4-b452-a6b19d4da52d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
6291db56-a064-4aba-b92a-7e2156cba41e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 |  | NULL | NULL |  | NULL
004cc409-6767-4f47-922e-70a181b3111c | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
0599d14a-ff5f-46fc-9842-8026c3dbe721 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
0f8d7fb0-459f-4606-bc8c-edf30432c8db | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
2b78c450-4ae6-4a52-9a7c-7d1b460a800f | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
2b167978-5f9b-43b3-a44e-888e986516f8 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
2a69ee6f-0001-4da2-9451-0e86a2c1baed | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
6ff21d50-881a-42b6-adca-1c6b573e7570 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
73a96c50-d579-4516-ae91-fd5d8950e3bf | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
33894339-aea8-4535-b979-2ad380646a01 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
4116cfc5-4215-41c5-a6e1-850c32a5ec54 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
b9ab27a1-b4d9-4f4b-a303-ccebc36945a5 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
f8834862-2132-4dd2-9862-6ec011e234dd | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
f9813daf-7509-41ee-ad7b-fb9cc7afba5c | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
e646d019-6aa8-4487-b200-28079532c5d0 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
8b2796f9-8091-4815-9bbb-cb765a2d2a1e | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
ff453540-dd5c-44b9-818e-e76993a5ef01 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
19ae7396-66de-49a5-ac06-abd4fee47054 | Pole | 2 | Distribution | 2020-06-10 | 2021-06-10 | Level 2 |  | NULL | NULL |  | NULL
d43ec500-5f73-4518-97f2-675408b934cf | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 |  | NULL | NULL |  | NULL
ecf79453-46aa-4172-affe-23f89b20b9ae | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
f290599e-7bc1-45ef-bd7d-03007011e779 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
9760bf70-9b7d-497f-a4e2-edb0753d230c | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
cfe2ccd5-422a-400c-80a6-92875bfed708 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
927a0a7d-7c51-4d82-ab78-e8b632ffdb82 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
a5feccf3-cfe4-4bb1-87d9-a168e6ed80cb | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
8129d2e4-8709-4d35-902c-93ce87740e5f | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
6e3e8a50-794f-4210-a1a0-24c7b4feee32 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
60f5e1d4-bfca-41b6-81ef-6112ec31ac01 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 |  | NULL | NULL |  | NULL
59e4e5f6-18f7-43d0-bcef-b155802e98d4 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3 |  | NULL | NULL |  | NULL
293b9178-b9e4-44f5-b557-6d233a3de302 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3 |  | NULL | NULL |  | NULL
d8bf584c-7a8c-4d25-9d4b-b3fcfb3efc43 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3 |  | NULL | NULL |  | NULL
d1811666-9286-46a2-8061-20744598e308 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3 |  | NULL | NULL |  | NULL
ed8b752a-a673-4962-9c22-df4d82be806a | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3 |  | NULL | NULL |  | NULL
98c62ce5-fdd6-462f-a119-8b62387e241e | Pole | 0 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
fb5e081a-0154-47c7-aa31-2ee4aa6ab4e9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
d28d08da-8a9a-4a83-a251-2fed91f2436b | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
e6893d0f-e805-4d12-b81a-ff3230f48099 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
8550362b-1f26-4be8-a3d1-8fd8e75a871d | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
1ec593a7-4f68-4903-982a-0c8ee6dd9ec9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
2ace12f2-9784-4ffa-8c4f-597075c9c8c4 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
942e4bd1-9fd6-4fa4-a47c-4765099b899b | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
6f1a0b58-bf7f-4f9a-85ab-998425147884 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
aca4ece7-5ace-402e-8cf7-2154b11186d9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
d7fe47f9-c662-486c-b60f-3a561ddb9737 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
11658340-a951-426c-bc97-aef0d57266b3 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
bee7bcdc-d2fd-4b28-8ef9-945f5765540d | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
dbdc1909-681e-4867-b01b-fd2e312c7738 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
9807aead-c4a8-4673-8768-cb1e1fcb79b0 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
0380c174-29e1-42db-a46c-2bf591038ef3 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
4c6750d6-1d06-4e02-b6aa-74a6a405019f | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 |  | NULL | NULL |  | NULL
5385694c-b7ea-4e2a-9856-aba709463f69 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
4d38c9a2-e0ea-4e68-9983-3ec0d32dc3d7 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
42de0a8e-f463-431c-84f9-74b432827e48 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
43e8f4a9-00cb-4995-8799-b07472ced851 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
2fac2070-83e2-49dd-8375-65f1ac739517 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
12588efb-58d3-4dd5-9415-3e45ef959629 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
ddb274d6-023c-45b8-a868-5e452090d704 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
a4b24059-d2ca-4db9-b7d9-7792cbaa8415 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
a57bde98-bd3e-4ed3-9b2c-c132720e5b05 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
dd961bcb-c36c-40c4-b2ad-c672534e5f52 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
c2d60c9c-3ccc-437d-a313-29344358e42f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
25fe7bf1-8a6a-4df0-ae24-fe9a006c4127 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
71a92032-cc44-4019-b3ef-03a16dea9727 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
62958aed-5be4-4e80-941b-315f2de15eaf | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
4b3d8b42-ec61-493a-b497-8c246586e6a2 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
23e03bcd-46a3-4169-9aa2-ebb46e3b7988 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
be827ee8-6726-4ac3-958b-ea21d218938f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
905504d0-9e30-43ce-910f-372bafa149cf | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
85725ea5-5553-4e30-b74c-27b04540523e | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
b74d8cd0-e943-4604-9678-6af45864fcc8 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
95958bba-fc1b-4c56-b82f-7dd30736e687 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
14e4d08b-32e9-464c-859c-206557919546 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
c3e77797-3f5d-4bfb-bc9b-1d6ee05b3d7b | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
4d75f31c-dc00-4a8f-b2e3-77f5e1ebe810 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
7a751178-337b-4718-93d3-cfbec13ef339 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 |  | NULL | NULL |  | NULL
f64acb2e-c98f-4038-98ae-5752f7650b31 | Pole | 2 | Distribution | 2020-06-17 | 2021-06-17 | Level 2 |  | 2022-02-14 | 2023-02-14 |  | Secondary pole is broke off and needs replaced the tree is holing the pole up now. Not sure if itGÇÖs our pole or customers pole.
dce68f65-4f23-4363-93a6-d36f8c80fe9e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
dcd2ac25-9eaf-44a8-9117-cd8540ec101d | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
a7951fc7-f848-4f22-afc9-2a6ffc3a4ed9 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
bc73a106-27f2-453e-8017-c9de226194a0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
c014fa42-d1d4-48b9-898e-0b1885ce8878 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | 2021-04-05 | 2026-04-04 |  | Arm ok, no tracking.
ba8e8ee3-723b-4739-b039-eb771634110a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
ce653643-a75e-47e3-a4f3-44fa8b82ea95 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
b7516126-c0ef-4d18-97e2-f4347694221a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
c1599ab9-7266-41da-8c23-e9beadb09126 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
bb98d7fa-2c72-4172-97b0-cb9abe553aae | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
e009a6fd-a426-4242-b8b3-4aefdbf018c4 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
602c59c6-4284-466d-b49c-287b8b50a721 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
5543403c-cd01-4d57-bd23-d62d524d4e03 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
3f660050-96ea-4eff-a87c-21b42e2a2770 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
882db907-2e16-4705-8b13-fef0cd1d9fdd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
bd5f70f0-e7b1-43c4-959e-1ca538087e52 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
ccafc5d3-4780-48a7-92f0-4e3b77312a66 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
23ac153c-a11e-4cc0-a74d-5ae3f4dc6f2e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
2854f145-7758-4242-932b-40d9bf7c1f98 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
121b0a16-9f60-4cd0-81ec-de8f90975d6f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
13b2b12c-4694-494b-bf0f-4949db7aa4c8 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
1849050b-a2be-4d37-9671-dbc35474c58f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
47620d6b-5844-42aa-a240-480623dd2a10 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
69eb1326-21b2-4ed7-bd5a-3950afb0a371 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
274cbf33-8770-4627-9dcf-95c261373c7a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
2d92a3ea-bd47-495a-943d-00aa49140d26 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
dafffccc-49ae-4098-b8ea-97f3d339b228 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
cd740d2f-4fb6-4d72-b109-b5af9413fc0f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
a93d94ef-5c3e-4e55-9aef-0d5cfd6f060f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
80b89359-e257-4176-a191-fa0fde99f6d1 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
8f5a474e-b911-40b8-9956-1a73928a83f0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
ebe854e2-10ca-4c69-bde3-d31f5894addc | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
042cd7f9-01c1-4c97-b3a3-2de190df6602 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
61e28d29-fb4b-4bd5-a644-a4445d70d0d9 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
58eeeba5-cc3a-4625-94e0-dac6000e66bb | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
363aa800-8034-4a9a-9647-4da1b7e8321d | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
3b7a4f42-efa3-4191-85e2-047e738de316 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
3a7a2532-caae-4be5-bef2-3e7c196b622e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
460366f8-75fb-4dfa-a44f-52869b92191e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
6f0f98f0-b3ad-4932-88db-869aad680f2c | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
67abe50f-763d-4505-90a1-5c21df6f0b00 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
74385126-e8ff-4b62-9239-6fab093db6de | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | 2021-04-05 | 2026-04-04 |  | NULL
75c6c19c-23e0-4a2f-9093-fbfd6b2c82aa | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
76ca1961-26bd-4a53-8ddb-679109929708 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
72a5e09d-451f-43de-a3c9-142a2221e2ca | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
7252cb95-08ad-4ba8-9f0c-93deaf06e8dd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | NULL | NULL |  | NULL
733c4f3d-8676-404b-9d13-00014b5fcc47 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
7f4c1647-2eb1-4ff3-bf35-658ac45ba797 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
6ddf18bd-5522-4b4e-a0a5-fc21bcd2a77a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
5ea0e2a3-f49f-4d72-a98d-ba8f1bb89e60 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
6187ee35-27d0-408c-b25f-685c6f4cff86 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
4a40846c-d6f3-4ba9-a0d4-4f6c1783bcee | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
471cafaf-ed83-4570-a7a7-a483791da6f5 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
52257f2f-699b-42ac-85bc-a8c0cba0ab37 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
3b41cf8b-8918-4512-bc2f-e96e4d9975d1 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
3fbb4c23-222c-4754-83f9-c06024bc26e4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
024f1dfa-f5cf-47b7-8c39-bacda515e7ad | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
02db2998-be85-4cd7-b008-30ed1fc15005 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
00cd6034-90ae-4c92-ab96-ec4797187743 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
0ba37e80-2aaf-4a13-877f-5ef357f58c41 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
df600a4d-b67d-4b6e-a6b8-ad77c019379f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
ceefe8f8-5fe1-48c9-8ba9-14f0a6acf560 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
96848c03-cd9f-4f8b-b9c7-da7510cf6f0d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
0b01c3f8-5563-4fa9-be0d-ef8cee63ab86 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
3360d1c9-02e2-4969-8c84-88e8fb2a69c7 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
f86f93b7-c168-4c85-ae7e-8f251e43242a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
fdc52b0c-8fd5-403a-ae54-5986169802de | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
f3400bd4-188d-4c92-982b-132bd4f1e955 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
9af747f0-dcc9-42fc-b9ad-6bbd91be0427 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
d1d7bcd7-6e85-4bcb-80e4-babf3c4eb51f | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
dc7f9438-4285-4007-bb4b-c52e6a345abd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
b7751c2c-6be5-43db-88c6-ec1edde17080 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
35247a14-7218-4971-8115-f2fbaeae2580 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
3d5f3b0e-76e3-49a3-9ea3-45a25874adb3 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
3923537c-b2dc-42a5-ab41-2b6683866076 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
1f86e085-6bc6-4058-b916-bd7d81948fdc | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
1fedba06-3edc-4961-9265-f421931c2425 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
6da1e94a-4500-43a6-b1ea-99040f7fa44a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
5e9e06b6-0807-4bf8-b61c-616fcf2b1ced | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
43c1b9f4-605d-43c2-af51-403c220536f7 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
3ec938b7-fb1e-4d77-bd02-c1c6d191c956 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
4639ab5e-ff57-4d4b-b238-41d347b528fd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
0e4fff38-eca0-4ea6-9047-e7949160e310 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
295e741b-0444-42cc-b9d4-a278db89ba1e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
2186f6d4-80f9-457d-a4ec-b0ecad324911 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
20bf6001-78af-4a0d-afc5-40110335257f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
c7100f98-1b10-456e-a32e-364fff9b2ae0 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
be89cbed-f794-4a3e-928f-9f1dc484a109 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
bffd744b-6f18-4239-bec0-0c1c39ab9b3c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
92db5668-0323-4947-8344-ef1cace2864d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
d587e5bf-ee41-4e4f-8f09-5fa7de5fc5e4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
4d08eb59-41a9-4271-b73b-fa021f7cf60b | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
4a76a857-e0db-427b-b038-1bebfdd1c073 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
496409a8-957d-48ed-b939-11e31b43278e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
6759a367-0d01-47af-9fe9-ccfedd1ec6fc | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
016bd0b4-ab54-4578-bebd-54201027436c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
111e8b90-16cb-4a16-be1c-5a78cd98bb84 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
24f11f4a-c7ce-4fd8-90e2-61a5ce2cf505 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
14eab584-ca74-449b-8b28-95e18ace810f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
1a5cab52-5491-4ecc-ada6-38ac1ecf5a75 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
c66e7fc9-3e30-44dc-9748-f365d63aa59d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
b1046a26-9670-4553-84d7-0244821568b2 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
bc082cc7-9d27-44f0-a03f-af80323e9115 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
a870008a-7a56-4e4b-9081-62c247b984f8 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
ac1e9bb3-2479-4d4f-a516-ace320ba0248 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
ae79c957-85d8-4126-93bb-48cfe524ac0e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
a1995b28-ab54-4271-8c21-865137b1185e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
a06f9b29-5bfc-4782-bfba-eeaf2b9cb502 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
973242ce-6831-40b2-afb2-2ddfaea2e86c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
8a813efc-1f90-4ddb-81f4-a94aae52ce28 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
d1ddf84c-9ac3-4f8e-baec-29fb1c328e59 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
b58c4337-fe71-470a-bf88-a860c1441de3 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
d7ec684e-5593-49b5-87cc-962d05b13cdc | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
d92edfbd-2989-499d-8710-3ef92315e503 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
f63ec69d-6c6e-4b3b-8db0-5fb57453e9fd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 |  | NULL | NULL |  | NULL
f6a88c60-ba9a-468d-b550-240f277ba0f5 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
11307c9a-348a-4634-a842-17b2bc617e8e | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9eb03c0d-d84d-4c47-ba5b-4dd9e449f92e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9a3c901c-ec77-4714-9858-197191b3277e | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
adb95c06-6aa5-467b-9fd4-e4ccad54ab5f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
11155b4e-d8a1-41de-80d1-721a10a46e01 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
14b1b9bb-6399-4855-b711-9434da84ef08 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
0c384509-d31d-4f33-bc00-eee02296eb58 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
f42dd436-4f49-43e4-846d-f473d1497df0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
1f5076f0-909c-41b7-a5fc-b526edcd0171 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
bacbba9d-24cc-47d8-be54-5e0f4ac4db19 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
cd6e785c-855d-4582-b955-f6b5517e27fa | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
eb15c717-e93e-47a6-9367-9daa1ace59e0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
ec7ab5d0-11c9-40f0-bfa0-ad5e59c02b6a | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9dcda6d2-9adf-4968-bf8f-98defc9706d6 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
db3a2ec9-db5d-4664-990e-acee3e624953 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
d70e2f5c-58de-4fdc-9c81-09adebd5a8c6 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
d5fac83e-6961-43be-b824-6c76f4005b4b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
d691ca28-27b1-4ec1-bc1c-a711cd2c027b | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
d2b0813d-d7c9-41ee-9100-aaeab7ef8491 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
e5b1e486-53bb-4adf-918f-e0864c6da55b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
8dd92974-28ab-4178-b432-222e3bf66269 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9b54d2b3-f79e-4b3e-93bf-4e02f4c577de | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
945e5153-e460-4407-a38e-134b5a338b22 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
a416bccc-e385-43bd-901f-6ef2f22a7f6f | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
a4738ee0-32a1-46b0-92e3-8d9bfe6cf5ad | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
b3978a2d-c517-41ee-b407-11a585bf96eb | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
c11f75fd-d5cc-4832-a573-24d7abe136c0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
c8445fe5-6159-4042-82e0-d30b275daf4c | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9b52c8f2-ad8f-4689-bb38-ff05775d6ca3 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
0e5b9d25-4fb1-42fb-8e8c-1cede50f1535 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9763e357-b051-4e7d-93d5-fd7dafd2e2a0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
2f43e28c-aea0-4720-9649-7d20005f0a30 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | 2022-11-09 | 2027-11-08 |  | Anchor has been installed and new guy wire as well
efc2d95c-e966-46b4-8cad-b1a9a0327fd3 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
8938d985-fd76-4bdb-b2ce-7203c56ca3e7 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
239a01e1-ba2f-4513-9604-c58cca19516e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
265debab-6d68-4896-b119-01dc4f5fd30b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
173567e0-cb2f-48ba-b379-95c413e4bbc5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
c39e7137-89e4-489f-8d12-a9473229ac32 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
a20cec94-5e73-4bb6-8753-d9fbe4874595 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
7b093877-434e-4afe-82a3-0634ff7c2009 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
e77bdbf4-a4f2-48ac-a141-9522595cccc2 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
6a0101cc-b040-4785-a94d-6dfead3e4d35 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
67f6543b-74f4-481b-aa6a-437c2813189f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
9d3b6db5-f354-40d4-9b6f-15e2178b313b | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
d0b98047-b4f2-4bd7-a235-ece05abb368d | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
b13797b8-66e9-4e91-b80d-3084fd7ff124 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
eaf8744e-cc6a-4f13-8c3d-ea4a88b0e40b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
daf5c354-220f-4576-8c48-8d406f16f5a6 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
2ca32e57-453d-4d14-aa06-2e98922bee0f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
32087715-86ce-45bd-b5c2-aaa2532014c5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
1d53278b-4333-40b2-a690-baf75dcbc5d5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
3f0aede7-2193-439a-ab5e-275d34e83af7 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
4c853d16-73b0-4d07-99e1-fef395e67089 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
4e6090fa-a289-4b6b-a426-e57eb3a47ad8 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
432b48f7-9e15-4c09-ac0e-d4f774afe696 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
0ac0c8e2-e5dd-4d65-a629-28048831e00e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
2dc10e8c-43ce-4889-9c0b-9571509d83c1 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
5397419f-3760-4435-9aa1-7259d14586ba | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
62b1cda1-254c-4bc1-bf8d-ca12df9f39d2 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
5cc87c91-672f-46a4-8132-e2abbb4528de | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
03114452-4eee-4113-aa19-a7899349f90b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | NULL | NULL |  | NULL
8361087a-9c3e-4fa0-aeff-af3355203f1b | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
7dc399fc-6b05-4983-9192-bb113b582d0d | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
79b23a67-d2e3-4ca3-9516-d9a10f2b7a40 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
5a3b9384-33f6-4c84-bc81-9de47f7f43f8 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
6a3cc61f-514f-4585-809a-ef0783b4978d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
671568b6-3d67-4abd-b075-b73a46ae9be1 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
485fccae-0846-4c6b-bcbd-841bee744d31 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
089d1e32-36b3-4a4b-94ad-04ca87094bfa | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
44a3ef4b-98db-44d4-8a4a-eb043aa2ce8f | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
039d7ab9-5c89-4a2b-9302-08d477fabea0 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
05856d6f-64e6-4102-9c88-f6809c0e9015 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
17ff1c88-8438-4a22-a3bb-f81a46a9b9e9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
ee4aa1a6-ecbc-4a80-9018-bc7d3c2faf98 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
caad1ad2-21a1-4f6f-a931-7007a1c44fd2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
ca6b90d4-2d4c-4056-ba6b-17f5b42947a4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
21dd1f4e-acec-4c91-bb6c-541016106b53 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
1a28444f-0187-4d71-b066-4d637bf88df9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
5591e8ed-22be-45d7-96ec-1d89c99e28f2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
0c1b9592-e898-4a7a-aa77-b2582f94fa04 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
12abae04-4c2a-4f18-84ed-89e038e285e9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
aed855f3-a0f4-441a-bd87-f53090f00454 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
b88f5c63-1dd2-42be-8e24-594eb0d77642 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
45060af8-637b-4b2d-b4f0-f8054ae16143 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
9b003c92-caee-4c4d-b18a-16533f830aa5 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
a925c989-d261-4fdb-b7a5-7d5faa313422 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
912e00e4-d44f-4eba-a324-3c6cf9f58ab4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
8f887f03-f5a7-40b3-9eb8-89626a5bee4a | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
e5ed5acf-f90e-4443-b65b-49640baf5228 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
98724d3d-0e04-4127-a63d-89ced6dff3ad | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
de4b462d-ce0a-4f59-8d16-a1cab842d645 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
deea4bc9-9ef1-45e2-8793-8c515cfc3031 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
e030bb8a-cd30-475f-8e01-f23227c4d985 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
bcf04c9f-c76e-4d6f-90b2-5c88e4449b1a | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
d0673a44-eec4-4dbb-a44e-98fd9f20a746 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
ef92b9c6-19de-4e27-83ee-12d8e99d778d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
2476a927-6cc2-419c-a714-ac75e5e74f41 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
34bd9831-dd25-45ae-9a5a-8505b1a230bd | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
f1bae1e0-c81d-47c7-9a49-b853bbaa8ea7 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
ad226c8a-0447-4453-ac74-ecc11dc58ac4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 |  | NULL | NULL |  | NULL
a7cec7a9-9054-4fb7-8450-8b2d6283c877 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
04bebec8-8a5a-499e-839d-5f3635adebc3 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
19ae9250-ec80-4d6a-bc85-28213d7eca13 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
d3b88be7-2c4d-4dcd-8965-8961cb73e174 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
b0a7f69a-37e8-4f80-94bb-32d35df8528d | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
edf83bfa-6151-4eac-b63e-33abc518b217 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
e7b77432-b78e-476f-9b9c-3c0c11045415 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
e80a4238-bee0-42f3-b4e2-a34b34278291 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
d2682e02-7aba-4199-998e-69243c831842 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
98ffcd3a-418b-4b1a-b964-c67028f62714 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
8c5882e1-dac8-4d1d-b0c5-192a405036bd | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
874e2e05-029c-447c-b6fe-9f4b8c57c95f | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
aaf091ac-d100-4aa7-9d32-ce8d06ff1d19 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
ab11dd14-a0e5-4887-86ac-2c345dadd443 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
bfe55a0f-3a28-441a-bdc5-d2e672bd5494 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
c1db789b-2672-45e7-8b51-6223e1e69bee | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
c3f2cbd6-ac4b-4ef0-aded-0cb7172a17e8 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
6ecd1eca-1fce-45b2-abda-82b5e17cea38 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
1483d12b-e665-4576-aa1b-b010a6f21d74 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
0b7c5dae-9b47-4f96-a4d2-7b64a75f7eb7 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
61b6aff5-e6f3-4937-9cba-acb41beffd60 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
698d282f-292d-4df2-bf40-834e8800b482 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
5570b5d7-33d6-4d2f-b389-06ed8022b1c3 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
29956b7f-ec0f-43f6-8fe9-f97990686847 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
e8218af6-7717-4d4a-a6b2-b1ba075e47b4 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
f1834de7-8c0f-4f89-925b-8aa0436bc679 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
10a25420-c12b-4fab-8fe0-7785fc4f162e | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
d291f631-a08c-459c-8d52-c03a33b9a713 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
c2e783e7-5a64-4ff9-9540-94a8c883fe33 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
b88edc8f-0dc6-4266-9baa-254862dcfb32 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
7e608a48-b485-4d0f-be98-265f06fec672 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
10994a1c-e862-499d-99aa-5c0d1d1a5721 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
b49ba89a-e2f3-43d4-a762-1b64c9673c63 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
4b8791d8-ceb1-4a03-903e-a072c1a957fb | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
4cab09c3-8c60-4b58-b7ca-15f48cd94d07 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
54d42a26-1e38-4522-b8d8-fee85db89470 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
3e82aae9-a5ca-4755-bda8-016105f231ba | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
70339f64-6fd3-423f-91c0-197b9122e000 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 |  | NULL | NULL |  | NULL
71af0cbc-2934-4f81-97af-86d4407feb7e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
716caf31-a3a5-4db2-bcef-9d175a8c12e4 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
7b899d9f-eec2-4024-9b71-2ece1dcb79b3 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
371f0990-793a-4128-bb68-65be4fe67121 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
56455d3f-cae2-4fdd-914e-46f91b0be54f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
52987523-dfe3-4bb6-aedc-c09e5df517e2 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
4c864429-e355-4b71-afdd-21c5ebec5d02 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
4b532bdf-88a2-4bb9-818c-d9127e2df87f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
49b74be3-0168-4d1e-952c-4450c7981ef9 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
b0aceb20-1ff8-4fe3-bb30-314f7b6d3db9 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
02e58939-3c4d-4c0c-8aa6-205e085404ab | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
77125cdd-8bad-464d-a039-daff3efda020 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
dd64b478-1578-4906-9424-a6f78b7ecd71 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
bf323f11-80d1-48ec-bb42-5e28d0779737 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
d8a89991-219d-49a6-9a63-6febcf5a043d | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
06afd339-c8d3-43f6-8464-7542998c4fc6 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
26339124-825e-40ec-915a-fffa7052bdac | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
c2866058-dd9a-42d4-8f90-cfc688e0cd46 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
c4a45a4c-57ae-4334-a2c7-311ae6cfcf82 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
d0228653-c7f8-4087-b513-ff1b4c937371 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
87d3f39c-c1f2-4dce-834e-341f0bec52da | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
ab1ef444-5aae-475a-b7cb-e0eb421901f6 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
e3088ea0-f521-4bef-87fb-39cdc23e2bc5 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
e4429fe8-ede8-472f-b03e-00757d01375e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
b1c14276-328a-486e-a4e7-6a67621b65a9 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
1ac8b35a-f9cf-42f0-b562-9980c4ba079d | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | 2022-02-08 | 2027-02-07 |  | Multiple woodpecker holes
2bc59a40-d6a5-45fe-aad7-ccce00411051 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
2e2ecc4b-9379-4450-879f-feea210b48e6 | Pole | 3 | Distribution | 2020-06-23 | 2020-12-20 | Level 2 |  | 2021-11-16 | 2022-05-15 |  | Pole is hollow at base. Sec lift pole
8090ad40-5ccd-4208-9f0b-120434b674db | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
f7147810-e152-4c85-b25d-d97e83ffd02e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
507edeba-5cb4-49ae-876f-e4b19d86d29f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
a929ad9d-d48e-44dc-a3b2-bf54d8d7b99f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
7cba5a89-d7bf-4934-8bea-36aac7c87da1 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
49191429-dff4-4d4f-a0d5-763c6a9305a3 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
44b178ae-c3ba-4f53-b211-e946903f463a | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | 2021-04-06 | 2026-04-05 |  | Pole top ok, arm needs attention
002fe135-38ea-4cf3-a441-6a06ae4fa972 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
9155ce3e-0816-434b-ac6d-bf79d1a9c117 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
7b858153-914b-421c-98bf-79e93c373e0a | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
999a6497-c49c-46f1-bbf2-d6ec19793e4c | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
a4ff24a2-2757-43c8-ab0d-f9472decfbd1 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
79396c85-28dc-41b7-97c0-10fd468e20ae | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
917abdc6-e03f-44b2-a578-8c6b474ddd46 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
8c3df28b-caed-4749-a636-9b10cd12e431 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | NULL | NULL |  | NULL
adc3f614-a6b0-4668-a12c-dc6f6c16d47c | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
6117b049-b1b7-4db0-97de-9b4d446a95d0 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
d3efbae6-5a18-46b2-a87b-c0cc3b2dd8b4 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
1fffa40f-168c-4c5a-96f3-7ace5c433a87 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
51c12225-f0a7-4bde-bdcf-9be7fb3184b5 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
e057a47f-8dab-445c-b650-91f8f5296eaf | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
a3c0c5f7-c4e0-4669-90b5-4b324db82ee0 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
9e07b871-8577-4097-9c72-79efca0bd079 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
c192c0d3-89c1-4ada-8475-774403aec93f | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
b04c6fff-951c-4d53-ae63-a00d2ba076c9 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
1f727005-d03d-4c80-b788-8b9f61afd3c2 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
104366a6-69a6-4bc2-b570-c221d630521f | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
e13a886f-4473-4389-829f-b8786a4c08ef | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
bab2724b-f600-43ce-b63e-3c69af96fc57 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
bac569a7-20e2-45a5-832f-7e6665904430 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
7d031917-c268-45e9-99ce-9c1c631ae30e | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
a76bcf26-87cb-4275-955b-582f6152e6ae | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
90edf98c-3ea8-4aec-952d-32387489bb11 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
2ed05423-321b-4ad3-a8b2-caa4c423738b | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
2b43afe4-ffc3-4b43-9ccf-dba75c65bcdb | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
5cf7502e-b68f-4b18-be04-b0f14b66f219 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
61f3292b-6d38-4605-8fdb-f272c6b85b37 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
4da846b7-2d95-4710-8a88-0e60645e55b8 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
02fee0a8-e4c7-4832-8bf3-8bc953161c59 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
d5253ffb-2d0f-4d58-8ade-62e43808e029 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
5fa3078a-7dc4-40d3-9faf-a585269cf9da | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
bbbbacdd-82ac-4f75-a7e8-a7f6b3973088 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
271dbae6-d155-4640-a474-23b6db1d9ab7 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
2cba7531-2b01-4ad6-a51b-c13d65176e13 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 |  | NULL | NULL |  | NULL
aa4a4f89-550c-434b-a987-2d285f6f57a5 | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3 |  | NULL | NULL |  | NULL
17cc363b-bb3a-48fe-a6f7-ab19fc71200e | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3 |  | NULL | NULL |  | NULL
121083f7-cab6-402e-a038-b8b0d40729ed | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3 |  | NULL | NULL |  | NULL
f71a341e-40c2-40dc-adcf-f7dda7623a1e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
aac4a932-fc7f-4c4e-9b8c-08537c9388be | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
ad7985d4-cd46-4f6e-84ab-61f86cc488a9 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
85951483-a278-464f-9fa7-0b3ba767d66c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
afb77e87-6c87-467c-845c-6729d5c06cdb | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
b957b650-276d-451b-8bdd-699c7dfba05c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
3f81c4c5-4e27-44c0-b0f3-8133c8a04c53 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
d6f704c0-14ab-4f61-a005-98c1035b286f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
be2c8d00-3ede-4f6c-9f34-fcc520ce8885 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
e4951624-5c90-4133-a059-7ccd435c250a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
fe200f70-1456-453e-a343-aab9690db571 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
28228cbc-9c8c-4a42-acaa-8b5e532176bd | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
2ced75f1-65d1-446c-8ecc-6544027cf994 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
010dea4b-5723-4c4e-b547-0f071701cd6c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
bb7900e9-22fd-4f03-9f50-549f3dac6d84 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
7ab4984f-0e02-429a-a669-a28fbacb10a1 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
5d8e0cb4-a54a-4b14-9d5a-06f07a5076d0 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
74b35813-f04c-42a6-a9e4-786970a9f75c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
9ef8814d-191b-438b-bfcf-85d36dce3c7c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
14635e22-68db-492e-9390-bbb0b42f63eb | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
f43b4113-1e8b-4972-b255-6e7de666817c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
676309f5-4399-462d-bbe5-56f3eba2a109 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
037f1e9c-2fa5-4b2f-89d7-94b71533a86e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
10929716-ffdb-4809-8965-18dca0f94032 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
410c85d8-c60b-4a47-8a2f-f518a34aa65a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
c431e01f-357d-4c27-9fb7-8c411e9087f7 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
fc4b0c68-1e8f-4ab5-9f5f-7f0481f8e37f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
fec1f6e4-ecf1-4d58-9992-7e4ec1c7ae43 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
ec8a747f-f7d6-4143-a01e-2d4a6d7712d8 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
153a8b97-1037-42e1-a826-3e07d0398f0a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
4761d2bd-df55-40bc-8b3f-685d08c65b50 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
4a1ba934-7f4d-45fa-ae17-00b0aab98e7d | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
44f132df-06a2-4366-997f-abe300570334 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
45b9385a-ff0d-46c3-a387-e629de452425 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
3616faf2-70ac-49be-9038-f43a55d4a132 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
7d6d4e47-cfcd-4bf2-8b92-3dfde0dd8885 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
6f49de98-44b8-42bd-9d32-cb230f76f77f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 |  | NULL | NULL |  | NULL
6eabcfea-503c-49ff-b0fb-37889e91c08d | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
69d727d2-eedc-4298-9e8f-d3d62cd4e230 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
78b36adc-1733-4dfa-87a7-4a106a55ca90 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
72696d1f-1fda-4026-9d7b-0d38893f9287 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
712d8bff-7077-48ef-8ed5-a30cc9ce6fd3 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
36de26e1-3f94-41d5-9cda-19889db7dc32 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
4148eb72-d1f1-448e-a4ee-f37ed6088bbc | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
3ca0b151-623f-4e70-8f50-4250096f3517 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
433a0535-2570-4e23-80d4-12c2fc438f06 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
147fb4d5-07ca-48c7-a541-91de53d4cd38 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
09986968-41e9-4962-b795-6364930f9a48 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
0eea7117-0804-4eb3-8dcb-7b4b51b1bd60 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
e7c7ceef-6e7f-4598-a673-b144b1c37c20 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
f751f785-c464-4c2f-8814-5594c759f51c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
94d58262-0436-4c54-9bad-7125a07b2dc6 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
8806c422-b2ce-46dd-94ac-80ab4e19fd4e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
72bc0fba-0e18-4f06-9b8f-91ba2213beab | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
85ef6292-47ab-47cc-b945-fc2cdb60db9e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
43802c10-c840-42c0-8b9b-9cf9137bb581 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
5333a12c-2e6e-4519-8b85-1a1564e03492 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
5c5638f9-db42-40c4-9f7d-edf5ea0bf692 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
54efb175-1c61-4a82-a4b4-5b5558d8709e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
642a93f6-411a-4897-8772-5eda69304c2e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
2b6fa4f7-0190-4d83-a802-6722a2886a76 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
37a47cf5-337d-4417-83c7-9b9e7b2d5d0a | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
3d588a01-bbcb-494a-a689-113ef6616ad2 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
107e3cb4-987e-4158-a158-c35f49ea3595 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
1284b4d1-d833-429e-b933-a357e900a647 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
06d73a8e-c88d-430b-952e-c4e7c2adce99 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
e442d116-3c58-4eee-a889-3832325663cd | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
3969bf77-0256-4c83-b6a1-e5b79a9885ae | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
8d0fbcf8-a48d-437a-b2ae-1620829e3d9b | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
556905b2-b911-4435-bcc2-364dc56bf95f | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
603d293b-69d3-42a2-bd67-cc8b06f420c9 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
3b821410-34b9-408e-ac3c-e0fe85a9607a | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
f28f6101-8cd5-4d7d-b260-cd6aa9b2bfe5 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
b0acd8a7-018b-4433-981a-0bdcfba8283c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
c3faa75c-5ee7-4d1d-900d-926287bef9c0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
1f118a43-0e56-49fb-a5a2-1ae5c07c9d61 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
187a3b78-cd7f-46b2-af5a-3b67deb63aba | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
f3cba543-55e0-40d2-b7dc-ae28bf2faa3c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
b69a0afe-0601-468f-929f-e6dc571b3be7 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
e242ea4e-dd01-494d-9d35-b9cd1c397f61 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
9bff3554-1abf-414c-9afc-0783bab946f0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
ce9c74b8-5406-4376-b450-30224704c272 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
a0b71633-ddd2-46c1-a6e8-e9a4b830df0c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
edfcb782-ead5-43fa-968d-e0c59fdcdfd9 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
e35752c3-be1f-40d4-ab58-98b3e3af8ba5 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
68415d3f-52bc-4364-9332-12143462bcd2 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
884975fc-2cb4-486f-8832-f749224689fe | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
9a1d3ded-fe52-4a59-a37d-6f97683426bf | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
02ef93b2-f9e4-4147-88b8-94e6bca6ce8d | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 |  | NULL | NULL |  | NULL
05a5439e-d149-4511-b22d-6b3ceb7a1086 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
14e377a1-e093-4ce3-ab63-bcf42dd61975 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
715c593d-701e-4002-8281-cbd554deba35 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
f7d6a012-fd71-4055-b6ab-7f5de486e797 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
b0cdb9cb-4328-4681-80f3-6fd185bb8a64 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
42b739f2-26ee-484c-ba18-02685a5eb480 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
621f1f70-d18a-4baf-a929-88724179afcc | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
21a861eb-0df7-466a-ae53-7c35c80d8164 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
ae900de9-ff22-4fd3-9141-a073c1bceaf0 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
dec80bf3-ee49-4446-a0e4-a62785713791 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
6b714a30-3bd4-4a5b-beb7-4aa4e85b633c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
1e1e89d4-14b7-4fc7-8322-8afd029686a1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
667dd612-ac84-42d9-b97f-8c04b6c2e2b1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
6ee4fa0d-2562-4aae-9f07-00203a52bb61 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
a411ab9b-0f0d-4435-b35a-a75bffb7548e | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
a46fa2d5-4ad8-4f18-964a-f6c47856ce0a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
a6d73656-12e9-4681-abe8-0ad1733ddda0 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
a92e6097-1c91-4ce6-b54d-1f3f65a8e68b | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
8bbf06fc-02e3-463e-8ee8-a298bd105e3a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
3a67bf18-b460-4590-8631-4f4296711e77 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
e1fdfed8-d81a-4ac2-850c-4c8748bb721c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
408f776d-c353-41d9-a29d-d729cfaa03d1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
c7f42114-e5f2-4636-9471-f99a17b12e6d | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
dddaf571-a30b-48dd-9bfc-345a72ac7d1f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
e366110a-a17d-4d19-b020-4ac22956f496 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
fac8e6d2-6fd7-4a4d-8eb7-cecbaea24ab7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
4816836e-d108-4928-95ff-bd9d22bd442b | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
ecd71f45-465a-4c15-b45c-ab328900bdd2 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
b464cdf1-9d79-4cd5-b151-6d6debdba853 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
a75c6235-372d-4ef5-acd8-9402b38bc7d8 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
6ce013c0-8231-4929-b0ca-ad121c5b5cb2 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
a691948e-9a3e-4464-abc1-edf2a248e796 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
e8f7ddfa-2f6f-4dd8-9724-073800ecbd1f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
f136a2cb-4126-4ff4-97e9-be365ddb5961 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
f569e62f-b536-4656-93c3-4a049b03836a | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
17204ebb-ada2-4803-b50a-cb89600c83b1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
61c10519-e229-4b28-91ca-2a5beac6bfc4 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
504c40b7-cd0d-4f19-b30d-2e869850c6c7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
2107f36e-a842-424b-b58b-a6556228af91 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
94f93e8f-bfc5-4d7f-8645-6d4d3784b6f7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
1425b2a4-e013-49a2-9817-2556d9be8c71 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
2878ce35-c745-4643-aca3-e5e1e41e46de | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
2e6afe47-8b4d-4b91-b05d-ea09faae6ebe | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
44962482-c053-4446-9e43-8ff3c0b98109 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
442ce52a-3ccf-4667-8b12-ab57d047ee6f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
80169dad-3e79-49fa-8733-3ba1a0554c11 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
0508e5c9-9634-4fb2-bd93-42beef939288 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 |  | NULL | NULL |  | NULL
74bac55c-1eb6-47d5-83c4-0b00cda2400c | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
5311c8c5-d4d3-4f79-ab1f-481dcf41bd9c | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
57e36233-b8f8-4085-984e-111b358905d7 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
3886ddc4-978e-4636-a374-20e7f080066b | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
3140b80e-652b-4b93-b08a-302508803a00 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
24363318-3afe-4cd7-a5b0-a1b36ae7ffcb | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
0f0c18fa-ed86-4758-89c0-d19a7d095d38 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
0d50f5e0-6b86-42ff-a529-0b77f181e8ac | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
1128dbda-f585-46b5-8643-76ac2cf0d407 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
f73768b7-aef2-4297-a9b1-ac19bc9dcefc | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
6adfa1cb-43a6-45dc-9c0e-9721bd8447d1 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
e6c5804a-585e-4dbc-94d8-71c18cbaea2f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
cdbe3ec8-7811-4481-aa48-bf62569eb7a8 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
2a8bfdc5-d62d-4526-b19c-c02b5f546988 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
5c4fc335-c8bd-47df-9d9a-25372f9f5c98 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | 2021-11-11 | 2026-11-10 |  | High sign in wrong location, missing vis strips, missing molding
0399be6e-35f2-410b-9925-5c644135282f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
0398fe52-2ba3-40f5-baaf-591472bce0de | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
1a8aec85-62d6-49c5-a333-dfd5cad287d3 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
c36cb937-9237-4e3a-ad29-fe2dfe0cf2c8 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
8fc5ec2a-52e9-4619-af19-55dd0653257d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
26456949-a6fb-4af8-a1ce-169b430c9b9d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
9935d440-1b9e-4127-8ddc-832fcf6930a3 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
d566079e-d3f5-4e65-b35a-e17117275520 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
b569d043-9aa1-47ae-a254-853040276277 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
415f4615-39a8-4bec-b443-0e8ac73c1bfb | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
bea4a1a8-d14b-4ac1-9c7c-6610cd1db4a5 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
1b117939-4685-40c1-b61a-cd9204e4d92a | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
b10a44e0-31e3-4afb-a6e7-be0e9156b789 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
b514cd60-bb09-45c3-8ff1-588f8b6d8191 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
cf2407c0-3a11-479d-9dd8-e9c11ecf9df7 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
c2e1e764-0581-4996-8e98-cf83d256f982 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
c2a14c40-f9af-4f1f-a412-0f929e414227 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
672dc76e-dc2d-4424-89fb-d5a6de907be7 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
63f09cb1-6076-48af-9870-5bd5ea1b07ff | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
9dd71ebf-c328-45f5-b058-277917ca4169 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
c481f239-aaff-40f7-8c5c-6095135ede3e | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
f9d98c21-da5a-481d-9141-b5b3e241c58f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
cf7186fb-1763-44a6-9ee6-988cc6ae9297 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
713a99d7-169c-4c4c-ae37-fa558a197479 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
52d25e4d-c469-4fec-8fe1-80762dc82227 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
17999798-87f1-4f99-b1ed-db74f51fb5b0 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
47963164-c2d7-4ad3-93c2-8b2ea740310e | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
4706b5f9-4362-4f9e-a161-72fda9ad1a0d | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
8c09ced1-900b-40fb-9b43-5153732e8573 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
cb573dd7-8f3e-4b6e-bedd-30c65e707dd9 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
1ed6e8bc-7d30-46f3-934e-e8870c76e87b | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
197fb920-d9b8-4af6-8d44-359d8f30a0f2 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
d4ccab76-7a51-49e2-bda4-48d9181e111e | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
fba4dd40-87ff-4f89-a805-697d00e74e47 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
cc3a0dda-5157-403e-807a-70550dfd90f9 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
a7d342db-42cf-4886-ad47-460c07bd2e22 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
a3f0da5f-84a0-4fc2-a292-4250e81f7aab | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | NULL | NULL |  | NULL
78247f7a-0352-44d0-8c6a-1c6698d9514c | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
d1d8edb0-1c90-4077-9a6d-4f43b53508e1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
41d5985d-c9d5-4adf-84ce-432a63725292 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
41269246-0aba-4fd3-8c17-8f3e1ccace21 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
2da97822-8553-414d-b81a-e68123316f96 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
ab3fa375-8bfc-49c2-87a1-3197fb2f69f7 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
95df34f4-d327-40a4-87e5-72d2c9787603 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
6e8aa700-b83b-4699-93b9-ba4444c935ec | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
8c17a871-df9c-4003-a610-f7d914dacca0 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
7ea1828b-8371-4ca1-9615-7b1a6ba4325e | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
96952dc0-5280-4fb2-b099-f802f86ad70a | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
9e8f5b3f-ed38-4423-8365-150d27ce4372 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
a9621bf2-8437-4ea5-910f-6db8fd57ef01 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
b1fe51d8-68e2-4ac2-863e-f9a5efb7affc | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
af23feef-c4b6-4a8f-ad12-492cf6b94286 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
47064fc4-cf1e-4e77-8e4d-66d79537a47d | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
2a71a7c7-6c6e-4648-aedb-cdf565a1464a | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
bab110b8-bd28-4fe1-baa5-0777ef860235 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
ba110dea-13aa-459d-bb0e-2fd554c8eeb4 | Pole | 2 | Distribution | 2020-07-01 | 2021-07-01 | Level 2 |  | 2021-05-20 | 2022-05-20 |  | repaired cracked line arm, pole needs replaced.
4e92bd42-3149-4c89-8703-ceab0a955c16 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
1380528d-05e1-44be-8659-b6c2ac92ebad | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
b3e8d100-9c01-4fca-9e47-25f0395d137b | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
681edcbb-e8c2-4781-97b8-a2fb9828edbd | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
dc8303f0-d0a3-429a-9640-eafcec41f31b | Pole | 3 | Distribution | 2020-07-01 | 2020-12-28 | Level 2 |  | 2021-11-12 | 2022-05-11 |  | Went to change out high signs and when pole was being climbed the top of the pole wobbles, top of pole is rotten and full of wood pecker holes. Unsafe to climb pole needs to be changed out.
e5406709-d765-4f8d-a5aa-478fb8a5ab2e | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
83b4395d-0dbb-4ee9-9587-fb6a0b0c70f1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
29e0707c-f938-46ce-8de7-b2d115555323 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
359c62bb-0d12-43b0-817c-067e390a1563 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
4ba583d3-8d0b-43d6-80e1-8345f3e1192c | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
7ec94654-ca3f-410e-9ac5-13236eaa97d3 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 |  | NULL | NULL |  | NULL
809e6db5-a91e-4d4b-ab4b-076127e93aad | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
6ddd0ecc-ba20-43c9-8d2d-b6c6e5b05203 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
491889b6-8361-46c7-a2dc-b64ada3a139c | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
2c0ac079-7793-43a0-a9bd-77394058e1d8 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
b73c318c-c739-45dc-95a4-efc087d84edb | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
e5719e0d-066c-4f55-a501-295b111763c5 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
21ed4afa-bad8-4973-9bff-ed07b02e4c17 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
3df0d63c-ef17-4ac3-9e30-2aa2a228b9b1 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
06cea37c-a8ea-4c08-8951-532495f3a242 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
d9d8b4be-d8eb-456c-802c-f3f3fdce077c | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3 |  | NULL | NULL |  | NULL
d750fa3b-40ca-464b-8b9d-8768d5fc19d7 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | 2021-03-25 | 2026-03-24 |  | Al blown replace
ef91043d-64ed-4241-90f7-eb7a661ad63f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
f4cb338e-d902-4a52-bd88-9a84c6f21ff4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
f8d52daa-332b-4eeb-8507-862ab852c93d | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
c7f95d63-a6ff-40ca-8a07-c9ccdeeb32ed | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
b444c3a0-9813-40c5-9758-a964b10e1a79 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
aaf4fa1b-7adb-4a32-9234-1e7ff0d4c097 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
a6d53c28-5e67-4a6d-9ccb-dfa957ae13d4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
87c437d6-7418-4019-8f61-abd750ff5749 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
ccf0ec6c-9f33-4d08-a33d-e4ee9ae9e966 | Pole | 3 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
4f67f863-89b3-4091-9c94-a6cf88fef633 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
0a720879-1a68-4922-8d53-4eb8cdb25b0a | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
7023fec6-cd05-40e2-9c67-1cd2548a17e9 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
7c68b51a-688a-4057-b5b4-ffdcbfe6deb8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
5ac9bf74-6775-4596-b6d1-ece0b5ce2f87 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
52ebe1db-c269-4f7a-8371-f92894b3dd9f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
50043214-c47a-4379-96dd-ad23350081ce | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
bc20f272-e776-4b4c-bfb2-93717e684dc5 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
9314ebea-407c-452d-97ed-5a114b37a1cb | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
e4766b0d-b291-440e-8fdf-2addc537b6f4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
ed52b673-d866-41f9-89bb-847012e7230c | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
24008e5f-3f22-499b-839f-240dc1400bb1 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
0cdcfefa-585e-4411-8005-f3ba4439e79b | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
0e83fa6f-3f1b-4a2f-99a5-3e56c06de4d6 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
476233b1-e400-4667-a56a-b7280ac65ff8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
156216d1-767d-4048-b862-a87db522f3ab | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
7047572e-f938-4c47-85ee-7322ab3e06a9 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | NULL | NULL |  | NULL
78b06658-fec5-4708-b8e9-7834dfda691c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
04eaeadf-3804-4277-9e99-99e0e161763c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
4cf14ed9-5d22-4c5d-a9ec-4e0a75642859 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
e94082b3-e375-46da-9330-b270df7ad367 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
a00d5fea-e2a4-42d6-b24a-bd0321b04678 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
bb5a472b-ab23-401e-8866-6039d3babc30 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
c162ec37-2c3d-4639-a0c3-5353b1b667ad | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
4ff1158b-4d31-4e2b-b2ad-77a685b556c1 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
56a1c32c-4e86-4583-abeb-af61764d2424 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
6059279f-5a46-4e2d-904e-1e86690766ba | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
60f56ba1-b348-4043-ada4-3678fb08c8d0 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
663ec697-531d-4437-86ed-8608796a2b73 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
6337d787-14a8-4e05-9eb8-0988212e4c8d | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
77b39cd6-fc8a-4702-bd83-e4daa89d1493 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
71cb4785-14a8-49ab-af12-e89cd1d9676e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
1b88f05f-27e8-4cc2-b6fb-c46d46c4d736 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
92764730-a935-47cf-8c26-20852a5a66cb | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 2021-02-27 | 2026-02-26 |  | Replace put at top of list
28f0a912-fa6c-4218-8c24-77bcdb8f5265 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
23ca360d-b7c9-4408-b14e-abbd08fd7549 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
9bd3f677-d4d9-4d76-94b1-7d2a1574364a | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
9c0abb0b-a348-4999-9343-0b6686df6525 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
b08acdce-6f5f-4e3d-be94-8f2d8f58a957 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
ad16868b-a539-40a0-bcb9-c25cfaf67c8f | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
bc724c11-dfb5-48cd-90d4-c5cfa93d6928 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
fff4b774-407a-49dc-985f-1654642809e6 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
dd386778-2810-43ef-960c-3afcd4f7e669 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 2021-04-27 | 2026-04-26 |  | Blown fuse on cat bank
e0d700c0-2d91-47bf-89cc-fddd6f43f41e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
db584575-0efa-46d9-9fa4-9fd064a1999c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
dd0eee9d-91e3-4089-a583-8bcdca49f43f | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | NULL | NULL |  | NULL
bc0f4971-62e5-453d-8419-1feea26b57a0 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
bd165113-6276-483e-957b-211cda272fec | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
a3b24d15-6bad-461d-809b-8b4e55389976 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
79c8bb23-b503-455c-80f0-98d18656e233 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
b8d9cb64-ffee-48fc-8bd7-394178ff9187 | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
ad0de100-52a0-45b0-b4c6-ce8968ad0963 | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
ed21d40c-e8e1-477a-b8cd-17538399044e | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
728285a9-0039-4f09-bd8f-b5e3baf66d8b | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
62e557c2-ef6e-41d1-bbec-eb0e9f0b96a2 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
21e0c81b-36e8-40d2-b1d0-d8e616cb36d9 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
885ee9b8-7720-4690-803b-fedda2eb4135 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
562335b2-7a72-4bf2-b31b-490945698c89 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | 2021-11-08 | 2026-11-07 |  | NULL
97cf3a0a-27aa-4ce5-8970-9818295f806f | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
05d73453-5a32-4012-a77c-de379b54be8b | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | NULL | NULL |  | NULL
09789e8b-a0a4-451b-ae99-4fdc82a78836 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
162252b0-ea0e-4964-ae08-628bc0d93fd2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
20b61a44-5209-4ce0-b705-5067d2780bfc | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
86d5d62e-0cea-4f00-af76-15aca8c6052e | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
9e17c0a4-319d-48e9-b786-6d85ce7282a5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
88d655b9-11c2-469d-aa38-a877bf790a8d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
3c0eb500-e11c-493a-9f08-4bb1c84b3562 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
b50dfc88-e6d6-4861-9730-67feea529433 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
eeb3e4f7-db32-4187-8127-fba22c230109 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
40e4332a-0b32-4532-8018-db31e8239325 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
2e08d494-cec7-4cfd-a681-33309fe959d2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
b8b29138-2ce1-4ce6-b1df-d2c4cdf4b0e8 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
b4a13217-5857-4480-997a-a7fa3a142f31 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
b983ea63-2431-4771-a381-96a53ce83e86 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
945791ae-ff42-4bd2-acd0-a9f043292e06 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
db9f0799-2bb9-4f61-a4f8-901221e66b31 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
509f1361-6031-43b4-923d-ff8b75fa87ba | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
7a755d73-b3aa-4eef-a717-16664cbf4b66 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
3785822e-c4e1-454e-8414-9b5bdace0334 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
350fd8f0-f559-4afe-80d0-8716e19defa5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
3099c0f9-3ace-4cae-8478-f4ddd8ff247c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
3e12d27f-881f-4efd-8707-42bc669ba974 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
f900cbb5-a9a3-491d-950d-c438424e3497 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
0d59c623-85e0-4a88-81f5-75c003a6efa1 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
2fbaf27d-5e82-405f-a1ba-850e6bbe4949 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
490d302b-80fa-4c9c-9c35-2c8584ef34bf | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
5c3f7a04-ad4c-4dd7-aaf3-c2d0d86848da | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
57c7666d-c431-497a-b51d-a1c9ecacf456 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
fb0fd933-8f31-4395-b381-7f9cfd812add | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
9beab15a-3606-4b07-adde-a707ae3600d3 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
9b649708-b3de-4368-b345-a4f4571ff944 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
ad8cd10f-c662-4538-81bb-56e8bafc3da2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
96d8d3f2-57a8-4a90-a89b-5e198f305d84 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
bb43f43b-84fe-433d-aef7-325e4f26608a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
be79c0fa-1065-4be5-ab0d-09bbf3bcfad4 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
c3eedc2d-ce18-4912-a4ed-56c23a29bbe7 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
c3adf9c8-7e1e-4719-a2fd-2a452800f245 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
5995cc07-d3c3-42d2-9493-28fc9097cf98 | Pole | 2 | Distribution | 2020-07-07 | 2021-07-07 | Level 2 |  | NULL | NULL |  | NULL
638f8a87-2f23-4abb-8016-c16a2d31875c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
d6e6c551-ff75-49d6-bb4b-53adc8f0ee9d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
8c2019d3-49f8-4e34-8a5e-43d8f50cf9a5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
75c12d75-f7ab-4d3f-956a-5e83cc171ea6 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
6590c18c-c624-4014-9a69-6fde521c7d20 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
6650820a-acf2-4374-b578-87596ef5a20f | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
afdec874-724a-41f5-9749-aa4cbbeca2c0 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
8cd19431-121a-4233-9960-dbb3ce26f551 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
d051843b-0edf-417b-a57c-babceefbdd8a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
a9ab6ab7-ee25-471c-abc0-3cd04d547907 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
f5680546-7a1d-479a-bf7e-ee89a155881c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
c5affcf9-f7d4-4d53-8365-4554100de38d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
0998404c-c5a6-40a5-8f52-f3557ce6b9c6 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
cac04a0c-751b-485f-bb86-bec8b74ced2a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
d8189565-6f54-47a3-96af-37d0e0c8cb1e | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 |  | NULL | NULL |  | NULL
b7e626c7-1448-4dd2-8ed3-7465dca1f582 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
be819848-1845-41fe-abda-9795370756e3 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
01a565ce-279b-4893-804d-ecfdd68e35d9 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
932a79dd-1490-416c-bc1f-322b3541d400 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
8658dc2e-4f45-40d4-a6b7-77ab6cb67a16 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
aab536c2-e237-4961-a3d7-12a9b2a3c86b | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
a724e85e-8c36-400d-8c46-6676d5332f1c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
3d8e0bc9-362f-42f9-8b65-801458a5fa23 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
a4515193-5a42-4a24-a5d7-6e865d9c9121 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
a510252a-8b76-4c18-8595-89194a2d5827 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
d0b24701-9db7-483f-ae69-1e34cff4bf30 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
367eb169-e2da-450c-b405-e9da58bd38e3 | Pole | 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
6aacb92f-84a4-4e71-b7a6-41208188f31f | Pole | 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
44402463-686c-49d2-9db5-3750d3c03ac9 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
72028981-a4fb-4d92-a513-50d4248076cc | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
78a22abb-4ec5-4736-bb66-0014495f0c32 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
62a85437-6942-408c-af20-a47ff7985bbf | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
625479c4-9bc4-483c-b3c6-675a7c5ccb60 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
5a48fcd4-4e98-48cf-8686-f49a80c17e5a | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
5df62bd9-4ad4-489f-8427-5134de5a3b66 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
3b33b767-d154-4729-a074-794e34aae61e | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
eb2ba522-29b7-4ebf-b8d2-4fa162eea7fb | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
88599f80-4282-4c60-8dfd-b74de6ab0141 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
8d3a2d38-10d6-4d82-94fc-69287e8fcd1b | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
0f9b104a-fbf8-45a5-a750-c150da9b58fb | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
039dab48-7ab6-424e-bd35-878ccccbc01c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
84ce554d-2b99-4049-9e09-0a4b8d13d550 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
07b47977-02ab-41a6-bab0-a2f5302dccdc | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
23a0855f-120f-4e32-9afe-f66bd242b4fe | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
183e1851-4f1d-4fad-98ca-65a576de818f | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 |  | NULL | NULL |  | NULL
102b8a1c-fbcb-4a53-8060-49b706605ef7 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
210ab97b-c5cc-4324-b224-dabf31dcb559 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
0b8a8bcb-4c87-4690-9a2a-ecab003e418b | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
efc89a8c-3e4f-4a97-9981-3e749ef5f250 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
1f590e13-c214-437c-af18-0313d881a3e2 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
b7f99e6e-1beb-4fa2-b4c8-4538d26fc979 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
67997b7c-f999-4a66-aec3-97263f7d05c8 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
7c24b7b7-0d82-4161-82a3-74e7313ea976 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
4a8b18bf-13ce-45e8-ae56-e7419af93bca | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
4448cb1a-4cb9-4159-9d03-9ec494115634 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
f797c6d5-623f-420d-bae9-530502569f82 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
28de7189-4749-474b-8420-97a96eeee4ce | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
db4bed87-98e1-43fb-ad7e-b9b884c25fdf | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
d73736c1-9f8d-4655-bb72-509b6cffc1d3 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
acb4af6f-8d13-4347-bafd-acd60cb4fdc7 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
96f06149-da11-4570-b19d-7c92371687fb | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
ce1e99ef-c521-4194-84ca-b41443e71a7f | Pole | 3 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
5cfaead7-7dd5-4c16-80b7-58955c44706e | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
7a46c49a-876f-4b95-aee0-75419a7da8ac | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
98bd97d3-30cd-4b4c-83ea-9e5169b023d8 | Pole | 3 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
8d792b1d-3fb7-471a-aecd-0f6ad0190807 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
a4208c9c-14f8-4057-965c-0432a4afeb94 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 |  | NULL | NULL |  | NULL
7fe208ac-aca7-476f-851c-423b6eb09d2d | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
c1d52933-9662-4b22-b58f-10bd7053c57d | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
c98f5eb4-afcd-4b07-919d-5ea45dfd8fd4 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
ac4820ca-6f3e-40ae-9e17-a637c7718ee8 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
af3fb385-e147-4899-804c-024c8a1f6832 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
b3a1be52-e478-45c8-be12-5601f631de34 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
fb871fe2-feb6-4397-a61b-be3cd4ff418b | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
f193becc-25b2-4289-a18a-17e6aaa3eff7 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
ae881877-ae5b-4df7-be28-3b08c4886ce6 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
ffeeca76-70f8-491f-add1-5b6698252e01 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
7f6c9254-b686-4c48-9886-03ae426df60b | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
94670d55-bb6c-4b2b-90a9-60cfa5b4fa0f | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
ce0a14a5-f0d3-4ee5-899b-d6b48a1e7b67 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
4bf086a1-ed82-4503-a500-ce8d481176a2 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
7a933010-5609-4515-ab08-3a982ae744df | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
72aca320-85d9-4a46-85a9-4b5ead644d56 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
a0abe18e-3705-47df-bf18-b480954c0e2d | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
a1f9a0a2-e669-4fb4-a817-a2d105e65044 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
a1cce40d-56c2-42eb-8d3b-3f2bab0ef617 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
ec82d171-f80f-4c41-9fd5-3e15894b2942 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
7c8dc814-d882-4c81-8df4-372dd3c350ef | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
029131b4-0785-4c56-a449-d29a9f038cc0 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
6fc92763-275d-4223-b5f8-d6dc1fdf00af | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
65d126ec-8de4-4cdb-82a3-2256b95e3272 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
bbd149d4-15a8-47c6-b462-40fa38bfd062 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
2340128f-e9f6-484f-a290-75a46f458ec5 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
284aba57-8f5a-406e-a1c2-8a5249514420 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
389e10e8-a939-4438-9e46-f5911de6b854 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 |  | NULL | NULL |  | NULL
02ab1997-8c82-4fb2-b9a9-5a60b1cacb34 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
a73d38f1-8039-4ec7-9abd-0697fd19651d | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
1d92fff8-9a0e-4add-a7b8-4a3d8cbef31c | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
68dbe3cf-51a5-4a8b-a69b-1470441af42f | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
115df9f9-1924-4a29-863e-6f73d130edfc | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
62d22d83-e2c3-4cf6-bf1a-714d8711b0e8 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
63c5c14f-7b73-4783-9033-a0d6afd485c7 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
75253ccb-161f-4d9e-9845-9208899056a5 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
74ad17b2-94fa-484a-a23e-10219704ab89 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
749c4458-f0ef-4a06-a7fc-a81f415b9e72 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
56873713-bee0-42aa-bdd0-67301e8755f6 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
2f06ca57-5ba2-437e-a1a7-843137e805ca | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
217869cb-f684-418c-9654-6378bf3dbddd | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
957def5e-9283-4ab8-92eb-474b7d9ae653 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
9a69eced-85c0-4013-98bf-0c1090de5121 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
cbaa88d1-e54f-4660-8061-3ef6e179edca | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
cd1090b9-c0f3-47a0-9d79-3f4123ffa402 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
b0ceec1e-d446-42bc-96f1-b6eadaf6378e | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
2e684ee6-cb95-4c8e-87f9-6d9ae3c5f8ba | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
e4defeb2-fd3c-462d-be4f-e1e992aa0946 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
e0940932-bb69-4de1-8219-5c8516485cc9 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 |  | NULL | NULL |  | NULL
ba1f1c0c-10cd-4dc2-bf79-f952bb78cc2b | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
8a9cb10a-a529-483f-bb27-5ba21e1b394e | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
8e8b354f-a8c1-4f66-be8d-84a0f54eacec | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
a383d047-e090-4873-99a5-63f9e264dbfd | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
aa09c30e-0565-46e3-aa35-6aaadf6c5a36 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
e2a9d5d3-bbcc-4546-851d-9bc70f285421 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
f668d65b-a29d-400b-b075-24f26c06c982 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
2d8c8f16-a95a-4956-ba3e-6f8fedc6772a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
6b255edd-ed25-4211-a360-fd29bb6523a9 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
aebbad7c-8d73-4286-bab2-fe126e229fa2 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
60d7a4b0-309c-4959-97a8-c8f8eee53299 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
85e50f89-6285-492b-aa29-10b3640a6c70 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
076acbaa-b9cb-4d2a-9226-fee4160a29a3 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
cef367a7-b2c9-4ad5-8f80-121802ecda91 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
b0fb093e-b5aa-4bcf-b75a-1856e6b6ff28 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
bfe33634-60fd-429b-bc08-9962ff00094a | Pole | 0 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
bad09e72-aaf4-45ef-bea1-5c1458b3e263 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
c931e7b2-c5c8-4423-9a35-3da57752328c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
c63a44b0-0588-4c9b-adaf-b97da5b8f899 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
ab7e51a4-7b28-4a86-9bcc-c2907a0371fc | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
a7647d6e-bd39-456a-8992-4e46ef6ad01c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
ad1b880b-50eb-4073-8e89-34c2f78a37c6 | Pole | 2 | Distribution | 2020-07-13 | 2021-07-13 | Level 2 |  | NULL | NULL |  | NULL
fc7b7975-62c7-4fe9-b9ff-dd6296f2f82a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
fc9db498-54ea-4e27-8b4f-20df72a77a84 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
81c50eca-4bb0-49a7-9aff-c40b70a659f5 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
61726dab-05cf-4d18-a83c-63985a3a274f | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
1be2113f-541a-4e01-ac94-5a027d03f037 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
218753f8-caa7-484b-a94f-0529f31e3cbc | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
25ac6250-68ad-4763-bf9b-560bf3fc0fe0 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
2655e768-b7c7-41ee-80a4-8027c0034c89 | Pole | 2 | Distribution | 2020-07-13 | 2021-07-13 | Level 2 |  | NULL | NULL |  | NULL
0f9bce5d-8ce8-4055-8a8d-6d20c3d800fb | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
6de9c915-8e96-4ca8-a40c-8c1e4ae75b86 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
bdf395ad-2726-4c91-b341-2023c4ddafa7 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
c348571e-90f1-4b22-84ca-21f5a0de7980 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
bc6aea75-f002-4862-9b31-a57090c5114a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
06cc3d5d-da4f-4a70-b401-3333bdf816b9 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
4af32f74-290c-4e46-bfc7-38f1d2506652 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
975dd9b4-3e59-45f3-896e-f2caee795652 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 |  | NULL | NULL |  | NULL
443e5d5e-531d-42b0-8d74-f81076661a30 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
03db0ec4-4589-4769-b418-ab0ad6033bfd | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
cf3a3473-814f-4f90-b63e-61d09e46ab87 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
0b2408bb-c402-4e00-b0e3-1e87406bedc1 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
0951fe77-6d9d-435d-8a92-a65818b547ac | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
278b1280-99c0-4d0d-b5a0-20d34567cc9f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
1e238023-4bb0-4b50-b19d-b866493a9284 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
5de3af97-792e-4441-9d67-ed157497ce0f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
5b3e361a-4d62-498c-bc8c-56c9572b50e6 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
6f16aa83-0e34-496a-b063-5d5de5da5dd4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
41b6bbbe-86fd-4427-82e1-3ee795c0b829 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
3a663fab-ccab-43b3-9855-436f204b5456 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
4418ad78-a931-4a91-81b6-5edf804a7ad7 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
39b54d10-77d6-42d1-84e3-a7e0975182d3 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | NULL
fdec1f1b-9296-465d-b4ba-c755a8a41b2c | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
f32a3838-ac6f-4d72-b52e-0d27cb592ee6 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
d39c399e-753b-437b-9d0e-d3dc6be72dfd | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
ea5e7a63-0ef1-4bfd-ba9f-02db6bfc5e19 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
d0765955-c15c-47ac-807e-d6b9b3402339 | Pole | 0 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
e369b04e-76dd-42fc-adf6-4973cd112cbf | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
dea1d9ad-92bf-4f30-9cd5-add90bf97b9f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
ab3c81f6-75d3-4b0c-9229-3fd4528ef3de | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
a03bbac5-6bfc-438c-b8c2-31c0c054bed2 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
956c84f9-db01-4958-a608-fe93cb8dfdba | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
9afb25a7-8e56-4334-911d-d028ee55accf | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
95971189-7f86-45ac-8418-103c47255113 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
c78c1a41-acd4-4896-b17c-e13250784c85 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
c880847e-38b9-4790-9b1d-d71d6c16cc5f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
bd1dcf2c-1154-4361-9706-667c0f14e630 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
afdf6967-245c-4d1d-b770-6592348bf19d | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
2045bdbe-cfce-4c5b-a2e4-d6c5e6a15783 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
35e8f7a6-252b-4da9-8882-c6b0a97da0b8 | Pole | 0 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
3102b1bc-61ea-43df-b1ee-d56aabdcaad4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
6c51d5cd-e64d-4d3e-a967-e5f3d2209bfb | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
5cf8556c-efac-4258-b13a-d3c8290edd88 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
b6ba2138-f206-4422-9413-18969e71f6cc | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
f6c6ac34-65f3-49f7-9e10-7b7fcba18f2b | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
a9c25284-649c-44e3-90a6-eaae94b995e4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
9c57eafa-c083-4bb7-a16d-a4c1a67f3ed5 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
b7be3051-26f3-4e9a-8ccb-2fa19c685529 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | NULL | NULL |  | NULL
b358ef18-8ea2-4482-a3ca-cdcea0fd882e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
b257a734-e34b-4568-aee1-4d762fbe0c91 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
96ec2302-57bf-43c6-a0e3-2637aa48559e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
940a890a-48db-4f3f-943f-e12b46eb80ee | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
003a1b8e-3dd1-4fd5-b7e1-9d1aad092aca | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
aba16b00-80bd-4bf6-92de-81f429fd6ca3 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
f1d7c57e-9957-423e-bee7-de69da3877bd | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
88255f82-12a8-4308-88c5-d7b40ccc7629 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
66bdfca1-8808-4a2c-a7ba-5b2832c5b813 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
6d511096-17b0-4c19-b602-da8243c37e94 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
591c2e28-1e91-49c3-b8bc-b46ccecb7668 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
6adefe5e-cae0-4f41-9fb3-9adb0c64eced | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
1f4b6be9-8e76-47f0-9b37-1893b79a5061 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
18577d8c-2af4-4625-97c8-c80a2b7bf16f | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
bab58fd8-ab16-4c02-8259-c05aca64b1a1 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
2ecd2313-5ce0-4fb1-8d43-7a55265fb8f4 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
806381ee-a00c-47aa-8268-1f1026f06f87 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
859f4d1c-a87f-4bee-be47-aa2788edf1a8 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
f6201cc8-5008-4a14-a9f2-9dce3da63b33 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | 2021-12-03 | 2026-12-02 |  | Repaired high sign
64f88342-f190-42eb-9149-603605a5a436 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
c1ef1f28-9135-4034-9d09-063294a5483b | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
57afcd7d-acd1-4dbd-b108-a8362e2028b2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
a6fe9675-0109-4adc-b758-352813f7f606 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
ae59537b-6c67-470f-91f7-87587e9c8065 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
e023329f-8498-4245-93b0-afa35662413a | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
fdd79a73-2537-4e9c-a915-7d156c10b1da | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
f9df9a55-39c9-4d6c-bd88-503f1d4b58c2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
e6db48f8-888b-4340-b755-d814f47fa8f5 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
9011ec9a-91ef-45cb-9b94-350e82bee796 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
d59c5e89-d456-4dbf-856f-95f32b046148 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
99cb0f3b-95e7-4fa7-a3ef-f7c9eb39d343 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
3f56cc60-3519-486a-80ea-feda0f55f465 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
4f789622-6ee9-4c56-b18f-207894de2d0c | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
5b2459c9-0c84-490f-98be-a72b3270cd73 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
25c8ab34-c4d1-4906-a0bc-7c28476aa6c8 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
21913b3f-17c6-4042-b66d-43882c9c7356 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
38da69a1-062c-406d-92d1-a4bac2960717 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
3d87b62e-86b6-4e3f-a187-ee47eb6046e5 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
4a3d8b56-c88a-40fd-a4fb-0d1fc8fef922 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | 2021-11-19 | 2026-11-18 |  | Missing pole #
3a460b97-8a06-48f0-ac28-901d3920a027 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
3a12d4cf-64f5-4eb4-8288-b822bc786964 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
5c9af004-5123-43b5-8fd4-e18472a598d3 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
863d578d-efb3-46da-b376-6cfa0fd284af | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
c2fe30d7-b47a-49f7-b525-52124b92718e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
056e4ce3-5902-4996-a68d-6f7306ec5bd6 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
6bcc5a1d-2d2d-4637-b413-681f433cd6b2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | NULL | NULL |  | NULL
6ba35320-b539-45dd-8812-51f43f0c4703 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
74629c3c-9de9-42ef-9865-9e1e4cbccb7d | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
fc87c65f-3146-4f17-beaa-5f90a8cffd09 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
168eceb0-93c6-45dc-b560-0396c5ff2b6f | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
0237034f-f68f-4caa-b5b5-1b3d4449a72e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
482d19a2-4a63-4692-b1ea-b97df1d84a20 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
15fdde60-0a4f-42b8-b934-489d6e8121af | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
a9f50b8c-543b-4c11-85bb-f384c1f33024 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
78f38334-8eb0-4a05-954e-34bf4f9c2d5b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
5e1d043f-b4ad-427b-beff-aa7026b36ff7 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
6504e2ae-260e-4814-af61-51052ed75d76 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
3d872ec7-743e-44ab-93f6-d71036cff90a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
55a2bbd2-728d-4e0c-8dc0-1de2f7ff7e6c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
3a9dc097-e4f2-4859-9c9a-8814593ccb8a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
efe1b942-82e5-408f-bfb3-a4852dbe45e3 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
b7eac2fd-45fd-4e75-9b14-086353456a7b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
a6d4657f-4e1e-4fe7-96d8-619b5959aa0a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
ce2a0f74-0a4f-403a-b434-cf8b74ffa268 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
77bff4ba-7e52-4065-8efe-3139cd48cb3e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
2928656e-8f23-47e3-82d7-bc5f867d6533 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
4567128c-ff18-472d-89d4-92d0d7721df0 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
4ca456d0-8d09-4503-abcf-671eee9c3bfc | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
1b40114b-b171-432d-876f-01a4c20913ab | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
18c3fff6-a0bd-4099-9727-456d63de6e14 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
0b04a3e1-67d8-4e0c-a93e-fc5f43765948 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
74f5eac6-b938-47de-9331-74315f348238 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
4d3fe422-2c5f-47c1-99db-8aa5c1f0d789 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
a6cbd979-8acd-40b8-b26d-154669f8795c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
5d4c9934-081a-4483-a6d5-7c2c0b2bae25 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
d0bb3155-c65b-4a5a-a2e3-62b8af6e2f9e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
d3d24e91-b9a0-4161-b809-bb708c53b175 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
8b402724-3a2e-4d75-9544-a537ed05743e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
0334c31c-299a-4b5f-b805-f2326f4f7220 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
80207ad2-8e9a-4226-8076-c0529428f921 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
1f114070-f894-42c6-8b01-a5d4632aaccb | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
61c93b86-24f7-46ea-be52-b2a36942afef | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
ec8f1c88-ca51-4c18-b26b-b985a8ea9e09 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
cf8753c5-d61c-4d35-a7f8-ff6b4ece8324 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
e5a1c66f-16f4-4644-aac5-fc2f6a0f0fdf | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
c06d3336-ea87-4d00-b924-c66bdc5c197e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 |  | NULL | NULL |  | NULL
926a72c5-58d0-4523-938a-7eb5f1b78a8d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
0f5a4247-7f07-4c99-9ba4-4813ae448809 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
70a0627f-ab7c-453f-8fcb-484b435c3452 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
a05a06e1-9d4f-44f8-a4da-d7975a901ec0 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
241ba7fa-c720-4591-986c-d3b18dc938f9 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | NULL | NULL |  | NULL
ff8c77ad-a4b7-4cca-a85b-0e341bde2859 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
01f717d1-7308-41ee-86a4-940501af91f9 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
7c4db3d1-1106-4899-a4eb-5377de5241e0 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
47575fa9-54ad-429b-9d93-235cc2d8c578 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | 2021-04-05 | 2022-04-05 |  | Unsafe to climb leaning badly
62db877e-3f07-4980-b74b-2bcb506a199d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
6db3f49a-4e61-405e-adda-5826b5597f62 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | NULL | NULL |  | NULL
aa630e89-aa2c-4391-84f1-97c61e7d3d82 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
9737481e-398a-4ed9-9e07-0416dd74317b | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
bad4e9da-5b75-43a8-95aa-b2c82050c272 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
fcf3f390-39f3-435e-ab90-25c3ca725889 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | NULL | NULL |  | NULL
e1754114-6a89-46c9-a307-b47eab8306f4 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
d752e5ab-64bf-4cd9-8e3a-fd4624510d79 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | 2022-03-08 | 2027-03-07 |  | Pole in good condition just natural cracks doesnGÇÖt need replaced
8e5e0aff-b933-4d89-a1db-64254aa84619 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | NULL | NULL |  | NULL
aed19e99-b51b-4af6-8e53-2cdf13a5a609 | Pole | 0 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | NULL | NULL |  | NULL
db932bb5-8bb9-4d90-80b3-855174819c6a | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
93b03910-1519-4d79-bcd9-a5a6578a8a12 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
24783cfb-5044-4bff-9a6b-281582e9c1e4 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
96dee2f0-7179-49de-bb4c-d9be812d50f3 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
92b50663-df2b-4ade-83f9-e6e8e754ec97 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
abf4326a-1ccd-4eea-9968-3990dfe656ac | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
ec65114b-27f6-4e39-b7f9-03bb08b23d8f | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
3f538d4a-ec5a-469d-9ef0-fa0a6260a2f9 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
344583d1-f707-4ff7-b50c-db6c291a323e | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
6f8b5209-cdcb-4711-8a9e-7d62f74c6144 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
6f2802bb-c03f-460c-8737-2d1e1d2e70f5 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
5ca68509-e990-44c1-bf0a-09ff47d10245 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
59c11797-c686-4198-98a8-360f1a092c54 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
12b002c6-86c3-46e5-ae29-fb22f34d2f94 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
4dff9202-a97c-48da-9870-9744cbe7b268 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | 2022-06-22 | 2023-06-22 |  | Pole leaning hard towards building. Triplex can be grabbed from stairs of the building Needs to be 35ft pole
b95397ff-1bff-4008-b171-68cb2bd58e68 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
f833f559-06cd-4272-821e-21572ce4406e | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
f9220b3c-33c9-4657-b286-389740b83b9b | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
93609343-806f-4598-b67f-1eaa9784a017 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
b71347e2-5250-4981-bbcb-38ae685dc42d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
1c3e7cff-0c2a-47b4-8f03-7556f7ca60bb | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
4815b3e9-76d4-40cd-b715-ab9e63a62be4 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
0dc9c97f-7a17-4bad-a8e8-5f452181e982 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
167b91ed-1f3c-4519-95de-ee4a519c2963 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | NULL | NULL |  | NULL
6bc63adf-03d4-4b31-a0a9-bb5f638750bc | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
55f7fcbc-abba-4161-878b-35b0ebefbbdf | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
f6e09d6b-a53a-4261-a4a3-d46456c8e254 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
e7c16dd1-9c91-4812-972f-7c1bcb5708e5 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
e7ef003c-d2f5-4286-b943-78fb99c2f935 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
11908b5f-0fde-4dba-bfd3-92ed8e4a3545 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
9c401bfb-2322-4c76-833a-fa11e6204837 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
bc093c8c-ecf9-4a3a-9bf3-b45cd6bea5c5 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
8e116f2c-86dc-495b-b264-eb6b074fd4c0 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
60bcc842-a224-43e2-9dd6-e1ce849175b7 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
84c1ff77-3191-471a-a3a8-57f29fd2a95f | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
87aa3d4c-0fb2-4fba-9072-6727f95cc351 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
6a2e5370-0f7a-4fe7-9e57-b33c403d3ef3 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 |  | NULL | NULL |  | NULL
5161549c-315a-4bd9-8be8-667f5aed786b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | NULL
6417255d-899b-4456-b3c6-fa37231f5386 | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
fb2ccd4c-2017-44d2-87e7-ae25026ec653 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
b816f01f-cdb6-47bb-af95-1d24dfa3e796 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
f464f476-f015-4750-b8d9-a98dd5b6c26f | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
d00805be-e237-4d7d-b3a4-b11fe00f07ba | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
a3e0fae0-27bc-4339-b082-c43b5de9e03f | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
8509fa78-d222-4e74-aa72-1846f285b24d | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
a962400c-fd23-4609-a5a7-4ae59a61c4e1 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
a92bbaf3-b018-434b-9c0c-3a57327715d9 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
ac043725-2f27-47fa-99d9-f1ca294dfdf1 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
8a484f29-fff7-4857-9089-2654b7eba806 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
b21923de-223f-49b6-8122-51a19ce0791f | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
d8a8f95a-5387-4e46-b565-124a697f9272 | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
f4593b9f-06de-4c7b-afd0-6b9df836ec22 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
c451203f-0202-4240-af51-175eba5a674b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2022-03-07 | 2027-03-06 |  | Still needs changed
30866adf-2311-4c6c-9ce0-050f651409cc | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
81f2ec27-6401-4940-8c63-63105b64f621 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | NULL
19268f5c-dfbf-437c-b14d-e8ca4d8d5a2b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
2311241d-3d0d-459b-ba7b-c8de086d8219 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
c4c63535-fa10-4603-9374-be4065b1f623 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
2804356c-9fe4-4a49-bc1f-17583af14fef | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 2022-06-25 | 2027-06-24 |  | Pole top rotten needs to be replaced
efbb483a-158f-49bb-85bf-29a970c0febe | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
4787aa03-530b-4213-beba-bafc340fa18e | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | NULL | NULL |  | NULL
cc3eaf5b-8fe8-402d-876e-746bf55e7f85 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
06ae4613-be32-4a1e-b034-6e1b01532978 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
196bc163-a8b6-4590-b677-4f85b86ff3a6 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
6b3c1700-406a-4410-9d58-bf50e1e2e85a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
816cb613-0007-4008-b5cf-dbd15e40c22c | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
28ddd9e1-2095-4504-a177-83922d788c04 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
17ed0436-cc43-45c9-bc37-3459a1b590b4 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
d0986280-a573-44b3-a36f-e142da9b98a6 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
85b474a4-0499-48ba-ab38-ffcfd2a4dfe2 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
e1aba768-76bb-4c00-8353-56688c2b1df2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
6c92aeeb-ea13-475d-b2dd-56b4dcceff1e | Pole | 2 | Distribution | 2020-07-20 | 2021-07-20 | Level 2 |  | 2022-03-31 | 2023-03-31 |  | Pole need to replaced bad shape move pole off owners driveway
06e02a1a-8240-44e0-a277-b80eac4c6ff4 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
7931707b-99c7-4120-8ed0-e097149de49d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
69fd2fe0-51d9-4fbe-ba2c-ba81f969327f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
596c30ac-3828-40db-a384-247fc8298fca | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
626ebcdd-4704-4010-a8f2-076f04d2b05a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
46936969-c8fb-4c15-b6e8-470a48a7e18d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
4305418b-d31a-4981-875c-5c025b4e9657 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
9e52205a-a613-47de-a1e7-5457af2c7402 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
73a73861-daa7-4c3f-a14c-58fbfb56a8b4 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
290bf067-f873-4001-aa45-bc06dee2ade8 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
e6d06425-ead1-475f-bf9e-f3d3c7e5c790 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
5ad2e8a0-37a4-49aa-aecc-3e80de2e686f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
fa420072-be74-4196-9c4b-2558018eb189 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
b2f48594-f25a-46be-b4d9-2d3e50b21e20 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
dbc765fd-5adf-420e-b00d-1544dbfcc9e2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
f8648ac4-9c88-441c-8e95-0dc27c7723d6 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
d2bc092e-634e-4ca0-be39-d42640e3999c | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
30b87931-03c0-4850-b683-2f30d7609a4f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
35fe3b8a-8969-4d06-8b13-bd1f63a3781f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
2a28e0ca-8af6-4972-a0e6-028beafc7f84 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
9564ef0a-02a7-4c72-9c69-ed3d50f1ac4b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
d1de1219-f68c-4ccc-9255-498c2c1832cd | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
d0aecece-4e54-491c-a62a-125922771b26 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
d6528172-7ee0-4858-971b-2e0d6f19aaf2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
85db31c4-72df-4cf5-ad74-8cb2c82e946b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
e3976782-8580-4c31-9870-32e8c144e65b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
bad97488-645d-433f-bccb-e862c482aef7 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
a86888b6-6692-4aca-9343-84360627b78e | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
9cb15299-16b9-4f1b-90bf-330239be398b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
c5dd986e-495d-48f7-be1c-a78e0835a290 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
bb13b521-2d96-473c-aec9-7d21f83b770d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
9612ab60-195d-4464-87fa-f77f2c8ff299 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
2ca30f9c-44c2-4b1f-819b-f0331d5f1d5e | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
7229fb24-2a3b-4ec6-a7ae-292bb838bea2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
4b217c92-9fd5-4cf8-b6c7-3a1606ff6dd1 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
c4551ab1-5a6f-4b02-9abf-7e1a8258ca49 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
efdede95-9920-4017-b8bb-5a86b3615374 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
ab2da9cb-b40a-47b1-a72e-ef95d3c05cb7 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
3a5f7a23-7bc9-450a-a5f6-d8537cec5340 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
611090df-9c8a-41d2-ae6f-82029f640a35 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
ff6992f4-747b-44c9-af52-294742064d1c | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 |  | NULL | NULL |  | NULL
694ccc4e-d5b4-4526-9b6a-2ea31f8cf2b2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
fbc61eb1-b8c0-41c0-a335-9fbd4d1b5658 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
8e0aab8d-ca63-42c8-9d7c-981a9fcf5c4f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | down graded to level 3
c70b88aa-de9c-46e8-86f6-c4b633986114 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
bda08f9b-eeb1-4fd5-88a8-3a0bd64601f9 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
ba08c030-cefb-4d9b-bfbe-5a994ecf831e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
b6d853d6-f71e-430c-b623-547e88375d43 | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
c5865cee-90a0-4085-8cc1-13936170ee9e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2021-03-23 | 2026-03-22 |  | down graded to level 3
c21f4584-7d63-4012-a386-39d322e656ae | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
da7599b7-749c-4b43-8474-2c4e8a0c3bad | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2022-03-10 | 2027-03-09 |  | Pole has cracks but not bad enough to fail the pole. DoesnGÇÖt need to be replaced
ced979d4-fa4d-4d59-96bc-57639d2353f8 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
92d9ce94-74b2-4d6c-829e-41e7e46e7d08 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
85c68410-ff3a-440c-bbcd-b64ef788ce01 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
8bb19de2-7608-47d3-8038-6e63998f79e4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
aca471ff-7d2e-4d82-9042-afea6052942d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
9cd705f6-8d6d-48f8-ab56-7a7bde2acd07 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
a4c7d7a8-396c-4809-93e8-77154a7a0f9d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
a349e40b-0ddc-49ac-9e78-72a187d965bb | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
d5108369-35a7-4d36-bb0d-80259427fbd2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
9409c75d-7c30-49b3-8146-fad952b09d54 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
dc0837f1-e8bc-4868-aa00-9d32837d377c | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
b5e13980-29b8-45e8-88e8-41f8d337ae76 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
f7dc410d-8814-4910-bc35-62597dfda333 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
f68f4919-e060-40fa-80b9-832faaaaf89b | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
f4aa5d71-2f63-4e72-b1d3-933e25c3c387 | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
f387ad30-1bd0-459f-8e75-32c891644940 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
6ff3febb-d5f9-4fea-af9d-121db7f0cd8f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
52abae4d-633f-4648-80e4-f87a66fdfcde | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
3253b362-4bba-4929-beb9-1c2410e24140 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
36dbf361-c960-4a34-931c-5a8f2374766d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
1258e9e6-143b-4ff1-913e-86cccc0089e4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
38358e00-bd4e-4880-8a0d-c4b02e134be4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
64b88181-53d1-4653-8691-2faf0d2e5b99 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
6ed0ac91-9311-4139-9280-68f3823b8899 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 2022-03-25 | 2027-03-24 |  | Base of pole sounds hollow
72f98bc5-e352-4f42-9d9d-edc4089c6c16 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
07620583-adf3-43cc-9a91-f6834a0b0554 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
8e34fb4f-63b5-4512-be3b-bfc452499ee4 | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
e7cac274-98c8-44c9-b6bb-9feb6ff071ee | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
275c3a42-3c2e-4a82-83df-8f8cc7b3f614 | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
362d7092-0399-4d99-861e-03d354a068ca | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
e5392381-9f70-43d8-ad9e-a1c9298bee5f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
fe617fe5-7c30-41f8-a77a-16bf41ce9204 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
12b57d87-721d-4b2b-96dc-aeb535649d5d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | NULL | NULL |  | NULL
9b2847ed-2921-4ad7-bf63-9dd326765631 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
a22d6ed9-e6ca-4e29-9171-6c0caceeef9a | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
04febacc-9966-4a43-87eb-69a86f1e24f0 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
f9e9047c-b34a-4ed8-b73c-daf01b292062 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
e0cc2876-9cd0-4a8f-bb2f-c03d14cd63c5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
60a9223b-21ef-455b-aa5b-5b6ff35fb81b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
16f4b1cf-f0f6-4e81-94a2-2595d9f7dd64 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
132456e1-0066-4fe2-b241-25a488e5a680 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2021-03-15 | 2026-03-14 |  | NULL
73b3a429-219d-4dd1-bf1d-10fce518c971 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
780fb113-4ded-4ce8-b6c9-bfba421c0616 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
8004e28c-2a38-460b-8e21-887038ef0251 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
66646f9d-524b-424c-a5f8-4cb771e41843 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
61fad609-a547-4a6c-a6ad-bc8ce0eae09e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
3c39e64d-f70e-4e1f-8251-021fe85f1fd1 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
3d7ba87d-8b13-4e08-bbcf-24c034797c1c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
098c164f-7e9d-4633-a5b4-88153739b5a5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
35802a8c-3856-4a9d-8eb8-03a9413009fb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
2e17ac99-11ae-45b8-a9f1-273d58ef5eb9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2022-03-24 | 2027-03-23 |  | Base of pole missing big chunks has been hit by plow. Pole top rotten. Pole needs replaced
50b568f2-695a-466a-b98d-2997535f785c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
cac63fa1-8a82-491d-92f8-e1330f14a5f9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
f05dcb78-2778-4503-ac04-9177a07287ff | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
1d9584ef-ebf1-4864-b4f3-5789b70bf57a | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
1963cb4c-b18a-4ebd-b74d-0182939b6df9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
f45cfb59-ba99-4a2b-b1c3-cd66d4fb930b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
11120c99-a2ad-475d-8dbe-b54e7075998c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
e00c735c-a286-43a1-a31a-00fb36379f4e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
c042e979-570b-4978-b783-689160cf81cb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
8b65fdf4-59bb-416e-9ee8-be0b341c8b5e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
84d37068-9341-44d8-964b-07ad838c664b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
ce40b536-e69b-4029-b28a-c833c18157fe | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
ce47d1ae-af91-4ebd-b247-ca19071bbcbe | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
f13e9beb-6897-4157-9214-e0c672b568cc | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
c9c8db20-aab1-48da-b1c7-1bd83eefbc2d | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
24b987f4-5597-40e5-af46-782b541fa24b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
b9463073-4e7b-4e41-8295-c1a0a13f00b5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
26e77652-6876-4728-a567-0a7925d3e879 | Pole | 2 | Distribution | 2020-07-22 | 2021-07-22 | Level 2 |  | 2021-03-11 | 2022-03-11 |  | Pole is rotted and cracked. Pole carries mainline for 3100
c32ab9ab-649d-459f-84f6-8ec644e9e737 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
c40364cc-d21e-4f86-ad44-46eee8975965 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
b2bdc967-b469-467d-8186-02b7f0ae0029 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
b7942559-3236-4f98-9a47-f6db44a637d7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
d85f85ff-5cbe-43a2-9ec1-20846a6e0d00 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
a08fb303-85d7-49de-8aec-e0829ad05dd3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
8ad250f5-f519-40c0-b058-4b8fcbbba1b7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
8dab747a-3709-498d-bcf7-506777190769 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
d53a06b9-9c2d-4e7c-a637-ec8a8f9a59a9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
da133657-de75-4ac4-9604-1690dbe4c606 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
da0e6c72-9e2d-4933-ba8e-ada24d403f75 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
e24506d0-e73f-4c09-a7b0-33b74c5bcb57 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
f77c1508-8f47-4721-9e1b-92e915f963cf | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
c678b42d-01f6-468f-b181-ced58d55b8ea | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
9d2cf61f-5a50-41c4-98b6-e174e1d019d6 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
9f1eafbe-ed7b-4906-acc1-7b1076608be3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
69208e43-3a14-48d5-99bf-1d3b0ae68c14 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
690883b7-c36b-470e-b002-9e20cb13309c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
0de55f19-e2f8-44be-9f62-df9912c0d1d7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
598c74c6-8ea9-4d3a-a02f-b83d41f8dc50 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
7914e5df-8243-4f12-874d-6f2b9c738878 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
0786dad8-bca3-499d-bc57-785b98ae8d2f | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
1a799a6a-5541-4ab2-82b8-3e5ed80819eb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
190b03f7-b251-4993-8382-15af1568e858 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
155762f0-4785-463c-8856-95f0551ef22d | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | NULL | NULL |  | NULL
1ad2d8df-a69e-473a-935e-3aaea16136ae | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
1ed3847d-f7fc-4074-89f9-7a6b653869e1 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
04475d42-57e2-4981-941e-2b3de281b128 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
92c622fe-9ed7-4249-9005-3899c4084d2e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
863aa4f2-b747-4f64-ae9b-8879f0fabd8b | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
2c0100ac-11c8-437d-bdf9-717f38ec384a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
363e3f99-74c0-4428-b074-bdba35b4b9b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
4478bc29-cce3-4387-a2cd-c32a3e1f3acf | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
4d7435e7-f3b7-439e-bca6-5981e48ce258 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
53e74fcf-a45b-4b18-847f-098712d8972a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
6ce6c076-5091-4dd0-83fb-b93cbd937e95 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-17 | 2026-03-16 |  | Replace pole unsafe to climb ,bad place for pole shape corner
5cb2ac38-d26c-404c-a8c9-f0d77e0c3be9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
d398e978-0e99-487c-9605-e8fbd109843b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
8f577979-a23c-4d3e-88ac-c169a0d7597b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
bd407c35-55c8-4b8e-8678-1f5bfcae0a03 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
bd13d8ad-9fae-40d2-b038-92498ae8218a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
b4d30087-ca3b-48d1-aeb1-e6960034c54c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
c92ae763-7071-404f-9f90-fc83c0fd6867 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-10 | 2026-03-09 |  | Pole old and cracked, however no pole change needed at this time.
5972564a-69b3-47ab-8170-913e61e0276c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-15 | 2026-03-14 |  | NULL
841db771-85ce-40f5-8c95-498545060e61 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
885704c2-940f-4d6c-834d-76a9dad1fc16 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
9c8222f1-a13b-4444-9c30-e8e4d6adc330 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
a71d4161-dc15-4cbd-8cf2-1ca301cd624f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
354d9ceb-7af8-425e-881d-9e6dab935a0f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
df78451d-0c2f-4b78-98bf-6bd6865c03b4 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
e3fd1a61-8c49-4ba8-9074-d018b8c85d2c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
419942b2-93f7-4f7b-93de-bbb8b9b2ee18 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
d7ffe809-1b0a-46e2-ad0d-6ab7239e3f48 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
d1f04ea7-6d73-410d-86ec-e34a73e428f7 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
0d8ee1c4-f016-48f5-be8e-32869cd24322 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
f28dc49c-cc67-4dfc-b9b6-f6662dd41d18 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
05a3f811-7a19-4417-a272-2f63df0e7920 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
ee7ac0e6-b9c2-4193-b7b9-aa9910a7fcb8 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
e0776c6d-73f9-46e2-8f4b-28cf2d1d77a6 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
8f09317d-dd5e-4588-a0db-2f9f2a0fef78 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 2021-03-15 | 2026-03-14 |  | NULL
f4719c35-e1e5-40f0-ae0d-44e4d223b884 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
f850e003-14ed-47c5-b712-81e45bc83a2e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
9b6a594c-0c09-43cb-b4e3-b62302ba649e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
3021d73c-a8be-44f2-b25a-46b72896598e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
944e1cd3-f96f-4d26-999e-1fd2623aff73 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
fb95a9e8-1af2-4c28-871b-9d0e00e3142a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
54cebd87-2719-4443-a224-8b692043b06f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
4398aa7d-1a63-4f83-924a-a414910ad33f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
37198e6e-e7ec-4d4d-af04-1ab1359c4c2c | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
78ce8d24-c839-4120-9cd0-b7a964b374b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
7acfc8db-4e08-45de-986e-ac95fde0dc49 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
7040eaef-d496-4f0b-8448-a8adad58fa11 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
085c2c25-5898-4f0a-bc5f-9385d146de45 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
25d9e6ee-5ea9-48ce-9fc5-e447f997294b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
60cd121f-d795-4c5f-917a-24e91332c073 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
4a39d4a5-6c73-4261-b391-da50cf40d701 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
27404532-3408-48ad-9a47-7a7cfcece515 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
00ce0865-0dd5-4d91-aa90-01561d97be37 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
d54a66e7-fb70-4ed9-bf6b-732d8ce29998 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
21565dca-9bcc-48c2-b026-e547c5d98e44 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
1b06439d-9ad4-4df0-a7ba-1fc62015f25f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
47fafa8c-cb3d-4110-9eb8-d8ecc0b3cf26 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | NULL | NULL |  | NULL
1d9c3aeb-79e0-4723-afcd-85eed64ca037 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
20f4af41-75d2-460d-a866-7a0db49de817 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
1d0983f2-c338-4fbe-bf9f-27907390bd05 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
7661cf2e-3116-4f35-976e-9a6cea7a067b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | 2022-07-12 | 2027-07-11 |  | Needs pole replaced
59909e58-1b08-4e5e-a859-5afc39079d77 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
5d8387f4-0713-46a7-ac75-d1df6ab20258 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
6df356bf-63eb-4276-9bd9-0dd80497962b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
435c05e2-3a99-45b1-a41d-0c3b4b9cd321 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
4a2b5025-4710-4276-a145-569f0cddbdb9 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
52e8104a-6e84-4f5b-87a5-fdb12a133772 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
68275e3c-66f1-49c2-bb85-4f36cee8c165 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
0b47ebd7-c425-421d-86b4-5d53573a560f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
b405f9e1-4769-4bcc-b9a1-0728c496b813 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
f91fee5e-7ef2-4260-8d16-bf1434bfc7d5 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
f57b86e8-a119-4adf-9f83-408cde6cfcc2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
fa0fd212-d8f8-4ad9-856d-5c08c4395da2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
f86cdc8b-1efb-440b-9f4c-e27753315103 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
3d28c191-d444-4a96-9e89-299617c57217 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
fdbfcc1b-3376-4b23-a829-1caa3373725d | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
d25e5082-eece-4711-a22b-cfc8ba2f7553 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
d545220d-91d9-4cba-81b2-77722478e04f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
ecb5faf9-6e0b-4b35-b555-a75dcebae774 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
e369c0ab-7a00-4cb0-84e4-a8040b994409 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
f6c3a41e-6d34-434a-8bfd-644f9b1fa854 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
eb6cb0cd-04db-4cfa-afde-6d40409cb012 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
e677af6b-a06c-40ee-94c3-7b25e6f97f7f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
62241ba0-b7e0-4af8-84bc-f9ce14c3a198 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | 2022-07-12 | 2027-07-11 |  | Need pole replacement
e0ba35fe-cb16-42cb-b192-aa5612a1b339 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
c0778902-b75b-4846-8def-337b8b43e207 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
867074a8-218a-4ae1-8e29-d22832ed1860 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
708a52bb-062e-4997-98ef-022033b3c3bb | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
115994ac-439f-44cb-9ab8-f0de01013b7e | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
1ac5ab46-f1b7-4aa0-8f25-f12dec34e942 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
b2aaaf91-eb36-4830-acec-b1c004751f78 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
89d6031e-8edf-49f6-91ee-9422099803c0 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
38687e2a-2c98-48e6-a05b-8ad2ab78fc64 | Pole | 3 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
ad3d56a0-1031-4e6c-b671-fa7f41777979 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
a61eea3e-4d56-494b-b7ce-f440da7f71a4 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
e4a0c59a-b115-466a-9505-8ce23b616aa1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
19baf206-5c26-4d6b-bbe5-8a2c704aa694 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
aed073ee-3047-4e68-9716-9053c86c2125 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
e0f896da-cf58-4b2c-a52e-6720c90a28d1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
e6f77305-c823-4467-90b6-6c054a208c3c | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
3d1aaf44-3d1a-4792-a657-a853978901a2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
802b8fc1-c6a7-4869-be3f-eadcd1ae393b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
aa64dc5b-aeee-4deb-9619-1f354a3e7fb3 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
1c12eec7-5ebf-424c-83a8-fd5f478a608a | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | NULL | NULL |  | NULL
31463294-66e3-4dfc-ad24-6c43d7ac1a8b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
9dd7c588-3bf2-45de-ac05-4010301dd772 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
9ba9c733-6653-46a6-a735-ea2c9baade51 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
76e58a45-cb14-4453-92fd-dffae4d9172f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
8ac96b96-71e9-47bf-952d-0212e8762f58 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
8a06853d-dcc7-4258-917d-37d0cccd6351 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
bfb2b51f-0065-480f-b240-6d6d417138ef | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
cf986275-b8c9-4115-a8ba-1246522517b1 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
d5af6537-e686-40ca-a17d-e24a9b91a5e5 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
2fce35c2-08fd-4336-97f7-70d8457934b3 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
bc0d92df-f8e9-4213-a4b8-651c5f98d9bd | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
a4ddd710-4d7e-460e-afd7-ba537d5f0c12 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
a58ffd25-d7a5-473c-9c53-133b954cd1b9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
a0ff8995-3177-47a1-8e4a-a49e3eb61fa0 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
9e72f818-3d7c-4d12-b55b-1ad6f5f80ba3 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
da0f11d5-e2ac-47ae-9d6b-8cec2b0e68c0 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
b3708441-83ea-4bdf-b5bd-350e20511b75 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
d8506054-6f8b-4ade-b5e7-b3f2679603fc | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
d66c665f-046d-4544-8ca1-2cb89af14429 | Pole | 2 | Distribution | 2020-07-25 | 2021-07-25 | Level 2 |  | NULL | NULL |  | NULL
95f90b1a-5519-4198-b78a-83e85d26ae7b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
faa804ab-0c23-4062-bbc9-394aa6f74b7d | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
ef11487d-6f1a-4269-91ce-e2205c6a2e7f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
653b50fa-bec5-4939-885d-46121f5cdcd9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
a2d42460-8559-47cc-b617-62c7bfb82140 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
5be44354-cfce-4926-af84-11da50b211fa | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
894bcc58-a829-418f-acd8-2ab8d55438f4 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
48fe73ee-9948-4386-a7e2-2420b1d71f42 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
46053864-22bb-47cd-9772-65731f1be5c7 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
40d16bb1-c5fd-4485-80db-25436f30aeaf | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
6af7a202-7a76-47b2-843d-d3405b8def54 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
5d4892a3-546d-426d-bd2b-27b4016a7b7b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
79cea3dc-6837-4cbf-a132-5dc114de007f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
1cbce5f6-c8c5-4558-95e1-588168863eb9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
2414fa95-46c4-4c84-a207-61d4018eb31d | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
24498ce0-e1fc-4109-808b-1d4071da1e88 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 |  | NULL | NULL |  | NULL
410758f3-b72c-439b-af9e-fb1771285d7f | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
6052ce87-bd3f-4ead-9833-c40e5fcbd947 | Pole | 3 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
16071641-3702-4977-bf43-a54664ef80cb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
04fb1bc2-11a2-4207-8216-58d6856f9f21 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
256c610f-a22d-47da-88eb-212cc5eb9987 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
19ce54f8-126f-41d6-bce6-55edc5d1add3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
16079d29-deaf-425a-be8a-2245f5bf19af | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
802a7fd7-ed36-446c-83ed-e631c056bce6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
3e253b70-8ed3-4288-84b6-d241933fd525 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
325fdf71-c816-44db-85ea-3843ce618bcc | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
536eeab0-bf6a-443b-ac5a-22f2b888f0f7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
ea2ee312-b599-48aa-a510-2375b951488a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
f97e627e-7e39-4f41-98c0-61ba9b377a09 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
5626322e-0487-4f57-9373-d0ad1ad1c27d | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
d6f48278-49b5-4c0d-9acd-d7d9bb6413c3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e07056a8-fe97-4a0c-aa40-5667a7f90580 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
ce51b1b2-4597-4f79-a22f-87a947b51394 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
97ef9a56-58d6-47f0-b54e-5adba61d01dc | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
ee2bad73-8101-4480-a5ff-1ec3567132c5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e75ffa6a-b9bf-45aa-a6ff-f1535dcc73cf | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e77d9ce5-76b2-4e8b-9f0c-1a425b5961c7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e3f47c04-c64c-47fe-aac7-7d357fe1a0e0 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e4d9c159-06ab-4a20-809e-1193d09d3872 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
e4a6e208-a721-4c91-af40-5065b5850b8b | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
a0c77977-a560-4a76-a444-7c7316b0995b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
a2e84a4a-54a6-4ab1-ba9e-f94b68ebe30a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
a9bf8b0b-9cef-44d2-b61f-b2ac60b9320b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
8534da5d-a8dc-4b42-8119-d0bd06e2f0e9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
88c264f9-e4a0-4a5b-b8df-4720c9ed66b4 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
8dc0c9db-6268-4b04-9b72-8c795e33b2d7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
bc9ed3f5-d2a1-416d-9e0a-1c7738dd7c37 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
1f983b94-d24d-45d5-b246-da45b6367fc7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
bac3de06-73bc-4427-bcb3-f9a181b0042c | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
5040948d-cecf-4677-a2de-3f9eaab147b9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
4a5579b2-7175-4948-9702-016a4d552df3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
3e4bf7d8-fe74-450d-a3f8-fb5655734b4d | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
7157b679-c570-49ff-a846-a6f08b4ff464 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
5fa544cd-2c65-4415-9d9a-43fcd2f78cd9 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
c5eade21-f3b4-41d7-9e41-90b2f6e046d2 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
52a7be7e-b1fb-42b4-8801-a7f34327bde7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
c984bb3d-c177-4894-8d44-24d6feab679a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
ca8196b6-beb6-4c75-82ba-61cc33c78fdb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
caca63a5-c510-4cef-9de8-ddfdc645f616 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
81180f46-e739-4a22-8676-936e05f70a26 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
cd0f9b49-edcd-44f5-af7e-082c4fc8b828 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
a63ebe2d-d7a5-42cf-9f66-e6d45152d6e1 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e81cd987-ec11-40d2-acf4-67599cf5c5b9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
d1de505c-6b60-4c06-a3e8-5ec1da9cb29b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
c1708261-48fa-4aca-b30b-a327cc7ae9c5 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
9ad72806-0e0a-4d42-8d2a-0bad5c92f8ba | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
90449a01-0b54-412d-a266-58b3fb1c403a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
bbb71932-fefe-47b1-83d0-5b92e63c3c98 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
266e7653-1c98-4d63-82be-8ba4a3f0236e | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 |  | NULL | NULL |  | NULL
24ede8d3-94c6-4693-9295-63130864f5a5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
d85e5374-c715-4a59-8e9a-21ece63cf463 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
c5bdc97f-e027-4039-8ec8-d3421ea340e3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
859602a5-0c5b-4ba9-9856-0375b091dbb4 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
b9516bdd-c9e5-4ec2-9ea7-ca8c8b7cc0bf | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
7221de15-46e0-4765-b4ba-4f00db901a85 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
6509f087-f157-4b0a-afeb-61a7bad2ae19 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
4498c0e0-4771-4f08-b24c-c2bf5b087968 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
f1f3a918-1ca1-4190-bd29-f4633a548a9e | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
26cc9f27-6d88-4c56-84a3-79d74c0f16ea | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
d0f14781-16ae-4395-acb6-bdc59bc37df6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
377ea0e0-3b5a-49c2-bc35-e62fc260b8f9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
0aafad34-42ac-476e-ac8c-54c862e16cbb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
240f5504-42f5-45bb-85e1-f8371f776cc0 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 |  | NULL | NULL |  | NULL
e0aea6cb-3892-41a2-a92c-c10ae6d50647 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
0549899d-67b7-4e22-a7b4-70f665d21b6f | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
5cbc8dfb-85d1-4533-bad3-75ba5e67bd63 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
e0e41d57-2316-4497-be09-37f8403ddfd4 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
ae5168cc-9f3e-4869-9dc2-a275595d773c | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
aacebaa4-e2c7-4490-b0d2-6ad7bba36c17 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
b6a2eebc-b732-4904-b7b3-2a91b74435e8 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
b791c4ff-1208-4a4e-ac5d-02706af92bf8 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
c26ed660-6679-4137-85dd-d702ec2bc333 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
88bac969-6de0-4066-84fa-f923d58dd592 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
9339479d-15e6-4b4e-a74c-63d32f9742f4 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
cf3366d4-2f94-4442-8694-a54ed5dbd9b1 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
57b9bdcc-ad8c-48d2-acdb-13697751ba2b | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
48ff97ee-f096-40e2-80c6-79ad6e0f1010 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
62d91f4e-7d90-4de3-93ea-cbb2d4086e17 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 |  | NULL | NULL |  | NULL
5b37d8a4-3fd3-401b-8a92-ee6324dc52c4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
5f4d106f-440f-41ca-95d2-b76e20e7514b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
6d58c532-f052-416a-951e-232b73d5ea98 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
7c69f66a-76c3-44f1-8297-8179bf540365 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
7007ce8e-ee20-4f47-baa1-9e7661759f97 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
74285a22-5e06-46e1-a1c1-63eb5b833fc0 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
4a9f5b49-79d2-4fbc-8854-78931865ba37 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
49b1aab9-da8c-4e05-a481-43e6c6b751ba | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
3495b74b-f180-441f-8bc1-0e87be8ef2e4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
193e3815-f98e-4087-ab8c-a98e2ec355ff | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
0ab79c47-1aee-490d-9cfa-74ce0f6d2067 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
1b308029-a7a1-48cd-962d-4c49080299c3 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
1f2c40fe-c02e-43cc-87c4-5bea377fa0d2 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
248f7ed7-2e31-466d-9fc7-0b5c8af7eae9 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
a6c86b8c-da3b-49ac-8efe-d12df7df666b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
1f916061-aaf9-4807-abe7-7d6191f0de6c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
36bcfa88-b9b0-49a5-826c-93a8fdee5f59 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
a631df52-39fc-4fea-8d46-4cf22257a836 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
f22dd979-5340-48fd-abca-7d9ba7801da3 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
dfc9c00f-4892-46db-a67b-6729c6027b55 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
d78ca063-ac73-4aa5-a0fb-978b23f7d073 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
d0bb76fd-5dca-481c-8b9e-8678aeaeaa8d | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
fdb40fdd-130a-4d12-8cac-410e008a66d2 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
3111d693-dfda-4ec7-9f2d-e2a45e58f8ee | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
e8d4af19-f666-4eff-a174-877bac0e1fa7 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
edce0504-399c-4c3b-a2cb-8ed6ab0ba374 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
eb6df2a8-0e23-4afa-8d55-a632337336c0 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
9784cba4-c0ce-4787-bdad-482aff9567a9 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
8dfc44b1-bf2e-4274-8197-6af57753517b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
8a064dec-25f2-40c4-bb8a-f4d4250bb05a | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
9ee2413c-d189-4b77-8edf-7431864abfa5 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
c0abcb83-c54c-4502-ae34-f8a6b4272d59 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
cc63cf0b-6844-4d5e-b954-53d1f8ef0e80 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
c876d12c-2b23-46b0-884c-a1de489372c4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
a586fa3a-5e0d-49a8-9f9e-a9b8e9cce037 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
b9ed212d-c65b-4da8-95a6-f9e331b51600 | Pole | 2 | Distribution | 2020-07-29 | 2021-07-29 | Level 2 |  | 2022-02-14 | 2023-02-14 |  | Pole definitely needs changed out
bbdf13b0-7cf4-448f-a4bf-3b5f07b0172c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
fe276f13-e176-4342-a789-6f96623eb761 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
693709ed-c576-4234-af7c-41068ab22b0d | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
e4cbb4b7-6344-44d1-9040-8190f557bddc | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
e433fabb-6d6e-4786-85be-7151856ba7fa | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | NULL | NULL |  | NULL
23e58721-722f-4dd5-a1e6-a5ba53f2d8a9 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
eb960ef1-6022-44c4-ac45-76ee623e3e26 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
e9f00fcb-48a4-4941-86ee-f9967f4b118d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
e84d9cfe-88b5-4eaa-8b9b-25ccca25c024 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
cff6b214-5ccd-4972-9dce-2ed3393d64d8 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
dbe3d212-618f-48d1-b1c0-40858e895c62 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
c703fc86-af30-48f2-a543-02218fd1832e | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
7df02f3d-fc07-4472-b9d0-d330e9b786c6 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
8a95f0dc-3de1-4647-a7be-e65e6605ffe9 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
8f07b11d-0467-4b2b-8b88-bd2251c54a23 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
98a3f311-9d56-4693-8e97-bcd26455e683 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
adea6fd4-30e3-4863-ad07-8a0e3b1c559d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
ab225ffb-46ce-4cd2-b5da-7efe58fbbb8c | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
b9b73726-0207-4b26-bc56-4ebdea9c8379 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
3bd02773-faf8-4a90-b71b-61909c00069f | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
4db217ec-acb2-4333-a444-fe91a09a2c29 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
56c25b00-1b97-4e8b-a119-6b2885c2aa25 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
23d5be88-bb3b-429f-b665-1038cac42329 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
39ab9892-5a96-47ee-9591-cce751d9ebce | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
2c28b806-2e23-414a-b770-db946a9555ed | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
fb45652f-bb6a-4972-a4f3-0fc3aa63669b | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
f21d7579-0fe1-4539-885f-fd8e9a067410 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
d99a9ea9-dfb4-4e10-a395-fb86f8ebb618 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
dfd7a173-f86e-4b4e-b5c4-febea764c9bd | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
dc85d9e8-fcc4-4350-a14c-db8f1d853ca3 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
848051fa-fb95-415f-a8df-1d4f439fdf51 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
8d8d8458-3a22-45b1-ae86-bbc984a36f85 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
d53bbb7b-4ef8-4252-a579-5e39eef82efe | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
b41fba4f-3a53-41bc-ab37-26ab8e59a45a | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
23b43a59-3d7f-41db-b121-1a6079b10cca | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
06b847b3-fec7-403a-aef5-743294ba574f | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
0b82095c-23db-4106-a52b-1aa08b274c02 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
163fd724-f184-4fa5-ad4c-87c14616ceac | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
2ed490fb-80c8-4625-83f6-0ac3618de835 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
4190bffe-e431-4f1a-93e0-295ae2cdeff5 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
467e2744-01dc-45b1-8cc4-09a5ed171bee | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
56b5d1c3-0811-4df6-96f4-ea94411eec24 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
74dfafd9-7fcb-418b-92f8-65c3e4a9cba6 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
67506e5e-7bd8-48ae-9efd-84cdd7f284d8 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
621f490a-019b-4906-8a66-c9c8709137df | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
5fbd73d2-389e-49dd-b3de-9d8ead41b493 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | NULL | NULL |  | NULL
5a441163-533b-45b0-9f6e-8b68f9d988dc | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
635888d4-19f9-4422-9cd3-40159f92eaf4 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
5d02d0ed-383c-4006-95bc-02c4de96f23c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
696f6861-cb91-4370-af66-0d7ed5758dd7 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
7c13e852-312a-461c-bb1c-43edb052e81c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
7cb9636b-fd28-489e-a13d-ea0273d0ab8e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
56640363-305b-4796-8fe4-b6a3a4edb1e0 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
4e5ddaff-d9ee-4aa7-b198-e914156e3f9b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
4992da7c-5d6b-406e-a560-46267d3355e9 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
3f9ca84c-ed45-4a74-a1c2-30b1d847890f | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
37fc1b02-059d-4954-8823-2897756d437b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
1622dcb3-4770-4139-932a-926a8334e95c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
126fd123-11a6-4211-91a8-e3a25ad0a677 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
0f600af8-e21d-4f48-a075-eaf85ac02ec8 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
0a3582ac-30be-4318-a20e-b370c5b950b2 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
2c6a54aa-4837-43d0-9123-b98373e88c1e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
224341ad-2cc7-4fe5-9e3b-d64159e5c262 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
1a100b9e-1185-41a1-bd2a-bdd3cb22140a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
1cc64aac-3612-4b75-95dc-1f3a7e674aa3 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
e2f77868-b496-4e70-b56e-3abff794696e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
952f498e-07e1-4040-be46-13afc3f2a7b6 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2 |  | 2021-04-16 | 2022-04-16 |  | Refer to change out pole due to stub. If pole topped would have standard clearance issue with comm cable.
d4ad8854-dd45-42e2-99b2-4372fd81d10f | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
99ab8b9e-c923-4ce0-b46c-8e9890dd9355 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
f5adcc77-8cea-4953-9be8-42183961fb0d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
b5c61d2b-7aa4-4f81-962c-04c1a5322f9a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
4ce1d739-0e10-4e61-ac8f-80b2d063391a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
ef021309-ef28-42e4-a38b-f52b39a3be3d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
bbeaad8d-7068-47d4-9943-344369aaef27 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2 |  | 2021-04-16 | 2022-04-16 |  | Refer to change out pole due to stub. If pole topped would have standard clearance issue with comm cable.
cb455cfb-e71c-49d4-bc3a-8e03a989c126 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
c05c5e37-46f8-4884-a4a1-02e55cf07d01 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
9e904ef8-ca92-4a6b-aceb-99903fd38385 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
9e1cc321-18c6-4c0f-a7da-55392c1ab5d9 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
a10efa60-7aaf-4d57-bd5d-3d98a3643c33 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
a32e8679-ade5-4414-b7b0-ea711c924fbf | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
a2c570fa-56be-4b0f-8341-14a6346dc187 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
87452c8a-2cb3-4d27-985e-79f8b0281f06 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
97d57daf-34d2-408b-9d7d-b7854ea01e12 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
9a38cb32-db3f-4718-ad8c-14d0301a8464 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
dc6844a5-dee1-4014-8e5e-f838a2050c65 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
3252dd4f-fc85-43fd-ac07-54e0bd73cec6 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
171cf388-e301-40cd-a45e-645246fa6494 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
96abef3b-ec1f-47fb-a988-f7c29c394695 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
78d4a2b9-8bad-41af-9a78-08ea968e0b3b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
7fd72772-4251-4e41-9ab5-4b8eb355eb4c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
9b6e34f3-c54b-4c12-a78f-46301bceee21 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
889bff9f-a31d-4850-b111-451f0e2ddf96 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
ccd2c51e-0b96-404f-a200-df16ef8e251d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
9bc6a260-8b08-4388-b606-cf0be95967fe | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
b9459af1-e01c-4ac5-97d4-f9c730bae24c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | NULL | NULL |  | NULL
4a77bfff-337e-457c-a8d5-db6a23d03727 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
73070146-f2d2-4e7b-8283-23b2f9780d9e | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
455d47fb-d0fe-488d-ad1f-66270ae21528 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
1cceb03c-0abd-464c-a263-ba99d2f8f8a9 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
001795d8-d8d7-47e5-ae00-a0f0a750b103 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
60d25ec9-0428-4b06-8fda-a2c588cbb12f | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
8e4e0149-8380-45bf-8b88-c4e89585699f | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
9d28af65-1aae-4c86-b959-1da10c160023 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
4dcd2a82-68dc-4042-814d-a94ea8fdbefa | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
c4fccad2-0f9a-46a5-bf54-406f1f4bf58e | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
e8f9bdf8-b321-43d3-9de9-d98143e3eed3 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
d6d4af7e-2867-4f1b-b381-d8e649626bd8 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
188852bf-7e31-4b74-a4c4-ab573fc2c8da | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
3edb2e98-a5ea-4b36-b962-97e7297549c9 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
3ec305a7-aaae-4075-9af0-f3363bf414be | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
5ea04825-81db-43de-b679-1a8403c36582 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | NULL | NULL |  | NULL
5caae9f5-c314-4bad-bebd-5abad13f0a0d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
4cfbd08c-11bd-4d9f-8869-8c7cca6cc794 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
67d2c9ff-bd9b-426f-93c4-ff16e405c140 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
6b661b0a-36a7-442c-b66d-3181bb9e6580 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
7bb558df-bd0a-4d42-ad2d-0eadf733395d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
709f3b95-8e3e-4bd0-9839-59f72ed8ba65 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
72209d37-2179-4077-98cd-c290167c1b57 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
721a006f-09c1-4752-a4e1-493d95098d0c | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
4126f051-f83a-495b-b0e8-0badba462f0e | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
3c532d41-4e11-4ff7-a6f0-fa5fa2755ad0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
36a22349-8c00-4aae-b1ab-13480c1db606 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
2df2ef07-ab06-4722-9193-34e78bf1b7f4 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
2f266d5f-de7a-407f-b136-73d3655c7278 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
304c4817-9e28-4f87-9f16-135ade81fdfe | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
2ebd9721-acaf-4a78-a137-6c52114f1ea1 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
489df34d-717f-4ac2-a712-1770661dddbf | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
4dfae9a6-30e1-471a-8045-b9a99c196d8d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
4b8a30f6-302c-4b76-8519-c472c4d7f8d3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
55501b28-ef41-46c4-bece-bf35aee83548 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
57bf5e4d-f016-4d6b-a6c7-0940cc00c167 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
15d39de6-8a7c-492e-b609-485393d48f25 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
0ffc3f4c-b098-4c17-b57f-1cea71085925 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
136f9d67-de17-43ab-ac44-412b12d45e4b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
09f6d240-905a-461b-8bf8-d77ed594f31d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
0dfe9e62-034e-4e88-8e99-f9eb51cc13d1 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
0b6c1320-fd8e-4acc-a649-1460e84bde4f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
0c2a266b-6b1c-44e1-8939-d6e9d4526f41 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
19d04e4a-0d37-47c3-b5fb-11be61ced039 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
1a5b203e-0bc2-4383-8309-bd1906cdf55f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
1e6fb41e-5421-4e77-b774-9513d2dfeab2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
1fa5b571-4852-4f94-9695-7aacccd59534 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
2325bf99-6f22-4c88-b432-566d72d80ad5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
9498c9ab-e901-42e2-9b13-41bd1e0eb7ab | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
d0bf7dad-6410-408c-adb1-cda2ef9b8bfe | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
d05e2b24-da5d-448a-ba90-0babb4cddf0f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
8304f19b-186a-46f6-bffe-b3a05bafd516 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
d7990b3b-b7fd-46e0-a899-26bce4bf9687 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
dfeafac8-b4fb-45b8-8136-032b2c9e23aa | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
df4fc912-ba3a-4c9e-a1db-761b3e0d19bf | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
dc133c13-1dd4-4d88-a78b-aa847c1dc480 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
e67594c6-80fc-4e14-9192-5021f583407e | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
e6a0f759-b684-40ca-9085-19665bd4fc0d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
e356b4a7-a764-4a4a-b250-ad8182334898 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
e9dba797-a711-46e3-9e8a-6e53b7504b84 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
ea4358c6-86c1-436e-954e-e4d293d61fd9 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
f1335eb3-1fbd-4245-b8e8-692cb8406e6f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
f0364de3-38b6-4579-a31a-87e341e14ae3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
fe634fba-7186-4898-a13b-626e52f7418d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
fb907482-ebcc-45e9-bdb7-7bb4c7325669 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
f78438a9-eb3d-4086-8839-40c985cbdb99 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
f2bede69-3eb9-477e-872a-f8621fd8fad8 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
c80d64e7-80f9-4c8c-97fe-d4a93e6ca127 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
c7f4c31a-bf49-42dd-a7eb-d8f3099fcc8b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
cc0bd53b-fa69-46de-ae60-616818616496 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
c8542491-e865-43e0-9a4f-67535513bdcb | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
caf4fd7d-271b-46d1-9397-e04d18e3f5b6 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
39a2f2d5-d782-434a-b82d-340e528ee5ac | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
bc0f2cc9-1474-4950-ac8b-6e6913b5e679 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
baec7f17-1d8d-4600-b986-4b813ce2beaa | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
bfe436a5-a729-4ecb-8e2c-51e71db67b09 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
b1436b1c-8bcf-4a80-a466-9863da5a9aad | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
9daaf1e5-89a2-4959-bf88-1dcf9a80ac27 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
a0e042cb-4458-4e5a-888d-46f2868fd6e2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
aa8b3c73-cb52-4308-9434-cc1cf2addde7 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
940a2b00-fccb-4f4c-8a56-2bc8c598dba0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
9b17161f-8c3f-4418-a8ca-bea4ef08e78a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
9980b6f7-5641-47fe-8c2a-9baf7c4d7f63 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
87068f74-60ad-4336-86a6-860dd8b55f42 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
885217dd-8276-4bae-ac68-0ccee650d88b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
85db1d0e-fa0f-481a-97e2-412e55aad0f3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
8b84ea1c-8793-48bd-9f46-3ce4aaf26963 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
8b81e8ce-de14-4e50-8b91-daee4836eae3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
8bdaf38b-c989-4c03-b4e1-936772e85375 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
018e380a-947c-4810-9bbd-0c50e0e4f599 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
130d4e00-1d0b-45db-8b0e-496b631714d4 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
3d4d78dd-42d1-4d3b-a50b-46859f1376a8 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
a4e2e557-f66f-40d3-8ef6-0967856bb59d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
6ea8b47c-7563-4659-850d-d0342618be7f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
224410c4-a0b1-40cb-bc33-1e20cd2ec6e7 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
2638f325-4898-471f-b39d-64d934e31970 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
3c6943ff-27fa-40b1-9c6e-a014d71fa691 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
2cb6e554-25b3-4ec2-948b-5e678c0acf70 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
38311ffc-3747-40c7-a198-201a7674bd44 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
ebf595ee-2fc5-44e1-87d2-ab94f7c0ff64 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
1e930df5-fef5-48bc-b718-c7c50f6d4e5b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
ff13701b-d8ed-40b1-a94b-400d0e2efe4a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
93ef954f-75a8-4751-bc2b-8ee73be93e61 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
974ed518-130e-49a4-b47a-95d2b85901a5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
d25628c9-a142-46d4-a40f-4dfa083cc8d2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
c907274e-1b71-46b4-b27c-fca780cbcbb0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
fcbf3fd4-b0cd-4760-b7f9-b2af1c0f0ccd | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
f4133813-d90d-4b8d-af40-55e5ea892bd0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
f10b59f1-d25e-477f-b843-5f13747e4fc0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
1107750b-4798-4e6f-bfe0-10f4c75a568f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
488f9a81-77b7-4613-80da-f523e1254c92 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
52ab1469-0867-4595-9493-2eb36542a309 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
3f92e769-2ca6-4559-9cec-124d6c66410a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
5a597158-95ef-4c9b-8142-400bd172e179 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
5dfd2579-bc42-435b-b102-9aec8fe0f2c0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
aa50cf13-be7c-4403-a954-0631041ae19a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
85d49349-3372-4df2-81b7-cddd8249a552 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
81891eb4-0285-4b00-b3dd-11e17543c1c2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
a2391e1c-451c-4256-9bff-b39d388eb895 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
ce7c1fb0-7d96-4c48-899d-b02d32e8521b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
db43b801-97eb-41eb-bf09-85908d5d355d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
ffbfb881-ae1b-4ba2-9e3b-c7d6cc7d423f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | NULL | NULL |  | NULL
e4c08b8f-339d-4eab-8ec3-9f9833d47261 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
eeb1defd-1415-4b79-9af7-ce79922ae44c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
ca15506c-e4b0-4ba2-bf8e-4ab83ab4c38b | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
bfd55422-aa1d-4c08-ae75-a4efd9a7f51d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
685a536c-c659-47fc-a9a1-413ab21c5d38 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
5ed22696-98cf-4d9b-91a0-7c4a728af6e9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
5909e2c8-2bc2-4b0e-b24d-fe8bbaaa0213 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
59638746-062d-43d1-b52a-7a41723fe40c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
7dc95049-cce7-4bab-b1a8-a879afffc607 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
932cc9ac-8528-4217-9936-e44a3bd76fa4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
3b77ffb5-ce56-453b-bf22-8cba81c67564 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
291692dd-fa0a-45b1-ab1d-7817cea70e53 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
0e3ea69b-4419-4f6b-8cd0-36be8afde6a9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
ec0e4c9e-7796-4b2f-904e-b8ae1c8560f7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
b3c8123c-8fa1-4a3b-a81a-dc33d7ecb83e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
6a035814-8aac-432d-b0a9-3ae643effc8f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
c3c3981e-fbda-4e9d-9400-801dce639daf | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
cf4df3f3-b5b8-465d-8dda-d02feb2c1058 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
9fe0a798-e1cd-402f-91bb-d4ab9718fc7c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
ab7400f7-bf2e-4b36-bd8c-4dc8f433a08f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
88338fbc-b0c9-46b8-9e36-fd0e0105b74d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
6aad7281-c469-44b7-8bf0-c61d80443e2e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
68ede30f-4e51-4571-bfb7-3425113c7667 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
82ba9dd8-8c34-48c7-93ff-3dff212e01eb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
63cad37a-749f-4094-aba0-47481db4c772 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
b73c7276-6cb9-4da3-a489-87c3dcce1f37 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
8d733888-c52a-406a-8a05-c3876ea94763 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
84d5b6e1-0965-4885-97ba-8b26177dac88 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
863f4b77-9867-48bf-8863-d416d79d74d2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2021-06-29 | 2026-06-28 |  | Changing to level three conductor that is not taped up is D energized once span to deadens pole
997021d0-b955-4107-a0c3-ad96636ad6f1 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
96e53035-709a-4439-9434-a986590e2dfa | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
92f3df32-83ba-489b-a899-0f29afe5c95e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
8ffe057a-b4e6-44b6-b085-6e94ba1eea1c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
a77ff628-6127-4bd8-9b4d-1b05e7540605 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
9e7c5562-1003-4660-8343-df5753778e7e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
ab285fb4-6940-4489-ad35-103d1972c094 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
909d9418-0f50-4293-945d-e0318b0175d9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
9f62e863-7b9e-40f4-97d6-570ef8aef2a0 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
b114f1d0-0e21-4b9c-9155-d245a0563289 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
bb6494c2-3cd1-4286-a88e-552f7da99374 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
c9acc18f-bd41-4539-b9ef-d3b4e3be4363 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
c94e826c-39a1-4559-8070-57d317f0c003 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
ceb57227-dd31-4ad7-9090-151b25e4f856 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
cf0bdde3-9846-4959-bc29-f3d3957bdb01 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
c6e2e9e6-3af1-4670-b774-95928ffc94b7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
c368069e-ab63-42e3-9d2d-acb03d404d1a | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
c21cf2fd-9ee5-4721-a0bc-2c3906d80d5e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
f515ffe5-fa3b-44c4-a54e-a214003da4b9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
fc20c68f-8a02-4d1c-8816-196bec0ebb3d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
f18fa482-e68f-4d93-9c77-59365cc3c7bc | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
ee40f41c-e415-4389-ad21-dd368a8dd9d2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
efb05e35-63c0-4d65-a961-5cf07756494f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e89d5933-a6c8-4c35-a3a6-c8dae02a3c41 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e7ed035e-3882-4647-9f92-34f5b1b39e10 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e3f816c8-d3ba-4b80-a92d-a318ec5a8d58 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e619b660-f1ea-4678-9fff-5c45931b6a7f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
dfbb6664-0216-49d1-802f-55a86a33ee09 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | No longer trees in primary. Moved to level three after re-inspection.
df8ab364-0589-4645-809a-dcf2aef9d528 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e00d3961-74a0-4de0-b612-b3287720a3eb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
dec26b87-b825-4210-aea5-ac46932ea715 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e13cdb5b-f8c6-4f15-8949-1f3f68280fa5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
e22be44a-1efa-4075-abfa-d0a2efa4b2d6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
d8c02533-cde1-4616-bcc4-764edfca56f2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
db5e2e0c-f22d-482a-9ed5-eac4f6e1e987 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
d18a9d65-36a9-4723-9bbe-2626220b0667 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
d21e9052-05af-4895-912a-4b87437d2abb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
d39a0d31-2b91-4f10-b5f8-90195a5ccb8c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
2a208ec8-3785-4200-81cf-7b99c6bd636d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
27db1a60-7eb3-41b3-bc90-36839b815a66 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
1c1ad66d-52b3-4521-b5d0-1e86a18117d3 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
0c666485-386c-4b59-900d-1efda3b4f1ce | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
0aa31781-2582-4845-962c-8cdd2631662d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
092f20eb-d98b-4121-b115-56890e9c3a25 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
1130cbaf-ca1f-4143-82fa-dc54f3c73e93 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
12bd148b-ddbc-4f02-bc02-35d66aa798a6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
155a9102-ce41-4525-96bb-4e9e218116d8 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
150a290a-fa44-431d-831a-0d45c6536cb9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
fa71151c-810d-415f-86d0-54c733efcefc | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
01e17ebc-bdf4-4a1c-9a4e-a4053a4b0a4c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2021-04-15 | 2026-04-14 |  | Pole split and has stub that needs changed out
016de47e-ac16-4ae9-974c-85cb069a0068 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
55e5a746-db68-460f-95f4-5e49528826fa | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
456d3608-9550-4e96-9efc-3472a392ebd5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
4593022f-da59-4d37-a1ba-2c861ea2c86c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
338cbd3a-4c85-405e-8b8f-bf4e678d6d11 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
2fc6b427-fc8d-4480-91dd-6e814be52699 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
2ded5301-cdcd-4744-9dcb-b1ac19c707f2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
2f5ffcfd-0698-465c-a3bf-2fe14e4ecde7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
364233ba-48a9-4630-8bab-77ddb66c71e4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
37441fdc-6a2b-4f0c-925a-fc14cdd0fe2d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
33b09294-571f-4543-81f8-de4eef4a698d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
385ac7fe-3ee9-489e-a3ec-c6ebc4b09bde | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
384e7e46-9b7c-428e-a620-258d6f42a838 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
39a94e2e-9455-437d-8111-959907cc1919 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
410d9361-8f75-40a8-a42e-46e8861c02bd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
3fc797ee-0868-4a15-aea4-103adc2ad54d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
71fcd5da-68f3-43ce-a2fa-85b365d8e59f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
726137b2-25fa-4d46-8530-4701ba8a5542 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
70509ffb-06f1-4f99-bc1b-924bd4a2fe25 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
6fe5b755-9c35-4afa-99d3-7390003f0382 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
6c399e4b-69e0-4410-80c5-7bd3109a4bd6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
77a87cf6-9909-46bb-83ff-d596eeeb422b | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
76697788-29fe-40a6-9345-64aeec456774 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
77435444-98e3-4c7e-a8e5-dcf56a5fb792 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
79005cb1-9a4d-4559-8664-97238b311bd0 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
7a26ca39-760d-4032-a468-1f38ffcdb0bd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
7dd236f7-5255-403e-b2c6-60efeb44f5b6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
69bf8ad4-c344-4782-8606-a006492712e4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
6a2604ac-328b-4e68-8fe4-e3cf9ae985f3 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
6642fc8c-3637-4f3d-938c-3bb2c92e70d7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
5eb88ab9-b27b-425c-917e-f94463d97d77 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
5f56bb5f-9cd6-4fb1-8a3c-a04c976b34dd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2021-05-24 | 2026-05-23 |  | Climber needs a high voltage assign and guy guard
59935878-a084-456d-9ecf-4bbf76be0387 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
5b3d9ee6-6933-403d-8222-47592c421b9c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | NULL | NULL |  | NULL
5934d853-9693-4572-9eee-2f39c7cba159 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
5f76f859-8d4c-41e6-af95-a34a107a73ac | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
5fc9948a-a322-402b-8a36-c511e264de74 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
66e88ea4-2b44-4628-96fd-37f36ace2cf6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
656cd643-361c-4c01-8138-e727a53db9ff | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | No immediate hazard to service or reliability moving to level 3
6b7bc8f4-f818-4114-accc-0ba4383e9104 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | No threat to service reliability moving to level III
7bec93b9-3acf-43fe-af3d-4bd326ff1cca | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
7d381d25-7b50-49ba-921c-dcd194958e55 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
3fbcfa36-5e57-4280-9b0c-b3eceb5e1303 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
3d951ac9-4003-49c1-9d35-9ba373c41067 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
3bc8d9bc-10f2-4183-acf3-fdbeb7fbaeef | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | No immediate threat to reliability of service changing to level 3
459f694b-8792-4467-ac68-cf8f98030fd1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
4a99594b-e709-4232-85ed-f2f830356b6a | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | 2021-11-10 | 2022-11-10 |  | Pole needs to be replaced
4d168164-34f7-4d5b-a4e6-42ca58b013fa | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
5303fd3b-93bf-449e-a899-b0cbc43a43d4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
01a1e930-8bfd-462a-9ff8-28c5ca3bcbd3 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
177ac5a9-cd72-4674-93be-03e0b26071a2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
14765d57-5199-4faf-8067-754407c46ec8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0af5cae6-5c55-43b8-bfe7-0e8e127c9cc2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0d1aeec7-c8ae-4d0e-890e-e418534f6367 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0b449792-eb3a-46c6-8f30-d04c1a4275a9 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
1c49a69d-3c87-437d-99ae-9913f423aa6b | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
1e3cc06f-87cf-48f5-ba76-37fbf86dd601 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
1e399946-4e29-446a-ada9-87a6f56a4436 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
1f55b1f0-e131-4dd8-a30f-9e0638fa8636 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
20355b09-f97b-49df-8aaa-181965450382 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
21814b91-fdf5-42f5-bd64-63d8de4714e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2257e7dc-45b9-4f4b-917e-fe1db5251496 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
1e47fb8a-633b-4db9-abfe-01d127932c0b | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
287a91da-c557-46ac-975b-684d2d417462 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2021-06-23 | 2026-06-22 |  | No issue with service laying on the ground at pole did see service still in tree cut on both sides looks like itGÇÖs for temp power when contractor gets panel set moving to level 3 8601 hwy 89 (Amanda lane)
28e94845-96fb-4387-a992-0d43789dbb43 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
28c6732b-7ce4-46c0-ae01-07714309cf4f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2a9cb56e-db86-4e1d-82fc-a3e544af255f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
d6ae9d52-065b-40fc-aba4-fea0f364199d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
d285b588-71ca-4067-9f56-d9d53cdebf18 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
b5bec8e3-8013-448c-9cd6-fd0017f81029 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
d7444693-fb4b-4bb8-8487-2c240599d7b2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
e4425c75-4c89-4ba2-a83a-726fd5ceb60a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
e731d4cd-5abd-43fa-9d39-0f3fe21fb5e8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
e7b3191f-e0aa-4b2f-a962-db5e98e91018 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
00ec779c-eb12-48d4-804f-c13cb846c68c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
f1caca33-bc9b-4326-ac62-14e643a2208a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
ce5de478-9be1-413f-bd57-290980287b40 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
ce9f8d44-26bb-4841-a8c8-d43966759fdd | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | 2021-11-08 | 2022-11-08 |  | All hardware sucking thru pole, rotten, needs to be replaced not topped.
cc10387c-8083-4a11-8741-08174f7ce52e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
ba4a9d4c-d19a-46bc-bba9-bbaa89a36618 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
bf65479c-d7fc-4dab-be80-f42c588c48eb | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
9dbf5f10-0543-4aca-b696-74a03a69a732 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
a5aa7bb1-6234-42d3-b7df-147264f95079 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
a8a8ccb3-3444-4e3a-8b6a-ab99a23e81fe | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
a8db26bb-c05f-47e0-a589-2bf2a05276c7 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
9a48666b-5954-4e17-8e2e-13c0c2af7ecd | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
9cffeb8c-cdb5-48de-ba82-41b5b3f2024e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
8b2830f1-2494-4494-9581-97041f0d8d82 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
8b399519-6373-4863-9ab5-b17050739f97 | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | NULL | NULL |  | NULL
8a927bb1-878b-42bc-b8c5-fbabdb4834e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
65605fe1-44cf-4653-857f-bfc088019f8c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
3de89cfa-4381-46d0-8356-6444256d0c60 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
1e6c7d78-b821-4305-bb63-665abbb459d2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0ee9daa5-cd0a-433e-a41b-ab2f09e097d1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0ab08512-65f3-404f-b99f-6f4110b1907d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0a6911e5-3ecb-499d-8519-23f292e2ee2a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
ff5a0709-52a6-403f-bfea-580d05329914 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
b1990580-29f9-4f5b-9f4e-aecc429e9a05 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
bf979a9a-e453-4e87-bd38-930a475e62d4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
bb1c0598-e0b7-469c-8e05-a5127d1d028a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
d523fe1f-f25b-4c80-abe0-90ef889f6d17 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
ea560e12-6bbe-4a21-8697-6ed8c3bd69d6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
e00e6ee7-915b-4846-bd3d-d3467e3f9a97 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2732e135-2118-40df-a459-a1351ff942e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
0989dc6e-ae07-4eda-8b9a-7947360344b6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
049e3cdb-38a5-461d-8e69-7a855821562f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
00784bfc-aa4e-401d-8cb3-5ea57aa86b66 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2235dfe3-7c8c-47b5-9bb3-bd5398c06db6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
16e854ad-3e9c-4559-8c18-4138240fd24e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2a886aa9-6ebd-4fe0-953c-ec90f93aa0a0 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2afe0aa0-29a4-4492-98e2-ba8d35e7c57d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
460f2025-530b-4c60-b4f4-22343d8eea7c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
2dce39a7-222e-4aea-8163-92d5c7de4644 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
36719411-5eb0-44cf-93bb-5f2a3381bae1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
6ab39443-84d3-4b43-9d17-9347d1511f5e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
70ec3213-18de-483f-93b3-f521470d788c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
7511b759-3986-49b9-8a46-92fc3f4daaf9 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
59ccace7-f6fb-4def-b050-181734132481 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
662a1fa6-a019-4578-86e2-e4d9e82bb285 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
bd906c22-52c1-4e53-855d-048666ebf3aa | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
c8917a6e-7690-4fd9-bf9b-6a5ad105f978 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
c6bda757-da5c-416e-a0d2-5f8b88c234e7 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
9d7ecb32-74e6-4b45-877d-45f01c9bb3c4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
94b0cee8-ecfd-40fa-a49e-c72042900252 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
85591d6f-5225-401a-8421-1aa41d5e44e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
e98947ef-2596-4287-af6c-fca455145239 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
ea8243de-0f7d-4e75-af5e-521bdb3f2b0a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
e8163cfe-dc38-44d4-9150-284e9a83f924 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
d7cfd504-78f0-4148-8f07-a8bfc885fccd | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
940ce92b-4bd0-4000-808a-814be67cbaf1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
948a7c6d-6da5-423f-b48d-7dd5785c6052 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | NULL | NULL |  | NULL
b7c5e067-fcd8-419b-8a8c-58f1ece0cdc5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
f21b2d06-6edd-433c-98dd-c78c9d99d776 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
8f591d33-5cb6-4257-825f-d8fae9d60b0c | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2021-06-01 | 2026-05-31 |  | Needs hardware tightedned
94a0f837-7a7f-4e5b-a606-433ae1e2d179 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
a0c24945-a699-48c2-af2a-07715f737b44 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
b797b66f-0f10-4012-91b0-216ae24bad62 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
bed3caaa-573f-450d-943a-ea560626a283 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
b86c43a0-ff8c-4e98-afea-44fd7fe37b3d | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
5baf9f7e-b80a-433a-a64d-d24ef462aedd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
306a8452-4d4c-43e2-9429-343854a70dd1 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
53c19b41-c407-4d31-ac65-922b982df8c5 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
3e844e3d-4274-4b58-b89f-4d9b01e6d81f | Pole | 3 | Transmission | 2020-08-06 | 2021-02-02 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
c5262d63-f7a7-4b6e-b548-009234183927 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
b20ef1aa-a86a-455b-b280-8532554c1277 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
fee556ad-f08c-4ab7-8dfc-5f6b7b765e34 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
8c673f87-a295-4fc9-b77d-9201603ef82a | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
89562b8d-c9f5-4dbc-9ab1-b3c708b740ba | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
8b27b12a-e1d8-4b29-843d-143c552a6787 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2021-06-30 | 2026-06-29 |  | Needs high-voltage sign stirrups and copper hot taps / Changing to level III
8b23763b-e982-41fe-8d50-ea375b106be3 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
86b60daf-887b-4caf-ab67-e30d06efd9de | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
99a04e76-b79c-4bca-a78b-469ba67619b0 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
9803feef-11e3-41c1-8fca-ee8702f1b767 | Pole | 2 | Transmission | 2020-08-06 | 2021-08-06 | Level 2 |  | NULL | NULL |  | NULL
8fa28f4b-faa9-425a-bb4f-3d10fbc02d78 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
90bf984b-2b8e-4ca4-98fb-561c49819037 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
93e5284d-7508-4b1a-a31c-3a63489558cc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
a8a66c1f-1872-407f-a13e-3074a1c2e581 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
9c60ff2c-058b-4549-bada-efba859c7ffc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
a5c7bef8-b9b7-4317-9206-20d6fc73fd21 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
6780215e-6d92-4338-8380-50603cd9effb | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
a060a7e6-f8ec-4845-9abf-b1bb5ce5a2df | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
bd51a076-16fd-452a-b2fc-fd5437ed8bc1 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
bf2ed20a-b677-454d-af48-a3a8b4f1ad2c | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
b092926a-4f95-4926-b0a6-8000ffc7f819 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
b81a658e-396a-48b4-b9aa-35564ff30269 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
c1717a43-c82f-428d-93d4-cccfc5f33e77 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
c3a00615-bd6f-480f-9a1b-ef9d536e0c56 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
c0a18295-55fe-4762-b589-76d5d83b3d82 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
c08ef8ff-b904-4b2c-9b7a-f5ec4d02185e | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
7b16aab1-5b31-4e76-994f-81f0155f3c40 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
f1f65302-a38c-4800-bcda-ebbbf44788be | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
d4883218-9e77-450a-a09c-ae2529abe71c | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
fdc0f9b1-3315-40be-980b-beafe5bd0791 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
a5bb8fab-4d50-4a13-91ac-8d83520dd434 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
eb488266-1193-40a7-887f-6f4ff76d29e5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
ede784ad-c97d-4b07-ada1-e9e942370bd8 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
ed28f450-96cf-4737-93ad-f9cdbf23fd67 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
1f812904-ae9e-4ee8-8eea-ce4e4fbb3535 | Pole | 2 | Transmission | 2020-08-06 | 2021-08-06 | Level 2 |  | NULL | NULL |  | NULL
e21d1c4b-40bc-4e24-a1ec-ce545d9874a9 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
e12f340d-b8e5-4437-a0dc-552558de9ebc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
d7997488-3ea8-4478-a492-b2b88e69131e | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
d6ebea98-2c75-4b76-88ba-e756ba58f37a | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
d9dc8d8c-cb3b-4dc7-a651-b46e88169341 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
d035dba8-17b6-49c1-8bd7-914b4f6e1bcc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
2ac5f31b-18a1-430f-b01f-244b6f330998 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
2bb14fb0-8ed5-42b7-a13d-0dac281e73b5 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
2c67edb4-a078-4b7c-87b2-a7c8d7c17bfa | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
27c7108d-946a-4542-a3fa-44291b8fc6e5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
273dd98e-be57-48fa-960f-23575d9ace86 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
21493901-e1ad-4891-bd75-8aef6c61586b | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
22b04be1-4ccb-449f-9929-b94d8b5bc871 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
23702c38-4150-40ce-aff3-5a032fee91cb | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
1fbb3618-1ef4-42ba-8d11-45589f9cb6fd | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
2167a372-0b16-489d-a25c-813e2199c73e | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
21277841-1680-42dd-860b-7e81da34e133 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
1cb4e5d9-7f76-4ae3-b4bb-492ee919388c | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
1be441be-fd15-424a-b32e-08f638bdfdbd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
0aae8441-c6b5-4752-99d7-5319d558b075 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
0798a37c-6e73-43be-a6af-9d527de937ce | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
152f7142-95eb-443d-bf16-4adb53721e55 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
04614e75-11ae-419d-a151-f8962ee01168 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
50d2d93c-64c0-448c-a8f6-a90585d6f9d2 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
51b846b8-f1e6-461a-81d9-06bd4346b6fd | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
4e1f38f0-b338-438a-9ceb-cf48f0d62f02 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
4f7c55ca-9bcc-4851-89e9-be2df314aa65 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
431d602f-04cd-40aa-9cd6-0a867182e4ed | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
3b142276-1b53-4ab6-b782-dcee543537f0 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
34a41090-2455-4a09-9d58-0018a6e1436e | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
336992f0-33d9-472b-a198-9a7f70d73ea6 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
2ed522c4-2c00-4c45-be3d-477a6e35e73e | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
7b1a224c-d871-447b-b280-e65de7e8b020 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
79b2a4dd-6511-42d1-868f-5322cd1d6370 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
797ecf81-1a20-469a-bfa5-2aec7609fbec | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
7d14871a-915c-42a5-8bd5-5a395461f090 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
7e0bf980-d8bc-4529-adbc-996b7aa5aa93 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
8038b02f-2539-485a-8f60-1cb29129256a | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
822112db-b37f-4904-8c6d-e54ee88b8d62 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
339260b7-56da-481b-812b-b5060715ecc9 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
749ce49c-ce96-4cf7-8548-9ceb7c928c31 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
66492662-7246-4545-9615-9486a83bd365 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
5cd7e909-36a5-4dbf-87c6-5a96c28a285d | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
5eff9fa5-ae71-4c6b-b9a1-24d8d5ef5f03 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3 |  | NULL | NULL |  | NULL
6384113b-954c-4046-8962-86b2f630d0f6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
631b9428-9efd-466b-833e-f73802a748a6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
670f770c-2367-49c9-aa26-3134c8f0a2cf | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
6d2c645d-b53e-4655-bad5-5d56d72b64ef | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
7633d2c6-12c4-4f55-a8f2-63aa8d59b96e | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
75aa3e2d-133f-424c-8700-c1a9216172c9 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
78338716-93a0-4bb6-8fbe-dcfaf66d0376 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
71b3b1c8-2433-43c1-84d3-721ddea6c241 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
7091401a-2cf8-44ff-91ef-8e5651c58f78 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
83c0920f-a3ea-488d-a74b-4bb14a3444c0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2021-06-01 | 2026-05-31 |  | Tighten hardware HV Sign needs changed out; need new upset bolt. Non GO stirups & bird guard
78c5593a-2ba5-436b-93ff-b66dda796582 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
79e9deca-358b-457a-b0de-968b6ee90b06 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
79a520d2-0a98-4212-8254-fc4f8bf73b94 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
7d838af6-e97d-44a2-8ff7-7dd12a0c243c | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
2e7a1a36-0959-4f56-9a54-b103d5b34f6f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
3dfe287f-2078-422a-b56c-8ea1e47efac4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
3e958964-2e7d-457b-97b3-590fed72085c | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
441c15d8-87bb-4617-9b9e-834d29b1a0d9 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
4bcd46ac-01d5-4b3a-875f-5d09d6a9f691 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
504d0ab9-e61e-4108-a817-4721caba8e2f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
54d6b2fd-d106-46b8-9913-881257d831fa | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
53ec9e31-08e1-43eb-b958-60ece6e6e657 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
5391c9a3-4564-420c-9504-23637ecc6973 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
57357c9c-4260-46d6-91e6-ee618d65e684 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
02246cbe-3a83-455a-b774-5911ef51b30f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
62054625-3946-455b-98ee-8afbab0f20d7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
c7347d5b-8e51-455f-a754-0aae2c6da479 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
15570870-31e7-40fc-bb11-b47a8031a01f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
144134f3-759d-481f-a7ef-602c3cc8b989 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
1029d0ee-ccb1-4168-aa4b-cdc166633f86 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
094f0ba7-79b7-4d9d-9cd1-8a4d310e5650 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
0ba60eab-d404-495f-aa44-cf6d1fc14b99 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
0d4077f1-04db-495f-b1ff-97570487daac | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
1b6c5f96-1900-4cdd-ac81-f61ac23a20e4 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
21aeb734-edba-4b2e-91b5-d718b296cd1b | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
2cdefd32-ab80-4864-8b80-80dc20b3d859 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
2b7e82c2-5850-4e5e-8b28-00093f17b058 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
d42b0df8-9bf9-46ab-88ec-457838d09f9d | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
d799e9ac-d124-4713-9a7c-c0d589d378d4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
d8513130-8605-4eb3-b92a-821d21c1614f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
e3284f93-d64e-44ac-80b5-38be06ad72bd | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
db98aabd-62dc-4bfe-beb9-e58c9734a5f0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
db9e3513-c175-4a57-a482-e5e8f6282133 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
0223d736-bf71-4c13-8be7-40cfd5051cd4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
93aa8a56-96f7-480f-b605-68aff92bfc92 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | 2021-05-17 | 2022-05-17 |  | Vibration dampener missing
987f479b-8039-440a-b286-fcac2b2a7a09 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
e38ade05-f812-4b3b-8351-e27efda55cc4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
e4c4d3cb-c410-460c-aee3-947a3c96d051 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
ecbdd67b-529e-44b6-bbfb-e05edbc80dd1 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
9eb4d24c-e04c-4494-9b2e-c86ee8d2deb2 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
b5be4d08-7f9b-4d72-b2c3-6f875059f1b4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
e95092dd-5f86-4f4d-9b14-e2faa64316d5 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
fd99e5b5-7ebc-4baa-a229-2e91211a0a60 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
988ca0e3-1467-49c8-b36d-bef4c9ab222b | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
f34e57ca-c632-4e55-b81e-9175f53c5a45 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
c56830f5-4972-4233-9d88-2812d201d127 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
c28b6284-6d21-4baf-906a-af4bd038798f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
cae9bbb5-e019-46dc-b780-31c6d71512f7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
cd6ee233-a8ff-4a4a-8880-bb43e9bad7a7 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
ba80bbf8-ce69-412b-95e2-ca531209a50e | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
af96a897-1d36-4bd5-9434-6a28ba0fbb74 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
bfeddf90-70b1-4f83-9fc6-e297d3df690a | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
9cc4f567-2d93-4b55-8d49-86cda292dcb4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
a0c744c0-8453-427b-934a-0d27604ea11a | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
a603589d-404a-4163-a1de-9309aabe10e0 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
acdde7ec-7dd9-4c89-915f-5a09470831b7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
ae7b9670-b59f-4cfb-9c42-5b0ae48ffede | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
abcc1f25-862a-4655-8237-5f54c8adf17a | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
95d5b573-c3eb-44d5-b1dd-50aa9de901de | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2021-06-01 | 2026-05-31 |  | Hardware needs tightening
95307ad0-66fa-47d0-8150-7beb6e60c230 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
952397e1-3130-49a7-8084-6dfaeb0da75e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
900b2a71-16cb-4cff-ab05-b775bf0fad3a | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
8f11bc46-f3c2-4be1-9811-d23156f8ef5e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
96a1e0a9-c7aa-4293-bfe2-348cfbe5850b | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
9bce5e35-3fd9-4dca-80f3-c1ad98b231cd | Pole | 0 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
89b76d8a-6f80-4695-98ca-de37aac708e8 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
7637161e-21ee-44a7-80b6-f7b4d37eed11 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
58ceca54-a69b-4265-beae-10bcdb14967c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
ff686600-44d8-454b-bb77-c03308af28e2 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
22fe7f11-5d91-4941-8645-a81f949cfe9c | Pole | 3 | Transmission | 2020-08-07 | 2021-02-03 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
9e85afe4-727c-46c6-a5fe-547454adeda6 | Pole | 3 | Transmission | 2020-08-07 | 2021-02-03 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
77910078-a650-4efe-ad18-4bf4d053be01 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
43990ec4-c3e9-4fee-bbba-626312ca730d | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2 |  | NULL | NULL |  | NULL
1a1496b2-c0c0-4a27-a30a-8ee41d4092a9 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
0988a21c-1ae9-433e-8a3c-48e39d169683 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
4f2b7a14-8989-4ae0-b19f-4f5c97080968 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
64725eca-f689-41d0-8925-050fe44435e8 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
6a1a7c52-a491-41e1-b2bf-4bd62b7abb37 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
7969d91b-d734-4237-8c96-a44b4be48c1e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
949cf6f0-584d-44ab-8202-79dd1f5cfcdf | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
93b164b3-f9ef-4b13-9734-422b08aef464 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
b7f500bc-cff1-4176-9ce7-330219743bec | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
da86f739-68db-471b-878c-c43d5c67e176 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
f4cedd95-44a0-4ce2-b023-410875eb848f | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
898fb4e4-2a41-4d44-97e9-9e41d64bf08c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
0033f633-775a-42a1-8d8b-5a5f681d458e | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | NULL | NULL |  | NULL
b5b7eaa5-a391-49e3-9b2c-d01e9e86f1d0 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
e262779a-7db1-4491-a6d8-086e748f6081 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
ce1fdb9c-d8ae-4185-ab97-3a3c61f60f32 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
96b8c7ca-f31a-484d-8570-396c38d818aa | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
8ed209a0-9924-4d32-a293-fd2c452feef2 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
7f2afca6-7bd3-4b31-9e5b-91991cb25e05 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
bb500cd1-4278-4b62-97f5-fd714f0c1778 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
af21bcd9-e913-49a9-9d60-d91e0175062a | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
61146b59-2f58-4c33-83ac-a6892b4a75c4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
49c141bd-86fd-4d37-94f5-2ee2479ab9fe | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
4615da5e-caff-4528-92a2-3c84b03b294c | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
384030ba-2fd3-40ce-8218-262c10ff1bb9 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0771a3fd-b22b-488a-bfea-ccb93d9025bc | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0a62a4fc-08a0-4811-aad9-1b0d73fd17c4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0d04d559-6add-494f-b154-163ddd155afc | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
f31620c4-3cc4-450d-bbfd-a5ff3870e74a | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
d2a9964d-2593-4591-8db1-5b95c98e4c8d | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
ab9841af-1aa9-4bbf-9d47-5c7e461e4c2d | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
1bebb68c-d6cc-4638-8dd7-e0af5c46e470 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
88b05b64-e38e-4f30-9ab5-ea3da6b979bd | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
9c137735-85a6-4d22-8473-2aaac15d119f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
980f09f8-9921-4048-825f-99afcb5d9c7c | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
9154720c-f78e-4969-a4da-a2d63af6b8c1 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
9557d04e-7e05-4905-8839-90a6778671f2 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
a9873b68-eac2-4780-9b11-3d2a7967842d | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
bbe6edfa-e325-47e1-843e-fa758a3a32cf | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
b9ba4abf-b5a5-4766-a983-f6b105826f9f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
b94ed509-ec1f-4dc3-898b-b4b12f1f9dc4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
b25d2d8c-4dca-40ac-a79f-7090a5638a54 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
b4208164-897b-4fa0-81a8-16ecd0ff19ab | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
cc602c02-c923-4901-b516-a3ca9a30498e | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
cddb1b7b-d8a0-4f05-82ac-70f66e4095f4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
c846bcea-9f1c-4acf-8d31-f9c28e55a50e | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
c160f3e8-6e96-4131-b409-7fcb66cc2237 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
c0651488-7b56-43f9-bd19-f8c1df98af19 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
f9dba5a7-7aa4-4822-b00a-f896dd24f44e | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
e9228c32-2489-481b-af57-491a11847902 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
e8ed8f4f-b11b-4888-85c7-64f818e6754f | Pole | 2 | Transmission | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
e8ad5662-8c0f-4209-9a0a-7bf58ce843a4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
e5fee9dc-b689-44d6-9157-f130b868ce51 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
e484adaa-c8d7-43d5-acb9-f93f4adc6695 | Pole | 2 | Distribution | 2020-08-08 | 2021-08-08 | Level 2 |  | NULL | NULL |  | NULL
9570cb38-1dc7-4630-815a-840d66c6d2fe | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
de5ac015-6037-4fa5-8802-cf5c951b6b4d | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
ded8bbee-d4a2-4034-8588-ff9738d3721b | Pole | 2 | Distribution | 2020-08-08 | 2021-08-08 | Level 2 |  | NULL | NULL |  | NULL
d94fe4fa-22a2-421b-b8ac-bce559f0ee3e | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
d6b027b0-79c8-4973-907a-080eb0c68013 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
d2146ed7-947c-4121-b85b-d983dfd9fd55 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
d293ce12-3567-4dcf-9817-528cc753b2d9 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
24d8636d-d2ad-448c-b203-cb55973ef767 | Pole | 2 | Transmission | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
262790ad-73d1-4107-acda-5f78efff53c9 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0f39039f-7552-41e2-9292-8a858bb32cf4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0b8ce194-b19c-4595-b2c8-95e5cc7a7415 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0b168aec-76d1-48ec-9d86-6777d1afb3a6 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
09d38a63-2124-4bfe-a326-4a89b64d92a4 | Pole | 3 | Transmission | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
09dfe4ef-a759-4b86-9016-2c895c06a713 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
0a163401-b722-4f99-a8ce-fd38fa842878 | Pole | 3 | Distribution | 2020-08-08 | 2021-02-04 | Level 2 |  | NULL | NULL |  | NULL
12451f30-7775-46bf-90e4-e5679e5678cb | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
114f1cc8-b4a5-434c-bcbe-d05606eb152f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
556ef512-1961-49f4-a841-f5032e796ebb | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
4e768e82-a505-4442-b95d-0c69977ebcee | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
52bea135-6342-49c4-b224-96a154c6fdec | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
48c67562-3f9e-42fc-925c-e91777125ac4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
354e0b99-e20d-412f-bead-bee2b7ef7cb0 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
381a9021-335e-4d31-8753-f4b5b3c3c402 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
3795a344-c14e-4004-a738-a09aa39db785 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
376d17c0-bcc5-4a4f-a959-401440a0937c | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
7e6acdf8-2059-41d4-bbbb-c8c0490b7a6c | Pole | 3 | Transmission | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
79aac699-d5fc-4aff-91b7-77075ead77d1 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
7f48c2cd-6592-4f00-85ba-093f316fc9dc | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
71ef0733-318a-4aaf-b2e2-ce5df17c64b7 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
76c48ad8-f71f-45a0-8c55-e86007388f7f | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
76631a4f-4d31-4b6c-9853-09a5d1af81eb | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
6d34b0ea-e4e8-4d78-a276-f3dd283ef829 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
6cd0a2e7-a269-4fda-aab6-0c9f54b5bdb0 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
66711678-afd0-4a1e-829d-75dcdc438fa3 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
67347856-db2e-4591-b79c-37ce9016f4f8 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
6333adf6-3f33-44ba-bd44-0f5a0a6e1f85 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
5df46407-b24d-4bd0-9a6b-52d6364d25b4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | NULL | NULL |  | NULL
6840d229-2c61-4b56-b767-50d2a9ba57be | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
676acd28-4dda-4019-a5d0-1f18a3771d98 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
6d34c4f4-418e-443a-8e05-fd1208133649 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
71f62ba5-20b9-413c-a158-b43c912507a3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
7dd5160d-be73-4133-bd97-b755def7547d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
83f69566-1b33-43b7-b18d-921305b57c0b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
829ea974-07c2-455f-a205-271d72e99bf7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
38217f5a-fd7d-4faf-994c-8b3a0c86ba9d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
3314f109-ef76-4222-87a0-ce35dbc9cd85 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | 2021-05-10 | 2026-05-09 |  | Vibration dampeners gone
344e7ce4-34cc-48a0-b396-4ebdda41cd7a | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
2f378d56-0883-4d52-8602-1f73fcaa44de | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
312564e7-7af6-4612-9d9a-200747f7c84e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
3e1644dd-fa31-4155-830c-28a9db266c12 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
3f18ce0d-a86d-4518-a486-a74fe1d4c001 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
4305e7cb-770c-4e32-a2ef-f981ea180cc7 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
5084c38a-7ff3-4f68-a164-b1135835b633 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
50c1ca9e-2ef3-473d-995a-e1906b0e2f6b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
55cf549a-ff24-44a4-ab8d-c49bc1d902c4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
544b6797-3133-4f1a-adf3-de312306f3bf | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
57db1d8a-50fc-42c9-8105-39ddaaf25e48 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
144fe3d9-06cc-42d6-aa6e-ef1285809bd7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
0ebcbba0-01ea-4b94-9d1e-f66ed002f129 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
0846c154-c3fb-429a-b0ef-0c4a15a265d9 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
0da049a3-ad51-409b-979f-08da6c2f9e03 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
0cc66d0d-b590-46b6-a33d-70d8b2e6bcc3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
27fbeef5-7241-4a5c-a0d7-947c2298347b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
25a1499d-73b7-4d37-823e-5ba4571711a2 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
2996ddf8-389e-43d2-99f9-c3234e9a1cf9 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
21be9825-f584-494f-b1ec-5e777ea1caef | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
1c041453-c3ee-40da-a0d9-f6120ab35595 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
2d25792b-ba3e-46ce-a419-53ae60fc0ed2 | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
058a6018-0adf-441f-98d4-700424598959 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
03c319fb-8baf-4b34-ae6b-4062f03464e3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
8ee43334-1b02-4a45-a3c7-fdea37e6bfb2 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
d2617a62-240b-406a-87ae-305d1ed393e3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
d48df17a-3d47-4e88-90de-b5f0cb1627b4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
d32fa763-e735-4d5b-96bd-a0d8304609cb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
d9b33f7e-82d5-4cab-a5eb-f3792a4ce0c8 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
da757bf2-cf77-47a3-a2d6-96416db0d4b5 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
d8287010-cae8-488e-898a-5ef93e2a83a0 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
94af3719-8cdb-46f6-9550-7e1ce66b02df | Pole | 3 | Transmission | 2020-08-10 | 2021-02-06 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
dfc0a50a-757e-4245-bb9e-0712f29de56b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
dc25532d-7634-433d-8268-bf0e8b64da12 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
838fb907-b3a0-406a-9072-1e399d78eefa | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
1c701eef-2410-47d2-b44f-84843338f3b6 | Pole | 3 | Transmission | 2020-08-10 | 2021-02-06 | Level 2 |  | NULL | NULL |  | 111 line to be re-inspected June 2021
e6f5ce70-efaf-4778-a0b0-27c2d8711c09 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
e4f1c3fa-1186-4d4a-a968-74da57d744a6 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
a45cbec3-f522-4a49-8d35-d5415c76ce83 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
e7dc4542-65f8-4fe9-8032-7318a6a81059 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
ef6f0b72-be91-498e-9930-1eb6026ddc8a | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
ef27f034-6f79-4de5-819f-c68ba9cf9bc2 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
fd413ece-688f-4af9-ae39-b329fc71feb0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
f1e5a4f5-4127-40a9-8a93-8b5e32abeef3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
c20929f2-2453-4652-8b67-1cdd3e4547f6 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
c51ee81f-4cec-4651-921d-e4603b37b1ea | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
cf3a9cd7-70de-4e90-8a99-349651712814 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
b839500b-6047-4905-b9c6-df7d9e1e532e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
b8e46f50-140e-4116-b0e1-461c915c0ed5 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
ba95fe97-7d4e-4fad-994a-e9e6716550fb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
4be147d2-adee-4e89-988d-99ddd736afe4 | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
be7608e9-79b7-43e4-942a-a7736ce6c78c | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
73c4a8cc-c28a-4133-adf5-f637528fc4eb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
9b86b828-25d3-42bc-864c-15a3a1fbaf41 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
8acfa16a-29ac-4bd7-9d9d-df7c3965c57f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
8cf50f29-a20f-47c2-8a96-fb48aeb7f68f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
8efbfe7e-51f5-4ae3-9891-e1721e725657 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
04fb9588-5210-4f12-9594-7a584ad9a3ee | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
ff42a9a2-01e6-4fba-8c9f-fad3174eef84 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
f66910c8-8ab7-4037-a14a-6107b39e388f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
ee0e9526-dce6-43af-ac23-0935a028973c | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2 |  | NULL | NULL |  | NULL
fc0a968b-6754-48e5-8fab-990a67545535 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
13fdc2a0-0af6-4114-bb88-2223c46c8f56 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
f24169b3-2c51-4482-a4ca-7269b0367f22 | Pole | 3 | Transmission | 2020-08-10 | 2021-02-06 | Level 2 |  | 2021-06-03 | 2021-11-30 |  | Two miner chips in two insulators
31a10354-8cb5-44db-b3d0-1cc82f2b5971 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
40ab11a5-779a-4454-aa04-8b481458511f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
5c82b238-5f98-458a-956a-9c3545cdd839 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
7ec4a4b0-2347-4191-8718-65a3f7f16ec0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
7c36f091-643d-436f-ac02-72472b8b16c9 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
6e9211bb-2b2f-41b9-9fc7-c9f9dce4317e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
c91acdcc-896f-492b-9147-0a505aabbc5e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
bb32c5ff-216b-47e6-bff6-8db03de960f0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
b2fe75f5-eb18-4b84-a7c3-77c92168e1d3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
af30944a-91df-4d34-ad3e-786e177bc4ae | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
ae2785c1-8b25-4425-9245-e228b8cb5357 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
8032e7d3-27aa-4e0d-8b05-623edea9d822 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
96a0cfa9-903b-4fde-ac99-3d4afe2a256f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
9a818497-6161-49c5-bc29-7d07af6968d1 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
a69946de-8393-4559-91e1-7863b21258f2 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
e6ae605c-f65c-4bc4-be0e-99a0a263fac7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
fa0a4eca-a786-442d-9a28-446dceefd54e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
ec4891e0-82c4-49f5-aa0e-af537bf7ead4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
d3185ad4-06db-4160-9f73-f5063a92d089 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
fe5f647f-afac-43d3-8dec-1dd946271f67 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | NULL | NULL |  | NULL
006bfd1d-bc17-44d5-8738-a5c00bbb089e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
fc8b3e11-3958-4591-9b02-41beba8fbdc7 | Pole | 2 | Transmission | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
f6dd73bd-431b-493a-91ac-0c2f940d93eb | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
f8700744-ccdb-4253-850a-bd057f73c9d0 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
db79698b-1db4-463b-a26e-5d6c05e9bf9e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
dbd4b02f-f6ee-4eca-94bd-477026884420 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
ee54b362-5fa9-4de7-a0c0-0ae338c7f04f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
ebbb8f7c-7c78-4345-add0-74535e2cc0d6 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
9c785737-6de2-42fa-8b37-9e8c94180b33 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
97431d8c-ede0-4f6b-a296-038a5bda8bbe | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
8c33ff4a-24e7-4011-aec1-cb27983fe88f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
837f2a58-5707-4160-b3d6-2645bc20efc8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
93950de4-201a-408f-8a6e-7c6acd39e430 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
90e578ca-ed6b-4d1c-a108-c3fd9b5f3619 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
ad886d2a-3bc3-4716-bab3-2b88cab9809f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
b79fc751-e5f4-45dd-a9bb-49f2d37aeca1 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
b366bd8e-ee08-48da-bd35-a2a7925a62fc | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
bafada88-8846-44d8-b260-8137cb4e898e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
ba748093-3ea4-4e04-b742-6b0e777143eb | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
b845ee1f-9879-4778-ba4f-da52c528f605 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
c7ed9cd8-0fa1-4edc-ba92-0117dd529295 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
cafd9538-2f84-4115-be4b-f05d84559eac | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
c4127e7d-8eba-4059-8dc3-0b3cb3f78b99 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
75118536-2cbc-4dbc-8668-24172c2a4751 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
73109797-ac64-46e8-ae0c-b908f41072dd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
682866e8-88a9-4cf2-9f01-3b3028168d22 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
7dd32696-157b-4907-a075-93889b3aea74 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
7db52768-7e70-4580-894d-084f51a8c2a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
76f1e667-e5b8-4001-828c-253512d3ef32 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
75390c82-54f8-492e-b7d2-6dd9b53043d7 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
5f1d12d6-a743-4ce5-8562-e716b8f12997 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
526ffd37-262c-4205-9eea-e5be282e2d83 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
5401313d-1f35-42fa-bf29-105eab38d294 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
6596c158-2bc3-4dca-9797-cd51ea69f4cd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
46a075e5-4d51-44de-89d0-65f1654a7678 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
4b1f6b6f-ceda-41e0-813d-5e106b5832ec | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
51cbfc7e-9349-43ec-aa40-691a27a897ed | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
31cab056-13dc-4efb-b5fe-0979fd87e6a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
381e4d13-0ee9-4bff-ae65-af96b01cf12a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
3e5fa1fa-12cb-446c-8a5a-9b65206fe7b8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
3d7f74df-c904-4d91-85d4-2f337bd32aed | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
01b43a7d-067d-4130-a078-809aba570e62 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
00b9fd77-89d5-44dc-af68-b394b3bcb59b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
075f2da0-2cc9-4c78-b741-83d30a00646a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
0b877b59-c620-4def-8f73-d418140aff7f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
19ce6b24-5e85-426b-957d-23b4a8ec34b9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
157bb57b-6160-4ad3-b33d-938a04cc3141 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
b5e5cf86-bd42-4ab7-a9e6-1e2656725532 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
fee37963-6c31-4923-8cee-f839e20d3903 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
5514772e-9065-4f53-9551-f1974eeb9a11 | Pole | 3 | Transmission | 2020-08-11 | 2021-02-07 | Level 2 |  | 2021-04-01 | 2021-09-28 |  | Pole dose have woodpecker holes at I would make it level 3 ,640 line
c8dd343d-d7ec-4b3f-b6f4-19b2a75df113 | Pole | 3 | Transmission | 2020-08-11 | 2021-02-07 | Level 2 |  | NULL | NULL |  | NULL
83be8f23-476f-4f63-8e17-e9d48fbe1e88 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | 2021-03-24 | 2022-03-24 |  | Need to pull pole back and add some slack back into line.
7b745c87-d2a8-4fad-a21b-817edefb5bb5 | Pole | 3 | Distribution | 2020-08-11 | 2021-02-07 | Level 2 |  | NULL | NULL |  | NULL
7d9da2b0-9b08-4441-9e66-d9b9e22ddc40 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
294a28b1-8042-4318-bd27-cf9f2bcaf2cf | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
35372b90-34f2-4d79-8fd5-85440191235b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
b705139c-25e8-4a75-a7bc-e7ff0e38e1bf | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | NULL | NULL |  | NULL
8df984a7-7a56-44d7-8f17-ed20bf4f9967 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | NULL | NULL |  | NULL
8550e1e9-b102-430e-a668-9e236f44565a | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
84c01308-3a30-4c7d-b891-4cf7978f9c0c | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
a96bb538-7baf-4806-b79c-8d254e55a3c9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
a84dbf8c-f31f-45e6-acaa-f8ae05bc7432 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
0033dc4f-c9fa-4faa-b3c9-08c64394c60b | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | 2021-03-24 | 2022-03-24 |  | Stub Pole & clearance issues. Veg issues have been addressed.
ade3a6c4-99d2-43fb-aaa2-bf5a74f6ca22 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
a0e56827-87e1-4427-8715-2aa99ce2c9db | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
a19ce921-79fa-4de1-85ff-e32b3808c4a7 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
a1e4527f-4e9c-4311-a375-48b43d1f8c1b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
9fd32fd6-56e5-4971-994e-530e138bb4f9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
2bc3fc72-e7bd-4e7d-973e-20f8c7648c08 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | NULL | NULL |  | NULL
b87c0910-ac42-4c1a-b720-74a05842bab5 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
ae907f3d-6a31-4c90-a77e-fd41d05d0cae | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
b15487ce-fe4e-4241-bf58-50ac4c3ac7dd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
f7411306-3cc2-4a63-b444-a90ae1eb35aa | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
99f38695-dde6-42db-946e-1b30230db0c5 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | NULL | NULL |  | NULL
ed0b9dbe-db40-496c-9601-e52c55514115 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
70d208eb-40bf-4003-8def-f3973169e86c | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
e6bddca9-9ae9-49e5-a5e8-843636da981f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
e70c8f33-d22f-4bdd-9795-ad89a080f7a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
dd9aa1ef-64e2-4d00-9bd1-22c57afaed0d | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
dc4b7b1d-a604-4354-a5a4-0b84f1d6976b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
e02a8c5a-c207-45ec-a9c9-c7e3ce25b97d | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
985c20df-ae78-4612-bec9-4d1d89a69440 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
e1c755d9-3507-4bc9-9dba-b9d636ab4f0d | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
d814d3cf-5a3d-4819-8709-c06ff4799632 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
986a7178-cadc-40e4-bd35-0db93472953f | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2021-02-11 | 2026-02-10 |  | Changed to level 3 pole does not need to be changed out, need to replace down guy, tighten hardware and replace 69kv jumper field phase.
d2dfd70f-c13d-411a-9bf2-a3f7200ee5ce | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
04e9ae6e-89fa-47da-9029-fc298ddc7393 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
02bfd782-dcfb-44df-97e3-4b624b0f7a90 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
1d7bcd56-23be-4e6f-ba43-f6409db8d3e6 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
232fd5a5-85e0-4d13-94f2-75c6d28c6e6b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
2a525730-764c-4233-9035-62bfe76f68e8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
2b4afd08-e386-4417-bb5d-c42a9906f8d1 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
0cf155d7-27fd-41b9-a1d0-4dc060be6bcc | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
0efd3256-decd-4030-83b8-2dd08fa277ff | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
11237a51-1789-4e9b-ad4c-25c91e699457 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
56679041-8d59-4dd7-9c4f-1669ae7b6f5b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
547d5850-1bcc-49bc-8e15-cdad790e3961 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
4fb66361-1bdd-4b4d-9e00-35ba4094317a | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
4d3f9d2f-da3f-4bc8-a847-525eb2f0a355 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
3f246742-297e-4197-82a4-038d21972036 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
3e95def7-3fb4-4148-9e8c-7a41a080dd95 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
3f1730e1-8fb6-486b-a06a-9b385a6780ab | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
40343078-60d8-4c22-9592-1ce3ebfdc203 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
38c48d19-ff5b-49d0-a69b-dff760465eee | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
35566c08-5d3d-419d-ae6a-90c12d56a86b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
83749815-9cbb-457e-b748-09983f982346 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
812c6d77-3d5e-4b4d-ab74-f87db9607451 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
7e78ff96-e4a6-4d70-8a63-15580687498a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
755a998c-b2d6-4607-95b0-74e78b5aa1b6 | Pole | 3 | Transmission | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
6013c15f-bb99-46e9-850e-4647a71c14d9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
6e09334c-2ea1-43b5-b31e-fa4c10074ecd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
5d72eebf-dc35-4ce8-b155-2f023a7b789b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
61908aa3-9b59-448a-ad92-021315eeff23 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | NULL | NULL |  | NULL
6205d9a2-2469-4b3f-ad52-042161682d67 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | NULL | NULL |  | NULL
5f3e222c-84fa-4206-b606-9477a0ae6c92 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
6e2e0070-4cba-4bdf-a681-a775a6d47d16 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
6db4ce95-3ecc-40ff-a7a4-e1d38fe36392 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
687a2a25-df42-4f4c-adbd-e537759e5154 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
69807d73-1c22-4d6f-9b92-bfab57e31c06 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
68a810e2-8dde-4b7f-8d92-0ba1ddb37f2a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
73d94ea0-b88f-407b-b54e-0e7fc593475a | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | NULL | NULL |  | NULL
7848c8f4-db12-42d8-b69b-34670cbd891e | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
7ce6f6f2-b5bc-4694-a166-ab17b07afcce | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
7bdba4b8-b2a7-4a04-8aef-fee4078b2f93 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
348d0cd8-bdcf-4350-8b50-9b17e6015d4d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
34bd7f36-21ef-4a46-b460-399432e0849d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
3198ca17-2857-4eca-83f3-f4d990bd6e69 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
31b3ec69-01a1-4773-8def-094fddf0113d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
391b6155-61f4-4c87-ac4a-913739009a25 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
3b22f3e7-f573-4537-97d6-bfae8209b083 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
3d45753b-7543-46eb-9e97-59c724149314 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
41019575-aed0-4603-8227-02f21ca13391 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
495c9d31-b037-4d23-8d6a-62b7ea696bbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
46b74e23-c1ed-4b1a-b2df-3d019ec001b9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
485dd898-327e-4d73-92b2-fd071ccb2c13 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
4fc70023-0783-468a-9f20-b2d4849c3046 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
520ca10b-7b06-4c05-95ad-83a3aa260a73 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2022-09-16 | 2027-09-15 |  | Needs guy guard and aluminum bells changed out.
54973d07-a59a-4eee-abfb-74bd97e1d9e8 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
58667738-cd0b-4e77-9c30-56d15717d138 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | 2022-02-02 | 2023-02-02 |  | Dozen or so wood pecker holes. Some a quarter to half way into pole
102a4ac4-9bc5-4da9-bd67-297582af2a91 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
166214a8-63d0-45c2-99f6-7b7c768e04ff | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
15c6a04e-c5cd-46e3-ac51-8511bf45ef03 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
0b5564e3-e707-4425-8b96-2efcfaf76433 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
062a10d4-0ad1-4b24-ae97-4ce6acd9b06b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
0abff65f-ffc5-4a5a-922b-7e0487ac1cbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
29c70cb0-66fe-42e2-9fcc-80bfe9e35963 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
290a2e00-67ef-4e7e-bcfb-5a58f387f714 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
20dfe33b-ccce-41bf-9f60-a04f09221578 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1c8a0104-57fa-4757-87ff-7204c7128ea5 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1dbd14da-8dd6-4c21-ad69-ee62d193e122 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1dc17a5b-5fa2-48e9-9c93-0d5a9cda3c70 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1aff95be-7f01-45d1-96e4-8a282c990974 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
01c4f125-4a07-4d39-ba73-b36005081ed9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
0475b47e-4b35-4548-946e-126a6d8530a7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
02ceb0c5-9c55-4bae-8743-1f002290c8af | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
713c4c87-4b62-407d-9568-1936fdd36062 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d392dcdd-700f-4565-8e05-732f57e64dbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d49c7247-c0fd-420c-b685-e841c29f4220 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d49a8cad-d360-44bf-9505-9e71c449e7ce | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d8069c6a-1394-4a06-9af3-e65bf837d125 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d8efe912-1f0c-4e76-b582-024667a4f7b2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d8afc4d0-96cb-4f8e-ad46-f144fecaa543 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | NULL | NULL |  | NULL
e0948f39-4546-4dae-935a-73b449e2d3b4 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
ddcb61a9-cd8e-4026-8f84-a3cdbba63208 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
ef6f1ff6-311e-4627-8108-c055103a940d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
e75afbaa-988a-49b7-829f-34e66362cd25 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
8fdcb8f4-6664-48f7-9d21-67c6ddd6a9cf | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
fafad9e8-5ed6-4569-a6a7-b0b7d0b0e9bc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
fd30dacd-455a-4da7-9961-07ba7fea4e6f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
b40af3fe-918c-40a1-9123-9487ba1808d9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
808e5343-03b2-45e7-ace0-ebda45409701 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | NULL | NULL |  | NULL
bae6aecc-9e41-4aa6-aba9-98c01139ff1a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
c1c5b4bc-0617-460c-95d1-9245d5e3789f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
a6c6a5ce-055d-4ed0-b594-1d0bbb9b4b27 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
a6c10575-5828-49e3-983c-f0bd5fb7300b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
9c716cea-353d-40a1-9ec5-ce5f191c4d3c | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
aaa89b44-3a31-44b1-a766-aae067cb74fd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
86a77624-595f-4d0b-b720-3c0289cb3762 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
898a41ed-20be-4ec5-963c-69f04a1378fc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
956e35e2-7a53-47ca-b7e6-c7367d8da01d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
591e4568-81ee-4b27-9730-20c49031e646 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
97191a49-590d-4e3e-bd8c-2aec9ca6b0ef | Pole | 2 | Transmission | 2020-08-12 | 2021-08-12 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | King pin bent significantly
df53b8c1-aca3-43e2-bcbc-1f46e621a914 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
3c75e3bc-a35f-43ea-8937-7c1cf618d08f | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | NULL | NULL |  | NULL
dd42ac7a-70eb-4ae6-a220-401ffe8e2add | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
22ccc302-5f2c-4519-9e35-c569fdd1b59d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1fd5a071-4782-40fb-8103-2383846142bd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1d900489-246c-49ae-aca1-fd1c881bfff7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1d4c5e9d-6f2c-401c-8741-1b03d4455716 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
1ef6a2c4-325d-4852-ab96-9204729e35d3 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
0563280c-a8f1-4a91-bfb3-3d31002c2dab | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d888170b-00e9-44fa-96d9-e5e4d9ac1296 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
cdd62acb-4b9d-41e6-bf85-3409a1cf0683 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
aaa4e655-a1e2-4c75-8b2f-e43d1bcf638b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
5c4ccbe4-8c31-40a8-8222-7620c29065eb | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | NULL | NULL |  | NULL
3110ea1c-5bd1-457f-b99a-15d5e39200e2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
2e5352df-3597-40e3-8c21-229edced4bfe | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
2a755204-0c03-44e8-b0bc-d6f4c4883d86 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
4f526001-1185-4acd-a3e3-60ddce305dde | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
5644e16a-bcab-4ca2-970c-151153bb536a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
488a93a6-640b-4d58-8782-45cc2e8fe4b8 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
66ed57dd-4f41-48a5-9515-c46c6bd8832a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
5e4d35b4-9d47-45b9-ba0a-5cb3ebfc7c83 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
7a3541b1-889e-4a6d-b340-564b584c4e06 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
7d4202ad-95e5-4a71-93f1-310e925e4c79 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
6e4eca6f-784a-422c-827f-2f2c48f752ee | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
6c87e8ba-2deb-4a68-82af-9846a0c87df2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
b968f4da-c5e9-44ce-ad50-349b008e5504 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
b195fce0-5199-4a1b-8bd2-05bc2a915fae | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
acd58bd4-fd0f-4884-8143-6e2288e4e7b1 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
91a5c92f-e227-4365-8b07-fe02f190015f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
9f5365f7-b542-4a6f-a2ff-ed82ae082bdc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
aacf146a-42a3-4109-ac98-33d80b5e8f82 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
aba25529-66af-4f4b-a588-37db8b05b647 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
ea472a04-0ce6-437c-85ff-7bf44bc30848 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
e59f7617-02c2-4c0e-9eb7-bc597227bba0 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
e65968f5-7e18-49b0-b78f-24e86351a72b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
e75e0ef3-2fb6-49ef-9d05-22ac64fa2702 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
e69ace64-164d-45b6-8455-2ec519773e4d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
dcaa42ba-9515-4d6e-aee3-4c0aa0546ef3 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d554d4b8-0a2b-438d-b512-c819333654d7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d00bc188-d698-433c-9534-1cb37aeb1b34 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
faa99ad4-c658-4666-b88c-3afb5c8f8d3a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | NULL | NULL |  | NULL
d355c38d-c720-455a-88a2-474753e17391 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
8f5f0054-1f46-4772-83f9-8dd4799107fe | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
bdc915b2-a1db-4ec7-8168-55c97915d24a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
61cbd3d2-64a2-4fa5-b64d-11106447c187 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
9636fd8d-8d86-4506-a690-0bf7744b2b66 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
2d0ff6d1-73bb-44f9-bdc0-35a427a5eeb8 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
084c6fbf-b655-4c63-9ec0-848f235c8a5f | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2022-04-28 | 2023-04-28 |  | Chance Glass Broken
912b9fe7-67df-43ea-a42d-aac7b52cf35d | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
cc490623-3855-4887-8da3-a719f481840e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
933f8ec1-0cbe-4407-b4dc-31448210676a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
d69c52d7-283c-4a45-b673-0af2dbdc1454 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
ab71b13d-5f8f-46e3-bc54-e128437b681b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
0b68a451-7788-4a8e-b2f6-22963332269a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
98017901-7984-43a0-93fa-36d3fb9df275 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
a8ef3ff7-fe49-4a2f-a780-4a1e09c6a143 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
4ea64335-cf60-4813-91af-71802974dcd2 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
b7088299-9c9a-4b05-8572-02b81c71cba0 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
9af49be3-c04f-4d03-8e26-0ce756b8d94f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
99e54a94-e9c5-4199-8644-420be1579690 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
978d0485-3a87-47ef-89f2-4b917128c02a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
85bc66bf-7687-4391-8bae-dfe9591a32bf | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
a9eeaef3-a442-4961-8028-a646554e990b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
abf02d38-2319-469d-8797-bbc3891146c6 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
a42a1a2d-6bc7-4f90-ae84-278747f82a67 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
a054ba27-f49d-4d8c-9b15-37b8990d174e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
c07be6dd-70fd-46e8-b60d-b1efe6c8aace | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
c49e23c9-b579-4bed-9a7a-30f0ddddd831 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
cd4f05de-8abe-446a-afdd-4ded7fc6f609 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
cb9ee7ef-be23-4461-982c-460181a3741c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
cb3e3a32-9690-4b29-afb7-4eb7d3009591 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
fa21e8b1-a328-4e21-a4ad-8745a8356b5e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
bd3a9134-f914-4056-aee1-43c622513394 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
f478c9d4-800d-41d5-a4b9-d609414a4d2c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
fc2a9cc0-b145-4d7e-82b2-581f5e3dae9f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
fb59c5da-9d0a-4da4-bf22-de2ebc621d54 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2021-06-29 | 2026-06-28 |  | Service is attached by wedge-bail on both sides wedge-bail is on service but no risk to public or reliability Considered idol hardware
ec7930f0-7f62-42ab-94a8-67802bfa1f5d | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
e91a6999-153c-4f2a-a9ff-d77fcf7a87fb | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
eedbf0fc-8bef-4e17-a50b-77e1bf3cf520 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
e426e70c-83f0-4d97-b9d5-a489163aa24c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
c2704209-38af-4944-9cb7-c02752a67019 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
835fa24a-4fea-4055-ae6e-c1e69ed2cb69 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
d3884099-007a-441f-9aed-cb2f0325a23e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2022-09-16 | 2027-09-15 |  | Crew changed out x-arm to 8GÇÖ fiberglass, pulled up slack on guy. still needs HV sign.
affad873-f0f4-43db-8a53-198fd472fe7f | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | Dead tree near line
391ef15f-25e3-4ab0-a834-d5bdc7b4ba78 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 2022-09-16 | 2023-09-16 |  | Distro and trans x-Arms needs replaced ASAP, someone has came by and changed out the fuses to fault tamers.
1bdc4cdb-ebb6-4fc1-a07b-4f54862572b3 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
21abeddc-f80c-4a61-bfe5-8534997917af | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
259f17ef-ae74-4b75-a494-b74bd2b14169 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
2a17f094-ddf9-42ab-8c8b-bbbc100136bf | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
0987eb82-2978-44d0-b7dd-206f5e9d4d47 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
0bd215ab-5e21-48cc-8770-8902b6d57ad9 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
0cb84489-4dea-4c60-b1e6-bbda3cdb677b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
16055c60-98fa-4f7a-a5de-94d6ea4d85ab | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
1651e3d4-1dc0-4225-92f1-72f11ec1776b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
583ae9ad-9adf-4156-8917-af0092ae617b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
15300369-90f5-4123-8f9e-a01ff2fe25c7 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
51f4b82e-c7d9-469f-82d6-abd100f15a7b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
4e8bef8e-2743-4080-afae-86c519fd1614 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
3f29dd34-b394-40bc-a23c-fd0822e757c6 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
3a1f98c4-1404-4e8a-939c-242c6c19fb4f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2022-10-18 | 2027-10-17 |  | Hard angle and pulling pole over.
3832ffc3-0b2e-4f35-99a9-07c81315971c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
2ffbb6ff-c91d-47b7-b5b5-7e2fe0033357 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
2f10f4fd-3dfb-4327-a5f5-8a5937e213cb | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
2fd1858b-a392-4140-8238-e41b1c936db7 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
35eabd22-f0ba-48a0-82b9-d5c0824ba6bd | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
792e710a-4a81-4ac8-a018-451aa41700f9 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
822f6a92-8e50-405d-a46b-85d0e9042c7c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
77377869-009b-45f5-9a6f-9ff1fb1b9245 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
70f916c6-9efa-433b-971d-73c8f98228de | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | NULL | NULL |  | NULL
701fb98a-9bcd-4ebf-8292-7ce080a7d127 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
697169ed-7b13-465a-b903-3ccc0b399a61 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
6891b239-c848-45c5-a415-81309ed07811 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
66def900-7600-469b-9faa-a900856c8057 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
6742c3d7-5014-4e77-89f7-f4dd00e36b2e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
65e9d501-aef8-489d-872b-ff59bcab4d54 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
6bc203fc-a5bc-4c9e-8d48-49fa7686d540 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
60e3173a-965b-4318-9238-e3b7f0b93670 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
61d768d2-4b69-489a-aee2-8bb8c4011422 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
5d2a72e3-8216-4bca-8ec0-14fe4a0eeb29 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
5d67f1eb-e5cc-4c50-8fed-144807184d44 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
5d1173d0-097f-4ccd-82b1-ee73f52109ee | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | NULL | NULL |  | NULL
595085a2-838d-4df9-9371-e890f10e5b05 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
61f32093-3370-4fe6-a39f-bf511de8c9c8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
6b233bca-6b80-4348-b1f8-c6c3b262269d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
6ad4a601-476d-4bd6-b3ea-8bfb599b5d1d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
71ed9e41-996b-43c0-a0da-87e5e5794a7f | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
813f1274-0381-4685-8794-0c66d8792b4f | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
81b1a7bc-60f5-476e-a969-4cf9c68186ab | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
7de91a19-9b7c-4271-8135-01f57ebd2ffd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
7d1fde50-8e5f-40dd-a9df-d7f1231b335a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
38195f22-dff8-432d-a9aa-aa4f964d8417 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
2ec6b880-ab4c-4c7d-bab9-acef35d11f55 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
2d9c2da4-f42d-4073-a244-09d973798eb6 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
535619d8-01bd-4ca8-bbbf-c2d65559bef2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
4718a946-4fa3-4680-9206-dd33e8b2362b | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
4bd83973-63e5-45ed-b637-947215fed7ad | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
4a1eb129-0dfa-43e3-a3a5-660a31b01deb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
43c865df-3edd-4779-8ab9-a6d019d91180 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
4482735b-d051-420c-b600-760171a56049 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
12212548-c09c-4714-bbeb-3bb6160da972 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
0c6e0603-2876-40b3-8edb-02adc4b6a0d7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
2b2c9ece-414e-4010-bda5-1b1853947f6a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
2d3df91d-46fa-4f41-b735-532d21dd4620 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
1e6d628a-6c56-445f-910e-ddd39aad3653 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
050067e0-6d79-4f65-bdb4-63af528f4cde | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
d29b1171-3281-4930-a1bc-d58cd937c498 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
d9265647-f7e7-4826-9bba-6aa620dbb0b4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
dbc64b55-54d2-467c-b22d-bedfa8d9bbdb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
d87f2178-c65a-4df4-a850-af77b89e9907 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
d8a0f4e8-e9e9-4120-9f5e-72e19a1e6697 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
df364ea1-a48a-451f-9d09-93d13c19b9c5 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
dfcfe4cb-a756-4869-8793-ed9f52bef5a4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
b12f5e9c-ac18-4f59-a37d-23c4f73437f2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
fd48d4f7-bbed-4371-8804-6bf3397382e4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
fe4ee3a0-bb3f-4d86-9fab-f2a147fadab5 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
f441916c-100f-45ef-8be8-ae11692e3706 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
f87581c4-6579-4365-ac11-9e767761d3bb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
f5f1b57f-b77f-41b2-8658-ef6b33321f46 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
f5d233e0-974b-4eb2-b89c-97752c3ecdd8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
af0f6cf6-8a59-4e8f-9a6d-f31231274621 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
cb687a34-fc7f-4367-909a-801ba3a2f0db | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
b510c45f-c689-4756-a5f0-85bcdfb9fd50 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
c5992e72-d5f6-457b-a13e-0a23aae26ae6 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
51d6d732-0f90-4609-b7db-509332696458 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
9c9e4b93-3de4-4b0e-aa47-8de5833f9240 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | NULL | NULL |  | NULL
9bf5754d-a001-4fde-be2c-31e52e3d5eac | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
a8e69d42-444a-414c-b6b7-5ecd7bcdcbc8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
84fad399-0aff-4cf7-8f39-292466aa5455 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
8b4649c4-c71d-460d-9116-d412ea6f609c | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
9b71307c-dfdb-4711-ab2b-e8a20fda2dfd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
916dda97-dded-4eaa-ab95-6abd17098b08 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
5c5bcf67-be2a-4afd-a874-d7038f1d4ae7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
60df7a83-e2b7-41de-899a-89af255ae74d | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Pole cracked from ground towards pole top
6b02b67e-2e4d-4745-b5b9-311f0e5e1df2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
09cbf493-2005-4a68-b940-e61155dfb64c | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
b22e7a3e-f920-4e74-83e7-699d76adb9d7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
81845573-b07d-441a-ac12-90653a46c47b | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
eedee0d2-7dfb-4736-9154-5cb4b357e8f9 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Prep for repairs
36ad5913-8cd7-42c7-828e-773a1888feda | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
4a8a7b63-cd99-40de-a477-f7d6bb21a378 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
b3577643-12b2-4928-93db-ea4baf3358dd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
acc70cb6-b822-4522-bd21-77a603905cf1 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | NULL | NULL |  | NULL
637bed12-26e7-4561-8741-64f2eb372892 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
5997646b-b80e-44c2-9263-36338731aa4a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
7a87e7a4-aed1-4461-9030-04ec47814c10 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
c9243a75-de5f-4a88-a89c-a2bb48669383 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
b8b81add-0d53-499d-804c-a9aac3129e4d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
00319bbe-a52c-476e-b92f-8d67cdf9d297 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | NULL | NULL |  | NULL
1152a63a-2a0e-4a25-a0eb-47f97a651d89 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
f4e36da8-0b4c-41b7-ac66-aa197514d18a | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
b8078155-979e-4aba-bb46-95049ffb048d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
c327e379-d2a0-4dc2-ab9e-39d5cf7772d6 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-04-13 | 2027-04-12 |  | Pole rotten, needs replace
989286d1-8539-4f15-98cc-8c47ef735132 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
46eeaf0e-dc62-4353-b605-a110e7b7fd8d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
388da06a-d796-4401-b0c4-f0cd0f4f2d88 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
91488720-29f3-45dd-b103-f3532d961515 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
fd668582-c75b-4e92-85c9-31d0f5ff75f7 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
84dfda52-8222-4551-b993-ea82dc159805 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
d3a0fe46-3ed2-431b-9a21-512f8fafd5dc | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
5a4bd463-45dd-4f9b-8430-6ab6cc5d383f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
3b5d666d-34e6-4f28-a604-061ce9813249 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
236604c4-9294-4cb2-b998-4538b47637bb | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
4836bf34-9269-4123-913f-a0d04f2507c3 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Pole needs replaced. Com equipment attached. Transformer is leaking.
d9696caa-4404-4b8b-a194-cfa39ac5ca60 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Pole stubbed and cracked.
a755a4c7-4357-441c-9e36-528414d4e700 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Pole stubbed and cracked. Needs his-strips
e5a0be90-e1c2-4b80-bb6e-442635ce73d0 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
95f95bff-3d70-4da6-81ed-04f0d659589d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
917ce863-0fe6-4434-9de4-9a2c0da7560d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
89ce9c8d-6786-49e6-9aa1-7f340250f257 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
864418c7-5d3b-4f8f-abc0-4368cf03e0ad | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
87c9e503-e571-4bac-8aa7-fcd7e8bf852f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
ad650805-040b-4934-bb05-b83e22cbb3cf | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
a5866153-51df-47a2-93bf-3e873729c1f4 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
a00f4933-b1dd-490e-bbc0-55da1ce2c64a | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
a1508a0e-8f74-4b2a-a416-b04d2dc3bc78 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
b5041df4-aa6b-4bc2-8fe5-3481ed039ffa | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
325e224d-b5ed-4082-bebf-a6a9123295ba | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
b12ca565-c372-42cb-877d-59db9e82567c | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
9fcde381-bc44-4000-8ba4-81d05f6e1a21 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
b348bcf3-f28f-47ac-89b4-e3176fb40321 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
c0089e0e-773a-4bf5-812b-46dcb14260a0 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
fdede023-b3e1-457a-af88-47fa1f6bc977 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
eaff128f-0a14-40a6-9208-ffa70e24cf01 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
ebdd8ec2-c8f5-4449-913a-6a4716585bb9 | Pole | 2 | Distribution | 2020-08-15 | 2021-08-15 | Level 2 |  | NULL | NULL |  | NULL
dc6c0124-508c-4376-9344-e45e9a81c989 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
e6f40188-8ccd-42dc-b207-172408ca5641 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
d85f947c-4a9c-4601-bd86-bdc3f739bc44 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
da66590b-acbb-458e-bbf7-1a6ea54ae44d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
d3aa8a2b-a2e0-45f2-b265-3e250c51223c | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
05800e39-c7d1-4b5b-a76e-c1c836d516bf | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
0211e8f8-b6ff-4830-876a-48b93cbd08b3 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
1f8b0832-4db5-4553-87ff-77ad4bba8b8b | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
490506b0-59ae-4dfe-bfd9-035280b95623 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
4e5266dc-8573-4028-8b70-07e5a49a2076 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
4f06e832-849d-449d-90b5-0407f1d96e58 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-01-17 | 2027-01-16 |  | Pole top split is not an issue.
54d9c368-af37-4469-96f2-0939976416d8 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
2fd3d56b-fe1f-4ded-bcb2-2cc3d2d4b39e | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
31b80abc-d615-4816-9e40-40405a6bb6b5 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
37c174c5-ddc5-4789-ae06-578e8fc9b9ac | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2022-04-13 | 2027-04-12 |  | Pole rotten needs replace
3617d431-76a1-4fb2-90d6-8ccca747ba20 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
7a92742c-4d5a-4c14-99a0-425bdefdef94 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
8157bf08-64f7-4a4b-bfbf-6327d5b1c540 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
7562d2cf-2ae6-40f3-b2e3-b6bd5d1d3eb5 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
651987c7-7b3d-4845-8225-0d3f6e7545c2 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
6db03cfe-d3c9-4a60-bf9a-6a3a06467bad | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
5a78c1b9-2070-470d-bdde-e2224132a44f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | NULL | NULL |  | NULL
64246506-5d8d-4682-8ec3-846c5c787df9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
6c2c97c0-5e55-4339-8638-93b95ed5fb96 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
6de3bd9c-aecb-4059-a602-2de95260446a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
744d1497-f8e6-444e-ab2d-f2d73c919b1d | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
7a19c449-2489-4962-81d0-a9af56ddac00 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
32c57763-aefe-415f-bf04-69341fe31c28 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
307d8277-ef02-442b-8ab6-fd169e6ca394 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
411ed8e8-44b6-4879-84ce-aba8c2921428 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
58a009cc-6878-4e63-8c78-b7de977c6cb2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
576ee34f-d0ae-480e-a976-b8a92aaa4971 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
55ba0fec-d19e-4fcd-888a-c18a6a2dacd6 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
48030b4f-b861-452c-9a92-4d2ac63cb503 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
45864e66-f483-4cc7-b32b-c96d77bdbc94 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
42dac4db-8e0d-437c-bd90-a7b328ae40d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
228db20d-9b6d-4847-9d06-ce75dcc32870 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
1e4367f4-2c9d-42d0-844a-303194872c6c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
2c114db1-886f-437c-b12c-1fb65ec0526e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
251a0bb4-83f3-4b78-b4a1-ff8bbb9bd5d2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
28146eac-d943-411f-8889-deb211631540 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
08ff3a2a-40ad-498f-b462-f6eb83c963f2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
08c5f11b-ad44-4173-b76c-b2af354dd03a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
161875ca-cdbd-4985-acce-7cbd1bb65e03 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
015c2480-1383-4725-8533-0ab38fea2293 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
d9772245-ef52-40b1-ac10-7eb5f1fd87b9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
117a341d-5365-441c-84c7-940a097f0c4e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
831c2938-fd76-45f8-a96c-d200701cf205 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
d29561a7-8405-4a5e-b5b0-b3878fd954d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
9c9043f2-2844-4085-b533-1fc2c13d8251 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
d794126c-74ad-4908-8120-3f7f9e5ddc95 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
d7c21f9f-9c8c-4152-8c10-516a78c9d365 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
e6fd3be4-9c85-4051-a8d0-4eafb561c95a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
e753e589-d39b-4991-86b0-3828f5360e5f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
e4be35d7-263d-42df-9492-8650436f5c1f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
e1202c72-2e24-46e8-953d-f9f4ba387f33 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
cbb6c1e3-b9e3-4d73-b866-0d23ff8da89f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
f959cab9-f391-4340-b0cd-0d11d74b9c1e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
f5f39dc4-94a1-49da-a567-f006b67ac6d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
f1ce3b9f-2443-4abb-a2a3-7c38ba45c3de | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
af718e4e-7ae4-4c6d-9257-92113c342ee9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
af6d4ddf-7a25-4c52-b979-d7f12bec1ce1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
7c78dff6-e125-4a0a-982d-a006e9900bce | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
b4031d0a-bf36-4ad6-85ac-bdd9db8d462b | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
b45fece8-d42d-467b-a9bf-e4345b362c31 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
cf20e5ab-7994-491d-8c48-f71752e2f9da | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
ced65230-8ce3-435d-b3cd-049e512f70f1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
674722df-ed2e-4c30-9007-ec44c3488dbe | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
6c54efa0-21fc-492f-98bd-b74d6e4e2454 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
c4ffec8e-09cb-4b96-9de1-e0052129e00e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
a1fb95c3-ca88-473f-a284-331bfaa60309 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
84ebc02e-44a8-4f14-b714-69c304893e6a | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
a64ba217-551f-4721-8ee5-0aba3c66d87d | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
a28035f5-b9fc-4552-a383-28122d72a803 | Pole | 2 | Transmission | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
ab4083ac-8340-4d40-a7f1-f0e60e08b1bd | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
9ccd0455-f1dc-4168-9bd6-d878bf39bfec | Pole | 2 | Transmission | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
9a79125a-0329-4a6f-b019-f9aaf71bc318 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
9605d1d6-55c8-44ad-b1ac-612445ea4b72 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
b9e9e230-6219-4fa4-8658-65c23f0e48f4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
4bff3a0c-b7d4-4331-98d9-79d737515a9c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Hotline clamp stirrups and HV sign, addressed. Pole needs replaced.
9d310ff6-a880-4d39-806b-4b1436070d18 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
d13ddcea-d37e-4bdc-8e15-bdd0df4b7f7c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Split top, loose braces
1cbc349e-79b0-47be-a206-08701acd7cbe | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
62a5cb90-d3b1-413b-be86-8b8d736caa62 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 | 2027-10-20 |  | Pole top split
89184d9c-8092-4880-8664-008afdf3310e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
2569924e-25dd-4879-8a83-33ccb91bae84 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
c870e2d3-6d0c-4a62-a313-96eac2328b7c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
aa78fa36-7666-4e67-986d-4320d1e1367a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
debf420f-9b73-46ea-b497-ece854a4cf1c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
7f4f1a4a-e575-404b-9e28-e92223e83328 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
a5edbeca-083b-47da-9a1c-4da37cef2b88 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
272bf117-5927-4e5b-b382-2d6ac69e0760 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
a9e4be83-4527-4c70-9391-944f0ddd012b | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
911c9549-651c-4991-88f1-fddeffb2239d | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
39b9e663-9ced-4562-b1f5-1c480aa6437c | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
69c44e45-3f6b-4aae-9c6e-2fdbf69a7ea3 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
53a5f6f2-079b-42f1-996e-4219f6bbdad2 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 |  | NULL | NULL |  | NULL
52de37d7-ab7f-4b7c-a2de-48c6320659a1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
3660f45a-20f7-4ce3-8114-0875951c52a3 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
16943990-539d-42c8-a9bd-3f047fc6e42e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
2f8b5669-282b-4c29-902d-dfce109c59be | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
51bfe483-4817-42c8-acbf-272e6b90525f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
56667e94-ec85-4255-96f4-c0de81248b9a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | NULL | NULL |  | NULL
5455ee15-0018-4cd2-a5d9-13c1d34dd292 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
5b66073f-3706-4bf2-ac6d-8c79ccb83394 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
6945c72c-9976-4651-906e-5bee6e6fa0b7 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
50e8adf4-2e8c-4ffa-85f9-fb1e5b90b288 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
50aee005-d410-4074-841d-9dd018e4d149 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
4e1a04cf-15f9-410d-85f2-6aecb95a8daf | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3e1a716d-83c3-41d9-842b-7f83dabd3755 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
2f55ab03-6f57-4749-8aa2-98d5b1b65d85 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
2ca83bdb-bd87-4fe0-acb7-bf91f62b1ac6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
18c35cdd-0462-4221-b7c8-aa3c5f36de69 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
1ca66a6a-b843-45b7-8176-ddd870e21726 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
9918e2d6-29a7-4611-8937-99fd60659765 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
b70a66b1-d15a-456f-aed5-d477aeca7050 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
ab4369bc-bf7b-4d8c-adc1-b875d68c72c2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
8dc2f7d5-a641-445d-954e-03cfddbc812b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
14e9bde6-b391-4cef-b64f-54fc50ac9ae0 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
fe5ade2b-d90f-4d54-aa14-feb27297b4bc | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
21c1ee9c-aa5b-4755-b5a2-549878cc4158 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
9c430c21-d296-450c-85c6-7a156c9579ed | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
99a23be1-a46e-4f88-a1f7-5923c07a7385 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
7fc858fb-3310-453c-baf7-a569db6ebc6c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
6188d1ff-0ee3-40da-ad4f-5d1365767bc8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3bafffc9-76f5-46ee-a490-d1d6aa2dbcdd | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
b707e4ea-b55f-4b59-9a73-22f5f85fb903 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
92c8b363-e6f3-479f-b643-2fab4f152750 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
8c36461c-d479-4f66-8004-085b96e9e8f9 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
88dc3f26-449d-4b7a-a4d6-7cb485ff3f5f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
9f3147e5-5128-4243-84df-eaccad993da6 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
c9295586-d953-48be-b98c-d4c5aa968576 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
b5c34493-c737-4286-b045-6d7fd8db6f70 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
afc78ec9-a571-452b-ba2f-e79af29f8ed4 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
dbef4d57-e519-4a39-bbac-b0006b42557e | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
db5738d8-5ac3-4429-9c39-386354d2b0c6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
ee2b3e8f-93ef-47df-99fc-a7b002203614 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
fe9d2d69-7444-4b6f-b96e-185ea21440b3 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
9cf01289-ab07-4f46-a4cb-49479fd9534e | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
876d703e-467b-4f13-8bf1-09bcf9af4b0c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
88c2707f-b121-4dfe-ba0d-789fdc2ad72e | Pole | 0 | Distribution | 2020-08-18 | 2021-08-18 | Level 2 |  | NULL | NULL |  | NULL
ab54b250-806c-4168-9e03-52650d47f7fe | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
ab444256-8dc6-43fb-8978-e839456af26a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
a877e69f-5cc3-42a3-b5b0-a702e90b470c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
a4e88dda-84b1-4171-a033-afebea131e5a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
94cab6d5-9e34-4e37-8330-ababbf11eafd | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
9d8c5c96-3dec-452b-8fd7-06d7412a2ce2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
a214e533-0789-4696-b2a9-2ece6e343bb2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
c5106f44-b5b7-4ebf-af75-cfdf2e5db260 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
cc8ff79a-1a27-4cba-a419-a08822ad3c63 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
807f6987-52b6-44eb-a6ae-a1bbc3705f0d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
c96067ff-f30a-44be-8894-ae47b1c897cb | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
cab6999d-b6b5-48bd-8d28-dd7cfd260ea6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
b98ff61c-6834-46f1-8b40-a043d0ed0251 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
afeb76ca-aa75-4cdb-8b3a-b8808df05d7c | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
b3f06a93-8ca7-4681-bde3-fdd11bf86898 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
f651612d-e0f7-4ad3-b916-652e318ff48a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
f9379adc-61d5-4744-975e-09ec8614da3a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
fc031a9f-3809-4d57-9c2c-fb6c3df2012c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
fe49a6bf-4d67-4632-b08d-43d24b4066b8 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
eee074ca-3b9a-4ef0-bace-a361bcb9bafb | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
ddac9ace-d50c-4064-a84a-cae86ceb6a90 | Pole | 2 | Transmission | 2020-08-18 | 2021-08-18 | Level 2 |  | NULL | NULL |  | NULL
e02bb811-23f5-4894-93dd-95d83d0c2e11 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2 |  | NULL | NULL |  | NULL
7c185836-647b-4458-a807-7d73341df16d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
e43255f8-b40a-4e16-a338-755868481c97 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
dbc9e480-1418-493e-8314-302d2f3b7778 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
d3372f1c-4378-4ab0-b729-13c787dc499f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
037f4bb6-ff16-42da-b708-14e877054505 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3c71a6af-e6ec-43af-9769-781499060547 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2 |  | NULL | NULL |  | NULL
1485262f-ca19-4be9-a707-c50541d554a7 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
184d0a28-a8bd-4c03-8f99-a834837b6407 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
10ff2d43-ca85-472d-b3f9-89a9e90f8ed5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
0ac890f6-d830-4aba-afe8-e8cb2f2cbe2a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
0874076c-938d-4888-9586-ba6f7d508656 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
0789bcda-fabb-40fd-b0e1-8c4a342cc89a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
0e057503-38a7-46ae-aa73-161e8e7ef00b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
2699c35c-8f25-4595-8b5a-24986bdef181 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
26219c65-5417-4716-a7ff-8be83d87fc8b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
2ae4a931-d30c-4f3f-89da-a031b868cc2a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
1c5a017b-5683-4c5a-a9dc-c9a8bc2a8c84 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
224c7fa6-2ef0-482d-86c0-b5ffd950b6d5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
451033b0-1758-4568-969d-3e6279118a92 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
453f9748-a296-48d3-bc0c-75f3653f60dc | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
4c2d2957-4fd0-4dbd-ac63-7e0dea3a1e58 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
55031869-6936-4e29-9700-a254e3170282 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
5339741f-0c7a-4201-a3b2-18e80f377f46 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3e8e3315-076c-4172-b85c-a110b3fe42f6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
38a44b26-7dce-4e61-aa8f-6e11d11e11f8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3d2f3246-cf5b-46b0-b0df-359820ccc940 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3b562847-952f-4668-8d90-f27aa9d9b91f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3bdcc904-3039-4424-9d36-549b44cb56a5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
325673a1-1d31-4513-bb68-1edff9a97ef5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
3548192a-ce1e-4a38-8955-52f57a6f4b0a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
811b999d-c62d-44de-8362-ac538008ba82 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
71be8d32-9e4f-4ba8-9a75-0a15e922a5ef | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
723a389d-ac75-41d5-b5d8-4f27cc245836 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
6eb674d0-4723-45cf-808c-a6510fce7c67 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
5d3b9254-7f11-4f5f-8862-a67c30ecaf43 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
5c93a722-7f9b-4af5-9dd5-92d18edd7c26 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | NULL | NULL |  | NULL
5cd5616c-6f7b-4efe-bc95-970d3669ce69 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
5c5719c5-37ef-4b2f-b782-42795374cb57 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
59c8fc01-639e-4a13-8721-b44943e46e04 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
6373f150-fffd-49c8-9097-937ea25a8796 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
6ce62036-f92c-4482-9a4e-7534971edc88 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
6a47356a-c822-4bdd-8074-be17c440c57e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
760f5dc9-240b-4373-9fd2-bd08f08ffbac | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
83ecbd07-9907-4007-b566-21b3b11a86d4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
7dd2857a-bc0c-412f-8aa5-d3dab831e510 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
7c01e3ad-66b4-41b2-b0de-539308e0a955 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
33cd40fd-68d5-49e7-b28e-e770d27a3c00 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
327120d5-ab67-4602-b121-4b63dbea0812 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
3aac25cd-18d4-42f6-8c11-945552fadc82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
3d5fbd3d-7774-4969-89ec-0980349482fe | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
39cfc813-49dd-4991-91f4-e8cbf7365957 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
38ae9491-c1c2-4fe1-9970-b14b5754915e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
517133dc-441f-41ae-ae6b-f6d1c433af9b | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
50790657-e212-43b6-b0eb-0dfa19a1ef78 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
5709ba8f-816b-43cc-a89f-343c48fb2433 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
4a42eff8-044f-4311-bf8f-00f6465692a4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
4b5f1c21-5255-482f-bda5-62bd6be6a9b4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
470755a4-efdf-4ab5-858e-073bf26e177c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
4546ef99-0c98-4b26-947d-dccdf90e223e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
462f680c-8c4d-4283-a9cb-c051c3deec25 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
443da5f5-40ff-4a48-9f8a-327cd6c62f82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
44c3317f-eef0-4f98-be55-2fb244b082bd | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
2663d61e-a9ea-4e55-9800-dc9d5647d33c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
2d30ac7f-4f81-4118-9d5a-3ad711d7ea80 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
25c7c50e-099c-48f9-985a-8d9503285c1f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
0f0aee21-1d63-490f-aa79-ab3c2850a307 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
1095a1f7-41d8-41b3-9c4e-9a910624b565 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
13b15da0-a934-482c-8aea-a35a358d0040 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
d23e8e37-7c92-4ce9-a670-4da00fff9de4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
b138b43e-3a72-4d7e-9bec-fe0735ea3a7d | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
d7f8e1eb-e163-4890-ac62-6a7fe6dd5a02 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
e6698b4a-c239-4dea-95ed-1e676c83091f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
e2b7dd9a-1898-4c4d-9607-98687ba39676 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
d6f421a1-cce8-461d-84cb-3ba32bf766ea | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
ef678ddb-5991-483e-ad56-c631c85f8f82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
f188fab2-03c6-44bf-bd2a-9054c657b3bf | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
b5e5a689-b304-48b7-95c4-8966b0c2c421 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
fd24a9a4-ef63-4840-bf6f-6a64480f8e27 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
af802fac-1402-41e8-83f8-cc888a43f354 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
b2316b78-20b9-437b-81e0-045b39f6d125 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
b9188a3e-207c-4189-ae54-2358ce7e1e40 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
175f1662-ec38-44ef-a219-48a74210c46f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
b45f0373-1ad9-4cfc-9278-7dd1ef3fc6ec | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
be93ec67-49c5-4db6-8fa6-0246a9f2b08a | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
bcf8b45a-8487-4bc7-a8e0-d7b363680fdd | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
c68bf7be-9539-4f76-9a6c-7efed0a94a35 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
c749493f-04f9-4087-a555-ddafafe7fbb2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
a4c41253-5265-412b-8590-07f4f07df7d4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
a74eadf3-e41b-41f7-89d8-5deab2996789 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
a8b5fe50-2c39-4c8a-b16f-793e6f10556a | Pole | 2 | Distribution | 2020-08-19 | 2021-08-19 | Level 2 |  | NULL | NULL |  | NULL
8aa38f18-e81d-45fa-a12d-856edbb8a495 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
9bb9420d-a7db-4ba1-8e1a-90986940145e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
911e85b5-ab1a-4e89-9ef3-c3e6760fd084 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
fe2f857e-3972-40cd-b6d3-f614903a91a2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
f4949f60-25a4-412f-87fd-b0a786be3b29 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
f273512b-7a48-4b91-8957-7ec60a965b61 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
93e27638-5729-44b6-b534-6dd6a741a88c | Pole | 0 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
86cff8e1-2989-4640-887d-a7ebab1535d7 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
b64f6e58-abcc-4bf5-bddb-1644a64c1fdb | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
2ff4b31f-402d-4b9a-847f-a93209956482 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
5baf3b98-ea75-4c18-807c-ca39ebbce0e6 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
46ee302a-de1d-48f4-9c81-235337c7ce5a | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
4369a697-45f6-4f7b-9df9-f4f7b462c5a1 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
44650334-5131-4870-9b56-a54802ed159f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
9e8598f9-4271-4af8-8da0-1b32cbc19519 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
29ef90b9-2ea8-4d25-81c1-b69b50a2a0f5 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
6089591b-f976-451d-964d-673d2418874e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
01edf49b-3de4-47ab-982d-47a4243edbcc | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
0fce14c2-b555-4cb2-85c5-4778229405c9 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
7a138981-8606-4d31-a4d4-a8c6a97c102c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
df5462c4-331b-426f-a4e3-8d572bd288e7 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
a15867d6-bc7a-4471-93a7-6b786534f678 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
8873423d-378a-4af6-8175-12a054520c81 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
d47facfb-c829-4102-9d60-886dbb6f4db6 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
09808cdd-b7ef-42fc-a490-904b7dd1a99c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
01c4f200-327a-482e-9420-a4b74a4a5075 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
40564c82-c3c5-42f5-b53c-f0cf24544ff2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
72663578-72f0-4579-a218-40d4ffbcb42c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
73fc4211-e067-4eb0-b436-3fb0d00b87c5 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
60ccd8e9-edda-4b5c-b244-68f461cdf38d | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
66466e1b-525a-4fef-91c5-975c99eb4cfb | Pole | 0 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | NULL | NULL |  | NULL
6d0a4a2f-a8ae-46d7-b318-eaca4913fdc5 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
49ad1175-8d66-4c68-8b57-22fad176056d | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
1d83f641-e17e-4a91-8a61-e8bdfd5a64f6 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
20037d15-fed1-4a24-b0fc-6db8a39955be | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
6b70e287-fac6-479f-ac15-3776e01d5080 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
a2c94345-e9a4-4cb8-8844-a62af37f2111 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
5d030dcd-6912-485a-8ca6-26e1afd3f51a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
5a5b48ef-833f-433c-8525-bbb26d81e678 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
7bde8c50-9400-4f08-89c3-a50632f44772 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
9dbc7287-6aa6-4a14-a5a1-7a16aef3d578 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
c900045f-f318-49ab-a830-a32f27695c96 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
ddbff38c-084d-414c-be5c-478240ed2285 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
080bdac0-5181-43a2-bd24-ccb91e925547 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
5c4017fb-fb9f-4167-8ffa-ff9fa7db18f7 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
5a6a2a72-367a-4962-800b-11cdcc428e29 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
31b4b520-499d-4290-beaf-7175e7afe03e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
85cb32f2-1c77-4b97-a761-57b880250339 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
c7c2562b-fae5-4fe0-b7bc-89253ca5dd1b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
ccdbe39e-5ed6-4209-ad84-c42c01c0e7d9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
f442b77e-cb66-422e-a8ea-e0596c67fe0d | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
96a498b7-c844-4958-bb33-ff0cd3a453e1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
886216f1-afd0-4ead-aea1-e3c173754212 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
848f5619-1dc7-4ae0-8906-23ed199b5d6c | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
a72476b1-1614-4a7f-a97a-c9dece18d7f1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
c129ca7d-ed0c-4254-b9c5-641333619ca9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
ccd478d1-b4a5-4c0d-bfaa-7a1a1e03360b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
b648586b-3fc7-45f8-acda-058f3a15894a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
9ef66c75-aebe-4eb1-a36b-4093959608e2 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
b199ce3f-8cd9-45cb-b9c0-53378891b31f | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
defbe8fc-f958-412a-81a4-402a0bd1ef2b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
e4d07fa4-9cfe-4bf1-b285-49503dfb244a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
e760087c-bb48-4c00-807c-29427a41bb11 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
98e69d14-a840-4608-a01a-e405bad3fe08 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
e7a8049b-d174-4b61-891a-9918452f9b24 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
d7e811b2-3721-4feb-8b2f-48d8f27ba946 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
4f406a31-3d44-4b89-a8f6-8409844660f9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
d8d9b280-4a8d-4609-a737-dab6528bc1a4 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
d9cfb9d4-94f0-4570-b691-1d71d00d4460 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
b56321e8-08a1-4803-b2cb-5b0812b55ade | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
d3c62967-cdf2-4341-8c88-536b7a30af00 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
11423224-828e-4e7b-a7b4-e6a7f4f3c75b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
0caca01c-db4d-483d-981f-f6230422b8d3 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
080420c0-d108-4057-976b-0baf9dd9aeae | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
04929957-94a1-43c6-94b2-8be6b2b3a8cb | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
0784caf9-122e-43c8-8c37-be7a23f9a8c1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
20701f49-a4ca-499e-a442-2596fd6990fc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
1cfea449-468e-44f3-b0f7-b7ad4ff6b767 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
046ce6c8-929e-41ad-9d43-7239d315b280 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
02c955f1-c0ea-43fc-b9df-a55734a8a077 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
434e1e55-a04f-4756-a7c0-817ad9f97aa9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
4f27343e-ad92-457e-aac7-df14b975fe9e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
4fd93608-f794-4726-98ec-6ebae4779bda | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
3ecf158b-3797-493d-81d5-fd83ff9946dc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
413a6a09-624c-4dd4-af88-7e92a1069c2c | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
30f1e271-0964-40fa-a120-75f53679680e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
36ef9d67-8998-401c-99db-330696393cd6 | Pole | 2 | Distribution | 2020-08-20 | 2021-08-20 | Level 2 |  | 2021-03-24 | 2022-03-24 |  | Will not meet clearance issue
721d35a2-de0f-427b-b61f-7f643b0aa11f | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | NULL | NULL |  | NULL
724b8804-5e98-40e5-bfce-24e62c9b9745 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
7254d6e7-1cbc-47ee-965f-dfc73cb7012b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
7046a946-aa1c-4421-8be2-7dd426be470d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
70170b6c-6ae3-4efc-9e25-bcfa526b0102 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
7464383b-60bf-474d-aa59-bac45025e8b1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
74a9ec57-97db-4ead-8bac-a45b658a4724 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
7bc4e703-2ef2-41ef-9c46-7c85d08bd49b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
65ee9b37-0b7f-44c4-8af2-d2b13933f0f7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
6788174a-cc61-4c97-ba38-c500cf43cfd3 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
69a730e0-23fe-49be-991d-2d0509a6f407 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
648f480a-ca28-4729-b215-58ce1b046b25 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
381e8af2-1000-4949-9235-6040da3568ef | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
2e56e6ed-6bf7-47b7-a989-fd412931f776 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
3f9a6f37-595a-4641-af67-8a8e3faba5d1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
3f0bd24e-ceb5-4c24-a68e-c51b13344ab7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
38b3744c-8a90-4ebe-87f6-f8014a1f0e82 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
503edd13-1405-4654-a70d-285465a4416c | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
578bccc9-a71a-48e9-ba9b-019c616783d4 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
5749e759-008b-420d-a6d0-a185be758918 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
423b9eaa-1d6e-4bcb-b984-8aa9c584c967 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
460515e4-f6fc-4904-bab4-ee97dea0cd9d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
1c0d7534-e690-4c0f-8e81-210c9bcee5c8 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
208899fb-877b-430e-a144-89ec87c5d537 | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2 |  | 2021-03-25 | 2022-03-25 |  | Pre for repairs
206dcf61-946e-4705-80f0-0bee6cfc2253 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
2256753b-572f-461e-87d3-1fbfae08fe5b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
2404b8fe-084e-46d3-bb1d-b3f5a56f3794 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
2acb6da7-16de-41b2-9381-8595a4426468 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
296e128c-6c61-446e-ad5b-afd9fea966f2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
120a58a8-b0c3-41d3-bb84-da1f25905a69 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
17a99d36-eed9-40ad-9aa3-ec8d689230d7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
181416d8-5923-4b0c-8cf5-091451d27d45 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
18e3e729-8144-43cb-a98b-e6b18d99a77b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
19b5d6be-7b33-440b-bfae-1db15d626e24 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d377aaf3-701d-4eff-ade6-67ccf33aab48 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d424608e-b920-4abd-8677-75990a249ece | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d065a93c-2b76-4ddb-a651-a0c8b1fec846 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
e41a0e8d-d0b9-48f0-a74c-4433a5b2fe7c | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
e0db0126-a525-4fba-b218-0e4187c4e56a | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
dfde9fdb-3f97-4c82-b1b2-c879ab736ccf | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
dd1a9414-6087-40f5-bfcd-a04017f99b0d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
fcf8168d-30e0-42ab-adb2-36e4655389f1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
eff1f07a-da92-4609-adfd-ff1fd725c85d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
ec57f022-d105-4971-a0a2-a20855e356ba | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
edb3418c-512f-46d7-8443-d9a508cc7672 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
e9e09793-9636-4526-a13b-cb424e4e6672 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
e9d88dc0-89c1-4ea9-93c6-5ecbad6c72a9 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
b3a1ef30-ccbd-486b-9c9a-92e252dc3985 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
b83e0265-85be-4f55-badd-a27c37b6edf2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
bbed361c-7952-4b23-a0f6-1f576c0fbcf2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
b536a166-6092-4f29-9fd5-2143c80ce1e8 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
c72408f7-cd4b-4530-a85f-8d9f97ef8ef0 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
c615d57c-94a5-409e-845f-f88c848eef43 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
a4b560e6-1d75-40cb-a115-e7764c2bf7e1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
a1f9bab8-3242-403f-8cf9-5a87f6f5b867 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
a243caf2-ed7b-4888-a349-634bd5d851c9 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
2b35dfb7-d39d-48bd-b6b8-b278f1df137b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
a0fc2ac0-9e91-43d1-b7a4-6889bfaf3f09 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
a9428bfe-0632-43bb-b908-445120f3e936 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
8b195a16-3acf-4455-b579-1d75f8cac2bf | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
95dc0d80-5869-468f-b4aa-b34c8819e8fb | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
dd7db983-9c8b-466e-9335-6082c40a9b30 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d8f09f6b-032a-4324-8d1b-23324449e63f | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d6c67903-58a8-4beb-8c54-31632b0ba073 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d4a7cb65-7f1c-4982-8440-273be46d92ba | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
d32d0d18-c709-426c-b914-db34bd194039 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
ff711c0b-540c-4490-8846-4c33771bf483 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
b02a0c2d-4dc9-4cf3-b256-40d1ff9ef270 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
b046d6b5-9f41-4f25-a3bd-d4b59c7628af | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
b4bd537e-8cb4-4d68-9778-a2fdddf7aad5 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
82fc94cc-c2af-4a25-bf7a-7f044b54971b | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2 |  | 2021-06-09 | 2022-06-09 |  | Pole top has a 2GÇÖ split down the center and cracked. Change to level 2
8ddd82c4-023f-4354-96e9-10b74739127e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
94149a5b-8f4a-4555-8f20-a0e5104bd592 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
ac4dd433-43cf-46b9-b6b6-568aeaa7c929 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
ac165c9b-15a1-49e8-965f-1769af3fd06e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
26359e5c-65fb-4759-b965-3ea13715fdf1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
2911651e-0244-4029-9114-11c08591aafa | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
c7bbf099-b30e-4738-b921-90db42b3aa68 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
f27d39e6-a57e-442d-bdb2-98c165f32a0e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
ff4ddf1d-a766-48e0-9172-3a52af9f0191 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
1f4cdf85-591a-4ffc-ba96-bd0cf71a06fb | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
16a43eae-fc46-4dca-bdfa-371eb00bda01 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
1b164444-d1c5-437a-90b4-67936087b88d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
4d33210b-47ca-4af3-912c-4b60024ea558 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
290bfdc5-072e-46f9-8c7c-2ae3816280ca | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
708b9374-1d03-487e-9584-ffc790998eb3 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | NULL | NULL |  | NULL
38b0a9f4-2f81-4691-9e88-0f0f66e84a2c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
9b6379f0-956a-4034-91c9-6ba5f91802f3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
c2284def-ce66-405d-96a6-e4b8f0699bcf | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
ebc7b5a6-e101-4da7-b444-003b4cf170f3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
1d911a6c-d51f-4dae-958e-1f864a1b066a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
ed1c1b49-16bd-451b-9582-827f27784724 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
2ea60b47-c3cb-4980-86b1-a7d86aef722a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
b6d072b7-22fb-42f6-97f0-6d10a2d1a6cb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
7205845a-d190-4a6e-b656-f2d75b1c0ce1 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
b6a87fb3-e863-43df-bbe3-65a8b7323bd0 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
b6bb7f89-b211-415a-83b5-89fca471306e | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
ffe96216-db00-4a09-840d-c79543dffda4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
93e1ea25-ed79-4b46-9119-1df8a838654a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
dadb22c0-33eb-4413-97e1-11d2f1da3d99 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
95344de2-059e-44da-87fe-eff7f0340c40 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
993bc072-b69d-4438-9527-14e3430aff12 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | 2022-01-17 | 2027-01-16 |  | Pole top is fine. O abnormalities in pole top
8b3703a8-8b2a-4429-99e5-3ff8c9ff6d37 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
8a735ec5-2713-47c2-91f0-271596c41001 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
8ce2769d-c402-41bc-a24f-6d47b4a2d5c4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
8f0be831-2257-4c68-899f-c8901df70abe | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
8df58217-fabd-4d04-994e-a0b3d66b49cb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
a09e5d65-3ee8-438f-a62d-1b04fd7abca0 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
9f85ee01-9a5b-40f6-ab78-a3341136817a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
a26ae3f6-57d8-4769-ba5a-d115a73f924c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
a4062a4d-8e86-4645-a051-5fc867a0e355 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
c2cbda82-13e6-4bbd-9b75-c594b88cfac8 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
cd0f189c-5904-4f67-9b8f-c99be5fa5130 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
c9ce0c68-3e3c-400f-8a61-f541e4c13666 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
caf10615-6298-43a4-83e3-6b71b9675914 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
cb7df45d-150d-4d00-a026-402a1e1107bc | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
c8f0f0b4-6bfd-40eb-b187-3e6bd285d61c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
b1b3fce1-6e7e-41a6-b32a-45ae0b6a2b65 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
af4c6123-df01-4cc8-9fdb-593b7b3e4e65 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
e9254aff-9023-4222-8427-0642bb90b0f8 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
ec3dcdd7-9c3f-41f4-97a2-a325d4153c1c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
7dffac05-9b4b-41f5-bcc5-71667cd534e7 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
fe7a8dd8-8790-45a2-b39e-812edd1361eb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
f9655750-ee7a-44a0-8f04-80135fcdcf77 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
fa9c2cd1-dd55-4c6f-a638-084f2a81fe81 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
f9fd398b-bc2c-458f-981e-80f73a36c463 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
de3aba20-9ef5-40fe-a095-ac3e0dfa3f52 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
e1b3ae38-18c4-491c-8fdd-e6c120a8b73c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
e0474074-20a1-4fb9-b3af-d7641d8cdcad | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
d188cb32-1117-4adb-a63f-afe3184569d2 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
e53b9ff8-377c-4624-8d57-fa8ae40e9fae | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
ce3f6533-b1db-4ecb-9b0b-109b863824b3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
d3d58892-96e0-47a0-841c-47234b991750 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
13c979b0-53df-42ea-b29a-161e807952fb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
138b0dad-0a7f-4e38-b381-4be4ee9a2f49 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
2a2c61a2-e97b-45ed-8a12-51f2093f176b | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
25dde5d3-9c0e-4a3a-bb29-c29926f5cc49 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
291ff5a2-1c7d-4228-b267-69eca0d406df | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
1beb9eed-ba0f-4dda-9d47-f2dee27912a5 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
03a54ad9-5348-4f0a-a037-bac73be6983f | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
fb35cad8-18b7-4afa-95fe-70cfb50e7f54 | Pole | 2 | Distribution | 2020-08-22 | 2021-08-22 | Level 2 |  | NULL | NULL |  | NULL
455f6c3d-6030-40e9-91e3-05c0ee958885 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
455bf8ee-ce56-4cd4-afbc-b1fff98db057 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
43f9115b-9101-40f2-b41a-9f811941ddec | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
4857f2bb-d3cf-4fd2-808a-8f0e3a6c27ff | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
4a2b7159-6a1c-4f46-b9e3-35f3cb7ea8fb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
4bd97999-6744-437d-a5d4-c513db99e08a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
574110f9-6a32-4710-a86c-8915792b1042 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
55aa453d-d19a-44da-98b8-ae57d0a16e5f | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
5047d9df-483e-463d-8cff-9352daba5a91 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
52c5b391-9858-4285-a4a9-b8dee6260a2a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
2fd3bf45-f566-4dc8-bbd2-6241c11a7da4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
36ae1088-f3a9-4747-9692-adb8d2bebbe7 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
5fcab607-b49a-44b8-a4d6-2e826096f695 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
798006f7-b816-421d-a0e1-2119e0cc3dda | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
83ca67f8-eb62-4096-819e-6dd136034245 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
6fed99d9-a3a0-4e88-ba36-a623728d58cf | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
714cace7-bdee-4b10-a429-dbf01f0d8817 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | NULL | NULL |  | NULL
71d11db3-e944-414c-bfaa-ce24d212da3e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
74229587-c37a-4884-ad39-1b24a79243d3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
73bd8e10-363d-4ae8-96c2-68505d266d8c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
737e8da1-2771-41f6-9524-ef0d3f6d00fe | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
77517874-dd3b-46ab-af63-71f1e66afa06 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
83e35432-4064-4aae-afda-55c42783f64a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
82f87c6f-e524-4581-919d-c438606b880f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
73d5aba5-3d28-4a5f-bc47-6e9decaafcbd | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
7f7e2670-8d9b-4e1c-85d4-d16716bffc07 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | NULL | NULL |  | NULL
7c2634b8-6da8-4192-8f1d-fbadfd13b428 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
7d43d86e-07fb-4fa3-ae2f-bd32605b066a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
5bc97d7f-e75e-464b-966c-8eaa206a0d12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
653e39c2-86c5-420a-93bd-823a9b33cd47 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
65cffca3-84ca-47bf-b564-d75dac5cdc08 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
6b2bbb73-3f82-4f9c-a0e8-927f38bcc7dc | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
6db749a1-1a5d-4c39-a1bd-7a12f61de856 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
322d579e-b470-434b-9fb9-617cebcf406e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
3bcb8731-93b6-4792-8428-c5206e100620 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
4083875d-9460-4504-89c3-7fe0e4b6405c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
41002bd6-f76f-4d7e-a8ef-911facb83c85 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
422d8a55-b179-4a29-ac5d-69f8235f292d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
50389f54-5bdc-4015-8318-a3b44dd125a9 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
53d78c6e-5722-4446-9f01-09481e51ff20 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
4bb4eb82-e238-4578-bb15-809d0e3feec5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
4a4f11ce-fc5b-49e3-8e5c-9e6c3a4944f1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
46f1eecb-5681-420e-b167-9567e773d5c8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
43a07d3d-b42f-44ec-bae9-02b23d36b2d1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0509118a-5be4-4204-895d-5d9ca101510e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
03959e41-5712-45e9-8064-9d0cd087740a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
1c8199c6-504a-4cd7-824c-9589720bfa24 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | NULL | NULL |  | NULL
1a6bc9eb-b33f-4881-9b83-bd83882dc9d6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
1a86563e-f6fa-4bb1-bb29-907fe461d184 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
20494439-07b4-4765-bb9b-9a10b9919d39 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
25a10e5e-b5b6-459b-a7e0-d85acf4759b7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
23c8095e-175c-424a-b73e-fa1e25bcb57a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
21d20f80-bd9d-4cf1-912d-28a5e25118d3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2a0d97f3-0303-4f8c-a13f-de23903c8c12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
29e8f289-377c-4710-9e73-25e90601395b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2ad9e6bb-cd42-4107-b85d-713c55e549a1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2d72985e-be3c-4906-8b4a-289b9060b7bb | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2c780323-ea7c-4568-a9a7-ff4d04d74b05 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
10e52de0-8ad8-47fd-ad88-4cc811f53231 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
194783d2-4339-4b29-aa4a-c5c6350ff681 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
17c89b67-9c69-43d1-851a-cdbd04caad12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
15cea97c-174c-4a49-a4a7-d4af04b3b229 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0c576fa3-328a-4596-b4a3-93a10eecf676 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0f277fe5-d973-4160-9ef4-936e0bf5473f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0f8278c0-5d4c-46ea-8eeb-0dcaae21c278 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
d34d85d1-ce18-4be3-8290-f469ee2d5f4f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b399f829-020a-4886-9382-685feb32e14b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
d9bf2872-c676-4c0e-9f77-33f997728f81 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
a45f56a7-54f0-4832-a465-50e732eb111f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
e41dde77-3a78-4ad0-a169-2815a08ec305 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
edfef705-72de-46be-b3f4-850b9d95c468 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
9db055d7-2483-45fb-b97c-470efc2fc826 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
e0deefa4-7549-4abd-b562-43394f0bc88c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
de0a915b-ead8-4c51-abbd-81b09d336567 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
ddf3ecab-d5c3-4b29-92f2-91b766903775 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
f3cce9bc-b5f8-479f-be7a-07dd22f5c398 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
f3dcbfd8-0e2e-420c-847d-81f844cffd16 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
e8c7318b-28de-406c-9fa9-6a5bdb753794 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
eac3aa17-2c63-4359-91cc-5152023cdc1f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
fd829f2b-ce2b-4922-97bd-589472d85208 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b1b4e4d7-b056-4319-9efa-242c22516399 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
1531b749-4268-450b-9d0f-fff2cce2c90c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b85d380c-57cf-4c64-9aad-1b995413088a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b76bfd6a-40e2-4079-a87e-b850886417ae | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b351a7f2-224d-4cd4-aca5-22122e479ac6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
37811f8c-b4fd-4615-86f7-c7938a590e7f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
4002d2ce-9bf0-4bf4-8688-f5857beca803 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
bc4f3a85-7192-43eb-9f56-26bc260cb3e8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
ccd99c5b-9b21-40f6-837f-4c788ec7d461 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
ce47a680-b0b4-4448-825a-92bd03b2acd6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
c0b3e5af-87c0-40da-8175-68dfe2b2cf8a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
c646a5b5-fc57-4f5d-be09-9db12d1cc650 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
c71cbab4-722b-4b47-a86b-33136ea63b77 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
c750e280-511c-43f3-8729-73715423dd5c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
a6f82906-da08-45ee-85f4-7cae9d535516 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
9c910675-6a06-492e-9ea8-b2026b6232ba | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
ac887a93-6032-495d-9319-29a17c154294 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
ad6bf67b-b398-49fd-8fd7-97736345f7b3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
a8c68e71-550f-4dd0-b3f4-8a768fe8728a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
aa45a9d2-4e27-4911-9157-4dd9ddad9397 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
8746834e-548b-4ea1-8698-f62cdda2d08c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
88308dbb-4ab0-46f3-bc5b-b11f0dbe02a1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
86d73140-d9c2-40dd-a974-9f80754c880d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
961222b1-4a34-4c6b-b4bf-b38aa160118d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
95ee95a7-d907-4b38-a868-7d3c30aaa927 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0f9baf43-159e-4d43-b950-dfda2d8b8b7a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
feb7c63c-674a-4f50-bf0b-b62233d13bd4 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
d4751484-6b66-46bb-a175-1e5165e64c05 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
cc0e2af0-179c-49f2-9df0-54ac69d1af88 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
e26e8dc8-b761-4c38-85a8-272adcf8f5c3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
e2ddcbad-e02d-41f6-896a-2ccece9bbd56 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
d39287cc-a79e-4099-932f-c76fbac2db39 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
d505db20-efbd-4d35-aafb-f5a08947d83b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
ffe7de67-0575-40da-ae6a-dbd636c5a3b9 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b4a4247f-7853-43ff-bdf5-b9ee9e8be258 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
a510717f-51cf-4a30-b879-a62b0bd6ef6b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
9417c7c2-27a3-4444-929d-99550aee1a7a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
7d4eb686-fda6-43e4-945b-326a3b89e5be | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
6635d941-e229-4b81-bbe0-ab452de061f8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
8bf43cfb-1590-4a26-8d4d-d33057e1545e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
30e20acc-170c-4051-a7f2-9b9c3cfe3ed5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
6459fb92-ba38-4e6a-9457-5d82fc8dca52 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
5c33c5eb-fed5-4029-b3b5-61a78f2d647d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
715570d0-7fee-454d-af52-64d6692fb73c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
eaa75bc6-f620-4fb9-9d8e-eada2a070958 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b70951ed-fb8f-4576-ba69-5605aa6bf76a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
afb61237-75a8-487c-a036-783048f8dcc6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2157e450-8c93-4cf2-91f6-d09d301af560 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
1e030840-5d4e-4de4-a1fb-22270c81a486 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0fe8598f-55a5-43a1-b1b0-c8eedfbc5eeb | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | NULL | NULL |  | NULL
1c69312c-875f-4482-9837-cb21ef73029f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
b24ac6c8-e066-45ff-b166-d6ff54da78f8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
5f3870d1-710b-4bc3-a3f9-672b0bdbd90c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
78e55c04-9191-4af6-9b78-29a17131859c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
f34f2a8f-96c7-4570-9d8e-2de9f097cca7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
255fc0f2-f0f1-4434-893f-38c5529608b8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
8bc662ce-450f-4725-8101-d0acc4878a3a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0dfa2a0d-43aa-4e39-ac2f-a6e18bf117a3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
cde96f37-e445-4374-ba98-c3b43593b3a7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
efa95dfa-f8de-40bf-a995-227fe933aba5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
07159db7-db1b-4b8f-82d8-27cea174a573 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0533f8d9-f359-4131-ad25-7aafad4fb232 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0ed56227-999a-4b37-af68-fdc8b0ea4438 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 |  | NULL | NULL |  | NULL
2bad306e-f2bb-4655-9e60-3200b56187e8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2c2653c5-5a40-4b2e-bd53-100e06ad2691 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
07bcb6db-ebf1-451e-b2b0-cbac7c0752fd | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
26b159dd-11e2-4cfc-874e-442d8894933e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
9cb92896-3a35-4ec1-abd6-a0d3a2353e61 | Pole | 2 | Transmission | 2020-08-24 | 2025-08-23 | Level 3 |  | 2021-05-10 | 2026-05-09 |  | Bent stack
3bc9967a-d0aa-4488-a474-f51e867c36e5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
2bf9a9cf-0f27-45b9-b079-82b5fc528394 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
0a34fe5f-7f51-4afd-8527-9dbf5b62a98d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
8d90996b-d904-47c1-a474-ddf27517edf7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | NULL | NULL |  | NULL
924b6453-1ba2-4430-9b56-ee7133ea44e2 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
2f68e0fd-edf7-409d-a930-564e5e540938 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
3a1eb240-3e97-4ea1-9eda-66939614ab67 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
96a224d1-7736-4cb7-bb4a-762385ab3a89 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5ff5527d-4d84-4af6-a6f9-28f25451bd7c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
045d07b0-95a0-42dc-a023-d0d23a813c5b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
69a7761f-4081-4dfe-b411-874b7a3f925d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
b97a270e-f6cd-4842-8213-9cfac3080aba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
72c073f8-70af-4d8f-8e05-1f186a8bf22e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
6bac055d-196b-4d53-8f2e-cf18665e5ba6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
ffe3cc2a-5f07-4aa9-a1be-7a193e39762c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
b1a97f1c-ffda-4c76-9ffd-0b2b7bf246c5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a0c8acef-2327-4529-a12c-0c556ee890d6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
0832fd9f-32ff-4381-9159-a4301b83620e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
6d1665d6-c454-4ddd-81f1-aefd3a96579b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
7c4721e4-5abd-443f-ad8b-1440a91fa3ad | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2 |  | NULL | NULL |  | NULL
d849511a-d182-4d41-b0e4-3dcf052a76bc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
898a9cae-21a5-4dfb-a943-0b88b56bd2ef | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
f3ccbce3-9af8-43f2-b636-c929063fb658 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
97e49778-1eee-4438-81ae-7040ea1f2905 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
976892ad-4b3a-4468-943b-f56b5bb6d73c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
974d755e-6c14-40a8-ac35-7f210a4b2b62 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9a7a7b73-82a9-49fe-ae6b-2f2ca24d9437 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9acc4129-1b85-4117-b0cf-508654e0bfb5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9979df8c-c3f8-4472-97a8-231e91ff0e6a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
91e29412-5c62-48a1-abad-8ec5da3020d4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
8f46bb38-599f-400c-ac58-15d64dcc60b0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
881aac50-c5ec-4d3b-880e-5d45778a6ba4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
8dced52f-467e-4903-b7b7-0dc9c8f286c7 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
8e1d1a36-483e-4ccc-967d-8fab40e487f5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
8ae398fe-aa12-461e-b480-6aa1975fd365 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a9fcd34b-63d1-4e67-a632-bde997c30517 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a94e18ce-e4a2-43e7-b4c4-f086c045997f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a9468f7c-0233-4c00-ad49-6b3c0d72f9a2 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a8b870fe-fe2c-4a73-8b64-1d177e7f9bf4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a7a57a60-4bb4-4295-955d-80307362806e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
ab3fe644-3280-4509-a0cd-1ce9fe622fa5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
ae0e8e50-910d-472e-9c14-ed5c90828881 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9fcd68a0-7631-456c-9a09-053129464caf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9e15aaf0-92f3-46e6-b145-a670d9c44397 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a0c62f60-bb66-4ba2-9d29-60ded7e52771 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
a6b117d3-dd97-4fec-8095-8c70969cffda | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9fae1d3d-4f03-44b4-8af0-6f867fb9a838 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
73cc2647-e5df-4549-b79d-1c4c63f0d7e3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
6e70763a-c65d-428c-846d-f43e4c0bd236 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5330c84f-9b80-495c-b861-aaf8ac0fb7c6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
c0bd06ff-25d5-4232-ac6c-646d5c7a30f6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
c4928fa6-2792-4b9b-a09a-517dcd2d6ec4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
c2d5ac84-42e3-44ff-831a-07e366207228 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
86b1e3cf-37a4-4aa5-b67b-090768153103 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
cf89e813-f253-4bab-8379-7659167d2626 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
7bfa8f18-4b4d-4e46-b2a9-9704e3009c4a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
7c02d2f9-1c8f-4cb2-81ce-70833d3c0d23 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
c00bbb7b-7e1e-4b98-9f01-f0c187deb66e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
bb270697-4253-4626-92da-a3daf117455e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
3205ee93-d368-4642-91e6-c88ee4d6ca54 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2 |  | NULL | NULL |  | NULL
35a966f3-027e-4a5d-bd6e-49dfbd6d8232 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
1cbbe529-3a0c-4c33-9565-d00c119d1b4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
1713e222-b452-4ff9-b79f-befb05579412 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2 |  | NULL | NULL |  | NULL
af5a584c-12ce-4b47-8f8d-32dd295a4b8d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
ea35d793-e5cd-4dc2-a152-599e7c234d9b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
e7ffc440-e131-4120-a669-f5981d147d4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
e84ff4e1-767a-48c3-bce3-e7ae339c907a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
ed826ba9-0ab5-49e7-8845-63cc5f73c967 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
f02875d6-5cad-4e73-b6ae-5148e25ee977 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
f045205c-8ebb-4859-baee-63ab05173ec9 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
ef024a55-ce9d-4dd0-bb79-3fa86937f5a4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
d5dc456b-2d99-46ed-82bc-fd0788a1edff | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
f2a0a66a-d58a-42dc-b1c4-a0981c57e4a1 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
f58c4eee-d8ec-4250-96e3-17cc55ae72f5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
f99159a9-291e-4c1a-9c09-802b0256a515 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
fbd31e49-2636-4be7-a69f-cb34531cf26d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
fe2a45e3-0af5-4a9a-b946-826f08320464 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
b22f93bd-b5e6-41f8-91d1-d0f974aed8dd | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
e1eb8ed2-847e-4b3e-8bae-a61b99063acf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
e769cda8-1713-42cb-8820-35f39edf7782 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
e6503596-9981-41ce-9bd2-2b398f47161a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
e5d333d2-d180-4deb-9e61-69d19076863f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
d7d0c8bc-56a1-4ced-90a6-cfa8b42e83bc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
d2c000c7-e232-490a-bf7d-939c6e93f729 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
d1af7df4-4c9c-4288-a5ad-7bd9e91bad88 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
876ec2b5-1023-412a-b8f1-258f5763c847 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2 |  | NULL | NULL |  | NULL
cd197258-db6c-4f2a-a989-758162450ca9 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
9028919b-c486-4a59-8250-909e35736c4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
d480a95b-8835-4a16-8963-49cb101fb3a1 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
0d80d7dc-eb08-4e31-8596-91016621b234 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
0d52d201-79dd-40e7-a479-9a4d412d3fe3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
091ac45c-1b4b-45e4-a73e-5e1b04c88ce6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
0689b605-fecd-4319-be07-2bdf5d64ae8d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
0642d086-0be9-426b-b9ac-9a801b57a878 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
08208c8b-bc39-4294-af3e-51e6ea1fb3bf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
158fc6d4-50af-45fe-b5f8-bc7132288d17 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
18e5d7d2-a28e-4db8-89fa-5d50abd3457a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
1201c7d1-dad6-456a-976c-22e94956bdf3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
2c8ed2ac-b841-49a0-811e-814adf031065 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
2b5a7faf-e1b4-497a-83f7-5b9788bef450 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
28b41204-6e2a-48ac-a8cd-775283fda1ba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
290650ee-3e72-48ee-9fc6-a0c054289240 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
21d5df52-4e67-445d-ac9c-725275a44f0e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
1a437a76-6ca1-443f-a2e7-344b91852719 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
1cfb9c8c-e949-4acc-b0d6-4a339c712a6d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
04240fbe-8615-4a27-9b7d-38f9c513796e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
05735387-2b6f-47f4-aa1b-ed79fed23364 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
4639c896-33ba-4496-8a7f-7f79b405920a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
471a5d38-e10d-4c5f-865e-c9911ce99d4b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
4bfebac9-2560-4f0c-a90e-91c671b8048e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5775b823-3452-45e4-9aac-6665444284ba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
508c141b-125d-4ba6-8992-7ad79f3ae5a6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
51634ef9-6b28-4308-a0ae-e33bf474a973 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
53479864-ed55-4c5c-9aa8-5d6d490e13fa | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
3ec8fbff-93a8-4042-8e0e-69bdb5d8cc91 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
3db2b8ec-f03f-4428-8c6c-29036754afe0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
3c007cde-26f1-428e-bc0b-f0653aa957db | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
31890bb4-24f5-4e2a-acb1-1a0b516b8fca | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
369067ac-d08b-43a7-a9de-afebe9bd2606 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
356c03e0-a104-4da7-8cc6-0bac1ac8e8d4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
3787a36b-b6c8-4ad2-bbd1-957fb132a548 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
6d8b2cf5-7dfd-466e-840a-4ce363c319a0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
6fba6b99-d8ef-499f-82b0-bd7e50630f65 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
64d293f7-bc29-49bf-b88f-087ab25c52d8 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5b36e71b-745e-459d-b7a9-3f095b896ce4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
591890f5-503c-4d4f-89e7-57bbf4109907 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5c7eb72a-e97b-4b09-aabf-984b8fc9b0ed | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5ef33cea-2239-4aea-9dc3-0f0e36e42d49 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5ec95d73-3fa9-4f7e-b013-15dc90e532b7 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
5eb99e4b-7408-4098-a89e-4f6e2401656f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
63af1910-deea-4bc6-85da-9a84b0d40ecc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
611acafe-5c5d-4f1f-bdac-b6df3554ad75 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
7cd7f51b-ae5a-43a0-bb83-dec7c55b1665 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
79edce01-d09b-4375-bf3e-f7596c38ed13 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
8189db7b-78fc-49c1-822e-edc1d7fc8aac | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
8376508e-1e64-4bf8-a050-2603dce0999d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
767d3999-9b67-49b7-846f-b276f2ed11bb | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | NULL | NULL |  | NULL
77770603-c699-451e-9cd2-c89bee6fe724 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
5ff4555d-16d5-442b-b2cf-2e107f2a3d0a | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
01cb9da3-0b8f-432c-9307-4a7db2c733fe | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
5ca9f5f0-d72d-473e-ac11-a09b29592f8b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
6a72f514-d73d-4f44-ad7d-4cc89870b633 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
6bd4377d-42dc-458e-8566-837751f2e86c | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
3397b717-6a1d-468f-a1f7-92d0ce515f6b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
33b0fef5-ade0-4330-a97a-740ba45b9e72 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
3225f821-7503-4c43-a498-7a49db9521ca | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
3a2d51a7-dfde-4c6f-bf0d-3fa928e81646 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
52c02616-77d7-4ad9-9bc4-b384471c32e9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
52fbbcf5-e938-464e-8da5-69fa5c9914bc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
5380d8b2-64cb-4e84-a136-2220df73533b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
00d60a2f-06a0-42cc-b9a1-1f60d02c75ce | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
cdd97878-adf4-4e4a-93ac-1d0f5b37dc0c | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2 |  | NULL | NULL |  | NULL
1d7c21e1-e5c1-4a80-a34c-e2da39a18e4f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
1d14d146-58de-4807-b155-55bf84040336 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
1dd0bae7-34c0-40d7-a0b3-535102a03610 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
22e4f44b-a759-490c-b839-445240cebcc1 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
26c1af08-e315-465c-ac33-01d1d34b3e5f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
29c2b704-f16f-4878-9132-7232a1bf211b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
d355a7f6-c74d-457f-92ef-524cf8b9f733 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
cf7c8f33-bdf1-4785-b5ef-eaa8042e9a1e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
d10d1ae8-fed7-4b57-95ad-26e705e8bd9d | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
9a88eaf9-1343-4e00-bdad-d69bb6dff177 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
d8deaadd-34d8-4a0b-9a29-d18a32500fdb | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
d2a1168d-3186-4da5-92d9-d7938ed6ed71 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
ec6c28d2-8fa2-40ef-aaee-fef93f43df06 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | 2021-06-05 | 2026-06-04 |  | Pole shows rot, has blown arrestor, needs stirups.
e72751a5-9167-47aa-ba5a-edc24c3df84f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
e6826095-e636-45b1-b778-9b4bb7f769a8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
cfed5938-97e1-446d-84f4-b9a5f27ba7ce | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
d18053e7-499f-4a62-ace9-81888de0cdc6 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
de085876-38a6-4ead-9c01-6002befaa8e9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
f9f29c55-d913-48c6-8637-d5c1f49368e6 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
fd1904d9-72be-4cfb-8870-5c97cc031ef5 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
f5b1afa2-64a6-4e5b-a9af-358a8543650c | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
f543e580-9cd5-4e30-b2ea-2181ce187df9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
f481de80-e9f0-4f28-9963-f82822e1d28e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
efa13b06-e773-4d0e-a26e-3891dac2cbf8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
7f6da5e2-be12-42fd-a778-f115bd52f6f3 | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2 |  | NULL | NULL |  | NULL
4f3a3287-3c04-4963-b179-080fd499da54 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
bf2218e3-0c44-4382-9254-b0622e8b71ff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
3f8dc028-e635-48af-85cd-f543515bf917 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
cac7c7cd-34d8-424b-b54f-eb4a431fe292 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
82ebaf66-a15e-427e-bc90-709990efd9ff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
c3d61466-d21f-4e92-9d0d-26b77aba4abe | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
5bc13482-3f2b-477d-983d-3dab41bc0945 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
c72fb72e-9b56-4a1c-b1d1-ca179a14dc4a | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
c60d00a5-e438-45e0-b550-aaad016bcaeb | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
c573c9ae-8745-4fc8-ac84-5c3f9aa7abff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
a6794192-54d4-42fd-823c-b47efdb794bd | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
a4f7f48f-db2c-42c9-9cdf-d1df945e981b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
ae9fbdc6-7ac2-4ca2-afe6-da00053e77bc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
a99ec8cb-7f02-4209-bc41-4ce76aef82ca | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
aa6d6ad3-b879-4e51-87c8-9aa7134b5902 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
86707e61-9fb6-4489-8c3f-5b1ace96c221 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
93401b71-f7c5-4f02-9b22-8cbc2ce288ab | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
973b227a-22f7-471c-b5e4-7b3ba06c0238 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
d02aa2b8-aaef-45b2-9443-64365ae13e13 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
91886048-4ca0-4d03-a1e9-2dc2a82e1b66 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
0f297c49-8f54-42c2-92c7-47c82d023893 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
b637846d-8322-420a-8540-53ee8aa180cf | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
baa7346d-0ea7-48a0-aba1-dfe196417946 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
71584111-5bb8-41ec-907a-0adf51d3a01a | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2 |  | NULL | NULL |  | NULL
e939a423-0475-4cbe-8888-8c9647736f19 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
071c7c18-3be8-44d7-a6b2-964c51c68a3e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
27a13a0c-95ee-4d45-85af-f2a41fead3b4 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
446d81be-8cbb-404e-bc7f-b56e9aed4f2b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
45bfebba-bb22-422f-bea3-3ad3a143a596 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
ef411a7f-9675-4d79-99ba-fc84c5628345 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | NULL | NULL |  | NULL
4b7f6609-6852-4b9f-8105-eb749f349cca | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2 |  | NULL | NULL |  | NULL
09f2f087-cf5b-4d0c-8bc1-97e6d8fb4080 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
50756823-7823-4f55-b0b8-5a8033ab8e38 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
0e35b734-55aa-4a24-9a4e-5c948587a09b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
856ec955-a16c-48a4-a9a2-aacd3beb4c2a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
cd2d3d8e-f489-4a64-8cda-22b1590e7e68 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
f2e81ad8-0d9e-4049-b150-976ad17adbc4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
45946db1-b2e0-4a65-a817-35d3f6213f5a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
5f51c0e1-2ca6-4cc5-aa74-65e76ad5affd | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
9a1b273e-9121-4994-a3dd-1eb8e9b6701e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
6ec94a68-fbd2-4c0c-99e6-7ccce0c7e657 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
a3e1f557-fefa-4874-979f-a2a78f9ff93a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
848106d3-1601-4cfe-8e4c-8abdd31b94a5 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
032ad3ab-2b61-4217-a907-57e46d336d85 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
1defc274-243b-4a96-978f-78ceade39019 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
091bb153-f365-4d07-8c27-ae892724630c | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
1cc492b6-ff0d-4d5f-aade-e5e6759b404c | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2 |  | NULL | NULL |  | NULL
1798505f-54cb-4398-86cb-08a8a90d930e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
87d519ef-56fe-4c58-880a-a699047ad4a7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
8d38071c-b43f-43af-87f4-67878ec71e22 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
c4c48f43-911d-4df8-a64c-9892edfffc89 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
b4544187-8b3f-46aa-bd11-bab0baceabe4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
7a5bdbfc-3f90-40a5-a7d0-611c441cb00f | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
cd81b8ae-90d2-4718-b515-09ab018943d3 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
bc67f35e-201a-4351-8a95-e26e4f36b615 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
45a927ba-06e5-48c3-bfe5-e5d8cee38537 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
1bb41ec6-65f0-458c-aa6c-7f2aa4551f7f | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
301f12b0-12e2-45e3-b254-9346adb5bc2d | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
13dbe904-9f5b-4758-b16d-5607247b3960 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
db55c75d-cac3-40c6-bb17-bcd6cb16d793 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
dc22ddff-c170-46e0-a217-a0569d0bd5b8 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
c72c9726-c8c3-45ca-87ec-e9a5835b60c9 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
c84207f2-f38f-455c-8c9a-8eff55723067 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
f34a9b28-5cd7-4a7d-88a2-d13c138c5076 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
007413c7-508c-4a71-ba33-6b12a56b51c3 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
d2e236e2-77f9-4e2d-9a21-0cfd1c4340c7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
9ab77f4d-12b0-45f3-9c01-b927f0ed0d58 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
ac7056c7-ca49-4e12-b6f7-d417889a9fb6 | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2 |  | NULL | NULL |  | NULL
d3ba9d5f-cfce-406b-ac3d-3bb283103ce4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
226fe9dd-8318-4d44-9bed-6367747b2001 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
129abf4c-d429-4522-8b80-7014ad9394b2 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
3fffadb8-90e3-4632-9c56-2b2cac05442a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
60747b85-18e5-4fcd-b6d1-a79930b5345e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
732e56f6-c64f-4310-8ff0-24b8e597fe0b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 |  | NULL | NULL |  | NULL
7462d635-af71-40fe-aafb-2428c71b078c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
80f1c292-d8ad-44ab-b8aa-3e5c19bb6bf5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
7e69918a-900c-4839-badc-f389b42b74b3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
7b8df639-6602-432c-8f3c-6ad8449e5a7e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
649596bb-7442-4225-baad-cdeee3342fac | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
58ee8569-2d99-4124-9bd4-32301f5e328f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
5b0306e9-c656-4f5a-b553-5add00bc9e9b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
656a3474-e118-402c-b4b4-a1b934d97c14 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
3efbc659-b90f-4e1f-a4e8-354c5950515e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
38e60757-40cc-4b7b-8ffe-b3134ca026e9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
3857a653-55e7-46c1-b39c-29a8c9df7b72 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
383b00ed-fd9c-431a-9a50-7fd5a9e59e09 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
3b77507c-1f0b-43b5-8020-024453af8ba2 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
3c1fe5cb-0cf2-4624-8b3f-c3d20a5bceea | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | NULL | NULL |  | NULL
2f83882d-da96-4a9e-b5c6-a1306ac8134c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
2faabb7c-eebb-4d7a-984f-167b91a13785 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
2e00d42c-a0ee-4987-968f-6eee4215b4b9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
36be8bf8-b35e-4b96-9bbe-47086a979a54 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
54ca7898-fb64-4326-a881-659240d53e8f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
57b80639-bada-4ac9-9f99-646a5209da48 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
4c000ed9-825b-4e61-a788-a78f17f43b8d | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
47676695-7d3f-428b-a6ca-23950b1f09b4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
45ad98a6-b982-40ce-91ee-b5baef752587 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
19650172-b43b-4681-9819-4b227a0fe108 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
0ae6c236-98da-4c1f-ad53-e30ae104f337 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
22d21458-98a9-46fc-885b-bfc1aadfcbee | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
2c0d3320-e06e-415f-82bf-950b82787cb3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
2cd4964f-54f9-4a2f-9030-a92d08681453 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | NULL | NULL |  | NULL
d4479c95-ddd1-435a-af96-aa47f6900c49 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
d3bfec49-5350-4530-a016-216aa13e0c1c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
d330751e-8cdf-4091-aeea-e690002ea98b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
d2dbf5ad-abbe-47ab-8703-243a822bd2dc | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
d2b6c5f2-2e68-4538-8baf-8fb8a6507517 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
989a3ae9-4376-4bed-ad43-7e95ed17d559 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
97478a66-a5e0-4e67-9956-d0a2c9cb25d7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
91489629-77af-472b-a704-e811758dfeaa | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
d252b023-84a9-475e-9b35-54887aa00539 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
e0bfa77e-b701-4216-b869-46b70a824265 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
e18ae2aa-2441-4dc4-a3ee-a42230fb04cd | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
dd1c355e-7928-45bf-8379-044e6fff89fb | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
fadeeb00-f555-4535-ac21-5644dcfd06ec | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
f36fb126-0344-4d6a-b8d5-a972a9b898df | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
ed867287-bddd-4287-9512-5ab9a3aa4ccd | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | NULL | NULL |  | NULL
c849c4d0-58e2-4291-a6a0-05e92d59f9b4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
c8760a75-1537-4b14-8d24-784498b6d1b5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
ae10270c-8ca5-47a7-8518-7eabdb0b5910 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | NULL | NULL |  | NULL
e7e1fc8d-b959-406b-a0f0-8bf09bc89ca6 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
efbb6374-935e-406f-93b4-f98e80901107 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
f04a10be-6ca2-4c17-97e0-23be546faade | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
018c1ed2-a704-4cac-975c-6c447cde1844 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
fa290195-eb15-409d-86f3-43149eafba13 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
b868d7b2-751f-4da4-8bb6-66dd65202301 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
b8e566e1-4e8e-46ae-ae92-94221113717f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
b0add2fe-8626-4508-9f61-558fc344dff0 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
b33ac467-9a25-4186-95fb-718498acf0ba | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
bc4bb32c-1e90-43b8-aadc-fe71bdd162a4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
1ecf6d8f-35cd-44ba-bfad-8f8bc8a2908c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
1bbc9d4e-5f98-4d3c-a8d5-ae1b6736e67f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
22f3cd7b-18f9-4273-bc58-592d3a172d7c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
22aaad18-0f1d-4be8-9fd3-43ccae48d198 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
65119417-d2bb-4d72-8255-643fed97dfd8 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
6792ca8b-be41-45e6-baeb-d8e89f109549 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
c74f1c9e-e8c1-48de-a8db-a70736d33a9e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
8828ad41-f56d-4175-967d-c391f39a0996 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
86abc42d-2766-419c-bdcd-c171faad51ae | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
8629dd4f-bb13-4e13-aa38-72edc96ee2d4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
9514ed02-f5f8-4ab3-a42b-792a3664635b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
aed0bfb8-4a5b-4b4b-9365-cd52214b81f3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
ac39aed1-7f6c-4a55-ba5c-84a88ac1e179 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
a512b0a5-726e-4e41-9291-da8874724915 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
9f492354-d461-4fab-8ce3-2d27b07c4077 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
465bd75e-3014-42e6-958b-b3b2565bd2c4 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 |  | NULL | NULL |  | NULL
fe027072-d689-4cfd-925f-0d0b57ea48ad | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
e7e9076b-b97a-453a-a794-298d157389f7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
a55a437f-4d29-4531-b24b-bd172c4305b0 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
ba683b89-189c-42bd-bd55-a771492b0d0f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
89e8ed6a-1056-43c4-8822-efc4a2923a3b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
9210f170-5482-459a-b767-1ed0f6447dc8 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
d0198959-7a5a-4d2d-b716-47f229529bc9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
c1a1f810-a23e-4212-ba94-9a7e1ae2f4ce | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
a889cad6-3f97-4eda-bf6d-489040f1c037 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
098295a0-3194-4d6e-b0f0-00f6d410de41 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
2d39bc14-75dc-4ac0-b4a1-31d46948b1e7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
fa549dd8-c467-4879-8f5c-6745fc543021 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
39264b2d-b9a4-4659-8d76-7cf8b26b0946 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
2c43fd7f-0a5d-47f9-84f0-42f5cee1653c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
717b07e8-4e05-43d4-9ac9-9f2d47ce7ad5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
0cdfff1f-d7b9-4da5-bf24-eb3fa7e9d5be | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
403b9f9d-e67e-4e25-85bb-da558b04b438 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
658d77a9-52c3-49d5-8fd1-cd4cd55db7a9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | NULL | NULL |  | NULL
a1646d65-ab36-4087-96cd-b05087cc6f8d | Pole | 2 | Distribution | 2020-08-29 | 2021-08-29 | Level 2 |  | NULL | NULL |  | NULL
2c439689-77aa-4f6f-814c-fb349df3b6ea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
575de996-da99-412d-a558-2cf7110578fd | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
27bb5e92-20b5-4e52-a586-94f1912beaf9 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
78a8d2c6-8337-4397-a4d7-27042f54ba92 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
58a291b9-e925-40e9-aaa0-43ff0d862112 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
37dfb10c-98b5-41cb-a7ea-6080dbad0b7a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
4c8d0cc6-f680-4d10-8de1-135fa285b48c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
b91daa42-5b8a-4937-96cc-214d1d91d12d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
c7426c0c-2f36-4540-a879-9365a174d7af | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
8541b4bb-f24d-466b-b02b-44873d091669 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
9d1ac5b8-87b4-406f-a331-4cd47be1fc6d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
aac16faa-286d-4438-8e85-59a574f86a0a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
93cbebe4-2038-4374-85d8-a9f38f38e7d1 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
91763030-325d-489f-9d19-412d9ea90357 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
9101ec35-8ae9-49e9-a4c8-d57fe2f99a7d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
910b841d-ca3d-4e94-954a-7e3f4f32f836 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
849dad03-256e-433d-ab1f-793ad7b63aea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
87dc14f8-f0dc-4deb-8f7c-7a1ed269e219 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
8a99b69e-6246-427e-a390-c9e44aa20e85 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
67f7b467-dfff-4428-8f4c-12d22df72a95 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
5842ce0d-a641-48c7-a73a-11fece367d83 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
c0549cc1-32df-4aef-a0bb-82dfbb4f44f0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
cf15e6fe-975f-49d7-a55b-8f729d5208f3 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
cfd2919a-372d-45b0-b103-c425fc173eb0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
7c5cd56b-b536-4a10-8795-cec4fd40226f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
24af0108-e145-4fb7-ae99-f5a40dc152bc | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
285a40f3-9da7-469e-96f2-f1a8c89f426f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
be6d0c99-898b-4327-bea2-ee9854cd983f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
419d5566-43b2-4339-89d4-abf786f432ec | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
b2473eb6-80f6-4e44-b4a7-664a0a0ab89e | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
afc49c8d-c96e-4371-8b01-2c61cdcb337a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
b92c4ebf-d938-4441-bd02-d24cee72bf1b | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
f9ba4a13-894c-46ec-adf1-ec131be8da44 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
f4af0ee8-60cb-4f1c-972e-f51c4ea9db87 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
eaf2b7bf-d29b-4912-8ea4-494fe2d13d3f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
8a94738b-4706-4581-805a-d7508ddaa86f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
e8d4726b-6658-4616-a51d-631eb3ac122d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
b95794e2-4d0a-4b81-87f2-13831c057df5 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
e233563f-1b50-420b-aefc-810d6cf91930 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
fe7277c5-c631-4eb9-9e36-a71d6000790b | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
e4869d67-af42-40af-ad79-30f3e004cc56 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
d2122a85-6c29-4e2b-93c5-142f68cb2fcb | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
958d6208-957b-4c19-b64f-1366d39e83be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
96ad6dd8-e019-43a9-bdd9-349c15e2dd6a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
a67244a2-99dc-4ed5-bfd8-c1bd2ef2f6be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
b3dda626-3f26-46bf-8441-4e20fab6bd0c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
a5ba7098-af8f-446f-b6f0-0db9c2190e0d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
a2b9158a-980c-4bb0-bed4-691466c63a15 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
d0656d07-e935-452a-8214-2fc076b0b432 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
d1b7adea-2503-4dfb-948b-d562f3d4aa82 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
9116c256-c4dc-4cf8-ba9b-d39dc25ff7af | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
252e052c-f447-4585-9f27-ff6d6e2339a9 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
20725891-8460-4ad7-a407-514b072b7795 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
1e1a7f7e-aa1e-4263-8194-6dc8993e25ea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
1f8a62ae-5655-4024-a415-325d13602523 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
1ba90aeb-83d7-4dcc-9ae2-e54b5da8e025 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
1370bfcb-0f40-4109-8523-e6b71d9eaf99 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
02154b5c-5733-475e-875d-70f6576fcc8a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
4bae78ef-a3d8-46db-bb32-f8f1961b1542 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
4fc7c861-6692-452b-bdac-1640d3f59d94 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
4e07c79a-398e-4ad5-8164-9cb68a487c5a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
32802c40-6d99-4836-97d3-4270f76e3dcd | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
2ea31130-dd9f-4633-9ff7-7d21c0b76b64 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
40f21d64-0531-48ab-bd98-6879d65034bf | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
6eee28bd-69ce-4015-987b-f5af6f8608f3 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
6db70c71-2f1c-42df-9183-6f6b6a7b5ad4 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
59e77797-a3ac-4efb-96dc-4a1615400290 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
649360f8-d65b-41a9-8b14-0a26a83052ce | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
79acb193-3355-46bb-a41a-75f656adf4be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
78b1e580-37f0-45c5-8508-2ad06b9476e0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
77106a3a-903b-46e9-8791-ba85e33dd47c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 |  | NULL | NULL |  | NULL
741d6642-5be6-4219-9783-4948204d0833 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
80f63447-0533-4ada-b654-b9631e0347a3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
59988cdd-c539-4a9e-a9ef-4c5d7aa4cd7e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
6c336089-7169-456e-80f1-c7736ca75aaf | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
3fa3b635-1bb3-4829-9667-3cc4b4066e8e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
40df8c8d-034a-4fec-98bb-ef97da437b93 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
3404e748-dec9-457d-895c-d21ecdd77e54 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
3576262b-4b01-4543-93a0-522ea5aba78e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
35c243a7-6cba-424c-bea9-943d130d74e2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
0747833b-7cc6-463a-b1b4-55d34f7f5e6a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
5419ed02-11a9-4ccc-88ca-ce8eb98e509f | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
43db67da-deff-41c6-aa3c-b1bbeb12a316 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
02c0e15c-b416-4dbe-ada3-1e7c60fea209 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
0488d860-8e13-4301-b664-3755ac68f5e0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
046dd7f6-f250-44ae-a93a-c471a0003ae3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
020fd888-a02e-4dff-ac8f-888762d08506 | Pole | 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2 |  | NULL | NULL |  | NULL
d2c99502-e285-4806-8cbe-815a720a4a89 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
8d1225ab-0eab-4a8c-8e27-db536b3a1003 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
17b46e6f-b804-46e7-aef0-5c7533f8824b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
0b1116ba-d827-4249-94ac-d4119160e231 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
1d16959b-37ce-405f-b3f9-32c129e77915 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
239ef321-6ebd-424e-b8bd-2461094f5392 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
25a748a8-a1d0-41c1-9722-b3f50ac2e647 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
23c853f9-00c4-4b86-88e6-55f55127cdf7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
240db039-f27b-4a44-a5ca-8968d2e4e581 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
2d44d5c1-c15e-4408-8ab3-7dff52602d7c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
2a3f068c-197a-411b-9db5-a959dcb804e2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
d539be7b-0e66-4011-9555-2d4dd5573359 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
89147cdd-15cc-41fe-abb1-3bb43f3ef51c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
a7a377b5-f6ce-4f4f-ace4-b8cee00359b3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
b1c745f4-5083-4796-a1c4-c7b641705168 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
dbeea258-a912-4ec6-aca1-384355ded232 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
d64855d8-8843-4cfd-b0a1-cc0e45b9d810 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
e4e3e716-8050-4205-a8ac-fae2c4107156 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
e684fce7-e87f-4a47-9a9a-f646ae16aff9 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
e199d637-2e3f-41c4-abb3-3b385ba62c47 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
f9664bae-2d45-46dd-93da-eff1e1a80b84 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
f60a4b47-fab6-46a0-afc9-178ac64f8a1b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
eae5ecf3-20c4-4bce-a8a2-fda3576491e0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
e90d2002-95ce-4f5d-aadf-70b08778a2f3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
c80d6530-165e-43df-a89e-0a8b2a734fc6 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
dc7688e3-764c-4518-97e3-803a2ff79980 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
b5cd0e67-c0bf-4698-b3e2-625165f658d1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
f1a4d153-fb12-40a2-bfea-e50f6abe6ebc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
f694ce95-f22d-4b53-958e-52cef46b9c83 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
bf438a78-0353-4109-a0a6-8f4a49f4ace2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
357c69d8-cdc5-4058-8a23-d3e5e5cb98dc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
bc12987d-59d7-49b1-b536-b51bc23cd288 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
7c479afd-a0a4-48fe-aa0b-a59f482471c2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
7e116651-da1b-4b64-ada3-06458605b742 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
83325ef1-434c-4d60-909f-267d766f7403 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
800ada78-e40b-4af1-aedc-505aa75a5968 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
cef986ba-2381-45dd-887c-dc7ba4435a13 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
52c93669-db64-4b56-9272-c6159f297f96 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
c6c67015-c860-4b6b-8bb9-91902f2bce86 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
79bfb517-adda-4dd6-a8ea-a2dc07e85f55 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
c4f224b7-c0a6-41d3-b214-37ad5049330c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
886b88ee-a8e3-47fa-bd29-d00df34e9069 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
8b8ab350-37c2-49ea-9121-51d78a21db27 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
87dac9fe-851d-4e22-b737-28b58fc487d1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
84755190-9622-402c-9776-541b9d281016 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
77897dde-06a4-466f-b792-15fd3254a2ce | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
940b0d13-1312-4f18-8427-e8fc56481ec4 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
97307ef0-0ad2-42b2-bf8c-6571261d36ba | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
a7bda126-e3f2-43f5-a0cd-8d540dd75049 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
9d5b6d10-6ac0-452c-956b-dcb6b88867c3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
a53ad0a7-b18d-487b-aa0a-70a5023394d0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
84e1196b-0153-4b13-ad7f-e99e0b0852ef | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
8a669dc2-aa45-4129-b35f-92d3a2dca667 | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
95e3c09a-7baa-4037-a878-f9fd4f94af2a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
9e05c523-b7f4-46cd-a687-d0d682684298 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
b4617974-1982-47cb-8672-13a5f005fece | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
b86717c7-beb6-495e-92aa-2cb90869310c | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
b86fa922-6699-4783-8d9f-4e50e54009c1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
b944276b-e247-456a-a95e-32db3f079b08 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
d137aa0a-c075-4b91-842e-14ebb0dfe363 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
f35cedbd-3d77-4094-b5e2-80ea631e78c0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
ecee9244-d93f-497b-877a-e525f2ae0b8d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
e11f3af3-6270-40e1-bfc4-d178f510132b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
ecb2de1f-4edb-4d7a-9801-0deab7f37c3a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
fb61b037-8890-471e-acac-f042c5b9adb7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
3c500bac-f68e-4ec3-9062-5161bca625fd | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
71a2b5e6-6936-4a9f-b326-994511fafe69 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
929bed08-2f14-4b60-be02-700ab3355c60 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
875d130f-b150-4cf3-88bd-41320835ac86 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
bd47fbd7-abee-459c-a648-481f979d985a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
062c2f04-7f46-48d0-99f1-44d9c6fb5188 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
5d09086a-2e2f-4ebd-9091-de50065ea0f7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
6118cef0-2623-4972-b1f9-434eec962a7d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
6c63fcfd-6d66-4f0f-8097-da502f1d6929 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
74f0ad61-dd7d-4a59-a5ed-51eaa371fefc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
2afb1480-243c-4bba-8e57-61d0019984e2 | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
51f67e93-04e1-4a0d-a2c7-8d664519d290 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
0d31ab71-ff97-4a68-a3e6-8278fe133e62 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
160d63fe-1595-4fe3-8ea4-be158c40c27c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
15eae9f4-1d60-4e82-a6c4-1e4f64ac0b42 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
27c24d24-0b53-4fe0-a923-e7df32ce2b7f | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 |  | NULL | NULL |  | NULL
241fa420-b339-4a73-a778-7cecbd4cf154 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
0452c33f-6125-4ed5-bec4-ed3b8a65b199 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
0cd2f3fd-3c6c-4520-b5c6-70effe16c1bb | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dbf77031-3d77-41f6-a0ca-6594a216e747 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
0b1a28ad-51a6-4e5c-8c05-7e1a04f884d9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
09d10548-d343-4feb-89b5-aeef8494d6dc | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 |  | NULL | NULL |  | NULL
4ff2e1e9-3ff3-4dce-b435-7265a02b8a59 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
40ca0c67-2eb0-4821-bdbb-9dad7fe6c6f9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
45c9ec24-b788-4594-9024-ee3ca5fa0444 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
2d4c6ff4-4348-4546-b247-18a591d570e4 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
338c0afb-45ac-4e4c-9c9d-632970961463 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
300d4d28-de23-460e-ab98-c7a5345ee175 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
7c1a5ce5-a610-49f6-afa4-05ca3188b95c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
7b419c2d-34a4-4423-87c6-d6d937673b43 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
79c89fec-cf61-4fe4-a3fe-e23ccd0222df | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
69de7782-3e45-422b-aa80-0f036d3c6633 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
71425b1d-dc09-43c6-a239-b2fde62f8e57 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
00ea67b3-d014-4f72-8a56-1eec72dac360 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
13cb38af-c27c-4246-9024-ed6375b925f5 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
0542e537-4b5a-417d-86e0-3039c14a5dd4 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
1f9fdb01-6ff5-4190-aafa-f6015a30eeda | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 |  | NULL | NULL |  | NULL
108ac909-658d-45db-819e-1807f2aa0960 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
04b2b7c6-09cd-43bf-af84-e69f59035c1f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
01eeb00e-9c7b-49d2-838f-9582360f1c3a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dd154be7-6396-47d6-ad5c-5b17a52e2012 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
e9753b4c-a67c-4829-8629-674a2fe942d9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
d95fe712-ff6a-4a25-98f9-d8a8ac6e40c8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
e617cb04-b05d-4fa8-9b41-296590d76e99 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dac227bb-8a69-492f-9c47-70b24a146074 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dabdb48b-6ef7-4f76-b4d3-d417ea1282ab | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
094e8042-ad7c-4b45-9ac0-92f60ebb085b | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
e2ceb37a-cef6-4cad-8c6b-1496e1b1215f | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
0fd6c225-61a9-407e-bfc3-dafb7ba9ca3a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
eb6920ce-79a4-466f-ae37-87fc5dbb44de | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
ce06f667-11fc-4299-8e9a-46d1a986fb8c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
ce36b1da-8f29-4946-8802-e0958bedf189 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
ce4b319a-5f73-48bb-8291-6378792d4f2c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
cf0a15a1-73cc-4921-9e7e-bebccb0c4a6a | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dd62f31f-5529-4d25-aaa0-fe3c17fdabd9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
b144cc85-6181-43d6-a3ba-9b8935c5ded5 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
c493cdc8-1f5b-4e88-b75e-42d613be479c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
be42a931-e725-48f5-870e-908d52782b4c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
9cb83f2e-272e-434d-a99a-c2725ef521df | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
9021155c-d406-4db8-9a3e-68dc02c56483 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
820202a5-1469-4bbd-a65d-4040b42e812b | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
7e0a3f3e-3101-4967-9843-29656b0658d3 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
87be9d3b-5bc6-458b-9500-006d9bfab959 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
a2e6fce6-c524-49e7-8e77-99f166a04b38 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
9593c5bb-8859-4d0a-b89d-579a93190b97 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
6598de81-29fb-444c-a292-7c462f6fa622 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
6675f7fe-66e1-42d8-802d-e07e9fc5c7c8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
58f9fbe3-6e1a-493f-9c09-980197e63350 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
cd1fb2f9-721f-4594-8fcb-c92d7cada6e7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
29a1421b-d404-427e-b99b-61dfc91c3c56 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
296dbc28-e97b-4fc6-88de-0830c0c866e8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
48d37046-a22f-4285-85ba-ea171c29b02f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
99e5ce0d-a2e3-4967-99cf-486898fd6ac9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
fbaea623-918b-491c-aa89-4f5454ee1360 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
fdcaeee7-fdfe-4fde-815e-8382fd31821d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
ed1ec319-8364-47e6-8a79-91132087eb31 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dc7568cd-6059-4b39-af9c-748517347e14 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
dd3f4ef2-aba8-4c98-91dd-e82cd8521feb | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
e0997e6c-cca2-497b-b835-90d92aed5f6b | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
d09b8b6f-2ab8-43da-a8a9-e91774f6655e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
f0bab855-33d6-4d15-8d7c-142df5e52731 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
efb84d4b-64f5-4ed6-b6c9-e8aec7df8cc1 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
f33666c9-d97d-45a1-b05f-29f40affb989 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
e3df9bfb-393f-4551-88b5-f58d8f2317de | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 |  | NULL | NULL |  | NULL
d55162ba-c472-433c-adf7-518ef7186212 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
d7103d61-3aab-4e98-a1ee-68f52282bc2e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
9f76e8b3-6fb6-4bfa-be87-b983fb0d6ea2 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
8c39bf06-f0a8-416b-88d7-b06f29272800 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
7fdaca81-d2c1-42b6-a2f8-1482fa2809ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
2bf0adde-0e08-46de-92c7-a3163bfdf5c7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
2540eb6a-ee4c-4927-8ce8-d8c47140014d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
28a1450d-3823-4925-b769-f2abc45ac855 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
1f430726-98d0-43d5-9ba1-978a9a60c34c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
1d7ffae3-6ebf-4158-8c4f-b85f03cf581d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
0748dd77-f736-4127-a1c7-4597a86d5c5e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
1febe576-cd49-4c54-b733-cb53e2826dcf | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
f8a9b4aa-8c29-4e54-a583-cb68d849f0b0 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
bb64e499-75bd-4afb-9122-afbbc0e62239 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 |  | NULL | NULL |  | NULL
ecb93fbf-51c2-4fb4-96f5-d630752a56b2 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 |  | NULL | NULL |  | NULL
42c4b99c-903b-4f0f-9189-d34173c9d46d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
02cf0692-0c5c-404d-9e77-c8c59dcd1e26 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
424b7ab3-beca-4966-9fdb-ccf133aa1279 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
42a4c11f-be39-4720-b107-e78c23c73ac5 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
4e54a16d-e9b3-4353-87fc-f120013a38e6 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
4f81ed6c-143f-43d5-a56e-cf9d22866d8f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
3809c851-ae48-48fa-94b8-e63cac41abc3 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
3f02a38a-f265-4bd5-a1e9-7d3f31b1a410 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
3cdebe1b-383c-4a18-a748-1482c78bd7a9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
38689df5-ed3a-4972-a768-a30870e2458c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
6af542a5-6a41-431a-b3e9-aa79140d3380 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
64ebcbf4-2e78-4dbe-ab72-a7fb5da8dc1d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
67abe691-35fb-4d6c-8251-a4930192d069 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
7eb2c6b3-f8fd-4cef-b728-e04c7a10f61e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
81148ac1-dd0f-4a8f-bae2-86d37b95eaa1 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
7386fbb0-4cea-49e4-b493-95e94bd119ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
729afbae-f6b3-4e3f-ac15-60baf56026ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 |  | NULL | NULL |  | NULL
720ff74d-c782-4a18-a0f9-01e8cd87bf8a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
6983ef13-e457-4102-a978-20114d4f1878 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
6f32cb28-8681-4ff8-bcfc-30e14ef7d7d2 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
63bd84d5-f025-4cee-84e9-6378fbbeee27 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
3671a876-f064-4e36-b861-d75f1c2349f8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
30f30b1e-da12-4b28-8673-597916f0fd55 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
30c82d42-2490-493b-9298-38f340310fc0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
4ca9d859-fd9c-4ea1-b0d3-9bb871a98fa4 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
4289eb5e-9202-465a-8a64-a5835eec2231 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
43accaba-0103-4976-b84f-ade8668a9958 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
450cf542-041d-4199-b502-74cf55cac66b | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
4bb75326-d7e4-4591-a838-240a5ebdf11b | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
028bba8c-b1f4-4b64-8dd5-f2a76f3d706c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
0ceb36db-0fb4-40e5-899b-d8555958f19a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
1b2750ce-dd1d-4157-a1c1-82c9ce5902d2 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
1da421fc-c7c8-4de7-934e-869945778fd8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
20d00224-fc97-456b-8e5e-3375e1bb6cb8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
2aca75ac-e5b2-48cf-9918-ef81c8b6eff1 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
d60536e3-4ae3-443f-b159-a8b533d22979 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
d359d0dc-37a4-471b-90e1-86dee87e79b7 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
d8b1a01b-6d84-4a14-8417-27129ac077d7 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
e5cd6b9e-331f-4cca-bc9b-a937b82f7a76 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
ef867c46-ca44-4738-8ff0-51be94d3b248 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
fea02365-3dec-4a27-bd4b-c94340890528 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
fa77a539-6489-4abd-8d45-4ce110d069cd | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
f53bf024-7ef8-4afd-b1ea-ca5b6f2f625e | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
b7c0ceb6-811d-440e-a34f-7c8a0c8015fc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
b25c2317-b76c-4b2e-baf9-08196d89a979 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
ca0f3982-9948-4978-9c5a-68da3c4388cb | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
c877b346-ab51-4811-b848-e518db1f365c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
c28ed16a-ec4c-48ba-b13b-cf0520b4de16 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
c25d9c3f-7191-425b-9ed9-a40a4fd5a201 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
943348fb-3449-45c9-8ee4-f0a88d9d7e66 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
94a56a3b-fec0-4a42-9056-10ed26262c8d | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
93a9fd03-49b9-45fb-bdd6-33a86d0cee24 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
9030198a-d4bb-47d9-b44f-05b835798f83 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
9099b8aa-6e93-4498-855a-05d35d914d04 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
96f21226-74b2-49fb-a8e6-04ab98866d82 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
84ad98db-b50f-45c8-93db-1d5014266fc6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
8673e38d-6d6e-4d40-ae6b-a1517c53f50d | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
85b45d95-927e-42e9-96bc-32ab87026aaf | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
8ee5b509-ba9c-4fe8-a9d7-59d9ec9fe80a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
ac2b75a3-7f9b-4b1b-a188-2420a6ef26bc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
a8d0f2a6-b09d-45b0-ab51-c2415c6b6e32 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
8d2ed11a-e266-4d3a-b968-e4de2b10703c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
a3b368e6-6baf-4913-8684-ba72e72c0c53 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
c31566fe-07e5-4295-a95f-065b8ef2b747 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
ecf7f048-e36a-477d-9aac-f03e39882b50 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
fe38089c-aa00-4512-9842-39a293bd7ed4 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
e26e8bb6-3661-4c63-bbaa-6c3cc6984930 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
66c9877b-0b55-417d-b957-59ce26913e30 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
795baf10-946f-482d-882b-8d48c7250918 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
9bb3c732-38c9-49c2-be62-6fd71f3fa4dc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
94e72f92-4961-4903-8097-99fda1b6b0c5 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
60bb171b-0d91-49cc-91a5-41d3778a5441 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
441c0487-52f2-4b01-a27f-1087429efb6c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
5ecc8eaf-db7f-4dc3-9bd5-31dea1878395 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
81f66b9f-bf0d-4df8-bb58-58316f9aabbc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
59c77c7f-d073-49a5-a5ef-b67f91b08aa0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
4afbf1a3-7284-4b92-ba5e-a590ac715f10 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
15ac1b4b-aa67-43f5-8c09-912543d2ab64 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
02d04093-143b-4f68-a648-2ca57cd362d6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
fed972e8-64f0-4526-9c95-5fb988785d82 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
6d0a4f46-f766-4226-9cc6-5065b4a1fed6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
6ad850d4-7b6a-42d4-be9b-d2f23f4be085 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
59e8d255-b4aa-4c17-bc15-739a56cc2794 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
d09ba523-b3db-4310-8479-7eaeac594469 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
19ce6161-2a94-41b7-bb83-fd8e507e286f | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
1f10ed99-3f21-4bec-a67b-d0361a453726 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 |  | NULL | NULL |  | NULL
793ee3f0-4ba2-4fff-84ea-78591fdea2e9 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
59bcd9f1-8d47-432f-b030-1c50ccd6a341 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
7c1c83b4-0e4c-4f4a-824e-428a7ceeca4a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
7c827a66-cdd9-4045-baa7-0c07096e7aa4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
32917b75-fa84-46c6-936f-b257d8ae43c5 | Pole | 0 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
42af15cf-e466-4908-8db0-71e72dc1590c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
45bc74f6-1240-4d96-ae1a-817faddc4129 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
ffd402e8-8849-4e5f-ada2-4667ae6e3c07 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
feb31db9-739c-4246-b217-67c4d3479010 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
ff161ed3-af56-4e06-93be-d635fe5f7b0c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
22192ba3-1c1f-46a5-a6df-d5f7e038f414 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
53d6e92f-b9b2-4d22-afa4-89d7fbc87490 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
5c39527f-40d5-4b47-a41a-52aaed79e30d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
8ff1bc52-0726-4352-b0b3-d831262c3a6c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
5908cb06-5cae-47f4-9330-4d66a5cb09ca | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
a99bd2e8-35cb-42b5-8c3f-9ba750389135 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
a6ecf43c-7e1b-4d0a-875f-bc0a168ce775 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
ccdf8de7-fa66-4912-b143-98fa6b727181 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
bee7f411-d34b-4f10-9e31-44f694ebd1f7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
c331422e-23c9-4e96-a6db-d4b80e116488 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
c997713d-0e5f-405d-b451-ab03b96270ed | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
a3997a6a-46ee-4788-8cfe-540f41f7fe94 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
8c0d2acd-fd47-410f-985b-9fff62dee6c7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
0f67fafc-bf6b-4578-9e13-e91edd72022e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
859e89c7-bc68-41dd-8bdd-17ed9bb5e533 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
cdf75ea9-fd3c-4178-a016-f0b75dfec632 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
eed2b923-49b4-4d34-b30c-8878b699ca62 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
e716486c-85a7-48b1-a136-0e43efa7958a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
25841d4e-d5a0-47ba-9d1e-1cb9133e32e7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
aba9bf91-affb-4196-b128-8faab3ce837b | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
2bd4b273-a600-4a5e-a6c4-9b6135c11bf7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
7dcd709c-7a36-4b59-b760-9554231998ad | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
88952e0b-115c-4252-a2b8-1977d941ce9a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
91ac1360-78a2-4775-babc-ed1ea48cc12a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
9001bb70-723a-4903-8848-888a2fb5af4f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
78e81f6d-1bd1-406b-8548-412d7e2c353a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
c779e182-c441-4de8-b6fd-b3b81fb0d70a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
c937511b-a453-4fd9-a638-daa60d69aea4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
ce6c2722-65f2-46b1-9a96-fd416b16eb61 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
8dee2d31-6e16-439c-9afe-8fc9332d6d7f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
b11e74be-b298-4cf1-9fff-8a32eabcf047 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
ab5a839b-d9d1-49bc-957b-1556dbecfd4d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
3e25d63d-4117-4aa8-b091-7970e8178931 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
f599e0ca-c8e7-4ee0-99cd-6ff51b213105 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
f870d706-5d5b-42cf-a78e-5df2c6358e5d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
fd115b23-38fe-43a7-9098-0892debe1571 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
ee5fe661-3c6b-4707-8e5f-ff0886e60c5d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
f0ca0045-f786-4618-8664-3cecb1df301c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
f449fc2a-d4bf-44d0-b996-c5b4efa1801e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
e7d139ee-40c5-4715-991f-976c48c684ae | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
e8d5fc16-ccc6-46cf-aa4a-bfcbfc2ec23e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
e07f3cef-361e-4278-ba0f-5648cc6ddbf8 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
93a67e1c-d8ba-4426-99b8-d3c37aa5dab6 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
8e9cb34d-8f3f-4f5e-b0e5-09ea686f46d5 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2 |  | NULL | NULL |  | NULL
d0fc5976-1529-416e-84c7-0ea6f9ebec77 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
2cff5f4a-2437-4440-9ade-5592907f087b | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
28dec882-be69-4b0d-898c-8226bb188e21 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
241a3ae9-d3a7-4a77-b10e-4c012f6b3bf1 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
1abc30e8-fd13-4041-b0f5-89406ac22b0f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
1d4d8048-9041-4d02-b767-246583ccdbf2 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
0e866a93-bfa2-4330-b155-ca7e6d295290 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
0e8a5916-9667-44f3-b805-289f3f7c5598 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
1821f34d-3e92-44ab-8a9f-fc76e4363942 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
1876de59-37d2-4888-a040-c80203093175 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
026eed93-a63f-487e-9762-9514fc61aa88 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
4b2730b9-1661-448f-b5ef-138721f0df29 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
40042331-70b4-47a7-ba96-d5ac8a91216e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
47cd5c0a-9d2d-4e6c-b0ed-15931ffac538 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2 |  | NULL | NULL |  | NULL
42de51ae-2f3c-481e-843b-6fe39b4edeb4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
4c61cb8b-fca6-41ea-8191-b67c7bbda8cd | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
4e2c152d-48f5-4274-8564-e2160cfdce48 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
50c2db88-5df4-472a-b1f1-5447b0163033 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
51213f38-9a94-4183-8c0e-ab1e8587dcd0 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
377d6ab5-d931-40c4-8a2b-b77469799d8e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
32c5e4a5-9ff1-4583-a848-61b592b3c704 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
40457e96-3d71-43b6-9645-28c65b9a7d93 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
64bd2ecd-5c2e-4a77-bb4a-e308e3b590fa | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
60a0e830-569b-4bc6-b760-272d102ac75d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
6f696f76-7ff9-49a4-accc-9ad1bd8059cf | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
74752e6e-b206-42ea-ae09-3f41d38f0439 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
7d3ed886-79d0-4e0e-94e1-92456a8147bd | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 |  | NULL | NULL |  | NULL
78b1020d-9295-4c28-9563-687964cd6f24 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
7379d2af-e4b6-40ef-afd2-556b87769b0d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
43d35486-ca0a-4731-8b39-0acfae6744fe | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
7249ee2b-ae13-4167-90a9-113c0db50b72 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
6118d409-b573-4433-b074-ebcc40146fca | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
599e071f-b927-4f9d-a839-7d6bb427e94c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
675beea7-8022-43c6-83d3-c552ef04193d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
3ec8c3f4-9955-4c1a-a33f-5e730b7f9da1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
3c73a0b7-ab99-4927-a417-92474c552f09 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
2ed8418c-495c-425a-8157-267f7a16bc3c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
0144a31f-f308-4520-82e2-885c76ec70ed | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
019f5c2a-ad86-42f7-b014-8bf30cace2df | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
ffe83f37-d44b-4b5a-ba2c-6f193843c5d1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
188e4e64-b8d5-4ad4-94e8-efddc3801ea8 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
04e3e2fe-194f-48af-8dc1-3622f6a40b74 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
0aebd7e9-f056-40be-816d-5961c129c4b2 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
1da0c206-20ca-4b4d-a5c9-5bde1909b10a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
1bc6be04-5cd4-4a10-acc7-94b09b27699c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
20f1b388-4757-4b77-b8c8-a89e117761af | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
23322787-dee5-4e83-bd8c-ba5a35a7ac0a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
2c1d4635-8652-438d-8ee3-69b9d4796bb9 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
2b3d117e-70cf-4eba-a855-96bb895608fd | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
29d29366-b49a-4217-b14a-58f8a04f7ffe | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
d30ec098-6943-4e28-a1c7-ae2fd67c8381 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
d62827ec-7323-4015-b7f9-29a92c85428c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
d74ab664-8fba-4068-8250-1a339149868a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
98653a36-9249-4f40-9ecf-adb4654c618b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
de1aeec2-d397-469a-8539-f275bfebd894 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
e78aa2d6-ce03-4b5b-b20a-f8f7d4038f87 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
f01c0809-a76e-4e7b-b101-445d0b805549 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
e3eeaac4-5add-475a-98a1-cc17c032dce4 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
f136769b-cb1a-4cba-bfa3-e0d7d74cbf41 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
f6d4d2e6-cebb-421d-ab71-3ce4021bb699 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
3761f46a-35b8-49b6-946f-63528659eee5 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
bde5e2d0-5723-4d0e-a62a-a654bbc4d037 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
b17dbbaf-b321-4a53-943b-d6cff3d0037b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
b18575dc-378f-4777-9b13-5314624f0fed | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
b8d9b0b0-c808-4ef5-a886-1a1e8c452c27 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
b988b884-c0b8-488e-a11d-19bad8120d7f | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
c78149bb-e550-4284-b0d1-b445fe292b27 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
58af91a2-9173-4891-bd46-f22d3af4f8d1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
a64a72ae-3ed7-4f07-a01b-00eea1c36dbb | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
a616811b-b3e8-4c0c-bbdf-e485917b6187 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
de8f1549-549d-4ca4-9f93-b3e94ec87361 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
ea88181f-b8ad-4a90-bde5-69b975ab296b | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2 |  | NULL | NULL |  | NULL
f0c532bd-1a74-4597-bbd4-60907b480179 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
f0c4d872-f970-4941-9bde-bfaad45c7af0 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
9dee83c4-429e-40f7-afee-7b5469bf8317 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
111d99d2-0abf-436c-9c59-b28c6e0a8a34 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
5333c5f7-dc2a-42c8-b0a1-7d51a85b4330 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
ce733115-7d3e-4afa-955b-4bcd0e10fa76 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
7622ffd3-0e55-435f-ad87-4c5fa95f9905 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
8846969b-ab27-4cd8-944c-a20f37ce3b6b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
c18b1e71-0bdd-4573-917c-1e6a1dbee7f2 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
bb2b8e75-a6ab-4739-b5d1-5dfe0038b779 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
986ce322-8b30-40f7-baf3-b98e99bef4e6 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
5e9d3dbe-83e3-4031-a451-f7607487bed4 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
4da17a15-1c32-40b8-8b6b-34c8a83edf07 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
2fe5873d-68a3-4a36-85bc-6166cd9f3480 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
2b100b8e-37cd-41bc-a6e7-cf7b2c630ca6 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
70c4f184-c4f8-4fcc-a79c-6364867aa3c0 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
59d8f02f-daa6-4005-aa82-b5201b40101a | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
6625a1b7-4aa3-4839-9560-d1b4c2c798de | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
62a2a326-04f4-477f-a4b4-ffae717d4338 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
1b5e87cb-9e6b-4225-8725-582dcad776fd | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
c9bd42c0-1988-446f-9dd8-dc4800b40448 | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2 |  | 2022-05-03 | 2023-05-03 |  | Broken tie wire. #2 acsr with aluminum tie.
552a5ca1-8004-4832-bc93-a8dc4572480d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
7b9dd334-23b4-4f0c-96ac-37f6f9effd9e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
326f9c67-dd0e-46fa-ba69-df3b0521600e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
a38335c1-5bf0-47c0-a335-611b5acc4e48 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
1fc88df2-c68c-4200-9db2-f4a7e98e3de3 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | NULL | NULL |  | NULL
2747e8ad-0167-406d-92b3-b10059bfa622 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
406a7372-3a54-4637-9f03-7a745b469b3c | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
96a41b9c-09d4-4427-850d-d1f0d48f9c1e | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
00b12d0f-273b-46f5-af10-0d8c19cfa9c2 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
aff8bc86-68e0-453b-a5f9-93840bda7eca | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
a24763e9-8525-411a-acf0-4a28c82220fe | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
7d1ad1bc-454c-47bd-8999-752f376c7faa | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
8ffd1c2e-9442-4098-83dd-25f3c734fb28 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
85d298f7-98ca-4fe4-a82e-b09b78e42448 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
b84f5f6d-b861-4f42-817d-693d2c26e82f | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
b43d9cde-796b-4e6b-be6c-6e05343becec | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
b3869d9e-d9b9-4cc2-99ca-6bca4151a640 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
afc68393-d89a-4a9a-8ea2-1c63fe8eb06a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
f5edade8-b947-4c0f-afd4-9b2cf4c1aea7 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
f8b161fc-0e9a-404c-99b2-ed5fd018c308 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
be284cae-e84a-48bd-ba5e-fcac4c0a0d67 | Pole | 2 | Distribution | 2020-09-05 | 2021-09-05 | Level 2 |  | 2022-02-25 | 2023-02-25 |  | Pole is marked rotten and top of pile is rotted as well, need job # to replace pole entirely.
53863e53-64a0-4226-8642-34cb2169d364 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
41b49b5f-9621-4809-b095-7288ac22ff6b | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
9e72ff63-ec9f-4430-ac3a-16f5b9ec1b94 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
c9c479a8-4418-43bb-84d0-e2eeb10e8ae5 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
d9884afb-8c3d-4684-9791-ea8c23cfb7c4 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
da7071ca-cacd-47eb-aa47-c6cfc507a48d | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
1fbfdcd5-613e-4f50-93ff-9f88a90018a1 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
0a1bbb28-fed4-4e68-bdd1-b7513814c362 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
0ced76c3-4d7b-48ae-abfb-1ad255951dc9 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
14ebf574-7f8e-41a2-b968-8e8da245e45b | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
14667c72-39fa-4889-bb72-e5fafcc0c209 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
10d96d76-610a-4198-bd15-e2982b8464ce | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
37d49d91-f96b-4f10-acac-42a82cf76338 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
052f5e46-e610-4fe7-b9c4-29b9fbb0c033 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
01e07b73-c11b-4788-8934-0a883d539e0a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
30a71c3c-efbe-4569-b745-24354b8b0729 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
37c14969-153a-41f0-8be2-4137adf34384 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
5105c557-1c73-4f7c-8c66-56a22fc92eff | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
4f86c94d-dae8-4a0e-99e6-081c8391feb0 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
498947c7-4d35-4419-a553-7c1c34293f97 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
687591f2-36b9-44a0-b23a-77303cb79d5a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
609169e2-a165-4a27-a080-e51de78251fe | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
76df2894-b548-44f2-9b3d-1fbf65014e5a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
83d11714-ab4d-4cd7-9c7d-2366b418a7c1 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 |  | NULL | NULL |  | NULL
2ea550ad-8ef0-49cb-9761-fdc48d5bfb8e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
8102d5dc-0f2b-4c0b-a698-e9ad86f47ad8 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
806a044a-1e7e-4440-b9cf-3c946f102d01 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
7c48afce-1b06-475b-a8d0-0698b0715c84 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
76e896a7-6e8d-4b5d-91b2-b0fe5140136c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
73490d40-4936-4a87-b5f1-77ab16ee65e2 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
636a27a1-b387-4d00-9ad3-5a1228759afc | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
69cc017a-5d89-464d-ac5b-4ec33c1ddbed | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
66120f86-56c2-4bfd-9430-bc20357231c1 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
48d3ec55-feeb-49d7-9a30-1a37c2e95bd2 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
42ae9b87-a6c6-43fc-9952-ce84e5559e6d | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
4db87775-266c-4b75-9591-9079baa6d8a5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
54c59ffb-9223-4b48-983d-2196acdc90fa | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
375ab800-c410-4131-b9c9-8fc3fabafa40 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
2fbda864-7b21-40d3-8a25-6992afe2fb9c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
393d7c17-7e53-4b80-90c7-9e855dff80bf | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
2abf4712-2189-4708-8a18-51848df4112a | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
240b50d4-c7eb-4bc0-a676-8a16bf2ea521 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
d6ca7524-6261-4ced-aa07-dbd39ab49a16 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
d3ebeb17-7ded-45c1-9864-239f5465c1d6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
d3085b44-6db7-4998-8f42-e7aa173344a5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
d041f2d5-d22d-47e2-be2a-89c5239369f1 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
dcae8831-43fb-4edc-8eef-f44370eef726 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
eda784c0-6fe5-44e1-835e-f3a702b2e559 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
f535d0c9-2c43-4f48-802c-066fbe4676d0 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
f44fb34b-0e6e-4c9e-afc8-13c2ef973133 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
f35668be-83fa-4190-9161-8da3e5ede8fd | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
bf414139-c891-4a38-8a27-c96b547b8ff6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
bb854659-af6f-4a5e-ae8d-775c1b200a91 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
8fc0ecc6-5811-4fc1-8b13-4d4bc637f719 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
92955c0d-8f91-44ab-84f5-dd61971d297c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
aad3c9ec-80ee-4d6b-ba65-99a040d897b6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
abf0df36-36dd-4d10-a1be-dbe52a03f3d4 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
a92fdd03-e53f-4461-98d2-fda5083039e7 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
8f042e4a-6974-41d1-a522-8237c4793bac | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
fa9f6063-133d-495c-8d5b-dfe8a4f89622 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
6fbe44da-810e-43c3-ba9c-19560823a653 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
a566bea4-f8cc-4c9d-ad0e-52f458024ac6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
7a4ace39-6521-4a1d-8c08-40f0a0d9918e | Pole | 2 | Transmission | 2020-09-08 | 2021-09-08 | Level 2 |  | 2021-05-10 | 2022-05-10 |  | Kingpin bent sideways on the angle
41e953e2-fc58-41c8-83a4-045ef44bab7e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
4d07c03b-e33f-4224-b4cb-43d894302b47 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
2b4a46c4-f79c-41df-8856-36bf667578d5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
2c94f8e6-2da7-4ece-8f84-b8bfd465d47b | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
55a7ecde-57c4-4e64-91f9-102c42ac961e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
78f5ca16-6f8b-4ae5-96dd-843cb92aac15 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
19a5b9fc-749c-40a4-948e-101072e56771 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 |  | NULL | NULL |  | NULL
15f5a249-a566-43ff-bac3-d50aaa28aaa2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
476fec00-2b69-4167-a662-f4f309809ea9 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
0b3484ec-82c1-4898-b34b-c221ee045f70 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
3a05872e-ab72-4941-b98f-0ab8e17e087a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
73270fdb-d3b1-44f9-ac89-01721fc49d3a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
66a86bde-102e-4e0f-9ee0-0de3d662e805 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
2bad7dd0-0984-4602-9ffb-7fbecbb194dd | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
71e6de20-9815-48c1-ba65-939bb5bc05e2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
007fdac0-cb4e-4e37-90d9-3a3349f9ebd5 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
07f6d1d4-a745-4314-bc68-39428f89bd87 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
dc2bcdc5-f3e3-42c0-9847-b44bf745bde1 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
ca5b430b-720c-45a8-87b8-72a944b0ec2c | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
cdc01b4d-b15b-4e32-8681-7eb967089f58 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
bfc4e19a-ec42-4224-9b83-9793801b6ce0 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
ad4610f3-cdc8-48bb-b50d-f1036c8ace75 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
ad86ba97-47ad-40a9-a66b-401cf8a70f89 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
a494f653-fba6-4b1b-bffa-568c25c45f58 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
9325734d-7db3-47aa-a039-385bd47c9ecc | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
96ec0dd6-0c31-4ace-8a66-8d06853c2d85 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
99f8a735-991d-4534-a5e2-bf46e44e9bdc | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
9bced209-5a6a-414b-821e-fc1df9483d55 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
bb4f430d-0792-4719-939e-2f40c5dc0d94 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
b14978a1-ae9d-4b9a-871c-22de517726e2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
b88b9f25-860e-4866-9055-904312608291 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
c351f124-b84c-4420-bf5f-1e11a6ee13f7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
c85d5613-8f6e-4bc6-87e5-a1c7252f5bd6 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
b50780e8-0311-4a48-b639-02a7f817676c | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
fbb628c3-0e1a-4128-937d-d315aae2ebd0 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
fcc9ee67-7cba-471b-ab96-8d89f84a73f8 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
e48c593f-e666-448e-9885-7b5160303671 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
f1c8bf7d-aad6-463c-9df5-6e7a7efe2ec7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
7bedcf8c-be74-4f77-a8b9-8050fe29473e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
6d30dc64-a57f-4fa5-a18c-87172319c6fb | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
b723812c-70f2-44a0-9c8b-e9c4dc0cd642 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
b6678cd0-091e-4dab-8177-3772efc3cd9a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
19fba032-bcc1-45cf-b87f-eb4ba2c174e7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
1c655b60-d492-40cb-9257-6c92d764b412 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
3789f0d9-5a8a-4ce8-9e9b-c0218362de42 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
8735d8b5-3937-4730-94aa-e7f489ce9e84 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
d2b7160e-789f-4a4a-a680-001b77ca3dcc | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2 |  | NULL | NULL |  | NULL
d9337983-775a-4461-beb0-697ac09c5a05 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
dda1f78f-6c90-4366-abb5-ab36e6526399 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
e1c723df-5942-452e-a8e4-5441e4ee90fa | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
24e4529f-9728-4a4d-9714-8f81c6853de3 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
11ec67f5-9c1e-45a5-9686-2e5d750bf4bd | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
10b04f77-b488-47e9-b35c-4b311c07eff7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
aefee700-0616-40c7-8795-c0b7a625f74e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
879fb521-a0f6-4a66-815b-12940472578f | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
385a498a-f6ca-459a-9057-e294cf77139b | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
3b971442-07c6-49ee-a7a9-a9f1e1349e29 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
3af34345-9d0e-48cd-a463-4f774261f162 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
3d386e16-9cf7-4545-a597-58fcfca2fcdb | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
353bc8c9-147e-41e8-851b-d03064a5c56e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
54b5d292-9787-4c8a-bace-241cfa6831b7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
58841f2d-54fe-4296-a20c-cbe15fcd1b56 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
5a2c25df-c168-43f8-a9dd-bc41d7455e19 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
77196ef7-113b-49a4-a25c-5c97513578df | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
7c187c63-4ac1-40e4-bfe0-2f31ba9ba143 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
79818e87-1936-4878-8dae-4019320e079a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | NULL | NULL |  | NULL
82f158c8-a3a2-47f3-a057-1cf7cc7f5983 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
71d5542e-7e9c-42cb-826e-3db4bfa9bfdd | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
70903d03-db04-46f8-b114-b595047587b8 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
69c6a510-4a23-4767-b433-56414a4a8f55 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
6f71e2c7-ce89-40f6-bd18-e67d501c6dec | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
435fc398-26bf-4571-9a80-f68662556def | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
30b094fe-0d15-42f7-9e3c-f26374988b93 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
3eba58dd-57a9-44cd-b792-ea6d6ec2a51f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
3ddd2f2c-3e80-400d-b3b1-dd632ace2c40 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
407bf218-0e81-4691-abed-136d398a3e35 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
10c84829-41c9-4047-9d4a-16636a3128b5 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
19e12a14-1a05-45af-b0e6-954e28c9ea70 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
0f2ebcad-ecab-4290-bb06-750f1bd97f51 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
08cc3064-e8d3-4142-a001-61100fa7252e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
24a52811-eb26-48a2-8e7f-238867955863 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
28e65c12-9e2e-474a-be83-454ac367bf56 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
e19acc34-e06c-406b-b384-c461968b757f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
e30174c1-5673-4617-8c30-481419c386ea | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
dffcc6e1-3005-4831-86a9-1b5d07ece2c6 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
d7674af9-0fc9-429f-8564-bab04a1bd0ba | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
cf928c1e-e5fb-45d2-adb9-787f81497bb6 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
d6bb383a-d6c5-4757-ac41-cefb820d7c56 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
d5fd6047-4915-45f6-b2d5-9636c87fe220 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
4010651b-9a16-4090-8425-5a10fab00e12 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
3b2f696c-1736-4687-b6f2-4192915f631c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
26a5a473-a5f6-4562-b8c4-1f35128adf8c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
1dcb4be3-30cb-4828-9ae5-14b8ce742746 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
864c79c2-b840-436b-b20d-132d0d4c14b9 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
8c52d151-6226-48f9-be80-b4d18df7b4f1 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
d0cfdcf9-12d6-45d8-9dbb-79f957841f13 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
e52524d3-0a65-42fd-a7c0-f408d6232394 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
ef2f3830-8bdc-473b-bc6c-5d5e3c0a2257 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
ef093c28-1799-456b-afde-e8118635aeba | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
f881a56e-ac93-4cc4-97a4-3d2cf6f933e7 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
0c3dbf29-5c48-4190-9f13-246d14cb1e4d | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
e8df1698-f47e-42c7-9331-be67c8b7ef86 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
cb2a11f2-d208-4ee7-8dc6-dafde46aface | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
c3f88970-c8ac-4350-9225-a98bb8ba1c5f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
71f40119-bc71-4064-8e99-7f18a6a2484c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
b3787423-b15e-42a0-8144-eed040a1464a | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
b4b7ef74-f0f1-4e35-8f7f-25f368e188b2 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
445468da-5be3-436a-9ef1-8a8b34522f3e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
96d21b30-8e4d-4aef-b099-2cf7ddac941c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
2dd013d8-8f60-46a8-a298-a040d821d64d | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
06094732-0d28-41d2-af3a-7302be409143 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
a8916749-cc5f-479c-8804-e50c7dcc4268 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
8bbaea22-21c4-4ad2-b7c1-c4df7f28f134 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
bba20c57-5a90-4bc9-85ac-9f1c5d3e7f1e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
5a2f144b-7621-42a0-8ea2-574ab12133cd | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | NULL | NULL |  | NULL
07069fb2-5304-4444-99d6-5b165010b9cd | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
246e587c-ee06-4d07-9bb8-17e62a8b9e48 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
b777cdb4-363f-42a4-828b-28109ffa5bef | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
c20fba24-b1c0-4eee-b816-d239cf852423 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
c9c01a04-41b6-46ba-b733-675fdca5698e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
9ca62d32-b106-408b-860a-11bbfaf6a79d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
98a5d338-02aa-435a-be64-3b77bcfdf4eb | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
dda6dcdb-915a-44b6-b01f-b4335150818d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
dbc0d419-3c41-4821-849e-7c0247f230e6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
00be9e54-14e0-40b4-963f-783681085ee5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
a87b6f9c-b48b-4f20-8c6a-d5d56bc572f6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ad0dc710-e286-4ca2-b190-7c54279903e9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ac2c3a92-5048-4329-8111-746b82aac626 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ac70b546-3509-47d4-a30d-da199e16d0eb | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
abb8cd0e-9b02-4d20-93ff-7d95cb1af307 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
9d979115-e9fd-4210-b01f-9dae17b6aef6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
a6bb3f46-0dee-4029-b1e1-915f491d80b3 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
9020629a-ccf4-4a82-a5f7-87fd81f23d2d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
88530dd5-6868-4f87-81dc-fd0022eea835 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
8601578b-c58f-46e3-a0ca-0398c6bd2fa5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
8e2d50e2-fe17-496c-ab82-7e0cfc9925d7 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
bcb3a97f-456f-4489-8141-276490866959 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
bbedcc58-d59e-40b4-b5e8-e690f94981ff | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
1fc849dd-2451-41a6-abdb-fb1049b05b14 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ba9b8ffe-4c61-482d-a9ad-d2f19342f84e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ae8fccf5-3142-4a3c-bb42-11af8844d968 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
c211d9c7-f71c-4c80-8ec6-a6c53286dd0d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
7a2f9074-de47-48b2-a9c5-a81414e10b19 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
c976e090-d0b9-4e22-b331-d72dd6d7e01f | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
f8459cd4-a447-461a-9738-f47a8fc3b581 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
d153fc80-566f-4787-b331-8f300c39f0bc | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
f51985c8-cb0e-4b2e-9da5-308ffa27e25a | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ee54049b-aeba-4f2a-9c13-67ecaf4a25bf | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
994f5a5c-4f3f-4179-8c5c-7bda58b75483 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
c0331e2c-fbf5-4cd3-b147-618faa155e33 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
c01d86e4-cd0e-473f-ba4b-7ad4812a5047 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
eaabc698-88c3-4daa-9155-d77e053d1d86 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
ead94f8c-f29f-4fb0-840e-10878e1ecd49 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
8ae3071a-7787-452d-8866-325ddd8b4d2b | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
8b23e39c-cc65-451e-9eea-f2d1baebedba | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
53b83bc1-c945-4103-810f-e103e07c8880 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
201df0c3-44ad-4f03-b2a7-6fd703227a4b | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
0ae4385d-8987-4a51-89d9-220c22a9d2cf | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
227076e0-3522-4396-a1fc-fd3126607bd9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
312028b5-da46-43de-b246-beaa87f8a2a2 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
2036f882-4de9-4ad1-ab93-cff7634e5d35 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
d62b3434-70fe-47da-a47a-1a462d9826a4 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
d8b2a13f-b851-4dbe-b751-090c379670b5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
94b9512c-28e8-4d4b-85f1-f86a654b30e7 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
dd7186c9-f289-460e-9a8c-04af99402f0e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
1ee99fdc-4900-48ac-93c9-1998500ae93d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
05de68df-cb14-47e4-b564-32e1008d89b9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
0dfc1b39-c2b9-49e3-a640-e18a4609bba6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
0cebb518-40d5-402a-8f70-0778e1139389 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
0bc962f4-7e68-4ead-a677-b7910bf77c62 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
17c1b3ed-698c-446e-b6a8-b17b92eaf191 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
17c155f4-c258-40b0-a588-41e830848475 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
136576f3-067c-4c70-bc58-c3ed1d828cee | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
046fcf7f-3e1e-4a86-9129-9ff828622dac | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
38d52519-20ab-4359-8758-f701609e7a82 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
39ffb9a0-9517-488b-bbb5-9261d40114ae | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
2fedb42e-f08d-41c7-bff4-b6cc6791b7ec | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
32320a52-aabf-4be4-be8f-7ca01287a010 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
50a00ead-c7a9-4a04-92ed-ac72fd7b4b30 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
69b36e18-d30e-444c-9569-d89ae132554c | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
66efadb2-d4e5-403d-8927-29a942926aad | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
632a2553-610b-48e4-8022-8a1d554914f1 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | NULL | NULL |  | NULL
61f41eca-2114-4dcf-8232-a3559f12b6ae | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
6774d447-f696-4a90-8325-f3ce1be506ab | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
6f00bbce-6bac-49c7-8616-27d9b0703203 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
6c4a54ba-d370-4451-9756-d9a3f5a7c0f3 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
70b0829f-74ad-4468-aa52-12cdfa06d7c8 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
7220c249-f551-4bf2-ab9f-fe4038e72af9 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
7553da92-b5a5-4e3a-8e40-acb6726eda82 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
734c6e77-d2eb-4181-a3f6-35dac2b83043 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
4d1cf6c4-cdb6-417d-9dbe-b90a5efeb6d6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
4e939279-f832-489f-948a-41ca884bc7e4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
4b06414f-8076-4c60-a1a2-e8805922d95e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
38946370-0838-4111-be8b-cf241ddf1c33 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
3f4d3ec9-2c51-4acb-bb84-d4e115e1ff84 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
163e8a9e-3a5a-43f6-9d4e-1ccfba73aacd | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
0c319c12-23a2-45d7-be58-283f2dcb12f4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
06b0d8f4-a9d1-49fa-91bc-74efe51457ae | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
21654e92-310e-4a09-b165-ee32b6bf795d | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
1ca7a044-c332-463d-a98c-6b36b1fc90b6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
257aedf9-3c0e-46f8-beda-b1beddbaacbd | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
25f5c736-d551-4930-8e41-51a1cda4fbfa | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
dc297714-4f0f-42c9-9348-412898baadcd | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
e78bc320-9752-4aa7-9564-47813cd6fb87 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
d8f1a664-5636-4020-995b-4479eb02dc7c | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
da72b4fd-0ad9-4747-a5b4-6911d648762b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
db063571-bea5-4468-bce5-2f3c382a3158 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
d08c887b-7e80-4488-979f-3e6014235aa6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
15cf07a7-56d7-497b-bab4-84660d8b852a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
b47a14d1-105d-4c69-8952-a08f3262052a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
edad180d-af49-4d38-9971-4391a9ce1299 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
fcd9b46c-3491-4c49-b1c3-aeec9f576b91 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
fc88c135-f63c-4ca6-94f4-d22989f0e019 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
c8f462f4-91d6-45eb-9a2d-153a801bf53b | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
cdf0ecfb-1a7f-414b-9639-22d8cb3167db | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
cf10adcf-7179-41eb-985c-19f1af5d42bc | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
b0de87ba-e3b0-4f4f-8d06-76a3d8c60f6b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
baf4cd56-dff3-49f1-9400-138a09cb5fb5 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
be1a67ff-9ee5-424e-9c65-032689bdcca4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
8b542ee7-b9d3-44f3-ad3b-f5eeda3cc86b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
872a3935-9cd2-44bd-b21c-5d4738959eb4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
9f9043e8-b8c5-48e3-bf62-6239c569e427 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
a269ead0-de83-4d7a-9aa7-0ae62cf741e9 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
aadae53c-71d4-4b7f-a582-a31bbd79c427 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
aeff464c-7fee-443d-9091-78b67a79b8c0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
594502b7-18b1-4f3a-9d74-f35218e7790b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
88fe2232-245d-4538-a6ce-4b34275cf0c1 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
ff3c09cd-251d-4306-a517-6d9082c544b3 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
f924a1a0-15ac-423a-a941-724e10b92eb0 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
fb3e4972-d35d-4610-a425-83779eaf94aa | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
cdfba419-7c3e-49db-8f2d-88f8b2238cd0 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
d208860b-fc78-4c95-8ccc-2a8d4178954e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
d49a18d4-bfd1-4509-9a62-daf135a843ad | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
d3df4e29-eb1b-4e76-8f19-8744e29f940f | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
ef23e86c-4acf-463e-a10e-e3f74c580c3d | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
e3e35637-ec93-4ea9-a3ce-851c60d10b8c | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
e9c96776-7433-41eb-a7a3-4f5fab9fef0a | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
e8505b70-dcf4-4dd6-922c-2ccaa4bb6d79 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
9a02260b-2a44-40ce-a817-7a4384261c63 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
9990b478-c4e4-4ecd-849e-ebe907e73454 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
9155ac75-ca35-4712-b5ab-146830acb411 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
cab342d0-2bef-4463-8368-1aa5d5ccb4df | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
bb76c009-be7a-4bba-a483-da41b3743b91 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
b4beaee6-2627-423f-90de-1e1e9d57a0d7 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
9254e558-b0bc-4f80-a46a-d487b061c3a0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
1691c318-562f-43d3-b54f-4030205c64ff | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
1ac7413e-69d1-4edb-9091-6cc19eef7c55 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
06604983-fa04-4aaf-be86-ef07b43fc7b0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
06755211-ab07-441e-9981-3b4edef33865 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
0712ed3c-753c-4061-b5f8-2836f1c77cef | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
0f07545b-e55f-4d04-82fe-3cda2c6ae59b | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
66e156d8-e695-4d11-816e-f899d950c393 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
4055c402-0c8b-4bcf-a47a-21cd851fbd60 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
b5e91be1-bd32-47e1-841a-32dd2ce308aa | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2022-03-01 | 2027-02-28 |  | Arms are not in need of repair at this time.
e27a9e6a-264e-4d80-bb44-f0f3e4ec453c | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | NULL | NULL |  | NULL
746d3295-42cc-44e6-9475-a5b550153674 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
3d9319f3-88c4-422c-901b-4cd2e2dbc9c0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
3db4a227-beba-4a17-bdd9-e48ca6425e88 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
3f26fa99-0f48-494c-885e-9a95a886e0c8 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
3ed28385-0648-4977-87a6-65a7d7a1fe66 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
16404d5d-b241-4eac-8015-cc30df8852bf | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
9234af58-456c-49d4-ad61-d21a411a6694 | Pole | 2 | Distribution | 2020-09-14 | 2021-09-14 | Level 2 |  | NULL | NULL |  | NULL
201a9dc9-63b6-45e9-ae6c-9534f67456b3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
1c669c99-126c-4efc-862f-91480eea31c5 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
8aed9894-cd25-4c07-a7db-76de1b4ae368 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
a3493de1-a56d-4952-8ae9-b8383a85242d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
a81f8630-108e-4a47-ade7-080ef714b268 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
d0e4dcb4-f883-4a7b-b998-7e882a986b74 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
cdec7f9b-9445-4227-b217-c1691deef7fb | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
fc43f010-3bfd-4a9f-88cf-e50d24db8908 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
9f883c68-681e-4422-a6b7-139e5c86449d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
a51abbcd-cb0f-49ec-9cd1-db12da4b3f32 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
9f774194-b8d7-4a48-9767-09e3fdfafa1a | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
a094e5f0-2dda-46f4-87b9-68b3aea4666e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
46a0c114-b7d3-4a0a-a855-772da5c09609 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
83a8c1c4-e015-4089-865e-e4daacbcaf66 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
96ea5888-fbb6-424b-a049-5adf718be119 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
983f8ae9-03e1-49a3-b856-45d5f93c6135 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
984de1fa-faed-4291-919b-7e77f6b01246 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
9b827a8d-2e06-4358-9460-25ffbb47fa92 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
be8b262a-684c-4e47-9bdd-f065634ae952 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
be90295b-349a-4878-98bf-33a2a2d7ec67 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
ba4c3707-710f-40c8-b5f4-9bdab567945e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
c67d3a4d-f21e-4d7b-a899-bc6aad27a9be | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
c55a605a-ed89-47a6-b36d-2c75c05fac98 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
f86a644c-9338-40d8-92d2-a1f3b75e6a8f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
fdb3aa6e-3ea3-44f6-b303-5f01c602ff79 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
ec50b6a9-9fe4-45f2-a5bc-45b6b71b6477 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
fe7a4988-1ccb-464e-814c-a7a524d0fb56 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
a574af9f-d02a-4e64-8ea5-08e12ccdde3b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
e827226c-a359-471e-b274-de887a36c47e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
eadc47fb-a021-4234-a4e4-6b277b3a7e2f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
e159490b-60f8-42ca-badb-3f026dd704ee | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
c55a2456-6b93-4050-911b-48f71a4c3e8d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
daef9cc9-1a31-4b38-b101-652e946f8b70 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
d3753484-90c2-40c6-aa44-3ca624190873 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
2ec02df7-19f7-410b-bfd0-9af776299377 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
3268f684-b4c0-4caa-bb35-a6f7a291a021 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
1ae76144-8199-475a-a238-9c5c36d35793 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
1f01ee3c-8b7e-4501-9d96-6e8a76ee9633 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
d02ad81d-c36c-4f03-8446-63f38b87a1a0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
d2a9aa10-7714-47f7-8cfc-652b51da1d80 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
dc21539b-4d1f-4990-8084-407e0b5d592b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
d8d3ef4d-b13a-4c14-bf38-864feed58533 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
d722d7ca-d9bb-422a-a8f2-6ae5321c69c3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
fa0f8be2-9eb2-4510-b8d1-8f2f636f6167 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
e6cacc72-dfbb-40c1-a08e-472b82fe849e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
e4fd0d7f-e763-44ab-9e26-9fc35bf3a22b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
df9bfc8b-c32a-4240-b8de-64a94b1edba1 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
289c49f7-0840-4bc0-a318-af0365dbc828 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
2ccd4649-4bd2-4208-ab69-7024a37c3a7e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
236987f1-51e5-4077-aa3f-567e317677f4 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
239ac3a8-1ac8-483a-ab08-bc48b883da89 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
21c27a95-45c8-4ae3-8cba-8a5ce930180c | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
142f4922-2844-4143-931a-25157e0c6c99 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
10054db1-627f-4676-9177-bcb9cd077701 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
00eaccc4-4087-4125-ba38-91a7ed63a24b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
78fc88c5-a130-4294-8c06-631a641c9794 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
3a7a4299-3220-414f-859f-6d963ab6b87c | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
30ea35ba-82a2-4395-b5ca-23767c9f4cff | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
2f940277-22be-42a7-8834-28da9b620be7 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
2e8b6799-1d7f-4dbc-90c5-e1a2916a9c67 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
37b626c9-790c-4620-8ff6-503f9536079e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
4a08e08d-85bb-4562-88c5-937f0c2a8ae0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
43e21dca-aab9-4819-81c9-33bbda26f39e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
6e743dcd-99a5-4a3c-8223-2ee7bd1c376e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
72783e60-b2da-468a-b64f-240f165d90a8 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
714d193b-5ad9-44a9-9ec8-1bd95146278f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
818f8593-eea8-4d65-95e4-707b548ab5e2 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
7f98a276-aaef-4e4e-8020-a5a6b515e965 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
79ff81be-c137-4ef6-b8fa-88490cc87c68 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
7c387807-4864-49b9-9be7-eaf0a5c3dc11 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
6b5a8c21-5912-495d-a809-0cdd73a5ade3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
679c7247-166d-4cda-8f68-754f0b779935 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
666fb3ed-e20d-40f0-8b03-913de4682d4d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | NULL | NULL |  | NULL
65e3b1da-37ee-4ec3-9bd3-4bc859c5a9b5 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
599ccb56-6f87-46da-9250-b2c7aaa4ba8f | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
5e644c34-f461-4598-a822-2f8d4f2319b9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
7eaa1565-1ad5-40dc-ab59-a8217d453bef | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
802c6196-7321-4988-a5a4-70c294cc4944 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
7606eb99-8600-4603-aaac-200e22ef804d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
756ee04b-8cc6-402d-a244-88780a075a63 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
43d17037-cffa-4d8b-9374-3b091af9a85e | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
498bdfc7-bad8-46cf-a701-ea01bdf5a587 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
477ae48d-10f0-4d68-98ab-8fa0bb030f8a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
3075c30e-85cc-4db1-8118-945536b7b927 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
107ba6d0-e1b6-4f10-9919-f37f2e208575 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
10c9ccd2-308e-485c-a558-0008371562a9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
14b98f8f-0c48-45db-8853-4a7482454431 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
067e4ac0-886f-4ac1-af54-32a63eab9b42 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
07fca404-4dc4-44f7-a404-09d8523b587c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
1a6ba33c-00cf-49b9-9043-41b91d4bc8e8 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
27be5e51-b051-440d-af43-b3cb806b36c1 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
9df6dcd8-3dcc-4589-8ab5-7c5e81e01996 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d737cfbc-e4cf-40aa-be91-063577e7f4a1 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d32c1bfb-84a2-43ff-a577-b81e9940f5c0 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d8ecff38-59cd-442a-84a1-36f2be89cb4d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d138fc4d-6fd1-49d0-8f13-6968a31b9586 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d13f7b66-b894-4757-8c5d-087da3ad415c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d1796ca6-f922-452d-890c-5dcf6bca29a6 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
d4a22035-e959-4264-9207-3c09be3820f9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
664e2e7a-b144-464d-af7c-d1132438b573 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
78972a0d-4932-4116-bc8b-092d55069718 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
43a896f4-c675-4bf8-9b67-dd69d08d987a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
df909596-d684-4343-b007-72b96d93e505 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
69790a6f-42f7-41ea-86dd-965fae409c41 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
e561d49f-34b7-4e88-ac3d-bb9024d46f51 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
8d92b1e6-efd4-4596-a0b8-518b9710e5e0 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
e506a92a-c8cc-485e-81e8-79a8a9c1cc32 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
8122da08-bc53-4fd5-a516-05fbf08d7e43 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
9cb6165e-f9d4-4165-a703-cfd2b5194f41 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
b5028673-0f01-4209-88bc-77c2e275cb10 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
3cb5e2a6-a19a-455c-bb52-4f0aecf94ff8 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
f7cbe413-6fd2-43c6-8a6f-d6e1ea7b3266 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
f7141845-a515-4116-a3de-da48789f83c9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
f1b8fcf7-c299-4f9b-84f1-75bf884592bd | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
f15f43c3-5a0c-4503-a204-6a5612dd845b | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
ce59f6cf-4f6b-403e-8916-8d871077ed7d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
bdc962b1-fa7f-4ca7-bfe5-8d6774347587 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
bcb375d3-66d5-4288-9aa7-41776c6ca9e7 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
8f90750d-0075-43ee-8c62-dccc27d04d6c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
89686f07-b95c-4cd6-91fc-00d97765fa55 | Pole | 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2 |  | NULL | NULL |  | NULL
d7dbcda5-3b07-4167-a103-e2395c77a380 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
ec7d63bf-2694-48cb-b862-a7141a854db5 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
8eb5ff86-91b6-440c-89ec-7c4dbdb06fcb | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
b886b911-20b3-4066-92e3-e8cc20675f44 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
c1720bef-4566-4d2f-8a1f-91269baad7f3 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
862f2dd9-360a-4444-8aef-b2870a42807f | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
8ae19aae-0071-4595-81dc-43884931423a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
90624ba7-6762-4402-9406-0b3d8e20251c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | NULL | NULL |  | NULL
ffcf7ca7-62a9-4256-a8b9-f71301012fff | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
b63d98e9-25ac-4df6-91ba-2a5e0883425f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
b7785d70-15a8-4224-961e-d2173cb94f85 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
d572c4ee-6734-4c64-9c51-c990f525caf2 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
908b1516-b4d2-4365-8a8c-d8fe544c1598 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
911c6faf-0b65-47ec-b1bd-9a34161166c1 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
9128dc83-f3a8-4507-9eff-afd05f5e9abb | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
92dd6c1f-e942-41c8-ac60-b0b426f174ba | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
970ed103-bd33-4f27-b406-6f87814c3a7f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
a1367e0f-1f7a-455b-9696-278ddb5bab36 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
aac668a0-e890-48b8-a57e-20028e3bc185 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
bd6e233c-0f91-4150-9600-9b03016c7374 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
afe872f4-e448-4231-ab4d-b3fd5ba0f220 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
ccfe3f15-bc48-48cb-8bfb-f355f95bd249 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
cc216c78-a960-45ec-b0a8-7f4ae515c58b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
c9317a3e-a7f2-43c4-9b07-c51f6793da44 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2 |  | NULL | NULL |  | NULL
f79fa4df-f779-49ee-8bc9-0b1948b9a3a9 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
a1e65cd2-52d2-4e57-8400-2591b1046bac | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
6e3025f3-316c-4dd5-9a86-76dd587a1607 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
72fd69f9-5bd4-428e-90b4-a7b4b42f0630 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
ef08833b-4fa6-4df6-bfb0-10e45e6a8bfb | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
e2719427-d0b9-4433-b28e-d9237ed649ad | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
7c1075e7-6c0c-43c7-a567-eebe29dc10fd | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
e6e6e4b0-56dc-4017-9280-a0cfa7a65284 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
25d3161f-6f1c-453b-be04-853f01ed7245 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
1920283a-ab84-4304-ba1c-b2b7e81a407b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
16f16a53-c628-498c-add5-2cde6af5614f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
00e53c6d-3ff6-452f-bf1c-fd95b05f1d8b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
06c91f96-2882-44df-a127-d9d7edb056e3 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2 |  | NULL | NULL |  | NULL
2faa00f9-2964-4f78-bdfe-0de414ea9a6a | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
37b978b8-efa6-4d26-95e7-f322863fdacc | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
3e69c394-2d6a-49f9-bf43-05ee6b6ffd72 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
591f3239-7835-4764-8b38-ddc7ed924b35 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
582ff41a-00ee-4ba6-90a3-f21790ab6d84 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
6fd0ea63-d3ed-4f83-aad4-f6ae44c01438 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | NULL | NULL |  | NULL
81df3ead-c173-42c8-92ae-29a5cd1a91f6 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2 |  | 2022-03-07 | 2023-03-07 |  | Pole cracked all the way up, already stubbed
79d02709-cf05-4575-a30f-190b4f420571 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
72c8b212-8d5b-4925-b63f-88ab55c0a1bc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
518b01b3-f0d1-412c-8fe8-597620965eb0 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
4998c980-b7fb-497c-a656-e76fe594a783 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
07f7bef7-e317-4cae-a372-0bb3492bed6a | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
260619ef-6aad-4159-a461-1062dbb9ed12 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
2a73b142-fce7-459b-b03c-3cc306567b45 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
c500eb9a-3614-42cb-a1e6-1f63f4815c4d | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
d66fe9e6-429e-4b7f-a14c-50d763735cbc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
4a93adc1-e7f3-4f81-9808-16b9b62a52ca | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
408f30e8-6d9e-4f0d-88f6-f11a9f89dbc6 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
552207e6-75b8-457e-bd52-b416f5780f45 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
f56d600a-0a69-4468-aa43-2511b6ecd3fa | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
f65c39d7-b294-41d6-8e96-30413e9716bc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
c6a77b7f-e804-4183-8913-475ea4635186 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
bfe9da00-69bc-4548-8219-ad57ae7eba4c | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
a349cab4-f321-487f-ae80-4e56731d67ab | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
9bd6ea73-c0f0-4846-9bdd-7f9c326bc4da | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
8db86714-7cd0-45a4-8838-b01231ed8491 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
84826027-e0e4-4e4e-86dd-e09c269dfb50 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | NULL | NULL |  | NULL
84740b3a-385b-4615-b2fd-0b49f99c79c9 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
87a69f7b-e368-4bb8-a01b-bb63429d8fff | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
8a22207f-5436-46b6-9d74-fcfa85b29d56 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
963c12c9-7b0f-467d-9c58-cbf6e88b5f04 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
97c6bb25-ce15-4cff-b3f1-b485ea909282 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
a29d1750-c86c-418f-a254-44d62cd85908 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
a4c4ca2a-cc13-4985-91b1-0f395446db77 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
aa2380d3-8eba-403f-b0c1-3f45abe71f18 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2021-04-16 | 2026-04-15 |  | Need to install split bolt at top of pole, pole ID installed 04/16/21
a87a505c-9c20-4cdf-8222-b72d9dcf5755 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
a7a0b342-c6ed-4b27-8685-0438b78c4833 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
ad0a2c1c-4861-4356-97f4-cb11c9d6134a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
9c0f69e4-5fc0-4a37-88c0-52f7e74af755 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
abc60e15-37a6-47f9-8211-e278b3351738 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
b01c07ed-d120-4b35-97ed-2bb63026fc1a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
b0d549f3-b255-42b5-a79e-09a0f619f941 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
af40d29d-b24f-444d-a48c-12bf5593a315 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
f25dc6da-ad0f-4012-9e9d-617087ec7230 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
c62b4dd9-4343-4492-83c1-667c5b157d80 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
d5385b7e-bf12-4cfd-944c-8ccc97c81c38 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
bbcb524b-b380-4a3d-922d-3975149be33f | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
f3b94888-8879-4bf2-8d5a-f37987967b66 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
b3b74663-4b02-4240-9a7e-879cbff5357d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
e98f4df7-9ef2-402b-9bb1-ca2eea3e3701 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
ce972377-fbf7-4a68-86b4-1ce8cd23b1b1 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
f3ede1de-0f44-4b95-8563-c50ffb570473 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
eb4eb104-f56c-4363-98a0-528a4b632402 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
d507778b-7f2b-43ac-a5ba-548a999bb32a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
d76a10eb-13f4-4cfb-9a22-6aaa31a618a3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
db8dda95-89d8-4d44-9c22-577164cd8c0d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
dc24ed84-4be8-492f-95c4-c286e84eba22 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
e5dc5cbb-8b70-4326-826e-a23fb01cba97 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
e465f5d5-0d4e-45e7-8b49-d11c88f1c759 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
faa36a05-6d01-427b-9b99-8c640ca26358 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
b762f9ee-8b1f-493d-93ba-a5b1a423e7f7 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
0af720ed-a0ee-422b-8ee4-5b43c9d33bc7 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
7f1e6e8f-b861-45e8-b507-f2f42b9aeac0 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
1a22c63e-20cf-4e46-b500-b518ba555114 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
0f6d8585-c96b-4b2a-8505-2ae85c885aed | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
161a6279-0e70-4b64-84c2-ae4db8cde788 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
1481e906-fc04-42e5-950f-5c1bdd2515f1 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
0169efcb-2ed4-46a6-938c-9355f405f29a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
02dd2efa-4a82-40e8-b0dc-a9bac672145c | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
eb13cd7a-4931-4ad0-8ff2-8fc8ba005ec0 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
4be75378-5f4a-459e-b458-0f1d1bbc600a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
42a95ff2-89a0-4cd9-9e15-e1938b7eded3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
4612ac93-3159-4bbc-aa74-44e409c85742 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
45eb5350-c97a-4f5a-a3b5-9ad2ab5dcd8b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
51dc9f81-f4da-4c03-a1b4-289c80803f41 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
563682f3-9b98-4d5c-8687-5e85323f1ea3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
55b091e8-0373-4266-ae34-a990caf18c71 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
3fd0bfd6-afa6-41b5-9c84-60dc6a75914d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
38c95a71-08e4-4b9e-81ec-db4c6fb63593 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
20cb28f7-61d3-4784-a45b-710a7678a36f | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
788f5ea1-9623-487a-9665-fd79e78b3c75 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
5c9472de-c4ea-409b-8b56-c7cefb2b086d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
5a135d5e-5a13-4681-b7d7-0c68a78c303b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
63167f0c-f143-4fb9-a8f2-a780200c68ba | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | NULL | NULL |  | NULL
5f641f14-f3dc-4074-8cfc-f0a209295355 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
67a26434-ecb7-41db-a708-04f4a2e0154f | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
7b282242-ebcf-4dfa-891a-b3538d922efc | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
7f718100-8722-49bc-a879-4a95d7106ba5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
280e46b9-6bb1-4010-9091-ffb217b83c58 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
72407f6f-3629-41ce-a150-e1fccc9ee5cf | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
725f8b5f-df3b-4b22-8c10-0a7eba33af26 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
71349818-7580-455a-91d0-048fd826e4c0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
38081f83-c28e-4b24-ac25-3d45d8cbd2ae | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
53f96c07-8016-463d-b808-94c49787328b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
02478bd8-57a8-4d1a-b6d8-c31b522adab2 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
18f6926d-bf28-4073-82ca-dcf1e0a03969 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2 |  | NULL | NULL |  | NULL
ba24abe6-05db-42c8-ac89-e73092c60d76 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2 |  | NULL | NULL |  | NULL
144964b2-28c4-4443-abdb-1fd432bc0ed2 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
16e75a48-71d7-446b-be1f-c011067d8713 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
0d230900-2629-4e0b-8ef3-951fd826b2d1 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
0c0994aa-3444-494a-a211-fca5f27b60a9 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
064f086c-54e6-4007-944b-398f79d3713b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
1d549433-8f37-42e9-9f9d-1ba386aa5086 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
2c7e8da3-493a-4221-a267-1f7825506d8a | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2022-05-27 | 2027-05-26 |  | Pole needs replacement
26964d70-51c6-4e86-a41c-f71119ecbe04 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
282e9eb5-ae62-4c61-81e0-8b54c6631b9e | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
e39e9540-d75b-42a3-8022-d79d6285dc98 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
ebd4b750-cf76-43b6-a3eb-4b31c0f8a773 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
dce02cab-2f64-464c-8787-ca752d541d8d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
d4740d9c-b482-466c-b338-3e22518f4a89 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
d3609e1b-52f4-4f31-8fbe-b3ffbeb041c8 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
d0552240-ad2d-41aa-99f2-ebc66d5e9463 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
75d1fc85-7755-4b72-bb93-b309d8ea3930 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
4e298a92-46c3-49d7-97ce-f85b1c05dc29 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
870336d2-780c-4d45-8f3a-9417175fa2c0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
eb8b3260-d6a5-4952-8cca-4c2a71e0f260 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
e20d97f5-d335-4f0f-a319-b09e13407e07 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
93082e1b-e7e9-4ce1-89a3-2a9b1944771c | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
d3a05c5c-8937-4030-a809-4a34d80200e4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
b0e14802-6165-4f88-8981-1bf04ed23404 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
7f413600-9fea-49c3-b532-925067d40b87 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
a7fccfc1-f161-452b-a740-090fe2e0d5c5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
3a3ac121-d4d6-4b9a-bc67-e354d823fd1d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
131e8968-d1fa-4c1c-b968-a7793e30c812 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
5f49e29a-51f0-45cc-9982-fb7d9fd98c68 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
4eda5d1e-d599-4a7a-a3ec-b02133a038d4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
ec5dc4ac-6a07-41b9-b61e-dad2c5c9e780 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
381d8814-d3a6-49ac-9848-8e76e63b0524 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
5eddef51-62f3-4b95-92f4-fd582d3511d4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
1b238d06-2938-44e0-a1f9-ae909ee178ff | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
f22e9fb5-b5d8-443c-ae18-be0d32f6fef7 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
f349b4b2-af6f-4d17-b93c-013a76e9ac07 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
fb46d411-5cc4-4e79-804f-728d4650d58b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
af3e8268-2e81-48be-8ea7-bb83170a2faf | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
bdae4cf3-59c7-4b0d-b646-d87e3150b3b8 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
8c37726f-b365-498a-9805-ea90dee7df35 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
c3696ce8-4cc0-44db-a49a-6d1d31802eb4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
c1555915-83f2-4cd7-a767-425ab9a0e932 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
c811748c-f3ed-4bca-8035-d2a263064ae5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
cd3c3e79-6e00-455a-b805-7faa5e05d82e | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
aaab666b-c2d6-4b26-ad9e-771fcb5536bb | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | NULL | NULL |  | NULL
aa8edd9c-7ee6-4212-9687-9bd38fabceea | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
ab03f6ad-35b0-4485-8bf0-efd1aca3b486 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
a24eb6f6-4d2e-4703-9556-06a97fa67214 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
54c8cf7f-92b9-4e44-b7e8-f70dd7ccce8b | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
c41c3d44-552f-4c17-970e-39011f68caba | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
15e24b26-d177-4193-94ee-ad0e83155867 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
5a114bab-ad6e-40c0-a4ea-80e597da421e | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
0e740a7b-7d29-43cf-a0cc-eaa21602b720 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
b932e7be-4127-4738-b0a8-d3d1f11b1af2 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
4ba63b2f-5b79-4c38-8a14-fc6435dce7bd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
b9f92c26-c72f-4180-ad0a-89742a7969e8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
73a70c41-d838-428c-b6b9-538bbf7b931c | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
1cefd6ff-8a39-4ba8-8f0d-813c43084c99 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
c2c9d79b-7d35-4742-939b-0373d22e0fc9 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
d17f322d-79ca-484e-92d4-de702ba0fdc6 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
d8a60def-06c9-4b60-8bc7-28f66a835e5d | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
de17cbb0-da00-46f3-9f93-90d2d5c86ed8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
e09a7e9d-ac55-4c4e-a5bd-0e14245c4336 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
e04b4164-2aba-44a5-ae76-1a7a99b0ca8e | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
e15d998b-37fe-4e12-9cd7-70b3452e2117 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
fc9763da-5feb-4619-8e0a-5bbef2f0a77c | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
2c99cbf7-7d26-411c-8af6-23b9e1158ebd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
22b8e8d0-a4de-462f-a08f-6e54f5c46c1f | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
1ea289ed-b6a2-4f3e-88f4-b140ea1499fe | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
14532269-d714-4010-bbcd-652cd9ae26d6 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
1117d1f1-fe70-409c-83e0-ec926de681d3 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
545fd7fd-e788-4d67-8c3c-2ef4dce14e1f | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
46101885-50f2-45f8-b1e7-a692a1a9b0f8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
387cc8e2-2d3d-49f9-8841-99d9abb071d9 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
3453d0d2-a655-49fb-9ad8-1810b75432ea | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
71e617a2-e939-4499-85f5-9e7210963caf | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
82174148-0a5f-4b46-9191-5bb750438556 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2022-04-15 | 2027-04-14 |  | Pole needs replacement, rotten pole top
693a1f56-5104-42de-a179-77cfc44456fd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
64760a9a-780e-4e14-a944-fc8fb47f47b7 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | NULL | NULL |  | NULL
62b08ee9-a921-4a59-b178-59b0f9970b6f | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
5c7bb953-d9c2-49e9-b1ea-ede13ebc527e | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
6d8a5646-6a38-4ee9-b4d8-ffce1f8eeabf | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
2bd3bd95-1be1-4b54-a30b-5d48625870a4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
d2e96ea3-ab61-40ac-acdd-a06e0b5a4be5 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
c34be656-3015-4e8a-b974-b59edbd8ce1e | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
c00852cf-094a-4399-8968-2ff75599306a | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
ab061379-8e68-42ff-89e2-09a998aab300 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
b00122b0-d174-4c6a-96ff-347b2d312b57 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
09e2028b-dd39-45e8-bb14-beeb43dba495 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
c1a0303f-de68-4cca-b4fe-a1950f6f6cb8 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
967b71e5-a348-4d23-b76c-7ff17325523b | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
8baf0207-8837-4fb0-8337-ef289fd5eba4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | NULL | NULL |  | NULL
f4622cbb-471d-4d00-9b02-87afe135a3e3 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
0b1fc06e-bb35-4fa0-94a6-407136e6821d | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
16cb6f18-110e-47bf-bb21-2b49c863a980 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
6d15505f-1c03-4442-87c5-e139ca184132 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
315893bc-8bf0-4169-9044-290fd14510ce | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
83c76b50-c5e2-4c44-bc14-26eae6d45f25 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
d9b8e866-edc7-4fcf-8651-68ded02b80f2 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
0372d406-43ea-4d8b-916e-baa6b619a8d9 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
6e91be45-74f8-4cee-a80d-b729442d818f | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3 |  | NULL | NULL |  | NULL
6008c623-14f8-411f-baba-30f99e57e83f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
725fcadf-d587-4187-8419-613508848c3e | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
310c89e6-3d96-4994-9742-19fd1f80d49d | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
40540f1a-ba90-415b-b62d-db6f03f4bcce | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
1dae268c-2c82-4f9d-b775-e99d9d9981df | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
19e3ca7b-42df-445f-ad31-1cd727a30780 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
183f7684-fa6d-4cee-bbfe-0815333cf09f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
d466c7a7-3f54-423c-82f3-e7e454879774 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
d3e2c850-037d-4970-8e4e-2b76531ce32c | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
fcca4c0c-971f-4d03-a6af-d299317a3ba2 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
88bf9e5b-712f-45d1-a757-18de6e8a9333 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
90f9aff7-b2ef-404b-9b07-99a10d537107 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
8eac32a1-3e4f-448a-8c52-9391a0b96aa7 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
9bde3b8e-b7a3-4337-82fe-645cfb8fdd7d | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
cac0e953-93eb-4e2b-b842-b7beb4e7fe30 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
c9b77d53-1992-4902-b026-1fa5f36365c1 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
2a6febca-9650-4a16-b64c-981622ad12b3 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
286b3b1e-002b-4299-9b00-12b89fae14ed | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
48c688de-4ac3-44e0-8eae-2028eaed4c5f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
69a6b781-5323-4678-8dce-296e4b8990a7 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
6a208164-8b29-4834-ba67-66f354dc6b2f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
75ac842b-131f-41aa-ac05-362e5fcb22e6 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
7b879260-8240-42ff-a819-d8237f735781 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
50ecd8b8-a11e-46d1-969c-127156a96abe | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
26985cbf-f6df-47d7-bd12-5a9ced24f730 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
05dad096-127c-4b2d-b6eb-d4d799332779 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
f1dfba25-bb98-4aaa-bafa-22ab77ddf652 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
9cd04e7c-24b0-4d52-b0da-4de823c37a05 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
899b4e46-63ff-4e11-8240-3528774fa842 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
b336bae1-4de4-42f8-8342-a75ac26107bd | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3 |  | NULL | NULL |  | NULL
b2569ea7-8267-40f5-bca5-841c9c6ddb77 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
b415ca9a-f0eb-4100-b34e-163e1f51c9c9 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
8ed4feb7-2f41-40d8-9025-568fb267ac03 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
963ea595-4ef4-4972-8113-5d0fe3facd00 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
a68f1ce3-f612-4e9b-adca-504d667a1a3d | Pole | 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
ab23d578-c5c6-4120-bb19-f10d6db7071a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
dc170a4d-fb8b-42fd-9283-5f9b4fe35c83 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
d84483d6-f80e-41b4-be8b-d718c0956194 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
d6e906d6-5694-4e6c-9401-5ff6bd6bda82 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
f56bacf5-2d6b-44c5-a39a-7da8d192985e | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
fbea8a5c-92f2-4a5d-a3d7-97eaaa819d7b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
11b6d47c-3ee6-4cda-8a23-64c1336cacf3 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
0904baa1-e4c8-4efd-bab8-68769a47e986 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
26c29f7a-590f-44ca-8869-c2c4b7b333e5 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
1d280027-04f6-47e4-80ac-48afe986e84f | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
1832dc12-5ef5-49b7-a70f-a4e2725c6458 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
7b2ef357-f3a4-483f-8008-1cd84f5b3a0a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
408da581-b792-48ab-a4f3-51d0de8a106b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
4470a632-25d9-4396-a577-3a6886bf6ff0 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
494375ba-3253-4c92-b4ce-4f13bfa61d7a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
cb5a1e7f-bd7f-4f71-a2bd-c0f2d2b84c54 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
b957c8dc-03aa-4a21-9c89-65b3c3948462 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
ada8989f-4023-4937-bc58-09c6f4260e01 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
97b4e740-f17f-48db-ba20-487b5984f0a6 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
a67a9c0a-fb0b-4c9f-ba60-057dfbe2e558 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
a7317bc6-9766-4721-9b7f-28780f5efcb7 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
863ee853-cd25-431c-8853-a1cd779a38d8 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
f86916e6-3703-48d9-93fe-f3aa0b357368 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
edc52a12-a097-4c4f-8b40-d08bbf974a6b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
f03bc64f-e118-4f33-9bc8-1d5c5ae7eb65 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
09d68a3f-e4ac-4b24-b4c6-b224611c70f8 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
1d4d29e3-ca10-4501-8219-0ce24e712dae | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
2959c08b-2d61-4dd4-b84a-c430ced94c0e | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
0113187d-969a-487c-8333-f82ec1ab6ae9 | Pole | 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
396105ff-5c6f-4ff2-b723-4c0aa1a2be6b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
4b87c4eb-d3d3-4a08-a3f3-001395047364 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
45718d8b-01e1-4314-8080-fe3183110c39 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
71ee2e78-4e14-4a2c-9dfb-96c1442394f5 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
704185da-3454-4160-989e-9fd85c65cac9 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
6f2509b5-adf1-4d7d-b0c2-135b63ff7362 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 |  | NULL | NULL |  | NULL
63e3eaf1-827b-4499-853f-a9ec0b84e3c8 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
63b2eaf6-1c5f-4c86-9fb1-9a2007e4565d | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
5e6bbac8-4251-4cf8-878f-4938327be4b0 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
7ee6f158-f093-45e7-897c-28564e0592ce | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
453ac828-a001-4bc5-992b-d2e535489cfd | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
583a377f-3d93-472c-84c0-1727816b6837 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
3048addc-d28a-48b6-991a-5eadd5fd03b7 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
33026ba8-873d-4ec1-b7dd-00a50d49fbd8 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
234b87d0-7609-4032-856c-432078f2e060 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
12b3c0a0-1434-4a0d-9f64-f79b23cad13b | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
ffa34a39-ef1f-4524-a636-595b49248c0f | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
f8e5a2e5-27dc-41eb-81e0-ed47b9664c2b | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
f312b6d3-ca7a-49d4-bc2d-b0972f9bd4a5 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
e8198807-4624-4b13-b2c9-18813a90ea6f | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
ec92a2d0-7117-4ea8-88c3-58125ed00aee | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
da2ad61b-7116-4fe9-bf8d-16631e499f5d | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
adf493ae-9310-4bee-8bc3-6c1ad88258ba | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
8bbaf5b8-eed4-473c-a4c2-9c4a38c62059 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
88c49d40-5d5e-4730-b4bb-92b017e0d0a4 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
855e5ef6-5b9f-4cbc-a685-611445b321bb | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
b2d8ee65-83c9-41f0-998a-316d649842bf | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
bb10f092-94a3-4482-84bc-724b83061830 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
97c109dc-80ed-4efc-ae8f-a930752a2d2c | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 |  | NULL | NULL |  | NULL
c599ca11-c9cc-4b3b-9b0e-3ec7b84ea11e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
9ef6f2d4-befd-4d2f-bc4e-315154660a62 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
121c6538-9c22-44d6-8b38-635f4ee35bbe | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
991e79e1-42d0-461c-ab21-cbff43d1e652 | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
919e5b7a-6e5c-4fce-abbc-8338266a90f4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
d991737a-6733-4501-8099-57a932b0cfbc | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2 |  | NULL | NULL |  | NULL
db981d8d-c628-4b01-85db-00da6c133ed1 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
d554ed87-db18-43b8-9ac1-02d309f18a41 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
df2a27f9-0f81-4a41-9b07-ab59748877ca | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
c4744b04-54c0-4252-8746-e113b5ec3142 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
09028e99-5d02-4bed-96a5-90b246972158 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
c29e85c3-a3bf-477e-8dac-224c4cb3445a | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
a036e711-0315-4a54-bac3-9b0a629c5e16 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
69a415e2-f048-4f07-a80e-7730dba5bc34 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
30e72115-8f73-424d-8ecc-79214094cae4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
ef5b64ba-f200-43da-8d7b-cfb8d4d0d8d2 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
ee4096df-31ee-4d06-9a61-f0be8e6b9bf4 | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2 |  | NULL | NULL |  | NULL
f18689de-38b8-4474-a6c5-3f927b0e0cff | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
ea722252-db7e-404e-a49a-3cd4e1da035d | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
f44551c7-83ae-4559-8f67-ea8339cc5246 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
de629e6e-b40b-43d5-9a7a-1f02c116e82e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
18b49776-fd89-48e8-8c0b-6d1fdc129e18 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
089f6d02-0269-470b-bf54-6f4f55bd4c69 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
0f09dd73-6162-4d90-b6e5-e5379e8855dd | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
2bec4f63-d4ec-4992-af66-98c7d088240e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
a7cc73c5-eecd-452d-a877-cedbcd85a55d | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2 |  | NULL | NULL |  | NULL
421dd21d-9307-4272-8c7c-d3e1f73b7d52 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
54516942-f08c-433f-9f28-5c853b4f85d9 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
74f4da9b-1906-4ee1-b31d-42ac1bb04bf4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
5cb8d148-fe45-4f79-a200-d18f987aa9da | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
62f13b10-e755-4c35-b337-ef6026af9916 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
6102cc02-baf7-4511-a4e8-285ac03b9361 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3 |  | NULL | NULL |  | NULL
5c6ab85f-c7d6-488f-bbf0-fa2a7d6aa742 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
59accfff-a725-4fe4-873e-d1b51220c0fa | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
6752692a-257c-4fb8-8c24-82ec0b574362 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
78122c3c-e98d-4114-8391-152c3079ccea | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
70823a40-febe-4108-8ad9-70d057ce54d9 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
71446ff4-9909-4f67-b0d9-d8865feba4a9 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
4fbe3f1c-1637-4f9d-8445-4b54b34c90db | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
49d3a1ce-fb6b-4e95-b78a-cabeda51a5f0 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
480c2983-675a-41c6-8f4d-7a6e449464a2 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
3a5b00d9-84c5-408a-b2d2-176951d3dee3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
3bb8cfcf-1147-47a1-bb53-747e552dcbca | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
2f5c0bb0-1200-406e-a1cb-3bcef4c7a133 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
2ba2bcfc-60e3-455a-bdd3-3051b79fd991 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
279f3360-6ee1-4438-9260-b6dea217540b | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
0822043e-147c-4566-9214-9ab66abbbe1f | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
171dae0b-a1e1-4c1c-9930-83cbf65851a3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
f8316d8a-d2de-4fed-82cc-31ced95672a1 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
eef020f1-e468-4325-a884-d2586f2c1dc3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
8a6fdd68-4c2e-4d42-9a43-1f56bde74c66 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
8dcef529-717f-4101-afb2-09d6a7cfcb27 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
ac42d891-175e-4b53-824b-afdc9ba92ff7 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
aad5284f-cf48-4794-a4da-2592de82e896 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
aa8e7ff1-c981-49e2-97eb-4e2577832c45 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
b4467d20-79ec-4adf-a2b9-7766baa4b143 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
be28be52-f91f-4fea-b065-be3ae65a7ba3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
c8b7d356-301c-43dd-aa43-95ef651f88d6 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
cd19da15-d082-4204-9b1d-35b3a4d24fc6 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3 |  | NULL | NULL |  | NULL
ce44f22d-89fb-452c-b5e3-4cdae58eb01a | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
c4794c18-ff10-4f09-8903-663680283b1c | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
8bea36d5-da4e-42a0-8afc-4ff8dd8dd1f0 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
b240550f-360f-47c9-bcfa-7c6639d619e4 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
aff9bcb2-33fc-4acd-8893-e768bb1398dc | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
a6e72fd3-7687-4b37-88fd-607cf2eb3de2 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
9111d2f5-b08b-410b-8aa2-fbf3068e7107 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
d48e861f-26bf-48ee-a4b5-e77f74542ca6 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
d15114f8-3dfd-4ad3-bcdf-d93f58ab86ca | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
8ed7a970-5ab6-47e2-bce3-59bf35b8c592 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
937bceaa-08e0-47a3-9008-73ec1e532314 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
ff3ce20a-11c1-493c-9066-67568265e51c | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
08112856-2b9d-4f15-a1c0-8b39d1bb64ee | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
08fe1380-7898-442a-8092-0642125d5e61 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
05c645a9-cd34-4c5f-b0bb-a00358e1f839 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
24b66aa1-e886-4701-bd93-f52c2188c94e | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
36ec1802-a5b0-4fcc-a0cc-e7ac3781cf33 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
3bf898ac-e17e-4a42-a0de-6dd4c2b373f2 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
409a1c2b-44ab-4c49-a6dc-08e5305f3b50 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
3f357e24-71d9-4c8c-a25b-09b8b09f7499 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
464a53fb-0379-4377-a9ba-2124d4b51c1c | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
70a02f91-77e8-416b-90c8-37f28f13f796 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
783d18df-429c-42cf-bfda-60aa13b6455a | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
6a01a572-5309-4914-93d6-db110c29b828 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3 |  | NULL | NULL |  | NULL
66805d0e-a7e2-41a7-af28-4c5dcf500c10 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
f43e52f3-c885-4794-b45a-fdb4db053711 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
76d9e0bb-037c-431c-b168-cf278af9d51f | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
52b71227-2f78-4064-9510-0a1d4214a2c1 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
fc630e9c-6c65-4728-95c6-a6625fb3a494 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
de3247ce-f59a-4b1d-ac4f-2b9c288080fc | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
2db263e1-28d3-4ecb-8bd7-780d6408c6d2 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
a78d19da-acfd-4a33-b7c6-dc81e657c7c4 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
0c05e7be-3d32-4e62-bfb2-a81a1d2c3991 | Pole | 0 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
e36a2c59-9285-4e5b-9b41-916363ade87f | Pole | 0 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 |  | NULL | NULL |  | NULL
b75ad0ca-e0a0-469f-b3d5-f729f419cee1 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
23624916-6017-4757-8054-d2a71d0d1e7d | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
0f469cfe-371a-4e0f-b808-0eaae1d8f827 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
5c28d58c-64ff-457b-a3af-be2a874f5acc | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
f4685233-5388-4328-8e88-53d5e2f87c01 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
7d8c80a0-cf74-4ab2-8108-1fbd84f60766 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
c66cebb7-58b5-460b-86ad-1da8d1f743c7 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
ab75932b-2c78-43d1-902b-3cbf6c81e4a7 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
bc5e5133-99a4-4e44-b7c4-6223673422eb | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
8b3644d2-6861-496a-8cc9-c17c552e9baf | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
0e8605ca-cf6e-4082-9e78-dc3b6ed24db3 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
0202af24-c134-487b-93f8-d56b5b5dff89 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
23921928-dd79-4922-828e-4525249c2020 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
7d75c011-f9e8-460f-b2dd-782b7ab47cb7 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
576da134-1eab-4915-905d-2ee96edcd332 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 |  | NULL | NULL |  | NULL
3b8c4552-f17b-417f-8b5e-b5134f299bd7 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
35da62bb-89f0-4555-8c23-d6e82a91cd79 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
31efd5c0-35aa-432b-ba18-725735bb42af | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
7451306b-464f-451e-a308-b8a879e2f521 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
0fd03e2b-6cfc-4c28-82b7-04dafb7755fb | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
259f747d-cab9-450d-a73c-bc97decc887f | Pole | 2 | Distribution | 2020-10-31 | 2021-10-31 | Level 2 |  | NULL | NULL |  | NULL
045821c8-1666-49a5-a4bf-e757974e75ae | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
2d05026f-d6f7-424e-be09-0a53a38b5fbe | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
95ddb1f1-d32d-4242-8aa4-4fe7898c177e | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
6328891d-e2d5-47e8-9fce-5ad49d6939a9 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
4a22d034-af5a-484a-80d0-d56cab2fc52a | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
97da06a5-91c6-4200-99a3-80429c15eb49 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
68b79d80-623b-415a-bb8f-e39003edfc9e | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | NULL | NULL |  | NULL
fa93d64e-e449-40b9-a04c-47c9e3a5d44a | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | NULL | NULL |  | NULL
fa3a6a3f-da62-49f4-8cb0-b8cffda0ee3e | Pole | 0 | Distribution | 2020-11-02 | 2021-11-02 | Level 2 |  | NULL | NULL |  | NULL
b58728be-315c-4702-b333-4650a1252bd1 | Pole | 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | NULL | NULL |  | NULL
2ac66b2f-e929-4ae6-a6ae-2fcdb3a43704 | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | NULL | NULL |  | NULL
72f060b6-aee7-4276-97e9-17a602834e7d | Pole | 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | NULL | NULL |  | NULL
7f2ff55a-d4b4-467c-8390-8cde4f3d9ad9 | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | NULL | NULL |  | NULL
4cbd9b67-e042-4eb6-acad-60eebb0ff06d | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | NULL | NULL |  | NULL
30188ccc-6c02-42a6-9593-d4bfab541819 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
3f0821eb-0661-41e1-beb0-ab8f2328c4b3 | Pole | 2 | Distribution | 2020-11-03 | 2021-11-03 | Level 2 |  | NULL | NULL |  | NULL
6fa3379f-28d8-47f3-9075-5dcee0021350 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
73c7aa1d-f3d3-4858-b5a4-7a30e63398cf | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
5aa1f991-42e3-49f9-a448-314cacfe0558 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
242938d9-ea14-48f9-a871-4b0fe2c56ce1 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
18b83043-c444-4081-92e3-17f2e0fcc1ce | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
16c4fbfc-1b2d-4e48-9411-33aa38fd24fe | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
13e66b18-4646-4c68-ba09-2ecfbeea5295 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
fd7a2ddb-6dbe-478a-bfbe-09e4977c6baa | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
fc508bcb-835e-47fb-98fd-b217a0253225 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
9e1c0331-0913-481a-b7f0-c3e55090b069 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
8a7c6375-a2f8-47f1-b34e-fbf98195de7d | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
857011e7-17e7-4989-b5f7-d8855b094072 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3 |  | NULL | NULL |  | NULL
70d06477-1cdf-4e60-a521-7aaa6ae06aa6 | Pole | 2 | Transmission | 2020-11-03 | 2021-11-03 | Level 2 |  | 2021-06-02 | 2022-06-02 |  | Arm rolled
a2870148-6a38-491c-a2b3-c69849e44dfd | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
52a264de-d18c-4886-b22e-9e9bdbb46bf3 | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
89706162-b9c4-4b79-b1b8-3a5769d6ca25 | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
af45b8e6-2d8b-420a-ac23-d86959b0f453 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
c67c4188-1292-440e-bd6a-91d3a40eeeb1 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
d2a06795-a4b5-4e0e-99e1-f6ba8276f609 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
10a46bdc-ff45-4cfb-b382-d32b53018fa3 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
6cdb0dd6-58bb-4a1b-879e-c8c92d1f03b9 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
74da15fb-1dd5-4e5a-b57b-6230b4e7212b | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
8203fb0f-5e11-48ba-959b-050786096a80 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
4006a461-8e7b-436a-9f94-3b80ffb7368d | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
3fa3edb9-0223-4c2f-bf5c-93a4d1912192 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
41c301ca-f8da-4262-a899-f0e928c5c567 | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
37e13b96-c9a0-4a56-b9cd-ca210701994d | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
36c24442-95a7-46d7-b483-e43348955130 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 |  | NULL | NULL |  | NULL
30714bc3-8a87-4d0e-914a-6efa49c4adc0 | Pole | 2 | Distribution | 2020-12-14 | 2021-12-14 | Level 2 |  | NULL | NULL |  | NULL
6f2768e7-417e-436d-a182-1bede09d23b1 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
05abd4a0-3ad4-4c26-9ab6-96c44e02f66d | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
f05649f1-0061-4aa5-a97f-37b282cfe320 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
ce355eb1-8741-4b1e-aa45-4559704fbef4 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
cd5019ab-cb16-4734-bbdd-2b9627301993 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
c8213d31-66e3-4e5e-9621-c7d7695d96e2 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
a6f42990-a933-4e30-93da-5bbe8b784519 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
a757e3f2-eeab-4dd3-b4d1-975da11a09a9 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
51ed5513-539c-43e4-978d-a60c01ada391 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 |  | NULL | NULL |  | NULL
cc79afd9-4068-483f-b32b-60ca551e2070 | Pole | 2 | Transmission | 2020-12-16 | 2025-12-15 | Level 3 |  | NULL | NULL |  | NULL
d311405d-07ff-4d02-a01a-9aeafdd5e2ee | Pole | 2 | Transmission | 2020-12-16 | 2025-12-15 | Level 3 |  | NULL | NULL |  | NULL
dcd9d11c-fca7-4ebc-b570-4d34ef118141 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 |  | NULL | NULL |  | NULL
e01786a2-1cbf-4fe9-a8a6-882b6f59dba2 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 |  | NULL | NULL |  | NULL
059cd3f8-3f05-4f08-8ac0-2007b0349c85 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 |  | NULL | NULL |  | NULL
1dfba368-0f8b-4bc7-9ea6-13bef4ed3455 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 |  | NULL | NULL |  | NULL
3d7daa0b-97c7-4848-b2f3-7c1161854d38 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 |  | NULL | NULL |  | NULL
42beeeb4-6d9f-45a3-8787-c8088dbace9d | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 |  | NULL | NULL |  | NULL
330852cd-9aae-48df-943e-96a15c57a544 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
6bbfbf2e-0990-432c-9763-3453ed37c7ed | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
638d596e-8576-4ba0-876d-6c5e126ca05b | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
1132b68c-088b-41ba-a207-4b380e802cbd | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
153031d3-51ca-4179-afb8-f4e0c2377643 | Pole | 2 | Distribution | 2020-12-18 | 2021-12-18 | Level 2 |  | NULL | NULL |  | NULL
d01164f6-447f-4225-b969-e271db983325 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
d0de9407-1752-4628-a809-8de834351d41 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
9deeeaf6-b96b-42bb-ad8d-0556629dcd01 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
a21b8b30-d55d-471e-9127-7b6faed0a8f8 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
31e90cb5-ce05-431d-92da-dce023a6746f | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | NULL | NULL |  | NULL
a73fee10-0e9d-47ba-937a-3f9687900e87 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 |  | NULL | NULL |  | NULL
8cf29a3a-1bcb-45d2-80e1-b792ad8fc960 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 |  | NULL | NULL |  | NULL
be3a6610-8ad3-4ae2-9c39-2372d418b8eb | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 |  | NULL | NULL |  | NULL
e7620f4c-5dde-4833-9dc3-0f86ba11b22d | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 |  | NULL | NULL |  | NULL
21cf93c0-8456-4c78-8f2f-da402b654f02 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 |  | NULL | NULL |  | NULL
3a34d26c-1b83-488e-b0db-cf3fcdcec3bf | Pole | 2 | Distribution | 2021-04-28 | 2026-04-27 | Level 3 |  | NULL | NULL |  | NULL
2a07577f-b3f4-4ce8-ae72-5d1ad47185d9 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
3ffb3f8e-f0c3-4551-907e-66e478986f1a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
7809daac-a066-4b4c-80a6-50fef4685c4f | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
18df15b7-dbcb-4eca-84d1-2be331080052 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
22f64a95-b562-44aa-9537-65f936ce9654 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
af57562b-db22-48aa-9b36-d89583ac5f7e | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
bec5e9e1-c8c5-46a8-96b7-ca73a130722b | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
e30160df-4c83-49c6-9980-367734f7c1fe | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
e7bafe57-13cd-45e5-aba3-70bc50025290 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
fb58cdeb-97b8-478c-9abd-e449ac77695a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
f5292a05-5d6f-4fd4-b118-08a7fc08a5ac | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
1e9d1d0a-bb27-469e-b595-5ff300ff273a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
0c88dec1-27d0-44a2-9cac-edc4127bf2d1 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
35ce2f0d-a464-4c34-b1e8-086b90711db3 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | NULL | NULL |  | NULL
bf71822f-1fe7-4f1c-beb4-3cd0f71b0a31 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
ba3c37c4-5184-4bab-8106-de6da6799464 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
a829abaf-bbb8-4fe5-9c0e-f80fe4af51b6 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
bb7d72a0-99f9-4841-b25c-90e8fd0e33f2 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
b2b532f3-0553-447e-a66d-3b730849b277 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
8e6b4499-3622-4999-a502-77eb608cd385 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
a91e7fd3-36a4-4083-857a-ad2a76aad36f | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
94a68f8e-9954-4fea-a59d-acb8a0b712fb | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
18b08b8c-1201-4f08-a90c-d91cab8251f1 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
0061582a-773f-43b5-8863-245bc0d08fa2 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
46c6109a-3376-435a-85fb-202def1b4017 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
5129bbb2-6cf7-4d34-aa5a-3b3795c0b3ce | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | NULL | NULL |  | NULL
c06e0d38-1814-494a-b657-b2e5dfaf63db | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3 |  | NULL | NULL |  | NULL
0f52bc9a-dedb-480d-9a2f-8be6e92238d4 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3 |  | NULL | NULL |  | NULL
2921d876-d683-4510-ae5b-fbab0913a353 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3 |  | NULL | NULL |  | NULL
01367fc4-8fc5-47d1-9109-edf3e1a5e4e4 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3 |  | NULL | NULL |  | NULL
7ebd0501-4c69-46c3-a9b3-fc7c3005632f | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3 |  | NULL | NULL |  | NULL
b32a9137-cbb3-44ff-a45e-560182f9885a | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3 |  | NULL | NULL |  | NULL
fb47b541-12d0-41ad-a428-5f7fc375958b | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3 |  | NULL | NULL |  | NULL
296bef50-d0da-4c12-b265-17e221248a61 | Pole | 2 | Distribution | 2021-05-05 | 2026-05-04 | Level 3 |  | NULL | NULL |  | NULL
c2c4fba6-8be8-4156-9ceb-38c84210ac45 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 |  | NULL | NULL |  | NULL
b36ffc38-4d5e-4250-a769-c9e388fec444 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 |  | NULL | NULL |  | NULL
37056221-fe6c-4de8-b617-a94feca8a471 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 |  | NULL | NULL |  | NULL
5ab2c315-aff3-4fc1-af2b-b6ebd77be984 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 |  | NULL | NULL |  | NULL
7c56fffb-b9fe-4224-9fbf-f1c6a93c2bb8 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 |  | NULL | NULL |  | NULL
18a40d05-90fd-445f-819c-db748d984211 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 |  | NULL | NULL |  | NULL
d92a770c-1c52-415f-b5f0-faca8fc6011f | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 |  | NULL | NULL |  | NULL
b3fe46b7-8243-43b2-83f8-8c761aeb50d3 | Pole | 2 | Distribution | 2021-06-04 | 2022-06-04 | Level 2 |  | NULL | NULL |  | NULL
cc953013-ddf2-4b47-b420-359eb93f1ffc | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 |  | NULL | NULL |  | NULL
8c3a30b8-c7e5-4e1f-b099-b21d51181055 | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 |  | NULL | NULL |  | NULL
8fdc8965-49d7-4753-bc91-051ed7b7cd59 | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 |  | NULL | NULL |  | NULL
126788a7-aa86-4ec6-95a8-5380489b1b7c | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 |  | NULL | NULL |  | NULL
63975c28-5e39-4be5-9e5a-366944612499 | Pole | 2 | Distribution | 2021-06-14 | 2026-06-13 | Level 3 |  | NULL | NULL |  | NULL
05fa339a-1700-4f68-87e0-aab5efa1b46f | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 |  | NULL | NULL |  | NULL
e6df7adf-b39b-4a70-a115-5e85cea4503d | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 |  | NULL | NULL |  | NULL
d779e54a-a832-447f-b43e-c84d7b64f4aa | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 |  | NULL | NULL |  | NULL
ba196846-799d-4408-ad22-d2bbc1452d0a | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 |  | NULL | NULL |  | NULL
c5a76494-d8de-4329-b5fc-812a5fd7d9dc | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 |  | NULL | NULL |  | NULL
b8b41498-3a32-45a6-acea-dab119d13be2 | Pole | 2 | Distribution | 2021-06-21 | 2022-06-21 | Level 2 |  | NULL | NULL |  | NULL
2ed40ae8-7ecb-4bc3-af77-9ab8c0527856 | Pole | 2 | Distribution | 2021-06-21 | 2022-06-21 | Level 2 |  | NULL | NULL |  | NULL
839e7ee8-7c40-4c80-9f50-87d0160630ea | Pole | 2 | Transmission | 2021-06-22 | 2026-06-21 | Level 3 |  | NULL | NULL |  | NULL
5ea583c9-58b8-4b65-84c7-4592c200aa38 | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3 |  | NULL | NULL |  | NULL
cb078fce-4181-4170-97d2-3d28a6c8a8ef | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3 |  | NULL | NULL |  | NULL
8c12109f-5e1c-4929-83ef-0326996a47d5 | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3 |  | NULL | NULL |  | NULL
fc642943-4c43-4530-9e1c-3507c790d03b | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3 |  | NULL | NULL |  | NULL
7618aadf-07d7-4222-a267-f7f7d9285122 | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3 |  | NULL | NULL |  | NULL
88170c15-148b-49b1-9483-32f69fb49d71 | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3 |  | NULL | NULL |  | NULL
2d0d5ff1-e53c-49b7-91a6-fa1a7d1a07cd | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3 |  | NULL | NULL |  | NULL
5b7c59f5-2241-4d5a-a61f-44619dc28cea | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 |  | NULL | NULL |  | NULL
14ee7c33-3957-46b1-8042-10df52c595c2 | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 |  | NULL | NULL |  | NULL
0e4e6094-7cc0-4cd4-8c93-c623e394cfd3 | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 |  | NULL | NULL |  | NULL
1c3d0e1c-ba90-461d-b685-dce35d0cef47 | Pole | 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3 |  | NULL | NULL |  | NULL
af972b85-ef7e-4fab-b62d-63e311958fa5 | Pole | 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3 |  | NULL | NULL |  | NULL
fcf297d2-10a7-4bb0-977e-a28aa527aa50 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3 |  | NULL | NULL |  | NULL
14219f68-abc9-47d6-9c31-f787b6450796 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3 |  | NULL | NULL |  | NULL
4a4474af-1995-41b4-9d01-f9405889bb78 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3 |  | NULL | NULL |  | NULL
c124d0af-8ed4-47b6-a135-dcf5e92c1360 | Pole | 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3 |  | NULL | NULL |  | NULL
34e3cfc8-e4d8-4bb8-8f9b-d73583d99c8d | Pole | 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3 |  | NULL | NULL |  | NULL
9ad01a60-27ea-4f2d-9b84-f99bc5076aca | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2022-10-19 | Level 2 |  | NULL | NULL |  | NULL
5193025a-5b67-4cc4-8604-8e93fc8e2d81 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
3c09ec68-ea4f-405a-a972-25afcdd34695 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
c7590ca7-0f57-463e-8661-044b781c6280 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
38b45260-c054-41ff-b95a-4f5841ef6436 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
af7fac7a-e34e-4471-94e0-851510639e15 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
c3e666c3-5df2-4e96-b060-6774d1cd4019 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
ecb03a07-2432-4e2c-a9f8-30195c936947 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3 |  | NULL | NULL |  | NULL
700098f9-95c1-4d46-bb5b-a0441f4ab144 | Subsurface Transformer | 2 | Distribution | 2021-10-20 | 2026-10-19 | Level 3 |  | NULL | NULL |  | NULL
0f48869a-73cd-4dd0-a399-20e4da546ec1 | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3 |  | NULL | NULL |  | NULL
18e79d39-bc5c-4ba1-96d7-51eac8aff3d4 | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3 |  | NULL | NULL |  | NULL
c8f7c641-dc69-428d-aa03-7d10624ad54d | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3 |  | NULL | NULL |  | NULL
f6f76c88-b3ea-48e9-9aba-271fdbdd66b4 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
b7b8c16d-993d-44d6-85ca-5786b2d08d54 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
59c289e0-f8e6-4231-94cf-a84fb953f7d4 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
3510d1f5-b55c-4026-a699-48009589fd8c | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
e144c5c7-892b-4b33-94db-1c202faaefee | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
5419f188-597b-4f87-ac2a-f85ca3a0088e | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
3a9dcaf6-0d0f-4631-849c-6da5b3fd2ad4 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
e6ec1743-2d0c-4896-92ab-9b58d88d6b77 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
4ae352cf-3849-433b-850d-bf137ac3614f | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
16d604cb-d4b6-4555-97a7-f540f28222e2 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
178690c6-20b4-4625-b0d2-ad7bb32b23f3 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
69b5b637-59f6-482d-944e-2f451b5b0397 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
7ed4bb36-60ba-423d-995c-cea3c157ab56 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
75ea10ca-c63c-4e90-8a6b-97d7fb348fab | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
282a7f03-51f0-4639-b6a4-fb5f21735e46 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
34d38710-c291-423f-bc5a-053b2f4338a4 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
3607a411-9506-4dd9-bde5-6d417a28f4a0 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
dfbf6508-3bc0-42d2-8ae7-1bcdab2f7041 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
e9026147-f9d7-44a6-910e-71e0489624aa | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
208033da-57b1-4f97-8a6d-4f91d396e108 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
042e8926-2c53-44bd-b440-5088822e1078 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
813bcc20-84da-4843-b1fc-2a810be994ec | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
a09553e3-7e4a-480e-837a-0161a44610c7 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
e3a8ee9e-1e0f-4bfe-b2e3-4587330ca0d2 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 |  | NULL | NULL |  | NULL
26ee2dea-6b75-4afe-8159-a40882cf5d0b | Vault/Box | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
c03ddda7-3e08-4c55-b886-6f6d4d377ee5 | Padmount Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
64125ed6-bf79-4bd5-b24b-cfae85f50f67 | Vault/Box | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
2f502134-ee12-46db-b322-bd84040b8394 | Subsurface Transformer | 0 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
f9c08220-3b95-456c-8660-2b98d8ac2897 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
ec44ca4f-a2ad-4dd4-83b0-03f3766314aa | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
6f28aa38-21b4-4d1c-8e29-1f09c4daf840 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
59dcf11c-5afa-4e0f-b760-1f9f74e4ee29 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
7da367c6-0a7d-4273-975f-8fd3299f27b3 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
948a5d2d-164b-4e9b-85a9-87574ea00e73 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
f3243f21-b472-48aa-b895-5759dc0954e3 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
067e54ae-6f41-4593-8219-f4b6caefbc14 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | NULL | NULL |  | NULL
168468f5-1a76-4702-a32c-68e40c8d4997 | Padmount Transformer | 2 | Distribution | 2021-10-22 | 2022-10-22 | Level 2 |  | NULL | NULL |  | NULL
0223c440-79de-4cc1-b6f3-3b99fbb4e611 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2 |  | NULL | NULL |  | NULL
896c3455-6340-4bea-ba2c-3a2ebd063f10 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 |  | NULL | NULL |  | NULL
698e8fb3-e5b1-42f4-95fc-055bb01c1e24 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 |  | NULL | NULL |  | NULL
9593a78c-fcaa-4dfd-be17-45943eb14fb0 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 |  | NULL | NULL |  | NULL
f833ecdf-bd46-4695-82f5-8a499459153b | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 |  | NULL | NULL |  | NULL
6df7862d-1a18-4493-8d17-5070bbd3807a | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
4edde5ec-f06a-4d0d-a9e3-2ad0a2a16f9f | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
d186e017-9afb-4ddb-8520-c7cbcdf14db2 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
b557800e-b205-4891-92b2-d173ce3c1667 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
b97cc0c4-568a-4b1b-83cb-681dffc0ccc6 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
1226f38f-6372-4b38-8ebf-db2acc652f06 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
257cace0-d5f5-4006-9363-9058a66e4ceb | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
f3f04387-269e-4300-8002-5ab516fc4df7 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
9d9bcdd6-28f2-43a1-a9ed-07e9161713d6 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
d0335cd1-ed87-4caf-b00a-b8edbb0f7ce5 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
5ea41cff-1efb-4996-827b-ec22ec35b5ec | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
a28afb3c-6a47-4909-8bcb-d96e2a66fba6 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
2a653d8b-0cb8-4cc2-a9d0-0b7e137608ce | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
d2b24d0b-51f5-4e33-ab76-5c8916cda60f | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
731c9e68-6eaf-4025-83ec-c99eea7335fe | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
173bbc1f-e2dd-49a0-9434-f4ff8d4befc5 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
09525167-8322-4e8a-88b5-ad0c01ed99a7 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
8dc31024-acc9-43c3-be5a-581331739be3 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
6dd0c98a-e008-4d06-96b7-10ccc7cd1f82 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
37aa2543-c5a9-4355-94de-15de40e25801 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
fecd6ad9-8d2a-45fc-9d21-1e135817ab51 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 |  | NULL | NULL |  | NULL
791e201f-de2a-4d61-9a7c-8117d626cef5 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 |  | NULL | NULL |  | NULL
67eacf97-c032-4b3d-a1bd-be19fb824b78 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 |  | NULL | NULL |  | NULL
2daa0614-4553-43b3-9a31-051a0e16b041 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 |  | NULL | NULL |  | NULL
b9ea6852-7497-44da-8f8b-d77c1b943033 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 |  | NULL | NULL |  | NULL
a9cbf5a1-fb57-4c92-8e76-664dcb70e241 | Padmount Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 |  | NULL | NULL |  | NULL
a9ae1d94-323b-4985-b0a8-208d43683390 | Padmount Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 |  | NULL | NULL |  | NULL
7cfdedad-72e3-449c-8de1-0af0106c75e2 | Padmount Switch | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 |  | NULL | NULL |  | NULL
b8c207f0-341f-45b2-a5dc-2f565c61c815 | Padmount Switch | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 |  | NULL | NULL |  | NULL
70475f39-c271-4181-b6c6-8f85749d583b | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 |  | NULL | NULL |  | NULL
69c5f10d-8eff-470f-aedd-ab4db63e9967 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 |  | NULL | NULL |  | NULL
d3de8ebe-423f-4820-9355-20ab83160314 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
ea278f9c-df96-4c88-90ab-79fd5f703f23 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
d9bd5f86-2789-47d1-95f2-8ef4e7546ecd | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
705954ad-496e-4cc0-b6c7-10e0d1e5534f | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
3a9e766f-4355-48a6-a98c-26413c184e08 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
c76a61c9-f3f7-47dd-9a91-409abc408bb0 | Padmount Transformer | 3 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
289c8014-190f-47e9-ac2d-755d631fc1a4 | Padmount Switch | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
cae5cd38-c6c4-455d-8ecf-babbbe45d76b | Padmount Switch | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
b95c5c5b-4dfb-4aa2-8956-8bcabdd6a8b5 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 |  | NULL | NULL |  | NULL
1662a1cd-5ceb-49b1-93fc-a780bc658dbf | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 |  | NULL | NULL |  | NULL
6c746ba8-da7e-4ad8-8790-70a1250c36d4 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 |  | NULL | NULL |  | NULL
ddcb61f1-817e-4f30-a5eb-1399cdeb7f15 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 |  | NULL | NULL |  | NULL
516d4ecf-2e7f-47ec-8b9e-cb0e6172279a | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 |  | NULL | NULL |  | NULL
def94314-7bf1-4d50-a301-c1377311a40a | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 |  | NULL | NULL |  | NULL
60e1dc24-1694-476a-8035-f63d08c7a5de | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 |  | NULL | NULL |  | NULL
dda5488c-0c0e-422f-bdb9-d392e60854ca | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
687bf21f-b12c-48bf-9870-c8de1c197818 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
a06a1ad2-9562-4b09-8f02-4a154d17f877 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
d6b82dd1-a08b-4b83-82a5-d2bd032df7d2 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
69d7491f-b958-4eb5-9cd1-5435458de94c | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
f752fed6-7947-407b-aaf2-bdd3a0357ef5 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
860516a4-f107-40dc-8538-e90fa6a756de | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
df7688d4-8313-4168-b7bf-a87b95666571 | Padmount Transformer | 0 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 |  | NULL | NULL |  | NULL
6f28b315-0e58-4612-ad5a-2a3853b04416 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
222913d1-64b2-4570-b54a-c92d197894b9 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
8eb42b9e-511f-4868-89ae-9d12db9fe120 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
cc851e0e-8d95-479b-a5a9-3d77768ae1be | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
1f47a02a-b72a-4272-8e35-70c46eca8481 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 |  | NULL | NULL |  | NULL
f618206c-89b0-4fc8-8f65-2a1b027669dc | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
3759326a-470d-4c7d-8311-25a0e44e0f4e | Million riser with bridge switches | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
667e43bc-507a-4413-8557-353f4a4898d3 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 |  | NULL | NULL |  | NULL
aeeb16c4-7b48-4227-8f43-0d4eee62ea2c | Other (Describe) | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
aaf28071-aeea-4c96-99df-6eab44cc2337 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
9f691f93-53a5-43e5-b44b-baf83c2ef448 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
c8cc97f7-4d0f-448c-aebc-cebb7276f32b | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
b50b99a7-fb00-4311-a1d9-a3f89d7864d6 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | 2021-11-01 | 2026-10-31 |  | NULL
8a336278-04fd-44fa-9ed4-c5d71dde4123 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
e03311d5-420b-422e-a9ab-3d0fc1e77fda | Million dip pole with bridge switches | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
30e9ec4f-8a1b-4d9e-8532-c854b4e6b4bd | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
576f7b80-f2d2-4731-be05-70a5d29b13e9 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
2194b38e-ecc9-42e7-ba81-98882a6802c5 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
263d957b-b8ec-4459-99d4-708c8f4cb8e5 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
899bc20c-4cb4-4be1-bf60-bc086ba5793b | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
6f123e8a-3cb2-41b9-aa62-e23a93ef5b19 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | NULL | NULL |  | NULL
49820070-79e5-40a8-bf91-1519dd8ce439 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
08424585-7ba5-4cff-b92e-801dd5235785 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
202306af-3d29-4b76-9fc9-c92977c5c6fc | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
a01c768e-377a-42fd-9b04-e254799656e7 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
bc562ff2-9873-4067-beb1-2f2520203035 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
7d7a2c81-2e1f-444f-b157-e14dfcb1a344 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
a226c54b-8224-45f2-a698-f0c54751d210 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
ea54d99a-af5a-4ee7-b2af-fb88850a308c | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
a16e8f1a-4a74-44d7-aac1-cd8b0e3e9a9f | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
0d9ba3c0-2cbc-4ac0-888c-67a632acd0e0 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2022-11-02 | Level 2 |  | NULL | NULL |  | NULL
b355d795-79e3-442c-8cf8-b69dfafbe192 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
2a17d956-d1d9-4688-8a05-e6366d70043f | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
34c4977c-6c47-4c0a-98a3-d647a63042a9 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
0fbb8efd-795b-47a9-844a-41c33711be26 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
2bcfa3c7-e207-4b2a-9fdb-162a328ebb25 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
40754894-3c03-4575-bdae-b16e8eda3e1d | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 |  | NULL | NULL |  | NULL
a0667eed-d8c1-4c75-b815-1d3ec28802f6 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
70b2142d-8af5-4574-91a6-0d128404f305 | Regulator | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
3f89810f-aec4-4c11-9464-bba99e81c671 | REGULATOR | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
f7fb82af-30e1-4070-aced-8e7e8b00fabd | Regulator | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
64d0c6e2-4180-4485-b091-665f21f54a1d | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
4cf051ed-03c2-4b86-93ad-d36824c5d1b7 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
23cfefa2-b7ac-4d1d-a846-ea7217718faa | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
0889c0ab-af53-4b52-966b-c7966de6c95e | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
93d7140b-c38d-4544-8943-d6f10f81c0d1 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
2764ddfa-0b63-4c37-8cc2-a6629c2dd847 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
2aac781f-1042-4840-8cf2-cece4975881b | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
ebfa4c12-246b-49b1-9f0f-3763bc8403ec | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
2c2b9acc-bc63-4d8c-a8eb-5612c880af46 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
f7a05631-3d06-42f7-886d-22c6ce62d088 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
3034fb3c-80d5-46f5-b837-b356ff07d96a | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
627e2ed8-2b7b-4ad5-9592-b2b9b1da2e03 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
663be561-e47d-4a4a-a947-9a6ed3226a13 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
62520226-2d13-44b5-98c4-39e513502843 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
706064f3-6b86-46b4-a599-35b72f63b403 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
bebc84c7-06b8-40db-bbe1-f514f12a8092 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
fb3f036c-8876-42ba-ba67-aed8dbd22c2f | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | NULL | NULL |  | NULL
4c547298-e4bd-485b-917b-51011cfbd4a1 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
c3a8e1af-bae3-4e0b-a94a-a90a8b1f5883 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
73b7c453-abd5-4af7-9ffc-7b8156c492be | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
8a7c0559-9c60-453e-9fc8-7530b67dce88 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
a0ea73a0-5f94-49b8-a85c-31731e089641 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
fd0b4574-5ba1-4562-b59f-68fb630ea61c | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
341f0cc8-8c7f-4c87-8032-1f3a48f11e10 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
2dd3e7a8-fdf4-4d1e-8536-f017c5ceb505 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
c0f1ca20-bbdf-4aa0-b0c9-1cb02cf1ed0a | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
e23e8807-3a89-4db3-8790-9130562e7746 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
a5386803-b15c-4a6f-bf05-638df8393114 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
1f9260c7-52f3-4899-bb23-d50f0f10e731 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
fe41d1c6-0e56-47e9-a73c-3040e69b2502 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
c5b9339d-41e8-44b3-80bc-90d403e4634c | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
a75e9ea7-3731-4bac-b931-04e78db08cf7 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
e51f68ea-cec8-4452-a21a-c62a1982412f | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
e2bb6d47-6f79-4d3c-ab96-0820c511eb40 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
f889f99b-8348-4eae-9e52-0725d6ac6b52 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 |  | NULL | NULL |  | NULL
cb93ed30-9033-443e-93f2-3bb708c9b8ea | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
f36d7db6-0938-472d-b286-e7d76932d14d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 |  | NULL | NULL |  | NULL
f9784fb5-d97f-44e6-aea9-2072689fe04d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 |  | NULL | NULL |  | NULL
3fd61d92-6f63-4b37-ba9a-b1b09c5ce596 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 |  | NULL | NULL |  | NULL
27c06025-52ce-4196-b682-3a241787ae85 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
e974d547-3d45-4077-a1ef-ecea5dcef47d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
bba9a32a-bb17-416c-aa4a-9af80ebfac5f | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
bed65d66-1f64-4025-9500-e2f2ba549cc3 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
9affb1e5-9dbb-418c-920a-daeb0018f39e | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
69241977-9715-4fec-ad36-d67f66b5f906 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
6c3a4663-78f2-4816-81b3-95a91e27fb16 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
b5057e47-e617-43af-a3cf-91b4802b90e5 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
74c0b6b5-b8d2-40a1-85f9-4c74c64bbdd4 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
1875650d-24c7-4293-8782-8c6e3824b99f | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
2792c957-ee85-4f28-bab0-56c2e206c72b | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
f6c9f6e3-df6c-4084-8b5e-a695bebdf92a | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
66e0e874-4e13-4d2f-a3ec-f2e723fc496e | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
2dd09a9c-c660-4e43-8e11-029d8ae9e48b | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
18fcb6ea-fd22-445b-b0b4-e1c64f157c4d | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 |  | NULL | NULL |  | NULL
9f401988-789d-4f66-80a9-765293f412af | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 |  | NULL | NULL |  | NULL
b9004984-ec78-4876-8754-7a73adee4943 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2021-11-08 | Level 1 |  | NULL | NULL |  | NULL
7ad44b3b-d63c-4695-a1ef-4f86f9eadee0 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
46d022c9-680e-4e20-8f99-55002d0e7284 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
577437d5-0a47-4e9c-a242-6670b40b3cfc | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 |  | NULL | NULL |  | NULL
56359f14-9ac2-4f85-9075-d22b8ecaab76 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
97e9c61d-d22e-4545-9191-e249545e43e4 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
f3353016-ac9f-4637-a0bc-487684cb63de | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
d664a045-7015-4ed1-b912-f92646a4c65b | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
9a921048-7e6f-4db6-9494-62177420aec9 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
b19740c6-82b3-4456-bc27-4dbc429cd91e | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
25f7629f-7d89-48d8-8852-a15c4657cc3f | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
fd2d7187-2411-42ed-81b8-58a4d3d71abb | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
319c29e1-03ea-4d14-8610-01d22d6f36a5 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
fd37a7ff-ec5c-49d6-b940-190d7817b22f | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
bd07ebc9-d428-4687-95c6-9e045b4fadb3 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
c2889f05-4510-4bf6-ab9b-3a4b66be74a3 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
00dc6f15-9045-4a19-93be-ce9de0c68255 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
719dbd3b-d751-45e9-87ab-af0d9109e15b | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
90c8650f-41e4-41aa-822c-fcf8ee06143a | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
d9d5b7f0-c1a6-493e-b2c6-e022dec25fd8 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
d33e239c-4582-4f45-bf1c-f22a3f9c29b5 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 |  | NULL | NULL |  | NULL
99265580-7cd9-4c07-b772-80aea4f639d1 | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 |  | NULL | NULL |  | NULL
95541ad0-168f-41ca-bcb2-d0b547cfbacc | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 |  | NULL | NULL |  | NULL
d56b7971-beb4-49a9-8dfc-cc670246da33 | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 |  | NULL | NULL |  | NULL
51788ff7-bb37-4122-a2d6-7e4d6b7e172c | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2 |  | NULL | NULL |  | NULL
a8ea1ae8-5656-4ce1-8b6f-08c89190871f | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2 |  | NULL | NULL |  | NULL
4abace26-9b92-462c-a909-ec21b40f503a | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
6ff67d57-ab95-4cbc-883b-367c9e4cfc15 | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
6098b3a4-42c1-45d9-a318-c394bae91b4f | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
06e4862b-57b0-4ee6-9c99-899fc65af24b | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
3ca8fda8-fcab-4e9c-8950-7876261c927f | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
e361cf1e-7e14-4baf-a0b8-3b432485a2cd | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
161128f5-5beb-464e-b4ed-b0cfb4d63550 | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
2c1a70d9-e6ae-4d34-a193-e6787d5cd9d8 | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 |  | NULL | NULL |  | NULL
c556ac8e-a705-4d00-9b78-97b085f2af0f | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3 |  | NULL | NULL |  | NULL
51ec8f6b-3653-493e-962e-330279c4d004 | Junction Enclosure | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3 |  | NULL | NULL |  | NULL
9f80bca3-d103-477c-9ec5-a389993ccd73 | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3 |  | NULL | NULL |  | NULL
8edd9b0d-26e7-48a1-b66e-fac80750d58b | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 |  | NULL | NULL |  | NULL
b822fca3-fd4c-47ea-9ddc-9167b560ad51 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 |  | NULL | NULL |  | NULL
48698bf5-585c-4c57-b8de-ec5aa34a7970 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 |  | NULL | NULL |  | NULL
154ab2c1-ae69-4121-a8de-166eaa9b3a14 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 |  | NULL | NULL |  | NULL
70058380-feae-409b-b1e3-47d2ad9e6e77 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 |  | NULL | NULL |  | NULL
d00c121c-2471-4af9-8c17-3a79b2777da5 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 |  | NULL | NULL |  | NULL
21bc4f74-b34f-45f6-b29e-a2dd5aecd76e | Padmount Switch | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 |  | NULL | NULL |  | NULL
c094b4dd-1902-47ff-a385-e48c5e994a19 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 |  | NULL | NULL |  | NULL
cb1e5547-d2dd-4b55-8a09-be2dc3b60a6a | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 |  | NULL | NULL |  | NULL
70c962d7-6162-4a7f-94d4-ad9df67d6c07 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 |  | NULL | NULL |  | NULL
c7b2ac54-938e-4cf5-a26d-cd52ae3b1b42 | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3 |  | NULL | NULL |  | NULL
d9340227-da6e-4f44-bacb-51dceb365b6e | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3 |  | NULL | NULL |  | NULL
6618f0f8-ebb0-4295-a4c0-6bfc3488c21e | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3 |  | NULL | NULL |  | NULL
a12c31c3-9ac8-4131-b5ea-77233fe0b020 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
a040db75-035a-43d4-bec6-c13c38f64046 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
e20eaa67-1091-4ce1-b285-a0e3f1931e75 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
f8615808-3fd3-40bc-9370-4ea665f9e3f3 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
69a59481-aed4-4173-9712-9f08c91585fe | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
304d7afb-bbed-456e-9ae8-f48dcb2304a2 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
95ede16f-c88d-46c4-b310-16cf8354ec48 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
241ab08b-d97b-42a8-a97e-99c77a7d6f79 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2 |  | NULL | NULL |  | NULL
c4928fcc-5509-493e-9b9a-2742942b5c46 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
9b024ff7-2807-44b3-9991-494a15a76622 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2 |  | NULL | NULL |  | NULL
f48ff40f-4ce2-4846-b1ed-ac068f6235e2 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | NULL | NULL |  | NULL
cc61fa4b-8928-4590-a4d1-bd72247967e8 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
36c17e5c-1cc8-421a-a50c-f67bb2d7ec7b | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
4435fc26-76b4-4a0e-a46c-8dcbfbc84136 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
6b3a6260-7875-48dc-a1fd-33bbbb986312 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
e5295df6-40db-4f53-89ce-ac6e73646e07 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
c370e1cd-6580-40e7-91f9-db0eeca2b9ae | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
8d4a8de5-304f-4643-a28a-05dc0f673e86 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
8d2fe2d9-43de-4491-a056-9a97584d3eb4 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 |  | NULL | NULL |  | NULL
4da60e94-641b-423a-9dad-5c5c95c6de2f | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3 |  | NULL | NULL |  | NULL
b36ebc00-f57f-414f-afef-b60fdadd8779 | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3 |  | NULL | NULL |  | NULL
f2859908-b0c1-49df-921c-ce5a60d0cbad | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3 |  | NULL | NULL |  | NULL
cc1f8089-8663-4abf-afb9-cb4b43c68fdb | Junction Enclosure | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | NULL | NULL |  | NULL
0b1f391b-32c2-4f14-92ab-711db48a41b7 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | NULL | NULL |  | NULL
4e8ef4c2-2c5e-4f71-bcfa-4845bc57d7da | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | NULL | NULL |  | NULL
97a720ee-e51b-46e1-88ab-58b6bfd08bc3 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | NULL | NULL |  | NULL
1b253976-9c2d-4270-a34f-813ab66503a0 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | NULL | NULL |  | NULL
8edfd2d7-e57e-4fe8-90ee-604aa24ac4a4 | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3 |  | NULL | NULL |  | NULL
c4ece5b2-7e7c-44d0-9cea-67796624633b | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3 |  | NULL | NULL |  | NULL
ff964d7f-6d24-449c-b315-071cc9b78f34 | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3 |  | NULL | NULL |  | NULL
7e1a7735-c75b-45e0-b5f7-42de67dcb4ad | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 |  | NULL | NULL |  | NULL
00fb24bf-98fe-4101-8238-883b65fe9137 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 |  | NULL | NULL |  | NULL
f8f2dd25-e607-49f7-bc2a-a2d8ae51067e | Padmount Switch | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 |  | NULL | NULL |  | NULL
855a23c1-8179-4082-8ca9-d7faeca7a793 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 |  | NULL | NULL |  | NULL
9e52e1e2-97ec-4ddd-94f0-6eecd1d46ef0 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
d1bc89fd-6369-4743-97c7-3ec1c295fc98 | Junction Enclosure | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
a628d59a-f18b-4ad5-a2de-7b8ef81e545b | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
28ae7b8f-a7fb-44e9-9bdf-bbe9ed769bf2 | Junction Enclosure | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
59dc15a0-980c-47bd-b5be-6d0074d4c738 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2022-12-01 | Level 2 |  | NULL | NULL |  | NULL
3d4bdd58-28cb-4bc1-8ab5-24a2b45ebda5 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
da876f43-5eca-4b84-b449-92617ba3821e | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
3431efa3-da78-4ad6-a734-9f8b13f762d9 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | NULL | NULL |  | NULL
c28aee0a-ceff-4572-bc48-2e5cb0a84e83 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | NULL | NULL |  | NULL
89dc8e3e-bbc0-46d8-93ef-8e076dbceb41 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | NULL | NULL |  | NULL
78f4a10a-4ad7-403d-85aa-6e1c501f5833 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | NULL | NULL |  | NULL
f79316fc-f799-462c-aa1b-9da0ca30754a | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | NULL | NULL |  | NULL
858ac9f1-67ea-4d93-b090-1448d44e0922 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | NULL | NULL |  | NULL
134b6581-1656-426b-8159-10bae2b929db | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | NULL | NULL |  | NULL
3fc33f72-480f-4986-b4d7-245969deafb7 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
c589af83-02ef-467f-aeee-7d217f1e8f13 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
5094ee40-d750-4e30-acc0-72c09561e678 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
6f081616-2a6d-4b22-9142-b6696dcea656 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
dc0f5871-0131-4f09-9527-17d704e73a1e | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
36be12e2-15f6-4ae7-8887-2f6823f3012c | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
ca4cb178-f6a7-4484-816e-59b7c67fe56a | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
f17ccf5b-a1c4-4a0a-9532-3522a4767fcc | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | NULL | NULL |  | NULL
14d6eb9f-89f0-4b12-9036-a3f7b388f9fa | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 |  | NULL | NULL |  | NULL
e3a29ce1-e303-4930-a89d-e0a322d3acc9 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 |  | NULL | NULL |  | NULL
cb869d06-bdaf-4ba4-a091-e77f580294ec | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 |  | NULL | NULL |  | NULL
80aa210b-37b6-4f13-a74e-2710845afc9e | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | NULL | NULL |  | NULL
2c97498b-cd6e-4150-b31d-c40916a8e36e | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | NULL | NULL |  | NULL
243d7ee1-f943-4ef4-ba74-67b07dabec33 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | NULL | NULL |  | NULL
26b0dcfa-de42-40df-9903-179e832b48d8 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | NULL | NULL |  | NULL
caba6f74-2b89-45f8-a32c-90a52d5d8b28 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 |  | NULL | NULL |  | NULL
0eb637ab-60cf-4b3b-b8ae-840ddb8b5cf1 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 |  | NULL | NULL |  | NULL
e70af0a7-2aa0-41cf-8c43-6486ee763173 | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | NULL | NULL |  | NULL
25ff2b77-ef21-4496-b38e-9a8111541a44 | Padmount Switch | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | NULL | NULL |  | NULL
9ae2ab3f-b422-4680-8c42-2921922e1c1f | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | NULL | NULL |  | NULL
a719487e-a750-441b-b85f-04a822e554bd | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | NULL | NULL |  | NULL
7f028d2a-90c8-44d1-b2c5-70c6d9c66a4e | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | NULL | NULL |  | NULL
5ee1b427-c329-4379-8db0-a2052d7642cc | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | NULL | NULL |  | NULL
3d3a05a7-c603-4c90-bad2-0dcebecd2e53 | Junction Enclosure | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | NULL | NULL |  | NULL
11f778af-d1c3-469f-a294-ebb58f0efb19 | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | NULL | NULL |  | NULL
de7edbd5-f702-4c28-a3ca-d686c7e9311a | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2022-12-20 | Level 2 |  | NULL | NULL |  | NULL
43ab3ef7-b7d2-45a5-8fda-42eb651834c2 | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | NULL | NULL |  | NULL
c32b12be-062f-4209-acce-3b56afc9ff2c | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 |  | NULL | NULL |  | NULL
2d968f2b-c0c2-48ac-a981-41d4c4c06d4d | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 |  | NULL | NULL |  | NULL
9bb99be4-599e-48de-a5a8-3adeb285894e | Junction Enclosure | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 |  | NULL | NULL |  | NULL
eba29318-c221-4eaf-b989-0ba7d80e26ab | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2022-12-21 | Level 2 |  | NULL | NULL |  | NULL
ceae8a3c-ebaa-48c5-96eb-3820c7acfeca | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
98880d10-31ab-4fd3-bd11-918b54d50281 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
edc285b9-13e1-4d0b-b27b-8ac71239b037 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
b043c885-86d2-4708-a4a8-d4c523c38710 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
9815eb27-a84d-4d74-90f4-48b89dbd5194 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
2d440729-aaad-4cbe-b9cf-29f1a2671023 | Padmount Transformer | 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
9b2b4f00-bf87-450b-b218-4bd61980c528 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
259e0f78-ef03-4bec-b5d0-52870c54dd63 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
6fdfe8d9-f1d1-4987-afa5-100642f24f8f | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
2f431f96-ba99-48fb-b4ed-144018357c85 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
4006d224-a3cd-41e1-bbf4-2f8e33663527 | Junction Enclosure | 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 |  | NULL | NULL |  | NULL
433df26e-b9fe-46b3-ac84-8f2d3d679ced | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
ed1651d5-b910-41dc-a308-9c61a77f537e | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
e0d50655-43ff-40fb-bb34-dd1edbc37ac3 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
1f24d5d0-8418-47f1-897d-4683b8869b3c | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
4a12f514-e185-4ea2-9ffc-50bb9db60e56 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
6a00524e-e4bb-48f7-ab2c-8930f7cddceb | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
08d547e8-a5c2-473a-a6be-84f511b6d5fb | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
f3182b1d-31f0-4c76-97f6-63e1d518d9ec | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
d9cf66c2-337d-4eb0-b597-6165a1a0e021 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
1eb15c5c-161b-4a25-b21c-3dba971c1f6f | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
a5eee544-b786-4e61-a196-4bd701207d97 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
dfcfdca6-6336-43ba-b883-e93be03864cf | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
1104ef60-88ca-43c9-bdf6-97494ad8fda6 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
00ae7a6e-21ce-43f3-8e6a-e9c5360de7fd | Padmount Switch | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
b9d0b771-b60d-40b9-bdb6-3f6e28f4a8d0 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
0277508f-0c50-4703-9be7-9125d4268361 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | NULL | NULL |  | NULL
1e9a1327-0c87-46d3-bf4e-f7d4a57910f0 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
bf15e60a-78ab-448d-b152-b3a0481513e7 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
7362db7c-3418-46b1-b363-050ebc6befd6 | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
86c714dc-ffa8-4b1a-848f-e5d8b0e30c5e | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
3cf79ed8-740f-4afc-abb6-af5a8d24cf81 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
85876347-5fe2-4ec0-a549-8c3ebe25f0a8 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
ebbebcd8-d748-458d-b72b-0b3cb3a8a81d | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | NULL | NULL |  | NULL
dfd24fd6-91b4-4bb8-8839-a82c1dc935e2 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2 |  | NULL | NULL |  | NULL
d266625c-43c3-4c3c-94e3-23d778ea75a3 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
01bebe7d-d676-4e4d-878b-d83a0d6dc154 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
00baae16-87f8-4ef0-a371-677f6b3fc9d0 | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
4734d0db-d69d-442d-9329-a72bd49e6426 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
0dbd06bf-73c9-47f4-b82c-fd93a575e3a5 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
c6690925-fa90-43e6-ba6d-049b1e0e9c3f | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
dbc3e3b3-ae05-4c5a-9963-18c961f030ea | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
4bf630e0-88f5-4909-bdc3-531419564305 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
f2a2a997-eeb8-4c09-877b-e9fdcb6035c0 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2 |  | NULL | NULL |  | NULL
2db31abf-c0c9-4fa2-9a85-9c046769046a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2 |  | NULL | NULL |  | NULL
c5d55497-e65c-4f7d-ab84-8e9cdf4e869a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
7c8bfe0b-609c-4ba6-a3c1-85b5d2ef29ba | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
1afa07df-5652-4731-a553-837aea85f6ef | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
7ecacf7e-521e-45bf-bb42-2b4274086fde | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2 |  | NULL | NULL |  | NULL
31a84e3a-8718-4206-8d68-4eb3f1824895 | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2023-01-20 | Level 2 |  | NULL | NULL |  | NULL
aea6ccf9-6fad-4278-87f5-ba0510d99b5f | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
29bce270-d482-4724-924d-613e6e3fb41a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3 |  | NULL | NULL |  | NULL
07721d5a-ad9b-47f9-8819-d39cf45b9d5c | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | NULL | NULL |  | NULL
472eb80e-191d-40fd-ade0-ae3e51c4e6d1 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | NULL | NULL |  | NULL
d267c7e5-4ceb-4199-97f7-bf2048740895 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | NULL | NULL |  | NULL
da6dacc1-4a6a-4394-957c-924cb73056d8 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | NULL | NULL |  | NULL
103f1ea9-8a8e-42f9-a2b3-3525f31e499a | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2023-01-21 | Level 2 |  | NULL | NULL |  | NULL
1f99e0f4-136f-406a-8262-107ae1a80f08 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | NULL | NULL |  | NULL
1aaa5c1f-bcb6-4cce-9787-100a211eb9e5 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | NULL | NULL |  | NULL
6cc1fc5a-97c5-4a06-a0a6-da51d2293a39 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | 2022-10-26 | 2027-10-25 |  | Has zip ties holding elbows on. Need bails for future (non emergency)
d26fd316-98a4-484a-b296-4ab7bd2d1fd5 | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3 |  | NULL | NULL |  | NULL
b65d9914-75b7-42d7-87c2-3a1b5618bdb9 | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3 |  | NULL | NULL |  | NULL
df04d907-f050-4e06-9ae5-67856b74cbd9 | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3 |  | NULL | NULL |  | NULL
32eac4d9-d7a9-4d84-afbd-d62f0f2bc1fa | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3 |  | NULL | NULL |  | NULL
fc498a09-326d-4d63-9f85-0e58a10d54c1 | Pole | 2 | Transmission | 2022-01-24 | 2023-01-24 | Level 2 |  | NULL | NULL |  | NULL
2b5846ce-5add-4fb6-b30e-110f0be2516c | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3 |  | NULL | NULL |  | NULL
222bee85-4956-4636-87b3-8d20690dc12e | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
ede85024-0ed1-4881-a165-cae441895ca2 | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
8dd8777f-cf04-4be3-b637-99cdbbccd3a6 | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
8f54a0c1-d79e-4053-adb3-8dbe11fabb40 | Pole | 2 | Transmission | 2022-01-25 | 2023-01-25 | Level 2 |  | NULL | NULL |  | NULL
c6449c3e-a68c-4ec4-958d-e4d29fdbb840 | Pole | 2 | Transmission | 2022-01-25 | 2023-01-25 | Level 2 |  | NULL | NULL |  | NULL
b646a044-212a-4883-b835-05df3135e9be | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
099b610b-3d59-4b76-957e-d75e3f85534a | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
1aa56628-a981-4cc2-9c27-8f81f0b0010e | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
900092a9-0d82-4ba2-8e68-2a871ec76873 | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
ffdb08e1-3cda-4d70-b378-a29db53c941b | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
7a8cc998-e2c9-46f8-acc3-c1ce1ebd65ce | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
6c046136-2827-4373-8563-bd0891df2e3a | Pole | 2 | Transmission | 2022-01-25 | 2023-01-25 | Level 2 |  | NULL | NULL |  | NULL
dd4c6a5b-6280-461a-9307-7810ce4d656a | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
79f94430-f7dd-4e43-b791-ac44b00b66bf | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
08977244-361d-49a6-a11d-b7ea84885b95 | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
89cff108-88f9-4315-9b45-e516a53c9b5f | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
4d986c89-524b-49a6-9c18-2c77865ba0b1 | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3 |  | NULL | NULL |  | NULL
228af172-de20-4126-8c9b-17f1104625e8 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
3b13e89d-65a8-4270-8810-28f708bfc6ea | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
71859952-679d-4912-8265-60faa7e2ef99 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
ed1f4cfe-c268-4216-abc5-e013378d3fef | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
99eb7146-2303-4774-b479-2df14edf0fea | Pole | 0 | Transmission | 2022-01-26 | 2023-01-26 | Level 2 |  | NULL | NULL |  | NULL
de0312a9-32dd-4e37-b7ea-5450062d4b14 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
8bf623ee-ebef-4f63-a753-3af34c5f53f2 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
2de29661-84fd-42b7-9355-fdb668ede5d7 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
6eed2db0-a166-431d-8bd6-c30d56d18c7c | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
468f2fdd-e8ea-4ee5-8a89-d9111ae6c9ea | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
df490ce5-67b8-4c04-b025-9f75b0f3f4d6 | Pole | 2 | Transmission | 2022-01-26 | 2023-01-26 | Level 2 |  | NULL | NULL |  | NULL
28a651f7-bf68-40a7-a7d4-87e2666f933b | Pole | 2 | Transmission | 2022-01-26 | 2023-01-26 | Level 2 |  | NULL | NULL |  | NULL
b07a6841-ec72-4547-80db-57b6fb1ba967 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
5f2162e3-67aa-44a3-9117-68f66bec77ca | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3 |  | NULL | NULL |  | NULL
043fae98-ccc9-44de-a7c0-fa93e21c647c | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
8bfd5005-be1f-41ac-8a4e-f257533a2c7e | Pole | 2 | Transmission | 2022-01-27 | 2023-01-27 | Level 2 |  | NULL | NULL |  | NULL
36db653b-49fa-4fff-a66e-f48cda801d8c | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
8d86757a-3c9b-42af-adc7-06796d9d7a29 | Pole | 0 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
854ae423-8952-4f95-b779-391c374b506b | Pole | 0 | Transmission | 2022-01-27 | 2023-01-27 | Level 2 |  | NULL | NULL |  | NULL
8c70cf5e-777d-4e6a-a0e3-216ed425c4a3 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
c55ae154-c776-4d22-8c01-d3618e007b92 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
5957e772-71c6-475b-a7b0-6c0c4f54115e | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
b816cc8d-e397-44c2-b931-b1693beffc76 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
4170f2d8-a3b3-4fd9-892d-02c99aeff2c0 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
159e1a8c-1def-4adf-85dc-753639c85d4e | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
af3c60aa-0c35-43c4-b18b-54a6a678f88d | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
55163faa-a6bf-4846-a22a-43f45272dba0 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
6e1d1192-67d8-43df-8937-bd582eeac2d0 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
191884e9-eb33-4f6f-bf76-653a77eeefa4 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3 |  | NULL | NULL |  | NULL
78e1a696-704a-4c47-bcee-1338dd0737c4 | Pole | 0 | Transmission | 2022-01-27 | 2023-01-27 | Level 2 |  | NULL | NULL |  | NULL
7b161d3f-c818-4639-a2bb-a97f1b8dc49e | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
310df571-c1f2-4150-b7d9-9590cc000ce0 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
9db076d1-85ab-4f7b-8fe6-cebe9e9e4372 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
240dd5b0-bf4b-4d2b-9958-dd0349c52e71 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
6dd8d446-3ba3-4675-81d8-13aadcafe105 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
30e9314b-3fc7-4ef3-8a8f-8672f6471c83 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
32ecb370-1fe2-4223-9aa3-b3b344016ad4 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
38ea6374-a530-4a97-8051-02e116fa36d8 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
bf41e8c1-f20b-4868-bd31-488ffc926480 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
64de3135-7326-462c-b984-7f93c432fe62 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
19034374-606f-44f0-bbca-bbc9c8e6c6d5 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
80b3a676-69ca-4447-8044-503c203f9f54 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
3e5aa20b-287f-4e65-8d89-20f2b57510ef | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
93ee02b8-6f36-4c48-a150-07ca5b99df53 | Padmount Transformer | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
bfbc3d9d-99ea-4edd-91aa-d26abf3aec1e | Padmount Transformer | 0 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 |  | NULL | NULL |  | NULL
c2494965-76d3-4f24-9c76-06d620e419d3 | Padmount Transformer | 2 | Distribution | 2022-01-28 | 2023-01-28 | Level 2 |  | NULL | NULL |  | NULL
fee644bf-d820-47ff-84ef-ed0a8f4c90fe | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
e7f8b7f3-8c67-4c62-a2d3-25de36bddacb | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2 |  | NULL | NULL |  | NULL
45272cd3-3f95-4a7b-bae8-62c8842024cf | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
5cfd89ec-b5bf-4403-a62b-7de5a991b46e | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
14a55c3d-7228-478b-9c15-e17f4b3f3dcc | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
79500704-6812-4c62-823b-ede8492e679d | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
453370c9-9491-4498-89a4-34d078f014b2 | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
a945fddb-f3c3-44de-a109-e0d56866c621 | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2 |  | NULL | NULL |  | NULL
79258e62-ee91-4690-9408-c165c6761acc | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
b2ae0f31-3cfd-41dc-9a14-e0695e2c3162 | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
74d3df68-d906-4449-be83-d39385d41faf | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
4683e080-f392-4e3b-95c2-a95e274ac53a | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
ec0ae177-610f-40dd-8840-854efb5ca0fc | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
3863d8ff-96e3-4363-8e01-44bd64f1e23d | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2 |  | NULL | NULL |  | NULL
ee8b96bf-0235-4a6d-b410-3adc36b03f94 | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
d53e934e-5450-43ab-981c-1a4c39321b26 | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
697dd3f0-21f1-48f0-bf87-f8c7b3d3a00a | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2 |  | NULL | NULL |  | NULL
c4e018ac-38c8-4b21-a021-3434ef36aed7 | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2 |  | NULL | NULL |  | NULL
0f04e37b-11c4-4417-839e-18c95bb58812 | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3 |  | NULL | NULL |  | NULL
89554432-36cf-4421-a905-75d794760a16 | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2 |  | NULL | NULL |  | NULL
8c24bf14-2eb8-4e22-888a-6337abc1cc7e | Pole | 0 | Transmission | 2022-02-01 | 2023-02-01 | Level 2 |  | NULL | NULL |  | NULL
c683f763-e432-4ba1-9825-fd7bf223df28 | Pole | 2 | Transmission | 2022-02-01 | 2023-02-01 | Level 2 |  | NULL | NULL |  | NULL
40ed4c65-72dc-40e1-bb31-024a4eaeb42f | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3 |  | NULL | NULL |  | NULL
cd06f12c-7067-4332-93c2-1bf2de1e0fac | Pole | 0 | Transmission | 2022-02-01 | 2023-02-01 | Level 2 |  | NULL | NULL |  | NULL
b5a819ee-8a32-44bd-9ab3-4557bc103c3d | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3 |  | NULL | NULL |  | NULL
f9f147e9-2310-4fd9-8566-3b168ad678f2 | Pole | 0 | Transmission | 2022-02-01 | 2027-01-31 | Level 3 |  | NULL | NULL |  | NULL
8e910bc3-7b15-4540-9482-fe25885e484c | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3 |  | NULL | NULL |  | NULL
bb6f0d85-ecd7-4884-a166-b09df0130823 | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3 |  | NULL | NULL |  | NULL
673b2574-95cf-4487-b75a-9bd29aeba34f | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3 |  | NULL | NULL |  | NULL
1804e337-8682-4fa3-90af-ab5a106c71e5 | Pole | 0 | Transmission | 2022-02-01 | 2023-02-01 | Level 2 |  | NULL | NULL |  | NULL
47a98e2f-f112-4294-9698-44510b7ddfe7 | Pole | 2 | Transmission | 2022-02-01 | 2023-02-01 | Level 2 |  | NULL | NULL |  | NULL
b66c6340-5f3a-4341-ac49-6bfce30c3977 | Pole | 2 | Transmission | 2022-02-01 | 2023-02-01 | Level 2 |  | NULL | NULL |  | NULL
181f236c-f525-4d85-acb5-0905fd151847 | Pole | 2 | Transmission | 2022-02-02 | 2023-02-02 | Level 2 |  | NULL | NULL |  | NULL
eef9f8e3-0d94-48c5-8767-e524d5a51daf | Pole | 2 | Transmission | 2022-02-02 | 2027-02-01 | Level 3 |  | NULL | NULL |  | NULL
0616218b-bb19-4d87-99e1-0e825bcd16ea | Pole | 2 | Transmission | 2022-02-02 | 2027-02-01 | Level 3 |  | NULL | NULL |  | NULL
7a202396-2fa4-4d61-aba4-2c26ca013098 | Pole | 2 | Transmission | 2022-02-02 | 2027-02-01 | Level 3 |  | NULL | NULL |  | NULL
e044ce00-f559-4a8f-b3ce-01599b55f35d | Pole | 2 | Transmission | 2022-02-02 | 2023-02-02 | Level 2 |  | NULL | NULL |  | NULL
e0a1751c-bdfa-4331-8979-9128fd95f145 | Pole | 2 | Transmission | 2022-02-02 | 2023-02-02 | Level 2 |  | NULL | NULL |  | NULL
eb0ee75f-54e1-4190-bbfc-c675345a4506 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
3b411f7d-7f84-4058-aeeb-38aeb8b9ae3e | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
4a7144a5-f9f3-4ff2-a4c9-94df8b05ec85 | Pole | 2 | Transmission | 2022-02-03 | 2023-02-03 | Level 2 |  | NULL | NULL |  | NULL
0a5f34bb-89c6-4d6f-88e6-975684f2b44d | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
ccfc32d6-007e-4975-aaf2-5b54592213bd | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
2ae45b42-6bdc-45a4-8c14-68dc424b9375 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
aaffcd1b-a947-42c5-b502-27c72cdab91b | Pole | 2 | Transmission | 2022-02-03 | 2023-02-03 | Level 2 |  | NULL | NULL |  | NULL
1b830366-a6c7-4b26-ae93-86da0e17ae57 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
8e8cc5cf-35da-4c8b-8bba-06cfc398c5a3 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
db955333-1b48-44ff-a86f-eb29f060cb2d | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3 |  | NULL | NULL |  | NULL
d91d5763-eb98-45d2-b25d-14175af96863 | Pole | 2 | Transmission | 2022-02-04 | 2023-02-04 | Level 2 |  | NULL | NULL |  | NULL
863da285-edbf-4295-b8c2-fe56458d6273 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3 |  | NULL | NULL |  | NULL
6f851d3c-aed8-43cb-83c7-ed251a712fb0 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3 |  | NULL | NULL |  | NULL
4caed8d0-3562-4ccf-8268-1666563489a4 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3 |  | NULL | NULL |  | NULL
5557cf6e-722e-449a-b1c9-9d5b57bf62ed | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3 |  | NULL | NULL |  | NULL
f00f17de-b84b-4d40-bccf-c6688a380e85 | Pole | 2 | Transmission | 2022-02-04 | 2023-02-04 | Level 2 |  | NULL | NULL |  | NULL
e491bab9-5918-49d5-910a-d85306c65fe7 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
50eec48a-d4d0-451b-8f8d-7bf69be83d88 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
ca052ec3-6474-4b71-9760-46f14f99c04b | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
3cd8779a-dd4f-4a80-bd0f-da912a22a440 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
7ae3c14f-2dbc-4e6d-bd76-be4e2ded08fb | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
3246d659-6d77-4831-90b6-cea9af7d79c8 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
5a44b1f9-daf3-47d2-9906-da650f080764 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
2ef13931-0df6-425f-baae-b99d67aa692b | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
9b504635-8529-47ad-987c-e9c222dfaf87 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
0f5d4677-fbd6-4d80-881f-e1aced3e76ba | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
59814633-5d78-46c3-98a6-d6a793ea0993 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
73c23c0f-66aa-4389-a9e0-3c4e21a9372d | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 |  | NULL | NULL |  | NULL
c8b0d519-5ed0-4d04-ad75-c9644ff6b414 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
4fee4d82-ce54-4497-92cd-bef5e1a98bcd | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
40731215-a42f-447e-8e09-2a70e393c3f5 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
48876cbb-c205-4317-900c-8b1b899ffb53 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
9d4aeb38-6c02-4d0d-9d96-ecf2b02be560 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
024a504a-a708-47ea-a6e1-6aea8430b429 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
2ba86207-016f-4a6c-8374-f575e54bc4d0 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
5e8d7c1c-19a9-4c15-bd56-e3877901be45 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
26733d3c-41e1-4939-b0c9-974e9b7aed94 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
fdb754c7-0348-4e32-8e09-bf70bf37e73c | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
47d9ac1c-3101-444c-a723-f6b156677068 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
c8948eb2-ee8e-4a7a-b39d-4d0fb33f4b2b | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
bd2ecedf-a2b4-4298-b714-ea376549d553 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
45d8b59e-b40d-437d-9a7c-2b9b922f4f0e | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
6fe1e808-51f9-4bbb-b36b-38c49894d5df | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
ba6e7d0f-d2c6-4b19-a729-2cf4fa5b6aba | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
96ed71cd-d30a-4844-86b5-88e009d4f810 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
c60090d2-1d60-416a-a60d-d31e4a6797b9 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
74d3db50-2958-4ea3-aae7-6ec687c6f7f3 | Pole | 0 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
93088519-5600-44c8-b679-2de6d10b40fb | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
e755036b-b4b9-46e2-9efe-88413bcaceed | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
829bc174-98ef-4def-b02c-c28427280eb9 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 |  | NULL | NULL |  | NULL
689a9694-35c7-4e5d-8fd6-76093054c955 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
94c1c1f8-c648-4047-ab7b-42658c6e8c22 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 |  | NULL | NULL |  | NULL
c897e307-c5e7-4f21-b76c-66ebb1c7c7b0 | Pole | 2 | Transmission | 2022-02-08 | 2023-02-08 | Level 2 |  | NULL | NULL |  | NULL
b1d99005-1e7a-4463-9842-bcd00c91afeb | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
361ad578-c9d1-44d6-83fd-a6171688612e | Pole | 2 | Transmission | 2022-02-08 | 2023-02-08 | Level 2 |  | NULL | NULL |  | NULL
a5cdc95e-52b2-4bbf-a91a-46e8ac3e68eb | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
24567a0a-842b-4466-8e30-ec5914884b87 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
27a4e67d-0b6f-45b8-bda6-d421370b0101 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
0d4d8486-686b-4e59-9502-cf8d8dec856d | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
b5aa8e4f-995f-4832-8c9d-a0f0382225c0 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
7b48c7b5-e511-40cf-9c07-908d5a0fcc4f | Pole | 2 | Transmission | 2022-02-08 | 2023-02-08 | Level 2 |  | NULL | NULL |  | NULL
8fd2d194-0cc3-4236-b131-692a3f7afe6e | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
262258f9-4b4a-4482-ab78-5c5d251ff5d4 | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
aab229c0-4d78-4d7d-ae92-e8778adf11b9 | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
3a508812-be8d-4175-855e-66a8a93c1e9f | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
c5a11c96-f73a-4aa4-a8e8-9b0f66fc6d10 | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
6e920e41-7726-4669-b859-7885e6e5d4ff | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
7867d964-1f89-4b8c-9e83-e87cc761370e | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
2f8b7c0e-9f64-40b0-9e06-c2e61b46ab5f | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
6541e1ef-582c-4724-abc1-27c4a5ff6ff1 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3 |  | NULL | NULL |  | NULL
aee47510-2510-4c8a-866a-dfc1851e7622 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
8b77616c-e838-4a9d-9d19-43e258cce374 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
8ebbf735-2967-43ce-a524-164f20cfb254 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
ad3fb623-0e83-4c5e-9c25-c81f37faa957 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
1418d789-7bc6-4a55-93a4-632676a3455d | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
409e354b-5e35-4b21-9f26-c5349fcaf695 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
65d2bf68-d300-4cd4-b5b8-897247934d06 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
3ecc3630-65b8-4cfa-b026-5aea84a78cc9 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
dc0dde83-37dc-46dc-abf8-e909708acf89 | Pole | 2 | Transmission | 2022-02-09 | 2023-02-09 | Level 2 |  | NULL | NULL |  | NULL
3a211bc7-0824-48e7-ab31-826154608772 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
bbb0feb7-c394-4e1f-b724-67b7a5aa828d | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
e62a2953-aa96-437a-adc0-6eca5113006a | Pole | 2 | Transmission | 2022-02-09 | 2023-02-09 | Level 2 |  | NULL | NULL |  | NULL
9c8a0198-fe64-4ece-a649-80e87f783fdd | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
04d57a4f-0ec3-42b6-914f-a3469fd5f3a2 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
f9deba75-bfe9-44f9-8b9b-6a996ee65564 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
4c4a84be-2c92-4176-b64c-03051d78995d | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
b164fc35-2500-44d9-9ece-ebfeb6b00cdf | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
b4aff6f8-b0f6-4950-a3c5-64249790acc4 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
b82ee00e-e10b-462c-b893-fd1c6cf6c836 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
3377288b-7821-4177-8bf7-5452691c702b | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
7838ca3b-97d3-41ed-864e-90337de4d2cb | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
e491c326-4ddc-480c-af9e-5cf024b89dd5 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
f5e435d2-8dcb-4ab3-8d2b-874bf6cfbc58 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
e28837f0-09b3-4e71-a818-70bd5fb9c6fd | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
685c2e3b-7e3a-4f84-afcb-a540db1bd42b | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
e94c659b-4d85-4b88-9972-6d2f0fc95a7b | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
0d19c7ec-c428-45af-9d00-249b7b29c16e | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
9e1bba3a-8133-4bcd-90e4-4a1ad40a0f54 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
f5f3a27d-0f28-41e2-b904-041b5222c77f | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
11b9b340-0f94-43dd-b4e7-f59a375faf5e | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3 |  | NULL | NULL |  | NULL
f4ed4a8c-c4a4-4a20-979c-921a00c4a32f | Pole | 2 | Transmission | 2022-02-10 | 2023-02-10 | Level 2 |  | 2022-03-01 | 2023-03-01 |  | Insulator broken on 7200 center phase
72180a74-92d1-4ee8-af48-47fe23503a02 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
373081f1-43f4-43b3-9ac0-ac3005b9bc1c | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
e1bc3482-f8dd-45b3-9c5c-02021907d297 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
ef2c5216-f05c-4c86-aa97-c358aa5d4da3 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
347a3df6-003d-4e15-a10e-c538cc3aa9c2 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
92273650-5c8c-4b31-80fb-371286773c33 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
7ca72158-fca3-4608-963a-606b7090802f | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
84f38b4c-878d-4aab-8e63-f0fca525ea00 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
98e997d0-bb60-416e-9d8d-00e00d072fc6 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
336ffc13-c07a-4ce2-908b-b94223b4b313 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
f8b26909-0c63-4bb4-a557-61764d582af3 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
afc2c3c2-8cc4-4f9a-bf8b-acf9f7e7afec | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
8577e9c9-d067-43e7-b353-dabea63707cd | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
4ba7a9c4-396a-4e83-b196-597dc613f730 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
641c09cd-7df8-49c1-89fd-0c28e7ab180e | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
fd25aefc-5092-45e8-8b3f-41191c2b6338 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
ea3ffd3d-76d1-472b-962c-05a5f788a14a | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
b5369aa0-9d84-4889-8a25-ba2d224cabd7 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
4e714cfe-6bfc-47c4-9d1d-9c79c9631560 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3 |  | NULL | NULL |  | NULL
5f3dff51-319e-46b0-98b6-e3656b60e743 | Pole | 2 | Transmission | 2022-02-11 | 2023-02-11 | Level 2 |  | NULL | NULL |  | NULL
7975eba6-4ada-453f-9f75-5f0e06d525a9 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
98797cd6-beba-4dd1-a582-96adbd90c85a | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
ef0f6d13-2f30-42cf-a839-16c3b8bd0f84 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
48cde3d7-c26e-4fee-b6f5-36d1b31c6894 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
a91bcfcf-9eed-4f03-bb0b-5e5807b9a478 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
2203535d-0869-461c-ab49-ed472ad0a845 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
1048a037-c19e-4410-a822-f54a33a094e2 | Pole | 2 | Transmission | 2022-02-11 | 2023-02-11 | Level 2 |  | NULL | NULL |  | NULL
f98781ca-7f80-4d10-9921-e9f3e33dfecf | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
5b5d578b-5cc4-49f1-909c-43d1aa697d7e | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
5027ec82-9617-45c1-b457-2c865828a8a4 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
3255b111-9ee4-4ea9-9911-131e79871f89 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
9eadc902-960d-462b-ae6a-85a890a2b9ed | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
e8ea4709-8a1f-41fc-bd5e-022f9f4e755b | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
85cf0826-67ef-469b-953f-fff1489e8e07 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
7889ba89-05dd-4b28-98b5-2c780633160b | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
640e56e0-8c5b-421e-ae26-999b8e6b038d | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
9a7e0f58-d901-472f-9d39-46d84a1deb44 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
27271a79-83ee-4590-bc95-201c162d2d62 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
0ed4b466-e953-4ed0-a059-eec179a89ccd | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
f93c7ddc-36bf-4e1f-aab6-bcc9ca37f7b9 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
6eafa25b-0379-4a53-a155-a00da1809bdf | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
0096ef7a-d300-41bb-894d-8731d7d42a20 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
8fdd7ca0-48ee-48e5-8706-1e05f3dc29a1 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
90dbe23a-5b6a-4fe4-847e-069aa09a1b87 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
7fd32072-5cc8-40b7-87e8-a7b5b9a3db60 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
854a7074-a592-4f1a-8b28-994790628182 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
86064895-eec6-4003-b4bf-25c639008185 | Pole | 2 | Transmission | 2022-02-11 | 2023-02-11 | Level 2 |  | NULL | NULL |  | NULL
a778c250-eeeb-44bb-81b9-94f18cf50bc8 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 |  | NULL | NULL |  | NULL
74624c63-4d4d-485d-821d-65a1725e9c91 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
9bfca67a-0300-4dbe-b484-7e9513d71de2 | Pole | 2 | Transmission | 2022-02-14 | 2023-02-14 | Level 2 |  | NULL | NULL |  | NULL
52bf416b-bc47-43d0-8ad9-ac88cbe69068 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
d9e040c1-b18f-4b27-a4a8-b2008765546b | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
17407ecf-d6ae-4333-a45f-c72e0dd2f76f | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
35475c42-c6bb-4c3b-8f31-ecc9fafb1fc2 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
b8daa9ae-7ca3-4e7b-b9d5-7b92c08e954c | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
3bfdd5a6-e333-4da7-a375-20004b5d6fc7 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
0b4dbea0-9aa1-4c2d-98af-0e14ef947e5b | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
5aff8b59-a6c4-4e8a-b3c1-87ab7457b5aa | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
90b0a8f3-97ea-48a5-b83b-b41ce2aba6e0 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
94d69d5e-b9c9-43e8-b57c-6b5f4214c313 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
29680063-05b2-4883-ae3e-bd1e250dd46c | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
36f334c7-a190-4f99-b45d-1e740329be2d | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
a44c9641-1ef0-4d78-a32a-2fe5306a978e | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
1cf59be6-c5e4-4755-aefd-924f11e06867 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
d6b20f75-a2c2-431e-86ff-7afeed876eb2 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
01f2f755-36c3-4cd8-85cb-6c5d1280b754 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
daeaf391-654d-4291-aa01-3ff6de002d49 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3 |  | NULL | NULL |  | NULL
18bd9e4c-5b55-47fb-801d-d163bfd77b96 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
87462660-e568-41cb-b54b-9a9c864adca1 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
7da9e69c-245a-42ae-af6b-417204b8571d | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2 |  | NULL | NULL |  | NULL
438f01c7-4e93-4fed-899b-db83aa2f520b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
55899d15-7725-4a37-b2ac-a02ae705d0ee | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
3c6b65c4-c447-44ba-8b8d-39cb1b955f06 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
487ad8dc-134c-47ab-9b38-4b7772b7d179 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
69f3fdb5-fc6c-4016-a37a-1c5b3981f9e1 | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2 |  | NULL | NULL |  | NULL
65be6773-48df-42d0-8a6c-69c015e3152d | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
c062b670-c241-4a35-b934-06669267a140 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
a78cc53e-7923-4c2b-bb1e-6cf59d8a332e | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
039d6d2a-b43d-49d4-9bb3-875ca5452b3d | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
ee4f3c52-702f-462c-8a6a-505e7d518d4b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
e090602f-3ae0-4894-8b91-6c55cfcc870d | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
f80faefa-f6a3-4b7d-a0da-2c08a49e03df | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
38853420-36b3-4547-8e53-0b4f46fe2305 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
553f2862-4976-4606-b812-4a351c550645 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
6bffbf8f-5193-4989-9d4d-868158074cb2 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
f7deaf33-5ee4-4c6b-a334-ec6c4138a5e6 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
a69f610f-2ce0-453c-bf6e-188cddc9421c | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2 |  | NULL | NULL |  | NULL
4e8d9aa4-a7e1-4e57-b12d-d3da98fc7707 | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2 |  | NULL | NULL |  | NULL
248d43da-8321-4808-a946-7cabdb32c13b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
e3f6bb7e-bd0b-4d80-950a-097a99a868bb | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
7e07d202-73f1-4563-a420-00fb3f5d7ffa | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
947bc1d4-4b8f-4b81-a2f2-63d56c37edbe | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
7931be79-59c6-4093-8bf0-f35fff6cfba1 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
02796879-2d8e-48f0-8d61-19999923fd7b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
b22ee7ef-2188-4ff5-b4b3-c54bea5237be | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
3f6dd675-87dc-4253-ab19-28b711bb2c96 | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2 |  | NULL | NULL |  | NULL
761e0631-9e18-4c18-b91d-11607bb6c248 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
da83ef42-52ad-42b2-b8c1-ec12b7d3294e | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
df0e6db0-e95b-47ff-8728-3bae6646c39b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
45ecfcbc-2389-4242-a5ce-de7064b1d746 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
383aa520-ca8f-4e32-9b16-df1d4a27ed0d | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
d890ee9a-0f14-4296-9bcb-cac84e5cb56a | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
b94ff1b6-54e0-4804-a8bd-29e125163ec3 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
3a89e89a-dd36-4b9e-a5ca-d48f3ac4ef29 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3 |  | NULL | NULL |  | NULL
2ec9f44d-2040-42a7-a15d-e49edf39d141 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
9b33a883-46e6-4e44-a5fb-cb23af6f1daf | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
c65a2464-72d2-4e03-b050-aa50e1bec388 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
ba1957ca-b71b-44d6-928c-e08a6c85191c | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
b0f2f717-f4ab-499f-8053-20af695ded7c | Pole | 2 | Transmission | 2022-02-17 | 2023-02-17 | Level 2 |  | NULL | NULL |  | NULL
b0b78394-d538-4c74-bd45-fa3c8b5519d8 | Pole | 2 | Transmission | 2022-02-17 | 2023-02-17 | Level 2 |  | NULL | NULL |  | NULL
2dafe234-c350-4a22-b05a-4618d50078c3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
7f8b7030-ef5a-4aa9-a69b-48627e76fb78 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
9d022b08-baf9-4dc3-851c-5f875c872ae3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
eeda8052-0c8c-45c1-b98f-525241ff9abd | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
5c4f95d1-d523-425e-9963-647e5a53c5fe | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
0ed6137f-68ab-468e-9627-772310bca331 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
701d94bc-9812-47e0-8ac8-132e8531acae | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
70d32056-7851-4462-aa51-fa56955ad38a | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
8621246a-ca6c-4f4d-9c76-f902012c90a3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
077c66c6-f44d-4523-b9e8-69a3c7cfa7b9 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
708ce6c9-1517-4ddc-a7be-264312b1ac38 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
74866de0-16c5-4b62-9d23-2b95b0ad037a | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
400aa66b-215c-4181-95ec-7b0e831f1bf7 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
9f3d9b3b-c7c8-4231-b897-17f0e3dcb676 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
c0382428-dc2b-4b99-8042-c74090e94096 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
9443dcbc-54a3-49f4-bd68-6a4199c6044e | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
f9e503a2-28d1-4614-9105-80b064f10829 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
0d0bbe7f-c4fc-4976-9fab-e6f5da0c688c | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
9dbdf0c5-a323-4342-af6d-5dad03f7cd5b | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
d73ac0c0-0bce-472f-b676-a3d01dae965d | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
271138f7-5681-485c-a4ad-f1121977cc3a | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
724923f7-f34c-451b-9e8c-fe74dd568deb | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
ea1fb652-0fd8-429d-80d0-084ea93c2976 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
99e20059-b9cc-4a3a-9f4b-b2912bf19144 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
9785ba76-1aba-41f1-864d-849a201fd1e3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
49cc4cbe-ae3a-4e43-9dc4-6547476d1c7c | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
0b995957-56d6-443c-8bca-8201f2e469d0 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
c759a3a6-d3ce-4df8-9543-3c2a63ed597b | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
5865ac4e-a73c-4af6-ad1b-2855f0e051fd | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
8d8d136e-295f-4bd5-a39e-370d80b33820 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
47ce586a-09a3-4662-99a2-8fff6187df98 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
44fe6654-06be-439c-887c-70312b9f1c44 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
4cffcaa4-5daf-41a9-8b4c-2a7062fe2ea1 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
c1b5acd2-946f-4d5f-a591-52b40de913ff | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
22d303dd-6f3f-4495-869f-f550c3c1c990 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
ae116213-af5f-42cc-b484-d2d33bee6dee | Pole | 2 | Transmission | 2022-02-17 | 2023-02-17 | Level 2 |  | NULL | NULL |  | NULL
20304509-bc34-492b-a313-18c2622fefdb | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
efbee5aa-3981-42f1-92b4-a6e75952b7bf | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
691e566d-b98f-4afc-8531-bb44156b2843 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3 |  | NULL | NULL |  | NULL
10f20064-542b-4830-af34-68bb174c67d5 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
8bd616ac-809a-4ef6-8ae4-aebb96ae6c54 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
66d67cb7-0a5e-4f49-92b2-dfcc25c0c996 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
877f8b4c-dc66-4311-908d-bbcea4e4d9be | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
7ae8bcc0-ff28-43ad-821f-34df53e64856 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
65a309c1-cf6b-4bed-bcae-32cb6208d3b2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
6a4a1c51-02a6-4b74-b82f-3fcac6619351 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
5bebe5ff-2c01-4b56-a77f-80dcc59928a2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
ac5e64b7-acb8-4a6c-bb1e-19af91331589 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
be5507f0-60d3-47e0-9691-1b65485e38c7 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
76bc5507-d5b8-4391-b358-fd12cb4faa44 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
67d30b97-97b0-4a62-84cd-7797cbc7b27a | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
20ebfdd9-851a-4144-ba77-0625426e7d2f | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
e3510e28-1307-4d46-9454-ec5d1a1ec04c | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
244f07ff-8cae-43b4-9289-1cc2efb2b7c4 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
5ce7533d-3ee9-41e1-b22f-ae9f635c88b4 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
d969d457-fe53-4ba4-b9e9-b87c641c08a8 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
9d0b1f07-aeca-4179-9c61-d5c19e29d82e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
ffd4779b-c0d9-4725-9b42-351f37b59c47 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
552f0a00-eef7-4833-8a3a-4c29ddbf7b79 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
f063a576-c2b0-4457-b0f0-97e0cb588a4e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
e9c86fb0-6313-4803-b85e-72184bea0efe | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
4e389dee-70ea-4356-81fb-848fef83676e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
a4b3aed5-09f3-42d6-9182-f9fe12c38c47 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
0f36032e-a34f-4754-91dc-47ff2a73a780 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
d8e7a254-8a3a-4de6-be80-3ae534416fe2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
96ee963a-a3aa-4fe7-8aba-3a3c507240dd | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
b5061134-142f-4342-8014-0a2d767e3bbc | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
c46eeda5-e1b1-4d5b-b74f-77cffee8366d | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
283a6378-1bd6-4d04-9e97-f397374239cb | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
96ac7bc1-1d28-4af4-8a56-4082430c47f2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
ce444bd1-7843-4a24-97ce-db8d482edaf0 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
37bc1523-6a11-4ff1-86d9-7279f88c8d46 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
10ed8733-af37-4da6-92c8-9fd2f663e4d9 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
f3cd9c1f-4c46-439e-8a76-2812b3465187 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
b574719a-7966-4dfb-b4f3-c52cc84fb70f | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
5e59230f-37cd-4b9b-9a74-00da4dfc6c55 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
1b3ce024-4b1d-422d-a0c3-3f9b51d9ee13 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
4fcae5b4-076c-4606-90eb-7451fcc61311 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
d422ad98-a166-4f00-b5c3-d0ffb783b6ff | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
54f4a338-1b7a-4e1f-a3df-9f70fe166300 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
fb9048f9-5624-4264-9d5b-e8011ad6c8c7 | Pole | 2 | Transmission | 2022-02-18 | 2023-02-18 | Level 2 |  | NULL | NULL |  | NULL
a1244c25-99ee-4524-b910-82767ebe789e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
f271782d-5511-4e1d-bdf3-28767b2d367d | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
9ebdfd81-25dc-409d-8f99-287299a905da | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
78061a04-4fec-4305-93a4-7cfd7a4b02ae | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 |  | NULL | NULL |  | NULL
859ba831-d0d3-4c11-84f3-8617d3494973 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 |  | NULL | NULL |  | NULL
d6f3c386-d7a5-4808-b5dd-fd681b500b73 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 |  | NULL | NULL |  | NULL
bc29ee4b-f7a0-4828-968d-3e0639b738ec | Pole | 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2 |  | NULL | NULL |  | NULL
10e876c6-2a1b-4a9c-bf84-44016aeb1892 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 |  | NULL | NULL |  | NULL
5187767b-3cdd-4cdb-8f9f-10e4aa4480da | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 |  | NULL | NULL |  | NULL
bbfbd9e5-2a43-4cf9-8d63-384354e6193b | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 |  | NULL | NULL |  | NULL
ff865cf6-cf44-45b0-861c-7d275610101b | Pole | 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2 |  | NULL | NULL |  | NULL
264b5ab0-413d-448c-8116-10d1869718da | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 |  | NULL | NULL |  | NULL
fe07a373-030c-4e43-91d6-e4896f5a4256 | Pole | 2 | Distribution | 2022-02-21 | 2023-02-21 | Level 2 |  | NULL | NULL |  | NULL
37fa9bba-bcbd-412a-95af-4e2d9e84c822 | Pole | 2 | Distribution | 2022-02-21 | 2023-02-21 | Level 2 |  | NULL | NULL |  | NULL
39633e0d-56ab-497f-8238-3a8df6bf0422 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
27bf932c-cdd0-42fa-bae3-ffae46450035 | Pole | 0 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
1d7adb21-0340-4c49-bdee-7f24895a2ca2 | Pole | 0 | Distribution | 2022-02-21 | 2023-02-21 | Level 2 |  | NULL | NULL |  | NULL
dd434e8d-f495-42ae-8a3c-fbc483fa85a6 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
77826756-5e17-4d26-b134-e37ade697d3d | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
89f49812-93ae-46ff-962f-b7b67ea85506 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
c8f056ac-db16-40d8-8fa4-89a632372d17 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
e234c2b7-5a0f-487f-a649-9d28f00d1a91 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
3987970c-c1ce-46c6-b15e-53928aa69149 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
02e2ef56-f561-4295-acac-ac41e9847395 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
e729f543-36a5-413d-b31c-4375990c69fc | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
935fcf7b-57f0-4309-b78f-19e5b8f9afb3 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
4b4c7bc1-cefd-4e62-be59-d42b422ceb0b | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 |  | NULL | NULL |  | NULL
0cd63da1-526d-4da0-ac70-547f15f64ce0 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 |  | NULL | NULL |  | NULL
88843017-9c65-45d8-93d1-b860d32ae628 | Pole | 2 | Distribution | 2022-02-22 | 2023-02-22 | Level 2 |  | NULL | NULL |  | NULL
c6096db7-aa5a-4245-a2c2-a96b032299cf | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 |  | NULL | NULL |  | NULL
6b61782c-fec9-4fae-bcdb-f8a67d3504f8 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 |  | NULL | NULL |  | NULL
ba12ac90-f81c-4d8d-9070-2cff1aceae74 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 |  | NULL | NULL |  | NULL
bd5384c7-4bd1-4745-97a1-ac54117d1068 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
f4b7252d-7706-4bb6-9124-504b40c9892b | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2 |  | NULL | NULL |  | NULL
ffe7051f-b693-481e-85a8-15ddc753f00a | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
6173cb7a-c893-47af-a28a-4a74f1e27324 | Pole | 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2 |  | NULL | NULL |  | NULL
7494c47b-292c-48e2-88e2-df9f87ce0379 | Pole | 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2 |  | NULL | NULL |  | NULL
5a4c2575-d784-4717-a5b9-5b04aecb63fb | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
07c28662-ceac-4cd0-90ce-8232d672aabc | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
f785a383-b8c7-4949-92c5-a96f19b711ea | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
7f527968-df73-49cc-9f05-cee645222c12 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
372548d8-5d80-4e58-8835-e36b0f7f89e0 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
8214c438-9985-4466-ae83-4df0a16e2e41 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
78875fd4-13a8-495b-85ed-64b32539bffa | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
8ea93489-bcfe-4f13-b958-deafc56beff1 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
3caf99d2-0abb-439c-9769-a4ff298a68f5 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
531a22fa-866b-4e53-ad53-89fd92e25d63 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
4b6d1296-b85e-48e6-a916-2b30cb4661b6 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
0140a406-6179-42b2-b2a0-71b36891e433 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
8623e559-0d0a-4e71-a711-b09f3f779f4f | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
efbcf980-3eb9-4358-b4b4-fab2c7cbd84a | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
630fd4ac-7b24-4af2-8518-c56c321a5816 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
b9628861-bc4b-4148-b1fd-949f998b1025 | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2 |  | NULL | NULL |  | NULL
124dea7d-f27f-4eaf-b349-c1c7a50111de | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
f43ef478-f816-4534-807e-30a5f1e2b999 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
5afd6502-8f0f-4a16-bf57-2f2f56ceb31e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
4909c102-847e-4b1b-b3b8-96117b2f076e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
0379701f-b44e-43d0-9341-899221cc2669 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
1c5378ec-3677-4013-b0b2-c329fd782dec | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
36069986-be44-4faa-8aa2-6eda045b2330 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
be02f36a-9b3d-4e56-b48c-c3225cb948d4 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
20450006-f432-4668-b702-b8e36c5bfddd | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
f064449a-ebf4-4c12-8b30-c523861c16b0 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
cac1df23-bf75-4e0c-b092-534cadd6ed8e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
c187a387-0679-4feb-ba14-1b09635120f3 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
7b4ed4b5-987c-4178-8126-47e8fc35ae06 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 |  | NULL | NULL |  | NULL
592a28d7-5d44-4ec4-9df9-d4a543d9502b | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
d5f16ab2-8a29-40b1-85ed-73ee67224e08 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
c19e6e65-7d10-4a44-a241-18982b285b54 | Pole | 2 | Transmission | 2022-02-24 | 2023-02-24 | Level 2 |  | NULL | NULL |  | NULL
5f74188c-7d0f-4654-903f-dd07b1ff2938 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
6ba47bd8-a400-42ee-b779-bb1cc7941ed6 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
bbef76b2-3d90-4a6b-b2a4-4a9c7b9a4934 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
f1e8c6c2-4de8-412c-aa2b-e4963cdf9c0c | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
16d8cd56-e13d-4341-9277-3a576765b208 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
d5049150-9b22-48c4-a7a7-a8b1ec4eb6b7 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
de35ac6e-74d0-42c4-bbe0-ce163b65e1c7 | Pole | 0 | Distribution | 2022-02-24 | 2023-02-24 | Level 2 |  | NULL | NULL |  | NULL
ee11176b-3a19-4089-8484-06d7561fa353 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
617233fe-4179-44f6-8e64-2079d1e94090 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
e7f729ce-ace2-4cd7-b676-9d4d161b25bd | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
4f6414e8-2baf-48f5-b9d8-7b32a0de8f13 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
a8b4ab2a-eb29-4e16-9782-63034f4d0465 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
0c1fa858-08cd-4b10-b081-f06df53fe855 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
8be489ac-8429-4a28-87ab-64885de3e9df | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
a0dd75d0-b4df-4f0f-b125-6856ded774d3 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
41d6a7ff-eb55-4d3b-adc1-f1ad1336eb34 | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
0d0ce0e9-ab78-4daf-89f7-b341bd58b579 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
fa420291-7268-418d-a286-ffc4591be4a5 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
7c3e3bb4-6a83-4dad-b9f8-7f3ed34fde94 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
eb996fe9-c479-441a-9a73-d88a38ca7f49 | Pole | 0 | Distribution | 2022-02-24 | 2023-02-24 | Level 2 |  | NULL | NULL |  | NULL
688af7c8-9566-4874-b32b-950521a06c76 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
50ec66bd-cf4a-43bd-86e2-f06446bbfb0e | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
ff36785d-4895-4b39-bcfd-64f13737584a | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
2241ac4b-d0c8-4428-b8d5-dcc663a03eca | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
d089bd9c-b2d7-4026-9d59-f64fc9a6ec5a | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
8020fb5f-2f00-4302-af7a-fef6bc43c26a | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
e7a4df91-179a-4d39-b3ea-90d33d5661a7 | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
4707987d-5239-43ec-a193-afa0d31cd8d0 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
eae58e54-52f9-4ea4-995c-125da0f0f215 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
653e1c9d-7ae1-4705-8755-43c539383418 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
ea66c5b7-9c80-4ad8-8e4f-c788116c06bd | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 |  | NULL | NULL |  | NULL
c8847889-53be-40b1-af9d-59ce98bc74ea | Pole | 2 | Transmission | 2022-02-24 | 2023-02-24 | Level 2 |  | NULL | NULL |  | NULL
193082a7-e68b-4ce4-8a3b-9b364ebc950c | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
d3b213f5-43c0-4075-84c3-bd43f7297c41 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
356e602a-f24f-4c41-b98a-1b0be6e758a3 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
19e6c6d5-3a10-431c-bd3b-6269206237cd | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
007adb36-353c-4d60-9351-f01847004a89 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
fcde8853-3f14-4a30-91b9-6e7d7e542ef6 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
2b6404e0-300e-4568-b19d-daeb5f1312ff | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
9e1f1fbd-075e-437b-96ed-f2611da9d845 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
ab3c6590-a4df-42c2-8121-9cf7647b2562 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
81eaa342-3487-479a-ba94-4d620a038329 | Pole | 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2 |  | NULL | NULL |  | NULL
e3aff06e-22a7-4b19-9110-190114a77c6d | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
2bf7b5bb-b699-4a78-a386-b22cc4a00aa8 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
1e4290a2-bf89-4ca7-b567-b0f90682ac45 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
e7b213d0-3779-4907-b2d9-3f148b7206f4 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
87acbce1-183e-469f-89bb-f3aafed8179e | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
809af1d9-399a-47c9-8fb6-8efba13a0af5 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
7c10a9ac-4ea9-498f-b730-4b1065e51329 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
aaecfa6c-cfa5-43f6-8b5c-d38d2a748b99 | Pole | 0 | Distribution | 2022-02-25 | 2023-02-25 | Level 2 |  | NULL | NULL |  | NULL
02287107-b5c9-47ad-a076-6b4080f37575 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
bb82f9b8-e802-473f-8a06-6d61c026f351 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
fac502ae-f6d8-4080-92ee-301b5930cafb | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 |  | NULL | NULL |  | NULL
83f5d058-7808-425a-b206-12cfdbffbee9 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
cbee412b-ea08-4e2e-8dd3-d840df3f1c60 | Pole | 0 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
42f85533-e863-4a93-87e7-99415f5e27e5 | Pole | 0 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
0d772885-a904-4855-a0e0-707a9fa963aa | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
fd91963e-a2cc-43a3-a68b-18168ae3086a | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
16402208-3df6-430e-8b4e-ee80422b2254 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
a265bb57-349a-40eb-9932-c92587748cde | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
766c83e0-a3aa-4e77-b637-e8ecaf1b61ed | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
35e5c18b-0dec-4bfc-bf48-1f60948ebfaa | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
c455f87c-68f4-4a74-8c62-9f34c883b9ab | Pole | 0 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
0b6fa2a9-15c2-4fb5-a732-95b67d772a09 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
a6107ee3-4637-4ff1-89f5-6e474a425c0a | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
62489f1b-d54a-41e2-a264-b7bafe0d0157 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
abecd5f2-eb6e-415a-9c75-aba7decef107 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
528d45cb-0f42-4079-b4b8-49fa9b7b5315 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
b44346f8-e0ac-49ec-b4b8-4b41fbd05c58 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
4de6ce0f-cb74-44fa-be5c-062afe46e7be | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
e13607fb-4ea9-4e5a-914b-bb659cba38c7 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
6c09af98-be98-4462-881f-f1d78def1e5c | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 |  | NULL | NULL |  | NULL
9231d6f7-6fa9-45e8-aec7-b40fecdc7368 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 |  | NULL | NULL |  | NULL
4aa52295-2248-4da6-b326-9dd4b4f35a9b | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
122eb7be-1c77-4245-a809-e09c54b2adfa | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | NULL | NULL |  | NULL
1aca49f4-c0cc-4aef-a70e-09b25742eab9 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
fe559a22-c1bd-4951-804f-41f2a2e465dd | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
727405c8-18bb-47d6-b2d6-6f98a423c685 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
2fa0521b-e61b-416a-8f2f-3c0c17fe21fc | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
e0db64da-2c9d-4cdc-b766-f48469b85041 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
1e45b898-c7f2-435e-8349-fc7809bc9f55 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
cb9757c8-d8a8-4991-8515-a062a28b9290 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
abc16615-7808-45bd-8c70-2b5542d2bcc1 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
a40c9abe-5c76-4fd4-a070-8f009638f197 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
d117c99e-354c-49ac-b4d8-105333acd364 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
2b9f9207-d3aa-442d-b07f-39d280f770b2 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
fc784963-eeb2-4201-822b-6048a528620f | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
ea17fc89-d740-4a5a-8096-ede5873481dc | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
4a28b787-6012-416f-8b40-7721bc6fcedf | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
25f2e63b-c85c-4234-9ffc-04de760a6776 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | NULL | NULL |  | NULL
24618b52-1670-4e55-a09c-e2d1fb43c8cd | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
e55eebf1-bf37-4a9a-bd12-b1932e810128 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
16d48e85-5980-4fb0-80e5-af92cd8c0c12 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | NULL | NULL |  | NULL
f31d21e5-944e-48ac-bcee-c29074c92159 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
a4347ef1-435d-48df-96da-8f1ed3f0eb54 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | NULL | NULL |  | NULL
0986680f-8214-4c22-94b3-8c32954200cb | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
6d074cf4-a17a-4fe5-bfe0-6de6cb56cce8 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | NULL | NULL |  | NULL
0ae7b352-2068-4074-8fab-d548e5c6c68b | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
3bbcdad2-e1dc-4fef-810a-019ee6ab95b1 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
859fd0c2-8fa4-4bf2-9659-587b4e5732ba | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
86d91ef0-bb98-44e9-941b-17e6c4447ff3 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
630e4df7-3669-4d57-87d2-cdffd369ea1c | Pole | 2 | Transmission | 2022-03-01 | 2023-03-01 | Level 2 |  | NULL | NULL |  | NULL
54c80c86-bda6-4faa-b364-0de74817354f | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
9eb1cdb7-024f-4897-ba8d-65150cefb10c | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
950a67c5-1730-4be5-b8f7-2437a7ad8fb3 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
0d16fe95-8650-4231-a428-68409e9a8f3a | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
9c4203c1-b39b-4541-b373-fa82aaacf2bd | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
68b18736-b7b4-4bca-8d46-59248f476a1c | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
dc5d2b55-535a-4145-9186-3c2a0aa11515 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
2c55fe27-4cd1-4e2a-ae51-18a99ba78830 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
964f3cce-fe69-45c0-8bf0-5f65bfa42529 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
d68284bd-a701-4957-a1b3-f3cb139f7a64 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
1dcabb81-1f56-4fea-bca5-f7f19f9bf01f | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
18973631-330a-44d1-9202-597c7ad5e5d4 | Pole | 2 | Distribution | 2022-03-01 | 2023-03-01 | Level 2 |  | NULL | NULL |  | NULL
7ca3e4fb-fb83-489d-98aa-772562220747 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
72c4c84c-87b0-455e-851d-825e40159edb | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
2ceee83f-745a-4463-ab2d-78d3abdec0a1 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
62bce5c0-f588-45f9-8106-4ba0db955ef6 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
d73636b1-e8b1-4abb-ba62-27cbdf69c45b | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | NULL | NULL |  | NULL
8a979b76-6ec7-41fc-8585-4eefc8cf724d | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
cba75e47-6f96-4558-9d85-e6d55a79ff4a | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
af8dfd74-8f2c-4b62-9813-3fcb014ba1e9 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
a36c39a2-d592-40bf-bb22-32899f3d83ba | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
19f71cb1-dbcd-4170-8ae6-25e7ed818a99 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
000345bd-beab-4323-b047-7f58ba23bfbe | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
5e33c42e-4c59-401e-9915-88db56c0ed59 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
468e7a72-aac9-4875-b6c6-7ca17a809add | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
b772229f-97fe-48d9-b003-e5f11e0eb8dd | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
680f696a-d323-4268-9363-35638b749d85 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
3df0bec5-a624-49bb-bd69-1c3c07bc2706 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
dfcf8a9d-eb91-4253-8590-a160c4caadd0 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
fa6c7baa-32de-4b98-ab22-a0e03ab650da | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
75ecbeb3-bf64-4fa9-ae16-d7357816e3e0 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
d1b72a86-f7be-4903-9054-deb205701c4f | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
2faa0286-4d2d-4802-a602-1c0e8b995b19 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
3659639d-9882-44da-bdbf-68aa293c1ee7 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
724d5e19-ee2c-46e8-b91e-82c5961309eb | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
3ef96de5-6e55-455d-9012-0c5a3bc12f1c | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
f88c8f7c-92a9-43f3-bb9f-b123e322da59 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
122a807f-c7ec-4aed-928e-6b3d4f503e18 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
14b43334-4892-43f3-a1a6-aa38552380b5 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
1c2f1ab1-2d58-4c48-bb42-ecbfefa48e04 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
118db6f3-3972-4377-b6ff-70f0658a1503 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
b8834e72-d29b-4778-b42f-e2b80f7f191a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
c7863bf5-26e3-4ffb-8f1b-71b33ed22fc6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
8d118ee1-dd6c-495d-b2cd-52df3a96953a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
e7f4af8e-02c8-44ad-a67e-14d3f4c94fbe | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
18e5b3be-284d-4902-a1ee-d6bb5ce2f183 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
0748d31d-9a0e-4785-9110-e2548baf68bf | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
2f111a29-6b32-457a-9820-681f39c0f7d4 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
6c215b98-b1b7-497e-8a66-3970d8a5494a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
43ffd650-ff5c-466c-b1d9-bd4eae98c628 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
89657559-0bcb-4d5f-b8e3-84122ca68424 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
27c9ae21-8533-4ae8-9740-3318625968de | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
b6260d5a-1901-4166-a6c1-b260bbeb57b6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
bac01e77-1f47-4cf2-8f25-54a526864b6e | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
fcc1597a-45de-4181-b63d-34996c6ce1ff | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
fd775da9-8175-45c0-8c64-c18753d96dbf | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
474acbbf-1f6b-40c5-ab4b-c83d0bf93411 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
72bb551f-6b47-4005-adea-85a9e259208e | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
8146167e-d080-4c28-8fe0-198b6e8a9165 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
7adc2332-94ef-496d-a96a-f6ec2947f265 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
7d018483-bba2-4200-9adc-8c381cc929e3 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
51708ac0-d11e-4bd3-8f62-d39b0431acc9 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
b2336ecc-a1d2-43f8-b9b6-427b9730dd83 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
fff10f7c-ed25-49bc-96de-64b2a069d9d6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
8bb2c126-9068-4690-ab94-4f64edd7f3ec | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
0e86a72c-b6bf-4b5b-8af1-ae60b9358040 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
33061a2a-6d36-4520-96b4-52f28f78dce1 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
70944a0d-756d-494f-b125-25dabe12863d | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | NULL | NULL |  | NULL
33f59594-0c27-45ee-b5ab-3493515073f6 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
06206f9d-eda9-4c5c-96ed-3f59c4327e0d | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
dbd1372c-c638-40b0-a3db-cd5693d7c804 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
620954ff-355a-49c5-ab33-e6a060c052cd | Pole | 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
7c1d2fd2-d98e-46eb-81a6-748860f7b50d | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
b413799e-05fd-45c5-802e-338b566158e2 | Pole | 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
aba0429d-c04c-49af-99a8-cea2d2e7aff6 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
4ac35a51-82d1-4533-9529-2c6634d7ceb8 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
9d132614-0aa3-494d-aac5-3e3d460483ed | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
1da73f04-c984-40a2-b8e6-9f9366d0df20 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
758290f2-01dd-4589-b57a-e87f0f5f5633 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | NULL | NULL |  | NULL
7e19f252-101e-4b08-b6e8-824cb7ed7eb6 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
c182d3be-fafd-4868-9269-acef9b47712b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
ec42faca-dcdb-498a-8bf6-a60434c3b19a | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
96708bff-8bc3-4550-a2fb-20e3b30d5e52 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
35b4d4d0-2fc3-436e-96ad-81964433385a | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
025e007c-06ce-4b46-bbc8-5cabb0bd4861 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
d500bc58-e23c-45c1-accd-4d30e52bc300 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
5c8cd669-43da-4290-bf9e-f9ac7d21bee8 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
2ded8066-d4b4-40f2-bd54-ddb7872365cd | Pole | 2 | Distribution | 2022-03-04 | 2023-03-04 | Level 2 |  | NULL | NULL |  | NULL
2024979d-c021-487a-a2fa-a2e6d07a09c6 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
9117be77-b5a9-4744-ac55-c52b5de5f09e | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
928bbc33-bdbe-438e-99a4-bea302d0435d | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
353766f1-44e7-4178-94c1-8ac40f110f3c | Pole | 2 | Distribution | 2022-03-04 | 2023-03-04 | Level 2 |  | NULL | NULL |  | NULL
45db216a-e14e-45c7-a114-8075f729ddad | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
6d4e04e6-91fd-44ad-922e-62012c0d31a8 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
24d2edde-aeb0-4236-bc19-ba4362ad2f40 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
819a3168-cac9-4bcd-a941-a3954609b813 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
2e409d41-287c-43f3-ac53-499d40a97fef | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
0f662efc-3ac0-4aa7-8a02-0ccfc133df98 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
c06e8002-8e70-4553-8c1b-822d3e181b18 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
43a65242-1c7c-4286-9d19-7d97648a390f | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
7e3b28cd-1d10-47c2-84e4-8c62190a6099 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
eff1c26a-66c2-4481-9297-519c502653d5 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
890ce002-3f41-4eb1-b37d-b6be1048d91b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
bf515492-9cd1-4193-90d2-9bf157917115 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | NULL | NULL |  | NULL
131a2118-e6cd-4620-b5f6-97f79bd425d6 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
47dd40eb-38a8-4772-aa88-a283ddcf0597 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
4b093598-5e42-4a39-9233-e1fa149ee236 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
7ed130d7-1186-4547-9330-9eaeda9697ad | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
194af122-7ba8-452d-92b4-2e945ff7b1bb | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
e0b22470-e823-4b0a-94e5-b34563b87d3a | Pole | 2 | Transmission | 2022-03-06 | 2023-03-06 | Level 2 |  | NULL | NULL |  | NULL
fac6a3a0-75c0-4c0e-ad42-252501c6f847 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
99fc7cda-66cb-4d16-9062-7493c69c22ed | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
9e2e4c11-0309-44e4-895a-2def76648e70 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 |  | NULL | NULL |  | NULL
9de101a5-29f0-4ef5-8b1d-7282e3de919a | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
26765015-9d89-4141-800e-c39046580bad | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
8eddc616-56e7-495f-bb7d-c5fe14e9b934 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
61ca8aa9-9f93-4772-b94a-3ed5add449ce | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
dba0de0b-e910-4ad9-b9e6-2f78914fc9ae | Pole | 2 | Transmission | 2022-03-07 | 2023-03-07 | Level 2 |  | NULL | NULL |  | NULL
c00c60ce-8573-4a4d-ba19-025391d89fbe | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
6e286861-2fe2-450a-8b00-e5f6fe613bf6 | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
5e0722d8-69a2-407c-a314-57a8661cffea | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
0e8625a3-c494-412e-836c-1be5916e8639 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
f0e1f223-0124-4ccf-bb14-f3bb9f41e348 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
2372f5c2-cc0a-49e6-ab1c-2dd7fcfc068f | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | NULL | NULL |  | NULL
ed0f6aea-7165-4fff-88d8-f9867587887d | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
c7fca155-0652-4ee4-aafd-7503a09ce007 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
061c8eba-3bb4-4ae2-b7f1-8549334a02f6 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
68836db5-75d8-4aad-a2be-cdcb197bb3e2 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
b11d56e4-ee07-4482-bac6-a5e36516ec30 | Pole | 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2 |  | NULL | NULL |  | NULL
f835e242-4b66-4e7c-aca2-3697a3f0e3a4 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
3f0c9acf-3bdb-4b70-b93b-c4aa35120ab6 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
f789fc99-b2a4-4bb9-bac7-c403caed68ae | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
e6c1721f-beb8-44ec-b219-19a1059a8b6d | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
c35d1544-aa74-4417-8cdc-e81f255d8238 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
464b835f-a798-4131-8016-4c214f0e213c | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
2f2523e0-7813-45e4-8a58-ef81b4ccec88 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
8c01093e-fe1e-4abd-af6a-3558a3e369c8 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
96fda099-61e5-4a65-854a-88b07f5157d5 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
17c4164c-08cf-44c6-8260-4c22c1d562a8 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
a97070f0-5eb5-4298-9b6c-ebac96bd5688 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
52b3bb82-a148-4fe7-9809-3d3e3af5559a | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
846e663b-edf0-44f5-a7c8-537674ae3985 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | NULL | NULL |  | NULL
a9167ffc-b364-4904-a8f5-90858cd97fe3 | Pole | 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2 |  | NULL | NULL |  | NULL
605e7139-bc15-4384-80a0-e9de124b5015 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | NULL | NULL |  | NULL
1df7f79b-a981-42fb-9ac5-455e1dd4b0b0 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | NULL | NULL |  | NULL
af0375a9-c7d2-4a90-8acc-34d85a7f13a4 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | NULL | NULL |  | NULL
b4476d03-25d1-4434-8c0c-a7902095b7d2 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | NULL | NULL |  | NULL
23537b86-62b8-4250-b35d-034eaa1c1141 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | NULL | NULL |  | NULL
e3246536-3dcf-44ef-86b3-5c19328aaaac | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | NULL | NULL |  | NULL
3762d4c0-5d25-4785-a9e3-5393c12cbe86 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
dbcbd99c-ce34-4b5b-9d40-0c33de97ba90 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
70ddc3ca-18fc-4e3d-bd71-0c7c693f97e4 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
13971505-5365-4f01-b581-24e6769325a5 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
84ae0376-9280-444b-acb0-b7842b97933d | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
16798d74-022e-4437-b25f-649b59081b37 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
44633787-88e7-4af9-8ec1-e9972e059db8 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
52b8496e-426a-4ded-a03e-132ef352601e | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
c6234b52-1401-4d86-a5bf-0b4e08381ece | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
d97f7481-1c54-4655-9e44-51522b00fd8f | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
a7b864e5-96ad-4fcb-8fe0-2a97a37e631c | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
676714d5-68aa-4c9c-976e-ef813cfdd699 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
7d05c622-4a5e-4882-a671-a9fd262946b0 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
1a7643da-9618-40e6-946a-8c2c2d56714b | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
d113c1ba-623b-49e3-94e8-7bb9c3f45b3f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
2372015e-64c0-44b8-82b4-73056cdde97f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
a9b2b03a-df52-4c65-9dfb-9318ccfb7f88 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
c20c1f1f-7462-4211-b5fe-e4148c16ef12 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
e7def9e7-d7af-4c6e-ad1d-d26eb717d698 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
025c4b62-5b4b-41ee-9419-e27acc7063a6 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 |  | NULL | NULL |  | NULL
1d33503c-9bc0-47e7-be14-b1b53691a757 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
d517e014-173a-4cb2-9a87-c627e1ed8a30 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2 |  | NULL | NULL |  | NULL
c22e7131-2579-48a3-ab97-aeb489c57316 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
b5c03242-7eaa-49c0-ae4e-6d9717f62e71 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
f13d4655-f3b0-47bb-82d5-09c840a3b9a3 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
279d1e14-2627-43da-8c7e-af99443f339f | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
3715d1fb-91fd-423d-afab-7c8bcae80623 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
5bd81093-f232-47fd-af7e-68e5c0bf90d3 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
5960d81e-af50-48d2-809b-ae69fa14be13 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
4ffc6e7e-0a2e-467f-9c1d-9cf72424c2b4 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
eee6c825-8770-4f13-9298-273ba7da5e09 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
033d17e9-55ab-4c53-818a-49b90ddc6cd6 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
141c7577-c329-4591-a877-0a7d83bbdeca | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
bb356c05-3af4-4b7b-bf4d-0d0ac2b45127 | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2023-03-11 | Level 2 |  | NULL | NULL |  | NULL
eb530aad-7b18-4fac-b711-865eb071c1b3 | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 |  | NULL | NULL |  | NULL
5a6ed601-50b4-406f-923c-17ec889eb8d1 | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
e0259b07-0c21-497c-b08a-7ed5e2506f97 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
ff1e9233-01b3-495b-a602-4c463825dc1c | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
7db679cf-c015-42ea-b516-0a4403ccf871 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
bb7567a0-885b-4452-86d5-374a14e2e18e | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
f4cc5c29-7835-4f72-9951-9bdf8a231d8b | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
7075171a-6818-43d2-84b0-f7c093960da3 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
94ace622-8c1a-4609-8a33-472cd42734ce | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
17d3c5ae-1a61-499b-85db-e0afebfb141a | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
4603d0bb-e271-4150-ac04-2241b42f860f | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
e59ccf2e-acb0-4adf-a134-86a8d15c4b63 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
d45e9353-79be-4969-9c66-566d481027a5 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
ecffc587-cbd4-4a44-b6bd-d80c02e982a7 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
f5b65d56-f626-44d4-8be2-369d271c7370 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 |  | NULL | NULL |  | NULL
7153b268-c1cf-40b4-aa2d-f4b3f25affbb | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2 |  | NULL | NULL |  | NULL
6aeebeca-82a7-4a2d-b9bb-6abc2d989058 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
8d79dd12-3bf3-4cf4-ba22-431cffa0d543 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
2ef72a3e-2478-4340-bbcc-a488360d832c | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
1c6a1ff4-0a94-49aa-8583-8f3abe9d7f26 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
482bc288-e8b7-4f39-88be-0a7740247e14 | Pole | 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3 |  | NULL | NULL |  | NULL
974c6e73-1861-4b99-90e5-856952a7e3bd | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
058b3238-f344-4a1c-bcec-4b27eb6f203c | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
7c24e023-b231-4b8f-91c5-0ec59d66f256 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
0478cc94-0f0e-48fb-9852-d500dc8bcf42 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 |  | NULL | NULL |  | NULL
5c3a802c-4785-4db0-94c5-f154d611ed32 | Pole | 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3 |  | NULL | NULL |  | NULL
2956fbb8-2b4d-4f3d-8950-2386873a3c59 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 |  | NULL | NULL |  | NULL
ba8d0a27-5b02-48eb-9c07-b4b7aec6d00e | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 |  | NULL | NULL |  | NULL
95e725ab-d539-4898-959c-e9efb0a6c79b | Pole | 0 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 |  | NULL | NULL |  | NULL
5ea6f806-94d2-45f8-afee-bfc21a9cbf00 | Pole | 0 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 |  | NULL | NULL |  | NULL
42b8af2d-2292-4e20-84f6-bd12843b48a1 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 |  | NULL | NULL |  | NULL
a4681f11-8df9-4cab-9864-b15c560da8b8 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
3b57e49f-aed7-4e4a-88e2-06675e5e4418 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
9932d08c-9950-4b33-a9ee-87efe222a449 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
38ca824a-2abc-4ad6-975f-4110e77e4fd9 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
84ef54bc-3380-4333-a157-497a39da266e | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
79096de5-208d-4f60-a25b-925873503991 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
af7de0d1-50fd-4fcd-a12a-e7c4a4a54ad7 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
c4f945aa-aab0-4a0f-bc6f-4f279b5f19a3 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
5360e95d-af7a-49ef-8025-dfea3146d5ce | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
68d65041-18be-47ff-a2d8-0f37eb7854f0 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
e56b0a19-d77c-434c-90c1-636d57a1142c | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
5600602a-e0b6-402b-9576-b8c528e3a1fb | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
ca843b56-99c9-4151-9145-7bd4b7645870 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
a5644755-c84f-4047-b25a-a818fd232486 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
81a9eefa-5d2e-4fc6-b919-d84d93a2f74c | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
cba3d22f-5dcf-41c5-a4b8-2e838459ff38 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
bc49c0ff-57c7-471f-92da-29a03735adc2 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
d5ea176f-2f85-43dd-850b-9a70d0726a03 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
42e3d468-2f5f-40f2-951f-286f35f35b1c | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
9743601d-a563-49a9-b989-53394adbcef1 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 |  | NULL | NULL |  | NULL
811602ef-6022-41d4-99e1-d86307e3e657 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 |  | NULL | NULL |  | NULL
30a5ebd3-baba-41ee-926c-6ac341664752 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
373bf0b7-ba44-4850-b54c-41ea75be2660 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
af4e0761-fae5-457c-b4f1-9ec961b0f9ad | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
828b8419-e97d-445f-a054-db36bc5cfdbe | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
6b4ae72c-2ea7-4e35-8810-0ffaf2bb1ea1 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
e3db88c7-f89c-4738-8cdb-81fe55a72999 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
1763ee4b-8321-454e-8bfc-b13cc1e079b6 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
48dd83f8-80a8-4950-aeee-27004f83fddb | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
9f148b51-c9aa-4630-bb30-0c5c88046c5e | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | NULL | NULL |  | NULL
b02104c0-7b96-4c69-91a8-309110eb8cb3 | Pole | 2 | Distribution | 2022-03-22 | 2023-03-22 | Level 2 |  | NULL | NULL |  | NULL
56166386-a26e-44c9-a6eb-d4262ef2a8d7 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
67b5eb10-2680-4429-9b60-994e45a85302 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
447ed10d-58ee-48d8-89a5-867fb454245c | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
5ca58bf3-0258-484b-bdc3-30ad06f4fdb7 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
7e043f09-b91b-4d40-8029-d46cb83e6b84 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
6dd3bb92-e7e5-4228-93a7-002478038549 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
7b5dee18-6d15-4e99-a3ae-8dfdabc965c4 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
c1baf5f6-97fa-4434-977c-b1e1136be72b | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
4acbd570-1d2d-4ffc-8438-a62d218c4ac4 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
dddb4116-46de-4952-a2c4-738668f1ea8a | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
8e20a9d7-45fe-468e-9f69-e23d7ce2e508 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
f89b896e-07a6-488f-96a5-543230fac341 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
a6bfd5ee-865a-4814-9e0e-1df0e7600bf9 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
23774c31-0797-47d4-b0e9-8bdd8bd27e94 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 |  | NULL | NULL |  | NULL
560db93d-3c89-4f60-a167-677f58802def | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
3ff87b0b-e34b-457f-be4a-8695265fc19c | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
140aa5fb-4683-4775-a87d-35ca405d2236 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
1aac4d42-464b-4da0-b231-20b6f6a06b97 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
ea9b8a76-f067-45f2-b25c-685d63c98253 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 |  | NULL | NULL |  | NULL
53373121-98de-448e-8c85-35b9576a6869 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
635f9fa8-3766-4c4c-9dbb-8ccf5eb329b5 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
0a7892d0-e1cc-49fb-88f8-147c3111999c | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
38b8cda4-4c09-4873-abd9-113c145665bb | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
a2fb0a9c-6906-4fb9-900a-4fac4be7bb0a | Pole | 2 | Transmission | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
16c7a8ca-d294-4077-8444-0473df29aca3 | Pole | 2 | Transmission | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
02f1711d-c3ca-4a27-9542-6712e192c178 | Pole | 2 | Transmission | 2022-03-24 | 2027-03-23 | Level 3 |  | NULL | NULL |  | NULL
b4884129-3fd9-4d6f-b444-1c305127ca1f | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
69aaa11c-e5c6-419c-9c55-729a62cd0f23 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
11243b97-53ab-4744-a034-24451762a977 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
513fd5a0-de8c-41da-9d72-1424d6b94193 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
bc74636c-5151-4683-b755-1a6d7a31847b | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
6aadc235-7fa4-4d37-aa2e-1fb1c9f33c10 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
6699147a-6673-431d-830b-225a8877bb19 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3 |  | NULL | NULL |  | NULL
b2efeb4d-1763-4ae4-b9dc-f8deff9b794a | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
a9e1c32c-16e2-4bf6-870f-594a27c27380 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
0a09f7b4-a52b-4f94-ad95-54c10d0e50f1 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
8ee6f7c2-e248-4b75-813a-f29ff833a560 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
33765a7c-2407-42da-af75-23c078fcc578 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
200ff739-41c9-4c5c-b5a6-d450709308b9 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
1a93eb3f-f827-489c-a224-2a114bfcc464 | Pole | 2 | Transmission | 2022-03-28 | 2023-03-28 | Level 2 |  | NULL | NULL |  | NULL
576433c1-00d5-4142-ab60-574f73f8b481 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
088d6e8b-8dfc-4af1-8424-a7b20328ee6b | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
f1eab8ff-b0b7-42cd-a2df-61ca5e145a62 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
eb64b061-18b7-4d35-8d61-aa1c863c4a85 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
be47bb45-9307-4fe5-a58d-b5404dcd5477 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2 |  | NULL | NULL |  | NULL
4e889c56-a03f-4a27-b96d-b61e7750e2e0 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
5a74840a-f070-47be-b881-55be4791cae5 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2 |  | NULL | NULL |  | NULL
7e9a6086-1a1e-4600-b621-64b022f371b6 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
ad30b0b4-deb0-4522-8234-f90c5af20818 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
9caefccc-45ee-4908-b9b4-6bb22162fda4 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
30ebaf39-0ece-440a-9dda-b9718906fa0c | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
2f7fe449-2991-4db1-9ed4-233caefc8f61 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
3eba6a40-cc51-4e45-9881-f709b53de4cb | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
7113c053-0d5e-4b37-ac1a-e0d5289233dd | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
ee0688f6-7625-4b66-8f99-be251eb47300 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
f9d49df4-00fb-497f-bfbf-417c02838a38 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
4c7c8abc-f686-40b3-bd47-59270d8226ca | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
f1796a26-08d3-4992-8b1d-64e4efe52a50 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 |  | NULL | NULL |  | NULL
69ee62c8-ae3c-4c3f-9e09-4154c499eb66 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
f09b139c-1fd8-44b1-b6f8-f3886641beaf | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
3e4d9860-54bc-4284-b86d-482d1087a4cf | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
b697c0d1-222d-449d-a7bc-49617e4acdc7 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
91361795-60df-4b1a-9321-0cfc53bf378c | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
0dbf0317-a7a8-4698-a4ca-3971775080b0 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
bed53dd8-e7b2-4f94-a8fc-2fd562ab41b2 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
41241f71-55e4-488a-b5a8-6343683eef57 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
99d7243f-5c8e-4660-a75e-fac5c6b459bd | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
56dcb4a9-f149-4118-94a7-fb0ae769b8bb | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
82ee6174-3cb0-4c52-afa9-ebd956c2e838 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
2ef54a15-4c10-49e5-b567-5e59d0700826 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
a4eca477-882c-4782-8ea4-8de3006f2571 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
f8100800-b33b-45ea-932e-630f87eb3779 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
b9cd256a-feb4-4d90-826d-9822a74540a3 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
f60e8afb-b15b-42ea-bbd2-a02f3193f59b | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
3680f66d-8301-4e4c-8077-ed8fe78e3c7d | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
054d5142-3c61-417b-93ed-a94b7bdfd801 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
4cf2f11f-0be7-4345-811d-b4c6af47fae1 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 |  | NULL | NULL |  | NULL
db47ef52-d8ab-4a74-8543-6e9adc9515b8 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
dae60379-6f06-412c-b840-9ea6044082c9 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
843ea2ba-a32b-45e7-b2d4-f9055a18cb86 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 |  | NULL | NULL |  | NULL
467f7c03-befd-4a18-ba8f-0168f99f851d | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
3ebe0cbb-27eb-41e0-b609-e6202b6571b0 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
77da13f2-e51e-4343-84a8-8a2bbd21f480 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
c54573f5-0856-4cf8-88f2-d2c71b3747b9 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
158ff743-f443-4039-8f3b-147887272a04 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
a285c7f0-7141-4cab-b006-5ce892882fef | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
f3b5b8b5-252a-4bfc-9474-f51b9a84c246 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
40129d3b-7c9a-4e64-8341-5b5bac0bfe11 | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
09f1c01d-3812-4691-a333-c4f67703de98 | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
80b7baf0-df49-479c-b1be-683135d89104 | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
84b52372-589a-4d67-b45d-6df73a7fe2dd | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
371f7c92-04ec-4d25-9929-44772f4a543d | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
2a75247d-d462-4a28-92d0-6ee95d5eab4f | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3 |  | NULL | NULL |  | NULL
ca4720c8-5ed2-4db6-a280-b55370cf589a | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
fb204016-655a-44a1-9307-fb449a10c57e | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
4c41728c-b3e3-48a1-9d54-839cac4e7513 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
cd68c314-02ea-47f3-a18d-6f8eebcd2459 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
0433e635-6459-45c2-a96f-dcb378c21e73 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
2526366c-7d72-463d-b87a-572826383f6c | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
f18805e4-d2db-40f3-8e7f-36fa9d0231fd | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
80ae8e82-c16f-4a96-9269-1ae027ba6cb8 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
31a70705-7cad-4c98-ad1b-346a1a5fa69c | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
c8bdab78-0c5b-4209-871e-e9ea2e4e3118 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
a9bfb66b-f162-4b34-98b5-7dda4204c231 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
f3007a7b-d884-4d87-9f70-33666733bf30 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
8b443ca0-7851-4a81-8ab8-8d63a71b476a | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
449a3fd9-6a15-4edb-adef-37eecac70186 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
3bb02784-7dc2-4e8c-a3c6-e36fd5d31219 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
b1aa0da5-f4a9-437c-90d0-ca0a246abe10 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
78e82791-ec49-4494-9f03-0e875b4e68b1 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
94b9925d-0c4c-4917-8b7a-3b98ee27b73d | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
fc83b659-098c-4bb4-81a2-adb559ab8f89 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
6d1b0110-1392-456a-94f9-dcf6ff4171bf | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
4fab5f0d-3051-44dc-85a5-b019491ad3cc | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
c4d29819-fed4-45ff-b7a7-ca68887233e9 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
88780bf0-6e73-41fe-9dff-845115867a46 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
54ccdac7-65e7-46aa-8772-7ac31e642101 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
3427a04e-af38-44c7-9dc0-03f25aea0c47 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
0d818849-b462-47b1-b64b-09034da53661 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
a6325903-5690-4566-a643-a95167b5973d | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
db67ef23-5606-4962-88af-aa13d23541ee | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
7ce90122-c092-4e49-bccb-85440ed0b30d | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
011ec3be-637c-4c53-8455-19bd724131e2 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
8d54dcdf-1a6c-49db-afda-98e99130de1d | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
8d4f6243-4f8c-42be-a198-dcbd678ae2c5 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
53c60202-2fc4-4d0f-8eb0-64fad0838449 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3 |  | NULL | NULL |  | NULL
6c6ce9cf-af7a-4b5e-9a32-872c136f8d6e | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2 |  | NULL | NULL |  | NULL
e8803a8d-62e6-4fea-8538-962bde8504f9 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
3fbedee7-5a99-4aee-9a4e-471dc904f736 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
57298da4-085e-4a72-9192-b84b02d621eb | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
77a734b1-f825-4a0d-bfde-f8fef4f64205 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
b419a52d-bd16-45fa-92d9-24da7540126b | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
aeb3f051-68ce-4d17-b99c-3a30c040d614 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
6753f49f-78be-43e9-b0e1-7ad99d995a72 | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
c1d3a587-eb86-4aff-8eee-3859a1a8b293 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2 |  | NULL | NULL |  | NULL
9ddd52ad-27a2-4940-b3bc-9183c21d6be5 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2 |  | NULL | NULL |  | NULL
60b388e9-9190-4be4-844d-0f31aed95a7e | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
70490651-8848-40de-b6b8-6db69485859e | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
88a46452-182b-40e8-a311-561508acf7cc | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
771a1a54-c679-4232-8d62-bfebeeeba78c | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
66a36bd6-ddf1-4343-8ded-318b84afcc04 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2 |  | NULL | NULL |  | NULL
11951544-ac09-410e-9b67-787b49f3dfd5 | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
b749afa2-f60d-4b16-a6ab-c8c92391fb2b | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
9d54261b-583d-4de6-9a34-5a3bc96ee7c8 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2 |  | NULL | NULL |  | NULL
3490a2ae-cf9d-443c-a876-3945b1a2ddd8 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
ce7d0427-8658-41c9-9497-c0adce5ac409 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
9517ff8b-70eb-4a79-9c2c-13f5d37f6027 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 |  | NULL | NULL |  | NULL
a64b714a-e86e-4c91-8616-7eaab0d4fde5 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2 |  | NULL | NULL |  | NULL
d0ca56b8-d416-4434-ae5c-41f9b51005c2 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2 |  | NULL | NULL |  | NULL
42416bc3-b0fb-42c1-9961-e231d17186db | Pole | 2 | Transmission | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
65aea2c3-65de-49ea-8c7b-da0da71d7c4c | Pole | 2 | Transmission | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
6ddc633d-747c-438e-9737-1ba3a0a6dc06 | Pole | 2 | Transmission | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
d34f4cf2-e8c8-456a-8526-104005306e15 | Pole | 2 | Transmission | 2022-04-04 | 2023-04-04 | Level 2 |  | NULL | NULL |  | NULL
c51b68ce-3e6a-43db-9fe1-9ef47b103ca9 | Pole | 2 | Transmission | 2022-04-04 | 2023-04-04 | Level 2 |  | NULL | NULL |  | NULL
588474a6-25a5-4a6b-b3e4-08a6f6898b19 | Pole | 2 | Transmission | 2022-04-04 | 2023-04-04 | Level 2 |  | NULL | NULL |  | NULL
a514a183-210e-4d3d-9669-be29f8443e5a | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
891c7007-934c-4802-926b-c92f036b54f8 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
536882ae-ee2d-4682-a30f-02f7efdd9622 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
3e4167d9-5472-4774-854a-6b53e05d62a5 | Pole | 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2 |  | NULL | NULL |  | NULL
e707e466-721c-4732-9532-a9f6cc279846 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
6490187f-9bae-4210-ace4-826a81fc03b8 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 |  | NULL | NULL |  | NULL
4b8543b4-81d4-43a2-b8c9-a9d1ba053787 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
0ca8a859-b5cb-4f82-b0c5-f891d553eb89 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
c8d0333c-1ab8-4836-9766-032e21e4742d | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
5e98754d-8e65-4817-b4ee-f93d0f3b5073 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
1357eced-8afd-4479-b82c-152944c3f572 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
a39dd90a-6368-42a5-8bdf-ff9f0348990f | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
ef7fea55-987a-43d3-9f22-203f7c6236a6 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
fad86c80-6615-4b44-8b56-5f6200dcffc0 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
9644509f-ddb0-408c-aea3-d01dbd944b83 | Pole | 2 | Transmission | 2022-04-05 | 2023-04-05 | Level 2 |  | NULL | NULL |  | NULL
c41d3b73-5ace-40ad-8145-f8563c8d2a53 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
c4998d00-7245-4eeb-bb67-208def1546f7 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
17110f8b-c3ee-4ff3-a026-e51494e1cf8c | Pole | 2 | Transmission | 2022-04-05 | 2023-04-05 | Level 2 |  | NULL | NULL |  | NULL
51fcd251-20d2-4d11-8ff0-5e3c30eaad34 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3 |  | NULL | NULL |  | NULL
04f67fff-4a65-4373-bdf0-ff776df5fe0f | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 |  | NULL | NULL |  | NULL
406e13b0-2310-4f0e-93c3-465097c609c8 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 |  | NULL | NULL |  | NULL
0dba6e19-acb0-4b5d-bff5-f55abb94f985 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 |  | NULL | NULL |  | NULL
b456e1ce-be9f-47fa-b2f9-6637c376e266 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 |  | NULL | NULL |  | NULL
5c4e7dde-77b3-4613-a6e6-7e362b1c0e91 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
ba31ea8c-07c5-4600-a7e5-0892d7adaa56 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
9dd4116d-078b-42f9-9b94-92ccf7f1ebd0 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
ce61d46f-6e7f-4e8a-96ca-f5e12021aa28 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
93df7ac3-a101-49e7-a9a0-081db111c960 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
ab44f8dc-89e3-4176-850f-793b3f19f46d | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2 |  | NULL | NULL |  | NULL
110e256e-ed09-42c0-977b-6ab387d4d360 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
989d3a22-55d6-4d04-be3e-072a0db3b5ab | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
7f5d4317-8e59-4210-8d36-86f829a70cf2 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
bd59abc6-3dd7-4d8f-9199-94f9be846fb5 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
3312cced-0c43-47c9-9268-33658a56b4ba | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
41ed7441-2394-478d-8c32-528aa9839a6a | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
06fbe163-02ab-4510-b071-ab68098ccbf1 | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2 |  | NULL | NULL |  | NULL
f073a40d-ec75-4bb8-bc0c-bd0bbf1fd031 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
f0a38a97-52b0-471b-ac55-f62e15c3613e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
47ab9d43-bf03-4de6-9615-c79cd8e6f57e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
c3a29af3-8df4-4143-8864-b06a10d0f73e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
759dd31a-a29e-47a2-acbf-3117e4dd7a3e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
453e5e4a-a4bf-4062-9c16-7154c57a7647 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
7f7458a2-d63f-4f1f-af4b-ead310ce806b | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2 |  | NULL | NULL |  | NULL
ec0e8d41-e7c9-428d-9be6-c293c45c8aa2 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 |  | NULL | NULL |  | NULL
ae8a5b56-5f09-49c5-879f-39a52004dce2 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
5f704f5b-9674-49fc-a084-041814e9145b | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
7458865c-ccb2-4f54-82a2-011af5d3522b | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
6a56aa29-5d24-4179-ab69-2d8a5118ae4e | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
92ebab34-88d2-4e0e-af9f-1a54dee52310 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
b18ac578-5674-49dd-a472-13aa899aedef | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
f3c25928-8609-4651-a68b-3a65dcf43984 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
cb3882a6-06d2-41ea-bad7-9ba7027598e6 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
31144e21-548e-437a-96b7-e0e1a0ca98f3 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
893d438e-38da-4a1c-8277-df8c921f331a | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
a9077e38-0a8a-4f05-bb09-d2e748847190 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
4d2b8ecc-c3f7-41b2-8868-bda740cad8a8 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
752f7f4e-4f9c-4523-9d70-effcd4b9fae5 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
50b30623-87c5-49eb-826b-7fe81ce79572 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
dbde7c58-9f55-429b-8dd8-d36bb2fe4f06 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
1c918c01-a2cc-4e59-8a5d-7d05f9392d6a | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 |  | NULL | NULL |  | NULL
5da1ffe8-e13c-4e1b-8d84-4f24e9a59222 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
cc00849c-8eb3-40fd-a6e7-ed38b13486ba | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
ccb378ae-b837-4738-8914-9a5503502d4a | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
a6a4386c-e04c-4192-ac0f-464059095588 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
54b8461e-4806-4f58-bfa3-70ed626e1606 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
1544ccbe-fbcc-477a-b0e7-85f33f0a08cb | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
25ff992f-3184-4b34-9463-ea896bb6ce19 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
fb2d214e-b91d-435f-9f3b-e2b0845207e1 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
ac825b42-2f9f-494f-8b6d-f2c0fbd2529e | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
b4b229c7-0dd0-4a81-ae1b-3a1b4db8ba28 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
7f9f2bf2-b36a-4093-8a23-d04f9dc0d04d | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 |  | NULL | NULL |  | NULL
a0e8e8b4-792d-481e-aff5-af88c1ab75b6 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
0f60ef12-9527-408a-a304-d1cd7f4d30b2 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
67c6b4e4-4d9c-456d-9889-c87907659f09 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
0a66d65a-3fa9-421a-a1f7-65d9dac49469 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
497d4a24-b574-49c4-b47b-d04eb2b34f0c | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
926910b6-22b4-4d03-8804-2453d9bf325e | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
c335708a-9c1c-4f52-bf0a-372951cf6e28 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
ccbbf5d6-424a-4913-b12b-3ce684553850 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
fee81b88-0170-40b1-ac9a-c7c944a7aa14 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
4771aac8-e424-4297-a657-bb9d8165da26 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
51d941da-1ea2-4b06-b1cf-ec2c7b918d12 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
344dcb0b-06e1-412a-91e2-0174a804f168 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
089da26f-0a22-4ca1-a226-62a94e2cc3a9 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
c3e0a445-ba3d-4db1-a5b6-2b7f678cdbf5 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
539206c6-785c-4360-a057-97571eb7e5e3 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
9441e91c-7b1d-4fae-8a31-5204036dc095 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
802ae38c-43be-4b1e-80ae-be0a03e89114 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
fcfb005b-5af5-44af-99dc-1f9859caa707 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
969808e2-e63f-4c96-8cad-34e50ca2ecc0 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 |  | NULL | NULL |  | NULL
f435a7b8-06f2-4b6b-9fdf-8eb65f08c292 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
ec7f82f8-4b5e-4598-9456-79c5cdfb747d | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
fc2c159a-ae49-4cb9-8688-dfea83f773a7 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
0255c325-77ac-4d86-bd16-8bfcf45f9eef | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
91263e8a-96e5-4cef-a764-64a1dc400f17 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
69c465b0-603c-49e9-9907-7b1bf9244dbb | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
e3342162-d6f8-46bc-b0ba-219d23c2d252 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
a05159f4-3bdb-4c11-a05d-1e6c4436e9f4 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
04033804-b4c3-4d80-830b-a7a95b8a0527 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
a1423266-f9b5-4b7d-8b63-98d7000c94dd | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
c5fc0e98-f616-40d7-b78e-acd718d8ce1d | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
85c234cd-3fb1-428f-9e56-78e3f210c822 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
6cc8fef2-8517-4e54-a02f-d6c447c29159 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
8c5cb3bc-b7b1-47b7-9657-3e2f254bdcfe | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
9b7fa005-09f1-4e72-8f0e-2bb4c688d2a6 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 |  | NULL | NULL |  | NULL
15a8510e-5caf-4f94-9c84-c23352144894 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 |  | NULL | NULL |  | NULL
95aadd0c-83fe-45a7-a906-9627397d36a0 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 |  | NULL | NULL |  | NULL
43605e97-3ece-477a-b27e-5858505b3b50 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
a7978a0b-a636-40ac-a42b-2b214aee9077 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
543fd334-c0c7-4361-9569-153ef40dce9d | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
5d7d532b-9cac-49b0-85b7-43685b3ce849 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 |  | NULL | NULL |  | NULL
b8a3c1c3-60dc-49ee-8451-c633fa64a3a4 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
407180b4-8080-4c0f-a1c5-5c48ee428a7f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
a148c546-02ae-4f0c-9be8-3204d556ff2d | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 |  | NULL | NULL |  | NULL
38bfc3a2-e04e-48d1-86cc-97d661b1b849 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
95ade939-2538-4008-a08a-a823d6d34b66 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
74d9f9d2-5c33-48fc-98f1-f7de4db96d26 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 |  | NULL | NULL |  | NULL
037de28d-f5aa-406c-bf65-922fca677062 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 |  | NULL | NULL |  | NULL
6caa2c64-cc49-40f9-9e73-38d20bafa34f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
46d1fafb-47ef-4b24-be4d-2d611d53b42f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
2303c569-23d0-4e2b-b11b-dc1230aac3f1 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 |  | NULL | NULL |  | NULL
37ced4df-2357-4c0d-b9bd-ac2b485fd4df | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
2e3e75b5-cb8e-44b1-8231-10e37d7be6c1 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
1b946904-148b-4bdf-bc48-70d5ea50b3db | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 |  | NULL | NULL |  | NULL
53e22257-d863-45aa-be5a-4b9ffeb2db7c | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
63639052-7d8a-4148-ba18-da2636ec976a | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
5149607e-d663-4d92-aeea-0b0e5e11edc0 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
d118a864-2860-4ba7-ba06-8da6829be47f | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
a1d4f08a-129a-452f-9c9a-9d8b7e8e747c | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
b08889ee-cab6-4d1f-9820-0cbb0b6c1890 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
58b1dc1a-2f93-45e5-a588-25d0000094be | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
d670ffb7-afd5-4a68-983c-14c8a5e8e42f | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
4daae178-c498-4952-973e-9e2ca33f41f5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
0cb11de0-c940-4107-85a0-a362719d60c1 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
eccfd6d8-acf6-4758-a83c-65180e565fb4 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
3519c253-e12f-425c-9bd3-f0f540b08283 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
46fa10f8-a381-4ff6-bf27-65ad50a860fc | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
7de8a9a8-846b-4e38-96e9-a4952b78d819 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
7cb83437-f6e7-4e3b-9150-24b9dff21a2f | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
5f9f2e8d-c191-46df-bda3-118d3523d4a2 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
22b5057e-3d76-4c55-8b83-048e78ea29a6 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
98219143-1471-4aaa-a415-ba60d1b34d14 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
3b25ab8d-845a-4f13-823a-e24707d3e252 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
b0578be8-ff41-49f0-ba78-8b5266a06dee | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
8739f452-dbb5-4f7e-9b92-be33290ec8c0 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
34188dce-9593-4da6-a8d3-a23c78bdd2e5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
c117febe-713a-4a78-9ee8-5730bd8cd8ac | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
eaf92ed2-82d7-4d73-926f-43b6498137f3 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
a696cbf6-2311-4295-bb81-6ca5690ad502 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 |  | NULL | NULL |  | NULL
e51699d1-2083-41bf-969d-ab7f570dc789 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 |  | NULL | NULL |  | NULL
98a38247-b04c-4ac1-a41a-1562fd198823 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
403edcc2-01cd-4a41-a9c2-0bf707958cf2 | Pole | 2 | Distribution | 2022-04-18 | 2023-04-18 | Level 2 |  | NULL | NULL |  | NULL
9406777b-4441-440a-9a39-08327bd49676 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
0bd4c211-2fa0-4ffc-a3a3-bcded4f6b868 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
e327c1cb-1cd4-4877-b74e-782d514eb4b8 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
1b308e41-8eef-4f01-8695-2f778faf43f6 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
4d7fbda5-e43c-46a5-b778-4afc68793f4f | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
b332e4f1-6cde-41b0-86f4-7d0b268d74ce | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
84533a32-7b4d-4dc8-ae99-e970c426cddc | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
52403095-c006-4df4-bda1-0ef42303f754 | Pole | 2 | Distribution | 2022-04-18 | 2023-04-18 | Level 2 |  | NULL | NULL |  | NULL
254b66a1-7352-4c51-9f61-8cac67d87333 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
56cf1067-2051-4971-8821-6c9641dd1a41 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 |  | NULL | NULL |  | NULL
56868fd5-9ff0-4f89-82d4-7be7a56e6942 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 |  | NULL | NULL |  | NULL
ab279528-8f1a-4ad8-b7c8-fea9d47704e1 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 |  | NULL | NULL |  | NULL
d091772c-f9c9-4cef-894a-56c98ff09b58 | Pole | 2 | Distribution | 2022-04-19 | 2023-04-19 | Level 2 |  | NULL | NULL |  | NULL
e05502a5-09c8-4f79-996c-f04ee625a61f | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 |  | NULL | NULL |  | NULL
180dddd5-3a08-4127-80af-d0a2337d7d6e | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 |  | NULL | NULL |  | NULL
6cba7a52-ab89-45a4-94ad-9102f1a5e49e | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 |  | NULL | NULL |  | NULL
9eb99346-4d3a-471c-aa00-1effa3959605 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2 |  | NULL | NULL |  | NULL
4e1d73d7-3d14-4f6a-9218-bfd869079ee8 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
f1b338dd-4222-4fb4-917c-e7faec94a149 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
9772a723-2f64-42e1-8cc0-5f1f82b1178e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
78d1ccd9-3911-4bd2-9c00-40f31eb4a38a | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
e7870a9e-d735-4842-a675-f0b52c9d1bc8 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
3abac912-64b6-4103-aabb-354e2cb0dae2 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
33c04f36-79c4-4646-b225-429b502f1886 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2 |  | NULL | NULL |  | NULL
97873176-0c76-4b9b-9c10-0f7645ee7bfb | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
bc9af2ee-8b89-4018-b278-d05b9f6c55db | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
273ba082-00f7-4349-a975-b4e9df59307e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
a73c2a3c-debb-483e-b3a2-a01985a052e9 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2 |  | NULL | NULL |  | NULL
e0dc8417-b16e-4bff-b3d4-49214f604e2f | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
db9b0309-2e8b-42ab-86d3-196ba68add20 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 |  | NULL | NULL |  | NULL
79a0ecdf-3fd3-4e45-8e16-323b372112cc | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2 |  | NULL | NULL |  | NULL
58bfd453-3669-4847-8464-c3906ea0539b | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
b41acc02-a3cb-4116-bbe4-ed092a439a81 | Pole | 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2 |  | NULL | NULL |  | NULL
21cc9ccd-84a4-4e94-b033-832ca5e79404 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
af2931f1-1663-45ca-9442-79950f592897 | Pole | 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2 |  | NULL | NULL |  | NULL
ee281a7a-954e-4279-8d5f-e3d4cdd508b5 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
6dd093d7-4d98-417b-8966-989557e8e47a | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
515f9e6a-b336-470c-a130-22c684af9fab | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
d5ec9669-37ab-439f-917f-9370f770d13a | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
1f30e40c-e8d0-4759-b5d3-68467e64ea48 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
a5ef761c-4fdf-43a0-95e4-cacbc7df56e4 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 |  | NULL | NULL |  | NULL
0cdaa5f0-aa98-4c2f-a7d5-d704aec50ed6 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 |  | NULL | NULL |  | NULL
044cc782-1ed1-4432-9585-6b85bb948fbf | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
a551285b-18dd-46b8-9be5-6324e3b5fb18 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
06b139f3-8c89-458e-af64-dc6b1526a460 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 |  | NULL | NULL |  | NULL
54c6c5c7-af47-4c91-92b2-813046992f50 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
47d0da06-5c16-43cf-9ea9-e78485957c69 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 |  | NULL | NULL |  | NULL
39247234-a6cf-497a-8401-46673d79b298 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
23bd6e0d-7625-4a8e-a9f1-8b199e2a657c | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 |  | NULL | NULL |  | NULL
c48b42c7-d669-4c37-98ad-fe93558dfe71 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
2a27cfc0-721c-433a-9041-b5969624522f | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
29b603ab-ec6d-44a9-8b96-6b949b6492d5 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
e79d5f6f-bec2-4403-b983-9f2af8015a75 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 |  | NULL | NULL |  | NULL
645df035-6d32-4acc-9e66-2e458f1374a3 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 |  | NULL | NULL |  | NULL
502368bb-6d99-4105-bda3-8490f7be749e | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
777597b1-ae99-42ef-8558-8ba002ddc946 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
04a9d646-9efd-4061-a678-7db7600e449a | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
8015a689-bd64-48c2-a191-5a0f687408d8 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
8bea342d-0196-48de-9f71-45cb08c431d5 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
9639183e-8204-41fb-88ed-13a524577e27 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
ef4075bd-e271-46ab-8913-3db49c6b78fb | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
31905159-7ab1-429b-8efc-06ae07dee55d | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
7df8c0c0-5b6a-4bd5-80e8-b7f7a98175c1 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
2406f9f3-e6fe-47e2-ae4a-d7416dd2b1c4 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
a008d37d-0cbd-4ee2-97f5-2d20d394eafb | Pole | 2 | Distribution | 2022-04-25 | 2023-04-25 | Level 2 |  | NULL | NULL |  | NULL
a7685d84-109d-4a27-b5ca-1deecf092af3 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
5d1cdcf7-cf77-4d35-ae7c-f4eabca8e997 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
3dbebf98-ac14-4bee-9c02-e676adaf0872 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
0abf462f-4a89-4ad1-93a1-5c809be35dfa | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
16a33b52-5c49-4a86-91c8-2c426afc256a | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
77b6f8ca-e4a6-4ef8-8e44-f9036fe953a1 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
b54999a0-3cfd-4075-95d7-bc9c75a9d4f2 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
d3e0b15a-ce35-4a71-811f-da58dc85a696 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
710d83bb-840c-4a36-86a3-5a843c89ee4d | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
c65a0758-fb70-4012-8743-352dfe10f458 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
c6a44c2d-b649-4509-ac88-16dff9f42731 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
eab6a9b3-f84e-46ef-9457-61187b254332 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
51b1eadd-a6ed-4bb3-be36-c36e88e52843 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
2f243988-2fa6-48d8-abe0-8492a97c81c5 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 |  | NULL | NULL |  | NULL
50bec5c4-71e5-4185-bf79-5361312f15b8 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
834a7a1e-47f1-41e2-b4e1-40aacdb85f78 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
038f91bd-8454-46a2-ae8a-e4908d660e69 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
9d29eb7a-6ea7-44e4-8ed6-023beb64f8d9 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
069ed871-507e-4c1e-846d-c92cc464c1c1 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
f4a4f0d8-bb92-4f64-b3e3-79cd6479c452 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
7bfc2379-96f5-4571-8714-afb7ee873d07 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
07d834e7-8f2b-49bc-87d1-27a6fd4dc5a4 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
cd37d0b4-ddbf-4d47-b6ad-43d58fdfce36 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
41b66920-69dd-48f1-b4b4-98ddbc999562 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
ae7f8db5-b9c1-414b-91ed-49c90a051ce9 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
a1fbe212-3bf1-4a34-9a17-263de4bf64fd | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
fb283363-5592-4be7-9764-10b624714f82 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
758e15ff-a633-4495-b376-8b9a44799092 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
663f2b28-a649-46ef-ae1f-4bf5ae717110 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
2fc4bc29-57bb-4649-a741-e1ca849c9dcf | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
07bfed0e-c746-4c8f-917a-4248316c2af2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
01d92645-4777-4f1d-b242-0334b457dfb2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
53a37f78-8993-4739-af06-b616d3ae3e77 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
72b0d48b-eb88-4c83-9be2-ae4576358aea | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
6a43f961-bb20-4849-907f-14538694b5e4 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
589ef09d-4c69-46b4-bd8e-274ab38f46bb | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
0367aa0d-f46a-432e-959b-d3859b0a17bb | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
d60e3007-fc96-476a-9381-ad3643717c56 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
0833051c-b789-492d-9806-12e8358f4344 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
17de24c2-dfd4-4fd5-98c5-57ccb2182bb5 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
61e83759-0271-443d-abff-525b6fd7e48c | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
5a417363-4ed5-4d92-8015-12be423cd2d2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
52f857ac-6d0f-4ba0-8e97-19cc8588bb8d | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
e4499eb4-909f-47c5-bc44-525058e7f990 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
ef23f2bd-81ca-4be9-8160-d13efa8306c7 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
b2606c75-08ed-491d-87b4-5d9f1cbfcce7 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
beb398ae-2ae3-4eca-9999-c9c5570f9792 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
8ea913ab-45b6-42fb-afbe-cf977650b049 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
85bcb33d-0c35-4fa8-be16-8f4a22edd160 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 |  | NULL | NULL |  | NULL
40f404f7-dc72-4dc7-8d67-686cfe847e3c | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 |  | NULL | NULL |  | NULL
8250d725-cc01-43cc-8f23-3254f0e72d0e | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
0629db64-83d4-41d5-80fd-22719b138975 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
a2d3c3ea-e3d7-4b30-8838-6aa3cabef393 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 |  | NULL | NULL |  | NULL
26768c99-8868-4ec8-b111-d76c648afdfb | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 |  | NULL | NULL |  | NULL
3636c18b-c058-4485-8039-e34bec8cba11 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
212cb912-e24e-4343-bd3e-bfc6145ffcb9 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
b6937104-4532-4756-93bf-b225d7135eb6 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
b5780f2f-838e-4fdf-8b5d-df06ce8e5484 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
8eb424bf-e1e1-463f-9772-2cca597d3be0 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 |  | NULL | NULL |  | NULL
54f86c39-892e-46d8-941c-f9ade22d4870 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
1fd43ccd-e5e4-4e3e-87df-4397fee6dc37 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
690e78ee-29c2-46a3-81d1-af6c4c5f1c79 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 |  | NULL | NULL |  | NULL
22bf9b5c-b001-4d92-902c-43c4733d2574 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
d366d640-46a0-4f93-9247-7c19cb93fcbf | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 |  | NULL | NULL |  | NULL
6ebf55f6-3536-4e8f-8754-927eaad90ecc | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
8b9d1e14-ace4-4f85-aba7-b989505dd28c | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
b5ca188e-f899-4b0a-96de-c11d5246f427 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
a985b574-9cde-45f0-8a41-e914321f1b1c | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
cb5945f0-9be0-45d6-8bfe-5bd12f4dd4af | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
0a0bacef-9fc4-499e-8558-647fd2c0be1f | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
564a106d-0ae7-4e5d-aa4c-e1fb43ea2901 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
8301bf99-a3a6-4415-82a0-5ad16bd85f1e | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
93d14fda-c6d3-4457-bdd7-bc80db8389e6 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 |  | NULL | NULL |  | NULL
0318d11f-2f87-450a-b603-43d888a89f72 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | NULL | NULL |  | NULL
3aa036e9-1a77-4653-aa81-42b481a56beb | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
f0d82822-32c0-4fb6-8dab-3838b94dd563 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
27e3db0d-9a6e-4c92-bdcb-60af8abe9e3d | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
fd946841-35c6-41e7-a1f7-55e477a766da | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
929101b3-b50a-4d44-84be-00e737994858 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
16a39b9b-e032-4f6a-a032-aa2a246c387c | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
d2d1e4dd-0faa-42c7-a490-9f331f9fd649 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
7a7993fc-5cfe-4c56-8496-d721b321e80c | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
77e090c7-9e60-4cf1-a15d-ea403e60a9fd | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
17a215a7-a6cb-425c-9e29-130efbaf6fe5 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
cb8582af-f8c6-4bf3-a8a8-b3b0e2f41052 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
3405dcee-99a7-426f-8fd8-bed4543525e9 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
b6ecde73-ce19-4b8e-8f61-e46186057791 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
daf56ca5-a16f-4ba9-b2ba-6b728127123b | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
fb9b2ead-06e9-4098-bbdf-db0fc5061f8c | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
42d32473-1f99-4f39-af4c-34f7cbca946c | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
0dda6f65-eb19-40b6-b945-4fd6ca182da7 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
4898f1f9-ca92-4abd-a39a-56c31bca5fcd | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
3f2d58af-39fd-41f0-bc76-431a4b0f6fce | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
2617f26d-02ce-4ab6-8fd0-91eff4d3c449 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 |  | NULL | NULL |  | NULL
198dbe61-54ae-406a-ac56-24a2c8805765 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
89271cb7-de87-400b-b17a-4c0701d14603 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
5e5568b1-4fd2-4063-89bf-358efa693e7f | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
82f7a0e2-0728-42d9-a38c-f0b89ecbc160 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
e1c833bf-37ca-4e04-8d08-70a7ebee73b6 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
a40b1cfd-b0af-4f5a-a559-507feb57f89a | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
f0d50760-95a9-4cc3-a86f-8c427405f517 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
ec81eb58-86e6-4ebf-a94e-aa7e70ab80c8 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
fdb9518d-3c84-4bbc-b469-0f43993ffffd | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 |  | NULL | NULL |  | NULL
d6ab7c48-9bab-4fbe-9b4d-9d860a9c2e0c | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
5e027456-795e-4b81-a8d0-86d8c146ea5a | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
33a55016-349e-41fc-a0c6-e49767add75e | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
341b548c-ae42-4302-9ae5-3897ce9f0680 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
24146a7b-51ee-4e81-931f-e2fd66909a79 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 |  | NULL | NULL |  | NULL
e1bc60cd-916d-4277-a384-2de9ebc1cd81 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
7aa47c82-9e5f-4760-8cf5-15e50e48708e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 |  | NULL | NULL |  | NULL
da380639-a5b4-4d9d-a9c1-5cf6b88927ce | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
9349ea89-26e4-455b-9bd8-3d9f11f2317e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 |  | NULL | NULL |  | NULL
5bcb458e-9e6d-408c-a2be-98e3b88b0ec9 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 |  | NULL | NULL |  | NULL
bff92b25-2566-489f-a195-93767608bd67 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
8fa52884-10f0-4eb6-86ee-aa719caf9619 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
5f92a481-35f9-4857-b3f2-eb108755e8fc | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
e203f001-da55-4f5c-8a55-2da7a8b35868 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 |  | NULL | NULL |  | NULL
e6494aea-47fa-482d-8648-15ab5747b169 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
a4fe59d9-672f-4c29-a3e8-738250b92127 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
246b2e48-94f1-4411-8a1c-d06c04444f16 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
594dd444-ca51-40d6-81a4-94385fd0dacf | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
1536684a-211c-40db-9af6-4199a916d950 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
1761b84e-f0c6-4206-ae56-3e9464a42f90 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
72db2865-e80d-4dad-898b-f9c98b309b2f | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
3d8bd53d-c6b2-49ae-b822-850928f81956 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
0234498d-ad8e-4b40-8afe-c0b403f2ac8b | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | NULL | NULL |  | NULL
2ea8cfcb-d4d0-449d-934b-dfd1aa8f6d8d | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 |  | NULL | NULL |  | NULL
a505d7a8-f7cd-4f25-a549-362868951d27 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 |  | NULL | NULL |  | NULL
68ebfe06-637e-4f88-896d-96645b530d1b | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 |  | NULL | NULL |  | NULL
318c7b46-e673-4d1c-b4cd-7f033c31d376 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 |  | NULL | NULL |  | NULL
0c8e7d8e-9899-4ba7-9984-e99feba3ad6f | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 |  | NULL | NULL |  | NULL
ca695a36-c0f7-49e5-92eb-87e275d4e714 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 |  | NULL | NULL |  | NULL
6b025a29-d9b0-45eb-8b6a-ceb7dc88b186 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 |  | NULL | NULL |  | NULL
4e8d5dc1-856f-4046-805e-8a954648c489 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 |  | NULL | NULL |  | NULL
df68ef83-7e79-4448-be29-50a71572d360 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 |  | NULL | NULL |  | NULL
7c473661-9e38-41b1-abcc-a26a97e1d21d | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 |  | NULL | NULL |  | NULL
e2095962-bdf5-4afe-8797-0233055b99e8 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 |  | NULL | NULL |  | NULL
076d4ef7-a837-4601-946a-029bef5e14ba | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
8a7b2d40-9237-4655-a519-21efd6f22c7d | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
228d2cb7-d7a6-4a36-a73a-283efe271485 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
89cf2416-36ec-48b1-bb4c-9052cb4369fd | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
bd894413-e933-4360-912d-a32f8fea01d7 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2 |  | NULL | NULL |  | NULL
6c05f3e6-37bf-4168-b966-e1438fc2d73a | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
eacb7d9c-4cba-425d-bed3-504356e99776 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
d7eb3ac1-6b18-4425-9cdd-373363321ecb | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
d8032f20-9dea-48b3-914d-27c54b7f6925 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
e52e8fe8-90d7-45f9-b80f-3df0403efeb3 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
a203d871-6590-4aec-8e96-ef991e36f81c | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
0c6f7350-a4ea-45fa-ab22-370ebbee41e7 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
61173988-c7b1-48ad-b17a-2d1497dceaa6 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2 |  | NULL | NULL |  | NULL
48518f1d-2595-40b5-8924-6b742fdcb17d | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
77182ab3-77f5-498f-beb5-85cc3deb90e0 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 |  | NULL | NULL |  | NULL
48c01278-af28-44e5-a26b-dd1d010abdf0 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
bf380df4-2c23-4518-80c6-9a6a4fb159d6 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2 |  | NULL | NULL |  | NULL
26e12f30-e2cf-4a51-ae6e-051856c267e4 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
92155074-1e9f-4f27-933a-53155c709102 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
a153e5b7-67ad-4956-af3f-21da2c6992aa | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
0f3a120b-7446-4255-8ec7-6c7f193af38e | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
ad92c3c1-1c63-48c8-8684-e93fb0e004a2 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
2dcec391-80df-4f4f-ad23-090ea3738b4f | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2 |  | NULL | NULL |  | NULL
7814f53c-c373-417c-a2d2-629c3ac77954 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
2d0208ab-1bdd-4532-a626-e644f08d8c7e | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
34f2c261-e464-4c56-be2f-3610ddae6394 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
eddc312f-48a3-4918-837c-2a59bb177e38 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2 |  | NULL | NULL |  | NULL
b97f01d5-fa57-44cb-815b-daac957d9caf | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 |  | NULL | NULL |  | NULL
500167d1-0ff0-4bba-bea2-7a5a742042af | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 |  | NULL | NULL |  | NULL
723a343f-4e51-4bf7-a265-9242d90af7b1 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 |  | NULL | NULL |  | NULL
8c54cc1f-12be-43df-becf-bc441ce52540 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 |  | NULL | NULL |  | NULL
ec320cce-d1a4-414b-957f-415718a43756 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 |  | NULL | NULL |  | NULL
5a163363-d9be-49d5-81cb-72b428b16110 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 |  | NULL | NULL |  | NULL
13336123-cfb2-4bd8-81e7-16fbb24084fa | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 |  | NULL | NULL |  | NULL
ea185c55-88be-4ea7-a3e9-af69dd064868 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 |  | NULL | NULL |  | NULL
0d3a0903-4db9-4957-9ba4-337edfac3076 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 |  | NULL | NULL |  | NULL
df73a8da-26a1-42cf-98f3-2ee96cc3c1e9 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 |  | NULL | NULL |  | NULL
838dce41-ca2d-4d97-a272-98ca91f47122 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 |  | NULL | NULL |  | NULL
f446b843-8afd-416b-821b-2148b5ec5c88 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
8b29ee0d-724e-40bb-ba29-ac0ebe8559a9 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
93ada3f8-e853-4787-a2ed-f0b7870cd766 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
3ae6c5d3-c414-424d-a062-5333682d7029 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
866b2edb-b250-4424-96b6-c3b86a0976b8 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
b0e440c5-168e-4668-8c38-693f00bd2aa7 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
352cd739-a6b4-4fb3-8e36-c3e93f22bb63 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
810f9668-2368-4863-98eb-093f7cf724fa | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
ad25fa49-2bb6-4179-8eda-e9ac9f8493ff | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
2737454e-4260-49eb-8111-875df1cb3b21 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
7f8d2fde-1755-4d97-91f0-eeb4f092bf32 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
026d47dc-553a-4ff9-a20f-23e44e64751b | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
b605ea32-f156-4465-8b97-a49162316d92 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
fe002313-099b-4a80-ac35-3a3fc9088b7c | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
5a5a41fb-162a-435d-937e-1b032e906c4c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
0b1e0fe6-1291-41a8-9a1d-861417c02db4 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
fe2e481d-f037-4f69-82f4-c7a5c959308c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
8a5a4df7-ccbc-4fe1-a564-d7c289f777c1 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
b5f26494-e562-47e3-a3bc-d18e02851bef | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
4392d768-0901-4ca6-9d77-2ed47f7efb4b | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
e7e3c85a-f8db-45d5-8aec-09f48a3bb715 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 |  | NULL | NULL |  | NULL
f13f49c2-aba6-4985-9435-eb679b8dad4a | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 |  | NULL | NULL |  | NULL
9ea2fde5-4db6-4f90-a51b-174fcdb5e656 | Pole | 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2 |  | NULL | NULL |  | NULL
ee2fd42a-3d23-4a9a-a0aa-58202834ac50 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
a5003db8-217d-4336-9f3f-db97e213fea6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
a42f0493-0684-486d-8333-e2289e0c3161 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
bf0aa8b5-a941-4939-a381-93910f7fc02e | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
f5781dcd-e01d-40c4-b100-2d9f63e273a9 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
f70d9920-31e0-487a-81d1-9d74e638dfb4 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
900da43b-04a7-45ae-81d1-de5f0af9f3b6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
dabed6aa-f8f0-4745-9501-28e7e84dcf8f | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
ce8c1933-be50-4ed5-8f7c-2ff099e88ca3 | Pole | 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2 |  | NULL | NULL |  | NULL
90783e95-7e39-4992-b4f8-71b3128a9482 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
63057f2e-0863-47c1-8d75-4a0eebe620af | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
1ccc9596-f125-47b2-ab94-951452106206 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
e22f244a-0041-4546-b830-e561007ff366 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
56b1a033-198d-4bc1-a07f-0eb32b0ed58b | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 |  | NULL | NULL |  | NULL
6ae0df42-bf1c-4842-83d3-fcb69c7acece | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
cf9c32c9-ead5-430c-a5b3-d98b54e04c52 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
edc9c05c-0227-461b-8f01-842471a3381d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
61bcc74d-e717-4103-883b-297b3173ed70 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 |  | NULL | NULL |  | NULL
30ac2746-26bb-46c5-87c6-acf4c25fb429 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 |  | NULL | NULL |  | NULL
b6dded03-7c16-42f9-a8b5-82641a92bef8 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 |  | NULL | NULL |  | NULL
73c34230-7354-4775-8ee6-23a6e3fa1583 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
108d34d8-4517-448c-be2a-1186078e302d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
547a0952-2197-4b32-9bbb-36d7249a625e | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
4c453254-238b-4546-802a-dc8ebee7a6c9 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 |  | NULL | NULL |  | NULL
e517c7dc-17cf-4c9b-8014-32d596d7b441 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
3fec7da1-48ae-4ce1-883c-83dd0f972d9a | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
0678f8a2-b3eb-4de3-8787-e17649350717 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
a3b2fc8a-8493-41d0-b4d3-8e0d75d04f29 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
99456af3-f563-4a5f-b6ae-8832e8654d17 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
ab67e711-e865-4782-bd62-2d367eb475cb | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
2c011b87-f707-4c13-b9dc-4bfc441020af | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
41947854-6932-4f22-b900-f1f6a97a7688 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
7e35ce2a-9bd4-47f5-8e97-f4fedfda30ab | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
dd6e61f7-a06b-466b-997a-a0a8649f4e58 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
f4506190-281a-465d-9d46-fd99a42d869f | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
ec391e67-c3be-43a3-aec4-a087563f7ff6 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
4dfd5545-7edf-4b19-9d31-458102a0974d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 |  | NULL | NULL |  | NULL
6629aca7-8fd5-4d3e-a714-eee9437ad511 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
49fb5ba0-64c5-4e38-b0f5-2a8c899d902f | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
3d9dac08-5e73-428a-9723-b3bcc0600b01 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
33b79351-792d-4d2d-835b-6d7d670c416d | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
9ed43638-b9d3-47f7-8d2b-087c225373ad | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
294674d8-d9f4-4e88-8461-86d97e46f4bb | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
78d3cfd8-53ce-4ff8-bf20-fe77d7eae1e8 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
be154a97-5b53-4013-9a8e-4b8643bf52bf | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
505e633f-bce3-47aa-85fc-1234122e8ba7 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
13100467-81e8-4d66-aa0b-f423075276be | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
220a05b6-c830-4ef5-a6da-fa4170b7b94f | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
972e7dbc-c100-486b-8177-670cb2803156 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
464fec34-0df9-4edb-af91-51643bc42449 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
d130fb4f-c85d-4ee6-a2d8-e42e79f0f899 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 |  | NULL | NULL |  | NULL
32c6b6d6-cb5f-407c-878d-0985e5c5acc0 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
e9ae9ee6-2fc5-4b44-9733-cd5cfb8bb0d9 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
7dc01b1c-02f4-4d88-ac33-1e5c9abc506b | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 |  | NULL | NULL |  | NULL
8fd1d9c4-bf77-49e7-9abf-b1012c4672fb | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3 |  | NULL | NULL |  | NULL
0204041b-1a77-41c7-9247-42c3b34be7aa | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 |  | NULL | NULL |  | NULL
256b66b1-2ddb-43cb-ad76-83810c9f160e | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3 |  | NULL | NULL |  | NULL
194dc582-a29f-4dbc-a317-91b32acef012 | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3 |  | NULL | NULL |  | NULL
38683f2a-5adb-440c-a1c2-81f1288d9be0 | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 |  | NULL | NULL |  | NULL
f724d32f-943c-4cdc-9711-87ce46c7939b | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 |  | NULL | NULL |  | NULL
d5aae43c-3c1e-4043-88d8-def61824f9db | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 |  | NULL | NULL |  | NULL
fa40f187-c389-41f5-9127-aa22ca5bfa94 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
afaad66e-9a9a-4bf5-afc2-7ee64c669dbb | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
d833749e-0c56-48ca-a0fb-7beff27afedc | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
f60dc076-11b1-4df4-b652-af532aea360c | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
637599e0-ec51-4add-9d1a-42663680cb5b | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
b3bf5bcd-09cb-418d-9e4b-aa111694b225 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
4f2a3573-f2d9-4ff3-b2a5-afe6de78150a | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
e84f7c0b-e5e0-41ac-891a-c728f3990d34 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
0680f341-6c1f-4e59-baf0-e1d4c69a21ae | Pole | 2 | Distribution | 2022-05-13 | 2023-05-13 | Level 2 |  | NULL | NULL |  | NULL
85ee3e80-4f20-42f4-a67d-38af9b9511d8 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 |  | NULL | NULL |  | NULL
9ed03e98-53ca-46a7-9617-77e5ed9ffb1f | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
06da5821-f246-4f7d-9c6f-752a68a848f1 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
db5f8dc4-33e8-41e9-bb0f-0ad577f75c62 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
d773336f-c1b1-4778-94e1-b32fa1bd9a10 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
396e1662-d2d0-4286-95fc-d376b2e62559 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
d4ce3d9c-87c4-4ca5-8d17-dc551a99da55 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
1ef8c973-b823-4a2f-a5d2-e06b849c4a90 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
47c89d3f-4265-4127-bae6-7ac6891e3a39 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
9d666eb6-1b72-4bbd-ad54-88d2094f5c34 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 |  | NULL | NULL |  | NULL
5a6e5bd4-88bd-441a-a0ce-17c749ae2ce3 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
a27edec6-3d6c-4d71-98db-6e854ae4fe9c | Pole | 2 | Distribution | 2022-05-16 | 2023-05-16 | Level 2 |  | NULL | NULL |  | NULL
519b67dd-89ac-4b6f-94f8-6e3f24d8e250 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
1159c80e-4c3b-45d0-bba4-21f8f8f4d773 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
6d6c1649-9610-420f-a93d-da286d9a99bc | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
9557e282-8f9d-4a1c-9f17-3c7931ec364d | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
22589855-1772-4d68-85af-91b3e958f9df | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
237dad7d-48a8-460e-8c48-89b67321a2aa | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
e2c3e5e5-b4db-4e9b-b384-c3a5d7977276 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
41b78726-5139-4e9c-bacc-525098d42ca4 | Pole | 2 | Distribution | 2022-05-16 | 2023-05-16 | Level 2 |  | NULL | NULL |  | NULL
ccf999ef-e5d5-4a6d-9874-66232e53efb9 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 |  | NULL | NULL |  | NULL
0f070b41-15c3-4d82-b992-9d73209fa178 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 |  | NULL | NULL |  | NULL
078072b0-71f3-49ad-bbfe-bf824f9b3cbf | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
cf4b55c9-5aba-43ca-b132-d30426043996 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 |  | NULL | NULL |  | NULL
2b8bd0da-72b9-4866-a727-2242c6f6e6e6 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
8b93c3a2-edd4-44c4-bae6-07877af99f1e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
eb36f181-a496-4a89-976d-cb0a48294277 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 |  | NULL | NULL |  | NULL
62a80d46-8938-4e92-90dc-5cf6e3998b80 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
c162c34b-39f3-4869-af08-224f7af9fee9 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
f589bd31-b3c8-4344-ae97-b49df98d8913 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
97df6be5-a6ed-4314-abb9-e8e2e1270fa0 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 |  | NULL | NULL |  | NULL
a6ce0b2e-ac23-4aaf-a34b-558ac239c1f7 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 |  | NULL | NULL |  | NULL
714a5bcf-804b-4038-a5d5-352eb694ab5e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
488caa30-ed3c-4f9b-9b11-c1e178d6b86e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
76feba2b-2651-4f98-8bb7-bd8a7faa8b1f | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
f2d4e6dc-2309-449c-b1a2-c556636c8fa4 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
4b62cb6e-b2d5-4723-ab9d-a64436a57b43 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
c4055f7e-19e9-401c-8d65-1c7cfca7f892 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
876a7730-77be-4090-bc98-50db532e4141 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
1070bec3-2966-4e39-8354-b72b3d08757f | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
8346f35e-f234-47aa-9434-a2116b44bb26 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
6e168b59-7a0b-4bba-a899-81f7a92ad7f6 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
f016d9cd-42e8-402d-9607-a374b1a1eacb | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
219e7cd2-12ca-4b13-a8b7-8621badafdeb | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 |  | NULL | NULL |  | NULL
0486a58f-bdb6-45b7-ba7d-28240ba67d45 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
82a7526d-7a2f-4475-a870-68c09b9c835b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
c830a559-ab82-4815-92d3-c2386f52acad | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
e915edc4-9537-4dbc-9a78-47734a6ab98e | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
90b4f5e9-41c8-48c4-9322-70be8a13ca5a | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
3b773101-870e-4a08-ae20-b02ab96a33c6 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
0640b799-8f6a-4f11-8d18-dabb435fe145 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
2edafc4e-a5e2-4c3b-a0df-6a25975ca7b0 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
46fa30e2-97c6-4a32-840b-7b3e9f31d2d8 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
6b04fb6a-31df-48d0-9fc0-334cd1a12725 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
a43c9627-0d8d-43a5-bfc4-4cd8414b681c | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
a519ae2b-006b-4b3e-928d-864d5ef4f0bc | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
74266696-695b-4964-b1dd-a2b63713e3c1 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
f8190310-fae6-4b2a-b517-ab1f4388407f | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
d0283dad-cc53-4d92-a7fe-42be13e315ea | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
6bbf3f82-28f2-426e-9b71-1d50074026ce | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
35d43c75-e3ef-41a7-b070-4c6eac7d844b | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
32333d13-64fa-47a1-9e56-dca8e3eef442 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
f89edeb2-c46a-49f4-8055-92bf361b8f29 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
0ad3329d-1306-423e-90dd-7b311f7760cd | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
4147ebb7-d785-437d-94f1-c63e15439295 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
662e0bfc-3131-4f47-8230-40fbc4fed84e | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
b3ac1287-4de5-49ba-a161-efe7e47413b8 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
c267a96e-9a05-4bd3-96de-095097d5e278 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
0707aaf2-c0ae-469f-88b0-3cb3981aa796 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
5ce1a4c8-5c74-4e61-8b60-a253f34df4b9 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
a26810fc-68ac-457e-8ea7-9abaccd6588a | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
5903c963-16cb-4a0f-8e38-f800c9e244e8 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
8732133a-438e-4ded-ad8b-cec9ba855769 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
92424739-e331-4e40-a749-7a329c235006 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
c311b3f2-bf1e-4e29-b177-17934cda0ece | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
175f420f-e847-4184-9998-fd23d168f48e | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | NULL | NULL |  | NULL
1864c947-254f-430d-811c-db73e773ef64 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
104950d2-0272-416f-8686-84215cf155b0 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
0d80419b-bf9f-4184-b4ae-4b27ae58c222 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
6b877e8d-8acc-4e10-b718-5eb75c248112 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
de823bc0-8d63-4926-a57d-7854fc53a55b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
aa65076f-4933-4807-b073-434bc9591816 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
a1ea593c-b185-4196-b046-595f5ba05e97 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | NULL | NULL |  | NULL
f3b1c574-0fc6-4e8b-898f-170248306465 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
3491b4d5-1c53-4b90-9947-3be1e233dfaa | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
123a9e06-62e8-4afd-ab56-247195019dbf | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
7b89fcb4-3cd3-43fa-9592-c47b1ca957e4 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
5c21b966-f6db-41a9-bf62-b3d9d2f34c3a | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
8460ce50-0b37-4933-ad25-95050f88c719 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
6f2df028-03e9-4e56-b18a-2c4bfb112639 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
571f0020-9591-4622-9474-2b8e91dfba03 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
d542c0d8-df17-4f29-9ec2-fc934ca050d7 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
536d83ea-f364-426f-93a5-0a620ea9406e | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
7d8414b7-ff9a-4d69-8992-df55ac0cbc62 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
c8e5f9a6-ce7e-48f2-80b5-a5e0ba803450 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
50d35370-528c-423c-bd11-8da4b094cd89 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
9c438d86-726c-4e65-a203-d2bcac9d287f | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | NULL | NULL |  | NULL
50abee65-818f-40b3-8141-6948c17c2d94 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
5220555d-530b-45d6-b4bd-ee50b223879a | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
ea5785b1-bf8a-4b71-89f4-3af532006b39 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
ec196a38-98dd-4e08-8eea-7c971650741f | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
304f1e88-33f1-48e3-ba34-7bbe004eb742 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
49e8d807-fce8-43c9-bceb-02bf5ed9d1f0 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
db876965-5197-403b-aefe-95aad0258ce1 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
4e7fa2fa-8c1f-4f5f-bee2-8b6dbe927515 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
93a335ca-82cf-4835-a281-331b5e83b781 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
52f93104-8448-4fef-ae59-88653391c9d6 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
3e4d08e2-1296-4bc4-b3bf-81756346a887 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
ade811e7-b55a-406e-bd85-e3cd30edb095 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | NULL | NULL |  | NULL
4ad9da18-917b-4291-8884-271f04675abf | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 |  | NULL | NULL |  | NULL
314e7b35-7ea7-4eae-9c90-e028ea06a985 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 |  | NULL | NULL |  | NULL
148c6197-d403-4754-8baf-666de4873008 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
449b87c6-5e53-40d2-8166-0665f7a1d879 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 |  | NULL | NULL |  | NULL
9c0e2499-44d6-4e31-aff9-74f207158bdb | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
82ea73e2-0efa-45ac-a8f9-98bf59bf105e | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
010e0020-c8cd-48fa-a80b-834f2967770e | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
ac237f28-9555-4f50-b984-7528333fadbb | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
7459bda8-3abb-466e-b42f-3268ac203cb3 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
055dc2a9-be82-49c3-afb8-88fb39888a0c | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 |  | NULL | NULL |  | NULL
ae24e9d1-bdec-41a3-a8c2-89f32bbc48b5 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 |  | NULL | NULL |  | NULL
09a260c3-77a5-4772-a258-5a1a5b66ea3a | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 |  | NULL | NULL |  | NULL
d68215e5-e57e-4acc-8292-2600f6410c6a | Pole | 2 | Distribution | 2022-05-23 | 2023-05-23 | Level 2 |  | NULL | NULL |  | NULL
2e353a9f-445b-4240-8dbd-3236eb6e8d23 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
47c58d6f-9aee-45f0-ae9f-05b326bb32d6 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
46fa1606-63bc-41e6-9f34-efad31c5f0b9 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
dc7877b6-a9b0-4fe9-8240-9ef7cc1dbfc9 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
d3043195-c9c8-4020-b207-be73e2db89cc | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
efc9b24c-0113-4f8d-8387-17679624b0db | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
3c50df41-b1cd-4c2b-97be-80611e16cbaa | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
71a4bc93-ed2c-485f-9823-2345f2cea45e | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
abe60f95-1731-414e-b847-a507c4ea0969 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
2f152e79-307e-41cf-a830-5f5389eec106 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
3a855c2b-1857-42c8-8850-c51d01e2f481 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
6e368a25-af71-4924-bcbf-00c3c50baef5 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
17b25550-373d-4c9d-bbcd-882f32c45001 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
5a41558a-d04e-4c48-b213-1a82a99d62b8 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
9155a036-ddce-4153-a0d0-44c851a12fca | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 |  | NULL | NULL |  | NULL
961f2713-774c-471c-8f08-c3b9cf972127 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
d5bb20d8-2408-45e9-b957-d2f5e1eba677 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
76f37124-91df-4cbe-8964-13cf992f56b1 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
5d553ff7-ee75-4cde-9563-0da84159e678 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
ceea8410-f62f-416a-a7c4-b23e273cf619 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
b5ab0eaa-c29c-4281-b77a-93d8b0114f33 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
9f99edc3-6bdf-40cf-910f-5f84dacab975 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
88fb5747-16b1-4f56-b066-ccb7fab27f4e | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
732c27b2-45de-4ed2-89e5-6e48a2bcfe04 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
0df625a4-db4e-4cee-a6cb-d4dadfd77d3a | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
3c50456e-25b7-4a83-b669-353187ff64f4 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
ebb27f0e-7932-483f-81b3-afdc68154065 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
fd340584-8b88-483b-bf90-26d3f8827736 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
60183bb6-6bcf-472c-8413-081fd6aac91d | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 |  | NULL | NULL |  | NULL
13b0b3ca-53ee-43b9-923e-5b6356603705 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
f4e22ffe-6b08-4517-85c6-75ca91aee3e9 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
8aeb2d85-050e-477e-af90-c4ebaf7c42c2 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 |  | NULL | NULL |  | NULL
f160d08f-6a1e-46d9-ac66-d902a79b9ed2 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
d7aff897-46aa-4afe-b1d1-dfa8685cb22d | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
22299901-0f59-4707-81b9-769ec8f650aa | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
59455992-9461-48e4-97ec-f5f9c665ccc5 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
de4f3f45-d0d4-4ba2-a3c6-bf3836c2d426 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
66115500-4bf0-4d9f-bc1c-b7d06e4bce20 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
5072ce8d-9834-4add-a63d-e52acb103917 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 |  | NULL | NULL |  | NULL
1dc314d0-11c2-4f43-aa8a-a4131e7c003f | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 |  | NULL | NULL |  | NULL
22b4cbd1-3d67-415c-a47a-50cbd2b022e6 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 |  | NULL | NULL |  | NULL
e526279b-ed7c-40eb-8099-3746fcdfec96 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 |  | NULL | NULL |  | NULL
7d2f1c1f-932e-488b-9765-49ad27882812 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 |  | NULL | NULL |  | NULL
3e92f47a-65e1-4e13-b072-7b1cb5e090e7 | Pole | 2 | Distribution | 2022-05-26 | 2023-05-26 | Level 2 |  | NULL | NULL |  | NULL
f449ab15-e9ff-45fd-bfae-cfcf326b07d7 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 |  | NULL | NULL |  | NULL
63365578-58ff-46e9-8336-cf747e38cde3 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 |  | NULL | NULL |  | NULL
35209a0e-9b48-4506-87da-501a290bdbaf | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 |  | NULL | NULL |  | NULL
e0c988d9-a902-49c3-9c95-34d6067e3fda | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 |  | NULL | NULL |  | NULL
a2473792-ef56-427d-a95d-423999bf95c1 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 |  | NULL | NULL |  | NULL
ac07bd03-ce8a-44be-bd89-d24904f5f391 | Pole | 2 | Distribution | 2022-05-27 | 2023-05-27 | Level 2 |  | NULL | NULL |  | NULL
7493ed1a-00af-4355-a092-383cf7c0d111 | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3 |  | NULL | NULL |  | NULL
9955d68a-5c5f-4d3f-ab30-f6c18feb4e1e | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3 |  | NULL | NULL |  | NULL
c2f59fab-62e9-450b-9c65-c109628b3cfe | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2 |  | NULL | NULL |  | NULL
77332381-4f14-4eb1-b441-72c8b5b8e7b9 | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3 |  | NULL | NULL |  | NULL
96efef68-d2ff-4ca3-a2fc-f0e3aeb407aa | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2 |  | NULL | NULL |  | NULL
80b85f3a-9117-41d0-9c76-d1e70b8f289f | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2 |  | NULL | NULL |  | NULL
877836b3-dd74-4bf5-9c6b-ff661710bbe3 | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2 |  | NULL | NULL |  | NULL
9b5c75b5-ec13-4479-a57a-3d5eca35c05d | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3 |  | NULL | NULL |  | NULL
a75dc238-4b55-4230-80b5-c570377e8fb5 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3 |  | NULL | NULL |  | NULL
25b2e274-6aaa-450a-aa2a-c3ceaf205b75 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3 |  | NULL | NULL |  | NULL
d9b309e3-a9ca-443d-925f-931b8c31be80 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 |  | NULL | NULL |  | NULL
a0e91ea1-20e1-4eed-b5c3-5408145d40c5 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 |  | NULL | NULL |  | NULL
344540d6-aa77-49c6-87b8-ee89545406f9 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 |  | NULL | NULL |  | NULL
544ea706-289a-48f0-8384-c72a8b6ab557 | Pole | 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3 |  | NULL | NULL |  | NULL
ab349ebf-3f7b-4b3e-802a-1025bc172f19 | Pole | 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3 |  | NULL | NULL |  | NULL
ba834cde-e3df-43f5-96d1-33b9be818e80 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 |  | NULL | NULL |  | NULL
c2f00bf4-d74b-4975-bed9-12f53f52f774 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 |  | NULL | NULL |  | NULL
cc09cfdc-7ce1-4808-852a-f933e92f2e84 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
a57bea5f-2613-4fad-926a-bd76af3440e8 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
a24df196-8d97-4a12-92e6-f5a8922fc6a0 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
568897e5-692f-4a67-9af5-1ba24d26a6bf | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
44d3930f-fed5-4551-95da-28560ea80bed | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
0257d981-50de-4016-92df-0a9a2290e96e | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
c72b6fa5-65cf-4ee6-b860-e9bbdd92d250 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
365ad973-8dea-4f3d-b539-c451969f6133 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
a9408bc8-7d43-408e-8ce0-21b554a0fa6f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
641c7bd6-7e31-4005-b8e0-0e00bc1a38b5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
ba4ef147-96b6-4d55-9e4b-4fe01bf5a68f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
0004ef32-55de-4796-a5d2-ef0815b5b4d5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
b3916c20-c8e8-47fe-88ac-41405a4752e1 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
43d4a2d2-071a-46c9-bb90-b2749196bc9f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
cd4a6116-442b-4d49-b794-8b71fd6785b8 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
1105f55c-a02b-4f8c-a1ab-ec093302f416 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
8b6b3e00-ee3e-48e7-a445-fce9cc685653 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
90fee683-d963-4d0e-9327-346e9f41b287 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
65e906ad-2194-410b-b868-fc5af8b4c6f6 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
28ff136d-8274-48a8-83ba-c3f34a0bf1e1 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
8eb7d97e-fabf-429c-ac5f-4a8efc01a614 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
85bd66b4-9b62-4760-8d76-49d1113c42fd | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2 |  | NULL | NULL |  | NULL
1dcc91c3-6439-4a25-b616-c0c3163c8238 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 |  | NULL | NULL |  | NULL
2b633708-0cef-4527-a8d4-9119b075dfd0 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
5a115124-8908-49a9-94a8-4fde1c0b83ff | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
0f3b29de-43a4-4019-a79d-eb0d26a27127 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
c3b3a404-477c-439a-9ce5-65cd6e2437b8 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
be5ece9f-9866-4eac-9334-2a0111a72dbd | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
fb367aff-2091-4b6b-b6dd-4b5368d95621 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
8347da64-97a9-4a07-816e-f71c74c97c51 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
d05e7b2e-80a6-4535-a5de-94064cea95bc | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
bdfc1123-ca3e-424f-a172-c484daa01e15 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
1091024c-4583-41af-ac5f-c8132f98a92d | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
04d90c31-c6cf-40db-a291-c14c7c0d019b | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
79df62d4-4dd2-4508-ba7f-6016607cdb70 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
2628c265-f38d-47c8-91f4-c3b899afc407 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
f0366e2f-3c13-4419-b8da-b0cb60dce6a2 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
ea5770a3-ff60-47eb-8279-807cb3b89135 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
a462f44b-488e-45ff-a864-6352b6f8ee8e | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
2a83371c-6805-483e-b8fa-115e4efd9845 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
b18384f7-d98d-4851-a203-1dd41237edff | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
a7e4c324-e7d0-49ed-a931-d2e0f25d95a1 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
c2b386f3-ff5b-4dd6-8cfe-eaba46a5655f | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
498bbc1e-87ed-402f-acaa-1e43184e88ef | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
89b7b56c-6ee6-4ea6-aa4f-c62b9e0b616c | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
6024e71a-260b-4ac9-96dc-e8be5c7a322d | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
17a22e5b-8b3d-4a7b-b9ef-36576707d486 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
75346032-5ffd-467a-a9dc-26765ebe63f9 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
6f69bad8-f7b3-456c-8901-297866b3168a | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
ef5123cb-d246-4d14-ba64-fff8b68cf143 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
e4207e32-3e57-4e46-aff9-bef016f2e1e3 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
6164a3fd-2e5d-4854-a49c-e1ba315485f8 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
5dbb384d-5ed2-4e9d-8243-c29615898e04 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
5c7abca4-93ab-415f-aae6-894390258a8b | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
0200fbf5-5e71-4d27-9bf2-1b0f89bf8a16 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
43501e18-0e84-4ad2-ab2d-2a2b9e7df184 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
a1e8170d-d7f9-4c71-ac3f-8e22425c7ecc | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
d6cd3eed-b6b8-4874-8349-92039cf7d9db | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2 |  | NULL | NULL |  | NULL
143bbcb1-4bff-4433-84e3-d094e278d229 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 |  | NULL | NULL |  | NULL
e2af2c61-872f-43dd-ae6c-a1ffa0134aff | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
d8a5981c-99a8-4882-bc7b-fe15da7e877c | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
94a0c8c5-2903-4047-bbea-5334412cd953 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2 |  | NULL | NULL |  | NULL
89243e80-21b9-4c81-abb0-ac874c6aef31 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
46b3736e-d55a-4b84-86f5-89b1306ae357 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
16957b7f-f983-4d49-889d-1c2c9b4c3e2a | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2 |  | NULL | NULL |  | NULL
0ed4cc9e-383b-4403-83f3-140be6a2aec1 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
811c29aa-d1ab-4bc5-b0de-4dc6d53e7404 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
eb6dc44a-b988-418a-a0ff-22d1cd79acdd | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
033e80b5-8fdd-4101-826b-1b3dbb4c5003 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
2d8f792a-2f8c-4947-b3e3-dda69c820c66 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
d4d0f64b-1b9a-466c-bab8-f5c5130ebc3f | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
00c6c0df-7ba4-46e4-9ca0-f596c6566e99 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
6ff2103e-9b57-43e2-a8e2-6a016c8de0cb | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
12c01b20-ec26-4be2-b598-24c2ed5b66ad | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2 |  | NULL | NULL |  | NULL
b53ba4da-4c50-41d4-83cb-4664dd6fe869 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
610a11c5-d848-4ba5-a3e9-4b9f049202c2 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
10e75c0d-ef4b-4388-b340-0c723134601e | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
c7f5bc57-50e9-463a-8a0f-1e97063e5d37 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2 |  | NULL | NULL |  | NULL
5e665a4a-1cfd-4b7c-b3c9-79ac17054773 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
7b4e4f45-4042-4bda-a3eb-93ddffa49b70 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
c043bef2-8c25-4843-a6d7-4c57315b35ac | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
1c1a3677-ba9b-49d0-a429-8e1417474d26 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
ad4bc031-31af-4954-a81a-dbadd5261944 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2 |  | NULL | NULL |  | NULL
6721eba9-26ee-4363-9e7d-f2baf93dfed9 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
e99a5261-5b6c-451c-ad50-e048655028ee | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
39c9cae9-f732-4d6e-9ce3-4fb4e0ad0de8 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
fd680597-8140-4f9e-afb9-d33fb48688eb | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
d34c369e-0670-458f-9779-ec2eee716336 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 |  | NULL | NULL |  | NULL
b3382cfd-c86f-403d-bc3e-889a8fa63c5d | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
d5daeaf8-1647-460c-9095-ec2bd3fd7fdd | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
e1b9709a-344d-4b43-857c-0d6c316f2268 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
7360a078-0a86-439d-a7c0-196dbda5fecc | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
bf012361-830d-45ef-a59e-602e4e18d229 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
2ae64c44-e90e-4ed1-81d0-6959f5fe1b3b | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
6e80bc61-8c7a-44ad-88b3-c3641cebfe45 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
fa02ba18-7868-4f64-87fd-aeb01f8e6926 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
dcac5f3e-4407-470e-be13-c09cf9a31e21 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
67afd26c-d3f6-4ce3-a851-501a1a857693 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
4d25a906-c4e2-4089-ab3d-4449c0fdc7b8 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
f94afe8d-cb88-42db-b43b-d702af3a8d7f | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
d4ae4378-3070-4ca1-9009-183da73c76e0 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
639521ae-05f0-4abd-b6c5-82b96a55caa1 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
a706e177-cd63-4ef9-984c-e27242f5da03 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
8131c11a-f9e8-488e-82f9-892003027963 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
0d1f616f-770b-420e-986d-f1fc7bd3a990 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
dc248d8d-c700-4bc9-a3ba-d55f7e2fc200 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
59369ff7-ec57-45e1-8bf9-c0577d184f35 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
590cf76c-a89a-4e81-b739-d18a1642ac34 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
b97a498c-5c5f-48ec-8343-cfd2184200d6 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
955f7bad-e0de-4d11-966e-c08488217d6b | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
030516a7-37e7-476b-af86-799f23d757ba | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 |  | NULL | NULL |  | NULL
16736fa8-722d-4f1b-92db-821095e5fd60 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
3894c5ad-c5ea-4bae-8275-5b100046b365 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
a48203eb-b6c2-4b4a-95f1-b19c22e55207 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
ca74a331-e4cc-4f8e-ad42-8574c45660dc | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
992ded53-33dd-4611-af76-9f92d103cf7d | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 |  | NULL | NULL |  | NULL
eec22a6c-64ac-407a-8e2d-9a47c73998c5 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
fc4b04ed-221c-4b43-8109-d0ec8d1e23eb | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
d8f0eaf7-a89c-447d-9b9a-ff7ffb3bdb28 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
ee259df9-03fc-4a09-9126-d0b360ffb060 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
8d8aa830-4e11-4ac9-a531-f31c1b7f7f8e | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
94e06f01-586d-4916-93b3-4858ba59a27d | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
547df3a8-d8cf-402b-87f7-886f2b88ebd8 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
3ff53d29-9563-4f26-a93f-3de4ac86d9c3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
19ec18cf-589b-4159-87e0-a0ce16964c5d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
a3a973dc-676b-49d3-9567-b008c3465bdf | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
776ba426-b852-4b74-ad93-8b094a7a7bf7 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
00b8c0a6-c1a8-4e54-8c60-19669f2de0f3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
d206aedf-c741-47e4-8256-a93cd5b71298 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
d0672f7a-c10b-4a24-be37-c98d5566b47c | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
a91b776b-9d8b-4edc-9a12-b7c48ed066f6 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
e2606b07-1c58-4746-9c85-884dac2ff3e3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
e0909b68-8b8a-4028-9a48-75c5c0763c5d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
c7ea0d7b-8c7e-420b-abe5-83e7ab9e7429 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
06b47d1d-c5fd-4fe8-b82d-dbd38ea8e0e2 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
b90cadbc-a988-42b6-b032-ee25c611af61 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
44ce2fcd-932b-443e-bd84-2dea92269b13 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
6aa2eeac-a9a8-49ad-8e90-7c088d354d00 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
6efafb16-b4b2-4eca-88a2-06a14c1ea4fa | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
59e80f05-3557-4c90-bcea-bc10df1be715 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
bb7ae4ec-850a-4889-be7b-c7769b3cc726 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
9f5f4036-0b0c-4ae0-b953-e198ca5a87df | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
6e8efdb5-9225-4f0b-bdab-a9e86d23f028 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
a093f7d3-98b4-45cd-9f44-5994f9f7e574 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
72e2909f-3a6c-4947-ad12-a6e0a22ea95f | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
bf041ecd-6b91-41f1-b71b-aceba9ac6631 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
5f5b4618-7268-428c-b0b8-09d42b89103d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
9bdf1422-0a23-4167-ad66-f099a033ed88 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
7a1111ea-8917-4aad-bf78-02a3f7e22a8c | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 |  | NULL | NULL |  | NULL
7fefae0a-266a-4014-8243-9d52caa0bced | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2 |  | NULL | NULL |  | NULL
7498583a-fd8a-499d-98db-67d2943192e0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
d21f36af-a788-41a6-a2f7-406f2ccf412a | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
249927ef-e0df-4e3d-8205-354d55f3fba0 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
3b53f5a8-10b0-4db1-a667-40d33a431ed7 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
356cd0ba-d898-4e07-907c-f35f19af5018 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
eec0317c-6a48-4eec-9716-7ce75e49df66 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
a34c196a-47ca-4983-bfaa-c8821936e298 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
5b15de2f-4970-41de-8235-aaaa4a3b6961 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
6734fe9d-87f6-4247-99ea-7163f41dc9a2 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
8b8256dd-84d7-48a0-8da3-6a035abf43e0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
5182dca2-ef61-4303-b834-52684d6930ee | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
1bddce8b-51af-493f-8ff2-fac9ee93b34e | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
a9cd4a66-b9b7-42ce-bc51-c7ced036d76f | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
efab264e-d833-4984-8b68-4cffa4b0faa3 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
8823bcf2-5a8b-4e38-a025-12a11cfb0f69 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
f2c2ad53-04ce-4783-a4d9-951e48be4994 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
80e726dd-8693-4556-94ee-30918a08623d | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
9afc7767-cc86-497c-bb2e-b61316415c7b | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
b5f6ae45-7962-4d58-b38a-06dcc5a2cd15 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
7e618191-a9e9-40e3-b7e0-2f90d7ee8142 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
d3d5c8c5-5f12-4ef5-aa51-97ea57ecbb41 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
910c4810-263c-4616-93a4-af5bb4c194d5 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
1cea45da-bc2d-42ed-abcd-f25cd56c82a3 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
7b09cb7c-f6dc-4ba3-8aae-e83bf299e90d | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
6dbbf8fc-a6db-4565-8976-7174e4606826 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
35ed2a18-82a2-4ab2-b79d-171d24206f13 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
bc7929a8-81eb-4f38-b040-4aab7bf60376 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
c2a855e3-f912-47da-a981-c5cb431607b0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
9f62e665-54f0-4c44-b33b-53c80657a277 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
a16e4a84-84a7-4f5d-9c1b-f86cf42893fb | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 |  | NULL | NULL |  | NULL
de614919-df7d-490e-b6aa-3ba696d31a37 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 |  | NULL | NULL |  | NULL
efd3f90f-9739-4c81-a469-48521dbe643d | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
1c1504b5-446d-4ff1-82eb-28faf23d02af | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
c21ec53c-ef54-444b-b8ce-623927a779a0 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
fc9d603a-221f-4c0e-aec3-1aa90c798efe | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
db6af8c7-5e20-4e33-b1d9-7cd021bf3786 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
39c1dac9-e06a-4b8c-bd8a-4c93aeac0196 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
1170992b-ed45-41ac-93a7-032a54eb0ebb | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
73ca89fe-85b5-4b96-9621-8e91e4a65ca9 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
5d124e0b-77b2-48e7-9313-3f3db4224a4c | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
5775a1e6-05d1-44b5-a543-7e4b7318f052 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
91da5b98-7af5-4a4f-ab56-6f8195f33720 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
3f9e0f34-cd83-4ba3-a1d2-bffcbd1108e2 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
e3eedb98-60df-4408-b15c-d986e8827147 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
0f30e4bf-789f-44d9-a930-8727944076c1 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
5b615b9c-ac4c-4d44-85a0-e409bb969a3c | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
8dfae59c-eed3-4df2-8281-c14d0df52f36 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
699324da-bb0d-4487-a086-e86d128a785b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
24c63960-2949-42cf-903e-ff759109994b | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
dd57316a-83fc-4d6f-81a2-dbc163e2924b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
c7e8802c-d27b-4b94-baa7-e10f88157697 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
ab02603e-840a-43a7-9f4c-325968540c93 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
f41478ee-683b-478b-b430-6641d9c61b4b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
261cabce-af69-41d1-a513-b03e51fed527 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
fc47e68d-ad6c-4e62-b3f2-e4668ed6ca13 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
d1a0409e-8058-4121-bcdd-874595064e6b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
b1a7d64c-7a21-4cee-819f-df93dc2eedd5 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
19cab8c8-0dfa-4322-8b4a-05320eb6f9fa | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
408ead9d-8c47-452b-86ea-166c4a7d60fd | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
1de2c696-a2b7-4b7a-ac6e-39f87a4dc1e5 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
d03823a5-9742-4526-a977-5a7534b82a18 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
b2f9c999-a4e5-4b34-aa30-10c7ac927129 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
8d0e55ff-e064-484e-8b42-b5e0c78a2695 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
55c92808-b9d6-41c7-ace1-392949910923 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
f0166268-2464-4c2c-9702-7aa32f362b69 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
a62bae72-306b-4eae-832a-2129fad5a76f | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
3314c839-49fd-4c84-94f0-ff403a2bdffc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
7a096404-c6db-401b-9c0e-6d69e51f83fc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
74c5dd60-f8d2-40d8-b606-4ac2f7096b0b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
804502ca-24d1-400f-a84d-0e9a9eb097cc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
3873a587-5e53-49e7-9d4a-2f9f5a677351 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 |  | NULL | NULL |  | NULL
00b3fd56-db6c-41ff-a851-5eff8b2cacdb | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 |  | NULL | NULL |  | NULL
34575d69-e68f-4379-9637-d26f15c8b743 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 |  | NULL | NULL |  | NULL
2a57d8cb-f0cc-4d12-be65-ad767a431439 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 |  | NULL | NULL |  | NULL
190563a1-0644-4d08-b1e4-23489e44ff24 | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2 |  | NULL | NULL |  | NULL
e63ee37c-9e77-4b4c-a390-1fe9daf492f7 | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2 |  | NULL | NULL |  | NULL
65afe448-4e5d-4267-aead-b056db2139d3 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 |  | NULL | NULL |  | NULL
f6162a34-a159-4591-bdd0-9495d27962b4 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 |  | NULL | NULL |  | NULL
6b6cdbbe-fcf8-460c-9a52-178b96039102 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 |  | NULL | NULL |  | NULL
ce749701-3e23-4323-9ee0-3daeba73ca6d | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2 |  | NULL | NULL |  | NULL
b142c4c5-82cc-4937-a8e4-2befc07d782c | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
a9b0bcdb-a1bf-4a10-a4ea-dd20a4ac0b5a | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
7d98426a-1568-40cf-99fb-d528cc8a41cf | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
43afcc3c-dc6b-40d9-b76d-b32e9627b339 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
f7b87618-6ab5-4a0c-9cd2-257dc9c646ce | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
d60e7213-0abf-4d68-a77e-c670919e64de | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
3f72c3c4-b139-4746-83be-66219e91b11c | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
53dec5b3-faa7-4bfc-a0c6-48c5cc985149 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
efcc95b5-2126-42ab-8708-b9881e78c60e | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
b7809b28-bd3d-4e4f-85a8-8d71e13df508 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
55ff8a66-62f9-4125-90f7-3fd21f8c442c | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
32e267c8-84fa-43f5-ae4a-81246921927b | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
1285fe7a-41ca-4da2-bcc7-e9f28b4f25ee | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
a57bfe1b-c179-46d0-b10e-ff93c631c020 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
45c74e7f-6f85-4b30-888b-4b7260c34cf6 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 |  | NULL | NULL |  | NULL
d1753f35-63fa-464c-b705-daf1cf8ac8bf | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
bad390b3-c903-4be0-93e4-942920b6bb8d | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
49e7d3c1-4baa-481f-8b7a-99b53ecf6011 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
3c2024f3-3bfd-4964-985b-a8a6e4811a87 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 |  | NULL | NULL |  | NULL
6caa5d57-2859-42c4-b6a8-4aff7aea2a62 | Pole | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
4cffdebe-6b28-4f95-8684-2ba580ee4cf0 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
4da1583a-09df-461d-98df-c52e9eef8c32 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2023-06-14 | Level 2 |  | NULL | NULL |  | NULL
8da15489-0c79-49d8-a2b5-d9657f001e25 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
01d772fd-37b6-4c2b-ba60-74b5953dc58e | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
31bd0687-5047-4776-aeec-5a0e59630cc2 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
62f41e21-fd72-44c0-9e40-428dc67e40d7 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
0ede8458-fe64-4fe8-aa1f-1001484e6c23 | Padmount Transformer | 0 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
4b047ca6-1b7e-4d8c-b79b-27fd2880956a | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
2356a8df-bed8-4722-a538-a0e13afdd20f | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
9d931224-1b1d-4b0c-a10c-3146752be6b3 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 |  | NULL | NULL |  | NULL
2d41216f-eb07-4d47-8ac4-d361b2cc6657 | Padmount Transformer | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3 |  | NULL | NULL |  | NULL
d5883e28-c8b9-4cfc-a5e6-3a6d407fd18c | Padmount Transformer | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3 |  | NULL | NULL |  | NULL
41c771ad-a229-48d4-b6ce-833512e9406d | Pole | 2 | Distribution | 2022-06-15 | 2023-06-15 | Level 2 |  | NULL | NULL |  | NULL
b7137f0b-e07e-4d6f-b28c-527d4970a1ed | Pole | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3 |  | NULL | NULL |  | NULL
1b437797-e7da-4b7f-9f33-a2353b7a05cd | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
c4c35c38-bb84-4a25-a2ba-8ae5cdb4c7e0 | Pole | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 |  | NULL | NULL |  | NULL
ac0a7736-89d2-4830-aca9-990ecbaee780 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
ef2b6b89-31e4-41f2-b08d-62fe967cd958 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
3be1b787-56a8-460f-a934-283c82edd225 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
18e8883c-5871-4d53-8b54-f822ff9b0bca | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
1cf96f06-cc51-48f4-af3b-69bb6b81b81d | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
bf32fec6-968c-4837-af4d-610d3f242349 | Padmount Switch | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
6ee10a26-a07e-405a-a205-dda0961b8089 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
cd1d59a7-4fc4-4b0d-86dc-4f87bcede5d4 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
3326eae9-8915-41ed-8c3a-ef82f50c8e29 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 |  | NULL | NULL |  | NULL
2ab9ebb6-a13e-455e-9d5d-eee2f3fc5415 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
c968c4f0-659f-4de5-a1e6-f4e6889ab438 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
13f53e72-f481-40ec-bc62-9184799269dc | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 |  | NULL | NULL |  | NULL
e3c72cee-d094-433c-8f7d-e7b6adda54d7 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
36e9404f-b39d-459a-87b2-8a4451fc4f9d | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 |  | NULL | NULL |  | NULL
0376c3be-b3c8-495b-957c-8b33413a41d1 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
98989c5f-65de-46e5-80dd-aa56cb001af5 | Padmount Transformer | 0 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
298880e0-5326-4328-ab84-29d25d0c3509 | Padmount Transformer | 0 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | NULL | NULL |  | NULL
a85af020-f1a8-4bb7-9b25-7d6ab1800b87 | Padmount Switch | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
5130edae-bd79-4ba5-bb9a-0a3700ed4e69 | Padmount Switch | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
5a47bdef-e192-447a-908c-febf0d336eca | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
94ead8eb-5256-4eec-9e73-cc55975f3aac | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
4bcae9be-09ad-4b8e-9d80-4edc59cfa6a4 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
3bab858e-5e11-40a5-8a19-325a0fe605b9 | Padmount Transformer | 0 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
d3c9cbf5-7f45-454c-b4b9-305dcb465d91 | Padmount Transformer | 0 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
b9dcc4c2-d986-4466-a298-b71daad4aed2 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
b4c67ffb-8e1b-4316-a2cb-13655371deb1 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
9fa3fb16-783e-439f-a137-d189d85edde6 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
1e0436ed-acd5-4707-9e0d-4b9caf87169b | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
c29af4d0-15bc-4a57-af8c-9349b7329734 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
9fefda5a-c474-4c3b-b008-51ecf675b89b | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
1cd58a7a-4a44-41f2-b43c-71405fb4fe55 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
daed959a-4d21-4774-b0e0-a6f3204eda5c | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
c19fde90-5337-4ab8-b411-2b6c4af6ba3a | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
8a69389e-42e4-4bf2-8fc6-3e0a7062ef4a | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
44bc7ca1-878e-4831-98ce-904617207a57 | Pole | 2 | Distribution | 2022-06-17 | 2023-06-17 | Level 2 |  | NULL | NULL |  | NULL
df52a1a8-0c31-44bf-8e75-6d7b9568ab17 | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
e47e950f-526a-4611-b10b-0276ebfc4323 | Pole | 2 | Distribution | 2022-06-17 | 2023-06-17 | Level 2 |  | NULL | NULL |  | NULL
e28a3cf3-c43f-442b-afcf-caff845f3b3e | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
8469ab74-35be-445a-ac3d-969d7431d8f4 | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
850c4a3c-16db-41c0-bd1c-7e4235e41cde | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
1f0ae53d-ed03-4fae-bad7-fed38ae00e9f | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
e4856038-cb1a-451c-8a7b-c4ca6595cdcb | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | NULL | NULL |  | NULL
d9bf59df-21ac-4e4c-94d3-f737205c5a93 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
b9158da8-200b-408a-b0b3-fb24709ef9fd | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
7e212068-3acf-47f4-9214-d7170a58f009 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
d7c209e0-3cd6-45ce-a082-cb48abee240d | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
ed9fe677-fa14-4fc9-a972-79aa488a92e3 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
a13d0258-61f1-43b1-9228-dce5c58695ec | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
5c779567-9f7b-4a49-bbb5-e3a9b15ce3aa | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
9797b6a0-a6ce-484d-99ef-e7b1277772e3 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
a183ea84-4574-42c4-83cf-160c72450850 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
cfa424be-1ade-43fa-b75e-5577b89676e5 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
c8b69eb6-aec6-48c1-9b49-bc58621544f4 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
af878fdd-e739-454c-b83c-0d3c8a3da074 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
32741ceb-896d-452b-96ba-e07359dffa68 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
03e35072-a4be-4ccc-913d-6eb56020644d | Padmount Switch | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
9da46770-0fda-41c3-87c3-2dac72b9aedd | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
edf775bc-9d7b-4a7c-b533-cec7cc2aeb91 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | NULL | NULL |  | NULL
4434c782-74d5-4f2c-a82c-96bddec5c6cf | Padmount Transformer | 2 | Distribution | 2022-06-20 | 2023-06-20 | Level 2 |  | NULL | NULL |  | NULL
de95aa96-8b3f-478f-ac18-01663b7bb0a6 | Padmount Transformer | 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3 |  | NULL | NULL |  | NULL
8e7c11bc-ab30-4a6a-bc20-03597152f93e | Padmount Switch | 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3 |  | NULL | NULL |  | NULL
b020aae7-2559-49d6-b69a-568c73d95411 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
73e61b9b-9c57-4cd1-b8a6-d973bd599f77 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
ecdaaf67-2f25-48e0-b1f1-17c861eee95e | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
c32741fe-cfac-41e6-8903-51d452f4222c | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
afbcdd41-9670-439b-9ffe-df89054667ae | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
6341d88c-4143-454a-8a88-a2c71eb74b70 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
2625c5b4-fb0e-4ad3-93fd-09e3dde8fc73 | Padmount Switch | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
83cb1b94-fe53-4233-ba65-b57df4a5f29c | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
2a6fc61d-ec28-49a9-a828-ac07c755ebe4 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
97f58b5d-8cef-4551-8b35-298f73685ad1 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 |  | NULL | NULL |  | NULL
c62a6fd3-3d2a-4738-83c5-9c116ff7d314 | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
0506b8a3-464f-4898-b97d-fbd1adc9cbef | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
3b34f210-1300-4f76-97de-97cf73055ebe | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
99d66450-6366-41fd-9cbd-ec5fc98f170e | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
cd54d625-24a3-4554-831c-b03562412bb2 | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
1f3e2d0b-4465-4596-8775-db561b7ecb54 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
a6ea84c3-f617-4943-93b4-b20a57622cff | Pole | 0 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
f57249bb-e0c6-4e31-b952-966facf30c04 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
86d0243f-c291-40c5-ac7b-cb1dbe150bfd | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
0f552bba-6a98-4f3f-bf4c-e1e6b54a2889 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
5ff51a71-1123-4167-a8f1-9b8cdb1bc2e2 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
b5ecf54b-8f71-492e-b9ef-5fd482eaddc5 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 |  | NULL | NULL |  | NULL
6b7360dd-d7ca-478d-a8f4-621faa5f32aa | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
7dea3583-8a76-4701-bbff-0d76c1d40381 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
fc00b21c-94d0-41e1-b78f-2da60c9f1c66 | Padmount Switch | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
9fe80817-b76a-41b7-b99a-6e5982e7301c | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2023-06-23 | Level 2 |  | NULL | NULL |  | NULL
9e31fbe7-495e-410e-be28-838fb43b055a | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
d13ec6ad-2fdf-41da-b0ea-8b8bcb119603 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
b507717d-4fef-4b44-9fbf-7080fd933f3c | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
da61a454-3b12-4842-b23f-f8ce9a5d9375 | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
f2144e7c-b2f0-4a5b-b261-25ea32aa872d | Other (Describe) | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
6c9aca1e-de70-4304-802d-23aac78d08b3 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
f3a74b06-ca89-44fc-9aa2-970b8f01b5ab | Other (Describe) | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
646e47e1-596b-4c18-9e99-e3b019554b14 | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
873c3160-dc6f-4c6d-9cd5-907452cd4bab | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | NULL | NULL |  | NULL
70c03c5e-c0eb-43b5-9304-5b4b58c14e51 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
3a916cab-3fa2-4352-8551-d7e195085c80 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
5bb253fb-2aba-44f5-b468-489eeeaba216 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2 |  | NULL | NULL |  | NULL
c8a68e42-6db8-45f8-a73c-3b63e6a8d181 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
c9e6a4a4-6892-431c-9c6e-9bff7f782e69 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
983332d7-a2d7-4f4e-87fa-337b7aca6c24 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
b8daf1f6-1c7a-49ea-9f87-a5455520c5e2 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
2876af88-cb1a-4ae9-a211-7396568f0ce7 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 |  | NULL | NULL |  | NULL
9ab7f456-a2d7-4bac-b9d6-a22a4ae06fce | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
0276fbd3-4b6d-4a0a-9b7d-f0d6a7d9d58a | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
e88d3cef-d974-4f40-b969-eaed7156703a | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
3ca1e1bb-6d6c-497f-9632-0c7bb1721885 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
ed42748d-cde4-4cea-8306-63913d379ec9 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
8eaa42d2-3c2a-43d8-868e-1c4607bea3cc | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
328f773a-3bbb-48cf-acf6-11c9c4514842 | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 |  | NULL | NULL |  | NULL
417ba8ba-aff3-4c3c-a6ca-712c8d56501d | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
57132dbf-b2ac-4061-a0c9-85a59e17da31 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
c7091109-e6cb-4bd3-aeda-bc71f46805d1 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
1cdd61bb-40cc-4898-a072-83625893d433 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
945759fd-7e64-461e-9003-579624b1b8a6 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
97333fea-8d0f-4cd7-b461-c7801cd23c3c | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
8bb83fdc-cf25-4ed3-a1b4-aaec1d4d16a1 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
250fb58a-d59f-4e30-acdf-da04a8325175 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
158284ec-87b6-44ff-8d88-744610aef02c | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
2e7582e2-17ba-40c1-b3f8-8230194c5720 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 |  | NULL | NULL |  | NULL
a045f6a4-5a5f-4005-a009-1d3e74085d87 | Riser | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
65a9971a-6362-4e5d-9cb4-3eaf1725e19f | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
46b5491d-a643-4ea0-9d7c-d7a875934113 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
652d85cd-7dca-4650-b09d-38be7c3593fa | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
039b0d1b-f16b-44e8-9c30-bef197d876ce | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
a7f44a4f-90ab-4f83-a5b9-d16942e0f474 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
a56054d6-e431-4b38-8102-c6340cd0a187 | Junction Enclosure | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
9b5df6df-a7fa-43bc-b655-8d4b230c40bc | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2023-06-28 | Level 2 |  | NULL | NULL |  | NULL
3aa680e5-bc9e-4303-8983-379d6a5bcc86 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 |  | NULL | NULL |  | NULL
8b167cad-ced3-48d0-970e-6006b5a91556 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
cb46753c-69b2-4b62-bfa8-fd6e22d45485 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
0687ca96-0d7d-499a-b133-6232b6a7a83a | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
5f0f0f98-d7a8-4f7b-8e1c-9eed7eab2f85 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
5ee63644-9e79-4756-a201-1bf59accbe53 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
d0248b90-8bf6-4a68-bff8-0331537d2212 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
3e50c77f-a7f2-4955-b0d0-5278041b75a2 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
3660f9c8-118f-4a67-a131-8be4912ccb05 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
e6196d01-9922-43cd-81e6-ed765dfbaead | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 |  | NULL | NULL |  | NULL
7142821b-0126-4800-b5ed-30fe0d80526b | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
ddf4c389-923c-467c-96b0-d0c119361cc2 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
ecad7c32-ba3f-452a-b4fc-8b8a34a72cfc | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
932cef69-6251-41a0-9c2b-d4e9c18b70b3 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
3c6e3906-5dbc-47c0-ab98-7c06e5d5b54d | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
4211b33e-172d-45bd-9697-8a989f875f1e | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
68d4db95-826e-4a41-99d6-adbacc591d9f | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
dc8b62e1-29cd-4951-9234-3c9c888e7a7b | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
a24192c7-d0e0-4b59-a80e-4c1dfa603c19 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2023-06-30 | Level 2 |  | NULL | NULL |  | NULL
b6a202cc-e85c-4595-9e38-5237c44102d4 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 |  | NULL | NULL |  | NULL
51d31739-f023-4f0a-af6b-356f3f09467a | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 |  | NULL | NULL |  | NULL
9b5f2d37-ff25-4842-8de1-153bd7b26a75 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 |  | NULL | NULL |  | NULL
6b836ade-5562-4df0-8732-4fb259dcd55e | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2023-07-01 | Level 2 |  | NULL | NULL |  | NULL
6a10e78d-e849-4d53-96ac-903f9d740ad9 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 |  | NULL | NULL |  | NULL
8f1cfaa6-fa5c-4bcd-8cac-67fb4803ad76 | Padmount Transformer | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | NULL | NULL |  | NULL
737883d5-c881-49dd-a4ba-11d018923726 | Junction Enclosure | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | NULL | NULL |  | NULL
c51783c2-eb7f-43dc-9154-9e496a6f7e5a | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | NULL | NULL |  | NULL
705da63e-2ba7-43f7-acd8-8bbb9dc75726 | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | NULL | NULL |  | NULL
9c1dd4ec-db04-49ac-8b38-729c84ad393f | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | NULL | NULL |  | NULL
a748300e-ff2d-42dc-89a4-eb1d9a4dbf57 | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | NULL | NULL |  | NULL
4c767dc1-5140-4492-9c75-4c402780a616 | Padmount Transformer | 2 | Distribution | 2022-07-06 | 2023-07-06 | Level 2 |  | NULL | NULL |  | NULL
543bdd87-6ad5-4467-a96b-1817cdf1685c | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
cad96719-c1ad-4544-ba90-3d96d7c9daa5 | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
9027305d-5ca5-4d5a-9787-94edef7f4c3d | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
7b81f885-698b-40f4-bf70-872bdb3a84c2 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2 |  | NULL | NULL |  | NULL
0eaec015-d283-49a0-b937-bbdabba47018 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2 |  | NULL | NULL |  | NULL
866d4f8a-f536-4f2c-a15e-2fe3d47e28fe | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
35c0a14f-e71e-4039-93ba-c1c0a0e077a3 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
af4a2120-e8a6-444a-8cf2-9f9173acc042 | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
39df8bba-e3ec-4586-a4f4-e88ea4e81a39 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
7f1ff962-6326-4560-80e9-9bdc6059841a | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
68e1d5e5-eff0-424a-9140-d7a6c56d949c | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
96f35bd5-2d54-4ad3-887f-2982b4691c8c | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 |  | NULL | NULL |  | NULL
b79fbdf9-cd7d-4c21-b4da-2da62d78492e | Pole | 2 | Distribution | 2022-07-08 | 2027-07-07 | Level 3 |  | NULL | NULL |  | NULL
92530485-8c67-4892-827b-293d16760fab | Riser | 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3 |  | NULL | NULL |  | NULL
d661365c-f23a-4424-b3a5-1608c055c038 | Padmount Transformer | 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3 |  | NULL | NULL |  | NULL
60d3794a-6e91-440e-b84e-7ed56015b922 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2 |  | NULL | NULL |  | NULL
6b23045f-95b2-4a67-ac9b-bbc5e6392a53 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2 |  | NULL | NULL |  | NULL
f5bef563-93a4-4e5c-8152-864e6dd8f6b1 | Junction Enclosure | 2 | Distribution | 2022-07-13 | 2027-07-12 | Level 3 |  | NULL | NULL |  | NULL
32a90151-c9ff-402a-8e34-3d86e01a9052 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2 |  | NULL | NULL |  | NULL
df73377f-8e16-4be6-a8e8-a831c9668a3f | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
b36e2ca2-b169-4493-9b73-e845e21fd800 | Padmount Switch | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
49c0182d-a1f1-46de-9431-6770c058615d | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
68a02437-a256-419e-a9d3-f894f99ad010 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
2c46a6b7-8e04-4748-afbe-a3cda8019211 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
365bee8d-1b6a-42a1-b2fc-77d25bdadf62 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
93f622d5-9481-4454-9711-a95cc62475c9 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
7043c738-d041-43cf-9b14-2807c0406316 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
b548237b-9408-400b-b565-8a28bf3d6739 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 |  | NULL | NULL |  | NULL
dc142e9c-5516-485e-8870-39690eb540fd | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 |  | NULL | NULL |  | NULL
179aeb7c-a58f-4c01-94bf-2733a6069c87 | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 |  | NULL | NULL |  | NULL
d6efa84d-31c2-4031-b7cb-6913f263534e | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 |  | NULL | NULL |  | NULL
14d3fbec-cdea-436a-b506-902b9b425279 | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2 |  | NULL | NULL |  | NULL
0eaa605b-90e2-4dbc-aa23-f842abb4441a | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2 |  | NULL | NULL |  | NULL
1e5b4693-4012-4541-94cf-5a10b67cf02c | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2 |  | NULL | NULL |  | NULL
572a067d-dbe9-492e-9d01-d8016fec4e2f | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 |  | NULL | NULL |  | NULL
cd408b5f-a09a-485f-8f27-e6803a712d42 | Padmount Transformer | 0 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 |  | NULL | NULL |  | NULL
39732bce-4537-47fc-a2a1-2444145d59fd | Padmount Transformer | 0 | Distribution | 2022-07-16 | 2023-07-16 | Level 2 |  | NULL | NULL |  | NULL
0dcdac62-15c1-4b4d-8bb5-ae602fbde396 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2023-07-16 | Level 2 |  | NULL | NULL |  | NULL
615eb800-1974-438d-b5e5-b83e4e8b78d6 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 |  | NULL | NULL |  | NULL
436bff65-1e42-4cdf-b38d-9154e6ca75eb | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 |  | NULL | NULL |  | NULL
9123d66e-a97f-433c-ab1d-0232923dacb8 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 |  | NULL | NULL |  | NULL
ba98a25d-f5f8-492a-abb7-8c54732f1ef8 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 |  | NULL | NULL |  | NULL
4d85fbd3-0ecd-4729-be4a-8415b59a261a | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | NULL | NULL |  | NULL
ed9c0452-40c1-4795-88a2-77612647cc3f | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | NULL | NULL |  | NULL
503b2711-da55-4704-9f2a-7c2d6d4d528f | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | NULL | NULL |  | NULL
5e15942c-10a5-499d-bc5e-5cf00d088373 | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | NULL | NULL |  | NULL
11deba5f-8923-4b68-b64f-fc0c83247e94 | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | NULL | NULL |  | NULL
0e1bf72d-2512-4448-ae30-bb458d249f82 | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 |  | NULL | NULL |  | NULL
3cbd90aa-9655-4e4f-a4ec-802bedc5e9d5 | Riser | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 |  | NULL | NULL |  | NULL
c97c87ec-f115-42a9-9eb6-7efcdc14342c | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 |  | NULL | NULL |  | NULL
ffc6ab46-5799-4009-924b-309c0bf5c4b0 | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 |  | NULL | NULL |  | NULL
916aae83-4ce8-466a-b377-bd1a2df74ada | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 |  | NULL | NULL |  | NULL
5f70c3c0-a585-4d1f-99c5-c2c97cdaddbe | Riser | 2 | Distribution | 2022-07-21 | 2023-07-21 | Level 2 |  | NULL | NULL |  | NULL
5621a3df-f5c6-4921-9d74-96aaac526093 | Riser | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 |  | NULL | NULL |  | NULL
915c9f2e-77c3-4454-b5d4-0816e8586cdf | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
91853f5b-ebfa-4c2d-802c-6777e74acc44 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
87bf2d25-51f5-4eda-a819-3e4bc1b3e078 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
1921a16a-9eb2-4a74-bd75-b59ed792a8d0 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
f020a51a-b5df-4f16-a610-6fc66e8217e3 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
b4c00fa9-e2d6-467d-9da7-1477bf4ad733 | Junction Enclosure | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
09b6a4c9-9d9a-4658-a262-ffae9d6a71f0 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
9d1360b0-d78b-4956-b9a7-c3cff338b71e | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
7d1c1ce3-6f82-499d-9d0e-ac6a13a28378 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 |  | NULL | NULL |  | NULL
be65b7a9-0606-4a77-bc91-6909cacb4fe5 | Junction Enclosure | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
e29ddcdd-dcdc-466d-86d7-4baed185d2d4 | Junction Enclosure | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
fdefdf95-fead-4925-b734-d1d13d0ac4ce | Padmount Transformer | 3 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
8778d3f4-313d-43a3-9601-be10799c26f9 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
2e3b666d-5a2a-4ebd-8ef5-c40eb21d0101 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
cdd81f99-0c1e-4117-bd49-8cc919fafbd3 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
830b5119-e30f-421b-985d-cacfda17d10b | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
ba8c44eb-52e6-42b9-a08e-023e286df4d2 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
6972277e-1219-4402-98b1-47968c05a7e4 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
1ce135df-0492-4f05-a54f-9bfd206d79cb | Padmount Switch | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
e3b24731-f94d-4b5e-8a1b-25cf57a7e5f1 | Padmount Switch | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
d00f29c3-9cf1-469f-ac39-107417483492 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
30dcd263-f462-417a-85ba-1ed216a3cb18 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
8afed30d-af2a-41f4-82e2-096f0182e553 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | NULL | NULL |  | NULL
31332b21-931a-44b4-956e-6993ef7ed5b5 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
4886971a-3471-44ca-a661-16449a1380a4 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
f503f765-03d2-4afe-8fb4-2de7d0fdb1d3 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
9075fa42-4c3d-487f-a422-210cffd4125d | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
294e7f47-d95b-497c-864a-d7d66db88130 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
956f4069-31b0-428d-8177-b463da41c82e | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
5321383c-e6de-4fff-a775-611f046675fa | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
a911aff4-9c38-4ffe-965d-b093eb1a13f2 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
0362e6ab-ce17-47fe-956a-9f771f25f8c8 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | NULL | NULL |  | NULL
1a27a9cf-dc7f-4bc3-b2e6-fbfe68a30b2c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
675e58bb-28dc-4e04-867a-1bd8b7207473 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 |  | NULL | NULL |  | NULL
d87e3694-0fc7-48a5-8c45-b29c3679e33c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
69642a7e-84c4-4db3-90da-e2d9b776a952 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
5a5bb1a4-1131-4fc2-8a5f-abb07ab05718 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
77793559-5287-440e-8def-2d3f2ed3bd11 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
d2a27a69-d475-4feb-8400-300c992ea1d1 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
4f595da1-4354-4fb8-acba-fd9314f20b0c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 |  | NULL | NULL |  | NULL
8dd3673d-4c38-4812-9032-9c7028bf5216 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 |  | NULL | NULL |  | NULL
95d79daf-b3b6-46a7-95cf-761c5a74859a | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
31813f44-b57a-4296-85b6-fd66ae276c82 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
0b50282c-7fd6-49fa-8b00-1f1305cab7f0 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | 2022-07-26 | 2027-07-25 |  | NULL
884194fe-1dee-4abe-9f39-1f907d53ada5 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | NULL | NULL |  | NULL
9e7ecdf4-4653-42ac-ad6d-850829b6f1d6 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
5ac12c6f-3ad7-463e-9239-feeed233a5f6 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2023-07-27 | Level 2 |  | NULL | NULL |  | NULL
0a06ac16-598c-424e-b4eb-233e72e13620 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
6afb2566-bd9a-4ff9-8468-a7468a5268d8 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
a9397d43-0dcd-4c29-a948-40b7010d35e0 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
f55618a6-1f62-48fe-8bf2-1115e5f41d21 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
341d56ad-4a32-4bb0-b9a9-8d3614f11eb2 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
a8abaf8e-5bc4-4ba0-85c2-e9a5c7efdfae | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
0b437a6f-992c-4b63-a4a0-8f63bd61e472 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 |  | NULL | NULL |  | NULL
e5687798-66d1-40cd-91a7-d3da0ce5a4b4 | Riser | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | NULL | NULL |  | NULL
861b19f4-6d5c-4e9c-9ba3-2c6ccad098db | Riser | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | NULL | NULL |  | NULL
250c9c34-9c2e-45bd-af09-ab33a48ca98c | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2023-07-29 | Level 2 |  | NULL | NULL |  | NULL
ea9c69b8-d525-414d-8a95-f15e5cc68fc7 | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | NULL | NULL |  | NULL
6cb5f3c7-bd45-459b-b014-f082c2b0ebb4 | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | NULL | NULL |  | NULL
65d3714c-1df3-4741-b98b-07d6a384ccbe | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | NULL | NULL |  | NULL
b0268673-e6c0-4cb0-ab9a-6609cf887d27 | Pole | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | NULL | NULL |  | NULL
c5e97d32-4cde-4060-9ba5-6b9dc2766f89 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
b50f0096-968c-48bf-9e26-a52003b046d3 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | NULL | NULL |  | NULL
db1089c1-261e-4831-81da-48dfce9f5005 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
7410d3df-1fed-4cea-80d6-315c4022df64 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
8e4a5f9f-6632-4d4f-a9f5-1d80070e9d15 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
b9a781ed-4ea7-4ce4-a8a3-f1a04afad7b8 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
a6715506-e507-48ed-887e-83fadb3014a5 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | NULL | NULL |  | NULL
ce38b17f-da91-472c-9395-7d1e3d7722cc | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | NULL | NULL |  | NULL
69a96925-cc06-440c-9b2f-475fc55218d0 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
34676611-518b-4fea-ac97-e8d8543a0ac5 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
f4343387-4bdd-4505-b3cf-a4b09f7a2010 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
2e744b36-b962-4744-8d66-c2e62ba5bb58 | Junction Enclosure | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | NULL | NULL |  | NULL
b0d7d791-1408-4a03-997f-e76303f83691 | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
551d7049-3680-4d3c-b86a-8ab3c0b39a03 | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
c61c9708-851f-4d07-b5e6-9688d560081a | Padmount Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
c12d6384-f464-4de5-95c3-64bddecf4c59 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
f60c47f7-4dc0-485d-bd3e-bcf1fdf28e54 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
d5636e90-0e1a-44fd-8e2a-62427b08c5d7 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
8932cfee-afd9-4c3a-a74a-1356c81f1554 | Subsurface Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
f181aca2-9243-4210-b20b-f296f4d959a0 | Subsurface Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
d5601299-ce56-48d1-a84b-0f66eca70bab | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
0be8bcc9-67f5-4258-b3dd-a5ae8079bebc | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 |  | NULL | NULL |  | NULL
97469f90-6197-4c07-b313-b1e18fa4a873 | Padmount Transformer | 2 | Distribution | 2022-08-11 | 2027-08-10 | Level 3 |  | NULL | NULL |  | NULL
435f3543-bb37-4136-8ba8-731182324c01 | Padmount Transformer | 2 | Distribution | 2022-08-11 | 2023-08-11 | Level 2 |  | NULL | NULL |  | NULL
9455b029-8445-47d2-ae09-d8435a7339a0 | Padmount Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 |  | NULL | NULL |  | NULL
e8094d4f-dc0b-479d-a747-5b551348ddd3 | Subsurface Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 |  | NULL | NULL |  | NULL
055d4a8a-a9f3-4084-98f4-33839fc50091 | Subsurface transformer in cabinet | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 |  | NULL | NULL |  | NULL
090d0960-c0bf-4243-a70d-952b018015c5 | Padmount Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 |  | NULL | NULL |  | NULL
68ff7442-50c4-42c1-957b-7353b5141e73 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 |  | NULL | NULL |  | NULL
0184cb9e-1316-4350-8fdc-49ad401c0bc9 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 |  | NULL | NULL |  | NULL
24468157-72e7-4e81-9a97-9131fea2a8aa | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 |  | NULL | NULL |  | NULL
d627965b-18e3-46f3-80c8-a090d628dd4d | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 |  | NULL | NULL |  | NULL
60c7352e-e2ca-41e4-b777-9c66b20e6f58 | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 |  | NULL | NULL |  | NULL
024331a3-be90-425c-973c-6606c5e02e06 | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 |  | NULL | NULL |  | NULL
73b33a60-718e-45e1-be66-7665d45bbb94 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 |  | NULL | NULL |  | NULL
22eb09b5-181a-41b7-878e-b93311d44e98 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 |  | NULL | NULL |  | NULL
535c7cf6-0fe5-4998-b175-8c659de3f0e2 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 |  | NULL | NULL |  | NULL
a71ef824-c2bc-4acd-9d39-bf5326eac1e6 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 |  | NULL | NULL |  | NULL
8ecb5ecd-7a8b-425d-938f-e04e52b56bc9 | Padmount Transformer | 2 | Distribution | 2022-08-18 | 2023-08-18 | Level 2 |  | NULL | NULL |  | NULL
f07da56a-f3cc-43de-9464-849917314445 | Padmount Transformer | 2 | Distribution | 2022-08-18 | 2027-08-17 | Level 3 |  | NULL | NULL |  | NULL
7aec2cde-0c8b-4373-ae05-963e468e25d8 | Padmount Transformer | 2 | Distribution | 2022-08-20 | 2023-08-20 | Level 2 |  | NULL | NULL |  | NULL
b9023123-e78a-4574-8077-001d9a4529ba | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
cfbef4e5-cbf9-40f4-9444-585ce549423a | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 |  | NULL | NULL |  | NULL
3e4c6145-134c-4104-a579-0b4309f9c94f | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
41375cd6-eebc-43fd-b564-7cfbd63d5278 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
93e03673-6637-4894-913c-77f87a7eace4 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
a28d12ef-69ed-41df-a1e7-c79e0bfaf05e | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
cc0a0498-0e59-4468-a87b-d5e286323e83 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 |  | NULL | NULL |  | NULL
e41871fe-103e-4997-94fd-40c37951a733 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
493f2e0d-d24c-493d-8e8f-1dc94a068fd1 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
64e39d77-1867-4417-8e0c-e715fc4f932c | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 |  | NULL | NULL |  | NULL
a767130c-dba3-4952-917f-3ecbef23df55 | Padmount Switch | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
87a165b5-ae73-4c59-bc68-0ac3fc94b44e | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 |  | NULL | NULL |  | NULL
af1cb5e4-d7c6-4250-ad1e-b0c8ba097f58 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
9871f144-207f-445a-83d2-e70b618e35f5 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
05424644-e141-48c3-b836-1e04f775c299 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
279b39fa-e1c9-4903-9c28-68043690652d | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
390e4d13-65ab-4011-90f0-4c9bfc1dbbe1 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 |  | NULL | NULL |  | NULL
7d8dd5db-5b95-4953-9214-71f4ea07b834 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
f5f7f618-595e-458b-9551-fc38426e872c | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 |  | NULL | NULL |  | NULL
fa9a583e-e74f-4d93-9403-9463f183dc81 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 |  | NULL | NULL |  | NULL
5a590a03-3348-42c7-a656-21ac9d10ae10 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 |  | NULL | NULL |  | NULL
8029cc16-eaec-49cf-af10-4ec84ae103f1 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 |  | NULL | NULL |  | NULL
6b1ae1a4-428b-4dba-97f2-a493b71f6c90 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
1183d39d-1dc9-4c4b-ad48-da44f6057a64 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | NULL | NULL |  | NULL
58942f1a-5036-44b2-91b6-f30a3ef7760f | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 |  | NULL | NULL |  | NULL
bfde1b03-fd7c-428a-9801-45647e7f245d | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 |  | NULL | NULL |  | NULL
986ff4b7-5132-4b0d-9221-aff00fb9ed4e | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 |  | NULL | NULL |  | NULL
3c855010-4141-4bd1-8816-7c7dd8e3e396 | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 |  | NULL | NULL |  | NULL
5bdf31cc-12ba-40bd-945b-df6d16365a4b | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 |  | NULL | NULL |  | NULL
575f5753-2477-4b9b-a2e1-a7602258edfc | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 |  | NULL | NULL |  | NULL
dd30c485-f732-48af-a419-c23e6af5be23 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 |  | NULL | NULL |  | NULL
889d3755-0ce9-4849-a53f-a410f3d60766 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 |  | NULL | NULL |  | NULL
2439f181-39ee-431e-89e9-0e27b0b4fb44 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 |  | NULL | NULL |  | NULL
4384139a-8914-4f69-898a-dcfc983d3606 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 |  | NULL | NULL |  | NULL
d689b31a-dfb8-45a3-84d8-941810274be7 | Pole | 2 | Transmission | 2022-11-23 | 2027-11-22 | Level 3 |  | NULL | NULL |  | NULL
0e390fe4-c150-4bb1-bd86-8ee5d6a963ca | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 |  | NULL | NULL |  | NULL
e4d54697-90b4-4c0f-8054-564699302bad | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 |  | NULL | NULL |  | NULL
89926fbb-cae6-49c3-b81a-361100e2f151 | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 |  | NULL | NULL |  | NULL
adef5ec6-94cb-4749-aa95-9a009b4f90c3 | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 |  | NULL | NULL |  | NULL
6683fc71-8b48-4287-b7c9-05b6e14e884c | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 |  | NULL | NULL |  | NULL
1d870439-b07c-4d3b-bd87-e32e995d0f1d | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 |  | NULL | NULL |  | NULL
603c4036-e86a-4ab3-8508-2af5613496a9 | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 |  | NULL | NULL |  | NULL
4352dc51-da21-420f-809f-1b5548caeb30 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3 |  | NULL | NULL |  | NULL
42227fd2-373a-4a01-9e11-4764b061fbd7 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3 |  | NULL | NULL |  | NULL
e4f3f827-471e-4a2a-b982-7f06b303bd95 | Pole | 2 | Transmission | 2023-06-20 | 2024-06-19 | Level 2 |  | NULL | NULL |  | NULL
e847e428-2001-4594-9788-ac74c41f48c7 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3 |  | NULL | NULL |  | NULL
e4be9cba-f2f3-466d-9af2-0b2bc4723c45 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3 |  | NULL | NULL |  | NULL
7922db2e-c76c-48bf-a145-26f598dd418e | Pole | 2 | Distribution | 2023-06-21 | 2028-06-19 | Level 3 |  | NULL | NULL |  | NULL
090e5d36-cbf9-400f-8e50-34018635d87e | Switching Cabinet | 2 | Distribution | 2023-07-11 | 2028-07-09 | Level 3 |  | NULL | NULL |  | NULL
090e5d36-cbf9-400f-8e50-34018635d87e | Switching Cabinet | 2 | Distribution | 2023-07-11 | 2028-07-09 | Level 3 |  | NULL | NULL |  | NULL
b00e2bbe-f01f-4ee4-8a40-646f84116fcd | UG Transformer | 2 | Distribution | 2023-07-11 | 2028-07-09 | Level 3 |  | NULL | NULL |  | NULL
fe307e8c-3986-4382-9dc2-fec8910c9c1b | UG Transformer | 2 | Distribution | 2023-07-12 | 2028-07-10 | Level 3 |  | NULL | NULL |  | NULL
ae4770c7-053c-4a59-b015-a477ed1e6242 | UG Transformer | 2 | Distribution | 2023-07-12 | 2028-07-10 | Level 3 |  | NULL | NULL |  | NULL
c2da7da1-9e0c-4ce7-883c-012b453ca938 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
c2da7da1-9e0c-4ce7-883c-012b453ca938 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
49ad5418-61de-4a93-a82e-7f6274004658 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
2b23f413-82a2-48a1-b9b1-c21f40468144 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
39ffeded-cccb-4954-8099-6270888eaf1c | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
0fecf000-b905-492c-8c7f-93c0eb7171c0 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
9b8ad226-de05-4471-b981-4dd6824b69d1 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
e9f8a133-11ee-4f2f-8187-e90800aebd23 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
585a69ca-d858-47d5-8c94-6c38c83069ad | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
585a69ca-d858-47d5-8c94-6c38c83069ad | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
585a69ca-d858-47d5-8c94-6c38c83069ad | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3 |  | NULL | NULL |  | NULL
b8af1c74-626a-4653-a483-ec2ed7d90e05 | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3 |  | NULL | NULL |  | NULL
ed706fac-ffe0-4170-9fef-99cd75253f95 | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3 |  | NULL | NULL |  | NULL
cb32f91b-1357-4e4b-9dc2-a5348573ca9a | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3 |  | NULL | NULL |  | NULL
931d1d42-61d8-4e44-b88b-f03273d11b9f | UG Transformer | 2 | Distribution | 2023-07-14 | 2024-07-13 | Level 2 |  | NULL | NULL |  | NULL
931d1d42-61d8-4e44-b88b-f03273d11b9f | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3 |  | NULL | NULL |  | NULL
49e76f4f-94c2-4687-a241-f676e1e212c0 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
586f02f5-ff26-4433-af0f-dde23d881e89 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
99fda636-ba57-4e8a-a0c4-4c801372308d | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
741884fb-4f44-403c-8d1f-2111bd8b1da3 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
9eea07db-e999-47a0-8a2d-882ff50c2868 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
6547ae66-7e11-4cda-a804-86ff73e218c6 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
c47234eb-2fda-409d-938f-f171af1ad631 | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
202d9c0e-0b64-4c97-964a-78f21bdd10ce | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2024-07-14 | Level 2 |  | NULL | NULL |  | NULL
202d9c0e-0b64-4c97-964a-78f21bdd10ce | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
202d9c0e-0b64-4c97-964a-78f21bdd10ce | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
783fc654-ee70-4334-8dd8-e6b243596d96 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
ff5341bc-f564-4027-a1ec-503460e6c2c0 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
8e9c7771-8214-4ad2-bbf6-6bf6a7e6862f | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
7091a91c-08a5-4dad-9dc3-de9245cbb564 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
f93241a4-bba7-43a7-98ef-0d516c5b5a65 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3 |  | NULL | NULL |  | NULL
ad2c6c22-877f-4693-aa0b-eb2cfff72198 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
093ab44a-17ae-43eb-997f-67d392b6576c | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2 |  | NULL | NULL |  | NULL
5e99a115-3f96-4694-b016-c281dcb6436e | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2 |  | NULL | NULL |  | NULL
8bcfb4ef-395f-4d90-9b3a-c221ccdbbff4 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
219ceacf-f780-4fd1-903b-38c2e374f00b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
219ceacf-f780-4fd1-903b-38c2e374f00b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
219ceacf-f780-4fd1-903b-38c2e374f00b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
aed033f3-153d-49b5-8d9f-503834a9debc | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
aed033f3-153d-49b5-8d9f-503834a9debc | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
aed033f3-153d-49b5-8d9f-503834a9debc | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2 |  | NULL | NULL |  | NULL
73845d1f-ddbc-46a0-9325-66af1de7b48a | Switching Cabinet | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
972f633f-c5f5-4a3c-98f5-bddccfc70b78 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
9604b66a-ae4e-4b52-9103-37f5b6c0390a | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
3389aa92-7c0f-4bee-b8ac-5d7ba8061414 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
3389aa92-7c0f-4bee-b8ac-5d7ba8061414 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
3389aa92-7c0f-4bee-b8ac-5d7ba8061414 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
8a0f8531-f1a4-4ce5-a2a0-a1f6ab790a2f | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2 |  | NULL | NULL |  | NULL
8a0f8531-f1a4-4ce5-a2a0-a1f6ab790a2f | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
e934856c-58f8-482d-8f8f-97144cbc370b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
268cfe86-f63f-4cf7-aca5-357f8945c226 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
972f633f-c5f5-4a3c-98f5-bddccfc70b78 | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2 |  | NULL | NULL |  | NULL
88814f6a-9294-450b-96bd-41730e945177 | Riser | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
724c48c7-c51c-41cb-9dca-4a04d0b4d542 | Riser | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3 |  | NULL | NULL |  | NULL
e4feea66-539f-4245-9d01-4d7b9be00901 | Riser | 2 | Distribution | 2023-07-18 | 2024-07-17 | Level 2 |  | NULL | NULL |  | NULL
627e58cd-03dc-4e9c-925e-fd668f6cc9a3 | Riser | 2 | Distribution | 2023-07-18 | 2024-07-17 | Level 2 |  | NULL | NULL |  | NULL
2c316183-eace-4469-83ab-85a12d1ab753 | Riser | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
1d34d315-42aa-43b7-a014-4aa83f43af95 | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
ad807f78-cbbe-4aa7-a7f8-747c187a67b1 | Switching Cabinet | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
9ab08fa6-7b4a-4319-8792-308a58d71c3f | Switching Cabinet | 2 | Distribution | 2023-07-18 | 2024-07-17 | Level 2 |  | NULL | NULL |  | NULL
51d1e3f2-d006-408b-9167-4d097d26075a | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
51d1e3f2-d006-408b-9167-4d097d26075a | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
51d1e3f2-d006-408b-9167-4d097d26075a | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
8e2cf5a9-101d-4ea8-8207-50635ababdad | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
7214ace2-32fe-4112-a57e-7f1fe19f47d1 | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
7214ace2-32fe-4112-a57e-7f1fe19f47d1 | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3 |  | NULL | NULL |  | NULL
e8e89b46-c1e1-471b-85f0-33577bbeb545 | UG Transformer | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3 |  | NULL | NULL |  | NULL
31f5541c-22c8-404c-93d9-a662bff55a1d | Riser | 2 | Distribution | 2023-07-19 | 2024-07-18 | Level 2 |  | NULL | NULL |  | NULL
1fd12b33-96fe-40b3-85db-446e9d72a90e | UG Transformer | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3 |  | NULL | NULL |  | NULL
c973809d-74b5-423d-8a25-b9bbbe791132 | UG Transformer | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3 |  | NULL | NULL |  | NULL
3d6dbb31-8604-452d-b2e3-1b6bd637b6a1 | Switching Cabinet | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3 |  | NULL | NULL |  | NULL
c1a60222-69e6-4192-ad9b-b9a5be9e0e17 | UG Transformer | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2 |  | NULL | NULL |  | NULL
3529b85b-517f-4c36-bb1c-a88e40812eac | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
3529b85b-517f-4c36-bb1c-a88e40812eac | UG Transformer | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2 |  | NULL | NULL |  | NULL
dedf249a-df86-437f-ab15-0b2d1705c2a0 | Riser | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2 |  | NULL | NULL |  | NULL
aa7b0f85-ba75-4e55-a668-3b9ba30a4f27 | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
aa7b0f85-ba75-4e55-a668-3b9ba30a4f27 | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
c1b41946-c03d-4cf7-922b-f3adcf0d1ced | Padmount-áSwitch | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
d66e16c4-daee-48a8-9539-32338ac7466d | Padmount-áSwitch | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
f936467a-7f58-423f-9d76-84a938f0ba2b | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
c1a60222-69e6-4192-ad9b-b9a5be9e0e17 | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3 |  | NULL | NULL |  | NULL
f8d87a04-5437-425a-8720-382ac942775d | Riser | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2 |  | NULL | NULL |  | NULL
e86f5750-ed06-4c7d-9b9a-dad1241d619b | Riser | 2 | Distribution | 2023-07-21 | 2024-07-20 | Level 2 |  | NULL | NULL |  | NULL
20a4021c-2811-4f05-8bae-fcd2f02904dc | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
807c49d3-5103-4302-9100-54b87760830c | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
cd233071-41f0-40e7-a0e5-ab62daf614c8 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
cd233071-41f0-40e7-a0e5-ab62daf614c8 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
cd233071-41f0-40e7-a0e5-ab62daf614c8 | UG Transformer | 2 | Distribution | 2023-07-21 | 2024-07-20 | Level 2 |  | NULL | NULL |  | NULL
ec332fc4-3c2f-49a9-8f6d-4269a1bb4e80 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
ec332fc4-3c2f-49a9-8f6d-4269a1bb4e80 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
12cf6afd-b2b3-4523-b9d9-30c2cf69fe96 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
12cf6afd-b2b3-4523-b9d9-30c2cf69fe96 | UG Transformer | 2 | Distribution | 2023-07-21 | 2024-07-20 | Level 2 |  | NULL | NULL |  | NULL
6e0da2e1-9b1c-4a9f-92f8-e84506b0b335 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3 |  | NULL | NULL |  | NULL
eea04e77-bdf2-4014-a362-d1d8bb2f9418 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
3d3adacd-688a-4df5-b1fb-da3131f3fd42 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
49fa3206-a8f8-4703-af50-f52ed1e2b01f | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
6392ab05-c86a-4c7e-a224-e9bb2e7194be | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
be791687-cdc1-4658-b03d-a6c2a57f58b7 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
8fd92af6-248e-4579-929b-85cd9a4aa35d | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
7ea2b5fb-d5b3-4f37-a7aa-25bb90e463e2 | Padmount-áTransformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
0957426b-5825-479b-8eb4-48d557b19cb1 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
9fc88b18-a7dd-423e-a8b5-f331c46c2738 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
9fc88b18-a7dd-423e-a8b5-f331c46c2738 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
4f84e8df-fafa-434e-b488-fc1cb576a412 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3 |  | NULL | NULL |  | NULL
b7fc6ee5-d271-4f61-9b80-a83955dfa9a2 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
52d38d9c-097e-4a94-a033-d1f94cfd012c | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
52d38d9c-097e-4a94-a033-d1f94cfd012c | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
ac491658-8fa0-4a9e-adf9-9204f4d81b63 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
ac491658-8fa0-4a9e-adf9-9204f4d81b63 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
ac491658-8fa0-4a9e-adf9-9204f4d81b63 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
ac126868-4db8-486b-a976-8ff9827e43ae | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
ac126868-4db8-486b-a976-8ff9827e43ae | UG Transformer | 2 | Distribution | 2023-07-25 | 2024-07-24 | Level 2 |  | NULL | NULL |  | NULL
d2948cc4-7a18-4455-aaca-c89025d24c6c | Riser | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
06e0e8ca-9fab-4761-b25a-8f17c53680f3 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3 |  | NULL | NULL |  | NULL
1a962da0-3d35-42ac-8569-eeb9469d0149 | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
1a962da0-3d35-42ac-8569-eeb9469d0149 | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
fe13df30-50b6-4649-86a1-fda96e1ec7fb | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
fe13df30-50b6-4649-86a1-fda96e1ec7fb | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
1f8396a4-2003-411e-8a92-26ae4922a60e | UG Transformer | 2 | Distribution | 2023-07-26 | 2024-07-25 | Level 2 |  | NULL | NULL |  | NULL
534a7df3-9755-460a-bd78-d6a7c7e31ac8 | Riser | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
c78ce37a-934b-40ec-822a-442348cf622e | Switching Cabinet | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
4bf70ddf-7dc4-48ef-9ba0-61358f8feb4a | UG Transformer | 3 | Distribution | 2023-07-26 | 2024-01-22 | Level 2 |  | NULL | NULL |  | NULL
32dbcdef-7633-4ce8-81f1-b695548afc69 | UG Transformer | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
b8e1015c-ec15-447a-8948-7c0dfb644321 | UG Transformer | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
b8e1015c-ec15-447a-8948-7c0dfb644321 | UG Transformer | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3 |  | NULL | NULL |  | NULL
c5dab43e-e49f-4c2e-842b-d4428b4e5bfb | UG Transformer | 2 | Distribution | 2023-07-27 | 2028-07-25 | Level 3 |  | NULL | NULL |  | NULL
69c8ea18-805f-443f-a05c-f403b2bddf72 | UG Transformer | 2 | Distribution | 2023-07-27 | 2028-07-25 | Level 3 |  | NULL | NULL |  | NULL
9766ac52-a5e1-4943-a0e2-ff337b47fe92 | Riser | 2 | Distribution | 2023-07-29 | 2024-07-28 | Level 2 |  | NULL | NULL |  | NULL
eb2872bd-5e84-4c7f-aa02-d14288984733 | Riser | 2 | Distribution | 2023-07-29 | 2024-07-28 | Level 2 |  | NULL | NULL |  | NULL
ba4bcd27-6cd3-4d1a-9b6f-d7f0bf6bd8f5 | Riser | 2 | Distribution | 2023-07-29 | 2024-07-28 | Level 2 |  | NULL | NULL |  | NULL
2793fa60-d2b9-4cca-a62e-dc50a1e0ad2e | Padmount-áTransformer | 2 | Distribution | 2023-07-31 | 2028-07-29 | Level 3 |  | NULL | NULL |  | NULL
7e5a12fe-6157-4700-9c6a-a1f982c4cd01 | Riser | 2 | Distribution | 2023-07-31 | 2024-07-30 | Level 2 |  | NULL | NULL |  | NULL
082bc590-82be-4263-a6ad-85ad8d9c7188 | UG Transformer | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 |  | NULL | NULL |  | NULL
082bc590-82be-4263-a6ad-85ad8d9c7188 | UG Transformer | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 |  | NULL | NULL |  | NULL
eb774b59-de36-441d-93d4-8c091737890c | Padmount-áTransformer | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 |  | NULL | NULL |  | NULL
25af01c1-9801-496b-90e4-e65b797d48ee | Pole | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 |  | NULL | NULL |  | NULL
25af01c1-9801-496b-90e4-e65b797d48ee | Pole | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 |  | NULL | NULL |  | NULL
56a68e5b-2c48-43e3-a8da-16edf14cceb6 | UG Transformer | 2 | Distribution | 2023-08-03 | 2028-08-01 | Level 3 |  | NULL | NULL |  | NULL
f99b957b-a5aa-4bbc-945b-b19030d27d28 | UG Transformer | 0 | Distribution | 2023-08-05 | 2028-08-03 | Level 3 |  | NULL | NULL |  | NULL
c4448545-1165-4d71-a048-f6684059948c | UG Transformer | 2 | Distribution | 2023-08-05 | 2024-08-04 | Level 2 |  | NULL | NULL |  | NULL
09c1127f-65e4-48d6-bfa4-de86496d3774 | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3 |  | NULL | NULL |  | NULL
5f7a055b-0b79-4eb7-ad9d-fcbc99612a1d | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3 |  | NULL | NULL |  | NULL
bc6b4799-6f59-4023-9b1e-c65c956a92d1 | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3 |  | NULL | NULL |  | NULL
bc6b4799-6f59-4023-9b1e-c65c956a92d1 | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3 |  | NULL | NULL |  | NULL
bc6b4799-6f59-4023-9b1e-c65c956a92d1 | Pole | 2 | Distribution | 2023-08-05 | 2024-08-04 | Level 2 |  | NULL | NULL |  | NULL
10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 |  | NULL | NULL |  | NULL
10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 |  | NULL | NULL |  | NULL
73a6df4e-5dbd-4be3-922f-33dbee3e7c57 | Pole | 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 |  | NULL | NULL |  | NULL
2ba08818-e9bf-422d-aaa7-ab5a3bab4546 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
2ba08818-e9bf-422d-aaa7-ab5a3bab4546 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
e17fde17-4dd0-4c45-bcc3-702827eff6ac | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
e17fde17-4dd0-4c45-bcc3-702827eff6ac | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
88252c7e-6d45-470a-b69c-26eb176c7432 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
88252c7e-6d45-470a-b69c-26eb176c7432 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
59699ea0-8488-4955-9d2b-fdab627fef4a | Switch | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
5d68e8d9-9a66-4b4b-844c-8223382e3a42 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
e4ff76a1-858f-401c-9a22-d3cff50d08b7 | Switch | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
53bd6099-69d1-483e-a6cf-7b951353ec9e | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
7429ccf5-9ca6-43d7-b891-0fe7e19f2253 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
7870c4d6-8685-47ab-bd95-6728d82ca87a | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
91f4fd99-78af-4227-b5b7-031d0e4affd6 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
90021dbd-8aca-4229-b8cc-b270799a24e3 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
1babbb9c-0c0f-4bd8-82d9-b572619de616 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 |  | NULL | NULL |  | NULL
fe5bfd0b-16da-41b5-987e-49529d383f01 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
da6c581b-31d0-40ba-9637-f04d7aff0249 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
82437ccc-2689-4506-ad18-0157147e699c | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
749cb7b6-ff3f-4210-972f-9933fde66bc7 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
b805ba8c-daf1-49e1-bdd8-1e25a7d47bde | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
b805ba8c-daf1-49e1-bdd8-1e25a7d47bde | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
ee55da44-c3eb-4e14-8912-39dbdee235c7 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
ee55da44-c3eb-4e14-8912-39dbdee235c7 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
0b64d76e-2543-4a3a-8a17-825bfe157b67 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
b218a9e9-8a18-45c5-b10c-462d491586f3 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
b218a9e9-8a18-45c5-b10c-462d491586f3 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
7e885feb-4419-487c-91bb-27338a56f9a5 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
7e885feb-4419-487c-91bb-27338a56f9a5 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 |  | NULL | NULL |  | NULL
8f0d7149-73bc-4b2f-99a6-0318bfdb78cc | Pole | 2 | Distribution | 2023-08-09 | 2024-08-08 | Level 2 |  | NULL | NULL |  | NULL
8f0d7149-73bc-4b2f-99a6-0318bfdb78cc | Pole | 2 | Distribution | 2023-08-09 | 2024-08-08 | Level 2 |  | NULL | NULL |  | NULL
cdb667a1-1ad6-4674-b6f1-603bb9edd36b | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 |  | NULL | NULL |  | NULL
33312161-3410-46df-84e9-d1dd54121209 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
9d2b8689-6f67-47d8-836e-22d1ab556f65 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
093fa2a8-d25c-4951-9f25-66114e85a606 | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 |  | NULL | NULL |  | NULL
093fa2a8-d25c-4951-9f25-66114e85a606 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
161f5bb3-c408-4270-bdf1-bf56d9c4c13d | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
4b0aea41-8804-4fb4-8a8a-08d0274b2831 | UG Transformer | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 |  | NULL | NULL |  | NULL
3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 |  | NULL | NULL |  | NULL
3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
a79307d7-546e-4597-a553-3f902306e604 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
314ac0bd-372e-4280-9274-9b5ca92c9c61 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
314ac0bd-372e-4280-9274-9b5ca92c9c61 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
0ceb50c6-05d1-42b3-906e-64786005e8a1 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
95ae16f9-0c3f-4f76-9844-46551ff52b15 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
3467600c-882b-4022-91be-fca076f96adf | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
87fbfaeb-7e6a-4a78-a7f1-1fc13357485a | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
87fbfaeb-7e6a-4a78-a7f1-1fc13357485a | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 |  | NULL | NULL |  | NULL
bb03438a-f3cf-4993-94dd-d0657497b523 | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 |  | NULL | NULL |  | NULL
bb03438a-f3cf-4993-94dd-d0657497b523 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 |  | NULL | NULL |  | NULL
32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
0b2edd57-e419-4eeb-ad72-8c1b26ee7304 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
ca5b3a34-133b-4062-ab26-c2695a6a7af5 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
ca5b3a34-133b-4062-ab26-c2695a6a7af5 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
577fb3b6-ae0f-4dc3-b71d-18a1b8a0e27a | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
db4777bf-e97f-425f-8bef-b4bba2f36e29 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
fbf22393-af38-4629-9fab-fbb52ab7e6f5 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
fbf22393-af38-4629-9fab-fbb52ab7e6f5 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
791f0da6-307c-4228-b721-3ee92d30b220 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
791f0da6-307c-4228-b721-3ee92d30b220 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 |  | NULL | NULL |  | NULL
a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
db82a00c-8503-4cb5-9ccc-66e0785dc73b | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
8555842f-337a-4c33-bf06-c60d6315ab95 | Pole | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 |  | NULL | NULL |  | NULL
72619d12-57c1-4cfd-858d-d6429a087f47 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2 |  | NULL | NULL |  | NULL
72619d12-57c1-4cfd-858d-d6429a087f47 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2 |  | NULL | NULL |  | NULL
72619d12-57c1-4cfd-858d-d6429a087f47 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
74f2946d-e8e1-4874-a36f-b2eb8b6e8efa | UG Transformer | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
af44782d-e74a-4eb5-b8c7-a9d5a0a793eb | UG Transformer | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
1a9baa8a-4da2-46be-b5f9-8319d9775b63 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
1e6ec8fc-b023-476e-9371-4052357e670e | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
dce7f710-19f1-46a5-93d7-ca8fce00a2c4 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2 |  | NULL | NULL |  | NULL
dce7f710-19f1-46a5-93d7-ca8fce00a2c4 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
0f4a8e90-636e-4fae-9205-20df91f47aa2 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 |  | NULL | NULL |  | NULL
1a9baa8a-4da2-46be-b5f9-8319d9775b63 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2 |  | NULL | NULL |  | NULL
d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2 |  | NULL | NULL |  | NULL
d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
d2aa4357-e6cb-49e9-8eda-18bc94d1aeaa | Pole | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
d2aa4357-e6cb-49e9-8eda-18bc94d1aeaa | Pole | 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2 |  | NULL | NULL |  | NULL
ebc37288-97d0-4831-bf37-2bd2db97971a | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
ebc37288-97d0-4831-bf37-2bd2db97971a | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
85041ef2-c7b8-4a1c-8eb9-f44d77321aaf | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
74ccbbf1-373a-4547-9d92-8db63838cf50 | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
880fb73d-b44a-4791-9c41-3ef1915f5d9a | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2 |  | NULL | NULL |  | NULL
4ddf43cc-990a-4c97-9677-bb8dea4f69bc | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | NULL | NULL |  | NULL
c374ec53-facb-48a6-9610-a660e7cb5af6 | Pole | 0 | Distribution | 2023-08-15 | 2028-08-13 | Level 3 |  | NULL | NULL |  | NULL
70442009-34a9-4cbf-b9d3-e9d99e77da76 | UG Transformer | 2 | Distribution | 2023-08-15 | 2028-08-13 | Level 3 |  | NULL | NULL |  | NULL
2051e2e1-8ae2-4dc5-8c39-aeca041a3b22 | Pole | 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2 |  | NULL | NULL |  | NULL
d3fb262c-bcf5-400c-ad9a-ad7f3cd07310 | Pole | 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2 |  | NULL | NULL |  | NULL
7003eb97-7f50-4bad-9bff-4f9eb93ec3c9 | Pole | 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2 |  | NULL | NULL |  | NULL
dae95481-ead8-4a05-b671-d263130d6fec | Pole | 0 | Distribution | 2023-08-15 | 2024-08-14 | Level 2 |  | NULL | NULL |  | NULL
dae95481-ead8-4a05-b671-d263130d6fec | Pole | 0 | Distribution | 2023-08-15 | 2028-08-13 | Level 3 |  | NULL | NULL |  | NULL
b43a8611-d1a5-4101-8cec-3edd7f69d696 | UG Transformer | 2 | Distribution | 2023-08-16 | 2024-08-15 | Level 2 |  | NULL | NULL |  | NULL
be95c557-170f-4528-b577-6b0ac7125401 | Regulator | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
4bcfeaa3-a764-4a04-b3af-0a8d7fc7abc3 | Regulator | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
3572f41a-64d5-40dd-9945-95f16d8538fd | UG Transformer | 2 | Distribution | 2023-08-16 | 2024-08-15 | Level 2 |  | NULL | NULL |  | NULL
035b289e-8b69-420a-897b-580b94e3a585 | Regulator | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
3572f41a-64d5-40dd-9945-95f16d8538fd | UG Transformer | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
58fc35cb-6f1e-4dbb-9786-70e9d7ca44a4 | Switch | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
b52016fc-3acb-4e82-aa9d-96145b447b64 | Switch | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
fd043d17-f221-4afc-9ae2-eb78936e6e24 | Switch | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
d22ee777-ac34-4da4-b5e4-5e2f8178894b | UG Transformer | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
d22ee777-ac34-4da4-b5e4-5e2f8178894b | UG Transformer | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 |  | NULL | NULL |  | NULL
ef93f18a-691d-4d20-a12e-d48025270f00 | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
0acb74fa-7883-4a85-b9a3-f513fea01aff | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
0acb74fa-7883-4a85-b9a3-f513fea01aff | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
cb29fbc4-d545-4512-bec6-05266cb4f477 | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
cb29fbc4-d545-4512-bec6-05266cb4f477 | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
cb29fbc4-d545-4512-bec6-05266cb4f477 | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
a6565349-b1ac-48c1-b8c8-031fbcb41239 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
a6565349-b1ac-48c1-b8c8-031fbcb41239 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
674aefc2-2390-4ed3-a25c-78b5b0d6c719 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
97c3c1d6-4931-45d7-ae00-f2f00e1230a4 | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
97c3c1d6-4931-45d7-ae00-f2f00e1230a4 | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
243eb73c-1079-4460-b014-11010f14499d | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
73e409f3-fa03-4f5f-a1e5-ebb0a3a91790 | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
0acb74fa-7883-4a85-b9a3-f513fea01aff | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
243eb73c-1079-4460-b014-11010f14499d | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3 |  | NULL | NULL |  | NULL
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2 |  | NULL | NULL |  | NULL
1f01ba0a-da2a-4971-aeb1-ada765205f84 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
ab926a43-ca86-4277-92e0-3d020c7ef43c | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
4b67c191-306b-4682-b7c8-5f538566f82e | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
bcf43e93-ebb3-4c85-b585-823195ae952b | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
5c223a31-d36f-4881-82a6-fe3ced9f3622 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
4b67c191-306b-4682-b7c8-5f538566f82e | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
1d97789e-38ac-4121-baf3-7b091231b6b1 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
1d97789e-38ac-4121-baf3-7b091231b6b1 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
cb9dd658-63b7-421c-b26f-7c3dd33b4280 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
f1f0595e-0a49-4c17-98c9-c8c5db110fa1 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | 2 | Distribution | 2023-08-22 | 2024-08-21 | Level 2 |  | NULL | NULL |  | NULL
abee0617-1a2f-4b78-bf34-fbbda211f50a | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | NULL | NULL |  | NULL
67e41575-96fe-497d-b435-7995e89f775d | Pole | 3 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
a7150367-c843-44e0-b95e-ac182f9d7c85 | Pole | 3 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
e1963b4b-b01c-4f34-8ba4-8d299acd4ce3 | Pole | 3 | Distribution | 2023-08-23 | 2024-02-19 | Level 2 |  | NULL | NULL |  | NULL
b18c1b61-daa4-4535-856e-c45919e8cd3a | Pole | 3 | Distribution | 2023-08-23 | 2024-02-19 | Level 2 |  | NULL | NULL |  | NULL
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
e0f03e02-e426-44f6-b5f7-8817feb70c65 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
4e022486-b6e0-4213-9f55-ecb5ab221f55 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
3527813a-a393-4926-a21d-3f48666ded19 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
7919200a-7112-4a35-b12a-0d9494d95094 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
7919200a-7112-4a35-b12a-0d9494d95094 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
378d6b5b-47a4-437b-9ff8-249935065b0c | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
c5376880-6048-4e10-947d-59f22e59a67c | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
4ae0a9da-9ecb-48e4-a553-8b68d38c57f5 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
052d70c3-0dd1-477b-816f-398ad52e2139 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 |  | NULL | NULL |  | NULL
19c2175d-2f27-4451-814f-43f4f026845c | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
19c2175d-2f27-4451-814f-43f4f026845c | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 |  | NULL | NULL |  | NULL
73ec8ebb-cf59-4ee3-bcc7-ed63994907d0 | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 |  | NULL | NULL |  | NULL
c4d9e107-dfed-4445-baa4-4059dfa7169b | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
c4d9e107-dfed-4445-baa4-4059dfa7169b | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 |  | NULL | NULL |  | NULL
967ae741-4d1a-44db-afc7-09ef9c374019 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
967ae741-4d1a-44db-afc7-09ef9c374019 | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 |  | NULL | NULL |  | NULL
7558a656-f808-4736-b44a-666d0a6cc3d6 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
7558a656-f808-4736-b44a-666d0a6cc3d6 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
ae387d68-5ba9-4ed3-b38c-45548ab67474 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
ae387d68-5ba9-4ed3-b38c-45548ab67474 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
450c2c55-7a7d-4fb8-bc95-3a7ec2fe20ac | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 |  | NULL | NULL |  | NULL
450c2c55-7a7d-4fb8-bc95-3a7ec2fe20ac | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | NULL | NULL |  | NULL
a0078f0f-ceda-4456-9c0a-f744f7a00be5 | Pole | 2 | Distribution | 2023-08-25 | 2024-08-24 | Level 2 |  | NULL | NULL |  | NULL
c2a30b56-94ba-41ac-870b-2e2d90302857 | Pole | 2 | Distribution | 2023-08-25 | 2024-08-24 | Level 2 |  | NULL | NULL |  | NULL
c2a30b56-94ba-41ac-870b-2e2d90302857 | Pole | 2 | Distribution | 2023-08-25 | 2028-08-23 | Level 3 |  | NULL | NULL |  | NULL
2693dc3e-af8b-4bd7-867e-45e1c3c67bcb | UG Transformer | 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3 |  | NULL | NULL |  | NULL
2693dc3e-af8b-4bd7-867e-45e1c3c67bcb | UG Transformer | 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3 |  | NULL | NULL |  | NULL
9fbe3716-89f7-470e-83ab-e7d6314272b3 | UG Transformer | 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3 |  | NULL | NULL |  | NULL
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2 |  | NULL | NULL |  | NULL
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2 |  | NULL | NULL |  | NULL
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2028-08-29 | Level 3 |  | NULL | NULL |  | NULL
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2 |  | NULL | NULL |  | NULL
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2 |  | NULL | NULL |  | NULL
81b94aa9-cd3e-418c-85d6-3285fb6db3c1 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2 |  | NULL | NULL |  | NULL
81b94aa9-cd3e-418c-85d6-3285fb6db3c1 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2 |  | NULL | NULL |  | NULL
81b94aa9-cd3e-418c-85d6-3285fb6db3c1 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2 |  | NULL | NULL |  | NULL
8ed218e7-d598-4c1b-9df7-b2428423e115 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2 |  | NULL | NULL |  | NULL
8ed218e7-d598-4c1b-9df7-b2428423e115 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2 |  | NULL | NULL |  | NULL
1c878b6f-c6bf-41d6-93bb-0eab61c70797 | Pole | 2 | Distribution | 2023-09-09 | 2028-09-07 | Level 3 |  | NULL | NULL |  | NULL
9ca5e4b5-5013-4c2f-9e35-9e998e0da0f1 | Pole | 0 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
454ceea3-c978-4c25-bd41-d6dba6c19948 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 |  | NULL | NULL |  | NULL
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 |  | NULL | NULL |  | NULL
3f76948d-08f8-4ecd-a084-d88560053acc | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
28b2c850-2182-47ff-8508-2bae4904181c | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 |  | NULL | NULL |  | NULL
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 |  | NULL | NULL |  | NULL
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 |  | NULL | NULL |  | NULL
451a8d6e-75fe-4e3c-a750-adb3a9f84d86 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
451a8d6e-75fe-4e3c-a750-adb3a9f84d86 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
3e326912-ac6a-4eaa-b012-d6d799777bd5 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 |  | NULL | NULL |  | NULL
956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
be91dead-a04f-4479-8398-32f972af61cf | Pole | 0 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 |  | NULL | NULL |  | NULL
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
479fe971-dd07-4db5-9b7d-41c8c4bcbb76 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
479fe971-dd07-4db5-9b7d-41c8c4bcbb76 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
479fe971-dd07-4db5-9b7d-41c8c4bcbb76 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
a9de1709-e999-4e83-bc0a-df157bd8b344 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
a9de1709-e999-4e83-bc0a-df157bd8b344 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
c28261fa-ee8d-460b-b3b8-df13b799d57c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
c28261fa-ee8d-460b-b3b8-df13b799d57c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
934872c2-62f5-4f7a-baf2-650a2b6b3524 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
934872c2-62f5-4f7a-baf2-650a2b6b3524 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
934872c2-62f5-4f7a-baf2-650a2b6b3524 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
fcbb726b-86cb-4953-b87d-17a403085c2f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
fcbb726b-86cb-4953-b87d-17a403085c2f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
fcbb726b-86cb-4953-b87d-17a403085c2f | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
bf590aa0-a752-4941-b813-c89467ba4baa | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
ca4d0fdd-4da8-4684-a8b9-a6348c94fa83 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
73bc6ea5-d236-43e1-a839-f9165107cb0c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
73bc6ea5-d236-43e1-a839-f9165107cb0c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
f7dc9064-5ee5-4ca7-8204-9974d4279645 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
f7dc9064-5ee5-4ca7-8204-9974d4279645 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0dbcbabc-72d2-4af7-8ba2-c96e1fb9da13 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0dbcbabc-72d2-4af7-8ba2-c96e1fb9da13 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
a9de1709-e999-4e83-bc0a-df157bd8b344 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 |  | NULL | NULL |  | NULL
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
a0c655b0-118b-4887-9e8f-a09cc7dac16d | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0dbcbabc-72d2-4af7-8ba2-c96e1fb9da13 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 |  | NULL | NULL |  | NULL
0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 |  | NULL | NULL |  | NULL
af631e78-0929-4686-9a6b-6190295ebaf6 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
af631e78-0929-4686-9a6b-6190295ebaf6 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
06a9c6ff-20c6-4e52-ae0b-d1dc51eeab04 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
65e0dc54-a129-47ad-8900-878ef9a2673f | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
65e0dc54-a129-47ad-8900-878ef9a2673f | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 |  | NULL | NULL |  | NULL
2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
49fa9a73-c609-4c81-ac09-04d2031aa554 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
1081d5d3-15b3-4cb2-b489-94416ac1a91c | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 |  | NULL | NULL |  | NULL
ce1111e2-8fac-4ba8-88a7-65568b7cb270 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
cc8d5550-a21c-41f5-ac6f-c72f38125443 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
721f0bad-bdc0-4009-b93c-0da5657c30d5 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
721f0bad-bdc0-4009-b93c-0da5657c30d5 | Switch | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 |  | NULL | NULL |  | NULL
da05f32c-ca4e-4a28-93d2-c3d362dde5a9 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
12493a3a-71c6-4597-ab06-bc306445855b | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
9da09cb6-02b1-4a88-8ff9-5a27491d333e | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
b9f088c5-f33a-4df0-a65b-3ea2bc138839 | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 |  | NULL | NULL |  | NULL
635cc53a-4aa4-44a1-9cde-e27e3770b3d6 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | NULL | NULL |  | NULL
288ac579-f6b2-4403-bbbd-b79504d89df8 | Switch | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 |  | NULL | NULL |  | NULL
af3dbaf5-db9f-4fa2-a3ed-4492bd352c94 | Switch | 2 | Distribution | 2023-10-03 | 2024-10-02 | Level 2 |  | NULL | NULL |  | NULL
4298ab5f-2240-400d-b9f9-c93090400e23 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 |  | NULL | NULL |  | NULL
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 |  | NULL | NULL |  | NULL
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2028-10-02 | Level 3 |  | NULL | NULL |  | NULL
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 |  | NULL | NULL |  | NULL
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 |  | NULL | NULL |  | NULL
01f1ae25-1fce-49eb-b04b-e5563c344c43 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 |  | NULL | NULL |  | NULL
9b67dfee-4368-47cc-b862-6ea82e09b621 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 |  | NULL | NULL |  | NULL
9b67dfee-4368-47cc-b862-6ea82e09b621 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 |  | NULL | NULL |  | NULL
ed94cc9b-ad66-4cbb-9bc9-2557f329cdd7 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 |  | NULL | NULL |  | NULL
ed94cc9b-ad66-4cbb-9bc9-2557f329cdd7 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 |  | NULL | NULL |  | NULL
f38d1b8e-ca13-40da-b5bf-e10b96a49c77 | Pole | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 |  | NULL | NULL |  | NULL
f38d1b8e-ca13-40da-b5bf-e10b96a49c77 | Pole | 2 | Distribution | 2023-10-05 | 2024-10-04 | Level 2 |  | NULL | NULL |  | NULL
b9da561a-be1f-4b06-9b72-41d54cf2060d | Pole | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 |  | NULL | NULL |  | NULL
f941ba6b-a553-40c4-9c7f-bed3fa9860cf | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 |  | NULL | NULL |  | NULL
e40d9236-f6c0-4ad0-9875-9aa53573e7b7 | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 |  | NULL | NULL |  | NULL
3e7c9e46-6945-4a6a-b6b8-87aacbac709b | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 |  | NULL | NULL |  | NULL
7524fd8e-bb2e-48bc-9393-910728de7545 | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 |  | NULL | NULL |  | NULL
be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 |  | NULL | NULL |  | NULL
be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 |  | NULL | NULL |  | NULL
50a11142-f99e-4a9b-884f-2a088221c9d4 | UG Transformer | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 |  | NULL | NULL |  | NULL
ae9bc4da-b916-4258-952e-8a9000986684 | Pole | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 |  | NULL | NULL |  | NULL
ae909aec-b467-4283-94a5-a037d6e84479 | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
50a11142-f99e-4a9b-884f-2a088221c9d4 | UG Transformer | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 |  | NULL | NULL |  | NULL
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
a7d573e9-2a48-4bb2-b378-e5290a7f9a40 | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
2da4b3a5-6afc-42c2-9eb3-fdb0620d0cd2 | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 |  | NULL | NULL |  | NULL
e532f368-125e-499a-b6fa-abb72ec66f2d | UG Transformer | 2 | Distribution | 2023-10-16 | 2028-10-14 | Level 3 |  | NULL | NULL |  | NULL
9686b69f-fe7d-46a5-bc05-effa7b4791cf | UG Transformer | 2 | Distribution | 2023-10-16 | 2024-10-15 | Level 2 |  | NULL | NULL |  | NULL
9686b69f-fe7d-46a5-bc05-effa7b4791cf | UG Transformer | 2 | Distribution | 2023-10-16 | 2028-10-14 | Level 3 |  | NULL | NULL |  | NULL
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 |  | NULL | NULL |  | NULL
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 |  | NULL | NULL |  | NULL
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 |  | NULL | NULL |  | NULL
f977c13d-1b5e-4a1b-bc1e-a8696300c618 | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 |  | NULL | NULL |  | NULL
e7ad16db-7eb9-4506-af8c-d4cdd950697e | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 |  | NULL | NULL |  | NULL
15c83ebc-94ba-4f4b-88f7-50f451ff2dca | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 |  | NULL | NULL |  | NULL
859eb4ab-bd5b-4954-96f4-76aef8b1990c | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 |  | NULL | NULL |  | NULL
671703ec-debb-4cb2-aa90-53dba2de032a | Pole | NULL | Distribution | 2023-11-29 | 2024-11-28 | Level 2 |  | NULL | NULL |  | NULL
0b050c6b-3321-4550-b545-ad0798795044 | Pole | NULL | Distribution | 2023-12-06 | 2023-12-08 | Level 1 |  | NULL | NULL |  | NULL
aac7007e-dcad-4a73-8e94-9a8b5485b683 | Pole | NULL | Distribution | 2023-12-06 | 2028-12-04 | Level 3 |  | NULL | NULL |  | NULL
7f362a64-449f-4d6b-b913-cfd55b773b3d | Pole | NULL | Distribution | 2023-12-20 | 2023-12-22 | Level 1 |  | NULL | NULL |  | NULL
8a2bc592-feb1-4115-a54b-37208522d155 | Pole | NULL | Distribution | 2023-12-21 | 2028-12-19 | Level 3 |  | NULL | NULL |  | NULL
1c02d811-0872-4269-9df3-741dca98edb5 | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
84611a73-f50d-47ac-a2c4-4c59368aff1e | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
c422d3c3-8743-4ec1-8e9a-307d896352eb | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
44494ca6-0c34-4c1f-94fe-09b23d040d7a | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
bdca8d03-4baa-4ae8-b0dd-34a747f1ef63 | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
6a1056b6-7305-4e70-be08-26787064493c | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
8ce98fc7-1ab9-44f7-a5ae-ea185e90f154 | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL
bcacf0bb-e722-4436-bb29-27cf4e90e43b | Pole | NULL | Distribution | 2023-12-21 | 2024-12-20 | Level 2 |  | NULL | NULL |  | NULL

## Table 14
Utility | Liberty
Table No. | 14
Date Modified
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution
HFTD 2 Distribution
HFTD 3 Distribution
Non-HFTD Transmission
HFTD 2 Transmission
HFTD 3 Transmission

## Table 15
Utility | Liberty
Table No. | 15
Date Modified | 2023-05-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Wildfire Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS | Comments
TPZ1261 |  | Primary | 83.9991 |  |  | 0.0023407 | 0.0022756 | 6.5057e-05
MULLER1296 |  | Primary | 78.188 |  |  | 0.00037423 | 0.00032853 | 4.5698e-05
MEY3400 |  | Primary | 143.647 |  |  | 0.00032986 | 0.00011523 | 0.00021463
TAH7300 |  | Primary | 190.8235 |  |  | 0.00027109 | 6.7424e-05 | 0.00020367
GLS7400 |  | Primary | 79.0224 |  |  | 0.00020004 | 0.00017586 | 2.417e-05
MEY3300 |  | Primary | 162.5108 |  |  | 0.00018587 | 8.1725e-05 | 0.00010415
STL3101 |  | Primary | 59.3724 |  |  | 0.00015508 | 1.2751e-05 | 0.00014233
POR31 |  | Primary | 31.9075 |  |  | 0.00014488 | 0.00014488 | 0
SQV8200 |  | Primary | 27.9706 |  |  | 8.5557e-05 | 8.393e-05 | 1.6267e-06
SQV7201 |  | Primary | 36.7944 |  |  | 8.1156e-05 | 5.9518e-05 | 2.1638e-05
608 |  | Primary | 17.3219 |  |  | 7.8716e-05 | 7.8715e-05 | 1.3e-09
MEY3200 |  | Primary | 116.2371 |  |  | 7.3462e-05 | 1.6879e-05 | 5.6583e-05
MEY3100 |  | Primary | 64.7987 |  |  | 7.2541e-05 | 1.6319e-05 | 5.6223e-05
STL3501 |  | Primary | 60.6142 |  |  | 6.3584e-05 | 3.0216e-06 | 6.0562e-05
TAH7100 |  | Primary | 59.2746 |  |  | 6.2619e-05 | 1.4548e-05 | 4.8071e-05
MEY3500 |  | Primary | 114.952 |  |  | 5.4543e-05 | 2.6597e-05 | 2.7946e-05
CAL204 |  | Primary | 7.0932 |  |  | 5.331e-05 | 5.331e-05 | 0
POR32 |  | Primary | 55.1117 |  |  | 5.0969e-05 | 5.0969e-05 | 0
TRK7204 |  | Primary | 8.9823 |  |  | 4.0907e-05 | 4.0907e-05 | 0
SRB51 |  | Primary | 14.3662 |  |  | 3.4184e-05 | 3.4184e-05 | 0