## Cover Sheet Tables 1-15
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines Appendix D,
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | Southern California Edison
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2024
Reporting Period quarter |  | Q1
Date Modified |  | 2024-05-01

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Wildfire Safety Community Meetings | Community meetings, primarily in SCE's HFRA, to share information about SCE’s WMP efforts | Share grid hardening, PSPS, and emergency preparedness updates, and highlight SCE's various programs, services, and resources. Also, receive direct feedback from meeting participants | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | DEP-1 | Community Outreach and Engagement_Public Outreach and Education Awareness Program_DEP-1_2023 | 585 | N/A | No | # of meetings | Continue or revise – determined based on the outcome of 2023 |  |  |  |  | Activity is scheduled to begin in Q2. |  |  |  | Quantitative Initiative |  |  |  |  | Planned
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | SCE Emergency Response Training | Technical training programs that prepare employees to perform their jobs safely, comply with regulatory requirements and laws, maintain system reliability, and leverage new technology | Provide effective emergency response and restore service during and after a major event. | Emergency Preparedness | 8.4 | Emergency Preparedness Plan |  | 8.4.2 | DEP-2 | Emergency Preparedness_Emergency Preparedness Plan_DEP-2_2023 | 540 | N/A | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | PSPS response teams are fully qualified/requalified by 7/1 annually to maintain readiness | In Q1, all PSPS readiness trainings are in the process of being developed and training dates are scheduled. |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Customer Research and Education | SCE develops surveys to capture customer feedback on SCE’s wildfire mitigation initiatives with a special emphasis on PSPS activities | Improve its understanding of how to reduce impacts of wildfires, PSPS, and wildfire mitigation work for its customers | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | DEP-4 | Community Outreach and Engagement_Public Outreach and Education Awareness Program_DEP-4_2023 | 586 | N/A | Yes | # of surveys | SCE plans to conduct at least three PSPS‐related customer studies in 2024 |  |  |  |  | 0 |  |  |  | Quantitative Initiative |  |  |  |  | Delayed | - SCE discussed with vendor ways to accelerate fieldwork next year (especially with challenges associated with collecting Business customer surveys) - Residential customer data collection concluded in early April and Business customer surveys will conclude in mid-to-late April (final reports due in May)
SCE | 2024-05-01 | Project | 2024-01-01 | 2024-12-31 | Aerial Suppression | SCE funds up to four aerial firefighting helicopters, support personnel and equipment to bolster firefighting capabilities | Fire suppression within SCE’s service area | Emergency Preparedness | 8.4 | External Collaboration and Coordination |  | 8.4.3 | DEP-5 | Emergency Preparedness_External Collaboration and Coordination_DEP-5_2023 | 556 | Wildfire vulnerability | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | SCE will continue to reassess availability and funding for aerial suppression resources in SCE’s service area annually to determine ongoing QRF strategy | SCE met target in Q1. Contracts were issued at the end of 2023 and final payment was provided to the agencies in January 2024. |  |  |  | Completed
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Distribution High Fire Risk‐Informed (HFRI) Inspections and Remediations (Ground and Aerial) | Distribution equipment and structures inspections beyond the GO 95 and GO 165 requirements | Detect equipment anomalies and mitigate ignition risks that cannot be detected during compliance ‐ driven programs alone | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | IN-1.1 | Grid Design, Operations, and Maintenance_Asset inspections_IN-1.1_2023 | 282 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Yes | # of structures in HFRA | Inspect 187,000 structures in HFRA |  |  |  |  | Ground: 40,047 Aerial: 36,363 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Transmission High Fire Risk‐Informed (HFRI) Inspections and Remediations (Ground and Aerial) | Transmission equipment and structures inspections beyond the GO 95 and GO 165 requirements | Detect equipment anomalies and mitigate ignition risks that cannot be detected during compliance ‐ driven programs alone | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | IN-1.2 | Grid Design, Operations, and Maintenance_Asset inspections_IN-1.2_2023 | 289 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Yes | # of structures in HFRA | Inspect 28,000 structures in HFRA |  |  |  |  | Ground: 7,308 Aerial: 7,235 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Infrared Inspection of Energized Overhead Distribution Facilities and Equipment | Infrared (IR) inspections on its distribution circuits that can detect conditions often not visible to the human eye | Detect deteriorated connection points on electrical equipment such as conductors, insulators, splices or connectors that over time can lead to failures if left unmitigated and pose ignition risks | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | IN-3 | Grid Design, Operations, and Maintenance_Asset inspections_IN-3_2023 | 297 | Equipment ignition likelihood | Yes | # of distribution circuit miles in HFRA | Inspect 5,300 distribution overhead circuit miles in HFRA** |  |  |  |  | Activity is scheduled to begin in Q2. |  |  |  | Quantitative Initiative |  |  |  |  | Planned
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Infrared Inspection, Corona Scanning, and High-Definition Imagery of Energized Overhead Transmission facilitates and Equipment | Infrared (IR) inspections on its transmission circuits that can detect conditions often not visible to the human eye | Detect deteriorated connection points on electrical equipment such as conductors, insulators, splices or connectors that over time can lead to failures if left unmitigated and pose ignition risks | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | IN-4 | Grid Design, Operations, and Maintenance_Asset inspections_IN-4_2023 | 300 | Equipment ignition likelihood | Yes | # of transmission circuit miles in HFRA | Inspect 1,000 transmission overhead circuit miles in HFRA |  |  |  |  | 164.9 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Generation High Fire Risk Informed Inspections in HFRA | Inspections of generation-related assets in HFRA | Identify potential ignition risks on generation-related assets and mitigate the ignition driver risks through system hardening | Grid Design, Operations, and Maintenance | 8.1 | Equipment Inspections, Maintenance, and Repair |  | 8.1.4 | IN-5 | Grid Design, Operations, and Maintenance_Equipment Inspections, Maintenance, and Repair_IN-5_2023 | 303 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Yes | # of structures in HFRA | Inspect 160 generation related assets in HFRA |  |  |  |  | Activity is scheduled to begin in Q2. |  |  |  | Quantitative Initiative |  |  |  |  | Planned
SCE | 2024-05-01 | Project | 2022-01-01 | 2024-12-31 | Inspection and Maintenance Tools | InspectForce is the centralized asset inspection product used for planning and executing inspections | Improves the effectiveness and speed of inspections, data quality and record accuracy, and helps ensure that information is available, accessible, and timely to support wildfire mitigation activities. | Grid Design, Operations, and Maintenance | 8.1 | Asset Management and Inspection Enterprise System(s) |  | 8.1.5 | IN-8 | Grid Design, Operations, and Maintenance_Asset Management and Inspection Enterprise System(s)_IN-8_2023 | 321 | N/A | Yes | Qualitative Initiative | Qualitative Initiative | [8 empty] | Execute the approved designs / recommendations for incorporating distribution ground and InspectCam capabilities into single digital platform | In Q1, SCE completed Solution Architecture Document (SAD) for design to incorporate distribution ground and InspectCam capabiltiies into a single digital platform. |  |  |  | In Progress
SCE | 2024-05-01 | Project | 2022-01-01 | 2024-12-31 | Transmission Conductor and Splice Assessment | Identification of anomalies / issues in order to replace or remediate conductors and/or splices that have a higher probability of failure | Reduce transmission conductor wire down events | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | IN-9 | Grid Design, Operations, and Maintenance_Asset inspections_IN-9_2023 | 305 | N/A | Yes | # Spans/splices | Will inspect 25 spans with Line Vue Will inspect 50 splices with X-Ray |  |  |  |  | Line Vue: 16 X-Ray: 36 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Customer Care Programs (Critical Care Backup Battery (CCBB) Program) | Supports all customers enrolled in Medical Baseline (MBL) that reside in a HFRA to provide a battery-powered portable backup solution | Allows eligible customers to operate critical medical equipment during power outages due to PSPS events or other emergencies | Emergency Preparedness | 8.4 | Customer Support in Wildfire and PSPS Emergencies |  | 8.4.6 | PSPS-2 | Emergency Preparedness_Customer Support in Wildfire and PSPS Emergencies_PSPS-2_2023 | 572 | PSPS vulnerability | No | % of batteries delivered | Complete 85% of battery deliveries to eligible customers within 30 calendar days* of program enrollment, subject to customer availability, reschedule requests and battery supply constraints * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day |  |  |  |  | 100% |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Customer Care Programs (Portable Power Station and Generator Rebates) | Provides up to five $75 rebates to customers for purchasing a portable power station for their home or small business resiliency needs | Provide additional opportunities to increase customer resiliency | Emergency Preparedness | 8.4 | Customer Support in Wildfire and PSPS Emergencies |  | 8.4.6 | PSPS-3 | Emergency Preparedness_Customer Support in Wildfire and PSPS Emergencies_PSPS-3_2023 | 572 | PSPS vulnerability | No | % of rebates processed | Process 85% of all rebate claims within 30 business days* of receipt from website vendor; excluding website related delays and subject to receiving all required customer information * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day measurement |  |  |  |  | 100% |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Weather Stations | Validate real‐time conditions in the field during elevated fire conditions and are used to provide critical situational awareness for PSPS decision‐making and help improve weather models. | Help SCE make decisions during potential fire conditions, including PSPS de-energization and re-energizations | Situational Awareness and Forecasting | 8.3 | Environmental Monitoring Systems |  | 8.3.2 | SA-1 | Situational Awareness and Forecasting_Environmental Monitoring Systems_SA-1_2023 | 454 | PSPS vulnerability | No | # of weather stations installed | Install 50 weather stations in SCE's HFRA |  |  |  |  | 10 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Weather and Fuels Modeling | Weather and fuels modeling including weather forecasts and historic weather data spanning the entire SCE service area | Maintain and enhance operational weather and fuel forecasting capabilities | Situational Awareness and Forecasting | 8.3 | Weather Forecasting |  | 8.3.5 | SA-3 | Situational Awareness and Forecasting_Weather Forecasting_SA-3_2023 | 469 | PSPS vulnerability | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | Equip 200 weather station locations with machine learning capabilities | In Q1, SCE identified over 300 potential weather station locations for new machine learning. |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Fire Science Enhancements | Various modeling tools to predict fire ignition and consequence outputs such as fire perimeter size, structures impacted, populations affected, and injury and death | Expand data analysis, emphasize fire potential forecasting, and improve modeling efforts as it relates to fire science | Situational Awareness and Forecasting | 8.3 | Environmental Monitoring Systems |  | 8.3.2 | SA-8 | Situational Awareness and Forecasting_Environmental Monitoring Systems_SA-8_2023 | 457 | PSPS vulnerability | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | Provide vendor with analytics report and work with the vendor to complete a plan on future improvements | In Q1, SCE provided the analytics report to the vendor for analysis. |  |  |  | In Progress
SCE | 2024-05-01 | Project | 2022-01-01 | 2024-12-31 | High Definition (HD) Cameras | HD camera installations resolves gaps in SCE’s spatial data and provides improved fire confirmation capabilities | Helps IMTs and first responders more quickly assess and respond to reported fires | Situational Awareness and Forecasting | 8.3 | Ignition Detection Systems |  | 8.3.4.2 | SA-10 | Situational Awareness and Forecasting_Ignition Detection Systems_SA-10_2023 | 492 | Wildfire vulnerability, PSPS vulnerability | No | # of HD cameras installed | Install 10 HD Cameras |  |  |  |  | Activity is scheduled to begin in Q2. |  |  |  | Quantitative Initiative |  |  |  |  | Planned
SCE | 2024-05-01 | Pilot | N/A, activity classified as pilot | N/A, activity classified as pilot | Early Fault Detection (EFD) | EFD technology detects high frequency radio emissions that can occur from arcing or partial discharge conditions on the electric system | EFD could potentially be used to monitor the overall health of the electric system which may inform operational decisions during high‐risk conditions. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems |  | 8.3.3 | SA-11 | Situational Awareness and Forecasting_Grid Monitoring Systems_SA-11_2023 | 469 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of locations | Install Early Fault Detection (EFD) at 50 locations |  |  |  |  | 16 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Covered Conductor | Replacing bare wire with conductor / components (fire-resistant poles, composite crossarms, FR3 transformers, wildlife covers, surge arresters, polymer insulators and vibration dampers) to protect against the arcing, faults, or energy release that can come from incidental contact. | Reduce CFO, EFF and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | 8.1 | Covered Conductor Installation |  | 8.1.2.1.1 | SH-1 | Grid Design, Operations, and Maintenance_Covered Conductor Installation_SH-1_2023 | 251 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition, PSPS Likelihood | No | # of circuit miles in HFRA | Install 1,050 circuit miles of covered conductor in SCE’s HFRA |  |  |  |  | 108.15 |  |  |  | Quantitative Initiative |  |  |  |  | Delayed | - Recovery plan being developed: Program Management (PM) to work with partner organizations to review work line by line in each region to develop monthly execution recovery pace (to be complete by end of April) - Meeting weekly with Environmental counterparts to work to resolve constraints - Increased focus on closing out work in our system of record as soon as the work order is field complete - Moving secondary contractor to San Joaquin region to support execution - Establishing a strike team to maximize covered conductor execution in Bishop
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Undergrounding Overhead Conductor | Undergrounding greatly reduces wildfire and PSPS risk by virtually eliminating the possibility for objects to contact energized conductor as well as greatly limiting the ignition-causing potential from equipment failures | Reduce CFO, EFF and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | 8.1 | Undergrounding of Electric Lines and/or Equipment |  | 8.1.2.2 | SH-2 | Grid Design, Operations, and Maintenance_Undergrounding of Electric Lines and/or Equipment_SH-2_2023 | 256 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition, PSPS Likelihood | No | # of circuit miles in HFRA | Convert 16 circuit miles of overhead to underground in SCE's HFRA |  |  |  |  | 0.08 |  |  |  | Quantitative Initiative |  |  |  |  | Delayed | - Continue to work with partner organizations to address constraints Conversion of UG installed miles to OH removed miles to be complete by mid April - Review 2024 projects for material demands and confirm availability - Newly established strike team created to review targeted undergrounding processes
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Installation of System Automation Equipment - RAR / RCS | Installing RARs and RCSs to accommodate enhanced settings which can help to sectionalize circuits and control the flow of electricity remotely | Reduce CFO and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | 8.1 | Other Grid Topology Improvements to Minimize Risk of Ignitions |  | 8.1.2.10 | SH-5 | Grid Design, Operations, and Maintenance_Other Grid Topology Improvements to Minimize Risk of Ignitions _SH-5_2023 | 271 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of RARs / RCSs installed and operationalized | SCE will install 5 RAR/RCS sectionalizing devices subject to 2023 PSPS analysis and subject to change |  |  |  |  | Activity is scheduled to begin in Q2. |  |  |  | Quantitative Initiative |  |  |  |  | Planned
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Circuit Breaker Relay Hardware for Fast Curve | Upgrading circuit breakers and installing fast curve settings to increase the speed of the relay detecting a fault and deenergizes a circuit | Reduce CFO and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | 8.1 | Other Grid Topology Improvements to Mitigate or Reduce PSPS Events |  | 8.1.2.11 | SH-6 | Grid Design, Operations, and Maintenance_Other Grid Topology Improvements to Mitigate or Reduce PSPS Events _SH-6_2023 | 273 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of installations and placed into service | Replace/upgrade remaining 10 CB relay units with fast curve settings in SCE’s HFRA, subject to resource constraints and other execution risks |  |  |  |  | 5 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Transmission Open Phase Detection | Facilitates detection and de-energization of an open phase (broken transmission conductor) before it can contact a grounded object and create a fault event. | Refine circuit protection strategies to further reduce wildfire risk while balancing system reliability | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems |  | 8.3.3 | SH-8 | Situational Awareness and Forecasting_Grid Monitoring Systems_SH-8_2023 | 470 | Equipment ignition likelihood | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | Retrofit TOPD at 5 locations with trip capabilities where alarm mode was previously deployed and that serve HFRA circuitry | In Q1, SCE completed its first milestone of establishing the project artifacts for the 5 in-scope locations. |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Tree Attachment Remediation | Program removes electrical equipment from trees and installs them on new fire-resistant poles | Reduce EFF Risk | Grid Design, Operations, and Maintenance | 8.1 | Traditional Overhead Hardening |  | 8.1.2.5 | SH-10 | Grid Design, Operations, and Maintenance_Traditional Overhead Hardening_SH-10_2023 | 258 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of tree attachment remediations | Remediate 500 tree attachments in SCE’s HFRA |  |  |  |  | 5 |  |  |  | Quantitative Initiative |  |  |  |  | Delayed | - Escalated material concern through supply chain who is working directly with aerial cable manufacturer - The manufacturer has committed to increased aerial cable delivery volumes in May/June to provide enough material for projects in San Joaquin Region - Rural region work to commence in summertime once snow melts
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Long Span Initiative | LiDAR on distribution long spans helps to identify locations with potential conductor clash issues and remediates the highest risk locations upon field validation | Reduce Wire to Wire Risk | Grid Design, Operations, and Maintenance | 8.1 | Covered Conductor Installation |  | 8.1.2.1.1 | SH-14 | Grid Design, Operations, and Maintenance_Covered Conductor Installation_SH-14_2023 | 263 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of remediations | Remediate 1,000 spans in SCE’s HFRA |  |  |  |  | 256 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Vibration Damper Retrofit | Retrofit aims to stop wind-driven vibration (known as Aeolian vibration) that may lead to conductor abrasion or fatigue over time. | Reduce Wire to Wire Risk | Grid Design, Operations, and Maintenance | 8.1 | Covered Conductor Installation |  | 8.1.2.1.1 | SH-16 | Grid Design, Operations, and Maintenance_Covered Conductor Installation_SH-16_2023 | 254 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # structures | Retrofit vibration dampers on 500 structures where covered conductor is already installed in SCE’s HFRA |  |  |  |  | 13 |  |  |  | Quantitative Initiative |  |  |  |  | Delayed | - Work being assigned to District crews to simplify costs being charged. - As of April 10th, a total of 45 vibration damper retrofits have been completed.
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Rapid Earth Fault Current Limiters (REFCL) (Ground Fault Neutralizer) | Detects ground faults on one phase of a three-phase powerline and rapidly reduces the voltage on the faulted conductor while boosting the voltage on the two remaining phases. Ignitions caused by single phase to ground faults can be mitigated with the use of the Ground Fault Neutralizer which reduces fault energy. | Reduce CFO and EFF Risk | Grid Design, Operations, and Maintenance | 8.1 | Emerging Grid Hardening Technology Installations and Pilots |  | 8.1.2.6 | SH-17 | Grid Design, Operations, and Maintenance_Emerging Grid Hardening Technology Installations and Pilots_SH-17_2023 | 266 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | SCE will complete construction of GFN at one substation (Banducci) | In Q1, SCE is meeting internal plan YTD but will not meet its year-end target to complete construction of GFN at one substation due to long lead times to obtain materials needed to complete work. |  |  |  | Delayed | - Design in progress. - Continue to work with vendors to finalize vendor drawings. - Ground bank ordered in Q4 of 2023, expected delivery early Q1 of 2025.
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Rapid Earth Fault Current Limiters (REFCL) (Grounding Conversion) | The REFCL grounding conversion applications act to reduce energy and ignition risk associated with single phase to ground faults. | Reduce CFO and EFF Risk | Grid Design, Operations, and Maintenance | 8.1 | Emerging Grid Hardening Technology Installations and Pilots |  | 8.1.2.6 | SH-18 | Grid Design, Operations, and Maintenance_Emerging Grid Hardening Technology Installations and Pilots_SH-18_2023 | 268 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | Qualitative Initiative | Qualitative Initiative | [8 empty] | SCE will target four locations for grounding conversion, subject to land availability | In Q1, SCE finalized location and Initiated development of Construction Standards, as well as placed material purchase orders and work order design is currently in progress. |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Hazard Tree Management Program | Identifies trees that pose a risk to electric facilities based on the tree’s observed structural integrity and site conditions. | Reduce Contact From Vegetation Risk | Vegetation Management & Inspections | 8.2 | Vegetation Inspections |  | 8.2.2.1 | VM-1 | Vegetation Management & Inspections_Vegetation Inspections_VM-1_2023 | 418 | Contact from vegetation ignition likelihood | Yes | # grids/circuits* | Inspect 408 grids/circuits and prescribe mitigation for hazardous trees with strike potential within those grids in SCE’s HFRA** |  |  |  |  | 137 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Structure Brushing | Removal of vegetation around all poles and structures subject to PRC 4292 | Reduce EFF Risk | Vegetation Management & Inspections | 8.2 | Pole Clearing |  | 8.2.3.1 | VM-2 | Vegetation Management & Inspections_Pole Clearing_VM-2_2023 | 408 | Equipment ignition likelihood, Contact from vegetation ignition likelihood | Yes | # structures brushed | Inspect and clear (where clearance is needed) 63,700 structures*, with the exception of poles for which there are customer access or environmental constraints *These structures are in addition to poles subject to PRC 4292 |  |  |  |  | 4583 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Expanded Clearances for Legacy Facilities | Remove / clear additional vegetation using the standard remediation methods of trims, removals, and/or weed abatement to render the defensible space around a generation facility even more vegetation free | Reduce Contact From Vegetation and EFF Risk | Vegetation Management & Inspections | 8.2 | Clearance |  | 8.2.3.3 | VM-3 | Vegetation Management & Inspections_Clearance_VM-3_2023 | 416 | Equipment ignition likelihood, Contact from vegetation ignition likelihood | Yes | # of sites treated | Perform vegetation treatment and maintenance to 50 sites |  |  |  |  | 15 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Dead and Dying Tree Removal | Patrols in HFRA to identify and remove dead, dying, or diseased trees affected by drought conditions and/or insect infestation. | Reduce Contact From Vegetation Risk | Vegetation Management & Inspections | 8.2 | Clearance |  | 8.2.3.3 | VM-4 | Vegetation Management & Inspections_Clearance_VM-4_2023 | 419 | Contact from vegetation ignition likelihood | Yes | # of grids | Inspect 485 grids/circuits and prescribe mitigation for dead and dying trees with strike potential within those grids/circuits** |  |  |  |  | 176 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Project | 2022-01-01 | 2024-12-31 | VM Work Management Tool | Data Warehouse used for Routine Vegetation Management inspections and resulting mitigations | Consolidated work tracking and reporting to optimize operations and improve data accuracy | Vegetation Management & Inspections | 8.2 | Vegetation Management Enterprise System |  | 8.2.4 | VM-6 | Vegetation Management & Inspections_Vegetation Management Enterprise System_VM-6_2023 | 426 | N/A | Yes | Qualitative Initiative | Qualitative Initiative | [8 empty] | Monitor stabilization of Arbora and develop plan and begin execution of plan to enable additional VM maintenance programs | In Q1, SCE completed draft system stabilization metrics for existing maintenance programs. |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Detailed Inspections for the Prescription, Where Necessary and Feasible, of Expanded Vegetation Clearances from Distribution Lines in HFRA | Distribution expanded line clearances to mitigate the risk of vegetation contact with energized conductors | Reduce Contact From Vegetation Risk | Vegetation Management & Inspections | 8.2 | Clearance |  | 8.2.3.3 | VM-7 | Vegetation Management & Inspections_Clearance_VM-7_2023 | 412 | Contact from vegetation ignition likelihood | Yes | # of grids | SCE plans to inspect 770 grids within our distribution system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year** |  |  |  |  | 231 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | Detailed Inspections for the Prescription, Where Necessary and Feasible, of Expanded Vegetation Clearances from Transmission Lines in HFRA | Transmission expanded line clearances to mitigate the risk of vegetation contact with energized conductors | Reduce Contact From Vegetation Risk | Vegetation Management & Inspections | 8.2 | Clearance |  | 8.2.3.3 | VM-8 | Vegetation Management & Inspections_Clearance_VM-8_2023 | 412 | Contact from vegetation ignition likelihood | Yes | # of grids | SCE plans to inspect 416 circuits within our transmission system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year** |  |  |  |  | 99 |  |  |  | Quantitative Initiative |  |  |  |  | In Progress
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | LiDAR Distribution Vegetation Inspections | LiDAR as an inspection and measurement tool acquired via air patrol to identify clearances between high-voltage distribution lines and vegetation. | Make substantial progress on evaluation of incorporation of remote sensing technology into vegetation inspections | Vegetation Management & Inspections | 8.2 | Vegetation Inspections |  | 8.2.2.1 | VM-9 | Vegetation Management & Inspections_Vegetation Inspections_VM-9_2023 | 398 | N/A | Yes | # circuit miles | SCE will inspect at least 1,020 HFRA circuit miles *Subject to change based on technology, program adjustments, and grid/circuits layout |  |  |  |  | Activity is scheduled to begin in Q2. |  |  |  | Quantitative Initiative |  |  |  |  | Planned
SCE | 2024-05-01 | Program | N/A, activity classified as program | N/A, activity classified as program | LiDAR Transmission Vegetation Inspections | LiDAR as an inspection and measurement tool acquired via air patrol to identify clearances between high-voltage transmission lines and vegetation. | Make substantial progress on evaluation of incorporation of remote sensing technology into vegetation inspections | Vegetation Management & Inspections | 8.2 | Vegetation Inspections |  | 8.2.2.1 | VM-10 | Vegetation Management & Inspections__VM-10_2023 | 398 | N/A | Yes | # circuit miles | SCE will inspect at least 1,500 HFRA circuit miles *Subject to change based on program adjustments and evolution of remote sensing technologies |  |  |  |  | 316.82 |  |  |  | Quantitative Initiative |  |  |  |  | Delayed | - Work with vendors to establish revised performance targets to complete backlog of planned scope. - Continue to onboard the secondary vendors on SCE processes and requirements to support primary vendor.

## Table 2
| Utility | Southern Califonia Edison | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-05-01 | HWW = High wind warning / RFW = Red flag warning
[10 empty] | Actuals | Projected
| Table 2: Performance Metrics | [8 empty] | 1
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 17 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 288 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 38 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 361 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 101 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 2529 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events.
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 48 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HWW/RFW.
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 4 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 78 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HWW/RFW.
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 3 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 345 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HFTD & "Unknown" HWW/RFW.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 10 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 191 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 28 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 226 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 83 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 1891 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 4 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 14 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 5 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 25 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 6 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 97 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 34 | 58 | 49 | 41 | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 30 | 62 | 49 | 36 | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 9 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 190 | 491 | 471 | 450 | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 856 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 2256 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 584 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 1824 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 656 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 1760 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 1192 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 1688 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 1192 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 1192 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 1208 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 1408 |  |  |  | hours | SCE does not capture specific hour distribution to completion. Values here are captured in days an multiplied by an 8 hour day to convert.
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours | Notifications created 1/1/20 and later
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 56 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 1 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 51 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 1 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 14 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 1 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 45 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 2 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 109 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 279 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 674 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 149 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 629 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 37 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 998 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 245 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 1052 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 201 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 936 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 611 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1462 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 1000 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 7273 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 353 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 7021 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 3365 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 7997 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 1090.5 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 4375 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 264 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 4230 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 6197 |  |  |  | hours
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | Routine | N/A | 79368 | 163543 | 163543 | 163543 | Number of orders
| 6. Vegetation management work orders | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | Routine | N/A | 35840 | 35136.0909 | 35136.0909 | 35136.0909 | Number of orders | For Veg Past Due WOs, SCE reports the number of open work points in 6a that have exceeded internal targets of 30 days <Regulatory Clearance Distance (RCD) and 90 days between RCD and Trigger Clearance Distance (TCD).
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 957750 | 889962.5833 | 889962.5833 | 889962.5833 | Number of orders
| 7. Asset management work orders | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 24329 | 24337.3333 | 24337.3333 | 24337.3333 | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Hours | For metric 8a, data for crew response time to a locked circuit breaker incident is not readily availableis not currently available as SCE does not make it mandatory to track arrival time of the crew for instances not involving hazard conditions such as 911 or wire down calls. Documentation takes time away from restoring customers and therefore not tracked for other purposesSCE will continue to review the available information in its outage systems to provide this information in a future filing. Currently, aAny average on a quarterly basisquarterly data would not reflect only 911 and wire down events and is not a good representation of our overall true response time. | Metric Not Available at this Time.
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of fatalities | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-15 should not be construed as an admission of any wrongdoing or liability by SCE. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report.
| 9. Fatalities and injuries due to utility-related ignitions | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of injuries | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-15 should not be construed as an admission of any wrongdoing or liability by SCE. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report.
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 39 |  |  |  | 1000 | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. Ignition costs include only those repair WOs that have been closed by time of report out. Additional costs may still be pending.
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of structures | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-15 should not be construed as an admission of any wrongdoing or liability by SCE. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report.
| 11. Structures damaged or destroyed by utility-related ignitions | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Number of structures | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-15 should not be construed as an admission of any wrongdoing or liability by SCE. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. | Data point is not currently tracked.
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 13 |  |  |  | Acres | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-15 should not be construed as an admission of any wrongdoing or liability by SCE. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report.
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 2 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 6 |  |  |  | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | AGP Inspections | HFTD Tier 2 | Distribution | Patrol Inspection | other | 43139 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 10326 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed aerial inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | ODI + HFRI | HFTD Tier 2 | Distribution | Detailed Inspection | other | 11270 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | IR-Aerial | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | IPI + IR Ground | HFTD Tier 2 | Distribution | Other Inspection | other | 259 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. Dist "Other" contains Dist IR Scan and Intrusive Pole Inspection (both ground inspection programs).
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | AGP Inspections | HFTD Tier 2 | Distribution | Patrol Inspection | other | 1462.4046 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 350.0496 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | ODI + HFRI | HFTD Tier 2 | Distribution | Detailed Inspection | other | 382.051 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | IR-Aerial | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | IPI + IR Ground | HFTD Tier 2 | Distribution | Other Inspection | other | 8.7801 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 10 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 4483 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 6 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 1698 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | AGP Inspections | HFTD Tier 3 | Distribution | Patrol Inspection | other | 56811 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 26037 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed aerial inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | ODI + HFRI | HFTD Tier 3 | Distribution | Detailed Inspection | other | 28603 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | IR-Aerial | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | IPI + IR Ground | HFTD Tier 3 | Distribution | Other Inspection | other | 113 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. Dist "Other" contains Dist IR Scan and Intrusive Pole Inspection (both ground inspection programs).
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | AGP Inspections | HFTD Tier 3 | Distribution | Patrol Inspection | other | 1925.883 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 882.6498 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | ODI + HFRI | HFTD Tier 3 | Distribution | Detailed Inspection | other | 969.6367 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | IR-Aerial | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | IPI + IR Ground | HFTD Tier 3 | Distribution | Other Inspection | other | 3.8307 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 33 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 6 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 15792 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 9 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 4657 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | AGP Inspections | Non-HFTD | Distribution | Patrol Inspection | other | 228746 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Dist Aerial completed in HFRA only
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | Aerial | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | ODI + HFRI | Non-HFTD | Distribution | Detailed Inspection | other | 63276 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | IPI + IR Ground | Non-HFTD | Distribution | Other Inspection | other | 1170 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. Dist "Other" for non-HFTD contains Intrusive Pole Inspection counts only, as Dist IR is only conducted in HFRA.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | AGP Inspections | Non-HFTD | Distribution | Patrol Inspection | other | 6839.6113 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE Dist Aerial completed in HFRA only
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | Aerial | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | ODI + HFRI | Non-HFTD | Distribution | Detailed Inspection | other | 1891.9817 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | IPI + IR Ground | Non-HFTD | Distribution | Other Inspection | other | 34.9835 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 5 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 56 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 12 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 20632 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 28 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 16998 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | Trans Routine | HFTD Tier 2 | Transmission | Patrol Inspection | other | 10 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. For Trans Patrol Inspections, SCE tracks counts of circuits inspected.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 4210 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | Trans Det +Trans HFRA | HFTD Tier 2 | Transmission | Detailed Inspection | other | 3493 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. Trans Detailed and Trans HFRA inspections use different conversion methods as such the count of structures inspected to circuit mi relationship is varied.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | IR-Aerial | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 722 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. SCE Trans "Other" type inspections consists of Trans IR Scan (in which scans are completed 100% by helicopter) and Intrusive Pole Inspections (Ground).
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | IPI | HFTD Tier 2 | Transmission | Other Inspection | other | 41 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. SCE Trans "Other" type inspections consists of Trans IR Scan (in which scans are completed 100% by helicopter) and Intrusive Pole Inspections (Ground).
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | Trans Routine | HFTD Tier 2 | Transmission | Patrol Inspection | other | 113 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 499.8331 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | Trans Det +Trans HFRA | HFTD Tier 2 | Transmission | Detailed Inspection | other | 473 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. Trans Detailed and Trans HFRA inspections use different conversion methods as such the count of structures inspected to circuit mi relationship is varied.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | IR-Aerial | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 85.7196 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | IPI | HFTD Tier 2 | Transmission | Other Inspection | other | 4.8677 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 8 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 127 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 49 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 161 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 4 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 49 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 45 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | Trans Routine | HFTD Tier 3 | Transmission | Patrol Inspection | other | 19 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. For Trans Patrol Inspections, SCE tracks counts of circuits inspected.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 3025 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | Aerial | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | Trans Det +Trans HFRA | HFTD Tier 3 | Transmission | Detailed Inspection | other | 3830 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. Trans Detailed and Trans HFRA inspections use different conversion methods as such the count of structures inspected to circuit mi relationship is varied.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | IR-Aerial | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 667 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. SCE Trans "Other" type inspections consists of Trans IR Scan (in which scans are completed 100% by helicopter) and Intrusive Pole Inspections (Ground).
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | IPI | HFTD Tier 3 | Transmission | Other Inspection | other | 5 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. SCE Trans "Other" type inspections consists of Trans IR Scan (in which scans are completed 100% by helicopter) and Intrusive Pole Inspections (Ground).
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | Trans Routine | HFTD Tier 3 | Transmission | Patrol Inspection | other | 210 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 359.1437 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | Aerial | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | Trans Det +Trans HFRA | HFTD Tier 3 | Transmission | Detailed Inspection | other | 562 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. Trans Detailed and Trans HFRA inspections use different conversion methods as such the count of structures inspected to circuit mi relationship is varied.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | IR-Aerial | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 79.1897 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | IPI | HFTD Tier 3 | Transmission | Other Inspection | other | 0.59363 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 6 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 108 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 34 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 252 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 71 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 36 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 73 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | Trans Routine | Non-HFTD | Transmission | Patrol Inspection | other | 113 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. For Trans Patrol Inspections, SCE tracks counts of circuits inspected.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans Aerial inspection is HFTD only
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans Aerial inspection is HFTD only
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | Trans Det +Trans HFRA | Non-HFTD | Transmission | Detailed Inspection | other | 37 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. Trans Detailed and Trans HFRA inspections use different conversion methods as such the count of structures inspected to circuit mi relationship is varied.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. SCE Trans "Other" type inspections consists of Trans IR Scan (in which scans are completed 100% by helicopter) and Intrusive Pole Inspections (Ground). | SCE Trans IR scan is HFTD only
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | IPI | Non-HFTD | Transmission | Other Inspection | other | 106 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | For 2020, SCE tracked the completed other inspections by the year and in order to represent the 2020 completed asset inspection by quarter, SCE evenly distributed the completed inspections to each of the four quarters in 2020. SCE Trans "Other" type inspections consists of Trans IR Scan (in which scans are completed 100% by helicopter) and Intrusive Pole Inspections (Ground).
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | Trans Routine | Non-HFTD | Transmission | Patrol Inspection | other | 1256 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE Trans Aerial inspection is HFTD only
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE Trans Aerial inspection is HFTD only
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | Trans Det +Trans HFRA | Non-HFTD | Transmission | Detailed Inspection | other | 411 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. Trans Detailed and Trans HFRA inspections use different conversion methods as such the count of structures inspected to circuit mi relationship is varied.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE Trans IR scan is HFTD only
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | IPI | Non-HFTD | Transmission | Other Inspection | other | 8.0589 |  |  |  | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 560 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 20 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 9 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 288 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 11 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 33 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 2602 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 33 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 1999 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 31 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 25 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 6921 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 103 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 6 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 3135 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 5 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 55 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 12 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 11 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 11467 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 662 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 9376 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 10 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 128 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 107 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 160 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 32 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 7 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 17 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 2 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 78 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 79 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 177 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 2 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 47 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 19 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 11 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 385 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 7 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 35 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 321 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 37890 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 465 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 0 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 1149 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 90137 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 1231 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 4 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 1897 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | 135325 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 4659 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 3 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | 2276 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 7863 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 1 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 52 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 8056 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 19 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of non0routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 330 |  |  |  | # of trees found to be non0compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | 7088 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 7 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | 36 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Percentage of customers notified of evacuation | SCE has no jurisdiction over evacuation orders. SCE diligently requested and followed up with local governments and law enforcement, and was only able to obtain information from one county. Even then, the information provided included high-level estimations of evacuation counts estimated by the local government and law enforcement entity for a limited amount of fires. Because of this, SCE is unable to obtain the requested data, analyze it, and report on evacuation related requirements in this table. SCE anticipates this to be a recurring challenge going forward. | SCE does not track this metric.

## Table 3
Utility | Southern California Edison
Table No. | 3
Date Modified | 2024-05-01
[5 empty] | Actual | Projected
Table 3: List and description of additional metrics |  |  |  |  | 1
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Number of CPUC reportable ignitions in HFRA | Count of the number of CPUC reportable ignitions in HFRA | To measure changes in rate of ignitions between years | Factors outside of SCE's control (e.g., wind, live fuel moisture) have a significant effect on CPUC reportable ignition counts in HFRA. | Annual submission of CPUC reportable ignition totals to CPUC | 3 | 38.9808 | 37.844 | 37.0722
2. Number of wire downs in HFRA | Count of the number of wire downs in HFRA | To measure changes in rate of fault events which are a pre-cursor both ignition and safety events | Number of wire down incidents in HFRA based on cause. These metrics may help to provide insight on controllable and uncontrollable risks or help plan future activities to focus on a particular type of fault or outage that may be of wildfire risk. | Deep-dive audits of select portions of utility grid | 130 | 360.5342 | 360.1761 | 360.5014
3. Number of outages in HFRA | Count of the number of outages in HFRA | To measure changes in rate of wire down events which are a pre-cursor both ignition and safety events | Number of faults in HFRA based on cause. These metrics may help to provide insight on controllable and uncontrollable risks or help plan future activities to focus on a particular type of fault or outage that may be of wildfire risk. | Deep-dive audits of select portions of utility grid | 503 | 2017.7963 | 1945.887 | 1892.4631
4. # of asset management ignition risk-related work orders that are past due (excluding GO95 exceptions) | Count of the total past due T&D ignition risk work orders, excluding GO95 exceptions | To meaure the past due asset-related work orders that have ignition risk and are not subject to GO95 exceptions | This metric will help track past due work order that are related to wildfire risk mitigation and that are largely within the utility's control for addressing. |  | 4715 | 4021 | 4021 | 4021
5. Number of Tree-Caused Circuit Interruptions (TCCIs) in HFRA (ODRM data) | Count of TCCIs in HFRA | To measure trends in how vegetation is causing risk events when contacting overhead circuitry in HFRA | Vegetation that comes into contact with energized circuits can cause a circuit interruption (e.g., fault), however there may be cases with vegetation comes into contact with SCE infrastructure and no fault occurs. |  | 44 | 57 | 54.15 | 51.4425 |  | For Q1 2024 no filter was used, data is from ODRM. For Q4 2023 no filter was used, data is from ODRM. For Q2 2023 no filter was used, data is from ODRM (Duplicates are not reported). For Q1 2023 no filter was used, data is from ODRM (Duplicates are not reported). The number of TCCIs exclude anything that was human caused, no cause/not tree related, and uncategorized. There are also 11 pending review TCCIs that is included in the Q4 (Depending on the result of review Q4 number might change).Projections are an estimate only and actual performance is dependent on weather and other factors.
6. Number of trees inspected where at least some vegetation was found in a non-compliant condition in HFRA - Routine | Count of instances in HFRA where vegetation found in non-compliant condition through Routine Line Clearing programs | To meaure the extent to which vegetation exists in non-compliant condition | Routine Line Clearing activities will identify instances in which vegetation exists in a non-compliant condition |  | 3428 | 15782.35 | 14993.2325 | 14243.5709 |  | Projections are an estimate only and actual performance is dependent on weather and other factors.
7. Frequency of PSPS events (total) | Count of PSPS events in which de-energization has occurred | To measure trends in how many de-energization events occur each year | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | 0 | 7 | 7 | 7 |  | SCE uses a 2020-2022 PSPS event average to forecast 2023-2025 events. SCE does not forecast a reduction in events from the 2020-2022 average as overall circuit scope reduction may not reduce event count
8. Scope of PSPS events (total) | Count of circuit de-energized | To meaure trends in how may circuits are de-energized due to PSPS events | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | 0 | 225 | 212 | 199 |  | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year.
9. Duration of PSPS (total) | Customer hours de-energized due to PSPS | To measure trends in the amount of customer hours de-energized due to PSPS | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | 0 | 2516572 | 2290080 | 2083972 |  | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year.
10. # of customers impacted by PSPS | Count of customers de-enrgized due to PSPS | To measure trends in the number of customers de-energized due to PSPS | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | 0 | 126361 | 107408 | 91297 |  | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year.
11a. Customer recall of SCE wildfire and preparedness communications - System Wide | The percentage of surveyed customers across SCE's service area who responded that they recalled communications from SCE about the threat of wildfire and how they can prepare for them. | To help measure the effectiveness of its community outreach and engagement activities by measuring customer awareness of SCE’s wildfire messaging and customer wildfire and PSPS programs and services. | Results can be impacted by volume of PSPS events experienced per year, level of marketing and outreach to customers, severity of fire season, and other factors. | In-Language Wildfire Mitigation / PSPS Communications Effectiveness Survey | 0 | 48 | 48 | 48 | % | The survey that generates these results is performed twice annually, once once toward the start of Q3 and once toward the end of Q4. Therefore, figures are not provided for Q1 or Q2.
11b. Customer recall of SCE wildfire and preparedness communications - HFRA only | The percentage of surveyed customers across SCE's HFRA who responded that they recalled communications from SCE about the threat of wildfire and how they can prepare for them. | To help measure the effectiveness of its community outreach and engagement activities by measuring customer awareness of SCE’s wildfire messaging and customer wildfire and PSPS programs and services. | Results can be impacted by volume of PSPS events experienced per year, level of marketing and outreach to customers, severity of fire season, and other factors. | In-Language Wildfire Mitigation / PSPS Communications Effectiveness Survey | 0 | 56 | 56 | 56 | % | The survey that generates these results is performed twice annually, once once toward the start of Q3 and once toward the end of Q4. Therefore, figures are not provided for Q1 or Q2.

## Table 4
Utility | Southern California Edison
Table No. | 4
Date Modified | 2024-05-01
Note: These columns are placeholders for future QR submissions.
Table 4: Weather patterns |  |  | 1
Metric type | # | Metric name | 2024 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
1. Red flag warning only overhead circuit mile days | 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 0 | Red flag warning overhead circuit mile days, see above for definition
1. Red flag warning only overhead circuit mile days | 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 0 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 6335.3009 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
2. Wind condition overhead circuit mile days | 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 15721.5001 | High wind warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 28699.1165 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
3. Wind condition and Red flag warning overhead circuit mile days | 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
4. Fire potential index overhead circuit mile days | 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 0 | Fire potential index overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.c. | Fire potential index circuit mile days - non-HFTD | 0 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed) |  |  |  | Not available.

## Table 5
| Utility | Southern California Edison | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-05-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[8 empty] | Actual number of risk events | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q1
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | No | 8 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 3 | 33.1943 | 33.1641 | 33.229 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 2.9293 | 2.9266 | 2.9324 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 19 | 93.2346 | 93.1164 | 93.4526 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 4.7327 | 4.7267 | 4.7438 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 1.7935 | 1.7912 | 1.7977 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0.21959 | 0.21959 | 0.21959 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 89 | 298.0424 | 297.8564 | 298.3986 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 5 | 27.4274 | 27.4102 | 27.4601 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 7 | 35.1717 | 35.1498 | 35.2138 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 1.3785 | 1.3785 | 1.3785 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0.004892 | 0.004892 | 0.004892 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.0 | 3rd party contact | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.0 | 3rd party contact | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.0 | Other contact from object | Distribution | Non-HFTD | No | 3 | 13.1247 | 13.1081 | 13.1285 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.2 | Other contact from object | Distribution | HFTD Tier 2 | No | 2 | 0.25385 | 0.25353 | 0.25393 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | No | 0 | 0.61146 | 0.61069 | 0.61164 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.0 | Other contact from object | Transmission | Non-HFTD | No | 0 | 0.009067 | 0.009067 | 0.009067 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.2 | Other contact from object | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 203.4891 | 203.4891 | 203.4891 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 8.4702 | 8.4702 | 8.4702 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 10.121 | 10.121 | 10.121 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 1.0919 | 1.0919 | 1.0919 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 83 | 230.8538 | 230.6673 | 231.1153 | # risk events (excluding ignitions) | Note: A portion of this data includes "Unknown" HFTD.
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 26 | 42.7625 | 42.7279 | 42.8109 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 52 | 93.8653 | 93.7894 | 93.9716 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 0.011826 | 0.011826 | 0.011826 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0.004929 | 0.004929 | 0.004929 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 3 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 1.9894 | 1.9894 | 1.9894 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0.21123 | 0.21123 | 0.21123 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 14 | 47.3282 | 47.3282 | 47.3282 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 1 | 7.8078 | 7.8078 | 7.8078 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 8.1921 | 8.1921 | 8.1921 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 0.59807 | 0.59807 | 0.59807 | # risk events (excluding ignitions) | Note: A portion of this data includes "Unknown" HFTD.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0.3615 | 0.3615 | 0.3615 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0.63983 | 0.63983 | 0.63983 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | No | 34 | 71.3036 | 71.1655 | 71.1518 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | No | 3 | 3.8474 | 3.84 | 3.8392 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | No | 1 | 7.1697 | 7.1558 | 7.1544 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | No | 0 | 0.005528 | 0.005528 | 0.005528 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 4 | 26.3099 | 26.2704 | 26.2163 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 1.6634 | 1.6609 | 1.6575 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 1.82 | 1.8172 | 1.8135 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0.005528 | 0.005528 | 0.005528 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 1.835 | 1.835 | 1.835 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | No | 5 | 5.4403 | 5.4403 | 5.4403 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | No | 0 | 0.41446 | 0.41446 | 0.41446 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | No | 0 | 0.41446 | 0.41446 | 0.41446 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | No | 0 | 0.29933 | 0.29933 | 0.29933 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | No | 0 | 0.021642 | 0.021642 | 0.021642 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | No | 0 | 0.021642 | 0.021642 | 0.021642 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | No | 0 | 1.0001 | 0.99809 | 0.98932 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 4 | 71.9197 | 71.9197 | 71.9197 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 1 | 3.0774 | 3.0774 | 3.0774 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 8.3283 | 8.3283 | 8.3283 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0.22789 | 0.22789 | 0.22789 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 6 | 17.9058 | 17.8716 | 17.8706 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 1 | 0.89311 | 0.89141 | 0.89136 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 3.5556 | 3.5488 | 3.5486 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 1 | 1.2968 | 1.2968 | 1.2968 | # risk events (excluding ignitions) | Note: A portion of this data includes "Unknown" HFTD.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0.060113 | 0.060113 | 0.060113 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0.010509 | 0.010509 | 0.010509 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 6.2068 | 6.1947 | 6.1934 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0.5577 | 0.55662 | 0.5565 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0.010215 | 0.010195 | 0.010193 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 25 | 198.1203 | 197.7388 | 197.2466 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 4 | 12.1234 | 12.1 | 12.0699 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 1 | 12.9985 | 12.9734 | 12.9412 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0.72344 | 0.72344 | 0.72344 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0.25818 | 0.25818 | 0.25818 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 2 | 1.2189 | 1.2189 | 1.2189 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.049608 | 0.049608 | 0.049608 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.018569 | 0.018569 | 0.018569 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 1 | 12.8785 | 12.8785 | 12.8785 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0.000168 | 0.000168 | 0.000168 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 9.29e-05 | 9.29e-05 | 9.29e-05 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | No | 44 | 145.4754 | 145.1931 | 145.1622 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | No | 2 | 22.7137 | 22.6696 | 22.6648 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | No | 13 | 35.0802 | 35.0122 | 35.0047 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | No | 0 | 0.11019 | 0.11019 | 0.11019 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | No | 0 | 0.054035 | 0.054035 | 0.054035 | # risk events (excluding ignitions)
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 6 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | No | 11 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 74 | 503.6743 | 500.2201 | 494.9232 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 8 | 47.6435 | 45.568 | 44.7865 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 9 | 66.2166 | 63.1707 | 60.6245 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 4 | 16.3727 | 16.3727 | 16.3727 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 3.797 | 3.7 | 3.6059 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 1 | 5.0501 | 4.9636 | 4.8776 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 125 | 846.6854 | 845.7848 | 843.3977 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 1 | 28.0227 | 27.8133 | 27.722 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 4 | 25.147 | 24.5507 | 24.8185 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 5 | 30.0683 | 30.0683 | 30.0683 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 2.0966 | 2.0966 | 2.0966 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 1.4891 | 1.4891 | 1.4891 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 101 | 454.2456 | 453.8739 | 453.2061 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 3 | 29.9326 | 29.8952 | 30.025 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 9 | 57.612 | 58.2721 | 58.5831 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 3 | 20.7565 | 20.5326 | 20.5269 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 1.7452 | 1.7446 | 1.7444 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | No | 13 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | No | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | 9 | 98.3413 | 98.0462 | 97.7264 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 8.398 | 7.9068 | 7.4871 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 12.5712 | 11.6501 | 10.9305 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes | 3 | 5.9494 | 5.9035 | 5.9014 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 102 | 175.1937 | 175.1017 | 174.807 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 18 | 44.7531 | 42.5444 | 41.3097 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 28 | 77.1636 | 72.5996 | 70.6338 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 1 | 0.24437 | 0.24437 | 0.24437 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 1.4299 | 1.4299 | 1.4299 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 2 | 1.6928 | 1.6816 | 1.667 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 10.4996 | 10.4996 | 10.4996 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0.74983 | 0.74983 | 0.74983 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 1.4998 | 1.4998 | 1.4998 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 8 | 32.7752 | 32.7734 | 32.7692 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 1 | 1.3104 | 1.3104 | 1.3104 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 1 | 3.5662 | 3.3692 | 3.2127 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 3.6189 | 3.6189 | 3.6189 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 1.1237 | 1.1237 | 1.1237 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0.74884 | 0.74884 | 0.74884 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 120 | 609.5489 | 607.9625 | 605.8275 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 15 | 63.0708 | 59.9076 | 58.071 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 23 | 100.2712 | 95.4653 | 92.8042 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 10 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 4 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 149 | 479.8438 | 478.6123 | 476.8374 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 15 | 47.2426 | 46.4404 | 46.403 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 20 | 53.255 | 52.1093 | 52.372 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 5.0308 | 5.0308 | 5.0308 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0.054882 | 0.054882 | 0.054882 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 26 | 191.0492 | 190.2666 | 189.9551 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 1 | 3.1558 | 3.1558 | 3.1558 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 6.2556 | 5.6763 | 5.0475 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 1 | 5.603 | 5.603 | 5.603 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0.50594 | 0.50594 | 0.50594 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0.00594 | 0.00594 | 0.00594 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 159 | 694.2424 | 693.0039 | 691.9622 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 33 | 73.8677 | 64.8978 | 57.8073 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 22 | 132.6352 | 119.381 | 110.0412 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | No | 25 | 70.7605 | 70.6428 | 70.3956 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | No | 1 | 9.61 | 8.9257 | 8.6172 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | No | 2 | 12.1877 | 11.2031 | 10.7052 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrestor | Distribution | Non-HFTD | Yes | 9 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrestor | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 12 | 91.0497 | 90.8809 | 90.6537 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 2 | 18.9319 | 18.285 | 17.8869 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 4 | 7.8277 | 7.4667 | 7.1641 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 12 | 73.4724 | 73.4386 | 73.3722 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 2 | 5.3846 | 5.3846 | 5.3846 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 9.1563 | 8.644 | 7.8294 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 205 | 1663.397 | 1656.344 | 1647.444 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 16 | 230.2307 | 222.1104 | 216.2654 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 34 | 310.7854 | 300.5502 | 286.8855 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 2.7141 | 2.7141 | 2.7141 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0.085579 | 0.085579 | 0.085579 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0.085579 | 0.085579 | 0.085579 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | 19 | 94.2507 | 94.0322 | 93.7566 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 4 | 7.3774 | 7.3462 | 7.3413 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 3 | 13.1469 | 12.958 | 12.8081 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes | 6 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 4 | 27.3482 | 27.3317 | 27.2836 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 1.5292 | 1.5955 | 1.5723 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.017658 | 0.017347 | 0.017541 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 9.1084 | 9.0949 | 9.0765 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0.022772 | 0.022669 | 0.022604 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0.017862 | 0.017862 | 0.017862 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 5 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 6 | 10.2317 | 10.2239 | 10.2175 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 1.2681 | 1.2658 | 1.2594 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0.074446 | 0.074383 | 0.074295 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0.000861 | 0.000861 | 0.000861 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 6.87e-05 | 6.87e-05 | 6.87e-05 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 27 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 4 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 3 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | No | 3 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | No | 1244 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | No | 133 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | No | 241 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | No | 13 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | No | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | No | 5 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 319 | 1537.316 | 1533.696 | 1530.453 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 51 | 215.744 | 212.1381 | 209.4628 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 33 | 270.2319 | 270.2319 | 270.2319 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 50 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 7 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 8 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | No | 408 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | No | 32 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | No | 58 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | No | 35 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | No | 10 | 0 | 0 | 0 | # risk events (excluding ignitions)

## Table 6
| Utility | Southern California Edison | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-05-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[7 empty] | Actual number of ignitions | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q1
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 0 | 6.1334 | 6.0963 | 6.0412 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 1.4453 | 1.3762 | 1.3416 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 2.5912 | 2.4647 | 2.3354 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 1.6319 | 1.6319 | 1.6319 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0.95998 | 0.93667 | 0.91507 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 1.6532 | 1.6276 | 1.6031 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 2 | 13.5921 | 13.5782 | 13.5388 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 1.1781 | 1.1709 | 1.1657 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 1.9844 | 1.9163 | 1.9288 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0.44221 | 0.44221 | 0.44221 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0.11841 | 0.11841 | 0.11841 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0.11841 | 0.11841 | 0.11841 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 2 | 7.2537 | 7.2485 | 7.2394 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.8391 | 0.8349 | 0.83998 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 2 | 2.7065 | 2.7332 | 2.7478 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0.34583 | 0.34471 | 0.34471 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0.19866 | 0.19856 | 0.19853 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 2.4647 | 2.4544 | 2.4429 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0.35327 | 0.32633 | 0.30104 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0.54001 | 0.48792 | 0.44428 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0.072848 | 0.072089 | 0.072089 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0.07259 | 0.071543 | 0.070688 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0.146 | 0.14473 | 0.14353 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 1 | 8.19 | 8.1856 | 8.1707 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 0 | 2.8666 | 2.749 | 2.6777 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 0 | 2.9958 | 2.8223 | 2.7431 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 0.035829 | 0.035829 | 0.035829 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0.035698 | 0.035363 | 0.035023 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0.97497 | 0.97493 | 0.97485 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0.016904 | 0.015816 | 0.014216 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0.062326 | 0.062326 | 0.062326 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 1 | 12.2891 | 12.2587 | 12.2094 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 0 | 1.2978 | 1.2301 | 1.1827 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 4.4531 | 4.2812 | 4.1524 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0.28116 | 0.28116 | 0.28116 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 0 | 4.0671 | 4.0567 | 4.041 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 0 | 0.70331 | 0.68869 | 0.67858 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 0 | 1.8469 | 1.8195 | 1.817 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 0.031163 | 0.031163 | 0.031163 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 0.27276 | 0.27114 | 0.27035 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0.043915 | 0.036314 | 0.028716 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0.031163 | 0.031163 | 0.031163 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0.74168 | 0.73996 | 0.73838 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0.29353 | 0.28706 | 0.27901 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0.022632 | 0.019882 | 0.016783 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 1.0351 | 1.0327 | 1.0285 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0.39521 | 0.36612 | 0.34412 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0.38851 | 0.35562 | 0.32862 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 0 | 0.29155 | 0.29155 | 0.29155 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0.29155 | 0.29155 | 0.29155 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 1.381 | 1.3771 | 1.3724 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0.031163 | 0.031163 | 0.031163 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 1.0336 | 1.0317 | 1.029 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0.022796 | 0.021857 | 0.020874 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0.023125 | 0.021815 | 0.020222 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 1.1693 | 1.1687 | 1.1676 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0.78235 | 0.78072 | 0.77287 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 11.1972 | 11.1459 | 11.0774 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0.58827 | 0.57257 | 0.5581 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 1.0075 | 0.97448 | 0.92343 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 3.6934 | 3.6846 | 3.6726 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1.1384 | 1.1282 | 1.1211 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 1.2185 | 1.2017 | 1.1836 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0.39943 | 0.39943 | 0.39943 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0.074131 | 0.072555 | 0.070692 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 2.267 | 2.2654 | 2.2604 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.02363 | 0.023286 | 0.022276 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.70582 | 0.69416 | 0.70047 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0.18824 | 0.18788 | 0.18736 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0.071003 | 0.07062 | 0.070322 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 0.25816 | 0.25816 | 0.25816 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0.0081629 | 0.0081629 | 0.0081629 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 0 | 3.5538 | 3.5512 | 3.5491 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0.0084123 | 0.008401 | 0.0083802 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0.35618 | 0.35561 | 0.35453 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0.0081629 | 0.0081629 | 0.0081629 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 2.5339 | 2.5273 | 2.518 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0.75926 | 0.74806 | 0.73863 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0.068688 | 0.068688 | 0.068688 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0.37462 | 0.37462 | 0.37462 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0.5265 | 0.5265 | 0.5265 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0.6775 | 0.6775 | 0.6775 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0.30347 | 0.30347 | 0.30347 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0.0081629 | 0.0081629 | 0.0081629 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions

## Table 7
| Utility | Southern California Edison
| Table No. | 7
| Date Modified | 2024-05-01
[7 empty] | Actual | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q1
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 3469 | 3552 | 3552 | 3552 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 12935 | 12996 | 12996.04 | 12996.04 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 2797 | 2843 | 2843.17 | 2843.17 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 6404 | 6464 | 6464 | 6464 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 472 | 473 | 473 | 473 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 2304 | 2331 | 2331 | 2331 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 584 | 589.01 | 590.16 | 590.16 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 397 | 406 | 406.15 | 406.15 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 1046 | 1059.06 | 1061.11 | 1061.11 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 813 | 828 | 831.01 | 831.01 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 226 | 222 | 222 | 222 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 794 | 802 | 802 | 802 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 754 | 760.05 | 760.33 | 760.33 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 165 | 168 | 168 | 168 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 2592 | 2609.66 | 2626.11 | 2626.11 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 1569 | 1600 | 1602.69 | 1602.69 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 149 | 148 | 148 | 148 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 350 | 358 | 358 | 358 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 469 | 509 | 509 | 509 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 2668 | 2770 | 2770 | 2770 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 269 | 276 | 276 | 276 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 2282 | 2377 | 2377 | 2377 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 37 | 38 | 38 | 38 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 2007 | 2040 | 2040 | 2040 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 197 | 195 | 195 | 195 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 219 | 217 | 217 | 217 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 257 | 253 | 253 | 253 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 728 | 723 | 723 | 723 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 33 | 32 | 32 | 32 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 556 | 553 | 553 | 553 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 237 | 236 | 236 | 236 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 201 | 202 | 202 | 202 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 423 | 420 | 420 | 420 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 1266 | 1267 | 1267 | 1267 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 22 | 22 | 22 | 22 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 1. Overhead circuit miles | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 249 | 250 | 250 | 250 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 6226 | 6451 | 6451 | 6451 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 13332 | 13353 | 13353 | 13353 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 1611 | 1684 | 1684.04 | 1684.04 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 2296 | 2287 | 2287 | 2287 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 58 | 58 | 58 | 58 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 249 | 254 | 254 | 254 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 1157 | 1143.79 | 1147.09 | 1147.09 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 634 | 635 | 635.23 | 635.23 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 748 | 736.37 | 741.18 | 741.18 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 316 | 297 | 310.74 | 310.74 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 36 | 37 | 37 | 37 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 109 | 109 | 109 | 109 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 1895 | 1885.09 | 1892.45 | 1892.45 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 283 | 280.13 | 280.22 | 280.22 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 1616 | 1598.27 | 1668.95 | 1668.95 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 442 | 429.05 | 451.91 | 451.91 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 15 | 14 | 14 | 14 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 61 | 61 | 61 | 61 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 15 | 15 | 15 | 15 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 219 | 211 | 211 | 211 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 1 | 1 | 1 | 1 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 37 | 35 | 35 | 35 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 19 | 19 | 19 | 19 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 7 | 5 | 5 | 5 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 6 | 7 | 7 | 7 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 1 | 2 | 2 | 2 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 5 | 6 | 6 | 6 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 11 | 12 | 12 | 12 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 9 | 9 | 9 | 9 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 7 | 9 | 9 | 9 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 9 | 8 | 8 | 8 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 2. Underground circuit miles | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 7840 | 8337 | 8337 | 8337 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 32117 | 34949 | 34949 | 34949 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 2476 | 2494 | 2494 | 2494 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 5072 | 4920 | 4920 | 4920 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 197 | 195 | 195 | 195 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 917 | 907 | 907 | 907 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 1250 | 1284 | 1284 | 1284 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 1056 | 1075 | 1075 | 1075 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 1036 | 1036 | 1036 | 1036 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 622 | 656 | 656 | 656 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 156 | 150 | 150 | 150 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 365 | 371 | 371 | 371 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 2699 | 2794 | 2794 | 2794 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 561 | 810 | 810 | 810 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 2971 | 3002 | 3002 | 3002 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 1337 | 1349 | 1349 | 1349 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 165 | 164 | 164 | 164 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 3. Critical facilities | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 203 | 225 | 225 | 225 | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 859949 | 845308 | 845308 | 845308 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 2706840 | 2660413 | 2660413 | 2660413 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 172931 | 170607 | 170607 | 170607 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 88957 | 84981 | 84981 | 84981 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 8345 | 8441 | 8441 | 8441 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 3748 | 3747 | 3747 | 3747 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 109400 | 107185 | 107185 | 107185 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 52298 | 51117 | 51117 | 51117 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 69422 | 67095 | 67095 | 67095 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 10921 | 9331 | 9331 | 9331 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 5538 | 5270 | 5270 | 5270 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 2298 | 2353 | 2353 | 2353 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 228942 | 225712 | 225712 | 225712 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 8190 | 7586 | 7586 | 7586 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 145083 | 143222 | 143222 | 143222 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 9026 | 8436 | 8436 | 8436 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 6106 | 5955 | 5955 | 5955 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 4. Residential customers | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 866 | 838 | 838 | 838 | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | 67543 | 66760 | 66760 | 66760 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 400907 | 398376 | 398376 | 398376 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | 14421 | 14345 | 14345 | 14345 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 46185 | 45861 | 45861 | 45861 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 788 | 809 | 809 | 809 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 2515 | 2438 | 2438 | 2438 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 7097 | 6974 | 6974 | 6974 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 6113 | 5929 | 5929 | 5929 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 4809 | 4667 | 4667 | 4667 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 2474 | 2399 | 2399 | 2399 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 610 | 581 | 581 | 581 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 1006 | 1029 | 1029 | 1029 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 21059 | 20823 | 20823 | 20823 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 8374 | 8464 | 8464 | 8464 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 13153 | 12968 | 12968 | 12968 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 6551 | 6472 | 6472 | 6472 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 576 | 571 | 571 | 571 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 5. Commercial customers | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 540 | 553 | 553 | 553 | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | 308682 | 299920 | 299920 | 299920 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 1072817 | 1034683 | 1034683 | 1034683 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | 61237 | 60847 | 60847 | 60847 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 35582 | 34044 | 34044 | 34044 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 2765 | 2768 | 2768 | 2768 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 1050 | 1083 | 1083 | 1083 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 26613 | 25441 | 25441 | 25441 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 9138 | 9042 | 9042 | 9042 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 17324 | 17107 | 17107 | 17107 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 2246 | 1892 | 1892 | 1892 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 922 | 917 | 917 | 917 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 514 | 539 | 539 | 539 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 46351 | 45392 | 45392 | 45392 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 1619 | 1520 | 1520 | 1520 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 26729 | 27152 | 27152 | 27152 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 1726 | 1673 | 1673 | 1673 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 1602 | 1703 | 1703 | 1703 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 6. AFN customers | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 197 | 214 | 214 | 214 | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | 65 | 63 | 63 | 63 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 378 | 374 | 374 | 374 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | 21 | 21 | 21 | 21 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 219 | 218 | 218 | 218 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 6 | 6 | 6 | 6 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 107 | 103 | 103 | 103 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 11 | 12 | 12 | 12 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 14 | 13 | 13 | 13 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 11 | 10 | 10 | 10 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 38 | 37 | 37 | 37 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 5 | 5 | 5 | 5 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 31 | 29 | 29 | 29 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 15 | 15 | 15 | 15 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 8 | 8 | 8 | 8 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 23 | 23 | 23 | 23 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 38 | 38 | 38 | 38 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 1 | 1 | 1 | 1 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 7. Substations | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 5 | 5 | 5 | 5 | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | 12 | 11 | 11 | 11 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 11 | 14 | 14 | 14 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | 24 | 22 | 22 | 22 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 14 | 15 | 15 | 15 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 9 | 9 | 9 | 9 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 122 | 111 | 111 | 111 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 93 | 88 | 88 | 88 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 134 | 129 | 129 | 129 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 181 | 168 | 168 | 168 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 25 | 23 | 23 | 23 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 136 | 120 | 120 | 120 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 131 | 128 | 128 | 128 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 57 | 52 | 52 | 52 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 349 | 339 | 339 | 339 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 371 | 342 | 342 | 342 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 14 | 13 | 13 | 13 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.
| 8. Weather stations | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 70 | 63 | 63 | 63 | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete.

## Table 8
| Utility | Southern California Edison | Notes:
| Table No. | 8 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2024-05-01
[7 empty] | Actual | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q1
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 3 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | -7 | 0 | 0.04 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 1 | 0 | 0.17 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 4 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 1 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 | 0.01 | 1.15 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | -1 | 0 | 0.15 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | -4 | 0.06 | 2.05 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | -7 | 0 | 3.01 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 1 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | -5 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | -3 | 0.05 | 0.28 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | -2 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | -10 | 0.66 | 16.45 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | -15 | 0 | 2.69 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | -1 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | -1 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | -2 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | -1 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 1 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Planned net addition (or removal) - overhead circuit miles | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 8 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 13 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 5 | 0 | 0.04 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 2 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 1 | 0.79 | 3.3 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0.23 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 2 | 0.37 | 4.81 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 3 | 0 | 13.74 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 1 | 0.09 | 7.36 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0.13 | 0.09 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 3 | 7.27 | 70.68 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 1 | 2.05 | 22.86 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 2 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 1 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 1 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 1 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Planned net addition (or removal) - underground circuit miles | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 1 | 0 | -1 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 4 | -3 | 0 | -4 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 3 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | -1 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 1 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 2 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 1 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Planned net addition (or removal) - Substations | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | -1 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 2 |  |  | 11 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  | 8 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 1 |  |  | 6 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 3 |  |  | 25 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 |  |  | 2 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  | 22 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  | 9 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 1 |  |  | 1 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 1 |  |  | 16 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 3 |  |  | 62 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  | 0 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 4. Planned net addition (or removal) - Weather stations | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  | 7 | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.

## Table 9
| Utility | Southern California Edison
| Table No. | 9
| Date Modified | 2024-05-01
[7 empty] | Actual | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q1
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0 | 2.6 | 19.08 | 1.92 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0 | 1.2 | 78.65 | 87.22 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0 | 0 | 3.99 | 0.35 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0 | 0 | 5.34 | 0.04 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | 0.12 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 | 2.93 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 | 0.14 | 6.58 | 0.01 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0.09 | 0.25 | 3.25 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 0 | 0 | 1.32 | 2.33 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0.68 | 0.1 | 0.24 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0.31 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | 0 | 4.47 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
| 1. Number of overhead circuit miles planned for upgrade | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability. | Metric not tracked/availabe at this time.
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | 1 | 12 | 14 | 7 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 2 | 48 | 34 | 23 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | 3 | 1 | 1 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 1 | 13 | 6 | 6 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 1 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 4 | 5 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 1 | 1 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 1 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 2 | 1 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 1 | 5 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 4 | 3 | 2 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 1 | 0 | 1 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 1 | 0 | 2 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 3 | 2 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 2. Number of substations planned for upgrades | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 2 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 2 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 1 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 1 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 3 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.
| 3. Number of weather stations planned for upgrades | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. Furthermore, projections are subject to change due to operating constraints, changes in priority, and resource availability.

## Table 10
Utility | Southern California Edison | Notes:
Table No. | 10 | "PSPS" = Public Safety Power Shutoff. In future submissions update planned upgrade numbers with actuals
Date Modified | 2024-05-01
|  |  |  | Actual | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q1
Metric type | # | Wind Warning Status | Metric name | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | 0 |  |  |  | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.a. | HWW only | Frequency of PSPS events (total) | 0 |  |  |  | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.a. | HWW & RFW | Frequency of PSPS events (total) | 0 |  |  |  | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.a. | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | 0 | 7 | 7 | 7 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | SCE does not forecast a reduction in events from the 2020-2022 quarterly average as overall circuit scope reduction may not reduce event count. SCE does not forecast based on wind warning status.
| 1.b. | RFW only | Scope of PSPS events (total) | 0 |  |  |  | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two.
| 1.b. | HWW only | Scope of PSPS events (total) | 0 |  |  |  | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two.
| 1.b. | HWW & RFW | Scope of PSPS events (total) | 0 |  |  |  | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two.
| 1.b. | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | 0 | 225 | 212 | 199 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. SCE does not forecast based on wind warning status.
| 1.c. | RFW only | Duration of PSPS events (total) | 0 |  |  |  | Customer hours per year
| 1.c. | HWW only | Duration of PSPS events (total) | 0 |  |  |  | Customer hours per year
| 1.c. | HWW & RFW | Duration of PSPS events (total) | 0 |  |  |  | Customer hours per year
| 1.c. | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | 0 | 2516572 | 2290080 | 2083972 | Customer hours per year | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. SCE does not forecast based on wind warning status.
| 1.d. | RFW only | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. An update to the logic was done in Q1 of 2023 to better align outage data with Fast Curve enabled circuit days. Slight adjustment made to align 2022 with 2023 logic
| 1.d. | HWW only | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. An update to the logic was done in Q1 of 2023 to better align outage data with Fast Curve enabled circuit days. Slight adjustment made to align 2022 with 2023 logic
| 1.d. | HWW & RFW | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. An update to the logic was done in Q1 of 2023 to better align outage data with Fast Curve enabled circuit days. Slight adjustment made to align 2022 with 2023 logic
| 1.d. | None | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. An update to the logic was done in Q1 of 2023 to better align outage data with Fast Curve enabled circuit days. Slight adjustment made to align 2022 with 2023 logic
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days | A discrepancy in the datetime format created additional counts that created a large discrepancy in Ckt Mile Days. This was fixed with the most recent data collection and 2022 numbers were adjusted.
| 1.e | HWW only | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days | A discrepancy in the datetime format created additional counts that created a large discrepancy in Ckt Mile Days. This was fixed with the most recent data collection and 2022 numbers were adjusted.
| 1.e | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days | A discrepancy in the datetime format created additional counts that created a large discrepancy in Ckt Mile Days. This was fixed with the most recent data collection and 2022 numbers were adjusted.
| 1.e | None | Circuit mile days with fast-trip settings enabled (total) | 20986 |  |  |  | Circuit mile days | A discrepancy in the datetime format created additional counts that created a large discrepancy in Ckt Mile Days. This was fixed with the most recent data collection and 2022 numbers were adjusted.
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | 4617645.8167 |  |  |  | Total customer hours of planned outages per year | Customer Hours of Interruption for Planned Outages (Customers interrupted multiplied by Hours of Interruption). Antcipate data related to planned outages will change as SCE finishes an enhancement project to improve planned outage reporting.
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | 2240104.59 |  |  |  | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | 0 |  |  |  | Total customer hours of outages due to fast-trip per year | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. Customer hours are customer hours of interruption (customers multiplied by their duration)
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | 25.432 |  |  |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Includes both planned and unplanned outages. No PSPS events for this period. March data validations for unplanned interruptions are in progress, so data is subject to change. Antcipate data related to planned outages will change as SCE finsihes an enhancement project to improve planned outage reporting.
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | 25.432 |  |  |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Includes both planned and unplanned outages. No PSPS events for this period. March data validations for unplanned interruptions are in progress, so data is subject to change. Antcipate data related to planned outages will change as SCE finsihes an enhancement project to improve planned outage reporting.
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | 0.22496 |  |  |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Includes both planned and unplanned outages. No PSPS events for this period. March data validations for unplanned interruptions are in progress, so data is subject to change. Antcipate data related to planned outages will change as SCE finsihes an enhancement project to improve planned outage reporting.
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | 0.22496 |  |  |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Includes both planned and unplanned outages. No PSPS events for this period. March data validations for unplanned interruptions are in progress, so data is subject to change. Antcipate data related to planned outages will change as SCE finsihes an enhancement
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | 0 |  |  |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year | This number is the total number of Critical Infrastructure customers impacted (de-energized) by a PSPS event
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | 0 | 126361 | 107408 | 91297 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. SCE does not forecast based on wind warning status.
| 4.b. | N/A | # of medical baseline customers impacted by PSPS | 0 |  |  |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.c. | N/A | # of customers notified prior to initiation of PSPS event | 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | This number is the total number of customers in-scope for a potential PSPS de-energization.
| 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | This number is the total number of MBL customers in-scope for a potential PSPS de-energization.
| 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | This number is the total number of customers impacted (de-energized) by a PSPS event. NOTE: This is a subset number of K40.
| 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | This number is the total number of MBL customers impacted (de-energized) by a PSPS event. NOTE: This is a subset number of K41.
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | 0 |  |  |  | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | 0 |  |  |  | Number of customers | Sum total of all de-energized customers for each outage incident / total number of outage incidents.
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | 0 |  |  |  | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | 0 |  |  |  | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | 0 |  |  |  | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours | De-en to prep-to-restore time (=MEDIAN,[ARRAY])
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours | De-en to prep-to-restore time (=PERCENTILE.INC,[ARRAY])
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. Median time of entire outage durations instead of inspection on circuit-segment
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. 95th percentile of entire outage durations instead of inspection on circuit-segment. 5% of durations are above value
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | 0 |  |  |  | Number of risk events

## Table 11
Utility | Southern California Edison | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2024-05-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actuals |  |  |  | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compliance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2024 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Community Outreach and Engagement | Public outreach and education awareness program | DEP-1.2, DEP-4 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.5.2 of SCE's 2023-2025 WMP | Please refer to section 8.5.2 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 14920.5266 | 14920.5266 | 0 | 0 | 14581.2015 | 14581.2015 | 0 | 0 | 14701.0467 | 14701.0467
Community Outreach and Engagement | Engagement with access and functional needs populations | 8.5.3 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.5.3 of SCE's 2023-2025 WMP | Please refer to section 8.5.3 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 2010.1689 | 2010.1689 | 0 | 0 | 2048.8315 | 2048.8315 | 0 | 0 | 2088.5971 | 2088.5971
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning | 8.5.4 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.5.4 of SCE's 2023-2025 WMP | Please refer to section 8.5.4 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts related to collaboration efforts for local wildfire mitigation planning are addressed as part of sections 8.4.4 (Public emergency communication strategy) and 8.4.5 (Preparedness and planning for service restoration)
Community Outreach and Engagement | Best practice sharing with other utilities | 8.5.5 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.5.5 of SCE's 2023-2025 WMP | Please refer to section 8.5.5 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecast for Best practice sharing with other utilities is incorporated in wildfire activities related to risk and asset management, vegetation management, and operations & protocols. Section 8.5.5 of the WMP discusses several ways in which SCE collaborates with other utilities.
Emergency Preparedness | Emergency preparedness plan | DEP-2 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.4.2 of SCE's 2023-2025 WMP | Please refer to section 8.4.2 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 15626.645 | 15626.645 | 0 | 0 | 13069.4328 | 13069.4328 | 0 | 0 | 13877.2942 | 13877.2942
Emergency Preparedness | External collaboration and coordination | DEP-5 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2020 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.4.3 of SCE's 2023-2025 WMP | Please refer to section 8.4.3 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 35000 | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0 | 35000 | 35000
Emergency Preparedness | Public emergency communication strategy | 8.4.4 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.4.4 of SCE's 2023-2025 WMP | Please refer to section 8.4.4 of SCE's 2023-2025 WMP | [6 empty] | 12101.0472 | 12101.0472 | 6530.528 | 6530.528 | 6502.7064 | 6502.7064 | 6580.523 | 6580.523 | 4060.9564 | 4060.9564 | 4954.923 | 4954.923
Emergency Preparedness | Preparedness and planning for service restoration | 8.4.5 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.4.5 of SCE's 2023-2025 WMP | Please refer to section 8.4.5 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 7472.8467 | 7472.8467 | 0 | 0 | 7698.2861 | 7698.2861 | 0 | 0 | 8121.5813 | 8121.5813
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | PSPS-2, PSPS-3 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.4.6 of SCE's 2023-2025 WMP | Please refer to section 8.4.6 of SCE's 2023-2025 WMP | [6 empty] | 5402.5095 | 5402.5095 | 29284.2712 | 29284.2712 | 203.2096 | 203.2096 | 25479.2155 | 25479.2155 | 609.1435 | 609.1435 | 27719.0639 | 27719.0639
Grid Design, Operations, and Maintenance | Covered conductor installation | SH-1, SH-14, SH-16 | Wire-to-wire contact | Contact from object | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.1 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.1 of SCE's 2023-2025 WMP | [6 empty] | 897276.4647 | 897276.4647 | 857.0888 | 857.0888 | 782097.8098 | 782097.8098 | 872.6131 | 872.6131 | 490219.3344 | 490219.3344 | 898.6881 | 898.6881
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | SH-5, SH-6, SH-15 | Equipment failure | Contact from object | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.10 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.10 of SCE's 2023-2025 WMP | [6 empty] | 7789.464 | 7789.464 | 6587.8019 | 6587.8019 | 4531.5688 | 4531.5688 | 1859.3015 | 1859.3015 | 9306.6221 | 9306.6221 | 1676.5649 | 1676.5649
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | SH-4, SH-6, SH-14 | Equipment failure | Wire-to-wire contact | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.11 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.11 of SCE's 2023-2025 WMP | [6 empty] | 4540.6995 | 4540.6995 | 3396.9985 | 3396.9985 | 4896.7466 | 4896.7466 | 4009.3694 | 4009.3694 | 4376.3478 | 4376.3478 | 4122.772 | 4122.772
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | 8.1.2.12 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.12 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.12 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for new and alternate technologies is included under costs related to Grid Design, Operations, and Maintenance, and Situational Awareness and Forecasting.
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | SH-2 | Contact from object | Wire-to-wire contact | 2019 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.2 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.2 of SCE's 2023-2025 WMP | [6 empty] | 27962.4622 | 27962.4622 | 1340.5609 | 1340.5609 | 60897.0168 | 60897.0168 | 0 | 0 | 317077.8319 | 317077.8319 | 0 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | 8.1.2.3 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.3 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.3 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SCE’s Pole Loading Program was completed in 2021. See Q4 2023 QDR non-spatial table for costs incurred in 2021. Poles are also replaced as part of SCE’s HFRI inspections and maintenance programs.
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | 8.1.2.4 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.4 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.4 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Transmission pole/tower replacements and reinforcements is included in IN-1.2 (Asset inspections and Equipment inspections, maintenance, and repair).
Grid Design, Operations, and Maintenance | Traditional overhead hardening | SH-10 | Contact from object | Wire-to-wire contact | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.5 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.5 of SCE's 2023-2025 WMP | [6 empty] | 16696.7356 | 16696.7356 | 0 | 0 | 18202.4373 | 18202.4373 | 0 | 0 | 10569.5167 | 10569.5167 | 0 | 0
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots | SH-17, SH-18 | Contact from object | Equipment failure | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.6 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.6 of SCE's 2023-2025 WMP | [6 empty] | 21175.7675 | 21175.7675 | 250 | 250 | 35878.1592 | 35878.1592 | 350 | 350 | 45796.0702 | 45796.0702 | 500 | 500
Grid Design, Operations, and Maintenance | Microgrids | SH-12 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2020 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.7 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.7 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SCE does not have a forecast for Microgrids. See chapter narrative, section 8.1.2.7.1, for further discussion.
Grid Design, Operations, and Maintenance | Installation of system automation equipment | 8.1.2.8 | Contact from object | Equipment failure | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.8 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.8 of SCE's 2023-2025 WMP | [6 empty] | 2583.6406 | 0 | 0 | 0 | 2629.6186 | 0 | 0 | 0 | 1529.5106 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Line removals (in HFTD) | 8.1.2.9 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.2.9 of SCE's 2023-2025 WMP | Please refer to section 8.1.2.9 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 129.7392 | 129.7392 | 0 | 0 | 130.2861 | 130.2861 | 0 | 0 | 166.0583 | 166.0583
Grid Design, Operations, and Maintenance | Asset inspections | IN-1.1, IN-1.2, IN-3, IN-4, IN-9 | Equipment failure | Contact from object | 2017 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.3.1 of SCE's 2023-2025 WMP | Please refer to section 8.1.3.1 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 137845.6705 | 53662.3654 | 0 | 0 | 139889.3929 | 52339.767 | 0 | 0 | 142187.4789 | 53875.9847
Grid Design, Operations, and Maintenance | Equipment inspections, maintenance, and repair | IN-1.1, IN-1.2, IN-5, IN-9 | Equipment failure | Contact from object | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.4 of SCE's 2023-2025 WMP | Please refer to section 8.1.4 of SCE's 2023-2025 WMP | [6 empty] | 734673.7227 | 121075.7227 | 210811.869 | 80004.869 | 600075.8138 | 136992.8138 | 219371.0786 | 84009.0786 | 448019.981 | 135864.981 | 92200.8908 | 86124.8908
Grid Design, Operations, and Maintenance | Asset management and inspection enterprise system(s) | DG-1, IN-8 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2021 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.5 of SCE's 2023-2025 WMP | Please refer to section 8.1.5 of SCE's 2023-2025 WMP | [6 empty] | 15845.791 | 15845.791 | 6389.3436 | 6389.3436 | 9909.6095 | 9909.6095 | 5845.3828 | 5845.3828 | 4824.648 | 4824.648 | 5924.5923 | 5924.5923
Grid Design, Operations, and Maintenance | Quality assurance / quality control | 8.1.6 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.6 of SCE's 2023-2025 WMP | Please refer to section 8.1.6 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Quality assurance and quality control is included in various WMP activities.
Grid Design, Operations, and Maintenance | Open work orders | 8.1.7 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.7 of SCE's 2023-2025 WMP | Please refer to section 8.1.7 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Costs for open work orders are included in the various initiative activities of Grid Design, Operations, and Maintenance
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops) | 8.1.8.1 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.8.1 of SCE's 2023-2025 WMP | Please refer to section 8.1.8.1 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fast Curve settings on devices such as the Remote Automatic Reclosers (RARs) (SH-5) and substation circuit breaker relays (SH-6) are addressed as part of Other Grid Topology Improvements. Budget associated with High Impedance Relay Evaluation (Hi-Z), Transmission Open Phase Detection (TOPD), and Distribution Open Phase Detection (DOPD) are addressed as part of Grid Monitoring Systems.
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops) | 8.1.8.2 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.8.2 of SCE's 2023-2025 WMP | Please refer to section 8.1.8.2 of SCE's 2023-2025 WMP | [6 empty] | 3246.2032 | 3246.2032 | 0 | 0 | 956.0878 | 956.0878 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) | 8.1.8.3 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.8.3 of SCE's 2023-2025 WMP | Please refer to section 8.1.8.3 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) is addressed as part of Emergency Preparedness (DEP-2)
Grid Design, Operations, and Maintenance | Workforce Planning | 8.1.9 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.1.9 of SCE's 2023-2025 WMP | Please refer to section 8.1.9 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SCE incurred workforce planning related costs in 2022 and 2023.
Overview of the Service Territory | Environmental compliance and permitting | 5.4.5 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 5.4.5 of SCE's 2023-2025 WMP | Please refer to section 5.4.5 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 41410.1563 | 41410.1563 | 0 | 0 | 46341.3738 | 46341.3738 | 0 | 0 | 48402.2851 | 48402.2851
Risk Methodology and Assessment | Risk Methodology and Assessment | 6 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 6 of SCE's 2023-2025 WMP | Please refer to section 6 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.2664 | 137.2664
Situational Awareness and Forecasting | Environmental monitoring systems | SA-1, SA-8 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.3.2 of SCE's 2023-2025 WMP | Please refer to section 8.3.2 of SCE's 2023-2025 WMP | [6 empty] | 6736.688 | 6736.688 | 8351.7318 | 8351.7318 | 1171.3343 | 1171.3343 | 9718.7062 | 9718.7062 | 447.9127 | 447.9127 | 11541.6158 | 11541.6158
Situational Awareness and Forecasting | Grid monitoring systems | SA-11, SH-8 | Equipment failure for SH-8 | Vandalism / Theft for SH-8 | 2019 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.3.3 of SCE's 2023-2025 WMP | Please refer to section 8.3.3 of SCE's 2023-2025 WMP | [6 empty] | 3527.9507 | 3527.9507 | 1489.6 | 1489.6 | 3521.5051 | 3521.5051 | 1327.1 | 1327.1 | 14758.104 | 14758.104 | 853.2 | 853.2
Situational Awareness and Forecasting | Ignition detection systems | SA-8, SA-10 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2019 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.3.4 of SCE's 2023-2025 WMP | Please refer to section 8.3.4 of SCE's 2023-2025 WMP | [6 empty] | 263.656 | 263.656 | 5237.556 | 5237.556 | 131 | 131 | 5724.087 | 5724.087 | 0 | 0 | 5775.965 | 5775.965
Situational Awareness and Forecasting | Weather forecasting | SA-3 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.3.5 of SCE's 2023-2025 WMP | Please refer to section 8.3.5 of SCE's 2023-2025 WMP | [6 empty] | 703.598 | 703.598 | 6220.982 | 6220.982 | 0 | 0 | 5951.601 | 5951.601 | 2500 | 2500 | 5826.691 | 5826.691
Situational Awareness and Forecasting | Fire potential index | 8.3.6 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.3.6 of SCE's 2023-2025 WMP | Please refer to section 8.3.6 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for fire potential index is included in SA-3 (weather forecasting)
Vegetation Management and Inspection | Vegetation Inspections | VM-1, VM-9, VM-10 | Contact with vegetation |  | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.2.1 of SCE's 2023-2025 WMP | Please refer to section 8.2.2.1 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 81105.7039 | 60840.0537 | 0 | 0 | 91986.2131 | 68746.8203 | 0 | 0 | 150184.8399 | 123363.3566
Vegetation Management and Inspection | Pole clearing | VM-2 | Equipment failure |  | 2019 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.1 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.1 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 23852.1798 | 23852.1798 | 0 | 0 | 25915.3922 | 25915.3922 | 0 | 0 | 26196.7627 | 26196.7627
Vegetation Management and Inspection | Wood and slash management | 8.2.3.2 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.2 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.2 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for Wood and slash management activities are incorporated into vegetation management activities, and therefore relates to VM-1, VM-2, VM-3, VM-4, VM-7, and VM-8
Vegetation Management and Inspection | Clearance | VM-1, VM-3, VM-4, VM-7, VM-8 | Contact with vegetation |  | 2018 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.3 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.3 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 418435.4697 | 289597.6914 | 0 | 0 | 450423.5052 | 315842.873 | 0 | 0 | 458472.9447 | 319116.2262
Vegetation Management and Inspection | Fall-in mitigation | 8.2.3.4 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.4 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.4 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for Fall-in mitigation efforts are addressed as part of HTMP and therefore relates to VM-1
Vegetation Management and Inspection | Substation defensible space | 8.2.3.5 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.5 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.5 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for Substation defensible space are included in Clearance.
Vegetation Management and Inspection | High-risk species | 8.2.3.6 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.6 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.6 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for High-risk species are addressed through HTMP (VM-1) initiative and/or routine line clearing (VM-7 and VM-8) activities.
Vegetation Management and Inspection | Fire-resilient right-of-ways | 8.2.3.7 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.7 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.7 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 3786.252 | 2416.829 | 0 | 0 | 4070.203 | 2598.0798 | 0 | 0 | 4599.005 | 2935.6231
Vegetation Management and Inspection | Emergency response vegetation management | 8.2.3.8 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.3.8 of SCE's 2023-2025 WMP | Please refer to section 8.2.3.8 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for Emergency response vegetation management activities are addressed through inspection and line clearing programs, and therefore, relates to VM-7 and VM-8. Post-fire vegetation management activities are in response to fires which occur unexpectedly and is therefore not a planned fire mitigation initiative with forecasted scope.
Vegetation Management and Inspection | Vegetation management enterprise system | VM-6 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | 2021 | 2021 GRC | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.4 of SCE's 2023-2025 WMP | Please refer to section 8.2.4 of SCE's 2023-2025 WMP | [6 empty] | 2602.5663 | 2602.5663 | 3800.122 | 3800.122 | 2746.924 | 2746.924 | 4000.0344 | 4000.0344 | 2436.5738 | 2436.5738 | 4200 | 4200
Vegetation Management and Inspection | Quality assurance / quality control | 8.2.5 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.5 of SCE's 2023-2025 WMP | Please refer to section 8.2.5 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 10828.1436 | 10828.1436 | 0 | 0 | 11808.8854 | 11808.8854 | 0 | 0 | 12686.8561 | 12686.8561
Vegetation Management and Inspection | Open work orders | 8.2.6 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.6 of SCE's 2023-2025 WMP | Please refer to section 8.2.6 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Costs for open work orders are included in the various initiative activities of vegetation management and inspection
Vegetation Management and Inspection | Workforce Planning | 8.2.7 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 8.2.7 of SCE's 2023-2025 WMP | Please refer to section 8.2.7 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMP cost forecasts for Workforce planning (i.e., employee retention and upskilling) is incorporated into each vegetation management initiative and is therefore broadly addressed in all areas of vegetation management and inspection.
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | 7 | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. | Driver Targeted fields left blank as the activity 1) impacts wildfire or PSPS risk consequences, and not risk drivers or 2) is not a wildfire risk mitigation activity or 3) does not directly reduce wildfire risk and is considered a foundational item. |  |  | CPUC-approved memorandum accounts will be used to track costs for this activity to the extent SCE records costs above GRC authorized levels, pursuant to SCE’s incrementality methodology | Please refer to section 7 of SCE's 2023-2025 WMP | Please refer to section 7 of SCE's 2023-2025 WMP | [6 empty] | 0 | 0 | 5540.397 | 5540.397 | 0 | 0 | 5012.0099 | 5012.0099 | 0 | 0 | 4252.6215 | 4252.6215

## Table 12
Utility | Southern California Edison | Notes:
Table No. | 12
Date Modified | 2024-05-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | Method of Verification | Comments
Community Outreach and Engagement | Public Outreach and Education Awareness Program | DEP-1 | Quantitative | # of meetings | 4 | 4 | SCE will host at least four wildfire community safety meetings by region in targeted HFRA communities based on the impact of 2022 PSPS events and ongoing wildfire mitigation activities | No mid-year target | No mid-year target | Continue or revise – determined based on the outcome of 2023 |  |  | Continue or revise – determined based on the outcome of 2023-2024 | Link to the SCE.com site for meeting conducted and recordings posted | Items in RED were updated based on OEIS decision on 2024 proposed target updates issued on 5/31/24
Emergency Preparedness | Emergency Preparedness Plan | DEP-2 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | PSPS response teams are fully qualified/requalified by 7/1 annually to maintain readiness | No mid-year target | No mid-year target | PSPS response teams are fully qualified/requalified by 7/1 annually to maintain readiness |  |  | PSPS response teams are fully qualified/requalified by 7/1 annually to maintain readiness | IMT training roster
Community Outreach and Engagement | Public Outreach and Education Awareness Program | DEP-4 | Quantitative | # of surveys | 1 | 3 | SCE plans to conduct at least five PSPS‐related customer studies in 2023 | 1 | 1 | SCE plans to conduct at least three PSPS‐related customer studies in 2024 |  |  | SCE plans to conduct at least three PSPS‐related customer studies in 2025 | Detailed list of surveys with supporting information
Emergency Preparedness | External Collaboration and Coordination | DEP-5 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | Provide fire agencies with funding to support quick reaction force (QRF) program for 2023 | No mid-year target | No mid-year target | SCE will continue to reassess availability and funding for aerial suppression resources in SCE’s service area annually to determine ongoing QRF strategy |  |  | SCE will continue to reassess availability and funding for aerial suppression resources in SCE’s service area annually to determine ongoing QRF strategy | Copy of funding agreement | Items in RED were updated based on OEIS decision on 2024 proposed target updates issued on 5/31/24
Grid Design, Operations, and Maintenance | Asset inspections | IN-1.1 | Quantitative | # of structures in HFRA | 101320 | 172640 | Inspect 187,000 structures in HFRA | 101320 | 172640 | Inspect 187,000 structures in HFRA |  |  | Inspect 187,000 structures in HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Asset inspections | IN-1.2 | Quantitative | # of structures in HFRA | 14400 | 25800 | Inspect 28,000 structures in HFRA | 14440 | 25800 | Inspect 28,000 structures in HFRA |  |  | Inspect 28,000 structures in HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Asset inspections | IN-3 | Quantitative | # of distribution circuit miles in HFRA | 2295 | 5300** | Inspect 5,300** distribution overhead circuit miles in HFRA | 2295 | 5300** | Inspect 5,300 distribution overhead circuit miles in HFRA** |  |  | Inspect 5,300 distribution overhead circuit miles in HFRA** | Listing of completed work orders | Information marked with an ** denotes changes from the WMP filing that were submitted in the Errata dated April 6, 2023
Grid Design, Operations, and Maintenance | Asset inspections | IN-4 | Quantitative | # of transmission circuit miles in HFRA | 600 | 900 | Inspect 1,000 transmission overhead circuit miles in HFRA | 600 | 900 | Inspect 1,000 transmission overhead circuit miles in HFRA |  |  | Inspect 1,000 transmission overhead circuit miles in HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Asset inspections | IN-5 | Quantitative | # of structures in HFRA | 55 | 170 | Inspect 170 generation related assets in HFRA | 52 | 160 | Inspect 160 generation related assets in HFRA |  |  | Inspect 170 generation related assets in HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System(s) | IN-8 | Qualitative | Qualitative Initiative | Develop use cases to use In build of Proof of Concept (POC) to prove out design direction** | Develop POC of key design elements to validate design direction** | Complete detailed design to migrate the distribution ground inspection application to the single digital platform** | Conduct requirements gathering for incorporating distribution ground and InspectCam capabilities in single digital platform | Initiate solution analysis for incorporating distribution ground and InspectCam capabilities in single digital platform | Execute the approved designs / recommendations for incorporating distribution ground and InspectCam capabilities into single digital platform |  |  | Monitor utilization of inspection work management tool, and make enhancements as necessary | Completed user acceptance testing, screenshots of tool enhancements | Information marked with an ** denotes changes from the WMP filing that were submitted in the Errata dated April 6, 2023
Grid Design, Operation, and Maintenance | Asset inspections | IN-9 | Quantitative | # Spans/splices | Line Vue: 30 X-Ray: 30 | Line Vue: 45 X-Ray: 45 | Will inspect 50 spans with Line Vue Will inspect 50 splices with X-Ray | Line Vue: 20 X-Ray: 35 | Line Vue: 25 X-Ray: 50 | Will inspect 25 spans with Line Vue Will inspect 50 splices with X-Ray |  |  | Target to be developed based on an engineering analysis to be performed in 2023 and 2024 | Listing of completed work orders | Items in RED were updated based on OEIS decision on 2024 proposed target updates issued on 5/31/24
Emergency Preparedness | Customer Support in Wildfire and PSPS Emergencies | PSPS-2 | Quantitative | % of batteries delivered | No mid-year target | No mid-year target | Complete 85% of battery deliveries to eligible customers within 30 calendar days* of program enrollment, subject to customer availability, reschedule requests and battery supply constraints * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day | No mid-year target | No mid-year target | Complete 85% of battery deliveries to eligible customers within 30 calendar days* of program enrollment, subject to customer availability, reschedule requests and battery supply constraints * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day |  |  | Complete 85% of battery deliveries to eligible customers within 30 calendar days* of program enrollment, subject to customer availability, reschedule requests and battery supply constraints * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day | Year to date list of customer enrollment and battery deliveries
Emergency Preparedness | Customer Support in Wildfire and PSPS Emergencies | PSPS-3 | Quantitative | % of rebates processed | No mid-year target | No mid-year target | Process 85% of all rebate claims within 30 business days* of receipt from website vendor; excluding website related delays and subject to receiving all required customer information * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day measurement | No mid-year target | No mid-year target | Process 85% of all rebate claims within 30 business days* of receipt from website vendor; excluding website related delays and subject to receiving all required customer information * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day measurement |  |  | Process 85% of all rebate claims within 30 business days* of receipt from website vendor; excluding website related delays and subject to receiving all required customer information * Number of calendar/business days subject to change based on customer survey feedback to inform appropriate calendar/business day measurement | Year to date list of rebate claims and processing dates
Situational Awareness and Forecasting | Environmental Monitoring Systems | SA-1 | Quantitative | # of weather stations installed | No mid-year target | No mid-year target | Install 85 weather stations in SCE's HFRA | No mid-year target | No mid-year target | Install 50 weather stations in SCE's HFRA |  |  | Install 15 weather stations in SCE’s HFRA | List and location of installed weather stations
Situational Awareness and Forecasting | Weather Forecasting | SA-3 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | Equip 500 weather station locations with machine learning capabilities | No mid-year target | No mid-year target | Equip 200 weather station locations with machine learning capabilities |  |  | Implement machine learning at remaining weather station locations that meet eligible criteria, and for additional variables deemed necessary to improve PSPS planning | List and location of weather stations equipped with machine learning capabilities
Situational Awareness and Forecasting | Environmental Monitoring Systems | SA-8 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | Complete analytics report summarizing assessment of historical consequence data for improved fire spread modeling | No mid-year target | No mid-year target | Provide vendor with analytics report and work with the vendor to complete a plan on future improvements |  |  | Provide recommendation for how consequence metrics can be used for PSPS Decision-Making | Final analytics report
Situational Awareness and Forecasting | Ignition Detection Systems | SA-10 | Quantitative | # of HD cameras installed | No mid-year target | No mid-year target | Install 10 HD Cameras | No mid-year target | No mid-year target | Install 10 HD Cameras |  |  | No planned installs. Additional installs will be based on reassessment in 2024 | List and location of installed HD cameras
Situational Awareness and Forecasting | Grid Monitoring Systems | SA-11 | Quantitative | # of locations | No mid-year target | No mid-year target | Install Early Fault Detection (EFD) at 50 locations | No mid-year target | No mid-year target | Install Early Fault Detection (EFD) at 50 locations |  |  | Install Early Fault Detection (EFD) at 200 locations | Listing of completed work orders
Grid Design, Operations, and Maintenance | Covered Conductor Installation | SH-1 | Quantitative | # of circuit miles in HFRA | No mid-year target | No mid-year target | Install 1,100 circuit miles of covered conductor in SCE’s HFRA | No mid-year target | No mid-year target | Install 1,050 circuit miles of covered conductor in SCE’s HFRA |  |  | Install 700 circuit miles of covered conductor in SCE’s HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Undergrounding of Electric Lines and/or Equipment | SH-2 | Quantitative | # of circuit miles in HFRA | No mid-year target | No mid-year target | Convert 11 circuit miles of overhead to underground in SCE's HFRA | No mid-year target | No mid-year target | Convert 16 circuit miles of overhead to underground in SCE's HFRA |  |  | Convert 48 circuit miles of overhead to underground in SCE's HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Other Grid Topology Improvements to Minimize Risk of Ignitions | SH-5 | Quantitative | # of RARs / RCSs installed and operationalized | No mid-year target | No mid-year target | SCE will install 6 RAR/RCS sectionalizing devices subject to 2022 PSPS analysis and subject to change | No mid-year target | No mid-year target | SCE will install 5 RAR/RCS sectionalizing devices subject to 2023 PSPS analysis and subject to change |  |  | SCE will install 5 RAR/RCS sectionalizing devices subject to 2024 PSPS analysis and subject to change | Listing of completed work orders
Grid Design, Operations, and Maintenance | Other Grid Topology Improvements to Mitigate or Reduce PSPS Events | SH-6 | Quantitative | # of installations and placed into service | No mid-year target | No mid-year target | Replace/upgrade 75 CB relay units with fast curve settings in SCE’s HFRA | No mid-year target | No mid-year target | Replace/upgrade remaining 10 CB relay units with fast curve settings in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | N/A - Activity Sunsetting in 2024 | Listing of completed work orders
Situational Awareness and Forecasting | Grid Monitoring Systems | SH-8 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | Install TOPD at 5 locations that serve HFRA circuitry with both alarm and trip functionality | No mid-year target | No mid-year target | Retrofit TOPD at 5 locations with trip capabilities where alarm mode was previously deployed and that serve HFRA circuitry |  |  | Target to be determined based on further evaluation | Listing of completed work orders
Grid Design, Operations, and Maintenance | Traditional Overhead Hardening | SH-10 | Quantitative | # of tree attachment remediations | No mid-year target | No mid-year target | Remediate 400 tree attachments in SCE’s HFRA | No mid-year target | No mid-year target | Remediate 500 tree attachments in SCE’s HFRA |  |  | Remediate the balance of tree attachments in SCE’s HFRA, subject to change based on scope completed in previous years | Listing of completed work orders
Grid Design, Operations, and Maintenance | Covered Conductor Installation | SH-14 | Quantitative | # of remediations | No mid-year target | No mid-year target | Remediate 400 spans in SCE’s HFRA | No mid-year target | No mid-year target | Remediate 1,000 spans in SCE’s HFRA |  |  | Remediate 1,000 spans in SCE’s HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Covered Conductor Installation | SH-16 | Quantitative | # structures | No mid-year target | No mid-year target | Retrofit vibration dampers on 300 structures where covered conductor is already installed in SCE’s HFRA | No mid-year target | No mid-year target | Retrofit vibration dampers on 500 structures where covered conductor is already installed in SCE’s HFRA |  |  | Retrofit vibration dampers on 600 structures where covered conductor is already installed in SCE’s HFRA | Listing of completed work orders
Grid Design, Operations, and Maintenance | Emerging Grid Hardening Technology Installations and Pilots | SH-17 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | SCE will complete construction of GFN at two substations (Acton and Phelan) | No mid-year target | No mid-year target | SCE will complete construction of GFN at one substation (Banducci) |  |  | SCE will complete construction of GFN at four substations | Listing of completed work orders
Grid Design, Operations, and Maintenance | Emerging Grid Hardening Technology Installations and Pilots | SH-18 | Qualitative | Qualitative Initiative | No mid-year target | No mid-year target | SCE will complete grounding conversion at one location, subject to land availability | No mid-year target | No mid-year target | SCE will target four locations for grounding conversion, subject to land availability |  |  | SCE will target four locations for grounding conversion, subject to land availability | Listing of completed work orders
Vegetation Management & Inspection | Vegetation Inspections | VM-1 | Quantitative | # grids/circuits** | 260** | 350** | Inspect 412 grids/circuits and prescribe mitigation for hazardous trees with strike potential within those grids in SCE’s HFRA** | 250** | 358** | Inspect 408 grids/circuits and prescribe mitigation for hazardous trees with strike potential within those grids in SCE’s HFRA** |  |  | Inspect 440 grids/circuits and prescribe mitigation for hazardous trees with strike potential within those grids in SCE’s HFRA Note: 2025 schedule will be developed at the circuit/span level, subject to change** | Tracking of year-to-date completed grids/circuits for inspection and mitigation | Information marked with an ** denotes changes from the WMP filing that were submitted in the Errata dated April 6, 2023
Vegetation Management & Inspection | Pole Clearing | VM-2 | Quantitative | # structures brushed | 29870 | 63700 | Inspect and clear (where clearance is needed) 63,700 structures*, with the exception of poles for which there are customer access or environmental constraints *These structures are in addition to poles subject to PRC 4292 | 29870 | 63700 | Inspect and clear (where clearance is needed) 63,700 structures*, with the exception of poles for which there are customer access or environmental constraints *These structures are in addition to poles subject to PRC 4292 |  |  | Inspect and clear (where clearance is needed) 63,700 structures*, with the exception of poles for which there are customer access or environmental constraints *These structures are in addition to poles subject to PRC 4292 | Listing of work orders attempted, inspected and/or completed in calendar year
Vegetation Management & Inspection | Clearance | VM-3 | Quantitative | # of sites treated | 30 | 45 | Perform vegetation treatment and maintenance to 50 sites | 30 | 45 | Perform vegetation treatment and maintenance to 50 sites |  |  | Perform vegetation treatment and maintenance to 60 sites | Listing of all completed work orders
Vegetation Management & Inspection | Clearance | VM-4 | Quantitative | # grids/circuits** | 298** | 433** | Inspect 509 grids/circuits and prescribe mitigation for dead and dying trees with strike potential within those grids/circuits** | 281** | 424** | Inspect 485 grids/circuits and prescribe mitigation for dead and dying trees with strike potential within those grids/circuits** |  |  | Inspect 536 grids/circuits and prescribe mitigation for dead and dying trees with strike potential within those grids/circuits Note: 2025 schedule will be developed at the circuit/span level, subject to change** | Tracking of year-to-date completed grids/circuits for inspection and mitigation | Information marked with an ** denotes changes from the WMP filing that were submitted in the Errata dated April 6, 2023
Vegetation Management & Inspection | Vegetation Management Enterprise System | VM-6 | Qualitative | Qualitative Initiative | Develop release schedule/plan for Arbora supplemental VM (emergent work) capabilities; and OCM and Business Readiness plan​ | Initiate UAT of developed capabilities | Enable supplemental Vegetation Management (emergent work) tree maintenance program capabilities in Arbora by end of year | Document backlog of enhancements identified during stabilization | Initiate creation of plan to prioritize and enable additional VM programs in Arbora | Monitor stabilization of Arbora and develop plan and begin execution of plan to enable additional VM maintenance programs |  |  | Monitor stabilization of Arbora and continue execution of plan to enable additional VM maintenance programs | System evidence of the capability to assign non-routine work activity in work management tool
Vegetation Management & Inspection | Clearance | VM-7 | Quantitative | # grids/circuits** | 514** | 753** | SCE plans to inspect 770 grids within our distribution system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year** | 308** | 539** | SCE plans to inspect 770 grids within our distribution system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year** |  |  | SCE plans to inspect 770 grids/circuits within our distribution system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year Note: 2025 schedule will be developed at the circuit /span level, subject to change** | Listing of all completed work orders | Information marked with an ** denotes changes from the WMP filing that were submitted in the Errata dated April 6, 2023
Vegetation Management & Inspection | Clearance | VM-8 | Quantitative | # grids/circuits** | 273** | 378** | SCE plans to inspect 416 circuits within our transmission system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year** | 273** | 378** | SCE plans to inspect 416 circuits within our transmission system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year** |  |  | SCE plans to inspect 416 circuits within our transmission system* * To inform trimming prescriptions in the January to December calendar year, with inspections occurring as early as November 1 in the prior year Note: 2025 schedule will be developed at the circuit /span level, subject to change** | Listing of all completed work orders | Information marked with an ** denotes changes from the WMP filing that were submitted in the Errata dated April 6, 2023
Vegetation Management & Inspection | Vegetation Inspections | VM-9 | Quantitative | # circuit miles | 650 | 1020 | SCE will inspect at least 1,020 HFRA circuit miles *Subject to change based on technology, program adjustments, and grid/circuits layout | 650 | 1020 | SCE will inspect at least 1,020 HFRA circuit miles *Subject to change based on technology, program adjustments, and grid/circuits layout |  |  | SCE will inspect at least 1,020 HFRA circuit miles *Subject to change based on technology, program adjustments, and grid/circuits layout. Targets for 2025 for HFRA LiDAR miles assume continuation of support of ground inspections and do not reflect SCE’s planned transition to remote sensing for inspections | Listing of all completed work orders
Vegetation Management & Inspection | Vegetation Inspections | VM-10 | Quantitative | # circuit miles | 1390 | 1700 | SCE will inspect at least 1,820 HFRA circuit miles *Subject to change based on program adjustments and evolution of remote sensing technologies | 973 | 1335 | SCE will inspect at least 1,500 HFRA circuit miles *Subject to change based on program adjustments and evolution of remote sensing technologies |  |  | SCE will inspect at least 1,750 HFRA circuit miles *Subject to change based on program adjustments and evolution of remote sensing technologies. Targets for 2025 for HFRA LiDAR miles assume continuation of support of ground inspections and do not reflect SCE’s planned transition to remote sensing for inspections | Listing of all completed work orders

## Table 13
Utility | Southern California Edison |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2024-05-01
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
SCE to provide supplemental file due to file size

## Table 14
Utility | Southern California Edison
Table No. | 14
Date Modified | 2024-05-01
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
HFTD 2 Distribution | 50.4142 | 0.056154 | 25.0226 | 14.2387 | 8.6717 | 2.1121 | 2.0147 | 5.4244 | 1.2123 | 1.2123 | 50.4704 | N/A | N/A | N/A | N/A | 0.010352
HFTD 3 Distribution | 145.0217 | 0.070897 | 47.2181 | 27.1026 | 17.8099 | 2.3056 | 3.0713 | 8.242 | 1.2005 | 1.2005 | 145.0926 | N/A | N/A | N/A | N/A | 0.0086019
HFTD 2 Transmision | 0.051737 | 0 | 0.03255 | 0 | 0.03255 | 0 | 1.5894 | 5.4244 | 1.1966 | 1.1966 | 0.051737 | N/A | N/A | N/A | N/A
HFTD 3 Transmision | 0.6387 | 0 | 0.23804 | 0.055023 | 0.18302 | 0 | 2.6832 | 8.242 | 1.1731 | 1.1731 | 0.6387 | N/A | N/A | N/A | N/A
Non-HFTD Distribution | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Non-HFTD Transmision | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Table 15
Utility | Southern California Edison
Table No. | 15
Date Modified | 2024-05-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
ABACUS | Circuit | Distribution | 1.2334 |  | HFTD 2 | 0.003641 | 0.0027408 | 0.00090027 | 0.0072365 | 0.004765 | 0.00013857 | 0.0023329 | N/A | 0.0024599 | 0.37875 | N/A | N/A | 1.0916 | 0.36598 | N/A | 1.0916
ABRAHAM | Circuit | Distribution | 0.79958 |  | HFTD 3 | 0.0015793 | 0.00050559 | 0.0010737 | 0.022165 | 0.015777 | 0.00034688 | 0.0060404 | N/A | 0.028091 | 0.022811 | N/A | N/A | 1.0725 | 0.038223 | N/A | 1.0725
ACADEMY | Circuit | Distribution | 9.8078 |  | HFTD 3 | 0.0028066 | 0.0028036 | 3.0568e-06 | 0.010816 | 0.0050164 | 0.0014143 | 0.0043849 | N/A | 0.0047956 | 0.25921 | N/A | N/A | 1.1303 | 0.00063741 | N/A | 1.1303
ACADIAN | Circuit | Distribution | 3.905 |  | HFTD 2 | 0.0033495 | 0.0033394 | 1.0131e-05 | 0.0025926 | 0.0024625 | 1.8852e-05 | 0.00011118 | N/A | 0.0012539 | 1.2881 | N/A | N/A | 1.2148 | 0.0080794 | N/A | 1.2148
ACAPULCO | Circuit | Distribution | 6.819 |  | HFTD 3 | 0.024649 | 0.024649 | 0 | 0.0036481 | 0.0021142 | 4.0413e-05 | 0.0014935 | N/A | 0.0037027 | 6.7565 | N/A | N/A | 1.3254 | 0 | N/A | 1.3254
ACCENT | Circuit | Distribution | 1.6049 |  | HFTD 2 | 0.0007098 | 0.00065889 | 5.0919e-05 | 0.002986 | 0.0011762 | 0.00013743 | 0.0016724 | N/A | 0.0042621 | 0.22066 | N/A | N/A | 1.136 | 0.011947 | N/A | 1.136
ACE | Circuit | Distribution | 4.5111 |  | HFTD 3 | 0.0040055 | 0.0040055 | 0 | 0.0073726 | 0.0040826 | 0.000834 | 0.002456 | N/A | 0 | 0.54329 | N/A | N/A | 1.0945 |  | N/A | 1.0945
ACOSTA | Circuit | Distribution | 4.6004 |  | HFTD 2 | 0.01516 | 0.014774 | 0.00038543 | 0.0037529 | 0.0017937 | 0.00010877 | 0.0018504 | N/A | 0.024259 | 3.9368 | N/A | N/A | 1.2663 | 0.015888 | N/A | 1.2663
ACRES | Circuit | Distribution | 7.3647 |  | HFTD 3 | 0.0083078 | 0.0083028 | 5.051e-06 | 0.0089284 | 0.0041842 | 0.00042015 | 0.0043241 | N/A | 0.005694 | 0.92992 | N/A | N/A | 1.1951 | 0.00088707 | N/A | 1.1951
ACROBAT | Circuit | Distribution | 11.8343 |  | HFTD 3 | 0.037746 | 0.037689 | 5.6793e-05 | 0.006313 | 0.003393 | 9.451e-05 | 0.0028255 | N/A | 0.022492 | 5.9701 | N/A | N/A | 1.2277 | 0.002525 | N/A | 1.2277
AGATE | Circuit | Distribution | 7.1505 |  | HFTD 2 | 0.0024176 | 0.0023997 | 1.7953e-05 | 0.012987 | 0.0064382 | 0.0018581 | 0.0046903 | N/A | 0.002562 | 0.18478 | N/A | N/A | 1.1284 | 0.0070072 | N/A | 1.1284
AGNEW | Circuit | Distribution | 0.58808 |  | HFTD 2 | 0.0032462 | 0.0032462 | 0 | 0.0015791 | 0.00048504 | 0.00011264 | 0.00098142 | N/A | 0.065651 | 2.0557 | N/A | N/A |  | 0 | N/A
AIDAN | Circuit | Distribution | 2.7305 |  | HFTD 2 | 0.023127 | 0.023106 | 2.0804e-05 | 0.0050558 | 0.0026459 | 0.00019533 | 0.0022146 | N/A | 0.0034262 | 4.5702 | N/A | N/A | 1.2175 | 0.0060721 | N/A | 1.2175
ALLVIEW | Circuit | Distribution | 3.2449 |  | HFTD 3 | 0.014368 | 0.014348 | 1.9551e-05 | 0.010149 | 0.0062571 | 0.0023396 | 0.0015524 | N/A | 0.030766 | 1.4138 | N/A | N/A | 1.0091 | 0.00063548 | N/A | 1.0091
ALOLA #2 | Circuit | Distribution | 3.5806 | Top 5% Highest Risk | HFTD 3 | 0.070045 | 0.070045 | 0 | 0.003265 | 0.0011436 | 0.0011484 | 0.0009731 | N/A | 0.017301 | 21.4531 | N/A | N/A | 1.0077 | 0 | N/A | 1.0077
ALPINE | Circuit | Distribution | 11.4296 | Top 5% Highest Risk | HFTD 3 | 0.053472 | 0.053459 | 1.3623e-05 | 0.017486 | 0.01325 | 0.0021564 | 0.002079 | N/A | 0.068916 | 3.0573 | N/A | N/A | 1.2628 | 0.00019767 | N/A | 1.2628
AMBERJACK | Circuit | Distribution | 0.73497 |  | HFTD 2 | 0.015715 | 0.015615 | 9.9603e-05 | 0.0054007 | 0.0027383 | 7.7717e-05 | 0.0025847 | N/A | 0.0071889 | 2.8913 | N/A | N/A | 1.1166 | 0.013855 | N/A | 1.1166
AMBERSKY | Circuit | Distribution | 3.0853 |  | HFTD 2 | 0.0012862 | 0.0012862 | 0 | 0.0078694 | 0.0044305 | 0.00082152 | 0.0026174 | N/A | 0.0013206 | 0.16344 | N/A | N/A | 1.1419 | 0 | N/A | 1.1419
AMBRUS | Circuit | Distribution | 4.1411 |  | HFTD 3 | 0.0035708 | 0.003552 | 1.8834e-05 | 0.019358 | 0.0072629 | 0.00040009 | 0.011695 | N/A | 0.005735 | 0.18349 | N/A | N/A | 1.0899 | 0.003284 | N/A | 1.0899
AMETHYST | Circuit | Distribution | 1.6174 | Top 5% Highest Risk | HFTD 3 | 0.12127 | 0.12112 | 0.00015213 | 0.012499 | 0.0071079 | 0.0002779 | 0.005113 | N/A | 0.013813 | 9.6903 | N/A | N/A | 1.1142 | 0.011013 | N/A | 1.1142
ANACONDA | Circuit | Distribution | 2.0267 |  | HFTD 3 | 0.0018021 | 0.0011733 | 0.00062876 | 0.017297 | 0.0097988 | 0.00015893 | 0.0073396 | N/A | 0.046204 | 0.067833 | N/A | N/A | 1.0894 | 0.013608 | N/A | 1.0894
ANGELES | Circuit | Distribution | 9.8675 |  | HFTD 2 | 0.0091698 | 0.0091657 | 4.1206e-06 | 0.014918 | 0.0058684 | 0.0058598 | 0.0031902 | N/A | 0.015685 | 0.61439 | N/A | N/A | 1.2036 | 0.00026271 | N/A | 1.2036
ANGUS | Circuit | Distribution | 24.6088 |  | HFTD 3 | 0.0022338 | 0.00222 | 1.3809e-05 | 0.0039204 | 0.0023444 | 0.00022654 | 0.0013494 | N/A | 0.021381 | 0.56627 | N/A | N/A | 1.2769 | 0.00064586 | N/A | 1.2769
ANN | Circuit | Distribution | 0.66518 |  | HFTD 2 | 4.1083e-05 | 4.1083e-05 | 0 | 0.0013311 | 0.00061521 | 0.00013282 | 0.00058312 | N/A | 0 | 0.030863 | N/A | N/A | 1.0487 |  | N/A | 1.0487
ANTLER | Circuit | Distribution | 1.9262 |  | HFTD 2 | 0.00034026 | 0.00034026 | 0 | 0.00052715 | 0.0002412 | 7.8183e-05 | 0.00020776 | N/A | 0 | 0.64547 | N/A | N/A | 1.0635 |  | N/A | 1.0635
ANTON | Circuit | Distribution | 29.4809 |  | HFTD 3 | 0.0036279 | 0.0036251 | 2.8032e-06 | 0.0063129 | 0.0033777 | 0.00020295 | 0.0027322 | N/A | 0.04129 | 0.57423 | N/A | N/A | 1.2269 | 6.7891e-05 | N/A | 1.2269
ANZAR | Circuit | Distribution | 3.9858 |  | HFTD 3 | 0.0025019 | 0.0025019 | 0 | 0.00301 | 0.0020888 | 5.0394e-05 | 0.00087089 | N/A | 0.0093635 | 0.83117 | N/A | N/A |  | 0 | N/A
APPALOUSA | Circuit | Distribution | 7.9286 |  | HFTD 2 | 0.016648 | 0.016647 | 6.5797e-07 | 0.0049234 | 0.0022418 | 0.00054456 | 0.0021371 | N/A | 0.0018893 | 3.3812 | N/A | N/A | 1.1057 | 0.00034827 | N/A | 1.1057
APPLETON | Circuit | Distribution | 10.6305 |  | HFTD 3 | 0.0019865 | 0.001957 | 2.9495e-05 | 0.015289 | 0.0070074 | 0.00021938 | 0.008062 | N/A | 0.014464 | 0.12801 | N/A | N/A | 1.0801 | 0.0020391 | N/A | 1.0801
ARABIA | Circuit | Distribution | 1.467 |  | HFTD 2 | 0.0014527 | 0.0012886 | 0.00016408 | 0.0049432 | 0.0030681 | 4.2858e-05 | 0.0018322 | N/A | 0.006085 | 0.26068 | N/A | N/A | 1.2393 | 0.026966 | N/A | 1.2393
ARAPAHO | Circuit | Distribution | 17.9263 |  | HFTD 2 | 0.047068 | 0.047066 | 1.3305e-06 | 0.0060214 | 0.0023757 | 0.00012507 | 0.0035206 | N/A | 0.0049898 | 7.8165 | N/A | N/A | 1.257 | 0.00026664 | N/A | 1.257
ARBORETUM | Circuit | Distribution | 12.597 |  | HFTD 3 | 0.043225 | 0.043222 | 3.2312e-06 | 0.02204 | 0.0070091 | 0.0016116 | 0.01342 | N/A | 0.022272 | 1.961 | N/A | N/A | 1.1215 | 0.00014508 | N/A | 1.1215
ARCHIE | Circuit | Distribution | 15.5832 |  | HFTD 3 | 0.0021261 | 0.0021261 | 3.7666e-10 | 0.0011188 | 0.00062673 | 2.8867e-05 | 0.00046319 | N/A | 0.00084638 | 1.9004 | N/A | N/A | 1.5 | 4.4502e-07 | N/A | 1.5
ARCTURUS | Circuit | Distribution | 3.5577 |  | HFTD 2 | 0.010542 | 0.010542 | 0 | 0.014831 | 0.0093869 | 0.0032676 | 0.0021761 | N/A | 0.0013164 | 0.71082 | N/A | N/A | 1.3876 | 0 | N/A | 1.3876
ARGONAUT | Circuit | Distribution | 2.3578 |  | HFTD 2 | 0.014345 | 0.014342 | 2.1149e-06 | 0.0033217 | 0.0023295 | 7.9839e-05 | 0.00091244 | N/A | 0.0065458 | 4.3177 | N/A | N/A | 1.0683 | 0.00032309 | N/A | 1.0683
ARIEL | Circuit | Distribution | 0.37633 | Top 5% Highest Risk | HFTD 3 | 0.056866 | 0.056866 | 0 | 0.013565 | 0.0039194 | 0.00016559 | 0.0094799 | N/A | 0.0026753 | 4.1922 | N/A | N/A | 1.2048 | 0 | N/A | 1.2048
ARLENE | Circuit | Distribution | 6.4561 |  | HFTD 3 | 0.0089945 | 0.0089922 | 2.2566e-06 | 0.010224 | 0.0066637 | 0.00015262 | 0.0034081 | N/A | 0.011047 | 0.87949 | N/A | N/A | 1.1019 | 0.00020427 | N/A | 1.1019
ARLINGTON | Circuit | Distribution | 1.5974 |  | HFTD 2 | 0.00035825 | 0.00026105 | 9.7198e-05 | 0.0096166 | 0.0062276 | 0.00033982 | 0.0030492 | N/A | 0.0019855 | 0.027146 | N/A | N/A | 1.1002 | 0.048955 | N/A | 1.1002
ARMADA | Circuit | Distribution | 4.8883 |  | HFTD 3 | 0.034575 | 0.034574 | 8.1049e-07 | 0.0070587 | 0.0039986 | 0.00026542 | 0.0027948 | N/A | 0.0039592 | 4.898 | N/A | N/A | 1.0399 | 0.00020471 | N/A | 1.0399
ARMOUR | Circuit | Distribution | 7.8484 |  | HFTD 3 | 0.043468 | 0.043462 | 5.7383e-06 | 0.01388 | 0.0096396 | 0.0014871 | 0.0027532 | N/A | 0.033232 | 3.1313 | N/A | N/A | 1.1298 | 0.00017267 | N/A | 1.1298
ARTIST | Circuit | Distribution | 4.3579 |  | HFTD 2 | 0.0026412 | 0.0026253 | 1.5939e-05 | 0.011198 | 0.0054074 | 0.0018544 | 0.0039366 | N/A | 0.0032811 | 0.23443 | N/A | N/A | 1.09 | 0.0048579 | N/A | 1.09
ASHLEY | Circuit | Distribution | 3.2194 |  | HFTD 3 | 0.03617 | 0.036166 | 4.0583e-06 | 0.010914 | 0.0057072 | 0.001414 | 0.0037933 | N/A | 0.0093421 | 3.3136 | N/A | N/A | 1.1137 | 0.00043441 | N/A | 1.1137
ATENTO | Circuit | Distribution | 30.393 |  | HFTD 3 | 0.030769 | 0.030758 | 1.0549e-05 | 0.0060578 | 0.0032063 | 0.00088694 | 0.0019645 | N/A | 0.032178 | 5.0774 | N/A | N/A | 1.3164 | 0.00032782 | N/A | 1.3164
ATLANTA | Circuit | Distribution | 5.0106 |  | HFTD 3 | 0.022054 | 0.022025 | 2.8223e-05 | 0.012486 | 0.010399 | 0.00014229 | 0.0019446 | N/A | 0.016112 | 1.764 | N/A | N/A | 1.2066 | 0.0017516 | N/A | 1.2066
ATMORE | Circuit | Distribution | 5.8179 |  | HFTD 2 | 0.0010293 | 0.0010048 | 2.4528e-05 | 0.0070058 | 0.0040425 | 0.00024242 | 0.0027209 | N/A | 0.0029939 | 0.14342 | N/A | N/A | 1.0768 | 0.0081926 | N/A | 1.0768
AUBURN | Circuit | Distribution | 1.2637 |  | HFTD 2 | 0.0036926 | 0.0036903 | 2.298e-06 | 0.0029678 | 0.0017681 | 0.00036421 | 0.00083554 | N/A | 0 | 1.2435 | N/A | N/A | 1.065 | inf | N/A | 1.065
AUTUMN | Circuit | Distribution | 7.8304 | Top 5% Highest Risk | HFTD 2 | 0.056791 | 0.056136 | 0.00065508 | 0.016605 | 0.0060291 | 0.0007723 | 0.0098032 | N/A | 0.10923 | 3.3808 | N/A | N/A | 1.0732 | 0.0059972 | N/A | 1.0732
AVANTI | Circuit | Distribution | 3.2021 |  | HFTD 2 | 0.0052427 | 0.0045837 | 0.00065892 | 0.0077323 | 0.0041373 | 0.00033928 | 0.0032557 | N/A | 0.022899 | 0.59281 | N/A | N/A | 1.1265 | 0.028775 | N/A | 1.1265
AVENGER | Circuit | Distribution | 11.5325 |  | HFTD 2 | 0.0015371 | 0.0015315 | 5.6603e-06 | 0.0020982 | 0.0017628 | 2.0444e-05 | 0.00031496 | N/A | 0.0024544 | 0.7299 | N/A | N/A | 1.1014 | 0.0023062 | N/A | 1.1014
AVENIDA | Circuit | Distribution | 12.2548 |  | HFTD 2 | 0.0040893 | 0.004086 | 3.3555e-06 | 0.0057744 | 0.0020659 | 0.0012424 | 0.0024662 | N/A | 0.013966 | 0.7076 | N/A | N/A | 1.1449 | 0.00024027 | N/A | 1.1449
AVIATOR | Circuit | Distribution | 18.8025 |  | HFTD 2 | 0.0079987 | 0.0079946 | 4.1183e-06 | 0.0040616 | 0.0025725 | 5.8693e-05 | 0.0014304 | N/A | 0.0029086 | 1.9683 | N/A | N/A | 1.1581 | 0.0014159 | N/A | 1.1581
BABYLON | Circuit | Distribution | 3.9227 |  | HFTD 2 | 0.0045904 | 0.0045904 | 0 | 0.0021725 | 0.0013246 | 0.00011429 | 0.0007336 | N/A | 0 | 2.113 | N/A | N/A | 1.096 |  | N/A | 1.096
BACHELOR | Circuit | Distribution | 9.3244 |  | HFTD 2 | 0.00060161 | 0.00060161 | 0 | 0.012107 | 0.0032024 | 0.0032921 | 0.005613 | N/A | 0.0022509 | 0.049689 | N/A | N/A | 1.1175 | 0 | N/A | 1.1175
BADGER | Circuit | Distribution | 2.7978 |  | HFTD 2 | 0.0027986 | 0.001999 | 0.00079954 | 0.0083083 | 0.0027752 | 0.00017049 | 0.0053626 | N/A | 0.0099263 | 0.24061 | N/A | N/A | 1.0973 | 0.080548 | N/A | 1.0973
BALCOM | Circuit | Distribution | 19.6232 |  | HFTD 3 | 0.0025994 | 0.0025883 | 1.1041e-05 | 0.0054721 | 0.0032329 | 6.1183e-05 | 0.0021781 | N/A | 0.0056263 | 0.473 | N/A | N/A | 1.0544 | 0.0019624 | N/A | 1.0544
BALDWIN | Circuit | Distribution | 14.8199 |  | HFTD 2 | 0.010686 | 0.01068 | 6.2688e-06 | 0.014272 | 0.0075951 | 0.0031598 | 0.0035169 | N/A | 0.0083077 | 0.74829 | N/A | N/A | 1.0973 | 0.00075458 | N/A | 1.0973
BALLOON | Circuit | Distribution | 4.8627 |  | HFTD 3 | 0.031572 | 0.031564 | 8.4163e-06 | 0.0059674 | 0.0039852 | 0.00013198 | 0.0018503 | N/A | 0.00065606 | 5.2894 | N/A | N/A | 1.0943 | 0.012829 | N/A | 1.0943
BARLEY FLATS | Circuit | Distribution | 3.2774 |  | HFTD 2 | 0.0095716 | 0.0094866 | 8.4996e-05 | 0.0087067 | 0.0038942 | 0.00080315 | 0.0040093 | N/A | 0.0038216 | 1.0896 | N/A | N/A | 1.0879 | 0.022241 | N/A | 1.0879
BARRINGTON | Circuit | Distribution | 29.8285 |  | HFTD 3 | 0.0028983 | 0.0028937 | 4.6523e-06 | 0.0033604 | 0.0020112 | 0.00011685 | 0.0012323 | N/A | 0.024762 | 0.8611 | N/A | N/A | 1.164 | 0.00018788 | N/A | 1.164
BASIL | Circuit | Distribution | 2.0523 |  | HFTD 2 | 0.0083599 | 0.0083444 | 1.5498e-05 | 0.0031508 | 0.0026373 | 4.1417e-05 | 0.000472 | N/A | 0.0039643 | 2.6484 | N/A | N/A | 1.2989 | 0.0039094 | N/A | 1.2989
BATTALION | Circuit | Distribution | 0.2594 |  | HFTD 2 | 0.0012338 | 0.00021782 | 0.001016 | 0.035732 | 0.015612 | 0.00098624 | 0.019133 | N/A | 0.00083821 | 0.006096 | N/A | N/A | 1.041 | 1.2121 | N/A | 1.041
BAUXITE | Circuit | Distribution | 3.6099 |  | HFTD 2 | 0.0029702 | 0.0029702 | 0 | 0.0069262 | 0.0034143 | 0.001111 | 0.0024009 | N/A | 0.0013376 | 0.42884 | N/A | N/A | 1.1111 | 0 | N/A | 1.1111
BAYLINER | Circuit | Distribution | 2.417 |  | HFTD 2 | 0.030997 | 0.030995 | 2.1285e-06 | 0.012005 | 0.0087123 | 0.00030063 | 0.0029921 | N/A | 0.0014788 | 2.5819 | N/A | N/A | 1.1404 | 0.0014394 | N/A | 1.1404
BAZOOKA | Circuit | Distribution | 0.44819 |  | HFTD 2 | 0.001078 | 0.00093062 | 0.0001474 | 0.0011773 | 0.00061176 | 9.8621e-05 | 0.00046693 | N/A | 0.0036815 | 0.79046 | N/A | N/A | 1.0838 | 0.040039 | N/A | 1.0838
BEAR VALLEY | Circuit | Distribution | 20.6874 |  | HFTD 3 | 0.0092779 | 0.0092643 | 1.3601e-05 | 0.0052703 | 0.0028011 | 0.00038928 | 0.0020799 | N/A | 0.15114 | 1.7578 | N/A | N/A | 1.469 | 8.9987e-05 | N/A | 1.469
BECKER | Circuit | Distribution | 0.53422 |  | HFTD 2 | 5.8412e-05 | 5.0743e-05 | 7.6692e-06 | 0.005776 | 0.0036647 | 0.00032126 | 0.00179 | N/A | 0.00069715 | 0.0087852 | N/A | N/A | 1.0513 | 0.011001 | N/A | 1.0513
BEECHCRAFT | Circuit | Distribution | 1.3737 |  | HFTD 2 | 0.0016581 | 0.0016433 | 1.4757e-05 | 0.0026253 | 0.0018417 | 1.3447e-05 | 0.00077019 | N/A | 0.001426 | 0.62595 | N/A | N/A | 1.062 | 0.010348 | N/A | 1.062
BEELER | Circuit | Distribution | 1.4279 |  | HFTD 2 | 0.02816 | 0.028155 | 4.8925e-06 | 0.0048698 | 0.0038001 | 8.0165e-05 | 0.00098948 | N/A | 0.00029034 | 5.7816 | N/A | N/A | 1.1214 | 0.016851 | N/A | 1.1214
BELPAC | Circuit | Distribution | 5.2218 |  | HFTD 3 | 0.0011131 | 0.0010566 | 5.6495e-05 | 0.018542 | 0.006356 | 0.00060262 | 0.011583 | N/A | 0.017028 | 0.056985 | N/A | N/A | 1.0473 | 0.0033177 | N/A | 1.0473
BENCH | Circuit | Distribution | 23.3872 |  | HFTD 3 | 0.035453 | 0.035446 | 7.5633e-06 | 0.0039532 | 0.0029472 | 0.00011838 | 0.00088762 | N/A | 0.025699 | 8.9663 | N/A | N/A | 1.3899 | 0.0002943 | N/A | 1.3899
BERKSHIRE | Circuit | Distribution | 6.3069 | Top 5% Highest Risk | HFTD 2 | 0.070018 | 0.070017 | 1.4563e-06 | 0.022364 | 0.0067872 | 0.001155 | 0.014421 | N/A | 0.010661 | 3.1308 | N/A | N/A | 1.1991 | 0.0001366 | N/A | 1.1991
BERMITE | Circuit | Distribution | 1.5805 |  | HFTD 3 | 0.003943 | 0.0039245 | 1.8493e-05 | 0.026103 | 0.017526 | 0.00049187 | 0.0080851 | N/A | 0.0066882 | 0.15035 | N/A | N/A | 1.0743 | 0.0027651 | N/A | 1.0743
BEVERLY SL #1 | Circuit | Distribution | 0.63051 |  | HFTD 2 | 1.8681e-05 | 1.8681e-05 | 0 | 0.0049545 | 0.0018386 | 0.0005411 | 0.0025749 | N/A | 0.00019309 | 0.0037706 | N/A | N/A |  | 0 | N/A
BIANCO | Circuit | Distribution | 1.0237 |  | HFTD 2 | 0.032055 | 0.031908 | 0.00014718 | 0.0050148 | 0.0019548 | 0.00025895 | 0.002801 | N/A | 0.0017764 | 6.3628 | N/A | N/A | 1.044 | 0.082852 | N/A | 1.044
BIDDER | Circuit | Distribution | 22.143 |  | HFTD 3 | 0.0018124 | 0.0018123 | 9.1322e-08 | 0.005038 | 0.0032111 | 0.00050919 | 0.0013177 | N/A | 0 | 0.35972 | N/A | N/A | 1.0689 | inf | N/A | 1.0689
BIG CREEK-PORTAL | Circuit | Distribution | 22.4576 |  | HFTD 3 | 0.0026844 | 0.0026844 | 5.0483e-09 | 0.0085971 | 0.005961 | 0.0014409 | 0.0011952 | N/A | 0.024043 | 0.31225 | N/A | N/A | 1.6316 | 2.0997e-07 | N/A | 1.6316
BIG FALLS | Circuit | Distribution | 3.7847 |  | HFTD 3 | 0.017377 | 0.017373 | 4.3151e-06 | 0.016792 | 0.010676 | 0.003133 | 0.0029825 | N/A | 0.017319 | 1.0346 | N/A | N/A | 1.0115 | 0.00024915 | N/A | 1.0115
BIG ROCK | Circuit | Distribution | 15.9363 |  | HFTD 3 | 0.04266 | 0.042615 | 4.5081e-05 | 0.016503 | 0.0056139 | 0.00026483 | 0.010624 | N/A | 0.028486 | 2.5823 | N/A | N/A | 1.1503 | 0.0015825 | N/A | 1.1503
BIGFOOT | Circuit | Distribution | 2.3228 |  | HFTD 2 | 0.0024418 | 0.0024414 | 3.641e-07 | 0.011061 | 0.0080958 | 0.00050724 | 0.0024582 | N/A | 0.0080259 | 0.22072 | N/A | N/A | 1 | 4.5366e-05 | N/A | 1
BILLY | Circuit | Distribution | 0.27325 |  | HFTD 2 | 0.018557 | 0.018557 | 0 | 0.0052194 | 0.0035383 | 0.0001049 | 0.0015762 | N/A | 0.0052421 | 3.5554 | N/A | N/A |  | 0 | N/A
BIRCHIM | Circuit | Distribution | 53.0293 |  | HFTD 2 | 0.0043378 | 0.0043378 | 0 | 0.0017248 | 0.00075846 | 7.9357e-05 | 0.00088702 | N/A | 0.12503 | 2.5149 | N/A | N/A | 1.2326 | 0 | N/A | 1.2326
BLACKBIRD | Circuit | Distribution | 2.2097 |  | HFTD 3 | 0.025604 | 0.025585 | 1.9829e-05 | 0.0095598 | 0.0063994 | 9.3597e-05 | 0.0030668 | N/A | 0.0072402 | 2.6763 | N/A | N/A | 1.041 | 0.0027387 | N/A | 1.041
BLACKBURN | Circuit | Distribution | 2.8497 |  | HFTD 2 | 0.011471 | 0.011372 | 9.8876e-05 | 0.0073276 | 0.0069573 | 3.7042e-05 | 0.00033326 | N/A | 0.0029675 | 1.5519 | N/A | N/A | 1.1793 | 0.033319 | N/A | 1.1793
BLACKFOOT | Circuit | Distribution | 4.6503 |  | HFTD 2 | 0.02802 | 0.028015 | 5.6469e-06 | 0.0047274 | 0.0025107 | 0.00014406 | 0.0020726 | N/A | 0.0018334 | 5.9261 | N/A | N/A | 1.1516 | 0.00308 | N/A | 1.1516
BLACKHILLS | Circuit | Distribution | 1.2123 |  | HFTD 2 | 0.0057646 | 0.0051562 | 0.00060836 | 0.0060624 | 0.0030831 | 9.2243e-05 | 0.002887 | N/A | 0.0020361 | 0.85053 | N/A | N/A | 1.189 | 0.29878 | N/A | 1.189
BLEDSOE | Circuit | Distribution | 20.1245 |  | HFTD 2 | 0.0049846 | 0.0049814 | 3.2165e-06 | 0.0025478 | 0.0016497 | 3.43e-05 | 0.00086382 | N/A | 0.018483 | 1.9552 | N/A | N/A | 1.5395 | 0.00017402 | N/A | 1.5395
BLUE CUT | Circuit | Distribution | 41.1432 |  | HFTD 3 | 0.032496 | 0.032465 | 3.104e-05 | 0.0051678 | 0.0028669 | 5.9397e-05 | 0.0022415 | N/A | 0.15927 | 6.2822 | N/A | N/A | 1.3906 | 0.00019489 | N/A | 1.3906
BLUE RIDGE | Circuit | Distribution | 4.0575 |  | HFTD 3 | 0.01828 | 0.01828 | 4.195e-07 | 0.0098062 | 0.0045498 | 0.00043739 | 0.004819 | N/A | 0.010629 | 1.8641 | N/A | N/A | 1 | 3.9467e-05 | N/A | 1
BLUEBERRY | Circuit | Distribution | 0.41662 |  | HFTD 2 | 0.00029339 | 0.00012048 | 0.00017291 | 0.0061834 | 0.0027381 | 0.0004128 | 0.0030325 | N/A | 0.00087225 | 0.019484 | N/A | N/A | 1.0518 | 0.19823 | N/A | 1.0518
BOA | Circuit | Distribution | 2.7281 |  | HFTD 3 | 0.019214 | 0.01917 | 4.3907e-05 | 0.016762 | 0.0098632 | 0.00016061 | 0.0067383 | N/A | 0.0080259 | 1.1437 | N/A | N/A | 1.0618 | 0.0054707 | N/A | 1.0618
BOBBIT | Circuit | Distribution | 0.54065 |  | HFTD 2 | 0.0046063 | 0.0042483 | 0.00035795 | 0.0031548 | 0.0021492 | 0.00013126 | 0.00087435 | N/A | 0.00032263 | 1.3466 | N/A | N/A | 1.1009 | 1.1095 | N/A | 1.1009
BOBBY | Circuit | Distribution | 2.9174 |  | HFTD 2 | 0.004538 | 0.0045338 | 4.1294e-06 | 0.010749 | 0.0039692 | 0.00042972 | 0.0063504 | N/A | 0.00027855 | 0.42178 | N/A | N/A | 1.1364 | 0.014825 | N/A | 1.1364
BOBSLED | Circuit | Distribution | 2.315 |  | HFTD 2 | 0.0054618 | 0.0027219 | 0.0027399 | 0.016646 | 0.0042683 | 0.0011031 | 0.011275 | N/A | 0.031621 | 0.16351 | N/A | N/A | 1.0267 | 0.086648 | N/A | 1.0267
BODKIN | Circuit | Distribution | 2.0022 |  | HFTD 3 | 0.030031 | 0.030028 | 2.8192e-06 | 0.0081754 | 0.0032723 | 0.00010883 | 0.0047943 | N/A | 0.00075232 | 3.673 | N/A | N/A | 1.2151 | 0.0037474 | N/A | 1.2151
BOGART | Circuit | Distribution | 1.8439 |  | HFTD 2 | 0.0018335 | 0.0018335 | 0 | 0.015891 | 0.0027403 | 0.010215 | 0.0029356 | N/A | 0 | 0.11538 | N/A | N/A | 1.0722 |  | N/A | 1.0722
BOLLERO | Circuit | Distribution | 1.7622 |  | HFTD 2 | 0.0056367 | 0.0055326 | 0.00010402 | 0.0046446 | 0.0017441 | 3.215e-05 | 0.0028683 | N/A | 0.0032548 | 1.1912 | N/A | N/A | 1.2012 | 0.031959 | N/A | 1.2012
BOMBAY | Circuit | Distribution | 3.9486 |  | HFTD 2 | 0.0015106 | 0.0015 | 1.0612e-05 | 0.0030687 | 0.0021134 | 0.00012586 | 0.0008294 | N/A | 0.0048972 | 0.48881 | N/A | N/A | 1.0712 | 0.002167 | N/A | 1.0712
BONANZA | Circuit | Distribution | 39.003 |  | HFTD 3 | 0.021234 | 0.021222 | 1.1521e-05 | 0.0053756 | 0.0027448 | 7.6118e-05 | 0.0025546 | N/A | 0.051852 | 3.9479 | N/A | N/A | 1.1566 | 0.00022219 | N/A | 1.1566
BONNEVILLE | Circuit | Distribution | 14.0489 |  | HFTD 2 | 0.0040356 | 0.0040345 | 1.1284e-06 | 0.0018268 | 0.0010952 | 5.752e-05 | 0.0006741 | N/A | 0.010102 | 2.2085 | N/A | N/A | 1.2509 | 0.0001117 | N/A | 1.2509
BONNIE | Circuit | Distribution | 0.33268 |  | HFTD 2 | 0.014438 | 0.014392 | 4.5854e-05 | 0.017185 | 0.0054982 | 0.0010589 | 0.010628 | N/A | 0.00093606 | 0.83747 | N/A | N/A | 1.0419 | 0.048987 | N/A | 1.0419
BOOTLEGGER | Circuit | Distribution | 90.8514 |  | HFTD 3 | 0.043192 | 0.043187 | 4.4525e-06 | 0.0047679 | 0.002906 | 3.2975e-05 | 0.0018288 | N/A | 0.064841 | 9.058 | N/A | N/A | 1.1583 | 6.8668e-05 | N/A | 1.1583
BORCHARD | Circuit | Distribution | 3.6464 |  | HFTD 3 | 0.0049535 | 0.0049374 | 1.6094e-05 | 0.015475 | 0.0082819 | 0.00085826 | 0.0063345 | N/A | 0.0063845 | 0.31906 | N/A | N/A | 1.0448 | 0.0025207 | N/A | 1.0448
BOULDER | Circuit | Distribution | 10.9567 |  | HFTD 2 | 0.0028135 | 0.0027931 | 2.0404e-05 | 0.0047018 | 0.0029453 | 0.00016225 | 0.0015942 | N/A | 0.022845 | 0.59405 | N/A | N/A | 1.2584 | 0.00089313 | N/A | 1.2584
BOUQUET | Circuit | Distribution | 30.0298 |  | HFTD 3 | 0.024871 | 0.024862 | 8.7736e-06 | 0.0048828 | 0.0027426 | 7.4398e-05 | 0.0020658 | N/A | 0.035431 | 5.0919 | N/A | N/A | 1.135 | 0.00024762 | N/A | 1.135
BOXCAR | Circuit | Distribution | 0.81253 |  | HFTD 2 | 2.5991e-05 | 2.5991e-05 | 0 | 0.00025522 | 8.739e-05 | 1.6252e-06 | 0.00016621 | N/A | 0 | 0.10184 | N/A | N/A | 1.2869 |  | N/A | 1.2869
BRADLEY | Circuit | Distribution | 1.6896 |  | HFTD 2 | 0.002062 | 0.002062 | 0 | 0.006036 | 0.0043638 | 0.00010332 | 0.0015688 | N/A | 0 | 0.34162 | N/A | N/A | 1.0841 |  | N/A | 1.0841
BRAKEMAN | Circuit | Distribution | 9.158 |  | HFTD 2 | 0.0024616 | 0.0024616 | 0 | 0.005548 | 0.0030662 | 0.00068302 | 0.0017988 | N/A | 0.002323 | 0.4437 | N/A | N/A | 1.0822 | 0 | N/A | 1.0822
BRAND | Circuit | Distribution | 1.9976 |  | HFTD 3 | 0.0003891 | 0.00016877 | 0.00022033 | 0.017666 | 0.010223 | 0.00016744 | 0.0072757 | N/A | 0.014548 | 0.0095535 | N/A | N/A | 1.061 | 0.015145 | N/A | 1.061
BRAUN | Circuit | Distribution | 3.3226 |  | HFTD 2 | 0.0026558 | 0.0026525 | 3.2795e-06 | 0.0069728 | 0.0051792 | 0.00020284 | 0.0015907 | N/A | 7.6631e-05 | 0.38041 | N/A | N/A | 1.0891 | 0.042796 | N/A | 1.0891
BRENNAN | Circuit | Distribution | 5.1713 | Top 5% Highest Risk | HFTD 3 | 0.054794 | 0.054684 | 0.00011025 | 0.016418 | 0.0051146 | 0.00034989 | 0.010954 | N/A | 0.010451 | 3.3306 | N/A | N/A | 1.1256 | 0.010549 | N/A | 1.1256
BRETING | Circuit | Distribution | 0.26223 |  | HFTD 3 | 0.00032926 | 0.00032926 | 0 | 0.00045797 | 0.00010215 | 5.5743e-06 | 0.00035024 | N/A | 0 | 0.71895 | N/A | N/A | 1.0563 |  | N/A | 1.0563
BROADCAST | Circuit | Distribution | 18.3074 |  | HFTD 3 | 0.026505 | 0.026505 | 9.5227e-08 | 0.0030036 | 0.0021212 | 9.6239e-05 | 0.00078623 | N/A | 0.02267 | 8.8244 | N/A | N/A | 1.6 | 4.2006e-06 | N/A | 1.6
BROOKINGS | Circuit | Distribution | 0.36677 |  | HFTD 3 | 0.029707 | 0.029707 | 4.7066e-07 | 0.0071725 | 0.0038524 | 0.001777 | 0.0015431 | N/A | 0.024078 | 4.1418 | N/A | N/A | 1 | 1.9547e-05 | N/A | 1
BRUMFIELD | Circuit | Distribution | 1.2071 |  | HFTD 2 | 0.021455 | 0.021453 | 1.9814e-06 | 0.011634 | 0.0053384 | 0.0020092 | 0.0042868 | N/A | 0.00067762 | 1.8439 | N/A | N/A | 1.0184 | 0.0029241 | N/A | 1.0184
BRYDON | Circuit | Distribution | 5.2692 |  | HFTD 3 | 0.007489 | 0.0074737 | 1.5363e-05 | 0.0067746 | 0.0019488 | 0.00036691 | 0.0044588 | N/A | 0.0066979 | 1.1032 | N/A | N/A | 1.1749 | 0.0022937 | N/A | 1.1749
BRYN MAWR | Circuit | Distribution | 1.8061 |  | HFTD 3 | 0.0063214 | 0.0063085 | 1.2917e-05 | 0.0070941 | 0.0029878 | 0.00025615 | 0.0038501 | N/A | 0.0010493 | 0.88926 | N/A | N/A | 1.0552 | 0.01231 | N/A | 1.0552
BUCKBOARD | Circuit | Distribution | 2.808 |  | HFTD 2 | 0.008752 | 0.0087366 | 1.5402e-05 | 0.0056789 | 0.0038417 | 0.0003291 | 0.0015081 | N/A | 0.0019372 | 1.5384 | N/A | N/A | 1.2333 | 0.0079509 | N/A | 1.2333
BUCKHORN | Circuit | Distribution | 55.0263 |  | HFTD 3 | 0.0039557 | 0.003949 | 6.7105e-06 | 0.0039055 | 0.0025531 | 0.0001247 | 0.0012277 | N/A | 0.027311 | 1.0111 | N/A | N/A | 1.1199 | 0.0002457 | N/A | 1.1199
BUCKNER | Circuit | Distribution | 9.2544 |  | HFTD 3 | 0.0020278 | 0.0019741 | 5.3626e-05 | 0.012282 | 0.0080975 | 0.0027166 | 0.0014677 | N/A | 0.017903 | 0.16074 | N/A | N/A | 1.0761 | 0.0029954 | N/A | 1.0761
BUFFER | Circuit | Distribution | 6.6371 |  | HFTD 3 | 0.032122 | 0.0321 | 2.2126e-05 | 0.0061564 | 0.0027025 | 0.00010719 | 0.0033468 | N/A | 0.012133 | 5.214 | N/A | N/A | 1.2075 | 0.0018236 | N/A | 1.2075
BUNDY | Circuit | Distribution | 0.82415 |  | HFTD 2 | 0.020166 | 0.020103 | 6.286e-05 | 0.0080038 | 0.0066331 | 0.00012132 | 0.0012494 | N/A | 0.00038246 | 2.5117 | N/A | N/A | 1.0488 | 0.16436 | N/A | 1.0488
BURGUNDY | Circuit | Distribution | 3.5841 |  | HFTD 2 | 0.0046478 | 0.0043266 | 0.00032124 | 0.0061902 | 0.0032337 | 5.191e-05 | 0.0029045 | N/A | 0.0039239 | 0.69895 | N/A | N/A | 1.3631 | 0.081867 | N/A | 1.3631
BURLESON | Circuit | Distribution | 4.6531 |  | HFTD 3 | 0.00041048 | 0.00012967 | 0.00028081 | 0.011124 | 0.0044562 | 8.8202e-05 | 0.00658 | N/A | 0.063347 | 0.011657 | N/A | N/A | 1.097 | 0.0044329 | N/A | 1.097
BURNS | Circuit | Distribution | 3.1501 |  | HFTD 2 | 0.0074469 | 0.0074215 | 2.5397e-05 | 0.0031058 | 0.0025097 | 0.00014151 | 0.00045459 | N/A | 0.0046758 | 2.3895 | N/A | N/A | 1.1249 | 0.0054315 | N/A | 1.1249
BURNT MOUNTAIN | Circuit | Distribution | 16.0706 |  | HFTD 2 | 0.026457 | 0.026425 | 3.124e-05 | 0.0051144 | 0.0030178 | 5.4874e-05 | 0.0020417 | N/A | 0.015815 | 5.1669 | N/A | N/A | 1.0933 | 0.0019753 | N/A | 1.0933
BUTTERFIELD | Circuit | Distribution | 8.4247 |  | HFTD 2 | 0.013478 | 0.013466 | 1.1711e-05 | 0.0025786 | 0.0011583 | 0.00010525 | 0.001315 | N/A | 0.010976 | 5.2223 | N/A | N/A | 1.0688 | 0.001067 | N/A | 1.0688
CABANA | Circuit | Distribution | 1.2288 |  | HFTD 2 | 0.0045501 | 0.0040954 | 0.00045475 | 0.015179 | 0.0073608 | 0.00022895 | 0.0075895 | N/A | 0.0065381 | 0.2698 | N/A | N/A | 1.0963 | 0.069553 | N/A | 1.0963
CABOOSE | Circuit | Distribution | 0.29373 |  | HFTD 2 | 4.9274e-05 | 4.9274e-05 | 0 | 0.0050482 | 0.0026546 | 0.00019925 | 0.0021944 | N/A | 0 | 0.0097606 | N/A | N/A | 1.0664 |  | N/A | 1.0664
CACHUMA | Circuit | Distribution | 57.7232 |  | HFTD 3 | 0.0099254 | 0.0099218 | 3.5504e-06 | 0.0050304 | 0.0025379 | 0.00033024 | 0.0021622 | N/A | 0.016783 | 1.9724 | N/A | N/A | 1.1603 | 0.00021155 | N/A | 1.1603
CACTUS | Circuit | Distribution | 1.1339 |  | HFTD 2 | 0.0013634 | 0.001361 | 2.415e-06 | 0.0021705 | 0.0016135 | 1.1155e-05 | 0.00054583 | N/A | 0.0023319 | 0.62702 | N/A | N/A | 1.4825 | 0.0010356 | N/A | 1.4825
CADENA | Circuit | Distribution | 2.6354 |  | HFTD 3 | 0.0054324 | 0.005422 | 1.0433e-05 | 0.011073 | 0.0051785 | 0.00065465 | 0.0052396 | N/A | 0.0079456 | 0.48967 | N/A | N/A | 1.0296 | 0.001313 | N/A | 1.0296
CADILLAC | Circuit | Distribution | 2.1713 |  | HFTD 2 | 0.0029358 | 0.0029351 | 6.9262e-07 | 0.0045225 | 0.0024062 | 6.7243e-05 | 0.0020491 | N/A | 0.00040524 | 0.64901 | N/A | N/A | 1.1546 | 0.0017092 | N/A | 1.1546
CADWAY | Circuit | Distribution | 7.6573 |  | HFTD 3 | 0.0022374 | 0.0022055 | 3.1921e-05 | 0.0055432 | 0.0037989 | 0.00013193 | 0.0016123 | N/A | 0.0054678 | 0.39787 | N/A | N/A | 1.0924 | 0.005838 | N/A | 1.0924
CAESAR | Circuit | Distribution | 3.9875 |  | HFTD 3 | 0.0043621 | 0.0042346 | 0.00012758 | 0.013214 | 0.0073564 | 0.00024944 | 0.0056077 | N/A | 0.031059 | 0.32047 | N/A | N/A | 1.1102 | 0.0041077 | N/A | 1.1102
CAIN RANCH | Circuit | Distribution | 0.61289 |  | HFTD 2 | 0.032006 | 0.031951 | 5.4485e-05 | 0.037321 | 0.031299 | 0.0013578 | 0.0046643 | N/A | 0.0074064 | 0.85612 | N/A | N/A | 1.4421 | 0.0073564 | N/A | 1.4421
CAL POLY | Circuit | Distribution | 0.89681 |  | HFTD 2 | 0.0029954 | 0.0029849 | 1.0503e-05 | 0.0034649 | 0.0021403 | 0.00013926 | 0.0011853 | N/A | 0.00033831 | 0.86146 | N/A | N/A | 1.1971 | 0.031044 | N/A | 1.1971
CALAMAR | Circuit | Distribution | 13.6512 |  | HFTD 3 | 0.0071418 | 0.0071417 | 6.2546e-08 | 0.0042355 | 0.0023468 | 0.00014075 | 0.0017479 | N/A | 0.0037754 | 1.6862 | N/A | N/A | 1.2581 | 1.6567e-05 | N/A | 1.2581
CALGROVE | Circuit | Distribution | 16.6605 |  | HFTD 3 | 0.0046592 | 0.0046141 | 4.5075e-05 | 0.0083051 | 0.0047902 | 0.00012155 | 0.0033934 | N/A | 0.027997 | 0.55558 | N/A | N/A | 1.1838 | 0.00161 | N/A | 1.1838
CALIBER | Circuit | Distribution | 18.766 |  | HFTD 2 | 0.018025 | 0.017995 | 2.939e-05 | 0.0051492 | 0.0020079 | 7.0628e-06 | 0.0031342 | N/A | 0.01731 | 3.4948 | N/A | N/A | 1.2188 | 0.0016978 | N/A | 1.2188
CALIENTE | Circuit | Distribution | 35.0659 |  | HFTD 3 | 0.025378 | 0.025376 | 1.9491e-06 | 0.0063189 | 0.0032038 | 1.9648e-05 | 0.0030955 | N/A | 0.025247 | 4.016 | N/A | N/A | 1.0726 | 7.72e-05 | N/A | 1.0726
CALIMESA | Circuit | Distribution | 11.0328 |  | HFTD 2 | 0.022107 | 0.022105 | 2.8441e-06 | 0.0047739 | 0.0032614 | 0.00012419 | 0.0013883 | N/A | 0.010557 | 4.6303 | N/A | N/A | 1.1003 | 0.0002694 | N/A | 1.1003
CALORA | Circuit | Distribution | 0.48414 |  | HFTD 2 | 0.0026437 | 0.0025941 | 4.961e-05 | 0.0066134 | 0.005348 | 0.00017509 | 0.0010903 | N/A | 0.00078592 | 0.39225 | N/A | N/A | 1.0676 | 0.063123 | N/A | 1.0676
CALSPAR | Circuit | Distribution | 0.37645 |  | HFTD 2 | 0.044599 | 0.044556 | 4.3072e-05 | 0.022295 | 0.010254 | 0.00090841 | 0.011133 | N/A | 0.00012076 | 1.9984 | N/A | N/A | 1.0851 | 0.35668 | N/A | 1.0851
CALSTATE | Circuit | Distribution | 3.2758 |  | HFTD 3 | 0.028618 | 0.028461 | 0.00015724 | 0.0047951 | 0.002009 | 0.00016605 | 0.0026201 | N/A | 0.025803 | 5.9353 | N/A | N/A | 1.1554 | 0.0060938 | N/A | 1.1554
CAMP ANGELUS | Circuit | Distribution | 4.7322 |  | HFTD 3 | 0.011339 | 0.011322 | 1.6753e-05 | 0.0090276 | 0.0043629 | 0.00082724 | 0.0038374 | N/A | 0.033747 | 1.2542 | N/A | N/A | 1.5172 | 0.00049643 | N/A | 1.5172
CAMP NELSON | Circuit | Distribution | 4.8768 |  | HFTD 2 | 0.0061212 | 0.0061184 | 2.8506e-06 | 0.0074933 | 0.0033247 | 0.0026346 | 0.0015341 | N/A | 0.0035053 | 0.81651 | N/A | N/A | 1.318 | 0.00081322 | N/A | 1.318
CAMPANULA | Circuit | Distribution | 36.4854 |  | HFTD 2 | 0.01647 | 0.016433 | 3.719e-05 | 0.0035752 | 0.0026076 | 1.2557e-05 | 0.00095506 | N/A | 0.022678 | 4.5964 | N/A | N/A | 1.2867 | 0.00164 | N/A | 1.2867
CAMPBELL | Circuit | Distribution | 3.7272 |  | HFTD 2 | 0.00046323 | 0.00046323 | 0 | 0.0021936 | 0.00061775 | 3.2462e-05 | 0.0015434 | N/A | 0 | 0.21117 | N/A | N/A | 1.1208 |  | N/A | 1.1208
CAMPROCK | Circuit | Distribution | 5.795 |  | HFTD 2 | 0.00062324 | 0.00062275 | 4.938e-07 | 0.0045075 | 0.0039525 | 3.8351e-05 | 0.00051662 | N/A | 0.0051334 | 0.13816 | N/A | N/A | 1.1924 | 9.6194e-05 | N/A | 1.1924
CANAL | Circuit | Distribution | 11.3914 |  | HFTD 3 | 0.0044872 | 0.0044871 | 6.623e-08 | 0.0033947 | 0.0020007 | 0.00018559 | 0.0012084 | N/A | 0.01363 | 1.3218 | N/A | N/A | 1.7237 | 4.8592e-06 | N/A | 1.7237
CANCUN | Circuit | Distribution | 0.46229 |  | HFTD 3 | 0.022882 | 0.022874 | 7.7136e-06 | 0.016772 | 0.003242 | 0.00084425 | 0.012686 | N/A | 0.00032458 | 1.3638 | N/A | N/A | 1.0659 | 0.023765 | N/A | 1.0659
CANEBRAKE | Circuit | Distribution | 73.8589 |  | HFTD 3 | 0.0071764 | 0.0071764 | 0 | 0.0028902 | 0.0021887 | 3.7997e-05 | 0.0006634 | N/A | 0.13913 | 2.4831 | N/A | N/A | 1.1683 | 0 | N/A | 1.1683
CANET | Circuit | Distribution | 18.771 |  | HFTD 3 | 0.0020433 | 0.0020404 | 2.9155e-06 | 0.010732 | 0.008096 | 0.0003242 | 0.0023119 | N/A | 0.0071094 | 0.19012 | N/A | N/A | 1.0586 | 0.0004101 | N/A | 1.0586
CANTINA | Circuit | Distribution | 2.5578 |  | HFTD 2 | 0.01094 | 0.010561 | 0.00037924 | 0.018895 | 0.011433 | 0.00063737 | 0.0068256 | N/A | 0.0096707 | 0.55889 | N/A | N/A | 1.0312 | 0.039215 | N/A | 1.0312
CAPANERO | Circuit | Distribution | 9.0616 |  | HFTD 2 | 0.018342 | 0.018342 | 0 | 0.0084878 | 0.0071969 | 0.00047089 | 0.00082 | N/A | 0.002461 | 2.161 | N/A | N/A | 1.3969 | 0 | N/A | 1.3969
CARANCHO | Circuit | Distribution | 46.6004 |  | HFTD 3 | 0.0062081 | 0.0062078 | 3.6555e-07 | 0.0026989 | 0.0015613 | 0.00013817 | 0.00099938 | N/A | 0.013406 | 2.3001 | N/A | N/A | 1.117 | 2.7267e-05 | N/A | 1.117
CARATAN | Circuit | Distribution | 4.2261 |  | HFTD 2 | 0.00048161 | 0.00048128 | 3.2493e-07 | 0.0021587 | 0.00058477 | 5.8743e-06 | 0.001568 | N/A | 0.00035174 | 0.22295 | N/A | N/A | 1.1555 | 0.0009238 | N/A | 1.1555
CARBINE | Circuit | Distribution | 2.4289 |  | HFTD 2 | 0.02188 | 0.021869 | 1.1631e-05 | 0.0036994 | 0.0027132 | 7.0686e-05 | 0.00091555 | N/A | 0.0011997 | 5.9114 | N/A | N/A | 1.0962 | 0.0096953 | N/A | 1.0962
CARDINAL | Circuit | Distribution | 6.5717 |  | HFTD 3 | 0.011443 | 0.011443 | 8.9447e-07 | 0.0079679 | 0.0052212 | 0.00027297 | 0.0024737 | N/A | 0.0013203 | 1.4361 | N/A | N/A | 1.542 | 0.00067745 | N/A | 1.542
CAREY | Circuit | Distribution | 1.2356 |  | HFTD 2 | 0.0023301 | 0.0018456 | 0.00048448 | 0.0078187 | 0.0028626 | 0.00042973 | 0.0045263 | N/A | 0.0019769 | 0.23605 | N/A | N/A | 1.0731 | 0.24507 | N/A | 1.0731
CARLET | Circuit | Distribution | 4.0422 |  | HFTD 3 | 0.0050247 | 0.0049963 | 2.8432e-05 | 0.011482 | 0.006603 | 0.00041598 | 0.0044631 | N/A | 0.0057735 | 0.43514 | N/A | N/A | 1.0581 | 0.0049245 | N/A | 1.0581
CARMELITA | Circuit | Distribution | 5.358 |  | HFTD 2 | 0.0020684 | 0.0014997 | 0.00056869 | 0.0042207 | 0.0031373 | 6.255e-05 | 0.0010209 | N/A | 0.0067896 | 0.35532 | N/A | N/A | 1.1317 | 0.083759 | N/A | 1.1317
CARNEGIE | Circuit | Distribution | 1.2964 |  | HFTD 2 | 0.0038818 | 0.0038634 | 1.8489e-05 | 0.0071581 | 0.0042917 | 0.00096041 | 0.0019061 | N/A | 0.00015994 | 0.53972 | N/A | N/A | 1.0974 | 0.1156 | N/A | 1.0974
CARRIAGE | Circuit | Distribution | 5.7841 |  | HFTD 2 | 0.0054093 | 0.0052675 | 0.00014181 | 0.0042797 | 0.0035028 | 0.0001366 | 0.00064022 | N/A | 0.0067625 | 1.2308 | N/A | N/A | 1.1695 | 0.02097 | N/A | 1.1695
CARVER | Circuit | Distribution | 21.7206 |  | HFTD 2 | 0.0012845 | 0.0012845 | 0 | 0.0021381 | 0.00064307 | 1.9752e-05 | 0.0014753 | N/A | 0.0013746 | 0.60077 | N/A | N/A | 1.0852 | 0 | N/A | 1.0852
CASCADA | Circuit | Distribution | 2.1962 |  | HFTD 3 | 0.0064547 | 0.0064531 | 1.6479e-06 | 0.0096396 | 0.0044691 | 0.0012695 | 0.0039009 | N/A | 0.010553 | 0.66944 | N/A | N/A | 1.4344 | 0.00015616 | N/A | 1.4344
CASCADE | Circuit | Distribution | 7.8685 |  | HFTD 3 | 0.032939 | 0.032939 | 0 | 0.0062061 | 0.0030469 | 0.00026575 | 0.0028934 | N/A | 0 | 5.3076 | N/A | N/A | 1.1004 |  | N/A | 1.1004
CASE | Circuit | Distribution | 6.2385 |  | HFTD 2 | 0.010962 | 0.010962 | 4.8212e-09 | 0.0035201 | 0.0025229 | 0.00011447 | 0.00088274 | N/A | 0.004557 | 3.1141 | N/A | N/A | 1.3333 | 1.058e-06 | N/A | 1.3333
CASEY | Circuit | Distribution | 0.78722 |  | HFTD 3 | 0.008894 | 0.0088669 | 2.7082e-05 | 0.032413 | 0.021296 | 0.0017583 | 0.0093586 | N/A | 0.00021008 | 0.27356 | N/A | N/A | 1.0704 | 0.12892 | N/A | 1.0704
CASPER | Circuit | Distribution | 2.5893 |  | HFTD 2 | 0.00014329 | 0.00014247 | 8.132e-07 | 0.0016336 | 0.0013569 | 5.7652e-05 | 0.00021904 | N/A | 0.0029859 | 0.087213 | N/A | N/A | 1.4897 | 0.00027235 | N/A | 1.4897
CASSIDY | Circuit | Distribution | 6.3587 |  | HFTD 3 | 0.031772 | 0.031738 | 3.4322e-05 | 0.015791 | 0.0049659 | 0.00018548 | 0.010639 | N/A | 0.0025937 | 2.0099 | N/A | N/A | 1.0708 | 0.013233 | N/A | 1.0708
CASTRO | Circuit | Distribution | 34.7231 |  | HFTD 3 | 0.0017938 | 0.0017843 | 9.4994e-06 | 0.0037894 | 0.0023546 | 6.7795e-05 | 0.001367 | N/A | 0.010175 | 0.47087 | N/A | N/A | 1.2407 | 0.00093357 | N/A | 1.2407
CATARACT | Circuit | Distribution | 1.8667 |  | HFTD 2 | 0.0082502 | 0.008212 | 3.8177e-05 | 0.0083456 | 0.0028229 | 0.00020346 | 0.0053192 | N/A | 0.001444 | 0.98399 | N/A | N/A | 1.1667 | 0.026438 | N/A | 1.1667
CEDAR GLEN | Circuit | Distribution | 12.2664 | Top 5% Highest Risk | HFTD 3 | 0.05899 | 0.058951 | 3.9756e-05 | 0.011182 | 0.0075228 | 0.0017199 | 0.0019388 | N/A | 0.055387 | 5.2721 | N/A | N/A | 1.0568 | 0.00071778 | N/A | 1.0568
CEDAR PINES | Circuit | Distribution | 5.193 |  | HFTD 3 | 0.021775 | 0.021745 | 2.9714e-05 | 0.0083621 | 0.0043759 | 0.0016319 | 0.0023542 | N/A | 0.061028 | 2.6005 | N/A | N/A | 1.4249 | 0.0004869 | N/A | 1.4249
CELLO | Circuit | Distribution | 1.7625 |  | HFTD 3 | 0.0098664 | 0.0098064 | 5.9968e-05 | 0.011014 | 0.0050632 | 0.0004851 | 0.0054659 | N/A | 0.012185 | 0.89035 | N/A | N/A | 1.09 | 0.0049216 | N/A | 1.09
CENTAUR | Circuit | Distribution | 0.71434 |  | HFTD 2 | 0.0024769 | 0.0024297 | 4.7255e-05 | 0.0074863 | 0.0057274 | 0.00025285 | 0.0015061 | N/A | 0.0025328 | 0.32455 | N/A | N/A | 1.1136 | 0.018657 | N/A | 1.1136
CERAMIC | Circuit | Distribution | 0.27017 |  | HFTD 2 | 0.0068671 | 0.0067871 | 8.0054e-05 | 0.007792 | 0.0065754 | 0.0001931 | 0.0010235 | N/A | 0.0003318 | 0.87103 | N/A | N/A | 1.1456 | 0.24127 | N/A | 1.1456
CEREAL | Circuit | Distribution | 12.3054 |  | HFTD 3 | 0.015514 | 0.015509 | 4.9853e-06 | 0.012039 | 0.006513 | 0.0016257 | 0.0039001 | N/A | 0.011301 | 1.2883 | N/A | N/A | 1.1783 | 0.00044112 | N/A | 1.1783
CERRITO | Circuit | Distribution | 2.1388 | Top 5% Highest Risk | HFTD 3 | 0.14587 | 0.1458 | 7.2131e-05 | 0.015294 | 0.014252 | 0.00011132 | 0.00093003 | N/A | 0.010364 | 9.5332 | N/A | N/A | 1.1782 | 0.0069595 | N/A | 1.1782
CEYLON | Circuit | Distribution | 2.4189 |  | HFTD 2 | 0.0036797 | 0.0036651 | 1.4546e-05 | 0.0094176 | 0.0039399 | 0.00060577 | 0.0048719 | N/A | 0.00038124 | 0.38918 | N/A | N/A | 1.1474 | 0.038154 | N/A | 1.1474
CHAMPION | Circuit | Distribution | 0.43899 | Top 5% Highest Risk | HFTD 2 | 0.10405 | 0.10405 | 0 | 0.0094243 | 0.0041123 | 0.0012788 | 0.0040331 | N/A | 0.0040129 | 11.0404 | N/A | N/A | 1.0651 | 0 | N/A | 1.0651
CHANTRY | Circuit | Distribution | 7.9419 |  | HFTD 3 | 0.01202 | 0.012005 | 1.4962e-05 | 0.019469 | 0.0081796 | 0.0032247 | 0.0080641 | N/A | 0.0080304 | 0.61666 | N/A | N/A | 1.0521 | 0.0018632 | N/A | 1.0521
CHARDONNAY | Circuit | Distribution | 44.1826 |  | HFTD 3 | 0.029141 | 0.029141 | 5.0904e-07 | 0.0049741 | 0.0034905 | 0.00016419 | 0.0013194 | N/A | 0.0075264 | 5.8585 | N/A | N/A | 1.2249 | 6.7634e-05 | N/A | 1.2249
CHARIOT | Circuit | Distribution | 2.039 |  | HFTD 3 | 0.0040327 | 0.0038266 | 0.00020608 | 0.033025 | 0.027615 | 0.0001966 | 0.0052138 | N/A | 0.024078 | 0.11587 | N/A | N/A | 1.0933 | 0.0085591 | N/A | 1.0933
CHARLIE | Circuit | Distribution | 3.5755 |  | HFTD 2 | 0.0023577 | 0.0020672 | 0.00029053 | 0.0037144 | 0.0018997 | 7.2379e-05 | 0.0017423 | N/A | 0.009177 | 0.55653 | N/A | N/A | 1.293 | 0.031659 | N/A | 1.293
CHARLTON | Circuit | Distribution | 2.6085 |  | HFTD 2 | 0.0023659 | 0.0023079 | 5.7924e-05 | 0.0064548 | 0.0034253 | 0.00043451 | 0.002595 | N/A | 0.0023301 | 0.35756 | N/A | N/A | 1.1286 | 0.02486 | N/A | 1.1286
CHATEAU | Circuit | Distribution | 1.0539 |  | HFTD 2 | 0.0040644 | 0.0040644 | 0 | 0.011257 | 0.0049134 | 0.0010648 | 0.0052787 | N/A | 0.023251 | 0.36106 | N/A | N/A |  | 0 | N/A
CHATTANOOGA | Circuit | Distribution | 2.3379 |  | HFTD 2 | 0.0041767 | 0.0041493 | 2.735e-05 | 0.0029326 | 0.0022156 | 0.00016729 | 0.00054967 | N/A | 0.0039089 | 1.4149 | N/A | N/A | 1.0687 | 0.0069967 | N/A | 1.0687
CHAWA | Circuit | Distribution | 104.2748 |  | HFTD 3 | 0.032311 | 0.03231 | 4.0847e-07 | 0.005647 | 0.0034582 | 8.2472e-05 | 0.0021063 | N/A | 0.0099344 | 5.7217 | N/A | N/A | 1.1602 | 4.1117e-05 | N/A | 1.1602
CHELLA | Circuit | Distribution | 1.1101 |  | HFTD 2 | 0.00024038 | 0.0002351 | 5.2774e-06 | 0.0038432 | 0.001617 | 0.00034461 | 0.0018816 | N/A | 0 | 0.061174 | N/A | N/A | 1.0895 | inf | N/A | 1.0895
CHEVELLE | Circuit | Distribution | 17.9901 |  | HFTD 3 | 0.033618 | 0.033529 | 8.9329e-05 | 0.0048842 | 0.0024956 | 0.00021819 | 0.0021704 | N/A | 0.012723 | 6.8648 | N/A | N/A | 1.2144 | 0.0070211 | N/A | 1.2144
CHICO | Circuit | Distribution | 0.67359 |  | HFTD 2 | 0.0065384 | 0.0065384 | 0 | 0.037181 | 0.019521 | 0.010861 | 0.0067993 | N/A | 0.00011699 | 0.17585 | N/A | N/A | 1.0347 | 0 | N/A | 1.0347
CHILLON | Circuit | Distribution | 9.8123 |  | HFTD 3 | 0.034935 | 0.034896 | 3.8253e-05 | 0.0071817 | 0.0054344 | 0.00064813 | 0.0010991 | N/A | 0.063478 | 4.8591 | N/A | N/A | 1.3457 | 0.00060262 | N/A | 1.3457
CHINA PEAK | Circuit | Distribution | 7.9277 |  | HFTD 3 | 0.0047034 | 0.0047032 | 1.8791e-07 | 0.0094465 | 0.0054772 | 0.0022013 | 0.001768 | N/A | 0.0087514 | 0.49787 | N/A | N/A | 1.125 | 2.1472e-05 | N/A | 1.125
CHOLLA | Circuit | Distribution | 15.5803 |  | HFTD 2 | 0.011904 | 0.011901 | 3.0223e-06 | 0.0025588 | 0.0022221 | 0.00010901 | 0.00022766 | N/A | 0.021876 | 4.6512 | N/A | N/A | 1.2014 | 0.00013815 | N/A | 1.2014
CHUCK WAGON | Circuit | Distribution | 2.1199 |  | HFTD 3 | 0.0072716 | 0.0072388 | 3.2839e-05 | 0.0063025 | 0.0029784 | 0.00026038 | 0.0030637 | N/A | 0.006424 | 1.1486 | N/A | N/A | 1.07 | 0.0051118 | N/A | 1.07
CHUMASH | Circuit | Distribution | 0.45186 |  | HFTD 3 | 0.020588 | 0.02058 | 7.5034e-06 | 0.016465 | 0.0093105 | 0.00025284 | 0.0069021 | N/A | 0.013989 | 1.2499 | N/A | N/A | 1.0515 | 0.0005364 | N/A | 1.0515
CIENIGITAS | Circuit | Distribution | 1.1864 |  | HFTD 2 | 0.0014352 | 0.0013434 | 9.1704e-05 | 0.004541 | 0.0041288 | 0.00028066 | 0.00013157 | N/A | 0.0012919 | 0.29585 | N/A | N/A | 1.0386 | 0.070982 | N/A | 1.0386
CIRCLE | Circuit | Distribution | 13.8319 |  | HFTD 2 | 0.018793 | 0.018793 | 3.6517e-07 | 0.0040886 | 0.0024305 | 0.00010666 | 0.0015514 | N/A | 0.0194 | 4.5964 | N/A | N/A | 1.7341 | 1.8823e-05 | N/A | 1.7341
CISCO | Circuit | Distribution | 0.82962 |  | HFTD 3 | 0.0017259 | 0.0016976 | 2.8382e-05 | 0.0075108 | 0.0048283 | 0.00059093 | 0.0020916 | N/A | 0.0023684 | 0.22602 | N/A | N/A | 1.0861 | 0.011984 | N/A | 1.0861
CITY OF BANNING #2 | Circuit | Distribution | 0.46962 |  | HFTD 3 | 0.0043763 | 0.0043763 | 0 | 0.001357 | 0.00055585 | 3.7907e-05 | 0.00076325 | N/A | 0 | 3.225 | N/A | N/A |  |  | N/A
CLARINET | Circuit | Distribution | 12.4364 |  | HFTD 3 | 0.0092246 | 0.0091829 | 4.1701e-05 | 0.0070272 | 0.0040964 | 0.00012536 | 0.0028055 | N/A | 0.032717 | 1.3068 | N/A | N/A | 1.2025 | 0.0012746 | N/A | 1.2025
CLEMSON | Circuit | Distribution | 3.013 |  | HFTD 2 | 0.003433 | 0.0034051 | 2.7892e-05 | 0.0068681 | 0.0046653 | 0.00041281 | 0.00179 | N/A | 0.0030561 | 0.49578 | N/A | N/A | 1.128 | 0.0091266 | N/A | 1.128
CLOVE | Circuit | Distribution | 6.4947 |  | HFTD 3 | 0.022776 | 0.022774 | 2.049e-06 | 0.0053193 | 0.0033618 | 0.00012876 | 0.0018287 | N/A | 0.008207 | 4.2814 | N/A | N/A | 1.2044 | 0.00024966 | N/A | 1.2044
CLUB OAKS | Circuit | Distribution | 5.89 |  | HFTD 3 | 0.040959 | 0.040959 | 1.572e-07 | 0.0047418 | 0.0031065 | 0.00036115 | 0.0012741 | N/A | 0.0080827 | 8.6377 | N/A | N/A |  | 1.9449e-05 | N/A
CLYDESDALE | Circuit | Distribution | 8.4995 |  | HFTD 2 | 0.017224 | 0.017224 | 0 | 0.0047896 | 0.0034461 | 0.00015602 | 0.0011874 | N/A | 0 | 3.5961 | N/A | N/A | 1.2014 |  | N/A | 1.2014
COACHELLA | Circuit | Distribution | 7.3588 |  | HFTD 2 | 0.0014398 | 0.0014398 | 0 | 0.00032653 | 0.0002079 | 1.8016e-05 | 0.00010061 | N/A | 0.012997 | 4.4095 | N/A | N/A | 1.0902 | 0 | N/A | 1.0902
COBRA | Circuit | Distribution | 2.2286 |  | HFTD 3 | 0.0028137 | 0.0027043 | 0.00010942 | 0.019703 | 0.0094332 | 0.000274 | 0.0099958 | N/A | 0.017086 | 0.13725 | N/A | N/A | 1.0719 | 0.0064043 | N/A | 1.0719
CODONA | Circuit | Distribution | 0.46516 |  | HFTD 2 | 0.019107 | 0.019107 | 0 | 0.017019 | 0.013815 | 0.00068993 | 0.0025146 | N/A | 0 | 1.1227 | N/A | N/A | 1.0623 |  | N/A | 1.0623
COJO | Circuit | Distribution | 6.5366 |  | HFTD 2 | 0.00037527 | 0.00037495 | 3.1971e-07 | 0.0033824 | 0.0016444 | 0.00027163 | 0.0014663 | N/A | 0.021274 | 0.11085 | N/A | N/A | 1.2297 | 1.5028e-05 | N/A | 1.2297
COLDWATER | Circuit | Distribution | 1.5153 |  | HFTD 2 | 5.1647e-05 | 5.1363e-05 | 2.8393e-07 | 0.0078319 | 0.0044969 | 0.00073559 | 0.0025993 | N/A | 0.0026048 | 0.0065582 | N/A | N/A | 1.1908 | 0.000109 | N/A | 1.1908
COLLIER | Circuit | Distribution | 7.7872 |  | HFTD 3 | 0.010191 | 0.010188 | 3.4728e-06 | 0.0038584 | 0.002656 | 7.3635e-05 | 0.0011288 | N/A | 0.0023484 | 2.6404 | N/A | N/A | 1.0743 | 0.0014788 | N/A | 1.0743
COLLINS | Circuit | Distribution | 0.9982 |  | HFTD 3 | 0.0018053 | 0.0014516 | 0.00035373 | 0.022841 | 0.0067894 | 0.00022661 | 0.015825 | N/A | 0.017817 | 0.063553 | N/A | N/A | 1.048 | 0.019854 | N/A | 1.048
COLT | Circuit | Distribution | 0.96782 |  | HFTD 2 | 0.012981 | 0.012977 | 4.019e-06 | 0.0075996 | 0.0037515 | 0.00052579 | 0.0033223 | N/A | 0.0029321 | 1.7076 | N/A | N/A | 1.0541 | 0.0013707 | N/A | 1.0541
CONCEPCION | Circuit | Distribution | 36.3936 |  | HFTD 2 | 0.00092052 | 0.00091871 | 1.8049e-06 | 0.0040164 | 0.0020809 | 0.00040877 | 0.0015268 | N/A | 0.060877 | 0.22874 | N/A | N/A | 1.222 | 2.9649e-05 | N/A | 1.222
CONCORD | Circuit | Distribution | 1.4478 |  | HFTD 2 | 0.0036835 | 0.0036835 | 0 | 0.015866 | 0.0061076 | 0.0041658 | 0.0055923 | N/A | 0 | 0.23216 | N/A | N/A | 1.0296 |  | N/A | 1.0296
CONDOR | Circuit | Distribution | 71.5999 |  | HFTD 3 | 0.041983 | 0.041982 | 8.4752e-07 | 0.0050715 | 0.0029673 | 0.00031054 | 0.0017936 | N/A | 0.027742 | 8.2781 | N/A | N/A | 1.5908 | 3.055e-05 | N/A | 1.5908
CONEJO | Circuit | Distribution | 1.8088 |  | HFTD 3 | 0.00055452 | 0.00051489 | 3.963e-05 | 0.020239 | 0.012031 | 0.00030867 | 0.0078996 | N/A | 0.0064715 | 0.02544 | N/A | N/A | 1.046 | 0.0061237 | N/A | 1.046
CONESTOGA | Circuit | Distribution | 11.2045 |  | HFTD 2 | 0.0062595 | 0.0062551 | 4.3277e-06 | 0.0055341 | 0.0036322 | 9.4982e-05 | 0.001807 | N/A | 0.0047314 | 1.1303 | N/A | N/A | 1.1305 | 0.00091468 | N/A | 1.1305
CONFERENCE | Circuit | Distribution | 1.0066 |  | HFTD 3 | 0.018566 | 0.018566 | 0 | 0.02187 | 0.012357 | 0.0035103 | 0.0060025 | N/A | 0 | 0.84894 | N/A | N/A | 1.5318 |  | N/A | 1.5318
CONINE | Circuit | Distribution | 8.2198 |  | HFTD 3 | 0.022053 | 0.022048 | 5.6217e-06 | 0.011149 | 0.0044862 | 8.6913e-05 | 0.0065756 | N/A | 0.008228 | 1.9776 | N/A | N/A | 1.0938 | 0.00068324 | N/A | 1.0938
CONWAY | Circuit | Distribution | 18.9163 |  | HFTD 2 | 0.0016965 | 0.0016897 | 6.8936e-06 | 0.0016426 | 0.0010455 | 7.6839e-05 | 0.00052027 | N/A | 0.090311 | 1.0286 | N/A | N/A | 1.501 | 7.6331e-05 | N/A | 1.501
COOLER | Circuit | Distribution | 0.80539 |  | HFTD 3 | 0.013397 | 0.01318 | 0.00021694 | 0.0029728 | 0.0014234 | 0.00010282 | 0.0014466 | N/A | 0.021943 | 4.4336 | N/A | N/A | 1.1209 | 0.0098866 | N/A | 1.1209
COOLEY | Circuit | Distribution | 1.869 |  | HFTD 2 | 0.0019967 | 0.0017359 | 0.00026085 | 0.0036405 | 0.0019158 | 0.00010027 | 0.0016245 | N/A | 0.0021793 | 0.47683 | N/A | N/A | 1.0568 | 0.11969 | N/A | 1.0568
COPPERHEAD | Circuit | Distribution | 0.99855 |  | HFTD 3 | 0.00031458 | 0.00022178 | 9.2796e-05 | 0.027566 | 0.0087013 | 0.00011091 | 0.018754 | N/A | 0.0073864 | 0.0080455 | N/A | N/A | 1.0634 | 0.012563 | N/A | 1.0634
CORINTH | Circuit | Distribution | 4.8859 | Top 5% Highest Risk | HFTD 2 | 0.06974 | 0.06974 | 0 | 0.014865 | 0.014241 | 5.609e-05 | 0.00056742 | N/A | 0.0023298 | 4.6916 | N/A | N/A | 1.0733 | 0 | N/A | 1.0733
CORNWALL | Circuit | Distribution | 3.038 |  | HFTD 2 | 0.0058352 | 0.0058335 | 1.6746e-06 | 0.011758 | 0.0025045 | 0.00013701 | 0.0091168 | N/A | 0.00052227 | 0.49612 | N/A | N/A | 1.0914 | 0.0032063 | N/A | 1.0914
CORONITA | Circuit | Distribution | 0.52035 |  | HFTD 3 | 0.015316 | 0.014835 | 0.00048082 | 0.014806 | 0.0081185 | 0.00024728 | 0.00644 | N/A | 0.014229 | 1.002 | N/A | N/A | 1.1193 | 0.033791 | N/A | 1.1193
CORSAIR | Circuit | Distribution | 87.9668 |  | HFTD 3 | 0.011213 | 0.011213 | 1.4637e-07 | 0.0038203 | 0.0031605 | 7.3838e-05 | 0.00058588 | N/A | 0.0070934 | 2.9352 | N/A | N/A | 1.151 | 2.0635e-05 | N/A | 1.151
CORTESE | Circuit | Distribution | 2.4706 |  | HFTD 3 | 0.013648 | 0.013646 | 2.1307e-06 | 0.022388 | 0.014065 | 0.00041127 | 0.0079116 | N/A | 0.0064582 | 0.60953 | N/A | N/A | 1.0491 | 0.00032992 | N/A | 1.0491
COTTAGE GROVE | Circuit | Distribution | 4.2263 |  | HFTD 3 | 0.041407 | 0.041367 | 3.9403e-05 | 0.012287 | 0.0088754 | 0.0015963 | 0.0018157 | N/A | 0.046899 | 3.3666 | N/A | N/A | 1.0712 | 0.00084017 | N/A | 1.0712
COULTER | Circuit | Distribution | 1.112 |  | HFTD 3 | 0.0049882 | 0.0049881 | 9.355e-08 | 0.0077462 | 0.0037587 | 0.00069683 | 0.0032907 | N/A | 0.020065 | 0.64395 | N/A | N/A | 2 | 4.6625e-06 | N/A | 2
COVE | Circuit | Distribution | 3.5198 |  | HFTD 2 | 0.0095108 | 0.0085039 | 0.0010069 | 0.020723 | 0.016391 | 0.00023491 | 0.0040971 | N/A | 0.051655 | 0.41035 | N/A | N/A | 1.5247 | 0.019493 | N/A | 1.5247
COVENTRY | Circuit | Distribution | 21.061 |  | HFTD 3 | 0.016734 | 0.016724 | 1.0155e-05 | 0.0059011 | 0.0030018 | 0.0002544 | 0.0026449 | N/A | 0.021369 | 2.834 | N/A | N/A | 1.0447 | 0.00047523 | N/A | 1.0447
COVEVIEW | Circuit | Distribution | 2.1113 |  | HFTD 2 | 0.0041834 | 0.0041743 | 9.1671e-06 | 0.017843 | 0.01204 | 0.002213 | 0.0035897 | N/A | 0.0053506 | 0.23395 | N/A | N/A | 1.1379 | 0.0017133 | N/A | 1.1379
CRAB | Circuit | Distribution | 6.5722 |  | HFTD 3 | 0.042668 | 0.042668 | 0 | 0.014555 | 0.0091476 | 0.0012089 | 0.0041986 | N/A | 0.019942 | 2.9315 | N/A | N/A |  | 0 | N/A
CRABTREE | Circuit | Distribution | 4.0085 |  | HFTD 3 | 0.0016209 | 0.0016034 | 1.7525e-05 | 0.0070458 | 0.003339 | 0.00013631 | 0.0035705 | N/A | 0.0046342 | 0.22756 | N/A | N/A | 1.0732 | 0.0037818 | N/A | 1.0732
CRAM | Circuit | Distribution | 5.9363 |  | HFTD 3 | 0.0065174 | 0.0064153 | 0.00010204 | 0.0026777 | 0.0019173 | 5.7162e-05 | 0.00070329 | N/A | 0.010032 | 2.3958 | N/A | N/A | 1.1318 | 0.010171 | N/A | 1.1318
CRAWFORD | Circuit | Distribution | 0.76661 | Top 5% Highest Risk | HFTD 2 | 0.13777 | 0.1376 | 0.0001695 | 0.026473 | 0.017056 | 0.0036609 | 0.0057564 | N/A | 0.028091 | 5.1976 | N/A | N/A | 1.6352 | 0.0060342 | N/A | 1.6352
CRESCENTA | Circuit | Distribution | 24.4118 |  | HFTD 2 | 0.017855 | 0.017832 | 2.2955e-05 | 0.013397 | 0.0070822 | 0.0027059 | 0.0036091 | N/A | 0.037931 | 1.331 | N/A | N/A | 1.4458 | 0.00060517 | N/A | 1.4458
CRESTLINE | Circuit | Distribution | 12.3546 | Top 5% Highest Risk | HFTD 3 | 0.081946 | 0.081876 | 6.9873e-05 | 0.017071 | 0.0080871 | 0.0040406 | 0.0049435 | N/A | 0.083003 | 4.7962 | N/A | N/A | 1.2957 | 0.00084181 | N/A | 1.2957
CRESTWIND | Circuit | Distribution | 3.6421 |  | HFTD 2 | 0.0022689 | 0.0022689 | 0 | 0.013725 | 0.0089148 | 0.0017975 | 0.0030125 | N/A | 0.0013376 | 0.16532 | N/A | N/A | 1.3366 | 0 | N/A | 1.3366
CROFT | Circuit | Distribution | 4.6124 |  | HFTD 2 | 0.0057861 | 0.0057668 | 1.9255e-05 | 0.0075252 | 0.0050427 | 0.00051917 | 0.0019633 | N/A | 0.0050354 | 0.76634 | N/A | N/A | 1.0489 | 0.003824 | N/A | 1.0489
CROSBY | Circuit | Distribution | 1.4498 |  | HFTD 2 | 0.0076245 | 0.0076105 | 1.4006e-05 | 0.015633 | 0.0099856 | 0.00066361 | 0.0049841 | N/A | 0.0018815 | 0.48681 | N/A | N/A | 1.3991 | 0.0074441 | N/A | 1.3991
CROSSON | Circuit | Distribution | 9.9293 |  | HFTD 2 | 0.011944 | 0.011932 | 1.2189e-05 | 0.0069871 | 0.0033699 | 0.00025576 | 0.0033614 | N/A | 0.0038112 | 1.7077 | N/A | N/A | 1.0621 | 0.0031981 | N/A | 1.0621
CROWLEY | Circuit | Distribution | 15.7526 |  | HFTD 2 | 0.0017721 | 0.0017491 | 2.2975e-05 | 0.0027974 | 0.0019473 | 0.00016069 | 0.00068936 | N/A | 0.057298 | 0.62528 | N/A | N/A | 1.3299 | 0.00040097 | N/A | 1.3299
CRUMNER | Circuit | Distribution | 11.772 |  | HFTD 3 | 0.013072 | 0.013048 | 2.4229e-05 | 0.0095309 | 0.0049597 | 0.0010319 | 0.0035392 | N/A | 0.017655 | 1.369 | N/A | N/A | 1.0389 | 0.0013724 | N/A | 1.0389
CRUMP | Circuit | Distribution | 4.8696 |  | HFTD 3 | 0.015457 | 0.015441 | 1.6541e-05 | 0.015888 | 0.0086783 | 0.0021194 | 0.00509 | N/A | 0.031368 | 0.97186 | N/A | N/A | 1.278 | 0.00052732 | N/A | 1.278
CRUZ | Circuit | Distribution | 2.0635 |  | HFTD 3 | 0.0065912 | 0.0065664 | 2.4818e-05 | 0.019172 | 0.013211 | 0.0012313 | 0.0047299 | N/A | 0.00055066 | 0.3425 | N/A | N/A | 1.0409 | 0.04507 | N/A | 1.0409
CUDDEBACK | Circuit | Distribution | 22.5298 | Top 5% Highest Risk | HFTD 3 | 0.070026 | 0.070026 | 0 | 0.0089644 | 0.0042765 | 8.3057e-05 | 0.0046049 | N/A | 0.051094 | 7.8116 | N/A | N/A | 1.0444 | 0 | N/A | 1.0444
CUERVO | Circuit | Distribution | 0.43271 |  | HFTD 2 | 0.0028845 | 0.0027299 | 0.00015459 | 0.012543 | 0.0068541 | 0.00047829 | 0.005211 | N/A | 0.011468 | 0.21764 | N/A | N/A | 1.0786 | 0.01348 | N/A | 1.0786
CUPPLES | Circuit | Distribution | 1.7316 |  | HFTD 2 | 0.00021697 | 0.00021625 | 7.2301e-07 | 7.3764e-05 | 2.5176e-05 | 2.3691e-06 | 4.6219e-05 | N/A | 0.0033313 | 2.9316 | N/A | N/A | 1.1667 | 0.00021704 | N/A | 1.1667
CUSHENBURY | Circuit | Distribution | 8.0852 |  | HFTD 2 | 0.015976 | 0.015975 | 3.4029e-07 | 0.0023783 | 0.00094255 | 9.6605e-05 | 0.0013391 | N/A | 0.02274 | 6.7172 | N/A | N/A | 1 | 1.4965e-05 | N/A | 1
CUTHBERT | Circuit | Distribution | 22.8261 |  | HFTD 3 | 0.018465 | 0.018441 | 2.4164e-05 | 0.012152 | 0.0078287 | 0.00080807 | 0.0035153 | N/A | 0.03754 | 1.5175 | N/A | N/A | 1.0945 | 0.00064368 | N/A | 1.0945
CUYAMA | Circuit | Distribution | 39.7801 |  | HFTD 2 | 0.00062671 | 0.00062668 | 2.6855e-08 | 0.0022045 | 0.0013418 | 0.00022494 | 0.00063774 | N/A | 0.010974 | 0.28427 | N/A | N/A | 1.012 | 2.4472e-06 | N/A | 1.012
DALBA | Circuit | Distribution | 9.8835 |  | HFTD 3 | 0.026483 | 0.026455 | 2.847e-05 | 0.014915 | 0.011138 | 0.002144 | 0.0016331 | N/A | 0.034779 | 1.7737 | N/A | N/A | 1.0873 | 0.00081859 | N/A | 1.0873
DARTMOUTH | Circuit | Distribution | 16.5544 |  | HFTD 3 | 0.014867 | 0.014845 | 2.1389e-05 | 0.0066168 | 0.0047163 | 0.00063975 | 0.0012607 | N/A | 0.019381 | 2.2436 | N/A | N/A | 1.198 | 0.0011036 | N/A | 1.198
DAVENPORT | Circuit | Distribution | 77.4036 | Top 5% Highest Risk | HFTD 3 | 0.088548 | 0.088547 | 1.3401e-06 | 0.0094124 | 0.0064454 | 6.8026e-05 | 0.002899 | N/A | 0.033028 | 9.4074 | N/A | N/A | 1.1516 | 4.0576e-05 | N/A | 1.1516
DEACON | Circuit | Distribution | 3.4267 |  | HFTD 2 | 0.0012037 | 0.0011855 | 1.8136e-05 | 0.0053361 | 0.0026628 | 0.00011325 | 0.0025601 | N/A | 0.0010993 | 0.22217 | N/A | N/A | 1.0977 | 0.016497 | N/A | 1.0977
DEALER | Circuit | Distribution | 41.3791 |  | HFTD 2 | 0.024248 | 0.024229 | 1.9491e-05 | 0.003895 | 0.0021567 | 2.5186e-05 | 0.0017131 | N/A | 0.029282 | 6.2204 | N/A | N/A | 1.1764 | 0.00066564 | N/A | 1.1764
DEL CARBON | Circuit | Distribution | 10.9304 |  | HFTD 3 | 0.027076 | 0.027073 | 2.7016e-06 | 0.0077665 | 0.0033355 | 9.34e-05 | 0.0043376 | N/A | 0.0060387 | 3.4859 | N/A | N/A | 1.2431 | 0.00044738 | N/A | 1.2431
DELUZ | Circuit | Distribution | 12.1543 |  | HFTD 3 | 0.0089131 | 0.008913 | 7.7136e-08 | 0.0063802 | 0.0042489 | 0.00025257 | 0.0018787 | N/A | 0.0039047 | 1.397 | N/A | N/A | 1.0747 | 1.9755e-05 | N/A | 1.0747
DENTAL | Circuit | Distribution | 2.558 |  | HFTD 2 | 0.0090324 | 0.0090269 | 5.5621e-06 | 0.0064457 | 0.0047071 | 0.0002465 | 0.0014921 | N/A | 0.0010875 | 1.4005 | N/A | N/A | 1.1899 | 0.0051145 | N/A | 1.1899
DEVILS GATE | Circuit | Distribution | 4.5085 |  | HFTD 2 | 0.0050029 | 0.0049705 | 3.2377e-05 | 0.009634 | 0.0046312 | 0.001007 | 0.0039958 | N/A | 0.0066588 | 0.51593 | N/A | N/A | 1.0964 | 0.0048623 | N/A | 1.0964
DEVINE | Circuit | Distribution | 8.1463 |  | HFTD 3 | 0.00060849 | 0.00056587 | 4.2624e-05 | 0.013407 | 0.0068395 | 0.0006038 | 0.0059635 | N/A | 0.010299 | 0.042207 | N/A | N/A | 1.0507 | 0.0041385 | N/A | 1.0507
DICE | Circuit | Distribution | 6.005 | Top 5% Highest Risk | HFTD 2 | 0.053912 | 0.053912 | 2.7267e-07 | 0.0099312 | 0.0020461 | 0.0012243 | 0.0066608 | N/A | 0.024959 | 5.4286 | N/A | N/A | 1.6667 | 1.0925e-05 | N/A | 1.6667
DILL | Circuit | Distribution | 0.42584 |  | HFTD 2 | 0.0041123 | 0.004035 | 7.7251e-05 | 0.0040106 | 0.0022813 | 0.00016545 | 0.0015639 | N/A | 0.0040776 | 1.0061 | N/A | N/A | 1.1418 | 0.018945 | N/A | 1.1418
DINELY | Circuit | Distribution | 4.4989 |  | HFTD 3 | 0.026369 | 0.026369 | 6.976e-09 | 0.0045337 | 0.0029885 | 7.0094e-05 | 0.0014751 | N/A | 0.028196 | 5.8162 | N/A | N/A | 2 | 2.4741e-07 | N/A | 2
DINKEY CREEK | Circuit | Distribution | 7.4747 |  | HFTD 3 | 0.0014912 | 0.001491 | 1.7319e-07 | 0.0064751 | 0.0026644 | 0.0029069 | 0.00090377 | N/A | 0.0038562 | 0.23027 | N/A | N/A | 1.2614 | 4.4911e-05 | N/A | 1.2614
DOBLE | Circuit | Distribution | 18.721 |  | HFTD 2 | 0.0023321 | 0.002332 | 7.962e-08 | 0.0010822 | 0.00057421 | 0.00010334 | 0.0004047 | N/A | 0.023424 | 2.1548 | N/A | N/A | 1 | 3.3991e-06 | N/A | 1
DOCTORS | Circuit | Distribution | 3.8678 |  | HFTD 2 | 0.015253 | 0.01523 | 2.3705e-05 | 0.0062416 | 0.0031905 | 0.00018789 | 0.0028632 | N/A | 0.003819 | 2.4401 | N/A | N/A | 1.1191 | 0.0062071 | N/A | 1.1191
DOLORES | Circuit | Distribution | 1.7933 |  | HFTD 3 | 0.021846 | 0.021832 | 1.3467e-05 | 0.022175 | 0.014148 | 0.00095816 | 0.0070692 | N/A | 0.013961 | 0.98453 | N/A | N/A | 1.6831 | 0.00096456 | N/A | 1.6831
DOLPHIN | Circuit | Distribution | 1.4148 |  | HFTD 2 | 0.00056629 | 0.00056613 | 1.6436e-07 | 0.0013661 | 0.0010653 | 3.0571e-05 | 0.00027016 | N/A | 0.0012309 | 0.41442 | N/A | N/A | 1.1875 | 0.00013353 | N/A | 1.1875
DOMIC | Circuit | Distribution | 8.3471 |  | HFTD 2 | 0.0052418 | 0.0051973 | 4.4412e-05 | 0.0052498 | 0.0020628 | 0.0010618 | 0.0021252 | N/A | 0.002551 | 0.99 | N/A | N/A | 1.1304 | 0.017409 | N/A | 1.1304
DONLON | Circuit | Distribution | 7.1732 |  | HFTD 3 | 0.0038982 | 0.0038827 | 1.5523e-05 | 0.005761 | 0.0024747 | 0.00031697 | 0.0029693 | N/A | 0.0026731 | 0.67396 | N/A | N/A | 1.162 | 0.0058071 | N/A | 1.162
DONNER | Circuit | Distribution | 3.2731 |  | HFTD 3 | 0.0064963 | 0.0064872 | 9.1051e-06 | 0.0056384 | 0.0029878 | 0.00017041 | 0.0024802 | N/A | 0.0018057 | 1.1505 | N/A | N/A | 1.055 | 0.0050425 | N/A | 1.055
DOROF | Circuit | Distribution | 0.73426 |  | HFTD 2 | 0.00031039 | 0.00029123 | 1.9164e-05 | 0.0017028 | 0.0016058 | 8.4205e-07 | 9.6242e-05 | N/A | 0.00049268 | 0.17103 | N/A | N/A | 1.12 | 0.038897 | N/A | 1.12
DOWELL | Circuit | Distribution | 1.2628 |  | HFTD 2 | 0.00097845 | 0.00097845 | 0 | 0.0091042 | 0.0062767 | 0.00055291 | 0.0022746 | N/A | 0 | 0.10747 | N/A | N/A | 1.198 |  | N/A | 1.198
DREYER | Circuit | Distribution | 1.2175 |  | HFTD 2 | 0.0021891 | 0.0020855 | 0.00010355 | 0.0088383 | 0.0029712 | 0.0025778 | 0.0032893 | N/A | 0.0017144 | 0.23597 | N/A | N/A | 1.2317 | 0.060401 | N/A | 1.2317
DRILLER | Circuit | Distribution | 5.6037 |  | HFTD 3 | 0.0032908 | 0.0032908 | 0 | 0.0082629 | 0.0029051 | 5.3095e-05 | 0.0053047 | N/A | 0 | 0.39827 | N/A | N/A | 1.0728 |  | N/A | 1.0728
DRINKWATER | Circuit | Distribution | 2.326 |  | HFTD 3 | 0.0074848 | 0.0074847 | 1.2244e-07 | 0.0030287 | 0.0013328 | 0.00011555 | 0.0015804 | N/A | 0.012039 | 2.4712 | N/A | N/A | 1.6707 | 1.017e-05 | N/A | 1.6707
DRISKILL | Circuit | Distribution | 19.5884 |  | HFTD 3 | 0.026887 | 0.026877 | 9.7524e-06 | 0.012188 | 0.004509 | 0.00058186 | 0.0070974 | N/A | 0.0054679 | 2.2052 | N/A | N/A | 1.1548 | 0.0017836 | N/A | 1.1548
DUFFER | Circuit | Distribution | 1.0362 |  | HFTD 3 | 0.0019785 | 0.0018985 | 8.001e-05 | 0.007973 | 0.0039378 | 0.00090268 | 0.0031325 | N/A | 0.00057379 | 0.23811 | N/A | N/A | 1.0808 | 0.13944 | N/A | 1.0808
DUKE | Circuit | Distribution | 3.5413 |  | HFTD 2 | 0.016878 | 0.016793 | 8.477e-05 | 0.0040309 | 0.0021175 | 0.00024698 | 0.0016664 | N/A | 0.007001 | 4.1661 | N/A | N/A | 1.1244 | 0.012108 | N/A | 1.1244
DWP DRINKWATER | Circuit | Distribution | 0.6272 |  | HFTD 3 | 0.025025 | 0.025025 | 0 | 0.0054964 | 0.0038177 | 9.8022e-05 | 0.0015807 | N/A | 0.0035153 | 4.5529 | N/A | N/A |  | 0 | N/A
DYNAMO | Circuit | Distribution | 15.4538 |  | HFTD 2 | 0.0019376 | 0.0019372 | 3.5881e-07 | 0.0010853 | 0.0005716 | 5.7623e-05 | 0.00045607 | N/A | 0.11148 | 1.785 | N/A | N/A | 1.6316 | 3.2187e-06 | N/A | 1.6316
DYSART | Circuit | Distribution | 12.8367 | Top 5% Highest Risk | HFTD 2 | 0.075032 | 0.075032 | 4.2751e-07 | 0.0085264 | 0.0011484 | 0.00015964 | 0.0072184 | N/A | 0.02848 | 8.7999 | N/A | N/A | 1.4113 | 1.5011e-05 | N/A | 1.4113
EAGLE CREST | Circuit | Distribution | 9.7164 |  | HFTD 3 | 0.027165 | 0.027165 | 1.0683e-07 | 0.0045204 | 0.002852 | 0.00021528 | 0.0014531 | N/A | 0.0047363 | 6.0094 | N/A | N/A | 1.0317 | 2.2555e-05 | N/A | 1.0317
EASTER | Circuit | Distribution | 9.0284 |  | HFTD 2 | 0.011169 | 0.011156 | 1.3471e-05 | 0.0026316 | 0.0018271 | 8.4569e-05 | 0.00071991 | N/A | 0.0070146 | 4.2391 | N/A | N/A | 1.1375 | 0.0019205 | N/A | 1.1375
EBERT | Circuit | Distribution | 2.3427 |  | HFTD 2 | 0.011348 | 0.011332 | 1.6049e-05 | 0.0031096 | 0.0020622 | 0.00016218 | 0.00088523 | N/A | 0.0066882 | 3.6442 | N/A | N/A | 1.1635 | 0.0023996 | N/A | 1.1635
ECHO | Circuit | Distribution | 2.4442 |  | HFTD 3 | 0.0033697 | 0.0030964 | 0.00027327 | 0.01017 | 0.0074067 | 0.00054526 | 0.0022176 | N/A | 0.00072046 | 0.30448 | N/A | N/A | 1.1581 | 0.37929 | N/A | 1.1581
EGMONT | Circuit | Distribution | 0.4045 |  | HFTD 2 | 0.0079905 | 0.0079478 | 4.2679e-05 | 0.019526 | 0.015898 | 0.0011256 | 0.0025022 | N/A | 0.00071972 | 0.40704 | N/A | N/A | 1.2756 | 0.059299 | N/A | 1.2756
EL MIRADOR | Circuit | Distribution | 22.423 |  | HFTD 2 | 0.0042477 | 0.0042477 | 0 | 0.003699 | 0.0016713 | 9.9861e-05 | 0.0019278 | N/A | 0 | 1.1483 | N/A | N/A | 1.0908 |  | N/A | 1.0908
ELAINE | Circuit | Distribution | 0.65127 |  | HFTD 3 | 0.0044669 | 0.0044669 | 0 | 0.0083912 | 0.0038846 | 0.0018166 | 0.00269 | N/A | 0.0023104 | 0.53233 | N/A | N/A | 1.0077 | 0 | N/A | 1.0077
ELECTRA | Circuit | Distribution | 1.4167 |  | HFTD 3 | 0.013125 | 0.013115 | 1.0583e-05 | 0.0066295 | 0.0021492 | 0.00010235 | 0.0043779 | N/A | 0.0057988 | 1.9782 | N/A | N/A | 1.0229 | 0.0018251 | N/A | 1.0229
ELSTER | Circuit | Distribution | 57.1465 |  | HFTD 2 | 0.0057864 | 0.0057862 | 1.2518e-07 | 0.0065111 | 0.0032734 | 0.00021241 | 0.0030253 | N/A | 0.0012188 | 0.88868 | N/A | N/A | 1.164 | 0.00010271 | N/A | 1.164
EMPIRE | Circuit | Distribution | 0.26527 |  | HFTD 3 | 0.022866 | 0.022172 | 0.00069377 | 0.054078 | 0.027009 | 0.0056403 | 0.021429 | N/A | 0.00072732 | 0.41001 | N/A | N/A | 1.0376 | 0.95388 | N/A | 1.0376
ENCANTO | Circuit | Distribution | 5.3668 |  | HFTD 3 | 0.0015833 | 0.0015833 | 0 | 0.0060581 | 0.0033555 | 0.00046364 | 0.002239 | N/A | 0.00055457 | 0.26136 | N/A | N/A | 1.075 | 0 | N/A | 1.075
ENCHANTED | Circuit | Distribution | 6.1734 |  | HFTD 3 | 0.027854 | 0.027829 | 2.5206e-05 | 0.0059032 | 0.0028076 | 0.00021208 | 0.0028835 | N/A | 0.040368 | 4.7142 | N/A | N/A | 1.1264 | 0.00062441 | N/A | 1.1264
ENERGY | Circuit | Distribution | 32.5929 | Top 5% Highest Risk | HFTD 3 | 0.10884 | 0.10879 | 5.4271e-05 | 0.0089514 | 0.0054142 | 6.851e-05 | 0.0034687 | N/A | 0.073766 | 12.1534 | N/A | N/A | 1.3349 | 0.00073572 | N/A | 1.3349
EQUINOX | Circuit | Distribution | 17.7056 |  | HFTD 2 | 0.0012771 | 0.0012766 | 4.5929e-07 | 0.0020133 | 0.0017038 | 2.0297e-05 | 0.00028924 | N/A | 0.0015869 | 0.63408 | N/A | N/A | 1.3674 | 0.00028943 | N/A | 1.3674
ERIN | Circuit | Distribution | 3.8949 |  | HFTD 2 | 0.001969 | 0.0019288 | 4.0239e-05 | 0.011813 | 0.0062283 | 0.0032071 | 0.0023774 | N/A | 0.0026914 | 0.16328 | N/A | N/A | 1.0626 | 0.014951 | N/A | 1.0626
ERRINGER | Circuit | Distribution | 13.6073 |  | HFTD 3 | 0.00051402 | 0.00046892 | 4.5096e-05 | 0.013254 | 0.0093258 | 0.00026156 | 0.0036664 | N/A | 0.011591 | 0.03538 | N/A | N/A | 1.0663 | 0.0038904 | N/A | 1.0663
ERSKINE | Circuit | Distribution | 65.6951 |  | HFTD 3 | 0.020666 | 0.020648 | 1.7319e-05 | 0.003757 | 0.0021441 | 0.00022708 | 0.0013858 | N/A | 0.052321 | 5.4959 | N/A | N/A | 1.1637 | 0.00033101 | N/A | 1.1637
ESCALA | Circuit | Distribution | 8.4661 |  | HFTD 3 | 0.0060412 | 0.0060408 | 4.0297e-07 | 0.0013835 | 0.00065175 | 7.212e-05 | 0.00065959 | N/A | 0.0037772 | 4.3665 | N/A | N/A | 1.2331 | 0.00010668 | N/A | 1.2331
ESCAMILLA | Circuit | Distribution | 0.76045 |  | HFTD 2 | 0.00049069 | 0.00049069 | 0 | 0.014308 | 0.0036286 | 0.00023968 | 0.01044 | N/A | 0 | 0.034295 | N/A | N/A | 1.0489 |  | N/A | 1.0489
ESTABAN | Circuit | Distribution | 15.6579 |  | HFTD 2 | 0.0040355 | 0.0040248 | 1.0722e-05 | 0.0038401 | 0.0023763 | 0.00013338 | 0.0013304 | N/A | 0.0036174 | 1.0481 | N/A | N/A | 1.1213 | 0.002964 | N/A | 1.1213
ETHANAC | Circuit | Distribution | 0.59792 |  | HFTD 2 | 0.025777 | 0.025241 | 0.00053635 | 0.0043474 | 0.0023348 | 0.00021793 | 0.0017946 | N/A | 0.0020272 | 5.8059 | N/A | N/A | 1.0767 | 0.26458 | N/A | 1.0767
EVERETT | Circuit | Distribution | 3.6912 |  | HFTD 3 | 0.002961 | 0.0028945 | 6.6475e-05 | 0.014871 | 0.0050009 | 0.00024256 | 0.0096277 | N/A | 0.0062908 | 0.19464 | N/A | N/A | 1.0549 | 0.010567 | N/A | 1.0549
EVITA | Circuit | Distribution | 4.4458 |  | HFTD 3 | 0.0019451 | 0.0019244 | 2.0726e-05 | 0.0032282 | 0.0017839 | 9.3018e-05 | 0.0013512 | N/A | 0.0066882 | 0.59611 | N/A | N/A | 1.0582 | 0.0030989 | N/A | 1.0582
FACEMASK | Circuit | Distribution | 0.26374 | Top 5% Highest Risk | HFTD 3 | 0.076008 | 0.076008 | 0 | 0.0086391 | 0.0043711 | 0.00019883 | 0.0040693 | N/A | 0.00052904 | 8.798 | N/A | N/A | 1.0787 | 0 | N/A | 1.0787
FAIRLANE | Circuit | Distribution | 1.1819 |  | HFTD 2 | 0.015166 | 0.01328 | 0.0018866 | 0.0061738 | 0.0021339 | 3.9506e-05 | 0.0040004 | N/A | 0.019104 | 2.151 | N/A | N/A | 1.241 | 0.098753 | N/A | 1.241
FANO | Circuit | Distribution | 2.3698 |  | HFTD 2 | 0.023954 | 0.023922 | 3.2205e-05 | 0.009374 | 0.0028864 | 0.0003675 | 0.0061201 | N/A | 0.0019618 | 2.5519 | N/A | N/A | 1.2243 | 0.016416 | N/A | 1.2243
FARMINGTON | Circuit | Distribution | 11.4318 |  | HFTD 2 | 0.013516 | 0.013516 | 0 | 0.0025351 | 0.0021225 | 3.5409e-05 | 0.00037718 | N/A | 0 | 5.3314 | N/A | N/A | 1.0826 |  | N/A | 1.0826
FAYE | Circuit | Distribution | 36.695 |  | HFTD 3 | 0.013785 | 0.013769 | 1.6446e-05 | 0.0038976 | 0.0027803 | 2.1066e-05 | 0.0010962 | N/A | 0.11806 | 3.5326 | N/A | N/A | 1.242 | 0.0001393 | N/A | 1.242
FELDSPAR | Circuit | Distribution | 22.3056 |  | HFTD 2 | 0.0071333 | 0.0071333 | 0 | 0.007469 | 0.0049279 | 0.00083344 | 0.0017076 | N/A | 0 | 0.95506 | N/A | N/A | 1.5004 |  | N/A | 1.5004
FERRARA | Circuit | Distribution | 18.6198 |  | HFTD 3 | 0.017959 | 0.017905 | 5.3319e-05 | 0.0090065 | 0.0057541 | 0.00023378 | 0.0030186 | N/A | 0.071922 | 1.988 | N/A | N/A | 1.2295 | 0.00074134 | N/A | 1.2295
FIELDGATE | Circuit | Distribution | 2.4685 |  | HFTD 2 | 0.0015957 | 0.0015957 | 0 | 0.0070712 | 0.0031735 | 0.00023885 | 0.0036588 | N/A | 0 | 0.22566 | N/A | N/A | 1.1825 |  | N/A | 1.1825
FINGAL | Circuit | Distribution | 41.4794 | Top 5% Highest Risk | HFTD 3 | 0.053532 | 0.053532 | 0 | 0.008805 | 0.0066696 | 0.00011204 | 0.0020234 | N/A | 0.062371 | 6.0797 | N/A | N/A | 1.3854 | 0 | N/A | 1.3854
FIREBIRD | Circuit | Distribution | 12.0618 |  |  | 0.037903 | 0.037903 | 0 | 0.0038944 | 0.0015952 | 0.0003235 | 0.0019757 | N/A |  | 9.7327 | N/A | N/A |  |  | N/A
FLAGSTAFF | Circuit | Distribution | 0.8542 |  | HFTD 2 | 0.014919 | 0.014878 | 4.1348e-05 | 0.012562 | 0.011389 | 8.8571e-05 | 0.0010844 | N/A | 0.0047216 | 1.1844 | N/A | N/A | 1.094 | 0.0087571 | N/A | 1.094
FLANDERS | Circuit | Distribution | 5.902 |  | HFTD 2 | 0.04596 | 0.04596 | 4.6634e-07 | 0.020142 | 0.012969 | 0.0039464 | 0.0032264 | N/A | 0.017298 | 2.2818 | N/A | N/A | 1.6129 | 2.6959e-05 | N/A | 1.6129
FLEETWOOD | Circuit | Distribution | 0.78212 |  | HFTD 2 | 0.0013376 | 0.001198 | 0.00013961 | 0.0048779 | 0.0026003 | 0.00012957 | 0.002148 | N/A | 0.00057807 | 0.24559 | N/A | N/A | 1.1233 | 0.24151 | N/A | 1.1233
FLINTRIDGE | Circuit | Distribution | 5.5837 |  | HFTD 2 | 0.024822 | 0.02482 | 2.2997e-06 | 0.0099772 | 0.0072628 | 0.00062191 | 0.0020925 | N/A | 0.011647 | 2.4876 | N/A | N/A | 1.3664 | 0.00019746 | N/A | 1.3664
FLOODGATE | Circuit | Distribution | 40.9267 |  | HFTD 2 | 0.010326 | 0.010294 | 3.2171e-05 | 0.0017571 | 0.0011357 | 1.0234e-05 | 0.00061118 | N/A | 0.0016539 | 5.8586 | N/A | N/A | 1.1908 | 0.019451 | N/A | 1.1908
FLYCATCHER | Circuit | Distribution | 48.1462 |  | HFTD 3 | 0.042838 | 0.042804 | 3.4277e-05 | 0.0096462 | 0.0026351 | 6.7602e-05 | 0.0069435 | N/A | 0.10593 | 4.4374 | N/A | N/A | 1.1553 | 0.00032359 | N/A | 1.1553
FLYING D | Circuit | Distribution | 58.0947 |  | HFTD 2 | 0.0030238 | 0.0030234 | 4.0828e-07 | 0.0017716 | 0.0012017 | 5.4932e-05 | 0.00051504 | N/A | 0.011484 | 1.7066 | N/A | N/A | 1.0804 | 3.5553e-05 | N/A | 1.0804
FLYNN | Circuit | Distribution | 3.5697 |  | HFTD 2 | 0.0086475 | 0.0086261 | 2.1442e-05 | 0.0074379 | 0.0058209 | 0.00027191 | 0.0013451 | N/A | 0.0017102 | 1.1598 | N/A | N/A | 1.0209 | 0.012537 | N/A | 1.0209
FOOTHILL | Circuit | Distribution | 1.3017 |  | HFTD 2 | 0.0017506 | 0.0017051 | 4.5554e-05 | 0.0052904 | 0.002184 | 0.00080897 | 0.0022974 | N/A | 0.0012315 | 0.3223 | N/A | N/A | 1.0703 | 0.03699 | N/A | 1.0703
FORTRESS | Circuit | Distribution | 0.75557 |  | HFTD 2 | 0.01248 | 0.012191 | 0.00028862 | 0.0051618 | 0.0028276 | 0.00058712 | 0.0017471 | N/A | 0.0033451 | 2.3618 | N/A | N/A | 1.1021 | 0.08628 | N/A | 1.1021
FRISBIE | Circuit | Distribution | 0.87666 |  | HFTD 2 | 0.003104 | 0.0018963 | 0.0012077 | 0.0030277 | 0.0014548 | 2.6365e-05 | 0.0015466 | N/A | 0.0018438 | 0.62632 | N/A | N/A | 1.1754 | 0.65501 | N/A | 1.1754
FRONTIER | Circuit | Distribution | 0.67638 |  | HFTD 3 | 0.0034721 | 0.0034721 | 0 | 0.0052209 | 0.0025819 | 0.000185 | 0.0024539 | N/A | 0 | 0.66504 | N/A | N/A | 1.0942 |  | N/A | 1.0942
FROZEN | Circuit | Distribution | 6.9073 |  | HFTD 3 | 0.0016079 | 0.0016078 | 3.8296e-08 | 0.0006842 | 0.00028056 | 3.0264e-05 | 0.00037338 | N/A | 0.019027 | 2.3499 | N/A | N/A |  | 2.0128e-06 | N/A
FULLBACK | Circuit | Distribution | 0.77573 |  | HFTD 2 | 0.0097206 | 0.0097206 | 0 | 0.0055252 | 0.0045858 | 6.1499e-05 | 0.00087792 | N/A | 0 | 1.7593 | N/A | N/A | 1.0626 |  | N/A | 1.0626
GABBERT | Circuit | Distribution | 9.6063 |  | HFTD 3 | 0.010668 | 0.010604 | 6.4359e-05 | 0.0077064 | 0.0043499 | 0.00014034 | 0.0032162 | N/A | 0.029477 | 1.376 | N/A | N/A | 1.0906 | 0.0021834 | N/A | 1.0906
GALAHAD | Circuit | Distribution | 58.3556 |  | HFTD 3 | 0.010017 | 0.010011 | 6.4386e-06 | 0.0070336 | 0.0045057 | 0.00048761 | 0.0020402 | N/A | 0.042966 | 1.4233 | N/A | N/A | 1.1783 | 0.00014985 | N/A | 1.1783
GALENA | Circuit | Distribution | 1.4735 |  | HFTD 2 | 0.002532 | 0.0020593 | 0.00047267 | 0.004065 | 0.0027285 | 0.00013165 | 0.0012049 | N/A | 0.00086334 | 0.5066 | N/A | N/A | 1.217 | 0.54748 | N/A | 1.217
GAMBLER | Circuit | Distribution | 62.9768 |  | HFTD 2 | 0.021273 | 0.021266 | 6.3158e-06 | 0.0032542 | 0.0015036 | 0.00017644 | 0.0015742 | N/A | 0.049287 | 6.535 | N/A | N/A | 1.3731 | 0.00012814 | N/A | 1.3731
GARBONI | Circuit | Distribution | 6.3292 |  | HFTD 2 | 0.0054173 | 0.0054173 | 0 | 0.0024538 | 0.0019922 | 5.4912e-05 | 0.00040667 | N/A | 0.0011638 | 2.2077 | N/A | N/A | 1.1175 | 0 | N/A | 1.1175
GARDEN | Circuit | Distribution | 2.7506 |  | HFTD 2 | 0.0036633 | 0.0036573 | 5.9935e-06 | 0.0074807 | 0.0057515 | 0.0010141 | 0.00071511 | N/A | 0 | 0.4889 | N/A | N/A | 1.0532 | inf | N/A | 1.0532
GARY - 568 JA | Circuit | Distribution | 0.99256 |  | HFTD 2 | 3.6965e-05 | 3.6965e-05 | 0 | 0.003777 | 0.0013336 | 0.00024796 | 0.0021954 | N/A | 0 | 0.0097869 | N/A | N/A |  |  | N/A
GILLIBRAND | Circuit | Distribution | 12.0348 |  | HFTD 3 | 0.00025728 | 0.00015457 | 0.00010272 | 0.0094672 | 0.0062413 | 0.00095668 | 0.0022692 | N/A | 0.037366 | 0.016327 | N/A | N/A | 1.1687 | 0.0027489 | N/A | 1.1687
GILMAN | Circuit | Distribution | 2.5746 |  | HFTD 3 | 0.0049363 | 0.0049358 | 4.8005e-07 | 0.0020564 | 0.0014346 | 4.5309e-05 | 0.00057646 | N/A | 0.006774 | 2.4002 | N/A | N/A | 1.5333 | 7.0866e-05 | N/A | 1.5333
GINGER | Circuit | Distribution | 19.0737 |  | HFTD 3 | 0.0045989 | 0.0045974 | 1.4087e-06 | 0.0039588 | 0.0018171 | 6.0484e-05 | 0.0020813 | N/A | 0.016081 | 1.1613 | N/A | N/A | 1.367 | 8.7598e-05 | N/A | 1.367
GLASSCOCK | Circuit | Distribution | 16.8559 |  | HFTD 3 | 0.00032998 | 0.00027809 | 5.1892e-05 | 0.01916 | 0.0037521 | 8.8471e-05 | 0.01532 | N/A | 0.015845 | 0.014514 | N/A | N/A | 1.1649 | 0.0032749 | N/A | 1.1649
GLOBE MILLS | Circuit | Distribution | 1.0361 |  | HFTD 2 | 0.0019284 | 0.001727 | 0.00020147 | 0.0031541 | 0.0021175 | 8.6478e-05 | 0.00095018 | N/A | 0.0012045 | 0.54753 | N/A | N/A | 1.157 | 0.16727 | N/A | 1.157
GNATCATCHER | Circuit | Distribution | 58.922 |  | HFTD 3 | 0.025978 | 0.025977 | 1.1361e-06 | 0.0043364 | 0.0031896 | 5.1142e-05 | 0.0010957 | N/A | 0.026 | 5.9905 | N/A | N/A | 1.52 | 4.3696e-05 | N/A | 1.52
GOLDPAN | Circuit | Distribution | 0.30532 |  |  | 0.0097439 | 0.0097439 | 0 | 0.0012235 | 0.00042633 | 4.3188e-05 | 0.00075394 | N/A |  | 7.9642 | N/A | N/A | 1.1682 |  | N/A | 1.1682
GOLDSMITH | Circuit | Distribution | 11.9243 |  | HFTD 3 | 0.0019175 | 0.0018349 | 8.258e-05 | 0.009609 | 0.0043869 | 0.00028204 | 0.00494 | N/A | 0.022684 | 0.19095 | N/A | N/A | 1.1244 | 0.0036405 | N/A | 1.1244
GORGE | Circuit | Distribution | 11.1027 | Top 5% Highest Risk | HFTD 3 | 0.059765 | 0.059751 | 1.4769e-05 | 0.023214 | 0.010289 | 0.00046342 | 0.012462 | N/A | 0.02218 | 2.5739 | N/A | N/A | 1.2365 | 0.00066589 | N/A | 1.2365
GOWAN | Circuit | Distribution | 1.4265 |  | HFTD 2 | 0.0097877 | 0.0094385 | 0.00034923 | 0.0042296 | 0.002917 | 6.2135e-05 | 0.0012505 | N/A | 0.0019085 | 2.2315 | N/A | N/A | 1.1086 | 0.18299 | N/A | 1.1086
GRAHAM | Circuit | Distribution | 3.1424 |  | HFTD 3 | 0.022813 | 0.022813 | 0 | 0.0050022 | 0.0021542 | 0.0001173 | 0.0027307 | N/A | 0.0076011 | 4.5606 | N/A | N/A | 1.1706 | 0 | N/A | 1.1706
GRANDAD | Circuit | Distribution | 12.2465 |  | HFTD 3 | 0.0013955 | 0.0013955 | 5.5372e-09 | 0.0089127 | 0.0047981 | 0.00012679 | 0.0039877 | N/A | 0 | 0.15657 | N/A | N/A | 1.452 | inf | N/A | 1.452
GRANNY SMITH | Circuit | Distribution | 27.4435 |  | HFTD 3 | 0.02434 | 0.02434 | 1.6271e-07 | 0.0054048 | 0.0027069 | 4.3399e-05 | 0.0026545 | N/A | 0.011407 | 4.5034 | N/A | N/A | 1.1391 | 1.4264e-05 | N/A | 1.1391
GRAPEFRUIT | Circuit | Distribution | 0.76629 |  | HFTD 2 | 0.0042666 | 0.0042332 | 3.3376e-05 | 0.0077889 | 0.0041559 | 0.00097502 | 0.0026581 | N/A | 0.00085707 | 0.54349 | N/A | N/A | 1.0389 | 0.038942 | N/A | 1.0389
GRAVEL | Circuit | Distribution | 0.27133 |  | HFTD 3 | 0.00093685 | 0.00093685 | 0 | 0.0039492 | 0.00070616 | 0.00040172 | 0.0028413 | N/A | 0 | 0.23722 | N/A | N/A | 1.0693 |  | N/A | 1.0693
GREAT SALT | Circuit | Distribution | 6.5392 |  | HFTD 2 | 0.0050558 | 0.0050502 | 5.6177e-06 | 0.0012937 | 0.0010225 | 1.5557e-05 | 0.00025573 | N/A | 0.003614 | 3.9036 | N/A | N/A | 1.2031 | 0.0015544 | N/A | 1.2031
GREEN BEAR | Circuit | Distribution | 9.2098 |  | HFTD 3 | 0.006106 | 0.0060818 | 2.4186e-05 | 0.0060351 | 0.0038968 | 0.00040862 | 0.0017297 | N/A | 0.028827 | 1.0077 | N/A | N/A | 1.3621 | 0.00083899 | N/A | 1.3621
GREENWELL | Circuit | Distribution | 1.0058 |  | HFTD 2 | 6.0943e-05 | 6.0656e-05 | 2.8668e-07 | 0.0028713 | 0.001103 | 0.00010776 | 0.0016606 | N/A | 0.004472 | 0.021125 | N/A | N/A | 1.4211 | 6.4106e-05 | N/A | 1.4211
GRENADE | Circuit | Distribution | 2.3317 |  | HFTD 2 | 0.0014632 | 0.0013601 | 0.00010312 | 0.012242 | 0.0082778 | 0.0004521 | 0.0035119 | N/A | 0.0029928 | 0.1111 | N/A | N/A | 1.0414 | 0.034457 | N/A | 1.0414
GRIDLOCK | Circuit | Distribution | 0.89041 |  | HFTD 2 | 0.00035663 | 0.0003497 | 6.9237e-06 | 0.004717 | 0.0016824 | 0.00014308 | 0.0028916 | N/A | 0.0002575 | 0.074136 | N/A | N/A | 1.0757 | 0.026888 | N/A | 1.0757
GROUSE | Circuit | Distribution | 4.455 |  | HFTD 3 | 0.003107 | 0.003107 | 4.5114e-08 | 0.0041444 | 0.0025431 | 0.00067976 | 0.00092152 | N/A | 0.010439 | 0.74968 | N/A | N/A | 1 | 4.3217e-06 | N/A | 1
GRUWELL | Circuit | Distribution | 6.6288 |  | HFTD 2 | 0.01793 | 0.017925 | 5.2798e-06 | 0.003734 | 0.0023253 | 4.1806e-05 | 0.0013669 | N/A | 0.0040546 | 4.8005 | N/A | N/A | 1.1143 | 0.0013022 | N/A | 1.1143
GUARD | Circuit | Distribution | 1.9326 |  | HFTD 2 | 0.0099764 | 0.0099753 | 1.1485e-06 | 0.0060461 | 0.0031498 | 0.00033406 | 0.0025622 | N/A | 0.00075466 | 1.6499 | N/A | N/A | 1.0677 | 0.0015219 | N/A | 1.0677
GUFFY | Circuit | Distribution | 5.2661 | Top 5% Highest Risk | HFTD 3 | 0.075885 | 0.075881 | 3.9688e-06 | 0.016545 | 0.013553 | 0.00042947 | 0.0025634 | N/A | 0.0031625 | 4.5862 | N/A | N/A | 1.0972 | 0.001255 | N/A | 1.0972
GUINNESS | Circuit | Distribution | 0.51232 |  | HFTD 2 | 0.040542 | 0.040376 | 0.00016529 | 0.004567 | 0.0039996 | 2.9287e-05 | 0.00053811 | N/A | 0.0018818 | 8.8409 | N/A | N/A | 1.1312 | 0.087837 | N/A | 1.1312
GUITAR | Circuit | Distribution | 36.7775 |  | HFTD 3 | 0.0071056 | 0.0071056 | 0 | 0.0068443 | 0.0035891 | 0.00017241 | 0.0030828 | N/A | 0.038959 | 1.0382 | N/A | N/A | 1.1957 | 0 | N/A | 1.1957
GULL LAKE | Circuit | Distribution | 6.1693 |  | HFTD 2 | 0.012151 | 0.012101 | 5.0135e-05 | 0.0048214 | 0.0024547 | 0.00089136 | 0.0014754 | N/A | 0.018372 | 2.5098 | N/A | N/A | 1.2301 | 0.0027289 | N/A | 1.2301
GUNSITE | Circuit | Distribution | 3.124 |  | HFTD 3 | 0.00014424 | 0.00014424 | 0 | 0.001601 | 0.00046265 | 0.00015794 | 0.0009804 | N/A | 0.0013376 | 0.090092 | N/A | N/A | 1.75 | 0 | N/A | 1.75
GUSHER | Circuit | Distribution | 2.2608 |  | HFTD 2 | 0.004628 | 0.004628 | 0 | 0.0036541 | 0.0024065 | 0.00019347 | 0.0010541 | N/A | 0 | 1.2666 | N/A | N/A | 1.049 |  | N/A | 1.049
GUST | Circuit | Distribution | 28.5373 |  | HFTD 3 | 0.0090243 | 0.0090201 | 4.2365e-06 | 0.0028461 | 0.0013198 | 4.0728e-05 | 0.0014856 | N/A | 0.085871 | 3.1693 | N/A | N/A | 1.2359 | 4.9336e-05 | N/A | 1.2359
GUTIERREZ | Circuit | Distribution | 4.8783 |  | HFTD 2 | 0.005699 | 0.0056839 | 1.5049e-05 | 0.0077475 | 0.0058111 | 0.0011636 | 0.00077282 | N/A | 0.011442 | 0.73365 | N/A | N/A | 1.1067 | 0.0013152 | N/A | 1.1067
HACIENDA | Circuit | Distribution | 0.48798 |  | HFTD 3 | 0.00059078 | 0.00018117 | 0.00040961 | 0.018792 | 0.011121 | 0.000544 | 0.007127 | N/A | 0.0034201 | 0.0096407 | N/A | N/A | 1.0816 | 0.11977 | N/A | 1.0816
HACKBERRY | Circuit | Distribution | 6.2388 |  | HFTD 3 | 0.022025 | 0.022025 | 0 | 0.0082796 | 0.0043824 | 0.00020257 | 0.0036947 | N/A | 0 | 2.6602 | N/A | N/A | 1.1717 |  | N/A | 1.1717
HACKLER | Circuit | Distribution | 3.191 |  | HFTD 2 | 0.001504 | 0.001472 | 3.1996e-05 | 0.0072817 | 0.0023413 | 0.00017625 | 0.0047642 | N/A | 0.0077642 | 0.20216 | N/A | N/A | 1.0793 | 0.004121 | N/A | 1.0793
HAMMERHEAD | Circuit | Distribution | 0.75684 |  | HFTD 2 | 0.011735 | 0.011687 | 4.7779e-05 | 0.0040344 | 0.003122 | 5.5285e-05 | 0.00085713 | N/A | 0.0083065 | 2.8969 | N/A | N/A | 1.0454 | 0.005752 | N/A | 1.0454
HAMMOCK | Circuit | Distribution | 8.686 |  | HFTD 2 | 0.012441 | 0.012441 | 6.5936e-08 | 0.002269 | 0.00069633 | 9.2318e-05 | 0.0014804 | N/A | 0.004421 | 5.4831 | N/A | N/A | 1.2 | 1.4914e-05 | N/A | 1.2
HAMPSHIRE | Circuit | Distribution | 24.8132 |  | HFTD 3 | 0.0011587 | 0.0011505 | 8.2363e-06 | 0.0078895 | 0.0034083 | 0.00066497 | 0.0038162 | N/A | 0.010635 | 0.14582 | N/A | N/A | 1.1075 | 0.00077446 | N/A | 1.1075
HANDY | Circuit | Distribution | 1.2142 |  | HFTD 2 | 0.00016149 | 5.0722e-05 | 0.00011077 | 0.0060524 | 0.003836 | 0.00038552 | 0.0018308 | N/A | 0.0030596 | 0.0083805 | N/A | N/A | 1.2643 | 0.036204 | N/A | 1.2643
HARNAGE | Circuit | Distribution | 3.9451 |  | HFTD 2 | 0.0079708 | 0.0079577 | 1.3094e-05 | 0.0073143 | 0.0049876 | 4.2859e-05 | 0.0022839 | N/A | 0.0012614 | 1.088 | N/A | N/A | 1.0759 | 0.010381 | N/A | 1.0759
HASKELL | Circuit | Distribution | 17.426 |  | HFTD 2 | 0.011033 | 0.01103 | 2.7687e-06 | 0.012767 | 0.0067519 | 0.0021728 | 0.0038421 | N/A | 0.014925 | 0.86399 | N/A | N/A | 1.189 | 0.00018551 | N/A | 1.189
HASS | Circuit | Distribution | 19.3628 |  | HFTD 3 | 0.01391 | 0.0139 | 1.0293e-05 | 0.0052991 | 0.0027761 | 0.00042674 | 0.0020962 | N/A | 0.011596 | 2.6231 | N/A | N/A | 1.2636 | 0.00088759 | N/A | 1.2636
HAVEN | Circuit | Distribution | 0.38313 |  | HFTD 2 | 6.3212e-05 | 3.1061e-05 | 3.2152e-05 | 0.0031938 | 0.0016197 | 0.001084 | 0.0004901 | N/A | 0.00066208 | 0.0097251 | N/A | N/A | 1.0696 | 0.048561 | N/A | 1.0696
HEAPS PEAK | Circuit | Distribution | 5.7325 |  | HFTD 3 | 0.024043 | 0.024042 | 7.6858e-07 | 0.011535 | 0.0083417 | 0.0020198 | 0.0011736 | N/A | 0.067817 | 2.0842 | N/A | N/A | 1.5439 | 1.1333e-05 | N/A | 1.5439
HELENA | Circuit | Distribution | 3.792 |  | HFTD 2 | 0.021132 | 0.021117 | 1.5553e-05 | 0.016271 | 0.0065446 | 0.007161 | 0.0025655 | N/A | 0.003083 | 1.2978 | N/A | N/A | 1.098 | 0.0050446 | N/A | 1.098
HELENKA | Circuit | Distribution | 26.0227 |  | HFTD 2 | 0.018732 | 0.018731 | 1.5576e-06 | 0.0039503 | 0.0033673 | 6.0396e-05 | 0.00052265 | N/A | 0.005779 | 4.7415 | N/A | N/A | 1.2405 | 0.00026952 | N/A | 1.2405
HELICOPTER | Circuit | Distribution | 4.6419 |  | HFTD 2 | 0.0099064 | 0.0098918 | 1.4519e-05 | 0.0067237 | 0.0037783 | 7.2049e-05 | 0.0028734 | N/A | 0.0013386 | 1.4712 | N/A | N/A | 1.1098 | 0.010846 | N/A | 1.1098
HEMACINTO | Circuit | Distribution | 0.55711 |  | HFTD 2 | 0.006993 | 0.0068217 | 0.00017132 | 0.030286 | 0.0061889 | 0.0015323 | 0.022565 | N/A | 0.0006856 | 0.22524 | N/A | N/A | 1.1299 | 0.24989 | N/A | 1.1299
HENDERSON | Circuit | Distribution | 5.5519 |  | HFTD 2 | 0.00060284 | 0.00059365 | 9.1826e-06 | 0.0019139 | 0.0012539 | 2.2552e-05 | 0.00063747 | N/A | 0.0037361 | 0.31018 | N/A | N/A | 1.1009 | 0.0024578 | N/A | 1.1009
HERZ | Circuit | Distribution | 1.9258 |  | HFTD 2 | 0.0027319 | 0.0021428 | 0.00058915 | 0.0082827 | 0.0034976 | 0.00023836 | 0.0045468 | N/A | 0.0013803 | 0.25871 | N/A | N/A | 1.1571 | 0.42682 | N/A | 1.1571
HESSION | Circuit | Distribution | 4.4954 |  | HFTD 2 | 0.00070331 | 0.00060866 | 9.4646e-05 | 0.00027001 | 0.00017817 | 9.4039e-06 | 8.2427e-05 | N/A | 0.031955 | 2.2543 | N/A | N/A | 1.2664 | 0.0029619 | N/A | 1.2664
HI LINE | Circuit | Distribution | 18.6867 |  | HFTD 3 | 0.0018413 | 0.0018413 | 0 | 0.0030475 | 0.0013014 | 0.00012746 | 0.0016186 | N/A | 0 | 0.60419 | N/A | N/A | 1.2888 |  | N/A | 1.2888
HIGH SCHOOL | Circuit | Distribution | 7.457 | Top 5% Highest Risk | HFTD 3 | 0.061628 | 0.061603 | 2.5147e-05 | 0.01146 | 0.0073869 | 0.0024909 | 0.0015826 | N/A | 0.058965 | 5.3753 | N/A | N/A | 1.3251 | 0.00042647 | N/A | 1.3251
HIGHBALL | Circuit | Distribution | 2.1997 |  | HFTD 2 | 0.0087825 | 0.0085455 | 0.00023698 | 0.0070321 | 0.003553 | 3.9203e-05 | 0.00344 | N/A | 0.00071144 | 1.2152 | N/A | N/A | 1.1242 | 0.33311 | N/A | 1.1242
HILLARD | Circuit | Distribution | 4.7464 |  | HFTD 2 | 0.024298 | 0.024297 | 7.7596e-07 | 0.013584 | 0.0051713 | 0.0063453 | 0.0020673 | N/A | 0.017099 | 1.7887 | N/A | N/A | 1.235 | 4.5381e-05 | N/A | 1.235
HILLCREST | Circuit | Distribution | 19.4996 |  | HFTD 3 | 0.00060702 | 0.0005985 | 8.5258e-06 | 0.0081863 | 0.0038964 | 0.00019607 | 0.0040938 | N/A | 0.015619 | 0.073109 | N/A | N/A | 1.1739 | 0.00054585 | N/A | 1.1739
HILLFIELD | Circuit | Distribution | 11.0883 |  | HFTD 3 | 0.0019609 | 0.0019219 | 3.9047e-05 | 0.011893 | 0.0071443 | 0.000108 | 0.0046403 | N/A | 0.013107 | 0.1616 | N/A | N/A | 1.1118 | 0.0029791 | N/A | 1.1118
HILTON | Circuit | Distribution | 0.57849 |  | HFTD 2 | 0.017721 | 0.017675 | 4.5994e-05 | 0.029343 | 0.018552 | 0.0016847 | 0.0091058 | N/A | 0.0016787 | 0.60238 | N/A | N/A | 1.2557 | 0.027399 | N/A | 1.2557
HONEYCRISP | Circuit | Distribution | 1.2291 |  | HFTD 2 | 0.0085999 | 0.0084563 | 0.00014356 | 0.0052879 | 0.0031366 | 0.00037145 | 0.0017798 | N/A | 0.0091434 | 1.5992 | N/A | N/A | 1.138 | 0.015701 | N/A | 1.138
HONEYWELL | Circuit | Distribution | 2.8164 |  | HFTD 2 | 0.00055242 | 0.00053616 | 1.6255e-05 | 0.0099165 | 0.0073271 | 0.00062896 | 0.0019605 | N/A | 0.0031302 | 0.054067 | N/A | N/A | 1.0802 | 0.0051931 | N/A | 1.0802
HOOK CREEK | Circuit | Distribution | 4.0874 |  | HFTD 3 | 0.018924 | 0.018924 | 0 | 0.01281 | 0.009101 | 0.00092544 | 0.0027832 | N/A | 0 | 1.4773 | N/A | N/A | 1.1535 |  | N/A | 1.1535
HOOLIGAN | Circuit | Distribution | 8.2886 |  | HFTD 3 | 0.0054382 | 0.0053925 | 4.569e-05 | 0.0090613 | 0.004244 | 0.0005723 | 0.0042449 | N/A | 0.01059 | 0.59512 | N/A | N/A | 1.1543 | 0.0043145 | N/A | 1.1543
HOPE | Circuit | Distribution | 0.32864 |  | HFTD 2 | 0.0071831 | 0.0064275 | 0.00075563 | 0.0032396 | 0.0010824 | 0.00067149 | 0.0014857 | N/A | 0.020047 | 1.984 | N/A | N/A | 1.0978 | 0.037693 | N/A | 1.0978
HORIZON | Circuit | Distribution | 17.2424 |  | HFTD 2 | 0.029964 | 0.029953 | 1.1012e-05 | 0.014801 | 0.0059026 | 0.0016777 | 0.0072204 | N/A | 0.015082 | 2.0238 | N/A | N/A | 1.0484 | 0.00073017 | N/A | 1.0484
HORNTOAD | Circuit | Distribution | 25.9915 |  | HFTD 3 | 0.046615 | 0.046604 | 1.0402e-05 | 0.011808 | 0.0059807 | 0.0015504 | 0.0042766 | N/A | 0.018409 | 3.9469 | N/A | N/A | 1.3975 | 0.00056507 | N/A | 1.3975
HORTON | Circuit | Distribution | 1.2022 |  | HFTD 2 | 0.0020295 | 0.0019811 | 4.8433e-05 | 0.0035039 | 0.0019473 | 0.00011825 | 0.0014384 | N/A | 0.0020509 | 0.5654 | N/A | N/A | 1.0592 | 0.023615 | N/A | 1.0592
HOSPAT | Circuit | Distribution | 1.5 |  | HFTD 2 | 0.0018432 | 0.0016633 | 0.00017993 | 0.010521 | 0.0043789 | 0.00055545 | 0.0055869 | N/A | 0.0020907 | 0.15809 | N/A | N/A | 1.1839 | 0.086063 | N/A | 1.1839
HOSPITAL | Circuit | Distribution | 3.2287 |  | HFTD 3 | 0.0027907 | 0.0027821 | 8.6207e-06 | 0.0087106 | 0.0068214 | 0.00033067 | 0.0015585 | N/A | 0.0068687 | 0.31939 | N/A | N/A | 1.0221 | 0.0012551 | N/A | 1.0221
HOSS | Circuit | Distribution | 3.1758 |  | HFTD 3 | 0.014533 | 0.014264 | 0.00026837 | 0.016554 | 0.0088492 | 0.0018791 | 0.0058253 | N/A | 0.012106 | 0.86171 | N/A | N/A | 1.1235 | 0.022169 | N/A | 1.1235
HOT SPRINGS | Circuit | Distribution | 6.8849 |  | HFTD 2 | 0.013494 | 0.013424 | 7.0817e-05 | 0.013028 | 0.0055751 | 0.0057621 | 0.0016909 | N/A | 0.0054205 | 1.0304 | N/A | N/A | 1.0597 | 0.013065 | N/A | 1.0597
HOVATTER | Circuit | Distribution | 4.0287 |  | HFTD 2 | 0.0005747 | 0.00035062 | 0.00022407 | 0.0093791 | 0.0063058 | 0.00020211 | 0.0028712 | N/A | 0.0082078 | 0.037383 | N/A | N/A | 1.1978 | 0.0273 | N/A | 1.1978
HUBBLE | Circuit | Distribution | 0.84896 |  | HFTD 2 | 0.012076 | 0.0023225 | 0.0097538 | 0.0067156 | 0.0041395 | 0.00019131 | 0.0023848 | N/A | 0.0019165 | 0.34583 | N/A | N/A | 1.102 | 5.0893 | N/A | 1.102
HUCKLEBERRY | Circuit | Distribution | 23.8697 |  | HFTD 3 | 0.03428 | 0.034275 | 5.5017e-06 | 0.0073236 | 0.0023328 | 6.0909e-05 | 0.0049298 | N/A | 0.070403 | 4.68 | N/A | N/A | 1.1691 | 7.8146e-05 | N/A | 1.1691
HUGHES LAKE | Circuit | Distribution | 105.0546 |  | HFTD 3 | 0.031474 | 0.031462 | 1.212e-05 | 0.0064909 | 0.0041711 | 0.00019166 | 0.0021281 | N/A | 0.088635 | 4.8472 | N/A | N/A | 1.2038 | 0.00013674 | N/A | 1.2038
HUGO | Circuit | Distribution | 1.1423 |  | HFTD 3 | 0.0057045 | 0.0057044 | 1.4125e-07 | 0.0028829 | 0.0024084 | 8.315e-05 | 0.00039132 | N/A | 0 | 1.9787 | N/A | N/A | 1.4031 | inf | N/A | 1.4031
HUNTINGTON | Circuit | Distribution | 1.4218 |  |  | 0.00057558 | 0.00057558 | 0 | 0.0061748 | 0.0030879 | 0.0012068 | 0.0018802 | N/A |  | 0.093215 | N/A | N/A | 1 |  | N/A | 1
HURLEY | Circuit | Distribution | 8.2308 |  | HFTD 2 | 0.0094566 | 0.0093849 | 7.1637e-05 | 0.0077992 | 0.0044001 | 0.00049525 | 0.0029038 | N/A | 0.019576 | 1.2033 | N/A | N/A | 1.0541 | 0.0036595 | N/A | 1.0541
HURST | Circuit | Distribution | 22.4107 |  | HFTD 3 | 0.026999 | 0.026979 | 2.0506e-05 | 0.0085717 | 0.0059001 | 0.001015 | 0.0016566 | N/A | 0.025035 | 3.1474 | N/A | N/A | 1.0986 | 0.0008191 | N/A | 1.0986
ICE HOUSE | Circuit | Distribution | 1.3263 |  | HFTD 3 | 0.022322 | 0.02232 | 2.7882e-06 | 0.0063748 | 0.0042619 | 0.00031357 | 0.0017994 | N/A | 0.01836 | 3.5012 | N/A | N/A | 1.0276 | 0.00015187 | N/A | 1.0276
IDA | Circuit | Distribution | 11.3289 |  | HFTD 2 | 0.042373 | 0.042338 | 3.5507e-05 | 0.0044693 | 0.0027378 | 0.00022902 | 0.0015025 | N/A | 0.010171 | 9.473 | N/A | N/A | 1.1149 | 0.0034909 | N/A | 1.1149
INDEPENDENCE | Circuit | Distribution | 1.0635 |  | HFTD 2 | 0.0049492 | 0.0048701 | 7.9097e-05 | 0.0038492 | 0.0022235 | 0.00019568 | 0.00143 | N/A | 0.0054257 | 1.2652 | N/A | N/A | 1.0337 | 0.014578 | N/A | 1.0337
INTAKE | Circuit | Distribution | 34.4686 |  | HFTD 2 | 0.0066985 | 0.0066985 | 0 | 0.0024344 | 0.0013816 | 0.00013743 | 0.00091535 | N/A | 0 | 2.7516 | N/A | N/A | 1.0935 |  | N/A | 1.0935
INTERIOR | Circuit | Distribution | 34.9448 |  | HFTD 3 | 0.0014577 | 0.0014577 | 0 | 0.0024612 | 0.0011006 | 0.00010816 | 0.0012524 | N/A | 0 | 0.59227 | N/A | N/A | 1.1624 |  | N/A | 1.1624
INTERN | Circuit | Distribution | 0.4781 |  | HFTD 3 | 0.0089922 | 0.008911 | 8.1199e-05 | 0.012952 | 0.0076642 | 0.00019126 | 0.0050967 | N/A | 0.0007284 | 0.688 | N/A | N/A | 1.0722 | 0.11148 | N/A | 1.0722
INTERPACE | Circuit | Distribution | 11.4244 |  | HFTD 3 | 0.0022249 | 0.0022247 | 1.4469e-07 | 0.0021012 | 0.0013647 | 3.3111e-05 | 0.00070336 | N/A | 0.0083307 | 1.0588 | N/A | N/A | 1.1667 | 1.7368e-05 | N/A | 1.1667
INTREPID | Circuit | Distribution | 7.7456 |  | HFTD 3 | 0.00056889 | 0.00051549 | 5.3398e-05 | 0.01162 | 0.0051787 | 0.00047754 | 0.0059633 | N/A | 0.014451 | 0.044364 | N/A | N/A | 1.069 | 0.003695 | N/A | 1.069
INVADER | Circuit | Distribution | 10.119 |  | HFTD 2 | 0.0088428 | 0.0084916 | 0.00035125 | 0.013986 | 0.010581 | 0.00013463 | 0.00327 | N/A | 0.062898 | 0.60714 | N/A | N/A | 1.2936 | 0.0055845 | N/A | 1.2936
INYO LUMBER | Circuit | Distribution | 3.5672 |  | HFTD 2 | 0.034981 | 0.034078 | 0.00090313 | 0.0061664 | 0.0045551 | 0.00042619 | 0.0011851 | N/A | 0.023018 | 5.5264 | N/A | N/A | 1.1469 | 0.039236 | N/A | 1.1469
IRAN | Circuit | Distribution | 0.7932 |  | HFTD 2 | 0.00077859 | 0.00057214 | 0.00020645 | 0.012102 | 0.0032226 | 6.1658e-05 | 0.0088175 | N/A | 0.0015938 | 0.047277 | N/A | N/A | 1.2091 | 0.12953 | N/A | 1.2091
IRVINGTON | Circuit | Distribution | 0.29071 |  | HFTD 2 | 0.0024299 | 0.00025202 | 0.0021779 | 0.032333 | 0.008873 | 0.00054047 | 0.022919 | N/A | 0.0016126 | 0.0077947 | N/A | N/A | 1.2874 | 1.3506 | N/A | 1.2874
JADE | Circuit | Distribution | 0.87311 |  | HFTD 3 | 0.0036843 | 0.0035805 | 0.00010377 | 0.0045514 | 0.0022095 | 7.5524e-05 | 0.0022663 | N/A | 0.005689 | 0.78669 | N/A | N/A | 1.134 | 0.01824 | N/A | 1.134
JAKE | Circuit | Distribution | 2.7482 |  | HFTD 2 | 0.044456 | 0.044456 | 5.7502e-07 | 0.011288 | 0.0069314 | 0.002829 | 0.0015272 | N/A | 0.00089057 | 3.9384 | N/A | N/A | 1.011 | 0.00064567 | N/A | 1.011
JARVIS | Circuit | Distribution | 39.278 |  | HFTD 3 | 0.00955 | 0.0095438 | 6.2742e-06 | 0.0046698 | 0.0010617 | 8.3064e-05 | 0.003525 | N/A | 0.023556 | 2.0437 | N/A | N/A | 1.1401 | 0.00026635 | N/A | 1.1401
JEEP | Circuit | Distribution | 21.947 |  | HFTD 3 | 0.019535 | 0.019422 | 0.00011339 | 0.0063481 | 0.0046629 | 0.00047166 | 0.0012136 | N/A | 0.06968 | 3.0594 | N/A | N/A | 1.2811 | 0.0016273 | N/A | 1.2811
JELLYSTONE | Circuit | Distribution | 43.8123 |  | HFTD 2 | 0.038866 | 0.038849 | 1.7704e-05 | 0.0047842 | 0.0032433 | 9.1699e-05 | 0.0014492 | N/A | 0.053906 | 8.1202 | N/A | N/A | 1.2665 | 0.00032843 | N/A | 1.2665
JENKS LAKE | Circuit | Distribution | 15.4728 |  | HFTD 3 | 0.0066487 | 0.0066485 | 1.7477e-07 | 0.010027 | 0.0035389 | 0.0017036 | 0.0047849 | N/A | 0.018055 | 0.66304 | N/A | N/A | 1.1465 | 9.68e-06 | N/A | 1.1465
JERRY | Circuit | Distribution | 4.7308 |  | HFTD 2 | 0.0033254 | 0.0033187 | 6.7219e-06 | 0.0048637 | 0.0022111 | 0.0001544 | 0.0024982 | N/A | 0.00066269 | 0.68233 | N/A | N/A | 1.0449 | 0.010143 | N/A | 1.0449
JERUSALEM | Circuit | Distribution | 1.1101 |  | HFTD 2 | 0.0032776 | 0.0032675 | 1.0189e-05 | 0.0020068 | 0.0014324 | 3.6983e-05 | 0.00053743 | N/A | 0.0023714 | 1.6282 | N/A | N/A | 1.0665 | 0.0042967 | N/A | 1.0665
JOB | Circuit | Distribution | 7.2092 |  | HFTD 3 | 0.027634 | 0.027588 | 4.6439e-05 | 0.0084072 | 0.0037623 | 0.0029103 | 0.0017346 | N/A | 0.050889 | 3.2815 | N/A | N/A | 1.266 | 0.00091257 | N/A | 1.266
JOHNBOY | Circuit | Distribution | 0.34388 |  | HFTD 3 | 0.0068679 | 0.0067202 | 0.00014767 | 0.022954 | 0.0086457 | 0.00034843 | 0.01396 | N/A | 0.0080259 | 0.29276 | N/A | N/A | 1.0309 | 0.018399 | N/A | 1.0309
JOHNSONDALE | Circuit | Distribution | 2.5562 |  | HFTD 2 | 0.00084436 | 0.00084419 | 1.7218e-07 | 0.0032964 | 0.0021238 | 0.0005101 | 0.00066254 | N/A | 0.00048261 | 0.25609 | N/A | N/A | 1.1219 | 0.00035677 | N/A | 1.1219
JORDAN | Circuit | Distribution | 206.9191 |  | HFTD 2 | 0.001501 | 0.0015009 | 1.2782e-07 | 0.001574 | 0.00058939 | 0.00027995 | 0.00070466 | N/A | 0.014423 | 0.95355 | N/A | N/A | 1.1876 | 8.8622e-06 | N/A | 1.1876
JUAREZ | Circuit | Distribution | 1.2779 |  | HFTD 2 | 0.0097194 | 0.0097113 | 8.0681e-06 | 0.012806 | 0.004375 | 0.00063503 | 0.0077964 | N/A | 0.00055494 | 0.75832 | N/A | N/A | 1.0598 | 0.014539 | N/A | 1.0598
JUBILEE | Circuit | Distribution | 0.6861 |  | HFTD 2 | 0.0038045 | 0.0037321 | 7.2402e-05 | 0.0074008 | 0.0029805 | 0.00036606 | 0.0040542 | N/A | 0.0022633 | 0.50428 | N/A | N/A | 1.0792 | 0.031989 | N/A | 1.0792
JUDSON | Circuit | Distribution | 0.56102 |  | HFTD 2 | 0.0043586 | 0.0042636 | 9.5021e-05 | 0.0078222 | 0.003546 | 0.00011463 | 0.0041616 | N/A | 0.0004081 | 0.54506 | N/A | N/A | 1.052 | 0.23284 | N/A | 1.052
JULIUS | Circuit | Distribution | 7.9473 |  | HFTD 3 | 0.0023046 | 0.002282 | 2.2599e-05 | 0.011197 | 0.0069952 | 0.00010481 | 0.0040969 | N/A | 0.018658 | 0.20381 | N/A | N/A | 1.0577 | 0.0012112 | N/A | 1.0577
JUMBO | Circuit | Distribution | 0.81424 |  | HFTD 3 | 0.00049152 | 0.00049152 | 0 | 0.0064174 | 0.004975 | 0.00036877 | 0.0010737 | N/A | 0.23944 | 0.076592 | N/A | N/A |  | 0 | N/A
JUPITER | Circuit | Distribution | 4.9105 |  | HFTD 2 | 0.0013962 | 0.0013962 | 0 | 0.010951 | 0.0075942 | 0.0019389 | 0.0014178 | N/A | 0 | 0.1275 | N/A | N/A | 1.2979 |  | N/A | 1.2979
KANAN | Circuit | Distribution | 0.59815 |  | HFTD 3 | 0.0097556 | 0.0085955 | 0.00116 | 0.020209 | 0.0078714 | 0.00083326 | 0.011504 | N/A | 0.019886 | 0.42533 | N/A | N/A | 1.0982 | 0.058333 | N/A | 1.0982
KEENE | Circuit | Distribution | 39.6256 |  | HFTD 2 | 0.0040944 | 0.0040896 | 4.8011e-06 | 0.0020505 | 0.0015527 | 2.1086e-05 | 0.00047676 | N/A | 0.0010516 | 1.9944 | N/A | N/A | 1.3685 | 0.0045653 | N/A | 1.3685
KELLER | Circuit | Distribution | 1.2328 | Top 5% Highest Risk | HFTD 2 | 0.067699 | 0.067699 | 0 | 0.021821 | 0.017287 | 0.0016383 | 0.0028964 | N/A | 0 | 3.1024 | N/A | N/A | 1.0908 |  | N/A | 1.0908
KENO | Circuit | Distribution | 55.3396 |  | HFTD 2 | 0.032754 | 0.03271 | 4.3525e-05 | 0.0031665 | 0.0018869 | 2.7803e-05 | 0.0012519 | N/A | 0.042772 | 10.33 | N/A | N/A | 1.4892 | 0.0010176 | N/A | 1.4892
KERRY | Circuit | Distribution | 4.5765 |  | HFTD 2 | 0.0080557 | 0.0080532 | 2.4711e-06 | 0.0090369 | 0.0062155 | 0.00075376 | 0.0020676 | N/A | 0.0039607 | 0.89115 | N/A | N/A | 1.0935 | 0.00062392 | N/A | 1.0935
KEWAMEE | Circuit | Distribution | 1.5849 |  | HFTD 3 | 0.011152 | 0.011104 | 4.8644e-05 | 0.025203 | 0.0043652 | 0.00032065 | 0.020517 | N/A | 0.0040971 | 0.44057 | N/A | N/A | 1.1131 | 0.011873 | N/A | 1.1131
KICKAPOO TRAIL | Circuit | Distribution | 59.7255 |  | HFTD 3 | 0.024144 | 0.024136 | 8.3298e-06 | 0.0047771 | 0.003273 | 0.00012808 | 0.001376 | N/A | 0.050382 | 5.0524 | N/A | N/A | 1.0918 | 0.00016533 | N/A | 1.0918
KILKENNY | Circuit | Distribution | 5.7151 |  | HFTD 2 | 0.0035594 | 0.0035594 | 0 | 0.0070682 | 0.0024634 | 0.00032121 | 0.0042836 | N/A | 0 | 0.50358 | N/A | N/A | 1.0918 |  | N/A | 1.0918
KILTS | Circuit | Distribution | 4.1209 |  | HFTD 2 | 0.0091339 | 0.009114 | 1.9959e-05 | 0.010563 | 0.0083479 | 0.00030502 | 0.00191 | N/A | 0.0030046 | 0.86283 | N/A | N/A | 1.1829 | 0.0066427 | N/A | 1.1829
KIMDALE | Circuit | Distribution | 71.1672 |  | HFTD 2 | 0.02296 | 0.022959 | 8.8516e-07 | 0.0053367 | 0.0048126 | 7.1355e-05 | 0.00045275 | N/A | 0.0097409 | 4.302 | N/A | N/A | 1.2906 | 9.087e-05 | N/A | 1.2906
KINGSFORD | Circuit | Distribution | 1.2272 |  | HFTD 2 | 0.00092005 | 0.00079745 | 0.0001226 | 0.0079762 | 0.0039464 | 0.00052561 | 0.0035043 | N/A | 0.0038922 | 0.099978 | N/A | N/A | 1.0624 | 0.031499 | N/A | 1.0624
KINGTREE | Circuit | Distribution | 0.31886 |  | HFTD 2 | 0.0065237 | 0.0065237 | 0 | 0.0030436 | 0.00097691 | 5.5725e-05 | 0.0020109 | N/A | 0 | 2.1435 | N/A | N/A | 1.1012 |  | N/A | 1.1012
KINNELOA | Circuit | Distribution | 4.6621 |  | HFTD 2 | 0.021093 | 0.021065 | 2.8203e-05 | 0.012028 | 0.0046194 | 0.0014148 | 0.0059941 | N/A | 0.0021449 | 1.7513 | N/A | N/A | 1.1813 | 0.013149 | N/A | 1.1813
KINSEY | Circuit | Distribution | 48.5954 |  | HFTD 2 | 0.0013289 | 0.0013272 | 1.7225e-06 | 0.0018979 | 0.0012954 | 2.9385e-05 | 0.00057314 | N/A | 0.029702 | 0.69929 | N/A | N/A | 1.3641 | 5.7993e-05 | N/A | 1.3641
KIRBY | Circuit | Distribution | 1.2062 |  | HFTD 2 | 0.0032449 | 0.0031186 | 0.00012633 | 0.011343 | 0.0051398 | 0.00042625 | 0.0057768 | N/A | 0.00027308 | 0.27494 | N/A | N/A | 1.0499 | 0.4626 | N/A | 1.0499
KLEVEN | Circuit | Distribution | 2.7127 |  | HFTD 3 | 0.027426 | 0.027411 | 1.4591e-05 | 0.011886 | 0.0069139 | 0.00038109 | 0.0045909 | N/A | 0.0036587 | 2.3062 | N/A | N/A | 1.1264 | 0.003988 | N/A | 1.1264
KONA | Circuit | Distribution | 0.6182 |  | HFTD 2 | 0.0060077 | 0.0015912 | 0.0044165 | 0.0050701 | 0.0025992 | 2.615e-05 | 0.0024448 | N/A | 0.0003509 | 0.31383 | N/A | N/A | 1.0793 | 12.5864 | N/A | 1.0793
KOREA | Circuit | Distribution | 1.4023 |  | HFTD 2 | 0.018017 | 0.017941 | 7.5937e-05 | 0.01065 | 0.0070331 | 0.0010101 | 0.0026064 | N/A | 0.0021704 | 1.6847 | N/A | N/A | 1.2609 | 0.034988 | N/A | 1.2609
KUEHNER | Circuit | Distribution | 6.609 |  | HFTD 3 | 0.0027079 | 0.0025927 | 0.0001152 | 0.013213 | 0.0095153 | 0.00016436 | 0.0035336 | N/A | 0.014163 | 0.19622 | N/A | N/A | 1.1265 | 0.0081334 | N/A | 1.1265
KUFFEL | Circuit | Distribution | 5.2926 |  | HFTD 3 | 0.014876 | 0.014844 | 3.1305e-05 | 0.0083757 | 0.0054019 | 0.0010451 | 0.0019287 | N/A | 0.049493 | 1.7723 | N/A | N/A | 1.1861 | 0.00063252 | N/A | 1.1861
KULBERG | Circuit | Distribution | 1.4776 |  | HFTD 2 | 0.0062941 | 0.0062902 | 3.9083e-06 | 0.0038387 | 0.0032391 | 9.0576e-05 | 0.00050902 | N/A | 0.00056909 | 1.6386 | N/A | N/A | 1.0779 | 0.0068676 | N/A | 1.0779
KWIS | Circuit | Distribution | 0.94906 |  | HFTD 2 | 0.001148 | 0.0011426 | 5.4703e-06 | 0.0048103 | 0.0025227 | 0.00029622 | 0.0019913 | N/A | 9.3062e-05 | 0.23752 | N/A | N/A | 1.0614 | 0.058781 | N/A | 1.0614
LA GRANDE | Circuit | Distribution | 1.2079 | Top 5% Highest Risk | HFTD 2 | 0.062829 | 0.062665 | 0.0001633 | 0.011719 | 0.0045224 | 0.0010325 | 0.0061636 | N/A | 0.0031543 | 5.3475 | N/A | N/A | 1.1127 | 0.051771 | N/A | 1.1127
LA MANCHA | Circuit | Distribution | 8.5853 |  | HFTD 3 | 0.024179 | 0.024169 | 1.0335e-05 | 0.0068472 | 0.004263 | 0.00014971 | 0.0024345 | N/A | 0.01274 | 3.5297 | N/A | N/A | 1.0547 | 0.00081124 | N/A | 1.0547
LA RICA | Circuit | Distribution | 0.44147 |  | HFTD 2 | 0.00083189 | 0.00083081 | 1.0849e-06 | 0.0092628 | 0.007468 | 0.00038303 | 0.0014118 | N/A | 0.0023618 | 0.089693 | N/A | N/A | 1.1404 | 0.00045938 | N/A | 1.1404
LA SIERRA | Circuit | Distribution | 4.8651 |  | HFTD 2 | 0.015936 | 0.015912 | 2.4184e-05 | 0.0025856 | 0.0021651 | 4.7727e-05 | 0.0003728 | N/A | 0.0060454 | 6.154 | N/A | N/A | 1.1322 | 0.0040004 | N/A | 1.1322
LA VACA | Circuit | Distribution | 1.1101 |  | HFTD 3 | 0.0086511 | 0.0083867 | 0.00026446 | 0.031497 | 0.018951 | 0.0012687 | 0.011277 | N/A | 0.015356 | 0.26627 | N/A | N/A | 1.0565 | 0.017222 | N/A | 1.0565
LACRESTA | Circuit | Distribution | 10.1281 |  | HFTD 3 | 0.023003 | 0.023003 | 1.0146e-07 | 0.0042717 | 0.0019607 | 0.00018067 | 0.0021302 | N/A | 0.0092223 | 5.3851 | N/A | N/A | 1.0928 | 1.1002e-05 | N/A | 1.0928
LAKELAND | Circuit | Distribution | 19.9607 |  | HFTD 2 | 0.0035499 | 0.0035416 | 8.3332e-06 | 0.0041358 | 0.0025498 | 0.0006197 | 0.00096632 | N/A | 0.00683 | 0.85632 | N/A | N/A | 1.0681 | 0.0012201 | N/A | 1.0681
LAMANDA | Circuit | Distribution | 7.1367 |  | HFTD 3 | 0.045337 | 0.045331 | 5.6132e-06 | 0.015416 | 0.0076649 | 0.002184 | 0.005567 | N/A | 0.0043882 | 2.9406 | N/A | N/A | 1.4818 | 0.0012792 | N/A | 1.4818
LAMBDA | Circuit | Distribution | 0.82951 |  | HFTD 2 | 0.00016332 | 0.00016332 | 0 | 0.00496 | 0.0030381 | 8.8046e-05 | 0.0018338 | N/A | 0 | 0.032928 | N/A | N/A | 1.0476 |  | N/A | 1.0476
LANDERS | Circuit | Distribution | 0.32227 |  | HFTD 2 | 0.0062394 | 0.0062394 | 0 | 0.0011577 | 0.00039525 | 4.232e-06 | 0.00075826 | N/A | 0 | 5.3893 | N/A | N/A | 1.4028 |  | N/A | 1.4028
LANE | Circuit | Distribution | 3.3681 |  | HFTD 2 | 0.032206 | 0.032203 | 3.4868e-06 | 0.01366 | 0.010305 | 0.00090746 | 0.0024472 | N/A | 0.012786 | 2.3575 | N/A | N/A | 1.1751 | 0.0002727 | N/A | 1.1751
LANGER | Circuit | Distribution | 14.569 |  | HFTD 3 | 0.0085034 | 0.008486 | 1.7463e-05 | 0.010588 | 0.0060195 | 0.0012707 | 0.003298 | N/A | 0.022014 | 0.80145 | N/A | N/A | 1.071 | 0.00079328 | N/A | 1.071
LARCH | Circuit | Distribution | 4.0128 |  | HFTD 2 | 0.00044777 | 0.00044721 | 5.5434e-07 | 0.0014941 | 0.00056252 | 0.00018124 | 0.00075038 | N/A | 0.0037098 | 0.29931 | N/A | N/A | 1.4737 | 0.00014942 | N/A | 1.4737
LARK | Circuit | Distribution | 8.1995 |  | HFTD 3 | 0.033637 | 0.033636 | 9.8523e-07 | 0.017011 | 0.008602 | 0.0001913 | 0.0082178 | N/A | 0.02617 | 1.9773 | N/A | N/A | 1.1296 | 3.7647e-05 | N/A | 1.1296
LASKER | Circuit | Distribution | 19.4579 | Top 5% Highest Risk | HFTD 3 | 0.071206 | 0.07117 | 3.5615e-05 | 0.007838 | 0.0038893 | 4.168e-05 | 0.0039071 | N/A | 0.001814 | 9.0802 | N/A | N/A | 1.3504 | 0.019634 | N/A | 1.3504
LAST | Circuit | Distribution | 1.3761 |  | HFTD 2 | 0.011657 | 0.011586 | 7.0913e-05 | 0.0040662 | 0.0028021 | 4.2915e-05 | 0.0012211 | N/A | 0.011433 | 2.8494 | N/A | N/A | 1.1139 | 0.0062027 | N/A | 1.1139
LATTE | Circuit | Distribution | 1.1432 |  |  | 0.0029979 | 0.0029979 | 0 | 0.00177 | 0.00065406 | 8.0452e-05 | 0.0010355 | N/A |  | 1.6937 | N/A | N/A | 1.069 |  | N/A | 1.069
LAUDA | Circuit | Distribution | 4.9763 |  | HFTD 3 | 0.00079111 | 0.00079106 | 4.4918e-08 | 0.0017104 | 0.0011856 | 4.6186e-05 | 0.00047866 | N/A | 0.011027 | 0.4625 | N/A | N/A | 1.5 | 4.0736e-06 | N/A | 1.5
LAWMAN | Circuit | Distribution | 6.7766 |  | HFTD 2 | 0.00032837 | 0.00031491 | 1.3462e-05 | 0.0049331 | 0.0026614 | 0.00020162 | 0.0020702 | N/A | 0.0050686 | 0.063835 | N/A | N/A | 1.0667 | 0.0026559 | N/A | 1.0667
LAZARO | Circuit | Distribution | 0.81227 |  | HFTD 3 | 0.014827 | 0.014827 | 0 | 0.0088786 | 0.0076302 | 0.00042105 | 0.00082727 | N/A | 0.0094588 | 1.67 | N/A | N/A | 1.0718 | 0 | N/A | 1.0718
LEMONADE | Circuit | Distribution | 6.84 |  | HFTD 3 | 0.007092 | 0.0070832 | 8.7399e-06 | 0.0072451 | 0.0032196 | 0.00019028 | 0.0038352 | N/A | 0.004818 | 0.97765 | N/A | N/A | 1.3279 | 0.001814 | N/A | 1.3279
LEON | Circuit | Distribution | 1.2027 |  | HFTD 2 | 0.0056902 | 0.0056902 | 0 | 0.0042876 | 0.0032059 | 0.0001279 | 0.00095383 | N/A | 0.00062635 | 1.3271 | N/A | N/A | 1.0474 | 0 | N/A | 1.0474
LEONA | Circuit | Distribution | 3.7152 |  | HFTD 2 | 0.009249 | 0.0091119 | 0.00013705 | 0.005592 | 0.0043245 | 4.0792e-05 | 0.0012268 | N/A | 0.0091565 | 1.6294 | N/A | N/A | 1.1081 | 0.014967 | N/A | 1.1081
LESSER | Circuit | Distribution | 2.9533 |  | HFTD 3 | 0.0010823 | 0.0010758 | 6.4815e-06 | 0.0276 | 0.014283 | 0.0009372 | 0.01238 | N/A | 0.0026753 | 0.038978 | N/A | N/A | 1.0073 | 0.0024227 | N/A | 1.0073
LETTUCE | Circuit | Distribution | 0.308 |  | HFTD 3 | 0.0017049 | 0.0017049 | 0 | 0.0033296 | 0.0012271 | 0.00015886 | 0.0019437 | N/A | 0 | 0.51202 | N/A | N/A | 1.1905 |  | N/A | 1.1905
LEVECHE | Circuit | Distribution | 11.7715 |  | HFTD 2 | 0.0094462 | 0.0094028 | 4.3387e-05 | 0.0035184 | 0.0017635 | 4.7871e-05 | 0.001707 | N/A | 0.019054 | 2.6725 | N/A | N/A | 1.1129 | 0.002277 | N/A | 1.1129
LEXINGTON | Circuit | Distribution | 2.2594 |  | HFTD 3 | 0.0026658 | 0.0026572 | 8.5673e-06 | 0.0083683 | 0.0068229 | 0.00046447 | 0.0010809 | N/A | 0.0062326 | 0.31753 | N/A | N/A | 1.0337 | 0.0013746 | N/A | 1.0337
LILAC | Circuit | Distribution | 3.7101 |  | HFTD 2 | 0.0028565 | 0.0028565 | 0 | 0.010889 | 0.007168 | 0.0010539 | 0.0026675 | N/A | 0 | 0.26232 | N/A | N/A | 1.4715 |  | N/A | 1.4715
LIMA | Circuit | Distribution | 1.5123 |  | HFTD 2 | 0.0011654 | 0.0011593 | 6.0641e-06 | 0.014343 | 0.009181 | 0.0023486 | 0.002813 | N/A | 0.0061097 | 0.080828 | N/A | N/A | 1.0524 | 0.00099254 | N/A | 1.0524
LIMBER | Circuit | Distribution | 0.8641 |  | HFTD 2 | 0.034711 | 0.034703 | 8.5165e-06 | 0.019387 | 0.0026572 | 0.0019901 | 0.01474 | N/A | 0.0029156 | 1.79 | N/A | N/A | 1.1698 | 0.002921 | N/A | 1.1698
LIMITED | Circuit | Distribution | 18.8923 |  | HFTD 2 | 0.010284 | 0.010283 | 1.7771e-06 | 0.0048158 | 0.0027671 | 0.00035304 | 0.0016957 | N/A | 0.0013568 | 2.1352 | N/A | N/A | 1.1741 | 0.0013098 | N/A | 1.1741
LIMONITE | Circuit | Distribution | 2.8847 |  | HFTD 2 | 0.0046461 | 0.0046458 | 3.2387e-07 | 0.0031944 | 0.0019302 | 5.7314e-05 | 0.0012069 | N/A | 0.004359 | 1.4544 | N/A | N/A | 1 | 7.43e-05 | N/A | 1
LINDERO | Circuit | Distribution | 0.60964 |  | HFTD 3 | 0.0086967 | 0.0086536 | 4.3073e-05 | 0.024014 | 0.0098977 | 0.00061083 | 0.013505 | N/A | 0.0053506 | 0.36036 | N/A | N/A | 1.2911 | 0.0080502 | N/A | 1.2911
LINEBACKER | Circuit | Distribution | 0.68604 |  | HFTD 2 | 9.052e-05 | 7.9796e-05 | 1.0724e-05 | 0.0099248 | 0.0035688 | 0.00018294 | 0.006173 | N/A | 0.0034548 | 0.0080401 | N/A | N/A | 1.0341 | 0.0031042 | N/A | 1.0341
LINNET | Circuit | Distribution | 6.2817 |  | HFTD 3 | 0.017466 | 0.017463 | 3.8436e-06 | 0.0068736 | 0.0042903 | 0.00026609 | 0.0023173 | N/A | 0.010214 | 2.5405 | N/A | N/A | 1.2323 | 0.00037632 | N/A | 1.2323
LITTLE MOUNTAIN | Circuit | Distribution | 3.3933 |  | HFTD 2 | 0.0007643 | 0.0007643 | 0 | 0.001759 | 0.0008339 | 0.00010749 | 0.00081761 | N/A | 0.0090639 | 0.4345 | N/A | N/A |  | 0 | N/A
LIVERMORE | Circuit | Distribution | 2.4221 |  | HFTD 2 | 0.0085756 | 0.0085429 | 3.2696e-05 | 0.0055345 | 0.002035 | 8.3835e-05 | 0.0034157 | N/A | 0.0046872 | 1.5436 | N/A | N/A | 1.0485 | 0.0069757 | N/A | 1.0485
LOCKNER | Circuit | Distribution | 1.5265 |  | HFTD 2 | 0.016698 | 0.016575 | 0.00012317 | 0.0053192 | 0.0037023 | 0.00048947 | 0.0011274 | N/A | 0.0023685 | 3.1161 | N/A | N/A | 1.0586 | 0.052005 | N/A | 1.0586
LOPEZ | Circuit | Distribution | 28.2034 |  | HFTD 3 | 0.026339 | 0.026306 | 3.2957e-05 | 0.0064268 | 0.0028224 | 0.00014754 | 0.0034568 | N/A | 0.049774 | 4.0931 | N/A | N/A | 1.0676 | 0.00066213 | N/A | 1.0676
LOS CARNEROS | Circuit | Distribution | 0.29685 |  | HFTD 3 | 0.0067026 | 0.0067026 | 0 | 0.022907 | 0.013094 | 0.0014818 | 0.0083313 | N/A | 0 | 0.2926 | N/A | N/A | 1.0315 |  | N/A | 1.0315
LOTTO | Circuit | Distribution | 5.1696 |  | HFTD 2 | 0.022688 | 0.022688 | 0 | 0.0031552 | 0.002128 | 8.1922e-05 | 0.00094529 | N/A | 0 | 7.1906 | N/A | N/A | 1.4367 |  | N/A | 1.4367
LOUCKS | Circuit | Distribution | 6.7955 | Top 5% Highest Risk | HFTD 3 | 0.15669 | 0.15669 | 3.7844e-07 | 0.0098224 | 0.0022534 | 0.00016372 | 0.0074053 | N/A | 0.047444 | 15.9524 | N/A | N/A | 1.0931 | 7.9765e-06 | N/A | 1.0931
LOWELL | Circuit | Distribution | 5.6659 |  | HFTD 3 | 0.011352 | 0.011349 | 3.431e-06 | 0.011333 | 0.0057829 | 0.0016517 | 0.0038984 | N/A | 0.010149 | 1.0014 | N/A | N/A | 1.1128 | 0.00033807 | N/A | 1.1128
LUISENO | Circuit | Distribution | 33.9752 |  | HFTD 3 | 0.035329 | 0.035329 | 1.3914e-08 | 0.0052291 | 0.0026248 | 0.00016412 | 0.0024402 | N/A | 0.0029761 | 6.7562 | N/A | N/A | 1.9702 | 4.6752e-06 | N/A | 1.9702
LURING | Circuit | Distribution | 3.2665 |  | HFTD 3 | 0.015824 | 0.015799 | 2.4213e-05 | 0.017474 | 0.0089847 | 0.0046784 | 0.0038108 | N/A | 0.030766 | 0.90417 | N/A | N/A | 1.1597 | 0.00078701 | N/A | 1.1597
LYONS | Circuit | Distribution | 6.0136 |  | HFTD 3 | 0.0048568 | 0.0047585 | 9.8292e-05 | 0.015257 | 0.0071941 | 0.00014691 | 0.0079161 | N/A | 0.0090837 | 0.31189 | N/A | N/A | 1.0769 | 0.010821 | N/A | 1.0769
LYTLE | Circuit | Distribution | 0.54812 |  | HFTD 2 | 0.00036737 | 0.00019325 | 0.00017412 | 0.022009 | 0.012365 | 0.00013948 | 0.0095052 | N/A | 0.0021114 | 0.0087804 | N/A | N/A | 1.1396 | 0.082468 | N/A | 1.1396
MACIEL | Circuit | Distribution | 2.6052 |  | HFTD 3 | 0.039193 | 0.039185 | 8.1031e-06 | 0.0058502 | 0.0021424 | 5.0825e-05 | 0.0036569 | N/A | 0.010701 | 6.6981 | N/A | N/A | 1.1533 | 0.00075722 | N/A | 1.1533
MAGIC | Circuit | Distribution | 0.318 |  | HFTD 3 | 0.0073162 | 0.007307 | 9.2109e-06 | 0.019587 | 0.0067361 | 0.00037356 | 0.012477 | N/A | 0.0040129 | 0.37305 | N/A | N/A | 1.0068 | 0.0022953 | N/A | 1.0068
MAGUIRE | Circuit | Distribution | 62.4817 |  | HFTD 3 | 0.027009 | 0.027008 | 5.8522e-07 | 0.0044714 | 0.0030749 | 0.00015179 | 0.0012447 | N/A | 0.02444 | 6.0403 | N/A | N/A | 1.2514 | 2.3945e-05 | N/A | 1.2514
MAHOGANY | Circuit | Distribution | 30.4744 |  | HFTD 2 | 0.0016782 | 0.0016782 | 0 | 0.0038216 | 0.0012785 | 0.0016648 | 0.00087828 | N/A | 0 | 0.43912 | N/A | N/A | 1.3028 |  | N/A | 1.3028
MAIN ST. | Circuit | Distribution | 0.31925 |  | HFTD 3 | 0.0026809 | 0.0026809 | 0 | 0.00041959 | 0.00032013 | 5.2664e-06 | 9.4193e-05 | N/A | 0 | 6.3894 | N/A | N/A | 1.2136 |  | N/A | 1.2136
MAIZE | Circuit | Distribution | 2.9796 |  | HFTD 3 | 0.015458 | 0.015456 | 2.3155e-06 | 0.0017763 | 0.0008011 | 2.1764e-05 | 0.00095344 | N/A | 0.0088814 | 8.7009 | N/A | N/A | 1.1284 | 0.00026071 | N/A | 1.1284
MAJOR | Circuit | Distribution | 2.2083 |  | HFTD 2 | 0.0031005 | 0.0031005 | 0 | 0.010675 | 0.0065911 | 0.0013522 | 0.0027314 | N/A | 0 | 0.29045 | N/A | N/A | 1.5381 |  | N/A | 1.5381
MALAGA COVE | Circuit | Distribution | 1.3103 |  | HFTD 2 | 0.014888 | 0.014888 | 0 | 0.023296 | 0.013535 | 0.0049726 | 0.0047883 | N/A | 0 | 0.63909 | N/A | N/A | 1.0364 |  | N/A | 1.0364
MALLET | Circuit | Distribution | 0.61445 |  | HFTD 2 | 0.0040912 | 0.0040788 | 1.2394e-05 | 0.0072972 | 0.002857 | 0.00020251 | 0.0042377 | N/A | 8.5957e-05 | 0.55896 | N/A | N/A | 1.0727 | 0.14418 | N/A | 1.0727
MALOY | Circuit | Distribution | 2.4318 |  | HFTD 3 | 0.0048366 | 0.004829 | 7.5637e-06 | 0.0057753 | 0.0033435 | 0.00013324 | 0.0022985 | N/A | 0.0027473 | 0.83616 | N/A | N/A | 1.1386 | 0.0027531 | N/A | 1.1386
MAMBA | Circuit | Distribution | 12.9474 |  | HFTD 3 | 0.014189 | 0.014145 | 4.3742e-05 | 0.0062034 | 0.0027999 | 6.1147e-05 | 0.0033423 | N/A | 0.031067 | 2.2802 | N/A | N/A | 1.0849 | 0.001408 | N/A | 1.0849
MANDARIN | Circuit | Distribution | 2.4168 |  | HFTD 3 | 0.0064897 | 0.0064609 | 2.883e-05 | 0.0092355 | 0.0055013 | 0.00012282 | 0.0036114 | N/A | 0.0032565 | 0.69957 | N/A | N/A | 1.105 | 0.0088532 | N/A | 1.105
MANIFOLD | Circuit | Distribution | 0.65372 |  | HFTD 3 | 0.0003495 | 0.0003495 | 0 | 0.0013305 | 0.00095868 | 4.9225e-05 | 0.00032257 | N/A | 0.0035277 | 0.26269 | N/A | N/A |  | 0 | N/A
MARCUS | Circuit | Distribution | 7.2972 |  | HFTD 3 | 0.0018298 | 0.0018205 | 9.2889e-06 | 0.012368 | 0.0082777 | 6.7124e-05 | 0.0040227 | N/A | 0.011471 | 0.1472 | N/A | N/A | 1.161 | 0.00080978 | N/A | 1.161
MARL | Circuit | Distribution | 0.26715 |  | HFTD 2 | 3.6936e-07 | 3.6936e-07 | 0 | 4.5557e-05 | 2.7413e-05 | 3.996e-07 | 1.7744e-05 | N/A | 0 | 0.0081075 | N/A | N/A | 1.5232 |  | N/A | 1.5232
MARTINELLI | Circuit | Distribution | 0.30876 |  | HFTD 3 | 0.0079538 | 0.0079538 | 0 | 0.024361 | 0.0090216 | 0.00089211 | 0.014447 | N/A | 0 | 0.3265 | N/A | N/A | 1.3423 |  | N/A | 1.3423
MATILIJA | Circuit | Distribution | 22.6915 |  | HFTD 3 | 0.0093154 | 0.0093146 | 7.5314e-07 | 0.01179 | 0.00866 | 0.0019966 | 0.0011332 | N/A | 0.0038793 | 0.79006 | N/A | N/A | 1.1122 | 0.00019414 | N/A | 1.1122
MAXSON | Circuit | Distribution | 2.183 |  | HFTD 2 | 0.0032823 | 0.0031219 | 0.00016037 | 0.0050959 | 0.0020228 | 5.9474e-05 | 0.0030136 | N/A | 0.0012522 | 0.61263 | N/A | N/A | 1.105 | 0.12807 | N/A | 1.105
MAYBELL | Circuit | Distribution | 11.4403 |  | HFTD 2 | 0.010794 | 0.010792 | 2.0844e-06 | 0.0073368 | 0.0031946 | 0.00074975 | 0.0033925 | N/A | 0.003357 | 1.471 | N/A | N/A | 1.1337 | 0.0006209 | N/A | 1.1337
MAYER | Circuit | Distribution | 9.8527 |  | HFTD 2 | 0.0067158 | 0.0067158 | 3.3078e-09 | 0.0016329 | 0.00095944 | 6.5351e-05 | 0.00060812 | N/A | 0.0028624 | 4.1128 | N/A | N/A | 1 | 1.1556e-06 | N/A | 1
MC ALLISTER | Circuit | Distribution | 2.3957 |  | HFTD 2 | 0.0050395 | 0.0049782 | 6.1255e-05 | 0.0026656 | 0.0015879 | 0.0001269 | 0.00095081 | N/A | 0.0053382 | 1.8676 | N/A | N/A | 1.1699 | 0.011475 | N/A | 1.1699
MCBEAN | Circuit | Distribution | 6.1715 |  | HFTD 3 | 0.003898 | 0.0038157 | 8.2361e-05 | 0.024499 | 0.0077012 | 9.5834e-05 | 0.016702 | N/A | 0.025769 | 0.15575 | N/A | N/A | 1.1302 | 0.0031961 | N/A | 1.1302
MCCLENNY | Circuit | Distribution | 3.1197 |  | HFTD 2 | 0.014062 | 0.014062 | 3.063e-07 | 0.011359 | 0.0060476 | 0.0040461 | 0.0012654 | N/A | 0.014464 | 1.2379 | N/A | N/A | 1.2709 | 2.1176e-05 | N/A | 1.2709
MCGEE | Circuit | Distribution | 18.4548 |  | HFTD 2 | 0.0097247 | 0.0096804 | 4.4311e-05 | 0.0041396 | 0.0030124 | 0.00025956 | 0.00086759 | N/A | 0.038132 | 2.3385 | N/A | N/A | 1.1556 | 0.0011621 | N/A | 1.1556
MCLAUGHLIN | Circuit | Distribution | 0.37031 |  | HFTD 2 | 0.025048 | 0.025048 | 0 | 0.0061602 | 0.0049408 | 0.00027048 | 0.00094895 | N/A | 0 | 4.0661 | N/A | N/A | 1.0409 |  | N/A | 1.0409
MEANDER | Circuit | Distribution | 0.2649 |  | HFTD 2 | 0.00011887 | 9.0791e-05 | 2.8074e-05 | 0.011558 | 0.0046194 | 0.0023082 | 0.0046308 | N/A | 0.00014421 | 0.007855 | N/A | N/A | 1.0899 | 0.19467 | N/A | 1.0899
MEBANE | Circuit | Distribution | 5.8162 |  | HFTD 2 | 0.00035381 | 0.00035362 | 1.8376e-07 | 0.0015125 | 0.00078617 | 0.00014687 | 0.00057948 | N/A | 0.014714 | 0.2338 | N/A | N/A | 1.1667 | 1.2489e-05 | N/A | 1.1667
MEDAL | Circuit | Distribution | 12.0472 |  | HFTD 2 | 0.012647 | 0.012646 | 1.3749e-06 | 0.01069 | 0.0049594 | 0.0011636 | 0.0045673 | N/A | 0.00093099 | 1.183 | N/A | N/A | 1.1365 | 0.0014769 | N/A | 1.1365
MEDUSA | Circuit | Distribution | 2.4344 |  | HFTD 2 | 0.0015755 | 0.0015539 | 2.1599e-05 | 0.022503 | 0.02034 | 0.00010099 | 0.0020628 | N/A | 0.010957 | 0.06905 | N/A | N/A | 1.1751 | 0.0019714 | N/A | 1.1751
MEMPHIS | Circuit | Distribution | 18.104 |  | HFTD 2 | 0.020287 | 0.020285 | 2.0155e-06 | 0.0053969 | 0.0035424 | 0.00077404 | 0.0010804 | N/A | 0.0074969 | 3.7586 | N/A | N/A | 1.1194 | 0.00026885 | N/A | 1.1194
MENIFEE | Circuit | Distribution | 21.3825 |  | HFTD 2 | 0.033068 | 0.033068 | 0 | 0.0063052 | 0.0050175 | 0.00014779 | 0.0011399 | N/A | 0 | 5.2446 | N/A | N/A | 1.1359 |  | N/A | 1.1359
MENTRY | Circuit | Distribution | 1.5633 |  | HFTD 3 | 0.012407 | 0.012373 | 3.3976e-05 | 0.0075199 | 0.0042474 | 0.0001024 | 0.0031701 | N/A | 0.0045583 | 1.6453 | N/A | N/A | 1.0805 | 0.0074537 | N/A | 1.0805
MERLIN | Circuit | Distribution | 20.5411 |  | HFTD 3 | 0.015687 | 0.015678 | 9.3314e-06 | 0.0079023 | 0.0047849 | 0.00036714 | 0.0027502 | N/A | 0.034413 | 1.984 | N/A | N/A | 1.1399 | 0.00027116 | N/A | 1.1399
MESA GRANDE | Circuit | Distribution | 7.6818 |  | HFTD 3 | 0.030305 | 0.030301 | 4.1922e-06 | 0.003984 | 0.0033243 | 7.8793e-05 | 0.00058089 | N/A | 0.0052252 | 7.6057 | N/A | N/A | 1.179 | 0.00080229 | N/A | 1.179
METTLER | Circuit | Distribution | 33.9955 | Top 5% Highest Risk | HFTD 3 | 0.058118 | 0.058117 | 1.2507e-06 | 0.0096513 | 0.006369 | 0.00022068 | 0.0030616 | N/A | 0.09695 | 6.0216 | N/A | N/A | 1.2158 | 1.2901e-05 | N/A | 1.2158
MIDDLE ROAD | Circuit | Distribution | 21.0618 |  | HFTD 3 | 0.0020902 | 0.0020888 | 1.3993e-06 | 0.0044544 | 0.0032229 | 0.00047079 | 0.00076075 | N/A | 0.010207 | 0.46892 | N/A | N/A | 1.0575 | 0.0001371 | N/A | 1.0575
MILO | Circuit | Distribution | 9.6802 |  | HFTD 3 | 0.011474 | 0.011451 | 2.2975e-05 | 0.012661 | 0.0062356 | 0.00036629 | 0.006059 | N/A | 0.013316 | 0.90448 | N/A | N/A | 1.0494 | 0.0017255 | N/A | 1.0494
MILPAS | Circuit | Distribution | 1.0689 |  | HFTD 2 | 0.0047938 | 0.0046861 | 0.00010777 | 0.045929 | 0.020521 | 0.00098494 | 0.024423 | N/A | 0.0011352 | 0.10203 | N/A | N/A | 1.0406 | 0.094937 | N/A | 1.0406
MINT CANYON | Circuit | Distribution | 2.0912 |  | HFTD 3 | 0.0090405 | 0.0090012 | 3.9253e-05 | 0.010709 | 0.0055234 | 0.00036361 | 0.0048224 | N/A | 0.01193 | 0.84049 | N/A | N/A | 1.0487 | 0.0032904 | N/A | 1.0487
MIRAMAR | Circuit | Distribution | 2.5129 |  | HFTD 2 | 0.0080473 | 0.0080426 | 4.6703e-06 | 0.011941 | 0.0056996 | 0.0029147 | 0.0033268 | N/A | 0.0046237 | 0.67352 | N/A | N/A | 1.2779 | 0.0010101 | N/A | 1.2779
MIST | Circuit | Distribution | 51.6045 |  | HFTD 3 | 0.0010682 | 0.0010666 | 1.6679e-06 | 0.0033132 | 0.0018109 | 0.00020975 | 0.0012926 | N/A | 0.059769 | 0.32191 | N/A | N/A | 1.2073 | 2.7906e-05 | N/A | 1.2073
MOAB | Circuit | Distribution | 0.64874 |  | HFTD 2 | 0.010133 | 0.010123 | 9.5326e-06 | 0.0025793 | 0.0015177 | 0.00021804 | 0.00084356 | N/A | 0.021402 | 3.9248 | N/A | N/A | 1.0061 | 0.0004454 | N/A | 1.0061
MOCCASIN | Circuit | Distribution | 8.227 |  | HFTD 3 | 0.0067571 | 0.0067432 | 1.3851e-05 | 0.032995 | 0.027541 | 8.0714e-05 | 0.0053735 | N/A | 0.0076783 | 0.20437 | N/A | N/A | 1.089 | 0.0018039 | N/A | 1.089
MOCKINGBIRD | Circuit | Distribution | 8.149 |  | HFTD 2 | 0.0086766 | 0.0086637 | 1.2899e-05 | 0.0033336 | 0.0021069 | 0.00028592 | 0.00094074 | N/A | 0.038198 | 2.5989 | N/A | N/A | 1.0761 | 0.0003377 | N/A | 1.0761
MODJESKA | Circuit | Distribution | 1.4586 |  | HFTD 2 | 0.0049994 | 0.0048135 | 0.00018591 | 0.0009475 | 0.00074263 | 6.0518e-05 | 0.00014435 | N/A | 0.018077 | 5.0802 | N/A | N/A | 1.1175 | 0.010284 | N/A | 1.1175
MONACHE | Circuit | Distribution | 1.3291 |  | HFTD 2 | 0.0031444 | 0.0031444 | 0 | 0.0021246 | 0.0014263 | 1.6349e-06 | 0.00069667 | N/A | 0.00011396 | 1.48 | N/A | N/A | 1.1104 | 0 | N/A | 1.1104
MONARCH | Circuit | Distribution | 4.177 |  | HFTD 3 | 0.001346 | 0.0012027 | 0.00014324 | 0.017182 | 0.0091396 | 0.0012474 | 0.0067947 | N/A | 0.01558 | 0.070001 | N/A | N/A | 1.0325 | 0.0091937 | N/A | 1.0325
MONTGOMERY | Circuit | Distribution | 8.1493 |  | HFTD 3 | 0.00030197 | 0.00019283 | 0.00010915 | 0.013198 | 0.0065463 | 0.00019034 | 0.0064611 | N/A | 0.023558 | 0.014611 | N/A | N/A | 1.1303 | 0.0046331 | N/A | 1.1303
MONTREAL | Circuit | Distribution | 14.9095 |  | HFTD 3 | 0.0095448 | 0.0095187 | 2.6091e-05 | 0.0070888 | 0.0052495 | 0.00023951 | 0.0015999 | N/A | 0.014544 | 1.3428 | N/A | N/A | 1.493 | 0.0017939 | N/A | 1.493
MORELAND | Circuit | Distribution | 9.3972 |  | HFTD 3 | 0.0031243 | 0.0030877 | 3.6676e-05 | 0.012681 | 0.0088355 | 0.00019811 | 0.0036472 | N/A | 0.022087 | 0.24349 | N/A | N/A | 1.0741 | 0.0016606 | N/A | 1.0741
MORELLO | Circuit | Distribution | 6.817 |  | HFTD 2 | 0.015286 | 0.015285 | 1.5819e-06 | 0.0047569 | 0.0016199 | 0.00013033 | 0.0030066 | N/A | 0.018109 | 3.2132 | N/A | N/A | 1.1682 | 8.7354e-05 | N/A | 1.1682
MORGANSTEIN | Circuit | Distribution | 22.4813 |  | HFTD 3 | 0.013662 | 0.013645 | 1.66e-05 | 0.0062518 | 0.0032792 | 0.00072842 | 0.0022442 | N/A | 0.025122 | 2.1826 | N/A | N/A | 1.1542 | 0.00066074 | N/A | 1.1542
MORITZ | Circuit | Distribution | 26.5031 |  | HFTD 3 | 0.039213 | 0.039079 | 0.00013359 | 0.010249 | 0.0064819 | 0.00075513 | 0.0030124 | N/A | 0.11877 | 3.8128 | N/A | N/A | 1.1241 | 0.0011248 | N/A | 1.1241
MORONGO | Circuit | Distribution | 42.4349 |  | HFTD 2 | 0.0112 | 0.011189 | 1.037e-05 | 0.002445 | 0.0017507 | 0.00029636 | 0.00039788 | N/A | 0.062763 | 4.5764 | N/A | N/A | 1.2597 | 0.00016522 | N/A | 1.2597
MORRIS | Circuit | Distribution | 5.641 |  |  | 0.0065599 | 0.0065594 | 5.5182e-07 | 0.0029383 | 0.0021359 | 2.85e-05 | 0.00077382 | N/A |  | 2.2324 | N/A | N/A | 1.1998 |  | N/A | 1.1998
MT. GIVENS | Circuit | Distribution | 10.1676 |  | HFTD 3 | 0.00057212 | 0.00057207 | 5.2989e-08 | 0.0024828 | 0.0016515 | 0.00022074 | 0.00061055 | N/A | 0.014714 | 0.23041 | N/A | N/A | 1.2719 | 3.6013e-06 | N/A | 1.2719
MUDDY | Circuit | Distribution | 4.3259 |  | HFTD 2 | 0.0019142 | 0.0019051 | 9.18e-06 | 0.0048395 | 0.0045713 | 4.0943e-05 | 0.00022726 | N/A | 0.001451 | 0.39365 | N/A | N/A | 1.0794 | 0.0063265 | N/A | 1.0794
MULHOLLAND | Circuit | Distribution | 28.7513 |  | HFTD 3 | 0.038456 | 0.038455 | 1.4295e-06 | 0.0060313 | 0.0034762 | 0.00017402 | 0.0023811 | N/A | 0.0086767 | 6.3758 | N/A | N/A | 1.2742 | 0.00016475 | N/A | 1.2742
MUNICH | Circuit | Distribution | 0.42351 |  | HFTD 2 | 0.00069593 | 0.00028703 | 0.0004089 | 0.0030306 | 0.0011127 | 3.1138e-05 | 0.0018868 | N/A | 0.017153 | 0.094712 | N/A | N/A | 1.1073 | 0.023838 | N/A | 1.1073
MUSTANG | Circuit | Distribution | 54.8995 |  | HFTD 3 | 0.030906 | 0.03089 | 1.6518e-05 | 0.0089887 | 0.0041231 | 7.7823e-05 | 0.0047877 | N/A | 0.038668 | 3.4365 | N/A | N/A | 1.2286 | 0.00042719 | N/A | 1.2286
MUTUAL | Circuit | Distribution | 4.9159 |  | HFTD 3 | 0.051135 | 0.050772 | 0.00036268 | 0.009612 | 0.0063577 | 0.00097128 | 0.002283 | N/A | 0.027949 | 5.2822 | N/A | N/A | 1.0574 | 0.012977 | N/A | 1.0574
MYRTLE | Circuit | Distribution | 0.42391 |  | HFTD 3 | 0.0005702 | 0.0005324 | 3.7793e-05 | 0.025009 | 0.013273 | 0.0017056 | 0.010029 | N/A | 0.001644 | 0.021289 | N/A | N/A | 1.0439 | 0.022989 | N/A | 1.0439
NAPA | Circuit | Distribution | 8.5542 |  | HFTD 2 | 0.010816 | 0.01081 | 6.0696e-06 | 0.0039858 | 0.0022042 | 9.2465e-05 | 0.0016891 | N/A | 0.0024136 | 2.7122 | N/A | N/A | 1.2559 | 0.0025147 | N/A | 1.2559
NAPOLEON | Circuit | Distribution | 5.8595 |  | HFTD 2 | 0.042401 | 0.042351 | 4.9566e-05 | 0.0058105 | 0.0032957 | 0.00016451 | 0.0023502 | N/A | 0.0084638 | 7.2888 | N/A | N/A | 1.1165 | 0.0058563 | N/A | 1.1165
NASHVILLE | Circuit | Distribution | 5.5053 |  | HFTD 2 | 0.0039396 | 0.0039309 | 8.7669e-06 | 0.0078075 | 0.0053068 | 0.00047096 | 0.0020297 | N/A | 0.0040856 | 0.50347 | N/A | N/A | 1.058 | 0.0021458 | N/A | 1.058
NATIONS | Circuit | Distribution | 15.6263 |  | HFTD 2 | 0.035085 | 0.035084 | 8.1406e-07 | 0.0047225 | 0.0031884 | 0.00019924 | 0.0013349 | N/A | 0.0041489 | 7.4292 | N/A | N/A | 1.3306 | 0.00019621 | N/A | 1.3306
NAVEL | Circuit | Distribution | 0.31511 |  | HFTD 2 | 0.00037746 | 4.5644e-06 | 0.0003729 | 0.0005856 | 0.00024469 | 2.8028e-05 | 0.00031289 | N/A | 0.0011333 | 0.0077943 | N/A | N/A | 1.0481 | 0.32903 | N/A | 1.0481
NEAPOLITAN | Circuit | Distribution | 2.7562 |  | HFTD 2 | 0.0051072 | 0.0051019 | 5.3002e-06 | 0.0084414 | 0.0060505 | 0.00020867 | 0.0021822 | N/A | 0.0023476 | 0.60439 | N/A | N/A | 1.1958 | 0.0022577 | N/A | 1.1958
NEARGATE | Circuit | Distribution | 11.7626 |  | HFTD 3 | 0.016921 | 0.016891 | 3.0461e-05 | 0.015087 | 0.0064408 | 0.00017497 | 0.0084713 | N/A | 0.014526 | 1.1196 | N/A | N/A | 1.074 | 0.002097 | N/A | 1.074
NEPAL | Circuit | Distribution | 3.9417 |  | HFTD 3 | 0.013658 | 0.013629 | 2.8508e-05 | 0.010856 | 0.006827 | 0.00019065 | 0.0038379 | N/A | 0.0072221 | 1.2555 | N/A | N/A | 1.1389 | 0.0039473 | N/A | 1.1389
NERO | Circuit | Distribution | 8.5811 |  | HFTD 3 | 0.001891 | 0.0018787 | 1.2314e-05 | 0.015643 | 0.0062365 | 0.00014215 | 0.0092648 | N/A | 0.016811 | 0.12009 | N/A | N/A | 1.1649 | 0.00073249 | N/A | 1.1649
NICHOLAS | Circuit | Distribution | 26.0224 |  |  | 0.011276 | 0.011276 | 0 | 0.01048 | 0.00535 | 0.00027786 | 0.0048521 | N/A |  | 1.0759 | N/A | N/A | 1.2067 |  | N/A | 1.2067
NICOLE | Circuit | Distribution | 0.26708 |  | HFTD 2 | 0.0096075 | 0.0094392 | 0.0001683 | 0.054702 | 0.047836 | 0.00063856 | 0.0062281 | N/A | 0.0053672 | 0.17256 | N/A | N/A | 1.1308 | 0.031357 | N/A | 1.1308
NIGHTHAWK | Circuit | Distribution | 3.8132 |  | HFTD 3 | 0.01753 | 0.017525 | 4.691e-06 | 0.012403 | 0.0063282 | 0.00011275 | 0.0059616 | N/A | 0.0055521 | 1.413 | N/A | N/A | 1.032 | 0.00084492 | N/A | 1.032
NORTH BAY | Circuit | Distribution | 3.3228 |  | HFTD 3 | 0.01271 | 0.012699 | 1.1635e-05 | 0.0095072 | 0.0053791 | 0.0008092 | 0.0033189 | N/A | 0.012978 | 1.3357 | N/A | N/A | 1.0037 | 0.00089651 | N/A | 1.0037
NORTH SHORE | Circuit | Distribution | 13.9266 |  | HFTD 3 | 0.041942 | 0.041881 | 6.0781e-05 | 0.01208 | 0.0078141 | 0.00097414 | 0.0032917 | N/A | 0.065146 | 3.467 | N/A | N/A | 1.0931 | 0.00093301 | N/A | 1.0931
NORTHPARK | Circuit | Distribution | 30.8159 |  | HFTD 2 | 0.026671 | 0.026618 | 5.2801e-05 | 0.005555 | 0.0036469 | 0.00070613 | 0.001202 | N/A | 0.10313 | 4.7918 | N/A | N/A | 1.1628 | 0.00051196 | N/A | 1.1628
NORTHRIDGE | Circuit | Distribution | 0.42338 |  | HFTD 2 | 9.6236e-05 | 9.6236e-05 | 0 | 0.0094143 | 0.002486 | 0.0017797 | 0.0051485 | N/A | 0 | 0.010222 | N/A | N/A | 1.5149 |  | N/A | 1.5149
NOVA | Circuit | Distribution | 3.7477 |  | HFTD 2 | 0.0050222 | 0.0050044 | 1.783e-05 | 0.0028949 | 0.0016997 | 0.00014292 | 0.0010523 | N/A | 0.001067 | 1.7287 | N/A | N/A | 1.1317 | 0.016711 | N/A | 1.1317
NUBIA | Circuit | Distribution | 0.74812 |  | HFTD 2 | 0.0053932 | 0.00535 | 4.3111e-05 | 0.0059953 | 0.0032323 | 0.0002513 | 0.0025117 | N/A | 0.00094267 | 0.89237 | N/A | N/A | 1.0721 | 0.045733 | N/A | 1.0721
NUTMEG | Circuit | Distribution | 8.9547 |  | HFTD 3 | 0.026288 | 0.026287 | 4.0834e-07 | 0.0057252 | 0.0042153 | 0.00011776 | 0.0013921 | N/A | 0.00096431 | 4.5915 | N/A | N/A | 1.1731 | 0.00042345 | N/A | 1.1731
O'TOOLE | Circuit | Distribution | 5.8852 |  | HFTD 2 | 0.0038173 | 0.003815 | 2.2915e-06 | 0.0051457 | 0.0024499 | 0.00027962 | 0.0024162 | N/A | 0.0030205 | 0.7414 | N/A | N/A | 1.0719 | 0.00075865 | N/A | 1.0719
OAK GLEN | Circuit | Distribution | 25.8078 |  | HFTD 3 | 0.0065281 | 0.006523 | 5.1081e-06 | 0.0046469 | 0.0024381 | 0.00023394 | 0.0019749 | N/A | 0.016031 | 1.4037 | N/A | N/A | 1.1109 | 0.00031864 | N/A | 1.1109
OAK KNOLL | Circuit | Distribution | 4.6761 |  | HFTD 3 | 0.0046833 | 0.0046736 | 9.7097e-06 | 0.012129 | 0.0068223 | 0.00082215 | 0.0044843 | N/A | 0.03876 | 0.38533 | N/A | N/A | 1.339 | 0.00025051 | N/A | 1.339
OAKDALE | Circuit | Distribution | 12.7422 |  | HFTD 2 | 0.011587 | 0.011585 | 1.7754e-06 | 0.0066329 | 0.0054673 | 7.3542e-05 | 0.001092 | N/A | 0.00078344 | 1.7466 | N/A | N/A | 1.2336 | 0.0022662 | N/A | 1.2336
OAKWOOD | Circuit | Distribution | 4.7518 |  | HFTD 2 | 0.002342 | 0.0023407 | 1.2519e-06 | 0.013368 | 0.0095488 | 0.0015437 | 0.002276 | N/A | 0.0067362 | 0.17509 | N/A | N/A | 1.0718 | 0.00018585 | N/A | 1.0718
OLD MANS | Circuit | Distribution | 0.35366 |  | HFTD 2 | 0.00035667 | 0.00035667 | 0 | 0.019017 | 0.0045502 | 0.0013398 | 0.013127 | N/A | 0 | 0.018755 | N/A | N/A |  |  | N/A
OLIVER | Circuit | Distribution | 12.1604 |  | HFTD 2 | 0.0025673 | 0.0025673 | 2.0419e-08 | 0.0024032 | 0.0011254 | 9.1653e-05 | 0.0011862 | N/A | 0.0052676 | 1.0683 | N/A | N/A | 1 | 3.8764e-06 | N/A | 1
OLYMPIAD | Circuit | Distribution | 0.48946 |  | HFTD 2 | 0.017211 | 0.016904 | 0.00030695 | 0.011292 | 0.0041279 | 0.0014847 | 0.005679 | N/A | 0.020065 | 1.497 | N/A | N/A | 1.1808 | 0.015298 | N/A | 1.1808
OMEGA | Circuit | Distribution | 16.5602 |  | HFTD 3 | 0.042662 | 0.042662 | 0 | 0.010775 | 0.0044288 | 0.00018195 | 0.0061646 | N/A | 0 | 3.9592 | N/A | N/A | 1.1705 |  | N/A | 1.1705
ONAGA | Circuit | Distribution | 8.5716 |  | HFTD 2 | 0.0097518 | 0.0096865 | 6.5312e-05 | 0.0033001 | 0.0026598 | 4.2517e-05 | 0.00059779 | N/A | 0.013785 | 2.9352 | N/A | N/A | 1.0882 | 0.0047378 | N/A | 1.0882
ONBORD | Circuit | Distribution | 7.112 |  | HFTD 3 | 0.018332 | 0.018282 | 4.9674e-05 | 0.0059544 | 0.0037117 | 0.00014914 | 0.0020935 | N/A | 0.020572 | 3.0704 | N/A | N/A | 1.1881 | 0.0024146 | N/A | 1.1881
ORION | Circuit | Distribution | 4.3275 |  | HFTD 3 | 0.01123 | 0.011041 | 0.00018929 | 0.0084 | 0.0050708 | 5.4763e-05 | 0.0032744 | N/A | 0.027363 | 1.3144 | N/A | N/A | 1.0536 | 0.0069177 | N/A | 1.0536
OSLO | Circuit | Distribution | 2.5608 |  | HFTD 3 | 0.0052518 | 0.0051849 | 6.6925e-05 | 0.0017082 | 0.0011069 | 1.6622e-05 | 0.00058468 | N/A | 0.014947 | 3.0352 | N/A | N/A | 1.0498 | 0.0044774 | N/A | 1.0498
OVERHILL | Circuit | Distribution | 0.45184 |  | HFTD 2 | 9.0174e-05 | 9.0174e-05 | 0 | 0.0088212 | 0.0023294 | 0.0016676 | 0.0048242 | N/A | 0 | 0.010222 | N/A | N/A | 1.1189 |  | N/A | 1.1189
OVERLOOK | Circuit | Distribution | 3.1254 |  | HFTD 2 | 0.0032732 | 0.0032369 | 3.6223e-05 | 0.039046 | 0.035624 | 0.00062748 | 0.0027943 | N/A | 0.0057962 | 0.082901 | N/A | N/A | 1.0079 | 0.0062495 | N/A | 1.0079
OWENS | Circuit | Distribution | 5.995 |  | HFTD 2 | 0.0060191 | 0.0060187 | 3.7228e-07 | 0.0058686 | 0.0033922 | 0.00034233 | 0.0021342 | N/A | 0.0070301 | 1.0256 | N/A | N/A | 1.2018 | 5.2955e-05 | N/A | 1.2018
PADOVA | Circuit | Distribution | 0.61766 |  | HFTD 2 | 0.011721 | 0.011644 | 7.711e-05 | 0.0044962 | 0.0015591 | 0.00022888 | 0.0027082 | N/A | 0.0017694 | 2.5897 | N/A | N/A | 1.2073 | 0.043581 | N/A | 1.2073
PAINTED CAVE | Circuit | Distribution | 2.4216 |  | HFTD 3 | 0.0057522 | 0.0057519 | 3.1794e-07 | 0.0074786 | 0.0049536 | 0.00035829 | 0.0021667 | N/A | 0.0013185 | 0.76912 | N/A | N/A | 1.0068 | 0.00024114 | N/A | 1.0068
PALACE | Circuit | Distribution | 0.42065 |  | HFTD 3 | 0.006332 | 0.0060801 | 0.00025189 | 0.0098752 | 0.0078674 | 0.00016427 | 0.0018435 | N/A | 0.001727 | 0.61569 | N/A | N/A | 1.062 | 0.14586 | N/A | 1.062
PALMER | Circuit | Distribution | 7.4669 |  | HFTD 2 | 0.014601 | 0.0146 | 1.0774e-06 | 0.0082458 | 0.0029287 | 0.00089197 | 0.0044252 | N/A | 0.0061684 | 1.7705 | N/A | N/A | 1.3182 | 0.00017466 | N/A | 1.3182
PALOMA | Circuit | Distribution | 1.8025 |  | HFTD 3 | 0.031467 | 0.031393 | 7.3301e-05 | 0.012976 | 0.006979 | 0.00072571 | 0.0052712 | N/A | 0.0047272 | 2.4193 | N/A | N/A | 1.1 | 0.015506 | N/A | 1.1
PALOMINO | Circuit | Distribution | 5.825 |  | HFTD 2 | 0.02217 | 0.02217 | 0 | 0.0058214 | 0.0022103 | 0.00020304 | 0.0034081 | N/A | 0.00077236 | 3.8084 | N/A | N/A | 1.0584 | 0 | N/A | 1.0584
PANCAKE | Circuit | Distribution | 1.5349 |  | HFTD 2 | 0.0017109 | 0.0017109 | 0 | 0.0093094 | 0.0065614 | 0.0010577 | 0.0016904 | N/A | 0 | 0.18378 | N/A | N/A | 1.2397 |  | N/A | 1.2397
PANCHO | Circuit | Distribution | 1.0581 |  | HFTD 2 | 0.001687 | 0.0016582 | 2.8775e-05 | 0.00473 | 0.0022847 | 0.00021729 | 0.002228 | N/A | 0.00041045 | 0.35057 | N/A | N/A | 1.0942 | 0.070106 | N/A | 1.0942
PANHANDLE | Circuit | Distribution | 0.49152 |  |  | 0.01867 | 0.01867 | 0 | 0.0049598 | 0.001823 | 0.00055699 | 0.0025798 | N/A |  | 3.7642 | N/A | N/A | 1.0927 |  | N/A | 1.0927
PAR | Circuit | Distribution | 0.36884 |  | HFTD 3 | 0.026841 | 0.026841 | 0 | 0.028367 | 0.021517 | 0.0030076 | 0.0038417 | N/A | 0 | 0.94623 | N/A | N/A | 1.0129 |  | N/A | 1.0129
PARADISE | Circuit | Distribution | 17.0841 |  | HFTD 3 | 0.041528 | 0.041526 | 2.0818e-06 | 0.010514 | 0.0053821 | 0.00040859 | 0.0047237 | N/A | 0.013006 | 3.9495 | N/A | N/A | 1.2349 | 0.00016007 | N/A | 1.2349
PARCO | Circuit | Distribution | 0.47632 |  | HFTD 2 | 0.0036835 | 0.0031388 | 0.00054474 | 0.0064516 | 0.0044718 | 0.00036288 | 0.0016169 | N/A | 0.0013551 | 0.48651 | N/A | N/A | 1.1143 | 0.402 | N/A | 1.1143
PARINA | Circuit | Distribution | 0.71418 |  | HFTD 2 | 0.00097099 | 0.00093831 | 3.2672e-05 | 0.0042179 | 0.0018957 | 0.00019988 | 0.0021223 | N/A | 0.00081263 | 0.22246 | N/A | N/A | 1.0588 | 0.040205 | N/A | 1.0588
PASCAL | Circuit | Distribution | 12.4198 | Top 5% Highest Risk | HFTD 3 | 0.0589 | 0.058897 | 3.3911e-06 | 0.0048506 | 0.0039239 | 9.6176e-05 | 0.0008305 | N/A | 0.0050446 | 12.1422 | N/A | N/A | 1.2032 | 0.00067222 | N/A | 1.2032
PASCOE | Circuit | Distribution | 8.8434 |  | HFTD 3 | 0.018789 | 0.018787 | 2.6345e-06 | 0.01898 | 0.0096365 | 0.003231 | 0.0061122 | N/A | 0.03716 | 0.98983 | N/A | N/A | 1.449 | 7.0895e-05 | N/A | 1.449
PATHE | Circuit | Distribution | 0.52795 |  | HFTD 2 | 0.0066355 | 0.0066355 | 0 | 0.0091327 | 0.0064196 | 0.00038366 | 0.0023295 | N/A | 0 | 0.72657 | N/A | N/A | 1.0801 |  | N/A | 1.0801
PATRICIA | Circuit | Distribution | 47.369 |  | HFTD 3 | 0.011473 | 0.01147 | 2.5267e-06 | 0.0062262 | 0.0049876 | 0.00024957 | 0.00098908 | N/A | 0.015487 | 1.8422 | N/A | N/A | 1.0875 | 0.00016315 | N/A | 1.0875
PATRIOT | Circuit | Distribution | 7.3481 |  | HFTD 3 | 0.0039617 | 0.0039339 | 2.7817e-05 | 0.01351 | 0.0045484 | 0.00014429 | 0.0088169 | N/A | 0.014547 | 0.2912 | N/A | N/A | 1.0588 | 0.0019121 | N/A | 1.0588
PAWLEY | Circuit | Distribution | 69.1154 |  | HFTD 2 | 0.0058286 | 0.0058282 | 3.7983e-07 | 0.0068774 | 0.0029886 | 0.00088573 | 0.003003 | N/A | 0.010381 | 0.84744 | N/A | N/A | 1.0983 | 3.6589e-05 | N/A | 1.0983
PAWNEE | Circuit | Distribution | 63.6164 | Top 5% Highest Risk | HFTD 3 | 0.062627 | 0.062626 | 8.0534e-07 | 0.0069137 | 0.0056418 | 5.6951e-05 | 0.001215 | N/A | 0.0085153 | 9.0582 | N/A | N/A | 1.2358 | 9.4576e-05 | N/A | 1.2358
PAYNE | Circuit | Distribution | 9.5878 |  | HFTD 2 | 0.013121 | 0.013112 | 9.0497e-06 | 0.011748 | 0.0072547 | 0.00099766 | 0.0034962 | N/A | 0.0045855 | 1.1161 | N/A | N/A | 1.0884 | 0.0019735 | N/A | 1.0884
PEACOCK | Circuit | Distribution | 1.3404 |  | HFTD 2 | 0.021779 | 0.021779 | 0 | 0.018787 | 0.014653 | 0.00082825 | 0.0033053 | N/A | 0 | 1.1593 | N/A | N/A | 1.7588 |  | N/A | 1.7588
PEAR | Circuit | Distribution | 2.0227 |  | HFTD 2 | 0.004194 | 0.004181 | 1.2995e-05 | 0.009568 | 0.0058131 | 0.00025894 | 0.003496 | N/A | 0.0030905 | 0.43698 | N/A | N/A | 1.0801 | 0.0042048 | N/A | 1.0801
PEARCE | Circuit | Distribution | 3.4109 |  | HFTD 3 | 0.0014032 | 0.0013981 | 5.0552e-06 | 0.0098006 | 0.0085457 | 0.00018128 | 0.0010736 | N/A | 0.0043107 | 0.14265 | N/A | N/A | 1.0901 | 0.0011727 | N/A | 1.0901
PELONA | Circuit | Distribution | 1.4366 | Top 5% Highest Risk | HFTD 3 | 0.16579 | 0.16579 | 0 | 0.017756 | 0.0054871 | 0.00021299 | 0.012056 | N/A | 0.034175 | 9.3372 | N/A | N/A | 1.1395 | 0 | N/A | 1.1395
PENDLETON | Circuit | Distribution | 1.3205 |  | HFTD 2 | 0.015859 | 0.015782 | 7.6573e-05 | 0.0046581 | 0.0022603 | 0.00057649 | 0.0018213 | N/A | 0.0027574 | 3.3881 | N/A | N/A | 1.0549 | 0.02777 | N/A | 1.0549
PENSTOCK | Circuit | Distribution | 48.0008 |  | HFTD 3 | 0.029624 | 0.029561 | 6.2781e-05 | 0.0058328 | 0.0026876 | 3.1392e-05 | 0.0031138 | N/A | 0.066651 | 5.0681 | N/A | N/A | 1.3524 | 0.00094195 | N/A | 1.3524
PERIMETER | Circuit | Distribution | 19.6236 |  | HFTD 3 | 0.0094156 | 0.0094149 | 7.1624e-07 | 0.0064923 | 0.0044794 | 0.00070398 | 0.0013089 | N/A | 0.0090907 | 1.4502 | N/A | N/A | 1.2552 | 7.8788e-05 | N/A | 1.2552
PERRIS | Circuit | Distribution | 3.873 |  | HFTD 2 | 0.051662 | 0.051656 | 5.8445e-06 | 0.0060136 | 0.0022235 | 0.0010473 | 0.0027428 | N/A | 0.0013081 | 8.59 | N/A | N/A | 1.1393 | 0.0044679 | N/A | 1.1393
PETIT | Circuit | Distribution | 15.6471 |  | HFTD 3 | 0.0043773 | 0.0043614 | 1.5988e-05 | 0.0044519 | 0.0029215 | 0.00030114 | 0.0012292 | N/A | 0.013129 | 0.97966 | N/A | N/A | 1.3147 | 0.0012177 | N/A | 1.3147
PHEASANT | Circuit | Distribution | 12.442 | Top 5% Highest Risk | HFTD 3 | 0.058828 | 0.058828 | 1.4754e-07 | 0.0040155 | 0.0018386 | 0.00017369 | 0.0020033 | N/A | 0.008775 | 14.6503 | N/A | N/A | 1.5232 | 1.6813e-05 | N/A | 1.5232
PHOTON | Circuit | Distribution | 21.2724 |  | HFTD 2 | 0.015568 | 0.015568 | 0 | 0.005338 | 0.0018811 | 6.3562e-05 | 0.0033933 | N/A | 0.0011423 | 2.9166 | N/A | N/A | 1.0837 | 0 | N/A | 1.0837
PICK | Circuit | Distribution | 49.4952 |  | HFTD 3 | 0.051935 | 0.051934 | 6.2988e-07 | 0.0069856 | 0.0037936 | 6.0729e-05 | 0.0031313 | N/A | 0.040527 | 7.4344 | N/A | N/A | 1.0903 | 1.5542e-05 | N/A | 1.0903
PICKENS | Circuit | Distribution | 1.0033 |  | HFTD 2 | 0.0056715 | 0.005427 | 0.00024456 | 0.018401 | 0.0097629 | 0.0015707 | 0.0070673 | N/A | 0.0028537 | 0.29493 | N/A | N/A | 1.0495 | 0.0857 | N/A | 1.0495
PICKLE MEADOWS | Circuit | Distribution | 28.9087 |  | HFTD 2 | 0.0020295 | 0.0020276 | 1.9081e-06 | 0.0031306 | 0.0018067 | 0.00055387 | 0.00077001 | N/A | 0.074113 | 0.64769 | N/A | N/A | 1.5546 | 2.5746e-05 | N/A | 1.5546
PICONI | Circuit | Distribution | 22.116 |  | HFTD 3 | 0.046572 | 0.046571 | 1.6417e-07 | 0.0063308 | 0.0038931 | 0.00016753 | 0.0022702 | N/A | 0.0034986 | 7.3563 | N/A | N/A | 1.1739 | 4.6924e-05 | N/A | 1.1739
PIEDMONT | Circuit | Distribution | 0.64593 |  | HFTD 2 | 0.0040957 | 0.0040326 | 6.3042e-05 | 0.019099 | 0.011491 | 0.00035358 | 0.0072547 | N/A | 0.0024117 | 0.21114 | N/A | N/A | 1.4964 | 0.02614 | N/A | 1.4964
PIEDRA | Circuit | Distribution | 1.8351 |  | HFTD 2 | 0.0022079 | 0.0022051 | 2.7952e-06 | 0.0024188 | 0.0010453 | 7.787e-05 | 0.0012957 | N/A | 0.00036131 | 0.91165 | N/A | N/A | 1.0832 | 0.0077363 | N/A | 1.0832
PINE COVE | Circuit | Distribution | 27.5948 |  | HFTD 3 | 0.027387 | 0.027382 | 5.1923e-06 | 0.01369 | 0.0074943 | 0.0012347 | 0.0049605 | N/A | 0.033735 | 2.0002 | N/A | N/A | 1.2584 | 0.00015392 | N/A | 1.2584
PINEWOOD | Circuit | Distribution | 1.4473 |  | HFTD 2 | 0.027113 | 0.027018 | 9.469e-05 | 0.0023285 | 0.0019641 | 4.6299e-05 | 0.00031808 | N/A | 0.00040857 | 11.6034 | N/A | N/A | 1.18 | 0.23176 | N/A | 1.18
PINTO | Circuit | Distribution | 15.0412 |  | HFTD 2 | 0.023493 | 0.023492 | 1.2612e-07 | 0.0032178 | 0.0014808 | 0.00013576 | 0.0016013 | N/A | 0.037267 | 7.3007 | N/A | N/A | 2 | 3.3841e-06 | N/A | 2
PINWHEEL | Circuit | Distribution | 3.1613 |  | HFTD 2 | 0.0036965 | 0.0036961 | 4.4207e-07 | 0.0029471 | 0.0018766 | 5.1807e-05 | 0.0010186 | N/A | 0.01116 | 1.2542 | N/A | N/A | 1.8158 | 3.9614e-05 | N/A | 1.8158
PINZON | Circuit | Distribution | 3.0762 |  | HFTD 2 | 0.0062849 | 0.0062849 | 0 | 0.013185 | 0.0066003 | 0.0023057 | 0.0042793 | N/A | 0 | 0.47666 | N/A | N/A | 1.0331 |  | N/A | 1.0331
PIONEERTOWN | Circuit | Distribution | 67.9888 |  | HFTD 3 | 0.04613 | 0.046123 | 7.0028e-06 | 0.0066503 | 0.004002 | 0.00021793 | 0.0024304 | N/A | 0.06305 | 6.9355 | N/A | N/A | 1.1383 | 0.00011107 | N/A | 1.1383
PLACID | Circuit | Distribution | 28.8552 |  | HFTD 3 | 0.029452 | 0.029438 | 1.3878e-05 | 0.007322 | 0.0049563 | 8.8394e-05 | 0.0022773 | N/A | 0.012278 | 4.0205 | N/A | N/A | 1.0997 | 0.0011303 | N/A | 1.0997
PLATEAU | Circuit | Distribution | 26.8656 |  | HFTD 3 | 0.026633 | 0.026615 | 1.8355e-05 | 0.0080255 | 0.004884 | 0.00078784 | 0.0023537 | N/A | 0.029247 | 3.3163 | N/A | N/A | 1.2256 | 0.00062759 | N/A | 1.2256
PLAYBOY | Circuit | Distribution | 0.3651 |  | HFTD 2 | 0.00031203 | 0.00017776 | 0.00013427 | 0.021281 | 0.011786 | 0.0061481 | 0.0033465 | N/A | 0.00052243 | 0.0083531 | N/A | N/A | 1.0916 | 0.25701 | N/A | 1.0916
PLUTO | Circuit | Distribution | 7.0568 |  | HFTD 2 | 0.00013067 | 0.00013067 | 0 | 0.0088486 | 0.0072732 | 0.0004577 | 0.0011177 | N/A | 0.0013306 | 0.014768 | N/A | N/A | 1.5151 | 0 | N/A | 1.5151
POLYMER | Circuit | Distribution | 1.2 |  | HFTD 2 | 0.0021805 | 0.0021783 | 2.1632e-06 | 0.0050212 | 0.0022887 | 0.00024348 | 0.002489 | N/A | 0.0092962 | 0.43383 | N/A | N/A | 1.3296 | 0.00023269 | N/A | 1.3296
POPPET FLATS | Circuit | Distribution | 37.964 | Top 5% Highest Risk | HFTD 2 | 0.068028 | 0.068028 | 0 | 0.011629 | 0.0074027 | 0.00015173 | 0.0040747 | N/A | 0.26847 | 5.8498 | N/A | N/A | 1.3515 | 0 | N/A | 1.3515
PORCELAIN | Circuit | Distribution | 5.485 |  | HFTD 2 | 0.017418 | 0.017417 | 5.9566e-07 | 0.0050819 | 0.003552 | 0.00058757 | 0.00094232 | N/A | 0.004873 | 3.4273 | N/A | N/A | 1.012 | 0.00012224 | N/A | 1.012
PORPHYRY | Circuit | Distribution | 4.0378 |  | HFTD 3 | 0.0038022 | 0.0038019 | 2.9569e-07 | 0.0035961 | 0.0024545 | 8.0773e-05 | 0.0010608 | N/A | 0.008966 | 1.0572 | N/A | N/A | 1 | 3.298e-05 | N/A | 1
POSO PARK | Circuit | Distribution | 0.77902 |  | HFTD 2 | 0.016718 | 0.016718 | 0 | 0.012266 | 0.0055319 | 0.0042913 | 0.0024426 | N/A | 0.013376 | 1.363 | N/A | N/A | 1.6713 | 0 | N/A | 1.6713
POTATO | Circuit | Distribution | 2.5882 |  | HFTD 2 | 0.0019599 | 0.0014568 | 0.00050315 | 0.012379 | 0.0031541 | 0.0001401 | 0.0090844 | N/A | 0.0026544 | 0.11768 | N/A | N/A | 1.1077 | 0.18955 | N/A | 1.1077
POTTERY | Circuit | Distribution | 7.6825 |  | HFTD 2 | 0.0010324 | 0.0010305 | 1.8654e-06 | 0.0047566 | 0.0029616 | 0.00028294 | 0.0015121 | N/A | 0.0032827 | 0.21664 | N/A | N/A | 1.1008 | 0.00056825 | N/A | 1.1008
POULTRY | Circuit | Distribution | 26.6334 |  | HFTD 3 | 0.011459 | 0.011455 | 3.6484e-06 | 0.0057748 | 0.0027844 | 0.00080987 | 0.0021805 | N/A | 0.012054 | 1.9836 | N/A | N/A | 1.1821 | 0.00030266 | N/A | 1.1821
POWELL | Circuit | Distribution | 11.0473 |  | HFTD 3 | 0.0052213 | 0.0051843 | 3.703e-05 | 0.01222 | 0.0065919 | 0.00017078 | 0.0054573 | N/A | 0.037638 | 0.42424 | N/A | N/A | 1.0945 | 0.00098384 | N/A | 1.0945
POWER | Circuit | Distribution | 0.74661 |  | HFTD 2 | 0.0098058 | 0.0085784 | 0.0012275 | 0.0072489 | 0.0048579 | 0.0004104 | 0.0019806 | N/A | 0.0019487 | 1.1834 | N/A | N/A | 1.5066 | 0.6299 | N/A | 1.5066
PRADO | Circuit | Distribution | 0.37013 |  | HFTD 3 | 0.00024138 | 0.00019044 | 5.0934e-05 | 0.028207 | 0.017088 | 0.00084866 | 0.01027 | N/A | 0.0040129 | 0.0067518 | N/A | N/A | 1.0235 | 0.012693 | N/A | 1.0235
PREDATOR | Circuit | Distribution | 3.0405 |  | HFTD 2 | 0.0017266 | 0.0017182 | 8.3766e-06 | 0.0025656 | 0.0017392 | 7.6114e-05 | 0.00075027 | N/A | 0.0019293 | 0.66971 | N/A | N/A | 1.134 | 0.0043417 | N/A | 1.134
PRESLEY | Circuit | Distribution | 0.33956 |  | HFTD 3 | 0.00054641 | 0.00054641 | 0 | 0.0034261 | 0.0014624 | 6.6287e-05 | 0.0018974 | N/A | 0 | 0.15948 | N/A | N/A | 1.0487 |  | N/A | 1.0487
PRESTON | Circuit | Distribution | 1.3914 |  | HFTD 3 | 0.014947 | 0.014639 | 0.00030746 | 0.020603 | 0.0046679 | 0.00019341 | 0.015742 | N/A | 0.0014267 | 0.71055 | N/A | N/A | 1.1053 | 0.2155 | N/A | 1.1053
PRIMROSE | Circuit | Distribution | 12.5829 |  | HFTD 3 | 0.021495 | 0.021483 | 1.1892e-05 | 0.020766 | 0.0063987 | 0.0017415 | 0.012626 | N/A | 0.011088 | 1.0345 | N/A | N/A | 1.0983 | 0.0010725 | N/A | 1.0983
PRONGHORN | Circuit | Distribution | 25.8962 |  | HFTD 3 | 0.031486 | 0.031477 | 9.4136e-06 | 0.00684 | 0.0042539 | 8.2495e-05 | 0.0025036 | N/A | 0.023264 | 4.6019 | N/A | N/A | 1.2852 | 0.00040465 | N/A | 1.2852
PUESTA | Circuit | Distribution | 0.53537 |  | HFTD 2 | 0.00040783 | 0.00026682 | 0.00014101 | 0.0019283 | 0.00091896 | 0.00052961 | 0.00047971 | N/A | 0.00062475 | 0.13837 | N/A | N/A | 1.1624 | 0.22571 | N/A | 1.1624
PUFF | Circuit | Distribution | 8.8512 |  | HFTD 2 | 0.0040221 | 0.0040187 | 3.3609e-06 | 0.0033901 | 0.0028539 | 5.9973e-05 | 0.00047617 | N/A | 0.015991 | 1.1854 | N/A | N/A | 1.3753 | 0.00021018 | N/A | 1.3753
PURCHASE | Circuit | Distribution | 4.0412 | Top 5% Highest Risk | HFTD 3 | 0.072064 | 0.07206 | 3.9725e-06 | 0.012649 | 0.0063203 | 0.00084521 | 0.0054832 | N/A | 0.033114 | 5.697 | N/A | N/A | 1.2309 | 0.00011996 | N/A | 1.2309
PYLE | Circuit | Distribution | 2.1141 |  | HFTD 3 | 0.001478 | 0.001456 | 2.2005e-05 | 0.0051972 | 0.0024475 | 0.00010512 | 0.0026446 | N/A | 0.0030784 | 0.28015 | N/A | N/A | 1.0747 | 0.0071482 | N/A | 1.0747
PYTHON | Circuit | Distribution | 26.7118 |  | HFTD 3 | 0.027149 | 0.027121 | 2.7644e-05 | 0.0073457 | 0.003078 | 7.6192e-05 | 0.0041914 | N/A | 0.06263 | 3.6921 | N/A | N/A | 1.1347 | 0.00044139 | N/A | 1.1347
QUARRY | Circuit | Distribution | 4.522 |  | HFTD 2 | 0.0053467 | 0.0053112 | 3.5527e-05 | 0.0071079 | 0.0037342 | 0.00034132 | 0.0030323 | N/A | 0.0027317 | 0.74723 | N/A | N/A | 1.1933 | 0.013005 | N/A | 1.1933
QUICKSILVER | Circuit | Distribution | 16.9394 |  | HFTD 2 | 0.0049249 | 0.0049249 | 0 | 0.0093451 | 0.0055955 | 0.0015735 | 0.002176 | N/A | 0.0026358 | 0.52701 | N/A | N/A | 1.2946 | 0 | N/A | 1.2946
QUINBY | Circuit | Distribution | 2.8738 |  | HFTD 2 | 0.019446 | 0.01941 | 3.5435e-05 | 0.0046395 | 0.0024802 | 0.00012623 | 0.0020331 | N/A | 0.002617 | 4.1838 | N/A | N/A | 1.0889 | 0.01354 | N/A | 1.0889
QUIXOTE | Circuit | Distribution | 0.75878 |  | HFTD 2 | 0.0017077 | 0.0017074 | 3.7399e-07 | 0.0045225 | 0.0026945 | 3.1688e-05 | 0.0017964 | N/A | 0.0075344 | 0.37752 | N/A | N/A | 1.6316 | 4.9637e-05 | N/A | 1.6316
RACER | Circuit | Distribution | 1.7677 |  | HFTD 3 | 0.0016694 | 0.0016098 | 5.9615e-05 | 0.020537 | 0.012267 | 0.00024517 | 0.0080255 | N/A | 0.0079565 | 0.078384 | N/A | N/A | 1.1887 | 0.0074926 | N/A | 1.1887
RAINBOW | Circuit | Distribution | 14.8919 |  | HFTD 3 | 0.0043126 | 0.004306 | 6.5551e-06 | 0.0056972 | 0.0039283 | 0.00017599 | 0.0015929 | N/A | 0.015116 | 0.75582 | N/A | N/A | 1.1642 | 0.00043365 | N/A | 1.1642
RAISIN | Circuit | Distribution | 2.9174 |  | HFTD 2 | 0.0030512 | 0.0026177 | 0.00043343 | 0.012803 | 0.0092595 | 0.00032391 | 0.0032194 | N/A | 0.0031842 | 0.20446 | N/A | N/A | 1.1316 | 0.13612 | N/A | 1.1316
RAMAC | Circuit | Distribution | 7.0704 |  | HFTD 2 | 0.0003084 | 0.00029894 | 9.4563e-06 | 0.00068476 | 0.00040032 | 2.5601e-05 | 0.00025884 | N/A | 0.0018323 | 0.43656 | N/A | N/A | 1.1092 | 0.0051609 | N/A | 1.1092
RAMSGATE | Circuit | Distribution | 1.0497 |  | HFTD 3 | 0.020132 | 0.02 | 0.00013152 | 0.0030129 | 0.0019445 | 0.00027912 | 0.00078928 | N/A | 0.0068129 | 6.6382 | N/A | N/A | 1.0712 | 0.019304 | N/A | 1.0712
RANGER | Circuit | Distribution | 5.7427 | Top 5% Highest Risk | HFTD 3 | 0.092485 | 0.092455 | 3.0025e-05 | 0.017602 | 0.010033 | 0.0065327 | 0.0010364 | N/A | 0.048455 | 5.2524 | N/A | N/A | 1.1101 | 0.00061964 | N/A | 1.1101
RANIER | Circuit | Distribution | 2.8152 |  | HFTD 2 | 0.028899 | 0.028895 | 3.8395e-06 | 0.0054164 | 0.0034215 | 0.00022408 | 0.0017708 | N/A | 0.0049382 | 5.3347 | N/A | N/A | 1.1074 | 0.00077751 | N/A | 1.1074
RANKIN | Circuit | Distribution | 13.2533 |  | HFTD 2 | 0.0038356 | 0.0038353 | 3.3663e-07 | 0.0019816 | 0.0016514 | 3.6059e-05 | 0.00029416 | N/A | 0.016584 | 1.9354 | N/A | N/A | 1.0133 | 2.0299e-05 | N/A | 1.0133
RAVINE | Circuit | Distribution | 15.1352 |  | HFTD 2 | 0.0045097 | 0.0045086 | 1.123e-06 | 0.0095819 | 0.0042735 | 0.002343 | 0.0029654 | N/A | 0.0093076 | 0.47053 | N/A | N/A | 1.0494 | 0.00012065 | N/A | 1.0494
RAYBURN | Circuit | Distribution | 13.029 | Top 5% Highest Risk | HFTD 3 | 0.073041 | 0.072988 | 5.3547e-05 | 0.0082255 | 0.0056249 | 7.6778e-05 | 0.0025238 | N/A | 0.049582 | 8.8733 | N/A | N/A | 1.1122 | 0.00108 | N/A | 1.1122
READY | Circuit | Distribution | 2.3151 |  | HFTD 2 | 0.0039636 | 0.0039165 | 4.7103e-05 | 0.0079419 | 0.0053508 | 0.00038761 | 0.0022035 | N/A | 0.0029061 | 0.49314 | N/A | N/A | 1.0476 | 0.016208 | N/A | 1.0476
RED BARN | Circuit | Distribution | 0.30974 |  | HFTD 2 | 0.011642 | 0.011642 | 0 | 0.0014075 | 0.00088994 | 0.00013447 | 0.00038309 | N/A | 0 | 8.2712 | N/A | N/A | 1.3218 |  | N/A | 1.3218
RED BOX | Circuit | Distribution | 17.5743 |  | HFTD 3 | 0.001813 | 0.0018122 | 7.8789e-07 | 0.0026161 | 0.00082072 | 6.7578e-05 | 0.0017278 | N/A | 0.024781 | 0.69272 | N/A | N/A | 1.261 | 3.1794e-05 | N/A | 1.261
RED MOUNTAIN | Circuit | Distribution | 16.0301 |  | HFTD 3 | 0.0011274 | 0.0011267 | 7.3808e-07 | 0.0045199 | 0.0027818 | 0.00029435 | 0.0014437 | N/A | 0 | 0.24928 | N/A | N/A | 1.5519 | inf | N/A | 1.5519
REDBALL | Circuit | Distribution | 1.0763 |  | HFTD 2 | 0.0028404 | 0.00264 | 0.00020037 | 0.0023808 | 0.0018196 | 7.2062e-05 | 0.0004891 | N/A | 0.0078408 | 1.1089 | N/A | N/A | 1.0348 | 0.025555 | N/A | 1.0348
REDBANKS | Circuit | Distribution | 2.28 |  | HFTD 2 | 0.00032905 | 0.00032905 | 0 | 0.0016242 | 0.001319 | 1.0025e-05 | 0.00029517 | N/A | 0 | 0.20259 | N/A | N/A | 1.1087 |  | N/A | 1.1087
REDINGER | Circuit | Distribution | 0.28674 |  | HFTD 3 | 0.0023651 | 0.0023651 | 0 | 0.006151 | 0.0029444 | 0.0011118 | 0.0020948 | N/A | 0 | 0.38451 | N/A | N/A |  |  | N/A
REDSTONE | Circuit | Distribution | 0.30205 |  | HFTD 2 | 0.00042555 | 0.00042555 | 0 | 0.0027712 | 0.00063312 | 0.00038976 | 0.0017483 | N/A | 0 | 0.15356 | N/A | N/A | 1.1226 |  | N/A | 1.1226
REED | Circuit | Distribution | 1.9079 |  | HFTD 2 | 0.027137 | 0.027117 | 1.9866e-05 | 0.0045248 | 0.00261 | 0.00020251 | 0.0017122 | N/A | 0.0032621 | 5.993 | N/A | N/A | 1.0863 | 0.0060899 | N/A | 1.0863
REEDER | Circuit | Distribution | 0.42735 |  | HFTD 2 | 0.0057175 | 0.0056612 | 5.6298e-05 | 0.0047772 | 0.0019409 | 0.00033925 | 0.002497 | N/A | 0.00016156 | 1.1851 | N/A | N/A | 1.1872 | 0.34847 | N/A | 1.1872
REGATTA | Circuit | Distribution | 8.9792 |  |  | 0.0014451 | 0.0014451 | 0 | 0.0041217 | 0.0015151 | 0.00077854 | 0.0018281 | N/A |  | 0.3506 | N/A | N/A |  |  | N/A
REJADA | Circuit | Distribution | 3.7703 |  | HFTD 3 | 0.0041037 | 0.0040622 | 4.1433e-05 | 0.009269 | 0.0055385 | 0.00051169 | 0.0032189 | N/A | 0.02213 | 0.43826 | N/A | N/A | 1.0589 | 0.0018722 | N/A | 1.0589
RESORT | Circuit | Distribution | 17.1339 |  | HFTD 3 | 0.0050545 | 0.0050544 | 8.1975e-08 | 0.0036479 | 0.0023095 | 0.00013985 | 0.0011985 | N/A | 0.012964 | 1.3856 | N/A | N/A | 1.9386 | 6.3233e-06 | N/A | 1.9386
REVERSE PEAK | Circuit | Distribution | 25.1586 |  | HFTD 2 | 0.0058222 | 0.0057314 | 9.087e-05 | 0.0046127 | 0.0032906 | 0.00028443 | 0.0010377 | N/A | 0.13342 | 1.2425 | N/A | N/A | 1.1481 | 0.00068106 | N/A | 1.1481
RHINEDOLLAR | Circuit | Distribution | 1.9672 |  | HFTD 2 | 0.0010226 | 0.0009697 | 5.2938e-05 | 0.0023528 | 0.0010894 | 0.00059916 | 0.00066425 | N/A | 0.093635 | 0.41215 | N/A | N/A | 1.2069 | 0.00056537 | N/A | 1.2069
RHODA | Circuit | Distribution | 4.2683 |  | HFTD 3 | 0.04092 | 0.040904 | 1.6704e-05 | 0.0075117 | 0.0044785 | 0.00022081 | 0.0028124 | N/A | 0.011992 | 5.4453 | N/A | N/A | 1.0932 | 0.001393 | N/A | 1.0932
RICARDO | Circuit | Distribution | 3.3477 |  | HFTD 3 | 0.0058871 | 0.0058736 | 1.3533e-05 | 0.016167 | 0.0078073 | 0.00032838 | 0.0080315 | N/A | 0.0024317 | 0.3633 | N/A | N/A | 1.0516 | 0.0055651 | N/A | 1.0516
RIDGE | Circuit | Distribution | 22.2038 |  | HFTD 2 | 0.0050008 | 0.0049993 | 1.5863e-06 | 0.0040613 | 0.0028865 | 8.434e-05 | 0.0010905 | N/A | 0.024887 | 1.2309 | N/A | N/A | 1.1819 | 6.374e-05 | N/A | 1.1819
RIDGEMOOR | Circuit | Distribution | 0.67661 |  | HFTD 2 | 0.00030793 | 0.00024327 | 6.466e-05 | 0.013249 | 0.004975 | 0.00015978 | 0.0081142 | N/A | 0.00018229 | 0.018361 | N/A | N/A | 1.1147 | 0.35471 | N/A | 1.1147
RIM | Circuit | Distribution | 25.2792 |  | HFTD 3 | 0.026188 | 0.026122 | 6.5458e-05 | 0.0091941 | 0.0067493 | 0.00085275 | 0.001592 | N/A | 0.066914 | 2.8412 | N/A | N/A | 1.2379 | 0.00097825 | N/A | 1.2379
RITTER | Circuit | Distribution | 1.1996 |  | HFTD 2 | 0.0086568 | 0.0085644 | 9.2398e-05 | 0.0079324 | 0.005174 | 7.0027e-05 | 0.0026884 | N/A | 0.021148 | 1.0797 | N/A | N/A | 1.1477 | 0.004369 | N/A | 1.1477
RIVA | Circuit | Distribution | 33.7454 |  | HFTD 3 | 0.0069173 | 0.0069173 | 0 | 0.0096162 | 0.0074052 | 0.00058381 | 0.0016272 | N/A | 0 | 0.71933 | N/A | N/A | 1.1008 |  | N/A | 1.1008
RIVIERA | Circuit | Distribution | 4.7396 |  | HFTD 2 | 0.018062 | 0.018061 | 1.6287e-06 | 0.010972 | 0.0074952 | 0.0015586 | 0.0019181 | N/A | 0.0037382 | 1.6461 | N/A | N/A | 1.248 | 0.0004357 | N/A | 1.248
RMV 1243 | Circuit | Distribution | 1.9143 |  | HFTD 2 | 0.0027835 | 0.0027797 | 3.7938e-06 | 0.0043361 | 0.002673 | 0.00051961 | 0.0011435 | N/A | 0.0019775 | 0.64106 | N/A | N/A | 1.7885 | 0.0019185 | N/A | 1.7885
ROADRUNNER | Circuit | Distribution | 10.0238 |  | HFTD 2 | 0.016131 | 0.016121 | 1.0469e-05 | 0.0068529 | 0.0046992 | 9.9079e-05 | 0.0020546 | N/A | 0.0089057 | 2.3524 | N/A | N/A | 1.5112 | 0.0011756 | N/A | 1.5112
ROBIN | Circuit | Distribution | 14.0003 |  | HFTD 3 | 0.036837 | 0.036837 | 7.9776e-07 | 0.010875 | 0.0055657 | 0.0001625 | 0.005147 | N/A | 0.055633 | 3.3872 | N/A | N/A | 1.1875 | 1.434e-05 | N/A | 1.1875
ROBINSON CREEK | Circuit | Distribution | 16.5659 |  | HFTD 2 | 0.003185 | 0.0031496 | 3.5389e-05 | 0.0034074 | 0.0019133 | 0.00019895 | 0.0012952 | N/A | 0.042159 | 0.92435 | N/A | N/A | 1.5047 | 0.00083943 | N/A | 1.5047
ROCKCREEK | Circuit | Distribution | 14.4317 |  | HFTD 2 | 0.0057312 | 0.005712 | 1.9267e-05 | 0.0023258 | 0.0018596 | 8.5354e-05 | 0.00038087 | N/A | 0.067566 | 2.4559 | N/A | N/A | 1.8321 | 0.00028515 | N/A | 1.8321
ROCKHILL | Circuit | Distribution | 16.1178 |  | HFTD 2 | 0.0072409 | 0.0072406 | 2.7963e-07 | 0.0061327 | 0.0028518 | 0.00033097 | 0.0029499 | N/A | 0 | 1.1807 | N/A | N/A | 1.3133 | inf | N/A | 1.3133
ROCKRIDGE | Circuit | Distribution | 2.4263 |  | HFTD 2 | 0.02136 | 0.021351 | 9.4753e-06 | 0.0055941 | 0.0029276 | 0.00023011 | 0.0024364 | N/A | 0.0039757 | 3.8167 | N/A | N/A | 1.0771 | 0.0023833 | N/A | 1.0771
ROCKWELL | Circuit | Distribution | 8.1583 |  | HFTD 2 | 0.011598 | 0.011598 | 0 | 0.0056265 | 0.0039938 | 0.00024746 | 0.0013853 | N/A | 0 | 2.0614 | N/A | N/A | 1.1831 |  | N/A | 1.1831
ROI-TAN | Circuit | Distribution | 2.3597 |  | HFTD 2 | 0.0028101 | 0.0014961 | 0.001314 | 0.0033566 | 0.0019816 | 8.0131e-05 | 0.0012948 | N/A | 0.0021071 | 0.44571 | N/A | N/A | 1.158 | 0.6236 | N/A | 1.158
ROMANUS | Circuit | Distribution | 5.757 |  | HFTD 3 | 0.013728 | 0.013635 | 9.2912e-05 | 0.0071278 | 0.0039847 | 7.2055e-05 | 0.0030711 | N/A | 0.01249 | 1.913 | N/A | N/A | 1.087 | 0.0074389 | N/A | 1.087
ROMERO | Circuit | Distribution | 1.0063 |  | HFTD 3 | 0.048874 | 0.048846 | 2.7987e-05 | 0.007898 | 0.0041055 | 3.8e-05 | 0.0037545 | N/A | 0.004432 | 6.1846 | N/A | N/A | 1.0622 | 0.0063147 | N/A | 1.0622
ROS | Circuit | Distribution | 23.1354 |  | HFTD 2 | 0.0066077 | 0.006603 | 4.6952e-06 | 0.0024344 | 0.0017972 | 5.9842e-05 | 0.00057742 | N/A | 0.0092919 | 2.7124 | N/A | N/A | 1.1285 | 0.0005053 | N/A | 1.1285
ROSA | Circuit | Distribution | 4.6624 |  | HFTD 3 | 0.005557 | 0.0055537 | 3.2234e-06 | 0.012134 | 0.0054208 | 0.00057204 | 0.0061407 | N/A | 0 | 0.45772 | N/A | N/A | 1.0887 | inf | N/A | 1.0887
ROSEBUD | Circuit | Distribution | 24.2061 |  | HFTD 3 | 0.0050112 | 0.0050111 | 9.1629e-08 | 0.0076653 | 0.002844 | 0.001188 | 0.0036333 | N/A | 0.0079306 | 0.65373 | N/A | N/A | 1.2942 | 1.1554e-05 | N/A | 1.2942
ROSEMONT | Circuit | Distribution | 14.0307 |  | HFTD 2 | 0.0049256 | 0.0049076 | 1.8075e-05 | 0.015275 | 0.0059214 | 0.0036478 | 0.005706 | N/A | 0.024328 | 0.32128 | N/A | N/A | 1.1079 | 0.00074298 | N/A | 1.1079
ROTEC | Circuit | Distribution | 4.8943 |  | HFTD 2 | 0.045499 | 0.045484 | 1.4753e-05 | 0.0039582 | 0.0030153 | 0.00016238 | 0.00078047 | N/A | 0.00071962 | 11.4913 | N/A | N/A | 1.0681 | 0.020501 | N/A | 1.0681
ROUNDEL | Circuit | Distribution | 5.7942 |  | HFTD 2 | 0.021326 | 0.021302 | 2.4495e-05 | 0.0050507 | 0.0035413 | 6.9495e-05 | 0.0014399 | N/A | 0.01919 | 4.2176 | N/A | N/A | 1.1329 | 0.0012765 | N/A | 1.1329
ROWCO | Circuit | Distribution | 18.8032 |  | HFTD 3 | 0.025297 | 0.024935 | 0.00036241 | 0.0095842 | 0.0056735 | 0.0018434 | 0.0020672 | N/A | 0.24166 | 2.6016 | N/A | N/A | 1.4196 | 0.0014997 | N/A | 1.4196
ROXBURY | Circuit | Distribution | 0.45031 |  | HFTD 2 | 0.00046616 | 0.00046616 | 0 | 0.027969 | 0.012536 | 0.002334 | 0.013099 | N/A | 0.00037199 | 0.016667 | N/A | N/A | 1.0988 | 0 | N/A | 1.0988
ROYCE | Circuit | Distribution | 0.48186 |  | HFTD 2 | 0.0054616 | 0.0054616 | 0 | 0.008123 | 0.0041456 | 0.00078198 | 0.0031954 | N/A | 0.0076906 | 0.67236 | N/A | N/A |  | 0 | N/A
RUBIN | Circuit | Distribution | 7.7382 |  | HFTD 3 | 0.015189 | 0.015184 | 5.1711e-06 | 0.0067975 | 0.002774 | 0.00020167 | 0.0038219 | N/A | 0.0053506 | 2.2337 | N/A | N/A | 1.1607 | 0.00096646 | N/A | 1.1607
RUIZ | Circuit | Distribution | 7.4149 |  | HFTD 2 | 0.0050461 | 0.0050424 | 3.6834e-06 | 0.0040691 | 0.0026948 | 9.4909e-05 | 0.0012794 | N/A | 0.0029345 | 1.2392 | N/A | N/A | 1.0893 | 0.0012552 | N/A | 1.0893
RUSTIC | Circuit | Distribution | 18.5483 |  | HFTD 3 | 0.016725 | 0.016678 | 4.6923e-05 | 0.0042149 | 0.0023927 | 0.0001861 | 0.001636 | N/A | 0.040353 | 3.957 | N/A | N/A | 1.207 | 0.0011628 | N/A | 1.207
RYE | Circuit | Distribution | 1.6867 |  | HFTD 2 | 0.0012205 | 0.00085323 | 0.0003673 | 0.012239 | 0.003046 | 0.0062395 | 0.0029539 | N/A | 0.0023612 | 0.069712 | N/A | N/A | 1.1053 | 0.15556 | N/A | 1.1053
SABRINA | Circuit | Distribution | 7.7946 |  | HFTD 2 | 0.0067452 | 0.0066689 | 7.625e-05 | 0.0038699 | 0.0023108 | 0.00039727 | 0.0011618 | N/A | 0.11005 | 1.7233 | N/A | N/A | 1.3572 | 0.00069285 | N/A | 1.3572
SADDLEBACK | Circuit | Distribution | 6.9228 |  | HFTD 2 | 0.0315 | 0.0315 | 8.2276e-08 | 0.0041666 | 0.0015494 | 0.00020406 | 0.0024131 | N/A | 0.017646 | 7.5601 | N/A | N/A | 1.0182 | 4.6625e-06 | N/A | 1.0182
SAGEHEN | Circuit | Distribution | 29.7273 |  | HFTD 2 | 0.00036368 | 0.00035227 | 1.1414e-05 | 0.00035271 | 0.00034993 | 6.9388e-07 | 2.0884e-06 | N/A | 0.011667 | 0.99873 | N/A | N/A | 1.1423 | 0.00097829 | N/A | 1.1423
SAGINAW | Circuit | Distribution | 5.6856 |  | HFTD 3 | 0.0017461 | 0.0017441 | 2.064e-06 | 0.0046439 | 0.0013787 | 0.00097983 | 0.0022854 | N/A | 0.077149 | 0.37556 | N/A | N/A | 1.4737 | 2.6753e-05 | N/A | 1.4737
SAINT JO | Circuit | Distribution | 2.4546 |  | HFTD 2 | 0.004568 | 0.0045303 | 3.7698e-05 | 0.016493 | 0.0071006 | 0.0026746 | 0.0067176 | N/A | 0.0030221 | 0.27468 | N/A | N/A | 1.0864 | 0.012474 | N/A | 1.0864
SALT CREEK | Circuit | Distribution | 28.8831 |  | HFTD 2 | 0.0053933 | 0.0053923 | 9.9178e-07 | 0.0033634 | 0.0015353 | 0.00051637 | 0.0013117 | N/A | 0.019125 | 1.6032 | N/A | N/A | 1.222 | 5.1858e-05 | N/A | 1.222
SAN NICHOLAS | Circuit | Distribution | 7.3939 |  | HFTD 3 | 0.0020293 | 0.0020006 | 2.8717e-05 | 0.010143 | 0.007574 | 0.00041805 | 0.002151 | N/A | 0.01164 | 0.19724 | N/A | N/A | 1.0912 | 0.0024672 | N/A | 1.0912
SANCHO | Circuit | Distribution | 1.8171 |  | HFTD 2 | 0.00087077 | 0.00087052 | 2.5218e-07 | 0.0022028 | 0.0017308 | 2.3666e-05 | 0.00044837 | N/A | 0.013547 | 0.39518 | N/A | N/A | 1 | 1.8615e-05 | N/A | 1
SAND CANYON | Circuit | Distribution | 27.0107 |  | HFTD 3 | 0.030743 | 0.030698 | 4.5308e-05 | 0.0057641 | 0.0025107 | 7.2245e-05 | 0.0031812 | N/A | 0.060566 | 5.3256 | N/A | N/A | 1.1495 | 0.00074808 | N/A | 1.1495
SANTORINI | Circuit | Distribution | 3.3621 |  | HFTD 2 | 0.026874 | 0.026828 | 4.6204e-05 | 0.0063879 | 0.0039061 | 0.00023562 | 0.0022461 | N/A | 0.0066911 | 4.1998 | N/A | N/A | 1.3539 | 0.0069053 | N/A | 1.3539
SAUNDERS | Circuit | Distribution | 43.5958 | Top 5% Highest Risk | HFTD 3 | 0.060397 | 0.060395 | 1.5603e-06 | 0.010142 | 0.0078567 | 0.0010454 | 0.0012404 | N/A | 0.040569 | 5.9547 | N/A | N/A | 1.1338 | 3.846e-05 | N/A | 1.1338
SAUTERNE | Circuit | Distribution | 0.40115 |  | HFTD 2 | 0.0038646 | 0.001746 | 0.0021186 | 0.0061971 | 0.0040814 | 5.5647e-05 | 0.00206 | N/A | 0 | 0.28175 | N/A | N/A | 1.1213 | inf | N/A | 1.1213
SAVORY | Circuit | Distribution | 9.9789 |  | HFTD 2 | 0.008108 | 0.0080971 | 1.0955e-05 | 0.0039979 | 0.0022118 | 7.6506e-05 | 0.0017096 | N/A | 0.005569 | 2.0253 | N/A | N/A | 1.2016 | 0.0019671 | N/A | 1.2016
SAWPIT | Circuit | Distribution | 3.5537 |  | HFTD 3 | 0.014448 | 0.014448 | 0 | 0.0012265 | 0.00084312 | 0.00026624 | 0.0001171 | N/A | 0.028664 | 11.7806 | N/A | N/A |  | 0 | N/A
SCALP | Circuit | Distribution | 0.58462 |  | HFTD 2 | 0.020564 | 0.020542 | 2.1848e-05 | 0.0092589 | 0.0022826 | 0.0007458 | 0.0062305 | N/A | 0.0016577 | 2.2187 | N/A | N/A | 1.5856 | 0.01318 | N/A | 1.5856
SCHMIDT | Circuit | Distribution | 15.463 |  | HFTD 2 | 0.052875 | 0.052865 | 1.0403e-05 | 0.0056063 | 0.0046991 | 6.5033e-05 | 0.00084222 | N/A | 0.013449 | 9.4295 | N/A | N/A | 1.114 | 0.00077352 | N/A | 1.114
SCIURBA | Circuit | Distribution | 13.8151 |  | HFTD 2 | 0.0031087 | 0.0031087 | 0 | 0.01177 | 0.0039748 | 0.0035036 | 0.0042914 | N/A | 0 | 0.26412 | N/A | N/A | 1.0953 |  | N/A | 1.0953
SDGE 520 | Circuit | Distribution | 2.6285 |  | HFTD 3 | 0.019484 | 0.019484 | 1.6282e-07 | 0.0022681 | 0.0014444 | 0.00012574 | 0.00069795 | N/A | 0.0026112 | 8.5905 | N/A | N/A | 1.0094 | 6.2354e-05 | N/A | 1.0094
SDGE 521 | Circuit | Distribution | 3.6344 |  | HFTD 3 | 0.011909 | 0.011909 | 3.602e-08 | 0.0008356 | 0.00049382 | 6.9973e-05 | 0.00027181 | N/A | 0.0010594 | 14.2516 | N/A | N/A | 1.6376 | 3.3999e-05 | N/A | 1.6376
SEABOARD | Circuit | Distribution | 0.38068 |  |  | 0.0062464 | 0.0062464 | 0 | 0.038581 | 0.029302 | 0.001066 | 0.0082122 | N/A |  | 0.16191 | N/A | N/A | 1.2626 |  | N/A | 1.2626
SEACLIFF | Circuit | Distribution | 42.618 |  | HFTD 2 | 0.0044118 | 0.0044107 | 1.1315e-06 | 0.0078623 | 0.0040512 | 0.0013928 | 0.0024184 | N/A | 0.0079775 | 0.56099 | N/A | N/A | 1.1305 | 0.00014184 | N/A | 1.1305
SEAFORTH | Circuit | Distribution | 4.6443 |  | HFTD 2 | 0.013088 | 0.012855 | 0.00023283 | 0.00681 | 0.003421 | 2.5172e-05 | 0.0033638 | N/A | 0.00088486 | 1.8877 | N/A | N/A | 1.2317 | 0.26313 | N/A | 1.2317
SEAWOLF | Circuit | Distribution | 1.1577 |  | HFTD 2 | 0.045035 | 0.045031 | 4.0085e-06 | 0.013669 | 0.0099497 | 0.00031593 | 0.0034037 | N/A | 0.00039746 | 3.2943 | N/A | N/A | 1.1073 | 0.010085 | N/A | 1.1073
SEBASTIAN | Circuit | Distribution | 0.89561 |  | HFTD 2 | 0.0019602 | 0.0018354 | 0.00012482 | 0.0034205 | 0.0024369 | 0.00018651 | 0.00079709 | N/A | 0.0014991 | 0.53659 | N/A | N/A | 1.3059 | 0.083261 | N/A | 1.3059
SECO | Circuit | Distribution | 1.0175 |  | HFTD 2 | 0.010238 | 0.010118 | 0.00011995 | 0.010132 | 0.0052142 | 0.00082094 | 0.0040967 | N/A | 0.0022272 | 0.99864 | N/A | N/A | 1.1238 | 0.053857 | N/A | 1.1238
SEELEY | Circuit | Distribution | 6.8661 | Top 5% Highest Risk | HFTD 3 | 0.056626 | 0.05655 | 7.6017e-05 | 0.024072 | 0.01382 | 0.0021144 | 0.0081374 | N/A | 0.054077 | 2.3492 | N/A | N/A | 1.2326 | 0.0014057 | N/A | 1.2326
SEMINARY | Circuit | Distribution | 6.111 |  | HFTD 2 | 0.00238 | 0.0023598 | 2.0236e-05 | 0.0048142 | 0.0030158 | 0.0003143 | 0.0014841 | N/A | 0.0039455 | 0.49017 | N/A | N/A | 1.0848 | 0.005129 | N/A | 1.0848
SERRA | Circuit | Distribution | 19.8615 |  | HFTD 3 | 0.015707 | 0.015705 | 1.9764e-06 | 0.0074389 | 0.0030333 | 0.0006501 | 0.0037555 | N/A | 0.018855 | 2.1112 | N/A | N/A | 1.2687 | 0.00010482 | N/A | 1.2687
SESPE | Circuit | Distribution | 0.64986 |  | HFTD 3 | 0.00012684 | 0.00012514 | 1.7053e-06 | 0.003512 | 0.0019506 | 0.00029038 | 0.001271 | N/A | 0.0014367 | 0.035632 | N/A | N/A | 1.0088 | 0.001187 | N/A | 1.0088
SEXTON | Circuit | Distribution | 13.2788 |  | HFTD 3 | 0.0067611 | 0.0067277 | 3.3331e-05 | 0.0063939 | 0.004784 | 0.00054968 | 0.0010602 | N/A | 0.01337 | 1.0522 | N/A | N/A | 1.1285 | 0.002493 | N/A | 1.1285
SEYMOUR | Circuit | Distribution | 13.5547 |  | HFTD 3 | 0.0031164 | 0.0031163 | 8.3832e-08 | 0.0028147 | 0.001608 | 0.00029258 | 0.00091411 | N/A | 0.029401 | 1.1071 | N/A | N/A | 1 | 2.8513e-06 | N/A | 1
SHAKE | Circuit | Distribution | 4.8768 |  | HFTD 3 | 0.018014 | 0.018014 | 0 | 0.0039694 | 0.0023222 | 0.00048976 | 0.0011575 | N/A | 0.069147 | 4.5382 | N/A | N/A |  | 0 | N/A
SHAMROCK | Circuit | Distribution | 0.91108 |  | HFTD 3 | 0.0031947 | 0.0031658 | 2.8899e-05 | 0.016986 | 0.0068952 | 0.0023527 | 0.0077377 | N/A | 0.0083298 | 0.18638 | N/A | N/A | 1.0093 | 0.0034694 | N/A | 1.0093
SHASTA | Circuit | Distribution | 9.2128 |  | HFTD 2 | 0.015516 | 0.015513 | 2.5858e-06 | 0.0054445 | 0.0032454 | 0.00018536 | 0.0020138 | N/A | 0.0052487 | 2.8493 | N/A | N/A | 1.1591 | 0.00049266 | N/A | 1.1591
SHEEPHOLE | Circuit | Distribution | 0.41301 |  |  | 0.006314 | 0.006314 | 0 | 0.0014625 | 0.00076467 | 1.1939e-05 | 0.00068591 | N/A |  | 4.3172 | N/A | N/A | 1.279 |  | N/A | 1.279
SHEFFIELD | Circuit | Distribution | 33.9886 |  | HFTD 3 | 0.023024 | 0.023018 | 6.4002e-06 | 0.010262 | 0.0054972 | 0.00072748 | 0.0040374 | N/A | 0.031254 | 2.243 | N/A | N/A | 1.1241 | 0.00020478 | N/A | 1.1241
SHERBOURNE | Circuit | Distribution | 5.5983 |  | HFTD 2 | 0.0019088 | 0.0019088 | 0 | 0.0057259 | 0.00297 | 0.00093124 | 0.0018247 | N/A | 0 | 0.33337 | N/A | N/A | 1.1303 |  | N/A | 1.1303
SHETLAND | Circuit | Distribution | 1.2878 |  | HFTD 2 | 0.036642 | 0.036642 | 0 | 0.0093846 | 0.005202 | 0.00097166 | 0.003211 | N/A | 0 | 3.9044 | N/A | N/A | 1.0975 |  | N/A | 1.0975
SHINE | Circuit | Distribution | 0.91257 |  | HFTD 2 | 0.017267 | 0.01484 | 0.0024271 | 0.0077046 | 0.0043768 | 0.00040794 | 0.0029199 | N/A | 0.0026154 | 1.9262 | N/A | N/A | 1.1218 | 0.928 | N/A | 1.1218
SHIPLEY | Circuit | Distribution | 1.6436 |  |  | 0.015937 | 0.015937 | 0 | 0.0030552 | 0.0018414 | 7.3858e-05 | 0.0011399 | N/A |  | 5.2162 | N/A | N/A | 1.02 |  | N/A | 1.02
SHIRAZ | Circuit | Distribution | 3.9964 |  | HFTD 2 | 0.0015092 | 0.001098 | 0.00041115 | 0.005596 | 0.0025712 | 0.00010186 | 0.0029229 | N/A | 0.0023679 | 0.19622 | N/A | N/A | 1.1482 | 0.17363 | N/A | 1.1482
SHOPPER | Circuit | Distribution | 2.6775 |  | HFTD 2 | 0.00098786 | 0.00098701 | 8.4733e-07 | 0.0045108 | 0.002985 | 8.5317e-05 | 0.0014405 | N/A | 0.00041248 | 0.21881 | N/A | N/A | 1.0661 | 0.0020542 | N/A | 1.0661
SHOPPING | Circuit | Distribution | 0.36612 |  | HFTD 3 | 0.0013205 | 0.00094748 | 0.00037304 | 0.023389 | 0.012887 | 0.0009813 | 0.0095209 | N/A | 0.0079915 | 0.04051 | N/A | N/A | 1.0585 | 0.04668 | N/A | 1.0585
SHORELINE | Circuit | Distribution | 7.0987 |  | HFTD 2 | 0.0093382 | 0.0093382 | 0 | 0.0049763 | 0.0032039 | 0.0005901 | 0.0011823 | N/A | 0 | 1.8765 | N/A | N/A | 1.334 |  | N/A | 1.334
SHOVEL | Circuit | Distribution | 50.499 | Top 5% Highest Risk | HFTD 3 | 0.071594 | 0.071594 | 0 | 0.0065765 | 0.0025446 | 2.1338e-05 | 0.0040105 | N/A | 0.10587 | 10.8864 | N/A | N/A | 1.1263 | 0 | N/A | 1.1263
SHOWDOWN | Circuit | Distribution | 4.644 |  | HFTD 3 | 0.027955 | 0.027875 | 7.9995e-05 | 0.0061981 | 0.0028978 | 4.1026e-05 | 0.0032593 | N/A | 0.019445 | 4.4974 | N/A | N/A | 1.3722 | 0.0041138 | N/A | 1.3722
SIAM | Circuit | Distribution | 1.4829 |  | HFTD 2 | 0.035781 | 0.035691 | 9.0122e-05 | 0.011692 | 0.0035107 | 0.00055634 | 0.007625 | N/A | 0.0088816 | 3.0526 | N/A | N/A | 1.0942 | 0.010147 | N/A | 1.0942
SIENNA | Circuit | Distribution | 6.4588 |  | HFTD 3 | 0.015928 | 0.015902 | 2.5712e-05 | 0.015688 | 0.010175 | 0.00041126 | 0.0051016 | N/A | 0.013057 | 1.0137 | N/A | N/A | 1.1473 | 0.0019692 | N/A | 1.1473
SILICONE | Circuit | Distribution | 9.8293 |  | HFTD 2 | 0.0054665 | 0.0054665 | 0 | 0.0077113 | 0.0035678 | 0.00079915 | 0.0033444 | N/A | 0.0011421 | 0.70889 | N/A | N/A | 1.1565 | 0 | N/A | 1.1565
SILVA | Circuit | Distribution | 0.54922 |  | HFTD 2 | 0.028974 | 0.026863 | 0.0021107 | 0.0066086 | 0.0055382 | 0.00017655 | 0.00089384 | N/A | 0.020282 | 4.0649 | N/A | N/A | 1.0841 | 0.10407 | N/A | 1.0841
SIMS | Circuit | Distribution | 1.8369 |  | HFTD 2 | 0.029455 | 0.029293 | 0.00016143 | 0.0076187 | 0.0030642 | 0.00010352 | 0.004451 | N/A | 0.0009907 | 3.8449 | N/A | N/A | 1.1816 | 0.16295 | N/A | 1.1816
SINALOA | Circuit | Distribution | 5.3809 |  | HFTD 3 | 0.0029535 | 0.0028714 | 8.2012e-05 | 0.01177 | 0.0081993 | 0.00034084 | 0.0032299 | N/A | 0.0026622 | 0.24396 | N/A | N/A | 1.1843 | 0.030807 | N/A | 1.1843
SINKER | Circuit | Distribution | 1.6337 |  | HFTD 2 | 0.019154 | 0.019152 | 2.1986e-06 | 0.0024189 | 0.0012435 | 0.00021453 | 0.00096081 | N/A | 0.05083 | 7.9177 | N/A | N/A | 1.4101 | 4.3255e-05 | N/A | 1.4101
SITZMARK | Circuit | Distribution | 3.0583 |  | HFTD 2 | 0.0069243 | 0.005389 | 0.0015353 | 0.022014 | 0.0056817 | 0.0032401 | 0.013092 | N/A | 0.035801 | 0.24479 | N/A | N/A | 1.0908 | 0.042885 | N/A | 1.0908
SKI | Circuit | Distribution | 8.4678 |  | HFTD 2 | 0.021051 | 0.021051 | 0 | 0.0080834 | 0.0045795 | 0.00048775 | 0.0030162 | N/A | 0.021402 | 2.6043 | N/A | N/A |  | 0 | N/A
SKINKLE | Circuit | Distribution | 12.0263 |  | HFTD 2 | 0.00064156 | 0.00063914 | 2.4248e-06 | 0.0020325 | 0.0011439 | 3.6993e-05 | 0.00085164 | N/A | 0.001475 | 0.31446 | N/A | N/A | 1.0724 | 0.0016439 | N/A | 1.0724
SKINNER | Circuit | Distribution | 6.3548 |  | HFTD 2 | 0.017903 | 0.017903 | 4.0294e-09 | 0.005712 | 0.0035459 | 0.00061004 | 0.001556 | N/A | 0.004545 | 3.1343 | N/A | N/A | 2 | 8.8656e-07 | N/A | 2
SKY HI | Circuit | Distribution | 7.2316 |  | HFTD 2 | 0.0089639 | 0.0085647 | 0.00039925 | 0.0023176 | 0.0012867 | 3.3089e-05 | 0.00099782 | N/A | 0.0084909 | 3.6955 | N/A | N/A | 1.2042 | 0.047021 | N/A | 1.2042
SKYBORNE | Circuit | Distribution | 4.1346 |  | HFTD 2 | 0.0022853 | 0.0020316 | 0.00025364 | 0.0027911 | 0.0022319 | 2.45e-05 | 0.00053468 | N/A | 0.019498 | 0.72791 | N/A | N/A | 1.1837 | 0.013008 | N/A | 1.1837
SKYLAND | Circuit | Distribution | 8.7221 |  | HFTD 3 | 0.040319 | 0.040267 | 5.1174e-05 | 0.018568 | 0.0091235 | 0.0018915 | 0.0075531 | N/A | 0.05715 | 2.1686 | N/A | N/A | 1.1578 | 0.00089543 | N/A | 1.1578
SLAB | Circuit | Distribution | 0.97297 |  | HFTD 2 | 0.00078208 | 0.00078208 | 0 | 8.5222e-05 | 3.5759e-05 | 1.0166e-06 | 4.8446e-05 | N/A | 0 | 9.177 | N/A | N/A |  |  | N/A
SLALOM | Circuit | Distribution | 1.2225 |  | HFTD 2 | 0.0065389 | 0.0024798 | 0.0040591 | 0.021727 | 0.0082027 | 0.0014214 | 0.012103 | N/A | 0.041502 | 0.11413 | N/A | N/A | 1.0087 | 0.097805 | N/A | 1.0087
SLOPE | Circuit | Distribution | 2.0674 |  | HFTD 2 | 0.0453 | 0.042998 | 0.002303 | 0.018369 | 0.0083116 | 0.00099643 | 0.0090614 | N/A | 0.043784 | 2.3407 | N/A | N/A | 1.0323 | 0.052599 | N/A | 1.0323
SNO CAT | Circuit | Distribution | 3.282 |  | HFTD 3 | 6.1994e-05 | 6.1991e-05 | 2.6376e-09 | 0.0044911 | 0.00163 | 0.0013114 | 0.0015496 | N/A | 0.0047069 | 0.013803 | N/A | N/A | 1.6316 | 5.6036e-07 | N/A | 1.6316
SNOW VALLEY | Circuit | Distribution | 20.3356 |  | HFTD 3 | 0.0072189 | 0.0072005 | 1.836e-05 | 0.0092351 | 0.0051821 | 0.00091139 | 0.0031416 | N/A | 0.062624 | 0.77969 | N/A | N/A | 1.1856 | 0.00029318 | N/A | 1.1856
SNOWCREEK | Circuit | Distribution | 2.0114 |  | HFTD 2 | 0.021419 | 0.021297 | 0.00012195 | 0.0065217 | 0.0021129 | 0.0002501 | 0.0041587 | N/A | 0.063125 | 3.2655 | N/A | N/A | 1.5202 | 0.0019319 | N/A | 1.5202
SNOWDRIFT | Circuit | Distribution | 1.5717 | Top 5% Highest Risk | HFTD 2 | 0.085207 | 0.084453 | 0.00075386 | 0.023447 | 0.014374 | 0.0012805 | 0.007793 | N/A | 0.012858 | 3.6018 | N/A | N/A | 1.0333 | 0.058631 | N/A | 1.0333
SOCRATES | Circuit | Distribution | 3.9401 |  | HFTD 3 | 0.012053 | 0.012053 | 0 | 0.0086481 | 0.0038984 | 0.00022521 | 0.0045244 | N/A | 0 | 1.3937 | N/A | N/A | 1.1064 |  | N/A | 1.1064
SODA SPRINGS | Circuit | Distribution | 102.1171 |  | HFTD 2 | 0.0016204 | 0.0016201 | 3.3531e-07 | 0.0034863 | 0.0020788 | 0.00029223 | 0.0011152 | N/A | 0.011277 | 0.46471 | N/A | N/A | 1.1537 | 2.9734e-05 | N/A | 1.1537
SOGGY | Circuit | Distribution | 7.9508 |  | HFTD 2 | 0.0046571 | 0.0046501 | 7.0195e-06 | 0.0030823 | 0.0016227 | 2.1335e-05 | 0.0014383 | N/A | 0.0020436 | 1.5086 | N/A | N/A | 1.1926 | 0.0034348 | N/A | 1.1926
SONOMA | Circuit | Distribution | 34.3229 | Top 5% Highest Risk | HFTD 2 | 0.082235 | 0.082233 | 1.7638e-06 | 0.0067537 | 0.0036371 | 4.4892e-05 | 0.0030718 | N/A | 0.0033975 | 12.1759 | N/A | N/A | 1.1984 | 0.00051914 | N/A | 1.1984
SOPHIE | Circuit | Distribution | 30.5478 |  | HFTD 3 | 0.024223 | 0.024222 | 4.6422e-07 | 0.0039728 | 0.0028695 | 0.00014959 | 0.0009537 | N/A | 0.0050169 | 6.097 | N/A | N/A | 1.1642 | 9.2531e-05 | N/A | 1.1642
SORRENTO | Circuit | Distribution | 0.51561 |  | HFTD 2 | 0.0054028 | 0.0052818 | 0.00012104 | 0.019821 | 0.0069018 | 0.00095496 | 0.011964 | N/A | 0.014101 | 0.26648 | N/A | N/A | 1.0387 | 0.0085839 | N/A | 1.0387
SOUTHRIDGE | Circuit | Distribution | 0.49197 |  | HFTD 2 | 0.0060782 | 0.0060018 | 7.6447e-05 | 0.035108 | 0.021645 | 0.0017657 | 0.011697 | N/A | 0.0032822 | 0.17095 | N/A | N/A | 1.0894 | 0.023291 | N/A | 1.0894
SPANADA | Circuit | Distribution | 4.8233 |  | HFTD 3 | 0.0090102 | 0.009005 | 5.1155e-06 | 0.0088223 | 0.0046208 | 0.00015424 | 0.0040473 | N/A | 0.0041363 | 1.0207 | N/A | N/A | 1.4964 | 0.0012367 | N/A | 1.4964
SPARKS | Circuit | Distribution | 0.53036 |  | HFTD 2 | 0.0037111 | 0.0036443 | 6.6885e-05 | 0.0091151 | 0.0050444 | 0.00044379 | 0.0036268 | N/A | 0.00036619 | 0.39981 | N/A | N/A | 1.0889 | 0.18265 | N/A | 1.0889
SPARLING | Circuit | Distribution | 6.0566 |  | HFTD 2 | 0.010291 | 0.01029 | 1.1407e-06 | 0.0048651 | 0.0032558 | 0.00025549 | 0.0013538 | N/A | 0.0015499 | 2.1151 | N/A | N/A | 1.1087 | 0.00073596 | N/A | 1.1087
SPICE | Circuit | Distribution | 3.9598 |  | HFTD 2 | 0.014207 | 0.0142 | 6.8102e-06 | 0.0032112 | 0.0025342 | 7.0241e-05 | 0.00060677 | N/A | 0.0062761 | 4.422 | N/A | N/A | 1.1344 | 0.0010851 | N/A | 1.1344
SPIKE | Circuit | Distribution | 0.85555 |  | HFTD 2 | 0.0033108 | 0.0024983 | 0.00081246 | 0.0039289 | 0.0033186 | 4.055e-05 | 0.0005697 | N/A | 0.0016248 | 0.63588 | N/A | N/A | 1.1452 | 0.50003 | N/A | 1.1452
SPINKS | Circuit | Distribution | 1.7171 |  | HFTD 2 | 0.0083614 | 0.0083517 | 9.6181e-06 | 0.02392 | 0.01506 | 0.0056185 | 0.0032414 | N/A | 0.0053697 | 0.34915 | N/A | N/A | 1.0924 | 0.0017912 | N/A | 1.0924
SPLENDOR | Circuit | Distribution | 1.2279 |  | HFTD 3 | 0.0015981 | 0.0010488 | 0.0005493 | 0.019924 | 0.0088226 | 0.00044472 | 0.010657 | N/A | 0.02425 | 0.052638 | N/A | N/A | 1.0355 | 0.022652 | N/A | 1.0355
SPRAGUE | Circuit | Distribution | 29.981 |  | HFTD 3 | 0.0023061 | 0.0023038 | 2.3479e-06 | 0.00582 | 0.0047677 | 7.7173e-05 | 0.00097513 | N/A | 0.0066418 | 0.39584 | N/A | N/A | 1.2064 | 0.0003535 | N/A | 1.2064
SPUR | Circuit | Distribution | 0.25905 |  | HFTD 2 | 0.03353 | 0.031719 | 0.001811 | 0.015015 | 0.012945 | 2.3965e-05 | 0.0020464 | N/A | 0.0044182 | 2.1125 | N/A | N/A | 1.1559 | 0.40989 | N/A | 1.1559
SQUINT | Circuit | Distribution | 13.7656 |  | HFTD 3 | 0.011023 | 0.011008 | 1.4405e-05 | 0.0050574 | 0.0032435 | 0.00047469 | 0.0013392 | N/A | 0.037543 | 2.1767 | N/A | N/A | 1.4358 | 0.00038368 | N/A | 1.4358
STACK | Circuit | Distribution | 0.78408 |  | HFTD 2 | 0.004659 | 0.0040363 | 0.00062278 | 0.031595 | 0.023689 | 0.00061227 | 0.0072928 | N/A | 0.0021257 | 0.12775 | N/A | N/A | 1.0181 | 0.29297 | N/A | 1.0181
STAGELINE | Circuit | Distribution | 13.5905 |  | HFTD 3 | 0.0069943 | 0.0069911 | 3.1941e-06 | 0.0060269 | 0.0038986 | 0.00014004 | 0.0019882 | N/A | 0.0042748 | 1.16 | N/A | N/A | 1.1898 | 0.00074719 | N/A | 1.1898
STAGHORN | Circuit | Distribution | 2.0164 |  | HFTD 2 | 0.0052775 | 0.0051268 | 0.00015072 | 0.0084826 | 0.0038875 | 3.4508e-05 | 0.0045606 | N/A | 0.0019448 | 0.60439 | N/A | N/A | 1.1159 | 0.077501 | N/A | 1.1159
STANWOOD | Circuit | Distribution | 36.2611 |  | HFTD 3 | 0.036052 | 0.036044 | 7.4972e-06 | 0.0074009 | 0.0059231 | 0.00062194 | 0.00085593 | N/A | 0.048991 | 4.8702 | N/A | N/A | 1.1216 | 0.00015303 | N/A | 1.1216
STAR ROCK | Circuit | Distribution | 2.739 |  | HFTD 3 | 0.019851 | 0.019817 | 3.3811e-05 | 0.010783 | 0.0051862 | 0.00022427 | 0.0053722 | N/A | 0.016729 | 1.8378 | N/A | N/A | 1.0993 | 0.0020211 | N/A | 1.0993
STARGLOW | Circuit | Distribution | 40.7227 |  | HFTD 2 | 0.021763 | 0.021761 | 2.4182e-06 | 0.0025232 | 0.0014813 | 5.4566e-05 | 0.00098741 | N/A | 0.0074904 | 8.6242 | N/A | N/A | 1.2217 | 0.00032284 | N/A | 1.2217
STATLER | Circuit | Distribution | 28.3694 |  | HFTD 2 | 0.011717 | 0.011716 | 9.6616e-07 | 0.0094617 | 0.0048666 | 0.0019304 | 0.0026647 | N/A | 0.0012631 | 1.2382 | N/A | N/A | 1.3292 | 0.00076492 | N/A | 1.3292
STEARNS | Circuit | Distribution | 8.1402 |  | HFTD 3 | 0.00045735 | 0.00029591 | 0.00016144 | 0.0072041 | 0.0047643 | 0.00017235 | 0.0022675 | N/A | 0.037422 | 0.041075 | N/A | N/A | 1.098 | 0.0043141 | N/A | 1.098
STEEL | Circuit | Distribution | 13.7262 |  | HFTD 2 | 0.0011472 | 0.0011469 | 3.2763e-07 | 0.0026297 | 0.00099367 | 0.00011273 | 0.0015234 | N/A | 0.015703 | 0.43611 | N/A | N/A | 1.2774 | 2.0864e-05 | N/A | 1.2774
STEVENSON | Circuit | Distribution | 26.1263 |  | HFTD 2 | 0.0003491 | 0.00034898 | 1.1718e-07 | 0.0026099 | 0.0010396 | 0.00093472 | 0.00063558 | N/A | 0.014918 | 0.13371 | N/A | N/A | 1.4641 | 7.8549e-06 | N/A | 1.4641
STOCKER | Circuit | Distribution | 1.3021 |  | HFTD 2 | 0.00024115 | 0.00024115 | 0 | 0.0065241 | 0.0024294 | 0.00077049 | 0.0033242 | N/A | 0 | 0.036962 | N/A | N/A | 1.1277 |  | N/A | 1.1277
STONEMAN | Circuit | Distribution | 31.0012 |  | HFTD 3 | 0.026621 | 0.02662 | 9.7332e-07 | 0.0089579 | 0.0041552 | 0.0011119 | 0.0036908 | N/A | 0.0037221 | 2.9717 | N/A | N/A | 1.2094 | 0.0002615 | N/A | 1.2094
STONEWOOD | Circuit | Distribution | 6.3591 |  | HFTD 3 | 0.028182 | 0.028172 | 9.7678e-06 | 0.012908 | 0.0077518 | 0.0017679 | 0.0033882 | N/A | 0.0079394 | 2.1825 | N/A | N/A | 1.0848 | 0.0012303 | N/A | 1.0848
STORES | Circuit | Distribution | 27.3126 | Top 5% Highest Risk | HFTD 3 | 0.094002 | 0.094 | 1.7538e-06 | 0.0064906 | 0.0035884 | 0.00011719 | 0.0027851 | N/A | 0.048433 | 14.4825 | N/A | N/A | 1.0687 | 3.6212e-05 | N/A | 1.0687
STRATHERN | Circuit | Distribution | 10.8965 |  | HFTD 3 | 0.006797 | 0.0067286 | 6.8438e-05 | 0.0086968 | 0.0050209 | 0.00021928 | 0.0034566 | N/A | 0.026337 | 0.77369 | N/A | N/A | 1.1173 | 0.0025985 | N/A | 1.1173
STROH | Circuit | Distribution | 1.0728 |  | HFTD 2 | 0.003489 | 0.0034803 | 8.6775e-06 | 0.0070687 | 0.0039657 | 0.00037054 | 0.0027325 | N/A | 0.0014119 | 0.49236 | N/A | N/A | 1.0318 | 0.006146 | N/A | 1.0318
STROSNIDER | Circuit | Distribution | 15.7499 |  | HFTD 2 | 0.0074092 | 0.0073963 | 1.2876e-05 | 0.0079203 | 0.0018913 | 0.00023565 | 0.0057933 | N/A | 0.066656 | 0.93384 | N/A | N/A | 1.1393 | 0.00019318 | N/A | 1.1393
STUBBY | Circuit | Distribution | 16.4206 |  | HFTD 3 | 0.023504 | 0.023504 | 1.1809e-07 | 0.0028725 | 0.0015847 | 7.8884e-05 | 0.0012089 | N/A | 0.029067 | 8.1825 | N/A | N/A | 1.375 | 4.0626e-06 | N/A | 1.375
STUTZ | Circuit | Distribution | 9.5825 |  | HFTD 2 | 0.0022014 | 0.0022014 | 0 | 0.0090525 | 0.0035693 | 0.00014625 | 0.005337 | N/A | 0 | 0.24318 | N/A | N/A | 1.0608 |  | N/A | 1.0608
SUBIDA | Circuit | Distribution | 1.3584 |  | HFTD 2 | 0.025324 | 0.025034 | 0.00028955 | 0.0093256 | 0.0064896 | 0.00014325 | 0.0026927 | N/A | 0.0041892 | 2.6844 | N/A | N/A | 1.1055 | 0.069118 | N/A | 1.1055
SUCCESS | Circuit | Distribution | 40.031 |  | HFTD 2 | 0.0036435 | 0.0036418 | 1.6693e-06 | 0.0035999 | 0.0012816 | 0.00036384 | 0.0019544 | N/A | 0.00082074 | 1.0116 | N/A | N/A | 1.184 | 0.0020338 | N/A | 1.184
SUGARLOAF | Circuit | Distribution | 6.2455 |  | HFTD 2 | 0.0017876 | 0.0017868 | 8.4196e-07 | 0.010801 | 0.0065662 | 0.0019029 | 0.0023322 | N/A | 0.014633 | 0.16542 | N/A | N/A | 1.505 | 5.7538e-05 | N/A | 1.505
SUNDANCE | Circuit | Distribution | 6.9337 |  | HFTD 2 | 0.002012 | 0.0020111 | 8.0308e-07 | 0.0017666 | 0.0013112 | 3.8883e-05 | 0.0004165 | N/A | 0.0033645 | 1.1384 | N/A | N/A | 1.0941 | 0.00023869 | N/A | 1.0941
SURREY | Circuit | Distribution | 3.2334 |  | HFTD 2 | 0.021981 | 0.021981 | 0 | 0.0078656 | 0.0038754 | 0.0023034 | 0.0016868 | N/A | 0 | 2.7946 | N/A | N/A | 1.0034 |  | N/A | 1.0034
SUSAN | Circuit | Distribution | 1.6765 |  | HFTD 2 | 0.0032244 | 0.0027622 | 0.00046217 | 0.016685 | 0.0072078 | 0.00011992 | 0.0093573 | N/A | 0.0087686 | 0.16555 | N/A | N/A | 1.3267 | 0.052708 | N/A | 1.3267
SUTT | Circuit | Distribution | 19.7204 |  | HFTD 3 | 0.024464 | 0.024319 | 0.0001452 | 0.0075025 | 0.0032723 | 0.00027207 | 0.0039581 | N/A | 0.050496 | 3.2414 | N/A | N/A | 1.1413 | 0.0028754 | N/A | 1.1413
SWEETWATER | Circuit | Distribution | 2.5624 |  | HFTD 2 | 0.0078014 | 0.0070061 | 0.00079528 | 0.017413 | 0.0092857 | 0.000946 | 0.0071817 | N/A | 0.026403 | 0.40234 | N/A | N/A | 1.0495 | 0.030121 | N/A | 1.0495
SWIFT | Circuit | Distribution | 3.408 |  | HFTD 3 | 0.038661 | 0.038653 | 7.7494e-06 | 0.012294 | 0.0056842 | 0.0023841 | 0.004226 | N/A | 0.029407 | 3.144 | N/A | N/A | 1.0457 | 0.00026352 | N/A | 1.0457
TACKLE | Circuit | Distribution | 0.86283 |  | HFTD 3 | 0.0084482 | 0.0084458 | 2.4025e-06 | 0.0036601 | 0.0026108 | 0.00018887 | 0.00086038 | N/A | 0 | 2.3076 | N/A | N/A | 1.0739 | inf | N/A | 1.0739
TAGGERT | Circuit | Distribution | 13.3255 |  | HFTD 3 | 0.0070906 | 0.0070765 | 1.4088e-05 | 0.0071442 | 0.0045049 | 0.00039696 | 0.0022424 | N/A | 0.039157 | 0.99052 | N/A | N/A | 1.278 | 0.00035978 | N/A | 1.278
TAHQUITZ | Circuit | Distribution | 12.9786 |  | HFTD 3 | 0.0054784 | 0.0054775 | 8.6749e-07 | 0.0035465 | 0.0016718 | 0.00012159 | 0.0017531 | N/A | 0.022156 | 1.5445 | N/A | N/A | 1.1422 | 3.9154e-05 | N/A | 1.1422
TAIWAN | Circuit | Distribution | 17.0903 |  | HFTD 3 | 0.01813 | 0.018117 | 1.3347e-05 | 0.0030727 | 0.00137 | 8.0345e-05 | 0.0016223 | N/A | 0.040961 | 5.8961 | N/A | N/A | 1.3453 | 0.00032585 | N/A | 1.3453
TALLEY | Circuit | Distribution | 4.2872 |  | HFTD 3 | 0.00095843 | 0.00086662 | 9.181e-05 | 0.011937 | 0.0056138 | 0.00034088 | 0.0059824 | N/A | 0.016748 | 0.072599 | N/A | N/A | 1.1121 | 0.0054818 | N/A | 1.1121
TAMBOURINE | Circuit | Distribution | 0.82248 |  | HFTD 3 | 0.0052449 | 0.0048264 | 0.00041847 | 0.021636 | 0.011032 | 0.00076827 | 0.0098361 | N/A | 0.024009 | 0.22307 | N/A | N/A | 1.1133 | 0.01743 | N/A | 1.1133
TANAGER | Circuit | Distribution | 68.917 |  | HFTD 3 | 0.015388 | 0.015387 | 3.4436e-07 | 0.0033142 | 0.0021303 | 3.9022e-05 | 0.0011449 | N/A | 0.024188 | 4.6428 | N/A | N/A | 1.2721 | 1.4237e-05 | N/A | 1.2721
TANDEM | Circuit | Distribution | 13.5576 |  | HFTD 2 | 0.0037189 | 0.0037189 | 0 | 0.0068345 | 0.0040877 | 0.00040656 | 0.0023402 | N/A | 0 | 0.54414 | N/A | N/A | 1.1671 |  | N/A | 1.1671
TAPO | Circuit | Distribution | 17.9613 |  | HFTD 3 | 0.022211 | 0.022175 | 3.6368e-05 | 0.0069625 | 0.0038748 | 0.0002168 | 0.0028709 | N/A | 0.036823 | 3.1848 | N/A | N/A | 1.1025 | 0.00098765 | N/A | 1.1025
TATANKA | Circuit | Distribution | 4.4644 | Top 5% Highest Risk | HFTD 3 | 0.073215 | 0.073208 | 7.0775e-06 | 0.019832 | 0.0050515 | 0.0053289 | 0.0094513 | N/A | 0.013927 | 3.6914 | N/A | N/A | 1.0559 | 0.00050818 | N/A | 1.0559
TAVA | Circuit | Distribution | 2.4702 |  | HFTD 2 | 0.011799 | 0.011744 | 5.4992e-05 | 0.0022224 | 0.0015338 | 1.9306e-05 | 0.00066932 | N/A | 0.0013414 | 5.2842 | N/A | N/A | 1.2603 | 0.040994 | N/A | 1.2603
TECOLOTE | Circuit | Distribution | 12.6945 |  | HFTD 3 | 0.0050832 | 0.0050832 | 0 | 0.0048141 | 0.0031282 | 0.00057682 | 0.0011091 | N/A | 0.0023644 | 1.0559 | N/A | N/A | 1.093 | 0 | N/A | 1.093
TEE VEE | Circuit | Distribution | 6.4003 |  | HFTD 3 | 0.0039371 | 0.0039371 | 1.1726e-08 | 0.0037111 | 0.0020978 | 3.4435e-05 | 0.0015789 | N/A | 0.0051078 | 1.0609 | N/A | N/A | 1.8333 | 2.2956e-06 | N/A | 1.8333
TEJON | Circuit | Distribution | 57.6011 |  | HFTD 2 | 0.0095479 | 0.0095479 | 0 | 0.0035472 | 0.0022881 | 4.5334e-05 | 0.0012137 | N/A | 0.057442 | 2.6917 | N/A | N/A | 1.2932 | 0 | N/A | 1.2932
TEMPEST | Circuit | Distribution | 1.557 |  | HFTD 2 | 0.0028427 | 0.0028424 | 2.9027e-07 | 0.0023706 | 0.002064 | 4.28e-05 | 0.00026376 | N/A | 0.0052047 | 1.199 | N/A | N/A |  | 5.5771e-05 | N/A
TENDER | Circuit | Distribution | 3.3987 |  | HFTD 2 | 0.0041587 | 0.0039429 | 0.00021576 | 0.0025849 | 0.0012663 | 8.9262e-05 | 0.0012293 | N/A | 0.0030035 | 1.5254 | N/A | N/A | 1.2076 | 0.071836 | N/A | 1.2076
TENNECO | Circuit | Distribution | 109.3003 |  | HFTD 3 | 0.0077558 | 0.0077548 | 9.8167e-07 | 0.0056229 | 0.0043152 | 0.00028899 | 0.0010186 | N/A | 0.050361 | 1.3792 | N/A | N/A | 1.2068 | 1.9493e-05 | N/A | 1.2068
TERMINUS | Circuit | Distribution | 13.8306 |  | HFTD 2 | 0.00031124 | 0.00031118 | 6.2164e-08 | 0.0027619 | 0.0018037 | 0.00014149 | 0.00081671 | N/A | 0.00055878 | 0.11267 | N/A | N/A | 1.0997 | 0.00011125 | N/A | 1.0997
TERRA COTTA | Circuit | Distribution | 12.6808 |  | HFTD 2 | 0.0051805 | 0.0051805 | 1.8021e-08 | 0.0024851 | 0.0014326 | 8.1169e-05 | 0.00097135 | N/A | 0.0066828 | 2.0846 | N/A | N/A | 1.1667 | 2.6966e-06 | N/A | 1.1667
TERRAZZO | Circuit | Distribution | 0.36783 |  | HFTD 2 | 0.00010862 | 0.00010862 | 0 | 0.0095313 | 0.0027106 | 0.0036502 | 0.0031705 | N/A | 0 | 0.011397 | N/A | N/A | 1.0602 |  | N/A | 1.0602
TEST | Circuit | Distribution | 5.5229 |  | HFTD 2 | 0.0022262 | 0.0022226 | 3.6108e-06 | 0.010076 | 0.002893 | 0.0013111 | 0.0058714 | N/A | 0.000455 | 0.22059 | N/A | N/A | 1.1103 | 0.0079357 | N/A | 1.1103
TETLEY | Circuit | Distribution | 20.936 |  | HFTD 3 | 0.031622 | 0.03152 | 0.00010182 | 0.008318 | 0.0050463 | 0.0012427 | 0.002029 | N/A | 0.11696 | 3.7894 | N/A | N/A | 1.3371 | 0.00087059 | N/A | 1.3371
TEXFI | Circuit | Distribution | 2.1303 |  | HFTD 2 | 0.038974 | 0.038557 | 0.00041773 | 0.0069737 | 0.003753 | 0.0001238 | 0.0030969 | N/A | 0.0021332 | 5.5289 | N/A | N/A | 1.125 | 0.19582 | N/A | 1.125
THACHER | Circuit | Distribution | 81.983 |  | HFTD 3 | 0.0081676 | 0.0081672 | 3.5793e-07 | 0.0096529 | 0.0062718 | 0.00032076 | 0.0030604 | N/A | 0.013885 | 0.84609 | N/A | N/A | 1.1431 | 2.5778e-05 | N/A | 1.1431
THOMPSEN | Circuit | Distribution | 1.3115 |  | HFTD 2 | 0.00032009 | 0.0002986 | 2.1488e-05 | 0.0020689 | 0.0012127 | 0.00016094 | 0.0006953 | N/A | 0.0060128 | 0.14433 | N/A | N/A | 1.0445 | 0.0035737 | N/A | 1.0445
THORNTON | Circuit | Distribution | 0.46167 |  | HFTD 2 | 0.0086531 | 0.008416 | 0.00023709 | 0.012568 | 0.0090003 | 0.0010003 | 0.0025676 | N/A | 5.4192e-05 | 0.66963 | N/A | N/A | 1.227 | 4.375 | N/A | 1.227
THRUSH | Circuit | Distribution | 5.7059 |  | HFTD 3 | 0.0062065 | 0.0062037 | 2.8068e-06 | 0.0072677 | 0.0048455 | 0.00026157 | 0.0021606 | N/A | 0.0076987 | 0.8536 | N/A | N/A | 1.5668 | 0.00036458 | N/A | 1.5668
TICO | Circuit | Distribution | 44.2915 |  | HFTD 3 | 0.012131 | 0.012128 | 3.1763e-06 | 0.0092524 | 0.0052334 | 0.0011365 | 0.0028825 | N/A | 0.010526 | 1.3108 | N/A | N/A | 1.2523 | 0.00030175 | N/A | 1.2523
TIMBER CANYON | Circuit | Distribution | 28.1643 |  | HFTD 3 | 0.0020277 | 0.0020263 | 1.4506e-06 | 0.0041228 | 0.0025139 | 0.00012665 | 0.0014822 | N/A | 0.008591 | 0.49148 | N/A | N/A | 1.1145 | 0.00016885 | N/A | 1.1145
TIN MINE | Circuit | Distribution | 24.8858 |  | HFTD 2 | 0.0098719 | 0.0098679 | 4.0078e-06 | 0.0035841 | 0.0021712 | 5.9261e-05 | 0.0013536 | N/A | 0.0044005 | 2.7533 | N/A | N/A | 1.2968 | 0.00091077 | N/A | 1.2968
TIOGA | Circuit | Distribution | 4.1088 |  |  | 0.013977 | 0.013977 | 0 | 0.027058 | 0.022397 | 0.0010109 | 0.0036502 | N/A |  | 0.51653 | N/A | N/A | 1 |  | N/A | 1
TIPS | Circuit | Distribution | 0.45259 |  | HFTD 3 | 0.0038708 | 0.0037514 | 0.00011938 | 0.0069965 | 0.0040949 | 0.00035814 | 0.0025435 | N/A | 0.0011103 | 0.53619 | N/A | N/A | 1.0487 | 0.10752 | N/A | 1.0487
TITAN | Circuit | Distribution | 72.7425 |  | HFTD 3 | 0.016093 | 0.016079 | 1.4115e-05 | 0.0070126 | 0.0044692 | 2.9991e-05 | 0.0025134 | N/A | 0.052939 | 2.2929 | N/A | N/A | 1.1919 | 0.00026663 | N/A | 1.1919
TOGA | Circuit | Distribution | 3.8547 |  | HFTD 3 | 0.00067012 | 0.00063637 | 3.3756e-05 | 0.01721 | 0.01065 | 0.00025008 | 0.0063103 | N/A | 0.01046 | 0.036976 | N/A | N/A | 1.1717 | 0.003227 | N/A | 1.1717
TOLA | Circuit | Distribution | 5.0235 |  | HFTD 2 | 0.0092797 | 0.0092659 | 1.3842e-05 | 0.0062111 | 0.0048117 | 0.00015468 | 0.0012447 | N/A | 0.00069094 | 1.4918 | N/A | N/A | 1.1598 | 0.020034 | N/A | 1.1598
TOLL | Circuit | Distribution | 10.0506 |  | HFTD 2 | 0.016478 | 0.016478 | 0 | 0.0061769 | 0.0029063 | 0.00030295 | 0.0029676 | N/A | 0.19761 | 2.6677 | N/A | N/A | 1.5277 | 0 | N/A | 1.5277
TOLLHOUSE | Circuit | Distribution | 2.0058 |  | HFTD 3 | 0.002775 | 0.0027749 | 9.0209e-08 | 0.0084418 | 0.0068229 | 0.00057265 | 0.0010463 | N/A | 0.0046466 | 0.32871 | N/A | N/A | 1.3101 | 1.9414e-05 | N/A | 1.3101
TOMAHAWK | Circuit | Distribution | 6.7939 |  | HFTD 2 | 0.015129 | 0.015102 | 2.6295e-05 | 0.006083 | 0.0032378 | 0.00010866 | 0.0027366 | N/A | 0.0047739 | 2.4827 | N/A | N/A | 1.1441 | 0.0055081 | N/A | 1.1441
TONNER | Circuit | Distribution | 3.6978 |  | HFTD 3 | 0.0088349 | 0.0088349 | 0 | 0.0083387 | 0.0038675 | 0.00013065 | 0.0043406 | N/A | 0 | 1.0595 | N/A | N/A | 1.0972 |  | N/A | 1.0972
TONTO | Circuit | Distribution | 0.99526 |  | HFTD 2 | 0.044096 | 0.043044 | 0.0010524 | 0.0089172 | 0.0037575 | 4.8637e-05 | 0.0051111 | N/A | 0.00069654 | 4.827 | N/A | N/A | 1.1541 | 1.5109 | N/A | 1.1541
TORONTO | Circuit | Distribution | 18.2408 |  | HFTD 3 | 0.020947 | 0.020928 | 1.9528e-05 | 0.0098735 | 0.0069758 | 0.00062865 | 0.002269 | N/A | 0.053361 | 2.1196 | N/A | N/A | 1.2173 | 0.00036596 | N/A | 1.2173
TOWNSHIP | Circuit | Distribution | 19.6064 |  | HFTD 3 | 0.00019314 | 0.00015383 | 3.9306e-05 | 0.011512 | 0.0072656 | 0.00013921 | 0.0041072 | N/A | 0.016854 | 0.013363 | N/A | N/A | 1.1411 | 0.0023322 | N/A | 1.1411
TRAM | Circuit | Distribution | 3.8137 |  | HFTD 2 | 0.00091586 | 0.00090026 | 1.5598e-05 | 0.0018181 | 0.00052111 | 0.00010463 | 0.0011923 | N/A | 0.075871 | 0.49517 | N/A | N/A | 1.3158 | 0.00020558 | N/A | 1.3158
TRAUTWEIN | Circuit | Distribution | 8.2133 |  | HFTD 2 | 0.010628 | 0.010615 | 1.3328e-05 | 0.003966 | 0.0033093 | 2.5968e-05 | 0.00063077 | N/A | 0.0054149 | 2.6764 | N/A | N/A | 1.0962 | 0.0024614 | N/A | 1.0962
TREMAINE | Circuit | Distribution | 6.3654 | Top 5% Highest Risk | HFTD 3 | 0.091085 | 0.091078 | 6.8711e-06 | 0.019882 | 0.011063 | 0.0050993 | 0.0037202 | N/A | 0.031245 | 4.5808 | N/A | N/A | 1.0223 | 0.00021991 | N/A | 1.0223
TRESTLE | Circuit | Distribution | 2.8221 |  | HFTD 2 | 0.0004535 | 0.00044923 | 4.2715e-06 | 0.0051258 | 0.0020255 | 0.00015371 | 0.0029466 | N/A | 0.00056804 | 0.087641 | N/A | N/A | 1.1877 | 0.0075197 | N/A | 1.1877
TREVINO | Circuit | Distribution | 0.74092 |  | HFTD 2 | 0.00010404 | 0.00010404 | 0 | 0.015652 | 0.00872 | 0.00039602 | 0.006536 | N/A | 0.0087047 | 0.0066473 | N/A | N/A |  | 0 | N/A
TRIUNFO | Circuit | Distribution | 4.135 | Top 5% Highest Risk | HFTD 3 | 0.065514 | 0.06551 | 3.8333e-06 | 0.012634 | 0.0035542 | 0.00041198 | 0.0086681 | N/A | 0.0061878 | 5.1851 | N/A | N/A | 1.0234 | 0.0006195 | N/A | 1.0234
TROUT | Circuit | Distribution | 4.3316 |  | HFTD 2 | 0.014509 | 0.014509 | 0 | 0.01236 | 0.0052494 | 0.00073042 | 0.00638 | N/A | 0.024104 | 1.1739 | N/A | N/A |  | 0 | N/A
TRUMBLE | Circuit | Distribution | 4.8837 |  | HFTD 2 | 0.010859 | 0.010856 | 2.8018e-06 | 0.0029479 | 0.0017166 | 8.3094e-05 | 0.0011481 | N/A | 0.0012204 | 3.6826 | N/A | N/A | 1.0881 | 0.0022959 | N/A | 1.0881
TRUMP | Circuit | Distribution | 19.861 |  | HFTD 3 | 0.004071 | 0.0040706 | 4.9113e-07 | 0.0053141 | 0.0033984 | 0.00039806 | 0.0015177 | N/A | 0 | 0.76599 | N/A | N/A | 1.0974 | inf | N/A | 1.0974
TRUMPET | Circuit | Distribution | 34.5063 |  | HFTD 3 | 0.01885 | 0.018834 | 1.5568e-05 | 0.005829 | 0.0034659 | 0.00034503 | 0.0020181 | N/A | 0.03684 | 3.2311 | N/A | N/A | 1.2056 | 0.00042259 | N/A | 1.2056
TUBA | Circuit | Distribution | 7.6991 |  | HFTD 3 | 0.0095832 | 0.0095265 | 5.6738e-05 | 0.0069526 | 0.0042381 | 0.00044635 | 0.0022681 | N/A | 0.015859 | 1.3702 | N/A | N/A | 1.2079 | 0.0035775 | N/A | 1.2079
TUDOR | Circuit | Distribution | 14.2215 |  | HFTD 2 | 0.03092 | 0.030919 | 9.1423e-07 | 0.0079438 | 0.0073286 | 6.7814e-05 | 0.00054736 | N/A | 0.0031404 | 3.8922 | N/A | N/A | 1.2535 | 0.00029112 | N/A | 1.2535
TUFA | Circuit | Distribution | 25.0452 |  | HFTD 2 | 0.00096036 | 0.00092329 | 3.7069e-05 | 0.00087527 | 0.00063976 | 3.4532e-05 | 0.00020099 | N/A | 0.24158 | 1.0549 | N/A | N/A | 1.4486 | 0.00015345 | N/A | 1.4486
TULLY | Circuit | Distribution | 5.756 |  | HFTD 2 | 0.0088689 | 0.0088643 | 4.5006e-06 | 0.0084772 | 0.0044771 | 0.00091226 | 0.0030878 | N/A | 0.0032105 | 1.0457 | N/A | N/A | 1.3146 | 0.0014018 | N/A | 1.3146
TUNA | Circuit | Distribution | 2.5054 |  |  | 0.017562 | 0.017562 | 0 | 0.043655 | 0.037577 | 0.00070962 | 0.005369 | N/A |  | 0.40228 | N/A | N/A | 1.0605 |  | N/A | 1.0605
TUNGSTEN | Circuit | Distribution | 0.81604 | Top 5% Highest Risk | HFTD 3 | 0.076255 | 0.076255 | 0 | 0.011691 | 0.003619 | 5.8837e-05 | 0.0080132 | N/A | 0.024078 | 6.5225 | N/A | N/A |  | 0 | N/A
TUNNEL | Circuit | Distribution | 0.59239 |  | HFTD 3 | 0.02523 | 0.024471 | 0.00075912 | 0.0050568 | 0.0026225 | 7.5006e-05 | 0.0023593 | N/A | 0.000443 | 4.8391 | N/A | N/A | 1.1088 | 1.7136 | N/A | 1.1088
TURNPIKE | Circuit | Distribution | 2.1082 |  | HFTD 2 | 0.0052833 | 0.0051089 | 0.00017437 | 0.010319 | 0.0069583 | 0.0017668 | 0.0015941 | N/A | 0.0010788 | 0.49509 | N/A | N/A | 1.0666 | 0.16164 | N/A | 1.0666
TWIN LAKES | Circuit | Distribution | 4.4766 |  | HFTD 3 | 0.0077147 | 0.0074757 | 0.00023899 | 0.027928 | 0.01051 | 0.00021221 | 0.017206 | N/A | 0.041186 | 0.26767 | N/A | N/A | 1.0931 | 0.0058027 | N/A | 1.0931
TWIN PEAKS | Circuit | Distribution | 3.8187 | Top 5% Highest Risk | HFTD 3 | 0.064496 | 0.064494 | 2.3234e-06 | 0.024177 | 0.01153 | 0.0026702 | 0.0099769 | N/A | 0.15219 | 2.6676 | N/A | N/A | 2 | 1.5266e-05 | N/A | 2
TWISTER | Circuit | Distribution | 1.1775 |  | HFTD 2 | 0.0052969 | 0.0052969 | 0 | 0.011481 | 0.0023884 | 0.00053151 | 0.0085615 | N/A | 0 | 0.46134 | N/A | N/A | 1.0534 |  | N/A | 1.0534
UNDERWOOD | Circuit | Distribution | 20.0189 |  | HFTD 2 | 0.0077288 | 0.0075811 | 0.00014769 | 0.0025151 | 0.0014779 | 0.00021257 | 0.00082469 | N/A | 0.093535 | 3.0142 | N/A | N/A | 1.2127 | 0.001579 | N/A | 1.2127
UNIVERSITY | Circuit | Distribution | 0.48519 |  | HFTD 2 | 0.014434 | 0.014434 | 3.3779e-07 | 0.0053811 | 0.0016344 | 0.001304 | 0.0024427 | N/A | 0.0093635 | 2.6824 | N/A | N/A | 1.0018 | 3.6076e-05 | N/A | 1.0018
URBITA | Circuit | Distribution | 9.458 |  | HFTD 2 | 0.015217 | 0.015174 | 4.3402e-05 | 0.010613 | 0.0027535 | 0.00018073 | 0.0076792 | N/A | 0.014347 | 1.4297 | N/A | N/A | 1.233 | 0.0030252 | N/A | 1.233
UTE | Circuit | Distribution | 1.1539 | Top 5% Highest Risk | HFTD 2 | 0.086546 | 0.086546 | 0 | 0.010392 | 0.0020974 | 0.00037473 | 0.0079196 | N/A | 0.0077105 | 8.3284 | N/A | N/A |  | 0 | N/A
VAL VERDE | Circuit | Distribution | 3.288 |  | HFTD 3 | 0.0032282 | 0.0032245 | 3.7049e-06 | 0.033819 | 0.0075663 | 0.00012347 | 0.02613 | N/A | 0.012969 | 0.095345 | N/A | N/A | 1.0448 | 0.00028568 | N/A | 1.0448
VALLECITO | Circuit | Distribution | 16.3897 |  | HFTD 2 | 0.01119 | 0.011174 | 1.6288e-05 | 0.011551 | 0.0062298 | 0.0011534 | 0.0041675 | N/A | 0.002685 | 0.96736 | N/A | N/A | 1.0911 | 0.0060663 | N/A | 1.0911
VALLEY OF THE MOON | Circuit | Distribution | 8.0516 |  | HFTD 3 | 0.013708 | 0.013687 | 2.1487e-05 | 0.0075165 | 0.0053518 | 0.00074485 | 0.0014198 | N/A | 0.049445 | 1.8209 | N/A | N/A | 1.1509 | 0.00043456 | N/A | 1.1509
VALMONTE | Circuit | Distribution | 3.2369 |  | HFTD 2 | 0.0045303 | 0.0045303 | 0 | 0.019789 | 0.015522 | 0.0022324 | 0.0020346 | N/A | 0 | 0.22893 | N/A | N/A | 1.2924 |  | N/A | 1.2924
VANDERLIP | Circuit | Distribution | 1.8341 |  | HFTD 2 | 0.019262 | 0.019261 | 2.9787e-07 | 0.0093278 | 0.005322 | 0.0016751 | 0.0023308 | N/A | 0.0013376 | 2.0649 | N/A | N/A | 1.8441 | 0.00022268 | N/A | 1.8441
VARGAS | Circuit | Distribution | 1.3166 |  | HFTD 2 | 0.0044051 | 0.0026249 | 0.0017802 | 0.0063789 | 0.0033956 | 0.00032933 | 0.0026539 | N/A | 0.011689 | 0.4115 | N/A | N/A | 1.114 | 0.1523 | N/A | 1.114
VASQUEZ | Circuit | Distribution | 0.75079 |  | HFTD 3 | 0.0010205 | 0.00019716 | 0.00082329 | 0.0063899 | 0.004181 | 8.6843e-05 | 0.0021221 | N/A | 0.010315 | 0.030855 | N/A | N/A | 1.097 | 0.079813 | N/A | 1.097
VENGEANCE | Circuit | Distribution | 1.769 |  | HFTD 2 | 0.023703 | 0.023671 | 3.2712e-05 | 0.0049684 | 0.0023212 | 0.00028377 | 0.0023634 | N/A | 0.0044767 | 4.7643 | N/A | N/A | 1.0887 | 0.0073072 | N/A | 1.0887
VENUS | Circuit | Distribution | 8.7706 |  | HFTD 2 | 0.0022954 | 0.0022954 | 0 | 0.016334 | 0.010781 | 0.0033849 | 0.0021683 | N/A | 0.0011382 | 0.14053 | N/A | N/A | 1.4674 | 0 | N/A | 1.4674
VENWIND 4 | Circuit | Distribution | 1.7659 |  | HFTD 2 | 0.0040216 | 0.0040216 | 0 | 0.002537 | 0.0013507 | 5.1476e-05 | 0.0011349 | N/A | 0.081596 | 1.5852 | N/A | N/A |  | 0 | N/A
VERA CRUZ | Circuit | Distribution | 9.7674 |  | HFTD 3 | 0.021291 | 0.021289 | 2.1755e-06 | 0.0059224 | 0.0031936 | 0.00012784 | 0.0026009 | N/A | 0.0099995 | 3.5946 | N/A | N/A | 1.1334 | 0.00021756 | N/A | 1.1334
VERDEMONT | Circuit | Distribution | 12.9768 |  | HFTD 2 | 0.020013 | 0.02001 | 2.2142e-06 | 0.0089612 | 0.0041758 | 0.00030167 | 0.0044838 | N/A | 0.010823 | 2.233 | N/A | N/A | 1.5263 | 0.00020458 | N/A | 1.5263
VERDUGO | Circuit | Distribution | 25.5304 |  | HFTD 3 | 0.013371 | 0.01333 | 4.0874e-05 | 0.0032807 | 0.0020149 | 0.00019373 | 0.001072 | N/A | 0.037303 | 4.0632 | N/A | N/A | 1.1072 | 0.0010957 | N/A | 1.1072
VERDUN | Circuit | Distribution | 0.53996 |  | HFTD 2 | 0.002277 | 0.002277 | 0 | 0.020411 | 0.0074985 | 0.0017909 | 0.011122 | N/A | 0 | 0.11156 | N/A | N/A | 1.287 |  | N/A | 1.287
VETERANS | Circuit | Distribution | 4.9675 |  | HFTD 3 | 0.010299 | 0.010118 | 0.00018151 | 0.0051246 | 0.0027089 | 0.00015416 | 0.0022615 | N/A | 0.0074341 | 1.9743 | N/A | N/A | 1.0804 | 0.024416 | N/A | 1.0804
VIAVERDE | Circuit | Distribution | 2.006 |  | HFTD 2 | 0.0042984 | 0.0042828 | 1.5615e-05 | 0.0041342 | 0.002145 | 0.00028076 | 0.0017085 | N/A | 0.0020376 | 1.0359 | N/A | N/A | 1.099 | 0.0076635 | N/A | 1.099
VICASA | Circuit | Distribution | 45.6059 |  | HFTD 3 | 0.028124 | 0.028114 | 1.0327e-05 | 0.0095013 | 0.0058979 | 0.00088727 | 0.0027161 | N/A | 0.02017 | 2.9589 | N/A | N/A | 1.3144 | 0.000512 | N/A | 1.3144
VIDEO | Circuit | Distribution | 14.223 |  | HFTD 2 | 0.013233 | 0.013232 | 9.647e-07 | 0.0073903 | 0.0033744 | 0.0012478 | 0.0027682 | N/A | 0.011894 | 1.7905 | N/A | N/A | 1.6321 | 8.1109e-05 | N/A | 1.6321
VIENTO | Circuit | Distribution | 93.0519 |  | HFTD 3 | 0.017635 | 0.017626 | 8.9483e-06 | 0.0062814 | 0.0042137 | 0.0001312 | 0.0019366 | N/A | 0.056155 | 2.806 | N/A | N/A | 1.2054 | 0.00015935 | N/A | 1.2054
VIOLET | Circuit | Distribution | 5.3297 |  | HFTD 2 | 0.00046931 | 0.00046931 | 0 | 0.0092358 | 0.0048613 | 0.00078127 | 0.0035932 | N/A | 0 | 0.050815 | N/A | N/A | 1.2576 |  | N/A | 1.2576
VULCAN | Circuit | Distribution | 0.35782 |  | HFTD 2 | 0.0090567 | 0.0090558 | 8.2552e-07 | 0.031501 | 0.021462 | 0.0019919 | 0.0080469 | N/A | 0.028442 | 0.28748 | N/A | N/A | 1.6316 | 2.9025e-05 | N/A | 1.6316
WAHOO | Circuit | Distribution | 3.0623 |  | HFTD 2 | 0.00080416 | 0.00078652 | 1.7635e-05 | 0.0080801 | 0.0042585 | 0.00031271 | 0.003509 | N/A | 0.0015696 | 0.09734 | N/A | N/A | 1.0917 | 0.011235 | N/A | 1.0917
WAITE | Circuit | Distribution | 8.5793 |  | HFTD 2 | 0.025183 | 0.025179 | 4.1943e-06 | 0.0053141 | 0.0046209 | 6.0506e-05 | 0.00063263 | N/A | 0.0028544 | 4.7381 | N/A | N/A | 1.2554 | 0.0014694 | N/A | 1.2554
WAPELLO | Circuit | Distribution | 4.7453 |  | HFTD 3 | 0.035776 | 0.035772 | 4.1591e-06 | 0.010651 | 0.006627 | 0.00024961 | 0.0037739 | N/A | 0.0062438 | 3.3587 | N/A | N/A | 1.5171 | 0.00066612 | N/A | 1.5171
WARDELL | Circuit | Distribution | 0.8731 |  | HFTD 2 | 0.00039127 | 0.00032891 | 6.2363e-05 | 0.0053831 | 0.0032158 | 6.4144e-05 | 0.0021031 | N/A | 0.00032139 | 0.0611 | N/A | N/A | 1.081 | 0.19404 | N/A | 1.081
WARHAWK | Circuit | Distribution | 3.6813 |  | HFTD 2 | 0.025389 | 0.025336 | 5.3315e-05 | 0.0045587 | 0.0031268 | 8.5232e-05 | 0.0013467 | N/A | 0.007087 | 5.5577 | N/A | N/A | 1.1232 | 0.007523 | N/A | 1.1232
WEESHA | Circuit | Distribution | 3.3823 |  | HFTD 3 | 0.010799 | 0.010797 | 1.7146e-06 | 0.0089308 | 0.0053833 | 0.00057431 | 0.0029732 | N/A | 0.025271 | 1.209 | N/A | N/A | 1.0021 | 6.7849e-05 | N/A | 1.0021
WEIRICK | Circuit | Distribution | 0.73971 |  | HFTD 2 | 0.00054938 | 0.00037573 | 0.00017366 | 0.004202 | 0.0029801 | 0.0002137 | 0.0010082 | N/A | 0.00075174 | 0.089416 | N/A | N/A | 1.1243 | 0.23101 | N/A | 1.1243
WELCH | Circuit | Distribution | 15.6521 |  | HFTD 2 | 0.00070353 | 0.00070328 | 2.5021e-07 | 0.0028322 | 0.0010999 | 0.00010014 | 0.0016322 | N/A | 0.0011454 | 0.24831 | N/A | N/A | 1.1004 | 0.00021844 | N/A | 1.1004
WESTBLUFF | Circuit | Distribution | 17.6994 |  | HFTD 3 | 0.0065503 | 0.0065461 | 4.2034e-06 | 0.0026458 | 0.0021098 | 4.7302e-05 | 0.00048878 | N/A | 0.015855 | 2.4741 | N/A | N/A | 1.2989 | 0.00026511 | N/A | 1.2989
WESTBROOK | Circuit | Distribution | 3.4254 |  | HFTD 3 | 0.011145 | 0.011145 | 0 | 0.0017137 | 0.0014409 | 4.6486e-05 | 0.0002264 | N/A | 0 | 6.5033 | N/A | N/A | 1.0822 |  | N/A | 1.0822
WESTFALL | Circuit | Distribution | 4.7429 |  | HFTD 3 | 0.0054696 | 0.0054664 | 3.233e-06 | 0.0060463 | 0.0026459 | 0.0023311 | 0.0010692 | N/A | 0.002118 | 0.90409 | N/A | N/A | 1.1974 | 0.0015264 | N/A | 1.1974
WHIP | Circuit | Distribution | 3.5908 |  | HFTD 3 | 0.035744 | 0.035565 | 0.00017953 | 0.0059531 | 0.0034178 | 3.6378e-05 | 0.0024989 | N/A | 0.012269 | 5.9742 | N/A | N/A | 1.1864 | 0.014633 | N/A | 1.1864
WHIPSTOCK | Circuit | Distribution | 21.6231 |  | HFTD 3 | 0.022682 | 0.022682 | 0 | 0.010144 | 0.0060381 | 0.00021391 | 0.0038918 | N/A | 0 | 2.236 | N/A | N/A | 1.225 |  | N/A | 1.225
WHISPER | Circuit | Distribution | 0.29415 |  | HFTD 2 | 0.0021513 | 0.0020969 | 5.4452e-05 | 0.0050243 | 0.0040278 | 0.00020693 | 0.00078951 | N/A | 0.00094391 | 0.41735 | N/A | N/A | 1.0777 | 0.057688 | N/A | 1.0777
WHITECLIFF | Circuit | Distribution | 6.8535 |  | HFTD 3 | 0.006215 | 0.0061331 | 8.1948e-05 | 0.012461 | 0.0072207 | 0.00040888 | 0.0048318 | N/A | 0.013692 | 0.49217 | N/A | N/A | 1.1458 | 0.005985 | N/A | 1.1458
WHITEHORN | Circuit | Distribution | 2.8522 |  | HFTD 2 | 0.0074019 | 0.0072982 | 0.00010378 | 0.0035178 | 0.0032711 | 8.2371e-06 | 0.00023851 | N/A | 0.0033674 | 2.0746 | N/A | N/A | 1.1025 | 0.03082 | N/A | 1.1025
WHIZZIN | Circuit | Distribution | 2.4203 |  | HFTD 3 | 0.0011533 | 0.0010343 | 0.00011902 | 0.015105 | 0.0079632 | 0.00025723 | 0.0068842 | N/A | 0.015894 | 0.068474 | N/A | N/A | 1.0616 | 0.0074882 | N/A | 1.0616
WIGWAG | Circuit | Distribution | 0.65999 |  | HFTD 2 | 0.006196 | 0.003889 | 0.002307 | 0.0039123 | 0.0030092 | 0.00012463 | 0.00077846 | N/A | 0.0041876 | 0.99404 | N/A | N/A | 1.2809 | 0.55091 | N/A | 1.2809
WILDOMAR | Circuit | Distribution | 14.3311 |  | HFTD 3 | 0.014109 | 0.014109 | 3.1958e-09 | 0.0034817 | 0.0015247 | 0.00012276 | 0.0018343 | N/A | 0.0062831 | 4.0523 | N/A | N/A | 1 | 5.0863e-07 | N/A | 1
WILLOW SPRINGS | Circuit | Distribution | 0.3344 |  | HFTD 3 | 8.8825e-05 | 8.8825e-05 | 0 | 0.0004114 | 0.00032332 | 0 | 8.808e-05 | N/A | 0 | 0.21591 | N/A | N/A | 1.2109 |  | N/A | 1.2109
WILSON CREEK | Circuit | Distribution | 4.8583 |  | HFTD 3 | 0.0070557 | 0.0070415 | 1.4231e-05 | 0.010479 | 0.0035473 | 0.00075572 | 0.0061758 | N/A | 0.0051115 | 0.67198 | N/A | N/A | 1.1411 | 0.0027841 | N/A | 1.1411
WINERY | Circuit | Distribution | 59.6252 |  | HFTD 3 | 0.032484 | 0.032484 | 1.1251e-07 | 0.0059734 | 0.0045612 | 0.00012394 | 0.0012883 | N/A | 0.0072003 | 5.438 | N/A | N/A | 1.1408 | 1.5625e-05 | N/A | 1.1408
WINNEBAGO | Circuit | Distribution | 0.6675 |  | HFTD 2 | 0.0025656 | 0.0013408 | 0.0012248 | 0.0053128 | 0.0031834 | 0.00010696 | 0.0020224 | N/A | 0.0011162 | 0.25238 | N/A | N/A | 1.1447 | 1.0973 | N/A | 1.1447
WINTHROP | Circuit | Distribution | 0.35584 |  | HFTD 2 | 0.016547 | 0.016527 | 2.0663e-05 | 0.0058485 | 0.0025006 | 0.0004601 | 0.0028878 | N/A | 6.492e-05 | 2.8258 | N/A | N/A | 1.072 | 0.31829 | N/A | 1.072
WOBEGONE | Circuit | Distribution | 38.8868 | Top 5% Highest Risk | HFTD 2 | 0.063322 | 0.06332 | 1.8469e-06 | 0.0042513 | 0.0019197 | 4.7298e-05 | 0.0022843 | N/A | 0.013368 | 14.8943 | N/A | N/A | 1.3143 | 0.00013815 | N/A | 1.3143
WRIGLEY | Circuit | Distribution | 1.1508 |  | HFTD 3 | 0.001071 | 0.001071 | 0 | 0.0031616 | 0.0020242 | 9.8844e-05 | 0.0010385 | N/A | 0 | 0.33875 | N/A | N/A | 1.0537 |  | N/A | 1.0537
WYLE | Circuit | Distribution | 1.4396 |  | HFTD 2 | 0.0040098 | 0.0037788 | 0.00023101 | 0.011846 | 0.0042748 | 0.0017514 | 0.0058201 | N/A | 0.0018401 | 0.31898 | N/A | N/A | 1.0888 | 0.12554 | N/A | 1.0888
YARBOROUGH | Circuit | Distribution | 0.35458 |  | HFTD 2 | 0.00022228 | 4.3926e-05 | 0.00017835 | 0.0037924 | 0.0024969 | 0.00016138 | 0.0011341 | N/A | 0.010644 | 0.011583 | N/A | N/A | 1.035 | 0.016756 | N/A | 1.035
YORKTOWN | Circuit | Distribution | 2.4646 |  | HFTD 2 | 0.00056995 | 0.00056995 | 0 | 0.0061243 | 0.00301 | 9.2684e-05 | 0.0030216 | N/A | 0 | 0.093064 | N/A | N/A | 1.0663 |  | N/A | 1.0663
YOSEMITE | Circuit | Distribution | 4.1244 |  | HFTD 3 | 0.0023503 | 0.0021901 | 0.00016026 | 0.011647 | 0.0075154 | 0.00046094 | 0.0036706 | N/A | 0.017144 | 0.18804 | N/A | N/A | 1.2107 | 0.0093484 | N/A | 1.2107
YUCATAN | Circuit | Distribution | 2.4728 |  | HFTD 3 | 0.027201 | 0.027201 | 0 | 0.014335 | 0.0064664 | 0.00045282 | 0.0074157 | N/A | 0.0026753 | 1.8975 | N/A | N/A | 1.1626 | 0 | N/A | 1.1626
ZENDA | Circuit | Distribution | 49.2469 |  | HFTD 2 | 0.0033591 | 0.003357 | 2.14e-06 | 0.0016413 | 0.0013288 | 4.635e-05 | 0.00026618 | N/A | 0.045499 | 2.0453 | N/A | N/A | 1.1539 | 4.7034e-05 | N/A | 1.1539
ZINC | Circuit | Distribution | 3.8624 |  | HFTD 2 | 0.0012529 | 0.0012529 | 0 | 0.0067204 | 0.0043594 | 0.00066968 | 0.0016913 | N/A | 0.0013376 | 0.18643 | N/A | N/A | 1.1881 | 0 | N/A | 1.1881
ZIRCON | Circuit | Distribution | 0.40713 |  | HFTD 2 | 0.0099414 | 0.0099414 | 0 | 0.015099 | 0.0077773 | 0.0017509 | 0.0055705 | N/A | 0.0013376 | 0.65842 | N/A | N/A | 1.0298 | 0 | N/A | 1.0298
ZONE | Circuit | Distribution | 36.3283 |  | HFTD 3 | 0.0039632 | 0.0039582 | 4.9574e-06 | 0.0064841 | 0.0043266 | 0.00015564 | 0.0020019 | N/A | 0.028036 | 0.61045 | N/A | N/A | 1.173 | 0.00017682 | N/A | 1.173