## Cover Sheet Tables 1-15
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines, Appendix D
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | X
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2024
Reporting Period quarter |  | Q4 |  | Q1 | 2023
Date Modified |  | 2025-02-03 |  | Q2 | 2024
|  |  |  | Q3 | 2025
Q4

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
PGE | 2025-02-03 | Program |  |  | Detailed Inspection Transmission – Ground | Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. | This initiative includes detailed inspections (ground) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Ground Detailed Inspections |  | 8.1.3.1.1 | AI-02 | PGE_Grid Design, Operations and Maintenance_Ground Detailed Inspections_AI-02_2024 | 471 | Equipment ignition likelihood | Yes | # of structures | 20000 | 4000 | 12000 | 20000 | 20000 | 5357 | 21357 | 21680 | 21713 |  | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q1 target of 3,650 by completing 5,523 structures inspected. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q2 target of 12,000 by completing 21,383 structures inspected. This program status is 'In Progress' as we are 7 additional units to complete to meet our 2024 updated target. Please note that the Q1 completed units have been revised to 5,364 from 5,523. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the Q3 target of 20,000 by completing 21,702 structures inspected. This program is now "Completed' as we surpassed the updated target of 21,390 by completing 21,702 TYD. Please note that the Q2 completed units have been revised to 21,379 from 21,383. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. Please also note that the Q1 completed units have been revised to 5,357 from 5,364, Q2 completed units have been revised to 21,357 from 21,379, and Q3 completed units has been updated to 21,680 from 21,702. | Completed
PGE | 2025-02-03 | Program |  |  | Detailed Inspection Transmission – Aerial | Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. | This initiative includes detailed inspections (aerial) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Aerial Detailed Inspections |  | 8.1.3.1.2 | AI-04 | PGE_Grid Design, Operations and Maintenance_Aerial Detailed Inspections_AI-04_2024 | 472 | Equipment ignition likelihood | Yes | # of structures | 20000 | 5000 | 17000 | 20000 | 20000 | 5212 | 22135 | 22763 | 22865 |  | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q1 target of 3,100 by completing 5,253 structures inspected. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q2 target of 17,000 by completing 22,311 structures inspected. Please note that the Q1 units have been updated to 5201 from 5,253. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q3 target of 20,000 by completing 22,838 structures inspected. This program is now "Completed' as we surpassed the updated target of 22,274 by completing 22,838 TYD. Please note that the Q1 units have been updated to 5,219 from 5,201 and Q2 units have been updated to 22,208 from 22,311. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. Please also note that the Q1 units have been updated to 5,212 from 5,219, Q2 units have been updated to 22,135 from 22,208, and Q3 units are updated to 22,763 from 22,838. | Completed
PGE | 2025-02-03 | Program |  |  | Detailed Inspection Transmission – Climbing | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. | This initiative includes detailed inspections (climbing) of transmission poles which can reduce the potential for equipment failure which could case a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Climbing Detailed Inspections |  | 8.1.3.1.3 | AI-05 | PGE_Grid Design, Operations and Maintenance_Climbing Detailed Inspections_AI-05_2024 | 473 | Equipment ignition likelihood | Yes | # of structures | 1200 | 400 | 900 | 1200 | 1200 | 636 | 1216 | 1216 | 1216 |  | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q1 target of 280 by completing 661 structures inspected. | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q2 target of 1,150 by completing 1,216 structures inspected and completed the commitment for the year. Please note that the Q1 value has been updated to 636 from 661. | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We completed the target in Q2 by completing 1,216 structures. | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. | Completed
PGE | 2025-02-03 | Program |  |  | Perform transmission infrared inspections | In 2024, infrared patrols will be performed on energized transmission lines in HFTD areas resulting in infrared patrols on 4,000 miles of transmission line. | This initiative includes transmission infrared inspections which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Infrared Inspections |  | 8.1.3.1.4 | AI-06 | PGE_Grid Design, Operations and Maintenance_Infrared Inspections_AI-06_2024 | 474 | Equipment ignition likelihood | Yes | # of miles | 4000 | 1000 | 1500 | 3000 | 4000 | 1560.46 | 2652.8 | 3867 | 4339.38 |  | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q1 target of 600 by completing 1,363 circuit miles. | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q2 target of 1900 by completing 2550.19 circuit miles. Please note that the Q1 value has been updated to 1478.92 from 1,363. | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q3 target of 3,300 by completing 3,861.26 circuit miles. Please note that the Q1 value has been updated to 1,560.46 from 1,479 and Q2 value to 2,652.8 from 2,550.2. | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. Please also note that the Q3 value has been updated to 3,867 from 3,861.3. | Completed
PGE | 2025-02-03 | Program |  |  | Detailed Ground Inspections - Distribution | Complete detailed inspections on approximately 220,016 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. | This initiative includes detailed inspections of distribution poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Detailed Ground Inspections |  | 8.1.3.2.1 | AI-07 | PGE_Grid Design, Operations and Maintenance_Detailed Ground Inspections_AI-07_2024 | 481 | Equipment ignition likelihood | Yes | # of poles | 220016 | 26000 | 70000 | 150000 | 220016 | 26309 | 94233 | 175940 | 223146 |  | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. This target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. We have surpassed the Q2 target of 70,000 by completing 95,740 poles. Please note that Q1 value has been updated to 26,522 from 27,975. | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. We have surpassed the Q3 target of 150,000 by completing 175,940 poles. Please note that Q1 value has been updated to 26,309 from 26,522 and Q2 value to 94,233 to 95,740. | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. Please also note that, of the 223,146 inspections identified, included are 2,104 constrained inspections. | Completed
PGE | 2025-02-03 | Program |  |  | Supplemental Inspections - Substation Distribution | Complete supplemental inspections on 76 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | 8.1 | Asset Inspection Program - Substation |  | 8.1.3.3.1 | AI-08 | PGE_Grid Design, Operations and Maintenance_Asset Inspection Program - Substation_AI-08_2024 | 492 | Equipment ignition likelihood | Yes | # of Distribution Substations | 76 | 16 | 68 | 76 | 76 | 0 | 12 | 76 | 76 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | Please note that the Q1 progress is updated to 0 from 2. The Change Order rejection for this Target has mandated each commitment to complete supplemental Infrared (IR) and ground inspections for each substation, in addition to the aerial inspection. | Please note that the Q2 progress is updated to 12 from 14. |  | Completed
PGE | 2025-02-03 | Program |  |  | Supplemental Inspections - Substation Transmission | Complete supplemental inspections on 36 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | 8.1 | Asset Inspection Program - Substation |  | 8.1.3.3.1 | AI-09 | PGE_Grid Design, Operations and Maintenance_Asset Inspection Program - Substation_AI-09_2024 | 492 | Equipment ignition likelihood | Yes | # of Transmission Substations | 36 | 16 | 33 | 36 | 36 | 0 | 6 | 36 | 36 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | Please note that the Q1 target has been changed to 0 from 1. The Change Order rejection for this Target has mandated each commitment to complete supplemental Infrared (IR) and ground inspections for each substation, in addition to the aerial inspection. |  |  | Completed
PGE | 2025-02-03 | Program |  |  | Supplemental Inspections - Hydroelectric Substations and Powerhouses | Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | 8.1 | Asset Inspection Program - Substation |  | 8.1.3.3.1 | AI-10 | PGE_Grid Design, Operations and Maintenance_Asset Inspection Program - Substation_AI-10_2024 | 492 | Equipment ignition likelihood | Yes | # of Hydroelectric Substations and Powerhouses | 46 | 15 | 45 | 46 | 46 | 0 | 1 | 46 | 46 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | Please note that the Q1 target has been changed to 0 from 1. The Change Order rejection for this Target has mandated each commitment to complete supplemental Infrared (IR) and ground inspections for each substation, in addition to the aerial inspection. | Please note that the Q2 value has been updated to 1 from 4. |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-09-30 | Community Engagement - Meetings | PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | This initiative concerns customer and community events to further awareness of WMP activities. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-01 | PGE_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-01_2024 | 885 | Wildfire vulnerability | No | [10 empty] | PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | In Q1 of 2024, a total of five Regional Townhalls halls and one CWSP Safety Webinar were conducted. | A total of 14 events counting toward the CO-01 WMP initiative have been completed this year be end of Q2: 13 community events in Q2 of 2024, and one event in Q1 of 2024. In Q2 of 2024, PG&E conducted five Regional Townhalls, seven CWSP Safety Webinars, and one in-person Open House in Boulder Creek. | A total of 25 events counting toward the CO-01 WMP initiative have been completed YTD; 1 event in Q1; 13 events in Q2. In Q3, PG&E conducted 5 Regional Townhalls, 4 CWSP Safety Webinars, and 2 In-Person Open Houses. This initiative is complete for 2024 | This initiative was completed in Q3. | Completed
PGE | 2025-02-03 | Program |  |  | Community Engagement - Surveys | PG&E will complete two PSPS education and outreach surveys, barring External Factors. | This initiative concerns customer and community events to further awareness of WMP activities. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-02 | PGE_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-02_2024 | 885 | Wildfire vulnerability | Yes | # of surveys | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 |  | In Q1 of 2024, PG&E completed the PSPS Post-Season outreach survey, which is one of the two required surveys. |  |  | In Q4 of 2024, PG&E completed the PSPS Pre-Season outreach survey, which is the second and final survey completed for 2024. This initiative is complete for 2024. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-11-30 | Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP) | This initiative will complete the PSPS and Wildfire Tabletop and Functional Exercise to assist with our response to emergency activations, including wildfires. | Emergency Preparedness Plan | 8.4 | Drills, Simulations, and Tabletop Exercises |  | 8.4.2.3.1 | EP-01 | PGE_Emergency Preparedness Plan_Drills, Simulations, and Tabletop Exercises_EP-01_2024 | 821 | PSPS likelihood | No | [10 empty] | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP) | This work remains on track. The Public Safety Power Shutoff Tabletop (PSPS) Exercise was conducted on March 19, 2024. The after-action report for this exercise is under development. The Wildfire Tabletop exercise will take place during the April 15-19 PSPS Full Scale Exercise (FSE), and is on track to be held as scheduled. | This work remains on track. The after-action report for The Public Safety Power Shutoff (PSPS) Tabletop Exercise is complete. The PSPS Full Scale Exercise (FSE) and the Wildfire FSE were conducted on April 15-19, 2024. The after-action report is complete. The Wildfire Tabletop exercise will take place on August 22, 2024. | This work remains on track. The Wildfire Tabletop exercise was held on August 22, 2024. The after action report is scheduled to be completed by October 22, 2024, which will complete the work for the year. | The 2024 Wildfire and PSPS Tabletop and Functional exercises are complete. The PSPS TTX was held on March 19, 2024, the PSPS Functional exercise was held on April 15 to 19, 2024. The Wildfire Tabletop was held on August 22, 2024 and the after-action report completed on October 22, 2024. | Completed
PGE | 2025-02-03 | Program |  |  | Review, and revise the CERP and 2 Wildfire Related Annexes on a yearly basis | Review and revise the CERP (internal document number EMER-3001M) on a yearly basis. | This initiative will review, and revise the CERP and 2 Wildfire Related Annexes to provide emergency response and safely and expeditiously restore service, including during wildfires. | Emergency Preparedness Plan | 8.4 | Emergency Planning |  | 8.4.3.1 | EP-06 | PGE_Emergency Preparedness Plan_Emergency Planning_EP-06_2024 | 838 | PSPS likelihood | No | Company Emergency Response Plan (CERP) and the two wildfire related annexes | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 3 |  | The Wildfire Annex update was completed on March 29, 2024. This objective is on track to be completed in 2024. | This work remains on track. CERP is in the review and revision process with an expected publication date in Q4. | This work remains on track. The Wildfire Annex was completed on March 29, 2024 and the PSPS Annex was completed on July 31, 2024. The CERP document is in the review process and anticipated to be completed in Q4. | The Wildfire Annex was completed on March 29, 2024 and the PSPS Annex was completed on July 31, 2024. The CERP document review was completed in November 2024, making this commitment complete for 2024. | Completed
PGE | 2025-02-03 | Program |  |  | System Hardening - Distribution | Complete 470 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts, barring External Factors | This initiative will harden distribution circuit miles through overhead system hardening, undergrounding, and the removal of overhead lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Covered conductor installation |  | 8.1.2.1 | GH-01 | PGE_Grid Design, Operations and Maintenance_Covered conductor installation _GH-01_2024 | 397 | Equipment ignition likelihood | No | # of circuit miles | 280 | 13.4 | 58.8 | 125.8 | 280 | 17.24 | 100.25 | 212.43 | 348.28 |  | This target's Change Order request was approved, and as such we have updated the annual target and quarterly projected values. |  |  |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-03-29 | Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | This initiative will calculate the covered conductor effective using pervious year's outage data on the lines that have covered conductors for consideration in future system hardening workplans. | Grid Design, Operations and Maintenance | 8.1 | Covered conductor installation |  | 8.1.2.1 | GH-02 | PGE_Grid Design, Operations and Maintenance_Covered conductor installation _GH-02_2024 | 397 | Equipment ignition likelihood | No | [10 empty] | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | We met the 2024 milestones for this objective and consider this work complete for the year. The 2023 outage data--on the lines that have covered conductors for consideration in future system hardening workplans--was downloaded and we adjusted the recorded effectiveness calculation using this data. The documented results were shared with stakeholders to gain buy-in on any adjustments proposed to the covered conductor recorded effectiveness value. | This objective was completed in Q1 | This objective was completed in Q1 | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Program |  |  | 10K Undergrounding | Complete 250 circuit miles of undergrounding work. The 250-circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas | This initiative will underground electrical facilities to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | GH-04 | PGE_Grid Design, Operations and Maintenance_Undergrounding of electric lines and/or equipment_GH-04_2024 | 400 | Equipment ignition likelihood | No | # of circuit miles | 250 | 13 | 48 | 99 | 250 | 14.83 | 61.21 | 119.61 | 257.837 |  | This target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. |  |  |  | Completed
PGE | 2025-02-03 | Program |  |  | System Hardening - Transmission Shunt Splices | Install shunt splice(s) on 22 transmission lines. | This initiative will install shunt splice(s) on transmission lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Traditional overhead hardening - Transmission |  | 8.1.2.5.1 | GH-06 | PGE_Grid Design, Operations and Maintenance_Traditional overhead hardening - Transmission_GH-06_2024 | 436 | Equipment ignition likelihood | No | # of Transmission Lines | 22 | 0 | 6 | 14 | 22 | 1 | 6 | 15 | 23 |  |  |  | Please note that the Q2 progress has been updated to 6 from 7. |  | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Line Motor Switch Operator (MSO) - Replacements | Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. | This initiative will replace or remove Motor Switch Operators to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Motor Switch Operator (MSO) Switch Replacement |  | 8.1.2.10.3 | GH-09 | PGE_Grid Design, Operations and Maintenance_Motor Switch Operator (MSO) Switch Replacement_GH-09_2024 | 457 | Equipment ignition likelihood | No | # of MSOs replacements | 26 | 1 | 10 | 20 | 26 | 1 | 11 | 22 | 26 |  |  | The program surpassed the YTD Target of 9 with 10 units completed Q2 YTD, with 9 units completed within Q2. In June, 3 units were completed. Please note that 1 unit (Order # 35206526) was part of the original list of WMP MSO devices, but has been completed by another program under Order # 31438232 with a CN24 Date of 8/19/2022. As a result, we will be counting this unit as a 2024 completion. In total, we will be reporting 11 MSO devices as removed or replaced as part of the original list. Please note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled. | The program surpassed the YTD Target of 20 with 21 units completed Q3 YTD, with 10 units completed within Q3. In June, 3 units were completed. Please note that 1 unit (Order # 35206526) was part of the original list of WMP MSO devices, but has been completed by another program under Order # 31438232 with a CN24 Date of 8/19/2022. As a result, we will be counting this unit as a 2024 completion. In total, we will be reporting 21 MSO devices as removed or replaced as part of the original list. Please note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled. | Please note that one unit (Order # 35206526) was part of the original list of WMP MSO devices, but has been completed by another program under Order # 31438232 with a CN24 Date of August 19, 2022. As a result, we will be counting this unit as a 2024 completion. In total, we will be reporting 26 MSO devices as removed or replaced as part of the original list. Please note that Q3 units have been updated to 22 from 21. | Completed
PGE | 2025-02-03 | Program |  |  | Non-Exempt Expulsion Fuse - Removal | Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. | This initiative will remove non-exempt equipment that may generate electrical arcs, sparks, or hot material during its normal operation. | Grid Design, Operations and Maintenance | 8.1 | Non-Exempt Expulsion Fuses |  | 8.1.2.10.5 | GH-10 | PGE_Grid Design, Operations and Maintenance_Non-Exempt Expulsion Fuses_GH-10_2024 | 459 | Equipment ignition likelihood | No | # of fuses | 3000 | 80 | 980 | 2440 | 3000 | 215 | 1620 | 2523 | 3106 |  |  | Please note that the Q1 progress has been updated from 166 to 203 | Please note that the Q1 progress has been updated to 209 from 203 and Q2 progress to 1,614 from 1,534. | Please note that Q1 progress has been updated to 215 from 209, Q2 progress to 1620 from 1614, and Q3 progress to 2523 from 2447. | Completed
PGE | 2025-02-03 | Program |  |  | Asset Inspections - Quality Assurance | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 94% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative audits the quality of transmission and distribution system inspections, which can help identify gaps and implement improvements for inspections. | Grid Design, Operations and Maintenance | 8.1 | Quality Assurance (QA) |  | 8.1.6.1 | GM-01 | PGE_Grid Design, Operations and Maintenance_Quality Assurance (QA)_GM-01_2024 | 523 | Equipment ignition likelihood | No | % Pass Rate Audit Locations | Transmission Inspections – HFTD/HFRA : 500 audit locations*; 94% pass rate Distribution Inspections – HFTD/HFRA : 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | 92% | 92% | 92% | 92% | 100% | 99.81% | 99.88% | 99.8% |  | QA System Inspection Transmission Pass Rate: Total # of Tower Passed / Total # of Locations Audited Q1 – January - March (01/01/2024 – 03/30/2024): Pass Rate -> 100% Total # of Locations Audited -> 354 Total # of Locations Passed -> 354 Total # of Locations Failed -> 0 Year to Date (01/01/24 – 03/24/24): Pass Rate -> 100% Total # of Locations Audited -> 354 Total # of Locations Passed -> 354 Total # of Locations Failed -> 0 QA System Inspection Distribution – Expected to start April 2024 Pass Rate: Total # of Locations Passed / Total # of Locations Audited Q1 – January - March (01/01/2024 – 03/30/2024): Pass Rate -> NA Total # of Locations Audited -> NA Total # of Locations Passed -> NA Total # of Locations Failed -> NA Year to Date (01/01/24 – 03/30/24): Pass Rate -> NA Total # of Locations Audited -> NA Total # of Locations Passed -> NA Total # of Locations Failed -> NA This Target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. | QA System Inspection Transmission Q2: Pass Rate -> 99.93% Total # of Locations Audited -> 1456 Total # of Locations Passed -> 1455 Total # of Locations Failed -> 1 Year to Date (Q1 + Q2): Pass Rate -> 99.94% Total # of Locations Audited -> 1810 Total # of Locations Passed -> 1809 Total # of Locations Failed -> 1 Pass Rate: Total # of Locations Passed / Total # of Locations Audited QA System Inspection Distribution Q2: Pass Rate -> 99.60% Total # of Locations Audited -> 2725 Total # of Locations Passed -> 2714 Total # of Locations Failed -> 11 Year to Date (Q1 + Q2): Pass Rate -> 99.60% Total # of Locations Audited -> 2725 Total # of Locations Passed -> 2714 Total # of Locations Failed -> 11 | QA System Inspection Transmission Q3: Pass Rate -> 100% Total # of Locations Audited -> 933 Total # of Locations Passed -> 933 Total # of Locations Failed -> 0 Year to Date(Q1+Q2+Q3) Pass Rate -> 99.97% Total # of Locations Audited -> 2,981 Total # of Locations Passed -> 2,980 Total # of Locations Failed -> 1 QA System Inspection Distribution Q3 : Pass Rate -> 99.79% Total # of Locations Audited -> 2,916 Total # of Locations Passed -> 2,910 Total # of Locations Failed -> 6 Year to Date(Q1+Q2+Q3) Pass Rate -> 99.74% Total # of Locations Audited -> 6,183 Total # of Locations Passed -> 6,167 Total # of Locations Failed -> 16 | QA System Inspection Transmission Pass Rate -> 99.97% Total # of Locations Audited -> 2970 Total # of Locations Passed -> 2969 Total # of Locations Failed -> 1 QA System Inspection Distribution Pass Rate -> 99.69% Total # of Locations Audited -> 7098 Total # of Locations Passed -> 7076 Total # of Locations Failed -> 12 | Completed
PGE | 2025-02-03 | Program |  |  | Eliminate HFTD-HFRA Distribution Backlog | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 68 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 2-year period (2023 to 2024), from 151.1 risk units—as of January 1, 2023—by 102.7 risk units (68 percent). | This initiative is focused on closing out open E maintenance tags for distribution facilities in HFTD and HFRA areas. | Grid Design, Operations and Maintenance | 8.1 | Open Work Orders - Distribution |  | 8.1.7.2 | GM-03 | PGE_Grid Design, Operations and Maintenance_Open Work Orders - Distribution_GM-03_2024 | 531 | Equipment ignition likelihood | No | # of Distribution EC Tags | 64000 | 10012 | 29272 | 53432 | 64000 | 14116 | 37258 | 63711 | 96141 |  | As of Q1 2024, this work is on-track with: (1) 58% interim backlog ignition risk reduction, exceeding the interim target of 51%. Due to the lag time of closing additional distribution EC notifications counting in 2023, we can now report 53.8% of backlog ignition risk reduced in 2023 (an increase from the 52.2% we reported in our Q4 2023 QDR), with an additional 4.2% of backlog ignition risk reduced in Q1 2024, and a cumulative risk reduction of 58% towards our 68% 2024 target. (2) 7,754 distribution backlog ignition risk units completed, exceeding the interim target of 7,196 distribution backlog ignition risk unit completions. (3) 12,496 HFTD/HFRA units completed, exceeding interim target of 10,012 HFTD/HFRA unit completions. | As of Q2 2024, this work is on-track with: (1) 64.8% interim backlog ignition risk reduction, exceeding the interim target of 57.1%. Due to the lag time of closing additional distribution EC notifications counting in 2023, we can now report 53.8% of backlog ignition risk reduced in 2023 (an increase from the 52.2% we reported in our Q4 2023 QDR), with an additional 11.0% of backlog ignition risk reduced through Q2 2024, and a cumulative risk reduction of 64.8% towards our 68.0% 2024 target. (2) 22,493 distribution backlog ignition risk units completed, exceeding the interim target of 21,039 distribution backlog ignition risk unit completions. (3) 37,258 HFTD/HFRA units completed, exceeding interim target of 29,272 HFTD/HFRA unit completions. Please note that the Q1 progress has been updated from 12496 to 14116. | Q3 Progress: As of Q3 2024, this work is on-track with: (1) 71.7% interim backlog ignition risk reduction, exceeding the interim target of 64.7%. Due to the lag time of closing additional distribution EC notifications counting in 2023, we can now report 53.9% of backlog ignition risk reduced in 2023 (an increase from the 52.2% we reported in our Q4 2023 QDR), with an additional 17.8% of backlog ignition risk reduced through Q3 2024, and a cumulative risk reduction of 71.8% towards our 68.0% 2024 target. We have exceeded the 2024 year-end target for backlog ignition risk reduction percentage. (2) 38,063 distribution backlog ignition risk units closed, exceeding the interim target of 37,234 distribution backlog ignition risk unit closures. (3) 63,711 HFTD/HFRA units closed, exceeding interim target of 53,432 HFTD/HFRA unit closures. We have changed our year-end target for this metric, forecasting to close 84,000 HFTD/HFRA EC notifications, which is a change from the target at the beginning of the year of 64,000 HFTD/HFRA EC notification closures. This change is to align with the year-end forecast of HFTD/HFRA EC notification creation and maintain 25,000 more HFTD/HFRA EC closures than HFTD/HFRA EC creations. | As of Q4 2024, this work is complete with: (1) 73.4% backlog ignition risk reduction, exceeding the target of 68.0%. We have exceeded the 2024 year-end target for backlog ignition risk reduction percentage. (2) 53,526 distribution backlog ignition risk units closed, exceeding the target of 46,000 distribution backlog ignition risk unit closures. (3) 96,141 HFTD/HFRA units closed, exceeding the target of 94,456 HFTD/HFRA unit closures. The target of 94,456 unit closures for total HFTD/HFRA volume is attributed to closing out 25,000 more HFTD/HFRA tags than are created in 2024. In 2024, there were 69,456 HFTD/HFRA tags created. | Completed
PGE | 2025-02-03 | Program |  |  | EPSS - Down Conductor Detection (DCD) | Make capable for Down Conductor Detection (DCD) 400 protective device controllers or relays that protect distribution primary overhead conductor that travels through EPSS buffer areas and HFRA, barring External Factors. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | This initiative will make capable for Down Conductor Detection (DCD) 500 protective device controllers or relays to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Downed Conductor Detection (DCD) Devices |  | 8.1.2.10.1 | GM-06 | PGE_Grid Design, Operations and Maintenance_Downed Conductor Detection (DCD) Devices_GM-06_2024 | 455 | Equipment ignition likelihood | No | # of Protective Device Controllers or Relays that are DCD capable | 400 | 48 | 172 | 328 | 400 | 85 | 225 | 476 | 705 |  |  |  |  | Please note that Q2 units have been updated to 225 from 228, and the Q3 units to 476 from 484. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-02-15 | Updates on EPSS Reliability Study | Provide annually an updated EPSS reliability impact study per ACI 22-32 | This initiative provides updates on the EPSS reliability study. | Grid Design, Operations and Maintenance | 8.1 | EPSS Settings |  | 8.1.8.1.1 | GM-07 | PGE_Grid Design, Operations and Maintenance_EPSS Settings_GM-07_2024 | 561 | Equipment ignition likelihood | No | [10 empty] | Provide annually an updated EPSS reliability impact study per ACI 22-32 | PG&E provided an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study per Area for Continued Improvement (ACI) PG&E-22-32 to Energy Safety on February 15, 2024. This Objective is complete for 2024. | This objective was completed in Q1 | This objective was completed in Q1 | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Program |  |  | Asset Inspection – Quality Control | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 15,000 audit locations*; 92 percent pass rate System Inspection Transmission – HFTD (Field): 1,300 audit locations*; 92 percent pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 88 percent pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 88 percent pass rate Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | This initiative will perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program, to gain insight to improve asset inspection work on the field. | Grid Design, Operations and Maintenance | 8.1 | Quality Control (QC) |  | 8.1.6.1 | GM-09 | PGE_Grid Design, Operations and Maintenance_Quality Control (QC)_GM-09_2024 | 525 | Equipment ignition likelihood | No | % Pass Rate Audit Locations | System Inspection Transmission – HFTD: 16,300 audit locations*; 92 percent pass rate System Inspection Distribution – HFTD: 170,000 audit locations*; 88 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | 90% | 90% | 90% | 90% | 93% | 99.58 | 99.8 | 99.89 |  | QC System Inspection Transmission Quarter: January – March (01/01/2024 – 03/30/2024): Pass Rate -> 100.0% Total # of Locations Audited -> 913 Total # of Locations Passed -> 913 Total # of Locations Failed -> 0 Year to Date (01/01/24 – 03/30/2024): Pass Rate -> 100.0% Total # of Locations Audited -> 913 Total # of Locations Passed -> 913 Total # of Locations Failed -> 0 QC System Inspection Distribution Quarter: January – March (01/01/2024 – 03/30/2024): Pass Rate -> 93.0% Total # of Locations Audited -> 43 Total # of Locations Passed -> 40 Total # of Locations Failed -> 3 Year to Date (01/01/24 – 03/30/2024): Pass Rate -> 93.0% Total # of Locations Audited -> 43 Total # of Locations Passed -> 40 Total # of Locations Failed -> 3 This Target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. | QC System Inspection Transmission Quarter Q2: Pass Rate -> 99.96% Total # of Locations Audited -> 18321 Total # of Locations Passed -> 18314 Total # of Locations Failed -> 7 Year to Date (Q1 + Q2): Pass Rate -> 99.96% Total # of Locations Audited -> 19234 Total # of Locations Passed -> 19227 Total # of Locations Failed -> 7 QC System Inspection Distribution Quarter 2: Pass Rate -> 99.78% Total # of Locations Audited -> 62493 Total # of Locations Passed -> 62357 Total # of Locations Failed -> 136 Year to Date (Q1 + Q2): Pass Rate -> 99.78% Total # of Locations Audited -> 62536 Total # of Locations Passed -> 62397 Total # of Locations Failed -> 139 | QC System Inspection Transmission Quarter 3: Pass Rate -> 99.75% Total # of Locations Audited -> 1,989 Total # of Locations Passed -> 1,984 Total # of Locations Failed -> 5 Year to Date (Q1 - Q3): Pass Rate -> 99.95% Total # of Locations Audited -> 23,022 Total # of Locations Passed -> 23,010 Total # of Locations Failed -> 12 QC System Inspection Distribution Quarter 3: Pass Rate -> 99.83% Total # of Locations Audited -> 63,548 Total # of Locations Passed -> 63,438 Total # of Locations Failed -> 110 Year to Date (Q1 - Q3): Pass Rate -> 99.82% Total # of Locations Audited -> 139,236 Total # of Locations Passed -> 138,982 Total # of Locations Failed -> 254 | QC System Inspection Transmission Quarter 4: Pass Rate -> 99.75% Total # of Locations Audited -> 1989 Total # of Locations Passed -> 1984 Total # of Locations Failed -> 5 Year to Date (Q1 - Q4): Pass Rate -> 99.95% Total # of Locations Audited -> 23012 Total # of Locations Passed -> 23000 Total # of Locations Failed -> 12 QC System Inspection Distribution Quarter 4: Pass Rate -> 99.88% Total # of Locations Audited -> 36564 Total # of Locations Passed -> 36520 Total # of Locations Failed -> 44 Year to Date (Q1 - Q4): Pass Rate -> 99.83% Total # of Locations Audited -> 175376 Total # of Locations Passed -> 175084 Total # of Locations Failed -> 292 | Completed
PGE | 2025-02-03 | Program |  |  | Provide portable batteries to PG&E customers | Provide 4,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS | This initiative will provide new or replacement portable batteries to PG&E customers to assist them during emergency events, including wildfires. | Public Safety Power Shutoff | 8.5 | Customer Support in Wildfire and PSPS Emergencies |  | 8.5.3 | PS-06 | PGE_Public Safety Power Shutoff_Customer Support in Wildfire and PSPS Emergencies_PS-06_2024 | 892 | PSPS likelihood | No | # of batteries | 4000 | 65 | 410 | 1975 | 4000 | 681 | 1414 | 3069 | 4376 |  | PG&E has decided that it is important to our customers to continue including permanent batteries for this target, despite having this Change Order request rejected on procedural grounds. We will leverage the opportunity that Energy Safety provided to explain our deviation from the Change Order decision during the compliance process. Staying the course and providing permanent batteries is a better solution for our customers. In addition, there is no risk involved to our system or our customers by providing both portable and permanent batteries. For future QDR submissions, we will include the number of portable and number of permanent batteries we provided to customers within the comments section of this table for full transparency. | Please note the Q1 value has been updated from 682 to 678 and all the reported numbers for Q1 and Q2 are portable only. As stated in Q1 comments we are also providing the permanent batteries count. We have installed 278 permanent batteries in Q2 with a YTD count of 304 permanent batteries. These are in addition to the portable batteries installed. | Please note the Q1 value has been updated to 681 from 678, Q2 to 1,413 from 1,343 and all the reported numbers are portable only. As stated in Q1 and Q2 comments we are also providing the permanent batteries count. We have installed 350 permanent batteries in Q3 with a YTD count of 654 permanent batteries. These are in addition to the portable batteries installed. | Please note the Q2 value has been updated to 1,414 from 1,413, and the Q3 value to 3,069 from 3,062. Additionally, we installed a total of 1,051 permanent batteries in 2024. These permanent batteries are in addition to the 4,376 portable batteries installed. | Completed
PGE | 2025-02-03 | Program |  |  | PSPS Customer Impact Reduction | 18,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2024. | This initiative will focus on the reduction of customer events based on Wildfire mitigation projects and help improve PG&E's response to wildfires. | Public Safety Power Shutoff | 9.1 | Performance Metrics Identified by the Electrical Corporation |  | 9.1.5 | PS-07 | PGE_Public Safety Power Shutoff_Performance Metrics Identified by the Electrical Corporation_PS-07_2024 | 906 | PSPS likelihood | No | # of Customer events | 9980 | 527 | 1932 | 3932 | 9980 | 599 | 2526 | 4933 | 10529 |  | This target's Change Order request was approved, and as such we have updated the annual target and quarterly projected values. |  |  |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-12-31 | Pilot using drones for PSPS restoration | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | This initiative is a pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | Public Safety Power Shutoff | 9.1 | PSPS Restoration Pilot |  | 9.1.2 | PS-11 | PGE_Public Safety Power Shutoff_PSPS Restoration Pilot_PS-11_2024 | 906 | PSPS likelihood | No | [10 empty] | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | This work remains on track. In Q1, Unmanned Aircraft Systems (UAS) Operations documented 2023 PSPS UAS Patrols processes which include lessons learned for both PSPS exercises and live missions. Unmanned Aerial Vehicles (UAV) Patrols were determined to be especially beneficial during weather events with low visibility, as helicopters are unable to fly. UAS continues to participate and document the use of UAV during PSPS events. | This work remains on track. In Q2, Unmanned Aircraft Systems (UAS) Operations started PSPS exercises in June 2024 as part of our goal of continuing to run PSPS UAS exercises and begin documentation for 2024 findings. | This work remains on track. As of the end of Q3, Unmanned Aircraft Systems (UAS) have not been called out for any PSPS events in 2024. | PG&E has completed the objective to evaluate whether drones can be used to support PSPS restoration efforts. This involved running a pilot with the use of drones for PSPS patrol and damage assessment. The findings were presented in PG&E’s WRGSC on November 14, 2024. UAV Patrols demonstrated significant benefits, including reduced risk to personnel compared to ground patrols and minimal environmental impact compared to helicopter use. | Completed
PGE | 2025-02-03 | Program |  |  | Line Sensor - Installations | Install Line Sensor devices on 40 circuits feeding into HFTD areas or HFRA locations. | This initiative will help PG&E continuously measure current in real time and report events as they occur. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures |  | 8.3.3.1 | SA-02 | PGE_Situational Awareness and Forecasting_Grid Monitoring Systems, Existing Systems, Technologies, and Procedures_SA-02_2024 | 739 | Equipment ignition likelihood | No | # of circuits | 40 | 0 | 0 | 30 | 40 | 0 | 12 | 45 | 45 | [5 empty] | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Fault Anticipation (DFA) Installations | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit at the initiating substation. | This initiative will install Distribution Fault Anticipation (DFA) sensors on circuits to allow better detection and assistance in locating faults, abnormal power flow events, and categorization of events. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems, Planned Improvements |  | 8.3.3.3 | SA-10 | PGE_Situational Awareness and Forecasting_Grid Monitoring Systems, Planned Improvements _SA-10_2024 | 739 | Equipment ignition likelihood | No | DFA Sensors | 15 | 0 | 0 | 5 | 15 | 1 | 9 | 12 | 17 | [5 empty] | Completed
PGE | 2025-02-03 | Program |  |  | Early Fault Detection (EFD) Installations | Install Early Fault Detection (EFD) sensors on 2 circuits. | This initiative will install Early Fault Detection (EFD) sensors on circuits to detect failing equipment early and detect vegetation encroachment. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems, Planned Improvements |  | 8.3.3.3 | SA-11 | PGE_Situational Awareness and Forecasting_Grid Monitoring Systems, Planned Improvements _SA-11_2024 | 739 | Equipment ignition likelihood | No | EFD circuits | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 2 | [5 empty] | Completed
PGE | 2025-02-03 | Program |  |  | LiDAR Data Collection - Transmission | Complete LiDAR inspection of the Transmission System (17,500 circuit miles) of transmission lines. The final LiDAR data will inform the Transmission ground patrols by identifying vegetation related risk. The Transmission System circuit miles include HFTD / HFRA Transmission circuit miles. | This initiative includes the collection of LiDAR data for the Transmission System which can reduce the potential for asset-caused ignitions and wildfires. | Vegetation Management and Inspection | 8.2 | Routine Transmission NERC and Non-NERC |  | 8.2.2.1.1 | VM-01 | PGE_Vegetation Management and Inspection_Routine Transmission NERC and Non-NERC_VM-01_2024 | 655 | Contact from vegetation ignition likelihood | Yes | # of circuit miles | 17500 | 12031 | 16000 | 17000 | 17500 | 13379 | 17989 | 17989 | 17989 |  | Please note that we revised this annual target from 17,500 inspection to 18,004 inspections to align with our updated asset registry numbers. This Target's Change Order request was approved, and as such we updated the quarterly target values. | Please note that we revised this annual target from 17,500 inspection to 18,004 inspections to align with our updated asset registry numbers. Please note that there is a 15-mile gap to target due to data resolution and accuracy differences inherent to ETGIS and LIDAR and that this target has now been completed. The Q1 progress has been updated from 12,090 to 13,379. | Please note that we revised this annual target from 17,500 inspection to 18,004 inspections to align with our updated asset registry numbers. Please note that there is a 15-mile gap to target due to data resolution and accuracy differences inherent to ETGIS and LIDAR and that this target was completed in Q2. | This commitment was completed in Q3. | Completed
PGE | 2025-02-03 | Program |  |  | Pole Clearing Program | 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. | This initiative performs pole clearing inspections and work (where needed) for poles in HFTD and HFRA areas where clearance is not required by PRC Section 4292. Pole clearing can reduce the potential for a wildfire ignition. | Vegetation Management and Inspection | 8.2 | Pole Clearing |  | 8.2.3.1 | VM-02 | PGE_Vegetation Management and Inspection_Pole Clearing_VM-02_2024 | 679 | Contact from vegetation ignition likelihood | Yes | # of distribution poles | 63000 | 31500 | 47250 | 63000 | 63000 | 65919 | 79578 | 79988 | 79988 |  | Please note that we revised this annual target from 63,000 structures inspected to 67,196 structures inspected to align with our ending 2023 pole inventory. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q1 target of 56,299 by completing 59,202 structures inspected. | Please note that we revised this annual target from 63,000 structures inspected to 67,196 structures inspected to align with our ending 2023 pole inventory. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q2 target of 47,250 by completing 77,682 but the program is still 'In Progress', since the program can add additional poles until end of September. Please note that the Q1 values included work completed in Q4 of 2023. | Please note that we revised this annual target from 63,000 structures inspected to 67,196 structures inspected to align with our ending 2023 pole inventory. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated target of 67,196 by completing 79,692 poles and the program is now complete. Please note that the Q1 values included work completed in Q4 of 2023. Please note that the Q1 value is updated to 63,185 from 59,202 and Q2 value to 76,365 from 77,682. | Please note that additional high risk poles, without non-exempt equipment, were added to pole clearing inventory in 2024. Please note that Q1 value has been updated to 65,919 from 63,185, Q2 to 79,578 from 76,365 and Q3 to 79,988 from 79,692. | Completed
PGE | 2025-02-03 | Program |  |  | Focused Tree Inspection Program | Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees | This initiative will identify the Areas of Concern (AOC) and implement guidelines to reduce the risk associated with vegetation contact that could cause a potential ignition. | Vegetation Management and Inspection | 8.2 | Focused Tree Inspections |  | 8.2.2.2.5 | VM-03 | PGE_Vegetation Management and Inspection_Focused Tree Inspections_VM-03_2024 | 673 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 1500 | 73 | 300 | 1050 | 1500 | 78 | 382.48 | 1255.47 | 1568.18 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. | This initiative is on track with 386 miles inspected with 60.65 miles QC surveyed by end of Q2. PGE will complete QC survey on all the miles we inspect before end of the year. | This initiative is on track with 1255.47 miles inspected with 830.79 miles QC surveyed by end of Q3. PGE will complete QC survey on all the miles we inspect before end of the year. Please note that Q2 value has been updated to 382.48 from 386. |  | Completed
PGE | 2025-02-03 | Program |  |  | Tree Removal Inventory | Mitigate(c) 20,000 trees identified from the legacy EVM Program | This initiative will remove trees identified from the legacy EVM program to reduce the risk associated with vegetation contact causing a potential ignition. | Vegetation Management and Inspection | 8.2 | Fall-in Mitigation |  | 8.2.2.2.4 | VM-04 | PGE_Vegetation Management and Inspection_Fall-in Mitigation_VM-04_2024 | 672 | Contact from vegetation ignition likelihood | Yes | # of trees Removed | 20000 | 600 | 6200 | 14000 | 20000 | 8496 | 14633 | 18309 | 32480 |  | Please note that this target's Change Order request was rejected on procedural grounds, so we are listing the quarterly targets as they appear in our pre-Change Order/Base WMP submission. |  |  |  | Completed
PGE | 2025-02-03 | Program |  |  | Defensible Space Inspections - Distribution Substation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around distribution substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | 8.2 | Substation Defensible Space |  | 8.2.2.3.1 | VM-05 | PGE_Vegetation Management and Inspection_Substation Defensible Space_VM-05_2024 | 675 | Wildfire exposure potential | Yes | # of Distribution Substations | 131 | 125 | 130 | 131 | 131 | 109 | 131 | 131 | 131 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | The program has surpassed the Q2 target of 130 by completing 131 by end of Q2 and completed the commitment for the year | This initiative was completed in Q2. | This commitment was completed in Q2. Please note that the 2024 targets for VM-05 (Distribution Substation) has been misstated as 55 instead of 131 on page 683 of our 2023-2025 WMP R7. | Completed
PGE | 2025-02-03 | Program |  |  | Defensible Space Inspections - Transmission Substation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around transmission substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | 8.2 | Substation Defensible Space |  | 8.2.2.3.1 | VM-06 | PGE_Vegetation Management and Inspection_Substation Defensible Space_VM-06_2024 | 675 | Wildfire exposure potential | Yes | # of Transmission Substations | 55 | 37 | 55 | 55 | 55 | 48 | 54 | 54 | 54 |  | Please note that this target's Change Order request was rejected on procedural grounds, so we are listing the targets as they appear in our pre-Change Order/Base WMP submission. However, we note that we will only be able to complete inspections on 54 locations, not 55, because the ownership of the Belden PH substation was transferred to the Power Generation line of business. | All inspections for this initiative are complete. Please note that one of the 55 substations, the Belden Powerhouse, was transferred to Power Generation. This asset was, therefore, inspected as part of target VM-07. Inspections were completed for each of the remaining 54 substations as part of this initiative. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. | All inspections for this initiative are complete by end of Q2. Please note that one of the 55 substations, the Belden Powerhouse, was transferred to Power Generation. This asset was, therefore, inspected as part of target VM-07. Inspections were completed for each of the remaining 54 substations as part of this initiative. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. Please note that Q1 value has been updated to 48 from 47. | This commitment was completed in Q2. Please note that the 2024 targets for VM-06 (Transmission Substation) has been misstated as 131 instead of 55 on page 683 of our 2023-2025 WMP R7. | Completed
PGE | 2025-02-03 | Program |  |  | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around hydroelectric substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | 8.2 | Substation Defensible Space |  | 8.2.2.3.1 | VM-07 | PGE_Vegetation Management and Inspection_Substation Defensible Space_VM-07_2024 | 675 | Wildfire exposure potential | Yes | # of Hydroelectric Substations and Powerhouses | 61 | 24 | 61 | 61 | 61 | 53 | 59 | 59 | 59 |  | Please note that this target's Change Order request was rejected on procedural grounds, so we are listing the targets as they appear in our pre-Change Order/Base WMP submission. However we note that we will only be able to complete inspections on 59 locations, not 61, because of the following changes (three subtractions and one addition): (1) the divestiture of Deer Creek PH and Tule River PH; (2) the ownership transfer of Hamilton Branch PH to substation distribution; (3) and the addition of Kilarc PH substation. | The inspections on 59 powerhouses are complete. The remaining two powerhouses have been divested and PG&E no longer owns them. Therefore, work on this initiative is complete. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. | The inspections on 59 powerhouses were complete by Q2. The remaining two powerhouses have been divested and PG&E no longer owns them. Therefore, work on this initiative is complete. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. | This commitment was completed in Q2. | Completed
PGE | 2025-02-03 | Program |  |  | Vegetation Management – Quality Verification | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,675 audit locations*; 95% pass rate Transmission VM – HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing – HFTD: 1,926 audit locations*; 95% pass rate Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative performs Quality Assurance and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspection | 8.2 | Quality Assurance and Quality Control |  | 8.2.5 | VM-08 | PGE_Vegetation Management and Inspection_Quality Assurance and Quality Control_VM-08_2024 | 693 | Contact from vegetation ignition likelihood | No | # of Audit Locations % Pass Rate | 95% | 95% | 95% | 95% | 95% | 99.8% | 99.91% | 99.9% | 99.92% |  | QA Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Q1: Pass Rate -> 99.89% Location Inspected- 620 Total # of Audit Trees Inspected - 941 Total # of Audit Trees Passed -940 Total # of Audit Trees Failed -1 QA Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Q1: Pass Rate -> 99.80% Total # of Poles Audited -> 983 Total # of Poles Passed -> 981 Total # of Poles Failed -> 2 | QA Vegetation Management Distribution: Quarter 2: Pass Rate -> 99.93% Location Inspected - 1423 Total # of Audit Trees Inspected - 5862 Total # of Audit Trees Passed - 5858 Total # of Audit Trees Failed – 4 YTD: Pass Rate -> 99.91% Location Inspected -> 2368 Total # of Audit Trees Inspected - 8931 Total # of Audit Trees Passed - 8923 Total # of Audit Trees Failed - 8 QA Vegetation Management Transmission: Quarter 2: Pass Rate -> 100% Location Inspected - 1293 Total # of Audit Trees Inspected - 2110 Total # of Audit Trees Passed - 2110 Total # of Audit Trees Failed – 0 YTD: Pass Rate -> 100.00% Location Inspected - 1295 Total # of Audit Trees Inspected - 2112 Total # of Audit Trees Passed - 2112 Total # of Audit Trees Failed – 0 QA Pole Clearing: Quarter 2: Pass Rate -> 99.79% Total # of Poles Audited - 962 Total # of Poles Passed - 960 Total # of Poles Failed – 2 YTD: Pass Rate -> 99.82% Total # of Poles Audited - 2260 Total # of Poles Passed - 2256 Total # of Poles Failed - 4 Please note the updated Q1 Values: QA Vegetation Management Distribution: Quarter 1: Pass Rate -> 99.87% Location Inspected - 945 Total # of Audit Trees Inspected - 3069 Total # of Audit Trees Passed - 3065 Total # of Audit Trees Failed - 4 QA Vegetation Management Transmission: Pass Rate -> 100% Location Inspected - 02 Total # of Audit Trees Inspected - 02 Total # of Audit Trees Passed - 02 Total # of Audit Trees Failed - 0 QA Pole Clearing: Pass Rate: Pass Rate -> 99.85% Total # of Poles Audited - 1298 Total # of Poles Passed - 1296 Total # of Poles Failed - 2 | QA Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.95% Location Inspected - 1558 Total # of Audit Trees Inspected - 7596 Total # of Audit Trees Passed - 7592 Total # of Audit Trees Failed - 4 YTD: Pass Rate -> 99.93% Location Inspected -> 3,926 Total # of Audit Trees Inspected - 16,527 Total # of Audit Trees Passed - 16,515 Total # of Audit Trees Failed - 12 QA Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.95% Location Inspected - 886 Total # of Audit Trees Inspected - 2,140 Total # of Audit Trees Passed - 2,139 Total # of Audit Trees Failed - 1 YTD: Pass Rate -> 99.98% Location Inspected - 2,176 Total # of Audit Trees Inspected - 4,242 Total # of Audit Trees Passed - 4,241 Total # of Audit Trees Failed - 1 QA Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Quarter 3: Pass Rate -> 100.00% Total # of Poles Audited - 785 Total # of Poles Passed - 785 Total # of Poles Failed - 0 YTD: Pass Rate -> 99.87% Total # of Poles Audited - 3,045 Total # of Poles Passed - 3,041 Total # of Poles Failed - 4 | QA Vegetation Management Distribution Q4: Pass Rate -> 99.94% Location Inspected - 1340 Total # of Audit Trees Inspected - 6614 Total # of Audit Trees Passed - 6610 Total # of Audit Trees Failed - 4 YTD: Pass Rate -> 99.95% Location Inspected -> 4477 Total # of Audit Trees Inspected - 18513 Total # of Audit Trees Passed - 18504 Total # of Audit Trees Failed - 09 QA Vegetation Management Transmission Q4: Pass Rate -> 99.88% Location Inspected - 573 Total # of Audit Trees Inspected - 1733 Total # of Audit Trees Passed - 1731 Total # of Audit Trees Failed - 2 YTD: Pass Rate -> 99.95% Location Inspected - 2728 Total # of Audit Trees Inspected - 5949 Total # of Audit Trees Passed - 5946 Total # of Audit Trees Failed - 3 QA VC Pole Clearing Q4: Pass Rate -> 99.76% Total # of Poles Audited - 421 Total # of Poles Passed - 420 Total # of Poles Failed - 1 YTD: Pass Rate -> 99.86% Total # of Poles Audited - 3466 Total # of Poles Passed - 3461 Total # of Poles Failed - 5 | Completed
PGE | 2025-02-03 | Program |  |  | Routine Ground - Transmission | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | 8.2 | Routine Transmission – Ground |  | 8.2.2.1.1 | VM-13 | PGE_Vegetation Management and Inspection_Routine Transmission – Ground_VM-13_2024 | 655 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 17740 | 2250 | 9000 | 16000 | 17740 | 7620 | 13738 | 17009 | 17954 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. |  |  | Please note that the completed circuit miles include constraint miles. | Completed
PGE | 2025-02-03 | Program |  |  | Transmission Second Patrol | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | 8.2 | Transmission Second Patrol |  | 8.2.2.1.2 | VM-14 | PGE_Vegetation Management and Inspection_Transmission Second Patrol_VM-14_2024 | 658 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 5625 | 0 | 0 | 0 | 5625 | 0 | 0 | 5197 | 5848 |  | Please note that we revised this annual target from 5,625 circuit miles to 5,697 circuit miles to align with our most recent inspection data. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. The updated target for Q1 is 0 and this work remains on track as it is scheduled to begin in Q4. | Program to start in Q4. | We were able to start the program in July and were able to complete 5,197 inspections in Q3. | Please note that the completed circuit miles include constraint miles. | Completed
PGE | 2025-02-03 | Program |  |  | Integrated Vegetation Management - Transmission | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work | Vegetation Management and Inspection | 8.2 | Integrated Vegetation Management |  | 8.2.2.1.3 | VM-15 | PGE_Vegetation Management and Inspection_Integrated Vegetation Management_VM-15_2024 | 660 | Contact from vegetation ignition likelihood | Yes | Acres | 6504 | 0 | 2590 | 5690 | 6504 | 1785.51 | 5801.63 | 7822.59 | 7907 |  |  | Q1 progress is updated from 0 to 1785.51 due to internal quality review. |  |  | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Routine Patrol | Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide | This initiative will identify vegetation contact that could cause a potential ignition around Distribution equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | 8.2 | Distribution Routine Patrol |  | 8.2.2.2.1 | VM-16 | PGE_Vegetation Management and Inspection_Distribution Routine Patrol_VM-16_2024 | 664 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 78650 | 14459 | 31460 | 51123 | 78650 | 26126.7 | 48966.3 | 70311.32 | 78307.75 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. |  |  | Please note that the target for this commitment was set using ED GIS Data, however the attainment value was based on VM system of record which is not fully aligned with ED GIS Data. We are considering this target as complete due to all inspections being met per VM system of record. | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Second Patrol | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | This initiative will identify vegetation contact that could cause a potential ignition around Distribution equipment and aid in prescribing any needed vegetation mitigation work | Vegetation Management and Inspection | 8.2 | Distribution Second Patrol |  | 8.2.2.2.2 | VM-17 | PGE_Vegetation Management and Inspection_Distribution Second Patrol_VM-17_2024 | 667 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 25685 | 4841 | 10274 | 16695 | 25685 | 7952.35 | 13241 | 21296.8 | 27259.79 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. |  |  |  | Completed
PGE | 2025-02-03 | Program |  |  | VM for Operational Mitigations (VMOM) | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | This initiative will mitigate trees under the VM for Operational Mitigations program, on EPSS capable circuits. | Vegetation Management and Inspection | 8.2 | Mitigations of trees on EPSS capable circuits |  | 8.2.2.2.3 | VM-18 | PGE_Vegetation Management and Inspection_Mitigations of trees on EPSS capable circuits_VM-18_2024 | 670 | Contact from vegetation ignition likelihood | Yes | Trees | 6500 | 1000 | 3000 | 5000 | 6500 | 1488.5 | 4256 | 5121 | 6937 |  | Please note that we revised the Q2 and Q3 targets for this initiative to align with our most recent inspection data. However, we did not change the annual target or the Q1 and Q4 targets for this work. |  |  |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-01-31 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | This initiative will enhance the One VM application for routine, and second patrol to include capability to capture factors for prescribing trees for removal. | Vegetation Management and Inspection | 8.2 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) |  | 8.2.4 | VM-19 | PGE_Vegetation Management and Inspection_One VM Application Record Keeping Enhancement (Routine, Second Patrol)_VM-19_2024 | 691 | Contact from vegetation ignition likelihood | No | [10 empty] | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | The tasks scheduled for Q1: "Monitor and Track" and "Publish Bulletin TD-7102P-01-B036 and 5MM email" were both completed in January on time. The objective has been completed. | This commitment was completed in Q1. | This commitment was completed in Q1. | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-11-15 | Record Keeping Enhancement (VMOM, TRI) | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 and Tree Removal Inventory (TRI) | This initiative will enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 and Tree Removal Inventory (TRI). | Vegetation Management and Inspection | 8.2 | VMOM and TRI Record Keeping |  | 8.2.4 | VM-20 | PGE_Vegetation Management and Inspection_VMOM and TRI Record Keeping_VM-20_2024 | 691 | Contact from vegetation ignition likelihood | No | [10 empty] | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 and Tree Removal Inventory (TRI) | The tasks scheduled for Q1: "Deployment" and "Monitor and Track" were both timely completed in January. This objective remains on track for completion in 2024. Please note that, since this objective was written, the timeline of programs to be onboarded onto the One VM platform has been expedited, and by the time this objective is due, both the VMOM and TRI programs will be integrated into the One VM platform, and no longer utilizing VMPI2 or Field Maps. The One VM application already captures factors for prescribing trees for removal so the objective intent will still be met and consolidating this data in the One VM platform will improve data governance. | This work remains on track for completion in 2024. For TRI/Field Maps, the schema was approved. The next milestone for TRI/Field Maps will be rollout, which we hope to accomplish in Q3. For VMOM Additional Drop downs deployed per guidance of VASA and COA EDRS 2024-13425, this work was completed and deployed with the June 27, 2024 release. | In Q3, this initiative successfully completed the enhancements to the One VM system of record for the Vegetation Management for Operational Mitigation (VMOM) to make capability to capture factors for prescribing trees for removal. In Q3, Field Maps were enhanced to include a reason for removal field for TRI. | This commitment was completed in Q3. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-03-31 | FTI Record Keeping Enhancement | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. | This initiative will enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. | Vegetation Management and Inspection | 8.2 | Focused Tree Inspections Record Keeping |  | 8.2.2.2.5 | VM-21 | PGE_Vegetation Management and Inspection_Focused Tree Inspections Record Keeping_VM-21_2024 | 673 | Contact from vegetation ignition likelihood | No | [10 empty] | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. | All tasks were completed in Q1: "Sprint-4 (Dev + In-Sprint Testing), Sprint-4 Demo, Review, Retro - Code Merge to Code Merge to New Integration SB, Sprint-4 Integration Testing, Code Movement to SAFEUAT, UAT, Prod Go-Live, TRAQ Digitized Form Go-Live, Hypercare Support, One VM TRAQ Skill Permissions Job Aid. The objective has been completed. | This initiative was completed in Q1. | This initiative was completed in Q1. | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Program |  |  | Vegetation Management - Quality Control | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 80,000 audit locations*; 88% pass rate Transmission VM – HFTD: 13,500 audit locations*; 92% pass rate Vegetation Control Pole Clearing – HFTD: 11,500 audit locations*; 88% pass rate Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative performs Quality Control and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspection | 8.2 | Quality Control |  | 8.2.5.2 | VM-22 | PGE_Vegetation Management and Inspection_Quality Control_VM-22_2024 | 698 | Contact from vegetation ignition likelihood | No | % Pass Rate (# of Audit Locations) | 88% | 88% | 88% | 88% | 88% | 97.55% | 93.46% | 94.37% | 94.92% |  | QC Routine Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Q1: Pass Rate -> 96.4% Total # of Locations Audited -> 3384 Total # of Trees Audited -> 16665 Total # of Trees Passed -> 16073 Total # of Trees Failed -> 592 QC Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Q1: Pass Rate -> 98.7% Total # of Locations Audited -> 140 Total # of Trees Audited -> 157 Total # of Trees Passed -> 155 Total # of Trees Failed -> 2 | QC Vegetation Management Distribution: Quarter 2: Pass Rate 96.64% Location Inspected – 33,713 Total # of Audit Trees Inspected – 122,624 Total # of Audit Trees Passed – 118,499 Total # of Audit Trees Failed – 4,125 YTD: Pass Rate: 96.60% Location Inspected – 39,531 Total # of Audit Trees Inspected – 155,062 Total # of Audit Trees Passed – 149,796 Total # of Audit Trees Failed – 5,266 QC Vegetation Management Transmission: Quarter 2: Pass Rate 98.62% Location Inspected - 4,696 Total # of Audit Trees Inspected - 7,947 Total # of Audit Trees Passed - 7,837 Total # of Audit Trees Failed – 110 YTD: Pass Rate -> 98.62% Location Inspected - 4,861 Total # of Audit Trees Inspected - 8,159 Total # of Audit Trees Passed - 8,046 Total # of Audit Trees Failed – 113 QC Pole Clearing: Quarter 2: Pass Rate 81.44% Total # of Poles Audited - 6,794 Total # of Poles Passed - 5,533 Total # of Poles Failed – 1,261 YTD: Pass Rate 85.18% Total # of Poles Audited - 14,145 Total # of Poles Passed - 12,049 Total # of Poles Failed – 2,096 Please note the updated Q1 Values: QC Vegetation Management Distribution: Quarter 1: Pass Rate - 96.48% Location Inspected – 5,818 Total # of Audit Trees Inspected – 32,438 Total # of Audit Trees Passed – 31,297 Total # of Audit Trees Failed – 1,141 QC Vegetation Management Transmission: Quarter 1: Pass Rate -> 98.58% Location Inspected - 165 Total # of Audit Trees Inspected - 212 Total # of Audit Trees Passed - 209 Total # of Audit Trees Failed – 3 QC Pole Clearing: Pass Rate 88.64% Total # of Poles Audited - 7,351 Total # of Poles Passed - 6,516 Total # of Poles Failed – 835 | QC Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 97.59% Location Inspected – 35,081 Total # of Audit Trees Inspected – 163,750 Total # of Audit Trees Passed – 159,806 Total # of Audit Trees Failed – 3,944 YTD: Pass Rate: 97.11% Location Inspected – 74,612 Total # of Audit Trees Inspected – 318,812 Total # of Audit Trees Passed – 309,602 Total # of Audit Trees Failed – 9,210 QC Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.12% Location Inspected – 6661 Total # of Audit Trees Inspected – 14,047 Total # of Audit Trees Passed – 13,923 Total # of Audit Trees Failed - 124 YTD: Pass Rate -> 98.95% Location Inspected – 11,498 Total # of Audit Trees Inspected -22,146 Total # of Audit Trees Passed – 21,913 Total # of Audit Trees Failed - 233 QC Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Quarter 3: Pass Rate – 92.21% Total # of Poles Audited – 5107 Total # of Poles Passed – 4709 Total # of Poles Failed – 398 YTD: Pass Rate – 87.05% Total # of Poles Audited – 19,252 Total # of Poles Passed – 16,758 Total # of Poles Failed – 2,494 | QC Vegetation Management Distribution Q4: Pass Rate -> 98.68% Location Inspected – 9,888 Total # of Audit Trees Inspected – 52,617 Total # of Audit Trees Passed – 51,921 Total # of Audit Trees Failed - 696 YTD: Pass Rate -> 97.38% Spans Audited -> 80,391 Total # of Trees Audited -> 343,470 Total # of Trees Passed -> 334,479 Total # of Trees Failed -> 8,991 QC Vegetation Management Transmission Q4: Pass Rate -> 99.31% Location Inspected –4,445 Total # of Audit Trees Inspected – 10,358 Total # of Audit Trees Passed – 10,287 Total # of Audit Trees Failed - 71 YTD: Pass Rate -> 99.08% Spans Audited -> 15,897 Total # of Trees Audited -> 32,444 Total # of Trees Passed -> 32,147 Total # of Trees Failed -> 297 QC Pole Clearing Q4: Pass Rate – 98.03% Total # of Poles Audited – 2,488 Total # of Poles Passed – 2,439 Total # of Poles Failed – 49 YTD: Pass Rate -> 88.30% Total # of Poles Audited -> 21,740 Total # of Poles Passed -> 19,197 Total # of Poles Failed -> 2,543 | Completed
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | X | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2025-02-03 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | Projected
| Table 2: Performance Metrics | [8 empty] | Q4
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 42 | 122.8 | 14 | 14 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 50 | 181.2 | 218 | 218 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 13.2 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1706 | 5780.6 | 5322 | 5322 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 72 | 180.6 | 9 | 9 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 53 | 143.8 | 109 | 109 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 7.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 846 | 3604.8 | 2610 | 2610 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 224 | 744.2 | 147 | 147 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 174 | 556.2 | 1297 | 1297 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 105.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 8462 | 30172.4 | 38541 | 38541 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1 | 12.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 20 | 52.4 | 83 | 83 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0.8 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 241 | 704.6 | 484 | 484 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 14 | 17.6 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 23 | 63.4 | 36 | 36 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 160 | 584.2 | 302 | 302 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 15 | 62.2 | 3 | 3 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 63 | 85.8 | 351 | 351 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 10.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 598 | 2759.4 | 3890 | 3890 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 38 | 3 | 12 | 12 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 30 | 2 | 106 | 106 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1393 | 3742 | 4486 | 4486 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 38 | 1 | 7 | 7 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 27 | 8 | 53 | 53 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 602 | 1597 | 1917 | 1917 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 197 | 35 | 129 | 129 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 108 | 7 | 1116 | 1116 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 7787 | 30820 | 33802 | 33802 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 4 | 3 | 2 | 2 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 20 | 2 | 35 | 35 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 313 | 613 | 906 | 906 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 34 | 1 | 2 | 2 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 26 | 5 | 30 | 30 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 244 | 650 | 708 | 708 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 27 | 35 | 19 | 19 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 66 | 7 | 839 | 839 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 675 | 2324 | 4101 | 4101 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 18 | 17.8105 | 10 | 10 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 298 | 817.3053 | 900 | 900 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 33 | 2.9684 | 5 | 5 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 102 | 271.1158 | 314 | 314 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 48 | 16.8211 | 12 | 12 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 401 | 1223.9789 | 1130 | 1130 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 1671.5 | 1700 | 1600 | 1500 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 19479 | 4750 | 4650 | 4550 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 2027 | 1700 | 1600 | 1500 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 15273 | 4750 | 4650 | 4550 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 566 | 1700 | 1600 | 1500 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 15490 | 4750 | 4650 | 4550 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 3109 | 2700 | 2600 | 2500 | hours |  | Transmission only includes data from the legacy database.
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 8772 | 7800 | 7700 | 7600 | hours |  | Transmission only includes data from the legacy database.
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 2678.5 | 2700 | 2600 | 2500 | hours |  | Transmission only includes data from the legacy database.
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 7044 | 7800 | 7700 | 7600 | hours |  | Transmission only includes data from the legacy database.
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 2724 | 2700 | 2600 | 2500 | hours |  | Transmission only includes data from the legacy database.
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 7936 | 7800 | 7700 | 7600 | hours |  | Transmission only includes data from the legacy database.
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A |  | 0 | 0 | 0 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A |  | 2 | 2 | 2 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A |  | 0 | 0 | 0 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A |  | 2 | 2 | 2 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  | 0 | 0 | 0 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  | 6 | 6 | 6 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 1 | 1 | 1 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 2 | 10 | 27 | 27 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 1 | 5 | 1 | 1 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 15 | 12 | 29 | 29 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1 | 1 | 1 | 1 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 21 | 13 | 20 | 20 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A |  | 528 | 502 | 380 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A |  | 1273 | 1209 | 420 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A |  | 550 | 180 | 180 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A |  | 1251 | 220 | 200 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  | 46 | 44 | 42 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  | 869 | 826 | 785 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 329 | 331 | 400 | 411 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 835 | 1003.5 | 446 | 316 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 182 | 321.75 | 374 | 417 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 860 | 855.5 | 637 | 589 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 503 | 348 | 827 | 1048 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1533 | 1105.6667 | 1340 | 1526 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A |  | 1603 | 1664 | 1724 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A |  | 2803 | 2880 | 2958 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A |  | 1379 | 1421 | 1462 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A |  | 2731 | 2804 | 2877 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  | 1153 | 1095 | 1037 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  | 2772 | 2845 | 2917 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 919.5 | 1095 | 557 | 636 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 1959 | 1825 | 1470 | 1687 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 230 | 1095 | 506 | 594 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 1564 | 1825 | 1277 | 1452 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 472 | 1095 | 686 | 822 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1633 | 1825 | 1457 | 1646 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 98396 | 275000 | 275000 | 275000 | Number of orders | Data is in total number of trees.​ | This data includes Legacy (Distribution and Transmission) and One VM data.
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 110 | 105 | 100 | Number of orders | Data is in total number of trees and is based off P1/P2 and Second Patrol numbers. These numbers do not include constrained trees.
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 102885 | 644618 | 1000000 | 1082000 | Number of orders | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 14483 | 282584 | 624000 | 746000 | Number of orders | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Hours |  | For metric 8a, data for crew response time to a locked circuit breaker incident is only readily available for instances involving hazard conditions such as 911 or wire down calls. PG&E will continue to review the available information in its outage systems to provide this information in a future filing, although we anticipate creating a system to capture this data could take many months. Currently, any quarterly data would reflect only 911 and wire down events and is not a good representation of our overall response time.
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 357 | 0 | 0 | 0 | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 2 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 2 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 16808 | 224111 | 438012 | 438012 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 28454 | 0 | 147894 | 147894 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial".
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 614 | 219494 | 4712 | 4712 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 630.3 | 8660.905 | 16425 | 16425 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 1067.025 | 0 | 5546 | 5546 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 23.025 | 8482.4783 | 177 | 177 | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  | 0 | 13 | 13 | # of findings from these asset inspections | Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  | 0 | 414 | 414 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  | 1576.6357 | 6 | 6 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  | 2038.6667 | 2281 | 2281 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  | 0 | 206 | 206 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  | 0 | 19892 | 19892 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  | 54920.2451 | 1137 | 1137 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  | 6306 | 9656 | 9656 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  | 0 | 0 | 0 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  | 9501.3651 | 237 | 237 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  | 520.6667 | 1451 | 1451 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 25778 | 192913 | 200464 | 200464 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 6427 | 0 | 67060 | 67060 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial".
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 323 | 9578 | 2044 | 2044 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. Detailed ground inspections in HFTD Tier 3.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 966.675 | 7455.2395 | 7517 | 7517 | # of circuit miles inspected by the utility | Projected data is based on the delta change from 2021 to 2022 for 2023 projection. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 241.0125 | 0 | 2515 | 2515 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 12.1125 | 370.1476 | 77 | 77 | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  | 0 | 6 | 6 | # of findings from these asset inspections | Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  | 0 | 188 | 188 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  | 40.882 | 2 | 2 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  | 1254.6667 | 1043 | 1043 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  | 0 | 94 | 94 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  | 0 | 9020 | 9020 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  | 1448.6962 | 493 | 493 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  | 3344 | 4417 | 4417 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  | 0 | 0 | 0 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  | 281.7402 | 103 | 103 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  | 330 | 664 | 664 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 350954 | 950000 | 1301439 | 1301439 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projected data is based on the average of 2021 and 2022 patrols. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 201 | 0 | 5088 | 5088 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial".
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 90609 | 314929 | 328555 | 328555 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 13160.775 | 36713.3241 | 48804 | 48804 | # of circuit miles inspected by the utility | Projected data is based on the delta change from 2021 to 2022 for 2023 projection. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 7.5375 | 0 | 191 | 191 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 3397.8375 | 12170.6215 | 12321 | 12321 | # of circuit miles inspected by the utility | Projected data is based on the delta change from 2021 to 2022 for 2023 projection. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  | 0 | 78 | 78 | # of findings from these asset inspections | Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 15 | 15 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  | 4343.0968 | 1051 | 1051 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  | 11954.6667 | 10720 | 10720 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  | 0 | 703 | 703 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 907 | 907 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  | 101880.6445 | 106978 | 106978 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  | 12615.6667 | 13342 | 13342 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  | 0 | 0 | 0 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  | 19363.3623 | 23886 | 23886 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  | 1338.3333 | 1595 | 1595 | # of findings from these asset inspections |  | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 26000 | 40000 | 40000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection based on historical
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 73 | 20000 | 13000 | 15000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 19 | 19000 | 16000 | 18000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 1004.7857 | 4478.3671 | 4478.3671 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 2.7375 | 772.9121 | 1455.4693 | 1679.3877 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0.7125 | 734.2665 | 1791.3469 | 1791.3469 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 2 | 26 | 12 | 9 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 5 | 54 | 109 | 97 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 1 | 25 | 33 | 33 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 7 | 18 | 17 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 7 | 33 | 48 | 24 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 4 | 97 | 38 | 35 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 2 | 157 | 71 | 71 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 25 | 5802 | 3527 | 3463 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 9 | 2266 | 3016 | 2885 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 34 | 496 | 1353 | 1341 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 5 | 7 | 1 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 4 | 5 | 5 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 6 | 2340 | 2583 | 2536 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1 | 718 | 1569 | 1503 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 10 | 89 | 525 | 337 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 1544 | 16000 | 22000 | 22000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection based on historical
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 17 | 4000 | 7000 | 4000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 9 | 7000 | 3000 | 4000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 57.9 | 618.3297 | 2506.063 | 2506.063 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0.6375 | 154.5824 | 797.3837 | 455.6478 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0.3375 | 270.5192 | 341.7359 | 455.6478 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 1 | 4 | 11 | 11 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 4 | 18 | 48 | 48 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 5 | 21 | 12 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 3 | 2 | 2 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 4 | 13 | 13 | 11 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 6 | 17 | 17 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 5 | 25 | 41 | 41 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 6 | 1195 | 1596 | 908 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 7 | 470 | 398 | 541 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 15 | 149 | 432 | 432 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 2 | 2 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 1 | 1 | 1 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 426 | 1451 | 826 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 142 | 266 | 362 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 9 | 18 | 154 | 131 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 11957 | 63000 | 58000 | 58000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection based on historical
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 6587 | 25000 | 20000 | 13000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 5192 | 20000 | 22000 | 18000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 448.3875 | 2434.6731 | 6902.6852 | 6902.6852 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 247.0125 | 966.1401 | 2380.2363 | 1547.1536 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 194.7 | 772.9121 | 2618.2599 | 2142.2126 | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 2 | 39 | 74 | 27 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 43 | 186 | 260 | 260 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 15 | 70 | 125 | 120 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 18 | 34 | 81 | 23 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 50 | 203 | 172 | 152 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 9 | 274 | 83 | 71 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 33 | 221 | 127 | 127 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 2121 | 10111 | 6682 | 6437 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 614 | 4853 | 5564 | 1787 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 206 | 1223 | 1752 | 1752 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 6 | 27 | 33 | 16 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 1 | 88 | 43 | 43 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 2486 | 4145 | 5700 | 5490 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 890 | 1929 | 4972 | 1451 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 267 | 211 | 566 | 431 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  | 7 | 7 | 7 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  | 96 | 96 | 96 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  | 685 | 685 | 685 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  | 13 | 12 | 10 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  | 3798 | 4011 | 4223 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  | 687 | 299 | 300 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  | 6 | 7 | 7 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  | 326 | 293 | 260 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  | 195 | 182 | 169 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  | 3 | 3 | 3 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  | 79 | 79 | 79 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  | 401 | 401 | 401 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  | 1 | 1 | 1 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  | 2916 | 3118 | 3319 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  | 69 | 1 | 1 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  | 1 | 1 | 1 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  | 90 | 66 | 43 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  | 47 | 42 | 37 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  | 54 | 54 | 54 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  | 529 | 529 | 529 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  | 3428 | 3428 | 3428 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  | 54 | 42 | 31 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  | 4709 | 4799 | 4888 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  | 1118 | 1072 | 1027 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  | 3 | 2 | 2 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed |  | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  | 799 | 707 | 615 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  | 43 | 37 | 31 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data. | Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 2 | 26 | 12 | 9 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 5 | 56 | 107 | 97 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 1 | 67 | 34 | 33 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 7 | 19 | 17 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 7 | 34 | 52 | 24 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 4 | 53 | 28 | 35 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 19 | 67 | 56 | 71 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 681 | 9644 | 4274 | 3527 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 263 | 3739 | 2317 | 3016 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 178 | 752 | 1769 | 1341 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 3 | 4 | 3 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 2 | 3 | 3 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 143 | 557 | 2755 | 1079 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 82 | 190 | 900 | 351 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 119 | 100 | 388 | 411 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 1 | 4 | 11 | 11 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 4 | 19 | 48 | 48 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 5 | 21 | 12 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 4 | 2 | 2 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 4 | 13 | 13 | 11 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 4 | 13 | 20 | 17 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 1 | 43 | 56 | 41 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 466 | 3794 | 1781 | 908 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 116 | 1468 | 477 | 541 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 66 | 415 | 775 | 432 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 1 | 0 | 1 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 5 | 0 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 105 | 150 | 545 | 334 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 28 | 44 | 202 | 95 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 24 | 69 | 117 | 114 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 2 | 39 | 73 | 27 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 42 | 188 | 263 | 260 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 17 | 70 | 126 | 120 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 18 | 34 | 81 | 23 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 54 | 204 | 176 | 152 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 34 | 92 | 146 | 93 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 28 | 37 | 115 | 67 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 2571 | 1751 | 4769 | 2109 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 754 | 1156 | 2740 | 1342 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 418 | 1241 | 1621 | 1115 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 4 | 2 | 31 | 13 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 11 | 0 | 271 | 62 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 466 | 55 | 2244 | 708 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 316 | 125 | 1365 | 621 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 244 | 229 | 1140 | 565 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 | 483 | 0 | 0 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 56470 | 409746 | 435440 | 435440 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | 1 | 3033 | 2765 | 2765 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 26272 | 21611 | 18185 | 18185 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 3615 | 5 | 5 | 5 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 0 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 4698 | 17830 | 17830 | 17830 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 | 505 | 0 | 0 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 30906 | 285188 | 283000 | 283000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | 0 | 772 | 725 | 725 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 23938 | 27200 | 22802 | 22802 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 2309 | 2 | 2 | 2 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 0 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 4011 | 13380 | 13380 | 13380 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 | 35 | 0 | 0 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | 160109 | 717468 | 685206 | 685206 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | 0 | 766 | 708 | 708 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 2928 | 7118 | 6015 | 6015 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 416 | 9 | 9 | 9 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 | 0 | 0 | 0 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | 14451 | 33465 | 33465 | 33465 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 | 5500000 | 5500000 | 5500000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on Project Year. For 2024, and 2025, we expect approximately 5,500,000 trees.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 1693 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | We are unable to pull forecasted numbers by HFTD tier. We've have placed all forecasted units in Non-HFTD
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 | 5 | 4 | 2 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 0 | 3 | 0 | 1 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 | 2100000 | 2100000 | 2100000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on Project Year. For 2024, and 2025, we expect approximately 2,100,000 trees.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 545 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | We are unable to pull forecasted numbers by HFTD tier. We've have placed all forecasted units in NonHFTD. Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 | 47 | 10 | 10 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 | 3 | 1 | 1 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 | 11000000 | 11000000 | 11000000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on Project Year. For 2024, and 2025, we expect approximately 11,000,000 trees.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | 2315 | 64550 | 64550 | 64550 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | These are forecasted numbers for all HFTD tiers. We are unable to pull forecasted data by HFTD tier. Inspection Method "Other" includes ground patrols.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 | 90 | 623 | 100 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | 0 | 22 | 4 | 10 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Percentage of customers notified of evacuation |  | PG&E does not issue wildfire evacuation notices to customers and does not maintain metrics on the number of customers in an evacuation zone or the number of customers notified of evacuation orders. Because of this, PG&E is unable to report on evacuation related requirements in this table. PG&E anticipates this to be a recurring challenge going forward.

## Table 3
Utility | X
Table No. | 3
Date Modified | 2025-02-03
[5 empty] | Actual | Projected
Table 3: List and description of additional metrics |  |  |  |  | Q4
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
Customer Hours of PSPS per RFW OH Circuit Mile Day |  |  |  |  | 8.86 | 25.1 | 24.8 | 24.5

## Table 4
Utility | X
Table No. | 4
Date Modified | 2025-02-03
Table 4: Weather patterns |  |  | Q4
Metric type | # | Metric name | 2024 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 41831.5 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 19068.64 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 115554.48 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 1348.48 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 789.65 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 2575.02 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 43179.98 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 19858.29 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 118129.5 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 448428.46 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 164639.01 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 86731.4906 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)

## Table 5
| Utility | X | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2025-02-03
[8 empty] | Actual number of risk events | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q4
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 0 | 66 | 38 | 38 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 0 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 0 | 2 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | No | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | No | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 16 | 91 | 78 | 78 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 1 | 9 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 3 | 39 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 128 | 554 | 524 | 524 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 9 | 36 | 27 | 27 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 6 | 16 | 14 | 14 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 6 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 11 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 12 | 65 | 132 | 132 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 4 | 11 | 14 | 14 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 1 | 10 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.t.0 | 3rd party contact | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.d.0 | Other contact from object | Distribution | Non-HFTD | Yes | 1 | 17 | 68 | 68 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.d.2 | Other contact from object | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.t.0 | Other contact from object | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.t.2 | Other contact from object | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 189 | 1205 | 2187 | 2187 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 158 | 416 | 262 | 262 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 135 | 372 | 207 | 207 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 4 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 2 | 3 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 4 | 0 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 164 | 567 | 748 | 748 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 23 | 50 | 43 | 43 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 13 | 32 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 2 | 5 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | Yes | 1 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | No | 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | No | 0 | 4 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | No | 0 | 1 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 6 | 49 | 50 | 50 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 5 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 1 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 5 | 0 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 37 | 129 | 192 | 192 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 6 | 13 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 3 | 4 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 4 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 1 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 46 | 0 | 171 | 171 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 5 | 0 | 17 | 17 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 2 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 1 | 4 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 3 | 5 | 10 | 10 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 2 | 19 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | No | 32 | 0 | 36 | 36 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 48 | 0 | 10 | 10 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 25 | 0 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | No | 1 | 1 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 7 | 0 | 97 | 97 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 2 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | No | 0 | 0 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | No | 0 | 2 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | No | 0 | 0 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | No | 29 | 82 | 70 | 70 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | No | 1 | 6 | 10 | 10 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | No | 1 | 6 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 18 | 546 | 310 | 310 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 3 | 26 | 16 | 16 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 1 | 10 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | No | 2 | 7 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | No | 0 | 14 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | No | 0 | 7 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 532 | 1411.2 | 1638 | 1638 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 83 | 254.7 | 286 | 286 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 20 | 91.8 | 91 | 91 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 13 | 32 | 30 | 30 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 5 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 57 | 443 | 410 | 410 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 3 | 7 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 1 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 380 | 1754 | 1707 | 1707 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 37 | 95 | 133 | 133 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 22 | 45 | 62 | 62 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 11 | 54 | 59 | 59 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 5 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 31 | 294 | 231 | 231 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 11 | 38 | 36 | 36 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 10 | 15 | 15 | 15 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | No | 4 | 0 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | 37 | 159 | 175 | 175 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 11 | 17 | 29 | 29 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 7 | 2 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 20 | 16 | 16 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 766 | 2263 | 4931 | 4931 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 333 | 580 | 809 | 809 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 300 | 620 | 758 | 758 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 2 | 20 | 20 | 20 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 4 | 10 | 13 | 13 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 4 | 5 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 8 | 47 | 55 | 55 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 1 | 4 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 11 | 52 | 49 | 49 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 4 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 677 | 1567 | 2213 | 2213 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 86 | 109 | 200 | 200 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 50 | 57 | 93 | 93 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 4 | 10 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 2 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 2 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 217 | 184 | 433 | 433 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 21 | 3 | 31 | 31 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 4 | 0 | 13 | 13 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 4 | 10 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 1 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 269 | 677 | 825 | 825 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 30 | 74 | 113 | 113 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 11 | 38 | 47 | 47 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 212 | 803 | 977 | 977 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 29 | 72 | 90 | 90 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 7 | 49 | 52 | 52 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | No | 0 | 322 | 224 | 224 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | 0 | 47 | 30 | 30 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | 0 | 14 | 12 | 12 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 66 | 224 | 253 | 253 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 23 | 50 | 70 | 70 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 9 | 34 | 39 | 39 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | No | 12 | 20 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | No | 0 | 10 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | No | 0 | 10 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 25 | 110 | 112 | 112 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 8 | 20 | 20 | 20 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 2 | 14 | 13 | 13 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 8 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 494 | 947 | 1266 | 1266 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 91 | 170 | 239 | 239 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 37 | 76 | 96 | 96 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 8 | 15 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 2 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 26 | 80 | 78 | 78 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 8 | 21 | 24 | 24 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 1 | 13 | 12 | 12 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 3 | 4 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | No | 18 | 3 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 1 | 0 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 207 | 723 | 733 | 733 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 21 | 66 | 81 | 81 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 7 | 26 | 27 | 27 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 51 | 199 | 172 | 172 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 2 | 6 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 2 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 27 | 5 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 1 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 966 | 3888 | 3675 | 3675 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 157 | 430 | 472 | 472 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 64 | 179 | 206 | 206 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 7 | 2 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 20 | 56 | 54 | 54 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 4 | 12 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 4 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | 169 | 108 | 303 | 303 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 27 | 15 | 52 | 52 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 13 | 6 | 17 | 17 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes | 10 | 34 | 27 | 27 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 3 | 3 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 7605.77 | 5899 | 5899 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 1363.82 | 986 | 986 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 561.63 | 458 | 458 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 13 | 0 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 17 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 39 | 86 | 103 | 103 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 2 | 2 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 11 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 10 | 158 | 299 | 299 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 3 | 20 | 104 | 104 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 4 | 11 | 64 | 64 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 2 | 20 | 42 | 42 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 10 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 1 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | No | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | No | 12 | 20 | 24 | 24 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | No | 4 | 11 | 15 | 15 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | No | 0 | 8 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | Yes | 0 | 47.46 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | Yes | 0 | 3.39 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | Yes | 0 | 1.13 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | No | 4 | 165 | 206 | 206 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | No | 6 | 50 | 53 | 53 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | No | 1 | 16 | 15 | 15 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | No | 2842 | 10632.17 | 11431 | 11431 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 609 | 1328.9 | 1649 | 1649 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 330 | 541.26 | 741 | 741 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | No | 64 | 90 | 150 | 150 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 18 | 26 | 87 | 87 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 6 | 18 | 43 | 43 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 379 | 0 | 421 | 421 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 127 | 0 | 143 | 143 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 45 | 0 | 50 | 50 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | No | 45 | 80 | 139 | 139 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | No | 15 | 60 | 49 | 49 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | No | 3 | 14 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.

## Table 6
| Utility | X | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2025-02-03
[7 empty] | Actual number of ignitions | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q4
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 15 | 34 | 45 | 45 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 1 | 6.8747 | 3 | 3 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 1 | 3 | 3 | 3 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 4 | 4 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 2 | 20 | 15 | 15 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 2 | 2 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 2 | 1 | 1 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 8 | 36 | 39.5 | 39.5 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 2 | 2 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 6 | 3 | 3 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | 0 | 0 | 4.5 | 4.5 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | 2 | 23 | 12 | 12 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 4.9105 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 12 | 57 | 54 | 54 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 2 | 25.5346 | 18 | 18 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 5 | 16.6957 | 8 | 8 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 2 | 1.5 | 1.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 3 | 9 | 6.5 | 6.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 7 | 43 | 37 | 37 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 3 | 0.9821 | 5 | 5 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 1 | 2.9463 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 1 | 1.5 | 1.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 1 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 6 | 30 | 21.5 | 21.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 0 | 2.9463 | 3 | 3 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 0 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 1 | 0 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 8 | 5.5 | 5.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | No | 1 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 3 | 2.5 | 2.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 1 | 0 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 6 | 6 | 6 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | No | 3 | 0 | 5 | 5 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | No | 0 | 0 | 1 | 1 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | No | 0 | 0 | 1 | 1 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 8 | 5.5 | 5.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 13 | 15 | 15 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 20 | 14.5 | 14.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 4.9105 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 3.9284 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 5 | 7 | 5 | 5 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 1 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 4 | 8 | 4 | 4 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 1 | 1.9642 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 1 | 2 | 6 | 6 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 1.5 | 1.5 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 2 | 1.5 | 1.5 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 1 | 0 | 7.5 | 7.5 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 1 | 0.9821 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0.5 | 0.5 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 28 | 14 | 14 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1.9642 | 2 | 2 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 1 | 1 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 1 | 0 | 0 | # ignitions

## Table 7
| Utility | X
| Table No. | 7
| Date Modified | 2025-02-03
[7 empty] | Actual | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 4627.6352 | 4626.8062 | 4626.8062 | 4626.8062 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 9512.4855 | 9427.7867 | 9427.7867 | 9427.7867 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 6960.9373 | 6964.8843 | 6964.2888 | 6964.2649 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 28500.2013 | 28918.0957 | 28916.5517 | 28916.5838 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 423.5603 | 417.2495 | 414.7901 | 412.4651 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 5216.0764 | 4850.496 | 4850.496 | 4850.496 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 684.6329 | 676.2417 | 672.0564 | 672.0021 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 115.2903 | 111.8676 | 110.7105 | 110.2423 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 8457.7538 | 8542.8162 | 8479.2806 | 8433.5489 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 5343.8658 | 5382.2062 | 5373.0803 | 5371.2366 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 823.2718 | 791.5735 | 788.2493 | 771.2046 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 2346.4734 | 2354.5008 | 2343.5322 | 2324.9942 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 260.6652 | 267.8224 | 265.3791 | 260.6636 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 34.1546 | 33.3088 | 31.6778 | 31.6566 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 4095.0395 | 4128.5518 | 4067.9847 | 3924.0275 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 1678.6337 | 1694.6322 | 1671.444 | 1646.7885 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 343.7146 | 329.315 | 329.0328 | 326.7596 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 341.8437 | 342.0181 | 327.0256 | 324.6457 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 574.3635 | 588.3099 | 577.5943 | 577.5943 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 1604.3793 | 1594.5712 | 1610.296 | 1610.296 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 875.423 | 882.4176 | 884.0741 | 884.0741 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 7747.3875 | 7952.5809 | 7812.6742 | 7812.6742 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 47.3271 | 45.8319 | 47.4682 | 47.4682 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 1580.6756 | 1541.0439 | 1591.7092 | 1591.7092 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 100.6399 | 99.8541 | 101.2669 | 101.2669 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 116.2407 | 119.926 | 118.0885 | 118.0885 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 851.8958 | 862.0742 | 857.3767 | 857.3767 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 2054.2698 | 2067.8761 | 2066.4436 | 2066.4436 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 67.1669 | 72.8263 | 67.1932 | 67.1932 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 958.3237 | 996.3023 | 958.4114 | 958.4114 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 35.002 | 35.0025 | 35.0025 | 35.0025 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 23.1582 | 23.1582 | 23.1582 | 23.1582 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 300.9987 | 305.6539 | 300.9962 | 300.9962 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 753.7378 | 757.9541 | 753.7425 | 753.7425 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 27.054 | 27.036 | 27.0372 | 27.0372 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 133.1446 | 138.4021 | 133.1418 | 133.1418 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 6498.8749 | 6476.1865 | 6476.1865 | 6476.1865 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the GH-04 target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 12389.5336 | 12097.9196 | 12097.9196 | 12097.9196 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 2889.5433 | 2804.774 | 2805.5185 | 2805.5483 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 3543.241 | 3400.5188 | 3402.4488 | 3402.4088 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 59.8611 | 62.0248 | 65.0991 | 68.0053 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 162.7255 | 166.3555 | 166.3555 | 166.3555 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 352.7308 | 340.6206 | 345.8523 | 345.9201 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 51.3205 | 49.4138 | 50.8602 | 51.4454 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 1254.406 | 1137.3278 | 1216.7473 | 1273.912 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 535.9229 | 470.5939 | 482.0013 | 484.306 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 85.0558 | 71.1856 | 75.3408 | 96.6467 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 211.1209 | 189.4792 | 203.1899 | 226.3625 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 112.1369 | 119.9679 | 123.022 | 128.9164 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 7.2808 | 7.7861 | 9.8249 | 9.8513 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 657.6682 | 562.6023 | 638.3111 | 818.2576 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 206.7629 | 188.8152 | 217.8004 | 248.6198 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 31.3538 | 20.6153 | 20.968 | 23.8095 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 47.4201 | 33.607 | 52.3476 | 55.3226 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 23.521 | 10.8746 | 23.521 | 23.521 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 100.4945 | 36.3202 | 100.4948 | 100.4948 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 10.8743 | 23.3964 | 10.8746 | 10.8746 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 36.3053 | 99.8783 | 36.3053 | 36.3053 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 1.6534 | 1.1211 | 1.6534 | 1.6534 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0.14894 | 7.8594 | 0.14894 | 0.14894 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 1.1211 | 1.6534 | 1.1211 | 1.1211 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 7.8692 | 0.14894 | 7.8692 | 7.8692 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0.58353 | 0.58353 | 0.58353 | 0.58353 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0.35051 | 0.35051 | 0.35051 | 0.35051 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 13127 | 15539 | 13054 | 13054 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 30667 | 37488 | 30630 | 30630 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 6502 | 7423 | 6249 | 6249 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 8474 | 12596 | 8494 | 8494 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 231 | 241 | 202 | 202 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 679 | 796 | 635 | 635 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 988 | 1141 | 1055 | 1055 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 180 | 221 | 177 | 177 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 3018 | 3578 | 3232 | 3232 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 1434 | 1690 | 1545 | 1545 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 314 | 352 | 334 | 334 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 411 | 473 | 472 | 472 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 361 | 426 | 371 | 371 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 50 | 56 | 54 | 54 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 1675 | 1960 | 1760 | 1760 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 592 | 697 | 649 | 649 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 159 | 213 | 160 | 160 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 115 | 110 | 110 | 110 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 1240123 | 1228424 | 1232262 | 1232262 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 2598093 | 2546192 | 2576414 | 2576414 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 411369 | 403265 | 407421 | 407421 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 321627 | 312685 | 313217 | 313217 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 10100 | 10408 | 10007 | 10007 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 12808 | 10820 | 12716 | 12716 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 69605 | 72042 | 69398 | 69398 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 3751 | 3444 | 3749 | 3749 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 190988 | 195912 | 190956 | 190956 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 32715 | 27026 | 32420 | 32420 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 16457 | 17101 | 16387 | 16387 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 10266 | 8508 | 10261 | 10261 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 27309 | 27234 | 27202 | 27202 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 1803 | 1868 | 1801 | 1801 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 104584 | 105782 | 103802 | 103802 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 11426 | 9687 | 11406 | 11406 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 9131 | 9558 | 9107 | 9107 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 2553 | 1602 | 2553 | 2553 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | 98101 | 107089 | 97669 | 97669 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 307607 | 322682 | 306004 | 306004 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | 53802 | 60055 | 53563 | 53563 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 156200 | 165601 | 154963 | 154963 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 1822 | 1990 | 1804 | 1804 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 13390 | 12653 | 13199 | 13199 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 3258 | 3952 | 3237 | 3237 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 771 | 750 | 753 | 753 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 17969 | 19648 | 18002 | 18002 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 10870 | 10370 | 10835 | 10835 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 1682 | 1921 | 1685 | 1685 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 3366 | 3174 | 3343 | 3343 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 1296 | 1717 | 1287 | 1287 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 175 | 200 | 175 | 175 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 7875 | 8774 | 7871 | 7871 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 3346 | 3252 | 3343 | 3343 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 678 | 786 | 676 | 676 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 564 | 503 | 565 | 565 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | 334709 | 342839 | 291150 | 291150 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 861178 | 868502 | 739323 | 739323 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | 113088 | 113761 | 98813 | 98813 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 118389 | 119491 | 99380 | 99380 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 2938 | 3083 | 2632 | 2632 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 3901 | 3324 | 3134 | 3134 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 12330 | 13473 | 11615 | 11615 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 658 | 634 | 537 | 537 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 54386 | 57174 | 47895 | 47895 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 8079 | 6113 | 5218 | 5218 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 4570 | 4747 | 4142 | 4142 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 2600 | 1995 | 1699 | 1699 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 4394 | 4563 | 3857 | 3857 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 343 | 399 | 330 | 330 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 28136 | 28288 | 24429 | 24429 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 2592 | 2002 | 1724 | 1724 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 1780 | 1906 | 1587 | 1587 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 617 | 348 | 300 | 300 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | 96 | 87 | 100 | 100 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 202 | 216 | 206 | 206 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | 59 | 67 | 68 | 68 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 286 | 305 | 301 | 301 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 6 | 4 | 6 | 6 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 61 | 61 | 61 | 61 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 14 | 11 | 12 | 12 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 4 | 5 | 4 | 4 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 41 | 34 | 36 | 36 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 69 | 65 | 65 | 65 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 14 | 17 | 14 | 14 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 49 | 52 | 52 | 52 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 23 | 18 | 22 | 22 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 22 | 28 | 23 | 23 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 5 | 4 | 5 | 5 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 19 | 17 | 16 | 16 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | 22 | 20 | 22 | 22 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 35 | 20 | 31 | 31 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | 73 | 61 | 72 | 72 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 187 | 150 | 178 | 178 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 8 | 10 | 8 | 8 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 70 | 53 | 63 | 63 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 9 | 9 | 9 | 9 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 7 | 7 | 7 | 7 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 189 | 182 | 188 | 188 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 381 | 355 | 369 | 369 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 34 | 33 | 34 | 34 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 240 | 221 | 232 | 232 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 9 | 7 | 8 | 8 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 5 | 5 | 5 | 5 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 106 | 115 | 107 | 107 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 158 | 138 | 152 | 152 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 15 | 12 | 15 | 15 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 37 | 34 | 34 | 34 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.

## Table 8
| Utility | X |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2025-02-03 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | -0.23776 | -1.7999 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | -0.93844 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | -0.34193 | -60.992 | -0.59558 | -0.055101 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | -5.2321 | -17.9376 | -1.544 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | -0.52904 | -4.1272 | -2.4594 | -2.4643 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0.8125 | -8.5642 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | -2.9478 | -7.0284 | -4.1853 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | -0.31645 | -6.6406 | -1.1571 | -0.45322 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | -20.3976 | -80.1994 | -63.5356 | -44.9203 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | -9.7825 | -28.8992 | -9.1259 | -1.7255 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | -3.4508 | -6.3142 | -3.3242 | -17.0966 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | -2.7448 | -49.5734 | -10.9686 | -18.3959 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | -1.8758 | -4.1528 | -2.4433 | -4.8538 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | -1.631 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | -24.8965 | -59.1051 | -60.567 | -144.8624 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | -6.5989 | -12.9045 | -23.1882 | -24.7178 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0.0165 | -0.074433 | -0.28221 | -2.2695 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | -3.5399 | -1.6873 | -14.9925 | -2.1856 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0.031632 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | -0.28055 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | -0.32237 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | -36.3699 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0.24238 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 6.9e-05 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | -0.044003 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0.017327 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | -1e-06 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | -0.11679 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0.000344 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0.000292 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | -0.00048 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 8.93 | 1.7999 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 27.8463 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 13.0811 | 60.992 | 0.74447 | 0.068877 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 47.3461 | 17.9376 | 1.93 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 1.5347 | 4.1272 | 3.0742 | 3.0803 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 1.6951 | 8.5642 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 7.3043 | 7.0284 | 5.2317 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0.38059 | 6.6406 | 1.4463 | 0.56652 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 36.6344 | 80.1994 | 79.4195 | 56.1503 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 12.2435 | 28.8992 | 11.4074 | 2.1568 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 5.702 | 6.3142 | 4.1553 | 21.3708 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 13.4952 | 49.5734 | 13.7107 | 22.9948 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 4.5866 | 4.1528 | 3.0542 | 6.0673 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 2.0388 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 38.6949 | 59.1051 | 75.7088 | 181.0781 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 9.4626 | 12.9045 | 28.9852 | 30.8973 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 1.7261 | 0.074433 | 0.35277 | 2.8369 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 13.1384 | 1.6873 | 18.7406 | 2.732 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | -1 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | -4 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | -3 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | -10 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | -1 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 4 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | -1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.

## Table 9
| Utility | X
| Table No. | 9
| Date Modified | 2025-02-03
[7 empty] | Actual | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0.71818 | 0 | 0.03765 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0.38769 | 0 | 0.84952 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 3.2125 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 6.5309 | 7.7891 | 7.0067 | 3.7356 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 1.8006 | 4.3459 | 1.3792 | 0.7371 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 166.5816 | 140.3187 | 132.0856 | 129.9411 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 35.9663 | 75.8792 | 28.4566 | 54.5557 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 5.6983 | 10.9162 | 4.2616 | 35.1987 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 23.2017 | 60.1443 | 16.8361 | 41.082 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0.045455 | 1.3737 | 0 | 4.3082 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 2.8678 | 3.1656 | 2.5105 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 48.0697 | 58.0958 | 41.7092 | 182.6442 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 36.0081 | 35.5504 | 27.1501 | 55.426 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0.47064 | 0.29637 | 0.5286 | 2.8241 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 19.9384 | 22.1249 | 17.1887 | 6.335 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 1 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 1 | 1 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.

## Table 10
Utility | X |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2025-02-03 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q4
Metric type | # | Wind Warning Status | Metric name | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | 1 | 2 | 2 | 2 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW & RFW | Frequency of PSPS events (total) | 2 | 1.8 | 1.8 | 1.8 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | 4 | 3.8 | 3.8 | 3.8 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 1.b. | RFW only | Scope of PSPS events (total) | 97 | 134.4 | 134.4 | 134.4 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW & RFW | Scope of PSPS events (total) | 198 | 324.6 | 324.6 | 324.6 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | 864 | 459 | 459 | 459 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 1.c. | RFW only | Duration of PSPS events (total) | 724595 | 2795135.801 | 2763550.7661 | 2724861.055 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | HWW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | HWW & RFW | Duration of PSPS events (total) | 752610 | 9526845.295 | 9419171.854 | 9287303.448 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | 1563698 | 12321981.096 | 12182722.6201 | 12012164.503 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
| 1.d. | RFW only | Frequency of fast-trip events (total) | 137 | 37.6 | 36.8 | 36 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
|  | HWW only | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
|  | HWW & RFW | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
|  | None | Frequency of fast-trip events (total) | 660 | 2312.4 | 2263.2 | 2214 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | 517007 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
|  | None | Circuit mile days with fast-trip settings enabled (total) | 1417207.23 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | 2879851.2667 | 11265868.55 | 11265868.55 | 11265868.55 | Total customer hours of planned outages per year | Projected values are based on 3-year historical average.
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | 7374134.3833 | 33804724.6167 | 33804724.6167 | 33804724.6167 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year | Projected values are based on 3-year historical average.
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | 1608125.25 | 0 | 0 | 0 | Total customer hours of outages due to fast-trip per year | Projected values are based on the average of the last 2 years.
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | 122.7 | 476.9667 | 521.7 | 521.7 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Projected values are based on the average of the last 2 years. Data is reported in minutes. Projected Values have been converted to minutes to keep dataset aligned.
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | 106.4 | 387.4667 | 521.25 | 521.25 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Projected values are based on the average of the last 2 years. Data is reported in minutes. Projected values have been converted to minutes to keep dataset aligned.
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | 0.576 | 1.7237 | 1.507 | 1.507 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Projected values are based on the average of the last 2 years.
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | 0.569 | 1.678 | 1.5065 | 1.5065 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Projected values are based on the average of the last 2 years.
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | 48826 | 231908.4893 | 229287.7074 | 226077.6795 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | 48465 | 317151.1924 | 313527.2054 | 309137.8245 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | Projected values are based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Customer counts decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
4. Community outreach of PSPS metrics | 4.b. | N/A | # of medical baseline customers impacted by PSPS | 3291 | 24586.4934 | 24307.802 | 23967.4928 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | Projected values are based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Customer counts decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
4. Community outreach of PSPS metrics | 4.c. | N/A | # of customers notified prior to initiation of PSPS event | 72293 | 456339.1389 | 451124.695 | 444808.9492 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | Projected values are larger than the number of customers impacted (4a), because it includes additional customers who were notified but not de-energized.
4. Community outreach of PSPS metrics | 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | 4514 | 35054.0358 | 34656.6933 | 34171.4996 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | Projected values are larger than the number of Medical Baseline customers impacted (4b), because it includes additional customers who were notified but not de-energized.
4. Community outreach of PSPS metrics | 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | 48153 | 317151.1924 | 313527.2054 | 309137.8245 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | 3271 | 24586.4934 | 24307.802 | 23967.4928 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | 0 | 1 | 1 | 1 | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | 1961 | 1808.485 | 1808.485 | 1808.485 | Number of customers | Projected value was calculated by summing the total active customers on de-energized circuits for all events in a given quarter, divided by the number of de-energized circuit-events in the same quarter. The list of impacted circuits is based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | 8.86 | 25.1326 | 24.8486 | 24.5007 | =1.c. / RFW OH circuit mile days in time period | Projected values are based on 5-year historical average.
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | 332 | 444.8505 | 439.823 | 433.6655 | =1.c. / HWW OH circuit mile days in time period | Projected values are based on 5-year historical average.
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | 2.23 | 3.2682 | 3.2312 | 3.186 | =1.c. / FPI OH circuit mile days in time period | Projected values are based on 5-year historical average.
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | 28 | 29 | 29 | 29 | Time between de-energization and inspection on a circuit-segment basis in hours | Projected values are calculated based on the time between the start of de-energization due to PSPS, and the start of inspection (defined as the All Clear or Weather End time). Durations are based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Circuit segments are defined based on the device used to de-energize the circuit segment, not based on further sectionalization performed during the restoration process. If a circuit segment has multiple outage start times or All Clear time, the duration for that circuit segment is calculated as the max duration among the customers on that circuit segment.
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | 44 | 46 | 46 | 46 | Time between de-energization and inspection on a circuit-segment basis in hours | Projected values are calculated based on the time between the start of de-energization due to PSPS, and the start of inspection (defined as the All Clear or Weather End time). Durations are based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Circuit segments are defined based on the device used to de-energize the circuit segment, not based on further sectionalization performed during the restoration process. If a circuit segment has multiple outage start times or All Clear time, the duration for that circuit segment is calculated as the max duration among the customers on that circuit segment.
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | 0.5 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | 1.3 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | 15 | 225.0284 | 225.0284 | 225.0284 | Number of risk events | Projected risk events are based on the number of damages and hazards, as reported in post de-energization reports for past PSPS events. The list of events is based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. For lookback events which do not align with a past PSPS event, the number of risk events is approximated using the number of sustained outages which occurred during the hypothetical lookback event scope and duration, filtered to only include the types of outages which would have resulted in a damage or hazard (as reported in post de-energization reports).

## Table 11
Utility | X | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2025-02-03 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actuals |  |  |  | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2024 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Community Outreach and Engagement | Best practice sharing with other utilities |  | N/A - Foundational |  | 2021 | PSPS OII | n/a | In compliance | Customer Care portion: PSPS OII |  |  | 0 | 0 | 2820 | 733 | 0 | 0 | 3496.1115 | 3496.1115 | 0 | 0 | 19394.0333 | 19394.0333 | 0 | 0 | 3709.0247 | 3709.0247
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning |  | N/A - Foundational |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 9573.3873 | 2489.0807 | 0 | 0 | 11834.5776 | 11834.5776 | 0 | 0 | 12491.15 | 12491.15 | 0 | 0 | 12555.3034 | 12555.3034
Community Outreach and Engagement | Engagement with access and functional needs populations |  | N/A - Foundational |  | 2019 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3, GO 166 |  |  | 11170.1588 | 2904.2413 | 4657.0507 | 1210.8332 | 4062.5 | 4062.5 | 23346.5806 | 23346.5806 | 4028.6149 | 4028.6149 | 0 | 0 | 4184.375 | 4184.375 | 16012.978 | 16012.978
Community Outreach and Engagement | Public outreach and education awareness program | CO-01, CO-02, CO-04, CO-05 | N/A - Foundational |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 10433.0755 | 2712.5996 | 0 | 0 | 14931.7992 | 14931.7992 | 0 | 0 | 2149.8507 | 2149.8507 | 0 | 0 | 15841.1458 | 15841.1458
Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | All Consequences |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 2.2679 | 0.58965 | 5824.1657 | 1514.2831 | 187.5 | 187.5 | 14780.0164 | 14780.0164 | 85.8446 | 85.8446 | 9374.7469 | 9374.7469 | 198.9187 | 198.9187 | 15680.1194 | 15680.1194
Emergency Preparedness | Emergency preparedness plan | EP-01 | All Consequences |  | <2018 | 2023 GRC | n/a | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  | 0 | 0 | 11024.5747 | 2866.3894 | 0 | 0 | 4119 | 4119 | 0 | 0 | 1980.966 | 1980.966 | 0 | 0 | 4369.8471 | 4369.8471
Emergency Preparedness | External collaboration and coordination | EP-02, EP-04, EP-06, EP-07, EP-08, EP-09 | All Consequences |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 13727.34 | 3569.1084 | 0 | 0 | 17043.1514 | 17043.1514 | 0 | 0 | 17951.9869 | 17951.9869 | 0 | 0 | 18081.0793 | 18081.0793
Emergency Preparedness | Preparedness and planning for service restoration |  | All Consequences |  | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8700 | 8700 | 0 | 0 | 21148.596 | 21148.596 | 0 | 0 | 9229.83 | 9229.83
Emergency Preparedness | Public emergency communication strategy |  | All Consequences |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 4007.6363 | 1041.9855 | 0 | 0 | 8109.3037 | 8109.3037 | 0 | 0 | 7124.6794 | 7124.6794 | 0 | 0 | 8603.1603 | 8603.1603
Grid Design, Operations, and Maintenance | Asset inpsections | AI-01, AI-02, AI-03, AI-04, AI-05, AI-06, AI-07, AI-08, AI-09, AI-10 | Equipment / facility failure |  | Distribution - 2016 (focused on WMP work) Transmission - 2019 (when WSIP program started in full) Substation - 2019 Wildfire Safety Plan | Distribution - 2023 GRC Transmission - TO Rate Case Substation - 2023 GRC | n/a | Distribution - In compliance with WMP and GO 165 regulations. (Missed Inspections will be tracked and reported to the CPUC) Transmission - Exceeding compliance Substation - Supplemental substation inspections are performed in addition to routine based substation inspections thus exceeding GO 174 compliance. | Distribution - GO 95; GO 165 Transmission - GO 165 IV; GO 95 Rules 18B and 31.2 Substation - GO 174 |  |  | 0 | 0 | 165196.9654 | 83970.9786 | 0 | 0 | 192119.7232 | 91921.1166 | 0 | 0 | 140669.967 | 61570.522 | 0 | 0 | 192064 | 89100.2641
Grid Design, Operations, and Maintenance | Asset managmenet and inspection enterprise system(s) | AI-11 | N/A - Foundational | N/A - Foundational | n/a | n/a | n/a | n/a | n/a | Wildfire technology costs are aggregated in financials for "Other - Wildfire" |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | Wildfire technology costs are aggregated in financials for "Other - Wildfire"
Grid Design, Operations, and Maintenance | Covered conductor installation | GH-01, GH-02, GH-03 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC | n/a | In Compliance | TD-9001M CH 15 “Fire Area Design Guidance” in addition to all relevant standards; All projects in HFTD/HFRA/Buffer Zones |  |  | 134200.8977 | 134200.8977 | 0 | 0 | 67504.2203 | 67504.2203 | 0 | 0 | 134201 | 134201 | 0 | 0 | 248940 | 248940 | 0 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | Equipment / facility failure |  | <2018 | 2023 GRC | n/a | Not in compliance - due to the backlog of poles to be replaced and reinforced; but have plan to reduce backlog | GO 95 Rule 18 |  |  | 573290.7243 | 337717.1649 | 0 | 0 | 266489.6043 | 218852.845 | 5809.3098 | 0 | 433063.5536 | 251975.6874 | 0 | 0 | 930131.0725 | 853248.4118 | 6163.0968 | 0
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots |  | Equipment / facility failure |  | 2020 | 2022 WMP | n/a | not in compliance – we have non-exempt fuse equipment installed in fire areas. | Cal Fire Power Line Fire Prevention Field Guide establishes what is classified as non-exempt. TD-9100P-09 is the estimating standard for equipment in fire areas that references the above guide. |  |  | 227.9314 | 227.9314 | 730.0178 | 730.0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Equipment inspections, maintenance, and repair |  | Equipment / facility failure |  | - Distribution < 2018 - Transmission < 2018 - Substation - Circuit Breaker Maintenance and Installation initiative was introduced in the 2020 WMP. | - Distribution and Substation: 2023 GRC - Transmission: TO Rate Case | n/a | - Distribution - Not currently in compliance. Refer to Section 8.1.7.2 and associated target in 8.1.1.X GM-10 for information regarding transmission maintenance notifications. - Transmission - Not currently in compliance. Refer to Section 8.1.7.1 and associated target in 8.1.1.2 GM-09 for information regarding transmission maintenance notifications. - Substation - In Compliance with regulations | - Distribution - GO 95 Rule 18 - Transmission - GO 95 Rule 18 - Substation – CPUC General Order 174; WECC-FAC-501 |  |  | 849496.9028 | 403898.8051 | 242486.1252 | 147739.0266 | 949901.4699 | 455039.1133 | 200297.1813 | 75645.0114 | 798766.5998 | 420176.8267 | 263401.9675 | 258525.4905 | 963794.9437 | 458020.1763 | 331254.6659 | 210742.703
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops) | GM-07 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC | n/a | n/a | n/a |  |  | 46533.1515 | 46533.1515 | 73225.3812 | 67272.4672 | 42108.7201 | 42108.7201 | 133428.7944 | 133428.7944 | 86716.0392 | 86716.0392 | 95319.9248 | 95319.9248 | 71879 | 71879 | 121892 | 121892
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops) |  | N/A - Foundational | N/A - Foundational | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | Refer to 8.1.8.1 where EPSS financials are aggregated, also 8.1.8.2 Inspections |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | Refer to 8.1.8.1 where EPSS financials are aggregated, also 8.1.8.2 Inspections
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GH-07 | N/A - Foundational | N/A - Foundational | 2019 | 2023 GRC | n/a | n/a | n/a |  |  | 3398.4201 | 3398.4201 | 0 | 0 | 12759.2 | 12759.2 | 0 | 0 | 6907.369 | 6907.369 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Line removals (in HFTD) |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution - 2019 Transmission < 2018 | Distribution - 2023 GRC Transmission - Res.SED 6 | n/a | Distribution - In Compliance Transmission - In Compliance | Distribution: De-energization and removal of OH conductor in HFTD/HFRA; Utility Procedure: TD-2459P-01 “Idle Facility Program” Transmission: GO-95 rule 31.6 |  |  | 21622.4838 | 21622.4838 | 0 | 0 | 64023.161 | 21568.0233 | 0 | 0 | 15700 | 15700 | 0 | 0 | 21238 | 21238 | 0 | 0
Grid Design, Operations, and Maintenance | Microgrids |  | Consequence - PSPS |  | 2019 - Dist. Micro, CMEP, MIP, Clean Substation 2019 - Remote Grid | - Dist. Micro, CMEP, MIP, Clean Substation: Microgrid OIR, 2020 GRC, EPIC 3 - Remote Grid: 2023 GRC | - CMEP, MIP, Clean Substation: MGMA/MGBA - Remote Grid: n/a | - Dist. Micro, CMEP, MIP, Clean Substation: In compliance - Remote Grid: in compliance with required filing (Resolution E-5132) | n/a |  |  | 3094.5316 | 2266.936 | 7017.2759 | 5324.4245 | 6060.2315 | 6060.2315 | 8338.2782 | 8338.2782 | 8629.732 | 8629.732 | 8966.0275 | 8966.0275 | 6008.213 | 6008.213 | 38299.4646 | 38299.4646
Grid Design, Operations, and Maintenance | Open work orders | GM-02, GM-03, GM-08 | Equipment / facility failure |  | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | Most of the costs related to "Open Work Orders" are mapped to Maintenance section 8.1.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3180.6093 | 3180.6093 | 0 | 0 | 1489.431 | 1489.431 | 0 | 0 | 3374.3084 | 3374.3084
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | GH-08, GH-09, GH-10, GM-06 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC | n/a | Non-Exempt Expulsion Fuse Replacement portion - not in compliance, we have non-exempt fuse equipment installed in fire areas. | Non-Exempt Expulsion Fuse Replacement portion - Cal Fire Power Line Fire Prevention Field Guide establishes what is classified as non-exempt; TD-9100P-09 is the estimating standard for equipment in fire areas that references the above guide. |  |  | 43106.8621 | 43106.8621 | 0 | 0 | 40081.5684 | 40081.5684 | 0 | 0 | 31434.8513 | 31434.8513 | 0 | 0 | 21928.7323 | 21928.7323 | 0 | 0
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events |  | Consequence - PSPS |  | - Distribution - 2019 - Transmission - 2019/2020 | -Distribution - 2023 GRC - Transmission - TO Rate Case | n/a | - Distribution - In compliance per WMP commitments for replacements - Transmission - n/a | n/a |  |  | 0 | 0 | 0 | 0 | 1455.9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544.5667 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | Contact from object |  | Pertaining to Substation Animal Abatement: 2019 – Wildfire Safety Plan | Pertaining to Substation Animal Abatement: 2023 GRC | n/a | Pertaining to Substation Animal Abatement: Exceeds minimum substation maintenance and inspection requirements within GO 174 | Pertaining to Substation Animal Abatement: GO 174 |  |  | 6449.6891 | 2940.8499 | 4684.9424 | 1995.7247 | 0 | 0 | 1024.1647 | 764.1681 | 0 | 0 | 1054.8896 | 787.0931 | 0 | 0 | 1086.5363 | 810.7059
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) |  | N/A - Foundational | N/A - Foundational | <2018 | 2022 WMP | n/a | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 | General Operations |  | 224.028 | 58.2473 | 20667.55 | 5373.563 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | General Operations
Grid Design, Operations, and Maintenance | Quality assurance / quality control | GM-01, GM-09 | N/A - Foundational | N/A - Foundational | 2020 | 2023 GRC, 2022 WMP | n/a | In Compliance | GO 95 GO 128 GO 165 |  |  | 0 | 0 | 39486.3664 | 35690.3921 | 0 | 0 | 33808.8626 | 32977.9224 | 0 | 0 | 24119 | 24119 | 0 | 0 | 57475 | 57475
Grid Design, Operations, and Maintenance | Traditional overhead hardening | GH-05, GH-06, GH-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution - refer to Maintenance program in 8.1.4 Transmission before 2018 | Distribution - refer to Maintenance program in 8.1.4 Transmission - TO rate case | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution costs covered in the Maintenance programs, under 8.1.4 |  | 4042.3191 | 4042.3191 | 0 | 0 | 19134.1732 | 19134.1732 | 0 | 0 | 4900.0001 | 4900.0001 | 0 | 0 | 66538 | 66538 | 0 | 0
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements |  | Equipment / facility failure |  | <2018 | TO Rate Case | n/a | Refer to section 8.1.7.1 and associated target 8.1.1.2 GM-09 for information regarding transmission maintenance notifications. | GO 95 Rule 18 |  |  | 163814.3476 | 130677.1287 | 104042.1448 | 62655.3757 | 90847.6275 | 18447.657 | 91279.8781 | 8572.9218 | 72700 | 14762.5722 | 106659 | 10941.1162 | 96380.248 | 19571.1193 | 105326.0227 | 10804.3789
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | GH-04 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC | n/a | In Compliance | UG Design and Construction Standards; All projects in HFTD/HFRA/Buffer Zones |  |  | 999783.17 | 978748.8232 | 0 | 0 | 1175307.5973 | 1146057.5973 | 0 | 0 | 999783 | 978749 | 0 | 0 | 1215322 | 1209322 | 0 | 0
Grid Design, Operations, and Maintenance | Workforce Planning |  | N/A - Foundational | N/A - Foundational | <2018 | 2023 GRC | n/a | n/a - support function | n/a - support function | General Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overview of the Service Territory | Environmental compliance and permitting |  | N/A - Foundational | N/A - Foundational | <2018 | 2023 GRC | n/a | In Compliance | n/a - governed by various state, federal, local legislation | General Operations - costs are allocated to projects across the company when mitigations happen; so costs are already embedded in various programs and MWCs/MATs |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | General Operations - costs are allocated to projects across the company when mitigations happen; so costs are already embedded in various programs and MWCs/MATs
Risk Methodology and Assessment | Risk Methodology and Assessment |  | N/A - Foundational | N/A - Foundational | 2019 | 2022 WMP | n/a | Risk models - in compliance | n/a |  |  | 8413.1727 | 2187.4249 | 0 | 0 | 10750 | 3325.6654 | 0 | 0 | 7320.602 | 2264.7324 | 0 | 0 | 11404.675 | 3528.1984 | 0 | 0
Situational Awareness and Forecasting | Environmental monitoring systems | SA-01, SA-07, SA-08, SA-12 | N/A - Foundational | N/A - Foundational | 2018 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 1939.0494 | 1939.0494 | 2579.2281 | 2579.2281 | 3286.1036 | 3286.1036 | 3126.5412 | 3126.5412 | 1494.9857 | 1494.9857 | 3528.0021 | 3528.0021 | 3486.2274 | 3486.2274 | 3316.9476 | 3316.9476
Situational Awareness and Forecasting | Fire potential index |  | N/A - Foundational | N/A - Foundational | 2015 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 0 | 0 | 109.6274 | 109.6274 | 0 | 0 | 150.4726 | 150.4726 | 0 | 0 | 172 | 172 | 0 | 0 | 159.6363 | 159.6363
Situational Awareness and Forecasting | Grid monitoring systems | SA-02, SA-03, SA-09, SA-10, SA-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC | n/a | n/a | GO 95 |  |  | 6918.7213 | 6918.7213 | 2091.6296 | 2091.6296 | 8398.159 | 8398.159 | 3329.768 | 3329.768 | 12462.9994 | 12462.9994 | 2288.9131 | 2288.9131 | 10394.8668 | 10394.8668 | 3532.5509 | 3532.5509
Situational Awareness and Forecasting | Ignition detection systems |  | N/A - Foundational | N/A - Foundational | 2017 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 0.00012 | 0.00012 | 23219.5947 | 11419.4232 | 0 | 0 | 15324.18 | 15324.18 | 0 | 0 | 18929.0996 | 18929.0996 | 0 | 0 | 16257.4226 | 16257.4226
Situational Awareness and Forecasting | Weather forecasting | SA-04, SA-05, SA-06 | N/A - Foundational | N/A - Foundational | 2014 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 2609.191 | 2609.191 | 2290.423 | 2290.423 | 0 | 0 | 1976.0114 | 1976.0114 | 0 | 0 | 171.996 | 171.996 | 0 | 0 | 2096.3505 | 2096.3505
Vegetation Management and Inspection | Clearance |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | refer to 8.2.3.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Emergency response vegetation management |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | Vegetation Management Priority Tag Procedure (TD-7102P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  | 0 | 0 | 3033.3215 | 1089.4362 | 0 | 0 | 13000 | 7577.6 | 0 | 0 | 3528 | 2056.4441 | 0 | 0 | 12072.0546 | 7036.7078
Vegetation Management and Inspection | Fall-in mitigation |  | Vegetation Contact |  | 2023 | n/a | n/a | n/a | GO 95 Rule 35; PRC 4292; PRC 4293 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 123997 | 123997 | 0 | 0 | 309050 | 306178.9561 | 0 | 0 | 72540 | 72540
Vegetation Management and Inspection | Fire-resillient right-of-ways |  | Vegetation Contact |  | <2018 | TO Rate Case | n/a | In compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO); ANSI A300 (Part 7)-2018 Integrated Vegetation Management; State, county, and city weed abatement ordinances |  |  | 0 | 0 | 9164.3933 | 4416.3211 | 0 | 0 | 15553.158 | 15553.158 | 0 | 0 | 14577 | 14577 | 0 | 0 | 12680 | 12680
Vegetation Management and Inspection | High-risk species |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Open work orders | VM-09 | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489.431 | 1489.431 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Pole clearing | VM-02 | Vegetation Contact |  | <2018, 2021 | 2023 GRC, 2022 WMP | n/a | In compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  | 0 | 0 | 68512.3599 | 53929.184 | 0 | 0 | 31000 | 17049.5 | 0 | 0 | 28803 | 17574.7792 | 0 | 0 | 28787.2071 | 15832.4996
Vegetation Management and Inspection | Quality assurance / quality control | VM-08, VM-22 | N/A - Foundational | N/A - Foundational | <2018, 2019, 2021 | 2023 GRC, 2022 WMP | n/a | n/a | n/a |  |  | 0 | 0 | 53242.6456 | 42971.1978 | 0 | 0 | 49251 | 35187.2867 | 0 | 0 | 48654 | 48654 | 0 | 0 | 79481.4404 | 57427.5272
Vegetation Management and Inspection | Substation defensible space | VM-05, VM-06, VM-07 | Vegetation Contact |  | 2019 | 2023 GRC, 2022 WMP | n/a | In compliance | California PRC 4291; Substation Defensible Space Procedure LAND-4001P-01 |  |  | 0 | 0 | 4997.3752 | 4967.1713 | 0 | 0 | 4836.0004 | 4836.0004 | 0 | 0 | 5699.165 | 5699.165 | 0 | 0 | 3488 | 3488
Vegetation Management and Inspection | Vegetation management enterprise system | VM-12, VM-19, VM-20 | N/A - Foundational | N/A - Foundational | 2021 | 2023 GRC, 2022 WMP | n/a | n/a | n/a |  |  | 0 | 0 | 29511.717 | 7673.0464 | 0 | 0 | 38798 | 38798 | 0 | 0 | 27000 | 27000 | 0 | 0 | 16715.1525 | 16715.1525
Vegetation Management and Inspection | Wood and slash management |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | Best Management Practices (BMP) for Vegetation Management Activities (TD-7102P-01-JA01); Wood Management (TD-7102P-26) |  |  | 0 | 0 | 45596.1641 | 44023.0965 | 0 | 0 | 80400 | 79889.9338 | 0 | 0 | 79820.788 | 79022.5801 | 0 | 0 | 97690.7802 | 97071.0195
Vegetation Management and Inspection | Workforce Planning |  | N/A - Foundational | N/A - Foundational | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development |  | N/A - Foundational | All Drivers, All Consequences | n/a | n/a | n/a | n/a | n/a | cost partially in Section 6 - Risk Methodology and Assessment |  | 0 | 0 | 24023.5238 | 24023.5238 | [12 empty] | Cost partially in Section 6 - Risk Methodology and Assessment
Vegetation Management and Inspection | Vegetation Inspections - Distribution | VM-03, VM-04, VM-11, VM-16, VM-17, VM-18, VM-21 | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | GO 95 Rule 35; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23) |  |  | 0 | 0 | 1120994.9104 | 637789.385 | 0 | 0 | 795246 | 432220.4341 | 0 | 0 | 824370.7808 | 383183.3469 | 0 | 0 | 1134772 | 616754.6224
Vegetation Management and Inspection | Vegetation Inspections - Substation |  | Vegetation Contact |  | Substation - 2019 Wildfire Safety Plan | Substation - 2023 GRC | N/A | Substation – Defensible Space inspections and mitigation are performed in addition to routine and supplemental based substation inspections thus exceeding GO 174 compliance. | Substation - GO 174 |  |  | 0 | 0 | 980.8647 | 980.865 | 0 | 0 | 3356.6698 | 3356.6698 | 0 | 0 | 3457.3699 | 3457.3699 | 0 | 0 | 3561.091 | 3561.091
Vegetation Management and Inspection | Vegetation Inspections - Transmission | VM-01, VM-13, VM-14, VM-15 | Vegetation Contact |  | <2018 | TO Rate Case | n/a | In compliance | "NERC Standard FAC-003-04; GO 95 Rule 35; PRC 4292; PRC 4293; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01)" |  |  | 0 | 0 | 35280.09 | 13691.8225 | 0 | 0 | 35443.09 | 35443.09 | 0 | 0 | 33492.839 | 33492.839 | 0 | 0 | 100319 | 100319
Other | Other - Wildfire |  | N/A - Foundational | N/A - Foundational | n/a - this section supports projects and programs | 2023 GRC for Wildfire Technology | n/a | n/a - this section are support projects and programs | n/a - this section are support projects and programs |  |  | 58512.9031 | 53129.2531 | 81675.0309 | 67748.383 | 109538.4214 | 109538.4214 | 115625.5227 | 115625.5227 | 39312.5758 | 35228.9665 | 138440.1748 | 132569.0677 | 124660.1233 | 124660.1233 | 121973.457 | 121973.457
PSPS | Other - PSPS | PS-01, PS-02, PS-05, PS-06, PS-07, PS-08, PS-09, PS-10, PS-11 | Consequence - PSPS | No other consequences reflected | 2018 – PSPS program initiated | 2023 GRC and 2022 WMCE | n/a | In compliance | R.18-12-005 |  |  | 2695.9433 | 700.9454 | 74719.8455 | 72962.7217 | 3963.1799 | 3963.1799 | 93112.0087 | 93112.0087 | 2827.2911 | 2827.2911 | 89183.3297 | 89183.3297 | 2953 | 2953 | 90070 | 90070

## Table 12
Utility | X | Notes:
Table No. | 12
Date Modified | 2024-11-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | Method of Verification | Comments
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Ground | AI-02 | Quantitative | Transmission Structures | 18000 | 27000 | 27000 | 12000 | 20000 | 20000 | 13200 | 22000 | 22000 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Aerial | AI-04 | Quantitative | Transmission Structures | 17000 | 24000 | 24000 | 17000 | 20000 | 20000 | 13000 | 19000 | 19000 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Climbing | AI-05 | Quantitative | Transmission Structures | 1200 | 1700 | 1700 | 900 | 1200 | 1200 | 900 | 1200 | 1200 | Completed work orders
Grid Design, Operations and Maintenance | Perform transmission infrared inspections | AI-06 | Quantitative | Miles | 1500 | 3000 | 4000 | 1500 | 3000 | 4000 | 1000 | 2500 | 3500 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspections - Distribution | AI-07 | Quantitative | Distribution Poles | 30000 | 72532 | 234648 | 70000 | 150000 | 220016 | 109000 | 190000 | 244000 | Completed work orders
Grid Design, Operations and Maintenance | Supplemental Inspections - Substation Distribution | AI-08 | Quantitative | Distribution Substations | 46 | 52 | 52 | 68 | 76 | 76 | 71 | 78 | 78 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Grid Design, Operations and Maintenance | Supplemental Inspections - Substation Transmission | AI-09 | Quantitative | Transmission Substations | 31 | 34 | 34 | 33 | 36 | 36 | 38 | 41 | 41 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Grid Design, Operations and Maintenance | Supplemental Inspections - Hydroelectric Substations and Powerhouses | AI-10 | Quantitative | Hydroelectric Substations and Powerhouses | 41 | 41 | 41 | 45 | 46 | 46 | 37 | 40 | 40 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared | Tule River sub sold to SCE
Community Outreach and Engagement | Community Engagement - Surveys | CO-02 | Quantitative | Surveys | 1 | 1 | 2 | 1 | 1 | 2 |  |  | 2 | Survey results and analyses.
Emergency Preparedness Plan | Emergency Planning | EP-06 | Quantitative | 1 CERP and 2 wildfire related annexes |  |  | 3 |  |  | 3 |  |  | 3 | 1 CERP and 2 wildfire related annexes
Grid Design, Operations and Maintenance | Covered conductor installation | GH-01 | Quantitative | Circuit Miles |  |  | 420 |  |  | 280 |  |  | 520 | Post-construction projects, use as-built job package and Fire Safe Spans Inspection report (QA report from I-Auditor). In-construction projects, use design construction drawing and Fire Safe Spans Inspection report (QA report from I-Auditor).
Grid Design, Operations and Maintenance | Undergrounding of electric lines and/or equipment | GH-04 | Quantitative | Circuit Miles |  |  | 350 |  |  | 250 |  |  | 330 | Post-construction projects, use as-built job package and Fire Safe Spans Inspection report (QA report from I-Auditor). In-construction projects, use design construction drawing and Fire Safe Spans Inspection report (QA report from I-Auditor).
Grid Design, Operations and Maintenance | Traditional overhead hardening - Transmission | GH-05 | Quantitative | Circuit Miles |  |  | 43 |  |  | 0 |  |  | 5 | As-built job package.
Grid Design, Operations and Maintenance | Traditional overhead hardening - Transmission | GH-06 | Quantitative | Transmission Lines |  |  | 20 |  |  | 22 |  |  | 25 | As-built job package
Grid Design, Operations and Maintenance | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Quantitative | Distribution Sectionalizing Devices |  |  | 75 |  |  | N/A |  |  | N/A | Completed work orders
Grid Design, Operations and Maintenance | Other grid topology improvements to minimize risk of ignitions | GH-08 | Quantitative | Surge Arrestors |  |  | 663 |  |  | N/A |  |  | N/A | Completed work orders
Grid Design, Operations and Maintenance | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Quantitative | MSOs replacements |  |  | 20 |  |  | 26 |  |  | N/A | As-built job package
Grid Design, Operations and Maintenance | Non-Exempt Expulsion Fuses | GH-10 | Quantitative | Fuses |  |  | 3000 |  |  | 3000 |  |  | 1400 | Completed work orders
Grid Design, Operations and Maintenance | System Hardening – Transmission Conductor Segment Replacement | GH-11 | Quantitative | Transmission Lines |  |  | N/A |  |  | N/A |  |  | 2 | As-built job package
Grid Design, Operations and Maintenance | Asset Inspections - Quality Assurance | GM-01 | Quantitative | Pass Rate |  |  | Transmission 90% Distribution 80% |  |  | Transmission 94% Distribution 90% |  |  | Transmission 95% Distribution 95% | Final reports and field guides for all audits.
Grid Design, Operations and Maintenance | Open Work Orders - Transmission | GM-02 | Quantitative | Transmission LC Tags |  |  | 16831 |  |  | N/A |  |  | N/A | Completed notifications
Grid Design, Operations and Maintenance | Open Work Orders - Distribution | GM-03 | Quantitative | Percent Risk Reduction |  |  | 48% |  |  | 68% |  |  | 77% | Completed notifications | Note Table 1 shows quarterly EC distribution tags.
Grid Design, Operations and Maintenance | Protective Equipment and Device Settings | GM-06 | Quantitative | Protective Device Controllers or Relays that are DCD capable |  |  | 500 |  |  | 400 |  |  | 250 | Report with the number of protective device controllers or relays that were DCD capable
Grid Design, Operations and Maintenance | Asset Inspections - Quality Control | GM-09 | Quantitative | Pass Rate |  |  | Transmission 90% Distribution 80% |  |  | Transmission 92% Distribution 88% |  |  | Transmission 95% Distribution 95% | Final reports and field guides for all audits.
Public Safety Power Shutuff | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Quantitative | # of batteries |  |  | 4000 |  |  | 4000 |  |  | 3300 | Received waiver from customer. Contractor provided monthly log of deliveries with Account number.
Public Safety Power Shutuff | Performance Metrics Identified by the Electrical Corporation | PS-07 | Quantitative | # of Customer events |  |  | 15000 |  |  | 9980 |  |  | 13000 | Customer event reductions as measured by the static 5 year look back impacted by PSPS
Situational Awareness and Forecasting | Planned Improvements | SA-02 | Quantitative | Circuits |  |  | 40 |  |  | 40 |  |  | 40 | Completed job packages
Situational Awareness and Forecasting | Distribution Fault Anticipation (DFA) Installations | SA-10 | Quantitative | DFA Sensors |  |  | 5 |  |  | 15 |  |  | 15 | Report demonstrating the first communication between the sensor and the Headend software.
Situational Awareness and Forecasting | Early Fault Detection (EFD) Installations | SA-11 | Quantitative | EFD circuits |  |  | 2 |  |  | 2 |  |  | 4 | SAP report with notification completion date, circuit name, and location.
Vegetation Management and Inspection | LiDAR Routine Inspections - Transmission | VM-01 | Quantitative | Circuit Miles | 17500 | 17500 | 17500 | 16000 | 17000 | 17500 | 16000 | 17000 | 17500 | LiDAR Contractor Work Complete Attestation - (Vegetation Management Project Management Database). Data is uploaded to VMPI2 mobile device for Pre-Inspectors
Vegetation Management and Inspection | Pole Clearing Program | VM-02 | Quantitative | Distribution poles | 57750 | 77503 | 77503 | 47250 | 63000 | 63000 | 39000 | 52000 | 52000 | List of all poles in VM database as of October 1, 2022. (PCD2 App) All exceptions must be accordingly documented in the system of record
Vegetation Management and Inspection | Focused Tree Inspection (FTI) | VM-03 | Quantitative | Circuit Miles | 0 | 0 | 250 | 300 | 1050 | 1500 | 300 | 1050 | 1500 | QC Survey on all miles inspected
Vegetation Management and Inspection | Fall-in Mitigation | VM-04 | Quantitative | Trees Removed | 910 | 7310 | 15000 | 6200 | 14000 | 20000 | 5000 | 17500 | 25000 | Completed work orders
Vegetation Management and Inspection | Defensible Space Inspections - Distribution Substation | VM-05 | Quantitative | Distribution Substations | 130 | 131 | 131 | 130 | 131 | 131 | 124 | 131 | 131 | Preventative Notification numbers for each defensible space inspection
Vegetation Management and Inspection | Defensible Space Inspections - Transmission Substation | VM-06 | Quantitative | Transmission Substations | 55 | 55 | 55 | 55 | 55 | 55 | 49 | 54 | 55 | Preventative Notification numbers for each defensible space inspection | 2024 End of the year target is going to be 54. Please see Table 1 for additional details
Vegetation Management and Inspection | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | VM-07 | Quantitative | Hydroelectric Substations and Powerhouses | 61 | 61 | 61 | 61 | 61 | 61 | 48 | 59 | 61 | Preventative Notification numbers for each defensible space inspection | 2024 End of the year target is going to be 59. Please see Table 1 for additional details
Vegetation Management and Inspection | Quality Assurance / Quality Control | VM-08 | Quantitative | % Pass Rate |  |  | 95% |  |  | 95% |  |  | 95% | QV VM final reports
Vegetation Management and Inspection | Routine Ground - Transmission | VM-13 | Quantitative | Circuit Miles | 16396 | 17738 | 17740 | 9000 | 16000 | 17740 | 16396 | 17738 | 17740 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Transmission Second Patrol | VM-14 | Quantitative | Circuit Miles | 0 | 0 | 5625 | 0 | 0 | 5625 | 0 | 0 | 5625 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Integrated Vegetation Management - Transmission | VM-15 | Quantitative | Acres | 11151 | 11194 | 11194 | 2590 | 5690 | 6504 | 2500 | 5000 | 6504 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Distribution Routine Patrol | VM-16 | Quantitative | Circuit Miles | 41761 | 61806 | 79000 | 31460 | 51123 | 78650 | 31280 | 50830 | 78200 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Distribution Second Patrol | VM-17 | Quantitative | Circuit Miles | 18904 | 30952 | 43000 | 10274 | 16695 | 25685 | 10274 | 16695 | 25685 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | VM for Operational Mitigations (VMOM) | VM-18 | Quantitative | Trees | N/A | N/A | N/A | 3000 | 5000 | 6500 | 3000 | 5000 | 6500 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Vegetation Management - Quality Control | VM-22 | Quantitative | % Pass Rate |  |  | VM Distribution Routine 80% VM Transmission 88% VM Pole Clearing 80% |  |  | VM Distribution Routine 88% VM Transmission 92% VM Pole Clearing 88% |  |  | VM Distribution Routine 95% VM Transmission 95% VM Pole Clearing 95% | QC VM final reports

## Table 13
Utility | X |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2025-02-03
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
115600709 | pole | HFTD Tier 2 | Transmission | 2018-12-27 | 2020-12-27 | Level 3 | F | 2024-01-30 | 2023-12-27 | Level 3 | GO 165 Inspection
115600737 | pole | HFTD Tier 2 | Transmission | 2018-12-27 | 2020-12-27 | Level 3 | F | 2024-01-30 | 2023-12-27 | Level 3 | GO 165 Inspection
115683929 | other | Non-HFTD | Transmission | 2019-01-14 | 2021-01-14 | Level 3 | F | 2024-11-15 | 2024-01-14 | Level 3 | GO 165 Inspection
115713224 | pole | HFTD Tier 2 | Transmission | 2019-01-22 | 2020-01-22 | Level 2 | E | 2024-03-21 | 2024-01-22 | Level 3 | GO 165 Inspection
115714806 | other | Non-HFTD | Transmission | 2019-01-22 | 2020-01-22 | Level 3 | F |  | 2024-01-22 | Level 3
115721351 | pole | Non-HFTD | Transmission | 2019-01-23 | 2020-01-23 | Level 2 | E | 2024-11-15 | 2022-01-23 | Level 2 | Field Safety Reassessment
115735408 | other | Non-HFTD | Transmission | 2019-01-24 | 2021-01-24 | Level 3 | F | 2024-11-16 | 2024-01-24 | Level 3 | GO 165 Inspection
115755141 | pole | HFTD Tier 2 | Transmission | 2019-01-26 | 2020-01-26 | Level 2 | E | 2024-03-19 | 2024-01-26 | Level 3 | GO 165 Inspection
115785909 | other | Non-HFTD | Transmission | 2019-02-04 | 2021-02-04 | Level 3 | F | 2024-11-13 | 2024-02-04 | Level 3 | GO 165 Inspection
116471084 | pole | HFTD Tier 2 | Transmission | 2019-02-11 | 2021-02-11 | Level 3 | F | 2024-03-21 | 2024-02-11 | Level 3 | GO 165 Inspection
116475931 | pole | HFTD Tier 2 | Transmission | 2019-02-12 | 2021-02-12 | Level 3 | F | 2024-07-18 | 2024-02-12 | Level 3 | Field Safety Reassessment
116481187 | pole | HFTD Tier 2 | Transmission | 2019-02-12 | 2021-02-12 | Level 3 | F | 2024-03-21 | 2024-02-12 | Level 3 | GO 165 Inspection
116493267 | pole | HFTD Tier 2 | Transmission | 2019-02-15 | 2021-02-15 | Level 3 | F | 2024-03-26 | 2024-02-15 | Level 3 | GO 165 Inspection
116495826 | pole | HFTD Tier 2 | Transmission | 2019-02-15 | 2021-02-15 | Level 3 | F | 2024-03-18 | 2024-02-15 | Level 3 | GO 165 Inspection
116496409 | pole | HFTD Tier 2 | Transmission | 2019-02-16 | 2020-02-16 | Level 3 | F | 2023-03-01 | 2020-02-16 | Level 2 | Standards change
116618670 | pole | HFTD Tier 2 | Transmission | 2019-02-28 | 2021-02-28 | Level 3 | F | 2024-03-28 | 2024-02-28 | Level 3 | GO 165 Inspection
116632473 | other | Non-HFTD | Transmission | 2019-03-04 | 2021-03-04 | Level 3 | F | 2024-04-06 | 2024-03-04 | Level 3 | Standards change
116683867 | pole | HFTD Tier 2 | Transmission | 2019-03-07 | 2021-03-07 | Level 3 | F | 2024-03-11 | 2024-03-07 | Level 3 | GO 165 Inspection
116690568 | pole | HFTD Tier 2 | Transmission | 2019-03-07 | 2021-03-07 | Level 3 | F | 2024-05-10 | 2024-03-07 | Level 3 | GO 165 Inspection
116710636 | pole | Non-HFTD | Transmission | 2019-03-11 | 2021-03-11 | Level 3 | F | 2024-03-27 | 2024-03-11 | Level 3 | GO 165 Inspection
116714027 | pole | HFTD Tier 2 | Transmission | 2019-03-08 | 2020-03-08 | Level 3 | F | 2024-03-27 | 2020-03-08 | Level 2 | GO 165 Inspection
116715725 | pole | HFTD Tier 2 | Transmission | 2019-03-11 | 2020-03-11 | Level 2 | E | 2024-03-22 | 2020-03-11 | Level 2 | GO 165 Inspection
116723421 | pole | HFTD Tier 2 | Transmission | 2019-03-13 | 2021-03-13 | Level 3 | F | 2024-05-16 | 2024-03-13 | Level 3 | GO 165 Inspection
116744579 | pole | HFTD Tier 2 | Transmission | 2019-01-22 | 2021-01-22 | Level 3 | F | 2023-02-28 | 2024-01-22 | Level 3 | Standards change
116744660 | pole | HFTD Tier 2 | Transmission | 2019-01-25 | 2021-01-25 | Level 3 | F | 2024-05-30 | 2024-01-25 | Level 3 | GO 165 Inspection
116744866 | pole | Non-HFTD | Transmission | 2019-01-31 | 2021-01-31 | Level 3 | F | 2024-08-27 | 2024-01-31 | Level 3 | GO 165 Inspection
116744882 | pole | HFTD Tier 3 | Transmission | 2019-01-31 | 2021-01-31 | Level 3 | F | 2024-04-24 | 2024-01-31 | Level 3 | GO 165 Inspection
116744883 | pole | Non-HFTD | Transmission | 2019-01-31 | 2021-01-31 | Level 3 | F | 2024-12-30 | 2024-01-31 | Level 3 | Field Safety Reassessment
116744898 | pole | HFTD Tier 3 | Transmission | 2019-01-31 | 2021-01-31 | Level 3 | F | 2024-05-21 | 2024-01-31 | Level 3 | GO 165 Inspection
116744919 | pole | Non-HFTD | Transmission | 2019-02-01 | 2021-02-01 | Level 3 | F | 2024-12-13 | 2024-02-01 | Level 3 | Field Safety Reassessment
116744920 | pole | Non-HFTD | Transmission | 2019-02-01 | 2021-02-01 | Level 3 | F | 2024-12-13 | 2024-02-01 | Level 3 | Field Safety Reassessment
116744926 | pole | Non-HFTD | Transmission | 2019-02-01 | 2021-02-01 | Level 3 | F | 2024-12-13 | 2024-02-01 | Level 3 | Field Safety Reassessment
116744929 | pole | Non-HFTD | Transmission | 2019-02-01 | 2021-02-01 | Level 3 | F | 2024-12-18 | 2024-02-01 | Level 3 | Field Safety Reassessment
116744930 | pole | Non-HFTD | Transmission | 2019-02-01 | 2021-02-01 | Level 3 | F | 2024-12-13 | 2024-02-01 | Level 3 | Field Safety Reassessment
116744979 | pole | HFTD Tier 2 | Transmission | 2019-02-05 | 2021-02-05 | Level 3 | F | 2024-03-13 | 2024-02-05 | Level 3 | GO 165 Inspection
116745003 | pole | HFTD Tier 2 | Transmission | 2019-02-05 | 2020-02-05 | Level 2 | E | 2024-03-14 | 2024-02-05 | Level 3 | GO 165 Inspection
116817152 | pole | HFTD Tier 2 | Transmission | 2019-03-22 | 2021-03-22 | Level 3 | F | 2024-04-09 | 2024-03-22 | Level 3 | GO 165 Inspection
116982050 | pole | HFTD Tier 2 | Transmission | 2019-04-05 | 2021-04-05 | Level 3 | F | 2024-04-25 | 2024-04-05 | Level 3 | GO 165 Inspection
117007708 | pole | HFTD Tier 2 | Transmission | 2019-04-10 | 2020-04-10 | Level 2 | E | 2024-05-13 | 2024-04-10 | Level 3 | GO 165 Inspection
117023349 | other | HFTD Tier 2 | Transmission | 2019-04-11 | 2021-04-11 | Level 3 | F | 2024-06-06 | 2024-04-11 | Level 3 | GO 165 Inspection
117030406 | pole | HFTD Tier 2 | Transmission | 2019-04-03 | 2021-04-03 | Level 3 | F | 2024-04-06 | 2024-04-03 | Level 3 | GO 165 Inspection
117062899 | other | Non-HFTD | Transmission | 2019-04-15 | 2021-04-15 | Level 3 | F | 2024-04-06 | 2024-04-15 | Level 3 | Standards change
117114584 | pole | HFTD Tier 2 | Transmission | 2019-04-09 | 2021-04-09 | Level 3 | F | 2024-04-06 | 2024-04-09 | Level 3 | GO 165 Inspection
117130652 | pole | Non-HFTD | Transmission | 2019-04-30 | 2020-04-30 | Level 2 | E | 2024-03-22 | 2022-04-30 | Level 2 | Standards change
117213514 | anchor/guy | Non-HFTD | Transmission | 2019-04-29 | 2020-04-29 | Level 2 | E |  | 2020-04-29 | Level 2
117222638 | pole | HFTD Tier 2 | Transmission | 2019-04-22 | 2021-04-22 | Level 3 | F | 2024-04-29 | 2024-04-22 | Level 3 | GO 165 Inspection
117258629 | insulator and brushing | Non-HFTD | Transmission | 2019-05-17 | 2019-11-17 | Level 2 | E | 2024-08-22 | 2019-11-17 | Level 2 | GO 165 Inspection
117280993 | other | HFTD Tier 2 | Transmission | 2019-05-06 | 2021-05-06 | Level 3 | F | 2024-06-02 | 2024-05-06 | Level 3 | GO 165 Inspection
117281416 | other | Non-HFTD | Transmission | 2019-05-07 | 2021-05-07 | Level 3 | F | 2024-04-06 | 2024-05-07 | Level 3 | Standards change
117303963 | other | HFTD Tier 2 | Transmission | 2019-05-11 | 2021-05-11 | Level 3 | F | 2024-06-04 | 2024-05-11 | Level 3 | GO 165 Inspection
117304830 | other | HFTD Tier 2 | Transmission | 2019-05-11 | 2021-05-11 | Level 3 | F | 2024-06-05 | 2024-05-11 | Level 3 | GO 165 Inspection
117307957 | other | HFTD Tier 2 | Transmission | 2019-05-11 | 2021-05-11 | Level 3 | F | 2024-05-16 | 2024-05-11 | Level 3 | GO 165 Inspection
117328310 | other | HFTD Tier 2 | Transmission | 2019-05-15 | 2021-05-15 | Level 3 | F | 2024-05-15 | 2024-05-15 | Level 3 | GO 165 Inspection
117375859 | other | Non-HFTD | Transmission | 2019-05-17 | 2021-05-17 | Level 3 | F | 2024-04-06 | 2024-05-17 | Level 3 | Standards change
117376520 | other | HFTD Tier 2 | Transmission | 2019-05-18 | 2021-05-18 | Level 3 | F | 2024-06-04 | 2024-05-18 | Level 3 | GO 165 Inspection
117383916 | pole | Non-HFTD | Transmission | 2019-06-04 | 2021-06-04 | Level 3 | F | 2024-12-18 | 2024-06-04 | Level 3 | Field Safety Reassessment
117407672 | other | HFTD Tier 2 | Transmission | 2019-05-24 | 2021-05-24 | Level 3 | F | 2024-06-12 | 2024-05-24 | Level 3 | GO 165 Inspection
117408696 | other | HFTD Tier 2 | Transmission | 2019-05-23 | 2021-05-23 | Level 3 | F | 2024-04-06 | 2024-05-23 | Level 3 | Standards change
117408720 | pole | HFTD Tier 2 | Transmission | 2019-05-24 | 2021-05-24 | Level 3 | F | 2024-06-13 | 2024-05-24 | Level 3 | GO 165 Inspection
117418358 | pole | Non-HFTD | Transmission | 2019-02-28 | 2020-02-28 | Level 2 | E | 2023-08-04 | 2022-02-28 | Level 2 | Standards change
117433357 | other | HFTD Tier 2 | Transmission | 2019-06-07 | 2021-06-07 | Level 3 | F | 2024-06-10 | 2024-06-07 | Level 3 | GO 165 Inspection
117444050 | other | HFTD Tier 2 | Transmission | 2019-06-10 | 2021-06-10 | Level 3 | F | 2024-04-06 | 2024-06-10 | Level 3 | Standards change
117448570 | pole | HFTD Tier 2 | Transmission | 2019-06-13 | 2021-06-13 | Level 3 | F | 2024-03-14 | 2024-06-13 | Level 3 | GO 165 Inspection
117450987 | pole | HFTD Tier 2 | Transmission | 2019-06-12 | 2021-06-12 | Level 3 | F | 2024-03-27 | 2024-06-12 | Level 3 | GO 165 Inspection
117455896 | other | HFTD Tier 2 | Transmission | 2019-06-11 | 2021-06-11 | Level 3 | F | 2024-03-07 | 2024-06-11 | Level 3 | GO 165 Inspection
117456677 | other | Non-HFTD | Transmission | 2019-06-15 | 2024-06-15 | Level 3 | F | 2021-08-06 | 2024-06-15 | Level 3 | GO 165 Inspection
117458163 | pole | HFTD Tier 2 | Transmission | 2019-06-11 | 2021-06-11 | Level 3 | F | 2024-04-24 | 2024-06-11 | Level 3 | GO 165 Inspection
117459191 | other | HFTD Tier 2 | Transmission | 2019-06-12 | 2021-06-12 | Level 3 | F | 2024-04-16 | 2024-06-12 | Level 3 | GO 165 Inspection
117463602 | pole | Non-HFTD | Transmission | 2019-06-19 | 2021-06-19 | Level 3 | F | 2024-05-30 | 2024-06-19 | Level 3 | Field Safety Reassessment
117468285 | other | Non-HFTD | Transmission | 2019-06-18 | 2021-06-18 | Level 3 | F | 2024-04-06 | 2024-06-18 | Level 3 | Standards change
117493580 | other | Non-HFTD | Transmission | 2019-06-18 | 2021-06-18 | Level 3 | F | 2024-04-06 | 2024-06-18 | Level 3 | Standards change
117494647 | pole | Non-HFTD | Transmission | 2019-06-26 | 2021-06-26 | Level 3 | F | 2024-05-15 | 2024-06-26 | Level 3 | Field Safety Reassessment
117495336 | pole | Non-HFTD | Transmission | 2019-06-19 | 2021-06-19 | Level 3 | F | 2024-05-15 | 2024-06-19 | Level 3 | Field Safety Reassessment
117495895 | pole | Non-HFTD | Transmission | 2019-06-20 | 2022-06-20 | Level 2 | E | 2024-10-09 | 2020-06-20 | Level 2 | GO 165 Inspection
117497952 | pole | Non-HFTD | Transmission | 2019-06-20 | 2021-06-20 | Level 3 | F | 2024-04-01 | 2024-06-20 | Level 3 | GO 165 Inspection
117498843 | pole | Non-HFTD | Transmission | 2019-06-27 | 2021-06-27 | Level 3 | F | 2024-09-10 | 2024-06-27 | Level 3 | GO 165 Inspection
117498988 | other | HFTD Tier 2 | Transmission | 2019-06-25 | 2021-06-25 | Level 3 | F | 2023-06-07 | 2024-06-25 | Level 3 | Standards change
117502909 | other | HFTD Tier 2 | Transmission | 2019-06-18 | 2021-06-18 | Level 3 | F | 2024-04-06 | 2024-06-18 | Level 3 | Standards change
117564182 | other | Non-HFTD | Transmission | 2019-07-05 | 2021-07-05 | Level 3 | F | 2024-05-21 | 2024-07-05 | Level 3 | GO 165 Inspection
117583567 | pole | Non-HFTD | Transmission | 2019-07-10 | 2022-07-10 | Level 3 | F | 2024-08-06 | 2024-07-10 | Level 3 | GO 165 Inspection
117589263 | other | Non-HFTD | Transmission | 2019-07-11 | 2021-07-11 | Level 3 | F | 2024-04-06 | 2024-07-11 | Level 3 | Standards change
117594761 | other | HFTD Tier 2 | Transmission | 2019-07-03 | 2021-07-03 | Level 3 | F | 2024-05-10 | 2024-07-03 | Level 3 | GO 165 Inspection
117596853 | other | HFTD Tier 2 | Transmission | 2019-07-10 | 2021-07-10 | Level 3 | F | 2023-12-08 | 2024-07-10 | Level 3 | Standards change
117597007 | other | Non-HFTD | Transmission | 2019-07-12 | 2021-07-12 | Level 3 | F | 2024-08-01 | 2024-07-12 | Level 3 | GO 165 Inspection
117608416 | pole | Non-HFTD | Transmission | 2019-07-17 | 2021-07-17 | Level 3 | F | 2024-01-30 | 2024-07-17 | Level 3 | Standards change
117612152 | pole | Non-HFTD | Transmission | 2019-07-17 | 2021-07-17 | Level 3 | F | 2024-09-30 | 2024-07-17 | Level 3 | GO 165 Inspection
117613507 | other | Non-HFTD | Transmission | 2019-07-18 | 2021-07-18 | Level 3 | F | 2024-04-06 | 2024-07-18 | Level 3 | Standards change
117613520 | other | Non-HFTD | Transmission | 2019-07-18 | 2021-07-18 | Level 3 | F | 2024-04-06 | 2024-07-18 | Level 3 | Standards change
117619627 | other | Non-HFTD | Transmission | 2019-07-19 | 2021-07-19 | Level 3 | F | 2024-04-06 | 2024-07-19 | Level 3 | Standards change
117632523 | other | HFTD Tier 2 | Transmission | 2019-06-15 | 2021-06-15 | Level 3 | F | 2024-04-12 | 2024-06-15 | Level 3 | GO 165 Inspection
117641265 | other | Non-HFTD | Transmission | 2019-07-25 | 2021-07-25 | Level 3 | F | 2024-08-13 | 2024-07-25 | Level 3 | GO 165 Inspection
117674835 | other | Non-HFTD | Transmission | 2019-07-31 | 2021-07-31 | Level 3 | F | 2024-05-31 | 2024-07-31 | Level 3 | GO 165 Inspection
117674933 | other | Non-HFTD | Transmission | 2019-07-31 | 2021-07-31 | Level 3 | F | 2024-06-11 | 2024-07-31 | Level 3 | GO 165 Inspection
117713465 | other | Non-HFTD | Transmission | 2019-08-05 | 2021-08-05 | Level 3 | F | 2024-07-05 | 2024-08-05 | Level 3 | GO 165 Inspection
117721529 | crossarm | Non-HFTD | Transmission | 2019-08-06 | 2020-08-06 | Level 2 | E | 2023-10-18 | 2020-08-06 | Level 2 | Standards change
117724612 | other | Non-HFTD | Transmission | 2019-08-07 | 2021-08-07 | Level 3 | F | 2024-02-29 | 2024-08-07 | Level 3 | Standards change
117724648 | other | Non-HFTD | Transmission | 2019-08-07 | 2021-08-07 | Level 3 | F | 2024-02-29 | 2024-08-07 | Level 3 | Standards change
117745458 | other | HFTD Tier 2 | Transmission | 2019-08-09 | 2021-08-09 | Level 3 | F | 2024-04-06 | 2024-08-09 | Level 3 | Standards change
117757018 | pole | Non-HFTD | Transmission | 2019-08-14 | 2022-08-14 | Level 2 | E | 2024-09-05 | 2019-11-14 | Level 2 | GO 165 Inspection
117759781 | other | Non-HFTD | Transmission | 2019-08-15 | 2021-08-15 | Level 3 | F | 2024-04-06 | 2024-08-15 | Level 3 | Standards change
117766834 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-04-06 | 2024-08-16 | Level 3 | Standards change
117767312 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-04-06 | 2024-08-16 | Level 3 | Standards change
117767929 | other | HFTD Tier 2 | Transmission | 2019-08-08 | 2021-08-08 | Level 3 | F | 2024-09-06 | 2024-08-08 | Level 3 | GO 165 Inspection
117768508 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-04-06 | 2024-08-16 | Level 3 | Standards change
117768642 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-04-06 | 2024-08-16 | Level 3 | Standards change
117769394 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-08-05 | 2024-08-16 | Level 3 | GO 165 Inspection
117769445 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-08-05 | 2024-08-16 | Level 3 | GO 165 Inspection
117769717 | other | Non-HFTD | Transmission | 2019-08-16 | 2021-08-16 | Level 3 | F | 2024-04-06 | 2024-08-16 | Level 3 | Standards change
117786465 | other | Non-HFTD | Transmission | 2019-08-22 | 2021-08-22 | Level 3 | F | 2024-08-27 | 2024-08-22 | Level 3 | GO 165 Inspection
117812751 | other | Non-HFTD | Transmission | 2019-08-27 | 2021-08-27 | Level 3 | F | 2024-07-17 | 2024-08-27 | Level 3 | GO 165 Inspection
117813896 | other | Non-HFTD | Transmission | 2019-08-19 | 2021-08-19 | Level 3 | F | 2024-09-18 | 2024-08-19 | Level 3 | GO 165 Inspection
117816574 | pole | Non-HFTD | Transmission | 2019-08-28 | 2021-08-28 | Level 3 | F | 2024-09-11 | 2024-08-28 | Level 3 | GO 165 Inspection
117816601 | pole | Non-HFTD | Transmission | 2019-08-28 | 2021-08-28 | Level 3 | F | 2024-10-03 | 2024-08-28 | Level 3 | GO 165 Inspection
117826610 | other | Non-HFTD | Transmission | 2019-08-30 | 2021-08-30 | Level 3 | F | 2023-08-18 | 2024-08-30 | Level 3 | Standards change
117826674 | other | Non-HFTD | Transmission | 2019-08-30 | 2021-08-30 | Level 3 | F | 2023-07-28 | 2024-08-30 | Level 3 | Standards change
117847162 | other | Non-HFTD | Transmission | 2019-09-05 | 2021-09-05 | Level 3 | F | 2024-09-17 | 2024-09-05 | Level 3 | GO 165 Inspection
117847366 | other | Non-HFTD | Transmission | 2019-09-05 | 2021-09-05 | Level 3 | F | 2023-09-08 | 2024-09-05 | Level 3 | Standards change
117872058 | other | Non-HFTD | Transmission | 2019-09-11 | 2021-09-11 | Level 3 | F | 2024-11-25 | 2024-09-11 | Level 3 | GO 165 Inspection
117872142 | other | Non-HFTD | Transmission | 2019-09-11 | 2021-09-11 | Level 3 | F | 2024-11-26 | 2024-09-11 | Level 3 | GO 165 Inspection
117873338 | other | Non-HFTD | Transmission | 2019-08-23 | 2021-08-23 | Level 3 | F | 2024-04-06 | 2024-08-23 | Level 3 | Standards change
117886109 | other | Non-HFTD | Transmission | 2019-09-16 | 2021-09-16 | Level 3 | F | 2024-02-28 | 2024-09-16 | Level 3 | Standards change
117888472 | pole | HFTD Tier 2 | Transmission | 2019-09-17 | 2021-09-17 | Level 3 | F | 2024-05-08 | 2024-09-17 | Level 3 | GO 165 Inspection
117894483 | other | Non-HFTD | Transmission | 2019-09-18 | 2021-09-18 | Level 3 | F | 2024-04-06 | 2024-09-18 | Level 3 | Standards change
117897446 | other | Non-HFTD | Transmission | 2019-09-19 | 2021-09-19 | Level 3 | F | 2024-04-06 | 2024-09-19 | Level 3 | Standards change
117897542 | pole | Non-HFTD | Transmission | 2019-09-12 | 2021-09-12 | Level 3 | F | 2024-08-20 | 2024-09-12 | Level 3 | GO 165 Inspection
117917393 | other | Non-HFTD | Transmission | 2019-09-25 | 2021-09-25 | Level 3 | F | 2024-08-29 | 2024-09-25 | Level 3 | GO 165 Inspection
117918022 | other | Non-HFTD | Transmission | 2019-09-25 | 2021-09-25 | Level 3 | F | 2024-07-23 | 2024-09-25 | Level 3 | GO 165 Inspection
117918023 | other | Non-HFTD | Transmission | 2019-09-25 | 2021-09-25 | Level 3 | F | 2024-07-23 | 2024-09-25 | Level 3 | GO 165 Inspection
117919428 | other | Non-HFTD | Transmission | 2019-09-25 | 2021-09-25 | Level 3 | F | 2024-04-06 | 2024-09-25 | Level 3 | Standards change
117925599 | other | Non-HFTD | Transmission | 2019-09-27 | 2021-09-27 | Level 3 | F | 2024-04-06 | 2024-09-27 | Level 3 | Standards change
117931610 | pole | HFTD Tier 2 | Transmission | 2019-09-30 | 2021-09-30 | Level 3 | F | 2024-04-30 | 2024-09-30 | Level 3 | GO 165 Inspection
117932982 | insulator and brushing | Non-HFTD | Transmission | 2019-09-30 | 2020-09-30 | Level 2 | E | 2024-07-24 | 2022-09-30 | Level 2 | GO 165 Inspection
117941305 | other | Non-HFTD | Transmission | 2019-10-02 | 2021-10-02 | Level 3 | F | 2024-02-28 | 2024-10-02 | Level 3 | Standards change
117969898 | pole | Non-HFTD | Transmission | 2019-10-08 | 2021-10-08 | Level 3 | F | 2024-12-03 | 2024-10-08 | Level 3 | GO 165 Inspection
117971453 | other | Non-HFTD | Transmission | 2019-10-08 | 2021-10-08 | Level 3 | F | 2024-07-12 | 2024-10-08 | Level 3 | GO 165 Inspection
117983855 | other | Non-HFTD | Transmission | 2019-10-10 | 2021-10-10 | Level 3 | F | 2024-06-28 | 2024-10-10 | Level 3 | GO 165 Inspection
117988950 | other | Non-HFTD | Transmission | 2019-10-11 | 2021-10-11 | Level 3 | F | 2023-08-21 | 2024-10-11 | Level 3 | Standards change
118005620 | other | Non-HFTD | Transmission | 2019-10-15 | 2021-10-15 | Level 3 | F | 2024-08-27 | 2024-10-15 | Level 3 | GO 165 Inspection
118022433 | other | Non-HFTD | Transmission | 2019-10-18 | 2021-10-18 | Level 3 | F | 2024-07-15 | 2024-10-18 | Level 3 | GO 165 Inspection
118096996 | other | Non-HFTD | Transmission | 2019-10-24 | 2021-10-24 | Level 3 | F | 2024-04-06 | 2024-10-24 | Level 3 | Standards change
118097352 | other | Non-HFTD | Transmission | 2019-10-24 | 2021-10-24 | Level 3 | F | 2024-04-06 | 2024-10-24 | Level 3 | Standards change
118103918 | other | Non-HFTD | Transmission | 2019-10-25 | 2021-10-25 | Level 3 | F | 2024-04-06 | 2024-10-25 | Level 3 | Standards change
118103919 | other | Non-HFTD | Transmission | 2019-10-25 | 2021-10-25 | Level 3 | F | 2024-04-06 | 2024-10-25 | Level 3 | Standards change
118127650 | other | Non-HFTD | Transmission | 2019-10-31 | 2021-10-31 | Level 3 | F | 2023-10-31 | 2024-10-31 | Level 3 | GO 165 Inspection
118139034 | other | Non-HFTD | Transmission | 2019-11-04 | 2021-11-04 | Level 3 | F | 2024-10-30 | 2024-11-04 | Level 3 | GO 165 Inspection
118139038 | other | Non-HFTD | Transmission | 2019-11-04 | 2021-11-04 | Level 3 | F | 2024-10-30 | 2024-11-04 | Level 3 | GO 165 Inspection
118151884 | other | HFTD Tier 2 | Transmission | 2019-11-07 | 2021-11-07 | Level 3 | F | 2024-04-06 | 2024-11-07 | Level 3 | Standards change
118169893 | other | Non-HFTD | Transmission | 2019-11-13 | 2021-11-13 | Level 3 | F | 2023-04-06 | 2024-11-13 | Level 3 | Standards change
118201125 | other | Non-HFTD | Transmission | 2019-11-25 | 2021-11-25 | Level 3 | F | 2024-10-11 | 2024-11-25 | Level 3 | GO 165 Inspection
118224398 | pole | HFTD Tier 2 | Transmission | 2019-12-03 | 2021-12-03 | Level 3 | F | 2024-03-28 | 2024-12-03 | Level 3 | GO 165 Inspection
118232435 | other | Non-HFTD | Transmission | 2019-12-04 | 2021-12-04 | Level 3 | F | 2024-04-06 | 2024-12-04 | Level 3 | Standards change
118232438 | other | Non-HFTD | Transmission | 2019-12-04 | 2021-12-04 | Level 3 | F | 2024-04-06 | 2024-12-04 | Level 3 | Standards change
118232444 | other | Non-HFTD | Transmission | 2019-12-04 | 2021-12-04 | Level 3 | F | 2024-04-06 | 2024-12-04 | Level 3 | Standards change
118232464 | other | Non-HFTD | Transmission | 2019-12-04 | 2021-12-04 | Level 3 | F | 2024-04-06 | 2024-12-04 | Level 3 | Standards change
118241960 | pole | Non-HFTD | Transmission | 2019-12-05 | 2021-12-05 | Level 3 | F | 2024-03-14 | 2024-12-05 | Level 3 | GO 165 Inspection
118242922 | other | Non-HFTD | Transmission | 2019-11-24 | 2020-11-24 | Level 2 | E | 2024-02-23 | 2022-11-24 | Level 2 | Standards change
118261509 | other | Non-HFTD | Transmission | 2019-12-04 | 2021-12-04 | Level 3 | F | 2024-04-06 | 2024-12-04 | Level 3 | Standards change
118261532 | other | Non-HFTD | Transmission | 2019-12-05 | 2021-12-05 | Level 3 | F | 2024-04-06 | 2024-12-05 | Level 3 | Standards change
118264514 | anchor/guy | Non-HFTD | Transmission | 2019-12-12 | 2020-12-12 | Level 2 | E | 2023-07-25 | 2024-12-12 | Level 3 | Standards change
118264780 | anchor/guy | Non-HFTD | Transmission | 2019-12-12 | 2020-12-12 | Level 2 | E | 2024-04-09 | 2024-12-12 | Level 3 | GO 165 Inspection
118278405 | other | Non-HFTD | Transmission | 2019-12-16 | 2021-12-16 | Level 3 | F | 2024-07-29 | 2024-12-16 | Level 3 | GO 165 Inspection
118278481 | anchor/guy | Non-HFTD | Transmission | 2019-12-16 | 2020-12-16 | Level 2 | E | 2024-07-29 | 2024-12-16 | Level 3 | GO 165 Inspection
118429410 | other | Non-HFTD | Transmission | 2020-01-14 | 2022-01-14 | Level 3 | F | 2024-04-06 | 2025-01-14 | Level 3 | Standards change
118429785 | pole | Non-HFTD | Transmission | 2020-01-14 | 2022-01-14 | Level 3 | F | 2023-12-06 | 2025-01-14 | Level 3 | Standards change
118430077 | pole | Non-HFTD | Transmission | 2020-01-14 | 2021-01-14 | Level 2 | E | 2024-07-26 | 2023-01-14 | Level 2 | Field Safety Reassessment
118439977 | insulator and brushing | Non-HFTD | Transmission | 2020-01-17 | 2021-01-17 | Level 2 | E | 2024-03-22 | 2023-01-17 | Level 2 | Standards change
118439995 | insulator and brushing | Non-HFTD | Transmission | 2020-01-17 | 2021-01-17 | Level 2 | E | 2024-03-22 | 2023-01-17 | Level 2 | Standards change
118440310 | other | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 3 | F | 2024-06-17 | 2023-10-18 | Level 2 | Field Safety Reassessment
118473265 | pole | Non-HFTD | Transmission | 2020-01-27 | 2021-01-27 | Level 2 | E | 2023-09-22 | 2021-01-27 | Level 2 | Standards change
118498949 | other | Non-HFTD | Transmission | 2020-02-05 | 2021-02-05 | Level 2 | E | 2024-10-09 | 2021-02-05 | Level 2 | GO 165 Inspection
118500083 | anchor/guy | Non-HFTD | Transmission | 2020-02-05 | 2021-02-05 | Level 2 | E | 2024-06-14 | 2023-02-05 | Level 2 | GO 165 Inspection
118519808 | other | Non-HFTD | Transmission | 2020-02-10 | 2021-02-10 | Level 2 | E | 2024-02-06 | 2025-02-10 | Level 3 | Standards change
118522704 | other | Non-HFTD | Transmission | 2020-02-10 | 2022-02-10 | Level 3 | F | 2024-04-06 | 2025-02-10 | Level 3 | Standards change
118522713 | other | Non-HFTD | Transmission | 2020-02-10 | 2022-02-10 | Level 3 | F | 2024-04-06 | 2025-02-10 | Level 3 | Standards change
118530783 | pole | Non-HFTD | Transmission | 2020-02-13 | 2021-02-13 | Level 2 | E | 2023-07-05 | 2023-02-13 | Level 2 | Field Safety Reassessment
118548195 | pole | Non-HFTD | Transmission | 2020-02-19 | 2022-02-19 | Level 3 | F | 2024-01-11 | 2025-02-19 | Level 3 | Standards change
118548694 | other | Non-HFTD | Transmission | 2020-02-19 | 2022-02-19 | Level 3 | F | 2024-04-06 | 2025-02-19 | Level 3 | Standards change
118589834 | crossarm | Non-HFTD | Transmission | 2020-02-28 | 2021-02-28 | Level 2 | E | 2024-04-19 | 2023-02-28 | Level 2 | Field Safety Reassessment
118600713 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-10-10 | 2023-03-03 | Level 2 | GO 165 Inspection
118602997 | pole | HFTD Tier 3 | Transmission | 2020-03-03 | 2022-03-03 | Level 3 | F | 2024-04-15 | 2025-03-03 | Level 3 | GO 165 Inspection
118605383 | pole | Non-HFTD | Transmission | 2020-03-04 | 2021-03-04 | Level 2 | E | 2023-11-21 | 2023-03-04 | Level 2 | Standards change
118621651 | other | Non-HFTD | Transmission | 2020-03-05 | 2020-06-05 | Level 2 | E | 2024-12-03 | 2020-06-05 | Level 2 | Field Safety Reassessment
118640580 | pole | Non-HFTD | Transmission | 2020-01-20 | 2021-01-20 | Level 2 | E | 2023-10-16 | 2021-01-20 | Level 2 | Standards change
118640582 | pole | Non-HFTD | Transmission | 2020-02-13 | 2021-02-13 | Level 2 | E | 2023-08-04 | 2023-02-13 | Level 2 | Standards change
118652226 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-10-18 | 2023-03-03 | Level 2 | GO 165 Inspection
118654358 | pole | Non-HFTD | Transmission | 2020-03-03 | 2022-03-03 | Level 3 | F | 2024-10-10 | 2025-03-03 | Level 3 | GO 165 Inspection
118672235 | pole | Non-HFTD | Transmission | 2020-03-03 | 2022-03-03 | Level 3 | F | 2024-11-27 | 2025-03-03 | Level 3 | GO 165 Inspection
118672275 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-11-27 | 2023-03-03 | Level 2 | GO 165 Inspection
118672297 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-11-27 | 2023-03-03 | Level 2 | GO 165 Inspection
118680361 | pole | Non-HFTD | Transmission | 2020-03-03 | 2022-03-03 | Level 3 | F | 2024-10-10 | 2025-03-03 | Level 3 | GO 165 Inspection
118680832 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-08-09 | 2023-03-03 | Level 2 | GO 165 Inspection
118680914 | pole | Non-HFTD | Transmission | 2020-03-03 | 2022-03-03 | Level 3 | F | 2024-10-17 | 2025-03-03 | Level 3 | GO 165 Inspection
118680916 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-10-17 | 2023-03-03 | Level 2 | GO 165 Inspection
118680955 | insulator and brushing | Non-HFTD | Transmission | 2020-03-03 | 2021-03-03 | Level 2 | E | 2024-10-10 | 2023-03-03 | Level 2 | GO 165 Inspection
118722218 | insulator and brushing | Non-HFTD | Transmission | 2020-03-19 | 2021-03-19 | Level 2 | E | 2024-09-13 | 2023-03-19 | Level 2 | GO 165 Inspection
118722313 | insulator and brushing | Non-HFTD | Transmission | 2020-03-19 | 2021-03-19 | Level 2 | E | 2024-09-13 | 2023-03-19 | Level 2 | GO 165 Inspection
118787610 | pole | Non-HFTD | Transmission | 2020-04-07 | 2021-04-07 | Level 3 | F | 2023-12-07 | 2021-04-07 | Level 3 | Standards change
118796003 | other | Non-HFTD | Transmission | 2020-04-08 | 2021-04-08 | Level 2 | E | 2024-09-04 | 2025-04-08 | Level 3 | GO 165 Inspection
118796329 | pole | Non-HFTD | Transmission | 2020-04-08 | 2021-04-08 | Level 2 | E | 2024-10-16 | 2020-07-08 | Level 2 | GO 165 Inspection
118796374 | pole | Non-HFTD | Transmission | 2020-04-08 | 2021-04-08 | Level 2 | E | 2024-10-16 | 2023-04-08 | Level 2 | GO 165 Inspection
118796402 | pole | Non-HFTD | Transmission | 2020-04-08 | 2020-10-08 | Level 2 | E | 2024-10-16 | 2020-07-08 | Level 2 | GO 165 Inspection
118797317 | pole | Non-HFTD | Transmission | 2020-04-08 | 2020-07-08 | Level 2 | E | 2024-10-28 | 2020-07-08 | Level 2 | GO 165 Inspection
118801772 | pole | HFTD Tier 2 | Transmission | 2020-04-08 | 2022-04-08 | Level 3 | F | 2023-03-06 | 2025-04-08 | Level 3 | Standards change
118898652 | pole | Non-HFTD | Transmission | 2020-04-09 | 2022-04-09 | Level 3 | F | 2023-12-22 | 2025-04-09 | Level 3 | Standards change
118915643 | other | Non-HFTD | Transmission | 2020-04-13 | 2021-04-13 | Level 2 | E | 2022-11-10 | 2021-04-13 | Level 2 | GO 165 Inspection
118925789 | pole | HFTD Tier 3 | Transmission | 2020-04-15 | 2022-04-15 | Level 3 | F | 2024-05-09 | 2025-04-15 | Level 3 | GO 165 Inspection
118927210 | other | Non-HFTD | Transmission | 2020-04-16 | 2022-04-16 | Level 3 | F | 2024-02-28 | 2025-04-16 | Level 3 | Standards change
118928984 | anchor/guy | Non-HFTD | Transmission | 2020-04-16 | 2021-04-16 | Level 2 | E | 2024-01-25 | 2025-04-15 | Level 3 | Standards change
118929022 | anchor/guy | Non-HFTD | Transmission | 2020-04-16 | 2021-04-16 | Level 2 | E | 2024-01-25 | 2025-04-15 | Level 3 | Standards change
118929796 | other | Non-HFTD | Transmission | 2020-04-16 | 2022-04-16 | Level 3 | F | 2024-02-28 | 2025-04-16 | Level 3 | Standards change
118930031 | other | Non-HFTD | Transmission | 2020-04-16 | 2022-04-16 | Level 3 | F | 2024-04-06 | 2025-04-16 | Level 3 | Standards change
118930219 | other | Non-HFTD | Transmission | 2020-04-17 | 2022-04-17 | Level 3 | F | 2024-04-06 | 2025-04-17 | Level 3 | Standards change
118931389 | pole | Non-HFTD | Transmission | 2020-04-18 | 2021-04-18 | Level 2 | E | 2024-01-04 | 2021-04-18 | Level 2 | Standards change
118932048 | pole | Non-HFTD | Transmission | 2020-04-15 | 2021-04-15 | Level 2 | E | 2024-01-02 | 2025-04-15 | Level 3 | Standards change
118932487 | other | Non-HFTD | Transmission | 2020-04-17 | 2022-04-17 | Level 3 | F | 2024-02-28 | 2025-04-17 | Level 3 | Standards change
118932633 | pole | Non-HFTD | Transmission | 2020-04-17 | 2021-04-17 | Level 2 | E | 2024-01-04 | 2021-04-17 | Level 2 | Standards change
118934613 | pole | Non-HFTD | Transmission | 2020-04-17 | 2020-07-17 | Level 2 | E | 2024-10-18 | 2020-07-17 | Level 2 | Field Safety Reassessment
118937029 | other | Non-HFTD | Transmission | 2020-04-16 | 2022-04-16 | Level 3 | F | 2024-10-22 | 2025-04-16 | Level 3 | GO 165 Inspection
118937453 | other | Non-HFTD | Transmission | 2020-04-20 | 2021-04-20 | Level 2 | E | 2024-02-29 | 2023-04-19 | Level 2 | Standards change
118938246 | other | Non-HFTD | Transmission | 2020-04-20 | 2022-04-20 | Level 3 | F | 2024-07-22 | 2025-04-20 | Level 3 | GO 165 Inspection
118939981 | insulator and brushing | Non-HFTD | Transmission | 2020-04-21 | 2022-04-21 | Level 3 | F | 2023-11-16 | 2025-04-21 | Level 3 | Standards change
118947192 | other | Non-HFTD | Transmission | 2020-04-23 | 2022-04-23 | Level 3 | F | 2024-04-06 | 2025-04-23 | Level 3 | Standards change
118952486 | pole | Non-HFTD | Transmission | 2020-04-23 | 2022-04-23 | Level 3 | F | 2024-06-18 | 2025-04-23 | Level 3 | GO 165 Inspection
118952710 | other | Non-HFTD | Transmission | 2019-01-15 | 2021-01-15 | Level 3 | F | 2024-02-29 | 2024-01-15 | Level 3 | Standards change
118954301 | pole | Non-HFTD | Transmission | 2020-02-26 | 2021-02-26 | Level 2 | E | 2023-08-11 | 2023-02-26 | Level 2 | Standards change
118954770 | anchor/guy | Non-HFTD | Transmission | 2020-04-24 | 2021-04-24 | Level 2 | E | 2024-01-17 | 2025-04-24 | Level 3 | Standards change
118956784 | anchor/guy | Non-HFTD | Transmission | 2020-04-23 | 2021-04-23 | Level 2 | E | 2024-01-24 | 2025-04-23 | Level 3 | Standards change
118958911 | other | HFTD Tier 2 | Transmission | 2020-04-27 | 2022-04-27 | Level 3 | F | 2024-04-06 | 2025-04-27 | Level 3 | Standards change
118959878 | pole | Non-HFTD | Transmission | 2020-04-27 | 2021-04-27 | Level 2 | E | 2024-11-06 | 2023-04-27 | Level 2 | Field Safety Reassessment
118960821 | anchor/guy | Non-HFTD | Transmission | 2020-04-22 | 2021-04-22 | Level 2 | E | 2024-01-25 | 2025-04-22 | Level 3 | Standards change
118960884 | other | Non-HFTD | Transmission | 2020-04-27 | 2022-04-27 | Level 3 | F | 2024-04-11 | 2025-04-27 | Level 3 | Standards change
118964107 | pole | Non-HFTD | Transmission | 2020-04-30 | 2022-04-30 | Level 3 | F | 2024-05-02 | 2025-04-30 | Level 3 | GO 165 Inspection
118964781 | other | Non-HFTD | Transmission | 2020-04-29 | 2022-04-29 | Level 3 | F | 2024-02-28 | 2025-04-29 | Level 3 | Standards change
118964884 | anchor/guy | Non-HFTD | Transmission | 2020-04-23 | 2021-04-23 | Level 2 | E | 2024-07-16 | 2023-04-23 | Level 2 | GO 165 Inspection
118971828 | other | Non-HFTD | Transmission | 2020-04-30 | 2022-04-30 | Level 3 | F | 2024-04-06 | 2025-04-30 | Level 3 | Standards change
118976468 | insulator and brushing | Non-HFTD | Transmission | 2020-04-30 | 2021-04-30 | Level 2 | E | 2024-01-30 | 2023-04-30 | Level 2 | Standards change
118981800 | anchor/guy | Non-HFTD | Transmission | 2020-04-29 | 2021-04-29 | Level 2 | E | 2023-04-28 | 2025-04-29 | Level 3 | Standards change
118983102 | insulator and brushing | Non-HFTD | Transmission | 2020-05-04 | 2021-05-04 | Level 2 | E | 2024-08-21 | 2023-05-04 | Level 2 | GO 165 Inspection
118984878 | pole | Non-HFTD | Transmission | 2020-04-30 | 2023-04-30 | Level 2 | E | 2022-12-01 | 2023-04-30 | Level 2 | Field Safety Reassessment
118985701 | pole | Non-HFTD | Transmission | 2020-05-05 | 2022-05-05 | Level 3 | F | 2024-05-02 | 2025-05-05 | Level 3 | GO 165 Inspection
118988227 | anchor/guy | Non-HFTD | Transmission | 2020-04-30 | 2021-04-30 | Level 2 | E | 2024-01-18 | 2025-04-30 | Level 3 | Standards change
118989239 | anchor/guy | Non-HFTD | Transmission | 2020-04-29 | 2021-04-29 | Level 2 | E | 2023-01-23 | 2023-04-29 | Level 2 | Standards change
118990592 | pole | Non-HFTD | Transmission | 2020-05-01 | 2022-05-01 | Level 3 | F | 2024-03-28 | 2023-05-01 | Level 2 | GO 165 Inspection
118992302 | other | Non-HFTD | Transmission | 2020-05-01 | 2022-05-01 | Level 3 | F | 2024-10-30 | 2025-05-01 | Level 3 | GO 165 Inspection
118992380 | other | Non-HFTD | Transmission | 2020-05-05 | 2022-05-05 | Level 3 | F | 2023-12-22 | 2025-05-05 | Level 3 | Standards change
118992384 | pole | Non-HFTD | Transmission | 2020-05-01 | 2021-05-01 | Level 2 | E | 2024-11-14 | 2023-05-01 | Level 2 | GO 165 Inspection
118993514 | pole | Non-HFTD | Transmission | 2020-04-18 | 2021-04-18 | Level 2 | E | 2024-01-04 | 2021-04-18 | Level 2 | Standards change
118995075 | anchor/guy | Non-HFTD | Transmission | 2020-05-05 | 2021-05-05 | Level 2 | E | 2024-07-10 | 2025-05-03 | Level 3 | GO 165 Inspection
118995076 | pole | Non-HFTD | Transmission | 2020-05-05 | 2021-05-05 | Level 2 | E | 2024-07-10 | 2023-05-05 | Level 2 | GO 165 Inspection
118995603 | insulator and brushing | Non-HFTD | Transmission | 2020-05-01 | 2021-05-01 | Level 2 | E | 2024-07-18 | 2023-05-01 | Level 2 | GO 165 Inspection
118996315 | pole | Non-HFTD | Transmission | 2020-05-05 | 2022-05-05 | Level 3 | F | 2023-03-06 | 2025-05-05 | Level 3 | Standards change
118997959 | other | Non-HFTD | Transmission | 2020-05-05 | 2021-05-05 | Level 2 | E | 2024-09-23 | 2025-05-05 | Level 3 | GO 165 Inspection
118998017 | other | Non-HFTD | Transmission | 2020-05-05 | 2021-05-05 | Level 2 | E | 2023-04-07 | 2025-05-05 | Level 3 | Standards change
118998019 | other | Non-HFTD | Transmission | 2020-05-05 | 2022-05-05 | Level 3 | F | 2023-12-28 | 2025-05-05 | Level 3 | Standards change
118999985 | insulator and brushing | Non-HFTD | Transmission | 2020-05-01 | 2021-05-01 | Level 2 | E | 2024-12-04 | 2023-04-30 | Level 2 | Field Safety Reassessment
119002222 | anchor/guy | Non-HFTD | Transmission | 2020-05-08 | 2022-05-08 | Level 3 | F | 2024-07-10 | 2025-05-08 | Level 3 | GO 165 Inspection
119002225 | anchor/guy | Non-HFTD | Transmission | 2020-05-05 | 2021-05-05 | Level 2 | E | 2023-04-24 | 2023-05-05 | Level 2 | Standards change
119002900 | other | Non-HFTD | Transmission | 2020-05-04 | 2022-05-04 | Level 3 | F | 2023-12-28 | 2025-05-04 | Level 3 | Standards change
119004443 | insulator and brushing | Non-HFTD | Transmission | 2020-05-01 | 2021-05-01 | Level 2 | E | 2024-12-04 | 2023-05-01 | Level 2 | Field Safety Reassessment
119004779 | insulator and brushing | Non-HFTD | Transmission | 2020-04-30 | 2021-04-30 | Level 2 | E | 2024-11-20 | 2023-04-30 | Level 2 | GO 165 Inspection
119004840 | other | Non-HFTD | Transmission | 2020-04-30 | 2021-04-30 | Level 2 | E | 2024-11-20 | 2025-04-30 | Level 3 | GO 165 Inspection
119005195 | anchor/guy | Non-HFTD | Transmission | 2020-04-30 | 2021-04-30 | Level 2 | E | 2024-01-08 | 2025-04-29 | Level 3 | Standards change
119013387 | pole | Non-HFTD | Transmission | 2020-04-30 | 2021-04-29 | Level 2 | E | 2022-12-13 | 2021-04-29 | Level 2 | Standards change
119013405 | pole | Non-HFTD | Transmission | 2020-05-07 | 2023-05-05 | Level 2 | E | 2024-11-15 | 2021-05-07 | Level 2 | GO 165 Inspection
119014453 | anchor/guy | Non-HFTD | Transmission | 2020-05-07 | 2021-05-07 | Level 2 | E | 2023-12-29 | 2025-05-07 | Level 3 | Standards change
119016543 | other | Non-HFTD | Transmission | 2020-05-07 | 2021-05-07 | Level 2 | E | 2023-07-27 | 2023-05-07 | Level 2 | Standards change
119016844 | other | Non-HFTD | Transmission | 2020-05-08 | 2022-05-08 | Level 3 | F | 2024-10-25 | 2025-05-08 | Level 3 | GO 165 Inspection
119016954 | other | HFTD Tier 2 | Transmission | 2020-04-24 | 2022-04-24 | Level 3 | F | 2024-04-23 | 2025-04-24 | Level 3 | GO 165 Inspection
119016991 | other | Non-HFTD | Transmission | 2020-05-11 | 2021-05-11 | Level 2 | E | 2024-02-21 | 2021-05-11 | Level 2 | Standards change
119018090 | pole | Non-HFTD | Transmission | 2020-05-08 | 2021-05-08 | Level 2 | E | 2024-10-19 | 2023-05-08 | Level 2 | Field Safety Reassessment
119018098 | anchor/guy | Non-HFTD | Transmission | 2020-05-08 | 2021-05-08 | Level 2 | E | 2024-01-24 | 2025-05-06 | Level 3 | Standards change
119019829 | pole | Non-HFTD | Transmission | 2020-05-07 | 2023-05-05 | Level 2 | E | 2024-11-15 | 2020-11-07 | Level 2 | GO 165 Inspection
119022791 | other | Non-HFTD | Transmission | 2020-05-07 | 2021-05-07 | Level 2 | E | 2023-04-07 | 2025-05-07 | Level 3 | Standards change
119023460 | other | Non-HFTD | Transmission | 2020-05-07 | 2025-05-07 | Level 2 | E | 2024-10-05 | 2023-05-07 | Level 2 | GO 165 Inspection
119026608 | insulator and brushing | Non-HFTD | Transmission | 2020-05-08 | 2021-05-08 | Level 2 | E | 2024-11-21 | 2023-05-08 | Level 2 | Field Safety Reassessment
119026691 | anchor/guy | Non-HFTD | Transmission | 2020-05-07 | 2021-05-07 | Level 2 | E | 2024-01-23 | 2025-05-07 | Level 3 | Standards change
119026729 | anchor/guy | Non-HFTD | Transmission | 2020-05-04 | 2021-05-04 | Level 2 | E | 2024-11-04 | 2025-05-04 | Level 3 | GO 165 Inspection
119026793 | other | Non-HFTD | Transmission | 2020-05-07 | 2022-05-07 | Level 3 | F | 2024-04-06 | 2025-05-07 | Level 3 | Standards change
119026962 | other | Non-HFTD | Transmission | 2020-05-05 | 2022-05-05 | Level 3 | F | 2023-01-19 | 2025-05-05 | Level 3 | Standards change
119027178 | pole | Non-HFTD | Transmission | 2020-05-14 | 2021-05-14 | Level 2 | E | 2024-09-17 | 2023-05-14 | Level 2 | GO 165 Inspection
119028237 | insulator and brushing | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2024-10-07 | 2021-05-13 | Level 2 | GO 165 Inspection
119029343 | insulator and brushing | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2023-04-17 | 2023-05-13 | Level 2 | Standards change
119029493 | pole | Non-HFTD | Transmission | 2020-05-14 | 2022-05-14 | Level 3 | F | 2024-05-06 | 2025-05-14 | Level 3 | GO 165 Inspection
119029977 | other | Non-HFTD | Transmission | 2020-05-14 | 2021-05-14 | Level 2 | E | 2024-03-21 | 2023-05-14 | Level 2 | Standards change
119030016 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2023-12-20 | 2025-05-13 | Level 3 | Standards change
119030195 | pole | Non-HFTD | Transmission | 2020-05-14 | 2021-05-14 | Level 2 | E | 2024-10-22 | 2023-05-14 | Level 2 | GO 165 Inspection
119031275 | anchor/guy | Non-HFTD | Transmission | 2020-05-07 | 2021-05-07 | Level 2 | E | 2023-12-28 | 2025-05-07 | Level 3 | Standards change
119034269 | pole | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-02-01 | 2025-05-13 | Level 3 | Standards change
119035878 | other | Non-HFTD | Transmission | 2020-05-07 | 2022-05-07 | Level 3 | F | 2024-10-28 | 2025-05-07 | Level 3 | GO 165 Inspection
119035924 | other | Non-HFTD | Transmission | 2020-05-12 | 2022-05-12 | Level 3 | F | 2024-10-24 | 2025-05-12 | Level 3 | GO 165 Inspection
119035927 | other | Non-HFTD | Transmission | 2020-05-08 | 2022-05-08 | Level 3 | F | 2023-09-05 | 2025-05-08 | Level 3 | Standards change
119036272 | anchor/guy | Non-HFTD | Transmission | 2020-05-12 | 2021-05-12 | Level 2 | E | 2024-01-03 | 2025-05-12 | Level 3 | Standards change
119036461 | other | Non-HFTD | Transmission | 2020-05-13 | 2023-05-13 | Level 2 | E | 2024-05-03 | 2021-05-13 | Level 2 | Field Safety Reassessment
119036726 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-02-28 | 2025-05-13 | Level 3 | Standards change
119036729 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-02-28 | 2025-05-13 | Level 3 | Standards change
119036821 | other | Non-HFTD | Transmission | 2020-05-12 | 2022-05-12 | Level 3 | F | 2024-08-23 | 2025-05-12 | Level 3 | GO 165 Inspection
119037048 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-02-28 | 2025-05-13 | Level 3 | Standards change
119037049 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-02-28 | 2025-05-13 | Level 3 | Standards change
119037507 | insulator and brushing | Non-HFTD | Transmission | 2020-05-08 | 2021-05-08 | Level 2 | E | 2022-12-22 | 2023-05-08 | Level 2 | Standards change
119038034 | pole | Non-HFTD | Transmission | 2020-05-08 | 2021-05-08 | Level 2 | E | 2024-10-18 | 2023-05-08 | Level 2 | GO 165 Inspection
119038037 | pole | Non-HFTD | Transmission | 2020-05-08 | 2025-05-08 | Level 2 | E | 2023-09-08 | 2023-05-08 | Level 2 | Field Safety Reassessment
119039191 | anchor/guy | Non-HFTD | Transmission | 2020-05-12 | 2021-05-12 | Level 2 | E | 2024-09-23 | 2025-05-12 | Level 3 | GO 165 Inspection
119041330 | pole | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-02-01 | 2025-05-13 | Level 3 | Standards change
119042924 | other | Non-HFTD | Transmission | 2020-05-12 | 2022-05-12 | Level 3 | F | 2024-08-23 | 2025-05-12 | Level 3 | GO 165 Inspection
119046307 | other | Non-HFTD | Transmission | 2020-05-14 | 2022-05-14 | Level 3 | F | 2023-12-21 | 2025-05-14 | Level 3 | Standards change
119046933 | pole | HFTD Tier 3 | Transmission | 2020-05-12 | 2022-05-12 | Level 3 | F | 2024-03-12 | 2025-05-12 | Level 3 | GO 165 Inspection
119049345 | pole | Non-HFTD | Transmission | 2020-05-20 | 2021-05-20 | Level 2 | E | 2024-09-16 | 2023-05-20 | Level 2 | Field Safety Reassessment
119049402 | pole | Non-HFTD | Transmission | 2020-05-20 | 2021-05-20 | Level 2 | E | 2024-07-22 | 2025-05-20 | Level 3 | GO 165 Inspection
119049525 | other | Non-HFTD | Transmission | 2020-05-20 | 2022-05-20 | Level 3 | F | 2024-07-26 | 2025-05-20 | Level 3 | GO 165 Inspection
119059567 | pole | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2024-07-22 | 2023-05-13 | Level 2 | Field Safety Reassessment
119059710 | pole | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2023-06-01 | 2023-05-13 | Level 2 | Standards change
119060143 | other | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2024-02-01 | 2023-05-13 | Level 2 | Standards change
119060196 | other | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2024-11-18 | 2023-05-13 | Level 2 | GO 165 Inspection
119060329 | anchor/guy | Non-HFTD | Transmission | 2020-05-21 | 2021-05-21 | Level 2 | E | 2024-12-10 | 2023-05-21 | Level 2 | Field Safety Reassessment
119060605 | other | Non-HFTD | Transmission | 2020-05-21 | 2021-05-21 | Level 2 | E | 2024-09-03 | 2025-05-21 | Level 3 | GO 165 Inspection
119063068 | insulator and brushing | Non-HFTD | Transmission | 2020-05-12 | 2021-05-12 | Level 2 | E | 2024-04-04 | 2023-05-12 | Level 2 | GO 165 Inspection
119070735 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2023-12-06 | 2025-05-13 | Level 3 | Standards change
119070736 | pole | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2024-07-26 | 2023-05-13 | Level 2 | Field Safety Reassessment
119081191 | anchor/guy | Non-HFTD | Transmission | 2020-05-27 | 2021-05-27 | Level 2 | E | 2024-01-17 | 2025-05-27 | Level 3 | Standards change
119082955 | other | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2023-01-24 | 2025-05-18 | Level 3 | Standards change
119083415 | anchor/guy | Non-HFTD | Transmission | 2020-05-27 | 2021-05-27 | Level 2 | E | 2024-04-18 | 2025-05-25 | Level 3 | GO 165 Inspection
119085168 | other | Non-HFTD | Transmission | 2020-05-13 | 2022-05-13 | Level 3 | F | 2024-01-03 | 2025-05-13 | Level 3 | Standards change
119085659 | other | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2023-12-06 | 2025-05-18 | Level 3 | Standards change
119086429 | insulator and brushing | Non-HFTD | Transmission | 2020-05-08 | 2021-05-08 | Level 2 | E | 2024-08-13 | 2023-05-08 | Level 2 | GO 165 Inspection
119086984 | insulator and brushing | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2023-05-02 | 2023-05-13 | Level 2 | Standards change
119087035 | pole | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2023-05-02 | 2021-05-13 | Level 2 | Standards change
119087716 | insulator and brushing | Non-HFTD | Transmission | 2020-06-01 | 2021-06-01 | Level 2 | E | 2023-12-20 | 2023-06-01 | Level 2 | Standards change
119087796 | pole | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2024-11-14 | 2025-05-18 | Level 3 | GO 165 Inspection
119088043 | other | Non-HFTD | Transmission | 2020-06-01 | 2021-06-01 | Level 2 | E | 2024-12-04 | 2021-06-01 | Level 2 | Field Safety Reassessment
119088146 | conductor | Non-HFTD | Transmission | 2020-06-01 | 2021-06-01 | Level 2 | E | 2024-10-14 | 2023-06-01 | Level 2 | Field Safety Reassessment
119088489 | other | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2023-12-06 | 2025-05-18 | Level 3 | Standards change
119088695 | pole | Non-HFTD | Transmission | 2020-05-12 | 2021-05-12 | Level 2 | E | 2024-10-16 | 2025-05-12 | Level 3 | GO 165 Inspection
119096133 | other | Non-HFTD | Transmission | 2020-05-07 | 2022-05-07 | Level 3 | F | 2024-10-29 | 2025-05-07 | Level 3 | GO 165 Inspection
119097269 | other | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2023-12-06 | 2025-05-18 | Level 3 | Standards change
119097329 | conductor | Non-HFTD | Transmission | 2020-05-13 | 2021-05-13 | Level 2 | E | 2024-11-14 | 2020-11-13 | Level 2 | Field Safety Reassessment
119097423 | anchor/guy | Non-HFTD | Transmission | 2020-05-18 | 2021-05-18 | Level 2 | E | 2024-01-19 | 2025-05-18 | Level 3 | Standards change
119100800 | other | Non-HFTD | Transmission | 2020-05-18 | 2021-05-18 | Level 2 | E | 2024-01-18 | 2025-05-18 | Level 3 | Standards change
119100930 | other | Non-HFTD | Transmission | 2020-05-21 | 2022-05-21 | Level 3 | F | 2024-04-06 | 2025-05-21 | Level 3 | Standards change
119101074 | other | Non-HFTD | Transmission | 2020-05-18 | 2021-05-18 | Level 2 | E | 2024-01-18 | 2025-05-18 | Level 3 | Standards change
119101077 | other | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2023-12-06 | 2025-05-18 | Level 3 | Standards change
119101375 | pole | Non-HFTD | Transmission | 2020-06-03 | 2025-06-03 | Level 2 | E | 2024-10-22 | 2023-06-03 | Level 2 | GO 165 Inspection
119103125 | insulator and brushing | Non-HFTD | Transmission | 2020-05-07 | 2021-05-07 | Level 2 | E | 2024-04-09 | 2023-05-07 | Level 2 | GO 165 Inspection
119103431 | other | Non-HFTD | Transmission | 2020-05-18 | 2022-05-18 | Level 3 | F | 2024-04-06 | 2025-05-18 | Level 3 | Standards change
119104743 | insulator and brushing | Non-HFTD | Transmission | 2020-05-21 | 2021-05-21 | Level 2 | E | 2024-08-20 | 2023-05-21 | Level 2 | Field Safety Reassessment
119104755 | pole | Non-HFTD | Transmission | 2020-05-27 | 2021-05-27 | Level 2 | E | 2024-08-20 | 2023-05-27 | Level 2 | Field Safety Reassessment
119108357 | other | Non-HFTD | Transmission | 2020-05-20 | 2022-05-20 | Level 3 | F | 2024-04-06 | 2025-05-20 | Level 3 | Standards change
119109031 | other | HFTD Tier 3 | Transmission | 2020-05-19 | 2022-05-19 | Level 3 | F | 2024-04-06 | 2025-05-19 | Level 3 | Standards change
119110284 | anchor/guy | Non-HFTD | Transmission | 2020-05-20 | 2021-05-20 | Level 2 | E | 2024-10-30 | 2025-05-20 | Level 3 | GO 165 Inspection
119110543 | insulator and brushing | Non-HFTD | Transmission | 2020-05-18 | 2021-05-18 | Level 2 | E | 2024-01-30 | 2023-05-18 | Level 2 | Standards change
119110968 | insulator and brushing | Non-HFTD | Transmission | 2020-05-21 | 2021-05-21 | Level 2 | E | 2023-04-17 | 2023-05-21 | Level 2 | Standards change
119111330 | other | Non-HFTD | Transmission | 2020-05-20 | 2022-05-20 | Level 3 | F | 2024-02-29 | 2025-05-20 | Level 3 | Standards change
119111913 | other | Non-HFTD | Transmission | 2020-05-21 | 2022-05-21 | Level 3 | F | 2023-12-21 | 2025-05-21 | Level 3 | Standards change
119114105 | pole | Non-HFTD | Transmission | 2020-05-27 | 2021-05-27 | Level 2 | E | 2024-09-18 | 2023-05-27 | Level 2 | GO 165 Inspection
119114509 | other | Non-HFTD | Transmission | 2020-05-18 | 2021-05-18 | Level 2 | E | 2023-05-08 | 2025-05-18 | Level 3 | Standards change
119114685 | other | HFTD Tier 3 | Transmission | 2020-05-28 | 2022-05-28 | Level 3 | F | 2024-03-15 | 2025-05-28 | Level 3 | GO 165 Inspection
119114993 | pole | HFTD Tier 3 | Transmission | 2020-05-27 | 2022-05-27 | Level 3 | F | 2024-06-05 | 2025-05-27 | Level 3 | GO 165 Inspection
119115991 | other | Non-HFTD | Transmission | 2020-05-27 | 2021-05-27 | Level 2 | E | 2024-01-16 | 2025-05-27 | Level 3 | Standards change
119116072 | pole | Non-HFTD | Transmission | 2020-05-26 | 2021-05-26 | Level 2 | E | 2023-02-27 | 2023-05-26 | Level 2 | Standards change
119116078 | other | Non-HFTD | Transmission | 2020-05-26 | 2022-05-26 | Level 3 | F | 2024-04-01 | 2025-05-26 | Level 3 | GO 165 Inspection
119116082 | other | Non-HFTD | Transmission | 2020-05-21 | 2021-05-21 | Level 2 | E | 2024-09-23 | 2025-05-21 | Level 3 | GO 165 Inspection
119116120 | anchor/guy | Non-HFTD | Transmission | 2020-05-26 | 2021-05-26 | Level 2 | E | 2024-01-25 | 2025-05-26 | Level 3 | Standards change
119116587 | other | Non-HFTD | Transmission | 2020-05-22 | 2022-05-22 | Level 3 | F | 2024-04-06 | 2025-05-22 | Level 3 | Standards change
119116677 | insulator and brushing | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-09-13 | 2021-06-05 | Level 2 | GO 165 Inspection
119116678 | insulator and brushing | Non-HFTD | Transmission | 2020-05-27 | 2021-05-27 | Level 2 | E | 2024-11-25 | 2023-05-27 | Level 2 | Field Safety Reassessment
119116832 | pole | Non-HFTD | Transmission | 2020-05-26 | 2022-05-26 | Level 3 | F | 2023-01-19 | 2025-05-26 | Level 3 | Standards change
119117072 | pole | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-10-25 | 2021-06-05 | Level 2 | Field Safety Reassessment
119117075 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-04-06 | 2025-06-05 | Level 3 | Standards change
119117076 | anchor/guy | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-04-03 | 2025-06-05 | Level 3 | GO 165 Inspection
119117145 | insulator and brushing | Non-HFTD | Transmission | 2020-05-26 | 2021-05-26 | Level 2 | E | 2023-12-28 | 2023-05-26 | Level 2 | Standards change
119117386 | other | HFTD Tier 3 | Transmission | 2020-05-27 | 2022-05-27 | Level 3 | F | 2024-05-09 | 2025-05-27 | Level 3 | GO 165 Inspection
119117985 | other | HFTD Tier 2 | Transmission | 2020-06-01 | 2022-06-01 | Level 3 | F | 2023-04-27 | 2025-06-01 | Level 3 | GO 165 Inspection
119118808 | insulator and brushing | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-04-05 | 2023-06-05 | Level 2 | GO 165 Inspection
119119018 | other | HFTD Tier 2 | Transmission | 2020-05-22 | 2022-05-22 | Level 3 | F | 2024-04-06 | 2025-05-22 | Level 3 | Standards change
119122817 | other | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-11-25 | 2025-06-05 | Level 3 | Field Safety Reassessment
119122818 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-02-05 | 2025-06-05 | Level 3 | Standards change
119124138 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-07-24 | 2025-06-08 | Level 3 | GO 165 Inspection
119124249 | insulator and brushing | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2024-08-09 | 2023-06-06 | Level 2 | GO 165 Inspection
119126010 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-01-04 | 2025-06-05 | Level 3 | Standards change
119126093 | pole | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2023-03-28 | 2023-06-05 | Level 2 | Standards change
119126256 | other | HFTD Tier 2 | Transmission | 2020-06-03 | 2022-06-03 | Level 3 | F | 2023-06-16 | 2025-06-03 | Level 3 | Standards change
119126722 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-01-16 | 2025-06-08 | Level 3 | Standards change
119127096 | anchor/guy | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2024-07-10 | 2025-06-08 | Level 3 | GO 165 Inspection
119128502 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-04-06 | 2025-06-08 | Level 3 | Standards change
119129408 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-12 | 2025-06-08 | Level 3 | Standards change
119129713 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-04-06 | 2025-06-09 | Level 3 | Standards change
119131071 | other | Non-HFTD | Transmission | 2020-06-09 | 2021-06-09 | Level 2 | E | 2023-07-25 | 2025-06-09 | Level 3 | Standards change
119131073 | insulator and brushing | Non-HFTD | Transmission | 2020-06-09 | 2021-06-09 | Level 2 | E | 2024-11-04 | 2023-06-07 | Level 2 | GO 165 Inspection
119131405 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2023-12-11 | 2025-06-05 | Level 3 | Standards change
119132334 | insulator and brushing | Non-HFTD | Transmission | 2020-06-09 | 2021-06-09 | Level 2 | E | 2024-10-15 | 2021-06-09 | Level 2 | Field Safety Reassessment
119140220 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-02-28 | 2025-06-05 | Level 3 | Standards change
119141289 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-01-09 | 2025-06-09 | Level 3 | Standards change
119141340 | pole | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-18 | 2025-06-08 | Level 3 | Standards change
119141348 | other | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2024-09-23 | 2021-06-08 | Level 2 | GO 165 Inspection
119141927 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-07-03 | 2025-06-05 | Level 3 | Standards change
119142201 | anchor/guy | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2023-01-23 | 2025-06-08 | Level 3 | Standards change
119142855 | other | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-02-07 | 2023-06-05 | Level 2 | Standards change
119143014 | pole | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2024-07-16 | 2023-06-10 | Level 2 | GO 165 Inspection
119143251 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-30 | 2025-06-08 | Level 3 | Standards change
119144484 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-04-06 | 2025-06-08 | Level 3 | Standards change
119144944 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-02-29 | 2025-06-05 | Level 3 | Standards change
119144947 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2023-04-07 | 2025-06-05 | Level 3 | Standards change
119145880 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2024-01-04 | 2025-06-10 | Level 3 | Standards change
119146176 | pole | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-12-31 | 2023-06-05 | Level 2 | Field Safety Reassessment
119147303 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-01-09 | 2025-06-09 | Level 3 | Standards change
119147925 | pole | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2024-07-23 | 2023-06-10 | Level 2 | GO 165 Inspection
119148130 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-07-04 | 2025-06-08 | Level 3 | GO 165 Inspection
119148409 | pole | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2023-05-08 | 2023-06-10 | Level 2 | Field Safety Reassessment
119149277 | pole | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-12-22 | 2025-06-10 | Level 3 | Standards change
119149352 | pole | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2024-12-21 | 2023-06-08 | Level 2 | Field Safety Reassessment
119150563 | crossarm | Non-HFTD | Transmission | 2020-06-06 | 2021-06-06 | Level 2 | E | 2024-02-14 | 2023-06-06 | Level 2 | Field Safety Reassessment
119152260 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-10-29 | 2025-06-08 | Level 3 | GO 165 Inspection
119154208 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-09-05 | 2025-06-08 | Level 3 | GO 165 Inspection
119155688 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2023-01-10 | 2025-06-09 | Level 3 | Standards change
119155818 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-04-06 | 2025-06-05 | Level 3 | Standards change
119155826 | pole | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-10-19 | 2023-06-05 | Level 2 | Field Safety Reassessment
119155945 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-10-14 | 2025-06-08 | Level 3 | GO 165 Inspection
119156022 | pole | Non-HFTD | Transmission | 2020-06-05 | 2021-06-05 | Level 2 | E | 2024-06-20 | 2023-06-05 | Level 2 | GO 165 Inspection
119156161 | anchor/guy | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2023-12-22 | 2025-06-05 | Level 3 | Standards change
119156575 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2023-01-31 | 2025-06-05 | Level 3 | Standards change
119156919 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-01-12 | 2025-06-05 | Level 3 | Standards change
119158499 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-12-15 | 2025-06-10 | Level 3 | Standards change
119158820 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-23 | 2025-06-08 | Level 3 | Standards change
119158940 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-12 | 2025-06-08 | Level 3 | Standards change
119160464 | pole | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2023-10-31 | 2023-06-10 | Level 2 | Standards change
119160881 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2024-09-27 | 2023-06-10 | Level 2 | GO 165 Inspection
119160883 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-01-17 | 2025-06-10 | Level 3 | Standards change
119160973 | pole | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2024-12-20 | 2023-06-10 | Level 2 | Field Safety Reassessment
119161043 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-09-04 | 2025-06-08 | Level 3 | GO 165 Inspection
119161079 | anchor/guy | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2024-10-04 | 2023-06-08 | Level 2 | GO 165 Inspection
119161288 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-10-31 | 2025-06-09 | Level 3 | GO 165 Inspection
119161327 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2023-01-24 | 2025-06-09 | Level 3 | Standards change
119161347 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-01-12 | 2025-06-08 | Level 3 | Standards change
119161570 | other | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2024-10-18 | 2025-06-11 | Level 3 | GO 165 Inspection
119161579 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2023-01-17 | 2025-06-09 | Level 3 | Standards change
119161587 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-01-17 | 2025-06-10 | Level 3 | Standards change
119161651 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-04-06 | 2025-06-05 | Level 3 | Standards change
119161655 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-01-12 | 2025-06-08 | Level 3 | Standards change
119161927 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-01-24 | 2025-06-10 | Level 3 | Standards change
119162054 | other | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2023-12-04 | 2025-06-11 | Level 3 | Standards change
119162064 | pole | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2024-11-26 | 2023-06-10 | Level 2 | Field Safety Reassessment
119162172 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-10-28 | 2025-06-09 | Level 3 | GO 165 Inspection
119162274 | pole | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2024-01-04 | 2025-06-10 | Level 3 | Standards change
119162278 | splice | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2023-01-23 | 2023-06-08 | Level 2 | Standards change
119162328 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-10-24 | 2025-06-09 | Level 3 | GO 165 Inspection
119162380 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-19 | 2025-06-08 | Level 3 | Standards change
119162424 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-01-26 | 2025-06-08 | Level 3 | Standards change
119162564 | insulator and brushing | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2024-12-11 | 2023-06-11 | Level 2 | Field Safety Reassessment
119162566 | splice | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2024-09-04 | 2023-06-11 | Level 2 | GO 165 Inspection
119162767 | other | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2024-01-26 | 2025-06-11 | Level 3 | Standards change
119162821 | other | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 3 | F | 2023-01-13 | 2021-06-10 | Level 2 | Standards change
119163002 | other | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2024-09-05 | 2025-06-11 | Level 3 | GO 165 Inspection
119163085 | other | Non-HFTD | Transmission | 2020-06-05 | 2022-06-05 | Level 3 | F | 2024-02-05 | 2025-06-05 | Level 3 | Standards change
119163168 | other | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2024-04-06 | 2025-06-11 | Level 3 | Standards change
119163170 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-11-30 | 2025-06-10 | Level 3 | Standards change
119163176 | anchor/guy | Non-HFTD | Transmission | 2020-06-08 | 2021-06-08 | Level 2 | E | 2023-01-23 | 2025-06-08 | Level 3 | Standards change
119163256 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2023-01-30 | 2025-06-08 | Level 3 | Standards change
119163286 | other | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2024-10-18 | 2025-06-11 | Level 3 | GO 165 Inspection
119163315 | insulator and brushing | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2023-10-02 | 2023-06-11 | Level 2 | Standards change
119163382 | pole | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2023-04-05 | 2023-06-11 | Level 2 | Standards change
119163485 | other | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2023-04-18 | 2023-06-11 | Level 2 | Standards change
119163564 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-11-30 | 2025-06-10 | Level 3 | Standards change
119163571 | other | Non-HFTD | Transmission | 2020-06-11 | 2023-06-11 | Level 2 | E | 2024-10-23 | 2025-06-11 | Level 3 | GO 165 Inspection
119163682 | other | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2023-04-17 | 2023-06-11 | Level 2 | Standards change
119163718 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2024-02-28 | 2025-06-10 | Level 3 | Standards change
119163805 | other | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2024-01-18 | 2025-06-11 | Level 3 | Standards change
119163839 | other | Non-HFTD | Transmission | 2020-06-09 | 2022-06-09 | Level 3 | F | 2024-10-28 | 2025-06-09 | Level 3 | GO 165 Inspection
119163857 | other | Non-HFTD | Transmission | 2020-06-11 | 2025-06-11 | Level 3 | F | 2024-09-06 | 2023-06-11 | Level 2 | GO 165 Inspection
119163920 | other | Non-HFTD | Transmission | 2020-06-10 | 2021-06-10 | Level 2 | E | 2024-12-23 | 2023-06-10 | Level 2 | Field Safety Reassessment
119166329 | other | Non-HFTD | Transmission | 2020-06-10 | 2022-06-10 | Level 3 | F | 2023-01-13 | 2025-06-10 | Level 3 | Standards change
119169923 | other | HFTD Tier 3 | Transmission | 2020-06-12 | 2022-06-12 | Level 3 | F | 2023-05-06 | 2025-06-12 | Level 3 | Standards change
119170611 | pole | Non-HFTD | Transmission | 2020-06-11 | 2022-06-11 | Level 3 | F | 2023-02-03 | 2025-06-11 | Level 3 | Standards change
119172166 | other | Non-HFTD | Transmission | 2020-06-11 | 2025-06-11 | Level 3 | F | 2023-02-03 | 2023-06-11 | Level 2 | Standards change
119173438 | insulator and brushing | Non-HFTD | Transmission | 2020-06-11 | 2021-06-11 | Level 2 | E | 2024-09-03 | 2023-06-11 | Level 2 | GO 165 Inspection
119174720 | other | Non-HFTD | Transmission | 2020-06-08 | 2022-06-08 | Level 3 | F | 2024-10-22 | 2025-06-08 | Level 3 | GO 165 Inspection
119174950 | other | Non-HFTD | Transmission | 2020-04-16 | 2022-04-16 | Level 3 | F | 2024-02-28 | 2025-04-16 | Level 3 | Standards change
119174997 | pole | Non-HFTD | Transmission | 2020-06-12 | 2021-06-12 | Level 2 | E | 2023-10-03 | 2025-06-12 | Level 3 | Standards change
119176277 | pole | Non-HFTD | Transmission | 2020-06-16 | 2022-06-16 | Level 3 | F | 2024-02-05 | 2025-06-16 | Level 3 | Standards change
119176632 | anchor/guy | Non-HFTD | Transmission | 2020-06-12 | 2021-06-12 | Level 2 | E | 2023-01-23 | 2025-06-12 | Level 3 | Standards change
119176635 | anchor/guy | Non-HFTD | Transmission | 2020-06-12 | 2021-06-12 | Level 2 | E | 2023-01-23 | 2025-06-12 | Level 3 | Standards change
119177492 | anchor/guy | Non-HFTD | Transmission | 2020-04-16 | 2021-04-16 | Level 2 | E | 2024-10-22 | 2025-04-16 | Level 3 | GO 165 Inspection
119185111 | splice | Non-HFTD | Transmission | 2020-06-18 | 2021-06-18 | Level 2 | E | 2024-11-04 | 2023-06-18 | Level 2 | GO 165 Inspection
119185596 | anchor/guy | Non-HFTD | Transmission | 2020-06-18 | 2021-06-18 | Level 2 | E | 2023-01-19 | 2025-06-16 | Level 3 | Standards change
119185996 | other | Non-HFTD | Transmission | 2020-06-18 | 2025-06-18 | Level 3 | F |  | 2025-06-18 | Level 3
119187118 | other | Non-HFTD | Transmission | 2020-06-18 | 2022-06-18 | Level 3 | F | 2023-12-12 | 2025-06-18 | Level 3 | Standards change
119188207 | other | Non-HFTD | Transmission | 2020-06-18 | 2022-06-18 | Level 3 | F | 2023-12-12 | 2025-06-18 | Level 3 | Standards change
119189713 | other | Non-HFTD | Transmission | 2020-06-18 | 2025-06-18 | Level 3 | F |  | 2025-06-18 | Level 3
119196818 | other | Non-HFTD | Transmission | 2020-06-22 | 2022-06-22 | Level 3 | F | 2024-05-08 | 2025-06-22 | Level 3 | GO 165 Inspection
119196919 | other | HFTD Tier 2 | Transmission | 2020-06-19 | 2022-06-19 | Level 3 | F | 2023-04-14 | 2025-06-19 | Level 3 | Standards change
119196941 | other | Non-HFTD | Transmission | 2020-06-22 | 2022-06-22 | Level 3 | F | 2024-05-14 | 2025-06-22 | Level 3 | GO 165 Inspection
119199274 | other | HFTD Tier 2 | Transmission | 2020-06-22 | 2022-06-22 | Level 3 | F | 2024-04-16 | 2025-06-22 | Level 3 | GO 165 Inspection
119201788 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2024-10-29 | 2025-06-23 | Level 3 | GO 165 Inspection
119203675 | pole | Non-HFTD | Transmission | 2020-06-23 | 2021-06-23 | Level 2 | E | 2024-10-17 | 2023-06-23 | Level 2 | GO 165 Inspection
119203957 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2023-12-28 | 2025-06-23 | Level 3 | Standards change
119204728 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2023-12-12 | 2025-06-23 | Level 3 | Standards change
119205254 | other | Non-HFTD | Transmission | 2020-06-24 | 2022-06-24 | Level 3 | F | 2024-04-06 | 2025-06-24 | Level 3 | Standards change
119205383 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2023-01-24 | 2025-06-23 | Level 3 | Standards change
119205386 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2024-01-10 | 2025-06-23 | Level 3 | Standards change
119205389 | insulator and brushing | Non-HFTD | Transmission | 2020-06-23 | 2021-06-23 | Level 2 | E | 2024-10-16 | 2023-06-23 | Level 2 | Field Safety Reassessment
119205472 | other | Non-HFTD | Transmission | 2020-06-24 | 2022-06-24 | Level 3 | F | 2024-01-18 | 2025-06-24 | Level 3 | Standards change
119205993 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2024-01-10 | 2025-06-23 | Level 3 | Standards change
119207668 | pole | Non-HFTD | Transmission | 2020-04-21 | 2021-04-21 | Level 2 | E | 2023-03-16 | 2023-04-21 | Level 2 | Field Safety Reassessment
119208046 | other | Non-HFTD | Transmission | 2020-06-24 | 2022-06-24 | Level 3 | F | 2024-01-05 | 2025-06-24 | Level 3 | Standards change
119208356 | anchor/guy | Non-HFTD | Transmission | 2020-06-23 | 2021-06-23 | Level 2 | E | 2024-10-24 | 2025-06-23 | Level 3 | GO 165 Inspection
119208891 | pole | Non-HFTD | Transmission | 2020-06-24 | 2021-06-24 | Level 2 | E | 2024-01-19 | 2025-06-24 | Level 3 | Standards change
119209976 | pole | Non-HFTD | Transmission | 2020-06-24 | 2021-06-24 | Level 2 | E | 2024-10-24 | 2023-06-24 | Level 2 | GO 165 Inspection
119209977 | pole | Non-HFTD | Transmission | 2020-06-24 | 2021-06-24 | Level 2 | E | 2024-10-24 | 2023-06-24 | Level 2 | GO 165 Inspection
119211531 | other | Non-HFTD | Transmission | 2020-06-24 | 2022-06-24 | Level 3 | F | 2024-10-09 | 2025-06-24 | Level 3 | GO 165 Inspection
119218019 | other | Non-HFTD | Transmission | 2020-06-25 | 2022-06-25 | Level 3 | F | 2024-01-04 | 2025-06-25 | Level 3 | Standards change
119218417 | other | Non-HFTD | Transmission | 2020-06-25 | 2022-06-25 | Level 3 | F | 2023-01-10 | 2025-06-25 | Level 3 | Standards change
119219888 | other | Non-HFTD | Transmission | 2020-06-25 | 2022-06-25 | Level 3 | F | 2023-12-07 | 2025-06-25 | Level 3 | Standards change
119220597 | anchor/guy | Non-HFTD | Transmission | 2020-06-25 | 2021-06-25 | Level 2 | E | 2024-02-01 | 2025-06-25 | Level 3 | Standards change
119220867 | anchor/guy | Non-HFTD | Transmission | 2020-06-25 | 2021-06-25 | Level 2 | E | 2024-01-25 | 2025-06-25 | Level 3 | Standards change
119220972 | other | Non-HFTD | Transmission | 2020-06-25 | 2023-06-25 | Level 2 | E | 2024-11-06 | 2021-06-25 | Level 2 | Field Safety Reassessment
119221236 | other | HFTD Tier 2 | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-05-19 | 2025-06-26 | Level 3 | GO 165 Inspection
119221475 | pole | Non-HFTD | Transmission | 2020-06-25 | 2021-06-25 | Level 2 | E | 2024-08-26 | 2023-06-25 | Level 2 | Field Safety Reassessment
119222213 | other | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-04-06 | 2025-06-26 | Level 3 | Standards change
119222432 | anchor/guy | Non-HFTD | Transmission | 2020-06-24 | 2021-06-24 | Level 2 | E | 2024-10-03 | 2025-06-24 | Level 3 | GO 165 Inspection
119222565 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2024-07-16 | 2025-06-23 | Level 3 | GO 165 Inspection
119222626 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2023-12-12 | 2025-06-23 | Level 3 | Standards change
119222832 | other | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-01-02 | 2025-06-26 | Level 3 | Standards change
119222996 | other | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-04-06 | 2025-06-26 | Level 3 | Standards change
119227794 | other | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-10-17 | 2025-06-26 | Level 3 | GO 165 Inspection
119228276 | insulator and brushing | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2024-08-22 | 2023-06-26 | Level 2 | Field Safety Reassessment
119230357 | pole | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-10-25 | 2023-06-29 | Level 2 | GO 165 Inspection
119230616 | pole | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-11-01 | 2025-06-29 | Level 3 | GO 165 Inspection
119230743 | pole | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-08-16 | 2023-06-29 | Level 2 | GO 165 Inspection
119231220 | other | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-04-06 | 2025-06-26 | Level 3 | Standards change
119231481 | anchor/guy | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2024-01-25 | 2025-06-26 | Level 3 | Standards change
119231850 | pole | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-01-31 | 2025-06-29 | Level 3 | Standards change
119231971 | insulator and brushing | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-09-30 | 2023-06-29 | Level 2 | GO 165 Inspection
119231976 | other | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2024-04-06 | 2025-06-26 | Level 3 | Standards change
119232511 | anchor/guy | Non-HFTD | Transmission | 2020-06-25 | 2021-06-25 | Level 2 | E | 2024-01-18 | 2025-06-25 | Level 3 | Standards change
119232718 | insulator and brushing | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2022-12-21 | 2023-06-27 | Level 2 | Standards change
119232772 | other | HFTD Tier 2 | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-05-15 | 2025-06-29 | Level 3 | GO 165 Inspection
119232783 | pole | Non-HFTD | Transmission | 2020-06-24 | 2022-06-24 | Level 3 | F | 2024-10-09 | 2025-06-24 | Level 3 | GO 165 Inspection
119233109 | anchor/guy | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2024-01-25 | 2025-06-26 | Level 3 | Standards change
119233507 | other | HFTD Tier 2 | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-05-20 | 2025-06-29 | Level 3 | GO 165 Inspection
119233630 | other | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2024-02-06 | 2025-06-26 | Level 3 | Standards change
119233718 | pole | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-07-30 | 2023-06-29 | Level 2 | Field Safety Reassessment
119233817 | pole | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2023-12-27 | 2025-06-26 | Level 3 | Standards change
119233829 | anchor/guy | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2024-12-06 | 2025-06-26 | Level 3 | Field Safety Reassessment
119234450 | insulator and brushing | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2024-12-06 | 2023-06-26 | Level 2 | Field Safety Reassessment
119234790 | anchor/guy | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2023-10-20 | 2025-06-29 | Level 3 | Standards change
119235079 | insulator and brushing | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-10-05 | 2023-06-29 | Level 2 | GO 165 Inspection
119235116 | other | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-10-17 | 2025-06-29 | Level 3 | GO 165 Inspection
119235158 | other | Non-HFTD | Transmission | 2020-06-25 | 2022-06-25 | Level 3 | F | 2024-04-06 | 2025-06-25 | Level 3 | Standards change
119235394 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-10-17 | 2025-06-29 | Level 3 | GO 165 Inspection
119235414 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-04-06 | 2025-06-29 | Level 3 | Standards change
119235611 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-04-06 | 2025-06-29 | Level 3 | Standards change
119235612 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-01-09 | 2025-06-29 | Level 3 | Standards change
119235614 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-06-07 | 2025-06-29 | Level 3 | GO 165 Inspection
119236403 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-10-15 | 2025-06-29 | Level 3 | GO 165 Inspection
119236699 | other | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-04-06 | 2025-06-30 | Level 3 | Standards change
119236810 | other | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-09-11 | 2025-06-30 | Level 3 | GO 165 Inspection
119236939 | other | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-09-11 | 2025-06-30 | Level 3 | GO 165 Inspection
119237575 | crossarm | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2024-11-15 | 2023-06-30 | Level 2 | Field Safety Reassessment
119238432 | pole | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-09-28 | 2023-06-29 | Level 2 | GO 165 Inspection
119289907 | insulator and brushing | Non-HFTD | Transmission | 2020-06-30 | 2023-06-30 | Level 2 | E | 2024-10-29 | 2021-06-30 | Level 2 | GO 165 Inspection
119289931 | insulator and brushing | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2024-10-29 | 2023-06-30 | Level 2 | GO 165 Inspection
119290164 | other | Non-HFTD | Transmission | 2020-07-01 | 2022-07-01 | Level 3 | F | 2024-04-06 | 2025-07-01 | Level 3 | Standards change
119290400 | insulator and brushing | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2024-10-21 | 2023-06-28 | Level 2 | GO 165 Inspection
119290671 | other | HFTD Tier 2 | Transmission | 2020-07-01 | 2022-07-01 | Level 3 | F | 2024-05-24 | 2025-07-01 | Level 3 | GO 165 Inspection
119292994 | crossarm | Non-HFTD | Transmission | 2020-07-01 | 2021-07-01 | Level 2 | E | 2024-01-31 | 2023-07-01 | Level 2 | Field Safety Reassessment
119294057 | pole | Non-HFTD | Transmission | 2020-06-26 | 2021-06-26 | Level 2 | E | 2023-04-17 | 2023-06-26 | Level 2 | Standards change
119295044 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-07-15 | 2025-06-29 | Level 3 | GO 165 Inspection
119295516 | other | Non-HFTD | Transmission | 2020-07-01 | 2021-07-01 | Level 2 | E | 2023-08-02 | 2025-07-01 | Level 3 | Standards change
119295945 | anchor/guy | Non-HFTD | Transmission | 2020-07-01 | 2021-07-01 | Level 2 | E | 2024-02-01 | 2025-07-01 | Level 3 | Standards change
119296135 | other | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2023-04-17 | 2023-06-29 | Level 2 | Standards change
119296319 | other | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2024-09-28 | 2023-06-30 | Level 2 | GO 165 Inspection
119296347 | other | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-02-28 | 2025-06-30 | Level 3 | Standards change
119297341 | insulator and brushing | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2023-07-07 | 2023-06-30 | Level 2 | Standards change
119297349 | pole | Non-HFTD | Transmission | 2020-06-26 | 2022-06-26 | Level 3 | F | 2023-01-25 | 2025-06-26 | Level 3 | Standards change
119299203 | pole | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2023-10-02 | 2023-06-29 | Level 2 | Standards change
119300479 | pole | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2024-08-26 | 2023-06-30 | Level 2 | Field Safety Reassessment
119301057 | other | Non-HFTD | Transmission | 2020-06-29 | 2022-06-29 | Level 3 | F | 2024-02-28 | 2025-06-29 | Level 3 | Standards change
119301196 | pole | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-08-26 | 2023-06-29 | Level 2 | Field Safety Reassessment
119302064 | other | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-10-25 | 2025-06-30 | Level 3 | GO 165 Inspection
119303510 | other | Non-HFTD | Transmission | 2020-07-02 | 2022-07-02 | Level 3 | F | 2023-12-22 | 2025-07-02 | Level 3 | Standards change
119304432 | other | HFTD Tier 2 | Transmission | 2020-07-02 | 2022-07-02 | Level 3 | F | 2024-05-23 | 2025-07-02 | Level 3 | GO 165 Inspection
119305042 | other | Non-HFTD | Transmission | 2020-07-02 | 2022-07-02 | Level 3 | F | 2024-04-06 | 2025-07-02 | Level 3 | Standards change
119305044 | other | Non-HFTD | Transmission | 2020-07-02 | 2022-07-02 | Level 3 | F | 2023-08-03 | 2025-07-02 | Level 3 | Standards change
119308866 | insulator and brushing | Non-HFTD | Transmission | 2020-06-30 | 2021-06-30 | Level 2 | E | 2024-01-10 | 2025-06-30 | Level 3 | Standards change
119309326 | other | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-04-06 | 2025-06-30 | Level 3 | Standards change
119310127 | insulator and brushing | Non-HFTD | Transmission | 2020-06-29 | 2021-06-29 | Level 2 | E | 2024-11-20 | 2023-06-29 | Level 2 | Field Safety Reassessment
119310217 | other | Non-HFTD | Transmission | 2020-07-02 | 2022-07-02 | Level 3 | F | 2023-03-20 | 2025-07-02 | Level 3 | Standards change
119310350 | other | Non-HFTD | Transmission | 2020-07-02 | 2022-07-02 | Level 3 | F | 2024-08-27 | 2025-07-02 | Level 3 | GO 165 Inspection
119311410 | pole | Non-HFTD | Transmission | 2020-06-30 | 2022-06-30 | Level 3 | F | 2024-01-23 | 2025-06-30 | Level 3 | Standards change
119312651 | other | Non-HFTD | Transmission | 2020-07-02 | 2021-07-02 | Level 2 | E | 2023-05-03 | 2025-07-02 | Level 3 | Standards change
119313661 | other | Non-HFTD | Transmission | 2020-07-02 | 2021-07-02 | Level 2 | E | 2024-11-04 | 2025-07-02 | Level 3 | GO 165 Inspection
119316544 | other | Non-HFTD | Transmission | 2020-07-06 | 2022-07-06 | Level 3 | F | 2023-04-06 | 2025-07-06 | Level 3 | Standards change
119317070 | other | Non-HFTD | Transmission | 2020-07-02 | 2021-07-02 | Level 2 | E | 2023-03-31 | 2025-07-02 | Level 3 | Standards change
119317820 | other | Non-HFTD | Transmission | 2020-07-02 | 2021-07-02 | Level 2 | E | 2023-02-09 | 2025-07-02 | Level 3 | Standards change
119317838 | pole | Non-HFTD | Transmission | 2020-07-02 | 2021-07-02 | Level 2 | E | 2024-12-06 | 2023-07-02 | Level 2 | Field Safety Reassessment
119318296 | other | Non-HFTD | Transmission | 2020-07-06 | 2022-07-06 | Level 3 | F | 2023-08-03 | 2025-07-06 | Level 3 | Standards change
119320134 | insulator and brushing | Non-HFTD | Transmission | 2020-07-07 | 2021-07-07 | Level 2 | E | 2024-11-22 | 2023-07-07 | Level 2 | Field Safety Reassessment
119323694 | other | Non-HFTD | Transmission | 2020-07-07 | 2022-07-07 | Level 3 | F | 2024-02-16 | 2025-07-07 | Level 3 | Standards change
119323915 | other | Non-HFTD | Transmission | 2020-07-06 | 2022-07-06 | Level 3 | F | 2024-04-06 | 2025-07-06 | Level 3 | Standards change
119325266 | other | Non-HFTD | Transmission | 2020-07-07 | 2022-07-07 | Level 3 | F | 2024-04-06 | 2025-07-07 | Level 3 | Standards change
119326689 | other | Non-HFTD | Transmission | 2020-07-07 | 2022-07-07 | Level 3 | F | 2024-05-20 | 2025-07-07 | Level 3 | GO 165 Inspection
119326752 | other | Non-HFTD | Transmission | 2020-07-07 | 2022-07-07 | Level 3 | F | 2023-03-30 | 2025-07-07 | Level 3 | Standards change
119327779 | insulator and brushing | Non-HFTD | Transmission | 2020-07-07 | 2021-07-07 | Level 2 | E | 2024-11-15 | 2023-07-07 | Level 2 | Field Safety Reassessment
119328394 | anchor/guy | Non-HFTD | Transmission | 2020-07-06 | 2021-07-06 | Level 2 | E | 2023-08-08 | 2025-07-06 | Level 3 | Standards change
119330734 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2023-03-30 | 2025-07-08 | Level 3 | Standards change
119330929 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2023-03-30 | 2025-07-08 | Level 3 | Standards change
119331028 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-04-06 | 2025-07-08 | Level 3 | Standards change
119331413 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2023-07-13 | 2025-07-08 | Level 3 | Standards change
119332073 | pole | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-01-19 | 2025-07-08 | Level 3 | Standards change
119332076 | other | HFTD Tier 2 | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2023-04-04 | 2025-07-08 | Level 3 | Standards change
119332134 | insulator and brushing | Non-HFTD | Transmission | 2020-07-06 | 2021-07-06 | Level 2 | E | 2024-10-25 | 2023-07-06 | Level 2 | GO 165 Inspection
119334266 | pole | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-09-11 | 2025-07-08 | Level 3 | GO 165 Inspection
119335263 | other | HFTD Tier 2 | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-05-21 | 2025-07-08 | Level 3 | GO 165 Inspection
119336114 | other | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2023-03-28 | 2025-07-09 | Level 3 | Standards change
119337532 | other | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2024-04-06 | 2025-07-09 | Level 3 | Standards change
119338417 | pole | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2024-09-10 | 2023-07-09 | Level 2 | GO 165 Inspection
119338429 | insulator and brushing | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2024-09-10 | 2023-07-09 | Level 2 | GO 165 Inspection
119338669 | other | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2024-04-06 | 2025-07-09 | Level 3 | Standards change
119338804 | pole | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2023-02-03 | 2025-07-09 | Level 3 | Standards change
119339453 | other | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2024-12-02 | 2023-07-09 | Level 2 | Field Safety Reassessment
119339643 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-08-16 | 2025-07-08 | Level 3 | GO 165 Inspection
119340009 | other | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2024-04-06 | 2025-07-09 | Level 3 | Standards change
119340933 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-09-26 | 2025-07-08 | Level 3 | GO 165 Inspection
119340965 | pole | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2024-12-17 | 2023-07-09 | Level 2 | Field Safety Reassessment
119341180 | other | HFTD Tier 3 | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2023-04-01 | 2025-07-08 | Level 3 | GO 165 Inspection
119341326 | pole | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2024-03-20 | 2023-07-09 | Level 2 | Standards change
119341329 | pole | Non-HFTD | Transmission | 2020-07-09 | 2021-07-09 | Level 2 | E | 2024-03-20 | 2023-07-09 | Level 2 | Standards change
119341632 | switch | Non-HFTD | Transmission | 2020-07-08 | 2020-10-08 | Level 2 | E | 2023-08-16 | 2020-10-08 | Level 2 | Standards change
119341639 | splice | Non-HFTD | Transmission | 2020-07-08 | 2021-07-08 | Level 2 | E | 2024-02-01 | 2023-07-08 | Level 2 | Standards change
119341728 | other | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2024-11-15 | 2025-07-09 | Level 3 | GO 165 Inspection
119341898 | other | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2024-04-06 | 2025-07-09 | Level 3 | Standards change
119342040 | other | Non-HFTD | Transmission | 2020-07-07 | 2022-07-07 | Level 3 | F | 2024-04-06 | 2025-07-07 | Level 3 | Standards change
119342074 | other | Non-HFTD | Transmission | 2020-07-07 | 2022-07-07 | Level 3 | F | 2024-04-06 | 2025-07-07 | Level 3 | Standards change
119350378 | other | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2024-02-28 | 2025-07-09 | Level 3 | Standards change
119350656 | anchor/guy | Non-HFTD | Transmission | 2020-07-10 | 2021-07-10 | Level 2 | E | 2024-03-20 | 2025-07-10 | Level 3 | Standards change
119350898 | other | Non-HFTD | Transmission | 2020-07-10 | 2022-07-10 | Level 3 | F | 2024-11-12 | 2025-07-10 | Level 3 | GO 165 Inspection
119351174 | pole | Non-HFTD | Transmission | 2020-07-06 | 2022-07-06 | Level 3 | F | 2024-02-16 | 2025-07-06 | Level 3 | Standards change
119354590 | anchor/guy | Non-HFTD | Transmission | 2020-07-10 | 2021-07-10 | Level 2 | E | 2023-03-15 | 2025-07-10 | Level 3 | Standards change
119355171 | other | Non-HFTD | Transmission | 2020-07-10 | 2022-07-10 | Level 3 | F | 2024-04-06 | 2025-07-10 | Level 3 | Standards change
119355390 | other | Non-HFTD | Transmission | 2020-07-10 | 2022-07-10 | Level 3 | F | 2024-04-06 | 2025-07-10 | Level 3 | Standards change
119356419 | pole | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-03-28 | 2025-07-08 | Level 3 | GO 165 Inspection
119356578 | other | HFTD Tier 2 | Transmission | 2020-07-10 | 2022-07-10 | Level 3 | F | 2024-04-06 | 2025-07-10 | Level 3 | Standards change
119357062 | splice | Non-HFTD | Transmission | 2020-07-02 | 2021-07-02 | Level 2 | E | 2023-02-08 | 2023-07-02 | Level 2 | Standards change
119357525 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-02-28 | 2025-07-08 | Level 3 | Standards change
119357670 | other | Non-HFTD | Transmission | 2020-07-08 | 2022-07-08 | Level 3 | F | 2024-07-25 | 2025-07-08 | Level 3 | GO 165 Inspection
119357948 | pole | Non-HFTD | Transmission | 2020-07-09 | 2022-07-09 | Level 3 | F | 2023-02-02 | 2025-07-09 | Level 3 | Standards change
119358351 | other | HFTD Tier 3 | Transmission | 2020-07-10 | 2022-07-10 | Level 3 | F | 2024-04-06 | 2025-07-10 | Level 3 | Standards change
119360092 | pole | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2024-12-10 | 2023-07-13 | Level 2 | Field Safety Reassessment
119361223 | other | Non-HFTD | Transmission | 2020-07-13 | 2022-07-13 | Level 3 | F | 2024-08-03 | 2025-07-13 | Level 3 | GO 165 Inspection
119361645 | other | Non-HFTD | Transmission | 2020-07-13 | 2022-07-13 | Level 3 | F | 2024-08-06 | 2025-07-13 | Level 3 | GO 165 Inspection
119361721 | other | Non-HFTD | Transmission | 2020-07-01 | 2022-07-01 | Level 3 | F | 2024-04-06 | 2025-07-01 | Level 3 | Standards change
119361831 | other | Non-HFTD | Transmission | 2020-07-13 | 2022-07-13 | Level 3 | F | 2024-08-06 | 2025-07-13 | Level 3 | GO 165 Inspection
119362461 | pole | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2024-12-16 | 2023-07-13 | Level 2 | Field Safety Reassessment
119362693 | insulator and brushing | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2024-09-12 | 2023-07-13 | Level 2 | GO 165 Inspection
119363051 | other | Non-HFTD | Transmission | 2020-07-13 | 2025-07-13 | Level 2 | E | 2024-11-27 | 2023-07-13 | Level 2 | Field Safety Reassessment
119363128 | other | Non-HFTD | Transmission | 2020-07-13 | 2022-07-13 | Level 3 | F | 2024-08-29 | 2025-07-13 | Level 3 | GO 165 Inspection
119363336 | anchor/guy | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2023-02-11 | 2025-07-13 | Level 3 | Field Safety Reassessment
119363921 | other | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2024-07-25 | 2023-07-13 | Level 2 | GO 165 Inspection
119364336 | pole | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2023-07-21 | 2023-07-13 | Level 2 | Standards change
119366246 | splice | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2023-12-29 | 2023-07-13 | Level 2 | Standards change
119366698 | insulator and brushing | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2023-08-03 | 2025-07-14 | Level 3 | Standards change
119367580 | other | Non-HFTD | Transmission | 2020-07-14 | 2022-07-14 | Level 3 | F | 2024-08-12 | 2025-07-14 | Level 3 | GO 165 Inspection
119367977 | pole | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2024-10-15 | 2023-07-14 | Level 2 | Field Safety Reassessment
119368160 | pole | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2024-01-18 | 2023-07-14 | Level 2 | Field Safety Reassessment
119368262 | insulator and brushing | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2024-08-29 | 2023-07-14 | Level 2 | GO 165 Inspection
119368387 | other | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2024-11-27 | 2025-07-14 | Level 3 | Field Safety Reassessment
119368477 | insulator and brushing | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2024-08-27 | 2023-07-14 | Level 2 | GO 165 Inspection
119369125 | other | Non-HFTD | Transmission | 2020-07-14 | 2022-07-14 | Level 3 | F | 2024-10-28 | 2025-07-14 | Level 3 | GO 165 Inspection
119369293 | other | Non-HFTD | Transmission | 2020-07-14 | 2022-07-14 | Level 3 | F | 2024-04-06 | 2025-07-14 | Level 3 | Standards change
119370074 | crossarm | Non-HFTD | Transmission | 2020-07-14 | 2021-07-14 | Level 2 | E | 2024-08-06 | 2023-07-14 | Level 2 | GO 165 Inspection
119370267 | other | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2024-01-29 | 2025-07-13 | Level 3 | Standards change
119371851 | splice | Non-HFTD | Transmission | 2020-07-13 | 2021-07-13 | Level 2 | E | 2024-09-03 | 2023-07-13 | Level 2 | GO 165 Inspection
119372783 | pole | HFTD Tier 2 | Transmission | 2020-07-14 | 2022-07-14 | Level 3 | F | 2023-04-03 | 2025-07-14 | Level 3 | GO 165 Inspection
119373012 | insulator and brushing | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-10-07 | 2023-07-15 | Level 2 | GO 165 Inspection
119373592 | pole | Non-HFTD | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2023-03-01 | 2025-07-15 | Level 3 | Standards change
119373616 | other | Non-HFTD | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2023-01-20 | 2025-07-15 | Level 3 | Standards change
119373803 | other | Non-HFTD | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2023-01-20 | 2025-07-15 | Level 3 | Standards change
119374297 | other | Non-HFTD | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2023-01-19 | 2025-07-15 | Level 3 | Standards change
119374970 | other | Non-HFTD | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2023-01-19 | 2025-07-15 | Level 3 | Standards change
119375425 | pole | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2023-10-16 | 2023-07-15 | Level 2 | Field Safety Reassessment
119376445 | pole | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-08-15 | 2023-07-15 | Level 2 | GO 165 Inspection
119376719 | other | Non-HFTD | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2024-09-24 | 2025-07-15 | Level 3 | GO 165 Inspection
119377469 | other | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-10-07 | 2021-07-15 | Level 2 | GO 165 Inspection
119377472 | other | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-11-04 | 2021-07-15 | Level 2 | Field Safety Reassessment
119377486 | insulator and brushing | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-10-07 | 2023-07-15 | Level 2 | GO 165 Inspection
119377487 | insulator and brushing | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-10-04 | 2023-07-15 | Level 2 | GO 165 Inspection
119378443 | anchor/guy | Non-HFTD | Transmission | 2020-07-15 | 2021-07-15 | Level 2 | E | 2024-11-12 | 2025-07-15 | Level 3 | Field Safety Reassessment
119378457 | other | HFTD Tier 2 | Transmission | 2020-07-15 | 2022-07-15 | Level 3 | F | 2023-06-21 | 2025-07-15 | Level 3 | Standards change
119379281 | other | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2024-11-20 | 2025-07-16 | Level 3 | GO 165 Inspection
119379681 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2023-01-20 | 2025-07-16 | Level 3 | Standards change
119379792 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2023-01-20 | 2025-07-16 | Level 3 | Standards change
119380389 | pole | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2024-08-19 | 2025-07-16 | Level 3 | GO 165 Inspection
119380884 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-01-26 | 2025-07-16 | Level 3 | Standards change
119380924 | other | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2023-06-05 | 2025-07-16 | Level 3 | Standards change
119380929 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-10-11 | 2025-07-16 | Level 3 | GO 165 Inspection
119381270 | pole | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-10-14 | 2023-07-16 | Level 2 | GO 165 Inspection
119381309 | other | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2024-01-09 | 2025-07-16 | Level 3 | Standards change
119381343 | pole | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2023-12-15 | 2025-07-16 | Level 3 | Standards change
119382129 | other | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2023-01-20 | 2025-07-16 | Level 3 | Standards change
119421617 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-12-02 | 2025-07-16 | Level 3 | GO 165 Inspection
119464336 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2023-01-24 | 2025-07-17 | Level 3 | Standards change
119464368 | pole | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-12-21 | 2023-07-16 | Level 2 | Field Safety Reassessment
119464370 | pole | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2024-11-22 | 2023-07-17 | Level 2 | Field Safety Reassessment
119464416 | pole | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2023-03-23 | 2021-07-17 | Level 2 | Field Safety Reassessment
119464473 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2023-12-22 | 2025-07-17 | Level 3 | Standards change
119464876 | other | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2024-04-06 | 2025-07-16 | Level 3 | Standards change
119466285 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2023-01-23 | 2025-07-17 | Level 3 | Standards change
119466394 | other | HFTD Tier 2 | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2024-06-04 | 2025-07-16 | Level 3 | GO 165 Inspection
119466847 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-09-24 | 2025-07-17 | Level 3 | GO 165 Inspection
119466886 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-04-06 | 2025-07-17 | Level 3 | Standards change
119466934 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-02-01 | 2025-07-16 | Level 3 | Standards change
119467254 | pole | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-09-24 | 2025-07-17 | Level 3 | GO 165 Inspection
119467428 | pole | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2024-03-19 | 2023-07-17 | Level 2 | Standards change
119467444 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-09-24 | 2025-07-17 | Level 3 | GO 165 Inspection
119467550 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-04-06 | 2025-07-17 | Level 3 | Standards change
119467551 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-04-06 | 2025-07-17 | Level 3 | Standards change
119467706 | insulator and brushing | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2024-03-19 | 2023-07-17 | Level 2 | Standards change
119467825 | anchor/guy | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-01-29 | 2025-07-16 | Level 3 | Standards change
119467874 | anchor/guy | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2023-12-29 | 2025-07-17 | Level 3 | Standards change
119467904 | anchor/guy | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2023-01-23 | 2025-07-17 | Level 3 | Standards change
119468048 | insulator and brushing | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-08-29 | 2023-07-16 | Level 2 | Field Safety Reassessment
119468540 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-09-24 | 2025-07-17 | Level 3 | GO 165 Inspection
119469535 | pole | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2024-12-21 | 2021-07-16 | Level 2 | Field Safety Reassessment
119469634 | other | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2024-10-05 | 2021-07-17 | Level 2 | GO 165 Inspection
119470193 | other | Non-HFTD | Transmission | 2020-07-17 | 2023-07-17 | Level 2 | E | 2024-05-20 | 2021-07-17 | Level 2 | Field Safety Reassessment
119470219 | insulator and brushing | Non-HFTD | Transmission | 2020-07-16 | 2021-07-16 | Level 2 | E | 2023-09-05 | 2023-07-16 | Level 2 | Standards change
119471004 | other | Non-HFTD | Transmission | 2020-07-16 | 2022-07-16 | Level 3 | F | 2024-02-29 | 2025-07-16 | Level 3 | Standards change
119471061 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-02-21 | 2025-07-17 | Level 3 | Standards change
119472907 | insulator and brushing | Non-HFTD | Transmission | 2020-07-17 | 2021-07-17 | Level 2 | E | 2024-04-20 | 2025-07-17 | Level 3 | GO 165 Inspection
119474233 | other | Non-HFTD | Transmission | 2020-07-17 | 2022-07-17 | Level 3 | F | 2024-04-06 | 2025-07-17 | Level 3 | Standards change
119474757 | anchor/guy | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-08-12 | 2023-07-20 | Level 2 | GO 165 Inspection
119475126 | anchor/guy | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-01-26 | 2025-07-20 | Level 3 | Standards change
119475127 | pole | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-04-16 | 2023-07-20 | Level 2 | Field Safety Reassessment
119476424 | other | Non-HFTD | Transmission | 2020-07-20 | 2022-07-20 | Level 3 | F | 2024-04-06 | 2025-07-20 | Level 3 | Standards change
119476513 | pole | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2023-09-26 | 2021-07-20 | Level 2 | Standards change
119476551 | anchor/guy | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-11-23 | 2023-07-20 | Level 2 | Field Safety Reassessment
119476750 | splice | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2023-06-26 | 2023-07-20 | Level 2 | Standards change
119476930 | other | Non-HFTD | Transmission | 2020-07-20 | 2022-07-20 | Level 3 | F | 2021-06-16 | 2025-07-20 | Level 3 | GO 165 Inspection
119477045 | insulator and brushing | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-10-05 | 2023-07-20 | Level 2 | GO 165 Inspection
119477266 | other | Non-HFTD | Transmission | 2020-07-20 | 2022-07-20 | Level 3 | F | 2023-12-22 | 2025-07-20 | Level 3 | Standards change
119477314 | other | Non-HFTD | Transmission | 2020-07-20 | 2022-07-20 | Level 3 | F | 2023-12-22 | 2025-07-20 | Level 3 | Standards change
119477351 | pole | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-12-20 | 2023-07-20 | Level 2 | Field Safety Reassessment
119477807 | anchor/guy | Non-HFTD | Transmission | 2020-07-20 | 2021-07-20 | Level 2 | E | 2024-10-23 | 2023-07-20 | Level 2 | GO 165 Inspection
119478818 | other | Non-HFTD | Transmission | 2020-07-20 | 2022-07-20 | Level 3 | F | 2024-04-06 | 2025-07-20 | Level 3 | Standards change
119479437 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2023-01-24 | 2025-07-21 | Level 3 | Standards change
119479615 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2024-08-19 | 2025-07-21 | Level 3 | GO 165 Inspection
119479657 | other | Non-HFTD | Transmission | 2020-07-21 | 2021-07-21 | Level 2 | E | 2023-03-10 | 2021-07-21 | Level 2 | Standards change
119479827 | pole | Non-HFTD | Transmission | 2020-07-21 | 2025-07-21 | Level 2 | E | 2024-09-03 | 2023-07-21 | Level 2 | GO 165 Inspection
119479862 | other | Non-HFTD | Transmission | 2020-07-21 | 2021-07-21 | Level 2 | E | 2024-10-05 | 2021-07-21 | Level 2 | GO 165 Inspection
119480415 | other | Non-HFTD | Transmission | 2020-07-20 | 2022-07-20 | Level 3 | F | 2024-04-06 | 2025-07-20 | Level 3 | Standards change
119480438 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2024-04-06 | 2025-07-21 | Level 3 | Standards change
119480509 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2023-12-22 | 2025-07-21 | Level 3 | Standards change
119480807 | pole | Non-HFTD | Transmission | 2020-07-21 | 2021-07-21 | Level 2 | E | 2024-12-20 | 2021-07-21 | Level 2 | Field Safety Reassessment
119480870 | pole | Non-HFTD | Transmission | 2020-07-21 | 2021-07-21 | Level 2 | E | 2024-09-23 | 2023-07-21 | Level 2 | GO 165 Inspection
119481196 | pole | Non-HFTD | Transmission | 2020-07-21 | 2025-07-21 | Level 2 | E | 2024-09-06 | 2023-07-21 | Level 2 | GO 165 Inspection
119482961 | pole | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2023-12-22 | 2025-07-21 | Level 3 | Standards change
119482980 | pole | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2023-12-22 | 2025-07-21 | Level 3 | Standards change
119483276 | insulator and brushing | Non-HFTD | Transmission | 2020-07-21 | 2021-07-21 | Level 2 | E | 2024-12-05 | 2023-07-21 | Level 2 | Field Safety Reassessment
119483326 | insulator and brushing | Non-HFTD | Transmission | 2020-07-21 | 2021-07-21 | Level 2 | E | 2023-04-12 | 2025-07-21 | Level 3 | Standards change
119483367 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2024-04-06 | 2025-07-21 | Level 3 | Standards change
119483582 | anchor/guy | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2024-01-31 | 2025-07-21 | Level 3 | Standards change
119485087 | splice | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2023-01-20 | 2023-07-20 | Level 2 | Standards change
119485248 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2024-09-03 | 2025-07-21 | Level 3 | GO 165 Inspection
119485684 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-11-27 | 2023-07-22 | Level 2 | GO 165 Inspection
119485685 | other | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-11-27 | 2021-07-22 | Level 2 | GO 165 Inspection
119485694 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-10-05 | 2023-07-22 | Level 2 | GO 165 Inspection
119485700 | other | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-10-05 | 2021-07-22 | Level 2 | GO 165 Inspection
119486046 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2022-12-01 | 2021-07-22 | Level 2 | Field Safety Reassessment
119486462 | other | Non-HFTD | Transmission | 2020-07-21 | 2022-07-21 | Level 3 | F | 2024-08-29 | 2025-07-21 | Level 3 | GO 165 Inspection
119486644 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-04-19 | 2025-07-22 | Level 3 | GO 165 Inspection
119486650 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2023-01-12 | 2025-07-22 | Level 3 | Standards change
119486855 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2023-08-01 | 2025-07-22 | Level 3 | Standards change
119487380 | pole | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-09-06 | 2025-07-22 | Level 3 | GO 165 Inspection
119487873 | pole | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-10-25 | 2025-07-22 | Level 3 | GO 165 Inspection
119488253 | pole | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-08-23 | 2025-07-22 | Level 3 | GO 165 Inspection
119488379 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-12-05 | 2023-07-22 | Level 2 | Field Safety Reassessment
119488397 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-12-04 | 2023-07-22 | Level 2 | Field Safety Reassessment
119488398 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-12-05 | 2023-07-22 | Level 2 | Field Safety Reassessment
119488714 | pole | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2023-02-01 | 2025-07-22 | Level 3 | Standards change
119488978 | pole | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-09-06 | 2025-07-22 | Level 3 | GO 165 Inspection
119489496 | pole | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-09-20 | 2023-07-22 | Level 2 | GO 165 Inspection
119489498 | pole | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-09-20 | 2023-07-22 | Level 2 | GO 165 Inspection
119489499 | pole | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-09-20 | 2023-07-22 | Level 2 | GO 165 Inspection
119489624 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-04-06 | 2025-07-22 | Level 3 | Standards change
119489791 | pole | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-11-26 | 2023-07-22 | Level 2 | Field Safety Reassessment
119491998 | other | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2024-06-05 | 2025-07-23 | Level 3 | GO 165 Inspection
119492232 | anchor/guy | Non-HFTD | Transmission | 2020-07-23 | 2021-07-23 | Level 2 | E | 2024-01-25 | 2025-07-23 | Level 3 | Standards change
119492261 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2024-09-26 | 2025-07-23 | Level 3 | GO 165 Inspection
119492404 | pole | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-08-29 | 2023-07-22 | Level 2 | Field Safety Reassessment
119493105 | pole | Non-HFTD | Transmission | 2020-07-23 | 2021-07-23 | Level 2 | E | 2024-09-06 | 2023-07-23 | Level 2 | GO 165 Inspection
119493299 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-04-06 | 2025-07-22 | Level 3 | Standards change
119493407 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2024-06-24 | 2025-07-23 | Level 3 | GO 165 Inspection
119493475 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2024-02-01 | 2025-07-23 | Level 3 | GO 165 Inspection
119494717 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2023-02-15 | 2025-07-23 | Level 3 | Standards change
119494898 | anchor/guy | Non-HFTD | Transmission | 2020-07-23 | 2021-07-23 | Level 2 | E | 2023-01-20 | 2025-07-23 | Level 3 | Standards change
119495372 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2023-12-22 | 2025-07-23 | Level 3 | Standards change
119495380 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2024-08-19 | 2025-07-23 | Level 3 | GO 165 Inspection
119495460 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-03-19 | 2023-07-22 | Level 2 | Standards change
119495497 | other | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2023-12-19 | 2025-07-23 | Level 3 | Standards change
119495512 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2023-12-19 | 2025-07-23 | Level 3 | Standards change
119495661 | other | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2024-01-31 | 2025-07-22 | Level 3 | Standards change
119495906 | other | Non-HFTD | Transmission | 2020-07-23 | 2023-07-23 | Level 2 | E | 2024-11-26 | 2025-07-23 | Level 3 | Field Safety Reassessment
119495934 | pole | Non-HFTD | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2024-03-20 | 2025-07-23 | Level 3 | GO 165 Inspection
119497821 | other | Non-HFTD | Transmission | 2020-07-23 | 2021-07-23 | Level 2 | E | 2024-03-19 | 2025-07-23 | Level 3 | Standards change
119498146 | pole | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-08-27 | 2025-07-24 | Level 3 | GO 165 Inspection
119498192 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F | 2024-04-06 | 2025-07-22 | Level 3 | Standards change
119498516 | insulator and brushing | Non-HFTD | Transmission | 2020-07-23 | 2021-07-23 | Level 2 | E | 2023-06-14 | 2023-07-23 | Level 2 | Standards change
119498759 | insulator and brushing | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-12-04 | 2023-07-24 | Level 2 | Field Safety Reassessment
119498821 | pole | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-10-25 | 2023-07-24 | Level 2 | GO 165 Inspection
119498822 | other | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-10-25 | 2025-07-24 | Level 3 | GO 165 Inspection
119498991 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2023-01-20 | 2025-07-24 | Level 3 | Standards change
119499179 | insulator and brushing | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-10-31 | 2023-07-24 | Level 2 | Field Safety Reassessment
119499242 | pole | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2023-11-30 | 2025-07-24 | Level 3 | Standards change
119501381 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2023-01-12 | 2025-07-24 | Level 3 | Standards change
119501483 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-09-06 | 2025-07-24 | Level 3 | GO 165 Inspection
119501767 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2023-01-24 | 2025-07-24 | Level 3 | Standards change
119502357 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-09-03 | 2025-07-24 | Level 3 | GO 165 Inspection
119503124 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-04-06 | 2025-07-24 | Level 3 | Standards change
119503125 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-04-06 | 2025-07-24 | Level 3 | Standards change
119503786 | pole | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-11-23 | 2023-07-24 | Level 2 | Field Safety Reassessment
119504368 | insulator and brushing | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-08-30 | 2023-07-24 | Level 2 | GO 165 Inspection
119504601 | pole | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-10-02 | 2023-07-24 | Level 2 | GO 165 Inspection
119505133 | pole | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2022-12-14 | 2023-07-24 | Level 2 | Standards change
119505418 | pole | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-05-23 | 2021-07-24 | Level 2 | Field Safety Reassessment
119506321 | crossarm | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-03-19 | 2023-07-24 | Level 2 | Standards change
119506418 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2022-12-09 | 2025-07-24 | Level 3 | Standards change
119507402 | pole | Non-HFTD | Transmission | 2020-07-24 | 2021-07-24 | Level 2 | E | 2024-01-16 | 2023-07-24 | Level 2 | Standards change
119508878 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-09-06 | 2025-07-24 | Level 3 | GO 165 Inspection
119509272 | other | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-09-20 | 2025-07-27 | Level 3 | GO 165 Inspection
119509356 | pole | Non-HFTD | Transmission | 2020-07-24 | 2025-07-24 | Level 2 | E | 2024-09-06 | 2023-07-24 | Level 2 | GO 165 Inspection
119509399 | anchor/guy | Non-HFTD | Transmission | 2020-07-27 | 2025-07-27 | Level 3 | F | 2024-10-23 | 2021-01-27 | Level 2 | GO 165 Inspection
119510071 | pole | Non-HFTD | Transmission | 2020-05-12 | 2021-05-12 | Level 2 | E | 2024-11-05 | 2023-05-12 | Level 2 | GO 165 Inspection
119510435 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-04-06 | 2025-07-24 | Level 3 | Standards change
119511301 | pole | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-01-30 | 2025-07-27 | Level 3 | GO 165 Inspection
119511640 | pole | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-01-16 | 2025-07-27 | Level 3 | Standards change
119511696 | other | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-09-04 | 2025-07-27 | Level 3 | GO 165 Inspection
119512990 | insulator and brushing | Non-HFTD | Transmission | 2020-07-26 | 2021-07-26 | Level 2 | E | 2024-02-02 | 2025-07-26 | Level 3 | Standards change
119513020 | other | Non-HFTD | Transmission | 2020-07-27 | 2021-07-27 | Level 2 | E | 2023-03-11 | 2025-07-27 | Level 3 | Standards change
119513463 | anchor/guy | Non-HFTD | Transmission | 2020-07-27 | 2021-07-27 | Level 2 | E | 2024-07-25 | 2023-07-27 | Level 2 | GO 165 Inspection
119514678 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-09-05 | 2025-07-28 | Level 3 | GO 165 Inspection
119514879 | other | Non-HFTD | Transmission | 2020-07-27 | 2021-07-27 | Level 2 | E | 2024-10-07 | 2021-07-27 | Level 2 | GO 165 Inspection
119514882 | pole | Non-HFTD | Transmission | 2020-07-27 | 2021-07-27 | Level 2 | E | 2024-10-07 | 2023-07-27 | Level 2 | GO 165 Inspection
119515114 | pole | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-03-19 | 2023-07-28 | Level 2 | Standards change
119515317 | pole | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-12-13 | 2023-07-28 | Level 2 | Field Safety Reassessment
119515436 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-10-01 | 2025-07-28 | Level 3 | GO 165 Inspection
119515506 | other | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-08-30 | 2025-07-28 | Level 3 | GO 165 Inspection
119515590 | other | Non-HFTD | Transmission | 2020-07-22 | 2022-07-22 | Level 3 | F |  | 2025-07-22 | Level 3
119515593 | insulator and brushing | Non-HFTD | Transmission | 2020-07-22 | 2021-07-22 | Level 2 | E | 2023-05-23 | 2023-07-22 | Level 2 | Standards change
119515639 | other | HFTD Tier 3 | Transmission | 2020-07-23 | 2022-07-23 | Level 3 | F | 2023-04-03 | 2025-07-23 | Level 3 | GO 165 Inspection
119515659 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-04-06 | 2025-07-28 | Level 3 | Standards change
119515957 | other | Non-HFTD | Transmission | 2020-07-24 | 2022-07-24 | Level 3 | F | 2024-09-20 | 2025-07-24 | Level 3 | GO 165 Inspection
119516786 | insulator and brushing | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-01-23 | 2023-07-28 | Level 2 | Standards change
119517106 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-04-06 | 2025-07-28 | Level 3 | Standards change
119517267 | pole | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2022-12-14 | 2023-07-28 | Level 2 | Standards change
119517725 | pole | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-01-17 | 2023-07-28 | Level 2 | Standards change
119517817 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-04-06 | 2025-07-28 | Level 3 | Standards change
119518370 | pole | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-09-13 | 2025-07-28 | Level 3 | GO 165 Inspection
119518986 | insulator and brushing | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-01-10 | 2023-07-28 | Level 2 | Standards change
119519049 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-02-14 | 2025-07-28 | Level 3 | Standards change
119519080 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-04-06 | 2025-07-28 | Level 3 | Standards change
119519396 | pole | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-01-03 | 2025-07-28 | Level 3 | Standards change
119520035 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-01-10 | 2025-07-29 | Level 3 | Standards change
119520126 | pole | Non-HFTD | Transmission | 2020-07-28 | 2023-07-28 | Level 2 | E | 2024-11-06 | 2020-10-28 | Level 2 | GO 165 Inspection
119520262 | pole | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-10-02 | 2023-07-29 | Level 2 | GO 165 Inspection
119520309 | insulator and brushing | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-08-31 | 2023-07-29 | Level 2 | GO 165 Inspection
119520582 | pole | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-03-19 | 2023-07-28 | Level 2 | Standards change
119520585 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-04-06 | 2025-07-28 | Level 3 | Standards change
119520953 | other | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-11-25 | 2021-07-29 | Level 2 | Field Safety Reassessment
119521302 | insulator and brushing | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-08-30 | 2023-07-29 | Level 2 | GO 165 Inspection
119521335 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-10-28 | 2025-07-29 | Level 3 | GO 165 Inspection
119521604 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-09-11 | 2025-07-29 | Level 3 | GO 165 Inspection
119521860 | pole | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-11-05 | 2021-07-29 | Level 2 | Field Safety Reassessment
119521955 | pole | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-03-19 | 2023-07-29 | Level 2 | Standards change
119521994 | other | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-08-29 | 2025-07-29 | Level 3 | GO 165 Inspection
119522493 | anchor/guy | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-01-18 | 2025-07-29 | Level 3 | Standards change
119522497 | insulator and brushing | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2023-08-23 | 2023-07-29 | Level 2 | Standards change
119522680 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-04-06 | 2025-07-29 | Level 3 | Standards change
119523128 | pole | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-03-20 | 2025-07-29 | Level 3 | GO 165 Inspection
119524004 | anchor/guy | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-04-06 | 2025-07-29 | Level 3 | Standards change
119524343 | insulator and brushing | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-03-19 | 2023-07-29 | Level 2 | Standards change
119524634 | insulator and brushing | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-08-05 | 2023-07-29 | Level 2 | GO 165 Inspection
119524739 | pole | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-01-17 | 2025-07-29 | Level 3 | Standards change
119524779 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2023-01-23 | 2025-07-29 | Level 3 | Standards change
119524844 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-01-08 | 2025-07-29 | Level 3 | Standards change
119526898 | other | Non-HFTD | Transmission | 2020-07-30 | 2022-07-30 | Level 3 | F | 2024-09-13 | 2025-07-30 | Level 3 | GO 165 Inspection
119526930 | anchor/guy | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2024-07-09 | 2025-07-30 | Level 3 | GO 165 Inspection
119527006 | other | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2024-09-13 | 2025-07-30 | Level 3 | GO 165 Inspection
119527251 | insulator and brushing | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-03-19 | 2023-07-28 | Level 2 | Standards change
119527612 | other | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2024-10-16 | 2021-07-30 | Level 2 | GO 165 Inspection
119527832 | other | Non-HFTD | Transmission | 2020-07-30 | 2022-07-30 | Level 3 | F | 2024-04-06 | 2025-07-30 | Level 3 | Standards change
119529041 | insulator and brushing | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2024-12-06 | 2023-07-30 | Level 2 | Field Safety Reassessment
119529281 | anchor/guy | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2024-08-12 | 2025-07-30 | Level 3 | GO 165 Inspection
119529288 | other | Non-HFTD | Transmission | 2020-07-30 | 2022-07-30 | Level 3 | F | 2024-04-06 | 2025-07-30 | Level 3 | Standards change
119529325 | pole | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2022-12-13 | 2021-07-30 | Level 2 | Field Safety Reassessment
119529504 | other | Non-HFTD | Transmission | 2020-07-30 | 2022-07-30 | Level 3 | F | 2023-12-06 | 2025-07-30 | Level 3 | Standards change
119529779 | pole | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2024-07-22 | 2023-07-30 | Level 2 | GO 165 Inspection
119530327 | other | Non-HFTD | Transmission | 2020-07-30 | 2022-07-30 | Level 3 | F | 2024-04-06 | 2025-07-30 | Level 3 | Standards change
119534692 | pole | Non-HFTD | Transmission | 2020-07-31 | 2021-07-31 | Level 2 | E | 2023-09-23 | 2023-07-31 | Level 2 | Field Safety Reassessment
119534732 | other | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2023-12-04 | 2025-07-31 | Level 3 | Standards change
119534796 | pole | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2023-12-06 | 2025-07-31 | Level 3 | Standards change
119534989 | pole | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2024-09-23 | 2025-07-31 | Level 3 | GO 165 Inspection
119535346 | other | Non-HFTD | Transmission | 2020-07-29 | 2022-07-29 | Level 3 | F | 2024-04-06 | 2025-07-29 | Level 3 | Standards change
119535944 | other | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2024-04-06 | 2025-07-31 | Level 3 | Standards change
119536151 | other | Non-HFTD | Transmission | 2020-07-31 | 2021-07-31 | Level 2 | E | 2023-06-06 | 2025-07-31 | Level 3 | Standards change
119536273 | pole | Non-HFTD | Transmission | 2020-07-31 | 2021-07-31 | Level 2 | E | 2024-09-30 | 2023-07-31 | Level 2 | GO 165 Inspection
119536997 | pole | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2024-02-14 | 2025-07-31 | Level 3 | Standards change
119538661 | other | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2024-04-06 | 2025-07-31 | Level 3 | Standards change
119542254 | pole | Non-HFTD | Transmission | 2020-08-01 | 2021-08-01 | Level 2 | E | 2024-07-24 | 2023-08-01 | Level 2 | GO 165 Inspection
119549636 | anchor/guy | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2023-09-14 | 2025-08-03 | Level 3 | Standards change
119549742 | other | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2024-10-15 | 2023-08-03 | Level 2 | GO 165 Inspection
119550223 | other | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2024-07-10 | 2021-08-03 | Level 2 | GO 165 Inspection
119550319 | other | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2023-11-30 | 2025-08-03 | Level 3 | Standards change
119551687 | pole | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2023-01-13 | 2025-08-03 | Level 3 | Standards change
119552211 | anchor/guy | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2024-08-28 | 2025-08-03 | Level 3 | GO 165 Inspection
119553155 | other | Non-HFTD | Transmission | 2020-07-30 | 2021-07-30 | Level 2 | E | 2023-09-12 | 2025-07-30 | Level 3 | Standards change
119553850 | pole | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2023-12-20 | 2025-08-03 | Level 3 | Standards change
119554514 | insulator and brushing | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2023-07-27 | 2023-08-03 | Level 2 | Standards change
119556460 | pole | Non-HFTD | Transmission | 2020-08-04 | 2021-08-04 | Level 2 | E | 2024-10-17 | 2021-08-04 | Level 2 | GO 165 Inspection
119556741 | other | Non-HFTD | Transmission | 2020-08-04 | 2022-08-04 | Level 3 | F | 2024-04-06 | 2025-08-04 | Level 3 | Standards change
119557660 | other | Non-HFTD | Transmission | 2020-08-04 | 2022-08-04 | Level 3 | F | 2024-02-02 | 2025-08-04 | Level 3 | Standards change
119557782 | other | Non-HFTD | Transmission | 2020-08-04 | 2021-08-04 | Level 2 | E | 2023-03-08 | 2025-08-04 | Level 3 | Field Safety Reassessment
119558407 | pole | Non-HFTD | Transmission | 2020-08-04 | 2022-08-04 | Level 3 | F | 2024-01-03 | 2025-08-04 | Level 3 | Standards change
119559691 | other | Non-HFTD | Transmission | 2020-08-04 | 2022-08-04 | Level 3 | F | 2023-12-01 | 2025-08-04 | Level 3 | Standards change
119560162 | pole | Non-HFTD | Transmission | 2020-08-05 | 2021-08-05 | Level 2 | E | 2024-11-04 | 2023-08-05 | Level 2 | GO 165 Inspection
119560360 | insulator and brushing | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2022-12-13 | 2021-08-03 | Level 2 | Standards change
119561665 | other | Non-HFTD | Transmission | 2020-08-05 | 2022-08-05 | Level 3 | F | 2024-04-06 | 2025-08-05 | Level 3 | Standards change
119562280 | other | Non-HFTD | Transmission | 2020-08-05 | 2021-08-05 | Level 2 | E | 2024-01-16 | 2025-08-05 | Level 3 | Standards change
119564660 | other | Non-HFTD | Transmission | 2020-08-05 | 2021-08-05 | Level 2 | E | 2024-09-09 | 2021-08-05 | Level 2 | GO 165 Inspection
119564665 | other | Non-HFTD | Transmission | 2020-08-05 | 2021-08-05 | Level 2 | E | 2023-06-01 | 2025-08-05 | Level 3 | Standards change
119565075 | pole | Non-HFTD | Transmission | 2020-08-05 | 2022-08-05 | Level 3 | F | 2023-12-05 | 2025-08-05 | Level 3 | Standards change
119567075 | other | Non-HFTD | Transmission | 2020-08-06 | 2022-08-06 | Level 3 | F | 2024-10-05 | 2025-08-06 | Level 3 | GO 165 Inspection
119567385 | other | HFTD Tier 2 | Transmission | 2020-08-05 | 2022-08-05 | Level 3 | F | 2023-05-24 | 2025-08-05 | Level 3 | GO 165 Inspection
119567425 | other | Non-HFTD | Transmission | 2020-08-05 | 2021-08-05 | Level 2 | E | 2024-08-30 | 2023-08-05 | Level 2 | Field Safety Reassessment
119567911 | other | Non-HFTD | Transmission | 2020-08-05 | 2021-08-05 | Level 2 | E | 2024-06-25 | 2025-08-05 | Level 3 | GO 165 Inspection
119568071 | other | Non-HFTD | Transmission | 2020-08-06 | 2022-08-06 | Level 3 | F | 2024-04-06 | 2025-08-06 | Level 3 | Standards change
119569739 | other | Non-HFTD | Transmission | 2020-08-06 | 2022-08-06 | Level 3 | F | 2024-04-06 | 2025-08-06 | Level 3 | Standards change
119570215 | pole | Non-HFTD | Transmission | 2020-08-06 | 2021-08-06 | Level 2 | E | 2024-09-04 | 2023-08-06 | Level 2 | GO 165 Inspection
119570347 | anchor/guy | Non-HFTD | Transmission | 2020-08-06 | 2021-08-06 | Level 2 | E | 2024-11-20 | 2025-08-06 | Level 3 | GO 165 Inspection
119570724 | anchor/guy | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2024-12-02 | 2025-08-03 | Level 3 | GO 165 Inspection
119570725 | anchor/guy | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2024-12-02 | 2025-08-03 | Level 3 | GO 165 Inspection
119570727 | anchor/guy | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2024-12-02 | 2025-08-03 | Level 3 | GO 165 Inspection
119571362 | other | Non-HFTD | Transmission | 2020-08-06 | 2022-08-06 | Level 3 | F | 2024-04-06 | 2025-08-06 | Level 3 | Standards change
119571530 | other | Non-HFTD | Transmission | 2020-08-06 | 2022-08-06 | Level 3 | F | 2024-04-06 | 2025-08-06 | Level 3 | Standards change
119574886 | anchor/guy | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-08-31 | 2025-08-07 | Level 3 | GO 165 Inspection
119575065 | pole | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-01-22 | 2025-08-07 | Level 3 | Standards change
119575639 | pole | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-12-20 | 2023-08-07 | Level 2 | Field Safety Reassessment
119575967 | other | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-04-06 | 2025-08-07 | Level 3 | Standards change
119576120 | pole | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2023-01-25 | 2025-08-07 | Level 3 | Standards change
119576258 | other | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-10-04 | 2025-08-07 | Level 3 | GO 165 Inspection
119576313 | other | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-09-25 | 2025-08-07 | Level 3 | GO 165 Inspection
119576555 | other | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-06-26 | 2025-08-07 | Level 3 | GO 165 Inspection
119576778 | other | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-05-24 | 2025-08-07 | Level 3 | GO 165 Inspection
119576797 | other | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-03-14 | 2025-08-07 | Level 3 | Standards change
119577029 | pole | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-08-30 | 2023-08-07 | Level 2 | GO 165 Inspection
119577066 | other | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-05-22 | 2025-08-07 | Level 3 | GO 165 Inspection
119577673 | anchor/guy | Non-HFTD | Transmission | 2020-08-06 | 2025-08-06 | Level 2 | E | 2024-11-20 | 2023-08-06 | Level 2 | GO 165 Inspection
119578065 | other | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-02-23 | 2023-08-07 | Level 2 | Standards change
119578227 | connection device | Non-HFTD | Transmission | 2020-08-07 | 2021-08-07 | Level 2 | E | 2024-02-15 | 2023-08-07 | Level 2 | Standards change
119578365 | pole | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-09-23 | 2025-08-07 | Level 3 | GO 165 Inspection
119578368 | pole | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-09-23 | 2025-08-07 | Level 3 | GO 165 Inspection
119578375 | pole | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2023-01-18 | 2025-08-07 | Level 3 | Standards change
119579157 | other | Non-HFTD | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-05-10 | 2025-08-07 | Level 3 | GO 165 Inspection
119579383 | other | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2024-04-06 | 2025-08-08 | Level 3 | Standards change
119579434 | other | Non-HFTD | Transmission | 2020-08-08 | 2021-08-08 | Level 2 | E | 2024-07-23 | 2025-08-08 | Level 3 | GO 165 Inspection
119579668 | pole | Non-HFTD | Transmission | 2020-08-08 | 2021-08-08 | Level 2 | E | 2024-07-23 | 2023-08-08 | Level 2 | GO 165 Inspection
119579866 | other | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2023-01-12 | 2025-08-08 | Level 3 | Standards change
119580052 | pole | Non-HFTD | Transmission | 2020-08-08 | 2021-08-08 | Level 2 | E | 2024-09-16 | 2023-08-08 | Level 2 | GO 165 Inspection
119580154 | pole | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2024-10-15 | 2025-08-08 | Level 3 | GO 165 Inspection
119580611 | pole | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2024-10-15 | 2025-08-08 | Level 3 | GO 165 Inspection
119580718 | pole | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2023-02-28 | 2025-08-08 | Level 3 | Standards change
119580805 | insulator and brushing | Non-HFTD | Transmission | 2020-08-08 | 2021-08-08 | Level 2 | E | 2023-04-21 | 2023-08-08 | Level 2 | Standards change
119580957 | pole | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2024-08-21 | 2025-08-08 | Level 3 | GO 165 Inspection
119581062 | other | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2024-01-11 | 2025-08-08 | Level 3 | Standards change
119590897 | other | Non-HFTD | Transmission | 2020-08-03 | 2021-08-03 | Level 2 | E | 2024-10-05 | 2023-08-03 | Level 2 | GO 165 Inspection
119591111 | other | HFTD Tier 2 | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2023-03-07 | 2025-08-07 | Level 3 | Standards change
119591993 | other | Non-HFTD | Transmission | 2020-08-10 | 2021-08-10 | Level 2 | E | 2024-07-23 | 2021-08-10 | Level 2 | GO 165 Inspection
119592138 | pole | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2022-12-16 | 2025-08-10 | Level 3 | Standards change
119592765 | other | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2024-07-16 | 2025-08-10 | Level 3 | GO 165 Inspection
119592858 | insulator and brushing | Non-HFTD | Transmission | 2020-08-10 | 2021-08-10 | Level 2 | E | 2024-09-16 | 2023-08-10 | Level 2 | GO 165 Inspection
119593146 | insulator and brushing | Non-HFTD | Transmission | 2020-08-10 | 2021-08-10 | Level 2 | E | 2024-08-21 | 2023-08-10 | Level 2 | GO 165 Inspection
119593438 | insulator and brushing | Non-HFTD | Transmission | 2020-08-10 | 2021-08-10 | Level 2 | E | 2024-12-12 | 2023-08-10 | Level 2 | Field Safety Reassessment
119594700 | insulator and brushing | Non-HFTD | Transmission | 2020-08-10 | 2021-08-10 | Level 2 | E | 2024-10-30 | 2023-08-10 | Level 2 | GO 165 Inspection
119594791 | other | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2024-04-06 | 2025-08-10 | Level 3 | Standards change
119595144 | other | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2024-04-06 | 2025-08-10 | Level 3 | Standards change
119596104 | pole | Non-HFTD | Transmission | 2020-08-10 | 2021-08-10 | Level 2 | E | 2024-09-26 | 2023-08-10 | Level 2 | GO 165 Inspection
119596154 | other | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2024-01-18 | 2025-08-10 | Level 3 | Standards change
119596310 | other | Non-HFTD | Transmission | 2020-08-05 | 2022-08-05 | Level 3 | F | 2024-04-06 | 2025-08-05 | Level 3 | Standards change
119596852 | other | Non-HFTD | Transmission | 2020-08-08 | 2022-08-08 | Level 3 | F | 2024-06-11 | 2025-08-08 | Level 3 | GO 165 Inspection
119597714 | other | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2024-01-08 | 2025-08-11 | Level 3 | Standards change
119597826 | other | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2024-04-23 | 2025-08-11 | Level 3 | GO 165 Inspection
119598652 | pole | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2023-11-30 | 2025-08-11 | Level 3 | Standards change
119598704 | other | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2023-11-30 | 2025-08-11 | Level 3 | Standards change
119598879 | anchor/guy | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2024-01-17 | 2025-08-11 | Level 3 | Standards change
119599533 | other | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2024-09-30 | 2025-08-11 | Level 3 | GO 165 Inspection
119600659 | pole | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2023-12-26 | 2025-08-11 | Level 3 | Standards change
119600950 | pole | Non-HFTD | Transmission | 2020-08-11 | 2021-08-11 | Level 2 | E | 2024-09-26 | 2023-08-11 | Level 2 | Field Safety Reassessment
119601252 | pole | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2024-04-06 | 2025-08-11 | Level 3 | GO 165 Inspection
119601258 | pole | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2023-01-27 | 2025-08-11 | Level 3 | Standards change
119601499 | other | Non-HFTD | Transmission | 2020-08-11 | 2022-08-11 | Level 3 | F | 2024-06-27 | 2025-08-11 | Level 3 | GO 165 Inspection
119602628 | insulator and brushing | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-01-24 | 2023-08-12 | Level 2 | Standards change
119603604 | anchor/guy | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-12-18 | 2025-08-12 | Level 3 | GO 165 Inspection
119603625 | anchor/guy | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2023-08-22 | 2023-08-12 | Level 2 | Standards change
119603796 | other | Non-HFTD | Transmission | 2020-08-12 | 2025-08-12 | Level 2 | E | 2024-11-26 | 2021-08-12 | Level 2 | Field Safety Reassessment
119604107 | pole | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2023-12-07 | 2025-08-12 | Level 3 | Standards change
119604728 | insulator and brushing | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-08-16 | 2023-08-12 | Level 2 | Field Safety Reassessment
119604840 | anchor/guy | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2023-12-07 | 2025-08-12 | Level 3 | Standards change
119605108 | insulator and brushing | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-08-16 | 2023-08-12 | Level 2 | Field Safety Reassessment
119605350 | pole | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-03-15 | 2023-08-12 | Level 2 | Standards change
119605696 | pole | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2023-08-02 | 2023-08-12 | Level 2 | Standards change
119606188 | other | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-08-21 | 2025-08-12 | Level 3 | GO 165 Inspection
119607358 | other | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-01-04 | 2025-08-12 | Level 3 | Standards change
119607619 | pole | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-12-30 | 2021-08-12 | Level 2 | Field Safety Reassessment
119608127 | other | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-07-09 | 2025-08-12 | Level 3 | GO 165 Inspection
119608128 | other | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-01-08 | 2025-08-12 | Level 3 | Standards change
119608171 | other | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-06-27 | 2025-08-12 | Level 3 | GO 165 Inspection
119608526 | pole | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2023-12-26 | 2025-08-12 | Level 3 | Standards change
119608948 | other | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2023-06-16 | 2025-08-13 | Level 3 | Standards change
119609041 | insulator and brushing | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2023-07-24 | 2021-08-12 | Level 2 | Standards change
119609297 | insulator and brushing | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-08-22 | 2023-08-13 | Level 2 | Field Safety Reassessment
119609605 | insulator and brushing | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2023-06-15 | 2023-08-13 | Level 2 | Standards change
119609735 | pole | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-03-27 | 2025-08-13 | Level 3 | GO 165 Inspection
119610072 | other | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-10-09 | 2021-08-13 | Level 2 | GO 165 Inspection
119610781 | pole | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2023-12-26 | 2025-08-13 | Level 3 | Standards change
119610798 | other | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-01-11 | 2025-08-12 | Level 3 | Standards change
119610833 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-10-08 | 2025-08-13 | Level 3 | GO 165 Inspection
119610989 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-02-28 | 2025-08-13 | Level 3 | Standards change
119611178 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-04-06 | 2025-08-13 | Level 3 | Standards change
119611200 | insulator and brushing | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-10-30 | 2023-08-13 | Level 2 | GO 165 Inspection
119612526 | anchor/guy | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2023-08-17 | 2025-08-13 | Level 3 | Standards change
119612675 | splice | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-08-27 | 2023-08-13 | Level 2 | GO 165 Inspection
119612845 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-04-11 | 2025-08-13 | Level 3 | GO 165 Inspection
119612851 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2023-05-06 | 2025-08-13 | Level 3 | Standards change
119613034 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-01-08 | 2025-08-13 | Level 3 | Standards change
119613168 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2023-11-14 | 2025-08-13 | Level 3 | Standards change
119613286 | insulator and brushing | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-10-19 | 2023-08-13 | Level 2 | Field Safety Reassessment
119613349 | anchor/guy | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-01-04 | 2025-08-13 | Level 3 | Standards change
119613549 | pole | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-11-06 | 2023-08-13 | Level 2 | Field Safety Reassessment
119615013 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2023-02-02 | 2025-08-13 | Level 3 | Standards change
119615299 | pole | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-07-26 | 2021-08-14 | Level 2 | GO 165 Inspection
119615317 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-01-09 | 2025-08-14 | Level 3 | Standards change
119615355 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2023-01-19 | 2025-08-14 | Level 3 | Standards change
119615894 | pole | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-12-10 | 2021-08-14 | Level 2 | Field Safety Reassessment
119616405 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2023-10-12 | 2025-08-14 | Level 3 | Standards change
119616442 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-01-04 | 2025-08-14 | Level 3 | Standards change
119616499 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2023-12-18 | 2025-08-14 | Level 3 | Standards change
119616593 | pole | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-12-10 | 2023-08-14 | Level 2 | Field Safety Reassessment
119616654 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-01-10 | 2025-08-14 | Level 3 | Standards change
119616689 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-02-28 | 2025-08-14 | Level 3 | Standards change
119616802 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-02-28 | 2025-08-14 | Level 3 | Standards change
119616956 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-04-06 | 2025-08-14 | Level 3 | Standards change
119616987 | pole | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2023-12-26 | 2025-08-14 | Level 3 | Standards change
119617388 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-04-06 | 2025-08-14 | Level 3 | Standards change
119617708 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-01-04 | 2025-08-14 | Level 3 | Standards change
119617819 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2023-12-19 | 2025-08-14 | Level 3 | Standards change
119618254 | other | Non-HFTD | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-01-08 | 2025-08-13 | Level 3 | Standards change
119618333 | pole | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-01-04 | 2025-08-13 | Level 3 | Standards change
119618594 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-04-06 | 2025-08-14 | Level 3 | Standards change
119618727 | other | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-03-29 | 2025-08-14 | Level 3 | GO 165 Inspection
119618728 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-01-08 | 2025-08-14 | Level 3 | Standards change
119619052 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2023-12-01 | 2025-08-14 | Level 3 | Standards change
119619088 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2023-12-20 | 2025-08-14 | Level 3 | Standards change
119619166 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2023-12-14 | 2025-08-14 | Level 3 | Standards change
119619418 | insulator and brushing | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-10-30 | 2023-08-14 | Level 2 | GO 165 Inspection
119620625 | other | Non-HFTD | Transmission | 2020-08-15 | 2022-08-15 | Level 3 | F | 2024-09-17 | 2025-08-15 | Level 3 | GO 165 Inspection
119620729 | other | Non-HFTD | Transmission | 2020-08-15 | 2022-08-15 | Level 3 | F | 2024-09-16 | 2025-08-15 | Level 3 | GO 165 Inspection
119623105 | anchor/guy | Non-HFTD | Transmission | 2020-08-16 | 2021-08-16 | Level 2 | E | 2024-01-08 | 2025-08-16 | Level 3 | Standards change
119624568 | other | HFTD Tier 3 | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-04-06 | 2025-08-14 | Level 3 | Standards change
119626187 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-04-06 | 2025-08-14 | Level 3 | Standards change
119628125 | crossarm | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-04-09 | 2023-08-13 | Level 2 | GO 165 Inspection
119628518 | other | Non-HFTD | Transmission | 2020-08-17 | 2022-08-17 | Level 3 | F | 2024-01-08 | 2025-08-17 | Level 3 | Standards change
119629518 | other | Non-HFTD | Transmission | 2020-08-18 | 2021-08-18 | Level 2 | E | 2024-08-30 | 2025-08-18 | Level 3 | GO 165 Inspection
119629765 | pole | Non-HFTD | Transmission | 2020-08-17 | 2022-08-17 | Level 3 | F | 2024-08-20 | 2025-08-17 | Level 3 | GO 165 Inspection
119629871 | anchor/guy | Non-HFTD | Transmission | 2020-08-18 | 2021-08-18 | Level 2 | E | 2024-01-04 | 2025-08-18 | Level 3 | Standards change
119630383 | pole | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-08-23 | 2023-08-14 | Level 2 | GO 165 Inspection
119630444 | insulator and brushing | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-10-15 | 2023-08-14 | Level 2 | Field Safety Reassessment
119630529 | other | Non-HFTD | Transmission | 2020-08-13 | 2025-08-13 | Level 2 | E | 2024-08-19 | 2021-08-13 | Level 2 | GO 165 Inspection
119630720 | other | Non-HFTD | Transmission | 2020-08-18 | 2022-08-18 | Level 3 | F | 2024-04-06 | 2025-08-18 | Level 3 | Standards change
119632301 | pole | Non-HFTD | Transmission | 2020-08-18 | 2021-08-18 | Level 2 | E | 2024-10-24 | 2023-08-18 | Level 2 | GO 165 Inspection
119632530 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-09-23 | 2025-08-14 | Level 3 | GO 165 Inspection
119633441 | other | Non-HFTD | Transmission | 2020-08-18 | 2021-08-18 | Level 2 | E | 2024-01-08 | 2025-08-18 | Level 3 | Standards change
119633530 | pole | Non-HFTD | Transmission | 2020-08-18 | 2022-08-18 | Level 3 | F | 2024-10-15 | 2025-08-18 | Level 3 | GO 165 Inspection
119635629 | other | HFTD Tier 2 | Transmission | 2020-08-18 | 2022-08-18 | Level 3 | F | 2023-04-24 | 2025-08-18 | Level 3 | GO 165 Inspection
119638160 | pole | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-07-18 | 2023-08-19 | Level 2 | GO 165 Inspection
119638236 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-04-06 | 2025-08-19 | Level 3 | Standards change
119638239 | pole | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2023-08-03 | 2023-08-19 | Level 2 | Standards change
119638416 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2023-08-01 | 2025-08-19 | Level 3 | Standards change
119638438 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-04-29 | 2025-08-19 | Level 3 | Field Safety Reassessment
119638448 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-04-06 | 2025-08-19 | Level 3 | Standards change
119638475 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-04-06 | 2025-08-19 | Level 3 | Standards change
119638779 | pole | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2023-08-04 | 2023-08-19 | Level 2 | Standards change
119640047 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-10-30 | 2025-08-19 | Level 3 | GO 165 Inspection
119640109 | pole | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-10-08 | 2021-08-19 | Level 2 | GO 165 Inspection
119641599 | insulator and brushing | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-07-08 | 2023-08-19 | Level 2 | Field Safety Reassessment
119642085 | pole | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2023-08-01 | 2023-08-20 | Level 2 | Standards change
119643163 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-02-29 | 2025-08-19 | Level 3 | Standards change
119643598 | anchor/guy | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2024-01-26 | 2025-08-20 | Level 3 | Standards change
119643902 | pole | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2024-09-13 | 2023-08-20 | Level 2 | GO 165 Inspection
119644856 | other | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2023-06-05 | 2025-08-20 | Level 3 | Standards change
119645113 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-09-17 | 2025-08-20 | Level 3 | GO 165 Inspection
119645128 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-05-22 | 2025-08-20 | Level 3 | GO 165 Inspection
119645141 | insulator and brushing | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2024-10-24 | 2023-08-20 | Level 2 | GO 165 Inspection
119645273 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-10-30 | 2025-08-20 | Level 3 | GO 165 Inspection
119645711 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2023-03-06 | 2025-08-20 | Level 3 | Standards change
119645715 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-10-05 | 2025-08-20 | Level 3 | GO 165 Inspection
119645716 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-04-06 | 2025-08-20 | Level 3 | Standards change
119647214 | anchor/guy | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2024-07-08 | 2025-08-20 | Level 3 | GO 165 Inspection
119647438 | other | Non-HFTD | Transmission | 2020-08-21 | 2021-08-21 | Level 2 | E | 2023-03-07 | 2025-08-21 | Level 3 | Standards change
119647696 | other | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-10-08 | 2023-08-19 | Level 2 | GO 165 Inspection
119647876 | anchor/guy | Non-HFTD | Transmission | 2020-08-21 | 2025-08-21 | Level 2 | E | 2024-10-17 | 2023-08-21 | Level 2 | GO 165 Inspection
119648011 | pole | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2023-07-10 | 2023-08-19 | Level 2 | Standards change
119648337 | insulator and brushing | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-09-03 | 2023-08-19 | Level 2 | GO 165 Inspection
119648339 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-09-03 | 2025-08-19 | Level 3 | GO 165 Inspection
119648956 | pole | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-12-20 | 2023-08-19 | Level 2 | Field Safety Reassessment
119649076 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2023-01-19 | 2025-08-20 | Level 3 | Standards change
119649196 | pole | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-07-25 | 2025-08-20 | Level 3 | GO 165 Inspection
119649231 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-02-28 | 2025-08-20 | Level 3 | Standards change
119650768 | pole | Non-HFTD | Transmission | 2020-08-21 | 2021-08-21 | Level 2 | E | 2024-05-21 | 2023-08-21 | Level 2 | Field Safety Reassessment
119656063 | pole | Non-HFTD | Transmission | 2020-08-21 | 2021-08-21 | Level 2 | E | 2024-12-10 | 2023-08-21 | Level 2 | Field Safety Reassessment
119656079 | anchor/guy | Non-HFTD | Transmission | 2020-08-21 | 2021-08-21 | Level 2 | E | 2024-01-22 | 2025-08-21 | Level 3 | Standards change
119658142 | pole | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2024-08-22 | 2025-08-22 | Level 3 | GO 165 Inspection
119658845 | anchor/guy | Non-HFTD | Transmission | 2020-08-22 | 2023-08-22 | Level 2 | E | 2024-12-10 | 2021-08-22 | Level 2 | Field Safety Reassessment
119658849 | other | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2023-03-21 | 2025-08-22 | Level 3 | Standards change
119660824 | anchor/guy | Non-HFTD | Transmission | 2020-08-22 | 2025-08-22 | Level 2 | E | 2024-10-16 | 2023-08-22 | Level 2 | GO 165 Inspection
119661261 | splice | Non-HFTD | Transmission | 2020-08-22 | 2021-08-22 | Level 2 | E | 2023-01-24 | 2023-08-20 | Level 2 | Standards change
119662179 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2024-04-06 | 2025-08-19 | Level 3 | Standards change
119662492 | other | Non-HFTD | Transmission | 2020-08-21 | 2022-08-21 | Level 3 | F | 2024-08-03 | 2025-08-21 | Level 3 | GO 165 Inspection
119663054 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-08-07 | 2025-08-24 | Level 3 | Standards change
119663659 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2023-03-30 | 2025-08-19 | Level 3 | Standards change
119663783 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119663835 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-12-19 | 2025-08-24 | Level 3 | Standards change
119663836 | insulator and brushing | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2024-12-10 | 2023-08-24 | Level 2 | GO 165 Inspection
119663966 | anchor/guy | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2023-11-14 | 2025-08-19 | Level 3 | Standards change
119664178 | anchor/guy | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2024-01-11 | 2025-08-24 | Level 3 | Standards change
119664512 | other | Non-HFTD | Transmission | 2020-08-20 | 2021-08-20 | Level 2 | E | 2024-07-22 | 2025-08-20 | Level 3 | GO 165 Inspection
119664663 | other | Non-HFTD | Transmission | 2020-08-21 | 2025-08-21 | Level 2 | E | 2024-10-08 | 2023-08-21 | Level 2 | GO 165 Inspection
119666902 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-02-28 | 2025-08-20 | Level 3 | Standards change
119666906 | other | Non-HFTD | Transmission | 2020-08-21 | 2021-08-21 | Level 2 | E | 2024-01-16 | 2025-08-21 | Level 3 | Standards change
119667147 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-12-07 | 2025-08-24 | Level 3 | GO 165 Inspection
119669087 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-07-31 | 2025-08-24 | Level 3 | Standards change
119669095 | other | Non-HFTD | Transmission | 2020-08-25 | 2022-08-25 | Level 3 | F | 2024-04-06 | 2025-08-25 | Level 3 | Standards change
119669706 | insulator and brushing | Non-HFTD | Transmission | 2020-08-25 | 2021-08-25 | Level 2 | E | 2024-12-19 | 2023-08-25 | Level 2 | Field Safety Reassessment
119669903 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-07-12 | 2025-08-20 | Level 3 | GO 165 Inspection
119670241 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-04-06 | 2025-08-20 | Level 3 | Standards change
119670267 | other | Non-HFTD | Transmission | 2020-08-25 | 2022-08-25 | Level 3 | F | 2024-01-05 | 2025-08-25 | Level 3 | Standards change
119670911 | anchor/guy | Non-HFTD | Transmission | 2020-08-22 | 2021-08-22 | Level 2 | E | 2023-01-24 | 2025-08-22 | Level 3 | Standards change
119670919 | insulator and brushing | Non-HFTD | Transmission | 2020-08-22 | 2021-08-22 | Level 2 | E | 2023-03-20 | 2025-08-22 | Level 3 | Standards change
119671071 | insulator and brushing | Non-HFTD | Transmission | 2020-08-22 | 2021-08-22 | Level 2 | E | 2023-03-20 | 2025-08-22 | Level 3 | Standards change
119671466 | anchor/guy | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2023-01-19 | 2025-08-24 | Level 3 | Standards change
119672211 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2023-01-19 | 2025-08-20 | Level 3 | Standards change
119672216 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-07-11 | 2025-08-20 | Level 3 | GO 165 Inspection
119672498 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-04-06 | 2025-08-20 | Level 3 | Standards change
119672612 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-11-12 | 2025-08-20 | Level 3 | GO 165 Inspection
119673098 | other | Non-HFTD | Transmission | 2020-08-19 | 2022-08-19 | Level 3 | F | 2023-04-06 | 2025-08-19 | Level 3 | Standards change
119673315 | anchor/guy | Non-HFTD | Transmission | 2020-08-25 | 2021-08-25 | Level 2 | E | 2024-10-22 | 2025-08-25 | Level 3 | GO 165 Inspection
119673323 | other | Non-HFTD | Transmission | 2020-08-25 | 2022-08-25 | Level 3 | F | 2024-11-18 | 2025-08-25 | Level 3 | GO 165 Inspection
119673463 | other | Non-HFTD | Transmission | 2020-08-20 | 2022-08-20 | Level 3 | F | 2024-07-18 | 2025-08-20 | Level 3 | GO 165 Inspection
119673605 | pole | Non-HFTD | Transmission | 2020-08-26 | 2021-08-26 | Level 2 | E | 2024-10-04 | 2023-08-26 | Level 2 | GO 165 Inspection
119673646 | other | Non-HFTD | Transmission | 2020-08-26 | 2021-08-26 | Level 2 | E | 2024-10-04 | 2023-08-26 | Level 2 | GO 165 Inspection
119673973 | other | Non-HFTD | Transmission | 2020-08-21 | 2022-08-21 | Level 3 | F | 2024-04-06 | 2025-08-21 | Level 3 | Standards change
119674413 | other | Non-HFTD | Transmission | 2020-08-21 | 2022-08-21 | Level 3 | F | 2024-05-31 | 2025-08-21 | Level 3 | GO 165 Inspection
119674491 | pole | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2024-11-06 | 2023-08-24 | Level 2 | Field Safety Reassessment
119674727 | anchor/guy | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2023-01-24 | 2025-08-24 | Level 3 | Standards change
119674761 | other | Non-HFTD | Transmission | 2020-08-26 | 2021-08-26 | Level 2 | E | 2024-01-08 | 2025-08-26 | Level 3 | Standards change
119674862 | pole | Non-HFTD | Transmission | 2020-08-26 | 2022-08-26 | Level 3 | F | 2024-01-09 | 2025-08-26 | Level 3 | Standards change
119675090 | anchor/guy | Non-HFTD | Transmission | 2020-08-26 | 2021-08-26 | Level 2 | E | 2024-10-22 | 2025-08-26 | Level 3 | GO 165 Inspection
119675664 | pole | Non-HFTD | Transmission | 2020-08-21 | 2022-08-21 | Level 3 | F | 2024-10-30 | 2025-08-21 | Level 3 | GO 165 Inspection
119675933 | other | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2023-01-20 | 2025-08-22 | Level 3 | Standards change
119676032 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119676181 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119676186 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-07-27 | 2025-08-24 | Level 3 | Standards change
119678376 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-07-31 | 2025-08-24 | Level 3 | Standards change
119679718 | insulator and brushing | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2024-10-31 | 2025-08-24 | Level 3 | GO 165 Inspection
119679857 | insulator and brushing | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2024-04-04 | 2023-08-27 | Level 2 | GO 165 Inspection
119680114 | pole | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2022-12-14 | 2023-08-27 | Level 2 | Standards change
119680838 | insulator and brushing | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2024-08-16 | 2023-08-27 | Level 2 | Field Safety Reassessment
119681157 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2023-12-13 | 2025-08-27 | Level 3 | Standards change
119682122 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119682375 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2023-12-01 | 2023-08-27 | Level 2 | Standards change
119682429 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2023-12-01 | 2025-08-27 | Level 3 | Standards change
119682447 | anchor/guy | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2024-08-26 | 2023-08-27 | Level 2 | GO 165 Inspection
119684413 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119684648 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119684960 | other | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2024-04-06 | 2025-08-22 | Level 3 | Standards change
119685331 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119685426 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119685522 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-07-28 | 2025-08-24 | Level 3 | Standards change
119685660 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-02-29 | 2025-08-28 | Level 3 | Standards change
119685939 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-04-06 | 2025-08-28 | Level 3 | Standards change
119686117 | pole | Non-HFTD | Transmission | 2020-08-21 | 2022-08-21 | Level 3 | F | 2024-10-28 | 2025-08-21 | Level 3 | GO 165 Inspection
119686119 | other | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2024-04-06 | 2025-08-22 | Level 3 | Standards change
119686428 | anchor/guy | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2024-01-25 | 2025-08-27 | Level 3 | Standards change
119686446 | other | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2023-01-19 | 2025-08-22 | Level 3 | Standards change
119686543 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-02-29 | 2025-08-28 | Level 3 | Standards change
119686603 | pole | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-10-14 | 2023-08-28 | Level 2 | Field Safety Reassessment
119687323 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-08-21 | 2025-08-28 | Level 3 | GO 165 Inspection
119687350 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-04-06 | 2025-08-28 | Level 3 | Standards change
119687574 | insulator and brushing | Non-HFTD | Transmission | 2020-08-26 | 2021-08-26 | Level 2 | E | 2024-10-15 | 2023-08-26 | Level 2 | GO 165 Inspection
119687871 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119688331 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119688443 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119689679 | pole | Non-HFTD | Transmission | 2020-08-29 | 2022-08-29 | Level 3 | F | 2023-12-15 | 2025-08-29 | Level 3 | Standards change
119693036 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-01-19 | 2025-08-28 | Level 3 | Standards change
119693049 | pole | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2023-12-26 | 2025-08-28 | Level 3 | Standards change
119693050 | pole | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-01-26 | 2025-08-28 | Level 3 | Standards change
119693698 | other | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 3 | F | 2023-04-03 | 2021-08-31 | Level 3 | Field Safety Reassessment
119694580 | anchor/guy | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-01-18 | 2025-08-28 | Level 3 | Standards change
119695764 | pole | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-05-21 | 2023-08-31 | Level 2 | Field Safety Reassessment
119696379 | anchor/guy | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2024-09-30 | 2021-08-27 | Level 2 | GO 165 Inspection
119698992 | insulator and brushing | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-07-12 | 2023-09-01 | Level 2 | GO 165 Inspection
119699069 | pole | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2023-02-27 | 2025-08-28 | Level 3 | Standards change
119700426 | other | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2023-04-27 | 2025-08-28 | Level 3 | Field Safety Reassessment
119700428 | insulator and brushing | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-08-23 | 2021-08-28 | Level 2 | GO 165 Inspection
119700628 | pole | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-12-05 | 2023-09-01 | Level 2 | Field Safety Reassessment
119701317 | insulator and brushing | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-12-06 | 2023-09-01 | Level 2 | Field Safety Reassessment
119701599 | pole | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-11-27 | 2021-09-01 | Level 2 | Field Safety Reassessment
119701642 | anchor/guy | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-01-17 | 2025-08-28 | Level 3 | Standards change
119702164 | pole | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2023-03-31 | 2023-08-27 | Level 2 | Standards change
119702344 | pole | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2023-03-30 | 2023-08-28 | Level 2 | Standards change
119703731 | pole | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-12-10 | 2023-08-28 | Level 2 | Field Safety Reassessment
119703950 | anchor/guy | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-10-29 | 2023-08-28 | Level 2 | GO 165 Inspection
119704436 | pole | Non-HFTD | Transmission | 2020-09-01 | 2022-09-01 | Level 3 | F | 2023-12-26 | 2025-09-01 | Level 3 | Standards change
119704437 | other | Non-HFTD | Transmission | 2020-09-01 | 2022-09-01 | Level 3 | F | 2024-02-28 | 2025-09-01 | Level 3 | Standards change
119704484 | pole | Non-HFTD | Transmission | 2020-09-01 | 2022-09-01 | Level 3 | F | 2023-12-26 | 2025-09-01 | Level 3 | Standards change
119704559 | pole | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-08-30 | 2025-09-02 | Level 3 | GO 165 Inspection
119704722 | anchor/guy | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2023-07-22 | 2025-09-02 | Level 3 | GO 165 Inspection
119705336 | anchor/guy | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2023-11-06 | 2025-09-01 | Level 3 | Standards change
119705569 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119706339 | insulator and brushing | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2024-03-22 | 2023-09-02 | Level 2 | Standards change
119706387 | insulator and brushing | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-10-09 | 2021-02-28 | Level 2 | GO 165 Inspection
119706555 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119706763 | pole | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-12-10 | 2023-08-31 | Level 2 | Field Safety Reassessment
119707668 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119707751 | pole | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-12-10 | 2023-08-31 | Level 2 | Field Safety Reassessment
119708520 | pole | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-12-10 | 2023-08-31 | Level 2 | Field Safety Reassessment
119708615 | pole | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-12-11 | 2023-08-31 | Level 2 | Field Safety Reassessment
119709358 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-01-09 | 2025-09-02 | Level 3 | Standards change
119709361 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-01-09 | 2025-09-02 | Level 3 | Standards change
119709504 | insulator and brushing | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2023-08-08 | 2025-09-02 | Level 3 | Standards change
119709709 | other | Non-HFTD | Transmission | 2020-09-02 | 2025-09-01 | Level 2 | E | 2024-09-20 | 2025-09-02 | Level 3 | GO 165 Inspection
119710754 | anchor/guy | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2023-08-09 | 2025-09-03 | Level 3 | Standards change
119711169 | insulator and brushing | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-03-22 | 2023-09-01 | Level 2 | Standards change
119711274 | pole | Non-HFTD | Transmission | 2020-08-31 | 2021-08-31 | Level 2 | E | 2024-12-10 | 2023-08-31 | Level 2 | Field Safety Reassessment
119711463 | pole | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2024-09-23 | 2021-09-03 | Level 2 | GO 165 Inspection
119711492 | pole | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-12-10 | 2021-09-01 | Level 2 | Field Safety Reassessment
119711528 | anchor/guy | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2024-01-24 | 2025-09-02 | Level 3 | Standards change
119713286 | other | Non-HFTD | Transmission | 2020-08-22 | 2022-08-22 | Level 3 | F | 2023-01-24 | 2025-08-22 | Level 3 | Standards change
119714382 | anchor/guy | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2024-01-25 | 2025-09-03 | Level 3 | Standards change
119714465 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-02-14 | 2025-09-02 | Level 3 | Standards change
119714810 | insulator and brushing | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2024-01-22 | 2023-09-02 | Level 2 | Standards change
119716416 | other | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2024-09-16 | 2025-09-03 | Level 3 | GO 165 Inspection
119716438 | anchor/guy | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2024-01-25 | 2025-09-02 | Level 3 | Standards change
119716786 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2023-07-31 | 2025-09-03 | Level 3 | Standards change
119717018 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-09-11 | 2025-09-04 | Level 3 | GO 165 Inspection
119717123 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-02 | 2025-09-03 | Level 3 | GO 165 Inspection
119717124 | insulator and brushing | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2024-11-24 | 2023-09-02 | Level 2 | Field Safety Reassessment
119717126 | insulator and brushing | Non-HFTD | Transmission | 2020-09-02 | 2021-09-02 | Level 2 | E | 2024-09-10 | 2023-09-02 | Level 2 | Field Safety Reassessment
119717628 | pole | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-09-03 | 2025-09-04 | Level 3 | GO 165 Inspection
119717629 | pole | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2023-12-26 | 2025-09-04 | Level 3 | Standards change
119717665 | pole | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2023-12-26 | 2025-09-04 | Level 3 | Standards change
119717688 | pole | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2023-02-21 | 2025-09-04 | Level 3 | Standards change
119717696 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-01-10 | 2025-09-04 | Level 3 | Standards change
119718337 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-04-06 | 2025-08-28 | Level 3 | Standards change
119718927 | pole | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2023-07-18 | 2025-08-24 | Level 3 | Standards change
119718929 | other | Non-HFTD | Transmission | 2020-08-24 | 2022-08-24 | Level 3 | F | 2024-04-06 | 2025-08-24 | Level 3 | Standards change
119719051 | anchor/guy | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2023-07-06 | 2025-09-03 | Level 3 | Field Safety Reassessment
119719506 | other | Non-HFTD | Transmission | 2020-09-05 | 2022-09-05 | Level 3 | F | 2024-09-11 | 2025-09-05 | Level 3 | GO 165 Inspection
119720246 | anchor/guy | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2024-09-17 | 2025-09-03 | Level 3 | GO 165 Inspection
119720389 | insulator and brushing | Non-HFTD | Transmission | 2020-06-23 | 2021-06-23 | Level 2 | E | 2023-09-29 | 2021-06-23 | Level 2 | Standards change
119720411 | other | Non-HFTD | Transmission | 2020-06-23 | 2022-06-23 | Level 3 | F | 2024-02-02 | 2025-06-23 | Level 3 | Standards change
119720832 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-08-27 | 2025-07-28 | Level 3 | GO 165 Inspection
119720834 | pole | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-08-27 | 2025-07-28 | Level 3 | GO 165 Inspection
119720913 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-04-06 | 2025-09-03 | Level 3 | Standards change
119720930 | anchor/guy | Non-HFTD | Transmission | 2020-09-04 | 2021-09-04 | Level 2 | E | 2023-12-28 | 2025-09-04 | Level 3 | Standards change
119721257 | other | Non-HFTD | Transmission | 2020-05-04 | 2021-05-04 | Level 2 | E | 2023-01-19 | 2023-05-04 | Level 2 | Standards change
119721394 | pole | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2023-12-26 | 2025-07-31 | Level 3 | Standards change
119721519 | insulator and brushing | Non-HFTD | Transmission | 2020-07-29 | 2021-07-29 | Level 2 | E | 2024-10-23 | 2023-07-29 | Level 2 | GO 165 Inspection
119721610 | insulator and brushing | Non-HFTD | Transmission | 2020-07-31 | 2021-07-31 | Level 2 | E | 2024-10-05 | 2023-07-31 | Level 2 | GO 165 Inspection
119721699 | insulator and brushing | Non-HFTD | Transmission | 2020-07-31 | 2021-07-31 | Level 2 | E | 2024-10-07 | 2023-07-31 | Level 2 | GO 165 Inspection
119722554 | pole | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2023-12-26 | 2025-08-03 | Level 3 | Standards change
119722616 | insulator and brushing | Non-HFTD | Transmission | 2020-07-28 | 2021-07-28 | Level 2 | E | 2024-10-07 | 2023-07-28 | Level 2 | GO 165 Inspection
119723057 | other | Non-HFTD | Transmission | 2020-08-11 | 2021-08-11 | Level 2 | E | 2024-01-17 | 2025-08-11 | Level 3 | Standards change
119723072 | pole | Non-HFTD | Transmission | 2020-08-11 | 2021-08-11 | Level 2 | E | 2024-11-06 | 2023-08-11 | Level 2 | Field Safety Reassessment
119723668 | pole | Non-HFTD | Transmission | 2020-08-05 | 2023-08-05 | Level 2 | E | 2024-12-04 | 2021-08-05 | Level 2 | Field Safety Reassessment
119724125 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119724157 | pole | Non-HFTD | Transmission | 2020-09-08 | 2022-09-08 | Level 3 | F | 2023-04-24 | 2025-09-08 | Level 3 | Standards change
119726863 | anchor/guy | Non-HFTD | Transmission | 2020-08-12 | 2021-08-12 | Level 2 | E | 2024-01-16 | 2025-08-12 | Level 3 | Standards change
119730499 | other | Non-HFTD | Transmission | 2020-09-09 | 2023-09-09 | Level 2 | E | 2024-08-30 | 2021-09-09 | Level 2 | GO 165 Inspection
119741595 | pole | Non-HFTD | Transmission | 2020-09-10 | 2022-09-10 | Level 3 | F | 2024-09-10 | 2025-09-10 | Level 3 | GO 165 Inspection
119741624 | anchor/guy | Non-HFTD | Transmission | 2020-09-10 | 2021-09-10 | Level 2 | E | 2023-01-18 | 2023-09-10 | Level 2 | Standards change
119742739 | other | Non-HFTD | Transmission | 2020-09-10 | 2022-09-10 | Level 3 | F | 2023-08-08 | 2025-09-10 | Level 3 | Standards change
119742997 | insulator and brushing | Non-HFTD | Transmission | 2020-09-09 | 2021-09-09 | Level 2 | E | 2024-07-23 | 2023-09-09 | Level 2 | GO 165 Inspection
119750875 | other | Non-HFTD | Transmission | 2020-09-11 | 2022-09-11 | Level 3 | F | 2024-02-29 | 2025-09-11 | Level 3 | Standards change
119750974 | pole | Non-HFTD | Transmission | 2020-09-05 | 2021-09-05 | Level 2 | E | 2022-12-27 | 2023-09-05 | Level 2 | Standards change
119752459 | insulator and brushing | Non-HFTD | Transmission | 2020-09-11 | 2021-09-11 | Level 2 | E | 2024-09-04 | 2023-09-11 | Level 2 | Field Safety Reassessment
119752586 | pole | Non-HFTD | Transmission | 2020-09-11 | 2021-09-11 | Level 2 | E | 2024-07-29 | 2023-09-11 | Level 2 | Field Safety Reassessment
119752634 | insulator and brushing | Non-HFTD | Transmission | 2020-08-29 | 2021-08-29 | Level 2 | E | 2024-07-22 | 2023-08-29 | Level 2 | Field Safety Reassessment
119754280 | pole | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2024-08-05 | 2023-09-03 | Level 2 | GO 165 Inspection
119754288 | insulator and brushing | Non-HFTD | Transmission | 2020-09-01 | 2021-09-01 | Level 2 | E | 2024-03-22 | 2023-09-01 | Level 2 | Standards change
119754818 | pole | Non-HFTD | Transmission | 2020-09-04 | 2021-09-04 | Level 2 | E | 2024-09-20 | 2023-09-04 | Level 2 | GO 165 Inspection
119754871 | insulator and brushing | Non-HFTD | Transmission | 2020-09-04 | 2021-09-04 | Level 2 | E | 2024-09-20 | 2023-09-04 | Level 2 | GO 165 Inspection
119755849 | pole | Non-HFTD | Transmission | 2020-08-17 | 2021-08-17 | Level 2 | E | 2024-10-05 | 2023-08-17 | Level 2 | GO 165 Inspection
119755893 | anchor/guy | Non-HFTD | Transmission | 2020-08-14 | 2021-08-14 | Level 2 | E | 2024-01-29 | 2025-08-14 | Level 3 | Standards change
119757264 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-09-03 | 2025-09-03 | Level 3 | GO 165 Inspection
119757414 | pole | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2022-12-13 | 2021-09-03 | Level 2 | Field Safety Reassessment
119759859 | other | Non-HFTD | Transmission | 2020-09-14 | 2022-09-14 | Level 3 | F | 2024-04-06 | 2025-09-14 | Level 3 | Standards change
119760685 | pole | Non-HFTD | Transmission | 2020-09-03 | 2021-09-03 | Level 2 | E | 2024-01-19 | 2023-09-03 | Level 2 | Field Safety Reassessment
119762054 | pole | Non-HFTD | Transmission | 2020-09-04 | 2021-09-04 | Level 2 | E | 2024-01-17 | 2021-09-04 | Level 2 | Field Safety Reassessment
119763954 | other | Non-HFTD | Transmission | 2020-09-14 | 2022-09-14 | Level 3 | F | 2024-02-28 | 2025-09-14 | Level 3 | Standards change
119763988 | other | Non-HFTD | Transmission | 2020-09-14 | 2022-09-14 | Level 3 | F | 2024-04-06 | 2025-09-14 | Level 3 | Standards change
119764974 | pole | Non-HFTD | Transmission | 2020-09-12 | 2022-09-12 | Level 3 | F | 2023-12-26 | 2025-09-12 | Level 3 | Standards change
119767179 | anchor/guy | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2023-01-13 | 2025-09-15 | Level 3 | Standards change
119767468 | insulator and brushing | Non-HFTD | Transmission | 2020-08-13 | 2021-08-13 | Level 2 | E | 2024-07-17 | 2023-08-13 | Level 2 | Field Safety Reassessment
119767521 | other | Non-HFTD | Transmission | 2020-09-09 | 2023-09-09 | Level 2 | E | 2024-06-18 | 2021-09-09 | Level 2 | GO 165 Inspection
119770488 | anchor/guy | Non-HFTD | Transmission | 2020-09-16 | 2025-09-16 | Level 2 | E | 2024-09-04 | 2020-12-16 | Level 2 | GO 165 Inspection
119770717 | anchor/guy | Non-HFTD | Transmission | 2020-09-16 | 2021-09-16 | Level 2 | E | 2023-08-01 | 2025-09-16 | Level 3 | Standards change
119771391 | other | Non-HFTD | Transmission | 2020-09-16 | 2021-09-16 | Level 2 | E | 2023-05-23 | 2025-09-16 | Level 3 | Standards change
119774893 | insulator and brushing | Non-HFTD | Transmission | 2020-08-27 | 2021-08-27 | Level 2 | E | 2024-08-16 | 2023-08-27 | Level 2 | Field Safety Reassessment
119775361 | pole | Non-HFTD | Transmission | 2020-09-16 | 2021-09-16 | Level 2 | E | 2024-12-06 | 2023-09-16 | Level 2 | Field Safety Reassessment
119777862 | other | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-10-19 | 2025-07-27 | Level 3 | GO 165 Inspection
119778801 | pole | Non-HFTD | Transmission | 2020-09-17 | 2021-09-17 | Level 2 | E | 2024-12-10 | 2023-09-17 | Level 2 | Field Safety Reassessment
119778932 | other | Non-HFTD | Transmission | 2020-09-16 | 2021-09-16 | Level 2 | E | 2024-12-13 | 2021-09-16 | Level 2 | Field Safety Reassessment
119779529 | insulator and brushing | Non-HFTD | Transmission | 2020-09-10 | 2021-09-10 | Level 2 | E | 2024-01-19 | 2023-09-10 | Level 2 | Standards change
119780871 | other | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-02-28 | 2025-07-27 | Level 3 | Standards change
119781171 | other | Non-HFTD | Transmission | 2020-09-11 | 2021-09-11 | Level 2 | E | 2024-12-11 | 2023-09-11 | Level 2 | Field Safety Reassessment
119782426 | pole | Non-HFTD | Transmission | 2020-09-12 | 2023-09-12 | Level 2 | E | 2024-11-14 | 2020-12-12 | Level 2 | GO 165 Inspection
119782983 | insulator and brushing | Non-HFTD | Transmission | 2020-09-14 | 2021-09-14 | Level 2 | E | 2024-11-07 | 2023-09-14 | Level 2 | Field Safety Reassessment
119783777 | insulator and brushing | Non-HFTD | Transmission | 2020-09-17 | 2021-09-17 | Level 2 | E | 2024-01-19 | 2023-09-17 | Level 2 | Standards change
119784047 | pole | Non-HFTD | Transmission | 2020-09-17 | 2022-09-17 | Level 3 | F | 2023-12-26 | 2025-09-17 | Level 3 | Standards change
119784386 | insulator and brushing | Non-HFTD | Transmission | 2020-09-12 | 2021-09-12 | Level 2 | E | 2024-03-22 | 2023-09-12 | Level 2 | Standards change
119784453 | other | Non-HFTD | Transmission | 2020-09-12 | 2021-09-12 | Level 2 | E | 2023-03-13 | 2021-09-12 | Level 2 | Standards change
119784761 | other | Non-HFTD | Transmission | 2020-09-17 | 2021-09-17 | Level 2 | E | 2024-08-30 | 2021-09-17 | Level 2 | GO 165 Inspection
119785549 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-01-16 | 2025-07-28 | Level 3 | Standards change
119785707 | other | Non-HFTD | Transmission | 2020-07-28 | 2022-07-28 | Level 3 | F | 2024-02-28 | 2025-07-28 | Level 3 | Standards change
119785828 | anchor/guy | Non-HFTD | Transmission | 2020-09-14 | 2021-09-14 | Level 2 | E | 2023-09-07 | 2025-09-14 | Level 3 | Field Safety Reassessment
119785831 | other | Non-HFTD | Transmission | 2020-07-27 | 2022-07-27 | Level 3 | F | 2024-12-05 | 2025-07-28 | Level 3 | GO 165 Inspection
119786181 | pole | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-03-22 | 2023-09-15 | Level 2 | Standards change
119786267 | insulator and brushing | Non-HFTD | Transmission | 2020-09-12 | 2021-09-12 | Level 2 | E | 2023-10-02 | 2023-09-12 | Level 2 | Standards change
119786348 | insulator and brushing | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-03-22 | 2023-09-15 | Level 2 | Standards change
119786466 | insulator and brushing | Non-HFTD | Transmission | 2020-09-14 | 2021-09-14 | Level 2 | E | 2024-02-01 | 2023-09-14 | Level 2 | Standards change
119786590 | pole | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-03-22 | 2023-09-15 | Level 2 | Standards change
119786615 | pole | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-03-22 | 2023-09-15 | Level 2 | Standards change
119786657 | pole | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-11-22 | 2023-09-15 | Level 2 | Field Safety Reassessment
119786671 | pole | Non-HFTD | Transmission | 2020-09-16 | 2021-09-16 | Level 2 | E | 2023-12-21 | 2023-09-16 | Level 2 | Standards change
119787138 | insulator and brushing | Non-HFTD | Transmission | 2020-09-16 | 2021-09-16 | Level 2 | E | 2024-01-17 | 2023-09-16 | Level 2 | Standards change
119787288 | other | Non-HFTD | Transmission | 2020-09-17 | 2022-09-17 | Level 3 | F | 2024-01-10 | 2025-09-17 | Level 3 | Standards change
119787600 | other | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-03-22 | 2025-09-15 | Level 3 | Standards change
119787849 | insulator and brushing | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-10-05 | 2023-09-15 | Level 2 | GO 165 Inspection
119787916 | pole | Non-HFTD | Transmission | 2020-09-15 | 2021-09-15 | Level 2 | E | 2024-10-08 | 2023-09-15 | Level 2 | GO 165 Inspection
119789017 | insulator and brushing | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-08-19 | 2023-09-18 | Level 2 | GO 165 Inspection
119789039 | other | Non-HFTD | Transmission | 2020-09-18 | 2022-09-18 | Level 3 | F | 2024-09-09 | 2025-09-18 | Level 3 | GO 165 Inspection
119789083 | pole | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2023-03-27 | 2021-09-18 | Level 2 | Standards change
119789084 | insulator and brushing | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2023-08-14 | 2023-09-18 | Level 2 | Standards change
119789457 | other | Non-HFTD | Transmission | 2020-09-17 | 2021-09-17 | Level 2 | E | 2024-09-06 | 2021-09-17 | Level 2 | GO 165 Inspection
119789588 | insulator and brushing | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2023-07-18 | 2023-09-18 | Level 2 | Standards change
119789600 | insulator and brushing | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-10-02 | 2023-09-18 | Level 2 | Field Safety Reassessment
119789738 | insulator and brushing | Non-HFTD | Transmission | 2020-09-17 | 2021-09-17 | Level 2 | E | 2024-02-06 | 2023-09-17 | Level 2 | Standards change
119789785 | pole | Non-HFTD | Transmission | 2020-09-18 | 2023-09-18 | Level 2 | E | 2024-12-13 | 2021-03-18 | Level 2 | Field Safety Reassessment
119789789 | crossarm | Non-HFTD | Transmission | 2020-09-20 | 2021-09-20 | Level 2 | E | 2024-12-13 | 2023-09-20 | Level 2 | Field Safety Reassessment
119789800 | pole | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-12-14 | 2023-09-18 | Level 2 | Field Safety Reassessment
119789803 | pole | Non-HFTD | Transmission | 2020-09-18 | 2023-09-18 | Level 2 | E | 2024-12-13 | 2021-09-18 | Level 2 | Field Safety Reassessment
119789812 | pole | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-12-30 | 2023-09-18 | Level 2 | Field Safety Reassessment
119789814 | pole | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-12-14 | 2023-09-18 | Level 2 | Field Safety Reassessment
119789818 | crossarm | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-12-13 | 2023-09-18 | Level 2 | Field Safety Reassessment
119789969 | insulator and brushing | Non-HFTD | Transmission | 2020-09-18 | 2021-09-18 | Level 2 | E | 2024-10-02 | 2023-09-18 | Level 2 | Field Safety Reassessment
119790478 | other | Non-HFTD | Transmission | 2020-07-31 | 2022-07-31 | Level 3 | F | 2023-01-23 | 2025-07-31 | Level 3 | Standards change
119790542 | other | Non-HFTD | Transmission | 2020-08-03 | 2022-08-03 | Level 3 | F | 2024-02-28 | 2025-08-03 | Level 3 | Standards change
119791596 | anchor/guy | Non-HFTD | Transmission | 2020-08-19 | 2021-08-19 | Level 2 | E | 2024-01-16 | 2025-08-19 | Level 3 | Standards change
119792474 | anchor/guy | Non-HFTD | Transmission | 2020-09-21 | 2025-09-20 | Level 2 | E | 2024-10-29 | 2021-09-21 | Level 2 | GO 165 Inspection
119792611 | pole | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2024-12-18 | 2023-09-21 | Level 2 | Field Safety Reassessment
119792727 | other | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2024-10-10 | 2025-09-21 | Level 3 | GO 165 Inspection
119792789 | other | HFTD Tier 2 | Transmission | 2020-08-07 | 2025-08-07 | Level 3 | F |  | 2025-08-07 | Level 3
119793044 | pole | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2023-04-05 | 2023-09-21 | Level 2 | Standards change
119793472 | pole | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2023-03-23 | 2023-09-21 | Level 2 | Field Safety Reassessment
119794465 | pole | Non-HFTD | Transmission | 2020-09-21 | 2022-09-21 | Level 3 | F | 2024-01-09 | 2025-09-21 | Level 3 | Standards change
119794466 | other | Non-HFTD | Transmission | 2020-09-21 | 2022-09-21 | Level 3 | F | 2024-02-28 | 2025-09-21 | Level 3 | Standards change
119794535 | anchor/guy | Non-HFTD | Transmission | 2020-09-19 | 2021-09-19 | Level 2 | E | 2024-01-03 | 2025-09-19 | Level 3 | Standards change
119794710 | anchor/guy | Non-HFTD | Transmission | 2020-09-19 | 2021-09-19 | Level 2 | E | 2024-01-03 | 2025-09-19 | Level 3 | Standards change
119794711 | anchor/guy | Non-HFTD | Transmission | 2020-09-19 | 2021-09-19 | Level 2 | E | 2023-12-26 | 2025-09-19 | Level 3 | Standards change
119794862 | other | Non-HFTD | Transmission | 2020-09-18 | 2022-09-18 | Level 3 | F | 2024-02-28 | 2025-09-18 | Level 3 | Standards change
119795016 | other | HFTD Tier 2 | Transmission | 2020-08-05 | 2022-08-05 | Level 3 | F | 2023-03-10 | 2025-08-05 | Level 3 | Standards change
119795340 | anchor/guy | Non-HFTD | Transmission | 2020-09-19 | 2021-09-19 | Level 2 | E | 2024-09-05 | 2025-09-19 | Level 3 | GO 165 Inspection
119797403 | anchor/guy | Non-HFTD | Transmission | 2020-09-19 | 2021-09-19 | Level 2 | E | 2024-10-16 | 2025-09-19 | Level 3 | GO 165 Inspection
119798443 | pole | Non-HFTD | Transmission | 2020-09-22 | 2022-09-22 | Level 3 | F | 2023-02-02 | 2025-09-22 | Level 3 | Standards change
119798988 | pole | Non-HFTD | Transmission | 2020-09-22 | 2021-09-22 | Level 2 | E | 2024-12-30 | 2023-09-22 | Level 2 | Field Safety Reassessment
119800249 | pole | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2024-11-23 | 2023-09-21 | Level 2 | Field Safety Reassessment
119800372 | insulator and brushing | Non-HFTD | Transmission | 2020-09-17 | 2021-09-17 | Level 2 | E | 2024-10-25 | 2023-09-17 | Level 2 | GO 165 Inspection
119800658 | other | Non-HFTD | Transmission | 2020-09-21 | 2022-09-21 | Level 3 | F | 2024-04-06 | 2025-09-21 | Level 3 | Standards change
119801467 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2024-04-06 | 2025-09-23 | Level 3 | Standards change
119802617 | pole | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2024-07-30 | 2023-09-23 | Level 2 | Field Safety Reassessment
119802800 | anchor/guy | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2024-09-23 | 2023-09-23 | Level 2 | Field Safety Reassessment
119803266 | anchor/guy | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2024-01-22 | 2025-09-21 | Level 3 | Standards change
119803534 | pole | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2023-04-05 | 2023-09-23 | Level 2 | Standards change
119804226 | other | HFTD Tier 2 | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-04-24 | 2025-08-07 | Level 3 | GO 165 Inspection
119805137 | other | HFTD Tier 3 | Transmission | 2020-08-07 | 2022-08-07 | Level 3 | F | 2024-04-06 | 2025-08-07 | Level 3 | Standards change
119805432 | insulator and brushing | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2022-12-30 | 2023-09-21 | Level 2 | Standards change
119805464 | pole | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2024-12-03 | 2023-09-21 | Level 2 | Field Safety Reassessment
119805465 | pole | Non-HFTD | Transmission | 2020-09-21 | 2021-09-21 | Level 2 | E | 2024-12-03 | 2023-09-21 | Level 2 | Field Safety Reassessment
119805689 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119805771 | other | HFTD Tier 2 | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2023-04-17 | 2025-08-10 | Level 3 | Standards change
119805838 | other | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2024-04-06 | 2025-08-10 | Level 3 | Standards change
119805847 | other | Non-HFTD | Transmission | 2020-08-10 | 2022-08-10 | Level 3 | F | 2023-12-12 | 2025-08-10 | Level 3 | Standards change
119806033 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2024-01-29 | 2025-09-23 | Level 3 | Standards change
119806259 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2023-12-28 | 2025-09-23 | Level 3 | Standards change
119806283 | insulator and brushing | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2024-09-19 | 2023-09-23 | Level 2 | GO 165 Inspection
119806608 | other | Non-HFTD | Transmission | 2020-09-24 | 2022-09-24 | Level 3 | F | 2024-08-13 | 2025-09-24 | Level 3 | GO 165 Inspection
119807334 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2023-08-07 | 2025-09-23 | Level 3 | Standards change
119807372 | other | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2024-06-17 | 2023-09-23 | Level 2 | Field Safety Reassessment
119807475 | other | Non-HFTD | Transmission | 2020-09-24 | 2022-09-24 | Level 3 | F | 2024-10-17 | 2025-09-24 | Level 3 | GO 165 Inspection
119808105 | insulator and brushing | Non-HFTD | Transmission | 2020-09-24 | 2021-09-24 | Level 2 | E | 2024-12-06 | 2023-09-24 | Level 2 | Field Safety Reassessment
119808181 | other | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2023-01-18 | 2025-09-23 | Level 3 | Standards change
119808321 | insulator and brushing | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2023-07-11 | 2023-09-23 | Level 2 | Standards change
119808431 | pole | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2023-08-03 | 2025-08-12 | Level 3 | Standards change
119808646 | other | HFTD Tier 2 | Transmission | 2020-08-13 | 2022-08-13 | Level 3 | F | 2024-05-22 | 2025-08-13 | Level 3 | GO 165 Inspection
119808838 | pole | Non-HFTD | Transmission | 2020-09-24 | 2022-09-24 | Level 3 | F | 2023-07-20 | 2025-09-24 | Level 3 | Standards change
119809830 | other | HFTD Tier 2 | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-04-24 | 2025-08-12 | Level 3 | GO 165 Inspection
119809887 | pole | Non-HFTD | Transmission | 2020-08-17 | 2022-08-17 | Level 3 | F | 2024-09-11 | 2025-08-17 | Level 3 | GO 165 Inspection
119809936 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2023-12-28 | 2025-09-23 | Level 3 | Standards change
119810031 | other | Non-HFTD | Transmission | 2020-08-25 | 2022-08-25 | Level 3 | F | 2024-03-07 | 2025-08-25 | Level 3 | Standards change
119810081 | other | Non-HFTD | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-04-06 | 2025-08-12 | Level 3 | Standards change
119810085 | other | HFTD Tier 2 | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-05-02 | 2025-08-12 | Level 3 | GO 165 Inspection
119810204 | other | HFTD Tier 2 | Transmission | 2020-08-12 | 2022-08-12 | Level 3 | F | 2024-05-01 | 2025-08-12 | Level 3 | GO 165 Inspection
119810429 | other | Non-HFTD | Transmission | 2020-08-14 | 2022-08-14 | Level 3 | F | 2024-07-12 | 2025-08-14 | Level 3 | GO 165 Inspection
119811251 | other | HFTD Tier 3 | Transmission | 2020-08-26 | 2022-08-26 | Level 3 | F | 2024-04-06 | 2025-08-26 | Level 3 | Standards change
119811465 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119811524 | insulator and brushing | Non-HFTD | Transmission | 2020-09-19 | 2021-09-19 | Level 2 | E | 2024-10-29 | 2023-09-19 | Level 2 | GO 165 Inspection
119812936 | conductor | Non-HFTD | Transmission | 2020-09-25 | 2021-09-25 | Level 2 | E | 2024-07-10 | 2023-09-25 | Level 2 | Field Safety Reassessment
119813154 | pole | Non-HFTD | Transmission | 2020-09-25 | 2021-09-25 | Level 2 | E | 2023-04-17 | 2023-09-25 | Level 2 | Standards change
119813296 | pole | Non-HFTD | Transmission | 2020-09-25 | 2021-09-25 | Level 2 | E | 2023-04-17 | 2023-09-25 | Level 2 | Standards change
119814122 | other | Non-HFTD | Transmission | 2020-09-25 | 2022-09-25 | Level 3 | F | 2023-03-08 | 2025-09-25 | Level 3 | Standards change
119814150 | other | Non-HFTD | Transmission | 2020-09-25 | 2022-09-25 | Level 3 | F | 2024-04-06 | 2025-09-25 | Level 3 | Standards change
119816021 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119816174 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119816176 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119816177 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119816186 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-04-06 | 2025-08-28 | Level 3 | Standards change
119816324 | other | HFTD Tier 2 | Transmission | 2020-08-29 | 2022-08-29 | Level 3 | F | 2023-05-09 | 2025-08-29 | Level 3 | Standards change
119816371 | other | Non-HFTD | Transmission | 2020-08-31 | 2022-08-31 | Level 3 | F | 2024-04-06 | 2025-08-31 | Level 3 | Standards change
119816372 | other | Non-HFTD | Transmission | 2020-08-31 | 2022-08-31 | Level 3 | F | 2024-04-06 | 2025-08-31 | Level 3 | Standards change
119816374 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-10-09 | 2025-08-27 | Level 3 | GO 165 Inspection
119816375 | other | Non-HFTD | Transmission | 2020-08-05 | 2022-08-05 | Level 3 | F | 2024-04-06 | 2025-08-05 | Level 3 | Standards change
119816612 | other | Non-HFTD | Transmission | 2020-09-11 | 2022-09-11 | Level 3 | F | 2024-04-06 | 2025-09-11 | Level 3 | Standards change
119816637 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119816687 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119816745 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-04-06 | 2025-09-04 | Level 3 | Standards change
119816840 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-04-06 | 2025-09-04 | Level 3 | Standards change
119817270 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-04-06 | 2025-08-28 | Level 3 | Standards change
119817617 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-04-06 | 2025-08-27 | Level 3 | Standards change
119817619 | other | Non-HFTD | Transmission | 2020-08-27 | 2022-08-27 | Level 3 | F | 2024-10-24 | 2025-08-27 | Level 3 | GO 165 Inspection
119818079 | other | Non-HFTD | Transmission | 2020-08-28 | 2022-08-28 | Level 3 | F | 2024-04-06 | 2025-08-28 | Level 3 | Standards change
119818182 | other | Non-HFTD | Transmission | 2020-09-11 | 2021-09-11 | Level 2 | E | 2023-04-03 | 2023-09-11 | Level 2 | Standards change
119818240 | other | Non-HFTD | Transmission | 2020-08-31 | 2022-08-31 | Level 3 | F | 2024-06-28 | 2025-08-31 | Level 3 | GO 165 Inspection
119818245 | other | HFTD Tier 3 | Transmission | 2020-09-11 | 2022-09-11 | Level 3 | F | 2024-04-23 | 2025-09-11 | Level 3 | GO 165 Inspection
119818631 | other | HFTD Tier 2 | Transmission | 2020-09-01 | 2022-09-01 | Level 3 | F | 2024-03-07 | 2025-09-01 | Level 3 | GO 165 Inspection
119818721 | other | Non-HFTD | Transmission | 2020-08-31 | 2022-08-31 | Level 3 | F | 2024-04-06 | 2025-08-31 | Level 3 | Standards change
119819264 | other | Non-HFTD | Transmission | 2020-09-01 | 2022-09-01 | Level 3 | F | 2024-10-21 | 2025-09-01 | Level 3 | GO 165 Inspection
119819591 | other | Non-HFTD | Transmission | 2020-09-15 | 2022-09-15 | Level 3 | F | 2024-04-06 | 2025-09-15 | Level 3 | Standards change
119819592 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119819657 | other | Non-HFTD | Transmission | 2020-09-15 | 2022-09-15 | Level 3 | F | 2024-04-06 | 2025-09-15 | Level 3 | Standards change
119820025 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119820039 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119820391 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-04-06 | 2025-09-02 | Level 3 | Standards change
119820396 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-04-06 | 2025-09-03 | Level 3 | Standards change
119820455 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-04-06 | 2025-09-03 | Level 3 | Standards change
119820465 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-01 | 2025-09-03 | Level 3 | GO 165 Inspection
119820879 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-02 | 2025-09-03 | Level 3 | GO 165 Inspection
119821048 | insulator and brushing | Non-HFTD | Transmission | 2020-09-25 | 2021-09-25 | Level 2 | E | 2024-08-29 | 2023-09-25 | Level 2 | GO 165 Inspection
119821198 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-04-06 | 2025-09-03 | Level 3 | Standards change
119821984 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-09-27 | 2025-09-04 | Level 3 | GO 165 Inspection
119822051 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-04-06 | 2025-09-04 | Level 3 | Standards change
119822127 | pole | Non-HFTD | Transmission | 2020-09-23 | 2021-09-23 | Level 2 | E | 2024-09-23 | 2023-09-23 | Level 2 | GO 165 Inspection
119822289 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-01 | 2025-09-03 | Level 3 | GO 165 Inspection
119822835 | other | Non-HFTD | Transmission | 2020-09-28 | 2022-09-28 | Level 3 | F | 2024-04-06 | 2025-09-28 | Level 3 | Standards change
119822962 | pole | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2023-12-08 | 2025-09-03 | Level 3 | Standards change
119824219 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2023-01-17 | 2025-09-03 | Level 3 | Standards change
119824831 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-01 | 2025-09-03 | Level 3 | GO 165 Inspection
119824911 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-02 | 2025-09-03 | Level 3 | GO 165 Inspection
119825326 | anchor/guy | Non-HFTD | Transmission | 2020-09-28 | 2021-09-28 | Level 2 | E | 2024-02-01 | 2025-09-27 | Level 3 | GO 165 Inspection
119826090 | other | Non-HFTD | Transmission | 2020-09-29 | 2021-09-29 | Level 2 | E | 2024-10-16 | 2021-09-29 | Level 2 | GO 165 Inspection
119826426 | pole | Non-HFTD | Transmission | 2020-09-29 | 2021-09-29 | Level 2 | E | 2023-04-25 | 2023-09-29 | Level 2 | Standards change
119826575 | anchor/guy | Non-HFTD | Transmission | 2020-09-29 | 2021-09-29 | Level 2 | E | 2024-01-30 | 2025-09-29 | Level 3 | Standards change
119826796 | pole | Non-HFTD | Transmission | 2020-09-29 | 2021-09-29 | Level 2 | E | 2024-10-21 | 2023-09-29 | Level 2 | GO 165 Inspection
119826831 | insulator and brushing | Non-HFTD | Transmission | 2020-09-28 | 2021-09-28 | Level 2 | E | 2024-01-22 | 2023-09-28 | Level 2 | Standards change
119826908 | insulator and brushing | Non-HFTD | Transmission | 2020-09-24 | 2021-09-24 | Level 2 | E | 2024-01-19 | 2023-09-24 | Level 2 | Standards change
119827105 | insulator and brushing | Non-HFTD | Transmission | 2020-09-29 | 2021-09-29 | Level 2 | E | 2024-07-22 | 2023-09-29 | Level 2 | Field Safety Reassessment
119829523 | other | Non-HFTD | Transmission | 2020-09-29 | 2022-09-29 | Level 3 | F | 2023-02-08 | 2025-09-29 | Level 3 | Standards change
119829526 | other | Non-HFTD | Transmission | 2020-09-29 | 2022-09-29 | Level 3 | F | 2024-01-02 | 2025-09-29 | Level 3 | Standards change
119830183 | insulator and brushing | Non-HFTD | Transmission | 2020-09-28 | 2021-09-28 | Level 2 | E | 2024-07-25 | 2023-09-28 | Level 2 | GO 165 Inspection
119830300 | insulator and brushing | Non-HFTD | Transmission | 2020-09-28 | 2021-09-28 | Level 2 | E | 2023-12-19 | 2023-09-28 | Level 2 | Standards change
119830305 | insulator and brushing | Non-HFTD | Transmission | 2020-09-25 | 2021-09-25 | Level 2 | E | 2024-12-23 | 2023-09-25 | Level 2 | Field Safety Reassessment
119831393 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-09-18 | 2025-09-03 | Level 3 | GO 165 Inspection
119831954 | other | Non-HFTD | Transmission | 2020-09-30 | 2022-09-30 | Level 3 | F | 2024-05-20 | 2025-09-30 | Level 3 | GO 165 Inspection
119833004 | pole | Non-HFTD | Transmission | 2020-09-30 | 2021-09-30 | Level 2 | E | 2024-10-22 | 2023-09-30 | Level 2 | GO 165 Inspection
119833022 | pole | Non-HFTD | Transmission | 2020-09-30 | 2021-09-30 | Level 2 | E | 2024-10-22 | 2023-09-30 | Level 2 | GO 165 Inspection
119835267 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-04-06 | 2025-09-04 | Level 3 | Standards change
119835388 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2024-06-27 | 2025-09-02 | Level 3 | GO 165 Inspection
119835543 | other | Non-HFTD | Transmission | 2020-09-02 | 2022-09-02 | Level 3 | F | 2023-07-20 | 2025-09-02 | Level 3 | Standards change
119836119 | other | Non-HFTD | Transmission | 2020-10-01 | 2022-10-01 | Level 3 | F | 2023-11-30 | 2025-10-01 | Level 3 | Standards change
119836786 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-10-10 | 2023-10-01 | Level 2 | GO 165 Inspection
119836789 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2023-10-01 | Level 2 | E | 2024-10-10 | 2021-01-01 | Level 2 | GO 165 Inspection
119836830 | pole | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-10-18 | 2023-10-01 | Level 2 | GO 165 Inspection
119837257 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-10-10 | 2023-10-01 | Level 2 | GO 165 Inspection
119837299 | anchor/guy | Non-HFTD | Transmission | 2020-09-28 | 2021-09-28 | Level 2 | E | 2024-10-01 | 2025-09-28 | Level 3 | GO 165 Inspection
119837448 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2023-10-01 | Level 2 | E | 2024-11-12 | 2021-10-01 | Level 2 | GO 165 Inspection
119838186 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-11-27 | 2023-10-01 | Level 2 | GO 165 Inspection
119838368 | anchor/guy | Non-HFTD | Transmission | 2020-09-29 | 2021-09-29 | Level 2 | E | 2023-10-13 | 2025-09-29 | Level 3 | Standards change
119838466 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-10-10 | 2023-10-01 | Level 2 | GO 165 Inspection
119839242 | other | Non-HFTD | Transmission | 2020-10-01 | 2022-10-01 | Level 3 | F | 2023-12-20 | 2025-10-01 | Level 3 | Standards change
119844080 | other | Non-HFTD | Transmission | 2020-09-08 | 2022-09-08 | Level 3 | F | 2024-09-23 | 2025-09-08 | Level 3 | GO 165 Inspection
119844093 | other | Non-HFTD | Transmission | 2020-09-15 | 2022-09-15 | Level 3 | F | 2024-01-18 | 2025-09-15 | Level 3 | Standards change
119844158 | other | Non-HFTD | Transmission | 2020-09-04 | 2022-09-04 | Level 3 | F | 2024-04-06 | 2025-09-04 | Level 3 | Standards change
119844269 | other | Non-HFTD | Transmission | 2020-09-14 | 2022-09-14 | Level 3 | F | 2023-07-17 | 2025-09-14 | Level 3 | Standards change
119844302 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-09-27 | 2025-09-03 | Level 3 | GO 165 Inspection
119844336 | other | Non-HFTD | Transmission | 2020-09-03 | 2022-09-03 | Level 3 | F | 2024-08-02 | 2025-09-03 | Level 3 | GO 165 Inspection
119844718 | other | HFTD Tier 3 | Transmission | 2020-09-09 | 2022-09-09 | Level 3 | F | 2024-06-26 | 2025-09-09 | Level 3 | GO 165 Inspection
119844774 | insulator and brushing | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-08-31 | 2023-10-02 | Level 2 | GO 165 Inspection
119844911 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-03-22 | 2023-10-01 | Level 2 | Standards change
119845513 | other | HFTD Tier 3 | Transmission | 2020-09-16 | 2022-09-16 | Level 3 | F | 2024-05-25 | 2025-09-16 | Level 3 | GO 165 Inspection
119845592 | pole | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2023-06-13 | 2023-10-02 | Level 2 | Standards change
119845818 | pole | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-06-13 | 2023-10-02 | Level 2 | Field Safety Reassessment
119846076 | pole | Non-HFTD | Transmission | 2020-10-02 | 2022-10-02 | Level 3 | F | 2023-12-05 | 2025-10-02 | Level 3 | Standards change
119847593 | insulator and brushing | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2023-08-16 | 2025-10-02 | Level 3 | Standards change
119847595 | insulator and brushing | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2023-08-16 | 2025-10-02 | Level 3 | Standards change
119847673 | other | Non-HFTD | Transmission | 2020-10-02 | 2022-10-02 | Level 3 | F | 2024-04-06 | 2025-10-02 | Level 3 | Standards change
119848381 | other | Non-HFTD | Transmission | 2020-09-16 | 2022-09-16 | Level 3 | F | 2024-04-06 | 2025-09-16 | Level 3 | Standards change
119848782 | insulator and brushing | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-10-09 | 2023-10-02 | Level 2 | GO 165 Inspection
119850058 | other | Non-HFTD | Transmission | 2020-10-01 | 2022-10-01 | Level 3 | F | 2023-12-01 | 2025-10-01 | Level 3 | Standards change
119850248 | insulator and brushing | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2023-07-21 | 2023-10-01 | Level 2 | Standards change
119850730 | other | Non-HFTD | Transmission | 2020-09-16 | 2022-09-16 | Level 3 | F | 2024-04-30 | 2025-09-16 | Level 3 | GO 165 Inspection
119850850 | pole | Non-HFTD | Transmission | 2020-10-03 | 2021-10-03 | Level 2 | E | 2024-06-26 | 2023-10-03 | Level 2 | GO 165 Inspection
119850944 | other | Non-HFTD | Transmission | 2020-09-16 | 2022-09-16 | Level 3 | F | 2024-04-06 | 2025-09-16 | Level 3 | Standards change
119851016 | pole | Non-HFTD | Transmission | 2020-10-03 | 2021-10-03 | Level 2 | E | 2024-01-31 | 2023-10-03 | Level 2 | GO 165 Inspection
119851074 | insulator and brushing | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-10-07 | 2023-10-02 | Level 2 | GO 165 Inspection
119851136 | other | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-11-19 | 2025-10-02 | Level 3 | Field Safety Reassessment
119851160 | pole | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-10-07 | 2023-10-01 | Level 2 | GO 165 Inspection
119851632 | other | Non-HFTD | Transmission | 2020-09-18 | 2022-09-18 | Level 3 | F | 2023-08-03 | 2025-09-18 | Level 3 | Standards change
119851893 | other | Non-HFTD | Transmission | 2020-09-18 | 2022-09-18 | Level 3 | F | 2024-04-06 | 2025-09-18 | Level 3 | Standards change
119852362 | other | Non-HFTD | Transmission | 2020-10-02 | 2022-10-02 | Level 3 | F | 2024-04-06 | 2025-10-02 | Level 3 | Standards change
119852391 | other | Non-HFTD | Transmission | 2020-09-30 | 2022-09-30 | Level 3 | F | 2023-07-27 | 2025-09-30 | Level 3 | Standards change
119853559 | pole | Non-HFTD | Transmission | 2020-10-02 | 2022-10-02 | Level 3 | F | 2024-10-04 | 2025-10-02 | Level 3 | GO 165 Inspection
119854683 | other | Non-HFTD | Transmission | 2020-10-05 | 2022-10-05 | Level 3 | F | 2024-04-06 | 2025-10-05 | Level 3 | Standards change
119856370 | other | Non-HFTD | Transmission | 2020-10-03 | 2022-10-03 | Level 3 | F | 2024-04-06 | 2025-10-03 | Level 3 | Standards change
119858916 | insulator and brushing | Non-HFTD | Transmission | 2020-10-05 | 2021-10-05 | Level 2 | E | 2024-10-07 | 2023-10-05 | Level 2 | GO 165 Inspection
119858918 | other | Non-HFTD | Transmission | 2020-10-05 | 2021-10-05 | Level 2 | E | 2024-10-07 | 2021-10-05 | Level 2 | GO 165 Inspection
119859269 | pole | Non-HFTD | Transmission | 2020-10-06 | 2021-10-06 | Level 2 | E | 2023-12-28 | 2025-10-06 | Level 3 | Standards change
119863893 | insulator and brushing | Non-HFTD | Transmission | 2020-10-06 | 2021-10-06 | Level 2 | E | 2023-05-17 | 2023-10-06 | Level 2 | Standards change
119864257 | pole | Non-HFTD | Transmission | 2020-10-07 | 2022-10-07 | Level 3 | F | 2023-01-31 | 2025-10-07 | Level 3 | Standards change
119864306 | other | Non-HFTD | Transmission | 2020-10-07 | 2021-10-07 | Level 2 | E | 2024-08-28 | 2025-10-07 | Level 3 | GO 165 Inspection
119864487 | other | Non-HFTD | Transmission | 2020-10-06 | 2021-10-06 | Level 2 | E | 2024-09-29 | 2021-10-06 | Level 2 | Field Safety Reassessment
119865016 | insulator and brushing | Non-HFTD | Transmission | 2020-10-07 | 2021-10-07 | Level 2 | E | 2024-12-17 | 2023-10-07 | Level 2 | Field Safety Reassessment
119866008 | pole | Non-HFTD | Transmission | 2020-10-01 | 2021-10-01 | Level 2 | E | 2024-06-17 | 2023-10-01 | Level 2 | Field Safety Reassessment
119866130 | pole | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-10-05 | 2021-10-02 | Level 2 | GO 165 Inspection
119866135 | other | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2023-01-12 | 2023-10-02 | Level 2 | Standards change
119866940 | other | Non-HFTD | Transmission | 2020-09-28 | 2022-09-28 | Level 3 | F | 2024-06-21 | 2025-09-28 | Level 3 | GO 165 Inspection
119867877 | other | Non-HFTD | Transmission | 2020-10-06 | 2022-10-06 | Level 3 | F | 2023-08-09 | 2025-10-06 | Level 3 | Standards change
119867950 | other | Non-HFTD | Transmission | 2020-10-06 | 2022-10-06 | Level 3 | F | 2024-09-23 | 2025-10-06 | Level 3 | GO 165 Inspection
119869616 | insulator and brushing | Non-HFTD | Transmission | 2020-10-03 | 2021-10-03 | Level 2 | E | 2024-11-20 | 2023-10-03 | Level 2 | Field Safety Reassessment
119870384 | pole | Non-HFTD | Transmission | 2020-10-07 | 2021-10-07 | Level 2 | E | 2023-12-28 | 2023-10-07 | Level 2 | Standards change
119871119 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-01-08 | 2025-10-08 | Level 3 | Standards change
119871497 | conductor | Non-HFTD | Transmission | 2020-09-25 | 2021-09-25 | Level 2 | E | 2024-06-21 | 2023-09-25 | Level 2 | GO 165 Inspection
119872735 | other | Non-HFTD | Transmission | 2020-10-07 | 2022-10-07 | Level 3 | F | 2024-04-06 | 2025-10-07 | Level 3 | Standards change
119873424 | insulator and brushing | Non-HFTD | Transmission | 2020-10-07 | 2021-10-07 | Level 2 | E | 2024-12-19 | 2023-10-07 | Level 2 | Field Safety Reassessment
119873431 | other | Non-HFTD | Transmission | 2020-10-05 | 2022-10-05 | Level 3 | F | 2024-04-06 | 2025-10-05 | Level 3 | Standards change
119873563 | insulator and brushing | Non-HFTD | Transmission | 2020-10-05 | 2021-10-05 | Level 2 | E | 2024-03-25 | 2023-10-05 | Level 2 | Standards change
119874502 | pole | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-09-23 | 2023-10-08 | Level 2 | GO 165 Inspection
119875041 | pole | Non-HFTD | Transmission | 2020-10-08 | 2023-10-08 | Level 2 | E | 2024-08-30 | 2021-10-08 | Level 2 | GO 165 Inspection
119878586 | pole | Non-HFTD | Transmission | 2020-10-05 | 2021-10-05 | Level 2 | E | 2024-12-23 | 2023-10-05 | Level 2 | Field Safety Reassessment
119887522 | insulator and brushing | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-12-03 | 2023-10-08 | Level 2 | Field Safety Reassessment
119887695 | pole | Non-HFTD | Transmission | 2020-10-06 | 2021-10-06 | Level 2 | E | 2023-07-20 | 2023-10-06 | Level 2 | Standards change
119890621 | anchor/guy | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-07-11 | 2025-10-08 | Level 3 | GO 165 Inspection
119891105 | crossarm | Non-HFTD | Transmission | 2020-10-02 | 2021-10-02 | Level 2 | E | 2024-10-08 | 2023-10-02 | Level 2 | Field Safety Reassessment
119891193 | other | Non-HFTD | Transmission | 2020-10-12 | 2022-10-12 | Level 3 | F | 2023-12-28 | 2025-10-12 | Level 3 | Standards change
119891577 | pole | Non-HFTD | Transmission | 2020-10-05 | 2021-10-05 | Level 2 | E | 2024-09-29 | 2023-10-05 | Level 2 | Field Safety Reassessment
119891919 | insulator and brushing | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-12-27 | 2023-10-12 | Level 2 | Field Safety Reassessment
119891969 | insulator and brushing | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-02-06 | 2023-10-12 | Level 2 | Standards change
119893410 | pole | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2023-01-24 | 2025-10-09 | Level 3 | Standards change
119893921 | insulator and brushing | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-12-03 | 2023-10-08 | Level 2 | Field Safety Reassessment
119893965 | insulator and brushing | Non-HFTD | Transmission | 2020-10-06 | 2021-10-06 | Level 2 | E | 2023-05-23 | 2023-10-06 | Level 2 | Standards change
119895250 | insulator and brushing | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-09-23 | 2023-10-08 | Level 2 | Field Safety Reassessment
119895711 | insulator and brushing | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-01-16 | 2023-10-09 | Level 2 | Standards change
119895757 | anchor/guy | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-09-30 | 2025-10-08 | Level 3 | GO 165 Inspection
119896078 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-01-29 | 2025-10-09 | Level 3 | Standards change
119896151 | crossarm | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2022-12-13 | 2021-10-09 | Level 2 | Field Safety Reassessment
119896236 | pole | Non-HFTD | Transmission | 2020-10-13 | 2022-10-13 | Level 3 | F | 2024-11-08 | 2025-10-13 | Level 3 | GO 165 Inspection
119897192 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-09-11 | 2025-10-09 | Level 3 | GO 165 Inspection
119897302 | pole | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2022-12-13 | 2023-10-08 | Level 2 | Standards change
119897314 | other | Non-HFTD | Transmission | 2020-10-13 | 2021-10-13 | Level 2 | E | 2023-01-09 | 2025-10-13 | Level 3 | Standards change
119901943 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-07-25 | 2025-10-08 | Level 3 | GO 165 Inspection
119905844 | insulator and brushing | Non-HFTD | Transmission | 2020-10-14 | 2021-10-14 | Level 2 | E | 2024-07-15 | 2023-10-14 | Level 2 | GO 165 Inspection
119906512 | anchor/guy | Non-HFTD | Transmission | 2020-10-14 | 2021-10-14 | Level 2 | E | 2024-07-17 | 2021-04-14 | Level 2 | GO 165 Inspection
119906934 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-10-10 | 2025-10-08 | Level 3 | GO 165 Inspection
119906938 | insulator and brushing | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-07-24 | 2023-10-08 | Level 2 | GO 165 Inspection
119906986 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-04-06 | 2025-10-08 | Level 3 | Standards change
119907369 | insulator and brushing | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-09-11 | 2023-10-09 | Level 2 | GO 165 Inspection
119907446 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-09-24 | 2025-10-09 | Level 3 | GO 165 Inspection
119907509 | insulator and brushing | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2023-05-18 | 2023-10-08 | Level 2 | Standards change
119907531 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-10-01 | 2025-10-09 | Level 3 | GO 165 Inspection
119907748 | insulator and brushing | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-10-07 | 2023-10-08 | Level 2 | GO 165 Inspection
119907749 | other | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-10-07 | 2021-10-08 | Level 2 | GO 165 Inspection
119907751 | anchor/guy | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-01-03 | 2025-10-12 | Level 3 | Standards change
119910788 | other | Non-HFTD | Transmission | 2020-10-15 | 2022-10-15 | Level 3 | F | 2024-04-08 | 2025-10-15 | Level 3 | GO 165 Inspection
119911276 | other | Non-HFTD | Transmission | 2020-10-15 | 2022-10-15 | Level 3 | F | 2024-04-06 | 2025-10-15 | Level 3 | Standards change
119911564 | insulator and brushing | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-07-26 | 2023-10-12 | Level 2 | GO 165 Inspection
119912263 | other | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-08-14 | 2023-10-12 | Level 2 | GO 165 Inspection
119912434 | other | Non-HFTD | Transmission | 2020-10-08 | 2021-10-08 | Level 2 | E | 2024-08-23 | 2023-10-08 | Level 2 | GO 165 Inspection
119912438 | other | Non-HFTD | Transmission | 2020-10-09 | 2022-10-09 | Level 3 | F | 2023-12-18 | 2025-10-09 | Level 3 | Standards change
119912494 | crossarm | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2022-12-14 | 2023-10-12 | Level 2 | Standards change
119912513 | insulator and brushing | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-07-26 | 2023-10-12 | Level 2 | GO 165 Inspection
119912514 | insulator and brushing | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-07-26 | 2023-10-12 | Level 2 | GO 165 Inspection
119912583 | other | Non-HFTD | Transmission | 2020-10-12 | 2022-10-12 | Level 3 | F | 2023-12-26 | 2025-10-12 | Level 3 | Standards change
119912585 | insulator and brushing | Non-HFTD | Transmission | 2020-10-12 | 2021-10-12 | Level 2 | E | 2024-10-08 | 2023-10-12 | Level 2 | Field Safety Reassessment
119912797 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-11-01 | 2025-10-09 | Level 3 | GO 165 Inspection
119912849 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-10-01 | 2025-10-09 | Level 3 | GO 165 Inspection
119913769 | pole | Non-HFTD | Transmission | 2020-10-15 | 2021-10-15 | Level 2 | E | 2024-07-26 | 2023-10-15 | Level 2 | GO 165 Inspection
119913874 | insulator and brushing | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-09-11 | 2023-10-09 | Level 2 | GO 165 Inspection
119913877 | anchor/guy | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-09-11 | 2025-10-09 | Level 3 | GO 165 Inspection
119913943 | insulator and brushing | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-10-02 | 2023-10-09 | Level 2 | Field Safety Reassessment
119914058 | other | Non-HFTD | Transmission | 2020-10-15 | 2022-10-15 | Level 3 | F | 2024-01-08 | 2025-10-15 | Level 3 | Standards change
119914153 | insulator and brushing | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2024-08-13 | 2023-10-09 | Level 2 | GO 165 Inspection
119914485 | insulator and brushing | Non-HFTD | Transmission | 2020-10-15 | 2021-10-15 | Level 2 | E | 2024-08-15 | 2023-10-15 | Level 2 | GO 165 Inspection
119914520 | insulator and brushing | Non-HFTD | Transmission | 2020-10-15 | 2021-10-15 | Level 2 | E | 2024-08-15 | 2023-10-15 | Level 2 | GO 165 Inspection
119914722 | insulator and brushing | Non-HFTD | Transmission | 2020-10-15 | 2021-10-15 | Level 2 | E | 2024-08-15 | 2023-10-15 | Level 2 | GO 165 Inspection
119915415 | pole | Non-HFTD | Transmission | 2020-10-16 | 2022-10-16 | Level 3 | F | 2023-12-26 | 2025-10-16 | Level 3 | Standards change
119916260 | other | Non-HFTD | Transmission | 2020-10-16 | 2022-10-16 | Level 3 | F | 2024-04-06 | 2025-10-16 | Level 3 | Standards change
119916501 | other | Non-HFTD | Transmission | 2020-09-18 | 2022-09-18 | Level 3 | F | 2024-04-06 | 2025-09-18 | Level 3 | Standards change
119916538 | insulator and brushing | Non-HFTD | Transmission | 2020-10-13 | 2021-10-13 | Level 2 | E | 2024-09-03 | 2023-10-13 | Level 2 | GO 165 Inspection
119917139 | insulator and brushing | Non-HFTD | Transmission | 2020-10-13 | 2021-10-13 | Level 2 | E | 2024-01-23 | 2023-10-13 | Level 2 | Standards change
119917329 | other | Non-HFTD | Transmission | 2020-09-19 | 2022-09-19 | Level 3 | F | 2024-02-28 | 2025-09-19 | Level 3 | Standards change
119917345 | other | Non-HFTD | Transmission | 2020-09-19 | 2022-09-19 | Level 3 | F | 2024-04-06 | 2025-09-19 | Level 3 | Standards change
119917606 | other | Non-HFTD | Transmission | 2020-09-21 | 2022-09-21 | Level 3 | F | 2023-03-31 | 2025-09-21 | Level 3 | Standards change
119917640 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2024-02-28 | 2025-09-23 | Level 3 | Standards change
119917759 | other | Non-HFTD | Transmission | 2020-09-19 | 2022-09-19 | Level 3 | F | 2024-02-28 | 2025-09-19 | Level 3 | Standards change
119917837 | other | Non-HFTD | Transmission | 2020-09-25 | 2022-09-25 | Level 3 | F | 2024-04-06 | 2025-09-25 | Level 3 | Standards change
119917844 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2023-12-05 | 2025-09-23 | Level 3 | Standards change
119917846 | insulator and brushing | Non-HFTD | Transmission | 2020-10-09 | 2021-10-09 | Level 2 | E | 2023-11-10 | 2023-10-09 | Level 2 | Standards change
119918230 | other | Non-HFTD | Transmission | 2020-09-22 | 2022-09-22 | Level 3 | F | 2024-04-06 | 2025-09-22 | Level 3 | Standards change
119918233 | other | Non-HFTD | Transmission | 2020-09-22 | 2022-09-22 | Level 3 | F | 2024-04-06 | 2025-09-22 | Level 3 | Standards change
119918236 | other | Non-HFTD | Transmission | 2020-09-23 | 2022-09-23 | Level 3 | F | 2024-02-29 | 2025-09-23 | Level 3 | Standards change
119918264 | other | Non-HFTD | Transmission | 2020-09-29 | 2022-09-29 | Level 3 | F | 2023-12-05 | 2025-09-29 | Level 3 | Standards change
119918265 | other | Non-HFTD | Transmission | 2020-09-29 | 2022-09-29 | Level 3 | F | 2024-04-06 | 2025-09-29 | Level 3 | Standards change
119918338 | other | Non-HFTD | Transmission | 2020-06-24 | 2022-06-24 | Level 3 | F | 2023-12-13 | 2025-06-24 | Level 3 | Standards change
119918497 | other | Non-HFTD | Transmission | 2020-09-28 | 2022-09-28 | Level 3 | F | 2024-04-06 | 2025-09-28 | Level 3 | Standards change
119918559 | other | Non-HFTD | Transmission | 2020-09-28 | 2022-09-28 | Level 3 | F | 2023-01-20 | 2025-09-28 | Level 3 | Standards change
119918577 | other | Non-HFTD | Transmission | 2020-09-29 | 2022-09-29 | Level 3 | F | 2024-04-06 | 2025-09-29 | Level 3 | Standards change
119918650 | other | Non-HFTD | Transmission | 2020-09-28 | 2022-09-28 | Level 3 | F | 2024-04-06 | 2025-09-28 | Level 3 | Standards change
119920908 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-09-12 | 2021-10-19 | Level 2 | GO 165 Inspection
119920923 | insulator and brushing | Non-HFTD | Transmission | 2020-10-16 | 2021-10-16 | Level 2 | E | 2024-08-28 | 2023-10-16 | Level 2 | GO 165 Inspection
119921107 | insulator and brushing | Non-HFTD | Transmission | 2020-10-16 | 2021-10-16 | Level 2 | E | 2024-11-22 | 2023-10-16 | Level 2 | Field Safety Reassessment
119921514 | insulator and brushing | Non-HFTD | Transmission | 2020-10-16 | 2021-10-16 | Level 2 | E | 2024-01-19 | 2023-10-16 | Level 2 | Standards change
119922890 | insulator and brushing | Non-HFTD | Transmission | 2020-10-16 | 2021-10-16 | Level 2 | E | 2024-12-21 | 2023-10-16 | Level 2 | Field Safety Reassessment
119923371 | pole | Non-HFTD | Transmission | 2020-10-16 | 2022-10-16 | Level 3 | F | 2024-02-02 | 2025-10-16 | Level 3 | Standards change
119923498 | insulator and brushing | Non-HFTD | Transmission | 2020-10-16 | 2021-10-16 | Level 2 | E | 2024-09-09 | 2023-10-16 | Level 2 | GO 165 Inspection
119924883 | other | Non-HFTD | Transmission | 2020-10-19 | 2022-10-19 | Level 3 | F | 2023-12-07 | 2025-10-19 | Level 3 | Standards change
119924887 | anchor/guy | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-12-13 | 2021-10-19 | Level 2 | Field Safety Reassessment
119925082 | insulator and brushing | Non-HFTD | Transmission | 2020-10-16 | 2021-10-16 | Level 2 | E | 2024-02-06 | 2023-10-16 | Level 2 | Standards change
119925553 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-05-22 | 2025-10-19 | Level 3 | GO 165 Inspection
119925569 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-02-06 | 2023-10-19 | Level 2 | Standards change
119925619 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-10-15 | 2023-10-19 | Level 2 | GO 165 Inspection
119926496 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-09-09 | 2023-10-19 | Level 2 | GO 165 Inspection
119926675 | other | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-08-30 | 2025-10-19 | Level 3 | GO 165 Inspection
119927165 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-01-29 | 2023-10-19 | Level 2 | Standards change
119927408 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-09-09 | 2023-10-19 | Level 2 | GO 165 Inspection
119927439 | other | Non-HFTD | Transmission | 2020-10-20 | 2022-10-20 | Level 3 | F | 2024-05-22 | 2025-10-20 | Level 3 | GO 165 Inspection
119927443 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-12-22 | 2023-10-19 | Level 2 | Field Safety Reassessment
119927849 | other | Non-HFTD | Transmission | 2020-10-20 | 2022-10-20 | Level 3 | F | 2024-10-09 | 2025-10-20 | Level 3 | GO 165 Inspection
119928039 | other | Non-HFTD | Transmission | 2020-10-20 | 2022-10-20 | Level 3 | F | 2024-02-14 | 2025-10-20 | Level 3 | Standards change
119928140 | other | Non-HFTD | Transmission | 2020-10-19 | 2022-10-19 | Level 3 | F | 2024-01-12 | 2025-10-19 | Level 3 | Standards change
119928593 | pole | Non-HFTD | Transmission | 2020-10-19 | 2023-10-19 | Level 2 | E | 2024-09-04 | 2021-10-19 | Level 2 | GO 165 Inspection
119930098 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-12-21 | 2021-10-19 | Level 2 | Field Safety Reassessment
119931164 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-12-08 | 2023-10-19 | Level 2 | Field Safety Reassessment
119931166 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-01-22 | 2023-10-19 | Level 2 | Standards change
119932262 | anchor/guy | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-10-23 | 2025-10-20 | Level 3 | GO 165 Inspection
119932336 | insulator and brushing | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-03-20 | 2023-10-20 | Level 2 | Standards change
119932524 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-09-09 | 2023-10-19 | Level 2 | GO 165 Inspection
119932529 | insulator and brushing | Non-HFTD | Transmission | 2020-10-19 | 2021-10-19 | Level 2 | E | 2024-09-09 | 2023-10-19 | Level 2 | GO 165 Inspection
119933547 | insulator and brushing | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-08-28 | 2023-10-20 | Level 2 | GO 165 Inspection
119934106 | pole | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-09-20 | 2023-10-20 | Level 2 | GO 165 Inspection
119934409 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-28 | 2023-10-21 | Level 2 | GO 165 Inspection
119934555 | insulator and brushing | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2023-07-07 | 2023-10-20 | Level 2 | Standards change
119935028 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-10-08 | 2023-10-21 | Level 2 | GO 165 Inspection
119935602 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-10-28 | 2023-10-22 | Level 2 | GO 165 Inspection
119935639 | other | Non-HFTD | Transmission | 2020-10-20 | 2023-10-20 | Level 2 | E | 2024-08-23 | 2021-01-20 | Level 2 | GO 165 Inspection
119935748 | other | Non-HFTD | Transmission | 2020-10-21 | 2022-10-21 | Level 3 | F | 2024-01-12 | 2025-10-21 | Level 3 | Standards change
119935929 | insulator and brushing | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-08-28 | 2023-10-20 | Level 2 | GO 165 Inspection
119936481 | other | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-10-31 | 2023-10-20 | Level 2 | GO 165 Inspection
119936494 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-03-20 | 2023-10-21 | Level 2 | Standards change
119936774 | other | Non-HFTD | Transmission | 2020-10-21 | 2022-10-21 | Level 3 | F | 2024-01-05 | 2025-10-21 | Level 3 | Standards change
119936849 | other | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-29 | 2023-10-22 | Level 2 | GO 165 Inspection
119937441 | insulator and brushing | Non-HFTD | Transmission | 2020-10-20 | 2021-10-20 | Level 2 | E | 2024-11-30 | 2023-10-20 | Level 2 | Field Safety Reassessment
119937532 | pole | Non-HFTD | Transmission | 2020-10-22 | 2022-10-22 | Level 3 | F | 2024-08-29 | 2025-10-22 | Level 3 | GO 165 Inspection
119937572 | pole | Non-HFTD | Transmission | 2020-10-22 | 2022-10-22 | Level 3 | F | 2023-10-20 | 2025-10-22 | Level 3 | GO 165 Inspection
119937645 | other | Non-HFTD | Transmission | 2020-10-21 | 2022-10-21 | Level 3 | F | 2024-08-29 | 2025-10-21 | Level 3 | GO 165 Inspection
119938068 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-28 | 2023-10-21 | Level 2 | GO 165 Inspection
119938728 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-03-20 | 2023-10-21 | Level 2 | Standards change
119940270 | other | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-29 | 2021-10-22 | Level 2 | GO 165 Inspection
119941325 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-30 | 2023-10-21 | Level 2 | GO 165 Inspection
119943676 | pole | Non-HFTD | Transmission | 2020-10-24 | 2022-10-24 | Level 3 | F | 2024-09-04 | 2025-10-24 | Level 3 | GO 165 Inspection
119944882 | switch | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-11-22 | 2023-10-23 | Level 2 | Field Safety Reassessment
119946486 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-09-05 | 2023-10-23 | Level 2 | Field Safety Reassessment
119946969 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-10-08 | 2023-10-23 | Level 2 | GO 165 Inspection
119948207 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-22 | 2023-10-21 | Level 2 | GO 165 Inspection
119948281 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-12-10 | 2023-10-21 | Level 2 | Field Safety Reassessment
119948642 | pole | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-05-21 | 2023-10-22 | Level 2 | Field Safety Reassessment
119948747 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2023-07-11 | 2023-10-22 | Level 2 | Standards change
119948748 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2023-06-05 | 2023-10-22 | Level 2 | Standards change
119948902 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-23 | 2023-10-22 | Level 2 | GO 165 Inspection
119948961 | other | Non-HFTD | Transmission | 2020-10-22 | 2022-10-22 | Level 3 | F | 2023-12-28 | 2025-10-22 | Level 3 | Standards change
119949266 | insulator and brushing | Non-HFTD | Transmission | 2020-10-27 | 2021-10-27 | Level 2 | E | 2023-05-03 | 2023-10-27 | Level 2 | Standards change
119949535 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-12-08 | 2023-10-22 | Level 2 | Field Safety Reassessment
119949536 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-01-22 | 2023-10-22 | Level 2 | Standards change
119949540 | pole | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-08-29 | 2023-10-23 | Level 2 | GO 165 Inspection
119949592 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2023-05-05 | 2023-10-23 | Level 2 | Standards change
119949690 | other | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-05-23 | 2023-10-22 | Level 2 | Field Safety Reassessment
119949767 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-08-29 | 2023-10-23 | Level 2 | GO 165 Inspection
119949841 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-08-29 | 2023-10-23 | Level 2 | GO 165 Inspection
119950002 | anchor/guy | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2023-08-24 | 2025-10-22 | Level 3 | Standards change
119950463 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2023-10-22 | Level 2 | E | 2024-08-23 | 2021-10-22 | Level 2 | Field Safety Reassessment
119950569 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-03-19 | 2023-10-23 | Level 2 | Standards change
119950787 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-03-19 | 2023-10-23 | Level 2 | Standards change
119951023 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-12-20 | 2023-10-23 | Level 2 | Field Safety Reassessment
119951060 | insulator and brushing | Non-HFTD | Transmission | 2020-10-27 | 2021-10-27 | Level 2 | E | 2024-12-16 | 2021-10-27 | Level 2 | Field Safety Reassessment
119952168 | pole | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-28 | 2023-10-22 | Level 2 | GO 165 Inspection
119952169 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-28 | 2023-10-22 | Level 2 | GO 165 Inspection
119952958 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-29 | 2023-10-21 | Level 2 | GO 165 Inspection
119953055 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-29 | 2023-10-21 | Level 2 | GO 165 Inspection
119953293 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-28 | 2023-10-21 | Level 2 | GO 165 Inspection
119953351 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-08-28 | 2023-10-21 | Level 2 | GO 165 Inspection
119953664 | pole | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-12-02 | 2023-10-28 | Level 2 | Field Safety Reassessment
119953749 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2023-10-22 | Level 2 | E | 2024-08-29 | 2021-04-22 | Level 2 | GO 165 Inspection
119954152 | pole | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-03-19 | 2023-10-28 | Level 2 | Standards change
119954415 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-12-08 | 2023-10-22 | Level 2 | Field Safety Reassessment
119955521 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-03-19 | 2023-10-23 | Level 2 | Standards change
119956285 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-09-04 | 2023-10-23 | Level 2 | GO 165 Inspection
119956303 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-08-22 | 2023-10-23 | Level 2 | GO 165 Inspection
119956309 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-09-04 | 2023-10-23 | Level 2 | GO 165 Inspection
119956321 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-01-22 | 2023-10-23 | Level 2 | Standards change
119956326 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-08-22 | 2023-10-23 | Level 2 | GO 165 Inspection
119956445 | other | Non-HFTD | Transmission | 2020-10-23 | 2022-10-23 | Level 3 | F | 2023-12-28 | 2025-10-23 | Level 3 | Standards change
119958273 | insulator and brushing | Non-HFTD | Transmission | 2020-10-26 | 2021-10-26 | Level 2 | E | 2024-08-21 | 2023-10-26 | Level 2 | GO 165 Inspection
119958438 | other | Non-HFTD | Transmission | 2020-10-26 | 2022-10-26 | Level 3 | F | 2024-04-06 | 2025-10-26 | Level 3 | Standards change
119960132 | pole | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-12-02 | 2023-10-28 | Level 2 | Field Safety Reassessment
119960800 | insulator and brushing | Non-HFTD | Transmission | 2020-10-21 | 2021-10-21 | Level 2 | E | 2024-03-19 | 2023-10-21 | Level 2 | Standards change
119962013 | insulator and brushing | Non-HFTD | Transmission | 2020-10-26 | 2021-10-26 | Level 2 | E | 2024-08-19 | 2023-10-26 | Level 2 | GO 165 Inspection
119963131 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-10-09 | 2023-10-29 | Level 2 | GO 165 Inspection
119963568 | pole | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-23 | 2023-10-22 | Level 2 | GO 165 Inspection
119963670 | insulator and brushing | Non-HFTD | Transmission | 2020-10-22 | 2021-10-22 | Level 2 | E | 2024-08-29 | 2023-10-22 | Level 2 | GO 165 Inspection
119964003 | other | Non-HFTD | Transmission | 2020-10-27 | 2022-10-27 | Level 3 | F | 2024-07-20 | 2025-10-27 | Level 3 | GO 165 Inspection
119964552 | other | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2023-06-05 | 2025-10-29 | Level 3 | Standards change
119964855 | anchor/guy | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-01-24 | 2025-10-28 | Level 3 | Standards change
119965229 | anchor/guy | Non-HFTD | Transmission | 2020-08-24 | 2021-08-24 | Level 2 | E | 2024-07-29 | 2025-08-24 | Level 3 | GO 165 Inspection
119965297 | other | Non-HFTD | Transmission | 2020-10-27 | 2022-10-27 | Level 3 | F | 2024-10-18 | 2025-10-27 | Level 3 | GO 165 Inspection
119966073 | anchor/guy | Non-HFTD | Transmission | 2020-10-27 | 2021-10-27 | Level 2 | E | 2024-06-05 | 2025-10-27 | Level 3 | GO 165 Inspection
119966352 | anchor/guy | Non-HFTD | Transmission | 2020-10-27 | 2021-10-27 | Level 2 | E | 2024-06-17 | 2025-10-27 | Level 3 | GO 165 Inspection
119966355 | insulator and brushing | Non-HFTD | Transmission | 2020-10-27 | 2021-10-27 | Level 2 | E | 2024-06-17 | 2023-10-27 | Level 2 | GO 165 Inspection
119967374 | other | Non-HFTD | Transmission | 2020-10-23 | 2022-10-23 | Level 3 | F | 2024-08-12 | 2025-10-23 | Level 3 | GO 165 Inspection
119967378 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-03-21 | 2023-10-23 | Level 2 | Standards change
119967392 | other | Non-HFTD | Transmission | 2020-10-26 | 2022-10-26 | Level 3 | F | 2023-12-15 | 2025-10-26 | Level 3 | Standards change
119967397 | anchor/guy | Non-HFTD | Transmission | 2020-10-26 | 2021-10-26 | Level 2 | E | 2024-11-06 | 2025-10-26 | Level 3 | GO 165 Inspection
119967427 | insulator and brushing | Non-HFTD | Transmission | 2020-10-23 | 2021-10-23 | Level 2 | E | 2024-11-30 | 2023-10-23 | Level 2 | Field Safety Reassessment
119967581 | anchor/guy | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-11-10 | 2025-10-28 | Level 3 | GO 165 Inspection
119967960 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-02-05 | 2023-10-30 | Level 2 | Standards change
119970100 | other | Non-HFTD | Transmission | 2020-10-28 | 2022-10-28 | Level 3 | F | 2024-10-15 | 2025-10-28 | Level 3 | GO 165 Inspection
119970826 | insulator and brushing | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-11-27 | 2023-10-28 | Level 2 | GO 165 Inspection
119971273 | pole | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-10-23 | 2021-10-28 | Level 2 | GO 165 Inspection
119972601 | other | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-02-02 | 2025-11-02 | Level 3 | Standards change
119972868 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-04-06 | 2025-11-02 | Level 3 | Standards change
119973229 | pole | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-02-09 | 2021-11-02 | Level 2 | Field Safety Reassessment
119973284 | other | Non-HFTD | Transmission | 2020-10-28 | 2021-10-28 | Level 2 | E | 2024-11-01 | 2021-10-28 | Level 2 | GO 165 Inspection
119973337 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-08-29 | 2023-10-29 | Level 2 | GO 165 Inspection
119973664 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-02-06 | 2023-10-29 | Level 2 | Standards change
119973668 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-12-03 | 2023-10-29 | Level 2 | Field Safety Reassessment
119973687 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-12-08 | 2023-10-29 | Level 2 | Field Safety Reassessment
119973799 | other | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2023-06-09 | 2025-10-29 | Level 3 | Standards change
119973813 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-08-22 | 2025-11-02 | Level 3 | GO 165 Inspection
119973815 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-11-01 | 2023-11-02 | Level 2 | GO 165 Inspection
119973821 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-12-03 | 2023-10-29 | Level 2 | Field Safety Reassessment
119973823 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-12-21 | 2023-10-29 | Level 2 | Field Safety Reassessment
119973853 | pole | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-07-23 | 2025-10-30 | Level 3 | GO 165 Inspection
119973919 | other | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2023-12-18 | 2025-10-29 | Level 3 | Standards change
119973921 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-02-06 | 2023-10-29 | Level 2 | Standards change
119973938 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-01-18 | 2023-10-29 | Level 2 | Standards change
119973959 | insulator and brushing | Non-HFTD | Transmission | 2020-08-28 | 2021-08-28 | Level 2 | E | 2024-08-23 | 2023-08-28 | Level 2 | GO 165 Inspection
119975228 | anchor/guy | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-01-16 | 2025-11-03 | Level 3 | Standards change
119975404 | other | Non-HFTD | Transmission | 2020-10-28 | 2022-10-28 | Level 3 | F | 2024-10-15 | 2025-10-28 | Level 3 | GO 165 Inspection
119975497 | pole | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-12-13 | 2023-11-03 | Level 2 | Field Safety Reassessment
119975869 | pole | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-10-18 | 2025-11-03 | Level 3 | GO 165 Inspection
119976128 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-10-09 | 2023-10-29 | Level 2 | GO 165 Inspection
119976495 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-01-18 | 2023-10-29 | Level 2 | Standards change
119977132 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-08-29 | 2023-10-29 | Level 2 | GO 165 Inspection
119977135 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-08-29 | 2023-10-29 | Level 2 | GO 165 Inspection
119977746 | pole | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-09-26 | 2023-11-03 | Level 2 | GO 165 Inspection
119977797 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-08-27 | 2023-10-30 | Level 2 | GO 165 Inspection
119977915 | other | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2023-12-27 | 2025-10-29 | Level 3 | Standards change
119978256 | pole | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-05-30 | 2023-10-30 | Level 2 | Field Safety Reassessment
119978259 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-09-24 | 2023-10-29 | Level 2 | Field Safety Reassessment
119978498 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-10-16 | 2023-11-02 | Level 2 | GO 165 Inspection
119978580 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2023-12-20 | 2023-11-02 | Level 2 | Standards change
119978636 | insulator and brushing | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-08-19 | 2023-11-03 | Level 2 | GO 165 Inspection
119978726 | insulator and brushing | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-03-20 | 2023-11-03 | Level 2 | Standards change
119978739 | insulator and brushing | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-03-20 | 2023-11-03 | Level 2 | Standards change
119978780 | pole | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2023-01-11 | 2025-11-03 | Level 3 | Standards change
119978793 | other | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-08-16 | 2023-11-03 | Level 2 | GO 165 Inspection
119979718 | switch | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-03-20 | 2023-10-30 | Level 2 | Standards change
119980142 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-04-06 | 2025-11-03 | Level 3 | Standards change
119980423 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-10-08 | 2023-10-29 | Level 2 | GO 165 Inspection
119980727 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-09-10 | 2025-11-03 | Level 3 | GO 165 Inspection
119980775 | other | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2023-05-02 | 2025-11-03 | Level 3 | Standards change
119981258 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-09-10 | 2023-11-02 | Level 2 | GO 165 Inspection
119982093 | insulator and brushing | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-09-10 | 2023-11-03 | Level 2 | GO 165 Inspection
119982671 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-08-20 | 2023-10-30 | Level 2 | GO 165 Inspection
119982673 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-08-20 | 2023-10-30 | Level 2 | GO 165 Inspection
119982746 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-08-29 | 2023-10-30 | Level 2 | GO 165 Inspection
119983366 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-10-25 | 2023-11-02 | Level 2 | GO 165 Inspection
119983447 | pole | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-10-08 | 2023-11-02 | Level 2 | GO 165 Inspection
119983498 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-03-21 | 2023-11-02 | Level 2 | Standards change
119983589 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2023-06-05 | 2025-10-29 | Level 3 | Standards change
119983657 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2023-10-30 | Level 2 | E | 2024-10-08 | 2021-01-30 | Level 2 | GO 165 Inspection
119983676 | other | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2023-06-13 | 2025-11-02 | Level 3 | Standards change
119983678 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-08-16 | 2023-11-02 | Level 2 | Field Safety Reassessment
119983710 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-08-08 | 2023-11-02 | Level 2 | GO 165 Inspection
119983711 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-10-28 | 2023-11-02 | Level 2 | GO 165 Inspection
119983725 | other | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-07-25 | 2023-10-29 | Level 2 | GO 165 Inspection
119983726 | insulator and brushing | Non-HFTD | Transmission | 2020-10-29 | 2021-10-29 | Level 2 | E | 2024-01-18 | 2023-10-29 | Level 2 | Standards change
119983730 | pole | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-03-21 | 2023-11-02 | Level 2 | Standards change
119983747 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-08-29 | 2025-10-30 | Level 3 | GO 165 Inspection
119983751 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-10-08 | 2023-11-02 | Level 2 | GO 165 Inspection
119983753 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-10-08 | 2025-11-02 | Level 3 | GO 165 Inspection
119983757 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2023-02-02 | 2025-11-02 | Level 3 | Standards change
119983759 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-10-08 | 2025-10-30 | Level 3 | GO 165 Inspection
119983786 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-03-21 | 2023-11-02 | Level 2 | Standards change
119983787 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-02-05 | 2023-11-02 | Level 2 | Standards change
119983793 | other | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2024-07-25 | 2025-10-29 | Level 3 | GO 165 Inspection
119983813 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-03-21 | 2023-10-30 | Level 2 | Standards change
119983851 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-10-08 | 2023-11-02 | Level 2 | GO 165 Inspection
119983893 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-08-02 | 2025-10-30 | Level 3 | GO 165 Inspection
119983937 | anchor/guy | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2023-10-12 | 2025-11-02 | Level 3 | Standards change
119983986 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-02-06 | 2023-11-02 | Level 2 | Standards change
119983987 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-02-06 | 2023-11-02 | Level 2 | Standards change
119984000 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-08-27 | 2023-10-30 | Level 2 | GO 165 Inspection
119984012 | insulator and brushing | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-03-21 | 2023-10-30 | Level 2 | Standards change
119984820 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-09-10 | 2025-11-04 | Level 3 | GO 165 Inspection
119985937 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-07-23 | 2025-11-02 | Level 3 | GO 165 Inspection
119986131 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-07-23 | 2023-11-02 | Level 2 | GO 165 Inspection
119986473 | other | Non-HFTD | Transmission | 2020-10-30 | 2021-10-30 | Level 2 | E | 2024-05-20 | 2021-10-30 | Level 2 | Field Safety Reassessment
119987040 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-01-29 | 2023-11-04 | Level 2 | Standards change
119987168 | other | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2023-01-12 | 2023-11-03 | Level 2 | Standards change
119987309 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-01-04 | 2023-11-02 | Level 2 | Standards change
119987617 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-08-13 | 2025-11-02 | Level 3 | GO 165 Inspection
119987755 | pole | Non-HFTD | Transmission | 2020-11-03 | 2023-11-03 | Level 2 | E | 2024-10-22 | 2021-05-03 | Level 2 | GO 165 Inspection
119987991 | pole | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2022-12-13 | 2023-11-04 | Level 2 | Standards change
119987994 | crossarm | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-03-19 | 2023-11-04 | Level 2 | Standards change
119987995 | pole | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2023-03-08 | 2025-11-04 | Level 3 | Standards change
119988042 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-09-17 | 2023-11-04 | Level 2 | GO 165 Inspection
119988133 | pole | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2023-12-26 | 2025-11-03 | Level 3 | Standards change
119988143 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-03-19 | 2023-11-04 | Level 2 | Standards change
119988194 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-10-08 | 2023-11-04 | Level 2 | GO 165 Inspection
119988208 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-03-19 | 2023-11-04 | Level 2 | Standards change
119988225 | anchor/guy | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-10-15 | 2025-11-04 | Level 3 | GO 165 Inspection
119988394 | other | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-08-27 | 2023-11-03 | Level 2 | GO 165 Inspection
119988414 | pole | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-03-19 | 2023-11-04 | Level 2 | Standards change
119988440 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-04-06 | 2025-11-04 | Level 3 | Standards change
119988441 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2023-12-21 | 2025-11-03 | Level 3 | Standards change
119988445 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-01-31 | 2023-11-04 | Level 2 | Standards change
119989327 | insulator and brushing | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-01-31 | 2023-11-03 | Level 2 | Standards change
119990396 | other | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2024-02-14 | 2025-11-06 | Level 3 | Standards change
119991862 | other | Non-HFTD | Transmission | 2020-10-01 | 2022-10-01 | Level 3 | F | 2024-11-07 | 2025-10-01 | Level 3 | GO 165 Inspection
119991950 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-08-31 | 2025-11-04 | Level 3 | GO 165 Inspection
119992026 | anchor/guy | Non-HFTD | Transmission | 2020-11-05 | 2021-11-05 | Level 2 | E | 2024-12-05 | 2025-11-05 | Level 3 | Field Safety Reassessment
119992032 | anchor/guy | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-01-25 | 2025-11-04 | Level 3 | Standards change
119992037 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-10-16 | 2025-11-04 | Level 3 | GO 165 Inspection
119992297 | insulator and brushing | Non-HFTD | Transmission | 2020-11-05 | 2021-11-05 | Level 2 | E | 2024-10-16 | 2023-11-05 | Level 2 | GO 165 Inspection
119992568 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-03-19 | 2023-11-02 | Level 2 | Standards change
119992667 | insulator and brushing | Non-HFTD | Transmission | 2020-10-05 | 2021-10-05 | Level 2 | E | 2024-10-08 | 2023-10-05 | Level 2 | GO 165 Inspection
119992718 | anchor/guy | Non-HFTD | Transmission | 2020-11-04 | 2025-11-04 | Level 2 | E |  | 2025-11-04 | Level 3
119992794 | other | Non-HFTD | Transmission | 2020-11-05 | 2021-11-05 | Level 2 | E | 2024-10-08 | 2023-11-05 | Level 2 | GO 165 Inspection
119993110 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-04-06 | 2025-11-02 | Level 3 | Standards change
119993203 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-03-19 | 2023-11-02 | Level 2 | Standards change
119993266 | other | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2023-05-03 | 2025-11-06 | Level 3 | Standards change
119993299 | anchor/guy | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-01-10 | 2025-11-04 | Level 3 | Standards change
119993379 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-07-15 | 2025-11-05 | Level 3 | GO 165 Inspection
119993424 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-01-22 | 2023-11-04 | Level 2 | Standards change
119993471 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-03-19 | 2023-11-04 | Level 2 | Standards change
119993484 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-02-06 | 2023-11-02 | Level 2 | Standards change
119993534 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-08-22 | 2023-11-04 | Level 2 | GO 165 Inspection
119993775 | pole | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2024-07-08 | 2025-11-06 | Level 3 | GO 165 Inspection
119994152 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2023-12-28 | 2025-11-05 | Level 3 | Standards change
119994464 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-09-27 | 2023-11-04 | Level 2 | GO 165 Inspection
119994561 | other | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2023-05-02 | 2025-11-03 | Level 3 | Standards change
119994659 | insulator and brushing | Non-HFTD | Transmission | 2020-11-05 | 2021-11-05 | Level 2 | E | 2023-10-05 | 2025-11-05 | Level 3 | Standards change
119994939 | other | Non-HFTD | Transmission | 2020-10-05 | 2022-10-05 | Level 3 | F | 2024-10-14 | 2025-10-05 | Level 3 | GO 165 Inspection
119994983 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-04-06 | 2025-11-05 | Level 3 | Standards change
119995013 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-04-06 | 2025-11-04 | Level 3 | Standards change
119995023 | other | Non-HFTD | Transmission | 2020-10-02 | 2022-10-02 | Level 3 | F | 2024-04-06 | 2025-10-02 | Level 3 | Standards change
119995148 | anchor/guy | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-09-09 | 2023-11-06 | Level 2 | GO 165 Inspection
119995624 | other | Non-HFTD | Transmission | 2020-11-07 | 2021-11-07 | Level 2 | E | 2024-09-04 | 2025-11-07 | Level 3 | GO 165 Inspection
119995632 | pole | Non-HFTD | Transmission | 2020-10-02 | 2022-10-02 | Level 3 | F | 2024-02-14 | 2025-10-02 | Level 3 | Standards change
119995841 | other | Non-HFTD | Transmission | 2020-10-06 | 2022-10-06 | Level 3 | F | 2023-08-10 | 2025-10-06 | Level 3 | Standards change
119996963 | pole | Non-HFTD | Transmission | 2020-11-08 | 2021-11-08 | Level 2 | E | 2024-12-30 | 2023-11-08 | Level 2 | Field Safety Reassessment
119997500 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-04-06 | 2025-11-03 | Level 3 | Standards change
119997504 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-02-28 | 2025-11-04 | Level 3 | Standards change
119997764 | other | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-01-29 | 2025-11-06 | Level 3 | Standards change
119998023 | insulator and brushing | Non-HFTD | Transmission | 2020-11-05 | 2021-11-05 | Level 2 | E | 2024-03-18 | 2023-11-05 | Level 2 | Standards change
119998591 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-12-08 | 2023-11-04 | Level 2 | Field Safety Reassessment
119998822 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-08-13 | 2023-11-04 | Level 2 | GO 165 Inspection
119999378 | anchor/guy | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-09-05 | 2025-11-04 | Level 3 | GO 165 Inspection
119999550 | insulator and brushing | Non-HFTD | Transmission | 2020-11-04 | 2021-11-04 | Level 2 | E | 2024-10-22 | 2023-11-04 | Level 2 | GO 165 Inspection
120000806 | other | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-10-22 | 2021-11-06 | Level 2 | GO 165 Inspection
120000808 | insulator and brushing | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-10-22 | 2023-11-06 | Level 2 | GO 165 Inspection
120001739 | insulator and brushing | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-10-16 | 2023-11-06 | Level 2 | Field Safety Reassessment
120001801 | insulator and brushing | Non-HFTD | Transmission | 2020-11-03 | 2021-11-03 | Level 2 | E | 2024-08-29 | 2023-11-03 | Level 2 | GO 165 Inspection
120008750 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-12-21 | 2023-11-09 | Level 2 | Field Safety Reassessment
120008845 | other | Non-HFTD | Transmission | 2020-10-15 | 2022-10-15 | Level 3 | F | 2024-04-06 | 2025-10-15 | Level 3 | Standards change
120008849 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2023-12-01 | 2025-11-03 | Level 3 | Standards change
120009642 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-10-08 | 2023-11-09 | Level 2 | GO 165 Inspection
120009649 | other | Non-HFTD | Transmission | 2020-11-09 | 2022-11-09 | Level 3 | F | 2024-10-08 | 2025-11-09 | Level 3 | GO 165 Inspection
120009955 | insulator and brushing | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-12-06 | 2023-11-10 | Level 2 | Field Safety Reassessment
120010100 | insulator and brushing | Non-HFTD | Transmission | 2020-11-02 | 2021-11-02 | Level 2 | E | 2024-11-01 | 2023-11-02 | Level 2 | GO 165 Inspection
120010673 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-08-22 | 2023-11-09 | Level 2 | Field Safety Reassessment
120010701 | anchor/guy | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-01-19 | 2025-11-09 | Level 3 | Standards change
120010750 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2023-10-06 | 2023-11-09 | Level 2 | Standards change
120010857 | pole | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-12-20 | 2023-11-06 | Level 2 | Field Safety Reassessment
120010885 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-09-18 | 2023-11-09 | Level 2 | GO 165 Inspection
120010916 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-10-23 | 2023-11-09 | Level 2 | GO 165 Inspection
120011036 | insulator and brushing | Non-HFTD | Transmission | 2020-11-06 | 2021-11-06 | Level 2 | E | 2024-08-23 | 2023-11-06 | Level 2 | GO 165 Inspection
120012145 | other | Non-HFTD | Transmission | 2020-11-11 | 2022-11-11 | Level 3 | F | 2024-08-28 | 2025-11-11 | Level 3 | GO 165 Inspection
120012241 | other | Non-HFTD | Transmission | 2020-11-11 | 2022-11-11 | Level 3 | F | 2024-09-27 | 2025-11-11 | Level 3 | GO 165 Inspection
120013261 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-09-17 | 2023-11-09 | Level 2 | GO 165 Inspection
120013826 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-04-06 | 2025-11-10 | Level 3 | Standards change
120014866 | insulator and brushing | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-07-30 | 2023-11-10 | Level 2 | GO 165 Inspection
120014900 | insulator and brushing | Non-HFTD | Transmission | 2020-11-09 | 2021-11-09 | Level 2 | E | 2024-03-19 | 2023-11-09 | Level 2 | Standards change
120015014 | crossarm | Non-HFTD | Transmission | 2020-11-12 | 2021-11-12 | Level 2 | E | 2024-01-10 | 2023-11-12 | Level 2 | Field Safety Reassessment
120015321 | anchor/guy | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2023-01-19 | 2025-11-10 | Level 3 | Standards change
120015323 | anchor/guy | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-02-01 | 2025-11-10 | Level 3 | GO 165 Inspection
120015913 | pole | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-12-08 | 2023-11-10 | Level 2 | Field Safety Reassessment
120016188 | pole | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-12-26 | 2023-11-10 | Level 2 | Field Safety Reassessment
120016500 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-01-05 | 2025-11-10 | Level 3 | Standards change
120016701 | pole | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-03-28 | 2025-11-10 | Level 3 | GO 165 Inspection
120016761 | other | Non-HFTD | Transmission | 2020-11-12 | 2021-11-12 | Level 2 | E | 2024-08-14 | 2021-11-12 | Level 2 | GO 165 Inspection
120016899 | insulator and brushing | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-03-19 | 2023-11-10 | Level 2 | Standards change
120018067 | insulator and brushing | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-12-07 | 2025-11-10 | Level 3 | Field Safety Reassessment
120018268 | other | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-05-30 | 2025-11-10 | Level 3 | Field Safety Reassessment
120018708 | insulator and brushing | Non-HFTD | Transmission | 2020-11-10 | 2021-11-10 | Level 2 | E | 2024-08-31 | 2023-11-10 | Level 2 | GO 165 Inspection
120019729 | insulator and brushing | Non-HFTD | Transmission | 2020-11-12 | 2021-11-12 | Level 2 | E | 2024-10-11 | 2023-11-12 | Level 2 | GO 165 Inspection
120027607 | other | Non-HFTD | Transmission | 2020-11-12 | 2022-11-12 | Level 3 | F | 2022-12-13 | 2025-11-12 | Level 3 | Standards change
120031447 | pole | Non-HFTD | Transmission | 2020-11-12 | 2022-11-12 | Level 3 | F | 2024-10-10 | 2025-11-12 | Level 3 | GO 165 Inspection
120042708 | pole | Non-HFTD | Transmission | 2020-11-13 | 2021-11-13 | Level 2 | E | 2024-09-24 | 2023-11-13 | Level 2 | GO 165 Inspection
120042869 | anchor/guy | Non-HFTD | Transmission | 2020-11-12 | 2023-11-12 | Level 2 | E | 2024-10-10 | 2021-11-12 | Level 2 | GO 165 Inspection
120044599 | insulator and brushing | Non-HFTD | Transmission | 2020-11-13 | 2021-11-13 | Level 2 | E | 2024-02-16 | 2023-11-13 | Level 2 | Standards change
120047621 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-10-09 | 2025-11-16 | Level 3 | GO 165 Inspection
120047823 | pole | Non-HFTD | Transmission | 2020-11-16 | 2021-11-16 | Level 2 | E | 2024-12-18 | 2023-11-16 | Level 2 | Field Safety Reassessment
120047856 | other | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-10-28 | 2021-11-17 | Level 2 | GO 165 Inspection
120048055 | pole | Non-HFTD | Transmission | 2020-11-13 | 2021-11-13 | Level 2 | E | 2024-04-25 | 2023-11-13 | Level 2 | GO 165 Inspection
120048272 | other | Non-HFTD | Transmission | 2020-11-17 | 2022-11-17 | Level 3 | F | 2024-11-14 | 2025-11-17 | Level 3 | GO 165 Inspection
120061466 | insulator and brushing | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-12-31 | 2023-11-17 | Level 2 | Field Safety Reassessment
120071164 | other | Non-HFTD | Transmission | 2020-11-12 | 2021-05-12 | Level 2 | E | 2024-10-10 | 2021-05-12 | Level 2 | GO 165 Inspection
120071652 | other | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-11-01 | 2023-11-18 | Level 2 | GO 165 Inspection
120071653 | other | Non-HFTD | Transmission | 2020-11-18 | 2023-11-18 | Level 2 | E | 2024-10-28 | 2021-05-18 | Level 2 | GO 165 Inspection
120072301 | insulator and brushing | Non-HFTD | Transmission | 2020-11-16 | 2021-11-16 | Level 2 | E | 2024-10-23 | 2023-11-16 | Level 2 | GO 165 Inspection
120073661 | anchor/guy | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-10-31 | 2025-11-18 | Level 3 | GO 165 Inspection
120074611 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-03-08 | 2025-11-16 | Level 3 | GO 165 Inspection
120079077 | other | Non-HFTD | Transmission | 2020-11-18 | 2021-11-16 | Level 2 | E | 2024-10-10 | 2021-11-16 | Level 2 | GO 165 Inspection
120079239 | other | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-10-11 | 2025-11-17 | Level 3 | GO 165 Inspection
120079640 | anchor/guy | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-08-15 | 2023-11-17 | Level 2 | GO 165 Inspection
120081175 | insulator and brushing | Non-HFTD | Transmission | 2020-11-16 | 2021-11-16 | Level 2 | E | 2024-10-23 | 2023-11-16 | Level 2 | GO 165 Inspection
120081176 | insulator and brushing | Non-HFTD | Transmission | 2020-11-16 | 2021-11-16 | Level 2 | E | 2024-10-23 | 2023-11-16 | Level 2 | GO 165 Inspection
120081190 | anchor/guy | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-11-19 | 2025-11-17 | Level 3 | GO 165 Inspection
120081191 | insulator and brushing | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-11-19 | 2023-11-17 | Level 2 | GO 165 Inspection
120081702 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-06-21 | 2023-11-20 | Level 2 | GO 165 Inspection
120082507 | other | Non-HFTD | Transmission | 2020-11-20 | 2022-11-20 | Level 3 | F | 2024-04-06 | 2025-11-20 | Level 3 | Standards change
120085370 | insulator and brushing | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2024-10-29 | 2023-11-17 | Level 2 | GO 165 Inspection
120086263 | pole | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-12-30 | 2023-11-23 | Level 2 | Field Safety Reassessment
120087027 | pole | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-12-31 | 2021-11-23 | Level 2 | Field Safety Reassessment
120087102 | insulator and brushing | Non-HFTD | Transmission | 2020-11-17 | 2023-11-17 | Level 2 | E | 2024-10-23 | 2021-11-17 | Level 2 | GO 165 Inspection
120087792 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-10-17 | 2023-11-18 | Level 2 | GO 165 Inspection
120087794 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-10-17 | 2023-11-18 | Level 2 | GO 165 Inspection
120088003 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-10-24 | 2023-11-18 | Level 2 | GO 165 Inspection
120088776 | pole | HFTD Tier 2 | Transmission | 2020-11-17 | 2022-11-17 | Level 3 | F | 2024-03-22 | 2025-11-17 | Level 3 | GO 165 Inspection
120089535 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-08-14 | 2023-11-18 | Level 2 | GO 165 Inspection
120089664 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-09-17 | 2023-11-18 | Level 2 | GO 165 Inspection
120089860 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-09-16 | 2023-11-18 | Level 2 | GO 165 Inspection
120090438 | pole | Non-HFTD | Transmission | 2020-11-24 | 2022-11-24 | Level 3 | F | 2024-10-31 | 2025-11-24 | Level 3 | GO 165 Inspection
120094476 | other | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-12-30 | 2021-11-23 | Level 2 | Field Safety Reassessment
120094671 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-03-18 | 2023-11-18 | Level 2 | Standards change
120094820 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-09-17 | 2023-11-19 | Level 2 | Field Safety Reassessment
120094826 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-10-31 | 2023-11-19 | Level 2 | GO 165 Inspection
120094929 | insulator and brushing | Non-HFTD | Transmission | 2020-11-18 | 2021-11-18 | Level 2 | E | 2024-07-16 | 2023-11-18 | Level 2 | GO 165 Inspection
120095946 | other | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2023-08-24 | 2025-11-23 | Level 3 | Standards change
120097096 | insulator and brushing | Non-HFTD | Transmission | 2020-11-16 | 2021-11-16 | Level 2 | E | 2024-08-16 | 2023-11-16 | Level 2 | GO 165 Inspection
120097099 | anchor/guy | Non-HFTD | Transmission | 2020-11-16 | 2025-11-16 | Level 2 | E | 2024-08-16 | 2021-05-16 | Level 2 | GO 165 Inspection
120097119 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-02-06 | 2023-11-19 | Level 2 | Standards change
120097240 | pole | HFTD Tier 2 | Transmission | 2020-11-18 | 2022-11-18 | Level 3 | F | 2024-03-22 | 2025-11-18 | Level 3 | GO 165 Inspection
120097500 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-09-17 | 2025-11-19 | Level 3 | GO 165 Inspection
120097589 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-10-16 | 2023-11-19 | Level 2 | GO 165 Inspection
120097714 | other | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-08-21 | 2023-11-19 | Level 2 | GO 165 Inspection
120097719 | pole | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2024-07-23 | 2025-11-19 | Level 3 | GO 165 Inspection
120097801 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-10-15 | 2023-11-19 | Level 2 | GO 165 Inspection
120098269 | anchor/guy | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2023-05-05 | 2023-11-19 | Level 2 | Standards change
120098476 | pole | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-01-16 | 2025-11-16 | Level 3 | Standards change
120107190 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-10-16 | 2023-11-24 | Level 2 | GO 165 Inspection
120107481 | pole | Non-HFTD | Transmission | 2020-11-25 | 2022-11-25 | Level 3 | F | 2024-09-17 | 2025-11-25 | Level 3 | GO 165 Inspection
120107710 | other | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2024-11-12 | 2025-11-19 | Level 3 | GO 165 Inspection
120109730 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-09-12 | 2023-11-20 | Level 2 | GO 165 Inspection
120110261 | pole | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-06-03 | 2023-11-19 | Level 2 | Field Safety Reassessment
120110262 | other | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2023-12-20 | 2025-11-19 | Level 3 | Standards change
120110268 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-09-12 | 2023-11-20 | Level 2 | GO 165 Inspection
120110440 | other | Non-HFTD | Transmission | 2020-11-20 | 2022-11-20 | Level 3 | F | 2024-10-10 | 2025-11-20 | Level 3 | GO 165 Inspection
120110441 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-10-10 | 2023-11-20 | Level 2 | GO 165 Inspection
120110455 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2023-08-31 | 2023-11-20 | Level 2 | Standards change
120110514 | insulator and brushing | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-10-10 | 2023-11-19 | Level 2 | GO 165 Inspection
120110650 | anchor/guy | Non-HFTD | Transmission | 2020-11-17 | 2021-11-17 | Level 2 | E | 2023-07-19 | 2025-11-17 | Level 3 | Standards change
120110997 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2023-01-20 | 2023-11-20 | Level 2 | Standards change
120111004 | pole | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2023-11-06 | 2025-11-23 | Level 3 | Standards change
120111063 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-10-08 | 2023-11-20 | Level 2 | GO 165 Inspection
120111126 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-09-18 | 2023-11-20 | Level 2 | GO 165 Inspection
120111129 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-09-18 | 2023-11-20 | Level 2 | GO 165 Inspection
120111360 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-10-10 | 2023-11-20 | Level 2 | GO 165 Inspection
120111380 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-10-10 | 2023-11-20 | Level 2 | GO 165 Inspection
120111685 | other | Non-HFTD | Transmission | 2020-12-01 | 2022-12-01 | Level 3 | F | 2024-04-06 | 2025-12-01 | Level 3 | Standards change
120112295 | other | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2023-02-08 | 2023-11-23 | Level 2 | Standards change
120112466 | pole | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2024-10-23 | 2025-11-23 | Level 3 | GO 165 Inspection
120112572 | insulator and brushing | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-10-11 | 2023-11-23 | Level 2 | GO 165 Inspection
120112800 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2023-11-20 | Level 2 | E | 2024-10-16 | 2021-02-20 | Level 2 | GO 165 Inspection
120113563 | insulator and brushing | Non-HFTD | Transmission | 2020-11-20 | 2021-11-20 | Level 2 | E | 2024-10-16 | 2023-11-20 | Level 2 | GO 165 Inspection
120114288 | other | Non-HFTD | Transmission | 2020-11-19 | 2021-11-19 | Level 2 | E | 2024-03-18 | 2021-11-19 | Level 2 | Standards change
120114445 | pole | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2023-11-07 | 2025-11-23 | Level 3 | Standards change
120114694 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-10-17 | 2023-11-24 | Level 2 | GO 165 Inspection
120114695 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-10-17 | 2023-11-24 | Level 2 | GO 165 Inspection
120114699 | insulator and brushing | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-01-29 | 2023-11-23 | Level 2 | Standards change
120114913 | insulator and brushing | Non-HFTD | Transmission | 2020-11-23 | 2023-11-23 | Level 2 | E | 2024-10-23 | 2021-11-23 | Level 2 | GO 165 Inspection
120114918 | insulator and brushing | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-10-30 | 2023-11-23 | Level 2 | GO 165 Inspection
120114941 | insulator and brushing | Non-HFTD | Transmission | 2020-11-25 | 2021-11-25 | Level 2 | E | 2024-10-18 | 2023-11-25 | Level 2 | GO 165 Inspection
120114942 | insulator and brushing | Non-HFTD | Transmission | 2020-11-25 | 2021-11-25 | Level 2 | E | 2024-07-29 | 2023-11-25 | Level 2 | GO 165 Inspection
120114951 | other | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2024-11-04 | 2025-11-19 | Level 3 | GO 165 Inspection
120114954 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-09-18 | 2023-11-24 | Level 2 | GO 165 Inspection
120115007 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-10-18 | 2023-11-24 | Level 2 | GO 165 Inspection
120115014 | insulator and brushing | Non-HFTD | Transmission | 2020-11-25 | 2021-11-25 | Level 2 | E | 2024-01-18 | 2023-11-25 | Level 2 | Standards change
120115016 | other | Non-HFTD | Transmission | 2020-11-25 | 2022-11-25 | Level 3 | F | 2024-02-02 | 2025-11-25 | Level 3 | Standards change
120115042 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-10-17 | 2023-11-24 | Level 2 | GO 165 Inspection
120115070 | anchor/guy | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2023-08-01 | 2025-11-23 | Level 3 | Standards change
120117180 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-11-15 | 2023-12-01 | Level 2 | Field Safety Reassessment
120117939 | other | Non-HFTD | Transmission | 2020-11-25 | 2022-11-25 | Level 3 | F | 2024-04-06 | 2025-11-25 | Level 3 | Standards change
120118344 | other | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2024-04-06 | 2025-11-23 | Level 3 | Standards change
120119159 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-11-08 | 2023-11-24 | Level 2 | GO 165 Inspection
120119161 | anchor/guy | Non-HFTD | Transmission | 2020-11-25 | 2021-11-25 | Level 2 | E | 2023-12-29 | 2025-11-25 | Level 3 | Standards change
120119332 | pole | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-10-21 | 2023-12-01 | Level 2 | GO 165 Inspection
120119346 | pole | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-12-09 | 2021-12-01 | Level 2 | Field Safety Reassessment
120119406 | pole | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-12-27 | 2023-12-01 | Level 2 | Field Safety Reassessment
120119490 | crossarm | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-01-25 | 2023-12-01 | Level 2 | Standards change
120119491 | pole | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-12-23 | 2023-12-01 | Level 2 | Field Safety Reassessment
120119557 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-12-24 | 2023-11-24 | Level 2 | Field Safety Reassessment
120119977 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-09-10 | 2023-11-24 | Level 2 | GO 165 Inspection
120120020 | pole | Non-HFTD | Transmission | 2020-11-25 | 2022-11-25 | Level 3 | F | 2023-12-05 | 2025-11-25 | Level 3 | Standards change
120120028 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-10-31 | 2023-11-24 | Level 2 | GO 165 Inspection
120120137 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2023-11-24 | Level 2 | E | 2024-09-17 | 2021-11-24 | Level 2 | GO 165 Inspection
120120544 | pole | Non-HFTD | Transmission | 2020-11-30 | 2022-11-30 | Level 3 | F | 2024-10-16 | 2025-11-30 | Level 3 | GO 165 Inspection
120120584 | other | Non-HFTD | Transmission | 2020-11-25 | 2021-11-25 | Level 2 | E | 2024-10-29 | 2023-11-25 | Level 2 | GO 165 Inspection
120120709 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-09-27 | 2023-12-01 | Level 2 | GO 165 Inspection
120120780 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2021-11-24 | Level 2 | E | 2024-08-15 | 2023-11-24 | Level 2 | GO 165 Inspection
120120797 | pole | Non-HFTD | Transmission | 2020-11-25 | 2022-11-25 | Level 3 | F | 2024-09-18 | 2025-11-25 | Level 3 | GO 165 Inspection
120120918 | insulator and brushing | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-10-16 | 2023-11-30 | Level 2 | GO 165 Inspection
120120965 | pole | Non-HFTD | Transmission | 2020-12-01 | 2022-12-01 | Level 3 | F | 2024-08-08 | 2025-12-01 | Level 3 | GO 165 Inspection
120120984 | insulator and brushing | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-10-11 | 2023-11-30 | Level 2 | GO 165 Inspection
120120985 | insulator and brushing | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-10-16 | 2023-11-30 | Level 2 | GO 165 Inspection
120121013 | anchor/guy | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2023-12-26 | 2025-12-01 | Level 3 | Standards change
120121033 | insulator and brushing | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-10-16 | 2023-11-30 | Level 2 | GO 165 Inspection
120121047 | insulator and brushing | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2023-12-05 | 2023-11-30 | Level 2 | Standards change
120121051 | insulator and brushing | Non-HFTD | Transmission | 2020-11-25 | 2021-11-25 | Level 2 | E | 2024-10-09 | 2023-11-25 | Level 2 | GO 165 Inspection
120122047 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-03-15 | 2023-12-01 | Level 2 | Standards change
120122406 | other | Non-HFTD | Transmission | 2020-12-02 | 2021-12-02 | Level 2 | E | 2024-09-26 | 2023-12-02 | Level 2 | GO 165 Inspection
120125239 | insulator and brushing | Non-HFTD | Transmission | 2020-11-24 | 2023-11-24 | Level 2 | E | 2024-10-17 | 2021-02-24 | Level 2 | GO 165 Inspection
120125696 | insulator and brushing | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-01-18 | 2023-11-30 | Level 2 | Standards change
120125975 | other | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-10-16 | 2023-11-30 | Level 2 | GO 165 Inspection
120126187 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-08-08 | 2025-10-08 | Level 3 | GO 165 Inspection
120126240 | insulator and brushing | Non-HFTD | Transmission | 2020-12-02 | 2021-12-02 | Level 2 | E | 2024-10-10 | 2023-12-02 | Level 2 | GO 165 Inspection
120126247 | insulator and brushing | Non-HFTD | Transmission | 2020-12-02 | 2021-12-02 | Level 2 | E | 2024-12-06 | 2023-12-02 | Level 2 | Field Safety Reassessment
120126341 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-08-12 | 2025-10-08 | Level 3 | GO 165 Inspection
120126343 | other | Non-HFTD | Transmission | 2020-10-07 | 2022-10-07 | Level 3 | F | 2024-08-06 | 2025-10-07 | Level 3 | GO 165 Inspection
120126427 | other | Non-HFTD | Transmission | 2020-12-01 | 2022-12-01 | Level 3 | F | 2024-08-20 | 2025-12-01 | Level 3 | GO 165 Inspection
120126561 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-08-09 | 2023-12-01 | Level 2 | GO 165 Inspection
120126576 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-04-06 | 2025-10-08 | Level 3 | Standards change
120126588 | other | Non-HFTD | Transmission | 2020-10-08 | 2022-10-08 | Level 3 | F | 2024-08-06 | 2025-10-08 | Level 3 | GO 165 Inspection
120126622 | other | Non-HFTD | Transmission | 2020-10-12 | 2022-10-12 | Level 3 | F | 2024-09-12 | 2025-10-12 | Level 3 | GO 165 Inspection
120126693 | other | Non-HFTD | Transmission | 2020-10-07 | 2022-10-07 | Level 3 | F | 2024-04-06 | 2025-10-07 | Level 3 | Standards change
120126765 | other | Non-HFTD | Transmission | 2020-11-13 | 2022-11-13 | Level 3 | F | 2024-02-15 | 2025-11-13 | Level 3 | Standards change
120126797 | other | HFTD Tier 2 | Transmission | 2020-10-07 | 2022-10-07 | Level 3 | F | 2024-05-03 | 2025-10-07 | Level 3 | GO 165 Inspection
120126820 | other | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2024-09-18 | 2025-12-02 | Level 3 | GO 165 Inspection
120127984 | other | Non-HFTD | Transmission | 2020-10-13 | 2022-10-13 | Level 3 | F | 2024-01-02 | 2025-10-13 | Level 3 | Standards change
120128162 | other | Non-HFTD | Transmission | 2020-10-12 | 2022-10-12 | Level 3 | F | 2024-04-06 | 2025-10-12 | Level 3 | Standards change
120128165 | other | Non-HFTD | Transmission | 2020-10-12 | 2022-10-12 | Level 3 | F | 2024-04-06 | 2025-10-12 | Level 3 | Standards change
120128473 | other | Non-HFTD | Transmission | 2020-10-19 | 2022-10-19 | Level 3 | F | 2024-09-25 | 2025-10-19 | Level 3 | GO 165 Inspection
120128732 | other | Non-HFTD | Transmission | 2020-10-13 | 2022-10-13 | Level 3 | F | 2024-04-06 | 2025-10-13 | Level 3 | Standards change
120128861 | pole | Non-HFTD | Transmission | 2020-10-15 | 2022-10-15 | Level 3 | F | 2024-11-04 | 2025-10-15 | Level 3 | GO 165 Inspection
120128881 | other | Non-HFTD | Transmission | 2020-10-13 | 2022-10-13 | Level 3 | F | 2024-04-06 | 2025-10-13 | Level 3 | Standards change
120128887 | other | Non-HFTD | Transmission | 2020-10-13 | 2022-10-13 | Level 3 | F | 2024-10-24 | 2025-10-13 | Level 3 | GO 165 Inspection
120129279 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-08-21 | 2023-12-01 | Level 2 | GO 165 Inspection
120129444 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-08-21 | 2023-12-01 | Level 2 | GO 165 Inspection
120129632 | other | Non-HFTD | Transmission | 2020-10-13 | 2022-10-13 | Level 3 | F | 2024-04-06 | 2025-10-13 | Level 3 | Standards change
120129765 | other | Non-HFTD | Transmission | 2020-10-22 | 2022-10-22 | Level 3 | F | 2024-05-14 | 2025-10-22 | Level 3 | GO 165 Inspection
120129772 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-08-20 | 2023-12-01 | Level 2 | GO 165 Inspection
120129773 | insulator and brushing | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-08-20 | 2023-12-01 | Level 2 | GO 165 Inspection
120129885 | other | Non-HFTD | Transmission | 2020-10-20 | 2022-10-20 | Level 3 | F | 2023-12-27 | 2025-10-20 | Level 3 | Standards change
120129978 | other | Non-HFTD | Transmission | 2020-10-20 | 2022-10-20 | Level 3 | F | 2023-12-06 | 2025-10-20 | Level 3 | Standards change
120130084 | other | Non-HFTD | Transmission | 2020-10-20 | 2022-10-20 | Level 3 | F | 2024-04-06 | 2025-10-20 | Level 3 | Standards change
120130932 | insulator and brushing | Non-HFTD | Transmission | 2020-12-03 | 2021-12-03 | Level 2 | E | 2024-10-08 | 2023-12-03 | Level 2 | GO 165 Inspection
120131118 | other | Non-HFTD | Transmission | 2020-12-01 | 2022-12-01 | Level 3 | F | 2024-04-06 | 2025-12-01 | Level 3 | Standards change
120131314 | anchor/guy | Non-HFTD | Transmission | 2020-12-03 | 2021-12-03 | Level 2 | E | 2023-10-13 | 2025-12-03 | Level 3 | Standards change
120131484 | insulator and brushing | Non-HFTD | Transmission | 2020-12-03 | 2021-12-03 | Level 2 | E | 2024-03-15 | 2023-12-03 | Level 2 | Standards change
120131884 | pole | Non-HFTD | Transmission | 2020-12-04 | 2021-12-04 | Level 2 | E | 2023-08-24 | 2025-12-04 | Level 3 | Standards change
120132336 | pole | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2024-10-11 | 2025-12-02 | Level 3 | GO 165 Inspection
120132339 | other | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2024-10-16 | 2025-12-02 | Level 3 | GO 165 Inspection
120133292 | other | Non-HFTD | Transmission | 2020-10-27 | 2022-10-27 | Level 3 | F | 2023-12-20 | 2025-10-27 | Level 3 | Standards change
120133327 | other | Non-HFTD | Transmission | 2020-10-27 | 2022-10-27 | Level 3 | F | 2024-10-18 | 2025-10-27 | Level 3 | GO 165 Inspection
120133399 | insulator and brushing | Non-HFTD | Transmission | 2020-12-02 | 2021-12-02 | Level 2 | E | 2023-07-11 | 2023-12-02 | Level 2 | Standards change
120133405 | other | Non-HFTD | Transmission | 2020-10-23 | 2022-10-23 | Level 3 | F | 2024-04-06 | 2025-10-23 | Level 3 | Standards change
120133475 | other | Non-HFTD | Transmission | 2020-10-27 | 2022-10-27 | Level 3 | F | 2024-04-06 | 2025-10-27 | Level 3 | Standards change
120133672 | other | Non-HFTD | Transmission | 2020-10-19 | 2022-10-19 | Level 3 | F | 2024-04-06 | 2025-10-19 | Level 3 | Standards change
120133679 | other | Non-HFTD | Transmission | 2020-10-19 | 2022-10-19 | Level 3 | F | 2024-04-06 | 2025-10-19 | Level 3 | Standards change
120133735 | insulator and brushing | Non-HFTD | Transmission | 2020-12-03 | 2021-12-03 | Level 2 | E | 2024-08-08 | 2023-12-03 | Level 2 | GO 165 Inspection
120133798 | other | Non-HFTD | Transmission | 2020-10-19 | 2022-10-19 | Level 3 | F | 2024-01-03 | 2025-10-19 | Level 3 | Standards change
120133815 | other | Non-HFTD | Transmission | 2020-10-23 | 2022-10-23 | Level 3 | F | 2024-02-29 | 2025-10-23 | Level 3 | Standards change
120133897 | anchor/guy | Non-HFTD | Transmission | 2020-12-02 | 2021-12-02 | Level 2 | E | 2023-12-26 | 2025-12-02 | Level 3 | Standards change
120133905 | other | Non-HFTD | Transmission | 2020-10-16 | 2022-10-16 | Level 3 | F | 2023-12-15 | 2025-10-16 | Level 3 | Standards change
120133923 | other | Non-HFTD | Transmission | 2020-10-21 | 2022-10-21 | Level 3 | F | 2024-04-06 | 2025-10-21 | Level 3 | Standards change
120133969 | insulator and brushing | Non-HFTD | Transmission | 2020-12-04 | 2021-12-04 | Level 2 | E | 2024-10-30 | 2023-12-04 | Level 2 | GO 165 Inspection
120134120 | other | Non-HFTD | Transmission | 2020-10-21 | 2022-10-21 | Level 3 | F | 2024-02-28 | 2025-10-21 | Level 3 | Standards change
120134146 | other | Non-HFTD | Transmission | 2020-10-16 | 2022-10-16 | Level 3 | F | 2024-01-09 | 2025-10-16 | Level 3 | Standards change
120134209 | insulator and brushing | Non-HFTD | Transmission | 2020-12-04 | 2021-12-04 | Level 2 | E | 2024-08-29 | 2023-12-04 | Level 2 | GO 165 Inspection
120134260 | insulator and brushing | Non-HFTD | Transmission | 2020-12-04 | 2021-12-04 | Level 2 | E | 2024-08-29 | 2023-12-04 | Level 2 | GO 165 Inspection
120134282 | other | HFTD Tier 2 | Transmission | 2020-10-16 | 2022-10-16 | Level 3 | F | 2023-05-12 | 2025-10-16 | Level 3 | Standards change
120134316 | insulator and brushing | Non-HFTD | Transmission | 2020-12-04 | 2023-12-04 | Level 2 | E | 2024-07-31 | 2021-12-04 | Level 2 | GO 165 Inspection
120135337 | pole | Non-HFTD | Transmission | 2020-12-05 | 2022-12-05 | Level 3 | F | 2023-12-26 | 2025-12-05 | Level 3 | Standards change
120135562 | insulator and brushing | Non-HFTD | Transmission | 2020-12-02 | 2021-12-02 | Level 2 | E | 2024-08-08 | 2023-12-02 | Level 2 | GO 165 Inspection
120135773 | other | Non-HFTD | Transmission | 2020-12-04 | 2022-12-04 | Level 3 | F | 2024-04-06 | 2025-12-04 | Level 3 | Standards change
120135781 | insulator and brushing | Non-HFTD | Transmission | 2020-12-04 | 2021-12-04 | Level 2 | E | 2024-09-30 | 2023-12-04 | Level 2 | GO 165 Inspection
120136460 | anchor/guy | Non-HFTD | Transmission | 2020-12-04 | 2021-12-04 | Level 2 | E | 2023-10-31 | 2025-12-04 | Level 3 | Standards change
120136939 | pole | Non-HFTD | Transmission | 2020-12-07 | 2022-12-07 | Level 3 | F | 2023-12-26 | 2025-12-07 | Level 3 | Standards change
120137625 | pole | Non-HFTD | Transmission | 2020-10-26 | 2022-10-26 | Level 3 | F | 2023-12-26 | 2025-10-26 | Level 3 | Standards change
120138534 | pole | HFTD Tier 2 | Transmission | 2020-12-07 | 2022-12-07 | Level 3 | F | 2023-06-14 | 2025-12-07 | Level 3 | GO 165 Inspection
120139204 | other | HFTD Tier 2 | Transmission | 2020-08-31 | 2022-08-31 | Level 3 | F | 2024-05-21 | 2025-08-31 | Level 3 | GO 165 Inspection
120139260 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-08-14 | 2025-10-30 | Level 3 | GO 165 Inspection
120139397 | pole | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2024-09-28 | 2025-10-29 | Level 3 | GO 165 Inspection
120139421 | other | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2023-11-30 | 2025-10-29 | Level 3 | Standards change
120139452 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-01-22 | 2025-10-30 | Level 3 | Standards change
120139458 | pole | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2024-10-30 | 2025-10-29 | Level 3 | GO 165 Inspection
120139459 | other | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2024-04-06 | 2025-10-29 | Level 3 | Standards change
120139470 | other | Non-HFTD | Transmission | 2020-10-29 | 2022-10-29 | Level 3 | F | 2024-04-06 | 2025-10-29 | Level 3 | Standards change
120139491 | pole | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2023-11-30 | 2025-10-30 | Level 3 | Standards change
120139588 | other | Non-HFTD | Transmission | 2020-10-26 | 2022-10-26 | Level 3 | F | 2023-04-05 | 2025-10-26 | Level 3 | Standards change
120139879 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2023-12-21 | 2025-11-03 | Level 3 | Standards change
120140334 | pole | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2023-12-26 | 2025-11-02 | Level 3 | Standards change
120141059 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2023-12-13 | 2025-11-02 | Level 3 | Standards change
120142288 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-04-06 | 2025-11-02 | Level 3 | Standards change
120143966 | insulator and brushing | Non-HFTD | Transmission | 2020-12-07 | 2021-12-07 | Level 2 | E | 2024-01-23 | 2023-12-07 | Level 2 | Standards change
120144248 | other | Non-HFTD | Transmission | 2020-12-07 | 2021-12-07 | Level 2 | E | 2023-03-24 | 2025-12-07 | Level 3 | Standards change
120144443 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-01-02 | 2025-11-03 | Level 3 | Standards change
120144445 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-10-30 | 2025-10-30 | Level 3 | GO 165 Inspection
120144447 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-01-04 | 2025-10-30 | Level 3 | Standards change
120145161 | insulator and brushing | Non-HFTD | Transmission | 2020-12-07 | 2021-12-07 | Level 2 | E | 2024-10-25 | 2023-12-07 | Level 2 | GO 165 Inspection
120145168 | pole | Non-HFTD | Transmission | 2020-12-07 | 2021-12-07 | Level 2 | E | 2024-10-25 | 2023-12-07 | Level 2 | GO 165 Inspection
120145276 | other | Non-HFTD | Transmission | 2020-12-09 | 2022-12-09 | Level 3 | F | 2023-12-08 | 2025-12-09 | Level 3 | Standards change
120146634 | anchor/guy | Non-HFTD | Transmission | 2020-12-05 | 2021-12-05 | Level 2 | E | 2024-02-06 | 2023-12-05 | Level 2 | GO 165 Inspection
120146770 | insulator and brushing | Non-HFTD | Transmission | 2020-12-05 | 2021-12-05 | Level 2 | E | 2024-12-07 | 2023-12-05 | Level 2 | Field Safety Reassessment
120147906 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2023-12-21 | 2025-11-03 | Level 3 | Standards change
120148315 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-04-06 | 2025-11-03 | Level 3 | Standards change
120148502 | other | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2024-04-29 | 2025-11-02 | Level 3 | GO 165 Inspection
120148770 | pole | Non-HFTD | Transmission | 2020-11-02 | 2022-11-02 | Level 3 | F | 2023-12-20 | 2025-11-02 | Level 3 | Standards change
120150353 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-04-06 | 2025-11-03 | Level 3 | Standards change
120150422 | other | Non-HFTD | Transmission | 2020-10-30 | 2022-10-30 | Level 3 | F | 2024-07-24 | 2025-10-30 | Level 3 | GO 165 Inspection
120150530 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-04-06 | 2025-11-03 | Level 3 | Standards change
120150566 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-04-06 | 2025-11-04 | Level 3 | Standards change
120160796 | anchor/guy | Non-HFTD | Transmission | 2020-12-09 | 2021-12-09 | Level 2 | E | 2024-01-03 | 2025-12-09 | Level 3 | Standards change
120161542 | insulator and brushing | Non-HFTD | Transmission | 2020-12-09 | 2021-12-09 | Level 2 | E | 2024-08-06 | 2023-12-09 | Level 2 | GO 165 Inspection
120161548 | pole | Non-HFTD | Transmission | 2020-12-09 | 2023-12-09 | Level 2 | E | 2024-10-28 | 2021-12-09 | Level 2 | GO 165 Inspection
120161833 | pole | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-10-29 | 2025-11-04 | Level 3 | GO 165 Inspection
120162360 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-04-06 | 2025-11-03 | Level 3 | Standards change
120162506 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2024-07-16 | 2025-11-04 | Level 3 | GO 165 Inspection
120163149 | other | Non-HFTD | Transmission | 2020-11-04 | 2022-11-04 | Level 3 | F | 2023-12-26 | 2025-11-04 | Level 3 | Standards change
120163440 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2023-12-21 | 2025-11-05 | Level 3 | Standards change
120163447 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-04-06 | 2025-11-05 | Level 3 | Standards change
120164743 | other | Non-HFTD | Transmission | 2020-12-07 | 2022-12-07 | Level 3 | F | 2024-01-11 | 2025-12-07 | Level 3 | Standards change
120165131 | other | Non-HFTD | Transmission | 2020-12-04 | 2022-12-04 | Level 3 | F | 2024-04-06 | 2025-12-04 | Level 3 | Standards change
120176723 | insulator and brushing | Non-HFTD | Transmission | 2020-12-10 | 2021-12-10 | Level 2 | E | 2024-07-23 | 2023-12-10 | Level 2 | GO 165 Inspection
120176740 | pole | Non-HFTD | Transmission | 2020-12-09 | 2022-12-09 | Level 3 | F | 2024-09-06 | 2025-12-09 | Level 3 | GO 165 Inspection
120176832 | other | Non-HFTD | Transmission | 2020-12-09 | 2022-12-09 | Level 3 | F | 2024-04-06 | 2025-12-09 | Level 3 | Standards change
120177094 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-06-20 | 2025-11-05 | Level 3 | GO 165 Inspection
120177281 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-01-05 | 2025-11-05 | Level 3 | Standards change
120177766 | other | Non-HFTD | Transmission | 2020-12-09 | 2022-12-09 | Level 3 | F | 2024-11-05 | 2025-12-09 | Level 3 | GO 165 Inspection
120177830 | pole | Non-HFTD | Transmission | 2020-12-09 | 2022-12-09 | Level 3 | F | 2024-11-05 | 2025-12-09 | Level 3 | GO 165 Inspection
120178085 | pole | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-12-16 | 2023-12-11 | Level 2 | Field Safety Reassessment
120178087 | pole | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-12-16 | 2023-12-11 | Level 2 | Field Safety Reassessment
120178144 | anchor/guy | Non-HFTD | Transmission | 2020-12-10 | 2021-12-10 | Level 2 | E | 2023-01-12 | 2023-12-10 | Level 2 | Standards change
120189291 | other | Non-HFTD | Transmission | 2020-12-08 | 2022-12-08 | Level 3 | F | 2024-02-28 | 2025-12-08 | Level 3 | Standards change
120189298 | other | Non-HFTD | Transmission | 2020-12-08 | 2022-12-08 | Level 3 | F | 2024-01-08 | 2025-12-08 | Level 3 | Standards change
120190969 | pole | Non-HFTD | Transmission | 2020-12-10 | 2021-12-10 | Level 2 | E | 2024-12-16 | 2023-12-10 | Level 2 | Field Safety Reassessment
120191020 | insulator and brushing | Non-HFTD | Transmission | 2020-12-12 | 2021-12-12 | Level 2 | E | 2024-10-02 | 2023-12-12 | Level 2 | GO 165 Inspection
120191022 | insulator and brushing | Non-HFTD | Transmission | 2020-12-12 | 2023-12-12 | Level 2 | E | 2024-10-02 | 2021-12-12 | Level 2 | GO 165 Inspection
120191779 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-10-16 | 2025-11-05 | Level 3 | GO 165 Inspection
120191870 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2024-10-16 | 2025-11-05 | Level 3 | GO 165 Inspection
120192027 | anchor/guy | Non-HFTD | Transmission | 2020-12-10 | 2021-12-10 | Level 2 | E | 2024-01-09 | 2025-12-10 | Level 3 | Standards change
120192034 | insulator and brushing | Non-HFTD | Transmission | 2020-12-14 | 2021-12-14 | Level 2 | E | 2024-09-10 | 2023-12-14 | Level 2 | GO 165 Inspection
120192449 | insulator and brushing | Non-HFTD | Transmission | 2020-12-12 | 2021-12-12 | Level 2 | E | 2024-10-29 | 2023-12-12 | Level 2 | GO 165 Inspection
120192704 | insulator and brushing | Non-HFTD | Transmission | 2020-12-14 | 2021-12-14 | Level 2 | E | 2024-10-02 | 2023-12-14 | Level 2 | GO 165 Inspection
120192852 | insulator and brushing | Non-HFTD | Transmission | 2020-12-12 | 2021-12-12 | Level 2 | E | 2024-10-02 | 2023-12-12 | Level 2 | GO 165 Inspection
120192916 | pole | Non-HFTD | Transmission | 2020-12-12 | 2022-12-12 | Level 3 | F | 2024-10-02 | 2025-12-12 | Level 3 | GO 165 Inspection
120200328 | anchor/guy | Non-HFTD | Transmission | 2020-12-14 | 2021-12-14 | Level 2 | E | 2023-01-20 | 2025-12-14 | Level 3 | Standards change
120200731 | pole | Non-HFTD | Transmission | 2020-12-14 | 2021-12-14 | Level 2 | E | 2024-12-16 | 2023-12-14 | Level 2 | Field Safety Reassessment
120201104 | other | Non-HFTD | Transmission | 2020-11-03 | 2022-11-03 | Level 3 | F | 2024-01-18 | 2025-11-03 | Level 3 | Standards change
120201109 | pole | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2023-12-27 | 2025-11-06 | Level 3 | Standards change
120201155 | insulator and brushing | Non-HFTD | Transmission | 2020-12-14 | 2021-12-14 | Level 2 | E | 2023-12-29 | 2023-12-14 | Level 2 | Standards change
120201194 | insulator and brushing | Non-HFTD | Transmission | 2020-12-14 | 2021-12-14 | Level 2 | E | 2024-10-10 | 2023-12-14 | Level 2 | GO 165 Inspection
120201247 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2023-12-21 | 2025-11-05 | Level 3 | Standards change
120201272 | other | Non-HFTD | Transmission | 2020-12-12 | 2022-12-12 | Level 3 | F | 2024-10-07 | 2025-12-12 | Level 3 | GO 165 Inspection
120201316 | pole | Non-HFTD | Transmission | 2020-12-12 | 2021-12-12 | Level 2 | E | 2024-08-16 | 2025-12-12 | Level 3 | GO 165 Inspection
120201322 | other | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2024-09-11 | 2025-11-06 | Level 3 | GO 165 Inspection
120201339 | anchor/guy | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2023-12-29 | 2025-12-11 | Level 3 | Standards change
120203802 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2023-12-21 | 2025-11-05 | Level 3 | Standards change
120203845 | other | Non-HFTD | Transmission | 2020-11-05 | 2022-11-05 | Level 3 | F | 2023-12-21 | 2025-11-05 | Level 3 | Standards change
120204165 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-09-17 | 2023-12-11 | Level 2 | GO 165 Inspection
120204235 | insulator and brushing | Non-HFTD | Transmission | 2020-12-12 | 2021-12-12 | Level 2 | E | 2024-08-16 | 2023-12-12 | Level 2 | GO 165 Inspection
120204588 | other | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2024-01-12 | 2025-11-06 | Level 3 | Standards change
120204638 | insulator and brushing | Non-HFTD | Transmission | 2020-12-12 | 2021-12-12 | Level 2 | E | 2022-12-21 | 2023-12-12 | Level 2 | Standards change
120204871 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-08-30 | 2023-12-11 | Level 2 | GO 165 Inspection
120205004 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-01-29 | 2023-12-11 | Level 2 | Standards change
120205591 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-09-17 | 2025-12-11 | Level 3 | GO 165 Inspection
120205598 | pole | Non-HFTD | Transmission | 2020-12-11 | 2022-12-11 | Level 3 | F | 2024-09-17 | 2025-12-11 | Level 3 | GO 165 Inspection
120205599 | anchor/guy | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2023-07-14 | 2025-12-11 | Level 3 | Standards change
120205772 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-09-17 | 2023-12-11 | Level 2 | GO 165 Inspection
120205773 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-09-17 | 2023-12-11 | Level 2 | GO 165 Inspection
120205853 | insulator and brushing | Non-HFTD | Transmission | 2020-12-11 | 2021-12-11 | Level 2 | E | 2024-08-30 | 2023-12-11 | Level 2 | GO 165 Inspection
120206188 | pole | Non-HFTD | Transmission | 2020-12-15 | 2021-12-15 | Level 2 | E | 2024-12-03 | 2023-12-15 | Level 2 | Field Safety Reassessment
120206190 | other | Non-HFTD | Transmission | 2020-12-14 | 2022-12-14 | Level 3 | F | 2024-08-19 | 2025-12-14 | Level 3 | GO 165 Inspection
120206214 | pole | Non-HFTD | Transmission | 2020-12-15 | 2021-12-15 | Level 2 | E | 2024-12-03 | 2023-12-15 | Level 2 | Field Safety Reassessment
120206606 | pole | Non-HFTD | Transmission | 2020-12-15 | 2021-12-15 | Level 2 | E | 2024-08-27 | 2023-12-15 | Level 2 | GO 165 Inspection
120207564 | other | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2024-07-18 | 2025-11-06 | Level 3 | GO 165 Inspection
120208040 | other | Non-HFTD | Transmission | 2020-11-09 | 2022-11-09 | Level 3 | F | 2023-12-12 | 2025-11-09 | Level 3 | Standards change
120210248 | other | Non-HFTD | Transmission | 2020-11-09 | 2022-11-09 | Level 3 | F | 2024-04-06 | 2025-11-09 | Level 3 | Standards change
120210289 | other | Non-HFTD | Transmission | 2020-11-06 | 2022-11-06 | Level 3 | F | 2024-04-06 | 2025-11-06 | Level 3 | Standards change
120210691 | other | Non-HFTD | Transmission | 2020-11-09 | 2022-11-09 | Level 3 | F | 2024-08-29 | 2025-11-09 | Level 3 | GO 165 Inspection
120210755 | other | Non-HFTD | Transmission | 2020-12-12 | 2022-12-12 | Level 3 | F | 2024-04-06 | 2025-12-12 | Level 3 | Standards change
120211097 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-08-26 | 2025-11-10 | Level 3 | GO 165 Inspection
120211135 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-04-06 | 2025-11-10 | Level 3 | Standards change
120211235 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-02-13 | 2025-11-10 | Level 3 | Standards change
120211412 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-04-06 | 2025-11-10 | Level 3 | Standards change
120211746 | other | Non-HFTD | Transmission | 2020-11-13 | 2022-11-13 | Level 3 | F | 2024-01-16 | 2025-11-13 | Level 3 | Standards change
120211760 | other | Non-HFTD | Transmission | 2020-11-10 | 2022-11-10 | Level 3 | F | 2024-04-06 | 2025-11-10 | Level 3 | Standards change
120211840 | pole | Non-HFTD | Transmission | 2020-11-12 | 2022-11-12 | Level 3 | F | 2024-11-12 | 2025-11-12 | Level 3 | GO 165 Inspection
120211846 | other | Non-HFTD | Transmission | 2020-11-12 | 2022-11-12 | Level 3 | F | 2024-08-27 | 2025-11-12 | Level 3 | GO 165 Inspection
120211905 | insulator and brushing | Non-HFTD | Transmission | 2020-12-15 | 2021-12-15 | Level 2 | E | 2024-04-09 | 2023-12-15 | Level 2 | GO 165 Inspection
120212321 | insulator and brushing | Non-HFTD | Transmission | 2020-12-16 | 2021-12-16 | Level 2 | E | 2024-01-23 | 2023-12-16 | Level 2 | Standards change
120212322 | insulator and brushing | Non-HFTD | Transmission | 2020-12-16 | 2021-12-16 | Level 2 | E | 2024-01-10 | 2023-12-16 | Level 2 | Standards change
120212573 | other | Non-HFTD | Transmission | 2020-11-12 | 2022-11-12 | Level 3 | F | 2024-08-27 | 2025-11-12 | Level 3 | GO 165 Inspection
120216071 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-04-06 | 2025-11-16 | Level 3 | Standards change
120217070 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-04-06 | 2025-11-16 | Level 3 | Standards change
120217959 | other | Non-HFTD | Transmission | 2020-11-17 | 2022-11-17 | Level 3 | F | 2024-02-08 | 2025-11-17 | Level 3 | GO 165 Inspection
120218195 | other | Non-HFTD | Transmission | 2020-11-17 | 2022-11-17 | Level 3 | F | 2024-01-02 | 2025-11-17 | Level 3 | Standards change
120218453 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-04-06 | 2025-11-16 | Level 3 | Standards change
120218457 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-04-06 | 2025-11-16 | Level 3 | Standards change
120218458 | other | Non-HFTD | Transmission | 2020-11-16 | 2022-11-16 | Level 3 | F | 2024-01-04 | 2025-11-16 | Level 3 | Standards change
120220905 | insulator and brushing | Non-HFTD | Transmission | 2020-12-17 | 2021-12-17 | Level 2 | E | 2024-03-18 | 2023-12-17 | Level 2 | Standards change
120221028 | other | Non-HFTD | Transmission | 2020-12-16 | 2021-12-16 | Level 2 | E | 2024-11-26 | 2023-12-16 | Level 2 | GO 165 Inspection
120221698 | insulator and brushing | Non-HFTD | Transmission | 2020-12-16 | 2021-12-16 | Level 2 | E | 2024-03-18 | 2023-12-16 | Level 2 | Standards change
120221758 | insulator and brushing | Non-HFTD | Transmission | 2020-12-16 | 2021-12-16 | Level 2 | E | 2024-10-07 | 2023-12-16 | Level 2 | GO 165 Inspection
120222266 | insulator and brushing | Non-HFTD | Transmission | 2020-12-18 | 2021-12-18 | Level 2 | E | 2024-10-02 | 2023-12-18 | Level 2 | GO 165 Inspection
120224050 | pole | Non-HFTD | Transmission | 2020-12-17 | 2023-12-17 | Level 2 | E | 2024-11-07 | 2021-06-17 | Level 2 | Field Safety Reassessment
120224051 | insulator and brushing | Non-HFTD | Transmission | 2020-12-16 | 2021-12-16 | Level 2 | E | 2024-03-15 | 2023-12-16 | Level 2 | Standards change
120225028 | insulator and brushing | Non-HFTD | Transmission | 2020-12-18 | 2021-12-18 | Level 2 | E | 2024-10-02 | 2023-12-18 | Level 2 | GO 165 Inspection
120225108 | insulator and brushing | Non-HFTD | Transmission | 2020-12-18 | 2021-12-18 | Level 2 | E | 2024-02-06 | 2023-12-18 | Level 2 | Standards change
120225131 | insulator and brushing | Non-HFTD | Transmission | 2020-12-18 | 2021-12-18 | Level 2 | E | 2024-10-02 | 2023-12-18 | Level 2 | GO 165 Inspection
120226100 | other | Non-HFTD | Transmission | 2020-12-18 | 2022-12-18 | Level 3 | F | 2024-04-06 | 2025-12-18 | Level 3 | Standards change
120226194 | insulator and brushing | Non-HFTD | Transmission | 2020-12-18 | 2021-12-18 | Level 2 | E | 2024-09-03 | 2023-12-18 | Level 2 | GO 165 Inspection
120226445 | insulator and brushing | Non-HFTD | Transmission | 2020-12-18 | 2021-12-18 | Level 2 | E | 2024-10-03 | 2023-12-18 | Level 2 | GO 165 Inspection
120226763 | pole | Non-HFTD | Transmission | 2020-12-21 | 2021-12-21 | Level 2 | E | 2024-12-02 | 2023-12-21 | Level 2 | Field Safety Reassessment
120226814 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2023-07-26 | 2025-12-21 | Level 3 | Standards change
120226867 | insulator and brushing | Non-HFTD | Transmission | 2020-12-19 | 2021-12-19 | Level 2 | E | 2024-09-04 | 2023-12-19 | Level 2 | GO 165 Inspection
120226868 | insulator and brushing | Non-HFTD | Transmission | 2020-12-19 | 2021-12-19 | Level 2 | E | 2024-10-22 | 2023-12-19 | Level 2 | GO 165 Inspection
120227265 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-10-29 | 2025-12-21 | Level 3 | GO 165 Inspection
120227372 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-10-29 | 2025-12-21 | Level 3 | GO 165 Inspection
120227397 | insulator and brushing | Non-HFTD | Transmission | 2020-12-21 | 2021-12-21 | Level 2 | E | 2024-01-30 | 2023-12-21 | Level 2 | Standards change
120227457 | insulator and brushing | Non-HFTD | Transmission | 2020-12-21 | 2021-12-21 | Level 2 | E | 2024-10-29 | 2023-12-21 | Level 2 | GO 165 Inspection
120227790 | insulator and brushing | Non-HFTD | Transmission | 2020-12-22 | 2021-12-22 | Level 2 | E | 2024-10-29 | 2023-12-22 | Level 2 | GO 165 Inspection
120227944 | insulator and brushing | Non-HFTD | Transmission | 2020-12-22 | 2023-12-22 | Level 2 | E | 2024-11-04 | 2021-03-22 | Level 2 | GO 165 Inspection
120228082 | pole | Non-HFTD | Transmission | 2020-11-17 | 2022-11-17 | Level 3 | F | 2023-03-31 | 2025-11-17 | Level 3 | Standards change
120228085 | pole | Non-HFTD | Transmission | 2020-11-18 | 2022-11-18 | Level 3 | F | 2022-12-15 | 2025-11-18 | Level 3 | Standards change
120229057 | insulator and brushing | Non-HFTD | Transmission | 2020-12-22 | 2021-12-22 | Level 2 | E | 2024-10-29 | 2023-12-22 | Level 2 | GO 165 Inspection
120229059 | pole | Non-HFTD | Transmission | 2020-12-22 | 2022-12-22 | Level 3 | F | 2024-10-29 | 2025-12-22 | Level 3 | GO 165 Inspection
120229423 | pole | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2024-08-28 | 2025-11-19 | Level 3 | GO 165 Inspection
120229560 | pole | Non-HFTD | Transmission | 2020-11-17 | 2022-11-17 | Level 3 | F | 2024-01-29 | 2025-11-17 | Level 3 | Standards change
120229666 | other | Non-HFTD | Transmission | 2020-11-20 | 2022-11-20 | Level 3 | F | 2024-04-06 | 2025-11-20 | Level 3 | Standards change
120229749 | other | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2024-11-19 | 2025-11-19 | Level 3 | GO 165 Inspection
120229773 | other | Non-HFTD | Transmission | 2020-11-19 | 2022-11-19 | Level 3 | F | 2024-01-08 | 2025-11-19 | Level 3 | Standards change
120229953 | other | Non-HFTD | Transmission | 2020-12-22 | 2021-12-22 | Level 2 | E | 2023-04-13 | 2025-12-22 | Level 3 | Standards change
120231810 | insulator and brushing | Non-HFTD | Transmission | 2020-12-22 | 2023-12-22 | Level 2 | E | 2024-10-24 | 2021-06-22 | Level 2 | GO 165 Inspection
120231893 | insulator and brushing | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-08-28 | 2023-11-23 | Level 2 | GO 165 Inspection
120231906 | insulator and brushing | Non-HFTD | Transmission | 2020-11-23 | 2021-11-23 | Level 2 | E | 2024-08-28 | 2023-11-23 | Level 2 | GO 165 Inspection
120231988 | other | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2024-08-29 | 2025-11-23 | Level 3 | GO 165 Inspection
120232010 | insulator and brushing | Non-HFTD | Transmission | 2020-12-22 | 2021-12-22 | Level 2 | E | 2024-11-04 | 2023-12-22 | Level 2 | GO 165 Inspection
120232096 | insulator and brushing | Non-HFTD | Transmission | 2020-12-23 | 2021-12-23 | Level 2 | E | 2024-09-03 | 2023-12-23 | Level 2 | GO 165 Inspection
120232200 | pole | Non-HFTD | Transmission | 2020-12-23 | 2021-12-23 | Level 2 | E | 2024-12-31 | 2023-12-23 | Level 2 | Field Safety Reassessment
120232337 | other | Non-HFTD | Transmission | 2020-11-24 | 2022-11-24 | Level 3 | F | 2024-10-23 | 2025-11-24 | Level 3 | GO 165 Inspection
120232430 | insulator and brushing | Non-HFTD | Transmission | 2020-12-23 | 2021-12-23 | Level 2 | E | 2024-09-04 | 2023-12-23 | Level 2 | GO 165 Inspection
120232441 | other | HFTD Tier 2 | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2024-05-03 | 2025-11-23 | Level 3 | GO 165 Inspection
120232529 | other | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2024-01-10 | 2025-11-23 | Level 3 | Standards change
120232536 | other | Non-HFTD | Transmission | 2020-11-24 | 2022-11-24 | Level 3 | F | 2023-11-30 | 2025-11-24 | Level 3 | Standards change
120232545 | other | Non-HFTD | Transmission | 2020-11-23 | 2022-11-23 | Level 3 | F | 2024-04-06 | 2025-11-23 | Level 3 | Standards change
120232937 | other | Non-HFTD | Transmission | 2020-12-23 | 2022-12-23 | Level 3 | F | 2024-03-19 | 2025-12-23 | Level 3 | GO 165 Inspection
120235163 | insulator and brushing | Non-HFTD | Transmission | 2020-12-24 | 2021-12-24 | Level 2 | E | 2024-08-20 | 2023-12-24 | Level 2 | GO 165 Inspection
120237271 | other | HFTD Tier 3 | Transmission | 2020-12-01 | 2022-12-01 | Level 3 | F | 2024-04-24 | 2025-12-01 | Level 3 | GO 165 Inspection
120237702 | other | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2024-02-29 | 2025-12-02 | Level 3 | Standards change
120238070 | other | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2024-10-21 | 2025-12-02 | Level 3 | GO 165 Inspection
120238140 | other | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2024-09-28 | 2025-12-02 | Level 3 | GO 165 Inspection
120238466 | other | Non-HFTD | Transmission | 2020-12-03 | 2022-12-03 | Level 3 | F | 2024-04-06 | 2025-12-03 | Level 3 | Standards change
120238941 | other | Non-HFTD | Transmission | 2020-12-04 | 2022-12-04 | Level 3 | F | 2024-04-06 | 2025-12-04 | Level 3 | Standards change
120239104 | other | Non-HFTD | Transmission | 2020-12-03 | 2022-12-03 | Level 3 | F | 2024-04-06 | 2025-12-03 | Level 3 | Standards change
120240650 | other | Non-HFTD | Transmission | 2020-12-02 | 2022-12-02 | Level 3 | F | 2023-12-04 | 2025-12-02 | Level 3 | Standards change
120240967 | other | Non-HFTD | Transmission | 2020-12-03 | 2022-12-03 | Level 3 | F | 2024-12-10 | 2025-12-03 | Level 3 | GO 165 Inspection
120241824 | pole | Non-HFTD | Transmission | 2020-12-04 | 2022-12-04 | Level 3 | F | 2024-10-01 | 2025-12-04 | Level 3 | GO 165 Inspection
120243174 | other | Non-HFTD | Transmission | 2020-12-11 | 2022-12-11 | Level 3 | F | 2024-04-06 | 2025-12-11 | Level 3 | Standards change
120244168 | other | HFTD Tier 3 | Transmission | 2020-12-11 | 2022-12-11 | Level 3 | F | 2024-05-17 | 2025-12-11 | Level 3 | GO 165 Inspection
120244246 | other | Non-HFTD | Transmission | 2020-12-10 | 2022-12-10 | Level 3 | F | 2024-04-06 | 2025-12-10 | Level 3 | Standards change
120244249 | other | Non-HFTD | Transmission | 2020-12-11 | 2022-12-11 | Level 3 | F | 2024-04-06 | 2025-12-11 | Level 3 | Standards change
120244909 | other | Non-HFTD | Transmission | 2020-12-11 | 2022-12-11 | Level 3 | F | 2024-04-06 | 2025-12-11 | Level 3 | Standards change
120244941 | other | Non-HFTD | Transmission | 2020-12-14 | 2022-12-14 | Level 3 | F | 2024-04-06 | 2025-12-14 | Level 3 | Standards change
120252717 | other | Non-HFTD | Transmission | 2020-12-14 | 2022-12-14 | Level 3 | F | 2024-09-27 | 2025-12-14 | Level 3 | GO 165 Inspection
120253303 | other | Non-HFTD | Transmission | 2020-12-16 | 2022-12-16 | Level 3 | F | 2024-09-10 | 2025-12-16 | Level 3 | GO 165 Inspection
120254361 | other | HFTD Tier 3 | Transmission | 2020-12-16 | 2022-12-16 | Level 3 | F | 2024-03-26 | 2025-12-16 | Level 3 | GO 165 Inspection
120254859 | other | Non-HFTD | Transmission | 2020-12-17 | 2022-12-17 | Level 3 | F | 2024-02-28 | 2025-12-17 | Level 3 | Standards change
120255176 | other | HFTD Tier 3 | Transmission | 2020-12-18 | 2022-12-18 | Level 3 | F | 2024-04-18 | 2025-12-18 | Level 3 | GO 165 Inspection
120255286 | other | Non-HFTD | Transmission | 2020-12-16 | 2022-12-16 | Level 3 | F | 2024-04-06 | 2025-12-16 | Level 3 | Standards change
120255598 | other | Non-HFTD | Transmission | 2020-12-18 | 2022-12-18 | Level 3 | F | 2024-10-01 | 2025-12-18 | Level 3 | GO 165 Inspection
120255713 | other | Non-HFTD | Transmission | 2020-12-19 | 2022-12-19 | Level 3 | F | 2024-01-16 | 2025-12-19 | Level 3 | Standards change
120256632 | pole | Non-HFTD | Transmission | 2020-12-01 | 2021-12-01 | Level 2 | E | 2024-12-09 | 2023-12-01 | Level 2 | Field Safety Reassessment
120257333 | pole | Non-HFTD | Transmission | 2021-01-05 | 2022-01-05 | Level 2 | E | 2024-08-01 | 2024-01-05 | Level 2 | Field Safety Reassessment
120258088 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120258866 | other | Non-HFTD | Transmission | 2020-12-19 | 2022-12-19 | Level 3 | F | 2024-04-06 | 2025-12-19 | Level 3 | Standards change
120259035 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120259039 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120259765 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2023-11-14 | 2025-12-21 | Level 3 | Standards change
120259881 | other | Non-HFTD | Transmission | 2020-12-23 | 2022-12-23 | Level 3 | F | 2023-12-15 | 2025-12-23 | Level 3 | Standards change
120260365 | pole | Non-HFTD | Transmission | 2020-12-22 | 2022-12-22 | Level 3 | F | 2024-11-04 | 2025-12-22 | Level 3 | GO 165 Inspection
120260610 | other | Non-HFTD | Transmission | 2020-12-22 | 2022-12-22 | Level 3 | F | 2024-04-06 | 2025-12-22 | Level 3 | Standards change
120262269 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120262371 | pole | Non-HFTD | Transmission | 2020-12-22 | 2022-12-22 | Level 3 | F | 2023-01-19 | 2025-12-22 | Level 3 | Standards change
120264972 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120264978 | other | Non-HFTD | Transmission | 2020-12-22 | 2022-12-22 | Level 3 | F | 2024-10-23 | 2025-12-22 | Level 3 | GO 165 Inspection
120276210 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120281244 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-01-09 | 2025-12-21 | Level 3 | Standards change
120316800 | other | Non-HFTD | Transmission | 2020-12-23 | 2022-12-23 | Level 3 | F | 2023-07-21 | 2025-12-23 | Level 3 | Standards change
120330515 | other | Non-HFTD | Transmission | 2020-12-21 | 2022-12-21 | Level 3 | F | 2024-04-06 | 2025-12-21 | Level 3 | Standards change
120350771 | other | Non-HFTD | Transmission | 2020-12-23 | 2022-12-23 | Level 3 | F | 2024-01-02 | 2025-12-23 | Level 3 | Standards change
120420717 | other | Non-HFTD | Transmission | 2020-12-23 | 2022-12-23 | Level 3 | F | 2024-04-06 | 2025-12-23 | Level 3 | Standards change
120423135 | other | Non-HFTD | Transmission | 2020-12-23 | 2022-12-23 | Level 3 | F | 2024-01-08 | 2025-12-23 | Level 3 | Standards change
120426837 | insulator and brushing | Non-HFTD | Transmission | 2021-01-13 | 2022-01-13 | Level 2 | E | 2024-08-15 | 2024-01-13 | Level 2 | GO 165 Inspection
120427074 | insulator and brushing | Non-HFTD | Transmission | 2021-01-13 | 2022-01-13 | Level 2 | E | 2024-09-17 | 2024-01-13 | Level 2 | Field Safety Reassessment
120462101 | other | Non-HFTD | Transmission | 2021-01-25 | 2022-01-25 | Level 2 | E | 2024-08-02 | 2024-01-25 | Level 2 | Field Safety Reassessment
120464049 | other | Non-HFTD | Transmission | 2021-01-26 | 2022-01-26 | Level 2 | E | 2024-09-27 | 2024-01-26 | Level 2 | Field Safety Reassessment
120464136 | pole | Non-HFTD | Transmission | 2021-01-26 | 2022-01-26 | Level 2 | E | 2024-10-28 | 2024-01-26 | Level 2 | Field Safety Reassessment
120465684 | insulator and brushing | Non-HFTD | Transmission | 2021-01-26 | 2022-01-26 | Level 2 | E | 2022-12-21 | 2024-01-26 | Level 2 | Standards change
120469261 | insulator and brushing | Non-HFTD | Transmission | 2021-01-26 | 2022-01-26 | Level 2 | E | 2024-09-23 | 2024-01-26 | Level 2 | Field Safety Reassessment
120481273 | pole | Non-HFTD | Transmission | 2021-01-07 | 2022-01-07 | Level 2 | E | 2023-02-06 | 2024-01-07 | Level 2 | Standards change
120503815 | anchor/guy | Non-HFTD | Transmission | 2021-02-05 | 2022-02-05 | Level 2 | E | 2024-12-26 | 2024-02-05 | Level 2 | Field Safety Reassessment
120567515 | other | Non-HFTD | Transmission | 2021-02-23 | 2022-02-23 | Level 2 | E | 2023-01-23 | 2026-02-23 | Level 3 | Standards change
120583574 | switch | Non-HFTD | Transmission | 2021-02-27 | 2022-02-27 | Level 2 | E | 2023-02-25 | 2024-02-27 | Level 2 | GO 165 Inspection
120633287 | insulator and brushing | Non-HFTD | Transmission | 2021-03-11 | 2022-03-11 | Level 2 | E | 2024-12-23 | 2024-03-11 | Level 2 | Field Safety Reassessment
120637950 | other | Non-HFTD | Transmission | 2021-03-11 | 2023-03-11 | Level 3 | F | 2024-04-04 | 2026-03-11 | Level 3 | GO 165 Inspection
120646285 | insulator and brushing | Non-HFTD | Transmission | 2021-03-16 | 2022-03-16 | Level 2 | E | 2024-12-18 | 2024-03-16 | Level 2 | Field Safety Reassessment
120647237 | pole | Non-HFTD | Transmission | 2021-03-16 | 2022-03-16 | Level 2 | E | 2023-03-14 | 2024-03-16 | Level 2 | Standards change
120648398 | other | Non-HFTD | Transmission | 2021-03-15 | 2023-03-15 | Level 3 | F | 2024-09-04 | 2026-03-15 | Level 3 | GO 165 Inspection
120648516 | other | Non-HFTD | Transmission | 2021-03-15 | 2026-03-15 | Level 3 | F |  | 2026-03-15 | Level 3
120651582 | other | Non-HFTD | Transmission | 2021-03-15 | 2023-03-15 | Level 3 | F | 2024-01-12 | 2026-03-15 | Level 3 | Standards change
120652499 | other | Non-HFTD | Transmission | 2021-03-17 | 2023-03-17 | Level 3 | F | 2024-04-06 | 2026-03-17 | Level 3 | Standards change
120652790 | other | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2023-01-27 | 2026-03-17 | Level 3 | Standards change
120653474 | other | Non-HFTD | Transmission | 2021-03-16 | 2023-03-16 | Level 3 | F | 2024-07-19 | 2026-03-16 | Level 3 | GO 165 Inspection
120653736 | other | Non-HFTD | Transmission | 2021-03-17 | 2023-03-17 | Level 3 | F | 2024-04-06 | 2026-03-17 | Level 3 | Standards change
120653771 | other | Non-HFTD | Transmission | 2021-03-16 | 2022-03-16 | Level 2 | E | 2023-02-17 | 2026-03-16 | Level 3 | Standards change
120653881 | other | Non-HFTD | Transmission | 2021-03-15 | 2023-03-15 | Level 3 | F | 2024-04-06 | 2026-03-15 | Level 3 | Standards change
120654160 | insulator and brushing | Non-HFTD | Transmission | 2021-03-16 | 2022-03-16 | Level 2 | E | 2024-10-24 | 2024-03-16 | Level 2 | GO 165 Inspection
120654164 | insulator and brushing | Non-HFTD | Transmission | 2021-03-16 | 2022-03-16 | Level 2 | E | 2024-10-24 | 2024-03-16 | Level 2 | GO 165 Inspection
120656834 | insulator and brushing | Non-HFTD | Transmission | 2021-03-16 | 2022-03-16 | Level 2 | E | 2024-12-17 | 2024-03-16 | Level 2 | Field Safety Reassessment
120656859 | other | Non-HFTD | Transmission | 2021-03-16 | 2023-03-16 | Level 3 | F | 2023-12-05 | 2026-03-16 | Level 3 | Standards change
120657262 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-12-16 | 2024-03-17 | Level 2 | Field Safety Reassessment
120657626 | other | Non-HFTD | Transmission | 2021-03-15 | 2023-03-15 | Level 3 | F | 2023-08-03 | 2026-03-15 | Level 3 | Standards change
120657870 | other | Non-HFTD | Transmission | 2021-03-17 | 2023-03-17 | Level 3 | F | 2024-01-16 | 2026-03-17 | Level 3 | Standards change
120658035 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-12-02 | 2024-03-17 | Level 2 | Field Safety Reassessment
120658196 | other | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2023-10-10 | 2026-03-17 | Level 3 | Standards change
120658955 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-04-06 | 2026-03-18 | Level 3 | Standards change
120659269 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-04-06 | 2026-03-18 | Level 3 | Standards change
120660167 | switch | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2023-10-10 | 2024-03-18 | Level 2 | Standards change
120660225 | other | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-07-12 | 2024-03-18 | Level 2 | GO 165 Inspection
120661932 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-12-23 | 2024-03-17 | Level 2 | Field Safety Reassessment
120662114 | pole | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-10-24 | 2024-03-18 | Level 2 | GO 165 Inspection
120662290 | other | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-07-24 | 2026-03-17 | Level 3 | GO 165 Inspection
120662505 | pole | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-07-22 | 2024-03-18 | Level 2 | GO 165 Inspection
120662772 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-07-18 | 2026-03-18 | Level 3 | GO 165 Inspection
120663270 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2023-10-10 | 2024-03-17 | Level 2 | Standards change
120663433 | other | Non-HFTD | Transmission | 2021-03-19 | 2023-03-19 | Level 3 | F | 2023-03-03 | 2026-03-19 | Level 3 | Standards change
120663924 | anchor/guy | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2023-10-10 | 2026-03-19 | Level 3 | Standards change
120664130 | other | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2024-09-24 | 2026-03-19 | Level 3 | GO 165 Inspection
120664520 | insulator and brushing | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2023-10-10 | 2024-03-19 | Level 2 | Standards change
120664681 | other | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2024-12-06 | 2024-03-19 | Level 2 | Field Safety Reassessment
120666998 | anchor/guy | Non-HFTD | Transmission | 2021-03-20 | 2022-03-20 | Level 2 | E | 2023-10-10 | 2026-03-20 | Level 3 | Standards change
120667264 | other | Non-HFTD | Transmission | 2021-03-20 | 2023-03-20 | Level 3 | F | 2024-04-06 | 2026-03-20 | Level 3 | Standards change
120667267 | other | Non-HFTD | Transmission | 2021-03-20 | 2023-03-20 | Level 3 | F | 2024-04-06 | 2026-03-20 | Level 3 | Standards change
120668083 | other | Non-HFTD | Transmission | 2021-03-20 | 2023-03-20 | Level 3 | F | 2024-04-06 | 2026-03-20 | Level 3 | Standards change
120668224 | pole | Non-HFTD | Transmission | 2021-03-20 | 2023-03-20 | Level 3 | F | 2024-06-18 | 2026-03-20 | Level 3 | GO 165 Inspection
120668230 | pole | Non-HFTD | Transmission | 2021-03-20 | 2023-03-20 | Level 3 | F | 2024-06-18 | 2026-03-20 | Level 3 | GO 165 Inspection
120670032 | other | HFTD Tier 3 | Transmission | 2021-03-20 | 2023-03-20 | Level 3 | F | 2023-04-13 | 2026-03-20 | Level 3 | Standards change
120671423 | pole | Non-HFTD | Transmission | 2021-03-16 | 2023-03-16 | Level 3 | F | 2023-02-13 | 2026-03-16 | Level 3 | Standards change
120671493 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-10-24 | 2024-03-17 | Level 2 | GO 165 Inspection
120671521 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-09-24 | 2024-03-17 | Level 2 | GO 165 Inspection
120671557 | other | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2023-01-27 | 2026-03-19 | Level 3 | Standards change
120671703 | other | Non-HFTD | Transmission | 2021-03-15 | 2023-03-15 | Level 3 | F | 2024-09-17 | 2026-03-15 | Level 3 | GO 165 Inspection
120671731 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-12-17 | 2024-03-18 | Level 2 | Field Safety Reassessment
120672060 | other | Non-HFTD | Transmission | 2021-03-16 | 2023-03-16 | Level 3 | F | 2024-03-22 | 2026-03-16 | Level 3 | GO 165 Inspection
120672196 | insulator and brushing | Non-HFTD | Transmission | 2021-03-15 | 2022-03-15 | Level 2 | E | 2024-10-29 | 2024-03-15 | Level 2 | GO 165 Inspection
120672322 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-07-24 | 2024-03-17 | Level 2 | GO 165 Inspection
120672341 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-10-13 | 2026-03-22 | Level 3 | Standards change
120672342 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-10-13 | 2024-03-22 | Level 2 | Standards change
120672386 | pole | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-02-21 | 2026-03-22 | Level 3 | GO 165 Inspection
120672874 | insulator and brushing | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2024-10-24 | 2024-03-19 | Level 2 | GO 165 Inspection
120672882 | other | Non-HFTD | Transmission | 2021-03-19 | 2023-03-19 | Level 3 | F | 2024-10-24 | 2026-03-19 | Level 3 | GO 165 Inspection
120673008 | pole | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2024-02-07 | 2024-03-22 | Level 2 | Field Safety Reassessment
120673118 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-09-04 | 2026-03-22 | Level 3 | GO 165 Inspection
120673122 | splice | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-10-13 | 2024-03-22 | Level 2 | Standards change
120673289 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-12-17 | 2024-03-18 | Level 2 | Field Safety Reassessment
120673503 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-10-29 | 2024-03-18 | Level 2 | GO 165 Inspection
120673505 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2023-02-08 | 2024-03-18 | Level 2 | Standards change
120673593 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2024-01-18 | 2026-03-22 | Level 3 | Standards change
120673754 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-10-29 | 2026-03-18 | Level 3 | GO 165 Inspection
120674080 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2023-02-08 | 2024-03-17 | Level 2 | Standards change
120674378 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-12-17 | 2024-03-17 | Level 2 | Field Safety Reassessment
120674407 | insulator and brushing | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2023-03-13 | 2024-03-19 | Level 2 | Standards change
120674502 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-08-29 | 2026-03-22 | Level 3 | Standards change
120674549 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-07-18 | 2026-03-18 | Level 3 | GO 165 Inspection
120674567 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-03-07 | 2026-03-18 | Level 3 | GO 165 Inspection
120674709 | pole | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-10-13 | 2024-03-22 | Level 2 | Standards change
120674713 | insulator and brushing | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2024-11-23 | 2024-03-19 | Level 2 | Field Safety Reassessment
120675040 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-10-13 | 2026-03-22 | Level 3 | Standards change
120675176 | other | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2024-06-24 | 2026-03-22 | Level 3 | GO 165 Inspection
120675436 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-01-09 | 2026-03-22 | Level 3 | Standards change
120678062 | crossarm | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-11-14 | 2024-03-23 | Level 2 | Field Safety Reassessment
120678129 | pole | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-01-17 | 2024-03-23 | Level 2 | Field Safety Reassessment
120678137 | other | Non-HFTD | Transmission | 2021-03-19 | 2023-03-19 | Level 3 | F | 2023-12-05 | 2026-03-19 | Level 3 | Standards change
120678285 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-09-25 | 2024-03-17 | Level 2 | GO 165 Inspection
120678289 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2024-09-25 | 2024-03-17 | Level 2 | GO 165 Inspection
120678506 | other | Non-HFTD | Transmission | 2021-03-17 | 2023-03-17 | Level 3 | F | 2024-03-15 | 2026-03-17 | Level 3 | GO 165 Inspection
120678520 | other | Non-HFTD | Transmission | 2021-03-19 | 2023-03-19 | Level 3 | F | 2024-04-06 | 2026-03-19 | Level 3 | Standards change
120678525 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-10-29 | 2024-03-18 | Level 2 | GO 165 Inspection
120679150 | insulator and brushing | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2023-10-13 | 2024-03-17 | Level 2 | Standards change
120679151 | other | Non-HFTD | Transmission | 2021-03-17 | 2022-03-17 | Level 2 | E | 2023-10-13 | 2026-03-17 | Level 3 | Standards change
120679422 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-12-16 | 2024-03-18 | Level 2 | Field Safety Reassessment
120679827 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2024-01-09 | 2026-03-23 | Level 3 | Standards change
120680161 | insulator and brushing | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-10-29 | 2024-03-18 | Level 2 | GO 165 Inspection
120680187 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-10-29 | 2026-03-18 | Level 3 | GO 165 Inspection
120680334 | pole | Non-HFTD | Transmission | 2021-03-18 | 2022-03-18 | Level 2 | E | 2024-07-23 | 2024-03-18 | Level 2 | GO 165 Inspection
120680380 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-03-18 | 2026-03-22 | Level 3 | GO 165 Inspection
120683107 | insulator and brushing | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2024-12-24 | 2024-03-22 | Level 2 | Field Safety Reassessment
120683269 | pole | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-07-18 | 2024-03-23 | Level 2 | GO 165 Inspection
120683317 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-03-18 | 2026-03-22 | Level 3 | GO 165 Inspection
120683976 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2023-10-16 | 2026-03-22 | Level 3 | Standards change
120683988 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-03-18 | 2026-03-22 | Level 3 | GO 165 Inspection
120684141 | insulator and brushing | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-12-27 | 2024-03-23 | Level 2 | Field Safety Reassessment
120684144 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2024-03-14 | 2026-03-23 | Level 3 | GO 165 Inspection
120684378 | insulator and brushing | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-11-18 | 2024-03-23 | Level 2 | Field Safety Reassessment
120684416 | insulator and brushing | Non-HFTD | Transmission | 2021-03-24 | 2022-03-24 | Level 2 | E | 2024-12-10 | 2024-03-24 | Level 2 | Field Safety Reassessment
120684601 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2023-12-05 | 2026-03-23 | Level 3 | Standards change
120684606 | other | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-07-18 | 2026-03-23 | Level 3 | GO 165 Inspection
120684962 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2023-12-18 | 2026-03-22 | Level 3 | Standards change
120685060 | other | Non-HFTD | Transmission | 2021-03-24 | 2023-03-24 | Level 3 | F | 2024-01-02 | 2026-03-24 | Level 3 | Standards change
120686131 | other | Non-HFTD | Transmission | 2021-03-24 | 2023-03-24 | Level 3 | F | 2024-04-06 | 2026-03-24 | Level 3 | Standards change
120686164 | other | Non-HFTD | Transmission | 2021-03-18 | 2023-03-18 | Level 3 | F | 2024-11-12 | 2026-03-18 | Level 3 | GO 165 Inspection
120686218 | other | HFTD Tier 3 | Transmission | 2021-03-24 | 2023-03-24 | Level 3 | F | 2023-05-30 | 2026-03-24 | Level 3 | Standards change
120686354 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2024-01-02 | 2026-03-23 | Level 3 | Standards change
120686721 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2024-03-15 | 2026-03-23 | Level 3 | GO 165 Inspection
120686922 | anchor/guy | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2023-10-16 | 2026-03-23 | Level 3 | Standards change
120687250 | other | Non-HFTD | Transmission | 2021-03-24 | 2023-03-24 | Level 3 | F | 2024-04-06 | 2026-03-24 | Level 3 | Standards change
120687404 | other | Non-HFTD | Transmission | 2021-03-24 | 2023-03-24 | Level 3 | F | 2024-04-06 | 2026-03-24 | Level 3 | Standards change
120688947 | insulator and brushing | Non-HFTD | Transmission | 2021-03-24 | 2022-03-24 | Level 2 | E | 2024-12-11 | 2024-03-24 | Level 2 | Field Safety Reassessment
120689123 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2024-03-11 | 2026-03-23 | Level 3 | GO 165 Inspection
120689688 | insulator and brushing | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-12-24 | 2024-03-23 | Level 2 | Field Safety Reassessment
120690064 | pole | HFTD Tier 2 | Transmission | 2021-03-24 | 2023-03-24 | Level 3 | F | 2024-03-11 | 2026-03-24 | Level 3 | GO 165 Inspection
120691179 | pole | HFTD Tier 2 | Transmission | 2021-03-25 | 2023-03-25 | Level 3 | F | 2023-03-25 | 2026-03-25 | Level 3 | GO 165 Inspection
120691516 | pole | Non-HFTD | Transmission | 2021-03-25 | 2022-03-25 | Level 2 | E | 2024-11-13 | 2024-03-25 | Level 2 | Field Safety Reassessment
120691729 | other | Non-HFTD | Transmission | 2021-03-25 | 2023-03-25 | Level 3 | F | 2024-09-28 | 2026-03-25 | Level 3 | GO 165 Inspection
120692009 | anchor/guy | Non-HFTD | Transmission | 2021-03-25 | 2022-03-25 | Level 2 | E | 2023-10-16 | 2026-03-25 | Level 3 | Standards change
120696004 | other | Non-HFTD | Transmission | 2021-03-26 | 2024-03-26 | Level 2 | E | 2024-12-10 | 2026-03-26 | Level 3 | Field Safety Reassessment
120696250 | anchor/guy | Non-HFTD | Transmission | 2021-03-26 | 2022-03-26 | Level 2 | E | 2023-10-16 | 2026-03-26 | Level 3 | Standards change
120696255 | insulator and brushing | Non-HFTD | Transmission | 2021-03-26 | 2022-03-26 | Level 2 | E | 2024-06-17 | 2024-03-26 | Level 2 | GO 165 Inspection
120696268 | other | Non-HFTD | Transmission | 2021-03-26 | 2022-03-26 | Level 2 | E | 2024-12-26 | 2024-03-26 | Level 2 | Field Safety Reassessment
120696976 | other | Non-HFTD | Transmission | 2021-03-26 | 2023-03-26 | Level 3 | F | 2024-09-04 | 2026-03-26 | Level 3 | GO 165 Inspection
120697258 | pole | Non-HFTD | Transmission | 2021-03-26 | 2022-03-26 | Level 2 | E | 2024-12-11 | 2024-03-26 | Level 2 | Field Safety Reassessment
120697494 | other | Non-HFTD | Transmission | 2021-03-26 | 2023-03-26 | Level 3 | F | 2024-04-06 | 2026-03-26 | Level 3 | Standards change
120697677 | other | Non-HFTD | Transmission | 2021-03-26 | 2023-03-26 | Level 3 | F | 2023-01-30 | 2026-03-26 | Level 3 | Standards change
120699065 | other | Non-HFTD | Transmission | 2021-03-26 | 2022-03-26 | Level 2 | E | 2024-08-08 | 2024-03-26 | Level 2 | GO 165 Inspection
120700602 | other | Non-HFTD | Transmission | 2021-03-27 | 2023-03-27 | Level 3 | F | 2024-01-11 | 2026-03-27 | Level 3 | Standards change
120700679 | anchor/guy | Non-HFTD | Transmission | 2021-03-27 | 2022-03-27 | Level 2 | E | 2023-10-16 | 2026-03-27 | Level 3 | Standards change
120701077 | anchor/guy | Non-HFTD | Transmission | 2021-03-27 | 2023-03-27 | Level 3 | F | 2024-02-01 | 2026-03-27 | Level 3 | Standards change
120701095 | other | Non-HFTD | Transmission | 2021-03-27 | 2023-03-27 | Level 3 | F | 2024-01-19 | 2026-03-27 | Level 3 | Standards change
120701327 | other | Non-HFTD | Transmission | 2021-03-27 | 2023-03-27 | Level 3 | F | 2024-04-06 | 2026-03-27 | Level 3 | Standards change
120701342 | other | Non-HFTD | Transmission | 2021-03-27 | 2022-03-27 | Level 2 | E | 2023-05-11 | 2026-03-27 | Level 3 | Standards change
120701634 | other | Non-HFTD | Transmission | 2021-03-27 | 2023-03-27 | Level 3 | F | 2024-04-06 | 2026-03-27 | Level 3 | Standards change
120701721 | other | Non-HFTD | Transmission | 2021-03-27 | 2023-03-27 | Level 3 | F | 2024-02-15 | 2026-03-27 | Level 3 | Standards change
120701911 | splice | Non-HFTD | Transmission | 2021-03-27 | 2022-03-27 | Level 2 | E | 2023-10-16 | 2024-03-27 | Level 2 | Standards change
120702042 | pole | Non-HFTD | Transmission | 2021-03-27 | 2022-03-27 | Level 2 | E | 2024-10-29 | 2024-03-27 | Level 2 | GO 165 Inspection
120705147 | other | Non-HFTD | Transmission | 2021-03-27 | 2022-03-27 | Level 2 | E | 2024-04-22 | 2026-03-27 | Level 3 | GO 165 Inspection
120705766 | anchor/guy | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2023-10-16 | 2026-03-29 | Level 3 | Standards change
120706335 | anchor/guy | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2024-09-05 | 2026-03-29 | Level 3 | GO 165 Inspection
120706362 | other | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2024-12-02 | 2024-03-29 | Level 2 | Field Safety Reassessment
120706975 | other | HFTD Tier 3 | Transmission | 2021-03-29 | 2023-03-29 | Level 3 | F | 2024-05-23 | 2026-03-29 | Level 3 | GO 165 Inspection
120707094 | anchor/guy | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2023-10-16 | 2026-03-29 | Level 3 | Standards change
120707228 | other | Non-HFTD | Transmission | 2021-03-29 | 2023-03-29 | Level 3 | F | 2024-04-06 | 2026-03-29 | Level 3 | Standards change
120707353 | pole | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2024-05-03 | 2024-03-29 | Level 2 | GO 165 Inspection
120707815 | crossarm | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2024-11-14 | 2024-03-29 | Level 2 | Field Safety Reassessment
120709034 | other | Non-HFTD | Transmission | 2021-03-29 | 2023-03-29 | Level 3 | F | 2024-01-19 | 2026-03-29 | Level 3 | Standards change
120709201 | anchor/guy | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2023-10-16 | 2026-03-29 | Level 3 | Standards change
120709939 | other | Non-HFTD | Transmission | 2021-03-29 | 2023-03-29 | Level 3 | F | 2024-02-28 | 2026-03-29 | Level 3 | Standards change
120710974 | pole | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2024-12-20 | 2024-03-29 | Level 2 | Field Safety Reassessment
120711284 | other | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2023-10-16 | 2026-03-30 | Level 3 | Standards change
120712040 | other | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2023-12-19 | 2026-03-30 | Level 3 | Standards change
120712196 | insulator and brushing | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2024-07-10 | 2024-03-30 | Level 2 | GO 165 Inspection
120712844 | insulator and brushing | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2024-07-12 | 2026-03-30 | Level 3 | GO 165 Inspection
120713724 | other | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2024-04-06 | 2026-03-30 | Level 3 | Standards change
120713864 | other | Non-HFTD | Transmission | 2021-03-29 | 2022-03-29 | Level 2 | E | 2024-12-11 | 2024-03-29 | Level 2 | Field Safety Reassessment
120713865 | other | Non-HFTD | Transmission | 2021-03-30 | 2024-03-30 | Level 2 | E | 2024-11-05 | 2026-03-30 | Level 3 | Field Safety Reassessment
120713873 | other | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2024-04-06 | 2026-03-30 | Level 3 | Standards change
120713877 | other | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2024-02-28 | 2026-03-30 | Level 3 | Standards change
120713981 | pole | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2024-05-03 | 2024-03-30 | Level 2 | Field Safety Reassessment
120714174 | pole | HFTD Tier 3 | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2024-06-03 | 2026-03-30 | Level 3 | GO 165 Inspection
120714270 | anchor/guy | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2023-10-19 | 2026-03-30 | Level 3 | Standards change
120714272 | other | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2024-04-06 | 2026-03-30 | Level 3 | Standards change
120714892 | insulator and brushing | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2024-08-19 | 2024-03-30 | Level 2 | GO 165 Inspection
120715036 | pole | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2023-12-05 | 2026-03-30 | Level 3 | Standards change
120715066 | other | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2023-01-12 | 2026-03-30 | Level 3 | Standards change
120715291 | other | Non-HFTD | Transmission | 2021-03-30 | 2023-03-30 | Level 3 | F | 2024-04-06 | 2026-03-30 | Level 3 | Standards change
120715673 | insulator and brushing | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2023-10-19 | 2024-03-30 | Level 2 | Standards change
120715676 | insulator and brushing | Non-HFTD | Transmission | 2021-03-30 | 2022-03-30 | Level 2 | E | 2023-10-19 | 2024-03-30 | Level 2 | Standards change
120718183 | insulator and brushing | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2023-01-23 | 2026-03-31 | Level 3 | Standards change
120718306 | insulator and brushing | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2023-01-23 | 2026-03-31 | Level 3 | Standards change
120718468 | other | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2024-07-01 | 2026-03-31 | Level 3 | GO 165 Inspection
120718745 | anchor/guy | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2024-09-17 | 2024-03-31 | Level 2 | GO 165 Inspection
120719154 | other | Non-HFTD | Transmission | 2021-03-25 | 2022-03-25 | Level 2 | E | 2024-04-16 | 2022-03-25 | Level 2 | GO 165 Inspection
120719568 | pole | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2024-05-10 | 2024-03-31 | Level 2 | Field Safety Reassessment
120719796 | pole | Non-HFTD | Transmission | 2021-03-31 | 2024-03-30 | Level 2 | E | 2024-05-22 | 2021-09-30 | Level 2 | GO 165 Inspection
120720680 | other | Non-HFTD | Transmission | 2021-03-31 | 2023-03-31 | Level 3 | F | 2024-04-06 | 2026-03-31 | Level 3 | Standards change
120724035 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-02-28 | 2026-04-01 | Level 3 | Standards change
120724273 | insulator and brushing | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2023-10-05 | 2024-03-31 | Level 2 | Standards change
120724503 | insulator and brushing | Non-HFTD | Transmission | 2021-04-01 | 2022-04-01 | Level 2 | E | 2024-12-31 | 2024-04-01 | Level 2 | Field Safety Reassessment
120724590 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-01-09 | 2026-04-01 | Level 3 | Standards change
120725049 | pole | Non-HFTD | Transmission | 2021-04-01 | 2022-04-01 | Level 2 | E | 2024-11-26 | 2024-04-01 | Level 2 | Field Safety Reassessment
120725172 | pole | Non-HFTD | Transmission | 2021-04-01 | 2022-04-01 | Level 2 | E | 2024-06-17 | 2024-04-01 | Level 2 | Field Safety Reassessment
120725212 | other | Non-HFTD | Transmission | 2021-04-01 | 2024-04-01 | Level 2 | E | 2024-11-05 | 2022-04-01 | Level 2 | Field Safety Reassessment
120725259 | pole | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-05-23 | 2026-04-01 | Level 3 | GO 165 Inspection
120725790 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-04-06 | 2026-04-01 | Level 3 | Standards change
120725882 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-08-13 | 2026-04-01 | Level 3 | GO 165 Inspection
120726378 | other | Non-HFTD | Transmission | 2021-04-01 | 2022-04-01 | Level 2 | E | 2023-01-17 | 2024-04-01 | Level 2 | Standards change
120726465 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-08-14 | 2026-04-01 | Level 3 | GO 165 Inspection
120726483 | other | HFTD Tier 2 | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-04-06 | 2026-04-01 | Level 3 | Standards change
120728168 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-08-29 | 2026-04-01 | Level 3 | GO 165 Inspection
120734065 | insulator and brushing | Non-HFTD | Transmission | 2021-04-01 | 2022-04-01 | Level 2 | E | 2022-10-15 | 2022-04-01 | Level 2 | Field Safety Reassessment
120734075 | other | Non-HFTD | Transmission | 2021-03-31 | 2023-03-31 | Level 3 | F | 2024-04-06 | 2026-03-31 | Level 3 | Standards change
120734324 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-10-08 | 2026-04-02 | Level 3 | GO 165 Inspection
120734658 | other | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-05-15 | 2024-04-02 | Level 2 | Field Safety Reassessment
120735195 | other | Non-HFTD | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2023-05-15 | 2026-03-22 | Level 3 | GO 165 Inspection
120735670 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-01-12 | 2026-04-02 | Level 3 | Standards change
120735690 | other | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-12-11 | 2024-04-02 | Level 2 | Field Safety Reassessment
120735803 | pole | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-11-12 | 2024-04-02 | Level 2 | GO 165 Inspection
120735821 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-02-01 | 2026-04-02 | Level 3 | Standards change
120736000 | insulator and brushing | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-09-25 | 2024-04-02 | Level 2 | GO 165 Inspection
120736354 | other | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-04-06 | 2026-04-02 | Level 3 | Standards change
120736370 | insulator and brushing | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2023-11-15 | 2024-04-02 | Level 2 | Standards change
120736839 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-01-23 | 2026-04-02 | Level 3 | Standards change
120736850 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2023-12-05 | 2026-04-01 | Level 3 | Standards change
120737168 | pole | Non-HFTD | Transmission | 2021-04-01 | 2022-04-01 | Level 2 | E | 2024-07-26 | 2026-04-01 | Level 3 | GO 165 Inspection
120737323 | other | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-11-05 | 2024-04-02 | Level 2 | Field Safety Reassessment
120737447 | other | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2023-01-11 | 2026-04-02 | Level 3 | Standards change
120737526 | other | Non-HFTD | Transmission | 2021-04-02 | 2024-04-02 | Level 2 | E | 2024-12-11 | 2026-04-02 | Level 3 | Field Safety Reassessment
120737642 | other | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2023-12-04 | 2026-04-02 | Level 3 | Standards change
120737981 | pole | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-12-10 | 2024-04-02 | Level 2 | Field Safety Reassessment
120738175 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2023-01-17 | 2026-04-02 | Level 3 | Standards change
120738176 | pole | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2023-01-17 | 2026-04-02 | Level 3 | Standards change
120738190 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-08-30 | 2026-04-02 | Level 3 | GO 165 Inspection
120738214 | pole | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2023-12-07 | 2026-04-02 | Level 3 | Standards change
120738312 | other | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-08-30 | 2026-04-02 | Level 3 | GO 165 Inspection
120739116 | other | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2024-08-14 | 2026-04-03 | Level 3 | GO 165 Inspection
120739834 | other | Non-HFTD | Transmission | 2021-04-03 | 2024-04-03 | Level 2 | E | 2024-12-12 | 2022-04-03 | Level 2 | Field Safety Reassessment
120739839 | pole | Non-HFTD | Transmission | 2021-04-03 | 2023-04-03 | Level 3 | F | 2024-02-12 | 2026-04-03 | Level 3 | Standards change
120739852 | other | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2023-11-15 | 2024-04-03 | Level 2 | Standards change
120740059 | other | Non-HFTD | Transmission | 2021-04-03 | 2023-04-03 | Level 3 | F | 2024-04-06 | 2026-04-03 | Level 3 | Standards change
120740132 | other | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2023-11-15 | 2024-04-03 | Level 2 | Standards change
120740157 | anchor/guy | Non-HFTD | Transmission | 2021-04-03 | 2023-04-03 | Level 3 | F | 2024-01-02 | 2026-04-03 | Level 3 | Standards change
120740244 | insulator and brushing | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2024-12-31 | 2024-04-03 | Level 2 | Field Safety Reassessment
120740361 | other | Non-HFTD | Transmission | 2021-04-03 | 2023-04-03 | Level 3 | F | 2024-04-06 | 2026-04-03 | Level 3 | Standards change
120740387 | other | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2023-01-11 | 2026-04-03 | Level 3 | Standards change
120740793 | other | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2024-12-10 | 2024-04-03 | Level 2 | Field Safety Reassessment
120741187 | other | Non-HFTD | Transmission | 2021-04-03 | 2022-04-03 | Level 2 | E | 2023-01-27 | 2026-04-03 | Level 3 | Standards change
120741645 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-03-08 | 2026-04-01 | Level 3 | GO 165 Inspection
120741655 | other | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2023-01-17 | 2024-03-31 | Level 2 | Standards change
120741804 | insulator and brushing | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2024-12-31 | 2024-04-05 | Level 2 | Field Safety Reassessment
120742039 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2023-02-10 | 2026-04-05 | Level 3 | Standards change
120742109 | other | Non-HFTD | Transmission | 2021-04-05 | 2026-04-05 | Level 2 | E | 2024-04-05 | 2024-04-05 | Level 2 | GO 165 Inspection
120742244 | pole | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2024-12-23 | 2024-04-05 | Level 2 | Field Safety Reassessment
120742499 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-08-20 | 2026-04-05 | Level 3 | GO 165 Inspection
120742731 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-08-20 | 2026-04-05 | Level 3 | GO 165 Inspection
120742739 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-04-06 | 2026-04-05 | Level 3 | Standards change
120742810 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-04-06 | 2026-04-05 | Level 3 | Standards change
120743164 | insulator and brushing | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2023-01-23 | 2026-04-05 | Level 3 | Standards change
120743464 | other | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2024-07-01 | 2026-04-05 | Level 3 | GO 165 Inspection
120743496 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-08-20 | 2026-04-05 | Level 3 | GO 165 Inspection
120743621 | insulator and brushing | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2024-10-05 | 2024-03-31 | Level 2 | GO 165 Inspection
120743766 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-04-06 | 2026-04-05 | Level 3 | Standards change
120744011 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-01-26 | 2026-04-05 | Level 3 | Standards change
120744260 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-09-26 | 2026-04-05 | Level 3 | GO 165 Inspection
120744426 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-09-26 | 2026-04-05 | Level 3 | GO 165 Inspection
120744427 | insulator and brushing | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2024-12-31 | 2024-04-05 | Level 2 | Field Safety Reassessment
120745843 | insulator and brushing | Non-HFTD | Transmission | 2021-04-02 | 2022-04-02 | Level 2 | E | 2024-12-04 | 2024-04-02 | Level 2 | Field Safety Reassessment
120746053 | splice | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2023-11-15 | 2024-04-05 | Level 2 | Standards change
120746123 | insulator and brushing | Non-HFTD | Transmission | 2021-03-19 | 2022-03-19 | Level 2 | E | 2024-09-24 | 2024-03-19 | Level 2 | GO 165 Inspection
120747500 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-03-08 | 2026-04-05 | Level 3 | GO 165 Inspection
120748052 | other | Non-HFTD | Transmission | 2021-03-23 | 2022-03-23 | Level 2 | E | 2024-08-23 | 2024-03-23 | Level 2 | GO 165 Inspection
120748094 | pole | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-12-23 | 2022-04-06 | Level 2 | Field Safety Reassessment
120748115 | pole | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2023-02-10 | 2026-04-06 | Level 3 | Standards change
120748116 | other | Non-HFTD | Transmission | 2021-04-06 | 2024-04-06 | Level 2 | E | 2024-12-10 | 2022-04-06 | Level 2 | Field Safety Reassessment
120748297 | pole | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-07-30 | 2024-04-06 | Level 2 | Field Safety Reassessment
120748419 | insulator and brushing | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2023-11-15 | 2024-04-05 | Level 2 | Standards change
120748586 | other | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-04-06 | 2026-04-06 | Level 3 | Standards change
120748602 | other | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2023-12-15 | 2026-04-06 | Level 3 | Standards change
120748679 | other | Non-HFTD | Transmission | 2021-04-06 | 2024-04-06 | Level 2 | E | 2024-07-29 | 2022-04-06 | Level 2 | GO 165 Inspection
120748690 | pole | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-11-14 | 2026-04-06 | Level 3 | GO 165 Inspection
120748783 | insulator and brushing | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2023-01-20 | 2024-04-06 | Level 2 | Standards change
120749195 | pole | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-11-14 | 2024-04-06 | Level 2 | GO 165 Inspection
120749222 | other | Non-HFTD | Transmission | 2021-03-24 | 2022-03-24 | Level 2 | E | 2024-07-17 | 2022-03-24 | Level 2 | GO 165 Inspection
120749398 | other | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-04-06 | 2026-04-06 | Level 3 | Standards change
120749471 | other | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-04-06 | 2026-04-06 | Level 3 | Standards change
120749884 | pole | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2023-01-20 | 2026-04-06 | Level 3 | Standards change
120750005 | other | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-12-10 | 2024-04-06 | Level 2 | Field Safety Reassessment
120750038 | other | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-04-06 | 2026-04-06 | Level 3 | Standards change
120750440 | insulator and brushing | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-12-09 | 2024-04-06 | Level 2 | GO 165 Inspection
120750618 | other | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-08-30 | 2024-04-06 | Level 2 | GO 165 Inspection
120751640 | other | Non-HFTD | Transmission | 2021-03-31 | 2022-03-31 | Level 2 | E | 2023-02-10 | 2026-03-31 | Level 3 | Standards change
120754629 | pole | HFTD Tier 2 | Transmission | 2021-03-22 | 2023-03-22 | Level 3 | F | 2024-03-11 | 2026-03-22 | Level 3 | GO 165 Inspection
120755197 | insulator and brushing | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2024-12-09 | 2024-04-07 | Level 2 | GO 165 Inspection
120755290 | other | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2024-04-06 | 2026-04-07 | Level 3 | Standards change
120756164 | anchor/guy | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2024-09-20 | 2026-04-07 | Level 3 | GO 165 Inspection
120756525 | other | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2024-04-06 | 2026-04-07 | Level 3 | Standards change
120756830 | other | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2024-04-06 | 2026-04-07 | Level 3 | Standards change
120757798 | other | Non-HFTD | Transmission | 2021-04-02 | 2023-04-02 | Level 3 | F | 2024-10-29 | 2026-04-02 | Level 3 | GO 165 Inspection
120757888 | other | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2023-01-20 | 2024-04-07 | Level 2 | Standards change
120758206 | other | Non-HFTD | Transmission | 2021-03-23 | 2023-03-23 | Level 3 | F | 2024-03-11 | 2026-03-23 | Level 3 | GO 165 Inspection
120758510 | other | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2024-04-06 | 2026-04-07 | Level 3 | Standards change
120758714 | other | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2024-04-06 | 2026-04-07 | Level 3 | Standards change
120758809 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-01-08 | 2026-04-05 | Level 3 | Standards change
120759160 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-03-07 | 2026-04-01 | Level 3 | GO 165 Inspection
120759332 | insulator and brushing | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2024-12-31 | 2024-04-07 | Level 2 | Field Safety Reassessment
120759581 | pole | Non-HFTD | Transmission | 2021-04-07 | 2023-04-07 | Level 3 | F | 2023-12-13 | 2026-04-07 | Level 3 | Standards change
120761765 | pole | HFTD Tier 2 | Transmission | 2021-03-25 | 2023-03-25 | Level 3 | F | 2024-04-09 | 2026-03-25 | Level 3 | GO 165 Inspection
120761908 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-03-06 | 2026-04-01 | Level 3 | GO 165 Inspection
120762142 | other | Non-HFTD | Transmission | 2021-04-01 | 2023-04-01 | Level 3 | F | 2024-03-04 | 2026-04-01 | Level 3 | GO 165 Inspection
120762560 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-09-09 | 2026-04-08 | Level 3 | GO 165 Inspection
120762579 | pole | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2023-01-20 | 2026-04-08 | Level 3 | Standards change
120762735 | pole | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-09-27 | 2024-04-08 | Level 2 | GO 165 Inspection
120762773 | pole | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2024-12-17 | 2024-04-05 | Level 2 | Field Safety Reassessment
120762981 | other | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-12-13 | 2024-04-08 | Level 2 | Field Safety Reassessment
120763189 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-09-10 | 2026-04-08 | Level 3 | GO 165 Inspection
120763236 | splice | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-06-21 | 2024-04-08 | Level 2 | GO 165 Inspection
120763271 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-09-10 | 2026-04-08 | Level 3 | GO 165 Inspection
120763493 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-04-06 | 2026-04-08 | Level 3 | Standards change
120763946 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-01-08 | 2026-04-05 | Level 3 | Standards change
120764089 | other | Non-HFTD | Transmission | 2021-03-21 | 2023-03-21 | Level 3 | F | 2023-12-22 | 2026-03-21 | Level 3 | Standards change
120764175 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-04-06 | 2026-04-05 | Level 3 | Standards change
120764301 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-04-06 | 2026-04-08 | Level 3 | Standards change
120764346 | insulator and brushing | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-12-31 | 2024-04-08 | Level 2 | Field Safety Reassessment
120765052 | anchor/guy | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2023-11-15 | 2026-04-08 | Level 3 | Standards change
120765086 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-04-06 | 2026-04-08 | Level 3 | Standards change
120765171 | pole | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2023-01-31 | 2026-04-08 | Level 3 | Standards change
120765408 | pole | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2023-12-06 | 2026-04-05 | Level 3 | Standards change
120765489 | pole | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-11-17 | 2024-04-08 | Level 2 | Field Safety Reassessment
120765576 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-04-08 | 2026-04-05 | Level 3 | GO 165 Inspection
120765685 | pole | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2023-01-31 | 2026-04-08 | Level 3 | Standards change
120765726 | pole | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-10-16 | 2026-04-08 | Level 3 | GO 165 Inspection
120765938 | pole | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-11-26 | 2024-04-08 | Level 2 | Field Safety Reassessment
120769554 | other | HFTD Tier 2 | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-04-10 | 2026-04-08 | Level 3 | GO 165 Inspection
120769795 | pole | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2023-02-10 | 2026-04-08 | Level 3 | Standards change
120769799 | splice | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2023-11-15 | 2024-04-07 | Level 2 | Standards change
120769933 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2023-12-15 | 2026-04-05 | Level 3 | Standards change
120770143 | anchor/guy | Non-HFTD | Transmission | 2021-04-05 | 2022-04-05 | Level 2 | E | 2023-03-15 | 2026-04-05 | Level 3 | Standards change
120770987 | pole | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2024-11-26 | 2024-04-09 | Level 2 | Field Safety Reassessment
120771037 | pole | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2024-01-03 | 2026-04-09 | Level 3 | Standards change
120771065 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-03-07 | 2026-04-05 | Level 3 | GO 165 Inspection
120771489 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2024-08-26 | 2026-04-09 | Level 3 | GO 165 Inspection
120771778 | insulator and brushing | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2023-01-20 | 2026-04-09 | Level 3 | Standards change
120772212 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2023-12-15 | 2026-04-09 | Level 3 | Standards change
120772248 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2024-02-01 | 2026-04-09 | Level 3 | Standards change
120772527 | other | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2024-11-21 | 2024-04-06 | Level 2 | Field Safety Reassessment
120772634 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2023-12-12 | 2026-04-09 | Level 3 | Standards change
120772791 | anchor/guy | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2024-12-02 | 2026-04-09 | Level 3 | GO 165 Inspection
120772901 | other | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-01-09 | 2026-04-06 | Level 3 | Standards change
120773077 | pole | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2023-01-20 | 2026-04-09 | Level 3 | Standards change
120773802 | splice | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2023-11-15 | 2024-04-09 | Level 2 | Standards change
120773808 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F |  | 2026-04-09 | Level 3
120773898 | pole | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2023-12-07 | 2026-04-06 | Level 3 | Standards change
120773902 | other | Non-HFTD | Transmission | 2021-04-08 | 2023-04-08 | Level 3 | F | 2024-04-06 | 2026-04-08 | Level 3 | Standards change
120773911 | pole | Non-HFTD | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2023-12-07 | 2026-04-06 | Level 3 | Standards change
120774246 | anchor/guy | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2023-01-18 | 2024-04-09 | Level 2 | Standards change
120774530 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2024-04-06 | 2026-04-09 | Level 3 | Standards change
120785815 | other | HFTD Tier 3 | Transmission | 2021-04-10 | 2023-04-10 | Level 3 | F | 2024-04-06 | 2026-04-10 | Level 3 | Standards change
120785880 | anchor/guy | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2023-11-16 | 2026-04-07 | Level 3 | Standards change
120786035 | anchor/guy | Non-HFTD | Transmission | 2021-04-10 | 2022-04-10 | Level 2 | E | 2024-06-17 | 2026-04-10 | Level 3 | GO 165 Inspection
120786374 | pole | Non-HFTD | Transmission | 2021-04-10 | 2023-04-10 | Level 3 | F | 2024-01-02 | 2026-04-10 | Level 3 | Standards change
120786589 | other | Non-HFTD | Transmission | 2021-04-10 | 2023-04-10 | Level 3 | F | 2024-04-06 | 2026-04-10 | Level 3 | Standards change
120786628 | insulator and brushing | Non-HFTD | Transmission | 2021-04-10 | 2022-04-10 | Level 2 | E | 2024-08-22 | 2024-04-10 | Level 2 | Field Safety Reassessment
120786911 | pole | Non-HFTD | Transmission | 2021-04-10 | 2023-04-10 | Level 3 | F | 2024-01-02 | 2026-04-10 | Level 3 | Standards change
120787074 | pole | HFTD Tier 2 | Transmission | 2021-04-10 | 2023-04-10 | Level 3 | F | 2024-03-11 | 2026-04-10 | Level 3 | GO 165 Inspection
120787127 | anchor/guy | Non-HFTD | Transmission | 2021-04-10 | 2022-04-10 | Level 2 | E | 2024-10-17 | 2026-04-10 | Level 3 | GO 165 Inspection
120787213 | insulator and brushing | Non-HFTD | Transmission | 2021-04-10 | 2022-04-10 | Level 2 | E | 2023-01-20 | 2026-04-10 | Level 3 | Standards change
120787392 | other | Non-HFTD | Transmission | 2021-04-10 | 2022-04-10 | Level 2 | E | 2023-01-27 | 2026-04-10 | Level 3 | Standards change
120787874 | insulator and brushing | Non-HFTD | Transmission | 2021-04-10 | 2022-04-10 | Level 2 | E | 2024-08-19 | 2024-04-10 | Level 2 | GO 165 Inspection
120791653 | pole | Non-HFTD | Transmission | 2021-04-11 | 2026-04-11 | Level 2 | E | 2024-10-10 | 2024-04-11 | Level 2 | GO 165 Inspection
120793342 | pole | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-12-27 | 2026-04-12 | Level 3 | Standards change
120793532 | pole | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-01-31 | 2026-04-12 | Level 3 | Standards change
120793704 | anchor/guy | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2024-11-24 | 2024-04-12 | Level 2 | Field Safety Reassessment
120794034 | anchor/guy | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2023-03-31 | 2026-04-12 | Level 3 | Standards change
120795078 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-11-14 | 2026-04-12 | Level 3 | GO 165 Inspection
120795482 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-12-27 | 2026-04-12 | Level 3 | Standards change
120795590 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-04-06 | 2026-04-12 | Level 3 | Standards change
120795966 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-04-06 | 2026-04-12 | Level 3 | Standards change
120796007 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-04-06 | 2026-04-12 | Level 3 | Standards change
120796008 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-01-18 | 2026-04-12 | Level 3 | Standards change
120796148 | pole | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2024-11-06 | 2024-04-12 | Level 2 | Field Safety Reassessment
120796180 | pole | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-01-31 | 2026-04-12 | Level 3 | Standards change
120796296 | other | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2024-11-04 | 2024-04-12 | Level 2 | GO 165 Inspection
120796620 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-12-27 | 2026-04-12 | Level 3 | Standards change
120798053 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-01-05 | 2026-04-12 | Level 3 | Standards change
120798887 | other | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2024-10-08 | 2026-04-09 | Level 3 | GO 165 Inspection
120799453 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-04-06 | 2026-04-12 | Level 3 | Standards change
120801304 | pole | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2023-02-07 | 2024-04-12 | Level 2 | Standards change
120801656 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-01-09 | 2026-04-12 | Level 3 | Standards change
120804024 | pole | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2023-01-18 | 2024-04-13 | Level 2 | Standards change
120804232 | anchor/guy | Non-HFTD | Transmission | 2021-04-06 | 2022-04-06 | Level 2 | E | 2023-01-13 | 2026-04-06 | Level 3 | Standards change
120804275 | other | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-11-22 | 2024-04-13 | Level 2 | Field Safety Reassessment
120805045 | other | Non-HFTD | Transmission | 2021-04-13 | 2023-04-13 | Level 3 | F | 2023-12-15 | 2026-04-13 | Level 3 | Standards change
120805428 | other | Non-HFTD | Transmission | 2021-04-13 | 2023-04-13 | Level 3 | F | 2024-04-06 | 2026-04-13 | Level 3 | Standards change
120805540 | pole | HFTD Tier 2 | Transmission | 2021-04-06 | 2023-04-06 | Level 3 | F | 2024-03-11 | 2026-04-06 | Level 3 | GO 165 Inspection
120805815 | other | Non-HFTD | Transmission | 2021-04-13 | 2023-04-13 | Level 3 | F | 2023-12-29 | 2026-04-13 | Level 3 | Standards change
120806964 | other | Non-HFTD | Transmission | 2021-04-13 | 2023-04-13 | Level 3 | F | 2024-04-06 | 2026-04-13 | Level 3 | Standards change
120807316 | crossarm | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-10-03 | 2024-04-13 | Level 2 | Field Safety Reassessment
120807744 | insulator and brushing | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2023-01-24 | 2024-04-13 | Level 2 | Standards change
120811974 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-08-16 | 2024-04-14 | Level 2 | GO 165 Inspection
120812142 | anchor/guy | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-11-13 | 2026-04-14 | Level 3 | GO 165 Inspection
120812227 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-11-04 | 2024-04-14 | Level 2 | Field Safety Reassessment
120812317 | other | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2023-12-27 | 2026-04-14 | Level 3 | Standards change
120812660 | other | Non-HFTD | Transmission | 2021-04-05 | 2023-04-05 | Level 3 | F | 2024-03-06 | 2026-04-05 | Level 3 | GO 165 Inspection
120812807 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-24 | 2024-04-14 | Level 2 | Standards change
120812941 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-11-04 | 2024-04-14 | Level 2 | Field Safety Reassessment
120813209 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-17 | 2024-04-14 | Level 2 | Standards change
120813644 | insulator and brushing | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2024-10-29 | 2024-04-07 | Level 2 | GO 165 Inspection
120813646 | insulator and brushing | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2024-10-29 | 2024-04-07 | Level 2 | GO 165 Inspection
120813972 | pole | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-12-13 | 2024-04-14 | Level 2 | Field Safety Reassessment
120813990 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-24 | 2024-04-14 | Level 2 | Standards change
120814191 | pole | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-01-03 | 2026-04-14 | Level 3 | Standards change
120814236 | pole | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-11-06 | 2024-04-14 | Level 2 | Field Safety Reassessment
120814654 | other | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2023-02-13 | 2026-04-14 | Level 3 | Standards change
120814735 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-25 | 2026-04-14 | Level 3 | Standards change
120814966 | anchor/guy | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-12 | 2026-04-14 | Level 3 | Standards change
120815303 | pole | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-01-03 | 2026-04-14 | Level 3 | Standards change
120815354 | other | Non-HFTD | Transmission | 2021-04-08 | 2022-04-08 | Level 2 | E | 2024-04-04 | 2024-04-08 | Level 2 | GO 165 Inspection
120815475 | other | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-09-28 | 2026-04-14 | Level 3 | GO 165 Inspection
120815692 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-17 | 2024-04-14 | Level 2 | Standards change
120815874 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-09-23 | 2024-04-14 | Level 2 | GO 165 Inspection
120816754 | pole | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2023-02-10 | 2026-04-14 | Level 3 | Standards change
120817609 | splice | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-10-20 | 2024-04-14 | Level 2 | Standards change
120817693 | splice | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-10-20 | 2024-04-14 | Level 2 | Standards change
120819249 | pole | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-01-03 | 2026-04-15 | Level 3 | Standards change
120819286 | other | Non-HFTD | Transmission | 2021-04-14 | 2024-04-14 | Level 2 | E | 2024-06-20 | 2022-04-14 | Level 2 | GO 165 Inspection
120819821 | pole | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-01-03 | 2026-04-15 | Level 3 | Standards change
120819825 | anchor/guy | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-04-04 | 2026-04-15 | Level 3 | Standards change
120820294 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-09-23 | 2024-04-15 | Level 2 | GO 165 Inspection
120820437 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-09-23 | 2024-04-15 | Level 2 | GO 165 Inspection
120820557 | pole | Non-HFTD | Transmission | 2021-04-14 | 2024-04-13 | Level 2 | E | 2024-10-05 | 2022-04-13 | Level 2 | GO 165 Inspection
120820573 | pole | HFTD Tier 3 | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-06-10 | 2026-04-14 | Level 3 | GO 165 Inspection
120820744 | insulator and brushing | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2024-12-24 | 2024-04-09 | Level 2 | Field Safety Reassessment
120820758 | pole | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-11-18 | 2026-04-14 | Level 3 | GO 165 Inspection
120820806 | pole | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-01-23 | 2024-04-15 | Level 2 | Standards change
120820836 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-01-23 | 2024-04-15 | Level 2 | Standards change
120820838 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-09-27 | 2022-04-15 | Level 2 | GO 165 Inspection
120821223 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-04-06 | 2026-04-15 | Level 3 | Standards change
120821410 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-04-09 | 2026-04-15 | Level 3 | GO 165 Inspection
120821956 | pole | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-11-13 | 2026-04-14 | Level 3 | GO 165 Inspection
120822006 | splice | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-10-20 | 2024-04-14 | Level 2 | Standards change
120822007 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-01-19 | 2026-04-15 | Level 3 | Standards change
120822174 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-04-06 | 2026-04-15 | Level 3 | Standards change
120822205 | other | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-11-20 | 2022-04-15 | Level 2 | GO 165 Inspection
120822313 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-10-20 | 2024-04-14 | Level 2 | Standards change
120822316 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-08 | 2024-04-15 | Level 2 | Standards change
120822459 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-01-25 | 2024-04-14 | Level 2 | Standards change
120824167 | splice | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-10-07 | 2024-04-15 | Level 2 | GO 165 Inspection
120824216 | pole | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-12-11 | 2024-04-15 | Level 2 | Field Safety Reassessment
120824260 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-11-14 | 2024-04-15 | Level 2 | Field Safety Reassessment
120824263 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2023-12-27 | 2026-04-15 | Level 3 | Standards change
120827078 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-08 | 2024-04-15 | Level 2 | Standards change
120827469 | pole | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2023-02-09 | 2026-04-15 | Level 3 | Standards change
120827679 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-01-09 | 2026-04-15 | Level 3 | Standards change
120827803 | pole | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-11-26 | 2024-04-15 | Level 2 | Field Safety Reassessment
120828121 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-04-06 | 2026-04-16 | Level 3 | Standards change
120828368 | pole | HFTD Tier 2 | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-04-29 | 2026-04-16 | Level 3 | GO 165 Inspection
120828787 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-10-07 | 2024-04-14 | Level 2 | GO 165 Inspection
120829008 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-01-22 | 2026-04-16 | Level 3 | Standards change
120829026 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-04-06 | 2026-04-16 | Level 3 | Standards change
120829084 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-01-22 | 2026-04-16 | Level 3 | Standards change
120829148 | other | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2024-06-20 | 2024-04-16 | Level 2 | GO 165 Inspection
120830255 | other | HFTD Tier 2 | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-04-06 | 2026-04-16 | Level 3 | Standards change
120831411 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-04-26 | 2026-04-16 | Level 3 | GO 165 Inspection
120831798 | splice | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2023-10-20 | 2024-04-16 | Level 2 | Standards change
120831853 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-04-06 | 2026-04-16 | Level 3 | Standards change
120832546 | other | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2024-09-24 | 2024-04-15 | Level 2 | GO 165 Inspection
120833075 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-01-09 | 2026-04-16 | Level 3 | Standards change
120833125 | anchor/guy | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2023-10-20 | 2026-04-16 | Level 3 | Standards change
120833213 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2024-10-07 | 2026-04-09 | Level 3 | GO 165 Inspection
120833231 | other | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2024-04-06 | 2026-04-17 | Level 3 | Standards change
120833358 | insulator and brushing | Non-HFTD | Transmission | 2021-04-09 | 2022-04-09 | Level 2 | E | 2024-12-17 | 2024-04-09 | Level 2 | Field Safety Reassessment
120833382 | anchor/guy | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-04-08 | 2026-04-17 | Level 3 | GO 165 Inspection
120833391 | other | Non-HFTD | Transmission | 2021-04-09 | 2023-04-09 | Level 3 | F | 2024-03-04 | 2026-04-09 | Level 3 | GO 165 Inspection
120833505 | insulator and brushing | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2023-10-20 | 2024-04-17 | Level 2 | Standards change
120833573 | insulator and brushing | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2023-10-20 | 2024-04-17 | Level 2 | Standards change
120833647 | insulator and brushing | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-07-24 | 2024-04-17 | Level 2 | GO 165 Inspection
120833741 | insulator and brushing | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-07-25 | 2024-04-17 | Level 2 | GO 165 Inspection
120833742 | insulator and brushing | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-07-25 | 2024-04-17 | Level 2 | GO 165 Inspection
120833791 | other | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2024-01-08 | 2026-04-17 | Level 3 | Standards change
120834165 | other | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2023-12-26 | 2026-04-17 | Level 3 | Standards change
120834271 | pole | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-12-18 | 2024-04-17 | Level 2 | Field Safety Reassessment
120834407 | anchor/guy | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2023-03-02 | 2026-04-17 | Level 3 | Standards change
120834533 | crossarm | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-12-18 | 2024-04-17 | Level 2 | Field Safety Reassessment
120834789 | anchor/guy | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2024-08-13 | 2024-04-17 | Level 2 | GO 165 Inspection
120835188 | crossarm | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2023-03-08 | 2024-04-17 | Level 2 | Standards change
120835723 | splice | Non-HFTD | Transmission | 2021-04-17 | 2022-04-17 | Level 2 | E | 2023-10-19 | 2024-04-17 | Level 2 | Standards change
120835776 | other | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2023-12-27 | 2026-04-17 | Level 3 | Standards change
120835783 | pole | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2024-01-09 | 2026-04-17 | Level 3 | Standards change
120838037 | other | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2024-04-26 | 2026-04-17 | Level 3 | GO 165 Inspection
120838070 | other | Non-HFTD | Transmission | 2021-04-17 | 2023-04-17 | Level 3 | F | 2024-04-26 | 2026-04-17 | Level 3 | GO 165 Inspection
120839720 | anchor/guy | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-01-17 | 2026-04-14 | Level 3 | Standards change
120840947 | other | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2023-02-08 | 2024-04-12 | Level 2 | Standards change
120841016 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2024-04-06 | 2026-04-12 | Level 3 | Standards change
120841275 | other | Non-HFTD | Transmission | 2021-04-12 | 2024-04-12 | Level 2 | E | 2024-11-15 | 2022-04-12 | Level 2 | GO 165 Inspection
120841783 | other | HFTD Tier 2 | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-04-30 | 2026-04-19 | Level 3 | GO 165 Inspection
120841825 | other | Non-HFTD | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-04-06 | 2026-04-19 | Level 3 | Standards change
120842627 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-12-27 | 2026-04-12 | Level 3 | Standards change
120843662 | other | Non-HFTD | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-05-09 | 2026-04-19 | Level 3 | GO 165 Inspection
120843752 | other | Non-HFTD | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-07-22 | 2026-04-19 | Level 3 | GO 165 Inspection
120844858 | insulator and brushing | Non-HFTD | Transmission | 2021-04-19 | 2022-04-19 | Level 2 | E | 2023-10-19 | 2024-04-19 | Level 2 | Standards change
120845668 | other | Non-HFTD | Transmission | 2021-04-19 | 2022-04-19 | Level 2 | E | 2024-01-19 | 2024-04-19 | Level 2 | Standards change
120848153 | other | Non-HFTD | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2023-12-27 | 2026-04-19 | Level 3 | Standards change
120848163 | pole | Non-HFTD | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-01-09 | 2026-04-19 | Level 3 | Standards change
120848525 | crossarm | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-09-25 | 2024-04-20 | Level 2 | GO 165 Inspection
120848618 | crossarm | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-09-25 | 2024-04-20 | Level 2 | GO 165 Inspection
120848742 | pole | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-12-09 | 2024-04-20 | Level 2 | Field Safety Reassessment
120849033 | anchor/guy | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2023-03-31 | 2026-04-20 | Level 3 | Standards change
120849229 | other | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-08-30 | 2026-04-20 | Level 3 | GO 165 Inspection
120849668 | pole | Non-HFTD | Transmission | 2021-04-20 | 2024-04-20 | Level 2 | E | 2024-10-02 | 2022-04-20 | Level 2 | Field Safety Reassessment
120849838 | anchor/guy | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2023-10-19 | 2026-04-20 | Level 3 | Standards change
120850366 | pole | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-10-04 | 2024-04-20 | Level 2 | GO 165 Inspection
120850476 | crossarm | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-12-13 | 2024-04-20 | Level 2 | Field Safety Reassessment
120850500 | anchor/guy | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-01-25 | 2026-04-13 | Level 3 | Standards change
120851068 | other | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2024-06-14 | 2022-04-12 | Level 2 | Field Safety Reassessment
120851795 | pole | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2022-12-14 | 2024-04-20 | Level 2 | Standards change
120852414 | other | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2023-01-25 | 2026-04-20 | Level 3 | Standards change
120852913 | pole | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2022-12-13 | 2024-04-20 | Level 2 | Standards change
120853408 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-04-06 | 2026-04-20 | Level 3 | Standards change
120854371 | other | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2023-10-19 | 2026-04-20 | Level 3 | Standards change
120857869 | pole | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2023-10-19 | 2026-04-20 | Level 3 | Standards change
120858221 | other | HFTD Tier 2 | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-05-24 | 2026-04-21 | Level 3 | GO 165 Inspection
120858445 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2023-10-26 | 2026-04-21 | Level 3 | Standards change
120858518 | insulator and brushing | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-08-30 | 2024-04-21 | Level 2 | GO 165 Inspection
120858918 | pole | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-10-02 | 2024-04-21 | Level 2 | Field Safety Reassessment
120859714 | other | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2023-02-10 | 2024-04-13 | Level 2 | Standards change
120859716 | other | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-11-18 | 2024-04-13 | Level 2 | GO 165 Inspection
120860098 | crossarm | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2022-12-15 | 2024-04-21 | Level 2 | Standards change
120860134 | other | Non-HFTD | Transmission | 2021-04-12 | 2023-04-12 | Level 3 | F | 2023-02-06 | 2026-04-12 | Level 3 | Standards change
120860160 | other | HFTD Tier 2 | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-05-31 | 2026-04-21 | Level 3 | GO 165 Inspection
120860202 | pole | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-12-13 | 2024-04-21 | Level 2 | Field Safety Reassessment
120860872 | anchor/guy | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-01-09 | 2026-04-20 | Level 3 | Standards change
120861480 | pole | HFTD Tier 3 | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-04-04 | 2026-04-21 | Level 3 | GO 165 Inspection
120862082 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-04-06 | 2026-04-21 | Level 3 | Standards change
120863465 | pole | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-01-09 | 2026-04-21 | Level 3 | Standards change
120863495 | pole | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-11-27 | 2024-04-21 | Level 2 | Field Safety Reassessment
120864030 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-09-05 | 2026-04-21 | Level 3 | GO 165 Inspection
120864611 | other | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2024-10-17 | 2024-04-22 | Level 2 | GO 165 Inspection
120865342 | pole | HFTD Tier 3 | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-03-18 | 2026-04-19 | Level 3 | GO 165 Inspection
120865630 | pole | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2024-01-04 | 2026-04-22 | Level 3 | Standards change
120866281 | pole | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2024-09-16 | 2026-04-22 | Level 3 | GO 165 Inspection
120866291 | pole | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2024-10-07 | 2024-04-22 | Level 2 | GO 165 Inspection
120866357 | crossarm | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2022-12-15 | 2024-04-22 | Level 2 | Standards change
120866820 | pole | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2024-11-13 | 2024-04-22 | Level 2 | Field Safety Reassessment
120867076 | anchor/guy | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2024-01-18 | 2026-04-22 | Level 3 | Standards change
120867298 | other | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2024-08-26 | 2026-04-22 | Level 3 | GO 165 Inspection
120867840 | anchor/guy | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2024-11-05 | 2024-04-22 | Level 2 | Field Safety Reassessment
120868128 | other | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-11-26 | 2024-04-21 | Level 2 | Field Safety Reassessment
120872131 | pole | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2023-01-30 | 2026-04-20 | Level 3 | Standards change
120872579 | pole | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-01-04 | 2026-04-23 | Level 3 | Standards change
120872936 | other | HFTD Tier 3 | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-05-31 | 2026-04-23 | Level 3 | GO 165 Inspection
120873152 | crossarm | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-11-15 | 2024-04-23 | Level 2 | Field Safety Reassessment
120873212 | other | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2023-10-18 | 2024-04-23 | Level 2 | Standards change
120873244 | pole | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-01-04 | 2026-04-23 | Level 3 | Standards change
120873498 | other | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-04-06 | 2026-04-23 | Level 3 | Standards change
120873760 | pole | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-05-20 | 2024-04-23 | Level 2 | Field Safety Reassessment
120874234 | anchor/guy | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2023-10-18 | 2026-04-22 | Level 3 | Standards change
120874649 | insulator and brushing | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-11-18 | 2024-04-23 | Level 2 | Field Safety Reassessment
120874932 | other | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-08-26 | 2024-04-23 | Level 2 | GO 165 Inspection
120875117 | anchor/guy | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2023-10-18 | 2026-04-23 | Level 3 | Standards change
120875227 | other | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-08-26 | 2024-04-23 | Level 2 | GO 165 Inspection
120875290 | other | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-04-06 | 2026-04-23 | Level 3 | Standards change
120875360 | splice | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-07-16 | 2024-04-23 | Level 2 | GO 165 Inspection
120875692 | other | HFTD Tier 2 | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-05-28 | 2026-04-23 | Level 3 | GO 165 Inspection
120876949 | other | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-08-29 | 2026-04-23 | Level 3 | GO 165 Inspection
120877721 | other | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-04-06 | 2026-04-23 | Level 3 | Standards change
120878395 | pole | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2022-12-14 | 2024-04-23 | Level 2 | Standards change
120878500 | pole | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-11-13 | 2024-04-24 | Level 2 | Field Safety Reassessment
120878520 | anchor/guy | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2023-10-18 | 2026-04-23 | Level 3 | Standards change
120878524 | anchor/guy | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2023-10-18 | 2026-04-23 | Level 3 | Standards change
120878626 | insulator and brushing | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-11-15 | 2024-04-24 | Level 2 | Field Safety Reassessment
120878719 | pole | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-11-18 | 2024-04-24 | Level 2 | Field Safety Reassessment
120879016 | other | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2024-10-08 | 2024-04-24 | Level 2 | GO 165 Inspection
120879858 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-08-27 | 2024-04-24 | Level 2 | GO 165 Inspection
120879964 | anchor/guy | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-11-05 | 2024-04-24 | Level 2 | Field Safety Reassessment
120880661 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-08-27 | 2024-04-24 | Level 2 | GO 165 Inspection
120880755 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-08-28 | 2026-04-24 | Level 3 | GO 165 Inspection
120883033 | pole | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-12-09 | 2021-10-26 | Level 2 | Field Safety Reassessment
120884970 | conductor | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F |  | 2026-04-26 | Level 3
120885052 | pole | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-12-11 | 2024-04-26 | Level 2 | Field Safety Reassessment
120885153 | other | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-04-06 | 2026-04-26 | Level 3 | Standards change
120885387 | insulator and brushing | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-10-08 | 2024-04-26 | Level 2 | Field Safety Reassessment
120886044 | other | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-04-06 | 2026-04-26 | Level 3 | Standards change
120887162 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-01-10 | 2026-04-26 | Level 3 | Standards change
120887164 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-01-10 | 2026-04-26 | Level 3 | Standards change
120887299 | other | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-04-06 | 2026-04-26 | Level 3 | Standards change
120887406 | other | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2023-09-18 | 2026-04-26 | Level 3 | Standards change
120887551 | anchor/guy | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-01-22 | 2026-04-26 | Level 3 | Standards change
120887935 | other | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-08-28 | 2026-04-26 | Level 3 | GO 165 Inspection
120887936 | other | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-08-29 | 2024-04-26 | Level 2 | GO 165 Inspection
120888095 | other | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-08-29 | 2026-04-26 | Level 3 | GO 165 Inspection
120888145 | other | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-08-31 | 2024-04-26 | Level 2 | GO 165 Inspection
120888247 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-04-06 | 2026-04-27 | Level 3 | Standards change
120888700 | other | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-08-29 | 2024-04-27 | Level 2 | GO 165 Inspection
120888743 | other | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-08-29 | 2024-04-27 | Level 2 | GO 165 Inspection
120889303 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-04-06 | 2026-04-27 | Level 3 | Standards change
120890566 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-17 | 2026-04-27 | Level 3 | Standards change
120890742 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-04-06 | 2026-04-27 | Level 3 | Standards change
120891096 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-04-06 | 2026-04-27 | Level 3 | Standards change
120891097 | anchor/guy | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-17 | 2026-04-27 | Level 3 | Standards change
120892007 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-12-31 | 2024-04-27 | Level 2 | Field Safety Reassessment
120892352 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-12-26 | 2024-04-27 | Level 2 | Field Safety Reassessment
120892462 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-17 | 2026-04-27 | Level 3 | Standards change
120892534 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-11-22 | 2024-04-27 | Level 2 | Field Safety Reassessment
120892594 | other | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2023-02-10 | 2024-04-13 | Level 2 | Standards change
120893728 | anchor/guy | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-09-11 | 2026-04-28 | Level 3 | GO 165 Inspection
120894280 | insulator and brushing | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-09-24 | 2024-04-28 | Level 2 | GO 165 Inspection
120894528 | pole | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-01-04 | 2026-04-23 | Level 3 | Standards change
120894571 | pole | Non-HFTD | Transmission | 2021-04-23 | 2023-04-23 | Level 3 | F | 2024-01-04 | 2026-04-23 | Level 3 | Standards change
120894584 | pole | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2023-12-27 | 2026-04-24 | Level 3 | Standards change
120894590 | pole | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2023-12-27 | 2026-04-24 | Level 3 | Standards change
120894597 | pole | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2024-01-04 | 2026-04-24 | Level 3 | Standards change
120894670 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-01-04 | 2026-04-26 | Level 3 | Standards change
120894684 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-01-04 | 2026-04-26 | Level 3 | Standards change
120894685 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2023-12-27 | 2026-04-26 | Level 3 | Standards change
120894720 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120894723 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120894726 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120894733 | pole | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-01-04 | 2026-04-28 | Level 3 | Standards change
120894734 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120894735 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120894739 | pole | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-01-05 | 2026-04-28 | Level 3 | Standards change
120895373 | anchor/guy | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2023-10-09 | 2026-04-28 | Level 3 | Standards change
120895505 | pole | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2023-02-08 | 2026-04-15 | Level 3 | Standards change
120895563 | pole | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-12-09 | 2022-04-28 | Level 2 | Field Safety Reassessment
120895865 | pole | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-12-09 | 2024-04-28 | Level 2 | Field Safety Reassessment
120896020 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-08 | 2024-04-15 | Level 2 | Standards change
120896346 | other | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-09-05 | 2024-04-28 | Level 2 | GO 165 Inspection
120896645 | pole | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-01-05 | 2026-04-28 | Level 3 | Standards change
120896763 | other | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-11-18 | 2022-04-15 | Level 2 | GO 165 Inspection
120896766 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-10 | 2026-04-15 | Level 3 | Standards change
120897315 | other | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-06-17 | 2024-04-28 | Level 2 | Field Safety Reassessment
120897778 | pole | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-12-10 | 2024-04-28 | Level 2 | Field Safety Reassessment
120898738 | anchor/guy | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-03-08 | 2024-04-27 | Level 2 | Standards change
120898838 | anchor/guy | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120898845 | anchor/guy | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2023-03-08 | 2024-04-28 | Level 2 | Standards change
120898846 | other | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2023-03-08 | 2024-04-28 | Level 2 | Standards change
120898848 | anchor/guy | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-10-09 | 2026-04-27 | Level 3 | Standards change
120899187 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-01-17 | 2026-04-26 | Level 3 | Standards change
120899193 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2024-01-17 | 2026-04-26 | Level 3 | Standards change
120899779 | other | Non-HFTD | Transmission | 2021-04-29 | 2024-04-29 | Level 2 | E | 2024-12-09 | 2026-04-29 | Level 3 | Field Safety Reassessment
120899899 | other | Non-HFTD | Transmission | 2021-04-29 | 2023-04-29 | Level 3 | F | 2024-04-09 | 2026-04-29 | Level 3 | GO 165 Inspection
120900654 | other | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2023-12-15 | 2026-04-14 | Level 3 | Standards change
120900775 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-11-14 | 2024-04-14 | Level 2 | GO 165 Inspection
120900792 | other | Non-HFTD | Transmission | 2021-04-29 | 2023-04-29 | Level 3 | F | 2024-08-23 | 2026-04-29 | Level 3 | GO 165 Inspection
120900857 | pole | HFTD Tier 3 | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2024-04-16 | 2026-04-14 | Level 3 | GO 165 Inspection
120901054 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-08 | 2024-04-15 | Level 2 | Standards change
120901221 | other | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-12-10 | 2024-04-29 | Level 2 | Field Safety Reassessment
120901231 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-11-18 | 2024-04-15 | Level 2 | GO 165 Inspection
120903050 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-09 | 2026-04-15 | Level 3 | Standards change
120903287 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-09-18 | 2024-04-14 | Level 2 | Field Safety Reassessment
120903393 | insulator and brushing | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-09-06 | 2024-04-29 | Level 2 | GO 165 Inspection
120903410 | crossarm | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2022-12-19 | 2026-04-29 | Level 3 | Standards change
120903529 | insulator and brushing | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-09-06 | 2024-04-29 | Level 2 | GO 165 Inspection
120904114 | other | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-09-09 | 2024-04-29 | Level 2 | GO 165 Inspection
120904193 | insulator and brushing | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-12-09 | 2022-04-29 | Level 2 | GO 165 Inspection
120904694 | other | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2023-02-16 | 2024-04-29 | Level 2 | Standards change
120905326 | crossarm | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2023-06-08 | 2024-04-29 | Level 2 | GO 165 Inspection
120907053 | other | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-08-29 | 2026-04-29 | Level 3 | GO 165 Inspection
120907104 | other | Non-HFTD | Transmission | 2021-04-30 | 2024-04-30 | Level 2 | E | 2024-12-10 | 2026-04-30 | Level 3 | Field Safety Reassessment
120907118 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-11-18 | 2024-04-15 | Level 2 | GO 165 Inspection
120907229 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-10-10 | 2024-04-15 | Level 2 | Standards change
120907277 | other | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-04-06 | 2026-04-30 | Level 3 | Standards change
120907436 | pole | Non-HFTD | Transmission | 2021-04-30 | 2024-04-30 | Level 2 | E | 2024-10-03 | 2022-04-30 | Level 2 | Field Safety Reassessment
120908317 | pole | Non-HFTD | Transmission | 2021-04-29 | 2023-04-29 | Level 3 | F | 2023-12-28 | 2026-04-29 | Level 3 | Standards change
120908459 | other | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-04-06 | 2026-04-30 | Level 3 | Standards change
120908826 | other | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-04-06 | 2026-04-30 | Level 3 | Standards change
120909152 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-12-10 | 2024-04-30 | Level 2 | Field Safety Reassessment
120909297 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2023-02-09 | 2024-04-14 | Level 2 | Standards change
120909458 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-09-09 | 2024-04-30 | Level 2 | GO 165 Inspection
120909984 | pole | Non-HFTD | Transmission | 2021-04-30 | 2024-04-30 | Level 2 | E | 2024-12-10 | 2022-04-30 | Level 2 | Field Safety Reassessment
120910432 | anchor/guy | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-01-12 | 2026-04-30 | Level 3 | Standards change
120911046 | pole | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-01-09 | 2026-04-30 | Level 3 | Standards change
120911478 | other | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-04-06 | 2026-04-30 | Level 3 | Standards change
120912060 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-06-25 | 2022-04-30 | Level 2 | GO 165 Inspection
120912206 | pole | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-11-20 | 2024-04-30 | Level 2 | Field Safety Reassessment
120912309 | other | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2023-08-01 | 2026-05-01 | Level 3 | Standards change
120912355 | other | Non-HFTD | Transmission | 2021-04-30 | 2024-04-30 | Level 2 | E | 2023-10-11 | 2022-04-30 | Level 2 | Standards change
120912575 | other | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2023-11-30 | 2026-05-01 | Level 3 | Standards change
120913194 | anchor/guy | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-10-10 | 2026-04-15 | Level 3 | Standards change
120913222 | other | Non-HFTD | Transmission | 2021-05-01 | 2022-05-01 | Level 2 | E | 2024-12-09 | 2024-05-01 | Level 2 | Field Safety Reassessment
120913619 | other | HFTD Tier 2 | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2023-06-15 | 2026-05-01 | Level 3 | Standards change
120913754 | pole | Non-HFTD | Transmission | 2021-05-01 | 2022-05-01 | Level 2 | E | 2023-04-28 | 2024-05-01 | Level 2 | GO 165 Inspection
120913763 | pole | Non-HFTD | Transmission | 2021-05-01 | 2022-05-01 | Level 2 | E | 2023-04-28 | 2024-05-01 | Level 2 | GO 165 Inspection
120913843 | other | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2023-12-01 | 2026-05-01 | Level 3 | Standards change
120913985 | pole | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2024-01-10 | 2026-05-01 | Level 3 | Standards change
120913986 | pole | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2024-01-10 | 2026-05-01 | Level 3 | Standards change
120914001 | pole | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2023-01-25 | 2026-05-01 | Level 3 | Standards change
120914002 | pole | Non-HFTD | Transmission | 2021-05-01 | 2023-05-01 | Level 3 | F | 2024-01-05 | 2026-05-01 | Level 3 | Standards change
120915379 | other | Non-HFTD | Transmission | 2021-05-01 | 2022-05-01 | Level 2 | E | 2024-09-05 | 2024-05-01 | Level 2 | GO 165 Inspection
120919857 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-12-20 | 2024-05-03 | Level 2 | Field Safety Reassessment
120920212 | pole | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-01-05 | 2026-05-03 | Level 3 | Standards change
120920293 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2023-11-30 | 2026-05-03 | Level 3 | Standards change
120920418 | conductor | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-10-07 | 2026-05-03 | Level 3 | GO 165 Inspection
120920454 | other | Non-HFTD | Transmission | 2021-04-14 | 2022-04-14 | Level 2 | E | 2024-11-18 | 2024-04-14 | Level 2 | GO 165 Inspection
120920890 | pole | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2023-02-08 | 2024-04-22 | Level 2 | Standards change
120921119 | pole | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2024-01-19 | 2026-04-22 | Level 3 | Standards change
120921557 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-08-21 | 2024-05-03 | Level 2 | Field Safety Reassessment
120921914 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-09 | 2024-04-15 | Level 2 | Standards change
120922158 | anchor/guy | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2023-10-10 | 2026-05-03 | Level 3 | Standards change
120922295 | anchor/guy | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-07-10 | 2026-05-03 | Level 3 | GO 165 Inspection
120922593 | other | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-02-09 | 2024-04-15 | Level 2 | Standards change
120922708 | anchor/guy | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2023-03-08 | 2026-05-03 | Level 3 | Standards change
120923128 | insulator and brushing | Non-HFTD | Transmission | 2021-04-14 | 2024-04-14 | Level 2 | E | 2024-10-05 | 2021-10-14 | Level 2 | GO 165 Inspection
120923329 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2023-01-17 | 2024-04-15 | Level 2 | Standards change
120923544 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-11-26 | 2024-04-15 | Level 2 | Field Safety Reassessment
120924079 | pole | Non-HFTD | Transmission | 2021-05-03 | 2024-05-03 | Level 2 | E | 2024-11-20 | 2021-11-03 | Level 2 | Field Safety Reassessment
120924090 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-04-06 | 2026-05-03 | Level 3 | Standards change
120924384 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-12-16 | 2024-05-03 | Level 2 | Field Safety Reassessment
120924648 | pole | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-12-09 | 2024-05-03 | Level 2 | Field Safety Reassessment
120924708 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-09-13 | 2024-05-03 | Level 2 | GO 165 Inspection
120925330 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-01-02 | 2026-05-03 | Level 3 | Standards change
120927125 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-03-09 | 2026-05-04 | Level 3 | Standards change
120927214 | anchor/guy | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-07-10 | 2026-04-15 | Level 3 | GO 165 Inspection
120927334 | anchor/guy | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-01-08 | 2026-04-15 | Level 3 | Standards change
120928395 | pole | Non-HFTD | Transmission | 2021-04-26 | 2023-04-26 | Level 3 | F | 2023-03-08 | 2026-04-26 | Level 3 | Standards change
120928652 | other | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-11-13 | 2022-04-15 | Level 2 | GO 165 Inspection
120928804 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-10-04 | 2026-04-15 | Level 3 | GO 165 Inspection
120929054 | splice | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-02-05 | 2024-05-04 | Level 2 | Standards change
120929389 | insulator and brushing | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-01-17 | 2026-05-04 | Level 3 | Standards change
120929941 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2021-08-10 | 2026-05-04 | Level 3 | Standards change
120930523 | anchor/guy | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-10-11 | 2026-05-04 | Level 3 | Standards change
120930524 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-03-09 | 2026-05-04 | Level 3 | Standards change
120930582 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-01-11 | 2026-04-15 | Level 3 | Standards change
120930626 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-12-16 | 2024-05-04 | Level 2 | Field Safety Reassessment
120930830 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-04-06 | 2026-05-04 | Level 3 | Standards change
120931009 | insulator and brushing | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2022-12-27 | 2024-05-04 | Level 2 | Standards change
120931127 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-09-16 | 2024-05-04 | Level 2 | GO 165 Inspection
120931151 | insulator and brushing | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-09-24 | 2024-04-13 | Level 2 | GO 165 Inspection
120931156 | insulator and brushing | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-09-24 | 2024-04-13 | Level 2 | GO 165 Inspection
120931274 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-09-16 | 2024-05-04 | Level 2 | GO 165 Inspection
120931371 | insulator and brushing | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-01-09 | 2026-05-04 | Level 3 | Standards change
120931754 | insulator and brushing | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-01-18 | 2024-05-04 | Level 2 | Standards change
120931846 | pole | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-01-05 | 2026-05-04 | Level 3 | Standards change
120931999 | anchor/guy | Non-HFTD | Transmission | 2021-05-04 | 2026-05-04 | Level 2 | E | 2024-09-23 | 2022-05-04 | Level 2 | GO 165 Inspection
120932385 | other | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-06-14 | 2022-04-15 | Level 2 | Field Safety Reassessment
120932388 | pole | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2024-12-02 | 2024-04-16 | Level 2 | Field Safety Reassessment
120932683 | pole | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-02-05 | 2026-05-03 | Level 3 | Standards change
120932726 | anchor/guy | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2023-10-11 | 2026-04-16 | Level 3 | Standards change
120934088 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-06-20 | 2024-05-04 | Level 2 | GO 165 Inspection
120934100 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-08-28 | 2024-05-03 | Level 2 | GO 165 Inspection
120934112 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-06-21 | 2024-05-03 | Level 2 | GO 165 Inspection
120934810 | other | Non-HFTD | Transmission | 2021-04-14 | 2024-04-14 | Level 2 | E | 2024-11-14 | 2022-04-14 | Level 2 | GO 165 Inspection
120934813 | other | Non-HFTD | Transmission | 2021-04-15 | 2023-04-15 | Level 3 | F | 2024-01-09 | 2026-04-15 | Level 3 | Standards change
120936423 | pole | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-11-23 | 2024-05-05 | Level 2 | Field Safety Reassessment
120937041 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-10-08 | 2024-05-05 | Level 2 | Field Safety Reassessment
120938032 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-12-04 | 2024-05-05 | Level 2 | Field Safety Reassessment
120938122 | insulator and brushing | Non-HFTD | Transmission | 2021-04-15 | 2022-04-15 | Level 2 | E | 2024-11-18 | 2024-04-15 | Level 2 | GO 165 Inspection
120938155 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-11-24 | 2024-05-05 | Level 2 | GO 165 Inspection
120939342 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-11-20 | 2024-05-05 | Level 2 | Field Safety Reassessment
120941185 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-05-07 | 2024-05-06 | Level 2 | Field Safety Reassessment
120941633 | other | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-09-12 | 2024-05-06 | Level 2 | GO 165 Inspection
120943755 | other | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-12-09 | 2024-05-06 | Level 2 | Field Safety Reassessment
120943775 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-10-22 | 2022-05-06 | Level 2 | GO 165 Inspection
120943982 | anchor/guy | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2023-12-29 | 2026-05-06 | Level 3 | Standards change
120943985 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-12-09 | 2024-05-06 | Level 2 | Field Safety Reassessment
120944024 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2023-03-13 | 2026-05-06 | Level 3 | Standards change
120944294 | conductor | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-12-10 | 2024-05-06 | Level 2 | GO 165 Inspection
120944891 | pole | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2023-10-24 | 2026-05-06 | Level 3 | Standards change
120945178 | crossarm | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-11-20 | 2024-05-06 | Level 2 | Field Safety Reassessment
120945211 | anchor/guy | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2023-10-12 | 2026-05-06 | Level 3 | Standards change
120945266 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2023-01-25 | 2026-05-06 | Level 3 | Standards change
120945293 | pole | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2023-01-25 | 2026-05-06 | Level 3 | Standards change
120945294 | other | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-08-29 | 2026-05-06 | Level 3 | GO 165 Inspection
120945927 | other | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-08-30 | 2024-05-06 | Level 2 | GO 165 Inspection
120945929 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-01-19 | 2024-05-06 | Level 2 | Field Safety Reassessment
120945933 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-08-26 | 2024-05-05 | Level 2 | GO 165 Inspection
120947366 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-12-02 | 2024-05-05 | Level 2 | Field Safety Reassessment
120947605 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-10-12 | 2024-05-03 | Level 2 | Standards change
120948622 | pole | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-11-25 | 2024-05-05 | Level 2 | Field Safety Reassessment
120948629 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-11-25 | 2024-05-06 | Level 2 | Field Safety Reassessment
120948639 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-09-27 | 2024-05-06 | Level 2 | GO 165 Inspection
120948761 | pole | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2023-04-19 | 2024-05-07 | Level 2 | GO 165 Inspection
120948841 | other | Non-HFTD | Transmission | 2021-05-07 | 2023-05-07 | Level 3 | F | 2024-04-06 | 2026-05-07 | Level 3 | Standards change
120949206 | anchor/guy | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2023-10-12 | 2026-05-07 | Level 3 | Standards change
120949267 | insulator and brushing | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2024-10-03 | 2024-05-06 | Level 2 | Field Safety Reassessment
120949738 | anchor/guy | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2023-10-13 | 2026-05-07 | Level 3 | Standards change
120949988 | other | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2023-02-08 | 2024-04-16 | Level 2 | Standards change
120950049 | pole | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2024-12-01 | 2024-05-07 | Level 2 | Field Safety Reassessment
120950082 | pole | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2024-11-26 | 2024-05-07 | Level 2 | Field Safety Reassessment
120950492 | anchor/guy | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2023-10-13 | 2026-05-07 | Level 3 | Standards change
120950783 | pole | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2024-01-17 | 2024-05-07 | Level 2 | Field Safety Reassessment
120951457 | other | Non-HFTD | Transmission | 2021-05-07 | 2023-05-07 | Level 3 | F | 2024-07-10 | 2026-05-07 | Level 3 | GO 165 Inspection
120951590 | pole | Non-HFTD | Transmission | 2021-05-07 | 2023-05-07 | Level 3 | F | 2023-02-13 | 2026-05-07 | Level 3 | Standards change
120952120 | other | Non-HFTD | Transmission | 2021-05-07 | 2023-05-07 | Level 3 | F | 2024-04-06 | 2026-05-07 | Level 3 | Standards change
120952469 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-02-29 | 2026-05-08 | Level 3 | Standards change
120953283 | pole | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-03-30 | 2024-05-08 | Level 2 | Field Safety Reassessment
120953563 | splice | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-09-27 | 2024-05-08 | Level 2 | GO 165 Inspection
120953564 | pole | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-12-01 | 2024-05-08 | Level 2 | Field Safety Reassessment
120953573 | pole | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-12-01 | 2024-05-08 | Level 2 | Field Safety Reassessment
120990423 | other | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2023-02-08 | 2026-05-08 | Level 3 | Standards change
120990927 | anchor/guy | Non-HFTD | Transmission | 2021-05-10 | 2022-05-10 | Level 2 | E | 2023-10-13 | 2026-05-10 | Level 3 | Standards change
121005404 | pole | Non-HFTD | Transmission | 2021-05-10 | 2022-05-10 | Level 2 | E | 2024-01-17 | 2024-05-10 | Level 2 | Field Safety Reassessment
121012771 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2023-12-28 | 2026-05-05 | Level 3 | Standards change
121012776 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-10-13 | 2024-05-05 | Level 2 | Standards change
121013512 | insulator and brushing | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-08-26 | 2024-05-08 | Level 2 | GO 165 Inspection
121029357 | other | Non-HFTD | Transmission | 2021-05-10 | 2023-05-10 | Level 3 | F |  | 2023-05-10 | Level 3
121030921 | anchor/guy | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-08-30 | 2024-05-08 | Level 2 | GO 165 Inspection
121030922 | pole | Non-HFTD | Transmission | 2021-05-08 | 2024-05-06 | Level 2 | E | 2024-08-30 | 2022-05-06 | Level 2 | GO 165 Inspection
121035857 | other | Non-HFTD | Transmission | 2021-05-10 | 2023-05-10 | Level 3 | F | 2024-04-06 | 2026-05-10 | Level 3 | Standards change
121036119 | pole | Non-HFTD | Transmission | 2021-05-10 | 2022-05-10 | Level 2 | E | 2024-01-17 | 2024-05-10 | Level 2 | Field Safety Reassessment
121036759 | pole | Non-HFTD | Transmission | 2021-05-10 | 2022-05-10 | Level 2 | E | 2024-12-01 | 2024-05-10 | Level 2 | Field Safety Reassessment
121043893 | pole | Non-HFTD | Transmission | 2021-05-10 | 2022-05-10 | Level 2 | E | 2024-11-30 | 2024-05-10 | Level 2 | Field Safety Reassessment
121079033 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-09-23 | 2026-04-16 | Level 3 | GO 165 Inspection
121186661 | other | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-08-28 | 2024-05-08 | Level 2 | GO 165 Inspection
121188002 | other | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2024-10-04 | 2024-04-16 | Level 2 | GO 165 Inspection
121188066 | pole | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-08-28 | 2024-05-11 | Level 2 | Field Safety Reassessment
121188283 | insulator and brushing | Non-HFTD | Transmission | 2021-04-12 | 2022-04-12 | Level 2 | E | 2024-10-08 | 2024-04-12 | Level 2 | GO 165 Inspection
121188432 | pole | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-08-28 | 2024-05-11 | Level 2 | Field Safety Reassessment
121188584 | pole | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-01-17 | 2024-05-11 | Level 2 | Field Safety Reassessment
121188735 | anchor/guy | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-07-15 | 2024-05-11 | Level 2 | GO 165 Inspection
121188972 | other | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2023-01-11 | 2024-05-11 | Level 2 | Standards change
121189785 | pole | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-03-19 | 2024-05-11 | Level 2 | Field Safety Reassessment
121189833 | anchor/guy | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-01-25 | 2026-05-11 | Level 3 | Standards change
121190194 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-08-23 | 2026-05-11 | Level 3 | GO 165 Inspection
121190258 | other | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-11-13 | 2022-04-15 | Level 2 | GO 165 Inspection
121190589 | other | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2023-10-16 | 2024-04-20 | Level 2 | Standards change
121190926 | pole | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-01-22 | 2026-05-11 | Level 3 | Standards change
121191354 | anchor/guy | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-09-13 | 2026-05-11 | Level 3 | GO 165 Inspection
121191368 | insulator and brushing | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-08-28 | 2024-05-11 | Level 2 | GO 165 Inspection
121191687 | anchor/guy | Non-HFTD | Transmission | 2021-03-22 | 2022-03-22 | Level 2 | E | 2024-04-03 | 2026-03-22 | Level 3 | GO 165 Inspection
121191850 | pole | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-02-09 | 2024-05-11 | Level 2 | Field Safety Reassessment
121192034 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-04-06 | 2026-04-21 | Level 3 | Standards change
121192039 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-01-09 | 2026-04-21 | Level 3 | Standards change
121192064 | pole | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-07-24 | 2024-04-21 | Level 2 | GO 165 Inspection
121192288 | pole | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2024-02-09 | 2024-05-11 | Level 2 | Field Safety Reassessment
121315969 | other | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-04-06 | 2026-05-12 | Level 3 | Standards change
121316445 | other | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-04-06 | 2026-05-12 | Level 3 | Standards change
121317003 | other | HFTD Tier 2 | Transmission | 2021-05-10 | 2023-05-10 | Level 3 | F | 2024-06-13 | 2026-05-10 | Level 3 | GO 165 Inspection
121317354 | other | Non-HFTD | Transmission | 2021-04-13 | 2022-04-13 | Level 2 | E | 2024-08-19 | 2022-04-13 | Level 2 | GO 165 Inspection
121317976 | pole | Non-HFTD | Transmission | 2020-11-30 | 2021-11-30 | Level 2 | E | 2024-10-22 | 2023-11-30 | Level 2 | Field Safety Reassessment
121318187 | anchor/guy | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-01-11 | 2026-04-20 | Level 3 | Standards change
121318198 | other | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-04-06 | 2026-05-12 | Level 3 | Standards change
121318293 | anchor/guy | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2023-10-17 | 2026-05-12 | Level 3 | Standards change
121318355 | anchor/guy | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2023-10-17 | 2026-05-12 | Level 3 | Standards change
121318462 | other | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-08-30 | 2026-05-12 | Level 3 | GO 165 Inspection
121318698 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-06-20 | 2022-05-12 | Level 2 | GO 165 Inspection
121318705 | pole | Non-HFTD | Transmission | 2021-05-12 | 2024-05-12 | Level 2 | E | 2024-01-17 | 2022-05-12 | Level 2 | Field Safety Reassessment
121318790 | other | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2023-09-26 | 2026-05-12 | Level 3 | Standards change
121319261 | anchor/guy | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2023-10-17 | 2026-05-12 | Level 3 | Standards change
121319362 | pole | Non-HFTD | Transmission | 2021-04-21 | 2024-04-21 | Level 2 | E | 2024-11-07 | 2022-04-21 | Level 2 | Field Safety Reassessment
121319368 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2023-12-04 | 2024-04-16 | Level 2 | Standards change
121319439 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-03-30 | 2024-05-12 | Level 2 | Field Safety Reassessment
121319565 | other | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-04-06 | 2026-05-12 | Level 3 | Standards change
121319585 | insulator and brushing | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-01-23 | 2024-04-21 | Level 2 | Standards change
121320152 | other | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-04-06 | 2026-05-12 | Level 3 | Standards change
121320377 | pole | Non-HFTD | Transmission | 2021-05-12 | 2023-05-12 | Level 3 | F | 2024-10-14 | 2026-05-12 | Level 3 | GO 165 Inspection
121320438 | crossarm | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-01-31 | 2024-05-12 | Level 2 | Field Safety Reassessment
121320524 | insulator and brushing | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2023-02-14 | 2026-05-12 | Level 3 | Standards change
121320639 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-04 | 2026-04-20 | Level 3 | GO 165 Inspection
121320803 | insulator and brushing | Non-HFTD | Transmission | 2021-04-20 | 2022-04-20 | Level 2 | E | 2024-09-04 | 2024-04-20 | Level 2 | GO 165 Inspection
121320865 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-12-01 | 2024-05-12 | Level 2 | Field Safety Reassessment
121321026 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-01-24 | 2024-05-12 | Level 2 | Field Safety Reassessment
121321806 | insulator and brushing | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-09-04 | 2024-04-21 | Level 2 | GO 165 Inspection
121321807 | insulator and brushing | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2024-09-04 | 2024-04-21 | Level 2 | GO 165 Inspection
121321809 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2023-01-30 | 2026-04-20 | Level 3 | Standards change
121321872 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-09-27 | 2024-05-12 | Level 2 | GO 165 Inspection
121321992 | anchor/guy | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-11-27 | 2026-05-12 | Level 3 | GO 165 Inspection
121322147 | insulator and brushing | Non-HFTD | Transmission | 2021-04-20 | 2024-04-20 | Level 2 | E | 2024-09-05 | 2026-04-20 | Level 3 | GO 165 Inspection
121322341 | pole | HFTD Tier 2 | Transmission | 2021-05-12 | 2022-05-12 | Level 3 | F | 2023-06-01 | 2022-05-12 | Level 2 | GO 165 Inspection
121322661 | other | Non-HFTD | Transmission | 2021-04-16 | 2023-04-16 | Level 3 | F | 2024-01-02 | 2026-04-16 | Level 3 | Standards change
121322943 | pole | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2023-12-04 | 2026-04-22 | Level 3 | Standards change
121323023 | other | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2024-04-06 | 2026-04-22 | Level 3 | Standards change
121323027 | other | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2024-04-06 | 2026-04-22 | Level 3 | Standards change
121323797 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-06 | 2026-05-13 | Level 3 | Standards change
121323932 | pole | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2024-11-07 | 2024-05-13 | Level 2 | Field Safety Reassessment
121324272 | conductor | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2024-09-10 | 2024-05-13 | Level 2 | GO 165 Inspection
121324300 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-06 | 2026-05-13 | Level 3 | Standards change
121324565 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-06 | 2026-05-13 | Level 3 | Standards change
121324819 | anchor/guy | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2023-10-17 | 2026-05-13 | Level 3 | Standards change
121324933 | pole | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2024-08-20 | 2024-05-13 | Level 2 | Field Safety Reassessment
121325397 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-06-20 | 2022-05-12 | Level 2 | GO 165 Inspection
121325704 | other | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2023-02-28 | 2024-05-13 | Level 2 | Standards change
121326032 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-06-21 | 2026-05-13 | Level 3 | GO 165 Inspection
121326084 | pole | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2024-06-20 | 2022-05-12 | Level 2 | GO 165 Inspection
121326245 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-06 | 2026-05-13 | Level 3 | Standards change
121326338 | other | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2023-10-17 | 2026-05-13 | Level 3 | Standards change
121326780 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-06 | 2026-05-13 | Level 3 | Standards change
121327412 | anchor/guy | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2023-10-17 | 2026-05-13 | Level 3 | Standards change
121327504 | pole | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2024-12-01 | 2024-05-13 | Level 2 | Field Safety Reassessment
121327972 | pole | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2023-01-23 | 2026-05-13 | Level 3 | Standards change
121328180 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-06 | 2026-05-13 | Level 3 | Standards change
121328451 | splice | Non-HFTD | Transmission | 2021-05-13 | 2022-05-13 | Level 2 | E | 2024-07-12 | 2024-05-13 | Level 2 | GO 165 Inspection
121329387 | other | Non-HFTD | Transmission | 2021-04-22 | 2023-04-22 | Level 3 | F | 2024-04-06 | 2026-04-22 | Level 3 | Standards change
121329802 | other | Non-HFTD | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2023-12-22 | 2026-05-13 | Level 3 | Standards change
121330844 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-04 | 2026-04-20 | Level 3 | GO 165 Inspection
121330954 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-04 | 2026-04-20 | Level 3 | GO 165 Inspection
121331121 | other | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-10-25 | 2024-04-23 | Level 2 | GO 165 Inspection
121331165 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-04 | 2026-04-20 | Level 3 | GO 165 Inspection
121331384 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-05 | 2026-04-20 | Level 3 | GO 165 Inspection
121331566 | other | Non-HFTD | Transmission | 2021-05-14 | 2023-05-14 | Level 3 | F | 2024-01-05 | 2026-05-14 | Level 3 | Standards change
121331572 | pole | Non-HFTD | Transmission | 2021-04-30 | 2024-04-30 | Level 2 | E | 2024-12-09 | 2022-04-30 | Level 2 | Field Safety Reassessment
121331573 | pole | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-12-09 | 2024-04-30 | Level 2 | Field Safety Reassessment
121331574 | pole | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-12-09 | 2024-04-30 | Level 2 | Field Safety Reassessment
121331630 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-02-28 | 2026-04-20 | Level 3 | Standards change
121331894 | insulator and brushing | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2023-01-09 | 2024-04-22 | Level 2 | Standards change
121332063 | anchor/guy | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2023-10-17 | 2026-05-14 | Level 3 | Standards change
121332094 | other | Non-HFTD | Transmission | 2021-05-14 | 2023-05-14 | Level 3 | F | 2024-02-02 | 2026-05-14 | Level 3 | Standards change
121332316 | anchor/guy | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2023-01-30 | 2026-04-23 | Level 3 | Standards change
121332385 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-08-29 | 2024-04-24 | Level 2 | GO 165 Inspection
121332604 | other | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2023-10-17 | 2026-05-14 | Level 3 | Standards change
121332949 | other | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2023-12-26 | 2026-04-24 | Level 3 | Standards change
121333017 | pole | Non-HFTD | Transmission | 2021-04-23 | 2022-04-23 | Level 2 | E | 2024-10-23 | 2024-04-23 | Level 2 | GO 165 Inspection
121333103 | other | Non-HFTD | Transmission | 2021-04-14 | 2023-04-14 | Level 3 | F | 2023-12-15 | 2026-04-14 | Level 3 | Standards change
121333104 | anchor/guy | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2023-10-17 | 2026-04-26 | Level 3 | Standards change
121333244 | insulator and brushing | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-11-13 | 2024-05-14 | Level 2 | Field Safety Reassessment
121333401 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-04 | 2026-04-20 | Level 3 | GO 165 Inspection
121333488 | pole | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-10-17 | 2024-05-14 | Level 2 | Field Safety Reassessment
121333619 | pole | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-02-20 | 2024-04-26 | Level 2 | Field Safety Reassessment
121333777 | pole | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-11-20 | 2024-05-14 | Level 2 | GO 165 Inspection
121334006 | other | Non-HFTD | Transmission | 2021-05-14 | 2023-05-14 | Level 3 | F | 2024-02-28 | 2026-05-14 | Level 3 | Standards change
121334789 | pole | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-09-25 | 2024-05-14 | Level 2 | GO 165 Inspection
121335341 | switch | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-09-18 | 2022-05-14 | Level 2 | Field Safety Reassessment
121335363 | other | Non-HFTD | Transmission | 2021-04-13 | 2023-04-13 | Level 3 | F | 2024-06-03 | 2026-04-13 | Level 3 | GO 165 Inspection
121336109 | other | Non-HFTD | Transmission | 2021-04-19 | 2023-04-19 | Level 3 | F | 2024-04-06 | 2026-04-19 | Level 3 | Standards change
121336318 | other | Non-HFTD | Transmission | 2021-05-14 | 2023-05-14 | Level 3 | F | 2024-04-06 | 2026-05-14 | Level 3 | Standards change
121336446 | pole | Non-HFTD | Transmission | 2021-05-14 | 2024-05-14 | Level 2 | E | 2024-12-01 | 2022-05-14 | Level 2 | Field Safety Reassessment
121336553 | pole | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-12-01 | 2024-05-14 | Level 2 | Field Safety Reassessment
121336555 | pole | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-09-27 | 2024-05-14 | Level 2 | GO 165 Inspection
121336791 | insulator and brushing | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-09-04 | 2024-04-26 | Level 2 | GO 165 Inspection
121336815 | other | Non-HFTD | Transmission | 2021-04-16 | 2022-04-16 | Level 2 | E | 2023-02-08 | 2024-04-16 | Level 2 | Standards change
121336941 | insulator and brushing | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-12-04 | 2024-04-26 | Level 2 | Field Safety Reassessment
121337151 | other | Non-HFTD | Transmission | 2021-05-14 | 2023-05-14 | Level 3 | F | 2023-02-15 | 2026-05-14 | Level 3 | Standards change
121337794 | other | Non-HFTD | Transmission | 2021-04-21 | 2022-04-21 | Level 2 | E | 2023-01-12 | 2026-04-21 | Level 3 | Standards change
121337797 | other | Non-HFTD | Transmission | 2021-04-15 | 2024-04-15 | Level 2 | E | 2024-11-13 | 2022-04-15 | Level 2 | GO 165 Inspection
121338085 | anchor/guy | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2023-10-16 | 2026-04-26 | Level 3 | Standards change
121338392 | other | Non-HFTD | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2024-04-06 | 2026-05-15 | Level 3 | Standards change
121338454 | other | Non-HFTD | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2024-04-06 | 2026-05-15 | Level 3 | Standards change
121338479 | other | Non-HFTD | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2023-11-14 | 2026-05-15 | Level 3 | Standards change
121338519 | anchor/guy | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2023-08-08 | 2026-05-15 | Level 3 | Standards change
121338748 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2023-12-05 | 2026-04-27 | Level 3 | Standards change
121338873 | insulator and brushing | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-09-04 | 2024-04-26 | Level 2 | GO 165 Inspection
121338914 | other | Non-HFTD | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2024-04-06 | 2026-05-15 | Level 3 | Standards change
121339150 | pole | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2024-08-23 | 2024-05-15 | Level 2 | Field Safety Reassessment
121339942 | other | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2023-01-10 | 2026-05-15 | Level 3 | Standards change
121339951 | other | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2023-01-10 | 2026-05-15 | Level 3 | Standards change
121340132 | anchor/guy | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2024-05-02 | 2026-05-15 | Level 3 | GO 165 Inspection
121340224 | other | Non-HFTD | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2024-04-06 | 2026-05-15 | Level 3 | Standards change
121340569 | other | HFTD Tier 2 | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2023-12-08 | 2026-05-15 | Level 3 | Standards change
121340995 | other | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-09-05 | 2024-04-28 | Level 2 | GO 165 Inspection
121341208 | insulator and brushing | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2023-07-26 | 2026-04-28 | Level 3 | Standards change
121341299 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-04-06 | 2026-04-21 | Level 3 | Standards change
121342966 | other | Non-HFTD | Transmission | 2021-05-15 | 2023-05-15 | Level 3 | F | 2024-04-06 | 2026-05-15 | Level 3 | Standards change
121343191 | other | Non-HFTD | Transmission | 2021-05-12 | 2022-05-12 | Level 2 | E | 2023-02-08 | 2026-05-12 | Level 3 | Standards change
121344081 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2023-10-16 | 2026-04-24 | Level 3 | Standards change
121344360 | anchor/guy | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-09-05 | 2024-04-28 | Level 2 | GO 165 Inspection
121344558 | other | Non-HFTD | Transmission | 2021-05-17 | 2024-05-17 | Level 2 | E | 2024-08-15 | 2026-05-17 | Level 3 | GO 165 Inspection
121344559 | insulator and brushing | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2024-08-15 | 2024-05-17 | Level 2 | GO 165 Inspection
121344708 | other | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-02-16 | 2024-05-17 | Level 2 | Standards change
121344884 | conductor | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-10-16 | 2024-05-17 | Level 2 | Standards change
121345505 | insulator and brushing | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-01-19 | 2024-05-17 | Level 2 | Standards change
121345748 | pole | Non-HFTD | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-08-14 | 2026-05-17 | Level 3 | GO 165 Inspection
121346098 | other | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-02-13 | 2026-05-17 | Level 3 | Standards change
121346462 | other | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-02-16 | 2024-05-17 | Level 2 | Standards change
121346665 | pole | Non-HFTD | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-08-14 | 2026-05-17 | Level 3 | GO 165 Inspection
121346667 | insulator and brushing | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2024-12-16 | 2024-05-17 | Level 2 | Field Safety Reassessment
121346784 | other | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-02-14 | 2026-05-17 | Level 3 | Standards change
121346995 | other | Non-HFTD | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-09-11 | 2026-05-17 | Level 3 | GO 165 Inspection
121347312 | other | Non-HFTD | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-04-06 | 2026-05-17 | Level 3 | Standards change
121347753 | pole | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-03-24 | 2024-05-17 | Level 2 | Standards change
121348179 | pole | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2024-08-30 | 2026-04-24 | Level 3 | GO 165 Inspection
121348307 | other | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-04-06 | 2026-04-28 | Level 3 | Standards change
121348414 | pole | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2024-10-22 | 2024-05-17 | Level 2 | GO 165 Inspection
121348492 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-08-29 | 2026-04-24 | Level 3 | GO 165 Inspection
121348525 | insulator and brushing | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2023-01-17 | 2024-04-27 | Level 2 | Standards change
121348532 | other | Non-HFTD | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E | 2024-08-30 | 2024-04-24 | Level 2 | GO 165 Inspection
121348741 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-04-06 | 2026-04-27 | Level 3 | Standards change
121348816 | pole | Non-HFTD | Transmission | 2021-04-22 | 2022-04-22 | Level 2 | E | 2023-02-09 | 2024-04-22 | Level 2 | Standards change
121348861 | splice | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2023-10-16 | 2024-05-15 | Level 2 | Standards change
121348862 | pole | Non-HFTD | Transmission | 2021-05-15 | 2022-05-15 | Level 2 | E | 2024-07-10 | 2024-05-15 | Level 2 | GO 165 Inspection
121348877 | pole | Non-HFTD | Transmission | 2021-05-15 | 2024-05-15 | Level 2 | E | 2024-09-11 | 2021-11-15 | Level 2 | GO 165 Inspection
121351223 | insulator and brushing | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-01-22 | 2024-05-18 | Level 2 | Field Safety Reassessment
121351404 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2024-10-03 | 2026-05-18 | Level 3 | GO 165 Inspection
121351472 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-01-10 | 2026-04-21 | Level 3 | Standards change
121351477 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2023-03-21 | 2026-04-27 | Level 3 | Standards change
121351562 | anchor/guy | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-10-13 | 2026-05-18 | Level 3 | Standards change
121351669 | crossarm | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-01-31 | 2024-05-18 | Level 2 | Field Safety Reassessment
121351707 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-09-28 | 2026-04-27 | Level 3 | GO 165 Inspection
121351992 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2023-12-07 | 2026-05-18 | Level 3 | Standards change
121352048 | other | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-02-14 | 2026-05-18 | Level 3 | Standards change
121352252 | pole | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-07-30 | 2024-05-18 | Level 2 | Field Safety Reassessment
121352301 | anchor/guy | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-10-13 | 2026-05-18 | Level 3 | Standards change
121352527 | other | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-08-14 | 2024-05-18 | Level 2 | GO 165 Inspection
121352695 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2024-09-10 | 2026-05-18 | Level 3 | GO 165 Inspection
121353746 | insulator and brushing | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-07-26 | 2024-05-18 | Level 2 | GO 165 Inspection
121353752 | insulator and brushing | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-07-26 | 2024-05-18 | Level 2 | GO 165 Inspection
121353801 | crossarm | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-02-01 | 2026-05-18 | Level 3 | Standards change
121354001 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2024-04-06 | 2026-05-18 | Level 3 | Standards change
121354007 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2024-10-09 | 2026-05-18 | Level 3 | GO 165 Inspection
121354072 | pole | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2024-06-07 | 2024-05-18 | Level 2 | Field Safety Reassessment
121354083 | other | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-10-13 | 2026-05-18 | Level 3 | Standards change
121354359 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2023-12-11 | 2026-05-18 | Level 3 | Standards change
121355124 | anchor/guy | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-07-19 | 2026-05-18 | Level 3 | Standards change
121355155 | anchor/guy | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-07-19 | 2026-05-18 | Level 3 | Standards change
121355593 | anchor/guy | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-09-06 | 2024-04-29 | Level 2 | GO 165 Inspection
121355982 | other | Non-HFTD | Transmission | 2021-04-20 | 2023-04-20 | Level 3 | F | 2024-09-05 | 2026-04-20 | Level 3 | GO 165 Inspection
121355987 | other | Non-HFTD | Transmission | 2021-04-21 | 2023-04-21 | Level 3 | F | 2024-04-06 | 2026-04-21 | Level 3 | Standards change
121356807 | other | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-10-14 | 2026-04-28 | Level 3 | GO 165 Inspection
121356843 | other | Non-HFTD | Transmission | 2021-04-29 | 2023-04-29 | Level 3 | F | 2024-01-12 | 2026-04-29 | Level 3 | Standards change
121356871 | other | Non-HFTD | Transmission | 2021-04-27 | 2023-04-27 | Level 3 | F | 2024-04-06 | 2026-04-27 | Level 3 | Standards change
121357234 | anchor/guy | Non-HFTD | Transmission | 2021-05-18 | 2022-05-18 | Level 2 | E | 2023-10-13 | 2026-05-18 | Level 3 | Standards change
121357636 | other | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-04-04 | 2026-04-27 | Level 3 | GO 165 Inspection
121357953 | anchor/guy | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2023-08-10 | 2026-05-19 | Level 3 | Standards change
121358000 | other | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-11-01 | 2026-04-27 | Level 3 | GO 165 Inspection
121358933 | other | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-09-09 | 2026-05-19 | Level 3 | GO 165 Inspection
121359150 | other | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-04-06 | 2026-05-19 | Level 3 | Standards change
121359255 | other | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-08-28 | 2026-05-19 | Level 3 | GO 165 Inspection
121359318 | other | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-01-05 | 2026-05-19 | Level 3 | Standards change
121359947 | pole | Non-HFTD | Transmission | 2021-05-19 | 2024-05-19 | Level 2 | E | 2024-08-14 | 2026-05-19 | Level 3 | GO 165 Inspection
121360641 | pole | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2024-12-09 | 2024-05-19 | Level 2 | Field Safety Reassessment
121360776 | pole | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2024-08-13 | 2022-05-19 | Level 2 | Field Safety Reassessment
121360780 | other | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2023-10-13 | 2026-05-19 | Level 3 | Standards change
121360785 | other | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-04-06 | 2026-05-19 | Level 3 | Standards change
121360832 | insulator and brushing | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2024-09-23 | 2024-05-19 | Level 2 | GO 165 Inspection
121360955 | insulator and brushing | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2023-10-13 | 2024-05-19 | Level 2 | Standards change
121361174 | other | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-04-06 | 2026-05-19 | Level 3 | Standards change
121361280 | insulator and brushing | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2023-10-13 | 2024-05-19 | Level 2 | Standards change
121361533 | pole | Non-HFTD | Transmission | 2021-05-19 | 2023-05-19 | Level 3 | F | 2024-11-13 | 2026-05-19 | Level 3 | GO 165 Inspection
121361706 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-08-23 | 2024-04-30 | Level 2 | GO 165 Inspection
121362306 | anchor/guy | Non-HFTD | Transmission | 2021-05-11 | 2022-05-11 | Level 2 | E | 2023-01-11 | 2024-05-11 | Level 2 | Standards change
121362948 | other | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-04-06 | 2026-04-28 | Level 3 | Standards change
121363047 | anchor/guy | Non-HFTD | Transmission | 2021-05-19 | 2022-05-19 | Level 2 | E | 2023-07-19 | 2026-05-19 | Level 3 | Standards change
121363092 | other | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-09-28 | 2026-04-28 | Level 3 | GO 165 Inspection
121363115 | other | Non-HFTD | Transmission | 2021-04-26 | 2022-04-26 | Level 2 | E | 2024-08-30 | 2026-04-26 | Level 3 | GO 165 Inspection
121363205 | other | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-09-05 | 2024-04-29 | Level 2 | GO 165 Inspection
121363206 | other | Non-HFTD | Transmission | 2021-04-29 | 2022-04-29 | Level 2 | E | 2024-09-05 | 2024-04-29 | Level 2 | GO 165 Inspection
121363234 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-06-27 | 2026-04-30 | Level 3 | GO 165 Inspection
121363923 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-07-01 | 2026-04-30 | Level 3 | GO 165 Inspection
121363968 | other | Non-HFTD | Transmission | 2021-04-29 | 2023-04-29 | Level 3 | F | 2024-01-03 | 2026-04-29 | Level 3 | Standards change
121363971 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-10-16 | 2024-04-30 | Level 2 | GO 165 Inspection
121364019 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-09-10 | 2024-04-30 | Level 2 | GO 165 Inspection
121364106 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-10-16 | 2024-04-30 | Level 2 | GO 165 Inspection
121364153 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-10-13 | 2024-04-30 | Level 2 | Standards change
121364179 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-06-28 | 2026-04-30 | Level 3 | GO 165 Inspection
121364223 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-10-12 | 2024-04-30 | Level 2 | Standards change
121364224 | other | Non-HFTD | Transmission | 2021-04-29 | 2023-04-29 | Level 3 | F | 2023-12-28 | 2026-04-29 | Level 3 | Standards change
121364234 | insulator and brushing | Non-HFTD | Transmission | 2021-05-01 | 2022-05-01 | Level 2 | E | 2023-02-17 | 2024-05-01 | Level 2 | Standards change
121364236 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-10-12 | 2024-04-30 | Level 2 | Standards change
121364931 | pole | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2024-11-06 | 2024-05-20 | Level 2 | Field Safety Reassessment
121365324 | other | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-01-26 | 2026-05-20 | Level 3 | Standards change
121365612 | anchor/guy | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2022-05-20 | Level 2 | Standards change
121365693 | anchor/guy | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2026-05-20 | Level 3 | Standards change
121365743 | other | Non-HFTD | Transmission | 2021-04-28 | 2023-04-28 | Level 3 | F | 2024-09-12 | 2026-04-28 | Level 3 | GO 165 Inspection
121365882 | other | Non-HFTD | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2023-07-13 | 2026-05-20 | Level 3 | Standards change
121366111 | anchor/guy | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-07-26 | 2026-05-20 | Level 3 | Standards change
121366226 | other | HFTD Tier 2 | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2024-06-01 | 2026-05-20 | Level 3 | GO 165 Inspection
121366412 | pole | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2024-12-01 | 2024-05-20 | Level 2 | Field Safety Reassessment
121366453 | pole | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-02-06 | 2024-05-20 | Level 2 | Standards change
121366491 | other | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-03-27 | 2024-04-30 | Level 2 | GO 165 Inspection
121366622 | anchor/guy | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2026-05-20 | Level 3 | Standards change
121366692 | other | Non-HFTD | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2023-12-11 | 2026-05-20 | Level 3 | Standards change
121366807 | other | Non-HFTD | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2024-04-06 | 2026-05-20 | Level 3 | Standards change
121367201 | other | Non-HFTD | Transmission | 2021-04-28 | 2022-04-28 | Level 2 | E | 2024-09-06 | 2024-04-28 | Level 2 | GO 165 Inspection
121367368 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-03-20 | 2024-04-30 | Level 2 | Standards change
121367777 | anchor/guy | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2026-05-20 | Level 3 | Standards change
121368026 | other | Non-HFTD | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2024-04-06 | 2026-05-20 | Level 3 | Standards change
121368820 | insulator and brushing | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2024-12-04 | 2024-05-20 | Level 2 | Field Safety Reassessment
121368913 | pole | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2024-09-30 | 2024-05-20 | Level 2 | GO 165 Inspection
121368962 | other | Non-HFTD | Transmission | 2021-05-20 | 2024-05-20 | Level 2 | E | 2024-09-30 | 2022-05-20 | Level 2 | GO 165 Inspection
121369083 | insulator and brushing | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2023-02-17 | 2024-04-30 | Level 2 | Standards change
121369833 | insulator and brushing | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2024-05-20 | Level 2 | Standards change
121369860 | insulator and brushing | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2024-05-20 | Level 2 | Standards change
121370045 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2023-02-08 | 2026-05-03 | Level 3 | Standards change
121370089 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-02-29 | 2026-05-03 | Level 3 | Standards change
121370362 | anchor/guy | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-12 | 2026-05-20 | Level 3 | Standards change
121370470 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-06-27 | 2026-05-03 | Level 3 | GO 165 Inspection
121370514 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2023-02-06 | 2024-05-03 | Level 2 | Standards change
121370564 | pole | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2023-12-15 | 2024-05-03 | Level 2 | Standards change
121370728 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-08-29 | 2024-05-03 | Level 2 | GO 165 Inspection
121370818 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-04-06 | 2026-05-03 | Level 3 | Standards change
121370843 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-06-25 | 2022-05-03 | Level 2 | GO 165 Inspection
121370885 | other | Non-HFTD | Transmission | 2021-04-30 | 2023-04-30 | Level 3 | F | 2024-04-06 | 2026-04-30 | Level 3 | Standards change
121370947 | pole | Non-HFTD | Transmission | 2021-04-27 | 2022-04-27 | Level 2 | E | 2024-08-16 | 2024-04-27 | Level 2 | Field Safety Reassessment
121370953 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-03-19 | 2026-05-03 | Level 3 | GO 165 Inspection
121370998 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2023-12-28 | 2026-05-04 | Level 3 | Standards change
121371030 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-10-12 | 2024-05-04 | Level 2 | Standards change
121371050 | insulator and brushing | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2024-10-05 | 2024-05-20 | Level 2 | GO 165 Inspection
121371105 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-09-24 | 2026-05-04 | Level 3 | GO 165 Inspection
121371125 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2023-12-14 | 2026-05-03 | Level 3 | Standards change
121371210 | other | Non-HFTD | Transmission | 2021-04-30 | 2022-04-30 | Level 2 | E | 2024-06-28 | 2026-04-30 | Level 3 | GO 165 Inspection
121371219 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-02-28 | 2026-05-04 | Level 3 | Standards change
121372884 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-02-28 | 2026-05-04 | Level 3 | Standards change
121372903 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2023-12-15 | 2026-05-03 | Level 3 | Standards change
121373164 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-04-06 | 2026-05-21 | Level 3 | Standards change
121373193 | pole | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-09-03 | 2022-05-04 | Level 2 | Field Safety Reassessment
121373305 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-04-06 | 2026-05-21 | Level 3 | Standards change
121373342 | other | HFTD Tier 2 | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-04-06 | 2026-05-03 | Level 3 | Standards change
121373406 | other | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-06-28 | 2026-05-03 | Level 3 | GO 165 Inspection
121373574 | pole | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-08-20 | 2024-05-21 | Level 2 | Field Safety Reassessment
121373599 | other | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2023-02-08 | 2024-05-21 | Level 2 | Standards change
121373607 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-10-23 | 2026-05-21 | Level 3 | GO 165 Inspection
121373624 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2023-12-04 | 2026-05-05 | Level 3 | Standards change
121373635 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-10-11 | 2024-05-05 | Level 2 | Standards change
121373790 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-10-11 | 2024-05-05 | Level 2 | Standards change
121374063 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-04-06 | 2026-05-05 | Level 3 | Standards change
121374259 | other | Non-HFTD | Transmission | 2021-05-03 | 2023-05-03 | Level 3 | F | 2024-01-23 | 2026-05-03 | Level 3 | Standards change
121374330 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-02-03 | 2026-05-04 | Level 3 | Standards change
121374341 | pole | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-11-15 | 2026-05-21 | Level 3 | GO 165 Inspection
121374363 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-08-29 | 2024-05-03 | Level 2 | GO 165 Inspection
121374382 | other | Non-HFTD | Transmission | 2021-05-04 | 2024-05-04 | Level 2 | E | 2024-08-29 | 2021-08-04 | Level 2 | GO 165 Inspection
121374385 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-11-20 | 2026-05-05 | Level 3 | GO 165 Inspection
121374573 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-04-06 | 2026-05-21 | Level 3 | Standards change
121374674 | other | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-08-20 | 2024-05-21 | Level 2 | Field Safety Reassessment
121374726 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-01-12 | 2026-05-04 | Level 3 | Standards change
121374799 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-01-18 | 2026-05-21 | Level 3 | Standards change
121374847 | anchor/guy | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2023-10-11 | 2026-05-21 | Level 3 | Standards change
121374963 | splice | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2023-10-11 | 2024-05-21 | Level 2 | Standards change
121374992 | pole | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-12-09 | 2024-05-21 | Level 2 | Field Safety Reassessment
121375007 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-08-23 | 2024-05-03 | Level 2 | GO 165 Inspection
121375082 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-01-31 | 2026-05-04 | Level 3 | Standards change
121375172 | pole | Non-HFTD | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2024-10-23 | 2026-05-21 | Level 3 | GO 165 Inspection
121375196 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-10-11 | 2026-05-04 | Level 3 | Standards change
121375213 | other | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2023-10-11 | 2024-05-04 | Level 2 | Standards change
121375333 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-01-26 | 2024-05-21 | Level 2 | Standards change
121375336 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-04-06 | 2026-05-21 | Level 3 | Standards change
121375340 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121375343 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2023-12-29 | 2026-05-05 | Level 3 | Standards change
121375349 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121375362 | insulator and brushing | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-08-05 | 2024-05-21 | Level 2 | Field Safety Reassessment
121375443 | pole | Non-HFTD | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2024-10-23 | 2026-05-21 | Level 3 | GO 165 Inspection
121375449 | pole | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-01-17 | 2026-05-21 | Level 3 | Standards change
121375513 | pole | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2023-01-10 | 2026-05-04 | Level 3 | Standards change
121375552 | pole | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-08-01 | 2024-05-04 | Level 2 | Field Safety Reassessment
121375590 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-04-06 | 2026-05-05 | Level 3 | Standards change
121375876 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-09-04 | 2024-05-05 | Level 2 | GO 165 Inspection
121375953 | insulator and brushing | Non-HFTD | Transmission | 2021-05-03 | 2022-05-03 | Level 2 | E | 2024-08-26 | 2024-05-03 | Level 2 | GO 165 Inspection
121376086 | insulator and brushing | Non-HFTD | Transmission | 2021-05-04 | 2022-05-04 | Level 2 | E | 2024-08-26 | 2024-05-04 | Level 2 | GO 165 Inspection
121376090 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-09-24 | 2026-05-05 | Level 3 | GO 165 Inspection
121376125 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-12-11 | 2026-05-21 | Level 3 | Standards change
121376289 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-04-06 | 2026-05-21 | Level 3 | Standards change
121376376 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-12-11 | 2026-05-21 | Level 3 | Standards change
121376456 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-02-28 | 2026-05-04 | Level 3 | Standards change
121376830 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-12-06 | 2026-05-21 | Level 3 | Standards change
121376909 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-02-02 | 2026-05-05 | Level 3 | Standards change
121376953 | other | Non-HFTD | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2023-12-11 | 2026-05-21 | Level 3 | Standards change
121377247 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121377455 | pole | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-12-24 | 2024-05-21 | Level 2 | Field Safety Reassessment
121377499 | anchor/guy | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2023-10-10 | 2026-05-21 | Level 3 | Standards change
121377526 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-07-09 | 2026-05-05 | Level 3 | GO 165 Inspection
121377562 | pole | Non-HFTD | Transmission | 2021-05-21 | 2022-05-21 | Level 2 | E | 2024-08-21 | 2024-05-21 | Level 2 | Field Safety Reassessment
121377920 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-09-05 | 2026-05-05 | Level 3 | GO 165 Inspection
121378109 | pole | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-09-28 | 2024-05-05 | Level 2 | GO 165 Inspection
121378116 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-10-10 | 2026-05-05 | Level 3 | Standards change
121378131 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-08-02 | 2024-05-05 | Level 2 | Field Safety Reassessment
121378190 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-09-28 | 2024-05-05 | Level 2 | GO 165 Inspection
121378191 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-09-28 | 2026-05-05 | Level 3 | GO 165 Inspection
121378276 | other | Non-HFTD | Transmission | 2021-05-04 | 2023-05-04 | Level 3 | F | 2024-04-06 | 2026-05-04 | Level 3 | Standards change
121378318 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121378319 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121378422 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2023-12-04 | 2026-05-06 | Level 3 | Standards change
121378509 | other | Non-HFTD | Transmission | 2021-05-07 | 2023-05-07 | Level 3 | F | 2024-08-26 | 2026-05-07 | Level 3 | GO 165 Inspection
121378823 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121378826 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2023-12-04 | 2026-05-05 | Level 3 | Standards change
121378972 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2024-09-03 | 2024-05-05 | Level 2 | Field Safety Reassessment
121379475 | insulator and brushing | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-10-10 | 2024-05-05 | Level 2 | Standards change
121379512 | pole | Non-HFTD | Transmission | 2021-05-06 | 2022-05-06 | Level 2 | E | 2023-01-13 | 2026-05-06 | Level 3 | Standards change
121379788 | anchor/guy | Non-HFTD | Transmission | 2021-05-22 | 2022-05-22 | Level 2 | E | 2023-10-10 | 2026-05-22 | Level 3 | Standards change
121379861 | pole | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-01-23 | 2026-05-08 | Level 3 | Standards change
121379909 | pole | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2023-10-10 | 2026-05-08 | Level 3 | Standards change
121379980 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2023-12-04 | 2026-05-05 | Level 3 | Standards change
121380001 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-04-06 | 2026-05-08 | Level 3 | Standards change
121380332 | anchor/guy | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-01-05 | 2026-05-22 | Level 3 | Standards change
121380500 | pole | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2023-10-10 | 2026-05-08 | Level 3 | Standards change
121380597 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121380657 | pole | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2024-06-07 | 2024-05-07 | Level 2 | Field Safety Reassessment
121380684 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2023-12-11 | 2026-05-22 | Level 3 | Standards change
121380708 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121380757 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121380763 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-04-06 | 2026-05-08 | Level 3 | Standards change
121380837 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121380868 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121380898 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121380985 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-04-06 | 2026-05-08 | Level 3 | Standards change
121381072 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-04-06 | 2026-05-08 | Level 3 | Standards change
121381106 | other | Non-HFTD | Transmission | 2021-05-05 | 2022-05-05 | Level 2 | E | 2023-01-24 | 2026-05-05 | Level 3 | Standards change
121381158 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2024-04-06 | 2026-05-06 | Level 3 | Standards change
121381261 | anchor/guy | Non-HFTD | Transmission | 2021-05-07 | 2022-05-07 | Level 2 | E | 2024-09-16 | 2024-05-07 | Level 2 | GO 165 Inspection
121381419 | anchor/guy | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-09-03 | 2024-05-08 | Level 2 | GO 165 Inspection
121381557 | pole | Non-HFTD | Transmission | 2021-05-08 | 2022-05-08 | Level 2 | E | 2024-12-02 | 2024-05-08 | Level 2 | Field Safety Reassessment
121381698 | other | Non-HFTD | Transmission | 2021-05-06 | 2023-05-06 | Level 3 | F | 2023-12-26 | 2026-05-06 | Level 3 | Standards change
121381847 | other | HFTD Tier 2 | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-05-19 | 2026-05-11 | Level 3 | GO 165 Inspection
121382252 | other | HFTD Tier 2 | Transmission | 2021-05-10 | 2023-05-10 | Level 3 | F | 2024-06-07 | 2026-05-10 | Level 3 | GO 165 Inspection
121382653 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121382801 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383303 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-04-06 | 2026-05-08 | Level 3 | Standards change
121383312 | other | Non-HFTD | Transmission | 2021-05-08 | 2023-05-08 | Level 3 | F | 2024-01-10 | 2026-05-08 | Level 3 | Standards change
121383516 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383519 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383624 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383626 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383692 | other | Non-HFTD | Transmission | 2021-05-05 | 2023-05-05 | Level 3 | F | 2024-04-06 | 2026-05-05 | Level 3 | Standards change
121383714 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383717 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383929 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121383945 | other | HFTD Tier 2 | Transmission | 2021-05-10 | 2023-05-10 | Level 3 | F | 2024-06-05 | 2026-05-10 | Level 3 | GO 165 Inspection
121384007 | anchor/guy | Non-HFTD | Transmission | 2021-05-07 | 2026-05-07 | Level 3 | F |  | 2026-05-07 | Level 3
121384292 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121384293 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121384294 | pole | Non-HFTD | Transmission | 2021-05-22 | 2022-05-22 | Level 2 | E | 2024-12-01 | 2024-05-22 | Level 2 | Field Safety Reassessment
121384522 | other | HFTD Tier 2 | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121384893 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121385132 | pole | Non-HFTD | Transmission | 2021-05-22 | 2022-05-22 | Level 2 | E | 2024-08-05 | 2022-05-22 | Level 2 | Field Safety Reassessment
121385234 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121385376 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121386447 | pole | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-07-24 | 2026-05-22 | Level 3 | GO 165 Inspection
121386569 | insulator and brushing | Non-HFTD | Transmission | 2021-05-10 | 2022-05-10 | Level 2 | E | 2024-11-25 | 2026-05-10 | Level 3 | GO 165 Inspection
121386941 | anchor/guy | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-10-09 | 2026-05-24 | Level 3 | Standards change
121387207 | anchor/guy | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-10-09 | 2026-05-24 | Level 3 | Standards change
121387260 | anchor/guy | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-10-09 | 2026-05-24 | Level 3 | Standards change
121387322 | insulator and brushing | Non-HFTD | Transmission | 2021-05-20 | 2022-05-20 | Level 2 | E | 2023-10-09 | 2024-05-20 | Level 2 | Standards change
121387729 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121388000 | anchor/guy | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-10-09 | 2026-05-24 | Level 3 | Standards change
121388677 | splice | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-03-09 | 2024-05-24 | Level 2 | Standards change
121388811 | anchor/guy | Non-HFTD | Transmission | 2021-05-22 | 2022-05-22 | Level 2 | E | 2023-10-09 | 2026-05-22 | Level 3 | Standards change
121389810 | anchor/guy | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-10-09 | 2026-05-24 | Level 3 | Standards change
121390306 | pole | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2024-10-29 | 2024-05-24 | Level 2 | Field Safety Reassessment
121390526 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121390893 | insulator and brushing | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2024-10-29 | 2024-05-24 | Level 2 | Field Safety Reassessment
121391633 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121391801 | pole | HFTD Tier 3 | Transmission | 2021-05-13 | 2023-05-13 | Level 3 | F | 2024-04-03 | 2026-05-13 | Level 3 | GO 165 Inspection
121391872 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121392014 | pole | HFTD Tier 2 | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-04-30 | 2026-05-17 | Level 3 | GO 165 Inspection
121392257 | other | HFTD Tier 2 | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-04-06 | 2026-05-17 | Level 3 | Standards change
121393048 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-10-09 | 2026-05-25 | Level 3 | Standards change
121393290 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-10-10 | 2024-05-25 | Level 2 | GO 165 Inspection
121393318 | other | Non-HFTD | Transmission | 2021-05-11 | 2023-05-11 | Level 3 | F | 2024-04-06 | 2026-05-11 | Level 3 | Standards change
121393411 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2023-12-15 | 2026-05-25 | Level 3 | Standards change
121393648 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-10-09 | 2026-05-25 | Level 3 | Standards change
121393660 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-10-09 | 2026-05-25 | Level 3 | Standards change
121394225 | pole | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-01-17 | 2024-05-25 | Level 2 | Field Safety Reassessment
121394374 | splice | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-09-26 | 2024-05-25 | Level 2 | GO 165 Inspection
121394396 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-10-11 | 2026-05-25 | Level 3 | GO 165 Inspection
121395397 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-10-11 | 2024-05-25 | Level 2 | GO 165 Inspection
121395425 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-12-27 | 2026-05-25 | Level 3 | Standards change
121395429 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-10-09 | 2026-05-25 | Level 3 | Standards change
121395441 | other | HFTD Tier 2 | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-06-05 | 2026-05-17 | Level 3 | GO 165 Inspection
121395456 | other | HFTD Tier 2 | Transmission | 2021-05-17 | 2023-05-17 | Level 3 | F | 2024-05-16 | 2026-05-17 | Level 3 | GO 165 Inspection
121395465 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-10-09 | 2026-05-25 | Level 3 | Standards change
121395510 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-11-20 | 2024-05-25 | Level 2 | Standards change
121395946 | pole | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-10-14 | 2024-05-25 | Level 2 | Field Safety Reassessment
121395981 | other | HFTD Tier 2 | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2024-05-06 | 2026-05-18 | Level 3 | GO 165 Inspection
121399357 | pole | Non-HFTD | Transmission | 2021-05-26 | 2022-05-26 | Level 2 | E | 2024-10-11 | 2024-05-26 | Level 2 | GO 165 Inspection
121400679 | other | Non-HFTD | Transmission | 2021-05-26 | 2023-05-26 | Level 3 | F | 2024-04-06 | 2026-05-26 | Level 3 | Standards change
121401056 | pole | Non-HFTD | Transmission | 2021-05-26 | 2022-05-26 | Level 2 | E | 2024-11-04 | 2024-05-26 | Level 2 | GO 165 Inspection
121401237 | other | HFTD Tier 2 | Transmission | 2021-05-17 | 2026-05-17 | Level 3 | F | 2024-05-10 | 2026-05-17 | Level 3 | GO 165 Inspection
121402194 | pole | Non-HFTD | Transmission | 2021-05-26 | 2022-05-26 | Level 2 | E | 2024-08-30 | 2024-05-26 | Level 2 | GO 165 Inspection
121402816 | anchor/guy | Non-HFTD | Transmission | 2021-05-26 | 2022-05-26 | Level 2 | E | 2024-08-30 | 2024-05-26 | Level 2 | GO 165 Inspection
121405219 | other | HFTD Tier 3 | Transmission | 2021-05-20 | 2023-05-20 | Level 3 | F | 2023-05-15 | 2026-05-20 | Level 3 | Standards change
121405297 | other | HFTD Tier 2 | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-05-21 | 2026-05-21 | Level 3 | GO 165 Inspection
121405359 | other | HFTD Tier 2 | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-05-21 | 2026-05-21 | Level 3 | GO 165 Inspection
121405684 | other | HFTD Tier 2 | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-05-06 | 2026-05-22 | Level 3 | GO 165 Inspection
121406501 | other | Non-HFTD | Transmission | 2021-05-26 | 2023-05-26 | Level 3 | F | 2024-04-06 | 2026-05-26 | Level 3 | Standards change
121406881 | insulator and brushing | Non-HFTD | Transmission | 2021-05-26 | 2022-05-26 | Level 2 | E |  | 2022-05-26 | Level 2
121407277 | pole | Non-HFTD | Transmission | 2021-05-27 | 2022-05-27 | Level 2 | E | 2024-09-03 | 2024-05-27 | Level 2 | GO 165 Inspection
121407962 | pole | Non-HFTD | Transmission | 2021-05-27 | 2022-05-27 | Level 2 | E | 2023-11-27 | 2024-05-27 | Level 2 | Standards change
121408505 | anchor/guy | Non-HFTD | Transmission | 2021-05-27 | 2022-05-27 | Level 2 | E | 2023-11-27 | 2026-05-27 | Level 3 | Standards change
121417726 | other | Non-HFTD | Transmission | 2021-04-24 | 2023-04-24 | Level 3 | F | 2024-04-06 | 2026-04-24 | Level 3 | Standards change
121417788 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121417832 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121417925 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121417927 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121417935 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121417937 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121417939 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121417948 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121418050 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121418056 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121418057 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121418101 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121418195 | other | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-12-02 | 2026-05-25 | Level 3 | GO 165 Inspection
121418263 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121418290 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2022-12-20 | 2026-05-25 | Level 3 | Standards change
121418308 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121418360 | other | Non-HFTD | Transmission | 2021-05-25 | 2023-05-25 | Level 3 | F | 2024-04-06 | 2026-05-25 | Level 3 | Standards change
121418472 | anchor/guy | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-11-27 | 2026-05-25 | Level 3 | Standards change
121418581 | other | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-03-09 | 2026-05-25 | Level 3 | Standards change
121418818 | anchor/guy | Non-HFTD | Transmission | 2021-05-26 | 2022-05-26 | Level 2 | E | 2024-12-03 | 2026-05-26 | Level 3 | GO 165 Inspection
121420081 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121420286 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121420289 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121420309 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121420470 | anchor/guy | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2024-11-01 | 2026-05-24 | Level 3 | GO 165 Inspection
121420521 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121421056 | other | Non-HFTD | Transmission | 2021-05-28 | 2023-05-28 | Level 3 | F | 2024-02-28 | 2026-05-28 | Level 3 | Standards change
121421135 | other | Non-HFTD | Transmission | 2021-05-28 | 2022-05-28 | Level 2 | E | 2024-11-19 | 2024-05-28 | Level 2 | GO 165 Inspection
121421497 | other | Non-HFTD | Transmission | 2021-05-28 | 2023-05-28 | Level 3 | F | 2024-02-28 | 2026-05-28 | Level 3 | Standards change
121421833 | other | HFTD Tier 2 | Transmission | 2021-05-21 | 2023-05-21 | Level 3 | F | 2024-05-21 | 2026-05-21 | Level 3 | GO 165 Inspection
121421850 | other | Non-HFTD | Transmission | 2021-05-28 | 2022-05-28 | Level 2 | E | 2023-02-09 | 2024-05-28 | Level 2 | Standards change
121422206 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121422467 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2023-12-20 | 2024-05-25 | Level 2 | Standards change
121422748 | other | HFTD Tier 3 | Transmission | 2021-05-26 | 2023-05-26 | Level 3 | F | 2024-03-25 | 2026-05-26 | Level 3 | Standards change
121422783 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2022-05-25 | Level 2 | E | 2024-10-08 | 2024-05-25 | Level 2 | Field Safety Reassessment
121427609 | other | Non-HFTD | Transmission | 2021-05-28 | 2023-05-28 | Level 3 | F | 2024-04-06 | 2026-05-28 | Level 3 | Standards change
121428578 | pole | Non-HFTD | Transmission | 2021-05-24 | 2022-05-24 | Level 2 | E | 2023-03-03 | 2026-05-24 | Level 3 | Standards change
121431330 | anchor/guy | Non-HFTD | Transmission | 2021-05-29 | 2023-05-29 | Level 3 | F | 2024-12-05 | 2026-05-29 | Level 3 | GO 165 Inspection
121436457 | anchor/guy | Non-HFTD | Transmission | 2021-06-01 | 2023-06-01 | Level 3 | F | 2024-11-05 | 2026-06-01 | Level 3 | GO 165 Inspection
121437295 | anchor/guy | Non-HFTD | Transmission | 2021-06-01 | 2022-06-01 | Level 2 | E | 2023-01-17 | 2026-06-01 | Level 3 | Standards change
121437790 | insulator and brushing | Non-HFTD | Transmission | 2021-05-25 | 2026-05-25 | Level 2 | E | 2024-09-04 | 2024-05-25 | Level 2 | GO 165 Inspection
121445130 | pole | Non-HFTD | Transmission | 2021-05-07 | 2023-05-07 | Level 3 | F | 2024-01-10 | 2026-05-07 | Level 3 | Standards change
121445346 | pole | Non-HFTD | Transmission | 2021-06-02 | 2022-06-02 | Level 2 | E | 2023-02-09 | 2024-06-02 | Level 2 | Standards change
121445363 | other | Non-HFTD | Transmission | 2021-06-02 | 2022-06-02 | Level 2 | E | 2023-02-09 | 2024-06-02 | Level 2 | Standards change
121445429 | other | Non-HFTD | Transmission | 2021-06-02 | 2023-06-02 | Level 3 | F | 2024-04-06 | 2026-06-02 | Level 3 | Standards change
121445435 | other | Non-HFTD | Transmission | 2021-06-02 | 2023-06-02 | Level 3 | F | 2024-04-06 | 2026-06-02 | Level 3 | Standards change
121445441 | other | Non-HFTD | Transmission | 2021-06-02 | 2023-06-02 | Level 3 | F | 2024-04-06 | 2026-06-02 | Level 3 | Standards change
121446945 | other | HFTD Tier 3 | Transmission | 2021-05-27 | 2023-05-27 | Level 3 | F | 2024-06-04 | 2026-05-27 | Level 3 | GO 165 Inspection
121447043 | other | Non-HFTD | Transmission | 2021-05-24 | 2023-05-24 | Level 3 | F | 2024-04-06 | 2026-05-24 | Level 3 | Standards change
121450806 | anchor/guy | Non-HFTD | Transmission | 2021-06-03 | 2022-06-03 | Level 2 | E | 2023-01-30 | 2026-06-03 | Level 3 | Standards change
121450928 | pole | Non-HFTD | Transmission | 2021-06-03 | 2022-06-03 | Level 2 | E | 2024-12-07 | 2024-06-03 | Level 2 | Field Safety Reassessment
121452383 | pole | Non-HFTD | Transmission | 2021-05-28 | 2022-05-28 | Level 2 | E | 2023-07-27 | 2024-05-28 | Level 2 | Standards change
121452492 | splice | Non-HFTD | Transmission | 2021-05-28 | 2022-05-28 | Level 2 | E | 2023-07-26 | 2024-05-28 | Level 2 | Standards change
121452526 | pole | Non-HFTD | Transmission | 2021-05-28 | 2022-05-28 | Level 2 | E | 2023-08-25 | 2024-05-28 | Level 2 | Standards change
121466809 | insulator and brushing | Non-HFTD | Transmission | 2021-06-04 | 2022-06-04 | Level 2 | E | 2024-09-16 | 2024-06-04 | Level 2 | Field Safety Reassessment
121467666 | other | Non-HFTD | Transmission | 2021-06-04 | 2022-06-04 | Level 2 | E | 2024-05-15 | 2024-06-04 | Level 2 | Field Safety Reassessment
121467843 | insulator and brushing | Non-HFTD | Transmission | 2021-06-04 | 2022-06-04 | Level 2 | E | 2024-10-11 | 2024-06-04 | Level 2 | GO 165 Inspection
121468572 | other | Non-HFTD | Transmission | 2021-06-04 | 2022-06-04 | Level 2 | E | 2024-05-15 | 2024-06-04 | Level 2 | Field Safety Reassessment
121468868 | other | Non-HFTD | Transmission | 2021-06-04 | 2022-06-04 | Level 2 | E | 2024-05-15 | 2024-06-04 | Level 2 | Field Safety Reassessment
121469396 | other | Non-HFTD | Transmission | 2021-06-04 | 2022-06-04 | Level 2 | E | 2024-08-08 | 2024-06-04 | Level 2 | GO 165 Inspection
121473356 | anchor/guy | Non-HFTD | Transmission | 2021-06-05 | 2022-06-05 | Level 2 | E | 2024-11-18 | 2026-06-05 | Level 3 | GO 165 Inspection
121473392 | other | Non-HFTD | Transmission | 2021-06-05 | 2022-06-05 | Level 2 | E | 2024-08-14 | 2024-06-05 | Level 2 | GO 165 Inspection
121473508 | other | Non-HFTD | Transmission | 2021-06-05 | 2023-06-05 | Level 3 | F | 2024-04-06 | 2026-06-05 | Level 3 | Standards change
121473623 | other | Non-HFTD | Transmission | 2021-06-05 | 2022-06-05 | Level 2 | E | 2024-07-23 | 2024-06-05 | Level 2 | GO 165 Inspection
121473955 | pole | Non-HFTD | Transmission | 2021-06-05 | 2021-12-05 | Level 2 | E | 2024-08-01 | 2021-12-05 | Level 2 | Field Safety Reassessment
121475189 | other | Non-HFTD | Transmission | 2021-06-05 | 2023-06-05 | Level 3 | F | 2024-04-06 | 2026-06-05 | Level 3 | Standards change
121475846 | other | Non-HFTD | Transmission | 2021-06-05 | 2023-06-05 | Level 3 | F | 2024-04-06 | 2026-06-05 | Level 3 | Standards change
121480991 | anchor/guy | Non-HFTD | Transmission | 2021-05-17 | 2022-05-17 | Level 2 | E | 2023-11-29 | 2026-05-17 | Level 3 | Standards change
121481142 | insulator and brushing | Non-HFTD | Transmission | 2021-06-07 | 2022-06-07 | Level 2 | E | 2024-08-08 | 2024-06-07 | Level 2 | GO 165 Inspection
121485423 | other | HFTD Tier 2 | Transmission | 2021-05-29 | 2023-05-29 | Level 3 | F | 2024-04-23 | 2026-05-29 | Level 3 | GO 165 Inspection
121485742 | other | HFTD Tier 2 | Transmission | 2021-05-29 | 2023-05-29 | Level 3 | F | 2024-03-12 | 2026-05-29 | Level 3 | Standards change
121495397 | other | Non-HFTD | Transmission | 2021-06-09 | 2022-06-09 | Level 2 | E | 2023-11-29 | 2024-06-09 | Level 2 | Standards change
121495632 | pole | Non-HFTD | Transmission | 2021-06-09 | 2022-06-09 | Level 2 | E | 2024-10-14 | 2024-06-09 | Level 2 | Field Safety Reassessment
121496300 | pole | Non-HFTD | Transmission | 2021-06-09 | 2022-06-09 | Level 2 | E | 2024-08-30 | 2024-06-09 | Level 2 | GO 165 Inspection
121496631 | pole | Non-HFTD | Transmission | 2021-06-09 | 2022-06-09 | Level 2 | E | 2024-09-17 | 2024-06-09 | Level 2 | GO 165 Inspection
121497155 | insulator and brushing | Non-HFTD | Transmission | 2021-06-09 | 2022-06-09 | Level 2 | E | 2024-10-14 | 2024-06-09 | Level 2 | Field Safety Reassessment
121497338 | pole | Non-HFTD | Transmission | 2021-06-09 | 2022-06-09 | Level 2 | E | 2024-07-24 | 2024-06-09 | Level 2 | GO 165 Inspection
121499051 | pole | Non-HFTD | Transmission | 2021-06-03 | 2022-06-03 | Level 2 | E | 2024-09-26 | 2024-06-03 | Level 2 | GO 165 Inspection
121499818 | other | HFTD Tier 3 | Transmission | 2021-06-03 | 2023-06-03 | Level 3 | F | 2024-04-06 | 2026-06-03 | Level 3 | Standards change
121499939 | other | HFTD Tier 2 | Transmission | 2021-06-03 | 2023-06-03 | Level 3 | F | 2024-04-06 | 2026-06-03 | Level 3 | Standards change
121500430 | other | HFTD Tier 3 | Transmission | 2021-06-03 | 2023-06-03 | Level 3 | F | 2024-05-13 | 2026-06-03 | Level 3 | GO 165 Inspection
121512098 | other | HFTD Tier 3 | Transmission | 2021-06-05 | 2023-06-05 | Level 3 | F | 2024-02-26 | 2026-06-05 | Level 3 | GO 165 Inspection
121519836 | pole | Non-HFTD | Transmission | 2021-06-11 | 2022-06-11 | Level 2 | E | 2024-12-06 | 2024-06-11 | Level 2 | Field Safety Reassessment
121520409 | anchor/guy | Non-HFTD | Transmission | 2021-06-11 | 2022-06-11 | Level 2 | E | 2024-04-25 | 2026-06-11 | Level 3 | GO 165 Inspection
121520714 | other | Non-HFTD | Transmission | 2021-06-11 | 2022-06-11 | Level 2 | E | 2024-06-19 | 2024-06-11 | Level 2 | GO 165 Inspection
121524203 | other | HFTD Tier 2 | Transmission | 2021-06-08 | 2023-06-08 | Level 3 | F | 2024-05-03 | 2026-06-08 | Level 3 | GO 165 Inspection
121524465 | pole | HFTD Tier 2 | Transmission | 2021-06-11 | 2023-06-11 | Level 3 | F | 2024-05-02 | 2026-06-11 | Level 3 | GO 165 Inspection
121525167 | other | HFTD Tier 3 | Transmission | 2021-06-09 | 2023-06-09 | Level 3 | F | 2023-03-13 | 2026-06-09 | Level 3 | Standards change
121525230 | other | Non-HFTD | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2023-07-31 | 2026-06-12 | Level 3 | Standards change
121526679 | other | HFTD Tier 2 | Transmission | 2021-06-08 | 2023-06-08 | Level 3 | F | 2024-04-06 | 2026-06-08 | Level 3 | Standards change
121527145 | pole | HFTD Tier 2 | Transmission | 2021-06-08 | 2023-06-08 | Level 3 | F | 2024-05-21 | 2026-06-08 | Level 3 | GO 165 Inspection
121527561 | insulator and brushing | Non-HFTD | Transmission | 2021-06-12 | 2022-06-12 | Level 2 | E | 2024-04-05 | 2024-06-12 | Level 2 | GO 165 Inspection
121527845 | splice | Non-HFTD | Transmission | 2021-06-13 | 2022-06-13 | Level 2 | E | 2023-04-07 | 2024-06-13 | Level 2 | Standards change
121533332 | splice | Non-HFTD | Transmission | 2021-06-14 | 2022-06-14 | Level 2 | E | 2024-05-09 | 2024-06-12 | Level 2 | GO 165 Inspection
121533457 | pole | Non-HFTD | Transmission | 2021-06-14 | 2022-06-14 | Level 2 | E | 2023-11-29 | 2024-06-14 | Level 2 | Standards change
121533625 | insulator and brushing | Non-HFTD | Transmission | 2021-06-14 | 2022-06-14 | Level 2 | E | 2024-09-10 | 2024-06-14 | Level 2 | GO 165 Inspection
121536430 | other | HFTD Tier 2 | Transmission | 2021-06-14 | 2023-06-14 | Level 3 | F | 2023-05-09 | 2026-06-14 | Level 3 | Standards change
121541779 | insulator and brushing | Non-HFTD | Transmission | 2021-06-15 | 2022-06-15 | Level 2 | E | 2023-03-06 | 2024-06-15 | Level 2 | Standards change
121542918 | other | HFTD Tier 2 | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2024-05-06 | 2026-06-12 | Level 3 | GO 165 Inspection
121543186 | other | HFTD Tier 2 | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2024-04-06 | 2026-06-12 | Level 3 | Standards change
121545245 | other | HFTD Tier 2 | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2024-04-06 | 2026-06-12 | Level 3 | Standards change
121547355 | other | HFTD Tier 3 | Transmission | 2021-06-16 | 2023-06-16 | Level 3 | F | 2023-01-03 | 2026-06-16 | Level 3 | Standards change
121548524 | pole | Non-HFTD | Transmission | 2021-06-16 | 2022-06-16 | Level 2 | E | 2024-12-30 | 2024-06-16 | Level 2 | Field Safety Reassessment
121548905 | pole | Non-HFTD | Transmission | 2021-06-16 | 2022-06-16 | Level 2 | E | 2024-11-12 | 2024-06-16 | Level 2 | Field Safety Reassessment
121549306 | other | HFTD Tier 2 | Transmission | 2021-06-13 | 2023-06-13 | Level 3 | F | 2024-05-28 | 2026-06-13 | Level 3 | GO 165 Inspection
121550782 | other | HFTD Tier 2 | Transmission | 2021-06-13 | 2023-06-13 | Level 3 | F | 2024-06-03 | 2026-06-13 | Level 3 | GO 165 Inspection
121550880 | insulator and brushing | Non-HFTD | Transmission | 2021-06-13 | 2022-06-13 | Level 2 | E | 2024-10-01 | 2024-06-13 | Level 2 | GO 165 Inspection
121551230 | insulator and brushing | Non-HFTD | Transmission | 2021-06-13 | 2022-06-13 | Level 2 | E | 2024-05-22 | 2026-06-13 | Level 3 | GO 165 Inspection
121551644 | other | Non-HFTD | Transmission | 2021-06-16 | 2022-06-16 | Level 2 | E | 2024-09-13 | 2024-06-16 | Level 2 | GO 165 Inspection
121552091 | pole | Non-HFTD | Transmission | 2021-06-17 | 2022-06-17 | Level 2 | E | 2023-01-13 | 2024-06-17 | Level 2 | Standards change
121553064 | pole | Non-HFTD | Transmission | 2021-06-17 | 2022-06-17 | Level 2 | E | 2024-12-30 | 2024-06-17 | Level 2 | Field Safety Reassessment
121555092 | insulator and brushing | Non-HFTD | Transmission | 2021-06-17 | 2022-06-17 | Level 2 | E | 2024-07-10 | 2024-06-17 | Level 2 | GO 165 Inspection
121555157 | pole | Non-HFTD | Transmission | 2021-06-17 | 2022-06-17 | Level 2 | E | 2023-01-13 | 2024-06-17 | Level 2 | Standards change
121555555 | other | Non-HFTD | Transmission | 2021-06-17 | 2022-06-17 | Level 2 | E | 2023-02-03 | 2026-06-17 | Level 3 | Standards change
121555906 | pole | Non-HFTD | Transmission | 2021-06-17 | 2026-06-17 | Level 3 | F | 2023-12-28 | 2024-06-17 | Level 2 | Standards change
121556813 | other | HFTD Tier 2 | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2024-05-06 | 2026-06-12 | Level 3 | GO 165 Inspection
121556875 | other | Non-HFTD | Transmission | 2021-05-18 | 2023-05-18 | Level 3 | F | 2024-09-11 | 2026-05-18 | Level 3 | GO 165 Inspection
121556956 | anchor/guy | Non-HFTD | Transmission | 2021-06-14 | 2023-06-14 | Level 3 | F | 2024-05-09 | 2026-06-14 | Level 3 | GO 165 Inspection
121557011 | other | HFTD Tier 2 | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2024-05-06 | 2026-06-12 | Level 3 | GO 165 Inspection
121557270 | pole | Non-HFTD | Transmission | 2021-06-14 | 2022-06-14 | Level 2 | E | 2024-05-09 | 2024-06-14 | Level 2 | GO 165 Inspection
121560942 | other | Non-HFTD | Transmission | 2021-05-22 | 2023-05-22 | Level 3 | F | 2024-04-06 | 2026-05-22 | Level 3 | Standards change
121561187 | other | Non-HFTD | Transmission | 2021-06-18 | 2023-06-18 | Level 3 | F | 2024-04-06 | 2026-06-18 | Level 3 | Standards change
121561267 | other | Non-HFTD | Transmission | 2021-06-18 | 2023-06-18 | Level 3 | F | 2024-04-06 | 2026-06-18 | Level 3 | Standards change
121562681 | pole | Non-HFTD | Transmission | 2021-06-18 | 2022-06-18 | Level 2 | E | 2024-12-09 | 2024-06-18 | Level 2 | Field Safety Reassessment
121564188 | insulator and brushing | Non-HFTD | Transmission | 2021-06-18 | 2022-06-18 | Level 2 | E | 2024-09-16 | 2024-06-18 | Level 2 | GO 165 Inspection
121564501 | other | Non-HFTD | Transmission | 2021-06-18 | 2023-06-18 | Level 3 | F | 2024-04-06 | 2026-06-18 | Level 3 | Standards change
121564640 | other | Non-HFTD | Transmission | 2021-06-18 | 2023-06-18 | Level 3 | F | 2024-04-06 | 2026-06-18 | Level 3 | Standards change
121565770 | pole | HFTD Tier 3 | Transmission | 2021-06-07 | 2023-06-07 | Level 3 | F | 2024-05-08 | 2026-06-07 | Level 3 | GO 165 Inspection
121567928 | other | HFTD Tier 3 | Transmission | 2021-06-15 | 2023-06-15 | Level 3 | F | 2023-06-13 | 2026-06-15 | Level 3 | Standards change
121574710 | other | HFTD Tier 2 | Transmission | 2021-06-18 | 2023-06-18 | Level 3 | F | 2023-05-05 | 2026-06-18 | Level 3 | Standards change
121574738 | pole | Non-HFTD | Transmission | 2021-06-21 | 2022-06-21 | Level 2 | E | 2024-10-09 | 2026-06-21 | Level 3 | GO 165 Inspection
121574822 | pole | Non-HFTD | Transmission | 2021-06-21 | 2022-06-21 | Level 2 | E | 2024-11-08 | 2026-06-21 | Level 3 | GO 165 Inspection
121579430 | other | Non-HFTD | Transmission | 2021-06-22 | 2022-06-22 | Level 2 | E | 2023-03-03 | 2026-06-22 | Level 3 | Standards change
121579939 | other | Non-HFTD | Transmission | 2021-06-22 | 2022-06-22 | Level 2 | E | 2023-03-03 | 2026-06-22 | Level 3 | Standards change
121581228 | pole | Non-HFTD | Transmission | 2021-06-22 | 2024-06-22 | Level 2 | E | 2024-12-09 | 2022-06-22 | Level 2 | Field Safety Reassessment
121581496 | other | Non-HFTD | Transmission | 2021-06-22 | 2022-06-22 | Level 2 | E | 2024-06-17 | 2024-06-22 | Level 2 | Field Safety Reassessment
121581875 | pole | Non-HFTD | Transmission | 2021-06-22 | 2022-06-22 | Level 2 | E | 2024-12-03 | 2024-06-22 | Level 2 | Field Safety Reassessment
121582225 | other | Non-HFTD | Transmission | 2021-06-22 | 2022-06-22 | Level 2 | E | 2024-06-17 | 2024-06-22 | Level 2 | Field Safety Reassessment
121582378 | other | Non-HFTD | Transmission | 2021-06-22 | 2022-06-22 | Level 2 | E | 2023-02-17 | 2024-06-22 | Level 2 | Standards change
121582414 | other | Non-HFTD | Transmission | 2021-06-22 | 2023-06-22 | Level 3 | F | 2024-01-03 | 2026-06-22 | Level 3 | Standards change
121582437 | other | Non-HFTD | Transmission | 2021-06-22 | 2023-06-22 | Level 3 | F | 2024-04-06 | 2026-06-22 | Level 3 | Standards change
121584796 | pole | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-02-17 | 2024-06-23 | Level 2 | Standards change
121585201 | anchor/guy | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-10-17 | 2026-06-23 | Level 3 | GO 165 Inspection
121585487 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-04-29 | 2024-06-23 | Level 2 | GO 165 Inspection
121585608 | anchor/guy | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-17 | 2026-06-23 | Level 3 | Standards change
121585908 | anchor/guy | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-17 | 2026-06-23 | Level 3 | Standards change
121586041 | other | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-11-25 | 2024-06-23 | Level 2 | Field Safety Reassessment
121588544 | pole | Non-HFTD | Transmission | 2021-06-23 | 2024-06-23 | Level 2 | E | 2024-10-21 | 2021-12-23 | Level 2 | Field Safety Reassessment
121588676 | other | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-21 | 2024-06-23 | Level 2 | Standards change
121588677 | other | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-21 | 2024-06-23 | Level 2 | Standards change
121588679 | anchor/guy | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-21 | 2026-06-23 | Level 3 | Standards change
121588706 | anchor/guy | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-21 | 2026-06-23 | Level 3 | Standards change
121588945 | pole | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-02-01 | 2026-06-23 | Level 3 | Standards change
121588965 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121589398 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-01-02 | 2026-06-23 | Level 3 | Standards change
121589689 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-02-01 | 2024-06-23 | Level 2 | Standards change
121590766 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-11-21 | 2024-06-23 | Level 2 | Standards change
121591316 | other | Non-HFTD | Transmission | 2021-06-23 | 2024-06-23 | Level 2 | E | 2024-10-24 | 2022-06-23 | Level 2 | Field Safety Reassessment
121591476 | pole | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2023-01-23 | 2026-06-23 | Level 3 | Standards change
121591915 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-10-16 | 2024-06-23 | Level 2 | Field Safety Reassessment
121592429 | other | Non-HFTD | Transmission | 2021-06-24 | 2023-06-24 | Level 3 | F | 2024-04-06 | 2026-06-24 | Level 3 | Standards change
121592964 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-07-29 | 2024-06-24 | Level 2 | GO 165 Inspection
121593129 | other | Non-HFTD | Transmission | 2021-06-24 | 2023-06-24 | Level 3 | F | 2024-04-06 | 2026-06-24 | Level 3 | Standards change
121593906 | other | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-11-07 | 2026-06-24 | Level 3 | GO 165 Inspection
121593964 | other | Non-HFTD | Transmission | 2021-06-24 | 2023-06-24 | Level 3 | F | 2024-04-06 | 2026-06-24 | Level 3 | Standards change
121593979 | other | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-11-07 | 2022-06-24 | Level 2 | GO 165 Inspection
121595491 | anchor/guy | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-12-05 | 2026-06-24 | Level 3 | GO 165 Inspection
121595493 | anchor/guy | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-12-05 | 2026-06-24 | Level 3 | GO 165 Inspection
121595517 | insulator and brushing | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-07-22 | 2024-06-24 | Level 2 | GO 165 Inspection
121599083 | insulator and brushing | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2023-11-21 | 2024-06-25 | Level 2 | Standards change
121599334 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-12-13 | 2024-06-25 | Level 2 | Field Safety Reassessment
121599532 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2023-12-26 | 2026-06-25 | Level 3 | Standards change
121599955 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2023-12-26 | 2026-06-25 | Level 3 | Standards change
121600474 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-02-09 | 2024-06-25 | Level 2 | Field Safety Reassessment
121600917 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-09-24 | 2024-06-25 | Level 2 | GO 165 Inspection
121600919 | insulator and brushing | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2023-02-03 | 2024-06-25 | Level 2 | Standards change
121601034 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-09-26 | 2026-06-25 | Level 3 | GO 165 Inspection
121601313 | insulator and brushing | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-12-13 | 2024-06-25 | Level 2 | Field Safety Reassessment
121601929 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-04-06 | 2026-06-25 | Level 3 | Standards change
121603618 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121604362 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-08-28 | 2026-06-23 | Level 3 | GO 165 Inspection
121604363 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-08-28 | 2024-06-23 | Level 2 | GO 165 Inspection
121604981 | other | HFTD Tier 2 | Transmission | 2021-06-17 | 2023-06-17 | Level 3 | F | 2024-04-24 | 2026-06-17 | Level 3 | GO 165 Inspection
121606281 | conductor | Non-HFTD | Transmission | 2021-06-26 | 2022-06-26 | Level 2 | E | 2023-08-31 | 2024-06-26 | Level 2 | GO 165 Inspection
121607558 | other | Non-HFTD | Transmission | 2021-06-26 | 2022-06-26 | Level 2 | E | 2023-03-01 | 2026-06-26 | Level 3 | Standards change
121607592 | splice | Non-HFTD | Transmission | 2021-06-26 | 2022-06-26 | Level 2 | E | 2024-12-20 | 2024-06-26 | Level 2 | Field Safety Reassessment
121608242 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-11-07 | 2024-06-25 | Level 2 | Field Safety Reassessment
121608263 | anchor/guy | Non-HFTD | Transmission | 2021-06-26 | 2022-06-26 | Level 2 | E | 2024-01-09 | 2026-06-26 | Level 3 | Standards change
121608557 | other | Non-HFTD | Transmission | 2021-06-26 | 2023-06-26 | Level 3 | F | 2024-04-06 | 2026-06-26 | Level 3 | Standards change
121608843 | other | Non-HFTD | Transmission | 2021-06-24 | 2023-06-24 | Level 3 | F | 2024-04-06 | 2026-06-24 | Level 3 | Standards change
121609159 | other | Non-HFTD | Transmission | 2021-06-26 | 2023-06-26 | Level 3 | F | 2023-12-22 | 2026-06-26 | Level 3 | Standards change
121610199 | other | Non-HFTD | Transmission | 2021-06-26 | 2023-06-26 | Level 3 | F | 2023-12-22 | 2026-06-26 | Level 3 | Standards change
121610676 | anchor/guy | Non-HFTD | Transmission | 2021-06-27 | 2022-06-27 | Level 2 | E | 2023-11-08 | 2026-06-27 | Level 3 | Standards change
121610766 | insulator and brushing | Non-HFTD | Transmission | 2021-06-26 | 2022-06-26 | Level 2 | E | 2024-10-02 | 2024-06-26 | Level 2 | Field Safety Reassessment
121616842 | pole | Non-HFTD | Transmission | 2021-06-27 | 2022-06-27 | Level 2 | E | 2023-08-04 | 2024-06-27 | Level 2 | Standards change
121616999 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2023-07-20 | 2026-06-27 | Level 3 | Standards change
121617214 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2023-12-07 | 2026-06-27 | Level 3 | Standards change
121617712 | anchor/guy | Non-HFTD | Transmission | 2021-06-27 | 2022-06-27 | Level 2 | E | 2023-08-07 | 2026-06-27 | Level 3 | Standards change
121618286 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2024-07-29 | 2026-06-27 | Level 3 | GO 165 Inspection
121618324 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2024-01-04 | 2026-06-27 | Level 3 | Standards change
121618693 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2023-08-15 | 2026-07-02 | Level 3 | Standards change
121618874 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2023-08-15 | 2026-07-02 | Level 3 | Standards change
121621036 | other | Non-HFTD | Transmission | 2021-06-28 | 2023-06-28 | Level 3 | F | 2024-01-03 | 2026-06-28 | Level 3 | Standards change
121621310 | pole | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-08-01 | 2024-06-28 | Level 2 | Field Safety Reassessment
121621455 | other | Non-HFTD | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2024-04-06 | 2026-06-27 | Level 3 | Standards change
121621743 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-08-22 | 2024-06-23 | Level 2 | Field Safety Reassessment
121622011 | other | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2023-01-27 | 2024-06-28 | Level 2 | Standards change
121622090 | other | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2023-03-15 | 2024-06-28 | Level 2 | Standards change
121622188 | anchor/guy | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-09-06 | 2026-06-28 | Level 3 | GO 165 Inspection
121622655 | other | Non-HFTD | Transmission | 2021-06-28 | 2023-06-28 | Level 3 | F | 2024-08-21 | 2026-06-28 | Level 3 | GO 165 Inspection
121622757 | other | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2023-01-31 | 2024-06-28 | Level 2 | Standards change
121623395 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-11-18 | 2024-06-24 | Level 2 | Field Safety Reassessment
121623937 | other | Non-HFTD | Transmission | 2021-06-28 | 2023-06-28 | Level 3 | F | 2024-08-21 | 2026-06-28 | Level 3 | GO 165 Inspection
121624341 | other | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-06-06 | 2026-06-28 | Level 3 | GO 165 Inspection
121624785 | anchor/guy | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-09-06 | 2026-06-28 | Level 3 | GO 165 Inspection
121625021 | other | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-09-26 | 2026-06-28 | Level 3 | GO 165 Inspection
121625130 | pole | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-11-25 | 2024-06-28 | Level 2 | Field Safety Reassessment
121625848 | insulator and brushing | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2023-12-12 | 2024-06-28 | Level 2 | Standards change
121628459 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121628696 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121628742 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2023-02-03 | 2026-06-29 | Level 3 | Standards change
121628775 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-01-18 | 2026-06-29 | Level 3 | Standards change
121629102 | pole | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-09-20 | 2024-06-29 | Level 2 | GO 165 Inspection
121629209 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121629382 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-01-23 | 2026-06-29 | Level 3 | Standards change
121629539 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121629607 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121630337 | other | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-08-22 | 2026-06-29 | Level 3 | GO 165 Inspection
121630789 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121631821 | pole | Non-HFTD | Transmission | 2021-06-19 | 2022-06-19 | Level 2 | E | 2023-03-07 | 2024-06-19 | Level 2 | Standards change
121631922 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2023-03-01 | 2024-06-29 | Level 2 | Standards change
121633149 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121633389 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2023-03-31 | 2026-06-25 | Level 3 | Standards change
121633609 | crossarm | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-12-31 | 2024-06-28 | Level 2 | Field Safety Reassessment
121634025 | other | HFTD Tier 2 | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-06-08 | 2026-06-25 | Level 3 | GO 165 Inspection
121634172 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121634243 | other | Non-HFTD | Transmission | 2021-06-23 | 2026-06-23 | Level 3 | F |  | 2026-06-23 | Level 3
121634316 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-10-03 | 2024-06-24 | Level 2 | Field Safety Reassessment
121634404 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121634442 | pole | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-11-18 | 2024-06-23 | Level 2 | Field Safety Reassessment
121634482 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-10-01 | 2024-06-25 | Level 2 | Field Safety Reassessment
121634515 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121634586 | other | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2023-01-20 | 2024-06-23 | Level 2 | Standards change
121634591 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2023-03-31 | 2026-06-25 | Level 3 | Standards change
121634651 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121634653 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121634682 | insulator and brushing | Non-HFTD | Transmission | 2021-06-23 | 2022-06-23 | Level 2 | E | 2024-11-18 | 2024-06-23 | Level 2 | Field Safety Reassessment
121634931 | other | Non-HFTD | Transmission | 2021-06-23 | 2024-06-23 | Level 2 | E | 2024-10-24 | 2022-06-23 | Level 2 | Field Safety Reassessment
121635022 | anchor/guy | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2023-11-27 | 2026-06-24 | Level 3 | Standards change
121636179 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-10-23 | 2024-06-24 | Level 2 | Field Safety Reassessment
121636243 | anchor/guy | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2023-07-14 | 2024-06-25 | Level 2 | Standards change
121636375 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2023-03-08 | 2026-06-24 | Level 3 | Standards change
121636881 | other | Non-HFTD | Transmission | 2021-06-30 | 2023-06-30 | Level 3 | F | 2024-04-06 | 2026-06-30 | Level 3 | Standards change
121637279 | other | Non-HFTD | Transmission | 2021-06-30 | 2022-06-30 | Level 2 | E | 2023-11-27 | 2026-06-30 | Level 3 | Standards change
121637506 | anchor/guy | Non-HFTD | Transmission | 2021-06-26 | 2022-06-26 | Level 2 | E | 2023-11-27 | 2026-06-26 | Level 3 | Standards change
121637982 | other | HFTD Tier 3 | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-03-08 | 2026-06-25 | Level 3 | GO 165 Inspection
121638096 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-04-06 | 2026-06-25 | Level 3 | Standards change
121638526 | anchor/guy | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-11-05 | 2026-06-24 | Level 3 | GO 165 Inspection
121638581 | other | Non-HFTD | Transmission | 2021-06-30 | 2022-06-30 | Level 2 | E | 2024-12-30 | 2024-06-30 | Level 2 | Field Safety Reassessment
121638811 | other | Non-HFTD | Transmission | 2021-06-30 | 2022-06-30 | Level 2 | E | 2024-12-30 | 2024-06-30 | Level 2 | Field Safety Reassessment
121639956 | other | HFTD Tier 3 | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-02-28 | 2026-06-25 | Level 3 | GO 165 Inspection
121640189 | insulator and brushing | Non-HFTD | Transmission | 2021-06-30 | 2022-06-30 | Level 2 | E | 2023-11-27 | 2024-06-30 | Level 2 | Standards change
121640681 | other | Non-HFTD | Transmission | 2021-06-30 | 2022-06-30 | Level 2 | E | 2024-07-18 | 2024-06-30 | Level 2 | GO 165 Inspection
121641296 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121641430 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2023-03-31 | 2026-06-25 | Level 3 | Standards change
121641459 | other | HFTD Tier 3 | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-03-08 | 2026-06-25 | Level 3 | GO 165 Inspection
121641541 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-06-04 | 2024-06-25 | Level 2 | GO 165 Inspection
121641654 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2023-03-03 | 2026-06-25 | Level 3 | Standards change
121641731 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2024-05-06 | 2024-06-25 | Level 2 | Field Safety Reassessment
121642100 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-04-06 | 2026-06-25 | Level 3 | Standards change
121642162 | pole | Non-HFTD | Transmission | 2021-06-25 | 2022-06-25 | Level 2 | E | 2023-08-15 | 2024-06-25 | Level 2 | Standards change
121642165 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-04-06 | 2026-06-23 | Level 3 | Standards change
121642198 | other | Non-HFTD | Transmission | 2021-06-24 | 2023-06-24 | Level 3 | F | 2024-04-06 | 2026-06-24 | Level 3 | Standards change
121644107 | pole | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-07-25 | 2026-06-25 | Level 3 | GO 165 Inspection
121644537 | switch | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-22 | 2024-06-29 | Level 2 | Field Safety Reassessment
121644783 | pole | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-24 | 2024-06-29 | Level 2 | Field Safety Reassessment
121645714 | other | Non-HFTD | Transmission | 2021-07-01 | 2023-07-01 | Level 3 | F | 2024-04-06 | 2026-07-01 | Level 3 | Standards change
121646411 | anchor/guy | Non-HFTD | Transmission | 2021-07-01 | 2022-07-01 | Level 2 | E | 2024-09-20 | 2026-07-01 | Level 3 | GO 165 Inspection
121647115 | other | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2023-11-27 | 2026-06-28 | Level 3 | Standards change
121647422 | other | Non-HFTD | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F |  | 2026-06-23 | Level 3
121648925 | insulator and brushing | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-08-22 | 2024-06-28 | Level 2 | GO 165 Inspection
121649073 | other | HFTD Tier 2 | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-06-04 | 2026-06-25 | Level 3 | GO 165 Inspection
121649235 | pole | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-12-21 | 2024-06-28 | Level 2 | Field Safety Reassessment
121649309 | other | Non-HFTD | Transmission | 2021-06-28 | 2023-06-28 | Level 3 | F | 2024-04-06 | 2026-06-28 | Level 3 | Standards change
121653416 | anchor/guy | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-05-02 | 2026-06-28 | Level 3 | GO 165 Inspection
121653418 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-11-18 | 2024-06-24 | Level 2 | Field Safety Reassessment
121653427 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121653588 | pole | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-18 | 2024-06-29 | Level 2 | Field Safety Reassessment
121653759 | other | Non-HFTD | Transmission | 2021-06-28 | 2023-06-28 | Level 3 | F | 2024-06-25 | 2026-06-28 | Level 3 | GO 165 Inspection
121654255 | other | Non-HFTD | Transmission | 2021-06-24 | 2023-06-24 | Level 3 | F | 2023-03-31 | 2026-06-24 | Level 3 | Standards change
121654297 | other | HFTD Tier 2 | Transmission | 2021-06-27 | 2023-06-27 | Level 3 | F | 2024-04-06 | 2026-06-27 | Level 3 | Standards change
121654591 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2023-03-01 | 2026-07-02 | Level 3 | Standards change
121655045 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2023-11-27 | 2026-06-29 | Level 3 | Standards change
121655559 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-01-22 | 2026-06-29 | Level 3 | Standards change
121655743 | pole | Non-HFTD | Transmission | 2021-06-28 | 2022-06-28 | Level 2 | E | 2024-12-26 | 2024-06-28 | Level 2 | Field Safety Reassessment
121656078 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121656883 | crossarm | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-09-06 | 2022-06-29 | Level 2 | Field Safety Reassessment
121656932 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121657081 | other | Non-HFTD | Transmission | 2021-07-02 | 2024-07-02 | Level 2 | E | 2024-11-07 | 2026-07-02 | Level 3 | Field Safety Reassessment
121657154 | pole | Non-HFTD | Transmission | 2021-06-24 | 2022-06-24 | Level 2 | E | 2024-12-16 | 2024-06-24 | Level 2 | Field Safety Reassessment
121657585 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2023-11-27 | 2026-06-29 | Level 3 | Standards change
121658230 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121658706 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-01-26 | 2026-06-29 | Level 3 | Standards change
121659159 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-10-15 | 2026-06-29 | Level 3 | GO 165 Inspection
121659241 | splice | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2023-11-27 | 2024-07-02 | Level 2 | Standards change
121659250 | pole | Non-HFTD | Transmission | 2021-06-28 | 2023-06-28 | Level 3 | F | 2023-07-31 | 2026-06-28 | Level 3 | Standards change
121659480 | pole | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-07 | 2024-06-29 | Level 2 | Field Safety Reassessment
121659489 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121660217 | anchor/guy | Non-HFTD | Transmission | 2021-06-30 | 2022-06-30 | Level 2 | E | 2023-01-27 | 2026-06-30 | Level 3 | Standards change
121660546 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-01-11 | 2026-06-29 | Level 3 | Standards change
121660605 | pole | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-23 | 2024-06-29 | Level 2 | Field Safety Reassessment
121660608 | other | Non-HFTD | Transmission | 2021-07-01 | 2022-07-01 | Level 2 | E | 2023-01-25 | 2026-07-01 | Level 3 | Standards change
121660640 | pole | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-11-23 | 2024-07-02 | Level 2 | Field Safety Reassessment
121660676 | insulator and brushing | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-10-28 | 2024-07-02 | Level 2 | Field Safety Reassessment
121660861 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-07-22 | 2026-07-02 | Level 3 | GO 165 Inspection
121660865 | insulator and brushing | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-02-16 | 2024-07-02 | Level 2 | Standards change
121660989 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121661036 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121661101 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121661104 | other | Non-HFTD | Transmission | 2021-07-01 | 2023-07-01 | Level 3 | F | 2024-04-06 | 2026-07-01 | Level 3 | Standards change
121661454 | pole | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2024-07-10 | 2024-07-03 | Level 2 | Field Safety Reassessment
121661588 | other | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2024-11-07 | 2024-07-03 | Level 2 | Field Safety Reassessment
121661662 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2023-02-27 | 2026-07-02 | Level 3 | Standards change
121661665 | anchor/guy | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2023-03-09 | 2026-07-02 | Level 3 | Standards change
121661746 | other | Non-HFTD | Transmission | 2021-07-01 | 2024-07-01 | Level 2 | E | 2024-11-17 | 2026-07-01 | Level 3 | Field Safety Reassessment
121661971 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662194 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-04-06 | 2026-06-25 | Level 3 | Standards change
121662277 | pole | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2024-11-01 | 2024-07-03 | Level 2 | GO 165 Inspection
121662299 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662604 | insulator and brushing | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-17 | 2024-06-29 | Level 2 | Field Safety Reassessment
121662606 | insulator and brushing | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2023-01-27 | 2026-06-29 | Level 3 | Standards change
121662685 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662689 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662704 | insulator and brushing | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-12-23 | 2024-06-29 | Level 2 | Field Safety Reassessment
121662785 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662794 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662826 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2023-02-27 | 2026-07-02 | Level 3 | Standards change
121662872 | other | Non-HFTD | Transmission | 2021-07-01 | 2023-07-01 | Level 3 | F | 2024-04-06 | 2026-07-01 | Level 3 | Standards change
121662874 | other | Non-HFTD | Transmission | 2021-07-01 | 2023-07-01 | Level 3 | F | 2024-04-06 | 2026-07-01 | Level 3 | Standards change
121662905 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121662959 | other | Non-HFTD | Transmission | 2021-07-03 | 2023-07-03 | Level 3 | F | 2023-02-13 | 2026-07-03 | Level 3 | Standards change
121663021 | other | Non-HFTD | Transmission | 2021-06-30 | 2023-06-30 | Level 3 | F | 2024-04-06 | 2026-06-30 | Level 3 | Standards change
121663987 | pole | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-12-03 | 2024-07-02 | Level 2 | Field Safety Reassessment
121664055 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121664645 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121664760 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121665655 | pole | HFTD Tier 3 | Transmission | 2021-06-30 | 2023-06-30 | Level 3 | F | 2024-05-23 | 2026-06-30 | Level 3 | GO 165 Inspection
121666101 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121666316 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121667450 | insulator and brushing | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-11-17 | 2024-06-29 | Level 2 | Field Safety Reassessment
121667681 | other | Non-HFTD | Transmission | 2021-07-06 | 2022-07-06 | Level 2 | E | 2024-12-06 | 2024-07-03 | Level 2 | Field Safety Reassessment
121668232 | other | Non-HFTD | Transmission | 2021-07-03 | 2023-07-03 | Level 3 | F | 2024-02-29 | 2026-07-03 | Level 3 | Standards change
121668630 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121668717 | other | HFTD Tier 2 | Transmission | 2021-07-01 | 2023-07-01 | Level 3 | F | 2023-02-16 | 2026-07-01 | Level 3 | Standards change
121668912 | other | HFTD Tier 2 | Transmission | 2021-06-23 | 2023-06-23 | Level 3 | F | 2024-03-21 | 2026-06-23 | Level 3 | Standards change
121673582 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-07-24 | 2026-07-02 | Level 3 | GO 165 Inspection
121674379 | pole | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2024-11-22 | 2024-07-07 | Level 2 | Field Safety Reassessment
121675120 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121675122 | pole | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-12-08 | 2024-06-29 | Level 2 | Field Safety Reassessment
121675910 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121677328 | other | Non-HFTD | Transmission | 2021-06-30 | 2023-06-30 | Level 3 | F | 2024-04-06 | 2026-06-30 | Level 3 | Standards change
121678975 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-02-28 | 2026-07-02 | Level 3 | Standards change
121678978 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121679022 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-10-31 | 2026-07-02 | Level 3 | GO 165 Inspection
121679025 | insulator and brushing | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-10-31 | 2024-07-02 | Level 2 | GO 165 Inspection
121679392 | pole | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-07-10 | 2024-07-02 | Level 2 | Field Safety Reassessment
121680199 | other | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2024-09-03 | 2026-07-07 | Level 3 | GO 165 Inspection
121681425 | other | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-11-17 | 2024-07-08 | Level 2 | Field Safety Reassessment
121682306 | insulator and brushing | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-08-16 | 2024-07-08 | Level 2 | GO 165 Inspection
121683885 | insulator and brushing | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-11-30 | 2024-07-08 | Level 2 | Field Safety Reassessment
121684914 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121684924 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-02-22 | 2024-07-08 | Level 2 | Field Safety Reassessment
121685000 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121685070 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121685076 | pole | Non-HFTD | Transmission | 2021-07-05 | 2022-07-05 | Level 2 | E | 2024-07-10 | 2024-07-05 | Level 2 | Field Safety Reassessment
121685080 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121685227 | pole | Non-HFTD | Transmission | 2021-07-05 | 2022-07-05 | Level 2 | E | 2024-12-14 | 2024-07-05 | Level 2 | Field Safety Reassessment
121685378 | insulator and brushing | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-10-31 | 2024-07-02 | Level 2 | GO 165 Inspection
121685452 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-12-03 | 2024-07-02 | Level 2 | Field Safety Reassessment
121685514 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121685617 | other | HFTD Tier 3 | Transmission | 2021-06-12 | 2023-06-12 | Level 3 | F | 2024-02-29 | 2026-06-12 | Level 3 | Standards change
121685631 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-11-24 | 2024-07-02 | Level 2 | Field Safety Reassessment
121685758 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-04-06 | 2026-07-02 | Level 3 | Standards change
121685803 | other | Non-HFTD | Transmission | 2021-07-02 | 2022-07-02 | Level 2 | E | 2024-07-26 | 2022-07-02 | Level 2 | GO 165 Inspection
121687365 | other | Non-HFTD | Transmission | 2021-07-03 | 2023-07-03 | Level 3 | F | 2024-04-06 | 2026-07-03 | Level 3 | Standards change
121687420 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121687938 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-02-22 | 2024-07-08 | Level 2 | Field Safety Reassessment
121688086 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2023-09-18 | 2026-07-02 | Level 3 | Standards change
121689443 | other | Non-HFTD | Transmission | 2021-07-02 | 2023-07-02 | Level 3 | F | 2024-05-14 | 2026-07-02 | Level 3 | GO 165 Inspection
121689450 | other | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2024-01-24 | 2026-07-03 | Level 3 | Standards change
121689611 | anchor/guy | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2023-11-28 | 2026-07-03 | Level 3 | Standards change
121689910 | other | Non-HFTD | Transmission | 2021-06-25 | 2023-06-25 | Level 3 | F | 2024-04-06 | 2026-06-25 | Level 3 | Standards change
121690809 | other | Non-HFTD | Transmission | 2021-06-29 | 2023-06-29 | Level 3 | F | 2024-04-06 | 2026-06-29 | Level 3 | Standards change
121690904 | insulator and brushing | Non-HFTD | Transmission | 2021-07-09 | 2022-07-09 | Level 2 | E | 2024-11-17 | 2024-07-09 | Level 2 | Field Safety Reassessment
121691120 | other | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2024-12-13 | 2024-07-03 | Level 2 | Field Safety Reassessment
121705845 | other | Non-HFTD | Transmission | 2021-07-10 | 2023-07-10 | Level 3 | F | 2023-02-27 | 2026-07-10 | Level 3 | Standards change
121706049 | insulator and brushing | Non-HFTD | Transmission | 2021-07-10 | 2022-07-10 | Level 2 | E | 2024-08-16 | 2024-07-10 | Level 2 | Field Safety Reassessment
121706214 | anchor/guy | Non-HFTD | Transmission | 2021-07-10 | 2022-07-10 | Level 2 | E | 2024-01-17 | 2026-07-10 | Level 3 | Standards change
121707544 | pole | Non-HFTD | Transmission | 2021-07-07 | 2024-07-07 | Level 2 | E | 2024-11-23 | 2022-07-07 | Level 2 | Field Safety Reassessment
121707577 | other | Non-HFTD | Transmission | 2021-07-05 | 2023-07-05 | Level 3 | F | 2024-10-09 | 2026-07-05 | Level 3 | GO 165 Inspection
121707824 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-12-10 | 2024-07-08 | Level 2 | Field Safety Reassessment
121712254 | anchor/guy | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2024-01-17 | 2026-07-12 | Level 3 | Standards change
121712285 | pole | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2024-01-16 | 2024-07-12 | Level 2 | Field Safety Reassessment
121712455 | pole | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2024-01-16 | 2024-07-12 | Level 2 | Field Safety Reassessment
121714248 | anchor/guy | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2023-01-30 | 2026-07-07 | Level 3 | Standards change
121714440 | pole | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2024-08-22 | 2024-07-12 | Level 2 | Field Safety Reassessment
121714801 | anchor/guy | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2024-01-03 | 2026-07-03 | Level 3 | Standards change
121715567 | pole | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2024-08-22 | 2024-07-12 | Level 2 | GO 165 Inspection
121717252 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121717328 | anchor/guy | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2023-12-04 | 2026-07-08 | Level 3 | Standards change
121717739 | insulator and brushing | Non-HFTD | Transmission | 2021-07-03 | 2022-07-03 | Level 2 | E | 2023-01-26 | 2024-07-03 | Level 2 | Standards change
121718688 | pole | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2024-11-17 | 2022-01-12 | Level 2 | Field Safety Reassessment
121720501 | pole | Non-HFTD | Transmission | 2021-07-13 | 2022-07-13 | Level 2 | E | 2024-08-02 | 2024-07-13 | Level 2 | Field Safety Reassessment
121720741 | anchor/guy | Non-HFTD | Transmission | 2021-07-13 | 2022-07-13 | Level 2 | E | 2024-01-29 | 2026-07-13 | Level 3 | Standards change
121721078 | pole | Non-HFTD | Transmission | 2021-07-13 | 2022-07-13 | Level 2 | E | 2024-10-29 | 2022-07-13 | Level 2 | Field Safety Reassessment
121721906 | anchor/guy | Non-HFTD | Transmission | 2021-06-29 | 2022-06-29 | Level 2 | E | 2024-01-26 | 2026-06-29 | Level 3 | Standards change
121722173 | anchor/guy | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-01-17 | 2026-07-08 | Level 3 | Standards change
121722394 | insulator and brushing | Non-HFTD | Transmission | 2021-07-06 | 2022-07-06 | Level 2 | E | 2023-12-04 | 2026-07-06 | Level 3 | Standards change
121722508 | other | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2023-02-28 | 2026-07-08 | Level 3 | Standards change
121723547 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-02-22 | 2024-07-08 | Level 2 | Field Safety Reassessment
121723768 | anchor/guy | Non-HFTD | Transmission | 2021-07-13 | 2022-07-13 | Level 2 | E | 2024-11-19 | 2024-07-13 | Level 2 | GO 165 Inspection
121724479 | other | Non-HFTD | Transmission | 2021-07-06 | 2023-07-06 | Level 3 | F | 2024-10-31 | 2026-07-06 | Level 3 | GO 165 Inspection
121724743 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121724855 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121725005 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-11-12 | 2024-07-08 | Level 2 | Field Safety Reassessment
121725278 | insulator and brushing | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2023-12-04 | 2026-07-07 | Level 3 | Standards change
121725299 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-01-09 | 2026-07-08 | Level 3 | Standards change
121725465 | insulator and brushing | Non-HFTD | Transmission | 2021-07-06 | 2022-07-06 | Level 2 | E | 2023-12-04 | 2026-07-06 | Level 3 | Standards change
121726277 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121726466 | anchor/guy | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-11-04 | 2026-07-14 | Level 3 | GO 165 Inspection
121728298 | anchor/guy | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2024-01-30 | 2026-07-07 | Level 3 | Standards change
121728473 | anchor/guy | Non-HFTD | Transmission | 2021-07-14 | 2022-07-14 | Level 2 | E | 2024-10-01 | 2026-07-14 | Level 3 | GO 165 Inspection
121731339 | insulator and brushing | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-09-30 | 2024-07-08 | Level 2 | Field Safety Reassessment
121731431 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121731568 | other | Non-HFTD | Transmission | 2021-07-08 | 2024-07-08 | Level 2 | E | 2024-11-26 | 2026-07-08 | Level 3 | Field Safety Reassessment
121731625 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-12-31 | 2024-07-08 | Level 2 | Field Safety Reassessment
121731677 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121731684 | pole | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2024-11-27 | 2024-07-07 | Level 2 | Field Safety Reassessment
121731748 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-01-09 | 2026-07-08 | Level 3 | Standards change
121731769 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121731775 | anchor/guy | Non-HFTD | Transmission | 2021-07-07 | 2022-07-07 | Level 2 | E | 2023-01-06 | 2024-07-07 | Level 2 | Standards change
121731801 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-02-22 | 2024-07-08 | Level 2 | Field Safety Reassessment
121731850 | insulator and brushing | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-12-10 | 2024-07-08 | Level 2 | Field Safety Reassessment
121731851 | pole | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-12-10 | 2024-07-08 | Level 2 | Field Safety Reassessment
121731963 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121731968 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121732142 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-02-28 | 2026-07-08 | Level 3 | Standards change
121732263 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121732392 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-08-16 | 2026-07-08 | Level 3 | GO 165 Inspection
121733399 | pole | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-06-18 | 2026-07-14 | Level 3 | GO 165 Inspection
121733481 | other | Non-HFTD | Transmission | 2021-07-15 | 2022-07-15 | Level 2 | E | 2024-08-02 | 2024-07-15 | Level 2 | Field Safety Reassessment
121734243 | splice | Non-HFTD | Transmission | 2021-07-15 | 2022-07-15 | Level 2 | E | 2023-11-28 | 2024-07-15 | Level 2 | Standards change
121734654 | other | Non-HFTD | Transmission | 2021-07-15 | 2023-07-15 | Level 3 | F | 2024-08-05 | 2026-07-15 | Level 3 | GO 165 Inspection
121734964 | other | Non-HFTD | Transmission | 2021-07-15 | 2022-07-15 | Level 2 | E | 2024-09-19 | 2024-07-15 | Level 2 | GO 165 Inspection
121735018 | pole | Non-HFTD | Transmission | 2021-07-15 | 2022-07-15 | Level 2 | E | 2024-11-22 | 2024-07-15 | Level 2 | Field Safety Reassessment
121735232 | insulator and brushing | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2023-11-29 | 2022-07-08 | Level 2 | Standards change
121736814 | other | HFTD Tier 2 | Transmission | 2021-07-12 | 2023-07-12 | Level 3 | F | 2024-04-06 | 2026-07-12 | Level 3 | Standards change
121737067 | anchor/guy | Non-HFTD | Transmission | 2021-07-15 | 2022-07-15 | Level 2 | E | 2023-11-29 | 2026-07-15 | Level 3 | Standards change
121737360 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-02-15 | 2026-07-08 | Level 3 | Standards change
121738286 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121738330 | pole | Non-HFTD | Transmission | 2021-07-09 | 2022-07-09 | Level 2 | E | 2024-09-10 | 2024-07-09 | Level 2 | Field Safety Reassessment
121738462 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121738496 | insulator and brushing | Non-HFTD | Transmission | 2021-07-08 | 2022-07-08 | Level 2 | E | 2024-12-16 | 2024-07-08 | Level 2 | Field Safety Reassessment
121738570 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121738780 | pole | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2023-12-06 | 2026-07-09 | Level 3 | Standards change
121738834 | insulator and brushing | Non-HFTD | Transmission | 2021-07-12 | 2022-07-12 | Level 2 | E | 2023-11-29 | 2026-07-12 | Level 3 | Standards change
121741110 | other | Non-HFTD | Transmission | 2021-07-09 | 2023-07-09 | Level 3 | F | 2024-04-06 | 2026-07-09 | Level 3 | Standards change
121741598 | other | Non-HFTD | Transmission | 2021-07-13 | 2023-07-13 | Level 3 | F | 2024-04-06 | 2026-07-13 | Level 3 | Standards change
121742045 | other | Non-HFTD | Transmission | 2021-07-08 | 2023-07-08 | Level 3 | F | 2024-04-06 | 2026-07-08 | Level 3 | Standards change
121742207 | pole | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-08-01 | 2024-07-16 | Level 2 | Field Safety Reassessment
121744849 | pole | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-11-18 | 2024-07-16 | Level 2 | Field Safety Reassessment
121745571 | pole | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-08-01 | 2024-07-16 | Level 2 | Field Safety Reassessment
121745734 | other | HFTD Tier 2 | Transmission | 2021-07-12 | 2023-07-12 | Level 3 | F | 2024-04-06 | 2026-07-12 | Level 3 | Standards change
121747000 | other | HFTD Tier 2 | Transmission | 2021-07-15 | 2023-07-15 | Level 3 | F | 2024-05-02 | 2026-07-15 | Level 3 | GO 165 Inspection
121748160 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121748161 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121748182 | other | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-04-06 | 2026-07-14 | Level 3 | Standards change
121748248 | other | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-04-06 | 2026-07-14 | Level 3 | Standards change
121748382 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121748732 | pole | Non-HFTD | Transmission | 2021-07-17 | 2022-07-17 | Level 2 | E | 2024-01-11 | 2024-07-17 | Level 2 | Field Safety Reassessment
121748767 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121749075 | other | Non-HFTD | Transmission | 2021-07-17 | 2023-07-17 | Level 3 | F | 2024-04-06 | 2026-07-17 | Level 3 | Standards change
121749116 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121749151 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121749369 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121749551 | anchor/guy | Non-HFTD | Transmission | 2021-07-17 | 2022-07-17 | Level 2 | E | 2023-11-27 | 2026-07-17 | Level 3 | Standards change
121749799 | pole | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2023-12-06 | 2026-07-14 | Level 3 | Standards change
121749807 | other | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-04-06 | 2026-07-14 | Level 3 | Standards change
121749892 | pole | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2023-12-13 | 2026-07-14 | Level 3 | Standards change
121749910 | other | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-04-06 | 2026-07-14 | Level 3 | Standards change
121749923 | other | HFTD Tier 2 | Transmission | 2021-07-12 | 2023-07-12 | Level 3 | F | 2023-05-23 | 2026-07-12 | Level 3 | Standards change
121749926 | other | HFTD Tier 2 | Transmission | 2021-07-15 | 2023-07-15 | Level 3 | F | 2023-05-06 | 2026-07-15 | Level 3 | Standards change
121749936 | pole | Non-HFTD | Transmission | 2021-07-17 | 2022-07-17 | Level 2 | E | 2024-08-22 | 2024-07-17 | Level 2 | Field Safety Reassessment
121750168 | other | Non-HFTD | Transmission | 2021-07-17 | 2023-07-17 | Level 3 | F | 2024-04-06 | 2026-07-17 | Level 3 | Standards change
121750271 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121750329 | other | HFTD Tier 2 | Transmission | 2021-07-12 | 2023-07-12 | Level 3 | F | 2024-04-06 | 2026-07-12 | Level 3 | Standards change
121750404 | other | Non-HFTD | Transmission | 2021-07-17 | 2023-07-17 | Level 3 | F | 2024-04-06 | 2026-07-17 | Level 3 | Standards change
121750428 | other | Non-HFTD | Transmission | 2021-07-15 | 2023-07-15 | Level 3 | F | 2024-04-06 | 2026-07-15 | Level 3 | Standards change
121750439 | other | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-04-06 | 2026-07-14 | Level 3 | Standards change
121750466 | other | Non-HFTD | Transmission | 2021-07-15 | 2023-07-15 | Level 3 | F | 2024-04-06 | 2026-07-15 | Level 3 | Standards change
121750522 | other | Non-HFTD | Transmission | 2021-07-14 | 2023-07-14 | Level 3 | F | 2024-04-06 | 2026-07-14 | Level 3 | Standards change
121750539 | pole | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-09-17 | 2024-07-16 | Level 2 | Field Safety Reassessment
121750616 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121750835 | other | HFTD Tier 2 | Transmission | 2021-07-17 | 2023-07-17 | Level 3 | F | 2023-04-28 | 2026-07-17 | Level 3 | Standards change
121750836 | pole | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-09-17 | 2022-07-16 | Level 2 | Field Safety Reassessment
121750974 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121753502 | other | HFTD Tier 3 | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2024-03-08 | 2026-07-19 | Level 3 | GO 165 Inspection
121753706 | pole | Non-HFTD | Transmission | 2021-07-19 | 2022-07-19 | Level 2 | E | 2024-08-22 | 2024-07-19 | Level 2 | Field Safety Reassessment
121753861 | insulator and brushing | Non-HFTD | Transmission | 2021-07-19 | 2022-07-19 | Level 2 | E | 2024-11-18 | 2024-07-19 | Level 2 | Field Safety Reassessment
121754357 | other | Non-HFTD | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2024-02-28 | 2026-07-19 | Level 3 | Standards change
121754411 | insulator and brushing | Non-HFTD | Transmission | 2021-07-19 | 2022-07-19 | Level 2 | E | 2024-10-29 | 2024-07-19 | Level 2 | Field Safety Reassessment
121754466 | other | Non-HFTD | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2024-12-18 | 2026-07-19 | Level 3 | Standards change
121754822 | other | Non-HFTD | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2024-04-06 | 2026-07-19 | Level 3 | Standards change
121758771 | insulator and brushing | Non-HFTD | Transmission | 2021-07-19 | 2024-07-19 | Level 2 | E | 2024-11-05 | 2026-07-19 | Level 3 | GO 165 Inspection
121760016 | other | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2023-01-31 | 2024-07-20 | Level 2 | Standards change
121760990 | other | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2023-01-31 | 2026-07-20 | Level 3 | Standards change
121762290 | other | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2024-04-06 | 2026-07-20 | Level 3 | Standards change
121762618 | other | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2024-11-13 | 2026-07-20 | Level 3 | GO 165 Inspection
121766031 | insulator and brushing | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2022-12-15 | 2024-07-20 | Level 2 | Standards change
121767586 | insulator and brushing | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2023-11-27 | 2026-07-16 | Level 3 | Standards change
121767588 | pole | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2023-08-01 | 2024-07-20 | Level 2 | Standards change
121769205 | other | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-04-06 | 2026-07-21 | Level 3 | Standards change
121769627 | other | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-04-06 | 2026-07-21 | Level 3 | Standards change
121777302 | anchor/guy | Non-HFTD | Transmission | 2021-07-22 | 2022-07-22 | Level 2 | E | 2024-09-19 | 2026-07-22 | Level 3 | GO 165 Inspection
121777857 | other | Non-HFTD | Transmission | 2021-07-22 | 2023-07-22 | Level 3 | F | 2024-04-06 | 2026-07-22 | Level 3 | Standards change
121777917 | other | Non-HFTD | Transmission | 2021-07-22 | 2023-07-22 | Level 3 | F | 2024-04-06 | 2026-07-22 | Level 3 | Standards change
121778244 | insulator and brushing | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-11-19 | 2024-07-16 | Level 2 | Field Safety Reassessment
121778730 | anchor/guy | Non-HFTD | Transmission | 2021-07-22 | 2022-07-22 | Level 2 | E | 2023-11-28 | 2026-07-22 | Level 3 | Standards change
121779206 | anchor/guy | Non-HFTD | Transmission | 2021-07-22 | 2022-07-22 | Level 2 | E | 2023-11-28 | 2026-07-22 | Level 3 | Standards change
121783063 | pole | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2024-07-19 | 2026-07-20 | Level 3 | GO 165 Inspection
121783090 | other | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2024-04-06 | 2026-07-20 | Level 3 | Standards change
121783198 | other | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-05-06 | 2026-07-21 | Level 3 | GO 165 Inspection
121783202 | other | Non-HFTD | Transmission | 2021-07-16 | 2023-07-16 | Level 3 | F | 2024-04-06 | 2026-07-16 | Level 3 | Standards change
121783208 | pole | Non-HFTD | Transmission | 2021-07-16 | 2022-07-16 | Level 2 | E | 2024-09-27 | 2024-07-16 | Level 2 | Field Safety Reassessment
121783446 | other | Non-HFTD | Transmission | 2021-07-19 | 2022-07-19 | Level 2 | E | 2024-11-26 | 2024-07-19 | Level 2 | Field Safety Reassessment
121783764 | other | Non-HFTD | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2024-09-20 | 2026-07-19 | Level 3 | GO 165 Inspection
121783979 | other | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2024-04-06 | 2026-07-20 | Level 3 | Standards change
121783980 | other | Non-HFTD | Transmission | 2021-07-19 | 2024-07-19 | Level 2 | E | 2024-08-23 | 2022-07-19 | Level 2 | GO 165 Inspection
121784097 | other | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2024-02-15 | 2026-07-20 | Level 3 | Standards change
121784113 | other | Non-HFTD | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2023-07-29 | 2026-07-19 | Level 3 | Standards change
121784994 | insulator and brushing | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2023-11-28 | 2024-07-20 | Level 2 | Standards change
121785150 | other | Non-HFTD | Transmission | 2021-07-19 | 2023-07-19 | Level 3 | F | 2024-04-06 | 2026-07-19 | Level 3 | Standards change
121787154 | other | HFTD Tier 2 | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2023-02-21 | 2026-07-21 | Level 3 | Standards change
121787290 | other | HFTD Tier 2 | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2023-02-21 | 2026-07-21 | Level 3 | Standards change
121787659 | other | HFTD Tier 2 | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-04-26 | 2026-07-21 | Level 3 | GO 165 Inspection
121788685 | pole | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2024-06-14 | 2024-07-20 | Level 2 | Field Safety Reassessment
121788687 | other | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2024-06-14 | 2024-07-20 | Level 2 | Field Safety Reassessment
121790359 | insulator and brushing | Non-HFTD | Transmission | 2021-07-21 | 2022-07-21 | Level 2 | E | 2024-10-03 | 2024-07-21 | Level 2 | Field Safety Reassessment
121790424 | other | Non-HFTD | Transmission | 2021-07-24 | 2023-07-24 | Level 3 | F | 2024-04-06 | 2026-07-24 | Level 3 | Standards change
121790778 | pole | Non-HFTD | Transmission | 2021-07-20 | 2022-07-20 | Level 2 | E | 2024-07-31 | 2024-07-20 | Level 2 | GO 165 Inspection
121790899 | other | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2023-08-01 | 2026-07-21 | Level 3 | Standards change
121792688 | other | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-04-06 | 2026-07-21 | Level 3 | Standards change
121792710 | anchor/guy | Non-HFTD | Transmission | 2021-07-21 | 2022-07-21 | Level 2 | E | 2023-07-29 | 2026-07-21 | Level 3 | Standards change
121793140 | other | Non-HFTD | Transmission | 2021-07-22 | 2023-07-22 | Level 3 | F | 2024-04-06 | 2026-07-22 | Level 3 | Standards change
121793361 | pole | Non-HFTD | Transmission | 2021-07-22 | 2023-07-22 | Level 3 | F | 2024-01-19 | 2026-07-22 | Level 3 | Standards change
121795542 | other | Non-HFTD | Transmission | 2021-07-26 | 2023-07-26 | Level 3 | F | 2024-04-06 | 2026-07-26 | Level 3 | Standards change
121796254 | other | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-04-06 | 2026-07-21 | Level 3 | Standards change
121797045 | insulator and brushing | Non-HFTD | Transmission | 2021-07-26 | 2022-07-26 | Level 2 | E | 2024-11-30 | 2024-07-26 | Level 2 | Field Safety Reassessment
121798633 | other | Non-HFTD | Transmission | 2021-07-26 | 2024-07-26 | Level 2 | E | 2024-09-16 | 2022-07-26 | Level 2 | GO 165 Inspection
121801797 | other | Non-HFTD | Transmission | 2021-07-27 | 2023-07-27 | Level 3 | F | 2024-04-06 | 2026-07-27 | Level 3 | Standards change
121806356 | other | HFTD Tier 2 | Transmission | 2021-07-26 | 2023-07-26 | Level 3 | F | 2024-06-07 | 2026-07-26 | Level 3 | GO 165 Inspection
121806724 | insulator and brushing | Non-HFTD | Transmission | 2021-07-28 | 2022-07-28 | Level 2 | E | 2024-07-19 | 2026-07-28 | Level 3 | GO 165 Inspection
121807754 | pole | Non-HFTD | Transmission | 2021-07-28 | 2022-07-28 | Level 2 | E | 2022-12-15 | 2024-07-28 | Level 2 | Standards change
121807778 | pole | Non-HFTD | Transmission | 2021-07-28 | 2022-07-28 | Level 2 | E | 2024-10-25 | 2024-07-28 | Level 2 | GO 165 Inspection
121809304 | pole | Non-HFTD | Transmission | 2021-07-28 | 2022-07-28 | Level 2 | E | 2024-01-11 | 2024-07-28 | Level 2 | Field Safety Reassessment
121809342 | pole | Non-HFTD | Transmission | 2021-07-28 | 2022-07-28 | Level 2 | E | 2024-02-29 | 2024-07-28 | Level 2 | Field Safety Reassessment
121809611 | other | HFTD Tier 2 | Transmission | 2021-07-27 | 2023-07-27 | Level 3 | F | 2024-05-20 | 2026-07-27 | Level 3 | GO 165 Inspection
121809796 | other | Non-HFTD | Transmission | 2021-07-28 | 2023-07-28 | Level 3 | F | 2024-04-06 | 2026-07-28 | Level 3 | Standards change
121810860 | other | HFTD Tier 2 | Transmission | 2021-07-28 | 2023-07-28 | Level 3 | F | 2024-06-20 | 2026-07-28 | Level 3 | GO 165 Inspection
121813140 | other | Non-HFTD | Transmission | 2021-07-29 | 2022-07-29 | Level 2 | E | 2023-11-22 | 2026-07-29 | Level 3 | Standards change
121814288 | pole | Non-HFTD | Transmission | 2021-07-29 | 2022-07-29 | Level 2 | E | 2024-12-09 | 2024-07-29 | Level 2 | Field Safety Reassessment
121814470 | pole | Non-HFTD | Transmission | 2021-07-29 | 2022-07-29 | Level 2 | E | 2024-11-09 | 2024-07-29 | Level 2 | GO 165 Inspection
121814539 | pole | Non-HFTD | Transmission | 2021-07-29 | 2022-07-29 | Level 2 | E | 2024-10-22 | 2022-07-29 | Level 2 | GO 165 Inspection
121814554 | pole | Non-HFTD | Transmission | 2021-07-29 | 2024-07-29 | Level 2 | E | 2024-10-21 | 2022-07-29 | Level 2 | GO 165 Inspection
121814630 | insulator and brushing | Non-HFTD | Transmission | 2021-07-29 | 2022-07-29 | Level 2 | E | 2024-09-24 | 2024-07-29 | Level 2 | GO 165 Inspection
121814635 | insulator and brushing | Non-HFTD | Transmission | 2021-07-29 | 2024-07-29 | Level 2 | E | 2024-09-25 | 2021-10-29 | Level 2 | GO 165 Inspection
121814643 | insulator and brushing | Non-HFTD | Transmission | 2021-07-29 | 2024-07-29 | Level 2 | E | 2024-10-15 | 2022-07-29 | Level 2 | Field Safety Reassessment
121814738 | other | Non-HFTD | Transmission | 2021-07-29 | 2023-07-29 | Level 3 | F | 2024-04-06 | 2026-07-29 | Level 3 | Standards change
121814799 | pole | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2023-08-04 | 2026-07-21 | Level 3 | Standards change
121815466 | pole | Non-HFTD | Transmission | 2021-07-28 | 2021-10-28 | Level 2 | E | 2024-12-23 | 2021-10-28 | Level 2 | Field Safety Reassessment
121815708 | other | Non-HFTD | Transmission | 2021-07-20 | 2023-07-20 | Level 3 | F | 2024-04-06 | 2026-07-20 | Level 3 | Standards change
121815903 | insulator and brushing | Non-HFTD | Transmission | 2021-07-27 | 2022-07-27 | Level 2 | E | 2024-12-11 | 2024-07-27 | Level 2 | Field Safety Reassessment
121816032 | anchor/guy | Non-HFTD | Transmission | 2021-07-27 | 2022-07-27 | Level 2 | E | 2023-07-19 | 2026-07-27 | Level 3 | Standards change
121816649 | pole | Non-HFTD | Transmission | 2021-07-27 | 2022-07-27 | Level 2 | E | 2024-08-01 | 2024-07-27 | Level 2 | GO 165 Inspection
121819413 | pole | Non-HFTD | Transmission | 2021-07-30 | 2022-07-30 | Level 2 | E | 2024-12-09 | 2024-07-30 | Level 2 | Field Safety Reassessment
121821613 | other | Non-HFTD | Transmission | 2021-07-30 | 2023-07-30 | Level 3 | F | 2024-04-06 | 2026-07-30 | Level 3 | Standards change
121824923 | anchor/guy | Non-HFTD | Transmission | 2021-07-27 | 2022-07-27 | Level 2 | E | 2023-10-18 | 2026-07-27 | Level 3 | Standards change
121829742 | pole | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2024-12-18 | 2024-08-02 | Level 2 | Field Safety Reassessment
121830565 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121832902 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121833001 | pole | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2024-12-17 | 2024-08-02 | Level 2 | Field Safety Reassessment
121833473 | pole | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2024-09-16 | 2024-08-02 | Level 2 | GO 165 Inspection
121833832 | other | Non-HFTD | Transmission | 2021-08-02 | 2026-08-02 | Level 3 | F |  | 2026-08-02 | Level 3
121833847 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121833906 | anchor/guy | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2023-11-15 | 2026-08-02 | Level 3 | Standards change
121834055 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121834111 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121834125 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121834153 | other | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2023-02-07 | 2026-08-02 | Level 3 | Standards change
121834157 | other | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2023-02-06 | 2024-08-02 | Level 2 | Standards change
121836133 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-11-20 | 2024-08-03 | Level 2 | Field Safety Reassessment
121837031 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-11-20 | 2024-08-03 | Level 2 | Field Safety Reassessment
121837086 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-11-20 | 2024-08-03 | Level 2 | Field Safety Reassessment
121837574 | other | Non-HFTD | Transmission | 2021-08-02 | 2022-08-02 | Level 2 | E | 2023-02-06 | 2026-08-02 | Level 3 | Standards change
121838057 | anchor/guy | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2023-11-15 | 2026-08-03 | Level 3 | Standards change
121838292 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121838625 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121839354 | anchor/guy | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-12-05 | 2026-08-03 | Level 3 | Field Safety Reassessment
121839376 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121839389 | pole | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-01-16 | 2026-08-03 | Level 3 | Standards change
121839426 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121839472 | pole | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2023-12-06 | 2026-08-03 | Level 3 | Standards change
121839476 | other | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2023-02-07 | 2026-08-03 | Level 3 | Standards change
121839546 | other | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2023-02-06 | 2026-08-03 | Level 3 | Standards change
121839745 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121839770 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121839817 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121839903 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-09-27 | 2022-08-03 | Level 2 | Field Safety Reassessment
121840629 | pole | Non-HFTD | Transmission | 2021-08-04 | 2022-08-04 | Level 2 | E | 2024-11-25 | 2024-08-04 | Level 2 | Field Safety Reassessment
121841438 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121841756 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-12-18 | 2024-08-03 | Level 2 | Field Safety Reassessment
121842358 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121842470 | anchor/guy | Non-HFTD | Transmission | 2021-08-04 | 2022-08-04 | Level 2 | E | 2023-08-12 | 2026-08-04 | Level 3 | Standards change
121842838 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2023-12-26 | 2026-08-04 | Level 3 | Standards change
121843057 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-01-11 | 2026-08-04 | Level 3 | Standards change
121843089 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121843157 | pole | Non-HFTD | Transmission | 2021-08-04 | 2022-08-04 | Level 2 | E | 2024-12-30 | 2024-08-04 | Level 2 | Field Safety Reassessment
121843515 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-11-04 | 2026-08-03 | Level 3 | GO 165 Inspection
121843628 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2023-12-26 | 2026-08-04 | Level 3 | Standards change
121843747 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-04-19 | 2024-08-03 | Level 2 | Field Safety Reassessment
121844386 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121844791 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121844907 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121845453 | insulator and brushing | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-12-30 | 2024-08-03 | Level 2 | Field Safety Reassessment
121845460 | pole | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-01-25 | 2026-08-03 | Level 3 | Standards change
121845549 | insulator and brushing | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2023-02-06 | 2026-08-03 | Level 3 | Standards change
121845581 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121845610 | anchor/guy | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2023-11-15 | 2026-08-03 | Level 3 | Standards change
121845636 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121845637 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121845653 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-09-27 | 2024-08-03 | Level 2 | Field Safety Reassessment
121845780 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121845835 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121845899 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121845948 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121846023 | pole | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-10-21 | 2024-08-03 | Level 2 | Field Safety Reassessment
121846025 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-08-07 | 2026-08-04 | Level 3 | GO 165 Inspection
121846734 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121847155 | splice | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2023-11-17 | 2024-08-05 | Level 2 | Standards change
121847338 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121847626 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2023-12-26 | 2026-08-05 | Level 3 | Standards change
121847670 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2023-12-26 | 2026-08-05 | Level 3 | Standards change
121847843 | other | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2023-01-30 | 2026-08-05 | Level 3 | Standards change
121848214 | pole | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2024-10-17 | 2024-08-05 | Level 2 | Field Safety Reassessment
121848400 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121848565 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2023-12-26 | 2026-08-05 | Level 3 | Standards change
121848838 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2024-02-12 | 2026-08-05 | Level 3 | Standards change
121848894 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2024-04-06 | 2026-08-05 | Level 3 | Standards change
121849333 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121851255 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2024-04-06 | 2026-08-05 | Level 3 | Standards change
121852908 | other | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2023-11-17 | 2026-08-05 | Level 3 | Standards change
121852940 | pole | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2024-09-30 | 2024-08-05 | Level 2 | Field Safety Reassessment
121854161 | insulator and brushing | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2024-12-11 | 2024-08-05 | Level 2 | Field Safety Reassessment
121854280 | pole | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2024-01-12 | 2026-08-06 | Level 3 | Standards change
121854425 | pole | Non-HFTD | Transmission | 2021-08-06 | 2022-08-06 | Level 2 | E | 2024-09-27 | 2024-08-06 | Level 2 | Field Safety Reassessment
121854510 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2023-12-26 | 2026-08-06 | Level 3 | Standards change
121855040 | crossarm | Non-HFTD | Transmission | 2021-08-03 | 2022-08-03 | Level 2 | E | 2024-10-08 | 2024-08-03 | Level 2 | Field Safety Reassessment
121855100 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2023-12-26 | 2026-08-06 | Level 3 | Standards change
121857648 | other | Non-HFTD | Transmission | 2021-08-06 | 2022-08-06 | Level 2 | E | 2023-11-17 | 2026-08-06 | Level 3 | Standards change
121858073 | crossarm | Non-HFTD | Transmission | 2021-08-06 | 2022-08-06 | Level 2 | E | 2024-09-30 | 2024-08-06 | Level 2 | GO 165 Inspection
121858252 | pole | Non-HFTD | Transmission | 2021-08-03 | 2024-08-03 | Level 2 | E | 2024-12-02 | 2021-11-03 | Level 2 | Field Safety Reassessment
121858334 | pole | Non-HFTD | Transmission | 2021-08-06 | 2022-08-06 | Level 2 | E | 2024-12-11 | 2024-08-06 | Level 2 | Field Safety Reassessment
121858457 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121858459 | other | Non-HFTD | Transmission | 2021-08-02 | 2023-08-02 | Level 3 | F | 2024-04-06 | 2026-08-02 | Level 3 | Standards change
121858515 | other | Non-HFTD | Transmission | 2021-08-05 | 2023-08-05 | Level 3 | F | 2024-04-06 | 2026-08-05 | Level 3 | Standards change
121858516 | other | Non-HFTD | Transmission | 2021-08-03 | 2023-08-03 | Level 3 | F | 2024-04-06 | 2026-08-03 | Level 3 | Standards change
121858902 | other | Non-HFTD | Transmission | 2021-08-04 | 2023-08-04 | Level 3 | F | 2024-04-06 | 2026-08-04 | Level 3 | Standards change
121859099 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2024-04-06 | 2026-08-06 | Level 3 | Standards change
121859207 | insulator and brushing | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2024-12-19 | 2024-08-05 | Level 2 | Field Safety Reassessment
121862954 | splice | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2023-01-17 | 2024-08-09 | Level 2 | Standards change
121863143 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2024-04-06 | 2026-08-06 | Level 3 | Standards change
121863231 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2024-04-06 | 2026-08-06 | Level 3 | Standards change
121863463 | anchor/guy | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2023-11-17 | 2026-08-09 | Level 3 | Standards change
121864099 | other | Non-HFTD | Transmission | 2021-08-09 | 2026-08-09 | Level 3 | F |  | 2026-08-09 | Level 3
121864353 | pole | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-03-14 | 2024-08-09 | Level 2 | Field Safety Reassessment
121864444 | pole | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-11-20 | 2024-08-09 | Level 2 | Field Safety Reassessment
121864617 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2024-08-27 | 2026-08-06 | Level 3 | GO 165 Inspection
121864739 | anchor/guy | Non-HFTD | Transmission | 2021-08-05 | 2022-08-05 | Level 2 | E | 2023-11-17 | 2026-08-05 | Level 3 | Standards change
121864921 | pole | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-11-20 | 2024-08-09 | Level 2 | Field Safety Reassessment
121865388 | other | Non-HFTD | Transmission | 2021-08-09 | 2026-08-09 | Level 3 | F |  | 2026-08-09 | Level 3
121865772 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121866124 | pole | Non-HFTD | Transmission | 2021-08-09 | 2024-08-09 | Level 2 | E | 2024-11-24 | 2021-11-09 | Level 2 | Field Safety Reassessment
121866264 | splice | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-11-06 | 2024-08-09 | Level 2 | GO 165 Inspection
121877416 | anchor/guy | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2023-09-19 | 2024-08-09 | Level 2 | Standards change
121879224 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121879226 | pole | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-01-19 | 2024-08-09 | Level 2 | Field Safety Reassessment
121879476 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-11-25 | 2024-08-10 | Level 2 | Field Safety Reassessment
121879477 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-10-18 | 2026-08-10 | Level 3 | GO 165 Inspection
121879512 | splice | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-01-09 | 2024-08-09 | Level 2 | Standards change
121879588 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-11-25 | 2024-08-10 | Level 2 | Field Safety Reassessment
121880133 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121880829 | other | Non-HFTD | Transmission | 2021-08-10 | 2024-08-10 | Level 2 | E | 2024-11-06 | 2022-08-10 | Level 2 | Field Safety Reassessment
121880830 | splice | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-11-17 | 2024-08-10 | Level 2 | Standards change
121880983 | splice | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2023-11-20 | 2024-08-09 | Level 2 | Standards change
121881085 | anchor/guy | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-01-17 | 2026-08-10 | Level 3 | Standards change
121881608 | splice | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-11-20 | 2024-08-10 | Level 2 | Standards change
121881655 | splice | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2023-11-20 | 2024-08-09 | Level 2 | Standards change
121881883 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-01-12 | 2024-08-10 | Level 2 | Field Safety Reassessment
121884698 | splice | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-11-15 | 2024-08-10 | Level 2 | GO 165 Inspection
121885042 | crossarm | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-09-25 | 2024-08-10 | Level 2 | GO 165 Inspection
121885122 | pole | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-10-25 | 2024-08-11 | Level 2 | Field Safety Reassessment
121885316 | pole | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-01-19 | 2024-08-09 | Level 2 | Field Safety Reassessment
121886258 | splice | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-11-20 | 2024-08-10 | Level 2 | Standards change
121886779 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2023-02-07 | 2026-08-11 | Level 3 | Standards change
121887126 | other | Non-HFTD | Transmission | 2021-08-06 | 2023-08-06 | Level 3 | F | 2024-04-06 | 2026-08-06 | Level 3 | Standards change
121887178 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-09 | 2026-08-11 | Level 3 | GO 165 Inspection
121887489 | pole | Non-HFTD | Transmission | 2021-08-10 | 2024-08-10 | Level 2 | E | 2024-08-16 | 2022-08-10 | Level 2 | Field Safety Reassessment
121887645 | crossarm | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-12-02 | 2024-08-11 | Level 2 | GO 165 Inspection
121887880 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121887892 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121887967 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121888060 | insulator and brushing | Non-HFTD | Transmission | 2021-08-06 | 2022-08-06 | Level 2 | E | 2023-01-18 | 2026-08-06 | Level 3 | Standards change
121888068 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121888163 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121888165 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121888166 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121888167 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-10-14 | 2024-08-10 | Level 2 | Field Safety Reassessment
121888279 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121888302 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121888303 | other | Non-HFTD | Transmission | 2021-08-09 | 2024-08-09 | Level 2 | E | 2024-11-12 | 2026-08-09 | Level 3 | Field Safety Reassessment
121888323 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121888346 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-11-22 | 2024-08-10 | Level 2 | Field Safety Reassessment
121888385 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121889418 | anchor/guy | Non-HFTD | Transmission | 2021-08-12 | 2026-08-12 | Level 2 | E | 2024-09-17 | 2024-08-12 | Level 2 | GO 165 Inspection
121889577 | pole | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2023-09-13 | 2026-08-10 | Level 3 | Standards change
121889731 | other | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-11-26 | 2024-08-10 | Level 2 | GO 165 Inspection
121889872 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2023-10-09 | 2024-08-12 | Level 2 | Standards change
121889975 | anchor/guy | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-01-24 | 2026-08-10 | Level 3 | Standards change
121890087 | anchor/guy | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2023-02-03 | 2022-08-12 | Level 2 | Standards change
121890267 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121890356 | anchor/guy | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2023-11-20 | 2024-08-12 | Level 2 | Standards change
121891006 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121891400 | anchor/guy | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-11-20 | 2026-08-10 | Level 3 | Standards change
121891455 | other | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-05-21 | 2022-08-11 | Level 2 | Field Safety Reassessment
121891611 | pole | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-11-06 | 2024-08-11 | Level 2 | Field Safety Reassessment
121891678 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-12-04 | 2024-08-12 | Level 2 | Field Safety Reassessment
121892783 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-05 | 2024-08-12 | Level 2 | Field Safety Reassessment
121893029 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-15 | 2024-08-12 | Level 2 | Field Safety Reassessment
121893275 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2023-12-07 | 2026-08-10 | Level 3 | Standards change
121893649 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121893957 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121894206 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2024-02-20 | 2024-08-10 | Level 2 | Field Safety Reassessment
121894238 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121894269 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121894343 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121894350 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121894440 | pole | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-01-31 | 2024-08-09 | Level 2 | Field Safety Reassessment
121894460 | anchor/guy | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2023-11-21 | 2026-08-11 | Level 3 | Standards change
121894481 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121894560 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121894621 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2023-12-07 | 2026-08-10 | Level 3 | Standards change
121894645 | pole | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-01-23 | 2026-08-10 | Level 3 | Standards change
121894680 | insulator and brushing | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2023-11-21 | 2026-08-09 | Level 3 | Standards change
121894700 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121894783 | pole | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-12-03 | 2024-08-11 | Level 2 | Field Safety Reassessment
121896313 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-09-25 | 2024-08-12 | Level 2 | GO 165 Inspection
121896396 | splice | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-09-25 | 2024-08-12 | Level 2 | GO 165 Inspection
121896480 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121896482 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121896511 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2023-12-07 | 2026-08-10 | Level 3 | Standards change
121896551 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121896783 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121897631 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2023-12-12 | 2026-08-13 | Level 3 | Standards change
121897820 | other | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-02-28 | 2026-08-10 | Level 3 | Standards change
121898148 | splice | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2023-11-21 | 2024-08-12 | Level 2 | Standards change
121898395 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121898708 | splice | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2023-11-21 | 2024-08-12 | Level 2 | Standards change
121898859 | splice | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-27 | 2024-08-13 | Level 2 | GO 165 Inspection
121898960 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-09-25 | 2026-08-12 | Level 3 | GO 165 Inspection
121899126 | insulator and brushing | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2023-03-02 | 2024-08-13 | Level 2 | GO 165 Inspection
121899273 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-12-19 | 2024-08-12 | Level 2 | Field Safety Reassessment
121899403 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-04-06 | 2026-08-13 | Level 3 | Standards change
121899802 | insulator and brushing | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-27 | 2026-08-13 | Level 3 | GO 165 Inspection
121901579 | anchor/guy | Non-HFTD | Transmission | 2021-08-06 | 2022-08-06 | Level 2 | E | 2024-10-30 | 2024-08-06 | Level 2 | GO 165 Inspection
121903341 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-04-06 | 2026-08-12 | Level 3 | Standards change
121904558 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121904905 | insulator and brushing | Non-HFTD | Transmission | 2021-08-10 | 2022-08-10 | Level 2 | E | 2023-01-23 | 2026-08-10 | Level 3 | Standards change
121905058 | splice | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2023-11-21 | 2024-08-13 | Level 2 | Standards change
121905521 | splice | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2023-11-21 | 2024-08-13 | Level 2 | Standards change
121906702 | splice | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-11 | 2024-08-13 | Level 2 | GO 165 Inspection
121906801 | anchor/guy | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2023-11-21 | 2026-08-16 | Level 3 | Standards change
121907061 | pole | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-11-22 | 2024-08-16 | Level 2 | Field Safety Reassessment
121907105 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121907390 | pole | Non-HFTD | Transmission | 2021-05-14 | 2022-05-14 | Level 2 | E | 2024-11-09 | 2024-05-14 | Level 2 | GO 165 Inspection
121907755 | insulator and brushing | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-02-06 | 2024-08-16 | Level 2 | Standards change
121907833 | insulator and brushing | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-10-31 | 2024-08-16 | Level 2 | GO 165 Inspection
121908233 | splice | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-25 | 2024-08-13 | Level 2 | GO 165 Inspection
121908498 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121908902 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2023-05-08 | 2026-08-12 | Level 3 | Standards change
121908941 | pole | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-05-21 | 2024-08-11 | Level 2 | Field Safety Reassessment
121909057 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-04-06 | 2026-08-12 | Level 3 | Standards change
121909081 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121909084 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2023-06-10 | 2026-08-12 | Level 3 | Standards change
121909150 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-20 | 2024-08-16 | Level 2 | Field Safety Reassessment
121909195 | other | Non-HFTD | Transmission | 2021-08-11 | 2026-08-11 | Level 3 | F | 2023-09-13 | 2026-08-11 | Level 3 | GO 165 Inspection
121909240 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-05 | 2024-08-12 | Level 2 | Field Safety Reassessment
121909241 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121909326 | other | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2023-02-28 | 2026-08-11 | Level 3 | Standards change
121909348 | pole | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-02-20 | 2024-08-11 | Level 2 | Field Safety Reassessment
121909353 | other | Non-HFTD | Transmission | 2021-08-09 | 2022-08-09 | Level 2 | E | 2024-01-31 | 2024-08-09 | Level 2 | Field Safety Reassessment
121909364 | anchor/guy | Non-HFTD | Transmission | 2021-08-11 | 2022-08-11 | Level 2 | E | 2024-01-17 | 2026-08-11 | Level 3 | Standards change
121909367 | other | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-27 | 2024-08-12 | Level 2 | Field Safety Reassessment
121909437 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121909478 | pole | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-27 | 2024-08-13 | Level 2 | GO 165 Inspection
121909489 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121909506 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121909529 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-04-06 | 2026-08-13 | Level 3 | Standards change
121909530 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121909545 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-04-06 | 2026-08-13 | Level 3 | Standards change
121909580 | pole | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-11-20 | 2024-08-13 | Level 2 | Field Safety Reassessment
121909647 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-04-06 | 2026-08-12 | Level 3 | Standards change
121910068 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121911194 | anchor/guy | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-10-03 | 2024-08-17 | Level 2 | GO 165 Inspection
121912715 | splice | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-09-27 | 2024-08-17 | Level 2 | GO 165 Inspection
121912825 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2023-12-20 | 2026-08-17 | Level 3 | Standards change
121912892 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-11-20 | 2024-08-17 | Level 2 | Field Safety Reassessment
121913203 | crossarm | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-25 | 2024-08-13 | Level 2 | GO 165 Inspection
121913476 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121913490 | other | Non-HFTD | Transmission | 2021-08-12 | 2024-08-12 | Level 2 | E | 2024-07-23 | 2022-08-12 | Level 2 | GO 165 Inspection
121913495 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-07-23 | 2024-08-12 | Level 2 | GO 165 Inspection
121913567 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-09-17 | 2026-08-13 | Level 3 | GO 165 Inspection
121913602 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-08-22 | 2026-08-13 | Level 3 | GO 165 Inspection
121913604 | pole | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-01-22 | 2026-08-13 | Level 3 | Standards change
121913606 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2023-03-21 | 2026-08-11 | Level 3 | Standards change
121913652 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-04-06 | 2026-08-13 | Level 3 | Standards change
121913653 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121913700 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-07-22 | 2024-08-12 | Level 2 | GO 165 Inspection
121913722 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121913739 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-05 | 2024-08-12 | Level 2 | Field Safety Reassessment
121913743 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-04-06 | 2026-08-12 | Level 3 | Standards change
121913749 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121913770 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121913805 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-04-06 | 2026-08-12 | Level 3 | Standards change
121913816 | other | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-12-18 | 2024-08-13 | Level 2 | Field Safety Reassessment
121913907 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-22 | 2024-08-12 | Level 2 | Field Safety Reassessment
121913908 | other | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-22 | 2024-08-12 | Level 2 | Field Safety Reassessment
121913936 | pole | Non-HFTD | Transmission | 2021-08-13 | 2022-08-13 | Level 2 | E | 2024-09-27 | 2024-08-13 | Level 2 | GO 165 Inspection
121913948 | other | Non-HFTD | Transmission | 2021-08-09 | 2023-08-09 | Level 3 | F | 2024-04-06 | 2026-08-09 | Level 3 | Standards change
121913999 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-05-12 | 2024-08-17 | Level 2 | Standards change
121914005 | insulator and brushing | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-09-27 | 2026-08-12 | Level 3 | GO 165 Inspection
121914012 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2023-12-26 | 2026-08-12 | Level 3 | Standards change
121914021 | other | Non-HFTD | Transmission | 2021-08-10 | 2023-08-10 | Level 3 | F | 2024-04-06 | 2026-08-10 | Level 3 | Standards change
121914024 | insulator and brushing | Non-HFTD | Transmission | 2021-08-13 | 2024-08-13 | Level 2 | E | 2024-12-01 | 2026-08-13 | Level 3 | Field Safety Reassessment
121914026 | other | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-25 | 2024-08-12 | Level 2 | Field Safety Reassessment
121914030 | other | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-25 | 2024-08-12 | Level 2 | Field Safety Reassessment
121914085 | pole | Non-HFTD | Transmission | 2021-08-12 | 2022-08-12 | Level 2 | E | 2024-11-05 | 2024-08-12 | Level 2 | Field Safety Reassessment
121914206 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-04-06 | 2026-08-13 | Level 3 | Standards change
121914208 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-04-06 | 2026-08-12 | Level 3 | Standards change
121914305 | pole | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-01-17 | 2024-08-16 | Level 2 | Field Safety Reassessment
121914809 | insulator and brushing | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-12-30 | 2024-08-16 | Level 2 | Field Safety Reassessment
121914842 | other | Non-HFTD | Transmission | 2021-08-16 | 2024-08-16 | Level 2 | E | 2024-11-25 | 2026-08-16 | Level 3 | Field Safety Reassessment
121915063 | splice | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-07-04 | 2024-08-17 | Level 2 | GO 165 Inspection
121915289 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121915324 | other | Non-HFTD | Transmission | 2021-08-13 | 2023-08-13 | Level 3 | F | 2024-04-06 | 2026-08-13 | Level 3 | Standards change
121915496 | other | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-10-09 | 2026-08-16 | Level 3 | GO 165 Inspection
121915632 | other | Non-HFTD | Transmission | 2021-08-12 | 2023-08-12 | Level 3 | F | 2024-01-12 | 2026-08-12 | Level 3 | Standards change
121915635 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121916007 | other | Non-HFTD | Transmission | 2021-08-11 | 2023-08-11 | Level 3 | F | 2024-04-06 | 2026-08-11 | Level 3 | Standards change
121916215 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-10-14 | 2024-08-18 | Level 2 | Field Safety Reassessment
121916430 | anchor/guy | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-02-17 | 2026-08-18 | Level 3 | Standards change
121916904 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-09-18 | 2022-08-17 | Level 2 | GO 165 Inspection
121917216 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-11-05 | 2024-08-17 | Level 2 | Field Safety Reassessment
121917344 | pole | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-12-01 | 2024-08-16 | Level 2 | Field Safety Reassessment
121917549 | insulator and brushing | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-12-31 | 2024-08-18 | Level 2 | Field Safety Reassessment
121917920 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121917966 | anchor/guy | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-12-29 | 2026-08-18 | Level 3 | Standards change
121917996 | anchor/guy | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-12-29 | 2026-08-18 | Level 3 | Standards change
121918089 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121918183 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2024-04-06 | 2026-08-17 | Level 3 | Standards change
121918189 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2024-04-06 | 2026-08-17 | Level 3 | Standards change
121918365 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-01-24 | 2026-08-17 | Level 3 | Standards change
121918871 | pole | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-12-01 | 2024-08-16 | Level 2 | Field Safety Reassessment
121919330 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-11-07 | 2024-08-17 | Level 2 | Field Safety Reassessment
121919582 | other | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-12-08 | 2026-08-17 | Level 3 | Standards change
121920016 | pole | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-10-14 | 2024-08-19 | Level 2 | Field Safety Reassessment
121920065 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-01-24 | 2024-08-17 | Level 2 | Field Safety Reassessment
121920116 | pole | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-11-06 | 2024-08-19 | Level 2 | Field Safety Reassessment
121920686 | splice | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-06-13 | 2024-08-18 | Level 2 | GO 165 Inspection
121920800 | insulator and brushing | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-11-22 | 2024-08-17 | Level 2 | Standards change
121920853 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-01-02 | 2026-08-18 | Level 3 | Standards change
121921268 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-02-07 | 2024-08-17 | Level 2 | Field Safety Reassessment
121921436 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-12-20 | 2024-08-17 | Level 2 | Field Safety Reassessment
121921669 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2024-04-06 | 2026-08-17 | Level 3 | Standards change
121922392 | pole | Non-HFTD | Transmission | 2021-08-19 | 2024-08-19 | Level 2 | E | 2024-09-19 | 2022-08-19 | Level 2 | GO 165 Inspection
121922609 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121922643 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2023-01-31 | 2024-08-17 | Level 2 | Standards change
121922696 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121922745 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-01-24 | 2026-08-17 | Level 3 | Standards change
121923838 | anchor/guy | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-02-01 | 2026-08-18 | Level 3 | Standards change
121923933 | other | Non-HFTD | Transmission | 2021-08-17 | 2026-08-17 | Level 3 | F |  | 2026-08-17 | Level 3
121924204 | other | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-11-22 | 2026-08-17 | Level 3 | Standards change
121924475 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2024-04-06 | 2026-08-17 | Level 3 | Standards change
121924710 | other | Non-HFTD | Transmission | 2021-08-20 | 2024-08-20 | Level 2 | E | 2024-10-04 | 2022-08-20 | Level 2 | GO 165 Inspection
121924742 | anchor/guy | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-01-17 | 2026-08-20 | Level 3 | Standards change
121924757 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-08 | 2024-08-20 | Level 2 | Field Safety Reassessment
121925050 | splice | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-09-19 | 2024-08-19 | Level 2 | GO 165 Inspection
121925135 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121925202 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-01-31 | 2024-08-17 | Level 2 | Field Safety Reassessment
121925460 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-02 | 2024-08-20 | Level 2 | Field Safety Reassessment
121925605 | other | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-12-10 | 2024-08-18 | Level 2 | Field Safety Reassessment
121925746 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2023-12-08 | 2026-08-17 | Level 3 | Standards change
121925959 | anchor/guy | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-04-05 | 2024-08-18 | Level 2 | GO 165 Inspection
121927300 | splice | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-11-22 | 2024-08-20 | Level 2 | Standards change
121927328 | anchor/guy | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-01-17 | 2026-08-20 | Level 3 | Standards change
121927986 | insulator and brushing | Non-HFTD | Transmission | 2021-08-19 | 2026-08-19 | Level 2 | E | 2024-09-19 | 2024-08-19 | Level 2 | GO 165 Inspection
121930252 | other | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-10-04 | 2026-08-20 | Level 3 | GO 165 Inspection
121930259 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2024-04-06 | 2026-08-17 | Level 3 | Standards change
121930292 | other | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-12-10 | 2024-08-19 | Level 2 | Field Safety Reassessment
121930372 | splice | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-12-11 | 2024-08-19 | Level 2 | Field Safety Reassessment
121930416 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-11-06 | 2024-08-17 | Level 2 | Field Safety Reassessment
121930417 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-11-18 | 2024-08-20 | Level 2 | Field Safety Reassessment
121930436 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-12-13 | 2024-08-17 | Level 2 | Field Safety Reassessment
121930493 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-09-18 | 2024-08-18 | Level 2 | GO 165 Inspection
121930635 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-10-07 | 2024-08-20 | Level 2 | GO 165 Inspection
121930636 | other | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-11-27 | 2026-08-18 | Level 3 | Standards change
121930753 | anchor/guy | Non-HFTD | Transmission | 2021-08-21 | 2022-08-21 | Level 2 | E | 2024-08-21 | 2026-08-21 | Level 3 | GO 165 Inspection
121930784 | pole | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-11-06 | 2024-08-17 | Level 2 | Field Safety Reassessment
121930844 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-22 | 2024-08-20 | Level 2 | Field Safety Reassessment
121930925 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-10 | 2024-08-20 | Level 2 | Field Safety Reassessment
121930962 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121930964 | conductor | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-11-27 | 2024-08-18 | Level 2 | Standards change
121930968 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121931091 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-11-01 | 2024-08-18 | Level 2 | Field Safety Reassessment
121931287 | pole | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2024-01-17 | 2024-08-16 | Level 2 | Field Safety Reassessment
121931396 | other | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2023-11-27 | 2026-08-16 | Level 3 | Standards change
121931529 | other | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-11-27 | 2026-08-17 | Level 3 | Standards change
121931821 | pole | Non-HFTD | Transmission | 2021-08-21 | 2022-08-21 | Level 2 | E | 2023-02-07 | 2024-08-21 | Level 2 | Standards change
121931840 | crossarm | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2022-12-15 | 2026-08-18 | Level 3 | Standards change
121931847 | other | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-10-05 | 2026-08-18 | Level 3 | GO 165 Inspection
121931848 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-10-05 | 2026-08-18 | Level 3 | GO 165 Inspection
121932149 | insulator and brushing | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2022-12-15 | 2022-08-18 | Level 2 | Standards change
121933325 | other | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-11-27 | 2026-08-17 | Level 3 | Standards change
121933940 | other | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-08-19 | 2026-08-18 | Level 3 | GO 165 Inspection
121933943 | other | Non-HFTD | Transmission | 2021-08-18 | 2024-08-18 | Level 2 | E | 2024-06-14 | 2022-08-18 | Level 2 | Field Safety Reassessment
121938314 | insulator and brushing | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-01-30 | 2024-08-17 | Level 2 | Standards change
121938351 | insulator and brushing | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-11-27 | 2026-08-17 | Level 3 | Standards change
121938551 | other | Non-HFTD | Transmission | 2021-08-17 | 2023-08-17 | Level 3 | F | 2024-04-06 | 2026-08-17 | Level 3 | Standards change
121938673 | conductor | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-12-10 | 2024-08-19 | Level 2 | Field Safety Reassessment
121938822 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-11-07 | 2024-08-18 | Level 2 | Field Safety Reassessment
121939626 | pole | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-11-20 | 2024-08-23 | Level 2 | Field Safety Reassessment
121939810 | other | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-10-22 | 2026-08-23 | Level 3 | GO 165 Inspection
121939963 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-09-10 | 2024-08-18 | Level 2 | GO 165 Inspection
121940253 | insulator and brushing | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-12-17 | 2024-08-18 | Level 2 | Field Safety Reassessment
121940368 | insulator and brushing | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2023-11-27 | 2024-08-17 | Level 2 | Standards change
121940481 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-06-11 | 2024-08-18 | Level 2 | Field Safety Reassessment
121940522 | pole | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-10-22 | 2024-08-23 | Level 2 | GO 165 Inspection
121940598 | other | Non-HFTD | Transmission | 2021-08-16 | 2023-08-16 | Level 3 | F | 2024-04-06 | 2026-08-16 | Level 3 | Standards change
121940730 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-09-03 | 2026-08-18 | Level 3 | GO 165 Inspection
121940818 | other | Non-HFTD | Transmission | 2021-08-16 | 2022-08-16 | Level 2 | E | 2023-11-27 | 2026-08-16 | Level 3 | Standards change
121940835 | insulator and brushing | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-11-27 | 2026-08-19 | Level 3 | Standards change
121941721 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121942015 | other | Non-HFTD | Transmission | 2021-08-23 | 2023-08-23 | Level 3 | F | 2024-08-29 | 2026-08-23 | Level 3 | GO 165 Inspection
121942106 | insulator and brushing | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-03-06 | 2026-08-19 | Level 3 | Standards change
121942454 | other | Non-HFTD | Transmission | 2021-06-03 | 2022-06-03 | Level 2 | E | 2023-11-27 | 2026-06-03 | Level 3 | Standards change
121942748 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-04-06 | 2026-08-18 | Level 3 | Standards change
121942767 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2023-03-24 | 2026-08-19 | Level 3 | Standards change
121942815 | insulator and brushing | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-07-10 | 2022-08-18 | Level 2 | GO 165 Inspection
121942872 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-04-06 | 2026-08-18 | Level 3 | Standards change
121942878 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121942879 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121942956 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-07 | 2024-08-20 | Level 2 | Field Safety Reassessment
121942957 | other | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-03-03 | 2026-08-19 | Level 3 | Standards change
121942970 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-10 | 2024-08-20 | Level 2 | Field Safety Reassessment
121942977 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-08-27 | 2024-08-20 | Level 2 | GO 165 Inspection
121943023 | insulator and brushing | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-11-27 | 2024-08-19 | Level 2 | Standards change
121943113 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-01-03 | 2026-08-18 | Level 3 | Standards change
121943119 | pole | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-03-13 | 2024-08-18 | Level 2 | Standards change
121943120 | other | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-11-25 | 2024-08-19 | Level 2 | Field Safety Reassessment
121943137 | other | Non-HFTD | Transmission | 2021-08-18 | 2024-08-18 | Level 2 | E | 2024-11-26 | 2022-08-18 | Level 2 | Field Safety Reassessment
121943188 | pole | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-12-10 | 2024-08-19 | Level 2 | Field Safety Reassessment
121943269 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121943291 | other | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-11-27 | 2026-08-20 | Level 3 | Standards change
121943312 | anchor/guy | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-11-27 | 2026-08-19 | Level 3 | Standards change
121943315 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2023-01-25 | 2026-08-18 | Level 3 | Standards change
121943325 | other | Non-HFTD | Transmission | 2021-08-18 | 2023-08-18 | Level 3 | F | 2024-04-06 | 2026-08-18 | Level 3 | Standards change
121943333 | other | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-11-27 | 2026-08-19 | Level 3 | Standards change
121943405 | other | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2023-11-27 | 2026-08-18 | Level 3 | Standards change
121943418 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121943460 | pole | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-01-25 | 2024-08-19 | Level 2 | Standards change
121943470 | other | Non-HFTD | Transmission | 2021-08-18 | 2022-08-18 | Level 2 | E | 2024-11-25 | 2024-08-18 | Level 2 | Field Safety Reassessment
121943500 | insulator and brushing | Non-HFTD | Transmission | 2021-08-17 | 2022-08-17 | Level 2 | E | 2024-07-22 | 2024-08-17 | Level 2 | GO 165 Inspection
121943912 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-10 | 2024-08-20 | Level 2 | Field Safety Reassessment
121943942 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121944066 | pole | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-10-25 | 2024-08-24 | Level 2 | GO 165 Inspection
121944793 | pole | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-11-13 | 2024-08-19 | Level 2 | Field Safety Reassessment
121944952 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-01-31 | 2024-08-20 | Level 2 | Standards change
121945130 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-10 | 2024-08-20 | Level 2 | Field Safety Reassessment
121945165 | pole | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-02-08 | 2024-08-24 | Level 2 | Standards change
121945359 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-01-16 | 2026-08-24 | Level 3 | Standards change
121945396 | other | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-11-06 | 2024-08-23 | Level 2 | Field Safety Reassessment
121946360 | other | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-01-31 | 2024-08-20 | Level 2 | Standards change
121946384 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-11-30 | 2024-08-20 | Level 2 | Field Safety Reassessment
121946618 | pole | Non-HFTD | Transmission | 2021-07-21 | 2023-07-21 | Level 3 | F | 2024-09-06 | 2026-07-21 | Level 3 | GO 165 Inspection
121947030 | other | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-10-07 | 2024-08-19 | Level 2 | GO 165 Inspection
121947039 | anchor/guy | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2024-10-07 | 2026-08-19 | Level 3 | GO 165 Inspection
121947051 | pole | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-10 | 2024-08-20 | Level 2 | Field Safety Reassessment
121947749 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2023-12-28 | 2026-08-20 | Level 3 | Standards change
121947997 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121948013 | switch | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-09-16 | 2024-08-24 | Level 2 | GO 165 Inspection
121948819 | pole | Non-HFTD | Transmission | 2021-08-23 | 2023-08-23 | Level 3 | F | 2024-11-14 | 2026-08-23 | Level 3 | GO 165 Inspection
121950295 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121950494 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121950922 | other | Non-HFTD | Transmission | 2021-08-23 | 2023-08-23 | Level 3 | F | 2024-04-06 | 2026-08-23 | Level 3 | Standards change
121951443 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121951445 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-01-31 | 2024-08-20 | Level 2 | Standards change
121951463 | crossarm | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-12-11 | 2024-08-20 | Level 2 | Field Safety Reassessment
121951500 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121951507 | anchor/guy | Non-HFTD | Transmission | 2021-08-19 | 2022-08-19 | Level 2 | E | 2023-11-28 | 2026-08-19 | Level 3 | Standards change
121951581 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121951673 | other | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-11-28 | 2026-08-20 | Level 3 | Standards change
121951674 | other | Non-HFTD | Transmission | 2021-08-20 | 2026-08-20 | Level 3 | F |  | 2026-08-20 | Level 3
121951695 | pole | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2023-12-19 | 2026-08-20 | Level 3 | Standards change
121951698 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-01-04 | 2026-08-20 | Level 3 | Standards change
121951704 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-04-06 | 2026-08-20 | Level 3 | Standards change
121951729 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-10-24 | 2024-08-24 | Level 2 | Field Safety Reassessment
121951758 | insulator and brushing | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-08-31 | 2024-08-23 | Level 2 | GO 165 Inspection
121951817 | anchor/guy | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-08-26 | 2024-08-23 | Level 2 | GO 165 Inspection
121951887 | other | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2023-11-28 | 2026-08-20 | Level 3 | Standards change
121954325 | pole | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-11-14 | 2024-08-24 | Level 2 | GO 165 Inspection
121954488 | other | Non-HFTD | Transmission | 2021-08-23 | 2024-08-23 | Level 2 | E | 2024-08-07 | 2022-08-23 | Level 2 | GO 165 Inspection
121955108 | other | Non-HFTD | Transmission | 2021-08-25 | 2024-08-25 | Level 2 | E | 2024-10-07 | 2022-08-25 | Level 2 | GO 165 Inspection
121955525 | pole | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2023-01-31 | 2026-08-24 | Level 3 | Standards change
121955709 | other | Non-HFTD | Transmission | 2021-08-19 | 2023-08-19 | Level 3 | F | 2024-04-06 | 2026-08-19 | Level 3 | Standards change
121956023 | other | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-01-24 | 2024-08-20 | Level 2 | Standards change
121956063 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-11-14 | 2026-08-24 | Level 3 | GO 165 Inspection
121956404 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-07-10 | 2022-08-24 | Level 2 | GO 165 Inspection
121956698 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-10-04 | 2024-08-20 | Level 2 | GO 165 Inspection
121958848 | pole | Non-HFTD | Transmission | 2021-08-21 | 2022-08-21 | Level 2 | E | 2022-08-11 | 2022-08-21 | Level 2 | Field Safety Reassessment
121959419 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-04-18 | 2026-08-24 | Level 3 | GO 165 Inspection
121960137 | anchor/guy | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-11-19 | 2026-08-26 | Level 3 | GO 165 Inspection
121960611 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-08-27 | 2024-08-24 | Level 2 | GO 165 Inspection
121960822 | other | Non-HFTD | Transmission | 2021-08-26 | 2023-08-26 | Level 3 | F | 2023-02-08 | 2026-08-26 | Level 3 | Standards change
121960943 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-07-03 | 2024-08-24 | Level 2 | GO 165 Inspection
121962427 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2023-03-24 | 2026-08-20 | Level 3 | Standards change
121964308 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-11-30 | 2024-08-20 | Level 2 | Field Safety Reassessment
121964539 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-01-11 | 2026-08-24 | Level 3 | Standards change
121964997 | other | Non-HFTD | Transmission | 2021-08-23 | 2023-08-23 | Level 3 | F | 2024-08-16 | 2026-08-23 | Level 3 | GO 165 Inspection
121965153 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-03-03 | 2024-08-26 | Level 2 | Standards change
121965299 | anchor/guy | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-11-29 | 2026-08-26 | Level 3 | Standards change
121965443 | other | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-02-13 | 2026-08-26 | Level 3 | Standards change
121965579 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-12-12 | 2024-08-24 | Level 2 | Field Safety Reassessment
121965587 | insulator and brushing | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2023-01-20 | 2024-08-27 | Level 2 | Standards change
121966132 | anchor/guy | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2024-01-03 | 2026-08-25 | Level 3 | Standards change
121966193 | anchor/guy | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2023-12-29 | 2026-08-27 | Level 3 | Standards change
121966280 | other | Non-HFTD | Transmission | 2021-08-25 | 2023-08-25 | Level 3 | F | 2024-04-06 | 2026-08-25 | Level 3 | Standards change
121966391 | insulator and brushing | Non-HFTD | Transmission | 2021-08-20 | 2022-08-20 | Level 2 | E | 2024-08-27 | 2024-08-20 | Level 2 | GO 165 Inspection
121966395 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2024-08-27 | 2026-08-20 | Level 3 | GO 165 Inspection
121966823 | other | Non-HFTD | Transmission | 2021-08-20 | 2023-08-20 | Level 3 | F | 2023-12-19 | 2026-08-20 | Level 3 | Standards change
121967129 | other | Non-HFTD | Transmission | 2021-08-26 | 2023-08-26 | Level 3 | F | 2024-08-28 | 2026-08-26 | Level 3 | GO 165 Inspection
121967370 | pole | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2023-09-30 | 2024-08-27 | Level 2 | GO 165 Inspection
121967521 | pole | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-08-12 | 2026-08-26 | Level 3 | Field Safety Reassessment
121967581 | other | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-01-31 | 2024-08-26 | Level 2 | Standards change
121968142 | other | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2024-07-23 | 2024-08-27 | Level 2 | GO 165 Inspection
121968300 | switch | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2022-12-13 | 2024-08-26 | Level 2 | Standards change
121968303 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-11-05 | 2026-08-26 | Level 3 | GO 165 Inspection
121968471 | pole | Non-HFTD | Transmission | 2021-08-28 | 2022-08-28 | Level 2 | E | 2024-12-03 | 2024-08-28 | Level 2 | Field Safety Reassessment
121968619 | other | Non-HFTD | Transmission | 2021-08-28 | 2023-08-28 | Level 3 | F | 2024-08-27 | 2026-08-28 | Level 3 | GO 165 Inspection
121968698 | insulator and brushing | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2024-03-06 | 2024-08-27 | Level 2 | GO 165 Inspection
121969130 | other | Non-HFTD | Transmission | 2021-08-28 | 2023-08-28 | Level 3 | F | 2024-01-26 | 2026-08-28 | Level 3 | Standards change
121969922 | other | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-11-05 | 2026-08-26 | Level 3 | GO 165 Inspection
121970671 | pole | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-09-06 | 2024-08-30 | Level 2 | Field Safety Reassessment
121971810 | other | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-08-21 | 2026-08-30 | Level 3 | GO 165 Inspection
121972259 | insulator and brushing | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2024-08-31 | 2024-08-25 | Level 2 | GO 165 Inspection
121972329 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-08-21 | 2026-08-30 | Level 3 | GO 165 Inspection
121972432 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-04-06 | 2026-08-30 | Level 3 | Standards change
121972688 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-09-20 | 2026-08-24 | Level 3 | GO 165 Inspection
121972976 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-08-22 | 2026-08-30 | Level 3 | GO 165 Inspection
121973547 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-08-21 | 2026-08-30 | Level 3 | GO 165 Inspection
121974243 | other | Non-HFTD | Transmission | 2021-08-26 | 2023-08-26 | Level 3 | F | 2024-08-28 | 2026-08-26 | Level 3 | GO 165 Inspection
121974635 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-01-02 | 2026-08-30 | Level 3 | Standards change
121974676 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-03-08 | 2026-08-26 | Level 3 | Standards change
121974698 | other | Non-HFTD | Transmission | 2021-08-26 | 2023-08-26 | Level 3 | F | 2023-08-17 | 2026-08-26 | Level 3 | Standards change
121974765 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-08-30 | 2024-08-24 | Level 2 | GO 165 Inspection
121974802 | other | Non-HFTD | Transmission | 2021-08-24 | 2024-08-24 | Level 2 | E | 2024-07-24 | 2026-08-24 | Level 3 | GO 165 Inspection
121974804 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-07-16 | 2024-08-24 | Level 2 | GO 165 Inspection
121974840 | pole | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-01-31 | 2024-08-24 | Level 2 | Standards change
121974856 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-09-03 | 2024-08-24 | Level 2 | GO 165 Inspection
121974857 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-09-03 | 2024-08-24 | Level 2 | GO 165 Inspection
121974858 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-09-03 | 2026-08-24 | Level 3 | GO 165 Inspection
121974985 | insulator and brushing | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2024-08-31 | 2024-08-25 | Level 2 | GO 165 Inspection
121974989 | other | Non-HFTD | Transmission | 2021-08-25 | 2023-08-25 | Level 3 | F | 2024-08-31 | 2026-08-25 | Level 3 | GO 165 Inspection
121975065 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-11-13 | 2024-08-24 | Level 2 | GO 165 Inspection
121975131 | insulator and brushing | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2024-09-10 | 2024-08-23 | Level 2 | Field Safety Reassessment
121975132 | other | Non-HFTD | Transmission | 2021-08-25 | 2023-08-25 | Level 3 | F | 2024-01-04 | 2026-08-25 | Level 3 | Standards change
121975136 | other | Non-HFTD | Transmission | 2021-08-25 | 2026-08-25 | Level 3 | F |  | 2026-08-25 | Level 3
121975137 | pole | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2023-03-24 | 2024-08-25 | Level 2 | Standards change
121975173 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-12-03 | 2024-08-24 | Level 2 | Field Safety Reassessment
121975273 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-01-31 | 2026-08-24 | Level 3 | Standards change
121975276 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-01-23 | 2024-08-24 | Level 2 | Standards change
121975411 | insulator and brushing | Non-HFTD | Transmission | 2021-08-23 | 2022-08-23 | Level 2 | E | 2023-02-02 | 2024-08-23 | Level 2 | Standards change
121975583 | other | Non-HFTD | Transmission | 2021-08-25 | 2023-08-25 | Level 3 | F | 2024-08-27 | 2026-08-25 | Level 3 | GO 165 Inspection
121976368 | anchor/guy | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2023-12-29 | 2026-08-31 | Level 3 | Standards change
121976833 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-03-03 | 2026-08-24 | Level 3 | Standards change
121976940 | insulator and brushing | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2023-01-31 | 2026-08-27 | Level 3 | Standards change
121978248 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-09-24 | 2024-08-31 | Level 2 | Field Safety Reassessment
121978588 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-01-20 | 2024-08-24 | Level 2 | Standards change
121978685 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2023-12-28 | 2026-08-31 | Level 3 | Standards change
121978720 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-02-01 | 2024-08-24 | Level 2 | Standards change
121979092 | other | Non-HFTD | Transmission | 2021-08-25 | 2023-08-25 | Level 3 | F | 2024-07-26 | 2026-08-25 | Level 3 | GO 165 Inspection
121979227 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-04-06 | 2026-08-24 | Level 3 | Standards change
121979858 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-12-06 | 2024-08-26 | Level 2 | Field Safety Reassessment
121979859 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-08-27 | 2026-08-24 | Level 3 | GO 165 Inspection
121980010 | insulator and brushing | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-08-27 | 2024-08-24 | Level 2 | GO 165 Inspection
121980274 | other | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-02-05 | 2024-08-29 | Level 2 | Standards change
121980276 | anchor/guy | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2023-12-05 | 2026-08-27 | Level 3 | Standards change
121980308 | anchor/guy | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2023-12-08 | 2026-08-31 | Level 3 | Standards change
121980326 | other | Non-HFTD | Transmission | 2021-08-25 | 2023-08-25 | Level 3 | F | 2024-01-04 | 2026-08-25 | Level 3 | Standards change
121980333 | pole | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2023-02-16 | 2024-08-24 | Level 2 | Standards change
121980461 | anchor/guy | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-12-05 | 2026-08-26 | Level 3 | Standards change
121980464 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2023-12-05 | 2024-08-26 | Level 2 | Standards change
121980598 | insulator and brushing | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2024-09-24 | 2024-08-25 | Level 2 | Field Safety Reassessment
121980636 | insulator and brushing | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2024-05-21 | 2024-08-25 | Level 2 | Field Safety Reassessment
121980674 | other | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-02-14 | 2024-08-31 | Level 2 | Standards change
121980681 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-08-13 | 2026-08-31 | Level 3 | GO 165 Inspection
121980683 | anchor/guy | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2023-12-29 | 2026-08-25 | Level 3 | Standards change
121980730 | other | Non-HFTD | Transmission | 2021-08-24 | 2022-08-24 | Level 2 | E | 2024-12-16 | 2022-08-24 | Level 2 | Field Safety Reassessment
121980978 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-08-27 | 2026-08-24 | Level 3 | GO 165 Inspection
121981384 | pole | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-12-30 | 2024-08-31 | Level 2 | Field Safety Reassessment
121981827 | other | Non-HFTD | Transmission | 2021-08-24 | 2023-08-24 | Level 3 | F | 2024-01-10 | 2026-08-24 | Level 3 | Standards change
121981901 | other | Non-HFTD | Transmission | 2021-08-26 | 2023-08-26 | Level 3 | F | 2024-07-23 | 2026-08-26 | Level 3 | GO 165 Inspection
121981980 | pole | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2024-07-25 | 2024-08-27 | Level 2 | GO 165 Inspection
121981989 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-03 | 2026-08-31 | Level 3 | Standards change
121982123 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-04-06 | 2026-09-01 | Level 3 | Standards change
121982203 | pole | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2023-01-31 | 2024-08-30 | Level 2 | Standards change
121982234 | switch | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-11-17 | 2024-08-26 | Level 2 | Field Safety Reassessment
121982401 | other | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-08-31 | 2026-09-01 | Level 3 | GO 165 Inspection
121982416 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-25 | 2026-08-31 | Level 3 | Standards change
121983031 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-04-06 | 2026-09-01 | Level 3 | Standards change
121983153 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-25 | 2026-08-31 | Level 3 | Standards change
121984028 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-08-17 | 2026-09-01 | Level 3 | GO 165 Inspection
121984121 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-11-20 | 2026-09-01 | Level 3 | GO 165 Inspection
121984147 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2023-12-27 | 2026-08-31 | Level 3 | Standards change
121984214 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-11-19 | 2026-09-01 | Level 3 | GO 165 Inspection
121984374 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-11-19 | 2026-09-01 | Level 3 | GO 165 Inspection
121984422 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-11-19 | 2026-09-01 | Level 3 | GO 165 Inspection
121984493 | insulator and brushing | Non-HFTD | Transmission | 2021-08-25 | 2022-08-25 | Level 2 | E | 2024-10-28 | 2024-08-25 | Level 2 | GO 165 Inspection
121985536 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-10-24 | 2026-09-01 | Level 3 | GO 165 Inspection
121985563 | insulator and brushing | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-12-13 | 2024-09-01 | Level 2 | Field Safety Reassessment
121985567 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2023-01-12 | 2026-09-01 | Level 3 | Standards change
121986470 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-10-14 | 2026-08-30 | Level 3 | GO 165 Inspection
121986479 | other | Non-HFTD | Transmission | 2021-08-27 | 2023-08-27 | Level 3 | F | 2024-04-06 | 2026-08-27 | Level 3 | Standards change
121986526 | other | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2024-11-24 | 2024-08-27 | Level 2 | Field Safety Reassessment
121986607 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-10-22 | 2024-08-26 | Level 2 | GO 165 Inspection
121986796 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-10-14 | 2026-08-30 | Level 3 | GO 165 Inspection
121986985 | pole | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-11-26 | 2024-08-30 | Level 2 | Field Safety Reassessment
121987058 | pole | Non-HFTD | Transmission | 2021-08-28 | 2022-08-28 | Level 2 | E | 2023-03-09 | 2024-08-28 | Level 2 | Standards change
121988619 | other | Non-HFTD | Transmission | 2021-08-25 | 2026-08-25 | Level 3 | F |  | 2026-08-25 | Level 3
121988885 | other | Non-HFTD | Transmission | 2021-09-02 | 2024-09-02 | Level 2 | E | 2024-11-06 | 2026-09-02 | Level 3 | Field Safety Reassessment
121989315 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-12-27 | 2024-09-02 | Level 2 | Field Safety Reassessment
121989772 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-04-06 | 2026-09-02 | Level 3 | Standards change
121990080 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-08-31 | 2026-09-02 | Level 3 | GO 165 Inspection
121990313 | other | Non-HFTD | Transmission | 2021-08-30 | 2024-08-30 | Level 2 | E | 2024-12-18 | 2026-08-30 | Level 3 | Field Safety Reassessment
121990673 | insulator and brushing | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-02-01 | 2026-08-30 | Level 3 | Standards change
121990679 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-11-05 | 2024-09-02 | Level 2 | GO 165 Inspection
121990783 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-12-03 | 2024-09-02 | Level 2 | Field Safety Reassessment
121991344 | insulator and brushing | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-12-04 | 2024-08-30 | Level 2 | Field Safety Reassessment
121991537 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-16 | 2026-08-31 | Level 3 | Standards change
121991696 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-01-02 | 2026-08-30 | Level 3 | Standards change
121992224 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-04-06 | 2026-08-31 | Level 3 | Standards change
121992229 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-04 | 2026-08-31 | Level 3 | Standards change
121992334 | other | Non-HFTD | Transmission | 2021-08-27 | 2023-08-27 | Level 3 | F | 2024-09-13 | 2026-08-27 | Level 3 | GO 165 Inspection
121992363 | insulator and brushing | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-09-13 | 2024-09-01 | Level 2 | GO 165 Inspection
121992469 | insulator and brushing | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2024-09-13 | 2024-08-27 | Level 2 | GO 165 Inspection
121993080 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-02-09 | 2026-08-31 | Level 3 | Standards change
121993201 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-29 | 2026-08-31 | Level 3 | Standards change
121993366 | other | Non-HFTD | Transmission | 2021-08-30 | 2024-08-30 | Level 2 | E | 2024-11-25 | 2026-08-30 | Level 3 | Field Safety Reassessment
121993401 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-04-06 | 2026-08-31 | Level 3 | Standards change
121993514 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2024-08-31 | Level 2 | E | 2024-09-03 | 2022-08-31 | Level 2 | GO 165 Inspection
121993603 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-03 | 2026-08-31 | Level 3 | Standards change
121993691 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2023-01-31 | 2024-08-31 | Level 2 | Standards change
121993718 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2023-02-17 | 2026-08-31 | Level 3 | Standards change
121993811 | pole | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-10-02 | 2024-08-26 | Level 2 | Field Safety Reassessment
121993865 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-04-06 | 2026-08-31 | Level 3 | Standards change
121995730 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-08-20 | 2024-08-26 | Level 2 | GO 165 Inspection
121995753 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-04-06 | 2026-08-31 | Level 3 | Standards change
121995758 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2023-03-24 | 2024-09-02 | Level 2 | Standards change
121995839 | other | Non-HFTD | Transmission | 2021-08-27 | 2023-08-27 | Level 3 | F | 2024-01-18 | 2026-08-27 | Level 3 | Standards change
121995973 | anchor/guy | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-09-09 | 2026-08-30 | Level 3 | GO 165 Inspection
121995994 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-11-13 | 2024-08-31 | Level 2 | Field Safety Reassessment
121996364 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-10-08 | 2026-09-02 | Level 3 | GO 165 Inspection
121996525 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-10-04 | 2026-08-31 | Level 3 | GO 165 Inspection
121996550 | insulator and brushing | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2024-09-17 | 2026-09-03 | Level 3 | GO 165 Inspection
121996904 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-12-26 | 2024-08-31 | Level 2 | Field Safety Reassessment
121997264 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-04-06 | 2026-08-31 | Level 3 | Standards change
121997304 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-03 | 2026-08-31 | Level 3 | Standards change
121997438 | insulator and brushing | Non-HFTD | Transmission | 2021-08-27 | 2022-08-27 | Level 2 | E | 2023-07-03 | 2024-08-27 | Level 2 | GO 165 Inspection
121997458 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-25 | 2026-08-31 | Level 3 | Standards change
121997482 | insulator and brushing | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-12-16 | 2024-08-30 | Level 2 | Field Safety Reassessment
121997692 | other | Non-HFTD | Transmission | 2021-09-01 | 2026-09-01 | Level 3 | F | 2024-08-30 | 2026-09-01 | Level 3 | GO 165 Inspection
121997724 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-03 | 2026-08-31 | Level 3 | Standards change
121997824 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2023-01-17 | 2026-08-31 | Level 3 | Standards change
121998014 | other | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2024-07-26 | 2026-09-03 | Level 3 | GO 165 Inspection
121998183 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2023-12-19 | 2024-08-31 | Level 2 | Standards change
121998274 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-08-13 | 2026-08-31 | Level 3 | GO 165 Inspection
121998383 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2023-12-29 | 2026-08-31 | Level 3 | Standards change
121998389 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-01-10 | 2026-08-30 | Level 3 | Standards change
121998846 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-02-02 | 2026-08-31 | Level 3 | Standards change
121999474 | pole | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-08-22 | 2024-09-01 | Level 2 | Field Safety Reassessment
122001588 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-04-06 | 2026-08-31 | Level 3 | Standards change
122001628 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-01-03 | 2026-09-01 | Level 3 | Standards change
122001637 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-08-31 | 2024-08-31 | Level 2 | GO 165 Inspection
122001697 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-01-09 | 2026-08-30 | Level 3 | Standards change
122001780 | insulator and brushing | Non-HFTD | Transmission | 2021-08-26 | 2022-08-26 | Level 2 | E | 2024-10-29 | 2024-08-26 | Level 2 | GO 165 Inspection
122001820 | other | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2024-06-20 | 2026-09-03 | Level 3 | GO 165 Inspection
122001834 | insulator and brushing | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-08-13 | 2024-09-02 | Level 2 | Field Safety Reassessment
122001861 | other | Non-HFTD | Transmission | 2021-08-26 | 2023-08-26 | Level 3 | F | 2022-12-21 | 2026-08-26 | Level 3 | Standards change
122001907 | anchor/guy | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2023-11-29 | 2026-09-01 | Level 3 | Standards change
122001957 | other | Non-HFTD | Transmission | 2021-08-23 | 2023-08-23 | Level 3 | F | 2024-06-12 | 2026-08-23 | Level 3 | GO 165 Inspection
122002034 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-08-31 | 2026-08-30 | Level 3 | GO 165 Inspection
122002058 | other | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2023-03-24 | 2024-09-01 | Level 2 | Standards change
122002161 | other | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-09-04 | 2024-09-01 | Level 2 | GO 165 Inspection
122002162 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-04 | 2026-08-31 | Level 3 | Standards change
122002290 | insulator and brushing | Non-HFTD | Transmission | 2021-08-30 | 2022-08-30 | Level 2 | E | 2024-08-22 | 2024-08-30 | Level 2 | GO 165 Inspection
122002417 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-03 | 2026-08-31 | Level 3 | Standards change
122002508 | pole | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2023-03-24 | 2024-09-01 | Level 2 | Standards change
122002658 | other | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-11-01 | 2026-09-01 | Level 3 | GO 165 Inspection
122002689 | pole | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-12-16 | 2024-08-31 | Level 2 | Field Safety Reassessment
122002738 | pole | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2023-03-07 | 2024-09-01 | Level 2 | Standards change
122002739 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-01-03 | 2026-09-01 | Level 3 | Standards change
122002793 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2023-02-17 | 2026-08-31 | Level 3 | Standards change
122002875 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2023-01-31 | 2026-08-31 | Level 3 | Standards change
122006639 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122006732 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2023-10-09 | 2024-08-31 | Level 2 | Standards change
122007038 | insulator and brushing | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2024-02-07 | 2024-09-03 | Level 2 | Standards change
122007323 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122007381 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122007525 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122007569 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-01-03 | 2026-09-01 | Level 3 | Standards change
122007798 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122007845 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122007897 | other | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-10-28 | 2026-09-01 | Level 3 | GO 165 Inspection
122007915 | pole | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2024-09-09 | 2024-09-07 | Level 2 | GO 165 Inspection
122008432 | other | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-08-02 | 2024-09-01 | Level 2 | Field Safety Reassessment
122008466 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-08-31 | 2024-08-31 | Level 2 | GO 165 Inspection
122008947 | anchor/guy | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2024-07-26 | 2024-09-07 | Level 2 | GO 165 Inspection
122009435 | other | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2024-11-01 | 2026-09-07 | Level 3 | GO 165 Inspection
122009498 | pole | Non-HFTD | Transmission | 2021-09-07 | 2024-09-07 | Level 2 | E | 2024-10-11 | 2022-09-07 | Level 2 | GO 165 Inspection
122012552 | pole | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-01-12 | 2026-09-01 | Level 3 | Standards change
122012559 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-01-11 | 2026-09-01 | Level 3 | Standards change
122012893 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-12-16 | 2024-08-31 | Level 2 | Field Safety Reassessment
122013759 | other | Non-HFTD | Transmission | 2021-09-08 | 2026-09-08 | Level 3 | F |  | 2026-09-08 | Level 3
122014257 | other | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2023-12-27 | 2024-09-08 | Level 2 | Standards change
122014351 | other | Non-HFTD | Transmission | 2021-09-01 | 2026-09-01 | Level 3 | F |  | 2026-09-01 | Level 3
122014606 | pole | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-01-18 | 2026-09-02 | Level 3 | Standards change
122014790 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2023-12-01 | 2026-09-07 | Level 3 | Standards change
122015262 | other | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2024-10-05 | 2024-09-07 | Level 2 | GO 165 Inspection
122015901 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2023-02-17 | 2026-09-03 | Level 3 | Standards change
122016219 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2024-01-03 | 2026-09-03 | Level 3 | Standards change
122016226 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-12-06 | 2024-09-02 | Level 2 | Field Safety Reassessment
122016394 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-04-06 | 2026-09-02 | Level 3 | Standards change
122016463 | other | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2023-02-08 | 2026-09-03 | Level 3 | Standards change
122016509 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2023-08-04 | 2026-09-03 | Level 3 | Standards change
122016519 | anchor/guy | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-08-26 | 2026-09-02 | Level 3 | GO 165 Inspection
122016542 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-03-30 | 2026-09-02 | Level 3 | Standards change
122016607 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-10 | 2026-08-31 | Level 3 | Standards change
122016638 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-09-04 | 2024-08-31 | Level 2 | GO 165 Inspection
122016660 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-01-03 | 2026-08-30 | Level 3 | Standards change
122018566 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2024-01-10 | 2026-09-03 | Level 3 | Standards change
122019837 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2024-04-06 | 2026-09-03 | Level 3 | Standards change
122019986 | splice | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2023-12-06 | 2024-09-07 | Level 2 | Standards change
122020070 | insulator and brushing | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2022-12-15 | 2024-09-08 | Level 2 | Standards change
122020195 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-09-03 | 2024-08-31 | Level 2 | GO 165 Inspection
122020196 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2022-08-31 | Level 2 | E | 2024-09-03 | 2024-08-31 | Level 2 | GO 165 Inspection
122020197 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-09-03 | 2024-08-31 | Level 2 | GO 165 Inspection
122020294 | insulator and brushing | Non-HFTD | Transmission | 2021-08-31 | 2024-08-31 | Level 2 | E | 2024-08-31 | 2022-08-31 | Level 2 | GO 165 Inspection
122020429 | other | Non-HFTD | Transmission | 2021-08-30 | 2023-08-30 | Level 3 | F | 2024-04-06 | 2026-08-30 | Level 3 | Standards change
122020646 | insulator and brushing | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2024-02-14 | 2024-09-03 | Level 2 | Standards change
122020747 | other | Non-HFTD | Transmission | 2021-09-09 | 2023-09-09 | Level 3 | F | 2023-12-08 | 2026-09-09 | Level 3 | Standards change
122021081 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-10-08 | 2026-09-02 | Level 3 | GO 165 Inspection
122021267 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-12-12 | 2026-09-02 | Level 3 | Standards change
122021279 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2023-12-12 | 2026-09-03 | Level 3 | Standards change
122021436 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-02-02 | 2026-09-02 | Level 3 | Standards change
122021526 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122021532 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2024-04-06 | 2026-09-03 | Level 3 | Standards change
122021591 | anchor/guy | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-01-18 | 2026-09-02 | Level 3 | Standards change
122021593 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-12-07 | 2026-09-02 | Level 3 | Standards change
122021631 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-03 | 2026-08-31 | Level 3 | Standards change
122021673 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-03 | 2026-09-02 | Level 3 | Standards change
122021675 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-06-15 | 2026-09-02 | Level 3 | Standards change
122021687 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2023-08-04 | 2026-09-03 | Level 3 | Standards change
122021695 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2024-01-10 | 2026-09-03 | Level 3 | Standards change
122021724 | anchor/guy | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2023-08-02 | 2024-09-03 | Level 2 | Standards change
122021774 | other | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2023-12-14 | 2024-09-03 | Level 2 | Standards change
122021842 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-01-04 | 2026-08-31 | Level 3 | Standards change
122021843 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122021937 | anchor/guy | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2024-01-05 | 2026-09-07 | Level 3 | Standards change
122021944 | other | Non-HFTD | Transmission | 2021-08-31 | 2023-08-31 | Level 3 | F | 2024-08-27 | 2026-08-31 | Level 3 | GO 165 Inspection
122033539 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2024-06-19 | 2026-09-08 | Level 3 | GO 165 Inspection
122033560 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2024-06-19 | 2026-09-08 | Level 3 | GO 165 Inspection
122033561 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2024-06-19 | 2026-09-08 | Level 3 | GO 165 Inspection
122033640 | insulator and brushing | Non-HFTD | Transmission | 2021-09-07 | 2024-09-07 | Level 2 | E | 2024-10-05 | 2024-09-07 | Level 2 | GO 165 Inspection
122033707 | insulator and brushing | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2023-02-14 | 2022-09-07 | Level 2 | Standards change
122033896 | insulator and brushing | Non-HFTD | Transmission | 2021-09-01 | 2022-09-01 | Level 2 | E | 2024-12-17 | 2024-09-01 | Level 2 | Field Safety Reassessment
122034277 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-03 | 2026-09-02 | Level 3 | Standards change
122034357 | other | Non-HFTD | Transmission | 2021-09-03 | 2023-09-03 | Level 3 | F | 2024-04-06 | 2026-09-03 | Level 3 | Standards change
122034569 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2024-04-06 | 2026-09-08 | Level 3 | Standards change
122034629 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-04-06 | 2026-09-10 | Level 3 | Standards change
122034709 | other | Non-HFTD | Transmission | 2021-09-01 | 2023-09-01 | Level 3 | F | 2024-01-11 | 2026-09-01 | Level 3 | Standards change
122034951 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122034960 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2024-04-06 | 2026-09-08 | Level 3 | Standards change
122035010 | other | Non-HFTD | Transmission | 2021-09-09 | 2023-09-09 | Level 3 | F | 2024-04-06 | 2026-09-09 | Level 3 | Standards change
122035017 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-11-04 | 2024-09-02 | Level 2 | GO 165 Inspection
122035300 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-04-06 | 2026-09-10 | Level 3 | Standards change
122035526 | anchor/guy | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-09-18 | 2026-09-08 | Level 3 | GO 165 Inspection
122035842 | pole | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-11-27 | 2024-09-02 | Level 2 | Field Safety Reassessment
122035844 | pole | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2024-12-20 | 2024-09-03 | Level 2 | Field Safety Reassessment
122036030 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2023-12-12 | 2026-09-02 | Level 3 | Standards change
122036037 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-03 | 2026-09-02 | Level 3 | Standards change
122036097 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-10 | 2026-09-02 | Level 3 | Standards change
122036295 | pole | Non-HFTD | Transmission | 2021-09-03 | 2022-09-03 | Level 2 | E | 2023-03-06 | 2024-09-03 | Level 2 | Standards change
122036296 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-03 | 2026-09-02 | Level 3 | Standards change
122036560 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-06-24 | 2026-09-02 | Level 3 | GO 165 Inspection
122036597 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-08-08 | 2026-09-07 | Level 3 | GO 165 Inspection
122036880 | anchor/guy | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-01-10 | 2026-09-10 | Level 3 | Standards change
122037222 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-07-31 | 2026-09-10 | Level 3 | GO 165 Inspection
122037611 | pole | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-08-13 | 2024-09-08 | Level 2 | GO 165 Inspection
122037921 | pole | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-06-19 | 2024-09-08 | Level 2 | GO 165 Inspection
122037926 | pole | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-06-19 | 2024-09-08 | Level 2 | GO 165 Inspection
122039249 | pole | Non-HFTD | Transmission | 2021-09-11 | 2022-09-11 | Level 2 | E | 2024-12-03 | 2024-09-11 | Level 2 | Field Safety Reassessment
122041157 | pole | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2023-08-10 | 2026-09-08 | Level 3 | Standards change
122041577 | other | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2023-01-26 | 2026-09-13 | Level 3 | Standards change
122041724 | pole | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-12-08 | 2024-09-13 | Level 2 | Field Safety Reassessment
122043171 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-03 | 2026-09-02 | Level 3 | Standards change
122043365 | other | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2023-08-02 | 2024-09-10 | Level 2 | Standards change
122043415 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-04-06 | 2026-09-13 | Level 3 | Standards change
122043522 | insulator and brushing | Non-HFTD | Transmission | 2021-09-08 | 2024-09-08 | Level 2 | E | 2024-10-05 | 2024-09-08 | Level 2 | GO 165 Inspection
122043576 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-04-06 | 2026-09-13 | Level 3 | Standards change
122043669 | pole | Non-HFTD | Transmission | 2021-09-09 | 2023-09-09 | Level 3 | F | 2024-01-16 | 2026-09-09 | Level 3 | Standards change
122044232 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2023-08-18 | 2026-09-10 | Level 3 | Standards change
122046235 | pole | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-12-27 | 2026-09-13 | Level 3 | Standards change
122046236 | pole | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-12-27 | 2026-09-13 | Level 3 | Standards change
122046528 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-04-06 | 2026-09-07 | Level 3 | Standards change
122047163 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122047226 | other | Non-HFTD | Transmission | 2021-09-09 | 2022-09-09 | Level 2 | E | 2023-07-21 | 2026-09-09 | Level 3 | Standards change
122047487 | anchor/guy | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-11-13 | 2026-09-10 | Level 3 | GO 165 Inspection
122047620 | pole | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-12-03 | 2024-09-14 | Level 2 | Field Safety Reassessment
122047768 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122047982 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122048029 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122048295 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-10-30 | 2026-09-14 | Level 3 | GO 165 Inspection
122048870 | other | Non-HFTD | Transmission | 2021-09-02 | 2023-09-02 | Level 3 | F | 2024-01-03 | 2026-09-02 | Level 3 | Standards change
122049208 | anchor/guy | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-01-08 | 2026-09-14 | Level 3 | Standards change
122049339 | insulator and brushing | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2023-02-08 | 2024-09-14 | Level 2 | Standards change
122050024 | pole | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-05-21 | 2024-09-10 | Level 2 | Field Safety Reassessment
122050050 | insulator and brushing | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-12-03 | 2024-09-13 | Level 2 | Field Safety Reassessment
122050091 | insulator and brushing | Non-HFTD | Transmission | 2021-09-07 | 2022-09-07 | Level 2 | E | 2024-11-27 | 2026-09-07 | Level 3 | GO 165 Inspection
122051148 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-04-06 | 2026-09-10 | Level 3 | Standards change
122051925 | pole | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2024-10-08 | 2024-09-15 | Level 2 | Field Safety Reassessment
122052071 | other | Non-HFTD | Transmission | 2021-09-07 | 2023-09-07 | Level 3 | F | 2024-01-03 | 2026-09-07 | Level 3 | Standards change
122052348 | insulator and brushing | Non-HFTD | Transmission | 2021-09-02 | 2022-09-02 | Level 2 | E | 2024-08-27 | 2024-09-02 | Level 2 | GO 165 Inspection
122052710 | crossarm | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-12-23 | 2024-09-08 | Level 2 | Field Safety Reassessment
122053149 | other | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2024-04-06 | 2026-09-15 | Level 3 | Standards change
122053497 | insulator and brushing | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-02-12 | 2024-09-10 | Level 2 | Standards change
122053812 | other | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2024-08-23 | 2026-09-15 | Level 3 | GO 165 Inspection
122053815 | other | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2024-08-23 | 2022-09-15 | Level 2 | GO 165 Inspection
122053908 | other | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2024-07-24 | 2026-09-15 | Level 3 | GO 165 Inspection
122054669 | pole | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2023-07-26 | 2024-09-08 | Level 2 | Standards change
122054735 | pole | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-01-16 | 2024-09-10 | Level 2 | Standards change
122055135 | switch | Non-HFTD | Transmission | 2021-09-15 | 2024-09-15 | Level 2 | E | 2024-01-11 | 2022-09-15 | Level 2 | Standards change
122055341 | insulator and brushing | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-12-11 | 2024-09-13 | Level 2 | Field Safety Reassessment
122055368 | anchor/guy | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-09-23 | 2026-09-13 | Level 3 | Field Safety Reassessment
122055434 | other | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2024-07-25 | 2026-09-15 | Level 3 | GO 165 Inspection
122055441 | insulator and brushing | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-09-30 | 2024-09-13 | Level 2 | Field Safety Reassessment
122055442 | anchor/guy | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2023-12-14 | 2026-09-13 | Level 3 | Standards change
122055476 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2023-07-31 | 2026-09-08 | Level 3 | Standards change
122055559 | pole | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2023-10-10 | 2024-09-08 | Level 2 | GO 165 Inspection
122055849 | other | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-11-15 | 2024-09-08 | Level 2 | GO 165 Inspection
122055951 | other | Non-HFTD | Transmission | 2021-09-08 | 2022-09-08 | Level 2 | E | 2024-11-15 | 2026-09-08 | Level 3 | GO 165 Inspection
122055971 | insulator and brushing | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2023-01-13 | 2024-09-15 | Level 2 | Standards change
122056024 | other | Non-HFTD | Transmission | 2021-09-11 | 2023-09-11 | Level 3 | F | 2023-12-06 | 2026-09-11 | Level 3 | Standards change
122056111 | pole | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-12-08 | 2024-09-10 | Level 2 | Field Safety Reassessment
122056115 | other | Non-HFTD | Transmission | 2021-09-09 | 2023-09-09 | Level 3 | F | 2023-07-26 | 2026-09-09 | Level 3 | Standards change
122056160 | other | Non-HFTD | Transmission | 2021-09-08 | 2023-09-08 | Level 3 | F | 2024-04-06 | 2026-09-08 | Level 3 | Standards change
122056551 | anchor/guy | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-01-11 | 2026-09-10 | Level 3 | Standards change
122057549 | other | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2023-01-23 | 2026-09-10 | Level 3 | Standards change
122057975 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-08-27 | 2026-09-14 | Level 3 | GO 165 Inspection
122058301 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-03-06 | 2026-09-13 | Level 3 | Standards change
122058433 | insulator and brushing | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-11-04 | 2024-09-13 | Level 2 | GO 165 Inspection
122058452 | other | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-10-31 | 2024-09-14 | Level 2 | Field Safety Reassessment
122058717 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-12-27 | 2026-09-13 | Level 3 | Standards change
122058754 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-09-25 | 2024-09-16 | Level 2 | GO 165 Inspection
122058918 | other | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-09-24 | 2024-09-16 | Level 2 | GO 165 Inspection
122059174 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2023-12-28 | 2026-09-14 | Level 3 | Standards change
122059317 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122059397 | other | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-11-07 | 2024-09-16 | Level 2 | Field Safety Reassessment
122060174 | anchor/guy | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-08-05 | 2024-09-16 | Level 2 | Field Safety Reassessment
122060311 | pole | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-12-30 | 2024-09-16 | Level 2 | Field Safety Reassessment
122060450 | pole | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-08-08 | 2024-09-10 | Level 2 | Field Safety Reassessment
122060556 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-04-06 | 2026-09-10 | Level 3 | Standards change
122060647 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-04-06 | 2026-09-10 | Level 3 | Standards change
122060713 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-12-27 | 2026-09-13 | Level 3 | Standards change
122060821 | other | Non-HFTD | Transmission | 2021-09-10 | 2023-09-10 | Level 3 | F | 2024-04-06 | 2026-09-10 | Level 3 | Standards change
122060852 | other | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-01-11 | 2024-09-14 | Level 2 | Standards change
122060871 | insulator and brushing | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2023-01-19 | 2026-09-10 | Level 3 | Standards change
122060901 | insulator and brushing | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2023-01-13 | 2024-09-15 | Level 2 | Standards change
122060931 | pole | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2023-03-02 | 2024-09-10 | Level 2 | Standards change
122061118 | pole | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2024-10-14 | 2022-09-10 | Level 2 | Field Safety Reassessment
122061153 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-10-30 | 2026-09-13 | Level 3 | GO 165 Inspection
122061349 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-01-05 | 2026-09-13 | Level 3 | Standards change
122061513 | insulator and brushing | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-11-26 | 2024-09-13 | Level 2 | Field Safety Reassessment
122061519 | pole | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-07-18 | 2026-09-13 | Level 3 | Standards change
122063296 | pole | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2024-11-06 | 2024-09-15 | Level 2 | Field Safety Reassessment
122063309 | other | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2023-02-08 | 2026-09-13 | Level 3 | Standards change
122063435 | other | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-12-18 | 2024-09-13 | Level 2 | Field Safety Reassessment
122063560 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2023-02-03 | 2024-09-16 | Level 2 | Standards change
122063588 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2024-09-16 | Level 2 | E | 2024-11-22 | 2026-09-16 | Level 3 | Field Safety Reassessment
122063622 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2023-02-08 | 2026-09-13 | Level 3 | Standards change
122063759 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2023-02-03 | 2026-09-16 | Level 3 | Standards change
122063829 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2024-01-11 | 2026-09-16 | Level 3 | Standards change
122063936 | anchor/guy | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-07-25 | 2026-09-17 | Level 3 | GO 165 Inspection
122064400 | insulator and brushing | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2024-12-18 | 2024-09-15 | Level 2 | Field Safety Reassessment
122064416 | anchor/guy | Non-HFTD | Transmission | 2021-09-11 | 2022-09-11 | Level 2 | E | 2024-07-10 | 2024-09-11 | Level 2 | GO 165 Inspection
122064553 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2023-12-27 | 2026-09-16 | Level 3 | Standards change
122064839 | insulator and brushing | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2023-02-06 | 2024-09-13 | Level 2 | Standards change
122064943 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-01-10 | 2026-09-13 | Level 3 | Standards change
122065303 | other | Non-HFTD | Transmission | 2021-09-17 | 2023-09-17 | Level 3 | F | 2024-04-06 | 2026-09-17 | Level 3 | Standards change
122065453 | other | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2024-07-25 | 2026-09-15 | Level 3 | GO 165 Inspection
122065477 | pole | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2023-02-03 | 2024-09-13 | Level 2 | Standards change
122065640 | other | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-07-08 | 2026-09-17 | Level 3 | GO 165 Inspection
122065689 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122065812 | insulator and brushing | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2023-02-23 | 2024-09-14 | Level 2 | Standards change
122065958 | pole | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-11-25 | 2024-09-17 | Level 2 | Field Safety Reassessment
122066825 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-01-03 | 2026-09-13 | Level 3 | Standards change
122067717 | insulator and brushing | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-08-22 | 2024-09-17 | Level 2 | GO 165 Inspection
122067858 | other | Non-HFTD | Transmission | 2021-09-17 | 2026-09-17 | Level 3 | F |  | 2026-09-17 | Level 3
122068548 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2024-04-06 | 2026-09-16 | Level 3 | Standards change
122068554 | pole | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-12-30 | 2024-09-17 | Level 2 | Field Safety Reassessment
122068602 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2023-12-05 | 2024-09-16 | Level 2 | Standards change
122068617 | other | Non-HFTD | Transmission | 2021-09-13 | 2023-09-13 | Level 3 | F | 2024-01-05 | 2026-09-13 | Level 3 | Standards change
122068648 | other | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-09-18 | 2026-09-17 | Level 3 | GO 165 Inspection
122068763 | insulator and brushing | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-09-23 | 2024-09-14 | Level 2 | GO 165 Inspection
122068965 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-01-10 | 2026-09-14 | Level 3 | Standards change
122069020 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2024-04-06 | 2026-09-16 | Level 3 | Standards change
122069205 | insulator and brushing | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-11-22 | 2024-09-14 | Level 2 | Field Safety Reassessment
122071432 | insulator and brushing | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-12-26 | 2024-09-13 | Level 2 | Field Safety Reassessment
122071495 | other | Non-HFTD | Transmission | 2021-09-14 | 2023-09-14 | Level 3 | F | 2024-04-06 | 2026-09-14 | Level 3 | Standards change
122073818 | anchor/guy | Non-HFTD | Transmission | 2021-09-10 | 2022-09-10 | Level 2 | E | 2023-01-31 | 2026-09-10 | Level 3 | Standards change
122073852 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2024-08-29 | 2026-09-20 | Level 3 | GO 165 Inspection
122073964 | anchor/guy | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-10-22 | 2026-09-20 | Level 3 | GO 165 Inspection
122074810 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2024-08-30 | 2026-09-20 | Level 3 | GO 165 Inspection
122074811 | other | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-08-30 | 2026-09-20 | Level 3 | GO 165 Inspection
122075837 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-08-29 | 2024-09-20 | Level 2 | GO 165 Inspection
122075949 | other | Non-HFTD | Transmission | 2021-09-20 | 2026-09-20 | Level 2 | E | 2024-08-30 | 2022-09-20 | Level 2 | GO 165 Inspection
122075959 | other | Non-HFTD | Transmission | 2021-09-18 | 2023-09-18 | Level 3 | F | 2024-04-06 | 2026-09-18 | Level 3 | Standards change
122076033 | other | Non-HFTD | Transmission | 2021-09-18 | 2023-09-18 | Level 3 | F | 2023-12-28 | 2026-09-18 | Level 3 | Standards change
122076225 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2023-01-13 | 2026-09-20 | Level 3 | Standards change
122076634 | pole | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-10-24 | 2024-09-21 | Level 2 | GO 165 Inspection
122077066 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-11-04 | 2024-09-20 | Level 2 | Field Safety Reassessment
122077322 | other | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-06-19 | 2024-09-20 | Level 2 | GO 165 Inspection
122078295 | other | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2023-02-08 | 2026-09-15 | Level 3 | Standards change
122078768 | pole | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-12-30 | 2024-09-21 | Level 2 | Field Safety Reassessment
122079072 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-07-11 | 2024-09-21 | Level 2 | GO 165 Inspection
122079120 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-12-06 | 2024-09-21 | Level 2 | Field Safety Reassessment
122079141 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-07-10 | 2024-09-21 | Level 2 | GO 165 Inspection
122079354 | other | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2023-12-29 | 2026-09-21 | Level 3 | Standards change
122080380 | other | Non-HFTD | Transmission | 2021-09-18 | 2023-09-18 | Level 3 | F | 2024-04-06 | 2026-09-18 | Level 3 | Standards change
122080726 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2023-02-06 | 2024-09-16 | Level 2 | Standards change
122080865 | other | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2023-02-08 | 2026-09-13 | Level 3 | Standards change
122080866 | pole | Non-HFTD | Transmission | 2021-09-13 | 2022-09-13 | Level 2 | E | 2024-11-07 | 2024-09-13 | Level 2 | Field Safety Reassessment
122081024 | insulator and brushing | Non-HFTD | Transmission | 2021-09-18 | 2022-09-18 | Level 2 | E | 2024-09-06 | 2024-09-18 | Level 2 | GO 165 Inspection
122081212 | other | Non-HFTD | Transmission | 2021-09-17 | 2023-09-17 | Level 3 | F | 2024-09-25 | 2026-09-17 | Level 3 | GO 165 Inspection
122081346 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2023-12-28 | 2026-09-16 | Level 3 | Standards change
122081566 | pole | Non-HFTD | Transmission | 2021-09-15 | 2022-09-15 | Level 2 | E | 2024-12-11 | 2022-09-15 | Level 2 | Field Safety Reassessment
122081609 | other | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2023-12-28 | 2026-09-15 | Level 3 | Standards change
122081668 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2023-01-31 | 2026-09-16 | Level 3 | Standards change
122081726 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-11-24 | 2024-09-16 | Level 2 | Field Safety Reassessment
122081865 | pole | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2024-11-27 | 2024-09-14 | Level 2 | Field Safety Reassessment
122081866 | anchor/guy | Non-HFTD | Transmission | 2021-09-14 | 2026-09-14 | Level 3 | F |  | 2026-09-14 | Level 3
122081944 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-12-01 | 2024-09-21 | Level 2 | Field Safety Reassessment
122081995 | other | Non-HFTD | Transmission | 2021-09-17 | 2023-09-17 | Level 3 | F | 2023-12-28 | 2026-09-17 | Level 3 | Standards change
122082006 | pole | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2023-12-13 | 2026-09-16 | Level 3 | Standards change
122082194 | pole | Non-HFTD | Transmission | 2021-09-20 | 2024-09-20 | Level 2 | E | 2024-12-09 | 2022-09-20 | Level 2 | GO 165 Inspection
122082205 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-09-24 | 2024-09-20 | Level 2 | GO 165 Inspection
122082415 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-28 | 2026-09-21 | Level 3 | Standards change
122082456 | other | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-11-05 | 2026-09-17 | Level 3 | GO 165 Inspection
122082583 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-11-19 | 2024-09-21 | Level 2 | GO 165 Inspection
122083273 | pole | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-12-30 | 2024-09-20 | Level 2 | Field Safety Reassessment
122083297 | pole | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-08-15 | 2024-09-22 | Level 2 | Field Safety Reassessment
122083479 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122083839 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-12-03 | 2024-09-21 | Level 2 | Field Safety Reassessment
122084522 | pole | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-12-30 | 2024-09-20 | Level 2 | Field Safety Reassessment
122084675 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122085430 | other | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2023-12-29 | 2026-09-16 | Level 3 | Standards change
122085501 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122086813 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2024-04-06 | 2026-09-20 | Level 3 | Standards change
122086929 | insulator and brushing | Non-HFTD | Transmission | 2021-09-18 | 2022-09-18 | Level 2 | E | 2024-12-11 | 2024-09-18 | Level 2 | Field Safety Reassessment
122086952 | other | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-08-30 | 2024-09-20 | Level 2 | GO 165 Inspection
122087008 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2024-01-09 | 2026-09-20 | Level 3 | Standards change
122087033 | other | Non-HFTD | Transmission | 2021-09-18 | 2023-09-18 | Level 3 | F | 2024-04-06 | 2026-09-18 | Level 3 | Standards change
122087061 | pole | Non-HFTD | Transmission | 2021-09-18 | 2022-09-18 | Level 2 | E | 2022-12-20 | 2024-09-18 | Level 2 | Standards change
122087207 | insulator and brushing | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2023-03-03 | 2024-09-17 | Level 2 | Standards change
122087209 | other | Non-HFTD | Transmission | 2021-09-17 | 2023-09-17 | Level 3 | F | 2023-12-29 | 2026-09-17 | Level 3 | Standards change
122087213 | other | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2023-03-13 | 2026-09-21 | Level 3 | Standards change
122087242 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-28 | 2026-09-21 | Level 3 | Standards change
122087275 | other | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-08-30 | 2024-09-20 | Level 2 | GO 165 Inspection
122087276 | other | Non-HFTD | Transmission | 2021-09-17 | 2023-09-17 | Level 3 | F | 2024-01-11 | 2026-09-17 | Level 3 | Standards change
122087286 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2023-12-28 | 2026-09-22 | Level 3 | Standards change
122087326 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2023-12-12 | 2026-09-20 | Level 3 | Standards change
122087333 | pole | Non-HFTD | Transmission | 2021-09-17 | 2023-09-17 | Level 3 | F | 2024-01-11 | 2026-09-17 | Level 3 | Standards change
122087351 | other | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-02-05 | 2024-09-16 | Level 2 | Standards change
122087724 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2022-12-14 | 2024-09-22 | Level 2 | Standards change
122088039 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-11-04 | 2024-09-20 | Level 2 | Field Safety Reassessment
122088256 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2023-12-19 | 2026-09-20 | Level 3 | Standards change
122089098 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-02-14 | 2024-09-23 | Level 2 | Standards change
122089225 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-08-08 | 2024-09-22 | Level 2 | Field Safety Reassessment
122089278 | pole | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-12-06 | 2022-09-23 | Level 2 | Field Safety Reassessment
122089809 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-07-12 | 2026-09-23 | Level 3 | GO 165 Inspection
122089999 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-05-01 | 2022-09-23 | Level 2 | GO 165 Inspection
122090034 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-01-08 | 2026-09-23 | Level 3 | Standards change
122090332 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2023-01-11 | 2024-09-23 | Level 2 | Standards change
122090379 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2023-12-28 | 2026-09-23 | Level 3 | Standards change
122090532 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-09-03 | 2026-09-23 | Level 3 | GO 165 Inspection
122090726 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-08-13 | 2026-09-22 | Level 3 | GO 165 Inspection
122091202 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-11-15 | 2024-09-22 | Level 2 | GO 165 Inspection
122091607 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2023-03-06 | 2026-09-20 | Level 3 | Standards change
122091759 | pole | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2023-03-01 | 2024-09-22 | Level 2 | Standards change
122091811 | other | Non-HFTD | Transmission | 2021-09-17 | 2022-09-17 | Level 2 | E | 2024-03-11 | 2024-09-17 | Level 2 | GO 165 Inspection
122091900 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122091932 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2024-04-06 | 2026-09-16 | Level 3 | Standards change
122092181 | other | Non-HFTD | Transmission | 2021-09-16 | 2023-09-16 | Level 3 | F | 2023-12-22 | 2026-09-16 | Level 3 | Standards change
122092308 | other | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-09-18 | 2024-09-20 | Level 2 | GO 165 Inspection
122092313 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-12 | 2026-09-21 | Level 3 | Standards change
122092368 | other | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2024-01-11 | 2026-09-20 | Level 3 | Standards change
122092375 | insulator and brushing | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2024-12-11 | 2024-09-16 | Level 2 | Field Safety Reassessment
122092461 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2024-01-18 | 2026-09-21 | Level 3 | Standards change
122092464 | other | Non-HFTD | Transmission | 2021-09-20 | 2026-09-20 | Level 3 | F |  | 2026-09-20 | Level 3
122092573 | insulator and brushing | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 2 | E | 2024-08-28 | 2024-09-20 | Level 2 | GO 165 Inspection
122092591 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-12-06 | 2024-09-23 | Level 2 | Field Safety Reassessment
122092656 | other | Non-HFTD | Transmission | 2021-09-21 | 2026-09-21 | Level 3 | F | 2024-09-18 | 2024-09-21 | Level 2 | GO 165 Inspection
122092802 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-29 | 2026-09-21 | Level 3 | Standards change
122092957 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2022-12-20 | 2026-09-21 | Level 3 | Standards change
122094274 | pole | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-05-20 | 2024-09-21 | Level 2 | Field Safety Reassessment
122094295 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-08-27 | 2024-09-22 | Level 2 | GO 165 Inspection
122094314 | other | Non-HFTD | Transmission | 2021-09-20 | 2026-09-20 | Level 2 | E | 2024-08-15 | 2024-09-20 | Level 2 | GO 165 Inspection
122094322 | other | Non-HFTD | Transmission | 2021-09-18 | 2023-09-18 | Level 3 | F | 2024-04-06 | 2026-09-18 | Level 3 | Standards change
122094403 | pole | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-09-17 | 2024-09-22 | Level 2 | Field Safety Reassessment
122094439 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122094520 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-01-16 | 2026-09-23 | Level 3 | Standards change
122094535 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-29 | 2026-09-21 | Level 3 | Standards change
122094552 | pole | Non-HFTD | Transmission | 2021-09-20 | 2022-09-20 | Level 3 | F | 2024-02-07 | 2022-09-20 | Level 2 | Field Safety Reassessment
122094856 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-01-04 | 2026-09-22 | Level 3 | Standards change
122095138 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-04-06 | 2026-09-23 | Level 3 | Standards change
122095407 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-20 | 2026-09-21 | Level 3 | Standards change
122095578 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2023-12-27 | 2026-09-21 | Level 3 | Standards change
122095704 | other | Non-HFTD | Transmission | 2021-09-16 | 2022-09-16 | Level 2 | E | 2023-01-30 | 2024-09-16 | Level 2 | Standards change
122095807 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-05-07 | 2024-09-21 | Level 2 | Field Safety Reassessment
122095988 | pole | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2024-10-17 | 2024-09-24 | Level 2 | Field Safety Reassessment
122096073 | pole | Non-HFTD | Transmission | 2021-09-20 | 2023-09-20 | Level 3 | F | 2024-09-12 | 2026-09-20 | Level 3 | GO 165 Inspection
122096451 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-11-25 | 2024-09-21 | Level 2 | Field Safety Reassessment
122096732 | insulator and brushing | Non-HFTD | Transmission | 2021-09-14 | 2022-09-14 | Level 2 | E | 2023-12-06 | 2024-09-14 | Level 2 | Standards change
122096919 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122097188 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2023-10-26 | 2026-09-22 | Level 3 | Standards change
122097197 | other | Non-HFTD | Transmission | 2021-09-18 | 2023-09-18 | Level 3 | F | 2024-04-06 | 2026-09-18 | Level 3 | Standards change
122097418 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-12-06 | 2024-09-21 | Level 2 | Field Safety Reassessment
122097448 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-10-28 | 2024-09-22 | Level 2 | GO 165 Inspection
122097627 | pole | Non-HFTD | Transmission | 2021-09-15 | 2023-09-15 | Level 3 | F | 2022-12-21 | 2026-09-15 | Level 3 | Standards change
122097685 | insulator and brushing | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-07-24 | 2024-09-21 | Level 2 | Field Safety Reassessment
122097814 | pole | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2024-12-12 | 2024-09-24 | Level 2 | Field Safety Reassessment
122098030 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-01-04 | 2026-09-23 | Level 3 | Standards change
122098206 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2024-09-23 | Level 2 | E | 2024-11-12 | 2022-09-23 | Level 2 | GO 165 Inspection
122098266 | pole | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-10-04 | 2026-09-24 | Level 3 | GO 165 Inspection
122098373 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2024-07-08 | 2026-09-21 | Level 3 | GO 165 Inspection
122098454 | pole | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2023-01-11 | 2026-09-24 | Level 3 | Standards change
122098540 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122098904 | other | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2024-02-16 | 2024-09-24 | Level 2 | Standards change
122100434 | other | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2024-04-06 | 2026-09-25 | Level 3 | Standards change
122100954 | other | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2024-04-06 | 2026-09-25 | Level 3 | Standards change
122101144 | pole | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2023-12-18 | 2026-09-25 | Level 3 | Standards change
122103348 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-05-13 | 2024-09-22 | Level 2 | Field Safety Reassessment
122103541 | splice | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2023-01-18 | 2024-09-25 | Level 2 | Standards change
122103972 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-01-03 | 2026-09-22 | Level 3 | Standards change
122104325 | other | Non-HFTD | Transmission | 2021-09-23 | 2026-09-23 | Level 3 | F | 2024-11-13 | 2026-09-23 | Level 3 | GO 165 Inspection
122104809 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2024-04-06 | 2026-09-27 | Level 3 | Standards change
122105474 | other | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2024-04-06 | 2026-09-25 | Level 3 | Standards change
122105901 | splice | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122106074 | splice | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2023-01-18 | 2024-09-25 | Level 2 | Standards change
122107092 | other | Non-HFTD | Transmission | 2021-09-27 | 2022-09-27 | Level 2 | E | 2024-07-10 | 2024-09-27 | Level 2 | GO 165 Inspection
122107219 | other | Non-HFTD | Transmission | 2021-09-21 | 2022-09-21 | Level 2 | E | 2024-10-11 | 2024-09-21 | Level 2 | GO 165 Inspection
122107430 | other | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2024-08-15 | 2022-09-22 | Level 2 | GO 165 Inspection
122107433 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2023-10-26 | 2026-09-23 | Level 3 | Standards change
122107453 | pole | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-10-10 | 2024-09-23 | Level 2 | GO 165 Inspection
122107459 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-12-02 | 2024-09-23 | Level 2 | Field Safety Reassessment
122107592 | other | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2024-02-05 | 2024-09-25 | Level 2 | Standards change
122108092 | splice | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122108575 | other | Non-HFTD | Transmission | 2021-09-27 | 2021-12-27 | Level 2 | E | 2024-12-30 | 2021-12-27 | Level 2 | Field Safety Reassessment
122108762 | anchor/guy | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122108879 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2024-07-09 | 2026-09-27 | Level 3 | GO 165 Inspection
122109123 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2023-12-27 | 2026-09-27 | Level 3 | Standards change
122109323 | insulator and brushing | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2024-01-17 | 2024-09-24 | Level 2 | Standards change
122109561 | other | Non-HFTD | Transmission | 2021-09-27 | 2022-09-27 | Level 2 | E | 2024-10-16 | 2026-09-27 | Level 3 | GO 165 Inspection
122109699 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-04-06 | 2026-09-23 | Level 3 | Standards change
122109861 | other | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2023-01-23 | 2026-09-23 | Level 3 | Standards change
122112238 | pole | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-12-09 | 2024-09-28 | Level 2 | Field Safety Reassessment
122112892 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-04-06 | 2026-09-28 | Level 3 | Standards change
122113169 | other | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2023-04-11 | 2024-09-28 | Level 2 | Standards change
122115429 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-04-06 | 2026-09-28 | Level 3 | Standards change
122115723 | insulator and brushing | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-10-29 | 2024-09-23 | Level 2 | GO 165 Inspection
122115761 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-04-06 | 2026-09-23 | Level 3 | Standards change
122115804 | other | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-08-27 | 2026-09-23 | Level 3 | GO 165 Inspection
122115905 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-09-26 | 2026-09-23 | Level 3 | GO 165 Inspection
122116109 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2023-12-27 | 2026-09-23 | Level 3 | Standards change
122116266 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122116483 | other | Non-HFTD | Transmission | 2021-09-23 | 2024-09-23 | Level 2 | E | 2024-11-04 | 2026-09-23 | Level 3 | Field Safety Reassessment
122116580 | insulator and brushing | Non-HFTD | Transmission | 2021-09-22 | 2022-09-22 | Level 2 | E | 2023-02-06 | 2024-09-22 | Level 2 | Standards change
122116591 | other | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-12-02 | 2024-09-23 | Level 2 | Field Safety Reassessment
122116599 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-01-08 | 2026-09-23 | Level 3 | Standards change
122116667 | pole | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-08-27 | 2024-09-23 | Level 2 | GO 165 Inspection
122116670 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122117560 | anchor/guy | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2023-08-11 | 2026-09-28 | Level 3 | Standards change
122117583 | other | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-12-29 | 2026-09-24 | Level 3 | Standards change
122117893 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-09 | 2024-09-29 | Level 2 | Field Safety Reassessment
122118188 | pole | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-01-11 | 2026-09-29 | Level 3 | Standards change
122118285 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122118436 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-04-06 | 2026-09-28 | Level 3 | Standards change
122119147 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122119308 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-09-13 | 2024-09-29 | Level 2 | GO 165 Inspection
122119432 | anchor/guy | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-01-19 | 2026-09-29 | Level 3 | Standards change
122119465 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-28 | 2024-09-29 | Level 2 | Standards change
122119927 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122120049 | other | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2023-11-29 | 2024-09-28 | Level 2 | Standards change
122120063 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-10-15 | 2024-09-29 | Level 2 | GO 165 Inspection
122120086 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-10-15 | 2026-09-29 | Level 3 | GO 165 Inspection
122120191 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-28 | 2024-09-29 | Level 2 | Standards change
122120893 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-28 | 2024-09-29 | Level 2 | Standards change
122121505 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-20 | 2024-09-29 | Level 2 | Standards change
122121623 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-09 | 2022-09-29 | Level 2 | Field Safety Reassessment
122121631 | crossarm | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-09 | 2022-09-29 | Level 2 | Field Safety Reassessment
122121871 | pole | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-12-30 | 2024-09-28 | Level 2 | Field Safety Reassessment
122122356 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122122362 | other | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2024-04-06 | 2026-09-25 | Level 3 | Standards change
122122583 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122122804 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2024-04-06 | 2026-09-27 | Level 3 | Standards change
122122873 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122123050 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122123071 | other | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2024-04-06 | 2026-09-25 | Level 3 | Standards change
122123153 | anchor/guy | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122123249 | anchor/guy | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122123302 | anchor/guy | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2023-01-17 | 2026-09-25 | Level 3 | Standards change
122123306 | anchor/guy | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-25 | 2024-09-24 | Level 2 | Standards change
122123337 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122123422 | splice | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-06 | 2024-09-28 | Level 2 | Standards change
122123434 | anchor/guy | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-01-30 | 2024-09-29 | Level 2 | Standards change
122123449 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2023-12-22 | 2026-09-23 | Level 3 | Standards change
122123516 | anchor/guy | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-01-26 | 2026-09-28 | Level 3 | Standards change
122123560 | insulator and brushing | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-12-11 | 2022-09-28 | Level 2 | Field Safety Reassessment
122123563 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-04-06 | 2026-09-23 | Level 3 | Standards change
122123574 | anchor/guy | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2024-07-24 | 2026-09-23 | Level 3 | GO 165 Inspection
122123600 | pole | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2024-11-14 | 2026-09-25 | Level 3 | GO 165 Inspection
122123625 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-04-06 | 2026-09-23 | Level 3 | Standards change
122123673 | other | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2023-09-18 | 2026-09-23 | Level 3 | Standards change
122123674 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-01-18 | 2026-09-24 | Level 3 | Standards change
122123704 | insulator and brushing | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122123735 | pole | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2024-12-06 | 2024-09-25 | Level 2 | Field Safety Reassessment
122123752 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-04-06 | 2026-09-24 | Level 3 | Standards change
122123753 | insulator and brushing | Non-HFTD | Transmission | 2021-09-25 | 2024-09-25 | Level 2 | E | 2024-11-24 | 2026-09-25 | Level 3 | Field Safety Reassessment
122124274 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-30 | 2024-09-29 | Level 2 | Field Safety Reassessment
122124350 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-07-10 | 2024-09-29 | Level 2 | GO 165 Inspection
122124383 | anchor/guy | Non-HFTD | Transmission | 2021-09-25 | 2022-09-25 | Level 2 | E | 2023-01-31 | 2026-09-25 | Level 3 | Standards change
122124520 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2023-12-27 | 2026-09-27 | Level 3 | Standards change
122124763 | insulator and brushing | Non-HFTD | Transmission | 2021-09-27 | 2022-09-27 | Level 2 | E | 2024-10-10 | 2024-09-27 | Level 2 | GO 165 Inspection
122125530 | pole | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2023-12-28 | 2024-09-30 | Level 2 | Standards change
122127991 | insulator and brushing | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-11-19 | 2024-09-29 | Level 2 | GO 165 Inspection
122128023 | insulator and brushing | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-11-12 | 2024-09-30 | Level 2 | GO 165 Inspection
122128325 | pole | Non-HFTD | Transmission | 2021-09-18 | 2022-09-18 | Level 2 | E | 2023-03-08 | 2024-09-18 | Level 2 | Standards change
122128827 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2024-04-06 | 2026-09-30 | Level 3 | Standards change
122129822 | pole | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-12-07 | 2024-09-30 | Level 2 | Field Safety Reassessment
122129910 | other | Non-HFTD | Transmission | 2021-09-24 | 2022-09-24 | Level 2 | E | 2023-01-18 | 2024-09-24 | Level 2 | Standards change
122129916 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-12-30 | 2026-09-28 | Level 3 | Field Safety Reassessment
122130165 | crossarm | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-08-07 | 2024-09-28 | Level 2 | Field Safety Reassessment
122130193 | anchor/guy | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-08-07 | 2024-09-28 | Level 2 | Field Safety Reassessment
122130254 | insulator and brushing | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-09-28 | 2024-09-30 | Level 2 | GO 165 Inspection
122130394 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2024-04-06 | 2026-09-27 | Level 3 | Standards change
122130510 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-12-09 | 2026-09-24 | Level 3 | GO 165 Inspection
122130515 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-12-28 | 2026-09-29 | Level 3 | Standards change
122130557 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2023-12-29 | 2026-09-28 | Level 3 | Standards change
122130614 | other | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-02-05 | 2024-09-29 | Level 2 | Standards change
122130673 | insulator and brushing | Non-HFTD | Transmission | 2021-09-27 | 2022-09-27 | Level 2 | E | 2024-07-24 | 2024-09-27 | Level 2 | GO 165 Inspection
122130704 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2023-12-28 | 2026-09-27 | Level 3 | Standards change
122130829 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-04-06 | 2026-09-28 | Level 3 | Standards change
122130899 | other | Non-HFTD | Transmission | 2021-09-28 | 2024-09-28 | Level 2 | E | 2024-11-26 | 2022-09-28 | Level 2 | Field Safety Reassessment
122130979 | other | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2023-12-28 | 2026-09-28 | Level 3 | Standards change
122131008 | pole | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-12-13 | 2024-09-28 | Level 2 | Field Safety Reassessment
122131089 | other | Non-HFTD | Transmission | 2021-09-25 | 2023-09-25 | Level 3 | F | 2024-04-06 | 2026-09-25 | Level 3 | Standards change
122131183 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-04-06 | 2026-09-28 | Level 3 | Standards change
122132443 | insulator and brushing | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-11-19 | 2024-09-28 | Level 2 | Field Safety Reassessment
122132582 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-04-06 | 2026-09-28 | Level 3 | Standards change
122132585 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-12-01 | 2026-09-29 | Level 3 | Standards change
122132661 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-11-04 | 2024-09-29 | Level 2 | GO 165 Inspection
122132673 | other | Non-HFTD | Transmission | 2021-09-23 | 2023-09-23 | Level 3 | F | 2024-06-24 | 2026-09-23 | Level 3 | GO 165 Inspection
122132719 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2024-04-06 | 2026-09-30 | Level 3 | Standards change
122132751 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2024-04-06 | 2026-09-27 | Level 3 | Standards change
122132843 | insulator and brushing | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2023-02-10 | 2024-09-28 | Level 2 | Standards change
122132909 | other | Non-HFTD | Transmission | 2021-09-27 | 2023-09-27 | Level 3 | F | 2023-12-29 | 2026-09-27 | Level 3 | Standards change
122132954 | other | Non-HFTD | Transmission | 2021-09-21 | 2023-09-21 | Level 3 | F | 2024-04-06 | 2026-09-21 | Level 3 | Standards change
122133039 | other | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-02-05 | 2024-09-29 | Level 2 | Standards change
122133045 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2023-12-29 | 2026-09-28 | Level 3 | Standards change
122133120 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-11-05 | 2024-09-29 | Level 2 | Field Safety Reassessment
122133267 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-09 | 2024-09-29 | Level 2 | Field Safety Reassessment
122133269 | pole | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-09-18 | 2024-10-01 | Level 2 | Field Safety Reassessment
122133360 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-01-09 | 2026-09-29 | Level 3 | Standards change
122133430 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-11-01 | 2024-09-29 | Level 2 | GO 165 Inspection
122133681 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-02-17 | 2026-09-29 | Level 3 | Standards change
122133963 | other | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2023-01-25 | 2026-09-28 | Level 3 | Standards change
122133972 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2023-12-22 | 2026-09-28 | Level 3 | Standards change
122134025 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-12-28 | 2026-09-29 | Level 3 | Standards change
122134127 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-08-20 | 2024-09-29 | Level 2 | GO 165 Inspection
122134166 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2023-12-22 | 2026-09-28 | Level 3 | Standards change
122134293 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122134394 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2024-04-06 | 2026-09-30 | Level 3 | Standards change
122134552 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2023-12-29 | 2026-09-28 | Level 3 | Standards change
122134856 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122135020 | insulator and brushing | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-10-07 | 2024-09-28 | Level 2 | GO 165 Inspection
122135106 | pole | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-12-10 | 2024-10-01 | Level 2 | Field Safety Reassessment
122135130 | insulator and brushing | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-09-29 | 2024-10-01 | Level 2 | Field Safety Reassessment
122135244 | insulator and brushing | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2023-11-17 | 2024-10-01 | Level 2 | Standards change
122135264 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2024-04-06 | 2026-09-30 | Level 3 | Standards change
122135266 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-02 | 2024-09-29 | Level 2 | Field Safety Reassessment
122135603 | insulator and brushing | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-09-18 | 2024-10-01 | Level 2 | Field Safety Reassessment
122135659 | pole | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2023-11-17 | 2024-10-01 | Level 2 | Standards change
122135856 | other | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2023-12-26 | 2026-10-01 | Level 3 | Standards change
122136154 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122136268 | insulator and brushing | Non-HFTD | Transmission | 2021-10-01 | 2024-10-01 | Level 2 | E | 2024-08-19 | 2022-10-01 | Level 2 | GO 165 Inspection
122136376 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-11-26 | 2024-10-01 | Level 2 | Field Safety Reassessment
122136408 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-09-18 | 2024-10-01 | Level 2 | Field Safety Reassessment
122136526 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-04-04 | 2024-09-29 | Level 2 | GO 165 Inspection
122136865 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-02-15 | 2026-09-29 | Level 3 | Standards change
122136965 | other | Non-HFTD | Transmission | 2021-09-29 | 2024-09-29 | Level 2 | E | 2024-12-13 | 2026-09-29 | Level 3 | Field Safety Reassessment
122137120 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-02-10 | 2026-09-29 | Level 3 | Standards change
122137211 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-09-16 | 2024-10-01 | Level 2 | GO 165 Inspection
122137274 | pole | Non-HFTD | Transmission | 2021-09-27 | 2022-09-27 | Level 2 | E | 2024-10-09 | 2024-09-27 | Level 2 | GO 165 Inspection
122139588 | other | Non-HFTD | Transmission | 2021-10-02 | 2022-10-02 | Level 2 | E | 2024-09-18 | 2024-10-02 | Level 2 | Field Safety Reassessment
122139691 | other | Non-HFTD | Transmission | 2021-10-02 | 2022-10-02 | Level 2 | E | 2023-11-17 | 2026-10-02 | Level 3 | Standards change
122142040 | other | Non-HFTD | Transmission | 2021-10-02 | 2022-10-02 | Level 2 | E | 2024-10-09 | 2026-10-01 | Level 3 | GO 165 Inspection
122142926 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-04-06 | 2026-10-04 | Level 3 | Standards change
122143042 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-04-06 | 2026-10-04 | Level 3 | Standards change
122143457 | pole | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2023-01-11 | 2026-10-04 | Level 3 | Standards change
122143599 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2023-12-28 | 2026-09-30 | Level 3 | Standards change
122144352 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-04-06 | 2026-10-04 | Level 3 | Standards change
122144437 | pole | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2024-07-24 | 2026-10-01 | Level 3 | GO 165 Inspection
122144809 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2024-10-04 | Level 2 | E | 2024-10-25 | 2022-10-04 | Level 2 | GO 165 Inspection
122147286 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2023-12-28 | 2026-10-04 | Level 3 | Standards change
122147737 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2023-11-17 | 2026-10-05 | Level 3 | Standards change
122149208 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-04-06 | 2026-10-05 | Level 3 | Standards change
122149354 | other | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2023-12-28 | 2026-10-01 | Level 3 | Standards change
122149952 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-09-13 | 2026-10-05 | Level 3 | GO 165 Inspection
122149954 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-09-13 | 2024-10-05 | Level 2 | GO 165 Inspection
122150174 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2023-11-14 | 2026-09-30 | Level 3 | Standards change
122150623 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-10-24 | 2024-10-04 | Level 2 | GO 165 Inspection
122150894 | anchor/guy | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2023-11-27 | 2026-10-05 | Level 3 | Standards change
122151768 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-12-30 | 2024-09-29 | Level 2 | Field Safety Reassessment
122151874 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2023-12-29 | 2026-09-28 | Level 3 | Standards change
122151879 | other | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2024-06-21 | 2026-10-01 | Level 3 | GO 165 Inspection
122152091 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-08-19 | 2026-10-01 | Level 3 | GO 165 Inspection
122152170 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2023-12-05 | 2026-10-04 | Level 3 | Standards change
122152220 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-04-06 | 2026-09-29 | Level 3 | Standards change
122152261 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2024-01-04 | 2026-09-30 | Level 3 | Standards change
122152273 | insulator and brushing | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-08-20 | 2024-09-30 | Level 2 | GO 165 Inspection
122152277 | other | Non-HFTD | Transmission | 2021-09-24 | 2023-09-24 | Level 3 | F | 2024-02-12 | 2026-09-24 | Level 3 | Standards change
122152356 | other | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2023-12-29 | 2026-10-01 | Level 3 | Standards change
122152408 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-01-25 | 2026-09-29 | Level 3 | Standards change
122152441 | other | Non-HFTD | Transmission | 2021-10-04 | 2024-10-04 | Level 2 | E | 2024-08-19 | 2022-10-04 | Level 2 | GO 165 Inspection
122152451 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-01-02 | 2026-09-28 | Level 3 | Standards change
122152597 | other | Non-HFTD | Transmission | 2021-09-30 | 2024-09-30 | Level 2 | E | 2024-12-02 | 2026-09-30 | Level 3 | Field Safety Reassessment
122152603 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2023-01-31 | 2024-10-04 | Level 2 | Standards change
122152645 | other | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-08-19 | 2024-10-04 | Level 2 | GO 165 Inspection
122152709 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-02-08 | 2026-09-29 | Level 3 | Standards change
122152713 | other | Non-HFTD | Transmission | 2021-09-28 | 2023-09-28 | Level 3 | F | 2024-02-01 | 2026-09-28 | Level 3 | Standards change
122152730 | other | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-11-01 | 2024-10-04 | Level 2 | GO 165 Inspection
122152894 | other | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2024-02-01 | 2026-10-01 | Level 3 | Standards change
122154051 | insulator and brushing | Non-HFTD | Transmission | 2021-10-02 | 2024-10-02 | Level 2 | E | 2024-12-02 | 2022-10-02 | Level 2 | Field Safety Reassessment
122154103 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122154247 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-11-01 | 2022-10-04 | Level 2 | GO 165 Inspection
122154673 | pole | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-12-17 | 2022-10-06 | Level 2 | Field Safety Reassessment
122155289 | pole | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-10-16 | 2024-10-06 | Level 2 | Field Safety Reassessment
122156901 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-09-12 | 2024-10-05 | Level 2 | GO 165 Inspection
122157229 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-09-12 | 2024-10-05 | Level 2 | GO 165 Inspection
122157348 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-09-11 | 2024-10-05 | Level 2 | GO 165 Inspection
122157680 | pole | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-07-23 | 2024-10-05 | Level 2 | GO 165 Inspection
122158044 | other | Non-HFTD | Transmission | 2021-10-02 | 2023-10-02 | Level 3 | F | 2024-01-04 | 2026-10-02 | Level 3 | Standards change
122158081 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-11-05 | 2022-10-06 | Level 2 | Field Safety Reassessment
122158140 | anchor/guy | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-01-18 | 2026-09-29 | Level 3 | Standards change
122158297 | insulator and brushing | Non-HFTD | Transmission | 2021-10-02 | 2022-10-02 | Level 2 | E | 2024-12-11 | 2024-10-02 | Level 2 | Field Safety Reassessment
122158381 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-12-02 | 2024-10-06 | Level 2 | Field Safety Reassessment
122158418 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122158496 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-11-28 | 2026-10-06 | Level 3 | Standards change
122158567 | other | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2023-11-28 | 2026-10-04 | Level 3 | Standards change
122158579 | other | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-02-01 | 2026-09-30 | Level 3 | Standards change
122158620 | insulator and brushing | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-12-31 | 2024-09-30 | Level 2 | Field Safety Reassessment
122158660 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-10-09 | 2024-10-04 | Level 2 | GO 165 Inspection
122158751 | other | Non-HFTD | Transmission | 2021-09-30 | 2023-09-30 | Level 3 | F | 2023-12-28 | 2026-09-30 | Level 3 | Standards change
122158760 | other | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-29 | 2026-09-29 | Level 3 | Standards change
122158809 | other | Non-HFTD | Transmission | 2021-10-02 | 2022-10-02 | Level 2 | E | 2024-10-23 | 2026-10-02 | Level 3 | GO 165 Inspection
122158924 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2023-12-22 | 2026-09-29 | Level 3 | Standards change
122159750 | pole | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-10-16 | 2024-10-07 | Level 2 | Field Safety Reassessment
122160329 | anchor/guy | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-01-03 | 2026-10-07 | Level 3 | Standards change
122160392 | anchor/guy | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2023-12-12 | 2026-10-07 | Level 3 | Standards change
122160723 | insulator and brushing | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2023-12-04 | 2026-09-29 | Level 3 | Standards change
122161490 | other | Non-HFTD | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2023-12-18 | 2026-10-07 | Level 3 | Standards change
122163131 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-01-10 | 2026-10-06 | Level 3 | Standards change
122163282 | insulator and brushing | Non-HFTD | Transmission | 2021-09-28 | 2022-09-28 | Level 2 | E | 2024-08-20 | 2024-09-28 | Level 2 | GO 165 Inspection
122163393 | other | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-01-30 | 2024-10-07 | Level 2 | Standards change
122163558 | other | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-01-30 | 2024-10-07 | Level 2 | Standards change
122163570 | pole | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-12-30 | 2024-10-07 | Level 2 | Field Safety Reassessment
122163670 | insulator and brushing | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-10-11 | 2024-10-07 | Level 2 | GO 165 Inspection
122164154 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-03-15 | 2022-10-01 | Level 2 | Standards change
122164169 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-04-06 | 2026-10-04 | Level 3 | Standards change
122164174 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-08-20 | 2024-10-05 | Level 2 | GO 165 Inspection
122164220 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-04-06 | 2026-10-04 | Level 3 | Standards change
122164237 | other | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2023-12-22 | 2026-10-04 | Level 3 | Standards change
122164285 | insulator and brushing | Non-HFTD | Transmission | 2021-10-05 | 2024-10-05 | Level 2 | E | 2022-08-05 | 2024-10-05 | Level 2 | Field Safety Reassessment
122164381 | insulator and brushing | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-11-23 | 2024-10-07 | Level 2 | Field Safety Reassessment
122164382 | anchor/guy | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-01-12 | 2026-10-07 | Level 3 | Standards change
122164396 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2023-02-17 | 2024-10-04 | Level 2 | Standards change
122164405 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2023-12-05 | 2026-10-04 | Level 3 | Standards change
122164433 | insulator and brushing | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-10-03 | 2024-10-07 | Level 2 | GO 165 Inspection
122164459 | pole | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-12-16 | 2024-10-04 | Level 2 | Field Safety Reassessment
122164476 | pole | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2022-12-20 | 2024-10-07 | Level 2 | Standards change
122164524 | insulator and brushing | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-11-05 | 2024-10-05 | Level 2 | GO 165 Inspection
122164530 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-09-26 | 2022-10-06 | Level 2 | GO 165 Inspection
122164552 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-01-16 | 2026-10-04 | Level 3 | Standards change
122165816 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-09-30 | 2026-10-06 | Level 3 | GO 165 Inspection
122165827 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122165828 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-04-06 | 2026-10-05 | Level 3 | Standards change
122165837 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2023-12-21 | 2026-10-05 | Level 3 | Standards change
122165884 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122165893 | pole | Non-HFTD | Transmission | 2021-10-05 | 2024-10-05 | Level 2 | E | 2024-09-23 | 2022-01-05 | Level 2 | Field Safety Reassessment
122166009 | other | Non-HFTD | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2024-01-25 | 2026-10-07 | Level 3 | Standards change
122166113 | other | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2023-02-14 | 2026-10-05 | Level 3 | Standards change
122166221 | insulator and brushing | Non-HFTD | Transmission | 2021-10-01 | 2024-10-01 | Level 2 | E | 2024-08-19 | 2022-10-01 | Level 2 | GO 165 Inspection
122166257 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-08-19 | 2024-10-01 | Level 2 | GO 165 Inspection
122166322 | other | HFTD Tier 2 | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2024-04-06 | 2026-10-07 | Level 3 | Standards change
122166362 | pole | Non-HFTD | Transmission | 2021-09-29 | 2022-09-29 | Level 2 | E | 2024-11-01 | 2024-09-29 | Level 2 | GO 165 Inspection
122166444 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-02-07 | 2026-10-08 | Level 3 | Standards change
122166726 | other | Non-HFTD | Transmission | 2021-10-01 | 2023-10-01 | Level 3 | F | 2023-12-21 | 2026-10-01 | Level 3 | Standards change
122166930 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-01-04 | 2026-10-05 | Level 3 | Standards change
122166992 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-12-01 | 2024-10-08 | Level 2 | Field Safety Reassessment
122167056 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122167096 | conductor | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-11-01 | 2022-10-06 | Level 2 | GO 165 Inspection
122167221 | other | Non-HFTD | Transmission | 2021-10-01 | 2022-10-01 | Level 2 | E | 2024-11-26 | 2024-10-01 | Level 2 | Field Safety Reassessment
122167285 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-09-23 | 2026-10-06 | Level 3 | GO 165 Inspection
122167308 | other | Non-HFTD | Transmission | 2021-10-02 | 2023-10-02 | Level 3 | F | 2023-12-29 | 2026-10-02 | Level 3 | Standards change
122167391 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2023-12-22 | 2026-10-06 | Level 3 | Standards change
122167554 | pole | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-09-17 | 2024-10-08 | Level 2 | Field Safety Reassessment
122167770 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-09-24 | 2026-10-08 | Level 3 | GO 165 Inspection
122167772 | anchor/guy | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-02-25 | 2026-10-08 | Level 3 | GO 165 Inspection
122167775 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2023-12-22 | 2026-10-06 | Level 3 | Standards change
122167810 | pole | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-09-28 | 2024-10-06 | Level 2 | GO 165 Inspection
122167857 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-09-18 | 2026-10-08 | Level 3 | GO 165 Inspection
122167950 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-11-13 | 2024-10-04 | Level 2 | GO 165 Inspection
122167958 | insulator and brushing | Non-HFTD | Transmission | 2021-10-04 | 2022-10-04 | Level 2 | E | 2024-11-13 | 2024-10-04 | Level 2 | GO 165 Inspection
122168009 | insulator and brushing | Non-HFTD | Transmission | 2021-09-30 | 2022-09-30 | Level 2 | E | 2024-08-20 | 2026-09-30 | Level 3 | GO 165 Inspection
122168067 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-04-06 | 2026-10-05 | Level 3 | Standards change
122168068 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-01-11 | 2026-10-06 | Level 3 | Standards change
122168081 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-12-08 | 2026-10-08 | Level 3 | Standards change
122168366 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-02-15 | 2024-10-06 | Level 2 | Standards change
122168569 | anchor/guy | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-01-16 | 2026-10-08 | Level 3 | Standards change
122169106 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-12-29 | 2026-10-08 | Level 3 | Standards change
122169473 | pole | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-09-17 | 2024-10-08 | Level 2 | Field Safety Reassessment
122169588 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-12-08 | 2024-10-08 | Level 2 | Standards change
122169769 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122170127 | anchor/guy | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-02-25 | 2026-10-08 | Level 3 | GO 165 Inspection
122171891 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-03-13 | 2024-10-08 | Level 2 | Standards change
122172145 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2023-12-08 | 2026-10-09 | Level 3 | Standards change
122183424 | other | Non-HFTD | Transmission | 2021-10-10 | 2023-10-10 | Level 3 | F | 2023-12-08 | 2026-10-10 | Level 3 | Standards change
122183523 | other | Non-HFTD | Transmission | 2021-10-10 | 2023-10-10 | Level 3 | F | 2024-06-21 | 2026-10-10 | Level 3 | GO 165 Inspection
122184100 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-02-05 | 2024-10-08 | Level 2 | Standards change
122186014 | pole | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-07-31 | 2022-10-06 | Level 2 | Field Safety Reassessment
122186110 | other | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-02-14 | 2026-10-06 | Level 3 | Standards change
122186312 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-12-13 | 2026-10-06 | Level 3 | Standards change
122186496 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2023-12-29 | 2026-10-09 | Level 3 | Standards change
122186747 | anchor/guy | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-10-07 | 2024-10-11 | Level 2 | GO 165 Inspection
122186824 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-01-18 | 2024-10-09 | Level 2 | Standards change
122187332 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-12-28 | 2026-10-08 | Level 3 | Standards change
122187420 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-08-26 | 2026-10-05 | Level 3 | GO 165 Inspection
122187542 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-10-03 | 2026-10-06 | Level 3 | GO 165 Inspection
122187798 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-11-13 | 2026-10-08 | Level 3 | GO 165 Inspection
122187799 | pole | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-11-13 | 2026-10-08 | Level 3 | GO 165 Inspection
122188089 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-08-27 | 2026-10-08 | Level 3 | GO 165 Inspection
122188705 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-09-24 | 2024-10-09 | Level 2 | GO 165 Inspection
122188709 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-02-01 | 2024-10-08 | Level 2 | Standards change
122189134 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-04-06 | 2026-10-12 | Level 3 | Standards change
122189344 | other | Non-HFTD | Transmission | 2021-10-09 | 2024-10-09 | Level 2 | E | 2024-06-17 | 2022-10-09 | Level 2 | Field Safety Reassessment
122191985 | pole | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2024-12-18 | 2024-10-12 | Level 2 | Field Safety Reassessment
122192484 | pole | Non-HFTD | Transmission | 2021-10-05 | 2022-10-05 | Level 2 | E | 2024-11-25 | 2024-10-05 | Level 2 | Field Safety Reassessment
122192496 | pole | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-10-11 | 2024-10-07 | Level 2 | GO 165 Inspection
122192541 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122192613 | other | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-08-15 | 2022-10-06 | Level 2 | GO 165 Inspection
122192615 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-08-15 | 2022-10-06 | Level 2 | GO 165 Inspection
122192860 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-01-09 | 2026-10-12 | Level 3 | Standards change
122192924 | other | Non-HFTD | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2024-09-24 | 2026-10-07 | Level 3 | GO 165 Inspection
122192934 | other | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-02-14 | 2024-10-06 | Level 2 | Standards change
122193018 | insulator and brushing | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-01-23 | 2024-10-06 | Level 2 | Standards change
122193057 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122193092 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-11-19 | 2024-10-08 | Level 2 | Field Safety Reassessment
122193108 | insulator and brushing | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-02-05 | 2024-10-07 | Level 2 | Standards change
122193140 | pole | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2023-02-16 | 2024-10-10 | Level 2 | Standards change
122193156 | other | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-08-20 | 2026-10-11 | Level 3 | GO 165 Inspection
122193171 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2023-12-28 | 2026-10-11 | Level 3 | Standards change
122193228 | pole | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-09-28 | 2024-10-11 | Level 2 | GO 165 Inspection
122193229 | other | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-09-28 | 2022-10-11 | Level 2 | GO 165 Inspection
122193323 | insulator and brushing | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-08-09 | 2024-10-11 | Level 2 | GO 165 Inspection
122193926 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2023-12-28 | 2026-10-11 | Level 3 | Standards change
122194306 | insulator and brushing | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-12-10 | 2024-10-13 | Level 2 | Field Safety Reassessment
122194800 | pole | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-02-08 | 2024-10-13 | Level 2 | Field Safety Reassessment
122194892 | anchor/guy | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-12-29 | 2026-10-13 | Level 3 | Standards change
122195161 | anchor/guy | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-12-29 | 2026-10-13 | Level 3 | Standards change
122195529 | other | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-01-27 | 2026-10-13 | Level 3 | Standards change
122195539 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-01-02 | 2026-10-11 | Level 3 | Standards change
122196717 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-01-10 | 2026-10-06 | Level 3 | Standards change
122196922 | other | Non-HFTD | Transmission | 2021-10-05 | 2023-10-05 | Level 3 | F | 2024-04-06 | 2026-10-05 | Level 3 | Standards change
122198332 | other | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-10-29 | 2026-10-06 | Level 3 | GO 165 Inspection
122199563 | other | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-01-31 | 2026-10-08 | Level 3 | Standards change
122199840 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-04-06 | 2026-10-08 | Level 3 | Standards change
122199849 | other | Non-HFTD | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2023-12-01 | 2026-10-07 | Level 3 | Standards change
122199918 | insulator and brushing | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2024-08-20 | 2024-10-12 | Level 2 | GO 165 Inspection
122199946 | other | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-08-30 | 2024-10-08 | Level 2 | Field Safety Reassessment
122199970 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-04-06 | 2026-10-08 | Level 3 | Standards change
122199993 | insulator and brushing | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2022-12-16 | 2022-10-08 | Level 2 | Standards change
122200122 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-12-21 | 2026-10-08 | Level 3 | Standards change
122200141 | insulator and brushing | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-09-13 | 2024-10-11 | Level 2 | GO 165 Inspection
122200733 | other | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2023-02-17 | 2026-10-12 | Level 3 | Standards change
122200765 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-02-03 | 2026-10-08 | Level 3 | Standards change
122201366 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-12-06 | 2026-10-08 | Level 3 | Standards change
122205690 | pole | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-09-01 | 2026-10-08 | Level 3 | Standards change
122205723 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2023-01-13 | 2024-10-06 | Level 2 | Standards change
122205739 | other | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2024-12-30 | 2026-10-14 | Level 3 | Field Safety Reassessment
122206839 | other | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2023-03-02 | 2024-10-14 | Level 2 | Standards change
122207084 | pole | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2023-03-24 | 2024-10-14 | Level 2 | Standards change
122208992 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122209084 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2023-01-23 | 2024-10-09 | Level 2 | Standards change
122209470 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2024-04-06 | 2026-10-08 | Level 3 | Standards change
122209837 | other | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-11-20 | 2026-10-08 | Level 3 | Standards change
122209860 | pole | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-11-24 | 2024-10-09 | Level 2 | Field Safety Reassessment
122210156 | other | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-11-20 | 2026-10-13 | Level 3 | Standards change
122211517 | insulator and brushing | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2023-11-20 | 2024-10-11 | Level 2 | Standards change
122212089 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-02 | 2026-10-13 | Level 3 | Standards change
122212247 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-11 | 2026-10-13 | Level 3 | Standards change
122212669 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-10-08 | 2026-10-13 | Level 3 | GO 165 Inspection
122213142 | switch | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2023-11-20 | 2024-10-12 | Level 2 | Standards change
122213350 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-08-27 | 2026-10-13 | Level 3 | GO 165 Inspection
122213758 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2024-04-06 | 2026-10-15 | Level 3 | Standards change
122213807 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-02 | 2026-10-13 | Level 3 | Standards change
122213863 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-09-24 | 2024-10-09 | Level 2 | GO 165 Inspection
122214956 | other | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-08-28 | 2024-10-15 | Level 2 | GO 165 Inspection
122214964 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2024-04-06 | 2026-10-15 | Level 3 | Standards change
122215149 | pole | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-12-08 | 2024-10-15 | Level 2 | Field Safety Reassessment
122215799 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2023-12-29 | 2026-10-13 | Level 3 | Standards change
122215909 | pole | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-12-10 | 2024-10-07 | Level 2 | Field Safety Reassessment
122216051 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2022-12-21 | 2026-10-16 | Level 3 | Standards change
122216181 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2024-01-31 | 2026-10-09 | Level 3 | Standards change
122216295 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-04-06 | 2026-10-16 | Level 3 | Standards change
122216308 | insulator and brushing | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2023-11-20 | 2026-10-16 | Level 3 | Standards change
122216382 | pole | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2023-01-31 | 2026-10-09 | Level 3 | Standards change
122216396 | pole | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-12-09 | 2024-10-16 | Level 2 | Field Safety Reassessment
122216422 | other | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2023-11-20 | 2026-10-08 | Level 3 | Standards change
122216533 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2023-02-14 | 2026-10-15 | Level 3 | Standards change
122216762 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-08-30 | 2026-10-16 | Level 3 | GO 165 Inspection
122216780 | anchor/guy | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-02-01 | 2026-10-16 | Level 3 | Standards change
122216798 | pole | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-10-30 | 2024-10-15 | Level 2 | GO 165 Inspection
122217134 | anchor/guy | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2023-11-20 | 2026-10-16 | Level 3 | Standards change
122217284 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-01-18 | 2026-10-11 | Level 3 | Standards change
122217489 | insulator and brushing | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-10-16 | 2024-10-16 | Level 2 | GO 165 Inspection
122217548 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-10-31 | 2026-10-16 | Level 3 | GO 165 Inspection
122219499 | other | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-01-10 | 2026-10-18 | Level 3 | Standards change
122219733 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2023-12-11 | 2026-10-06 | Level 3 | Standards change
122219786 | pole | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-07-19 | 2024-10-18 | Level 2 | GO 165 Inspection
122220560 | pole | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2023-10-31 | 2024-10-18 | Level 2 | Standards change
122221407 | pole | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-11-15 | 2026-10-18 | Level 3 | GO 165 Inspection
122221480 | pole | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-11-15 | 2026-10-18 | Level 3 | GO 165 Inspection
122221630 | pole | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-11-15 | 2026-10-18 | Level 3 | GO 165 Inspection
122221634 | pole | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-11-15 | 2026-10-18 | Level 3 | GO 165 Inspection
122222907 | pole | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-11-14 | 2024-10-11 | Level 2 | Field Safety Reassessment
122222968 | pole | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-07-09 | 2024-10-18 | Level 2 | GO 165 Inspection
122224010 | insulator and brushing | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2023-01-31 | 2024-10-14 | Level 2 | Standards change
122224844 | other | Non-HFTD | Transmission | 2021-10-16 | 2024-10-16 | Level 2 | E | 2024-12-02 | 2026-10-16 | Level 3 | Field Safety Reassessment
122224846 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2023-02-15 | 2026-10-15 | Level 3 | Standards change
122225163 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-10-25 | 2026-10-16 | Level 3 | GO 165 Inspection
122225254 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-11-15 | 2026-10-19 | Level 3 | GO 165 Inspection
122225370 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-11-14 | 2026-10-19 | Level 3 | GO 165 Inspection
122225583 | pole | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-09-30 | 2024-10-19 | Level 2 | GO 165 Inspection
122225672 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-11-14 | 2026-10-19 | Level 3 | GO 165 Inspection
122225807 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-11-14 | 2026-10-19 | Level 3 | GO 165 Inspection
122226031 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-11-14 | 2026-10-19 | Level 3 | GO 165 Inspection
122226256 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-11-09 | 2026-10-19 | Level 3 | GO 165 Inspection
122229025 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-10-30 | 2024-10-19 | Level 2 | GO 165 Inspection
122229474 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-04-06 | 2026-10-11 | Level 3 | Standards change
122229525 | other | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-12-13 | 2024-10-11 | Level 2 | Field Safety Reassessment
122229552 | insulator and brushing | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-10-31 | 2024-10-18 | Level 2 | GO 165 Inspection
122229624 | insulator and brushing | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2024-01-04 | 2024-10-12 | Level 2 | Standards change
122229627 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-04-06 | 2026-10-11 | Level 3 | Standards change
122229673 | other | Non-HFTD | Transmission | 2021-10-18 | 2026-10-18 | Level 3 | F |  | 2026-10-18 | Level 3
122229731 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2023-12-22 | 2026-10-11 | Level 3 | Standards change
122229763 | other | Non-HFTD | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2024-08-28 | 2026-10-07 | Level 3 | GO 165 Inspection
122229794 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-04-06 | 2026-10-13 | Level 3 | Standards change
122229880 | other | Non-HFTD | Transmission | 2021-10-08 | 2022-10-08 | Level 2 | E | 2024-10-28 | 2024-10-08 | Level 2 | GO 165 Inspection
122229939 | insulator and brushing | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-12-07 | 2024-10-15 | Level 2 | Field Safety Reassessment
122229950 | anchor/guy | Non-HFTD | Transmission | 2021-10-06 | 2022-10-06 | Level 2 | E | 2024-01-10 | 2026-10-06 | Level 3 | Standards change
122229995 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2023-12-06 | 2026-10-13 | Level 3 | Standards change
122230011 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2023-02-17 | 2026-10-15 | Level 3 | Standards change
122230182 | other | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2023-02-15 | 2024-10-11 | Level 2 | Standards change
122230201 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-12-31 | 2026-10-11 | Level 3 | Field Safety Reassessment
122230207 | insulator and brushing | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2024-10-10 | 2024-10-07 | Level 2 | GO 165 Inspection
122230230 | other | Non-HFTD | Transmission | 2021-10-13 | 2026-10-13 | Level 3 | F | 2024-09-03 | 2024-10-13 | Level 2 | GO 165 Inspection
122230236 | other | Non-HFTD | Transmission | 2021-10-07 | 2023-10-07 | Level 3 | F | 2024-01-11 | 2026-10-07 | Level 3 | Standards change
122230244 | insulator and brushing | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-11-24 | 2024-10-18 | Level 2 | Field Safety Reassessment
122230247 | pole | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-10-10 | 2024-10-19 | Level 2 | Field Safety Reassessment
122230433 | pole | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2023-02-16 | 2024-10-12 | Level 2 | Standards change
122230466 | pole | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-11-25 | 2024-10-11 | Level 2 | Field Safety Reassessment
122230479 | pole | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2024-12-23 | 2024-10-14 | Level 2 | Field Safety Reassessment
122230581 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2024-09-13 | 2026-10-09 | Level 3 | GO 165 Inspection
122231121 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-09-28 | 2022-10-19 | Level 2 | GO 165 Inspection
122232123 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-04-06 | 2026-10-20 | Level 3 | Standards change
122233221 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-04-06 | 2026-10-19 | Level 3 | Standards change
122233492 | other | Non-HFTD | Transmission | 2021-09-29 | 2023-09-29 | Level 3 | F | 2024-01-16 | 2026-09-29 | Level 3 | Standards change
122233631 | pole | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2023-06-10 | 2024-10-20 | Level 2 | GO 165 Inspection
122234410 | anchor/guy | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-07-04 | 2026-10-20 | Level 3 | GO 165 Inspection
122234686 | insulator and brushing | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-10-30 | 2024-10-18 | Level 2 | GO 165 Inspection
122235013 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-04-06 | 2026-10-20 | Level 3 | Standards change
122235237 | pole | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-12-20 | 2022-10-20 | Level 2 | Field Safety Reassessment
122235278 | anchor/guy | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-06-18 | 2026-10-20 | Level 3 | GO 165 Inspection
122235581 | other | Non-HFTD | Transmission | 2021-10-19 | 2024-10-19 | Level 2 | E | 2024-07-18 | 2026-10-19 | Level 3 | GO 165 Inspection
122235695 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-03-04 | 2026-10-09 | Level 3 | GO 165 Inspection
122235723 | other | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-01-12 | 2024-10-13 | Level 2 | Standards change
122235767 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-01-08 | 2026-10-12 | Level 3 | Standards change
122235796 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-01-02 | 2026-10-12 | Level 3 | Standards change
122235879 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-10-08 | 2026-10-13 | Level 3 | GO 165 Inspection
122235883 | other | Non-HFTD | Transmission | 2021-10-07 | 2022-10-07 | Level 2 | E | 2023-02-08 | 2026-10-07 | Level 3 | Standards change
122235895 | insulator and brushing | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-11-06 | 2024-10-13 | Level 2 | Field Safety Reassessment
122235898 | pole | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2024-12-10 | 2024-10-12 | Level 2 | Field Safety Reassessment
122235988 | pole | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-08-31 | 2026-10-20 | Level 3 | GO 165 Inspection
122235997 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2024-08-29 | 2026-10-09 | Level 3 | GO 165 Inspection
122236061 | insulator and brushing | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2024-08-06 | 2024-10-12 | Level 2 | Field Safety Reassessment
122236105 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-04-06 | 2026-10-12 | Level 3 | Standards change
122236128 | pole | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-01-19 | 2026-10-08 | Level 3 | Standards change
122236171 | pole | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2023-02-27 | 2026-10-12 | Level 3 | Standards change
122236275 | anchor/guy | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-01-10 | 2026-10-13 | Level 3 | Standards change
122236278 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-01-03 | 2026-10-11 | Level 3 | Standards change
122236286 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-10-29 | 2026-10-13 | Level 3 | GO 165 Inspection
122236364 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122236365 | other | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2023-03-13 | 2026-10-11 | Level 3 | Standards change
122236427 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-01-04 | 2026-10-12 | Level 3 | Standards change
122241281 | pole | Non-HFTD | Transmission | 2021-10-21 | 2022-10-21 | Level 2 | E | 2024-12-10 | 2024-10-21 | Level 2 | Field Safety Reassessment
122241422 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2024-10-17 | 2026-10-15 | Level 3 | GO 165 Inspection
122241661 | pole | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-11-14 | 2024-10-11 | Level 2 | Field Safety Reassessment
122242164 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-09-18 | 2026-10-19 | Level 3 | GO 165 Inspection
122242220 | pole | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-12-02 | 2024-10-20 | Level 2 | Field Safety Reassessment
122242237 | other | Non-HFTD | Transmission | 2021-10-12 | 2024-10-12 | Level 2 | E | 2024-10-31 | 2026-10-12 | Level 3 | Field Safety Reassessment
122242318 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2023-01-27 | 2026-10-19 | Level 3 | Standards change
122242423 | other | Non-HFTD | Transmission | 2021-10-04 | 2023-10-04 | Level 3 | F | 2024-08-20 | 2026-10-04 | Level 3 | GO 165 Inspection
122242462 | pole | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-12-18 | 2026-10-13 | Level 3 | Standards change
122242499 | anchor/guy | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2023-01-12 | 2026-10-14 | Level 3 | Standards change
122242538 | pole | Non-HFTD | Transmission | 2021-10-21 | 2022-10-21 | Level 2 | E | 2024-12-04 | 2024-10-21 | Level 2 | Field Safety Reassessment
122242564 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2023-12-27 | 2026-10-12 | Level 3 | Standards change
122242650 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2023-12-11 | 2026-10-09 | Level 3 | Standards change
122242674 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-02 | 2026-10-13 | Level 3 | Standards change
122243781 | other | Non-HFTD | Transmission | 2021-10-06 | 2023-10-06 | Level 3 | F | 2024-04-06 | 2026-10-06 | Level 3 | Standards change
122243836 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-03 | 2026-10-13 | Level 3 | Standards change
122243855 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-04-06 | 2026-10-11 | Level 3 | Standards change
122243887 | insulator and brushing | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2024-12-10 | 2024-10-14 | Level 2 | Field Safety Reassessment
122243888 | anchor/guy | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2024-01-30 | 2024-10-14 | Level 2 | Standards change
122243899 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-01-02 | 2026-10-22 | Level 3 | Standards change
122243903 | other | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-01-24 | 2024-10-11 | Level 2 | Standards change
122243905 | other | Non-HFTD | Transmission | 2021-10-09 | 2023-10-09 | Level 3 | F | 2024-01-04 | 2026-10-09 | Level 3 | Standards change
122244051 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-04-06 | 2026-10-11 | Level 3 | Standards change
122244098 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-10-29 | 2026-10-13 | Level 3 | GO 165 Inspection
122244154 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-01-18 | 2024-10-09 | Level 2 | Standards change
122244212 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-04-06 | 2026-10-13 | Level 3 | Standards change
122244335 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2023-12-22 | 2026-10-11 | Level 3 | Standards change
122244406 | other | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-09-13 | 2026-10-13 | Level 3 | GO 165 Inspection
122244409 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-09-13 | 2026-10-13 | Level 3 | GO 165 Inspection
122244414 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-02 | 2026-10-16 | Level 3 | Standards change
122244424 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-02-02 | 2026-10-20 | Level 3 | Standards change
122244579 | anchor/guy | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2023-01-06 | 2026-10-09 | Level 3 | Standards change
122244755 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-03 | 2026-10-13 | Level 3 | Standards change
122244948 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2023-12-22 | 2026-10-11 | Level 3 | Standards change
122245125 | insulator and brushing | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2024-10-28 | 2022-10-09 | Level 2 | GO 165 Inspection
122245311 | pole | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-08-28 | 2024-10-19 | Level 2 | GO 165 Inspection
122245312 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-08-28 | 2026-10-19 | Level 3 | GO 165 Inspection
122245360 | pole | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2023-02-15 | 2024-10-14 | Level 2 | Standards change
122245365 | pole | Non-HFTD | Transmission | 2021-10-09 | 2022-10-09 | Level 2 | E | 2023-01-23 | 2024-10-09 | Level 2 | Standards change
122245445 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2023-12-28 | 2026-10-14 | Level 3 | Standards change
122245490 | other | Non-HFTD | Transmission | 2021-10-12 | 2022-10-12 | Level 2 | E | 2023-01-23 | 2026-10-12 | Level 3 | Standards change
122245492 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2023-02-14 | 2026-10-13 | Level 3 | Standards change
122245496 | pole | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-12-30 | 2024-10-13 | Level 2 | Field Safety Reassessment
122245551 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2023-12-18 | 2026-10-15 | Level 3 | Standards change
122245598 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-04-06 | 2026-10-13 | Level 3 | Standards change
122245878 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2024-10-19 | Level 2 | E | 2024-08-28 | 2022-10-19 | Level 2 | GO 165 Inspection
122245903 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-08-28 | 2026-10-19 | Level 3 | GO 165 Inspection
122245931 | other | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2023-02-27 | 2026-10-22 | Level 3 | Standards change
122246098 | other | Non-HFTD | Transmission | 2021-10-08 | 2023-10-08 | Level 3 | F | 2023-12-28 | 2026-10-08 | Level 3 | Standards change
122246450 | anchor/guy | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2023-11-07 | 2026-10-22 | Level 3 | Standards change
122246855 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-01-09 | 2026-10-22 | Level 3 | Standards change
122246919 | pole | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-10-23 | 2026-10-22 | Level 3 | GO 165 Inspection
122247400 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-01-11 | 2026-10-22 | Level 3 | Standards change
122247621 | anchor/guy | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2023-12-06 | 2026-10-22 | Level 3 | Standards change
122249443 | pole | Non-HFTD | Transmission | 2021-10-23 | 2022-10-23 | Level 2 | E | 2024-09-20 | 2024-10-23 | Level 2 | Field Safety Reassessment
122250224 | other | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-06-27 | 2026-10-15 | Level 3 | GO 165 Inspection
122250484 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-01-02 | 2026-10-22 | Level 3 | Standards change
122250723 | other | Non-HFTD | Transmission | 2021-10-12 | 2026-10-12 | Level 3 | F |  | 2026-10-12 | Level 3
122250837 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-12-27 | 2024-10-22 | Level 2 | Field Safety Reassessment
122250951 | pole | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2022-12-27 | 2024-10-14 | Level 2 | Standards change
122250971 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-02-05 | 2024-10-22 | Level 2 | Standards change
122251039 | pole | Non-HFTD | Transmission | 2021-10-11 | 2022-10-11 | Level 2 | E | 2024-12-11 | 2024-10-11 | Level 2 | Field Safety Reassessment
122251116 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-16 | 2026-10-13 | Level 3 | Standards change
122251155 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-02-01 | 2026-10-13 | Level 3 | Standards change
122251317 | other | Non-HFTD | Transmission | 2021-10-11 | 2023-10-11 | Level 3 | F | 2024-09-30 | 2026-10-11 | Level 3 | GO 165 Inspection
122251331 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-02-02 | 2026-10-12 | Level 3 | Standards change
122251336 | other | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-02-14 | 2024-10-13 | Level 2 | Standards change
122251338 | pole | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-10-28 | 2024-10-13 | Level 2 | GO 165 Inspection
122251381 | other | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2023-12-29 | 2026-10-15 | Level 3 | Standards change
122251410 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-01-11 | 2026-10-12 | Level 3 | Standards change
122257995 | anchor/guy | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2024-01-10 | 2026-10-14 | Level 3 | Standards change
122258741 | pole | Non-HFTD | Transmission | 2021-10-26 | 2023-10-26 | Level 3 | F | 2024-08-27 | 2026-10-26 | Level 3 | GO 165 Inspection
122260404 | insulator and brushing | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-11-23 | 2024-10-18 | Level 2 | Field Safety Reassessment
122260583 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2023-12-28 | 2026-10-13 | Level 3 | Standards change
122260645 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2023-06-15 | 2026-10-12 | Level 3 | Standards change
122260666 | insulator and brushing | Non-HFTD | Transmission | 2021-10-15 | 2024-10-15 | Level 2 | E | 2024-10-23 | 2022-10-15 | Level 2 | GO 165 Inspection
122260881 | other | Non-HFTD | Transmission | 2021-10-21 | 2023-10-21 | Level 3 | F | 2024-01-02 | 2026-10-21 | Level 3 | Standards change
122260951 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-01-04 | 2026-10-14 | Level 3 | Standards change
122260959 | other | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2023-12-12 | 2026-10-18 | Level 3 | Standards change
122261003 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-03 | 2026-10-13 | Level 3 | Standards change
122261039 | other | Non-HFTD | Transmission | 2021-10-12 | 2023-10-12 | Level 3 | F | 2024-10-29 | 2026-10-12 | Level 3 | GO 165 Inspection
122261042 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-08 | 2026-10-13 | Level 3 | Standards change
122261181 | insulator and brushing | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-12-31 | 2024-10-20 | Level 2 | Field Safety Reassessment
122261203 | pole | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2024-12-06 | 2022-10-13 | Level 2 | Field Safety Reassessment
122261233 | other | Non-HFTD | Transmission | 2021-10-13 | 2022-10-13 | Level 2 | E | 2023-02-03 | 2026-10-13 | Level 3 | Standards change
122261240 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2023-12-26 | 2026-10-13 | Level 3 | Standards change
122261301 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-04 | 2026-10-16 | Level 3 | Standards change
122261317 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122261331 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-09-28 | 2026-10-13 | Level 3 | GO 165 Inspection
122262288 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-10-24 | 2026-10-27 | Level 3 | GO 165 Inspection
122262520 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-10-23 | 2026-10-27 | Level 3 | GO 165 Inspection
122263089 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-04-06 | 2026-10-19 | Level 3 | Standards change
122263662 | other | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-04-06 | 2026-10-13 | Level 3 | Standards change
122263781 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-08-28 | 2026-10-19 | Level 3 | GO 165 Inspection
122264113 | anchor/guy | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2024-05-08 | 2022-10-26 | Level 2 | GO 165 Inspection
122264496 | anchor/guy | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-01-18 | 2026-10-19 | Level 3 | Standards change
122264879 | conductor | Non-HFTD | Transmission | 2021-10-26 | 2024-10-26 | Level 2 | E | 2024-09-28 | 2022-10-26 | Level 2 | GO 165 Inspection
122265820 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-26 | 2026-10-16 | Level 3 | Standards change
122265863 | other | Non-HFTD | Transmission | 2021-10-21 | 2022-10-21 | Level 2 | E | 2023-12-06 | 2026-10-21 | Level 3 | Standards change
122265895 | conductor | Non-HFTD | Transmission | 2021-10-13 | 2023-10-13 | Level 3 | F | 2024-01-12 | 2026-10-13 | Level 3 | Standards change
122265944 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-10 | 2026-10-16 | Level 3 | Standards change
122266136 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2023-02-13 | 2026-10-27 | Level 3 | Standards change
122266137 | pole | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-12-31 | 2024-10-27 | Level 2 | Field Safety Reassessment
122266159 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-01-19 | 2026-10-22 | Level 3 | Standards change
122266203 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-10 | 2026-10-16 | Level 3 | Standards change
122266217 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2023-12-27 | 2026-10-27 | Level 3 | Standards change
122266264 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-09-28 | 2026-10-16 | Level 3 | GO 165 Inspection
122266380 | conductor | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-08-27 | 2024-10-15 | Level 2 | GO 165 Inspection
122266449 | insulator and brushing | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2024-09-18 | 2024-10-26 | Level 2 | GO 165 Inspection
122267110 | anchor/guy | Non-HFTD | Transmission | 2021-10-23 | 2022-10-23 | Level 2 | E | 2024-09-10 | 2026-10-23 | Level 3 | GO 165 Inspection
122269184 | other | Non-HFTD | Transmission | 2021-10-28 | 2023-10-28 | Level 3 | F | 2024-04-06 | 2026-10-28 | Level 3 | Standards change
122269225 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122269553 | pole | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2024-11-12 | 2024-10-28 | Level 2 | GO 165 Inspection
122269620 | pole | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2024-06-17 | 2024-10-28 | Level 2 | Field Safety Reassessment
122270020 | pole | Non-HFTD | Transmission | 2021-10-28 | 2023-10-28 | Level 3 | F | 2023-02-01 | 2026-10-28 | Level 3 | Standards change
122270241 | other | Non-HFTD | Transmission | 2021-09-22 | 2023-09-22 | Level 3 | F | 2024-04-06 | 2026-09-22 | Level 3 | Standards change
122270435 | pole | Non-HFTD | Transmission | 2021-10-28 | 2023-10-28 | Level 3 | F | 2024-11-08 | 2026-10-28 | Level 3 | GO 165 Inspection
122270767 | insulator and brushing | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-12-01 | 2024-10-15 | Level 2 | Field Safety Reassessment
122270792 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-01-26 | 2026-10-19 | Level 3 | Standards change
122271281 | other | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-08-30 | 2026-10-16 | Level 3 | GO 165 Inspection
122271333 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2024-04-06 | 2026-10-15 | Level 3 | Standards change
122271390 | other | Non-HFTD | Transmission | 2021-10-21 | 2026-10-21 | Level 3 | F |  | 2026-10-21 | Level 3
122271393 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2023-12-06 | 2026-10-16 | Level 3 | Standards change
122271422 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-09-17 | 2026-10-16 | Level 3 | GO 165 Inspection
122271469 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122271522 | other | HFTD Tier 2 | Transmission | 2021-10-28 | 2023-10-28 | Level 3 | F | 2024-04-06 | 2026-10-28 | Level 3 | Standards change
122271569 | other | Non-HFTD | Transmission | 2021-10-15 | 2023-10-15 | Level 3 | F | 2023-12-26 | 2026-10-15 | Level 3 | Standards change
122271702 | insulator and brushing | Non-HFTD | Transmission | 2021-10-21 | 2022-10-21 | Level 2 | E | 2024-02-01 | 2024-10-21 | Level 2 | Standards change
122271703 | insulator and brushing | Non-HFTD | Transmission | 2021-10-21 | 2022-10-21 | Level 2 | E | 2023-12-07 | 2024-10-21 | Level 2 | Standards change
122271756 | other | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2023-02-16 | 2026-10-18 | Level 3 | Standards change
122271817 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-04 | 2026-10-16 | Level 3 | Standards change
122271818 | insulator and brushing | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2022-12-12 | 2026-10-15 | Level 3 | Standards change
122271880 | other | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2023-01-30 | 2026-10-18 | Level 3 | Standards change
122271905 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2023-12-05 | 2026-10-19 | Level 3 | Standards change
122273063 | insulator and brushing | Non-HFTD | Transmission | 2021-10-25 | 2022-10-25 | Level 2 | E | 2024-08-16 | 2024-10-25 | Level 2 | GO 165 Inspection
122273951 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2024-04-06 | 2026-10-29 | Level 3 | Standards change
122274287 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2023-12-27 | 2026-10-27 | Level 3 | Standards change
122274623 | other | Non-HFTD | Transmission | 2021-10-21 | 2024-10-21 | Level 2 | E | 2024-06-17 | 2022-10-21 | Level 2 | Field Safety Reassessment
122274648 | other | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2023-01-31 | 2026-10-18 | Level 3 | Standards change
122274767 | other | Non-HFTD | Transmission | 2021-10-23 | 2023-10-23 | Level 3 | F | 2024-01-02 | 2026-10-23 | Level 3 | Standards change
122274880 | other | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-01-03 | 2026-10-18 | Level 3 | Standards change
122274964 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122275140 | other | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-01-08 | 2026-10-18 | Level 3 | Standards change
122275205 | insulator and brushing | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-02-05 | 2024-10-16 | Level 2 | Standards change
122275297 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-12-09 | 2026-10-16 | Level 3 | GO 165 Inspection
122275431 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2023-09-22 | 2026-10-14 | Level 3 | Standards change
122275487 | other | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-08-30 | 2026-10-18 | Level 3 | GO 165 Inspection
122275594 | anchor/guy | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2023-12-07 | 2026-10-27 | Level 3 | Standards change
122275688 | other | Non-HFTD | Transmission | 2021-10-14 | 2023-10-14 | Level 3 | F | 2024-04-06 | 2026-10-14 | Level 3 | Standards change
122276243 | other | Non-HFTD | Transmission | 2021-10-29 | 2024-10-29 | Level 2 | E | 2024-12-06 | 2022-10-29 | Level 2 | Field Safety Reassessment
122276559 | other | Non-HFTD | Transmission | 2021-10-18 | 2023-10-18 | Level 3 | F | 2024-04-06 | 2026-10-18 | Level 3 | Standards change
122276890 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-12-27 | 2024-10-29 | Level 2 | Field Safety Reassessment
122276895 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-11-30 | 2024-10-29 | Level 2 | GO 165 Inspection
122278121 | anchor/guy | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2023-12-06 | 2026-10-30 | Level 3 | Standards change
122278454 | insulator and brushing | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-12-10 | 2024-10-30 | Level 2 | Field Safety Reassessment
122279056 | pole | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-11-01 | 2026-10-30 | Level 3 | GO 165 Inspection
122279819 | anchor/guy | Non-HFTD | Transmission | 2021-10-31 | 2022-10-31 | Level 2 | E | 2024-11-12 | 2026-10-31 | Level 3 | GO 165 Inspection
122280241 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2023-03-06 | 2024-10-29 | Level 2 | Standards change
122280973 | pole | Non-HFTD | Transmission | 2021-11-01 | 2023-11-01 | Level 3 | F | 2023-02-02 | 2026-11-01 | Level 3 | Standards change
122281811 | other | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2024-08-16 | 2024-10-28 | Level 2 | GO 165 Inspection
122282406 | pole | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-10-16 | 2024-11-01 | Level 2 | GO 165 Inspection
122283620 | other | Non-HFTD | Transmission | 2021-11-01 | 2023-11-01 | Level 3 | F | 2024-01-10 | 2026-11-01 | Level 3 | Standards change
122283703 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-10-30 | 2026-10-29 | Level 3 | GO 165 Inspection
122283860 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-09-10 | 2026-10-22 | Level 3 | GO 165 Inspection
122283866 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2023-01-25 | 2026-10-22 | Level 3 | Standards change
122284304 | pole | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-12-09 | 2024-10-30 | Level 2 | Field Safety Reassessment
122284387 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2023-12-29 | 2026-10-29 | Level 3 | Standards change
122284519 | anchor/guy | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-01-16 | 2026-10-29 | Level 3 | Standards change
122284615 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2024-01-05 | 2026-10-29 | Level 3 | Standards change
122284622 | pole | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-10-30 | 2024-10-30 | Level 2 | GO 165 Inspection
122284715 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-10-23 | 2026-10-22 | Level 3 | GO 165 Inspection
122284743 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2023-12-18 | 2026-10-29 | Level 3 | Standards change
122284887 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2023-12-27 | 2026-10-29 | Level 3 | Standards change
122285045 | other | Non-HFTD | Transmission | 2021-10-16 | 2023-10-16 | Level 3 | F | 2024-01-02 | 2026-10-16 | Level 3 | Standards change
122285080 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-11-19 | 2024-10-19 | Level 2 | GO 165 Inspection
122286511 | other | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-12-23 | 2024-11-02 | Level 2 | Field Safety Reassessment
122286769 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-01-31 | 2024-11-02 | Level 2 | Standards change
122287125 | other | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2023-03-06 | 2024-11-01 | Level 2 | Standards change
122288575 | pole | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2024-12-02 | 2024-10-15 | Level 2 | Field Safety Reassessment
122288868 | other | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-12-13 | 2024-11-02 | Level 2 | Field Safety Reassessment
122289332 | other | Non-HFTD | Transmission | 2021-10-30 | 2023-10-30 | Level 3 | F | 2024-10-04 | 2026-10-30 | Level 3 | GO 165 Inspection
122289753 | insulator and brushing | Non-HFTD | Transmission | 2021-11-01 | 2022-02-01 | Level 2 | E | 2024-06-18 | 2022-02-01 | Level 2 | Field Safety Reassessment
122290015 | other | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-09-26 | 2024-11-01 | Level 2 | GO 165 Inspection
122290442 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-12-20 | 2024-11-02 | Level 2 | Field Safety Reassessment
122290592 | other | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-01-26 | 2024-11-02 | Level 2 | Standards change
122290966 | other | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-12-26 | 2024-10-30 | Level 2 | Field Safety Reassessment
122291494 | other | Non-HFTD | Transmission | 2021-11-01 | 2023-11-01 | Level 3 | F | 2023-12-27 | 2026-11-01 | Level 3 | Standards change
122291644 | pole | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-09-11 | 2024-10-30 | Level 2 | Field Safety Reassessment
122292137 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2024-11-02 | Level 2 | GO 165 Inspection
122292138 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2024-11-02 | Level 2 | GO 165 Inspection
122292258 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2023-01-25 | 2026-10-19 | Level 3 | Standards change
122292423 | other | Non-HFTD | Transmission | 2021-10-26 | 2023-10-26 | Level 3 | F | 2023-01-11 | 2026-10-26 | Level 3 | Standards change
122292429 | other | Non-HFTD | Transmission | 2021-10-21 | 2023-10-21 | Level 3 | F | 2024-04-06 | 2026-10-21 | Level 3 | Standards change
122292467 | pole | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-11-27 | 2024-11-02 | Level 2 | Field Safety Reassessment
122292525 | crossarm | Non-HFTD | Transmission | 2021-10-14 | 2022-10-14 | Level 2 | E | 2024-08-21 | 2024-10-14 | Level 2 | GO 165 Inspection
122292649 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-09-30 | 2024-10-22 | Level 2 | Field Safety Reassessment
122292651 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-11-21 | 2024-10-19 | Level 2 | GO 165 Inspection
122292653 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-11-21 | 2024-10-19 | Level 2 | GO 165 Inspection
122292722 | insulator and brushing | Non-HFTD | Transmission | 2021-10-21 | 2022-10-21 | Level 2 | E | 2023-12-13 | 2024-10-21 | Level 2 | Standards change
122292800 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2023-12-18 | 2026-10-22 | Level 3 | Standards change
122292817 | insulator and brushing | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2023-01-26 | 2024-10-28 | Level 2 | Standards change
122292859 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-08-29 | 2026-10-19 | Level 3 | GO 165 Inspection
122292874 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2023-07-03 | 2024-10-19 | Level 2 | GO 165 Inspection
122292964 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2024-11-02 | Level 2 | GO 165 Inspection
122293028 | other | Non-HFTD | Transmission | 2021-10-26 | 2023-10-26 | Level 3 | F | 2024-04-06 | 2026-10-26 | Level 3 | Standards change
122293111 | insulator and brushing | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-08-22 | 2024-10-20 | Level 2 | GO 165 Inspection
122293179 | pole | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-12-11 | 2024-10-20 | Level 2 | Field Safety Reassessment
122293198 | insulator and brushing | Non-HFTD | Transmission | 2021-10-18 | 2022-10-18 | Level 2 | E | 2024-09-26 | 2024-10-18 | Level 2 | GO 165 Inspection
122293235 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-08-20 | 2026-10-19 | Level 3 | GO 165 Inspection
122307380 | pole | Non-HFTD | Transmission | 2021-10-23 | 2022-10-23 | Level 2 | E | 2023-12-07 | 2024-10-23 | Level 2 | Standards change
122307548 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-11-12 | 2024-10-22 | Level 2 | GO 165 Inspection
122307604 | other | Non-HFTD | Transmission | 2021-11-03 | 2024-11-03 | Level 2 | E | 2024-11-27 | 2022-11-03 | Level 2 | Field Safety Reassessment
122308128 | other | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-02-02 | 2026-11-03 | Level 3 | Standards change
122308930 | insulator and brushing | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2024-01-31 | 2024-11-03 | Level 2 | Standards change
122309723 | insulator and brushing | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-02-10 | 2022-11-03 | Level 2 | Standards change
122309801 | pole | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2024-08-26 | 2024-11-03 | Level 2 | Field Safety Reassessment
122310105 | other | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2024-05-21 | 2022-11-03 | Level 2 | Field Safety Reassessment
122310254 | other | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-02-06 | 2026-11-03 | Level 3 | Standards change
122310672 | other | Non-HFTD | Transmission | 2021-10-26 | 2023-10-26 | Level 3 | F | 2024-01-08 | 2026-10-26 | Level 3 | Standards change
122311727 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-09-10 | 2026-10-22 | Level 3 | GO 165 Inspection
122311811 | insulator and brushing | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-03-20 | 2024-10-16 | Level 2 | GO 165 Inspection
122311815 | other | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-07-26 | 2022-10-27 | Level 2 | GO 165 Inspection
122312006 | other | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-07-26 | 2022-10-27 | Level 2 | GO 165 Inspection
122312530 | insulator and brushing | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2024-01-29 | 2024-11-03 | Level 2 | Standards change
122312550 | other | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-12-06 | 2026-11-03 | Level 3 | Standards change
122312580 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-01-10 | 2026-10-27 | Level 3 | Standards change
122312841 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-04-06 | 2026-10-20 | Level 3 | Standards change
122312922 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-10-29 | 2024-10-29 | Level 2 | GO 165 Inspection
122312967 | anchor/guy | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-01-12 | 2026-10-30 | Level 3 | Standards change
122314004 | pole | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-01-17 | 2022-10-29 | Level 2 | Standards change
122314381 | insulator and brushing | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-08-16 | 2024-10-30 | Level 2 | GO 165 Inspection
122315413 | other | Non-HFTD | Transmission | 2021-10-26 | 2023-10-26 | Level 3 | F | 2024-01-19 | 2026-10-26 | Level 3 | Standards change
122320219 | pole | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-07-12 | 2024-10-29 | Level 2 | GO 165 Inspection
122320258 | pole | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2023-02-02 | 2026-11-04 | Level 3 | Standards change
122321321 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-08-13 | 2024-10-22 | Level 2 | Field Safety Reassessment
122321358 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-02-05 | 2024-11-04 | Level 2 | Standards change
122321434 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2023-01-11 | 2026-10-22 | Level 3 | Standards change
122321651 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-10-08 | 2024-11-04 | Level 2 | Field Safety Reassessment
122322284 | pole | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-12-23 | 2024-11-04 | Level 2 | Field Safety Reassessment
122322499 | other | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2023-01-26 | 2026-10-26 | Level 3 | Standards change
122322520 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-08-28 | 2026-10-19 | Level 3 | GO 165 Inspection
122322544 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2023-12-27 | 2026-10-27 | Level 3 | Standards change
122322630 | other | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2023-01-26 | 2026-10-26 | Level 3 | Standards change
122322808 | pole | Non-HFTD | Transmission | 2021-10-23 | 2023-10-23 | Level 3 | F | 2024-10-16 | 2026-10-23 | Level 3 | GO 165 Inspection
122322852 | insulator and brushing | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-08-16 | 2024-11-01 | Level 2 | GO 165 Inspection
122322854 | insulator and brushing | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-08-16 | 2024-11-01 | Level 2 | GO 165 Inspection
122322866 | other | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-01-09 | 2026-10-20 | Level 3 | Standards change
122322885 | other | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2024-10-17 | 2024-10-26 | Level 2 | GO 165 Inspection
122322977 | anchor/guy | Non-HFTD | Transmission | 2021-10-15 | 2022-10-15 | Level 2 | E | 2023-12-18 | 2026-10-15 | Level 3 | Standards change
122323124 | other | Non-HFTD | Transmission | 2021-10-26 | 2023-10-26 | Level 3 | F | 2024-11-26 | 2026-10-26 | Level 3 | GO 165 Inspection
122323130 | other | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2023-02-14 | 2026-10-19 | Level 3 | Standards change
122323380 | insulator and brushing | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-09-06 | 2024-10-20 | Level 2 | GO 165 Inspection
122324475 | insulator and brushing | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2024-12-10 | 2024-10-26 | Level 2 | Field Safety Reassessment
122324498 | other | Non-HFTD | Transmission | 2021-10-21 | 2023-10-21 | Level 3 | F | 2024-01-02 | 2026-10-21 | Level 3 | Standards change
122324525 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-04-06 | 2026-10-20 | Level 3 | Standards change
122324526 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2024-04-06 | 2026-10-29 | Level 3 | Standards change
122324592 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-01-04 | 2026-10-20 | Level 3 | Standards change
122324652 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-01-08 | 2026-11-04 | Level 3 | Standards change
122324732 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-07-17 | 2024-11-02 | Level 2 | Field Safety Reassessment
122324935 | other | Non-HFTD | Transmission | 2021-10-21 | 2024-10-21 | Level 2 | E | 2024-06-17 | 2022-10-21 | Level 2 | Field Safety Reassessment
122325051 | other | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-10-21 | 2026-10-29 | Level 3 | GO 165 Inspection
122325213 | pole | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2023-02-03 | 2024-11-02 | Level 2 | Standards change
122325368 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-01-16 | 2026-10-27 | Level 3 | Standards change
122325457 | other | Non-HFTD | Transmission | 2021-10-26 | 2022-10-26 | Level 2 | E | 2023-03-06 | 2026-10-26 | Level 3 | Standards change
122325565 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-10-15 | 2024-11-04 | Level 2 | GO 165 Inspection
122325596 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-07 | 2024-11-02 | Level 2 | GO 165 Inspection
122325598 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-08-22 | 2024-10-19 | Level 2 | GO 165 Inspection
122325689 | other | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2023-12-20 | 2026-10-19 | Level 3 | Standards change
122325732 | pole | Non-HFTD | Transmission | 2021-10-19 | 2023-10-19 | Level 3 | F | 2024-08-22 | 2026-10-19 | Level 3 | GO 165 Inspection
122325733 | insulator and brushing | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-08-22 | 2024-10-19 | Level 2 | GO 165 Inspection
122325859 | pole | Non-HFTD | Transmission | 2021-10-19 | 2022-10-19 | Level 2 | E | 2024-11-18 | 2024-10-19 | Level 2 | Field Safety Reassessment
122325960 | other | Non-HFTD | Transmission | 2021-10-23 | 2023-10-23 | Level 3 | F | 2024-09-11 | 2026-10-23 | Level 3 | GO 165 Inspection
122326088 | pole | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-05-03 | 2024-11-04 | Level 2 | Field Safety Reassessment
122326128 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-10-30 | 2024-10-22 | Level 2 | GO 165 Inspection
122326180 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2024-10-30 | 2026-10-22 | Level 3 | GO 165 Inspection
122326242 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-04-06 | 2026-10-20 | Level 3 | Standards change
122326269 | other | Non-HFTD | Transmission | 2021-10-21 | 2023-10-21 | Level 3 | F | 2024-04-06 | 2026-10-21 | Level 3 | Standards change
122326299 | switch | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2023-02-03 | 2024-10-22 | Level 2 | Standards change
122326380 | insulator and brushing | Non-HFTD | Transmission | 2021-10-20 | 2022-10-20 | Level 2 | E | 2024-12-27 | 2024-10-20 | Level 2 | Field Safety Reassessment
122326499 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-01-11 | 2026-11-05 | Level 3 | Standards change
122326500 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2024-12-26 | 2024-10-22 | Level 2 | Field Safety Reassessment
122326770 | conductor | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-10-24 | 2026-11-05 | Level 3 | GO 165 Inspection
122326835 | pole | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-11-27 | 2024-10-29 | Level 2 | Field Safety Reassessment
122326891 | other | Non-HFTD | Transmission | 2021-10-30 | 2023-10-30 | Level 3 | F | 2023-12-12 | 2026-10-30 | Level 3 | Standards change
122326974 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-11-20 | 2026-11-02 | Level 3 | GO 165 Inspection
122326977 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2023-02-08 | 2024-10-29 | Level 2 | Standards change
122327009 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-08-21 | 2026-11-03 | Level 3 | GO 165 Inspection
122327086 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-12-07 | 2024-11-05 | Level 2 | Field Safety Reassessment
122327403 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2023-02-08 | 2024-10-29 | Level 2 | Standards change
122327515 | other | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-12-10 | 2024-11-04 | Level 2 | Field Safety Reassessment
122327570 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-01-04 | 2026-11-05 | Level 3 | Standards change
122327585 | pole | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-10-10 | 2024-11-04 | Level 2 | Field Safety Reassessment
122327937 | pole | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2024-08-31 | 2026-10-28 | Level 3 | GO 165 Inspection
122328090 | pole | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-11-20 | 2026-11-03 | Level 3 | GO 165 Inspection
122328298 | anchor/guy | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-01-29 | 2026-11-02 | Level 3 | Standards change
122328317 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2023-12-28 | 2026-11-05 | Level 3 | Standards change
122328576 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2023-10-26 | 2026-10-22 | Level 3 | Standards change
122328669 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-12-13 | 2024-11-05 | Level 2 | Field Safety Reassessment
122328689 | crossarm | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-12-21 | 2024-11-05 | Level 2 | Field Safety Reassessment
122329609 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2023-12-27 | 2026-11-05 | Level 3 | Standards change
122329680 | other | Non-HFTD | Transmission | 2021-10-30 | 2023-10-30 | Level 3 | F | 2024-01-05 | 2026-10-30 | Level 3 | Standards change
122329749 | insulator and brushing | Non-HFTD | Transmission | 2021-10-22 | 2022-10-22 | Level 2 | E | 2023-02-02 | 2026-10-22 | Level 3 | Standards change
122329752 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2023-02-16 | 2026-10-27 | Level 3 | Standards change
122329755 | other | Non-HFTD | Transmission | 2021-10-22 | 2023-10-22 | Level 3 | F | 2023-01-25 | 2026-10-22 | Level 3 | Standards change
122329776 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2023-12-27 | 2026-10-27 | Level 3 | Standards change
122329858 | anchor/guy | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-02-02 | 2024-11-03 | Level 2 | Standards change
122329885 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-01-11 | 2026-11-03 | Level 3 | Standards change
122329896 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-09-16 | 2026-10-27 | Level 3 | GO 165 Inspection
122330011 | pole | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-11-15 | 2022-11-05 | Level 2 | GO 165 Inspection
122330056 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-01-05 | 2026-10-27 | Level 3 | Standards change
122330147 | other | Non-HFTD | Transmission | 2021-11-01 | 2023-11-01 | Level 3 | F | 2024-02-01 | 2026-11-01 | Level 3 | Standards change
122330162 | other | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2024-01-11 | 2026-11-03 | Level 3 | Standards change
122330209 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2023-12-20 | 2026-11-03 | Level 3 | Standards change
122330258 | insulator and brushing | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-10-24 | 2024-10-27 | Level 2 | GO 165 Inspection
122330279 | anchor/guy | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-01-12 | 2026-10-27 | Level 3 | Standards change
122330362 | other | Non-HFTD | Transmission | 2021-11-06 | 2023-11-06 | Level 3 | F | 2023-02-17 | 2026-11-06 | Level 3 | Standards change
122330743 | other | Non-HFTD | Transmission | 2021-10-30 | 2023-10-30 | Level 3 | F | 2024-04-06 | 2026-10-30 | Level 3 | Standards change
122330744 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2023-10-26 | 2026-10-29 | Level 3 | Standards change
122330852 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-04-06 | 2026-11-03 | Level 3 | Standards change
122330866 | other | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2023-01-26 | 2026-11-06 | Level 3 | Standards change
122330906 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-04-06 | 2026-10-27 | Level 3 | Standards change
122332209 | anchor/guy | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-01-12 | 2026-10-27 | Level 3 | Standards change
122332309 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-01-05 | 2026-11-03 | Level 3 | Standards change
122332397 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-10-29 | 2024-10-29 | Level 2 | GO 165 Inspection
122332419 | insulator and brushing | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-01-31 | 2024-11-01 | Level 2 | Standards change
122334958 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-11-05 | 2026-11-08 | Level 3 | GO 165 Inspection
122336468 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2023-02-14 | 2024-11-08 | Level 2 | Standards change
122337495 | insulator and brushing | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-10-05 | 2024-11-08 | Level 2 | GO 165 Inspection
122337993 | anchor/guy | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-01-12 | 2026-10-27 | Level 3 | Standards change
122338174 | insulator and brushing | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-08-06 | 2024-11-08 | Level 2 | Field Safety Reassessment
122338364 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2023-01-11 | 2026-11-03 | Level 3 | Standards change
122338675 | insulator and brushing | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2023-01-31 | 2024-11-08 | Level 2 | Standards change
122338714 | insulator and brushing | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-12-07 | 2024-10-30 | Level 2 | Field Safety Reassessment
122338718 | anchor/guy | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-01-22 | 2026-11-01 | Level 3 | Standards change
122338791 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-12-23 | 2024-11-08 | Level 2 | Field Safety Reassessment
122338802 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-12-31 | 2024-11-08 | Level 2 | Field Safety Reassessment
122338977 | pole | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-12-09 | 2024-11-01 | Level 2 | Field Safety Reassessment
122339006 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2023-02-03 | 2024-11-04 | Level 2 | Standards change
122339030 | anchor/guy | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-01-12 | 2026-10-27 | Level 3 | Standards change
122339063 | anchor/guy | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-01-12 | 2026-10-27 | Level 3 | Standards change
122339095 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-10-08 | 2024-11-05 | Level 2 | GO 165 Inspection
122339163 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2023-01-25 | 2026-11-08 | Level 3 | Standards change
122339168 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-01-10 | 2026-11-08 | Level 3 | Standards change
122339185 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-04-06 | 2026-11-02 | Level 3 | Standards change
122339240 | other | Non-HFTD | Transmission | 2021-10-27 | 2022-10-27 | Level 2 | E | 2024-01-18 | 2026-10-27 | Level 3 | Standards change
122339248 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2024-11-02 | Level 2 | GO 165 Inspection
122339297 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-08-29 | 2024-11-08 | Level 2 | GO 165 Inspection
122339992 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-09-10 | 2026-10-27 | Level 3 | GO 165 Inspection
122340089 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2023-12-27 | 2026-11-09 | Level 3 | Standards change
122340313 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2024-04-06 | 2026-11-09 | Level 3 | Standards change
122340706 | conductor | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-10-15 | 2026-11-01 | Level 3 | GO 165 Inspection
122340870 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-04-06 | 2026-10-27 | Level 3 | Standards change
122340888 | pole | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-08-29 | 2024-11-09 | Level 2 | Field Safety Reassessment
122340981 | other | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-10-29 | 2024-11-09 | Level 2 | GO 165 Inspection
122340986 | pole | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-09-04 | 2022-11-09 | Level 2 | Field Safety Reassessment
122341015 | other | Non-HFTD | Transmission | 2021-10-27 | 2023-10-27 | Level 3 | F | 2024-04-06 | 2026-10-27 | Level 3 | Standards change
122341127 | other | Non-HFTD | Transmission | 2021-11-09 | 2024-11-09 | Level 2 | E | 2024-12-16 | 2026-11-09 | Level 3 | Field Safety Reassessment
122342524 | pole | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2023-02-14 | 2024-11-06 | Level 2 | Standards change
122342527 | other | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2023-02-14 | 2024-11-06 | Level 2 | Standards change
122342706 | other | Non-HFTD | Transmission | 2021-10-30 | 2023-10-30 | Level 3 | F | 2024-04-06 | 2026-10-30 | Level 3 | Standards change
122343251 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-11-20 | 2026-11-02 | Level 3 | GO 165 Inspection
122343905 | pole | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-11-20 | 2024-11-09 | Level 2 | GO 165 Inspection
122343934 | insulator and brushing | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2023-01-31 | 2024-11-09 | Level 2 | Standards change
122344896 | pole | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-10-28 | 2024-11-09 | Level 2 | GO 165 Inspection
122344908 | other | Non-HFTD | Transmission | 2021-11-09 | 2024-11-09 | Level 2 | E | 2024-12-30 | 2022-11-09 | Level 2 | Field Safety Reassessment
122345342 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-10-15 | 2024-11-04 | Level 2 | GO 165 Inspection
122345806 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-04-06 | 2026-11-04 | Level 3 | Standards change
122345901 | other | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2024-01-02 | 2026-10-28 | Level 3 | Standards change
122345954 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-10-16 | 2026-11-03 | Level 3 | GO 165 Inspection
122345993 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2023-12-28 | 2026-11-03 | Level 3 | Standards change
122346087 | insulator and brushing | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-01-17 | 2024-11-01 | Level 2 | Standards change
122346100 | other | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-11-19 | 2026-11-02 | Level 3 | GO 165 Inspection
122346109 | other | Non-HFTD | Transmission | 2021-11-03 | 2024-11-03 | Level 2 | E | 2024-12-16 | 2026-11-03 | Level 3 | Field Safety Reassessment
122346128 | anchor/guy | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-10-18 | 2026-11-09 | Level 3 | GO 165 Inspection
122346140 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2023-12-18 | 2026-10-29 | Level 3 | Standards change
122346141 | other | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2023-12-18 | 2026-10-29 | Level 3 | Standards change
122346143 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-01-05 | 2026-11-03 | Level 3 | Standards change
122346156 | pole | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2023-08-02 | 2024-11-02 | Level 2 | Standards change
122346171 | pole | Non-HFTD | Transmission | 2021-10-28 | 2022-10-28 | Level 2 | E | 2024-01-31 | 2024-10-28 | Level 2 | Standards change
122346175 | pole | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2024-12-11 | 2024-11-06 | Level 2 | Field Safety Reassessment
122346300 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-04-06 | 2026-11-02 | Level 3 | Standards change
122346305 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-10-29 | 2024-11-05 | Level 2 | GO 165 Inspection
122346348 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-07-09 | 2026-11-04 | Level 3 | GO 165 Inspection
122358002 | insulator and brushing | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2023-01-31 | 2024-11-09 | Level 2 | Standards change
122358422 | pole | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-10-24 | 2026-11-10 | Level 3 | GO 165 Inspection
122358615 | other | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2026-11-02 | Level 3 | GO 165 Inspection
122358616 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2024-11-02 | Level 2 | GO 165 Inspection
122358619 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-11-01 | 2024-11-08 | Level 2 | GO 165 Inspection
122359738 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2023-02-08 | 2024-11-08 | Level 2 | Standards change
122360297 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-01-02 | 2026-11-05 | Level 3 | Standards change
122361473 | pole | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-12-03 | 2026-11-10 | Level 3 | Field Safety Reassessment
122361478 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-29 | 2024-11-10 | Level 2 | GO 165 Inspection
122361621 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-29 | 2026-11-10 | Level 3 | GO 165 Inspection
122361808 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2023-02-14 | 2026-11-10 | Level 3 | Standards change
122362014 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-01-09 | 2026-11-10 | Level 3 | Standards change
122362268 | insulator and brushing | Non-HFTD | Transmission | 2021-10-30 | 2022-10-30 | Level 2 | E | 2024-02-05 | 2024-10-30 | Level 2 | Standards change
122362295 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2023-12-19 | 2026-11-11 | Level 3 | Standards change
122362599 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2024-11-10 | Level 2 | E | 2024-11-13 | 2022-05-10 | Level 2 | Field Safety Reassessment
122362608 | other | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2023-12-19 | 2024-11-06 | Level 2 | Standards change
122362642 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-04-06 | 2026-11-02 | Level 3 | Standards change
122362647 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-04-06 | 2026-11-04 | Level 3 | Standards change
122362683 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-11-08 | 2026-11-05 | Level 3 | GO 165 Inspection
122362699 | anchor/guy | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-01-10 | 2026-11-01 | Level 3 | Standards change
122362711 | other | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-11-08 | 2024-11-05 | Level 2 | GO 165 Inspection
122362762 | other | Non-HFTD | Transmission | 2021-11-08 | 2024-11-08 | Level 2 | E | 2024-12-30 | 2022-11-08 | Level 2 | Field Safety Reassessment
122362763 | other | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2023-01-27 | 2026-11-04 | Level 3 | Standards change
122362774 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2023-02-15 | 2024-10-29 | Level 2 | Standards change
122362777 | other | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-12-30 | 2024-11-04 | Level 2 | Field Safety Reassessment
122362822 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2023-02-13 | 2026-11-08 | Level 3 | Standards change
122362851 | pole | Non-HFTD | Transmission | 2021-10-28 | 2023-10-28 | Level 3 | F | 2023-02-27 | 2026-10-28 | Level 3 | Standards change
122362856 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2023-12-21 | 2026-11-02 | Level 3 | Standards change
122362939 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-12-30 | 2024-11-08 | Level 2 | Field Safety Reassessment
122363037 | other | Non-HFTD | Transmission | 2021-11-06 | 2024-11-06 | Level 2 | E | 2024-12-30 | 2022-11-06 | Level 2 | Field Safety Reassessment
122363077 | other | Non-HFTD | Transmission | 2021-10-29 | 2023-10-29 | Level 3 | F | 2024-04-06 | 2026-10-29 | Level 3 | Standards change
122363101 | other | Non-HFTD | Transmission | 2021-10-30 | 2024-10-30 | Level 2 | E | 2024-12-08 | 2022-10-30 | Level 2 | Field Safety Reassessment
122363119 | pole | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2023-08-02 | 2026-11-04 | Level 3 | Standards change
122363205 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-15 | 2024-11-10 | Level 2 | GO 165 Inspection
122363537 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2023-12-27 | 2026-11-10 | Level 3 | Standards change
122363624 | insulator and brushing | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2024-12-10 | 2024-11-06 | Level 2 | Field Safety Reassessment
122363672 | other | Non-HFTD | Transmission | 2021-11-10 | 2024-11-10 | Level 2 | E | 2024-11-27 | 2026-11-10 | Level 3 | Field Safety Reassessment
122363973 | other | Non-HFTD | Transmission | 2021-11-11 | 2023-11-11 | Level 3 | F | 2024-11-24 | 2026-11-11 | Level 3 | GO 165 Inspection
122364038 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-10-25 | 2024-11-08 | Level 2 | GO 165 Inspection
122364613 | other | Non-HFTD | Transmission | 2021-11-06 | 2023-11-06 | Level 3 | F | 2024-10-09 | 2026-11-06 | Level 3 | GO 165 Inspection
122364888 | other | Non-HFTD | Transmission | 2021-11-11 | 2023-11-11 | Level 3 | F | 2024-11-13 | 2026-11-11 | Level 3 | GO 165 Inspection
122364992 | other | Non-HFTD | Transmission | 2021-11-11 | 2022-11-11 | Level 2 | E | 2024-11-12 | 2026-11-11 | Level 3 | GO 165 Inspection
122366104 | anchor/guy | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-01-17 | 2026-11-02 | Level 3 | Standards change
122366109 | other | Non-HFTD | Transmission | 2021-10-28 | 2023-10-28 | Level 3 | F | 2023-01-11 | 2026-10-28 | Level 3 | Standards change
122367180 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-04-06 | 2026-11-02 | Level 3 | Standards change
122367190 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-12-31 | 2024-11-08 | Level 2 | Field Safety Reassessment
122367202 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-01-04 | 2026-11-03 | Level 3 | Standards change
122367238 | pole | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2024-09-24 | 2024-11-06 | Level 2 | GO 165 Inspection
122367270 | other | Non-HFTD | Transmission | 2021-11-01 | 2023-11-01 | Level 3 | F | 2023-12-18 | 2026-11-01 | Level 3 | Standards change
122367276 | other | Non-HFTD | Transmission | 2021-11-08 | 2024-11-08 | Level 2 | E | 2024-10-29 | 2022-11-08 | Level 2 | GO 165 Inspection
122367336 | insulator and brushing | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-02-06 | 2024-11-03 | Level 2 | Standards change
122367476 | pole | Non-HFTD | Transmission | 2021-11-01 | 2022-11-01 | Level 2 | E | 2024-12-30 | 2024-11-01 | Level 2 | Field Safety Reassessment
122367610 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-09-23 | 2024-11-02 | Level 2 | Field Safety Reassessment
122367702 | other | Non-HFTD | Transmission | 2021-11-02 | 2023-11-02 | Level 3 | F | 2024-04-06 | 2026-11-02 | Level 3 | Standards change
122367744 | other | Non-HFTD | Transmission | 2021-11-12 | 2022-11-12 | Level 2 | E | 2023-02-14 | 2026-11-12 | Level 3 | Standards change
122367887 | insulator and brushing | Non-HFTD | Transmission | 2021-10-29 | 2022-10-29 | Level 2 | E | 2024-01-31 | 2024-10-29 | Level 2 | Standards change
122367953 | other | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-10-15 | 2026-11-04 | Level 3 | GO 165 Inspection
122368181 | other | Non-HFTD | Transmission | 2021-11-12 | 2023-11-12 | Level 3 | F | 2024-01-08 | 2026-11-12 | Level 3 | Standards change
122368342 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-12-30 | 2024-11-08 | Level 2 | Field Safety Reassessment
122368442 | anchor/guy | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-01-17 | 2026-11-04 | Level 3 | Standards change
122368444 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2024-01-05 | 2026-11-08 | Level 3 | Standards change
122368448 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-08-29 | 2024-11-08 | Level 2 | GO 165 Inspection
122368455 | other | Non-HFTD | Transmission | 2021-11-12 | 2022-11-12 | Level 2 | E | 2024-12-13 | 2024-11-12 | Level 2 | Field Safety Reassessment
122368565 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2023-12-20 | 2026-11-04 | Level 3 | Standards change
122368573 | insulator and brushing | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-11-22 | 2024-11-08 | Level 2 | Field Safety Reassessment
122368621 | other | Non-HFTD | Transmission | 2021-11-09 | 2024-11-09 | Level 2 | E | 2024-12-11 | 2022-11-09 | Level 2 | Field Safety Reassessment
122368914 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2023-02-03 | 2024-11-04 | Level 2 | Standards change
122368971 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-01-02 | 2026-11-05 | Level 3 | Standards change
122369096 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-10-14 | 2024-11-08 | Level 2 | GO 165 Inspection
122369412 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-12-06 | 2024-11-04 | Level 2 | Field Safety Reassessment
122369741 | other | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2023-01-06 | 2026-11-02 | Level 3 | Standards change
122369975 | pole | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-31 | 2024-11-02 | Level 2 | GO 165 Inspection
122370130 | insulator and brushing | Non-HFTD | Transmission | 2021-11-02 | 2022-11-02 | Level 2 | E | 2024-10-30 | 2024-11-02 | Level 2 | GO 165 Inspection
122370160 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2023-08-11 | 2026-11-09 | Level 3 | Standards change
122370576 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-29 | 2024-11-10 | Level 2 | GO 165 Inspection
122370670 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-29 | 2026-11-10 | Level 3 | GO 165 Inspection
122371560 | other | Non-HFTD | Transmission | 2021-11-12 | 2023-11-12 | Level 3 | F | 2024-04-06 | 2026-11-12 | Level 3 | Standards change
122376162 | other | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-09-06 | 2024-11-04 | Level 2 | GO 165 Inspection
122376263 | other | Non-HFTD | Transmission | 2021-11-15 | 2023-11-15 | Level 3 | F | 2024-01-08 | 2026-11-15 | Level 3 | Standards change
122377182 | other | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2023-01-19 | 2024-11-15 | Level 2 | Standards change
122377915 | other | Non-HFTD | Transmission | 2021-11-15 | 2023-11-15 | Level 3 | F | 2024-01-08 | 2026-11-15 | Level 3 | Standards change
122378248 | insulator and brushing | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-11-20 | 2024-11-15 | Level 2 | GO 165 Inspection
122378473 | insulator and brushing | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-10-23 | 2024-11-15 | Level 2 | GO 165 Inspection
122378497 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-08-21 | 2024-11-10 | Level 2 | GO 165 Inspection
122378717 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-10-16 | 2026-11-05 | Level 3 | GO 165 Inspection
122378757 | other | Non-HFTD | Transmission | 2021-11-09 | 2024-11-09 | Level 2 | E | 2024-11-19 | 2022-11-09 | Level 2 | GO 165 Inspection
122378800 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-08-22 | 2022-11-10 | Level 2 | GO 165 Inspection
122378809 | switch | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-08-14 | 2022-11-10 | Level 2 | Field Safety Reassessment
122378823 | other | Non-HFTD | Transmission | 2021-11-05 | 2024-11-05 | Level 2 | E | 2024-12-10 | 2022-11-05 | Level 2 | Field Safety Reassessment
122378919 | other | Non-HFTD | Transmission | 2021-11-15 | 2024-11-15 | Level 2 | E | 2024-10-25 | 2022-11-15 | Level 2 | GO 165 Inspection
122379044 | pole | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-12-31 | 2024-11-15 | Level 2 | Field Safety Reassessment
122379102 | other | Non-HFTD | Transmission | 2021-11-15 | 2024-11-15 | Level 2 | E | 2024-12-11 | 2022-11-15 | Level 2 | Field Safety Reassessment
122379732 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2024-11-16 | Level 2 | E | 2024-12-01 | 2022-11-16 | Level 2 | Field Safety Reassessment
122380768 | other | Non-HFTD | Transmission | 2021-11-06 | 2023-11-06 | Level 3 | F | 2024-08-19 | 2026-11-06 | Level 3 | GO 165 Inspection
122381529 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-10-08 | 2024-11-16 | Level 2 | GO 165 Inspection
122381575 | other | Non-HFTD | Transmission | 2021-11-06 | 2023-11-06 | Level 3 | F | 2024-01-05 | 2026-11-06 | Level 3 | Standards change
122381970 | anchor/guy | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2023-11-30 | 2026-11-16 | Level 3 | Standards change
122381992 | pole | Non-HFTD | Transmission | 2021-11-16 | 2023-11-16 | Level 3 | F | 2023-02-08 | 2026-11-16 | Level 3 | Standards change
122382062 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2024-06-05 | 2026-11-08 | Level 3 | GO 165 Inspection
122382212 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-01-05 | 2026-11-10 | Level 3 | Standards change
122382225 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-04-04 | 2026-11-08 | Level 3 | GO 165 Inspection
122383198 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2024-04-06 | 2026-11-08 | Level 3 | Standards change
122383259 | other | Non-HFTD | Transmission | 2021-11-15 | 2024-11-15 | Level 2 | E | 2024-09-06 | 2022-11-15 | Level 2 | GO 165 Inspection
122383329 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-12-01 | 2024-11-16 | Level 2 | Field Safety Reassessment
122384046 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2024-04-06 | 2026-11-03 | Level 3 | Standards change
122384155 | other | Non-HFTD | Transmission | 2021-11-16 | 2026-11-16 | Level 3 | F | 2024-09-05 | 2024-11-16 | Level 2 | GO 165 Inspection
122384317 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2024-11-08 | 2026-11-08 | Level 3 | GO 165 Inspection
122384319 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-04-06 | 2026-11-04 | Level 3 | Standards change
122384364 | other | Non-HFTD | Transmission | 2021-10-30 | 2023-10-30 | Level 3 | F | 2024-04-06 | 2026-10-30 | Level 3 | Standards change
122384460 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2024-01-05 | 2026-11-08 | Level 3 | Standards change
122384474 | other | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2024-12-09 | 2024-11-04 | Level 2 | Field Safety Reassessment
122384503 | other | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2023-02-14 | 2024-11-09 | Level 2 | Standards change
122384551 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-04-06 | 2026-11-04 | Level 3 | Standards change
122384563 | insulator and brushing | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2023-12-13 | 2026-11-04 | Level 3 | Standards change
122384564 | pole | Non-HFTD | Transmission | 2021-11-04 | 2022-11-04 | Level 2 | E | 2023-09-07 | 2024-11-04 | Level 2 | Standards change
122384566 | other | Non-HFTD | Transmission | 2021-11-04 | 2023-11-04 | Level 3 | F | 2024-01-26 | 2026-11-04 | Level 3 | Standards change
122385361 | pole | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-11-27 | 2024-11-16 | Level 2 | Field Safety Reassessment
122385451 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-04-06 | 2026-11-17 | Level 3 | Standards change
122385895 | other | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-01-26 | 2024-11-17 | Level 2 | Standards change
122386046 | pole | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-11-27 | 2024-11-16 | Level 2 | Field Safety Reassessment
122386186 | insulator and brushing | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-08-06 | 2024-11-09 | Level 2 | Field Safety Reassessment
122386763 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-08-23 | 2024-11-16 | Level 2 | GO 165 Inspection
122387187 | other | Non-HFTD | Transmission | 2021-11-16 | 2023-11-16 | Level 3 | F | 2024-01-26 | 2026-11-16 | Level 3 | Standards change
122387239 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-04-06 | 2026-11-17 | Level 3 | Standards change
122387638 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-05-01 | 2026-11-10 | Level 3 | GO 165 Inspection
122387655 | pole | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-05-10 | 2024-11-09 | Level 2 | Field Safety Reassessment
122387715 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-01-04 | 2026-11-05 | Level 3 | Standards change
122388326 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2023-01-26 | 2026-11-10 | Level 3 | Standards change
122388328 | pole | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-08-29 | 2024-11-10 | Level 2 | GO 165 Inspection
122388440 | other | Non-HFTD | Transmission | 2021-11-05 | 2023-11-05 | Level 3 | F | 2024-04-06 | 2026-11-05 | Level 3 | Standards change
122388443 | other | Non-HFTD | Transmission | 2021-11-02 | 2024-11-02 | Level 2 | E | 2024-07-26 | 2026-11-02 | Level 3 | GO 165 Inspection
122389651 | other | Non-HFTD | Transmission | 2021-11-08 | 2024-11-08 | Level 2 | E | 2024-10-25 | 2022-11-08 | Level 2 | GO 165 Inspection
122390715 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2023-01-27 | 2026-11-08 | Level 3 | Standards change
122390716 | other | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2023-01-27 | 2026-11-08 | Level 3 | Standards change
122391314 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-29 | 2026-11-10 | Level 3 | GO 165 Inspection
122391821 | other | Non-HFTD | Transmission | 2021-11-06 | 2023-11-06 | Level 3 | F | 2024-04-06 | 2026-11-06 | Level 3 | Standards change
122391824 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2023-12-05 | 2026-11-05 | Level 3 | Standards change
122392113 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-08-30 | 2024-11-05 | Level 2 | GO 165 Inspection
122392353 | pole | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-08-29 | 2024-11-08 | Level 2 | GO 165 Inspection
122392481 | other | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-12-31 | 2024-11-15 | Level 2 | Field Safety Reassessment
122392743 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2024-04-06 | 2026-11-09 | Level 3 | Standards change
122394076 | crossarm | Non-HFTD | Transmission | 2021-09-23 | 2022-09-23 | Level 2 | E | 2023-03-07 | 2024-09-23 | Level 2 | Standards change
122394195 | other | Non-HFTD | Transmission | 2021-11-17 | 2024-11-17 | Level 2 | E | 2024-09-23 | 2022-02-17 | Level 2 | Field Safety Reassessment
122394233 | other | Non-HFTD | Transmission | 2021-11-03 | 2023-11-03 | Level 3 | F | 2023-12-01 | 2026-11-03 | Level 3 | Standards change
122394267 | other | Non-HFTD | Transmission | 2021-11-15 | 2023-11-15 | Level 3 | F | 2024-01-18 | 2026-11-15 | Level 3 | Standards change
122394300 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2024-01-05 | 2026-11-09 | Level 3 | Standards change
122394337 | other | Non-HFTD | Transmission | 2021-11-18 | 2022-11-18 | Level 2 | E | 2024-02-01 | 2024-11-18 | Level 2 | Standards change
122394364 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-04-06 | 2026-11-10 | Level 3 | Standards change
122394508 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2024-04-06 | 2026-11-09 | Level 3 | Standards change
122394609 | other | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2023-02-13 | 2024-11-15 | Level 2 | Standards change
122394699 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-10-16 | 2024-11-05 | Level 2 | GO 165 Inspection
122394724 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-10-16 | 2024-11-05 | Level 2 | GO 165 Inspection
122394787 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-12-03 | 2024-11-10 | Level 2 | Field Safety Reassessment
122394918 | other | Non-HFTD | Transmission | 2021-11-15 | 2023-11-15 | Level 3 | F | 2023-01-17 | 2026-11-15 | Level 3 | Standards change
122394940 | insulator and brushing | Non-HFTD | Transmission | 2021-11-03 | 2022-11-03 | Level 2 | E | 2023-10-18 | 2024-11-03 | Level 2 | Standards change
122395048 | pole | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-08-14 | 2024-11-15 | Level 2 | GO 165 Inspection
122396457 | pole | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2023-01-17 | 2026-11-08 | Level 3 | Standards change
122396828 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2023-12-04 | 2024-11-05 | Level 2 | Standards change
122397038 | pole | Non-HFTD | Transmission | 2021-11-19 | 2022-11-19 | Level 2 | E | 2024-08-23 | 2024-11-19 | Level 2 | GO 165 Inspection
122397100 | other | Non-HFTD | Transmission | 2021-11-15 | 2024-11-15 | Level 2 | E | 2024-09-10 | 2026-11-15 | Level 3 | Field Safety Reassessment
122397101 | other | Non-HFTD | Transmission | 2021-11-16 | 2023-11-16 | Level 3 | F | 2023-12-06 | 2026-11-16 | Level 3 | Standards change
122397191 | other | Non-HFTD | Transmission | 2021-11-09 | 2022-11-09 | Level 2 | E | 2024-07-29 | 2024-11-09 | Level 2 | GO 165 Inspection
122397303 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-11-27 | 2024-11-10 | Level 2 | Field Safety Reassessment
122397314 | other | Non-HFTD | Transmission | 2021-11-16 | 2024-11-16 | Level 2 | E | 2024-08-30 | 2026-11-16 | Level 3 | Field Safety Reassessment
122397334 | other | Non-HFTD | Transmission | 2021-11-08 | 2023-11-08 | Level 3 | F | 2024-01-05 | 2026-11-08 | Level 3 | Standards change
122397391 | insulator and brushing | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-12-07 | 2024-11-15 | Level 2 | Field Safety Reassessment
122397438 | insulator and brushing | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-12-31 | 2024-11-15 | Level 2 | Field Safety Reassessment
122397689 | other | Non-HFTD | Transmission | 2021-11-09 | 2023-11-09 | Level 3 | F | 2024-04-06 | 2026-11-09 | Level 3 | Standards change
122397711 | insulator and brushing | Non-HFTD | Transmission | 2021-11-05 | 2022-11-05 | Level 2 | E | 2024-10-29 | 2024-11-05 | Level 2 | GO 165 Inspection
122397732 | insulator and brushing | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2024-10-29 | 2024-11-10 | Level 2 | GO 165 Inspection
122398042 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-04-06 | 2026-11-10 | Level 3 | Standards change
122398208 | anchor/guy | Non-HFTD | Transmission | 2021-11-08 | 2022-11-08 | Level 2 | E | 2024-01-30 | 2024-11-08 | Level 2 | Standards change
122398832 | other | Non-HFTD | Transmission | 2021-11-17 | 2024-11-17 | Level 2 | E | 2024-05-03 | 2022-11-17 | Level 2 | Field Safety Reassessment
122399119 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-07-23 | 2022-11-16 | Level 2 | GO 165 Inspection
122399259 | other | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2023-12-28 | 2024-11-15 | Level 2 | Standards change
122399269 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-07-22 | 2026-11-17 | Level 3 | GO 165 Inspection
122399504 | other | Non-HFTD | Transmission | 2021-11-19 | 2022-11-19 | Level 2 | E | 2023-01-23 | 2026-11-19 | Level 3 | Standards change
122399675 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2023-12-21 | 2026-11-17 | Level 3 | Standards change
122401102 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-09-11 | 2026-11-17 | Level 3 | GO 165 Inspection
122401215 | other | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-09-03 | 2026-11-16 | Level 3 | GO 165 Inspection
122401237 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2023-01-27 | 2026-11-10 | Level 3 | Standards change
122401239 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2023-12-26 | 2026-11-10 | Level 3 | Standards change
122401260 | pole | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-08-30 | 2024-11-16 | Level 2 | Field Safety Reassessment
122401372 | other | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-02-05 | 2024-11-15 | Level 2 | Standards change
122401487 | insulator and brushing | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-11-14 | 2024-11-17 | Level 2 | GO 165 Inspection
122401598 | other | Non-HFTD | Transmission | 2021-11-16 | 2023-11-16 | Level 3 | F | 2024-04-06 | 2026-11-16 | Level 3 | Standards change
122401689 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2023-12-20 | 2026-11-17 | Level 3 | Standards change
122401896 | other | Non-HFTD | Transmission | 2021-11-10 | 2023-11-10 | Level 3 | F | 2024-04-06 | 2026-11-10 | Level 3 | Standards change
122401930 | insulator and brushing | Non-HFTD | Transmission | 2021-11-15 | 2022-11-15 | Level 2 | E | 2024-08-06 | 2024-11-15 | Level 2 | Field Safety Reassessment
122402030 | insulator and brushing | Non-HFTD | Transmission | 2021-11-19 | 2022-11-19 | Level 2 | E | 2023-03-09 | 2024-11-19 | Level 2 | Standards change
122402036 | other | Non-HFTD | Transmission | 2021-11-19 | 2022-11-19 | Level 2 | E | 2024-12-30 | 2024-11-19 | Level 2 | Field Safety Reassessment
122402078 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-01-19 | 2026-11-17 | Level 3 | Standards change
122402080 | anchor/guy | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2023-02-28 | 2026-11-17 | Level 3 | Standards change
122402121 | insulator and brushing | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-01-19 | 2024-11-17 | Level 2 | Standards change
122402273 | other | Non-HFTD | Transmission | 2021-11-16 | 2023-11-16 | Level 3 | F | 2024-04-06 | 2026-11-16 | Level 3 | Standards change
122402453 | pole | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-08-09 | 2024-11-17 | Level 2 | GO 165 Inspection
122402456 | other | Non-HFTD | Transmission | 2021-11-10 | 2022-11-10 | Level 2 | E | 2023-02-15 | 2024-11-10 | Level 2 | Standards change
122402471 | other | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2023-01-27 | 2026-11-17 | Level 3 | Standards change
122402606 | other | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-11-27 | 2024-11-17 | Level 2 | GO 165 Inspection
122403431 | pole | Non-HFTD | Transmission | 2021-11-20 | 2022-11-20 | Level 2 | E | 2024-08-04 | 2024-11-20 | Level 2 | GO 165 Inspection
122403927 | other | Non-HFTD | Transmission | 2021-11-19 | 2022-11-19 | Level 2 | E | 2023-01-27 | 2026-11-19 | Level 3 | Standards change
122403935 | anchor/guy | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-12-10 | 2026-11-22 | Level 3 | GO 165 Inspection
122403939 | anchor/guy | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-12-10 | 2026-11-22 | Level 3 | GO 165 Inspection
122403941 | other | Non-HFTD | Transmission | 2021-11-19 | 2023-11-19 | Level 3 | F | 2024-01-05 | 2026-11-19 | Level 3 | Standards change
122404163 | other | Non-HFTD | Transmission | 2021-11-19 | 2023-11-19 | Level 3 | F | 2023-12-21 | 2026-11-19 | Level 3 | Standards change
122404291 | switch | Non-HFTD | Transmission | 2021-11-19 | 2022-11-19 | Level 2 | E | 2024-01-30 | 2024-11-19 | Level 2 | Standards change
122405366 | other | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-11-12 | 2024-11-16 | Level 2 | GO 165 Inspection
122405456 | other | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2023-12-20 | 2024-11-22 | Level 2 | Standards change
122406499 | pole | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-01-30 | 2024-11-16 | Level 2 | Field Safety Reassessment
122406960 | pole | Non-HFTD | Transmission | 2021-11-16 | 2023-11-16 | Level 3 | F | 2023-08-24 | 2026-11-16 | Level 3 | Standards change
122407348 | other | Non-HFTD | Transmission | 2021-11-18 | 2023-11-18 | Level 3 | F | 2024-04-06 | 2026-11-18 | Level 3 | Standards change
122408205 | other | Non-HFTD | Transmission | 2021-11-19 | 2023-11-19 | Level 3 | F | 2023-12-22 | 2026-11-19 | Level 3 | Standards change
122408644 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2022-11-16 | Level 2 | E | 2024-12-09 | 2024-11-16 | Level 2 | Field Safety Reassessment
122409084 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-09-19 | 2026-11-17 | Level 3 | GO 165 Inspection
122409382 | pole | Non-HFTD | Transmission | 2021-11-23 | 2022-11-23 | Level 2 | E | 2024-12-09 | 2024-11-23 | Level 2 | Field Safety Reassessment
122409581 | insulator and brushing | Non-HFTD | Transmission | 2021-11-23 | 2022-11-23 | Level 2 | E | 2024-12-24 | 2024-11-23 | Level 2 | Field Safety Reassessment
122410814 | other | Non-HFTD | Transmission | 2021-11-17 | 2023-11-17 | Level 3 | F | 2024-01-09 | 2026-11-17 | Level 3 | Standards change
122412029 | insulator and brushing | Non-HFTD | Transmission | 2021-11-23 | 2022-11-23 | Level 2 | E | 2023-01-31 | 2024-11-23 | Level 2 | Standards change
122413143 | pole | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-11-07 | 2024-11-22 | Level 2 | GO 165 Inspection
122413752 | pole | Non-HFTD | Transmission | 2021-11-06 | 2022-11-06 | Level 2 | E | 2024-12-11 | 2024-11-06 | Level 2 | Field Safety Reassessment
122414347 | other | Non-HFTD | Transmission | 2021-11-19 | 2023-11-19 | Level 3 | F | 2024-04-06 | 2026-11-19 | Level 3 | Standards change
122415111 | other | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-01-05 | 2026-11-22 | Level 3 | Standards change
122415431 | insulator and brushing | Non-HFTD | Transmission | 2021-11-24 | 2022-11-24 | Level 2 | E | 2024-12-04 | 2024-11-24 | Level 2 | Field Safety Reassessment
122418264 | other | Non-HFTD | Transmission | 2021-11-23 | 2023-11-23 | Level 3 | F | 2024-01-09 | 2026-11-23 | Level 3 | Standards change
122418452 | other | Non-HFTD | Transmission | 2021-11-22 | 2023-11-22 | Level 3 | F | 2023-12-04 | 2026-11-22 | Level 3 | Standards change
122418652 | pole | Non-HFTD | Transmission | 2021-11-26 | 2022-11-26 | Level 2 | E | 2024-08-13 | 2024-11-26 | Level 2 | Field Safety Reassessment
122422991 | other | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-10-04 | 2024-11-22 | Level 2 | GO 165 Inspection
122425562 | other | Non-HFTD | Transmission | 2021-11-18 | 2023-11-18 | Level 3 | F | 2023-12-27 | 2026-11-18 | Level 3 | Standards change
122425981 | other | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2023-12-21 | 2024-11-17 | Level 2 | Standards change
122426949 | anchor/guy | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-01-18 | 2026-11-17 | Level 3 | Standards change
122427173 | insulator and brushing | Non-HFTD | Transmission | 2021-11-30 | 2022-11-30 | Level 2 | E | 2024-01-17 | 2024-11-30 | Level 2 | Standards change
122427510 | other | Non-HFTD | Transmission | 2021-11-30 | 2022-11-30 | Level 2 | E | 2024-02-05 | 2026-11-30 | Level 3 | Standards change
122430928 | other | Non-HFTD | Transmission | 2021-11-29 | 2023-11-29 | Level 3 | F | 2024-01-05 | 2026-11-29 | Level 3 | Standards change
122431161 | pole | Non-HFTD | Transmission | 2021-11-29 | 2022-11-29 | Level 2 | E | 2023-02-17 | 2024-11-29 | Level 2 | Standards change
122431188 | other | Non-HFTD | Transmission | 2021-11-29 | 2023-11-29 | Level 3 | F | 2024-01-05 | 2026-11-29 | Level 3 | Standards change
122431408 | pole | Non-HFTD | Transmission | 2021-11-29 | 2022-11-29 | Level 2 | E | 2023-02-17 | 2024-11-29 | Level 2 | Standards change
122432246 | other | Non-HFTD | Transmission | 2021-11-17 | 2022-11-17 | Level 2 | E | 2024-12-18 | 2024-11-17 | Level 2 | Field Safety Reassessment
122432740 | switch | Non-HFTD | Transmission | 2021-12-01 | 2022-12-01 | Level 2 | E | 2024-01-18 | 2024-12-01 | Level 2 | Standards change
122435875 | pole | Non-HFTD | Transmission | 2021-12-01 | 2022-12-01 | Level 2 | E | 2024-08-29 | 2024-12-01 | Level 2 | Field Safety Reassessment
122437123 | anchor/guy | Non-HFTD | Transmission | 2021-11-11 | 2022-11-11 | Level 2 | E | 2024-01-18 | 2026-11-11 | Level 3 | Standards change
122441111 | insulator and brushing | Non-HFTD | Transmission | 2021-12-03 | 2022-12-03 | Level 2 | E | 2023-12-07 | 2024-12-03 | Level 2 | Standards change
122441800 | other | Non-HFTD | Transmission | 2021-12-03 | 2022-12-03 | Level 2 | E | 2023-02-22 | 2024-12-03 | Level 2 | Standards change
122446879 | other | HFTD Tier 3 | Transmission | 2021-12-06 | 2023-12-06 | Level 3 | F | 2024-03-06 | 2026-12-06 | Level 3 | GO 165 Inspection
122447475 | insulator and brushing | Non-HFTD | Transmission | 2021-11-16 | 2024-11-16 | Level 2 | E | 2024-12-01 | 2022-11-16 | Level 2 | Field Safety Reassessment
122454839 | pole | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-11-07 | 2024-11-22 | Level 2 | GO 165 Inspection
122461780 | insulator and brushing | Non-HFTD | Transmission | 2021-12-09 | 2022-12-09 | Level 2 | E | 2024-05-22 | 2024-12-09 | Level 2 | GO 165 Inspection
122461806 | other | Non-HFTD | Transmission | 2021-12-09 | 2022-12-09 | Level 2 | E | 2024-10-28 | 2024-12-09 | Level 2 | GO 165 Inspection
122480004 | insulator and brushing | Non-HFTD | Transmission | 2021-12-12 | 2022-12-12 | Level 2 | E | 2024-10-10 | 2024-12-12 | Level 2 | GO 165 Inspection
122484144 | pole | Non-HFTD | Transmission | 2021-12-13 | 2023-12-13 | Level 3 | F | 2024-08-20 | 2026-12-13 | Level 3 | GO 165 Inspection
122484148 | pole | Non-HFTD | Transmission | 2021-12-13 | 2023-12-13 | Level 3 | F | 2024-10-21 | 2026-12-13 | Level 3 | GO 165 Inspection
122484191 | pole | Non-HFTD | Transmission | 2021-12-13 | 2023-12-13 | Level 3 | F | 2024-08-20 | 2026-12-13 | Level 3 | GO 165 Inspection
122485960 | pole | Non-HFTD | Transmission | 2021-10-16 | 2022-10-16 | Level 2 | E | 2024-09-18 | 2024-10-16 | Level 2 | GO 165 Inspection
122486613 | switch | Non-HFTD | Transmission | 2021-11-22 | 2022-11-22 | Level 2 | E | 2024-09-10 | 2022-11-22 | Level 2 | Field Safety Reassessment
122492570 | pole | Non-HFTD | Transmission | 2021-12-04 | 2022-12-04 | Level 2 | E | 2023-02-03 | 2024-12-04 | Level 2 | Standards change
122503870 | insulator and brushing | Non-HFTD | Transmission | 2021-12-19 | 2022-12-19 | Level 2 | E | 2024-07-25 | 2024-12-19 | Level 2 | GO 165 Inspection
122509848 | splice | Non-HFTD | Transmission | 2021-12-21 | 2022-12-21 | Level 2 | E | 2024-10-28 | 2022-06-21 | Level 2 | GO 165 Inspection
122511412 | other | Non-HFTD | Transmission | 2021-12-22 | 2023-12-22 | Level 3 | F | 2024-07-09 | 2026-12-22 | Level 3 | GO 165 Inspection
122534001 | insulator and brushing | Non-HFTD | Transmission | 2021-12-31 | 2022-12-31 | Level 2 | E | 2024-10-10 | 2024-12-31 | Level 2 | GO 165 Inspection
122558487 | conductor | Non-HFTD | Transmission | 2022-01-06 | 2023-01-06 | Level 2 | E | 2024-10-22 | 2025-01-06 | Level 2 | GO 165 Inspection
122573449 | insulator and brushing | Non-HFTD | Transmission | 2022-01-08 | 2023-01-08 | Level 2 | E | 2024-08-17 | 2025-01-08 | Level 2 | GO 165 Inspection
122573492 | insulator and brushing | Non-HFTD | Transmission | 2022-01-08 | 2023-01-08 | Level 2 | E | 2024-10-15 | 2025-01-08 | Level 2 | GO 165 Inspection
122578047 | insulator and brushing | Non-HFTD | Transmission | 2022-01-09 | 2023-01-09 | Level 2 | E | 2024-10-15 | 2025-01-09 | Level 2 | GO 165 Inspection
122774798 | insulator and brushing | Non-HFTD | Transmission | 2022-01-19 | 2023-01-19 | Level 2 | E | 2023-10-03 | 2025-01-19 | Level 2 | Standards change
122775800 | pole | Non-HFTD | Transmission | 2021-12-11 | 2022-12-11 | Level 2 | E | 2023-11-09 | 2024-12-11 | Level 2 | Standards change
122786320 | pole | Non-HFTD | Transmission | 2021-12-18 | 2022-12-18 | Level 2 | E | 2023-11-10 | 2024-12-18 | Level 2 | Standards change
122790596 | other | Non-HFTD | Transmission | 2022-01-22 | 2025-01-22 | Level 2 | E | 2024-08-29 | 2023-01-22 | Level 2 | GO 165 Inspection
122890762 | other | Non-HFTD | Transmission | 2022-01-27 | 2023-01-27 | Level 2 | E | 2023-01-26 | 2027-01-27 | Level 3 | Standards change
122917743 | pole | HFTD Tier 3 | Transmission | 2022-02-02 | 2024-02-02 | Level 3 | F | 2024-03-13 | 2027-02-02 | Level 3 | GO 165 Inspection
122918421 | pole | HFTD Tier 2 | Transmission | 2022-02-02 | 2024-02-02 | Level 3 | F | 2024-03-14 | 2027-02-02 | Level 3 | GO 165 Inspection
122920451 | other | Non-HFTD | Transmission | 2022-02-03 | 2023-02-03 | Level 2 | E | 2023-02-13 | 2027-02-03 | Level 3 | Standards change
122922326 | other | Non-HFTD | Transmission | 2022-02-03 | 2024-02-03 | Level 3 | F | 2024-04-06 | 2027-02-03 | Level 3 | Standards change
122924576 | pole | HFTD Tier 3 | Transmission | 2022-02-04 | 2024-02-04 | Level 3 | F | 2024-03-15 | 2027-02-04 | Level 3 | GO 165 Inspection
122926217 | other | HFTD Tier 3 | Transmission | 2022-01-27 | 2024-01-27 | Level 3 | F | 2024-04-06 | 2027-01-27 | Level 3 | Standards change
122926291 | crossarm | Non-HFTD | Transmission | 2022-02-04 | 2023-02-04 | Level 2 | E | 2024-02-16 | 2025-02-04 | Level 2 | Standards change
122942676 | pole | Non-HFTD | Transmission | 2022-02-07 | 2023-02-07 | Level 2 | E | 2023-09-18 | 2025-02-07 | Level 2 | GO 165 Inspection
122942833 | other | Non-HFTD | Transmission | 2022-02-07 | 2023-02-07 | Level 2 | E | 2023-11-30 | 2027-02-07 | Level 3 | Standards change
122945677 | other | Non-HFTD | Transmission | 2022-02-08 | 2024-02-08 | Level 3 | F | 2024-02-01 | 2027-02-08 | Level 3 | GO 165 Inspection
122947468 | other | Non-HFTD | Transmission | 2022-02-08 | 2024-02-08 | Level 3 | F | 2024-09-23 | 2027-02-08 | Level 3 | GO 165 Inspection
122950459 | other | Non-HFTD | Transmission | 2022-02-07 | 2023-02-07 | Level 2 | E | 2023-01-31 | 2025-02-07 | Level 2 | Standards change
122950696 | anchor/guy | Non-HFTD | Transmission | 2022-02-09 | 2024-02-09 | Level 3 | F | 2024-09-30 | 2027-02-09 | Level 3 | GO 165 Inspection
122950707 | anchor/guy | Non-HFTD | Transmission | 2022-02-09 | 2023-02-09 | Level 2 | E | 2024-09-30 | 2027-02-09 | Level 3 | GO 165 Inspection
122951344 | pole | HFTD Tier 2 | Transmission | 2022-02-07 | 2024-02-07 | Level 3 | F | 2024-03-27 | 2027-02-07 | Level 3 | GO 165 Inspection
122951408 | pole | Non-HFTD | Transmission | 2022-02-07 | 2024-02-07 | Level 3 | F | 2023-12-28 | 2027-02-07 | Level 3 | Standards change
122951664 | pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2024-02-05 | Level 3 | F | 2024-03-19 | 2027-02-05 | Level 3 | GO 165 Inspection
122952175 | pole | HFTD Tier 3 | Transmission | 2022-02-05 | 2024-02-05 | Level 3 | F | 2024-03-11 | 2027-02-05 | Level 3 | GO 165 Inspection
122952419 | other | HFTD Tier 2 | Transmission | 2022-02-08 | 2024-02-08 | Level 3 | F | 2024-03-18 | 2027-02-08 | Level 3 | GO 165 Inspection
122952492 | pole | Non-HFTD | Transmission | 2022-02-07 | 2024-02-07 | Level 3 | F | 2023-12-28 | 2027-02-07 | Level 3 | Standards change
122952509 | insulator and brushing | Non-HFTD | Transmission | 2022-02-08 | 2023-02-08 | Level 2 | E | 2024-03-19 | 2025-02-08 | Level 2 | GO 165 Inspection
122952524 | other | Non-HFTD | Transmission | 2022-02-08 | 2024-02-08 | Level 3 | F | 2023-01-31 | 2027-02-08 | Level 3 | Standards change
122966723 | pole | Non-HFTD | Transmission | 2022-02-10 | 2023-02-10 | Level 2 | E | 2023-01-25 | 2025-02-10 | Level 2 | Standards change
122966945 | other | Non-HFTD | Transmission | 2022-02-10 | 2023-02-10 | Level 2 | E | 2023-03-15 | 2025-02-10 | Level 2 | Standards change
122966981 | insulator and brushing | Non-HFTD | Transmission | 2022-02-10 | 2023-02-10 | Level 2 | E | 2023-01-31 | 2025-02-10 | Level 2 | Standards change
122969898 | anchor/guy | Non-HFTD | Transmission | 2022-02-11 | 2023-02-11 | Level 2 | E | 2024-01-19 | 2027-02-11 | Level 3 | Standards change
122971418 | insulator and brushing | Non-HFTD | Transmission | 2022-02-11 | 2023-02-11 | Level 2 | E | 2024-09-26 | 2025-02-11 | Level 2 | GO 165 Inspection
122971470 | pole | Non-HFTD | Transmission | 2022-02-11 | 2023-02-11 | Level 2 | E | 2024-09-13 | 2025-02-11 | Level 2 | GO 165 Inspection
122977512 | pole | Non-HFTD | Transmission | 2022-02-12 | 2023-02-12 | Level 2 | E | 2024-10-07 | 2025-02-12 | Level 2 | GO 165 Inspection
122977872 | other | Non-HFTD | Transmission | 2022-02-12 | 2024-02-12 | Level 3 | F | 2024-10-05 | 2027-02-12 | Level 3 | GO 165 Inspection
122979022 | other | Non-HFTD | Transmission | 2022-02-12 | 2024-02-12 | Level 3 | F | 2024-04-06 | 2027-02-12 | Level 3 | Standards change
122979062 | pole | Non-HFTD | Transmission | 2022-02-13 | 2023-02-13 | Level 2 | E | 2024-07-24 | 2025-02-13 | Level 2 | GO 165 Inspection
122985939 | other | Non-HFTD | Transmission | 2022-02-10 | 2024-02-10 | Level 3 | F | 2024-04-11 | 2027-02-10 | Level 3 | GO 165 Inspection
122986101 | other | HFTD Tier 2 | Transmission | 2022-02-11 | 2024-02-11 | Level 3 | F | 2024-04-06 | 2027-02-11 | Level 3 | Standards change
122987930 | pole | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2023-01-25 | 2025-02-16 | Level 2 | Standards change
122988866 | insulator and brushing | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-01-17 | 2025-02-16 | Level 2 | Standards change
122989201 | insulator and brushing | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-09-24 | 2025-02-16 | Level 2 | GO 165 Inspection
122989219 | pole | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-04-17 | 2025-02-16 | Level 2 | GO 165 Inspection
122989374 | insulator and brushing | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-09-24 | 2025-02-16 | Level 2 | GO 165 Inspection
122989375 | insulator and brushing | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-09-24 | 2025-02-16 | Level 2 | GO 165 Inspection
122990280 | insulator and brushing | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-09-13 | 2022-05-16 | Level 2 | GO 165 Inspection
122992411 | insulator and brushing | Non-HFTD | Transmission | 2022-02-15 | 2023-02-15 | Level 2 | E | 2024-10-28 | 2025-02-15 | Level 2 | GO 165 Inspection
122993378 | anchor/guy | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2024-01-31 | 2027-02-17 | Level 3 | GO 165 Inspection
122993471 | insulator and brushing | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2024-09-24 | 2025-02-17 | Level 2 | GO 165 Inspection
122993520 | pole | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2024-01-31 | 2025-02-17 | Level 2 | GO 165 Inspection
122993616 | pole | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2023-02-02 | 2027-02-17 | Level 3 | Standards change
122993981 | other | Non-HFTD | Transmission | 2022-02-16 | 2024-02-16 | Level 3 | F | 2023-12-28 | 2027-02-16 | Level 3 | Standards change
122994195 | insulator and brushing | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2024-11-13 | 2025-02-17 | Level 2 | Standards change
122994199 | pole | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2023-12-28 | 2027-02-17 | Level 3 | Standards change
122994350 | insulator and brushing | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2024-10-08 | 2025-02-17 | Level 2 | GO 165 Inspection
122998954 | insulator and brushing | Non-HFTD | Transmission | 2022-02-10 | 2023-02-10 | Level 2 | E | 2023-02-15 | 2027-02-10 | Level 3 | Standards change
123001170 | other | Non-HFTD | Transmission | 2022-02-15 | 2024-02-15 | Level 3 | F | 2024-01-19 | 2027-02-15 | Level 3 | Standards change
123001173 | other | Non-HFTD | Transmission | 2022-02-15 | 2024-02-15 | Level 3 | F | 2024-01-19 | 2027-02-15 | Level 3 | Standards change
123001761 | other | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2023-01-31 | 2025-02-16 | Level 2 | Standards change
123002805 | insulator and brushing | Non-HFTD | Transmission | 2022-02-22 | 2023-02-22 | Level 2 | E | 2024-07-18 | 2025-02-22 | Level 2 | GO 165 Inspection
123002980 | pole | HFTD Tier 2 | Transmission | 2022-02-22 | 2024-02-22 | Level 3 | F | 2024-06-07 | 2027-02-22 | Level 3 | GO 165 Inspection
123003031 | other | Non-HFTD | Transmission | 2022-02-16 | 2024-02-16 | Level 3 | F | 2023-12-28 | 2027-02-16 | Level 3 | Standards change
123003169 | insulator and brushing | Non-HFTD | Transmission | 2022-02-16 | 2023-02-16 | Level 2 | E | 2024-08-30 | 2025-02-16 | Level 2 | GO 165 Inspection
123003201 | other | Non-HFTD | Transmission | 2022-02-11 | 2024-02-11 | Level 3 | F | 2023-12-28 | 2027-02-11 | Level 3 | Standards change
123004095 | other | Non-HFTD | Transmission | 2022-02-14 | 2024-02-14 | Level 3 | F | 2023-12-28 | 2027-02-14 | Level 3 | Standards change
123006671 | other | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2023-02-03 | 2025-02-17 | Level 2 | Standards change
123008442 | other | Non-HFTD | Transmission | 2022-02-23 | 2024-02-23 | Level 3 | F | 2024-04-16 | 2027-02-23 | Level 3 | GO 165 Inspection
123008696 | anchor/guy | Non-HFTD | Transmission | 2022-02-23 | 2024-02-23 | Level 3 | F | 2023-05-24 | 2027-02-23 | Level 3 | Standards change
123009679 | other | Non-HFTD | Transmission | 2022-02-18 | 2023-02-18 | Level 2 | E | 2023-03-16 | 2025-02-18 | Level 2 | Standards change
123009882 | pole | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2023-02-03 | 2027-02-17 | Level 3 | Standards change
123017460 | other | HFTD Tier 2 | Transmission | 2022-02-15 | 2024-02-15 | Level 3 | F | 2024-05-31 | 2027-02-15 | Level 3 | GO 165 Inspection
123017837 | other | Non-HFTD | Transmission | 2022-02-23 | 2024-02-23 | Level 3 | F | 2023-12-29 | 2027-02-23 | Level 3 | Standards change
123017897 | insulator and brushing | Non-HFTD | Transmission | 2022-02-23 | 2023-02-23 | Level 2 | E | 2023-01-27 | 2025-02-23 | Level 2 | Standards change
123017998 | pole | Non-HFTD | Transmission | 2022-02-24 | 2023-02-24 | Level 2 | E | 2024-02-07 | 2025-02-24 | Level 2 | GO 165 Inspection
123018040 | pole | Non-HFTD | Transmission | 2022-02-24 | 2023-02-24 | Level 2 | E | 2024-01-31 | 2025-02-24 | Level 2 | GO 165 Inspection
123019329 | other | Non-HFTD | Transmission | 2022-02-24 | 2023-02-24 | Level 2 | E | 2024-01-16 | 2027-02-24 | Level 3 | Standards change
123020545 | other | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2023-12-29 | 2027-02-17 | Level 3 | Standards change
123024148 | other | Non-HFTD | Transmission | 2022-02-24 | 2023-02-24 | Level 2 | E | 2023-03-24 | 2025-02-24 | Level 2 | Standards change
123024312 | other | Non-HFTD | Transmission | 2022-02-24 | 2023-02-24 | Level 2 | E | 2023-02-15 | 2027-02-24 | Level 3 | Standards change
123026479 | insulator and brushing | Non-HFTD | Transmission | 2022-02-18 | 2023-02-18 | Level 2 | E | 2023-03-13 | 2025-02-18 | Level 2 | Standards change
123027030 | other | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2023-12-29 | 2027-02-17 | Level 3 | Standards change
123027886 | other | Non-HFTD | Transmission | 2022-02-18 | 2024-02-18 | Level 3 | F | 2023-04-12 | 2027-02-18 | Level 3 | Standards change
123028108 | other | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2023-12-29 | 2027-02-17 | Level 3 | Standards change
123028522 | anchor/guy | Non-HFTD | Transmission | 2022-02-25 | 2025-02-25 | Level 2 | E | 2024-05-02 | 2023-02-25 | Level 2 | GO 165 Inspection
123028652 | anchor/guy | Non-HFTD | Transmission | 2022-02-25 | 2025-02-25 | Level 2 | E | 2024-05-02 | 2023-02-25 | Level 2 | GO 165 Inspection
123028971 | pole | Non-HFTD | Transmission | 2022-02-25 | 2023-02-25 | Level 2 | E | 2023-02-13 | 2025-02-25 | Level 2 | Standards change
123029672 | insulator and brushing | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2023-02-15 | 2025-02-17 | Level 2 | Standards change
123029890 | other | Non-HFTD | Transmission | 2022-02-18 | 2023-02-18 | Level 2 | E | 2023-03-16 | 2027-02-18 | Level 3 | Standards change
123031100 | anchor/guy | Non-HFTD | Transmission | 2022-02-26 | 2023-02-26 | Level 2 | E | 2024-05-03 | 2025-02-26 | Level 2 | GO 165 Inspection
123032516 | other | Non-HFTD | Transmission | 2022-02-25 | 2023-02-25 | Level 2 | E | 2023-03-24 | 2025-02-25 | Level 2 | Standards change
123032677 | other | Non-HFTD | Transmission | 2022-02-28 | 2023-02-28 | Level 2 | E | 2023-02-10 | 2025-02-28 | Level 2 | Standards change
123033127 | other | Non-HFTD | Transmission | 2022-02-22 | 2024-02-22 | Level 3 | F | 2024-01-16 | 2027-02-22 | Level 3 | Standards change
123033230 | other | Non-HFTD | Transmission | 2022-02-17 | 2024-02-17 | Level 3 | F | 2024-10-28 | 2027-02-17 | Level 3 | GO 165 Inspection
123033253 | pole | Non-HFTD | Transmission | 2022-02-17 | 2023-02-17 | Level 2 | E | 2024-10-28 | 2025-02-17 | Level 2 | GO 165 Inspection
123033521 | pole | Non-HFTD | Transmission | 2022-02-25 | 2023-02-25 | Level 2 | E | 2024-08-01 | 2025-02-25 | Level 2 | GO 165 Inspection
123033630 | insulator and brushing | Non-HFTD | Transmission | 2022-02-28 | 2023-02-28 | Level 2 | E | 2024-11-19 | 2025-02-28 | Level 2 | GO 165 Inspection
123033686 | other | Non-HFTD | Transmission | 2022-02-28 | 2023-02-28 | Level 2 | E | 2023-07-06 | 2025-02-28 | Level 2 | Field Safety Reassessment
123033712 | other | HFTD Tier 2 | Transmission | 2022-02-28 | 2024-02-28 | Level 3 | F | 2024-04-22 | 2027-02-28 | Level 3 | GO 165 Inspection
123033943 | other | Non-HFTD | Transmission | 2022-02-23 | 2025-02-23 | Level 2 | E | 2024-05-13 | 2027-02-23 | Level 3 | GO 165 Inspection
123033975 | pole | Non-HFTD | Transmission | 2022-02-28 | 2023-02-28 | Level 2 | E | 2023-08-02 | 2025-02-28 | Level 2 | Standards change
123034446 | other | Non-HFTD | Transmission | 2022-02-24 | 2023-02-24 | Level 2 | E | 2023-03-24 | 2025-02-24 | Level 2 | Standards change
123035532 | other | Non-HFTD | Transmission | 2022-02-24 | 2024-02-24 | Level 3 | F | 2024-01-16 | 2027-02-24 | Level 3 | Standards change
123035860 | other | Non-HFTD | Transmission | 2022-03-01 | 2024-03-01 | Level 3 | F | 2023-10-26 | 2025-03-01 | Level 2 | Standards change
123037277 | other | Non-HFTD | Transmission | 2022-03-01 | 2023-03-01 | Level 2 | E | 2023-12-29 | 2025-03-01 | Level 2 | Standards change
123037820 | other | Non-HFTD | Transmission | 2021-10-20 | 2023-10-20 | Level 3 | F | 2024-04-06 | 2026-10-20 | Level 3 | Standards change
123043824 | other | Non-HFTD | Transmission | 2022-03-02 | 2024-03-02 | Level 3 | F | 2024-06-20 | 2027-03-02 | Level 3 | GO 165 Inspection
123044108 | other | Non-HFTD | Transmission | 2022-03-02 | 2024-03-02 | Level 3 | F | 2024-08-19 | 2027-03-02 | Level 3 | GO 165 Inspection
123044592 | other | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2024-05-29 | 2025-03-02 | Level 2 | GO 165 Inspection
123046393 | other | Non-HFTD | Transmission | 2022-03-02 | 2024-03-02 | Level 3 | F | 2024-06-15 | 2027-03-02 | Level 3 | GO 165 Inspection
123047119 | other | Non-HFTD | Transmission | 2022-03-01 | 2025-03-01 | Level 2 | E | 2023-03-10 | 2023-03-01 | Level 2 | Standards change
123047396 | insulator and brushing | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2023-03-03 | 2025-03-03 | Level 2 | Standards change
123048501 | pole | Non-HFTD | Transmission | 2022-03-03 | 2025-03-03 | Level 2 | E | 2024-07-16 | 2023-03-03 | Level 2 | GO 165 Inspection
123048515 | insulator and brushing | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2023-03-09 | 2025-03-02 | Level 2 | Standards change
123049176 | other | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2024-01-31 | 2025-03-03 | Level 2 | GO 165 Inspection
123049370 | insulator and brushing | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2024-02-15 | 2025-03-02 | Level 2 | GO 165 Inspection
123054019 | pole | Non-HFTD | Transmission | 2022-03-04 | 2023-03-04 | Level 2 | E | 2024-01-31 | 2025-03-04 | Level 2 | GO 165 Inspection
123054440 | pole | Non-HFTD | Transmission | 2022-03-04 | 2023-03-04 | Level 2 | E | 2023-02-03 | 2025-03-04 | Level 2 | Standards change
123055195 | other | Non-HFTD | Transmission | 2022-03-04 | 2023-03-04 | Level 2 | E | 2024-02-21 | 2025-03-04 | Level 2 | GO 165 Inspection
123055198 | insulator and brushing | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2024-02-14 | 2025-03-02 | Level 2 | GO 165 Inspection
123055212 | insulator and brushing | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2023-05-03 | 2025-03-03 | Level 2 | GO 165 Inspection
123055218 | insulator and brushing | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2023-05-24 | 2025-03-03 | Level 2 | GO 165 Inspection
123055219 | other | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2024-01-30 | 2027-03-03 | Level 3 | GO 165 Inspection
123055241 | other | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2024-01-16 | 2025-03-03 | Level 2 | Standards change
123055452 | pole | HFTD Tier 2 | Transmission | 2022-02-28 | 2024-02-28 | Level 3 | F | 2024-04-04 | 2027-02-28 | Level 3 | GO 165 Inspection
123057455 | pole | Non-HFTD | Transmission | 2022-03-04 | 2023-03-04 | Level 2 | E | 2023-02-03 | 2025-03-04 | Level 2 | Standards change
123057631 | insulator and brushing | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2023-03-09 | 2025-03-07 | Level 2 | Standards change
123058028 | anchor/guy | HFTD Tier 2 | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2024-05-21 | 2023-03-07 | Level 2 | GO 165 Inspection
123059931 | other | HFTD Tier 2 | Transmission | 2022-03-05 | 2024-03-05 | Level 3 | F | 2023-05-17 | 2027-03-05 | Level 3 | Standards change
123061434 | other | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2024-06-20 | 2025-03-07 | Level 2 | GO 165 Inspection
123061492 | pole | HFTD Tier 2 | Transmission | 2022-02-28 | 2024-02-28 | Level 3 | F | 2024-04-04 | 2027-02-28 | Level 3 | GO 165 Inspection
123062071 | other | HFTD Tier 2 | Transmission | 2022-03-04 | 2024-03-04 | Level 3 | F | 2023-05-05 | 2027-03-04 | Level 3 | Standards change
123067339 | other | HFTD Tier 2 | Transmission | 2022-03-07 | 2024-03-07 | Level 3 | F | 2023-07-06 | 2027-03-07 | Level 3 | Standards change
123071257 | other | Non-HFTD | Transmission | 2022-03-09 | 2024-03-09 | Level 3 | F | 2024-05-01 | 2027-03-09 | Level 3 | GO 165 Inspection
123072250 | pole | Non-HFTD | Transmission | 2022-03-09 | 2023-03-09 | Level 2 | E | 2023-05-03 | 2025-03-09 | Level 2 | Standards change
123072502 | other | Non-HFTD | Transmission | 2022-03-08 | 2023-03-08 | Level 2 | E | 2023-03-13 | 2025-03-08 | Level 2 | Standards change
123084847 | anchor/guy | Non-HFTD | Transmission | 2022-03-08 | 2023-03-08 | Level 2 | E | 2023-03-14 | 2027-03-08 | Level 3 | Standards change
123086307 | other | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2024-01-16 | 2025-03-02 | Level 2 | Standards change
123086457 | other | Non-HFTD | Transmission | 2022-03-10 | 2023-03-10 | Level 2 | E | 2024-10-21 | 2025-03-10 | Level 2 | GO 165 Inspection
123086486 | insulator and brushing | Non-HFTD | Transmission | 2022-03-08 | 2023-03-08 | Level 2 | E | 2024-10-22 | 2025-03-08 | Level 2 | GO 165 Inspection
123086488 | insulator and brushing | Non-HFTD | Transmission | 2022-03-08 | 2023-03-08 | Level 2 | E | 2024-10-22 | 2025-03-08 | Level 2 | GO 165 Inspection
123087917 | anchor/guy | Non-HFTD | Transmission | 2022-03-10 | 2023-03-10 | Level 2 | E | 2024-05-30 | 2025-03-10 | Level 2 | GO 165 Inspection
123090003 | insulator and brushing | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2023-03-09 | 2025-03-02 | Level 2 | Standards change
123090053 | insulator and brushing | Non-HFTD | Transmission | 2022-03-09 | 2023-03-09 | Level 2 | E | 2023-03-13 | 2025-03-09 | Level 2 | Standards change
123090059 | other | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2024-03-22 | 2027-03-03 | Level 3 | GO 165 Inspection
123090366 | pole | HFTD Tier 2 | Transmission | 2022-03-10 | 2024-03-10 | Level 3 | F | 2024-04-29 | 2027-03-10 | Level 3 | GO 165 Inspection
123090715 | other | Non-HFTD | Transmission | 2022-03-08 | 2023-03-08 | Level 2 | E | 2024-01-08 | 2027-03-08 | Level 3 | Standards change
123091370 | insulator and brushing | Non-HFTD | Transmission | 2022-03-05 | 2023-03-05 | Level 2 | E | 2023-03-13 | 2025-03-05 | Level 2 | Standards change
123091774 | other | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2023-02-16 | 2027-03-07 | Level 3 | Standards change
123091854 | insulator and brushing | Non-HFTD | Transmission | 2022-03-09 | 2023-03-09 | Level 2 | E | 2024-10-24 | 2025-03-09 | Level 2 | GO 165 Inspection
123092072 | other | Non-HFTD | Transmission | 2022-03-11 | 2023-03-11 | Level 2 | E | 2024-07-01 | 2025-03-11 | Level 2 | GO 165 Inspection
123092373 | other | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2024-03-06 | 2025-03-02 | Level 2 | GO 165 Inspection
123092808 | other | Non-HFTD | Transmission | 2022-03-03 | 2024-03-03 | Level 3 | F | 2024-03-22 | 2027-03-03 | Level 3 | GO 165 Inspection
123092861 | insulator and brushing | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2024-03-22 | 2025-03-03 | Level 2 | GO 165 Inspection
123092978 | anchor/guy | Non-HFTD | Transmission | 2022-03-04 | 2023-03-04 | Level 2 | E | 2024-09-06 | 2025-03-04 | Level 2 | GO 165 Inspection
123093260 | other | Non-HFTD | Transmission | 2022-03-08 | 2023-03-08 | Level 2 | E | 2024-10-04 | 2027-03-08 | Level 3 | GO 165 Inspection
123093558 | anchor/guy | Non-HFTD | Transmission | 2022-03-09 | 2023-03-09 | Level 2 | E | 2024-09-12 | 2027-03-09 | Level 3 | GO 165 Inspection
123094073 | pole | Non-HFTD | Transmission | 2022-03-12 | 2023-03-12 | Level 2 | E | 2024-08-13 | 2025-03-12 | Level 2 | Field Safety Reassessment
123094074 | pole | Non-HFTD | Transmission | 2022-03-12 | 2023-03-12 | Level 2 | E | 2024-08-13 | 2025-03-12 | Level 2 | Field Safety Reassessment
123094222 | insulator and brushing | Non-HFTD | Transmission | 2022-03-05 | 2023-03-05 | Level 2 | E | 2023-03-10 | 2025-03-05 | Level 2 | Standards change
123094272 | insulator and brushing | Non-HFTD | Transmission | 2022-03-10 | 2023-03-10 | Level 2 | E | 2023-04-26 | 2025-03-10 | Level 2 | GO 165 Inspection
123098261 | other | HFTD Tier 2 | Transmission | 2022-03-11 | 2024-03-11 | Level 3 | F | 2024-04-30 | 2027-03-11 | Level 3 | GO 165 Inspection
123099254 | other | HFTD Tier 2 | Transmission | 2022-03-11 | 2027-03-11 | Level 3 | F | 2024-04-25 | 2023-03-11 | Level 2 | GO 165 Inspection
123099695 | other | HFTD Tier 2 | Transmission | 2022-03-11 | 2024-03-11 | Level 3 | F | 2024-04-06 | 2027-03-11 | Level 3 | Standards change
123100649 | other | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2024-01-10 | 2025-03-07 | Level 2 | Standards change
123100740 | insulator and brushing | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2023-03-10 | 2025-03-07 | Level 2 | Standards change
123100744 | insulator and brushing | Non-HFTD | Transmission | 2022-03-12 | 2023-03-12 | Level 2 | E | 2023-03-13 | 2025-03-12 | Level 2 | GO 165 Inspection
123100843 | anchor/guy | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2024-01-08 | 2027-03-07 | Level 3 | Standards change
123101190 | insulator and brushing | Non-HFTD | Transmission | 2022-03-12 | 2023-03-12 | Level 2 | E | 2023-05-01 | 2025-03-12 | Level 2 | GO 165 Inspection
123101193 | insulator and brushing | Non-HFTD | Transmission | 2022-03-12 | 2023-03-12 | Level 2 | E | 2023-03-09 | 2025-03-12 | Level 2 | Standards change
123101932 | anchor/guy | Non-HFTD | Transmission | 2022-03-14 | 2023-03-14 | Level 2 | E | 2024-02-15 | 2027-03-14 | Level 3 | GO 165 Inspection
123101934 | insulator and brushing | Non-HFTD | Transmission | 2022-03-14 | 2023-03-14 | Level 2 | E | 2024-02-15 | 2025-03-14 | Level 2 | GO 165 Inspection
123102786 | other | Non-HFTD | Transmission | 2022-03-15 | 2023-03-15 | Level 2 | E | 2023-01-25 | 2025-03-15 | Level 2 | Standards change
123104094 | pole | Non-HFTD | Transmission | 2022-03-15 | 2023-03-15 | Level 2 | E | 2023-04-11 | 2025-03-15 | Level 2 | Standards change
123106102 | other | Non-HFTD | Transmission | 2022-03-16 | 2024-03-16 | Level 3 | F | 2023-03-17 | 2027-03-16 | Level 3 | Standards change
123106217 | insulator and brushing | Non-HFTD | Transmission | 2022-03-16 | 2023-03-16 | Level 2 | E | 2023-03-17 | 2025-03-16 | Level 2 | Standards change
123107413 | other | Non-HFTD | Transmission | 2022-03-16 | 2023-03-16 | Level 2 | E | 2024-07-15 | 2025-03-16 | Level 2 | GO 165 Inspection
123107572 | other | HFTD Tier 2 | Transmission | 2022-03-10 | 2024-03-10 | Level 3 | F | 2023-03-02 | 2027-03-10 | Level 3 | Standards change
123107788 | other | HFTD Tier 2 | Transmission | 2022-03-16 | 2024-03-16 | Level 3 | F | 2023-02-21 | 2027-03-16 | Level 3 | Standards change
123108462 | other | Non-HFTD | Transmission | 2022-03-16 | 2023-03-16 | Level 2 | E | 2024-07-15 | 2025-03-16 | Level 2 | GO 165 Inspection
123112674 | insulator and brushing | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-07-12 | 2025-03-17 | Level 2 | GO 165 Inspection
123112948 | insulator and brushing | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-07-12 | 2025-03-17 | Level 2 | GO 165 Inspection
123145074 | insulator and brushing | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-07-11 | 2025-03-17 | Level 2 | GO 165 Inspection
123145483 | pole | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2023-03-03 | 2025-03-17 | Level 2 | Standards change
123145503 | other | HFTD Tier 2 | Transmission | 2022-03-08 | 2024-03-08 | Level 3 | F | 2024-05-02 | 2027-03-08 | Level 3 | GO 165 Inspection
123149466 | other | Non-HFTD | Transmission | 2022-03-09 | 2024-03-09 | Level 3 | F | 2023-12-26 | 2027-03-09 | Level 3 | Standards change
123149469 | insulator and brushing | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2023-02-13 | 2025-03-17 | Level 2 | Standards change
123149536 | other | Non-HFTD | Transmission | 2022-03-10 | 2024-03-10 | Level 3 | F | 2024-01-16 | 2027-03-10 | Level 3 | Standards change
123150024 | anchor/guy | Non-HFTD | Transmission | 2022-03-10 | 2023-03-10 | Level 2 | E | 2024-08-13 | 2027-03-10 | Level 3 | GO 165 Inspection
123150029 | anchor/guy | Non-HFTD | Transmission | 2022-03-10 | 2023-03-10 | Level 2 | E | 2024-08-13 | 2027-03-10 | Level 3 | GO 165 Inspection
123150259 | anchor/guy | Non-HFTD | Transmission | 2022-03-10 | 2023-03-10 | Level 2 | E | 2023-08-09 | 2027-03-10 | Level 3 | Standards change
123152023 | insulator and brushing | Non-HFTD | Transmission | 2022-03-18 | 2023-03-18 | Level 2 | E | 2024-07-11 | 2025-03-18 | Level 2 | GO 165 Inspection
123152186 | other | HFTD Tier 2 | Transmission | 2022-03-11 | 2024-03-11 | Level 3 | F | 2024-04-06 | 2027-03-11 | Level 3 | Standards change
123152662 | pole | Non-HFTD | Transmission | 2022-03-18 | 2023-03-18 | Level 2 | E | 2023-03-07 | 2025-03-18 | Level 2 | Standards change
123155122 | other | HFTD Tier 2 | Transmission | 2022-03-15 | 2024-03-15 | Level 3 | F | 2023-01-24 | 2027-03-15 | Level 3 | Standards change
123155932 | pole | HFTD Tier 2 | Transmission | 2022-03-15 | 2024-03-15 | Level 3 | F | 2024-05-09 | 2027-03-15 | Level 3 | GO 165 Inspection
123156040 | insulator and brushing | Non-HFTD | Transmission | 2022-03-18 | 2023-03-18 | Level 2 | E | 2024-05-30 | 2025-03-18 | Level 2 | GO 165 Inspection
123158655 | insulator and brushing | Non-HFTD | Transmission | 2022-03-14 | 2023-03-14 | Level 2 | E | 2023-03-09 | 2025-03-14 | Level 2 | Standards change
123159119 | insulator and brushing | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-07-11 | 2025-03-21 | Level 2 | GO 165 Inspection
123159220 | pole | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-11-06 | 2025-03-21 | Level 2 | GO 165 Inspection
123159528 | other | Non-HFTD | Transmission | 2022-03-21 | 2025-03-21 | Level 2 | E | 2024-07-11 | 2027-03-21 | Level 3 | GO 165 Inspection
123159667 | other | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-10-29 | 2025-03-21 | Level 2 | GO 165 Inspection
123161547 | insulator and brushing | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-07-10 | 2025-03-21 | Level 2 | GO 165 Inspection
123162440 | other | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-07-10 | 2027-03-21 | Level 3 | GO 165 Inspection
123162505 | insulator and brushing | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-09-12 | 2025-03-21 | Level 2 | GO 165 Inspection
123162889 | pole | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-07-11 | 2025-03-21 | Level 2 | GO 165 Inspection
123164461 | anchor/guy | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-02-15 | 2025-03-17 | Level 2 | GO 165 Inspection
123165174 | pole | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2023-03-03 | 2025-03-22 | Level 2 | Standards change
123165501 | anchor/guy | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-11-05 | 2025-03-22 | Level 2 | GO 165 Inspection
123165972 | pole | Non-HFTD | Transmission | 2022-03-12 | 2023-03-12 | Level 2 | E | 2023-08-10 | 2025-03-12 | Level 2 | GO 165 Inspection
123166217 | pole | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2023-03-03 | 2025-03-22 | Level 2 | Standards change
123166644 | insulator and brushing | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-07-10 | 2025-03-22 | Level 2 | GO 165 Inspection
123167351 | other | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-12-30 | 2025-03-22 | Level 2 | Field Safety Reassessment
123170597 | anchor/guy | Non-HFTD | Transmission | 2022-03-23 | 2023-03-23 | Level 2 | E | 2023-03-01 | 2027-03-23 | Level 3 | Standards change
123172165 | pole | Non-HFTD | Transmission | 2022-03-23 | 2023-03-23 | Level 2 | E | 2023-03-03 | 2025-03-23 | Level 2 | Standards change
123172191 | pole | Non-HFTD | Transmission | 2022-03-23 | 2023-03-23 | Level 2 | E | 2023-01-20 | 2025-03-23 | Level 2 | Standards change
123172305 | other | Non-HFTD | Transmission | 2022-03-23 | 2023-03-23 | Level 2 | E | 2024-06-20 | 2027-03-23 | Level 3 | GO 165 Inspection
123172362 | other | Non-HFTD | Transmission | 2022-03-23 | 2024-03-23 | Level 3 | F | 2024-04-06 | 2027-03-23 | Level 3 | Standards change
123173788 | other | HFTD Tier 2 | Transmission | 2022-03-15 | 2024-03-15 | Level 3 | F | 2024-04-24 | 2027-03-15 | Level 3 | GO 165 Inspection
123176299 | pole | Non-HFTD | Transmission | 2022-03-23 | 2023-03-23 | Level 2 | E | 2023-02-03 | 2025-03-23 | Level 2 | Standards change
123176353 | other | Non-HFTD | Transmission | 2022-03-23 | 2025-03-23 | Level 2 | E | 2024-10-18 | 2023-03-23 | Level 2 | GO 165 Inspection
123176926 | insulator and brushing | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-06-15 | 2025-03-17 | Level 2 | GO 165 Inspection
123176984 | insulator and brushing | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-04-23 | 2025-03-22 | Level 2 | GO 165 Inspection
123178199 | insulator and brushing | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-07-09 | 2025-03-24 | Level 2 | GO 165 Inspection
123180108 | anchor/guy | HFTD Tier 2 | Transmission | 2022-03-24 | 2024-03-24 | Level 3 | F | 2024-05-20 | 2027-03-24 | Level 3 | GO 165 Inspection
123180250 | insulator and brushing | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-07-09 | 2025-03-24 | Level 2 | GO 165 Inspection
123180750 | other | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-06-26 | 2025-03-17 | Level 2 | GO 165 Inspection
123180867 | pole | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2023-03-03 | 2025-03-24 | Level 2 | Standards change
123180876 | pole | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2023-03-03 | 2025-03-24 | Level 2 | Standards change
123181092 | insulator and brushing | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-11-13 | 2025-03-24 | Level 2 | GO 165 Inspection
123182206 | insulator and brushing | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-07-09 | 2025-03-24 | Level 2 | GO 165 Inspection
123183709 | other | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-07-09 | 2025-03-24 | Level 2 | GO 165 Inspection
123184460 | pole | HFTD Tier 2 | Transmission | 2022-03-15 | 2024-03-15 | Level 3 | F | 2024-05-09 | 2027-03-15 | Level 3 | GO 165 Inspection
123184704 | other | HFTD Tier 2 | Transmission | 2022-03-11 | 2024-03-11 | Level 3 | F | 2023-02-24 | 2027-03-11 | Level 3 | Standards change
123184842 | insulator and brushing | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-04-23 | 2025-03-22 | Level 2 | GO 165 Inspection
123185077 | insulator and brushing | Non-HFTD | Transmission | 2022-03-17 | 2023-03-17 | Level 2 | E | 2024-02-22 | 2025-03-17 | Level 2 | GO 165 Inspection
123185512 | other | Non-HFTD | Transmission | 2022-03-21 | 2024-03-21 | Level 3 | F | 2024-06-27 | 2027-03-21 | Level 3 | GO 165 Inspection
123186875 | anchor/guy | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-06-27 | 2027-03-21 | Level 3 | GO 165 Inspection
123187045 | insulator and brushing | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2023-03-13 | 2025-03-21 | Level 2 | GO 165 Inspection
123187205 | insulator and brushing | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-10-21 | 2025-03-22 | Level 2 | GO 165 Inspection
123187361 | insulator and brushing | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2023-03-09 | 2025-03-22 | Level 2 | GO 165 Inspection
123187862 | pole | Non-HFTD | Transmission | 2022-03-25 | 2023-03-25 | Level 2 | E | 2023-03-03 | 2025-03-25 | Level 2 | Standards change
123187868 | pole | Non-HFTD | Transmission | 2022-03-25 | 2023-03-25 | Level 2 | E | 2023-03-03 | 2025-03-25 | Level 2 | Standards change
123188314 | pole | Non-HFTD | Transmission | 2022-03-25 | 2023-03-25 | Level 2 | E | 2024-11-02 | 2025-03-25 | Level 2 | GO 165 Inspection
123188398 | other | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-03-15 | 2023-03-21 | Level 2 | GO 165 Inspection
123189038 | anchor/guy | Non-HFTD | Transmission | 2022-03-25 | 2023-03-25 | Level 2 | E | 2024-07-09 | 2025-03-25 | Level 2 | GO 165 Inspection
123189141 | pole | Non-HFTD | Transmission | 2022-03-25 | 2023-03-25 | Level 2 | E | 2023-03-03 | 2025-03-25 | Level 2 | Standards change
123189150 | other | Non-HFTD | Transmission | 2022-03-21 | 2024-03-21 | Level 3 | F | 2024-06-26 | 2027-03-21 | Level 3 | GO 165 Inspection
123189156 | other | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-04-30 | 2025-03-22 | Level 2 | GO 165 Inspection
123189333 | anchor/guy | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-06-15 | 2025-03-21 | Level 2 | GO 165 Inspection
123189336 | other | Non-HFTD | Transmission | 2022-03-21 | 2024-03-21 | Level 3 | F | 2024-06-15 | 2027-03-21 | Level 3 | GO 165 Inspection
123189676 | pole | HFTD Tier 2 | Transmission | 2022-03-16 | 2024-03-16 | Level 3 | F | 2024-05-03 | 2027-03-16 | Level 3 | GO 165 Inspection
123189961 | other | Non-HFTD | Transmission | 2022-03-22 | 2024-03-22 | Level 3 | F | 2024-04-02 | 2027-03-22 | Level 3 | GO 165 Inspection
123190037 | insulator and brushing | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-04-29 | 2025-03-21 | Level 2 | GO 165 Inspection
123190988 | other | HFTD Tier 2 | Transmission | 2022-03-10 | 2024-03-10 | Level 3 | F | 2024-05-03 | 2027-03-10 | Level 3 | GO 165 Inspection
123191351 | anchor/guy | Non-HFTD | Transmission | 2022-03-25 | 2023-03-25 | Level 2 | E | 2024-11-02 | 2025-03-25 | Level 2 | GO 165 Inspection
123192523 | other | Non-HFTD | Transmission | 2022-03-24 | 2024-03-24 | Level 3 | F | 2024-06-27 | 2027-03-24 | Level 3 | GO 165 Inspection
123193121 | pole | HFTD Tier 2 | Transmission | 2022-03-19 | 2024-03-19 | Level 3 | F | 2024-04-26 | 2027-03-19 | Level 3 | GO 165 Inspection
123196339 | other | HFTD Tier 2 | Transmission | 2022-03-11 | 2024-03-11 | Level 3 | F | 2024-04-06 | 2027-03-11 | Level 3 | Standards change
123196431 | other | Non-HFTD | Transmission | 2022-03-21 | 2024-03-21 | Level 3 | F | 2024-01-04 | 2027-03-21 | Level 3 | Standards change
123196438 | pole | HFTD Tier 2 | Transmission | 2022-03-14 | 2024-03-14 | Level 3 | F | 2024-05-22 | 2027-03-14 | Level 3 | GO 165 Inspection
123196715 | anchor/guy | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-03-21 | 2025-03-24 | Level 2 | GO 165 Inspection
123196750 | insulator and brushing | Non-HFTD | Transmission | 2022-03-24 | 2023-03-24 | Level 2 | E | 2024-03-21 | 2025-03-24 | Level 2 | GO 165 Inspection
123196755 | insulator and brushing | Non-HFTD | Transmission | 2022-03-21 | 2027-03-21 | Level 2 | E | 2024-04-29 | 2022-06-21 | Level 2 | GO 165 Inspection
123197096 | pole | HFTD Tier 2 | Transmission | 2022-03-17 | 2024-03-17 | Level 3 | F | 2024-03-21 | 2027-03-17 | Level 3 | GO 165 Inspection
123197519 | anchor/guy | Non-HFTD | Transmission | 2022-03-23 | 2024-03-23 | Level 3 | F | 2024-04-16 | 2027-03-23 | Level 3 | GO 165 Inspection
123198111 | other | Non-HFTD | Transmission | 2022-03-26 | 2023-03-26 | Level 2 | E | 2024-02-08 | 2025-03-26 | Level 2 | GO 165 Inspection
123201294 | other | Non-HFTD | Transmission | 2022-03-26 | 2023-03-26 | Level 2 | E | 2024-02-12 | 2025-03-26 | Level 2 | Standards change
123202911 | pole | Non-HFTD | Transmission | 2022-03-28 | 2023-03-28 | Level 2 | E | 2023-03-09 | 2025-03-28 | Level 2 | Standards change
123205692 | insulator and brushing | Non-HFTD | Transmission | 2022-03-29 | 2023-03-29 | Level 2 | E | 2024-07-16 | 2025-03-29 | Level 2 | GO 165 Inspection
123210003 | other | HFTD Tier 2 | Transmission | 2022-03-22 | 2024-03-22 | Level 3 | F | 2024-04-06 | 2027-03-22 | Level 3 | Standards change
123210285 | pole | HFTD Tier 2 | Transmission | 2022-03-23 | 2024-03-23 | Level 3 | F | 2024-04-06 | 2027-03-23 | Level 3 | GO 165 Inspection
123210630 | pole | HFTD Tier 2 | Transmission | 2022-03-23 | 2024-03-23 | Level 3 | F | 2024-05-02 | 2027-03-23 | Level 3 | GO 165 Inspection
123211305 | other | HFTD Tier 2 | Transmission | 2022-03-22 | 2024-03-22 | Level 3 | F | 2024-04-06 | 2027-03-22 | Level 3 | Standards change
123211566 | other | HFTD Tier 2 | Transmission | 2022-03-25 | 2024-03-25 | Level 3 | F | 2024-04-17 | 2027-03-25 | Level 3 | GO 165 Inspection
123213398 | pole | Non-HFTD | Transmission | 2022-03-30 | 2023-03-30 | Level 2 | E | 2024-10-31 | 2025-03-30 | Level 2 | GO 165 Inspection
123213687 | anchor/guy | Non-HFTD | Transmission | 2022-03-30 | 2024-03-30 | Level 3 | F | 2023-04-22 | 2027-03-30 | Level 3 | Standards change
123213881 | other | HFTD Tier 2 | Transmission | 2022-03-18 | 2024-03-18 | Level 3 | F | 2024-05-02 | 2027-03-18 | Level 3 | GO 165 Inspection
123214750 | insulator and brushing | Non-HFTD | Transmission | 2022-03-30 | 2023-03-30 | Level 2 | E | 2024-06-26 | 2025-03-30 | Level 2 | GO 165 Inspection
123214751 | pole | Non-HFTD | Transmission | 2022-03-30 | 2023-03-30 | Level 2 | E | 2024-01-03 | 2025-03-30 | Level 2 | Standards change
123215545 | other | HFTD Tier 2 | Transmission | 2022-03-30 | 2024-03-30 | Level 3 | F | 2023-02-21 | 2027-03-30 | Level 3 | Standards change
123216200 | other | HFTD Tier 2 | Transmission | 2022-03-30 | 2024-03-30 | Level 3 | F | 2024-04-03 | 2027-03-30 | Level 3 | GO 165 Inspection
123216314 | insulator and brushing | Non-HFTD | Transmission | 2022-03-30 | 2023-03-30 | Level 2 | E | 2023-03-17 | 2025-03-30 | Level 2 | Standards change
123217000 | other | HFTD Tier 2 | Transmission | 2022-03-17 | 2024-03-17 | Level 3 | F | 2023-03-10 | 2027-03-17 | Level 3 | Standards change
123217570 | other | Non-HFTD | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2023-07-13 | 2027-03-31 | Level 3 | Standards change
123217698 | pole | Non-HFTD | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2024-08-15 | 2027-03-31 | Level 3 | GO 165 Inspection
123217850 | other | Non-HFTD | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2023-03-20 | 2027-03-31 | Level 3 | Standards change
123221139 | pole | Non-HFTD | Transmission | 2022-03-31 | 2023-03-31 | Level 2 | E | 2024-07-10 | 2025-03-31 | Level 2 | GO 165 Inspection
123222670 | pole | HFTD Tier 2 | Transmission | 2022-03-18 | 2024-03-18 | Level 3 | F | 2023-04-10 | 2027-03-18 | Level 3 | GO 165 Inspection
123222825 | other | HFTD Tier 2 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2023-02-27 | 2027-03-28 | Level 3 | Standards change
123223118 | other | Non-HFTD | Transmission | 2022-03-21 | 2023-03-21 | Level 2 | E | 2024-04-01 | 2027-03-21 | Level 3 | GO 165 Inspection
123223207 | pole | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-06-04 | 2025-03-22 | Level 2 | GO 165 Inspection
123223279 | other | HFTD Tier 2 | Transmission | 2022-03-24 | 2024-03-24 | Level 3 | F | 2023-06-20 | 2027-03-24 | Level 3 | Standards change
123223398 | other | Non-HFTD | Transmission | 2022-03-22 | 2023-03-22 | Level 2 | E | 2024-04-23 | 2025-03-22 | Level 2 | GO 165 Inspection
123225546 | other | Non-HFTD | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2024-06-20 | 2027-03-31 | Level 3 | GO 165 Inspection
123226002 | other | Non-HFTD | Transmission | 2022-03-30 | 2024-03-30 | Level 3 | F | 2024-06-26 | 2027-03-30 | Level 3 | GO 165 Inspection
123227099 | other | HFTD Tier 2 | Transmission | 2022-03-29 | 2024-03-29 | Level 3 | F | 2024-04-11 | 2027-03-29 | Level 3 | GO 165 Inspection
123230202 | other | HFTD Tier 3 | Transmission | 2022-03-23 | 2027-03-23 | Level 3 | F |  | 2027-03-23 | Level 3
123231273 | anchor/guy | HFTD Tier 2 | Transmission | 2022-03-23 | 2024-03-23 | Level 3 | F | 2024-04-16 | 2027-03-23 | Level 3 | GO 165 Inspection
123231275 | other | HFTD Tier 3 | Transmission | 2022-03-29 | 2024-03-29 | Level 3 | F | 2024-04-09 | 2027-03-29 | Level 3 | GO 165 Inspection
123235090 | other | HFTD Tier 3 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2024-04-06 | 2027-03-28 | Level 3 | Standards change
123235769 | pole | HFTD Tier 2 | Transmission | 2022-03-30 | 2024-03-30 | Level 3 | F | 2024-03-27 | 2027-03-30 | Level 3 | GO 165 Inspection
123237186 | other | HFTD Tier 2 | Transmission | 2022-03-24 | 2024-03-24 | Level 3 | F | 2024-04-18 | 2027-03-24 | Level 3 | GO 165 Inspection
123237839 | anchor/guy | Non-HFTD | Transmission | 2022-04-03 | 2023-04-03 | Level 2 | E | 2024-07-16 | 2027-04-03 | Level 3 | GO 165 Inspection
123238546 | other | Non-HFTD | Transmission | 2022-04-04 | 2025-04-04 | Level 2 | E | 2024-07-29 | 2022-10-04 | Level 2 | GO 165 Inspection
123239879 | anchor/guy | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2024-10-29 | 2025-04-04 | Level 2 | GO 165 Inspection
123241053 | other | HFTD Tier 2 | Transmission | 2022-03-25 | 2024-03-25 | Level 3 | F | 2024-05-16 | 2027-03-25 | Level 3 | GO 165 Inspection
123241389 | pole | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2024-08-29 | 2023-04-04 | Level 2 | GO 165 Inspection
123241479 | insulator and brushing | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2024-11-04 | 2022-07-04 | Level 2 | Field Safety Reassessment
123242050 | other | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2024-08-15 | 2025-04-04 | Level 2 | GO 165 Inspection
123243564 | pole | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2023-02-06 | 2025-04-04 | Level 2 | Standards change
123245379 | other | HFTD Tier 2 | Transmission | 2022-03-23 | 2024-03-23 | Level 3 | F | 2024-03-18 | 2027-03-23 | Level 3 | GO 165 Inspection
123246307 | other | HFTD Tier 2 | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2024-05-10 | 2027-03-31 | Level 3 | GO 165 Inspection
123247399 | pole | Non-HFTD | Transmission | 2022-04-05 | 2023-04-05 | Level 2 | E | 2024-03-11 | 2025-04-05 | Level 2 | GO 165 Inspection
123247852 | anchor/guy | Non-HFTD | Transmission | 2022-04-05 | 2024-04-05 | Level 3 | F | 2024-05-30 | 2027-04-05 | Level 3 | GO 165 Inspection
123249241 | other | Non-HFTD | Transmission | 2022-04-05 | 2024-04-05 | Level 3 | F | 2023-06-07 | 2027-04-05 | Level 3 | Standards change
123250088 | other | HFTD Tier 2 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2024-06-11 | 2027-03-28 | Level 3 | GO 165 Inspection
123250977 | insulator and brushing | Non-HFTD | Transmission | 2022-04-05 | 2022-07-05 | Level 2 | E | 2024-08-19 | 2022-07-05 | Level 2 | GO 165 Inspection
123251201 | other | HFTD Tier 3 | Transmission | 2022-04-05 | 2024-04-05 | Level 3 | F | 2024-04-06 | 2027-04-05 | Level 3 | Standards change
123256584 | pole | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2023-03-07 | 2025-04-06 | Level 2 | Standards change
123257283 | insulator and brushing | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2023-01-10 | 2025-04-06 | Level 2 | Standards change
123257755 | anchor/guy | HFTD Tier 2 | Transmission | 2022-04-06 | 2024-04-06 | Level 3 | F | 2024-04-10 | 2027-04-06 | Level 3 | GO 165 Inspection
123260232 | other | HFTD Tier 2 | Transmission | 2022-04-06 | 2024-04-06 | Level 3 | F | 2024-06-07 | 2027-04-06 | Level 3 | GO 165 Inspection
123260521 | other | HFTD Tier 2 | Transmission | 2022-03-25 | 2024-03-25 | Level 3 | F | 2024-04-17 | 2027-03-25 | Level 3 | GO 165 Inspection
123261434 | insulator and brushing | Non-HFTD | Transmission | 2022-04-07 | 2023-04-07 | Level 2 | E | 2024-02-08 | 2025-04-07 | Level 2 | Standards change
123264208 | insulator and brushing | Non-HFTD | Transmission | 2022-04-07 | 2023-04-07 | Level 2 | E | 2023-03-16 | 2025-04-07 | Level 2 | Field Safety Reassessment
123267090 | pole | Non-HFTD | Transmission | 2022-04-07 | 2023-04-07 | Level 2 | E | 2023-03-07 | 2025-04-07 | Level 2 | Standards change
123267091 | pole | Non-HFTD | Transmission | 2022-04-07 | 2023-04-07 | Level 2 | E | 2023-03-07 | 2025-04-07 | Level 2 | Standards change
123269053 | insulator and brushing | Non-HFTD | Transmission | 2022-04-01 | 2023-04-01 | Level 2 | E | 2023-03-09 | 2025-04-01 | Level 2 | GO 165 Inspection
123269402 | pole | Non-HFTD | Transmission | 2022-04-01 | 2025-04-01 | Level 2 | E | 2024-10-25 | 2023-04-01 | Level 2 | GO 165 Inspection
123269403 | other | Non-HFTD | Transmission | 2022-04-01 | 2023-04-01 | Level 2 | E | 2024-10-25 | 2025-04-01 | Level 2 | GO 165 Inspection
123269517 | other | Non-HFTD | Transmission | 2022-03-30 | 2023-03-30 | Level 2 | E | 2024-04-02 | 2025-03-30 | Level 2 | GO 165 Inspection
123269656 | insulator and brushing | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2024-03-29 | 2025-04-04 | Level 2 | GO 165 Inspection
123269722 | anchor/guy | Non-HFTD | Transmission | 2022-03-29 | 2024-03-29 | Level 3 | F | 2024-04-16 | 2027-03-29 | Level 3 | GO 165 Inspection
123269773 | other | HFTD Tier 2 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2024-05-31 | 2027-03-28 | Level 3 | GO 165 Inspection
123269911 | other | HFTD Tier 2 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2024-06-06 | 2027-03-28 | Level 3 | GO 165 Inspection
123269991 | other | HFTD Tier 2 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2024-05-31 | 2027-03-28 | Level 3 | GO 165 Inspection
123274900 | other | HFTD Tier 2 | Transmission | 2022-03-28 | 2024-03-28 | Level 3 | F | 2023-01-27 | 2027-03-28 | Level 3 | Standards change
123279079 | insulator and brushing | Non-HFTD | Transmission | 2022-04-08 | 2023-04-08 | Level 2 | E | 2024-10-17 | 2025-04-08 | Level 2 | GO 165 Inspection
123279868 | pole | Non-HFTD | Transmission | 2022-04-09 | 2024-04-09 | Level 3 | F | 2023-12-29 | 2027-04-09 | Level 3 | Standards change
123280915 | pole | HFTD Tier 3 | Transmission | 2022-04-09 | 2024-04-09 | Level 3 | F | 2024-04-06 | 2027-04-09 | Level 3 | GO 165 Inspection
123294114 | pole | Non-HFTD | Transmission | 2022-04-10 | 2023-04-10 | Level 2 | E | 2024-10-24 | 2025-04-10 | Level 2 | GO 165 Inspection
123294461 | insulator and brushing | Non-HFTD | Transmission | 2022-04-10 | 2023-04-10 | Level 2 | E | 2024-06-25 | 2025-04-10 | Level 2 | GO 165 Inspection
123294991 | insulator and brushing | Non-HFTD | Transmission | 2022-04-07 | 2023-04-07 | Level 2 | E | 2024-07-09 | 2025-04-07 | Level 2 | GO 165 Inspection
123297718 | pole | HFTD Tier 2 | Transmission | 2022-04-11 | 2024-04-11 | Level 3 | F | 2024-06-03 | 2027-04-11 | Level 3 | GO 165 Inspection
123300297 | other | Non-HFTD | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2024-06-20 | 2027-03-31 | Level 3 | GO 165 Inspection
123300417 | insulator and brushing | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2024-01-31 | 2025-04-06 | Level 2 | GO 165 Inspection
123300466 | other | Non-HFTD | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2024-06-17 | 2027-03-31 | Level 3 | GO 165 Inspection
123300510 | anchor/guy | Non-HFTD | Transmission | 2022-03-31 | 2023-03-31 | Level 2 | E | 2024-01-08 | 2027-03-31 | Level 3 | Standards change
123300709 | other | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2023-03-13 | 2027-04-04 | Level 3 | Standards change
123300805 | other | HFTD Tier 2 | Transmission | 2022-04-04 | 2024-04-04 | Level 3 | F | 2023-05-19 | 2027-04-04 | Level 3 | Standards change
123300853 | insulator and brushing | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2024-07-01 | 2025-04-06 | Level 2 | GO 165 Inspection
123301024 | insulator and brushing | Non-HFTD | Transmission | 2022-04-01 | 2023-04-01 | Level 2 | E | 2023-03-09 | 2025-04-01 | Level 2 | Standards change
123301052 | anchor/guy | Non-HFTD | Transmission | 2022-04-01 | 2023-04-01 | Level 2 | E | 2024-02-21 | 2025-04-01 | Level 2 | GO 165 Inspection
123301722 | anchor/guy | Non-HFTD | Transmission | 2022-04-12 | 2023-04-12 | Level 2 | E | 2023-12-12 | 2027-04-12 | Level 3 | Standards change
123312116 | other | Non-HFTD | Transmission | 2022-04-12 | 2024-04-12 | Level 3 | F | 2024-01-08 | 2025-04-12 | Level 2 | Standards change
123313011 | anchor/guy | Non-HFTD | Transmission | 2022-04-12 | 2023-04-12 | Level 2 | E | 2024-01-18 | 2027-04-12 | Level 3 | Standards change
123313642 | anchor/guy | Non-HFTD | Transmission | 2022-04-01 | 2023-04-01 | Level 2 | E | 2024-04-01 | 2025-04-01 | Level 2 | GO 165 Inspection
123313795 | other | HFTD Tier 2 | Transmission | 2022-03-29 | 2024-03-29 | Level 3 | F | 2023-01-23 | 2027-03-29 | Level 3 | Standards change
123313920 | other | HFTD Tier 3 | Transmission | 2022-04-05 | 2024-04-05 | Level 3 | F | 2023-04-26 | 2027-04-05 | Level 3 | Standards change
123316047 | other | Non-HFTD | Transmission | 2022-04-13 | 2024-04-13 | Level 3 | F | 2024-04-06 | 2027-04-13 | Level 3 | Standards change
123316874 | other | HFTD Tier 2 | Transmission | 2022-04-05 | 2024-04-05 | Level 3 | F | 2024-04-15 | 2027-04-05 | Level 3 | GO 165 Inspection
123317489 | other | Non-HFTD | Transmission | 2022-04-13 | 2024-04-13 | Level 3 | F | 2024-04-06 | 2027-04-13 | Level 3 | Standards change
123318357 | anchor/guy | Non-HFTD | Transmission | 2022-04-13 | 2023-04-13 | Level 2 | E | 2024-01-25 | 2027-04-13 | Level 3 | Standards change
123319580 | insulator and brushing | Non-HFTD | Transmission | 2021-04-07 | 2022-04-07 | Level 2 | E | 2024-12-10 | 2024-04-07 | Level 2 | GO 165 Inspection
123321066 | other | Non-HFTD | Transmission | 2022-04-13 | 2024-04-13 | Level 3 | F | 2023-01-18 | 2027-04-13 | Level 3 | Standards change
123321579 | other | HFTD Tier 3 | Transmission | 2022-04-04 | 2024-04-04 | Level 3 | F | 2024-04-06 | 2027-04-04 | Level 3 | Standards change
123321967 | pole | Non-HFTD | Transmission | 2022-04-13 | 2023-04-13 | Level 2 | E | 2024-08-14 | 2025-04-13 | Level 2 | GO 165 Inspection
123323054 | anchor/guy | Non-HFTD | Transmission | 2022-04-13 | 2023-04-13 | Level 2 | E | 2024-01-25 | 2027-04-13 | Level 3 | Standards change
123324386 | anchor/guy | Non-HFTD | Transmission | 2022-04-13 | 2023-04-13 | Level 2 | E | 2023-01-13 | 2025-04-13 | Level 2 | Standards change
123325892 | pole | HFTD Tier 3 | Transmission | 2022-03-31 | 2024-03-31 | Level 3 | F | 2024-05-31 | 2027-03-31 | Level 3 | GO 165 Inspection
123325955 | other | HFTD Tier 2 | Transmission | 2022-04-07 | 2024-04-07 | Level 3 | F | 2024-04-06 | 2027-04-07 | Level 3 | Standards change
123330027 | pole | HFTD Tier 3 | Transmission | 2022-04-08 | 2024-04-08 | Level 3 | F | 2024-05-17 | 2027-04-08 | Level 3 | GO 165 Inspection
123332477 | anchor/guy | Non-HFTD | Transmission | 2022-04-04 | 2023-04-04 | Level 2 | E | 2024-03-29 | 2025-04-04 | Level 2 | GO 165 Inspection
123334569 | other | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2023-01-18 | 2025-04-15 | Level 2 | Standards change
123337188 | other | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2023-01-18 | 2025-04-15 | Level 2 | Standards change
123338097 | insulator and brushing | Non-HFTD | Transmission | 2022-04-01 | 2023-04-01 | Level 2 | E | 2023-03-09 | 2025-04-01 | Level 2 | GO 165 Inspection
123338377 | splice | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2023-12-27 | 2025-04-15 | Level 2 | Standards change
123338784 | pole | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2024-04-25 | 2025-04-15 | Level 2 | GO 165 Inspection
123339213 | other | Non-HFTD | Transmission | 2022-04-15 | 2024-04-15 | Level 3 | F | 2023-01-26 | 2027-04-15 | Level 3 | Standards change
123339591 | other | Non-HFTD | Transmission | 2022-04-15 | 2024-04-15 | Level 3 | F | 2024-08-15 | 2027-04-15 | Level 3 | GO 165 Inspection
123339751 | pole | HFTD Tier 2 | Transmission | 2022-04-08 | 2024-04-08 | Level 3 | F | 2024-04-18 | 2027-04-08 | Level 3 | GO 165 Inspection
123339778 | anchor/guy | Non-HFTD | Transmission | 2022-04-15 | 2025-04-15 | Level 2 | E | 2024-09-06 | 2027-04-15 | Level 3 | GO 165 Inspection
123339858 | other | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2023-01-18 | 2025-04-15 | Level 2 | Standards change
123341196 | other | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2024-08-14 | 2025-04-15 | Level 2 | GO 165 Inspection
123341197 | pole | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2024-08-14 | 2025-04-15 | Level 2 | GO 165 Inspection
123342566 | insulator and brushing | Non-HFTD | Transmission | 2022-04-14 | 2023-04-14 | Level 2 | E | 2024-08-19 | 2025-04-14 | Level 2 | GO 165 Inspection
123343089 | other | Non-HFTD | Transmission | 2022-04-16 | 2024-04-16 | Level 3 | F | 2024-01-03 | 2027-04-16 | Level 3 | Standards change
123343510 | pole | Non-HFTD | Transmission | 2022-04-16 | 2024-04-16 | Level 3 | F | 2023-04-24 | 2027-04-16 | Level 3 | Standards change
123343687 | other | Non-HFTD | Transmission | 2022-04-16 | 2023-04-16 | Level 2 | E | 2023-01-17 | 2025-04-16 | Level 2 | Standards change
123346500 | other | HFTD Tier 2 | Transmission | 2022-04-06 | 2024-04-06 | Level 3 | F | 2023-06-07 | 2027-04-06 | Level 3 | Standards change
123346849 | other | HFTD Tier 2 | Transmission | 2022-04-11 | 2024-04-11 | Level 3 | F | 2022-12-22 | 2027-04-11 | Level 3 | Standards change
123354397 | insulator and brushing | Non-HFTD | Transmission | 2022-04-18 | 2023-04-18 | Level 2 | E | 2023-03-24 | 2025-04-18 | Level 2 | Standards change
123354514 | anchor/guy | HFTD Tier 2 | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-01-08 | 2027-04-18 | Level 3 | Standards change
123355925 | other | Non-HFTD | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-01-09 | 2027-04-18 | Level 3 | Standards change
123355966 | pole | Non-HFTD | Transmission | 2022-04-18 | 2023-04-18 | Level 2 | E | 2023-01-20 | 2025-04-18 | Level 2 | Standards change
123356873 | other | Non-HFTD | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2023-12-29 | 2027-04-18 | Level 3 | Standards change
123358718 | other | Non-HFTD | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2023-02-02 | 2027-04-18 | Level 3 | Standards change
123359540 | other | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2024-01-31 | 2025-04-06 | Level 2 | GO 165 Inspection
123359705 | other | HFTD Tier 2 | Transmission | 2022-04-13 | 2024-04-13 | Level 3 | F | 2024-06-10 | 2027-04-13 | Level 3 | GO 165 Inspection
123360909 | other | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2023-02-21 | 2025-04-19 | Level 2 | Standards change
123362566 | other | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2024-09-11 | 2027-04-19 | Level 3 | GO 165 Inspection
123363001 | crossarm | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2024-01-18 | 2025-04-19 | Level 2 | Standards change
123363015 | other | Non-HFTD | Transmission | 2022-04-19 | 2024-04-19 | Level 3 | F | 2023-06-30 | 2027-04-19 | Level 3 | Standards change
123363086 | crossarm | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2023-01-30 | 2025-04-19 | Level 2 | Standards change
123363242 | pole | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2023-01-20 | 2025-04-19 | Level 2 | Standards change
123364084 | pole | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2023-02-28 | 2025-04-19 | Level 2 | Standards change
123365700 | pole | Non-HFTD | Transmission | 2022-04-15 | 2023-04-15 | Level 2 | E | 2023-03-24 | 2025-04-15 | Level 2 | Standards change
123366124 | other | Non-HFTD | Transmission | 2022-04-19 | 2023-04-19 | Level 2 | E | 2024-05-28 | 2025-04-19 | Level 2 | GO 165 Inspection
123367283 | other | HFTD Tier 2 | Transmission | 2022-04-19 | 2024-04-19 | Level 3 | F | 2024-04-20 | 2027-04-19 | Level 3 | GO 165 Inspection
123367479 | pole | HFTD Tier 2 | Transmission | 2022-04-14 | 2024-04-14 | Level 3 | F | 2024-02-02 | 2027-04-14 | Level 3 | GO 165 Inspection
123370354 | other | HFTD Tier 2 | Transmission | 2022-04-14 | 2024-04-14 | Level 3 | F | 2024-04-23 | 2027-04-14 | Level 3 | GO 165 Inspection
123371246 | other | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2024-01-31 | 2025-04-06 | Level 2 | GO 165 Inspection
123373397 | pole | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-01-20 | 2025-04-20 | Level 2 | Standards change
123373942 | anchor/guy | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-12-26 | 2027-04-20 | Level 3 | Standards change
123375738 | other | HFTD Tier 2 | Transmission | 2022-04-20 | 2024-04-20 | Level 3 | F | 2024-04-06 | 2027-04-20 | Level 3 | Standards change
123376073 | other | HFTD Tier 2 | Transmission | 2022-04-05 | 2024-04-05 | Level 3 | F | 2024-04-06 | 2027-04-05 | Level 3 | Standards change
123376926 | pole | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2024-09-09 | 2025-04-20 | Level 2 | GO 165 Inspection
123377435 | insulator and brushing | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-03-01 | 2025-04-20 | Level 2 | Standards change
123377472 | pole | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-01-19 | 2025-04-20 | Level 2 | Standards change
123379711 | pole | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-09-19 | 2027-04-20 | Level 3 | Field Safety Reassessment
123380007 | insulator and brushing | Non-HFTD | Transmission | 2022-04-06 | 2023-04-06 | Level 2 | E | 2023-03-09 | 2025-04-06 | Level 2 | Standards change
123380375 | pole | HFTD Tier 2 | Transmission | 2022-04-13 | 2024-04-13 | Level 3 | F | 2024-05-20 | 2027-04-13 | Level 3 | GO 165 Inspection
123381830 | other | HFTD Tier 2 | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-05-24 | 2027-04-18 | Level 3 | GO 165 Inspection
123383266 | splice | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-02-23 | 2025-04-21 | Level 2 | Standards change
123383528 | other | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-01-19 | 2025-04-21 | Level 2 | Standards change
123386706 | insulator and brushing | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-03-01 | 2025-04-21 | Level 2 | Standards change
123386739 | pole | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-07-25 | 2025-04-21 | Level 2 | Standards change
123386909 | pole | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-03-07 | 2025-04-21 | Level 2 | Standards change
123390555 | other | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-02-07 | 2025-04-21 | Level 2 | Standards change
123392302 | pole | Non-HFTD | Transmission | 2022-04-22 | 2023-04-22 | Level 2 | E | 2023-01-19 | 2027-04-22 | Level 3 | Standards change
123394118 | insulator and brushing | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-02-27 | 2025-04-20 | Level 2 | Standards change
123394455 | other | HFTD Tier 3 | Transmission | 2022-04-19 | 2024-04-19 | Level 3 | F | 2024-05-07 | 2027-04-19 | Level 3 | GO 165 Inspection
123394593 | pole | Non-HFTD | Transmission | 2022-04-22 | 2023-04-22 | Level 2 | E | 2023-02-17 | 2025-04-22 | Level 2 | Standards change
123394677 | pole | HFTD Tier 3 | Transmission | 2022-04-22 | 2024-04-22 | Level 3 | F | 2024-05-28 | 2027-04-22 | Level 3 | GO 165 Inspection
123394952 | other | Non-HFTD | Transmission | 2022-04-22 | 2024-04-22 | Level 3 | F | 2024-04-06 | 2027-04-22 | Level 3 | Standards change
123395184 | other | Non-HFTD | Transmission | 2022-04-22 | 2023-04-22 | Level 2 | E | 2023-02-17 | 2025-04-22 | Level 2 | Standards change
123396195 | other | HFTD Tier 2 | Transmission | 2022-04-07 | 2024-04-07 | Level 3 | F | 2023-03-15 | 2027-04-07 | Level 3 | Standards change
123396314 | other | Non-HFTD | Transmission | 2022-04-22 | 2023-04-22 | Level 2 | E | 2024-04-25 | 2025-04-22 | Level 2 | GO 165 Inspection
123397193 | insulator and brushing | Non-HFTD | Transmission | 2022-04-22 | 2023-04-22 | Level 2 | E | 2023-01-12 | 2025-04-22 | Level 2 | Standards change
123401766 | other | HFTD Tier 2 | Transmission | 2022-04-23 | 2024-04-23 | Level 3 | F | 2023-05-20 | 2027-04-23 | Level 3 | Standards change
123401861 | pole | Non-HFTD | Transmission | 2022-04-23 | 2025-04-23 | Level 2 | E | 2024-06-05 | 2023-04-23 | Level 2 | GO 165 Inspection
123402485 | insulator and brushing | Non-HFTD | Transmission | 2022-04-23 | 2023-04-23 | Level 2 | E | 2024-08-22 | 2025-04-23 | Level 2 | GO 165 Inspection
123402928 | anchor/guy | Non-HFTD | Transmission | 2022-04-23 | 2023-04-23 | Level 2 | E | 2024-05-06 | 2025-04-23 | Level 2 | GO 165 Inspection
123403527 | insulator and brushing | Non-HFTD | Transmission | 2022-04-20 | 2027-04-20 | Level 2 | E | 2024-07-10 | 2025-04-20 | Level 2 | GO 165 Inspection
123403869 | anchor/guy | Non-HFTD | Transmission | 2022-04-23 | 2023-04-23 | Level 2 | E | 2023-09-07 | 2027-04-23 | Level 3 | Standards change
123405338 | other | Non-HFTD | Transmission | 2022-04-23 | 2027-04-23 | Level 2 | E | 2024-05-07 | 2023-04-23 | Level 2 | GO 165 Inspection
123406104 | insulator and brushing | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-07-11 | 2025-04-25 | Level 2 | GO 165 Inspection
123406383 | other | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-02-10 | 2025-04-25 | Level 2 | GO 165 Inspection
123406667 | insulator and brushing | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-04-09 | 2025-04-25 | Level 2 | GO 165 Inspection
123406690 | other | Non-HFTD | Transmission | 2022-04-22 | 2023-04-22 | Level 2 | E | 2024-11-25 | 2027-04-22 | Level 3 | GO 165 Inspection
123407200 | other | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-02-10 | 2025-04-25 | Level 2 | GO 165 Inspection
123408049 | other | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-04-09 | 2025-04-25 | Level 2 | GO 165 Inspection
123409628 | insulator and brushing | Non-HFTD | Transmission | 2022-04-11 | 2023-04-11 | Level 2 | E | 2024-07-10 | 2025-04-11 | Level 2 | GO 165 Inspection
123412383 | other | Non-HFTD | Transmission | 2022-04-25 | 2024-04-25 | Level 3 | F | 2024-11-27 | 2027-04-25 | Level 3 | GO 165 Inspection
123417671 | other | Non-HFTD | Transmission | 2022-04-25 | 2024-04-25 | Level 3 | F | 2024-05-04 | 2027-04-25 | Level 3 | GO 165 Inspection
123422070 | other | Non-HFTD | Transmission | 2022-04-25 | 2025-04-25 | Level 2 | E | 2024-10-23 | 2023-04-25 | Level 2 | GO 165 Inspection
123422128 | other | Non-HFTD | Transmission | 2022-04-26 | 2023-04-26 | Level 2 | E | 2023-08-28 | 2027-04-26 | Level 3 | Field Safety Reassessment
123422586 | insulator and brushing | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-11-21 | 2025-04-25 | Level 2 | GO 165 Inspection
123424019 | pole | Non-HFTD | Transmission | 2022-04-26 | 2023-04-26 | Level 2 | E | 2024-09-23 | 2025-04-26 | Level 2 | GO 165 Inspection
123425239 | other | Non-HFTD | Transmission | 2022-04-26 | 2024-04-26 | Level 3 | F | 2024-04-06 | 2027-04-26 | Level 3 | Standards change
123430964 | other | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-10-11 | 2027-04-25 | Level 3 | GO 165 Inspection
123431110 | other | Non-HFTD | Transmission | 2022-04-25 | 2025-04-25 | Level 2 | E | 2024-11-21 | 2027-04-25 | Level 3 | GO 165 Inspection
123432044 | other | Non-HFTD | Transmission | 2022-04-26 | 2022-07-26 | Level 2 | B | 2023-02-13 | 2025-04-26 | Level 2 | Standards change
123433296 | insulator and brushing | Non-HFTD | Transmission | 2022-04-26 | 2023-04-26 | Level 2 | E | 2024-10-21 | 2025-04-26 | Level 2 | GO 165 Inspection
123433299 | other | Non-HFTD | Transmission | 2022-04-26 | 2024-04-26 | Level 3 | F | 2024-10-31 | 2027-04-26 | Level 3 | GO 165 Inspection
123434048 | other | Non-HFTD | Transmission | 2022-04-25 | 2025-04-25 | Level 2 | E | 2024-11-21 | 2027-04-25 | Level 3 | GO 165 Inspection
123434888 | insulator and brushing | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2023-01-26 | 2025-04-27 | Level 2 | Standards change
123435103 | pole | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2023-03-02 | 2025-04-27 | Level 2 | Standards change
123435282 | insulator and brushing | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2024-08-15 | 2025-04-27 | Level 2 | GO 165 Inspection
123437145 | pole | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2023-02-27 | 2025-04-27 | Level 2 | Standards change
123438790 | insulator and brushing | Non-HFTD | Transmission | 2022-04-25 | 2025-04-25 | Level 2 | E | 2024-10-18 | 2027-04-25 | Level 3 | GO 165 Inspection
123439922 | pole | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2024-09-27 | 2025-04-27 | Level 2 | GO 165 Inspection
123440072 | other | Non-HFTD | Transmission | 2022-04-27 | 2025-04-27 | Level 2 | E | 2024-10-11 | 2027-04-27 | Level 3 | GO 165 Inspection
123440277 | other | Non-HFTD | Transmission | 2022-04-26 | 2023-04-26 | Level 2 | E | 2024-11-08 | 2025-04-26 | Level 2 | GO 165 Inspection
123441411 | pole | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2024-12-03 | 2023-04-27 | Level 2 | Field Safety Reassessment
123441519 | pole | Non-HFTD | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2023-07-13 | 2025-04-28 | Level 2 | Standards change
123442302 | insulator and brushing | Non-HFTD | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2024-09-12 | 2025-04-28 | Level 2 | GO 165 Inspection
123443925 | other | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2023-05-04 | 2027-04-28 | Level 3 | Standards change
123445098 | other | HFTD Tier 2 | Transmission | 2022-04-11 | 2024-04-11 | Level 3 | F | 2024-04-24 | 2027-04-11 | Level 3 | GO 165 Inspection
123447217 | pole | Non-HFTD | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2023-09-18 | 2025-04-28 | Level 2 | Field Safety Reassessment
123448076 | pole | Non-HFTD | Transmission | 2022-04-28 | 2025-04-28 | Level 2 | E | 2024-07-25 | 2023-04-28 | Level 2 | GO 165 Inspection
123457833 | insulator and brushing | Non-HFTD | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2024-08-26 | 2025-04-28 | Level 2 | GO 165 Inspection
123458189 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2023-12-29 | 2025-04-29 | Level 2 | Standards change
123458561 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2023-12-29 | 2025-04-29 | Level 2 | Standards change
123458565 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2024-09-18 | 2022-10-29 | Level 2 | Field Safety Reassessment
123458944 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2023-12-29 | 2025-04-29 | Level 2 | Standards change
123459284 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2023-12-29 | 2025-04-29 | Level 2 | Standards change
123459368 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2023-03-02 | 2027-04-29 | Level 3 | Standards change
123459511 | other | HFTD Tier 2 | Transmission | 2022-04-14 | 2024-04-14 | Level 3 | F | 2024-05-19 | 2027-04-14 | Level 3 | GO 165 Inspection
123460575 | insulator and brushing | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2024-08-22 | 2025-04-29 | Level 2 | GO 165 Inspection
123464090 | anchor/guy | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2024-11-16 | 2023-04-27 | Level 2 | GO 165 Inspection
123464204 | other | Non-HFTD | Transmission | 2022-04-30 | 2023-04-30 | Level 2 | E | 2023-07-20 | 2025-04-30 | Level 2 | Standards change
123465029 | insulator and brushing | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-03-10 | 2025-04-20 | Level 2 | Standards change
123465338 | pole | Non-HFTD | Transmission | 2022-04-30 | 2023-04-30 | Level 2 | E | 2023-01-25 | 2025-04-30 | Level 2 | Standards change
123465347 | pole | HFTD Tier 3 | Transmission | 2022-04-15 | 2024-04-15 | Level 3 | F | 2024-05-07 | 2027-04-15 | Level 3 | GO 165 Inspection
123466239 | other | HFTD Tier 2 | Transmission | 2022-04-13 | 2024-04-13 | Level 3 | F | 2023-05-24 | 2027-04-13 | Level 3 | GO 165 Inspection
123466993 | pole | Non-HFTD | Transmission | 2022-04-30 | 2023-04-30 | Level 2 | E | 2023-01-25 | 2025-04-30 | Level 2 | Standards change
123467319 | other | HFTD Tier 2 | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-05-24 | 2027-04-18 | Level 3 | GO 165 Inspection
123469270 | other | Non-HFTD | Transmission | 2022-04-30 | 2022-07-30 | Level 2 | B | 2024-09-13 | 2023-04-30 | Level 2 | GO 165 Inspection
123472844 | other | Non-HFTD | Transmission | 2022-05-02 | 2024-05-02 | Level 3 | F | 2023-12-29 | 2027-05-02 | Level 3 | Standards change
123473253 | other | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-01-11 | 2025-05-02 | Level 2 | Standards change
123473376 | other | Non-HFTD | Transmission | 2022-05-02 | 2024-05-02 | Level 3 | F | 2023-04-18 | 2027-05-02 | Level 3 | Standards change
123474083 | pole | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-03-02 | 2025-05-02 | Level 2 | Standards change
123474333 | anchor/guy | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-03-01 | 2027-05-02 | Level 3 | Standards change
123476600 | pole | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-05-29 | 2025-05-02 | Level 2 | GO 165 Inspection
123477235 | other | Non-HFTD | Transmission | 2022-05-02 | 2025-05-02 | Level 2 | E | 2024-10-01 | 2027-05-02 | Level 3 | GO 165 Inspection
123477611 | splice | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-03-10 | 2025-05-02 | Level 2 | Standards change
123477938 | other | Non-HFTD | Transmission | 2022-05-02 | 2024-05-02 | Level 3 | F | 2024-04-06 | 2027-05-02 | Level 3 | Standards change
123478700 | pole | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-02-27 | 2025-05-02 | Level 2 | Standards change
123480030 | anchor/guy | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-02-27 | 2025-05-02 | Level 2 | Standards change
123480308 | other | Non-HFTD | Transmission | 2022-04-14 | 2024-04-14 | Level 3 | F | 2024-04-06 | 2027-04-14 | Level 3 | Standards change
123483616 | other | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-06-19 | 2025-05-03 | Level 2 | GO 165 Inspection
123483750 | other | HFTD Tier 2 | Transmission | 2022-05-02 | 2024-05-02 | Level 3 | F | 2023-03-03 | 2027-05-02 | Level 3 | Standards change
123485061 | other | Non-HFTD | Transmission | 2022-05-03 | 2024-05-03 | Level 3 | F | 2024-01-12 | 2027-05-03 | Level 3 | Standards change
123487363 | anchor/guy | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2023-02-28 | 2027-05-03 | Level 3 | Standards change
123487614 | insulator and brushing | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-10-21 | 2025-05-03 | Level 2 | GO 165 Inspection
123487997 | insulator and brushing | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-10-21 | 2025-05-03 | Level 2 | GO 165 Inspection
123489559 | pole | HFTD Tier 2 | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-03-18 | 2027-05-03 | Level 3 | GO 165 Inspection
123489619 | other | HFTD Tier 2 | Transmission | 2022-05-03 | 2027-05-03 | Level 3 | F | 2024-04-02 | 2027-05-03 | Level 3 | GO 165 Inspection
123491356 | pole | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2023-03-10 | 2025-05-02 | Level 2 | Standards change
123491432 | pole | HFTD Tier 3 | Transmission | 2022-04-15 | 2024-04-15 | Level 3 | F | 2024-05-07 | 2027-04-15 | Level 3 | GO 165 Inspection
123491494 | other | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-05-29 | 2025-05-02 | Level 2 | GO 165 Inspection
123491701 | anchor/guy | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-11-04 | 2025-05-02 | Level 2 | GO 165 Inspection
123493188 | other | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-04-22 | 2025-05-03 | Level 2 | GO 165 Inspection
123494047 | insulator and brushing | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2023-01-10 | 2025-05-04 | Level 2 | Standards change
123494418 | anchor/guy | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-01-24 | 2027-05-04 | Level 3 | Standards change
123494682 | other | Non-HFTD | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-04-06 | 2027-05-04 | Level 3 | Standards change
123494719 | insulator and brushing | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-10-28 | 2025-05-04 | Level 2 | GO 165 Inspection
123495081 | pole | Non-HFTD | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-01-22 | 2027-05-04 | Level 3 | Standards change
123495463 | insulator and brushing | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-04-08 | 2025-05-04 | Level 2 | GO 165 Inspection
123496445 | other | HFTD Tier 2 | Transmission | 2022-04-15 | 2024-04-15 | Level 3 | F | 2024-03-18 | 2027-04-15 | Level 3 | GO 165 Inspection
123496459 | insulator and brushing | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-09-24 | 2025-05-04 | Level 2 | GO 165 Inspection
123496470 | other | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-09-24 | 2027-05-04 | Level 3 | GO 165 Inspection
123498034 | other | HFTD Tier 2 | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2023-05-18 | 2027-05-04 | Level 3 | Standards change
123498082 | insulator and brushing | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2023-12-15 | 2025-05-04 | Level 2 | Standards change
123498517 | pole | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2023-12-29 | 2025-05-04 | Level 2 | Standards change
123498850 | pole | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2023-12-29 | 2025-05-04 | Level 2 | Standards change
123498894 | anchor/guy | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-01-24 | 2027-05-04 | Level 3 | Standards change
123499401 | pole | Non-HFTD | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-01-22 | 2027-05-04 | Level 3 | Standards change
123501127 | insulator and brushing | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2024-06-28 | 2025-04-27 | Level 2 | GO 165 Inspection
123513347 | other | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2023-02-03 | 2027-05-05 | Level 3 | Standards change
123514249 | pole | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2023-12-29 | 2025-05-05 | Level 2 | Standards change
123514424 | insulator and brushing | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-11-20 | 2025-05-05 | Level 2 | GO 165 Inspection
123515882 | other | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-01-04 | 2025-05-05 | Level 2 | Standards change
123515973 | other | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2023-01-31 | 2027-05-05 | Level 3 | Standards change
123516797 | other | HFTD Tier 2 | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-04-06 | 2027-04-18 | Level 3 | Standards change
123516933 | insulator and brushing | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-11-20 | 2025-05-05 | Level 2 | GO 165 Inspection
123516944 | pole | Non-HFTD | Transmission | 2022-05-03 | 2024-05-03 | Level 3 | F | 2023-12-28 | 2027-05-03 | Level 3 | Standards change
123517595 | other | Non-HFTD | Transmission | 2022-05-03 | 2024-05-03 | Level 3 | F | 2024-04-06 | 2027-05-03 | Level 3 | Standards change
123517923 | insulator and brushing | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-11-22 | 2025-05-05 | Level 2 | GO 165 Inspection
123518274 | splice | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-01-03 | 2025-05-05 | Level 2 | Standards change
123519398 | pole | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-10-04 | 2025-05-05 | Level 2 | GO 165 Inspection
123520181 | other | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-10-24 | 2025-05-02 | Level 2 | GO 165 Inspection
123520405 | insulator and brushing | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-11-14 | 2025-05-03 | Level 2 | GO 165 Inspection
123520437 | other | HFTD Tier 2 | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-05-21 | 2027-04-18 | Level 3 | GO 165 Inspection
123520547 | pole | Non-HFTD | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2024-12-26 | 2023-04-28 | Level 2 | Field Safety Reassessment
123520664 | insulator and brushing | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-11-15 | 2025-05-03 | Level 2 | GO 165 Inspection
123522405 | pole | Non-HFTD | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2024-01-02 | 2025-04-28 | Level 2 | Standards change
123522463 | other | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-01-31 | 2027-05-06 | Level 3 | Standards change
123523746 | other | Non-HFTD | Transmission | 2022-04-18 | 2024-04-18 | Level 3 | F | 2024-04-06 | 2027-04-18 | Level 3 | Standards change
123525378 | other | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-02-01 | 2027-05-06 | Level 3 | Standards change
123525548 | insulator and brushing | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-02-27 | 2025-05-06 | Level 2 | Standards change
123525860 | splice | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-08-19 | 2023-05-06 | Level 2 | Standards change
123525952 | insulator and brushing | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2024-11-04 | 2027-05-06 | Level 3 | GO 165 Inspection
123526827 | other | HFTD Tier 3 | Transmission | 2022-04-19 | 2024-04-19 | Level 3 | F | 2024-04-06 | 2027-04-19 | Level 3 | Standards change
123526969 | other | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-02-01 | 2027-05-06 | Level 3 | Standards change
123527339 | other | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-02-03 | 2025-05-06 | Level 2 | Standards change
123527509 | other | HFTD Tier 3 | Transmission | 2022-04-21 | 2024-04-21 | Level 3 | F | 2024-02-28 | 2027-04-21 | Level 3 | GO 165 Inspection
123527583 | insulator and brushing | Non-HFTD | Transmission | 2022-05-06 | 2025-05-06 | Level 2 | E | 2024-06-11 | 2023-05-06 | Level 2 | GO 165 Inspection
123527695 | insulator and brushing | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2024-11-08 | 2027-05-06 | Level 3 | GO 165 Inspection
123527741 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2024-08-20 | 2023-04-29 | Level 2 | Field Safety Reassessment
123527746 | pole | Non-HFTD | Transmission | 2022-04-27 | 2023-04-27 | Level 2 | E | 2023-03-13 | 2025-04-27 | Level 2 | Standards change
123529224 | pole | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2023-03-10 | 2025-05-06 | Level 2 | Standards change
123530337 | insulator and brushing | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2024-09-24 | 2025-05-06 | Level 2 | GO 165 Inspection
123531365 | insulator and brushing | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2024-05-29 | 2025-05-06 | Level 2 | GO 165 Inspection
123532670 | other | HFTD Tier 2 | Transmission | 2022-04-19 | 2024-04-19 | Level 3 | F | 2024-06-07 | 2027-04-19 | Level 3 | GO 165 Inspection
123532813 | insulator and brushing | Non-HFTD | Transmission | 2022-05-07 | 2023-05-07 | Level 2 | E | 2024-09-24 | 2025-05-07 | Level 2 | GO 165 Inspection
123533682 | pole | Non-HFTD | Transmission | 2022-05-07 | 2023-05-07 | Level 2 | E | 2023-07-06 | 2025-05-07 | Level 2 | Standards change
123533768 | other | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2024-04-22 | 2025-05-06 | Level 2 | GO 165 Inspection
123533807 | pole | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2024-04-11 | 2027-04-28 | Level 3 | GO 165 Inspection
123536314 | pole | HFTD Tier 2 | Transmission | 2022-05-07 | 2024-05-07 | Level 3 | F | 2024-03-28 | 2027-05-07 | Level 3 | GO 165 Inspection
123536629 | insulator and brushing | Non-HFTD | Transmission | 2022-05-07 | 2023-05-07 | Level 2 | E | 2024-09-24 | 2025-05-07 | Level 2 | GO 165 Inspection
123537472 | anchor/guy | Non-HFTD | Transmission | 2022-05-07 | 2023-05-07 | Level 2 | E | 2024-01-12 | 2025-05-07 | Level 2 | Standards change
123538559 | insulator and brushing | Non-HFTD | Transmission | 2022-04-20 | 2023-04-20 | Level 2 | E | 2023-02-10 | 2025-04-20 | Level 2 | Standards change
123541064 | anchor/guy | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-07-03 | 2027-05-02 | Level 3 | GO 165 Inspection
123541286 | pole | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2024-11-18 | 2023-04-25 | Level 2 | Field Safety Reassessment
123541309 | other | Non-HFTD | Transmission | 2022-05-09 | 2023-05-09 | Level 2 | E | 2024-11-14 | 2025-05-09 | Level 2 | GO 165 Inspection
123541483 | anchor/guy | Non-HFTD | Transmission | 2022-05-07 | 2023-05-07 | Level 2 | E | 2024-06-06 | 2025-05-07 | Level 2 | GO 165 Inspection
123541770 | other | Non-HFTD | Transmission | 2022-05-09 | 2023-05-09 | Level 2 | E | 2023-07-06 | 2025-05-09 | Level 2 | Standards change
123542994 | insulator and brushing | Non-HFTD | Transmission | 2022-05-07 | 2023-05-07 | Level 2 | E | 2024-06-06 | 2027-05-07 | Level 3 | GO 165 Inspection
123545356 | other | Non-HFTD | Transmission | 2022-05-09 | 2023-05-09 | Level 2 | E | 2024-10-30 | 2025-05-09 | Level 2 | GO 165 Inspection
123545782 | other | Non-HFTD | Transmission | 2022-05-09 | 2024-05-09 | Level 3 | F | 2023-01-06 | 2027-05-09 | Level 3 | Standards change
123546738 | other | HFTD Tier 3 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2024-06-05 | 2027-04-28 | Level 3 | GO 165 Inspection
123546908 | other | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-10-21 | 2025-05-02 | Level 2 | GO 165 Inspection
123546947 | other | Non-HFTD | Transmission | 2022-05-03 | 2023-05-03 | Level 2 | E | 2024-11-13 | 2027-05-03 | Level 3 | GO 165 Inspection
123547079 | other | Non-HFTD | Transmission | 2022-05-02 | 2023-05-02 | Level 2 | E | 2024-10-21 | 2025-05-02 | Level 2 | GO 165 Inspection
123547119 | other | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-11-06 | 2027-05-05 | Level 3 | GO 165 Inspection
123547170 | insulator and brushing | Non-HFTD | Transmission | 2022-05-05 | 2023-05-05 | Level 2 | E | 2024-11-06 | 2025-05-05 | Level 2 | GO 165 Inspection
123547172 | other | HFTD Tier 2 | Transmission | 2022-04-21 | 2024-04-21 | Level 3 | F | 2024-05-23 | 2027-04-21 | Level 3 | GO 165 Inspection
123547179 | insulator and brushing | Non-HFTD | Transmission | 2022-05-09 | 2023-05-09 | Level 2 | E | 2024-10-29 | 2027-05-09 | Level 3 | GO 165 Inspection
123558625 | insulator and brushing | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-11-04 | 2025-05-10 | Level 2 | GO 165 Inspection
123558954 | other | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-10-02 | 2025-05-10 | Level 2 | GO 165 Inspection
123559913 | pole | HFTD Tier 2 | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-07-20 | 2023-05-10 | Level 2 | Field Safety Reassessment
123559939 | other | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-10-29 | 2025-05-10 | Level 2 | GO 165 Inspection
123560094 | other | Non-HFTD | Transmission | 2022-05-10 | 2027-05-10 | Level 3 | F |  | 2027-05-10 | Level 3
123560869 | other | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2022-12-20 | 2027-05-10 | Level 3 | Standards change
123560948 | other | HFTD Tier 2 | Transmission | 2022-04-21 | 2024-04-21 | Level 3 | F | 2023-04-18 | 2027-04-21 | Level 3 | Standards change
123561162 | other | Non-HFTD | Transmission | 2022-05-10 | 2024-05-10 | Level 3 | F | 2024-09-27 | 2025-05-10 | Level 2 | GO 165 Inspection
123562628 | other | Non-HFTD | Transmission | 2022-05-10 | 2024-05-10 | Level 3 | F | 2024-10-24 | 2027-05-10 | Level 3 | GO 165 Inspection
123562629 | other | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-10-24 | 2025-05-10 | Level 2 | GO 165 Inspection
123564271 | splice | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-01-04 | 2025-05-10 | Level 2 | Standards change
123568527 | pole | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2023-07-25 | 2025-05-11 | Level 2 | Standards change
123568535 | conductor | Non-HFTD | Transmission | 2022-05-11 | 2027-05-11 | Level 2 | E | 2024-10-23 | 2025-05-11 | Level 2 | GO 165 Inspection
123569211 | insulator and brushing | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2023-02-07 | 2025-05-11 | Level 2 | Standards change
123570507 | other | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2023-02-06 | 2025-05-11 | Level 2 | Standards change
123572449 | other | Non-HFTD | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-06-21 | 2027-05-11 | Level 3 | GO 165 Inspection
123572575 | other | HFTD Tier 2 | Transmission | 2022-04-29 | 2024-04-29 | Level 3 | F | 2024-06-14 | 2027-04-29 | Level 3 | GO 165 Inspection
123573181 | other | HFTD Tier 2 | Transmission | 2022-04-21 | 2024-04-21 | Level 3 | F | 2024-06-10 | 2027-04-21 | Level 3 | GO 165 Inspection
123573293 | anchor/guy | HFTD Tier 2 | Transmission | 2022-04-28 | 2023-04-28 | Level 2 | E | 2024-06-25 | 2023-04-28 | Level 2 | Standards change
123573314 | pole | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2023-09-22 | 2025-05-11 | Level 2 | Standards change
123573562 | pole | HFTD Tier 2 | Transmission | 2022-04-27 | 2024-04-27 | Level 3 | F | 2024-04-11 | 2027-04-27 | Level 3 | GO 165 Inspection
123575163 | pole | HFTD Tier 2 | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-04-17 | 2027-05-04 | Level 3 | GO 165 Inspection
123576204 | other | Non-HFTD | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2023-12-11 | 2027-05-12 | Level 3 | Standards change
123578994 | pole | HFTD Tier 3 | Transmission | 2022-04-27 | 2024-04-27 | Level 3 | F | 2024-05-16 | 2027-04-27 | Level 3 | GO 165 Inspection
123579882 | other | Non-HFTD | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2022-12-09 | 2027-05-12 | Level 3 | Standards change
123580383 | other | HFTD Tier 2 | Transmission | 2022-05-05 | 2024-05-05 | Level 3 | F | 2023-04-18 | 2027-05-05 | Level 3 | Standards change
123581864 | insulator and brushing | Non-HFTD | Transmission | 2022-05-12 | 2023-05-12 | Level 2 | E | 2024-04-11 | 2023-05-12 | Level 2 | GO 165 Inspection
123582463 | other | HFTD Tier 2 | Transmission | 2022-05-05 | 2024-05-05 | Level 3 | F | 2024-04-06 | 2027-05-05 | Level 3 | Standards change
123584051 | insulator and brushing | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-10-28 | 2025-05-10 | Level 2 | GO 165 Inspection
123584102 | insulator and brushing | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2023-03-13 | 2025-05-10 | Level 2 | Standards change
123584154 | other | HFTD Tier 2 | Transmission | 2022-05-06 | 2024-05-06 | Level 3 | F | 2024-04-06 | 2027-05-06 | Level 3 | Standards change
123585322 | insulator and brushing | Non-HFTD | Transmission | 2022-05-13 | 2023-05-13 | Level 2 | E | 2024-09-24 | 2025-05-13 | Level 2 | GO 165 Inspection
123585989 | insulator and brushing | Non-HFTD | Transmission | 2022-05-04 | 2023-05-04 | Level 2 | E | 2024-11-15 | 2025-05-04 | Level 2 | GO 165 Inspection
123586099 | other | Non-HFTD | Transmission | 2022-05-13 | 2023-05-13 | Level 2 | E | 2023-03-09 | 2027-05-13 | Level 3 | Standards change
123586144 | anchor/guy | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2024-06-25 | 2027-05-11 | Level 3 | GO 165 Inspection
123586146 | other | Non-HFTD | Transmission | 2022-05-11 | 2025-05-11 | Level 2 | E | 2024-06-25 | 2023-05-11 | Level 2 | GO 165 Inspection
123586253 | other | Non-HFTD | Transmission | 2022-05-05 | 2024-05-05 | Level 3 | F | 2024-10-16 | 2027-05-05 | Level 3 | GO 165 Inspection
123586472 | other | HFTD Tier 3 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2024-04-06 | 2027-04-28 | Level 3 | Standards change
123586508 | other | Non-HFTD | Transmission | 2022-05-13 | 2023-05-13 | Level 2 | E | 2023-01-06 | 2025-05-13 | Level 2 | Standards change
123586972 | other | HFTD Tier 2 | Transmission | 2022-05-03 | 2024-05-03 | Level 3 | F | 2024-04-06 | 2027-05-03 | Level 3 | Standards change
123586978 | other | HFTD Tier 2 | Transmission | 2022-05-03 | 2024-05-03 | Level 3 | F | 2024-04-06 | 2027-05-03 | Level 3 | Standards change
123587013 | insulator and brushing | Non-HFTD | Transmission | 2022-05-13 | 2025-05-13 | Level 2 | E | 2024-09-24 | 2022-08-13 | Level 2 | GO 165 Inspection
123589007 | other | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2023-03-01 | 2027-04-28 | Level 3 | Standards change
123589762 | other | Non-HFTD | Transmission | 2022-05-11 | 2025-05-11 | Level 2 | E | 2024-06-26 | 2023-05-11 | Level 2 | GO 165 Inspection
123591236 | other | Non-HFTD | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-06-27 | 2027-05-11 | Level 3 | GO 165 Inspection
123591807 | other | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-10-26 | 2025-05-10 | Level 2 | GO 165 Inspection
123593593 | other | Non-HFTD | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-06-26 | 2027-05-11 | Level 3 | GO 165 Inspection
123593777 | pole | HFTD Tier 2 | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-04-17 | 2027-05-04 | Level 3 | GO 165 Inspection
123594609 | pole | Non-HFTD | Transmission | 2022-05-14 | 2024-05-14 | Level 3 | F | 2024-08-28 | 2027-05-14 | Level 3 | GO 165 Inspection
123594929 | pole | Non-HFTD | Transmission | 2022-05-14 | 2023-05-14 | Level 2 | E | 2024-07-03 | 2025-05-14 | Level 2 | GO 165 Inspection
123595139 | pole | HFTD Tier 3 | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-03-08 | 2027-05-11 | Level 3 | GO 165 Inspection
123595395 | other | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2023-05-31 | 2027-04-28 | Level 3 | Standards change
123595401 | anchor/guy | Non-HFTD | Transmission | 2022-05-10 | 2023-05-10 | Level 2 | E | 2024-10-26 | 2025-05-10 | Level 2 | GO 165 Inspection
123596010 | other | HFTD Tier 2 | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-03-04 | 2027-05-04 | Level 3 | GO 165 Inspection
123596011 | other | HFTD Tier 2 | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-03-04 | 2027-05-04 | Level 3 | GO 165 Inspection
123596405 | other | HFTD Tier 2 | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2023-03-16 | 2027-05-12 | Level 3 | Standards change
123596587 | insulator and brushing | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2024-03-21 | 2025-05-11 | Level 2 | GO 165 Inspection
123596887 | pole | Non-HFTD | Transmission | 2022-05-09 | 2023-05-09 | Level 2 | E | 2024-08-15 | 2025-05-09 | Level 2 | GO 165 Inspection
123597067 | other | HFTD Tier 3 | Transmission | 2022-05-09 | 2024-05-09 | Level 3 | F | 2024-03-27 | 2027-05-09 | Level 3 | GO 165 Inspection
123597141 | other | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2024-04-06 | 2027-04-28 | Level 3 | Standards change
123597665 | insulator and brushing | Non-HFTD | Transmission | 2022-05-14 | 2023-05-14 | Level 2 | E | 2024-09-23 | 2025-05-14 | Level 2 | GO 165 Inspection
123597666 | other | Non-HFTD | Transmission | 2022-05-14 | 2024-05-14 | Level 3 | F | 2024-09-23 | 2027-05-14 | Level 3 | GO 165 Inspection
123597809 | other | HFTD Tier 2 | Transmission | 2022-05-14 | 2024-05-14 | Level 3 | F | 2024-06-01 | 2027-05-14 | Level 3 | GO 165 Inspection
123598781 | insulator and brushing | Non-HFTD | Transmission | 2022-05-15 | 2023-05-15 | Level 2 | E | 2023-07-06 | 2025-05-15 | Level 2 | Standards change
123598889 | other | Non-HFTD | Transmission | 2022-05-15 | 2025-05-15 | Level 2 | E | 2024-09-23 | 2027-05-15 | Level 3 | GO 165 Inspection
123601071 | other | Non-HFTD | Transmission | 2022-05-15 | 2024-05-15 | Level 3 | F | 2023-08-14 | 2027-05-15 | Level 3 | Standards change
123601675 | other | HFTD Tier 2 | Transmission | 2022-05-15 | 2024-05-15 | Level 3 | F | 2024-05-30 | 2027-05-15 | Level 3 | GO 165 Inspection
123604977 | other | Non-HFTD | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-04-06 | 2027-05-16 | Level 3 | Standards change
123606927 | other | HFTD Tier 2 | Transmission | 2022-04-29 | 2024-04-29 | Level 3 | F | 2024-06-29 | 2027-04-29 | Level 3 | GO 165 Inspection
123607039 | insulator and brushing | Non-HFTD | Transmission | 2022-05-16 | 2023-05-16 | Level 2 | E | 2023-12-11 | 2025-05-16 | Level 2 | Standards change
123607777 | pole | HFTD Tier 2 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-04-04 | 2027-05-16 | Level 3 | GO 165 Inspection
123608206 | insulator and brushing | Non-HFTD | Transmission | 2022-05-16 | 2023-05-16 | Level 2 | E | 2024-01-17 | 2025-05-16 | Level 2 | Standards change
123610817 | other | Non-HFTD | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2023-02-06 | 2027-05-16 | Level 3 | Standards change
123611115 | pole | Non-HFTD | Transmission | 2022-05-16 | 2023-05-16 | Level 2 | E | 2024-10-29 | 2025-05-16 | Level 2 | Field Safety Reassessment
123616637 | pole | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2023-02-06 | 2025-05-17 | Level 2 | Standards change
123616704 | insulator and brushing | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2023-01-30 | 2025-05-17 | Level 2 | Standards change
123616933 | pole | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2024-11-12 | 2025-05-17 | Level 2 | GO 165 Inspection
123618760 | insulator and brushing | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2024-02-13 | 2025-05-17 | Level 2 | Standards change
123619055 | pole | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2024-01-02 | 2025-05-17 | Level 2 | Standards change
123619623 | insulator and brushing | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2024-06-19 | 2025-05-17 | Level 2 | GO 165 Inspection
123620459 | pole | HFTD Tier 2 | Transmission | 2022-05-14 | 2024-05-14 | Level 3 | F | 2024-03-27 | 2027-05-14 | Level 3 | GO 165 Inspection
123621709 | insulator and brushing | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2024-10-28 | 2025-05-11 | Level 2 | GO 165 Inspection
123621810 | pole | HFTD Tier 2 | Transmission | 2022-05-14 | 2024-05-14 | Level 3 | F | 2024-03-27 | 2027-05-14 | Level 3 | GO 165 Inspection
123621840 | other | Non-HFTD | Transmission | 2022-05-17 | 2023-05-17 | Level 2 | E | 2024-06-05 | 2027-05-17 | Level 3 | GO 165 Inspection
123621955 | other | HFTD Tier 2 | Transmission | 2022-05-13 | 2024-05-13 | Level 3 | F | 2024-04-16 | 2027-05-13 | Level 3 | GO 165 Inspection
123622172 | other | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2024-06-14 | 2025-05-11 | Level 2 | GO 165 Inspection
123622221 | other | Non-HFTD | Transmission | 2022-05-11 | 2023-05-11 | Level 2 | E | 2023-02-28 | 2025-05-11 | Level 2 | Standards change
123622255 | other | Non-HFTD | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-01-10 | 2027-05-11 | Level 3 | Standards change
123624899 | insulator and brushing | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2024-01-02 | 2025-05-18 | Level 2 | Standards change
123625276 | other | HFTD Tier 2 | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2024-04-16 | 2027-05-12 | Level 3 | GO 165 Inspection
123625300 | anchor/guy | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2024-01-12 | 2027-05-18 | Level 3 | Standards change
123625938 | anchor/guy | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-07-21 | 2025-05-18 | Level 2 | Standards change
123626148 | insulator and brushing | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2024-08-15 | 2025-05-18 | Level 2 | GO 165 Inspection
123626271 | anchor/guy | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-10-02 | 2025-05-18 | Level 2 | Standards change
123627186 | other | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-02-13 | 2025-05-18 | Level 2 | Standards change
123627411 | insulator and brushing | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-03-06 | 2027-05-18 | Level 3 | Standards change
123627523 | insulator and brushing | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-02-06 | 2025-05-18 | Level 2 | Standards change
123628119 | other | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2024-01-02 | 2025-05-18 | Level 2 | Standards change
123628345 | other | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-03-06 | 2027-05-18 | Level 3 | Standards change
123629079 | other | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2024-04-06 | 2027-04-28 | Level 3 | Standards change
123631212 | pole | Non-HFTD | Transmission | 2022-04-29 | 2023-04-29 | Level 2 | E | 2023-03-31 | 2025-04-29 | Level 2 | Standards change
123631256 | pole | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2024-08-26 | 2025-05-18 | Level 2 | GO 165 Inspection
123631295 | other | Non-HFTD | Transmission | 2022-05-18 | 2024-05-18 | Level 3 | F | 2023-07-21 | 2027-05-18 | Level 3 | Standards change
123631846 | pole | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-04-10 | 2025-05-18 | Level 2 | Standards change
123632479 | pole | Non-HFTD | Transmission | 2022-05-18 | 2023-05-18 | Level 2 | E | 2023-02-07 | 2025-05-18 | Level 2 | Standards change
123632631 | pole | HFTD Tier 2 | Transmission | 2022-05-04 | 2024-05-04 | Level 3 | F | 2024-05-07 | 2027-05-04 | Level 3 | GO 165 Inspection
123632962 | pole | HFTD Tier 2 | Transmission | 2022-04-30 | 2024-04-30 | Level 3 | F | 2024-05-18 | 2027-04-30 | Level 3 | GO 165 Inspection
123633045 | other | HFTD Tier 3 | Transmission | 2022-04-29 | 2024-04-29 | Level 3 | F | 2023-04-18 | 2027-04-29 | Level 3 | Standards change
123638486 | pole | Non-HFTD | Transmission | 2022-05-19 | 2023-05-19 | Level 2 | E | 2023-05-08 | 2025-05-19 | Level 2 | Standards change
123639096 | insulator and brushing | Non-HFTD | Transmission | 2022-05-19 | 2023-05-19 | Level 2 | E | 2024-04-09 | 2025-05-19 | Level 2 | GO 165 Inspection
123639351 | other | Non-HFTD | Transmission | 2022-05-19 | 2024-05-19 | Level 3 | F | 2024-04-06 | 2027-05-19 | Level 3 | Standards change
123641744 | pole | Non-HFTD | Transmission | 2022-05-19 | 2023-05-19 | Level 2 | E | 2023-03-24 | 2025-05-19 | Level 2 | Standards change
123643469 | other | HFTD Tier 2 | Transmission | 2022-04-30 | 2024-04-30 | Level 3 | F | 2024-05-18 | 2027-04-30 | Level 3 | GO 165 Inspection
123644147 | anchor/guy | HFTD Tier 2 | Transmission | 2022-05-14 | 2024-05-14 | Level 3 | F | 2024-05-23 | 2027-05-14 | Level 3 | Standards change
123644242 | pole | HFTD Tier 3 | Transmission | 2022-05-02 | 2024-05-02 | Level 3 | F | 2024-05-22 | 2027-05-02 | Level 3 | GO 165 Inspection
123646178 | other | HFTD Tier 2 | Transmission | 2022-04-29 | 2024-04-29 | Level 3 | F | 2024-06-14 | 2027-04-29 | Level 3 | GO 165 Inspection
123647102 | other | HFTD Tier 2 | Transmission | 2022-04-28 | 2024-04-28 | Level 3 | F | 2023-05-31 | 2027-04-28 | Level 3 | Standards change
123648346 | other | HFTD Tier 2 | Transmission | 2022-04-29 | 2024-04-29 | Level 3 | F | 2024-04-10 | 2027-04-29 | Level 3 | GO 165 Inspection
123648938 | other | HFTD Tier 3 | Transmission | 2022-05-20 | 2024-05-20 | Level 3 | F | 2024-04-06 | 2027-05-20 | Level 3 | Standards change
123649904 | pole | Non-HFTD | Transmission | 2022-05-20 | 2023-05-20 | Level 2 | E | 2023-02-10 | 2025-05-20 | Level 2 | Standards change
123649955 | other | HFTD Tier 2 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-04-16 | 2027-05-16 | Level 3 | GO 165 Inspection
123653567 | other | HFTD Tier 3 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-04-06 | 2027-05-16 | Level 3 | Standards change
123654178 | other | HFTD Tier 2 | Transmission | 2022-05-05 | 2024-05-05 | Level 3 | F | 2024-04-30 | 2027-05-05 | Level 3 | GO 165 Inspection
123658869 | pole | Non-HFTD | Transmission | 2022-05-21 | 2022-08-21 | Level 2 | B | 2024-12-17 | 2022-11-21 | Level 2 | Field Safety Reassessment
123659867 | other | HFTD Tier 2 | Transmission | 2022-05-17 | 2024-05-17 | Level 3 | F | 2024-04-06 | 2027-05-17 | Level 3 | Standards change
123660284 | pole | HFTD Tier 3 | Transmission | 2022-05-21 | 2024-05-21 | Level 3 | F | 2023-06-24 | 2027-05-21 | Level 3 | GO 165 Inspection
123664148 | pole | HFTD Tier 3 | Transmission | 2022-05-22 | 2024-05-22 | Level 3 | F | 2023-06-16 | 2027-05-21 | Level 3 | GO 165 Inspection
123666788 | pole | HFTD Tier 2 | Transmission | 2022-05-06 | 2024-05-06 | Level 3 | F | 2024-06-06 | 2027-05-06 | Level 3 | Standards change
123667216 | anchor/guy | Non-HFTD | Transmission | 2022-05-23 | 2024-05-23 | Level 3 | F | 2024-01-12 | 2027-05-23 | Level 3 | Standards change
123670208 | other | HFTD Tier 2 | Transmission | 2022-05-20 | 2024-05-20 | Level 3 | F | 2024-06-10 | 2027-05-20 | Level 3 | GO 165 Inspection
123672377 | pole | Non-HFTD | Transmission | 2022-05-23 | 2023-05-23 | Level 2 | E | 2023-01-25 | 2025-05-23 | Level 2 | Standards change
123672577 | pole | Non-HFTD | Transmission | 2022-05-23 | 2023-05-23 | Level 2 | E | 2023-07-13 | 2025-05-23 | Level 2 | Standards change
123672594 | pole | Non-HFTD | Transmission | 2022-05-23 | 2023-05-23 | Level 2 | E | 2024-01-04 | 2025-05-23 | Level 2 | Standards change
123673756 | other | HFTD Tier 3 | Transmission | 2022-05-06 | 2024-05-06 | Level 3 | F | 2023-04-11 | 2027-05-06 | Level 3 | Standards change
123674076 | other | HFTD Tier 3 | Transmission | 2022-05-10 | 2024-05-10 | Level 3 | F | 2024-03-08 | 2027-05-10 | Level 3 | GO 165 Inspection
123677493 | other | HFTD Tier 2 | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-04-18 | 2027-05-11 | Level 3 | GO 165 Inspection
123677504 | pole | Non-HFTD | Transmission | 2022-05-24 | 2024-05-24 | Level 3 | F | 2024-01-02 | 2027-05-24 | Level 3 | Standards change
123678192 | anchor/guy | Non-HFTD | Transmission | 2022-05-24 | 2023-05-24 | Level 2 | E | 2023-02-08 | 2025-05-24 | Level 2 | Standards change
123683734 | pole | HFTD Tier 2 | Transmission | 2022-05-19 | 2024-05-19 | Level 3 | F | 2024-02-26 | 2027-05-19 | Level 3 | GO 165 Inspection
123684530 | other | HFTD Tier 3 | Transmission | 2022-05-17 | 2024-05-17 | Level 3 | F | 2024-03-26 | 2027-05-17 | Level 3 | GO 165 Inspection
123685548 | other | Non-HFTD | Transmission | 2022-05-02 | 2024-05-02 | Level 3 | F | 2023-07-05 | 2027-05-02 | Level 3 | Standards change
123685988 | pole | HFTD Tier 3 | Transmission | 2022-05-03 | 2024-05-03 | Level 3 | F | 2024-05-24 | 2027-05-03 | Level 3 | GO 165 Inspection
123686110 | other | HFTD Tier 2 | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2024-04-06 | 2027-05-12 | Level 3 | Standards change
123691339 | pole | Non-HFTD | Transmission | 2022-05-06 | 2023-05-06 | Level 2 | E | 2024-12-30 | 2023-05-06 | Level 2 | Field Safety Reassessment
123693902 | crossarm | Non-HFTD | Transmission | 2022-05-25 | 2023-05-25 | Level 2 | E | 2024-04-09 | 2025-05-25 | Level 2 | GO 165 Inspection
123694119 | other | Non-HFTD | Transmission | 2022-05-23 | 2024-05-23 | Level 3 | F | 2024-04-06 | 2027-05-23 | Level 3 | Standards change
123696464 | other | HFTD Tier 3 | Transmission | 2022-05-20 | 2024-05-20 | Level 3 | F | 2024-04-06 | 2027-05-20 | Level 3 | Standards change
123699103 | other | HFTD Tier 2 | Transmission | 2022-05-13 | 2027-05-13 | Level 3 | F | 2024-06-01 | 2027-05-13 | Level 3 | GO 165 Inspection
123699317 | other | Non-HFTD | Transmission | 2022-05-26 | 2024-05-26 | Level 3 | F | 2023-07-11 | 2027-05-26 | Level 3 | Standards change
123700045 | other | HFTD Tier 2 | Transmission | 2022-05-13 | 2024-05-13 | Level 3 | F | 2024-04-06 | 2027-05-13 | Level 3 | Standards change
123701178 | anchor/guy | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-07-19 | 2027-05-26 | Level 3 | Standards change
123706634 | pole | HFTD Tier 3 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-04-10 | 2027-05-16 | Level 3 | GO 165 Inspection
123706812 | other | Non-HFTD | Transmission | 2022-05-05 | 2024-05-05 | Level 3 | F | 2024-08-08 | 2027-05-05 | Level 3 | GO 165 Inspection
123707305 | pole | HFTD Tier 3 | Transmission | 2022-05-23 | 2024-05-23 | Level 3 | F | 2023-05-19 | 2027-05-23 | Level 3 | GO 165 Inspection
123707786 | other | HFTD Tier 2 | Transmission | 2022-05-18 | 2024-05-18 | Level 3 | F | 2024-05-02 | 2027-05-18 | Level 3 | GO 165 Inspection
123709064 | insulator and brushing | Non-HFTD | Transmission | 2022-05-24 | 2023-05-24 | Level 2 | E | 2024-08-07 | 2025-05-24 | Level 2 | GO 165 Inspection
123709729 | other | HFTD Tier 2 | Transmission | 2022-05-10 | 2024-05-10 | Level 3 | F | 2024-04-12 | 2027-05-10 | Level 3 | GO 165 Inspection
123713688 | pole | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-01-26 | 2025-05-26 | Level 2 | Standards change
123713764 | pole | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2024-09-28 | 2025-05-27 | Level 2 | GO 165 Inspection
123713880 | other | HFTD Tier 3 | Transmission | 2022-05-20 | 2024-05-20 | Level 3 | F | 2024-04-06 | 2027-05-20 | Level 3 | Standards change
123714157 | pole | HFTD Tier 2 | Transmission | 2022-05-27 | 2024-05-27 | Level 3 | F | 2024-02-20 | 2027-05-27 | Level 3 | GO 165 Inspection
123714213 | insulator and brushing | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-03-09 | 2025-05-26 | Level 2 | Standards change
123714401 | pole | HFTD Tier 2 | Transmission | 2022-05-27 | 2024-05-27 | Level 3 | F | 2024-02-01 | 2027-05-27 | Level 3 | GO 165 Inspection
123714616 | other | HFTD Tier 2 | Transmission | 2022-05-19 | 2024-05-19 | Level 3 | F | 2024-04-06 | 2027-05-19 | Level 3 | Standards change
123715158 | conductor | Non-HFTD | Transmission | 2022-05-09 | 2025-05-09 | Level 2 | E | 2024-08-15 | 2023-05-09 | Level 2 | GO 165 Inspection
123715286 | other | HFTD Tier 2 | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2024-04-16 | 2027-05-12 | Level 3 | GO 165 Inspection
123715355 | other | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2024-09-30 | 2025-05-27 | Level 2 | GO 165 Inspection
123717964 | other | HFTD Tier 2 | Transmission | 2022-05-30 | 2024-05-30 | Level 3 | F | 2023-06-02 | 2027-05-30 | Level 3 | Standards change
123722839 | pole | HFTD Tier 2 | Transmission | 2022-05-06 | 2024-05-06 | Level 3 | F | 2024-04-26 | 2027-05-06 | Level 3 | GO 165 Inspection
123723007 | anchor/guy | Non-HFTD | Transmission | 2022-05-31 | 2023-05-31 | Level 2 | E | 2024-01-05 | 2027-05-31 | Level 3 | Standards change
123726521 | pole | Non-HFTD | Transmission | 2022-05-31 | 2023-05-31 | Level 2 | E | 2024-01-04 | 2025-05-31 | Level 2 | Standards change
123728830 | other | HFTD Tier 2 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2024-03-20 | 2027-05-25 | Level 3 | GO 165 Inspection
123728975 | pole | Non-HFTD | Transmission | 2022-06-01 | 2023-06-01 | Level 2 | E | 2023-01-09 | 2025-06-01 | Level 2 | Standards change
123729426 | splice | Non-HFTD | Transmission | 2022-06-01 | 2023-06-01 | Level 2 | E | 2023-07-17 | 2025-06-01 | Level 2 | Standards change
123732563 | pole | Non-HFTD | Transmission | 2022-06-01 | 2023-06-01 | Level 2 | E | 2023-08-01 | 2025-06-01 | Level 2 | Standards change
123733425 | other | HFTD Tier 2 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2024-03-22 | 2027-05-25 | Level 3 | GO 165 Inspection
123734301 | other | HFTD Tier 2 | Transmission | 2022-05-18 | 2024-05-18 | Level 3 | F | 2024-05-06 | 2027-05-18 | Level 3 | GO 165 Inspection
123743764 | pole | HFTD Tier 3 | Transmission | 2022-05-23 | 2024-05-23 | Level 3 | F | 2024-04-30 | 2027-05-23 | Level 3 | GO 165 Inspection
123745149 | other | HFTD Tier 2 | Transmission | 2022-05-11 | 2024-05-11 | Level 3 | F | 2024-05-08 | 2027-05-11 | Level 3 | GO 165 Inspection
123745200 | pole | Non-HFTD | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-07-19 | 2027-06-02 | Level 3 | Field Safety Reassessment
123745572 | other | HFTD Tier 2 | Transmission | 2022-05-24 | 2024-05-24 | Level 3 | F | 2024-04-08 | 2027-05-24 | Level 3 | GO 165 Inspection
123747819 | other | HFTD Tier 2 | Transmission | 2022-05-18 | 2024-05-18 | Level 3 | F | 2024-05-01 | 2027-05-18 | Level 3 | GO 165 Inspection
123747877 | pole | Non-HFTD | Transmission | 2022-05-21 | 2023-05-21 | Level 2 | E | 2023-08-08 | 2025-05-21 | Level 2 | Standards change
123747960 | other | HFTD Tier 2 | Transmission | 2022-05-19 | 2024-05-19 | Level 3 | F | 2023-03-30 | 2027-05-19 | Level 3 | Standards change
123749015 | other | HFTD Tier 3 | Transmission | 2022-06-03 | 2024-06-03 | Level 3 | F | 2024-02-27 | 2027-06-03 | Level 3 | GO 165 Inspection
123749653 | other | HFTD Tier 2 | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2023-07-02 | 2027-05-12 | Level 3 | Standards change
123749975 | other | HFTD Tier 3 | Transmission | 2022-05-18 | 2024-05-18 | Level 3 | F | 2024-03-27 | 2027-05-18 | Level 3 | GO 165 Inspection
123750596 | other | HFTD Tier 2 | Transmission | 2022-05-12 | 2024-05-12 | Level 3 | F | 2024-04-18 | 2027-05-12 | Level 3 | GO 165 Inspection
123751340 | other | Non-HFTD | Transmission | 2022-06-03 | 2024-06-03 | Level 3 | F | 2024-04-06 | 2027-06-03 | Level 3 | Standards change
123751434 | other | HFTD Tier 3 | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-04-23 | 2027-06-02 | Level 3 | GO 165 Inspection
123752519 | pole | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2023-03-20 | 2025-05-27 | Level 2 | Standards change
123753351 | insulator and brushing | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2024-12-06 | 2023-05-27 | Level 2 | Field Safety Reassessment
123753466 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-05-07 | 2027-06-01 | Level 3 | GO 165 Inspection
123754082 | insulator and brushing | Non-HFTD | Transmission | 2022-06-03 | 2023-06-03 | Level 2 | E | 2024-01-23 | 2025-06-03 | Level 2 | Standards change
123758465 | pole | HFTD Tier 2 | Transmission | 2022-05-19 | 2024-05-19 | Level 3 | F | 2024-01-29 | 2027-05-19 | Level 3 | GO 165 Inspection
123758686 | other | HFTD Tier 2 | Transmission | 2022-05-18 | 2024-05-18 | Level 3 | F | 2023-03-06 | 2027-05-18 | Level 3 | Standards change
123758905 | pole | Non-HFTD | Transmission | 2022-06-03 | 2025-06-03 | Level 2 | E | 2024-09-17 | 2023-06-03 | Level 2 | GO 165 Inspection
123761204 | insulator and brushing | Non-HFTD | Transmission | 2022-06-04 | 2023-06-04 | Level 2 | E | 2023-01-23 | 2025-06-04 | Level 2 | Standards change
123766391 | other | HFTD Tier 3 | Transmission | 2022-06-05 | 2024-06-05 | Level 3 | F | 2023-02-21 | 2027-06-05 | Level 3 | Standards change
123767607 | other | HFTD Tier 2 | Transmission | 2022-06-05 | 2024-06-05 | Level 3 | F | 2024-04-06 | 2027-06-05 | Level 3 | Standards change
123769447 | pole | Non-HFTD | Transmission | 2022-06-01 | 2023-06-01 | Level 2 | E | 2023-07-18 | 2025-06-01 | Level 2 | Standards change
123769884 | other | Non-HFTD | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-06-25 | 2027-06-02 | Level 3 | GO 165 Inspection
123771119 | pole | HFTD Tier 3 | Transmission | 2022-05-20 | 2024-05-20 | Level 3 | F | 2024-05-13 | 2027-05-20 | Level 3 | GO 165 Inspection
123771549 | pole | HFTD Tier 3 | Transmission | 2022-05-13 | 2024-05-13 | Level 3 | F | 2024-06-11 | 2027-05-13 | Level 3 | GO 165 Inspection
123772053 | other | Non-HFTD | Transmission | 2022-06-02 | 2023-06-02 | Level 2 | E | 2024-06-24 | 2025-06-02 | Level 2 | GO 165 Inspection
123773663 | insulator and brushing | Non-HFTD | Transmission | 2022-06-06 | 2025-06-06 | Level 2 | E | 2024-09-06 | 2022-09-06 | Level 2 | GO 165 Inspection
123773712 | other | Non-HFTD | Transmission | 2022-05-31 | 2024-05-31 | Level 3 | F | 2024-04-06 | 2027-05-31 | Level 3 | Standards change
123773928 | pole | HFTD Tier 2 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-03-14 | 2027-05-16 | Level 3 | GO 165 Inspection
123774997 | insulator and brushing | Non-HFTD | Transmission | 2022-06-06 | 2023-06-06 | Level 2 | E | 2024-04-01 | 2025-06-06 | Level 2 | GO 165 Inspection
123775090 | pole | HFTD Tier 2 | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-04-20 | 2027-06-02 | Level 3 | GO 165 Inspection
123777347 | pole | HFTD Tier 2 | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-17 | 2027-06-07 | Level 3 | GO 165 Inspection
123778300 | other | HFTD Tier 3 | Transmission | 2022-05-13 | 2024-05-13 | Level 3 | F | 2024-03-11 | 2027-05-13 | Level 3 | Standards change
123778305 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-05-08 | 2027-06-01 | Level 3 | GO 165 Inspection
123778382 | pole | HFTD Tier 3 | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-03-19 | 2027-06-02 | Level 3 | GO 165 Inspection
123778630 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-03-28 | 2027-06-01 | Level 3 | GO 165 Inspection
123780256 | other | HFTD Tier 2 | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-04-22 | 2027-06-07 | Level 3 | Standards change
123782832 | other | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-05-06 | 2027-06-01 | Level 3 | GO 165 Inspection
123784307 | insulator and brushing | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2024-07-10 | 2025-06-07 | Level 2 | GO 165 Inspection
123784728 | anchor/guy | HFTD Tier 2 | Transmission | 2022-05-19 | 2024-05-19 | Level 3 | F | 2024-04-12 | 2027-05-19 | Level 3 | GO 165 Inspection
123785404 | pole | Non-HFTD | Transmission | 2022-06-08 | 2024-06-08 | Level 3 | F | 2023-01-17 | 2027-06-08 | Level 3 | Standards change
123785579 | pole | Non-HFTD | Transmission | 2022-06-08 | 2024-06-08 | Level 3 | F | 2023-12-01 | 2027-06-08 | Level 3 | Standards change
123785828 | pole | Non-HFTD | Transmission | 2022-06-08 | 2024-06-08 | Level 3 | F | 2023-12-01 | 2027-06-08 | Level 3 | Standards change
123785964 | pole | Non-HFTD | Transmission | 2022-06-01 | 2023-06-01 | Level 2 | E | 2023-01-30 | 2025-06-01 | Level 2 | Standards change
123789693 | other | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2024-01-22 | 2025-06-08 | Level 2 | Standards change
123789768 | other | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2024-09-12 | 2025-06-08 | Level 2 | GO 165 Inspection
123791721 | other | HFTD Tier 2 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2024-03-25 | 2027-05-25 | Level 3 | GO 165 Inspection
123793151 | other | HFTD Tier 3 | Transmission | 2022-05-24 | 2024-05-24 | Level 3 | F | 2024-06-27 | 2027-05-24 | Level 3 | Field Safety Reassessment
123793348 | other | Non-HFTD | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-06-25 | 2027-06-02 | Level 3 | GO 165 Inspection
123794538 | other | HFTD Tier 2 | Transmission | 2022-06-09 | 2024-06-09 | Level 3 | F | 2024-05-30 | 2027-06-09 | Level 3 | GO 165 Inspection
123795079 | pole | Non-HFTD | Transmission | 2022-06-09 | 2023-06-09 | Level 2 | E | 2023-02-06 | 2025-06-09 | Level 2 | Standards change
123796289 | other | HFTD Tier 3 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2024-04-06 | 2027-05-25 | Level 3 | Standards change
123796357 | other | HFTD Tier 2 | Transmission | 2022-06-09 | 2024-06-09 | Level 3 | F | 2023-06-07 | 2027-06-09 | Level 3 | Standards change
123801464 | pole | Non-HFTD | Transmission | 2022-05-23 | 2023-05-23 | Level 2 | E | 2024-05-22 | 2027-05-23 | Level 3 | GO 165 Inspection
123801467 | pole | Non-HFTD | Transmission | 2022-05-22 | 2023-05-22 | Level 2 | E | 2023-06-14 | 2025-05-22 | Level 2 | Standards change
123813697 | pole | HFTD Tier 2 | Transmission | 2022-05-07 | 2024-05-07 | Level 3 | F | 2024-04-06 | 2027-05-07 | Level 3 | GO 165 Inspection
123813859 | pole | HFTD Tier 2 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-02-01 | 2027-05-16 | Level 3 | GO 165 Inspection
123813922 | pole | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-02-03 | 2025-05-26 | Level 2 | Standards change
123814380 | other | HFTD Tier 2 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2023-04-20 | 2027-05-25 | Level 3 | Standards change
123814481 | other | Non-HFTD | Transmission | 2022-06-07 | 2027-06-07 | Level 3 | F | 2024-10-23 | 2027-06-07 | Level 3 | GO 165 Inspection
123815790 | insulator and brushing | Non-HFTD | Transmission | 2022-05-23 | 2023-05-23 | Level 2 | E | 2023-02-09 | 2025-05-23 | Level 2 | Standards change
123816101 | pole | HFTD Tier 2 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-04-23 | 2027-05-16 | Level 3 | GO 165 Inspection
123816445 | other | HFTD Tier 3 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2024-03-21 | 2027-05-25 | Level 3 | GO 165 Inspection
123816508 | pole | HFTD Tier 3 | Transmission | 2022-06-10 | 2022-12-10 | Level 2 | E | 2023-05-23 | 2027-06-10 | Level 3 | GO 165 Inspection
123817168 | anchor/guy | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2024-01-18 | 2027-05-26 | Level 3 | Standards change
123819293 | other | HFTD Tier 2 | Transmission | 2022-06-03 | 2024-06-03 | Level 3 | F | 2024-05-20 | 2027-06-03 | Level 3 | GO 165 Inspection
123821750 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | Standards change
123821898 | insulator and brushing | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-01-13 | 2025-05-26 | Level 2 | Standards change
123822415 | anchor/guy | Non-HFTD | Transmission | 2022-05-19 | 2023-05-19 | Level 2 | E | 2024-01-24 | 2027-05-19 | Level 3 | Standards change
123823409 | pole | HFTD Tier 2 | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | GO 165 Inspection
123824824 | pole | HFTD Tier 2 | Transmission | 2022-06-11 | 2024-06-11 | Level 3 | F | 2023-05-17 | 2027-06-11 | Level 3 | GO 165 Inspection
123825300 | pole | Non-HFTD | Transmission | 2022-06-11 | 2023-06-11 | Level 2 | E | 2024-07-24 | 2023-06-11 | Level 2 | GO 165 Inspection
123831870 | other | Non-HFTD | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2024-04-30 | 2027-06-13 | Level 3 | GO 165 Inspection
123831916 | other | Non-HFTD | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2024-04-30 | 2027-06-13 | Level 3 | GO 165 Inspection
123832124 | other | HFTD Tier 2 | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2023-03-01 | 2025-06-13 | Level 2 | Standards change
123832475 | pole | Non-HFTD | Transmission | 2022-06-13 | 2023-06-13 | Level 2 | E | 2023-03-08 | 2025-06-13 | Level 2 | Standards change
123834954 | pole | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2023-03-20 | 2025-05-27 | Level 2 | Standards change
123836983 | insulator and brushing | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-10-07 | 2027-06-14 | Level 3 | GO 165 Inspection
123837756 | other | Non-HFTD | Transmission | 2022-06-14 | 2024-06-14 | Level 3 | F | 2024-04-06 | 2027-06-14 | Level 3 | Standards change
123838732 | anchor/guy | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-02-01 | 2025-06-14 | Level 2 | GO 165 Inspection
123839442 | pole | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-07-29 | 2025-06-14 | Level 2 | GO 165 Inspection
123840783 | pole | Non-HFTD | Transmission | 2022-06-14 | 2022-12-14 | Level 2 | E | 2024-03-12 | 2022-12-14 | Level 2 | GO 165 Inspection
123841676 | other | Non-HFTD | Transmission | 2022-05-27 | 2024-05-27 | Level 3 | F | 2023-03-15 | 2027-05-27 | Level 3 | Standards change
123842117 | pole | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2023-01-12 | 2025-06-07 | Level 2 | Standards change
123842455 | other | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-01-30 | 2025-06-14 | Level 2 | Standards change
123842613 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-03-19 | 2027-06-01 | Level 3 | GO 165 Inspection
123842817 | other | Non-HFTD | Transmission | 2022-06-14 | 2024-06-14 | Level 3 | F | 2024-03-15 | 2027-06-14 | Level 3 | Standards change
123843209 | pole | Non-HFTD | Transmission | 2022-02-26 | 2023-02-26 | Level 2 | E | 2023-01-26 | 2025-02-26 | Level 2 | Standards change
123846428 | crossarm | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2024-03-13 | 2023-06-15 | Level 2 | GO 165 Inspection
123847912 | anchor/guy | Non-HFTD | Transmission | 2022-06-15 | 2024-06-15 | Level 3 | F | 2024-03-13 | 2027-06-15 | Level 3 | GO 165 Inspection
123847989 | anchor/guy | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-12-07 | 2027-06-15 | Level 3 | Standards change
123849215 | anchor/guy | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-08-02 | 2027-06-15 | Level 3 | Standards change
123849819 | other | HFTD Tier 2 | Transmission | 2022-06-15 | 2024-06-15 | Level 3 | F | 2024-04-22 | 2027-06-15 | Level 3 | GO 165 Inspection
123851953 | pole | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-10-18 | 2025-06-15 | Level 2 | Standards change
123852135 | other | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-06-25 | 2025-06-14 | Level 2 | GO 165 Inspection
123852563 | pole | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2024-08-14 | 2027-06-07 | Level 3 | GO 165 Inspection
123852853 | other | HFTD Tier 2 | Transmission | 2022-06-06 | 2024-06-06 | Level 3 | F | 2023-06-15 | 2027-06-06 | Level 3 | Standards change
123852918 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-05-07 | 2027-06-01 | Level 3 | GO 165 Inspection
123853115 | pole | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2023-03-03 | 2025-06-07 | Level 2 | Standards change
123853212 | pole | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2023-12-12 | 2025-06-08 | Level 2 | Standards change
123853213 | other | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-02-23 | 2027-05-26 | Level 3 | Standards change
123855435 | pole | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2024-07-23 | 2025-06-16 | Level 2 | GO 165 Inspection
123855436 | other | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2024-07-23 | 2027-06-16 | Level 3 | GO 165 Inspection
123857129 | pole | HFTD Tier 2 | Transmission | 2022-06-10 | 2024-06-10 | Level 3 | F | 2024-01-30 | 2027-06-10 | Level 3 | GO 165 Inspection
123858004 | pole | HFTD Tier 2 | Transmission | 2022-05-16 | 2024-05-16 | Level 3 | F | 2024-02-13 | 2027-05-16 | Level 3 | GO 165 Inspection
123858230 | other | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2024-01-23 | 2025-06-16 | Level 2 | Standards change
123859457 | other | HFTD Tier 2 | Transmission | 2022-06-16 | 2024-06-16 | Level 3 | F | 2024-05-20 | 2027-06-16 | Level 3 | GO 165 Inspection
123859848 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2024-04-02 | 2027-06-01 | Level 3 | GO 165 Inspection
123862284 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-07-30 | 2027-06-07 | Level 3 | GO 165 Inspection
123868255 | insulator and brushing | Non-HFTD | Transmission | 2022-06-07 | 2025-06-07 | Level 2 | E | 2024-08-14 | 2023-06-07 | Level 2 | GO 165 Inspection
123868421 | other | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2023-03-10 | 2027-06-16 | Level 3 | Standards change
123870024 | anchor/guy | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-06-05 | 2025-06-14 | Level 2 | GO 165 Inspection
123870028 | other | Non-HFTD | Transmission | 2022-06-14 | 2023-06-14 | Level 2 | E | 2024-06-05 | 2025-06-14 | Level 2 | GO 165 Inspection
123870051 | pole | HFTD Tier 3 | Transmission | 2022-06-18 | 2024-06-18 | Level 3 | F | 2024-05-01 | 2027-06-18 | Level 3 | GO 165 Inspection
123870610 | pole | HFTD Tier 2 | Transmission | 2022-06-14 | 2024-06-14 | Level 3 | F | 2024-04-04 | 2027-06-14 | Level 3 | GO 165 Inspection
123870645 | other | HFTD Tier 3 | Transmission | 2022-06-18 | 2027-06-18 | Level 3 | F |  | 2027-06-18 | Level 3
123871545 | other | HFTD Tier 2 | Transmission | 2022-06-18 | 2024-06-18 | Level 3 | F | 2024-05-21 | 2027-06-18 | Level 3 | GO 165 Inspection
123871844 | pole | HFTD Tier 2 | Transmission | 2022-06-14 | 2024-06-14 | Level 3 | F | 2024-04-02 | 2027-06-14 | Level 3 | GO 165 Inspection
123872457 | anchor/guy | HFTD Tier 2 | Transmission | 2022-06-04 | 2024-06-04 | Level 3 | F | 2024-04-23 | 2027-06-04 | Level 3 | GO 165 Inspection
123874312 | insulator and brushing | HFTD Tier 2 | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2024-10-25 | 2023-06-15 | Level 2 | Standards change
123883980 | other | Non-HFTD | Transmission | 2022-06-15 | 2024-06-15 | Level 3 | F | 2024-04-06 | 2027-06-15 | Level 3 | Standards change
123884905 | pole | HFTD Tier 2 | Transmission | 2022-05-20 | 2024-05-20 | Level 3 | F | 2024-01-30 | 2027-05-20 | Level 3 | GO 165 Inspection
123886035 | pole | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2024-01-02 | 2025-06-15 | Level 2 | Standards change
123886769 | anchor/guy | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2024-01-02 | 2027-06-21 | Level 3 | Standards change
123887046 | other | HFTD Tier 2 | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-04-25 | 2027-06-21 | Level 3 | Standards change
123887285 | other | Non-HFTD | Transmission | 2022-05-23 | 2024-05-23 | Level 3 | F | 2024-04-06 | 2027-05-23 | Level 3 | Standards change
123888019 | other | HFTD Tier 2 | Transmission | 2022-05-27 | 2024-05-27 | Level 3 | F | 2024-04-30 | 2027-05-27 | Level 3 | GO 165 Inspection
123890694 | splice | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-05-30 | 2025-06-21 | Level 2 | GO 165 Inspection
123892342 | pole | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2023-12-12 | 2025-06-08 | Level 2 | Standards change
123894347 | other | HFTD Tier 3 | Transmission | 2022-05-24 | 2024-05-24 | Level 3 | F | 2024-04-06 | 2027-05-24 | Level 3 | Standards change
123894387 | pole | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-03-07 | 2025-06-15 | Level 2 | Standards change
123896977 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2024-04-06 | 2027-06-22 | Level 3 | Standards change
123897849 | anchor/guy | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-02-28 | 2027-06-22 | Level 3 | Standards change
123897933 | pole | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2023-03-06 | 2027-06-01 | Level 3 | Standards change
123898183 | anchor/guy | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2024-09-18 | 2027-06-22 | Level 3 | GO 165 Inspection
123898185 | anchor/guy | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-03-24 | 2027-06-22 | Level 3 | Standards change
123898206 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2024-01-02 | 2025-06-22 | Level 2 | Standards change
123900063 | pole | HFTD Tier 2 | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2024-05-21 | 2027-06-22 | Level 3 | GO 165 Inspection
123900098 | other | HFTD Tier 2 | Transmission | 2022-06-22 | 2027-06-22 | Level 3 | F | 2024-05-17 | 2027-06-22 | Level 3 | GO 165 Inspection
123901162 | other | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2024-03-19 | 2025-06-15 | Level 2 | GO 165 Inspection
123901235 | anchor/guy | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2024-02-01 | 2027-06-07 | Level 3 | Standards change
123901475 | other | HFTD Tier 2 | Transmission | 2022-05-24 | 2024-05-24 | Level 3 | F | 2024-06-17 | 2027-05-24 | Level 3 | GO 165 Inspection
123902105 | pole | Non-HFTD | Transmission | 2022-06-03 | 2023-06-03 | Level 2 | E | 2023-03-09 | 2025-06-03 | Level 2 | Standards change
123903246 | other | HFTD Tier 2 | Transmission | 2022-06-06 | 2024-06-06 | Level 3 | F | 2023-06-21 | 2027-06-06 | Level 3 | Standards change
123903590 | pole | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2024-01-02 | 2025-06-23 | Level 2 | Standards change
123904157 | other | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2024-11-20 | 2025-06-23 | Level 2 | Field Safety Reassessment
123907304 | pole | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2023-03-10 | 2025-06-23 | Level 2 | Standards change
123908595 | pole | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2023-01-23 | 2025-06-23 | Level 2 | Standards change
123909395 | other | HFTD Tier 2 | Transmission | 2022-05-25 | 2024-05-25 | Level 3 | F | 2024-04-06 | 2027-05-25 | Level 3 | Standards change
123909554 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-31 | 2025-06-21 | Level 2 | Standards change
123909557 | pole | HFTD Tier 2 | Transmission | 2022-06-06 | 2024-06-06 | Level 3 | F | 2024-04-15 | 2027-06-06 | Level 3 | GO 165 Inspection
123909570 | splice | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-30 | 2025-06-21 | Level 2 | Standards change
123910333 | other | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2024-09-18 | 2025-06-15 | Level 2 | GO 165 Inspection
123911826 | pole | HFTD Tier 3 | Transmission | 2022-06-18 | 2024-06-18 | Level 3 | F | 2024-04-05 | 2027-06-18 | Level 3 | GO 165 Inspection
123912220 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | Standards change
123912579 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-03-03 | 2027-06-07 | Level 3 | Standards change
123912834 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | Standards change
123913388 | other | HFTD Tier 3 | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2024-04-06 | 2027-06-21 | Level 3 | Standards change
123913941 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-07-14 | 2027-06-21 | Level 3 | Standards change
123914562 | other | HFTD Tier 2 | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2023-03-30 | 2027-06-24 | Level 3 | Standards change
123914573 | pole | HFTD Tier 2 | Transmission | 2022-06-17 | 2024-06-17 | Level 3 | F | 2024-10-30 | 2027-06-17 | Level 3 | Field Safety Reassessment
123914879 | other | HFTD Tier 3 | Transmission | 2022-06-08 | 2024-06-08 | Level 3 | F | 2024-02-27 | 2027-06-08 | Level 3 | GO 165 Inspection
123915195 | insulator and brushing | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2024-05-09 | 2025-06-24 | Level 2 | GO 165 Inspection
123915360 | crossarm | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2024-01-02 | 2025-06-07 | Level 2 | Standards change
123915757 | switch | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-10-08 | 2022-09-21 | Level 2 | Field Safety Reassessment
123915767 | insulator and brushing | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2023-02-10 | 2025-06-23 | Level 2 | Standards change
123916463 | insulator and brushing | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-02-10 | 2025-06-24 | Level 2 | Standards change
123918976 | pole | HFTD Tier 3 | Transmission | 2022-06-06 | 2024-06-06 | Level 3 | F | 2024-06-10 | 2027-06-06 | Level 3 | GO 165 Inspection
123919395 | pole | HFTD Tier 3 | Transmission | 2022-06-17 | 2024-06-17 | Level 3 | F | 2024-04-02 | 2027-06-17 | Level 3 | GO 165 Inspection
123919422 | other | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-03-07 | 2025-06-24 | Level 2 | Standards change
123919748 | other | HFTD Tier 2 | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-12-20 | 2027-06-07 | Level 3 | Standards change
123920780 | other | HFTD Tier 2 | Transmission | 2022-05-31 | 2024-05-31 | Level 3 | F | 2024-04-06 | 2027-05-31 | Level 3 | Standards change
123920872 | insulator and brushing | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2023-03-15 | 2025-05-27 | Level 2 | Standards change
123921221 | pole | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-01-26 | 2025-05-26 | Level 2 | Standards change
123921560 | other | Non-HFTD | Transmission | 2022-06-25 | 2023-06-25 | Level 2 | E | 2024-03-19 | 2025-06-25 | Level 2 | GO 165 Inspection
123921730 | other | HFTD Tier 2 | Transmission | 2022-06-06 | 2024-06-06 | Level 3 | F | 2024-04-06 | 2027-06-06 | Level 3 | Standards change
123921745 | other | Non-HFTD | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2024-04-06 | 2027-06-23 | Level 3 | Standards change
123922117 | insulator and brushing | Non-HFTD | Transmission | 2022-06-21 | 2022-09-19 | Level 2 | E |  | 2022-09-19 | Level 2
123922204 | insulator and brushing | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2024-09-30 | 2027-05-27 | Level 3 | GO 165 Inspection
123922205 | other | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2024-09-30 | 2025-05-27 | Level 2 | GO 165 Inspection
123922207 | other | Non-HFTD | Transmission | 2022-06-01 | 2023-06-01 | Level 2 | E | 2023-01-30 | 2025-06-01 | Level 2 | Standards change
123922209 | other | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-01-13 | 2025-05-26 | Level 2 | Standards change
123922223 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-02-28 | 2025-06-22 | Level 2 | Standards change
123922588 | pole | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2024-02-08 | 2027-06-08 | Level 3 | GO 165 Inspection
123922881 | insulator and brushing | Non-HFTD | Transmission | 2022-05-31 | 2023-05-31 | Level 2 | E | 2023-12-04 | 2027-05-31 | Level 3 | Standards change
123922947 | pole | HFTD Tier 2 | Transmission | 2022-06-10 | 2024-06-10 | Level 3 | F | 2024-03-13 | 2027-06-10 | Level 3 | GO 165 Inspection
123923277 | other | HFTD Tier 2 | Transmission | 2022-06-25 | 2024-06-25 | Level 3 | F | 2023-03-07 | 2027-06-25 | Level 3 | Standards change
123923582 | pole | Non-HFTD | Transmission | 2022-06-25 | 2023-06-25 | Level 2 | E | 2023-05-30 | 2025-06-25 | Level 2 | Standards change
123923935 | anchor/guy | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2024-09-30 | 2025-05-26 | Level 2 | GO 165 Inspection
123923970 | insulator and brushing | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2024-09-30 | 2025-05-26 | Level 2 | GO 165 Inspection
123924738 | insulator and brushing | Non-HFTD | Transmission | 2022-06-25 | 2023-06-25 | Level 2 | E | 2024-08-14 | 2025-06-25 | Level 2 | GO 165 Inspection
123925453 | other | HFTD Tier 2 | Transmission | 2022-06-03 | 2024-06-03 | Level 3 | F | 2023-02-21 | 2027-06-03 | Level 3 | Standards change
123926080 | pole | HFTD Tier 2 | Transmission | 2022-05-31 | 2024-05-31 | Level 3 | F | 2024-01-30 | 2027-05-31 | Level 3 | GO 165 Inspection
123926222 | insulator and brushing | Non-HFTD | Transmission | 2022-05-26 | 2023-05-26 | Level 2 | E | 2023-03-21 | 2025-05-26 | Level 2 | Standards change
123926302 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | Standards change
123926303 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-07-21 | 2027-06-07 | Level 3 | Standards change
123926304 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-03-29 | 2027-06-07 | Level 3 | Standards change
123927672 | pole | Non-HFTD | Transmission | 2022-06-26 | 2023-06-26 | Level 2 | E | 2024-03-20 | 2025-06-26 | Level 2 | GO 165 Inspection
123929041 | insulator and brushing | Non-HFTD | Transmission | 2022-06-26 | 2023-06-26 | Level 2 | E | 2024-11-08 | 2025-06-26 | Level 2 | GO 165 Inspection
123929738 | anchor/guy | Non-HFTD | Transmission | 2022-06-26 | 2024-06-26 | Level 3 | F | 2024-07-09 | 2027-06-26 | Level 3 | GO 165 Inspection
123929898 | other | HFTD Tier 2 | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2024-04-06 | 2027-06-23 | Level 3 | Standards change
123930669 | pole | Non-HFTD | Transmission | 2022-06-27 | 2023-06-27 | Level 2 | E | 2022-08-16 | 2025-06-27 | Level 2 | Standards change
123930797 | other | Non-HFTD | Transmission | 2022-06-27 | 2024-06-27 | Level 3 | F | 2024-04-06 | 2027-06-27 | Level 3 | Standards change
123930975 | other | Non-HFTD | Transmission | 2022-06-27 | 2024-06-27 | Level 3 | F | 2024-04-06 | 2027-06-27 | Level 3 | Standards change
123936514 | other | HFTD Tier 2 | Transmission | 2022-06-01 | 2024-06-01 | Level 3 | F | 2023-04-10 | 2027-06-01 | Level 3 | Standards change
123936799 | other | Non-HFTD | Transmission | 2022-06-27 | 2023-06-27 | Level 2 | E | 2023-12-04 | 2025-06-27 | Level 2 | Standards change
123937566 | other | Non-HFTD | Transmission | 2022-06-27 | 2023-06-27 | Level 2 | E | 2024-01-18 | 2025-06-27 | Level 2 | Standards change
123942331 | pole | Non-HFTD | Transmission | 2022-06-28 | 2023-06-28 | Level 2 | E | 2024-04-23 | 2023-06-28 | Level 2 | GO 165 Inspection
123944192 | other | Non-HFTD | Transmission | 2022-06-28 | 2024-06-28 | Level 3 | F | 2024-04-06 | 2027-06-28 | Level 3 | Standards change
123945226 | other | HFTD Tier 2 | Transmission | 2022-06-26 | 2024-06-26 | Level 3 | F | 2024-04-06 | 2027-06-26 | Level 3 | Standards change
123951423 | other | HFTD Tier 2 | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2024-04-06 | 2027-06-24 | Level 3 | Standards change
123951480 | pole | HFTD Tier 2 | Transmission | 2022-06-27 | 2024-06-27 | Level 3 | F | 2024-02-16 | 2027-06-27 | Level 3 | GO 165 Inspection
123952126 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-08-30 | 2027-06-29 | Level 3 | GO 165 Inspection
123952328 | anchor/guy | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2024-02-12 | 2025-06-29 | Level 2 | GO 165 Inspection
123952429 | other | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-09 | 2027-06-21 | Level 3 | Standards change
123952671 | anchor/guy | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2024-12-21 | 2023-06-29 | Level 2 | Field Safety Reassessment
123952964 | insulator and brushing | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2024-08-30 | 2027-06-29 | Level 3 | GO 165 Inspection
123952972 | pole | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-09-08 | 2025-06-29 | Level 2 | Standards change
123953427 | other | HFTD Tier 3 | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2024-04-06 | 2027-06-13 | Level 3 | Standards change
123953501 | other | HFTD Tier 2 | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2024-05-23 | 2027-06-23 | Level 3 | GO 165 Inspection
123954140 | anchor/guy | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-01-18 | 2025-06-29 | Level 2 | Standards change
123955209 | pole | Non-HFTD | Transmission | 2022-06-10 | 2023-06-10 | Level 2 | E | 2024-08-10 | 2025-06-10 | Level 2 | GO 165 Inspection
123955444 | other | HFTD Tier 3 | Transmission | 2022-06-13 | 2022-09-13 | Level 2 | E | 2024-07-11 | 2022-09-13 | Level 2 | GO 165 Inspection
123955687 | pole | HFTD Tier 3 | Transmission | 2022-06-02 | 2024-06-02 | Level 3 | F | 2024-03-18 | 2027-06-02 | Level 3 | GO 165 Inspection
123956365 | insulator and brushing | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-02-10 | 2025-06-29 | Level 2 | Standards change
123956417 | anchor/guy | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-08-16 | 2027-06-29 | Level 3 | Standards change
123957001 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-04-06 | 2027-06-29 | Level 3 | Standards change
123957619 | anchor/guy | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-01-10 | 2027-06-21 | Level 3 | Standards change
123958740 | other | HFTD Tier 3 | Transmission | 2022-06-27 | 2024-06-27 | Level 3 | F | 2024-04-03 | 2027-06-27 | Level 3 | Standards change
123960169 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2024-04-23 | 2027-06-30 | Level 3 | GO 165 Inspection
123960383 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2023-01-19 | 2027-06-30 | Level 3 | Standards change
123960817 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2023-12-08 | 2027-06-30 | Level 3 | Standards change
123960829 | other | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-02-10 | 2027-06-30 | Level 3 | Standards change
123961376 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-07-31 | 2025-06-30 | Level 2 | Standards change
123962317 | insulator and brushing | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-03 | 2027-06-30 | Level 3 | Standards change
123962558 | splice | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-01-19 | 2025-06-30 | Level 2 | Standards change
123962638 | other | HFTD Tier 2 | Transmission | 2022-06-09 | 2024-06-09 | Level 3 | F | 2023-03-30 | 2027-06-09 | Level 3 | Standards change
123962640 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2023-01-17 | 2027-06-30 | Level 3 | Standards change
123962945 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-12-07 | 2025-06-30 | Level 2 | Field Safety Reassessment
123962979 | other | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-07-13 | 2025-06-30 | Level 2 | Standards change
123963431 | insulator and brushing | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-03 | 2027-06-30 | Level 3 | Standards change
123963604 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-01-31 | 2025-06-30 | Level 2 | GO 165 Inspection
123963617 | other | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-10-21 | 2027-06-30 | Level 3 | GO 165 Inspection
123964170 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2023-08-28 | 2027-06-30 | Level 3 | Standards change
123964515 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-07-12 | 2025-06-30 | Level 2 | Standards change
123965147 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-01-02 | 2025-06-30 | Level 2 | Standards change
123965465 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-09-01 | 2025-06-30 | Level 2 | Standards change
123966820 | other | HFTD Tier 2 | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2023-02-09 | 2027-06-22 | Level 3 | Standards change
123967348 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-01-10 | 2025-06-30 | Level 2 | Standards change
123968880 | anchor/guy | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2023-02-23 | 2025-06-16 | Level 2 | Standards change
123968955 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-04-06 | 2027-07-01 | Level 3 | Standards change
123969129 | anchor/guy | HFTD Tier 2 | Transmission | 2022-06-14 | 2024-06-14 | Level 3 | F | 2024-01-09 | 2027-06-14 | Level 3 | Standards change
123969255 | pole | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-01-19 | 2025-07-01 | Level 2 | Standards change
123969721 | pole | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-07-19 | 2025-06-29 | Level 2 | Standards change
123969731 | anchor/guy | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-07-28 | 2025-06-29 | Level 2 | Standards change
123969737 | pole | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-01-18 | 2025-07-01 | Level 2 | Standards change
123969896 | pole | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-01-19 | 2025-07-01 | Level 2 | Standards change
123969918 | insulator and brushing | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2024-08-29 | 2025-07-01 | Level 2 | GO 165 Inspection
123970377 | anchor/guy | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-01-19 | 2027-07-01 | Level 3 | Standards change
123970617 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-04-06 | 2027-07-01 | Level 3 | Standards change
123970782 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-08-20 | 2027-07-01 | Level 3 | GO 165 Inspection
123971085 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2023-07-12 | 2027-07-01 | Level 3 | Standards change
123971782 | other | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-01-10 | 2025-07-01 | Level 2 | Standards change
123972356 | other | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2024-08-16 | 2025-07-01 | Level 2 | GO 165 Inspection
123972486 | pole | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2024-07-18 | 2025-06-15 | Level 2 | GO 165 Inspection
123972487 | splice | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-02-28 | 2025-06-15 | Level 2 | Standards change
123972560 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-01-19 | 2027-07-01 | Level 3 | Standards change
123972668 | insulator and brushing | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-08-01 | 2025-07-01 | Level 2 | Standards change
123973263 | other | HFTD Tier 2 | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2023-03-03 | 2027-06-30 | Level 3 | Standards change
123973506 | pole | HFTD Tier 3 | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2024-06-11 | 2027-06-13 | Level 3 | GO 165 Inspection
123973569 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2024-04-06 | 2027-06-22 | Level 3 | Standards change
123974300 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-04-06 | 2027-07-01 | Level 3 | Standards change
123974854 | pole | HFTD Tier 2 | Transmission | 2022-06-09 | 2024-06-09 | Level 3 | F | 2024-05-08 | 2027-06-09 | Level 3 | GO 165 Inspection
123977247 | other | HFTD Tier 3 | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2023-05-10 | 2027-06-13 | Level 3 | Standards change
123980799 | pole | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2024-08-20 | 2025-07-02 | Level 2 | GO 165 Inspection
123980812 | anchor/guy | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-02-20 | 2027-06-30 | Level 3 | Standards change
123980853 | pole | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-01-19 | 2025-07-02 | Level 2 | Standards change
123980939 | other | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-01-10 | 2025-07-02 | Level 2 | Standards change
123980953 | other | HFTD Tier 2 | Transmission | 2022-06-28 | 2024-06-28 | Level 3 | F | 2024-06-08 | 2027-06-28 | Level 3 | GO 165 Inspection
123980956 | other | HFTD Tier 3 | Transmission | 2022-06-16 | 2024-06-16 | Level 3 | F | 2024-04-06 | 2027-06-16 | Level 3 | Standards change
123981280 | other | Non-HFTD | Transmission | 2022-06-07 | 2025-06-07 | Level 2 | E | 2024-10-25 | 2027-06-07 | Level 3 | GO 165 Inspection
123981341 | splice | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-03-10 | 2025-07-01 | Level 2 | Standards change
123981419 | pole | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2024-08-19 | 2025-07-02 | Level 2 | GO 165 Inspection
123981449 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-11-20 | 2027-06-29 | Level 3 | GO 165 Inspection
123981659 | pole | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2024-02-12 | 2025-06-29 | Level 2 | Standards change
123981679 | other | Non-HFTD | Transmission | 2022-07-01 | 2027-07-01 | Level 3 | F |  | 2027-07-01 | Level 3
123982009 | pole | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-03-02 | 2025-07-01 | Level 2 | Standards change
123982099 | other | Non-HFTD | Transmission | 2022-07-02 | 2024-07-02 | Level 3 | F | 2024-04-06 | 2027-07-02 | Level 3 | Standards change
123982577 | insulator and brushing | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-02-13 | 2025-06-30 | Level 2 | Standards change
123982589 | pole | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2024-01-03 | 2025-07-02 | Level 2 | Standards change
123982832 | other | HFTD Tier 3 | Transmission | 2022-06-13 | 2024-06-13 | Level 3 | F | 2024-04-06 | 2027-06-13 | Level 3 | Standards change
123982842 | pole | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2024-01-09 | 2027-07-01 | Level 3 | Standards change
123983207 | other | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-02-10 | 2027-07-02 | Level 3 | Standards change
123983285 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-01-03 | 2025-06-30 | Level 2 | Standards change
123983309 | insulator and brushing | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2024-09-05 | 2025-07-02 | Level 2 | GO 165 Inspection
123983348 | other | HFTD Tier 3 | Transmission | 2022-06-27 | 2024-06-27 | Level 3 | F | 2023-06-26 | 2027-06-27 | Level 3 | Standards change
123983568 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-09 | 2027-06-30 | Level 3 | Standards change
123983730 | other | Non-HFTD | Transmission | 2022-07-02 | 2024-07-02 | Level 3 | F | 2024-04-06 | 2027-07-02 | Level 3 | Standards change
123983798 | other | Non-HFTD | Transmission | 2022-07-02 | 2024-07-02 | Level 3 | F | 2024-04-06 | 2027-07-02 | Level 3 | Standards change
123984636 | other | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-02-10 | 2027-07-02 | Level 3 | Standards change
123985392 | other | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2023-03-15 | 2025-06-08 | Level 2 | Standards change
123985420 | other | Non-HFTD | Transmission | 2022-07-02 | 2024-07-02 | Level 3 | F | 2024-04-06 | 2027-07-02 | Level 3 | Standards change
123985460 | other | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2024-03-19 | 2025-06-16 | Level 2 | GO 165 Inspection
123985462 | pole | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2024-03-19 | 2025-06-16 | Level 2 | GO 165 Inspection
123985653 | other | Non-HFTD | Transmission | 2022-06-03 | 2024-06-03 | Level 3 | F | 2024-02-14 | 2027-06-03 | Level 3 | Standards change
123985710 | pole | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2023-03-20 | 2025-06-08 | Level 2 | Standards change
123986728 | insulator and brushing | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2023-02-15 | 2027-07-03 | Level 3 | Standards change
123986858 | other | Non-HFTD | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-04-06 | 2027-07-03 | Level 3 | Standards change
123986907 | other | Non-HFTD | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-09-26 | 2027-07-03 | Level 3 | GO 165 Inspection
123986918 | insulator and brushing | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2024-06-04 | 2027-07-03 | Level 3 | GO 165 Inspection
123986941 | anchor/guy | Non-HFTD | Transmission | 2022-07-03 | 2025-07-03 | Level 2 | E | 2024-07-22 | 2023-01-03 | Level 2 | GO 165 Inspection
123987225 | other | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2023-02-16 | 2025-07-03 | Level 2 | Standards change
123987315 | insulator and brushing | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2024-06-04 | 2025-07-03 | Level 2 | GO 165 Inspection
123987373 | other | Non-HFTD | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-04-06 | 2027-07-03 | Level 3 | Standards change
123987412 | insulator and brushing | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2024-06-04 | 2025-07-03 | Level 2 | GO 165 Inspection
123987457 | other | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2023-01-18 | 2025-07-03 | Level 2 | Standards change
123987496 | other | Non-HFTD | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-04-06 | 2027-07-03 | Level 3 | Standards change
123987564 | insulator and brushing | Non-HFTD | Transmission | 2022-07-03 | 2023-07-03 | Level 2 | E | 2023-01-20 | 2025-07-03 | Level 2 | Standards change
123988264 | other | Non-HFTD | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-01-03 | 2027-07-03 | Level 3 | Standards change
123988266 | other | Non-HFTD | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-01-03 | 2027-07-03 | Level 3 | Standards change
123990695 | insulator and brushing | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-06-05 | 2025-07-04 | Level 2 | GO 165 Inspection
123990709 | pole | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-01-03 | 2025-07-04 | Level 2 | Standards change
123991061 | pole | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-08-15 | 2025-07-04 | Level 2 | GO 165 Inspection
123991118 | pole | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-01-03 | 2025-07-04 | Level 2 | Standards change
123991136 | other | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2023-02-10 | 2027-07-04 | Level 3 | Standards change
123991203 | other | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-09-25 | 2025-07-04 | Level 2 | GO 165 Inspection
123991340 | pole | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2023-07-13 | 2025-07-04 | Level 2 | Standards change
123991559 | other | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-09-27 | 2025-07-04 | Level 2 | GO 165 Inspection
123991701 | pole | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2023-01-19 | 2025-07-04 | Level 2 | Standards change
123991755 | pole | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2023-01-19 | 2025-07-04 | Level 2 | Standards change
123992098 | other | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2024-09-28 | 2025-07-04 | Level 2 | GO 165 Inspection
123992218 | insulator and brushing | Non-HFTD | Transmission | 2022-07-04 | 2023-07-04 | Level 2 | E | 2023-02-10 | 2027-07-04 | Level 3 | Standards change
123993909 | other | HFTD Tier 2 | Transmission | 2022-06-26 | 2024-06-26 | Level 3 | F | 2024-04-08 | 2027-06-26 | Level 3 | GO 165 Inspection
123994062 | other | HFTD Tier 2 | Transmission | 2022-06-11 | 2024-06-11 | Level 3 | F | 2024-05-18 | 2027-06-11 | Level 3 | GO 165 Inspection
123994437 | pole | HFTD Tier 2 | Transmission | 2022-07-03 | 2024-07-03 | Level 3 | F | 2024-05-06 | 2027-07-03 | Level 3 | GO 165 Inspection
123994510 | other | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-02-14 | 2025-06-29 | Level 2 | Standards change
123994828 | pole | HFTD Tier 3 | Transmission | 2022-06-09 | 2024-06-09 | Level 3 | F | 2024-03-08 | 2027-06-09 | Level 3 | GO 165 Inspection
123995516 | switch | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2024-09-03 | 2025-07-05 | Level 2 | Field Safety Reassessment
123995653 | pole | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2023-02-15 | 2025-07-05 | Level 2 | Standards change
123996342 | other | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-03-08 | 2027-07-01 | Level 3 | Standards change
123998483 | anchor/guy | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-05-22 | 2025-06-30 | Level 2 | Standards change
124002717 | insulator and brushing | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2024-11-19 | 2027-07-01 | Level 3 | GO 165 Inspection
124004640 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-07-11 | 2025-06-30 | Level 2 | Standards change
124006052 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2024-04-06 | 2027-07-06 | Level 3 | Standards change
124006838 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2023-03-30 | 2027-07-06 | Level 3 | Standards change
124009044 | insulator and brushing | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2023-12-08 | 2025-06-08 | Level 2 | Standards change
124009272 | insulator and brushing | Non-HFTD | Transmission | 2022-07-06 | 2025-07-06 | Level 2 | E | 2024-07-11 | 2023-07-06 | Level 2 | GO 165 Inspection
124009551 | pole | Non-HFTD | Transmission | 2022-07-06 | 2027-07-06 | Level 3 | F | 2024-05-02 | 2027-07-06 | Level 3 | GO 165 Inspection
124009648 | other | Non-HFTD | Transmission | 2022-06-08 | 2024-06-08 | Level 3 | F | 2024-04-06 | 2027-06-08 | Level 3 | Standards change
124009723 | pole | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2023-12-11 | 2025-06-07 | Level 2 | Standards change
124009928 | pole | Non-HFTD | Transmission | 2022-06-08 | 2024-06-08 | Level 3 | F | 2023-12-12 | 2027-06-08 | Level 3 | Standards change
124009953 | crossarm | Non-HFTD | Transmission | 2022-06-16 | 2023-06-16 | Level 2 | E | 2023-02-24 | 2025-06-16 | Level 2 | Standards change
124010122 | pole | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-01-18 | 2027-06-07 | Level 3 | Standards change
124010333 | other | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-01-09 | 2027-06-21 | Level 3 | Standards change
124010490 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2024-04-06 | 2027-06-21 | Level 3 | Standards change
124010607 | other | Non-HFTD | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2024-04-06 | 2027-06-23 | Level 3 | Standards change
124010698 | insulator and brushing | Non-HFTD | Transmission | 2022-05-31 | 2023-05-31 | Level 2 | E | 2024-04-04 | 2025-05-31 | Level 2 | GO 165 Inspection
124010740 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-09 | 2025-06-21 | Level 2 | Standards change
124010830 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-09 | 2025-06-21 | Level 2 | Standards change
124011992 | other | Non-HFTD | Transmission | 2022-06-03 | 2024-06-03 | Level 3 | F | 2023-03-17 | 2027-06-03 | Level 3 | Standards change
124012235 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | Standards change
124012328 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2024-01-16 | 2027-06-22 | Level 3 | Standards change
124012839 | crossarm | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2023-03-20 | 2025-05-27 | Level 2 | Standards change
124013516 | pole | Non-HFTD | Transmission | 2022-06-03 | 2023-06-03 | Level 2 | E | 2024-10-09 | 2025-06-03 | Level 2 | GO 165 Inspection
124015587 | insulator and brushing | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-04-07 | 2025-06-21 | Level 2 | Standards change
124015675 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-04-06 | 2027-06-07 | Level 3 | Standards change
124016015 | pole | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-03-10 | 2025-06-24 | Level 2 | Standards change
124018182 | insulator and brushing | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2024-01-29 | 2025-07-06 | Level 2 | Standards change
124019548 | anchor/guy | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2024-08-05 | 2027-07-07 | Level 3 | GO 165 Inspection
124021949 | pole | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2023-03-07 | 2025-07-05 | Level 2 | Standards change
124022547 | anchor/guy | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2024-06-24 | 2027-06-07 | Level 3 | GO 165 Inspection
124022549 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2023-03-29 | 2027-06-07 | Level 3 | Standards change
124022822 | other | Non-HFTD | Transmission | 2022-06-07 | 2024-06-07 | Level 3 | F | 2024-08-15 | 2027-06-07 | Level 3 | GO 165 Inspection
124022824 | insulator and brushing | Non-HFTD | Transmission | 2022-06-08 | 2023-06-08 | Level 2 | E | 2023-12-11 | 2025-06-08 | Level 2 | Standards change
124023070 | other | Non-HFTD | Transmission | 2022-06-28 | 2024-06-28 | Level 3 | F | 2024-04-06 | 2027-06-28 | Level 3 | Standards change
124023285 | pole | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-07-11 | 2025-06-29 | Level 2 | Standards change
124023368 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-01-03 | 2025-06-30 | Level 2 | Standards change
124023421 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-07-14 | 2025-06-30 | Level 2 | Standards change
124025702 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-01-17 | 2027-07-01 | Level 3 | Standards change
124025950 | insulator and brushing | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2024-09-03 | 2025-07-07 | Level 2 | GO 165 Inspection
124026197 | other | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-03-08 | 2027-07-02 | Level 3 | Standards change
124026199 | insulator and brushing | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2024-02-09 | 2027-07-07 | Level 3 | GO 165 Inspection
124026281 | pole | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2023-03-07 | 2025-07-05 | Level 2 | Standards change
124026438 | pole | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-01-09 | 2027-07-01 | Level 3 | Standards change
124026491 | anchor/guy | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2023-03-15 | 2027-06-29 | Level 3 | Standards change
124026495 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-09 | 2025-06-30 | Level 2 | Standards change
124026798 | other | HFTD Tier 3 | Transmission | 2022-06-17 | 2024-06-17 | Level 3 | F | 2024-03-08 | 2027-06-17 | Level 3 | GO 165 Inspection
124026859 | other | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-03-07 | 2027-07-02 | Level 3 | Standards change
124028984 | anchor/guy | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-02-28 | 2025-07-01 | Level 2 | Standards change
124029288 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-07-31 | 2025-07-06 | Level 2 | Standards change
124029391 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2024-07-11 | 2027-07-06 | Level 3 | GO 165 Inspection
124029884 | other | Non-HFTD | Transmission | 2022-06-16 | 2024-06-16 | Level 3 | F | 2024-04-06 | 2027-06-16 | Level 3 | Standards change
124030006 | other | Non-HFTD | Transmission | 2022-06-16 | 2024-06-16 | Level 3 | F | 2023-04-05 | 2027-06-16 | Level 3 | Standards change
124032532 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2023-07-07 | 2027-07-01 | Level 3 | Standards change
124032968 | other | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-01-18 | 2025-07-06 | Level 2 | Standards change
124033006 | other | Non-HFTD | Transmission | 2022-06-20 | 2024-06-20 | Level 3 | F | 2024-01-29 | 2027-06-20 | Level 3 | Standards change
124033080 | insulator and brushing | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2024-02-02 | 2027-07-02 | Level 3 | Standards change
124033468 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2024-04-06 | 2027-07-06 | Level 3 | Standards change
124033563 | other | Non-HFTD | Transmission | 2022-06-20 | 2024-06-20 | Level 3 | F | 2023-04-07 | 2027-06-20 | Level 3 | Standards change
124050220 | other | Non-HFTD | Transmission | 2022-07-02 | 2024-07-02 | Level 3 | F | 2024-04-06 | 2027-07-02 | Level 3 | Standards change
124050416 | other | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-03-07 | 2025-07-02 | Level 2 | Standards change
124050633 | anchor/guy | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2023-01-19 | 2025-07-05 | Level 2 | Standards change
124050888 | insulator and brushing | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-01-20 | 2025-07-08 | Level 2 | Standards change
124052690 | insulator and brushing | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-02-21 | 2025-07-07 | Level 2 | Standards change
124052949 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2024-04-06 | 2027-07-06 | Level 3 | Standards change
124055199 | other | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2024-09-04 | 2027-07-08 | Level 3 | GO 165 Inspection
124055423 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2024-01-09 | 2027-07-06 | Level 3 | Standards change
124056150 | insulator and brushing | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-01-19 | 2025-07-11 | Level 2 | Standards change
124056465 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-03-15 | 2025-07-06 | Level 2 | Standards change
124059367 | insulator and brushing | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-03-09 | 2025-07-08 | Level 2 | Standards change
124060647 | other | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-13 | 2025-07-07 | Level 2 | Standards change
124061096 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-07 | 2025-07-07 | Level 2 | Standards change
124062365 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2024-04-06 | 2027-06-21 | Level 3 | Standards change
124065156 | insulator and brushing | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-02-06 | 2025-07-11 | Level 2 | Standards change
124066061 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124066296 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-10 | 2025-06-21 | Level 2 | Standards change
124066338 | other | Non-HFTD | Transmission | 2022-06-07 | 2023-06-07 | Level 2 | E | 2023-02-23 | 2025-06-07 | Level 2 | Standards change
124066451 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-07 | 2025-07-07 | Level 2 | Standards change
124066554 | insulator and brushing | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-13 | 2025-07-07 | Level 2 | Standards change
124066596 | other | HFTD Tier 3 | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2023-05-02 | 2027-06-24 | Level 3 | Standards change
124066633 | anchor/guy | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-01-25 | 2025-07-08 | Level 2 | Standards change
124067010 | pole | HFTD Tier 2 | Transmission | 2022-06-18 | 2024-06-18 | Level 3 | F | 2024-05-21 | 2027-06-18 | Level 3 | GO 165 Inspection
124067052 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-04-07 | 2027-06-21 | Level 3 | Standards change
124067074 | pole | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2024-11-15 | 2025-07-08 | Level 2 | GO 165 Inspection
124067255 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2024-04-06 | 2027-07-01 | Level 3 | Standards change
124067758 | insulator and brushing | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-01-25 | 2025-07-12 | Level 2 | Standards change
124068934 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-07 | 2025-07-07 | Level 2 | Standards change
124069192 | other | HFTD Tier 2 | Transmission | 2022-06-25 | 2024-06-25 | Level 3 | F | 2024-05-21 | 2027-06-25 | Level 3 | GO 165 Inspection
124070234 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-08 | 2025-07-07 | Level 2 | Standards change
124071705 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-01-30 | 2025-07-13 | Level 2 | Standards change
124072444 | insulator and brushing | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-03-09 | 2025-07-13 | Level 2 | Standards change
124072469 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124075388 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-09-08 | 2025-07-07 | Level 2 | Field Safety Reassessment
124075618 | other | HFTD Tier 2 | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2024-04-06 | 2027-06-23 | Level 3 | Standards change
124075768 | other | HFTD Tier 2 | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2023-05-30 | 2027-06-23 | Level 3 | GO 165 Inspection
124075805 | splice | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2024-07-11 | 2025-06-22 | Level 2 | GO 165 Inspection
124075873 | pole | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-01-20 | 2025-07-08 | Level 2 | Standards change
124075900 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-08 | 2025-07-07 | Level 2 | Standards change
124076551 | other | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-03-09 | 2027-07-12 | Level 3 | Standards change
124076627 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-01-30 | 2025-07-13 | Level 2 | Standards change
124076711 | pole | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-09-08 | 2025-07-07 | Level 2 | Field Safety Reassessment
124076761 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124077102 | anchor/guy | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-02-09 | 2027-07-02 | Level 3 | Standards change
124077246 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-03-24 | 2025-07-12 | Level 2 | Standards change
124077850 | pole | Non-HFTD | Transmission | 2022-07-13 | 2025-07-13 | Level 2 | E | 2024-06-24 | 2023-07-13 | Level 2 | GO 165 Inspection
124078137 | crossarm | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-03-24 | 2025-07-14 | Level 2 | Standards change
124078649 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2024-01-30 | 2027-07-14 | Level 3 | Standards change
124078968 | insulator and brushing | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-03-09 | 2027-07-13 | Level 3 | Standards change
124079358 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2024-11-12 | 2025-07-14 | Level 2 | GO 165 Inspection
124079417 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-02-16 | 2027-07-14 | Level 3 | Standards change
124079596 | insulator and brushing | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-03-09 | 2025-07-14 | Level 2 | Standards change
124079999 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2024-10-25 | 2023-07-18 | Level 2 | GO 165 Inspection
124080313 | other | Non-HFTD | Transmission | 2022-06-21 | 2027-06-21 | Level 3 | F |  | 2027-06-21 | Level 3
124081079 | other | HFTD Tier 2 | Transmission | 2022-07-10 | 2024-07-10 | Level 3 | F | 2024-06-12 | 2027-07-10 | Level 3 | GO 165 Inspection
124083924 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-07-27 | 2025-06-21 | Level 2 | Standards change
124086081 | insulator and brushing | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-03-08 | 2025-07-12 | Level 2 | Standards change
124086101 | other | HFTD Tier 2 | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2023-06-20 | 2027-06-24 | Level 3 | Standards change
124086122 | pole | HFTD Tier 2 | Transmission | 2022-06-15 | 2024-06-15 | Level 3 | F | 2024-04-03 | 2027-06-15 | Level 3 | GO 165 Inspection
124086240 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-03-30 | 2027-06-21 | Level 3 | Standards change
124086385 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2024-01-16 | 2027-06-22 | Level 3 | Standards change
124086862 | pole | Non-HFTD | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2023-07-12 | 2027-06-23 | Level 3 | Standards change
124086893 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-04-19 | 2025-07-13 | Level 2 | Standards change
124087488 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-12-06 | 2025-07-06 | Level 2 | Standards change
124087489 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-12-06 | 2025-07-06 | Level 2 | Standards change
124087765 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-02-28 | 2025-06-21 | Level 2 | Standards change
124088357 | other | HFTD Tier 2 | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2023-03-07 | 2027-06-24 | Level 3 | Standards change
124088386 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-02-10 | 2025-06-22 | Level 2 | Standards change
124088931 | pole | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-03-09 | 2025-07-11 | Level 2 | Standards change
124089091 | pole | HFTD Tier 2 | Transmission | 2022-07-09 | 2024-07-09 | Level 3 | F | 2024-02-10 | 2027-07-09 | Level 3 | GO 165 Inspection
124089277 | other | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2024-01-04 | 2027-07-15 | Level 3 | Standards change
124089597 | other | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-03-20 | 2027-06-15 | Level 3 | Standards change
124090064 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-10 | 2025-06-21 | Level 2 | Standards change
124090304 | splice | Non-HFTD | Transmission | 2022-06-15 | 2023-06-15 | Level 2 | E | 2023-03-09 | 2025-06-15 | Level 2 | Standards change
124091258 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124092125 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2023-01-27 | 2027-06-22 | Level 3 | Standards change
124092883 | splice | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-09 | 2025-06-21 | Level 2 | Standards change
124092885 | other | Non-HFTD | Transmission | 2022-07-11 | 2027-07-11 | Level 2 | E | 2022-08-20 | 2027-07-11 | Level 3 | GO 165 Inspection
124093268 | other | Non-HFTD | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2023-07-06 | 2027-06-23 | Level 3 | Standards change
124093322 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-07-14 | 2027-06-21 | Level 3 | Standards change
124094972 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-03-02 | 2025-07-12 | Level 2 | Standards change
124104629 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-03-09 | 2025-07-15 | Level 2 | Standards change
124105487 | other | HFTD Tier 2 | Transmission | 2022-06-28 | 2024-06-28 | Level 3 | F | 2024-05-02 | 2027-06-28 | Level 3 | GO 165 Inspection
124105681 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-04-26 | 2027-07-18 | Level 3 | GO 165 Inspection
124107849 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2024-07-26 | 2025-07-15 | Level 2 | GO 165 Inspection
124108083 | insulator and brushing | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-03-10 | 2025-07-18 | Level 2 | Standards change
124108119 | crossarm | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-01-09 | 2025-07-15 | Level 2 | Standards change
124108213 | insulator and brushing | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-01-09 | 2025-07-15 | Level 2 | Standards change
124109898 | other | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-08-23 | 2027-06-24 | Level 3 | Standards change
124110408 | insulator and brushing | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-12-02 | 2025-07-15 | Level 2 | GO 165 Inspection
124111418 | insulator and brushing | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-01-04 | 2025-07-18 | Level 2 | Standards change
124111716 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2024-01-04 | 2025-06-22 | Level 2 | Standards change
124111772 | anchor/guy | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-01-10 | 2027-07-18 | Level 3 | Standards change
124111828 | insulator and brushing | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2024-05-09 | 2025-07-15 | Level 2 | GO 165 Inspection
124112221 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124112293 | pole | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-01-10 | 2025-06-24 | Level 2 | Standards change
124112478 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-04-06 | 2027-07-12 | Level 3 | Standards change
124112532 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2024-04-06 | 2027-06-22 | Level 3 | Standards change
124112539 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-04-06 | 2027-07-12 | Level 3 | Standards change
124113396 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-03-30 | 2025-06-21 | Level 2 | Standards change
124114411 | pole | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-05-17 | 2025-06-24 | Level 2 | Standards change
124114417 | pole | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2023-03-10 | 2025-06-24 | Level 2 | Standards change
124116524 | anchor/guy | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-07-26 | 2027-07-18 | Level 3 | GO 165 Inspection
124117459 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-02-28 | 2025-07-19 | Level 2 | Standards change
124117914 | insulator and brushing | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-10-06 | 2025-07-18 | Level 2 | Standards change
124118622 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124119081 | other | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2024-09-30 | 2027-07-12 | Level 3 | GO 165 Inspection
124120704 | switch | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2024-12-23 | 2023-07-12 | Level 2 | Field Safety Reassessment
124120705 | other | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2024-01-04 | 2027-07-12 | Level 3 | Standards change
124121227 | pole | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-03-09 | 2027-06-29 | Level 3 | Standards change
124121872 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-17 | 2027-07-13 | Level 3 | Standards change
124121921 | anchor/guy | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-03-30 | 2027-06-21 | Level 3 | Standards change
124121983 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-02-28 | 2025-06-22 | Level 2 | Standards change
124122130 | other | Non-HFTD | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2024-04-06 | 2027-06-24 | Level 3 | Standards change
124123128 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-01-18 | 2025-06-22 | Level 2 | Standards change
124123185 | other | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-01-18 | 2025-06-22 | Level 2 | Standards change
124123750 | insulator and brushing | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2024-08-26 | 2025-07-19 | Level 2 | GO 165 Inspection
124123874 | splice | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-04-05 | 2025-06-21 | Level 2 | Standards change
124125927 | other | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-03-10 | 2027-07-19 | Level 3 | Standards change
124126101 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-08-23 | 2023-07-19 | Level 2 | Standards change
124127198 | other | HFTD Tier 2 | Transmission | 2022-06-23 | 2027-06-23 | Level 3 | F |  | 2027-06-23 | Level 3
124128367 | pole | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-12-12 | 2025-07-20 | Level 2 | Standards change
124130178 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2024-06-21 | 2027-07-14 | Level 3 | GO 165 Inspection
124130312 | crossarm | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2024-04-25 | 2025-07-15 | Level 2 | GO 165 Inspection
124131439 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-01-04 | 2025-07-18 | Level 2 | Standards change
124133224 | insulator and brushing | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-06-20 | 2025-07-20 | Level 2 | GO 165 Inspection
124134086 | anchor/guy | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-09-05 | 2023-07-20 | Level 2 | GO 165 Inspection
124134423 | other | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-03-20 | 2025-07-20 | Level 2 | Standards change
124134537 | pole | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-02-21 | 2027-07-20 | Level 3 | Standards change
124135884 | other | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-03-01 | 2027-07-20 | Level 3 | Standards change
124139930 | pole | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-01-30 | 2025-07-21 | Level 2 | Standards change
124140745 | other | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-01-04 | 2027-07-20 | Level 3 | Standards change
124140941 | other | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-03-15 | 2025-07-22 | Level 2 | Standards change
124141836 | insulator and brushing | Non-HFTD | Transmission | 2022-07-21 | 2022-10-21 | Level 2 | E | 2024-04-05 | 2022-10-21 | Level 2 | GO 165 Inspection
124141998 | other | HFTD Tier 2 | Transmission | 2022-06-25 | 2024-06-25 | Level 3 | F | 2024-04-06 | 2027-06-25 | Level 3 | Standards change
124142685 | crossarm | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-02-28 | 2025-07-15 | Level 2 | Standards change
124143244 | other | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-02-16 | 2025-07-21 | Level 2 | Standards change
124143449 | pole | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2024-01-04 | 2027-07-05 | Level 3 | Standards change
124143544 | pole | HFTD Tier 3 | Transmission | 2022-06-28 | 2024-06-28 | Level 3 | F | 2024-06-13 | 2027-06-28 | Level 3 | GO 165 Inspection
124143963 | anchor/guy | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-03-08 | 2025-07-22 | Level 2 | Standards change
124145500 | insulator and brushing | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-02-27 | 2025-07-21 | Level 2 | Standards change
124146568 | other | HFTD Tier 2 | Transmission | 2022-07-16 | 2024-07-16 | Level 3 | F | 2024-05-20 | 2027-07-16 | Level 3 | GO 165 Inspection
124146776 | pole | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-09-11 | 2025-07-22 | Level 2 | Standards change
124147525 | pole | HFTD Tier 2 | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2023-12-11 | 2027-07-14 | Level 3 | Standards change
124149511 | insulator and brushing | Non-HFTD | Transmission | 2022-07-23 | 2023-07-23 | Level 2 | E | 2024-01-04 | 2025-07-23 | Level 2 | Standards change
124151952 | pole | Non-HFTD | Transmission | 2022-07-24 | 2023-07-24 | Level 2 | E | 2024-06-29 | 2025-07-24 | Level 2 | GO 165 Inspection
124155845 | other | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2024-10-25 | 2027-07-22 | Level 3 | GO 165 Inspection
124156696 | insulator and brushing | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-02-08 | 2025-07-25 | Level 2 | GO 165 Inspection
124158059 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-04-06 | 2027-06-29 | Level 3 | Standards change
124158247 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-04-06 | 2027-06-29 | Level 3 | Standards change
124159218 | other | Non-HFTD | Transmission | 2022-07-25 | 2024-07-25 | Level 3 | F | 2023-01-26 | 2027-07-25 | Level 3 | Standards change
124160513 | other | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-11-04 | 2025-07-25 | Level 2 | GO 165 Inspection
124160755 | insulator and brushing | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-02-13 | 2025-07-25 | Level 2 | Standards change
124161028 | other | Non-HFTD | Transmission | 2022-07-25 | 2024-07-25 | Level 3 | F | 2024-08-16 | 2027-07-25 | Level 3 | GO 165 Inspection
124161904 | splice | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-10-03 | 2025-07-25 | Level 2 | Field Safety Reassessment
124162046 | anchor/guy | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-11-13 | 2027-07-25 | Level 3 | GO 165 Inspection
124162135 | other | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-02-03 | 2027-07-25 | Level 3 | Standards change
124162146 | insulator and brushing | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-03-10 | 2027-07-25 | Level 3 | Standards change
124162745 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124162964 | anchor/guy | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-01-30 | 2025-07-22 | Level 2 | Standards change
124162966 | anchor/guy | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-01-30 | 2025-07-22 | Level 2 | Standards change
124163674 | pole | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-03-09 | 2025-07-22 | Level 2 | Standards change
124164274 | other | Non-HFTD | Transmission | 2022-07-26 | 2024-07-26 | Level 3 | F | 2024-01-11 | 2027-07-26 | Level 3 | Standards change
124164689 | anchor/guy | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-01-30 | 2025-07-22 | Level 2 | Standards change
124165280 | other | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2024-08-12 | 2027-07-22 | Level 3 | GO 165 Inspection
124165739 | other | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-07-26 | 2027-07-26 | Level 3 | GO 165 Inspection
124166195 | other | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-02-14 | 2027-07-25 | Level 3 | Standards change
124166785 | pole | Non-HFTD | Transmission | 2022-06-12 | 2023-06-12 | Level 2 | E | 2023-01-20 | 2025-06-12 | Level 2 | Standards change
124167738 | insulator and brushing | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-10-29 | 2025-07-26 | Level 2 | GO 165 Inspection
124167815 | other | Non-HFTD | Transmission | 2022-07-26 | 2024-07-26 | Level 3 | F | 2023-11-30 | 2027-07-26 | Level 3 | Standards change
124168159 | other | Non-HFTD | Transmission | 2022-06-09 | 2023-06-09 | Level 2 | E | 2023-08-01 | 2025-06-09 | Level 2 | Standards change
124168448 | other | Non-HFTD | Transmission | 2022-06-27 | 2024-06-27 | Level 3 | F | 2024-06-27 | 2027-06-27 | Level 3 | GO 165 Inspection
124171584 | pole | Non-HFTD | Transmission | 2022-07-22 | 2024-07-22 | Level 3 | F | 2024-08-19 | 2027-07-22 | Level 3 | GO 165 Inspection
124172228 | other | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2024-09-26 | 2025-07-27 | Level 2 | GO 165 Inspection
124173454 | other | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2023-01-10 | 2027-07-27 | Level 3 | Standards change
124173689 | other | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2024-09-28 | 2025-07-27 | Level 2 | GO 165 Inspection
124174424 | insulator and brushing | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2024-09-28 | 2027-07-27 | Level 3 | GO 165 Inspection
124174651 | other | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2023-07-17 | 2025-07-26 | Level 2 | Standards change
124174653 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124174897 | other | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2023-01-10 | 2025-07-27 | Level 2 | Standards change
124175043 | other | Non-HFTD | Transmission | 2022-07-27 | 2024-07-27 | Level 3 | F | 2024-10-01 | 2027-07-27 | Level 3 | GO 165 Inspection
124175109 | other | Non-HFTD | Transmission | 2022-07-27 | 2024-07-27 | Level 3 | F | 2024-10-01 | 2027-07-27 | Level 3 | GO 165 Inspection
124175574 | anchor/guy | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-01-09 | 2027-07-20 | Level 3 | Standards change
124177879 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-28 | 2025-07-18 | Level 2 | Standards change
124177950 | other | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2024-01-04 | 2027-06-29 | Level 3 | Standards change
124178036 | other | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-02-16 | 2025-07-20 | Level 2 | Standards change
124178329 | other | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-04-06 | 2027-07-20 | Level 3 | Standards change
124178371 | other | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2023-02-10 | 2027-06-23 | Level 3 | Standards change
124178506 | other | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2023-01-20 | 2027-07-20 | Level 3 | Standards change
124179574 | switch | Non-HFTD | Transmission | 2022-07-28 | 2023-07-28 | Level 2 | E | 2023-03-13 | 2023-07-28 | Level 2 | Standards change
124179681 | pole | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2023-01-30 | 2025-07-26 | Level 2 | Standards change
124181092 | insulator and brushing | Non-HFTD | Transmission | 2022-07-28 | 2023-07-28 | Level 2 | E | 2023-03-16 | 2023-07-28 | Level 2 | Standards change
124186001 | other | Non-HFTD | Transmission | 2022-06-23 | 2024-06-23 | Level 3 | F | 2024-01-16 | 2027-06-23 | Level 3 | Standards change
124186380 | insulator and brushing | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-02-02 | 2027-06-21 | Level 3 | Standards change
124187014 | other | Non-HFTD | Transmission | 2022-06-24 | 2024-06-24 | Level 3 | F | 2024-04-06 | 2027-06-24 | Level 3 | Standards change
124187146 | other | HFTD Tier 2 | Transmission | 2022-07-28 | 2024-07-28 | Level 3 | F | 2024-04-06 | 2027-07-28 | Level 3 | Standards change
124187208 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2024-08-14 | 2025-06-22 | Level 2 | GO 165 Inspection
124187429 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-03-07 | 2025-07-15 | Level 2 | Standards change
124187449 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2023-03-21 | 2027-07-18 | Level 3 | Standards change
124187494 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-03-09 | 2025-07-06 | Level 2 | Standards change
124187653 | pole | Non-HFTD | Transmission | 2022-06-22 | 2023-06-22 | Level 2 | E | 2023-02-10 | 2025-06-22 | Level 2 | Standards change
124187658 | anchor/guy | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2024-01-10 | 2027-06-21 | Level 3 | Standards change
124187785 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124187809 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124187854 | pole | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2024-06-04 | 2025-06-29 | Level 2 | GO 165 Inspection
124187967 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-08-07 | 2025-06-21 | Level 2 | Standards change
124188038 | other | Non-HFTD | Transmission | 2022-06-22 | 2024-06-22 | Level 3 | F | 2023-07-26 | 2027-06-22 | Level 3 | Standards change
124188120 | other | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-07-26 | 2025-06-21 | Level 2 | Standards change
124190493 | other | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2023-05-03 | 2027-07-20 | Level 3 | Standards change
124190640 | pole | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-01-03 | 2027-07-20 | Level 3 | Standards change
124190680 | other | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2022-08-16 | 2027-06-30 | Level 3 | Standards change
124190909 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2024-04-06 | 2027-07-06 | Level 3 | Standards change
124190985 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-10 | 2027-06-30 | Level 3 | Standards change
124191119 | other | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-10-24 | 2027-07-25 | Level 3 | GO 165 Inspection
124191248 | insulator and brushing | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-01-31 | 2025-06-29 | Level 2 | Standards change
124191406 | other | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-01 | 2025-07-07 | Level 2 | Standards change
124191642 | anchor/guy | Non-HFTD | Transmission | 2022-07-06 | 2025-07-06 | Level 2 | E | 2024-07-11 | 2027-07-06 | Level 3 | GO 165 Inspection
124191777 | insulator and brushing | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-05-22 | 2027-06-30 | Level 3 | Standards change
124191964 | pole | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-08-14 | 2027-07-18 | Level 3 | GO 165 Inspection
124191969 | other | Non-HFTD | Transmission | 2022-06-21 | 2024-06-21 | Level 3 | F | 2023-04-05 | 2027-06-21 | Level 3 | Standards change
124192459 | splice | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2024-01-24 | 2025-06-24 | Level 2 | Standards change
124192650 | other | Non-HFTD | Transmission | 2022-07-15 | 2027-07-15 | Level 3 | F |  | 2027-07-15 | Level 3
124192829 | other | Non-HFTD | Transmission | 2022-06-28 | 2024-06-28 | Level 3 | F | 2023-07-13 | 2027-06-28 | Level 3 | Standards change
124193055 | other | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2024-04-06 | 2027-07-06 | Level 3 | Standards change
124193183 | pole | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-01-05 | 2025-07-26 | Level 2 | Standards change
124193600 | insulator and brushing | Non-HFTD | Transmission | 2022-07-28 | 2023-07-28 | Level 2 | E | 2023-03-24 | 2025-07-28 | Level 2 | Standards change
124193723 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124193953 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-01-02 | 2027-06-29 | Level 3 | Standards change
124194335 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124194532 | anchor/guy | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2023-03-01 | 2025-07-26 | Level 2 | Standards change
124194592 | pole | Non-HFTD | Transmission | 2022-06-28 | 2023-06-28 | Level 2 | E | 2023-07-27 | 2025-06-28 | Level 2 | Standards change
124194974 | splice | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2023-07-27 | 2025-06-21 | Level 2 | Standards change
124195071 | anchor/guy | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-09-29 | 2027-07-01 | Level 3 | Standards change
124195141 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-04-25 | 2025-06-21 | Level 2 | GO 165 Inspection
124195143 | pole | Non-HFTD | Transmission | 2022-06-21 | 2023-06-21 | Level 2 | E | 2024-04-25 | 2025-06-21 | Level 2 | GO 165 Inspection
124195434 | pole | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-12-07 | 2023-07-26 | Level 2 | Field Safety Reassessment
124197589 | pole | Non-HFTD | Transmission | 2022-07-30 | 2023-07-30 | Level 2 | E | 2024-01-16 | 2027-07-30 | Level 3 | Standards change
124197754 | pole | Non-HFTD | Transmission | 2022-07-30 | 2023-07-30 | Level 2 | E | 2024-02-02 | 2025-07-30 | Level 2 | Standards change
124197865 | other | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | Level 3 | F |  | 2027-06-30 | Level 3
124198554 | insulator and brushing | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2023-01-26 | 2025-07-29 | Level 2 | Standards change
124199181 | other | HFTD Tier 3 | Transmission | 2022-07-07 | 2024-07-07 | Level 3 | F | 2024-05-17 | 2027-07-07 | Level 3 | GO 165 Inspection
124201661 | pole | Non-HFTD | Transmission | 2022-07-31 | 2023-07-31 | Level 2 | E | 2023-01-30 | 2025-07-31 | Level 2 | Standards change
124202462 | insulator and brushing | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-08-11 | 2023-07-01 | Level 2 | Field Safety Reassessment
124202524 | pole | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2024-10-23 | 2023-01-21 | Level 2 | Field Safety Reassessment
124202666 | pole | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-07-21 | 2025-07-08 | Level 2 | Standards change
124203081 | other | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-04-22 | 2025-08-01 | Level 2 | GO 165 Inspection
124203340 | anchor/guy | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2023-11-30 | 2027-06-30 | Level 3 | Standards change
124203346 | other | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-09 | 2027-06-30 | Level 3 | Standards change
124204052 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-04-19 | 2025-08-01 | Level 2 | GO 165 Inspection
124204332 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-02-21 | 2025-08-01 | Level 2 | Standards change
124204486 | other | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-04-18 | 2025-08-01 | Level 2 | GO 165 Inspection
124204772 | pole | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2024-01-29 | 2025-07-22 | Level 2 | Standards change
124206524 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-07-21 | 2025-08-01 | Level 2 | Standards change
124209642 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-01-31 | 2025-08-01 | Level 2 | Standards change
124210101 | insulator and brushing | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-05-08 | 2025-08-02 | Level 2 | Standards change
124210748 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-04-04 | 2025-08-02 | Level 2 | Standards change
124211040 | other | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2024-06-17 | 2025-08-02 | Level 2 | GO 165 Inspection
124211213 | other | Non-HFTD | Transmission | 2022-07-01 | 2024-07-01 | Level 3 | F | 2023-07-07 | 2027-07-01 | Level 3 | Standards change
124211424 | insulator and brushing | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-08-01 | 2025-08-02 | Level 2 | Standards change
124212295 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-05-08 | 2025-06-30 | Level 2 | Standards change
124213140 | other | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2024-01-05 | 2027-07-08 | Level 3 | Standards change
124213664 | other | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-11-27 | 2025-08-02 | Level 2 | Standards change
124214833 | pole | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-01-05 | 2025-07-26 | Level 2 | Standards change
124214864 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2024-10-29 | 2023-08-02 | Level 2 | Field Safety Reassessment
124216551 | other | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2024-12-10 | 2027-07-06 | Level 3 | GO 165 Inspection
124216642 | other | Non-HFTD | Transmission | 2022-07-05 | 2023-07-05 | Level 2 | E | 2023-01-19 | 2025-07-05 | Level 2 | Standards change
124216932 | insulator and brushing | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-02-28 | 2027-07-11 | Level 3 | Standards change
124217243 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124217488 | other | Non-HFTD | Transmission | 2022-08-03 | 2024-08-03 | Level 3 | F | 2024-01-11 | 2027-08-03 | Level 3 | Standards change
124218555 | other | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-03-08 | 2027-07-12 | Level 3 | Standards change
124218675 | other | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-01-26 | 2025-08-03 | Level 2 | Standards change
124218880 | insulator and brushing | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-01-09 | 2025-06-29 | Level 2 | Standards change
124219024 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-04-06 | 2027-07-12 | Level 3 | Standards change
124219883 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-01-30 | 2025-06-30 | Level 2 | Standards change
124220108 | anchor/guy | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-05-16 | 2023-08-03 | Level 2 | Standards change
124220521 | other | Non-HFTD | Transmission | 2022-07-07 | 2024-07-07 | Level 3 | F | 2024-04-06 | 2027-07-07 | Level 3 | Standards change
124221498 | insulator and brushing | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-02-27 | 2025-07-06 | Level 2 | Standards change
124222027 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-12-20 | 2025-07-06 | Level 2 | Standards change
124224564 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-03-03 | 2025-07-06 | Level 2 | Standards change
124224774 | anchor/guy | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2024-01-22 | 2027-07-12 | Level 3 | Standards change
124225584 | other | Non-HFTD | Transmission | 2022-08-04 | 2024-08-04 | Level 3 | F | 2024-10-09 | 2027-08-04 | Level 3 | GO 165 Inspection
124225638 | pole | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-03-09 | 2027-06-30 | Level 3 | Standards change
124226015 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-07-27 | 2025-08-04 | Level 2 | Standards change
124226083 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124226172 | other | Non-HFTD | Transmission | 2022-06-29 | 2024-06-29 | Level 3 | F | 2024-01-02 | 2027-06-29 | Level 3 | Standards change
124226583 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-02-06 | 2025-08-04 | Level 2 | Standards change
124226605 | other | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2023-02-27 | 2025-06-30 | Level 2 | Standards change
124226632 | insulator and brushing | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2024-07-30 | 2025-08-04 | Level 2 | GO 165 Inspection
124226768 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2024-01-05 | 2025-08-04 | Level 2 | Standards change
124227239 | other | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-09 | 2025-08-04 | Level 2 | Standards change
124227773 | other | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-02-01 | 2027-07-07 | Level 3 | Standards change
124228075 | other | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-02-28 | 2027-07-07 | Level 3 | Standards change
124228229 | insulator and brushing | Non-HFTD | Transmission | 2022-06-30 | 2023-06-30 | Level 2 | E | 2024-04-15 | 2025-06-30 | Level 2 | GO 165 Inspection
124228290 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2024-04-06 | 2027-06-30 | Level 3 | Standards change
124228462 | other | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-03-08 | 2027-07-08 | Level 3 | Standards change
124229147 | other | Non-HFTD | Transmission | 2022-06-30 | 2024-06-30 | Level 3 | F | 2024-04-06 | 2027-06-30 | Level 3 | Standards change
124233132 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124233181 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124233203 | pole | Non-HFTD | Transmission | 2022-07-01 | 2023-07-01 | Level 2 | E | 2023-03-09 | 2025-07-01 | Level 2 | Standards change
124233218 | insulator and brushing | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-03-21 | 2027-07-14 | Level 3 | Standards change
124233286 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-04-06 | 2027-07-18 | Level 3 | Standards change
124233425 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2024-04-09 | 2025-07-14 | Level 2 | GO 165 Inspection
124233603 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-03-07 | 2027-07-14 | Level 3 | Standards change
124233789 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-12-12 | 2027-07-14 | Level 3 | Standards change
124233792 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-10-17 | 2025-08-05 | Level 2 | GO 165 Inspection
124234406 | insulator and brushing | Non-HFTD | Transmission | 2022-07-02 | 2023-07-02 | Level 2 | E | 2023-01-19 | 2025-07-02 | Level 2 | Standards change
124234490 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-09-03 | 2025-08-05 | Level 2 | GO 165 Inspection
124234928 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-03-02 | 2025-08-05 | Level 2 | Standards change
124235126 | pole | Non-HFTD | Transmission | 2022-08-05 | 2025-08-05 | Level 2 | E | 2024-10-17 | 2023-08-05 | Level 2 | GO 165 Inspection
124235142 | anchor/guy | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-04-13 | 2027-08-01 | Level 3 | Standards change
124235257 | anchor/guy | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-04-26 | 2025-07-19 | Level 2 | Standards change
124235487 | pole | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-03-09 | 2025-07-11 | Level 2 | Standards change
124235720 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-28 | 2025-07-18 | Level 2 | Standards change
124235804 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-10-17 | 2025-08-05 | Level 2 | GO 165 Inspection
124236680 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-04-19 | 2027-07-12 | Level 3 | Standards change
124236775 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-24 | 2025-08-04 | Level 2 | Standards change
124236828 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-24 | 2025-08-04 | Level 2 | Standards change
124237049 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-24 | 2025-08-04 | Level 2 | Standards change
124237109 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-24 | 2025-08-04 | Level 2 | Standards change
124237413 | other | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-02-28 | 2027-07-07 | Level 3 | Standards change
124237538 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2023-12-28 | 2027-07-14 | Level 3 | Standards change
124237679 | insulator and brushing | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2024-01-05 | 2025-07-14 | Level 2 | Standards change
124238055 | other | Non-HFTD | Transmission | 2022-08-05 | 2024-08-05 | Level 3 | F | 2024-04-06 | 2027-08-05 | Level 3 | Standards change
124238095 | pole | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-01-20 | 2025-07-08 | Level 2 | Standards change
124238126 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124238173 | splice | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-04-06 | 2025-07-08 | Level 2 | Standards change
124238412 | other | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-03-10 | 2027-07-11 | Level 3 | Standards change
124238451 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-02-07 | 2025-08-05 | Level 2 | Standards change
124238465 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-07-21 | 2023-08-05 | Level 2 | Standards change
124238669 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-24 | 2025-08-05 | Level 2 | Standards change
124238854 | insulator and brushing | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-13 | 2025-07-13 | Level 2 | Standards change
124239006 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2024-12-05 | 2023-07-12 | Level 2 | Field Safety Reassessment
124239217 | pole | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-03-09 | 2025-07-08 | Level 2 | Standards change
124239380 | insulator and brushing | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-01-20 | 2025-07-08 | Level 2 | Standards change
124239415 | splice | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-04-06 | 2025-07-08 | Level 2 | Standards change
124239597 | insulator and brushing | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2023-03-13 | 2025-07-07 | Level 2 | Standards change
124239632 | anchor/guy | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-02-27 | 2025-07-06 | Level 2 | Standards change
124240460 | anchor/guy | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-02-14 | 2027-07-14 | Level 3 | Standards change
124240749 | other | Non-HFTD | Transmission | 2022-08-02 | 2024-08-02 | Level 3 | F | 2024-04-06 | 2027-08-02 | Level 3 | Standards change
124240836 | other | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-02-06 | 2027-07-08 | Level 3 | Standards change
124240837 | pole | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2023-12-27 | 2027-07-14 | Level 3 | Standards change
124241050 | other | Non-HFTD | Transmission | 2022-07-07 | 2026-07-07 | Level 3 | F |  | 2027-07-07 | Level 3
124241094 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-02-17 | 2027-07-14 | Level 3 | Standards change
124241174 | pole | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-07-14 | 2025-07-06 | Level 2 | GO 165 Inspection
124241236 | pole | Non-HFTD | Transmission | 2022-08-06 | 2023-08-06 | Level 2 | E | 2023-07-27 | 2025-08-06 | Level 2 | Standards change
124241354 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124242182 | anchor/guy | Non-HFTD | Transmission | 2022-07-16 | 2023-07-16 | Level 2 | E | 2024-07-31 | 2027-07-16 | Level 3 | GO 165 Inspection
124242669 | anchor/guy | Non-HFTD | Transmission | 2022-08-06 | 2023-08-06 | Level 2 | E | 2024-01-09 | 2027-08-06 | Level 3 | Standards change
124242729 | anchor/guy | Non-HFTD | Transmission | 2022-08-06 | 2023-08-06 | Level 2 | E | 2023-03-13 | 2025-08-06 | Level 2 | Standards change
124242772 | other | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2024-02-21 | 2027-07-08 | Level 3 | Standards change
124243907 | insulator and brushing | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-02-15 | 2025-07-14 | Level 2 | Standards change
124244097 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2023-04-07 | 2027-07-11 | Level 3 | Standards change
124244677 | insulator and brushing | Non-HFTD | Transmission | 2022-08-08 | 2023-08-08 | Level 2 | E | 2023-03-06 | 2025-08-08 | Level 2 | Standards change
124244932 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2022-12-12 | 2025-07-18 | Level 2 | Standards change
124245389 | anchor/guy | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2024-11-12 | 2025-07-19 | Level 2 | GO 165 Inspection
124246396 | pole | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-02-28 | 2025-07-08 | Level 2 | Standards change
124246636 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-03-01 | 2025-08-04 | Level 2 | Standards change
124246741 | other | Non-HFTD | Transmission | 2022-08-08 | 2027-08-08 | Level 3 | F | 2024-10-23 | 2027-08-08 | Level 3 | GO 165 Inspection
124246912 | anchor/guy | Non-HFTD | Transmission | 2022-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 3
124247369 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-03-07 | 2025-07-12 | Level 2 | Standards change
124247471 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2024-04-06 | 2027-07-14 | Level 3 | Standards change
124247474 | other | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-03-14 | 2027-08-02 | Level 3 | Standards change
124248096 | insulator and brushing | Non-HFTD | Transmission | 2022-08-08 | 2023-08-08 | Level 2 | E | 2024-10-09 | 2025-08-08 | Level 2 | GO 165 Inspection
124248849 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-03-07 | 2025-08-09 | Level 2 | Standards change
124248908 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-03-07 | 2025-08-09 | Level 2 | Standards change
124250191 | insulator and brushing | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2023-02-28 | 2025-07-29 | Level 2 | Standards change
124250806 | anchor/guy | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-12-04 | 2027-08-09 | Level 3 | GO 165 Inspection
124250921 | other | Non-HFTD | Transmission | 2022-07-08 | 2024-07-08 | Level 3 | F | 2023-04-07 | 2027-07-08 | Level 3 | Standards change
124250923 | anchor/guy | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-04-26 | 2027-07-18 | Level 3 | Standards change
124251652 | insulator and brushing | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-02-28 | 2027-07-11 | Level 3 | Standards change
124251702 | other | Non-HFTD | Transmission | 2022-07-08 | 2024-07-08 | Level 3 | F | 2024-04-06 | 2027-07-08 | Level 3 | Standards change
124252064 | insulator and brushing | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2023-03-06 | 2025-07-29 | Level 2 | Standards change
124252584 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-01-09 | 2027-07-13 | Level 3 | Standards change
124252705 | anchor/guy | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-08-01 | 2027-08-09 | Level 3 | Standards change
124252918 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124253412 | other | Non-HFTD | Transmission | 2022-08-05 | 2024-08-05 | Level 3 | F | 2024-05-03 | 2027-08-05 | Level 3 | GO 165 Inspection
124254508 | splice | Non-HFTD | Transmission | 2022-07-07 | 2023-07-07 | Level 2 | E | 2024-01-10 | 2025-07-07 | Level 2 | Standards change
124254663 | other | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-01-26 | 2025-08-01 | Level 2 | Standards change
124254883 | other | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-02-28 | 2027-07-06 | Level 3 | Standards change
124255148 | other | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2024-06-18 | 2025-08-09 | Level 2 | GO 165 Inspection
124255355 | insulator and brushing | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2024-01-17 | 2025-08-09 | Level 2 | Standards change
124255605 | pole | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-02-21 | 2027-08-09 | Level 3 | Standards change
124255641 | other | Non-HFTD | Transmission | 2022-07-07 | 2024-07-07 | Level 3 | F | 2024-04-06 | 2027-07-07 | Level 3 | Standards change
124255754 | other | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-10-24 | 2027-08-01 | Level 3 | GO 165 Inspection
124255891 | insulator and brushing | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-02-27 | 2025-07-20 | Level 2 | Standards change
124256031 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124256096 | other | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-02-01 | 2027-07-06 | Level 3 | Standards change
124256202 | other | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-24 | 2027-08-03 | Level 3 | Standards change
124256241 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124256414 | other | Non-HFTD | Transmission | 2022-07-08 | 2024-07-08 | Level 3 | F | 2023-04-07 | 2027-07-08 | Level 3 | Standards change
124256612 | pole | Non-HFTD | Transmission | 2022-07-29 | 2024-07-29 | Level 3 | F | 2024-01-09 | 2027-07-29 | Level 3 | Standards change
124256718 | insulator and brushing | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2023-01-30 | 2025-07-29 | Level 2 | Standards change
124256762 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2023-04-19 | 2027-07-12 | Level 3 | Standards change
124256768 | anchor/guy | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-01-05 | 2027-08-05 | Level 3 | Standards change
124256867 | anchor/guy | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-03-20 | 2025-07-15 | Level 2 | Standards change
124257118 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124257132 | anchor/guy | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-05-06 | 2027-07-12 | Level 3 | GO 165 Inspection
124257182 | pole | HFTD Tier 2 | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-06-04 | 2027-07-11 | Level 3 | GO 165 Inspection
124257213 | pole | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-01-04 | 2027-07-18 | Level 3 | Standards change
124267800 | pole | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2022-09-22 | 2024-07-12 | Level 3 | GO 165 Inspection
124267805 | anchor/guy | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-03-10 | 2027-07-08 | Level 3 | Standards change
124267843 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-11 | 2025-07-14 | Level 2 | Standards change
124268024 | other | Non-HFTD | Transmission | 2022-07-08 | 2023-07-08 | Level 2 | E | 2023-03-09 | 2027-07-08 | Level 3 | Standards change
124268788 | other | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-02-01 | 2027-07-06 | Level 3 | Standards change
124268858 | crossarm | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-27 | 2025-07-18 | Level 2 | Standards change
124268923 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-06 | 2025-08-05 | Level 2 | Standards change
124268993 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2024-10-28 | 2025-08-10 | Level 2 | GO 165 Inspection
124269359 | insulator and brushing | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2024-08-13 | 2025-08-10 | Level 2 | GO 165 Inspection
124269969 | other | Non-HFTD | Transmission | 2022-06-29 | 2023-06-29 | Level 2 | E | 2023-02-28 | 2025-06-29 | Level 2 | Standards change
124270463 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-04-06 | 2027-08-10 | Level 3 | Standards change
124272203 | other | HFTD Tier 2 | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-30 | 2027-07-11 | Level 3 | GO 165 Inspection
124272724 | insulator and brushing | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2024-09-27 | 2025-08-10 | Level 2 | GO 165 Inspection
124274674 | other | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-27 | 2025-07-18 | Level 2 | Standards change
124275543 | insulator and brushing | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2024-01-05 | 2025-07-15 | Level 2 | Standards change
124275610 | pole | Non-HFTD | Transmission | 2022-07-06 | 2024-07-06 | Level 3 | F | 2023-12-13 | 2025-07-06 | Level 2 | Standards change
124275612 | other | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-03-10 | 2027-07-19 | Level 3 | Standards change
124276088 | anchor/guy | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2024-08-26 | 2027-07-13 | Level 3 | GO 165 Inspection
124276235 | pole | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-03-07 | 2025-08-11 | Level 2 | Standards change
124276248 | other | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-04-06 | 2027-07-20 | Level 3 | Standards change
124277315 | other | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-08-26 | 2027-08-11 | Level 3 | GO 165 Inspection
124277958 | pole | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-07-15 | 2023-08-11 | Level 2 | Field Safety Reassessment
124278587 | insulator and brushing | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-12-15 | 2025-08-11 | Level 2 | Standards change
124278588 | insulator and brushing | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-12-18 | 2025-08-11 | Level 2 | Standards change
124279441 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-16 | 2025-07-13 | Level 2 | Standards change
124279534 | anchor/guy | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2024-01-22 | 2027-07-12 | Level 3 | Standards change
124279804 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-16 | 2025-07-13 | Level 2 | Standards change
124281142 | insulator and brushing | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-01-19 | 2027-07-06 | Level 3 | Standards change
124281170 | other | Non-HFTD | Transmission | 2022-08-11 | 2025-08-11 | Level 2 | E | 2024-10-22 | 2023-08-11 | Level 2 | GO 165 Inspection
124281308 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-12-13 | 2025-07-12 | Level 2 | Standards change
124281386 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124281567 | other | Non-HFTD | Transmission | 2022-07-26 | 2024-07-26 | Level 3 | F | 2023-07-13 | 2027-07-26 | Level 3 | Standards change
124281569 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-04-06 | 2027-07-18 | Level 3 | Standards change
124281606 | other | Non-HFTD | Transmission | 2022-08-08 | 2024-08-08 | Level 3 | F | 2024-04-06 | 2027-08-08 | Level 3 | Standards change
124281645 | other | Non-HFTD | Transmission | 2022-07-21 | 2024-07-21 | Level 3 | F | 2023-07-31 | 2027-07-21 | Level 3 | Standards change
124281678 | other | Non-HFTD | Transmission | 2022-08-08 | 2024-08-08 | Level 3 | F | 2024-04-06 | 2027-08-08 | Level 3 | Standards change
124281680 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-04-06 | 2027-07-12 | Level 3 | Standards change
124281683 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-27 | 2027-07-13 | Level 3 | Standards change
124281845 | other | Non-HFTD | Transmission | 2022-07-21 | 2024-07-21 | Level 3 | F | 2024-01-16 | 2027-07-21 | Level 3 | Standards change
124281851 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-01-05 | 2025-07-18 | Level 2 | Standards change
124281867 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124281869 | anchor/guy | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2023-03-20 | 2027-07-27 | Level 3 | Standards change
124282135 | other | Non-HFTD | Transmission | 2022-08-08 | 2024-08-08 | Level 3 | F | 2024-04-06 | 2027-08-08 | Level 3 | Standards change
124282138 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-04-06 | 2027-07-18 | Level 3 | Standards change
124282327 | pole | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-04-26 | 2023-07-22 | Level 2 | Standards change
124282347 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-10-21 | 2027-07-18 | Level 3 | GO 165 Inspection
124282445 | pole | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-02-15 | 2025-07-11 | Level 2 | Standards change
124282541 | anchor/guy | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-04-07 | 2027-07-11 | Level 3 | Standards change
124282713 | pole | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-07-26 | 2025-07-25 | Level 2 | Standards change
124282731 | other | Non-HFTD | Transmission | 2022-07-19 | 2024-07-19 | Level 3 | F | 2024-04-06 | 2027-07-19 | Level 3 | Standards change
124282796 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-01-30 | 2025-07-19 | Level 2 | Standards change
124282827 | other | HFTD Tier 2 | Transmission | 2022-07-16 | 2024-07-16 | Level 3 | F | 2024-06-04 | 2027-07-16 | Level 3 | GO 165 Inspection
124283019 | other | Non-HFTD | Transmission | 2022-07-20 | 2024-07-20 | Level 3 | F | 2024-04-06 | 2027-07-20 | Level 3 | Standards change
124283255 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-04-06 | 2027-07-12 | Level 3 | Standards change
124283360 | anchor/guy | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2023-03-03 | 2027-07-26 | Level 3 | Standards change
124283404 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2024-04-06 | 2027-07-14 | Level 3 | Standards change
124283426 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124283653 | pole | Non-HFTD | Transmission | 2022-07-15 | 2025-07-15 | Level 2 | E | 2024-07-31 | 2023-07-15 | Level 2 | GO 165 Inspection
124283708 | other | Non-HFTD | Transmission | 2022-07-26 | 2024-07-26 | Level 3 | F | 2023-03-15 | 2027-07-26 | Level 3 | Standards change
124283792 | pole | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-04-03 | 2025-07-21 | Level 2 | Standards change
124284065 | other | Non-HFTD | Transmission | 2022-07-17 | 2024-07-17 | Level 3 | F | 2024-04-06 | 2027-07-17 | Level 3 | Standards change
124284073 | other | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-01-27 | 2025-07-11 | Level 2 | Standards change
124284136 | anchor/guy | Non-HFTD | Transmission | 2022-07-17 | 2023-07-17 | Level 2 | E | 2024-01-10 | 2027-07-17 | Level 3 | Standards change
124284420 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-14 | 2027-07-13 | Level 3 | Standards change
124284494 | insulator and brushing | Non-HFTD | Transmission | 2022-07-06 | 2023-07-06 | Level 2 | E | 2023-02-23 | 2025-07-06 | Level 2 | Standards change
124284575 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124284724 | insulator and brushing | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-02-01 | 2025-07-15 | Level 2 | Standards change
124284794 | other | Non-HFTD | Transmission | 2022-07-19 | 2024-07-19 | Level 3 | F | 2024-04-06 | 2027-07-19 | Level 3 | Standards change
124285013 | insulator and brushing | Non-HFTD | Transmission | 2022-07-11 | 2023-07-11 | Level 2 | E | 2023-02-28 | 2027-07-11 | Level 3 | Standards change
124285145 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2024-04-09 | 2025-07-14 | Level 2 | GO 165 Inspection
124285211 | other | HFTD Tier 3 | Transmission | 2022-07-22 | 2024-07-22 | Level 3 | F | 2024-04-06 | 2027-07-22 | Level 3 | Standards change
124285212 | insulator and brushing | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-03-14 | 2027-07-21 | Level 3 | Standards change
124285486 | other | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-16 | 2025-07-13 | Level 2 | Standards change
124285505 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124285550 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124285624 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124285656 | pole | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-01-09 | 2027-07-12 | Level 3 | Standards change
124285743 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2023-05-10 | 2027-07-15 | Level 3 | Standards change
124285975 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124285988 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124286115 | other | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-01-11 | 2027-07-12 | Level 3 | Standards change
124286164 | other | Non-HFTD | Transmission | 2022-07-29 | 2024-07-29 | Level 3 | F | 2024-04-06 | 2027-07-29 | Level 3 | Standards change
124286446 | other | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2024-09-25 | 2025-08-12 | Level 2 | GO 165 Inspection
124286890 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-11-02 | 2027-07-14 | Level 3 | Standards change
124287040 | insulator and brushing | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2023-12-05 | 2025-07-27 | Level 2 | Standards change
124287150 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-01-25 | 2025-07-15 | Level 2 | Standards change
124287192 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124287364 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-01-25 | 2025-07-15 | Level 2 | Standards change
124287365 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2024-04-06 | 2027-07-15 | Level 3 | Standards change
124287485 | other | Non-HFTD | Transmission | 2022-07-11 | 2024-07-11 | Level 3 | F | 2024-04-06 | 2027-07-11 | Level 3 | Standards change
124287486 | other | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-01-25 | 2025-07-15 | Level 2 | Standards change
124287755 | anchor/guy | Non-HFTD | Transmission | 2022-07-12 | 2024-07-12 | Level 3 | F | 2024-08-29 | 2027-07-12 | Level 3 | GO 165 Inspection
124287820 | insulator and brushing | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-07-28 | 2025-07-22 | Level 2 | Standards change
124287989 | crossarm | Non-HFTD | Transmission | 2022-08-13 | 2023-08-13 | Level 2 | E | 2023-03-01 | 2025-08-13 | Level 2 | Standards change
124288085 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-10-17 | 2027-07-14 | Level 3 | Standards change
124288324 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-01-09 | 2025-08-10 | Level 2 | Standards change
124288396 | splice | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-10-21 | 2025-07-25 | Level 2 | GO 165 Inspection
124288663 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-02-14 | 2027-07-13 | Level 3 | Standards change
124288837 | pole | Non-HFTD | Transmission | 2022-07-12 | 2023-07-12 | Level 2 | E | 2023-04-12 | 2025-07-12 | Level 2 | Standards change
124288923 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2024-06-21 | 2023-07-14 | Level 2 | GO 165 Inspection
124288946 | other | Non-HFTD | Transmission | 2022-07-13 | 2024-07-13 | Level 3 | F | 2024-04-06 | 2027-07-13 | Level 3 | Standards change
124288965 | other | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-03-06 | 2027-07-14 | Level 3 | Standards change
124288968 | anchor/guy | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2024-01-09 | 2027-07-13 | Level 3 | Standards change
124289020 | insulator and brushing | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-03-06 | 2025-07-14 | Level 2 | Standards change
124289102 | pole | Non-HFTD | Transmission | 2022-08-13 | 2023-08-13 | Level 2 | E | 2023-03-08 | 2025-08-13 | Level 2 | Standards change
124289103 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2024-04-06 | 2027-07-14 | Level 3 | Standards change
124289280 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2023-03-21 | 2027-07-14 | Level 3 | Standards change
124289540 | pole | HFTD Tier 3 | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2024-03-20 | 2027-07-14 | Level 3 | GO 165 Inspection
124289660 | other | Non-HFTD | Transmission | 2022-07-14 | 2024-07-14 | Level 3 | F | 2023-03-21 | 2027-07-14 | Level 3 | Standards change
124289718 | crossarm | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2024-01-08 | 2025-07-15 | Level 2 | Standards change
124289891 | other | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-11-02 | 2027-07-15 | Level 3 | Standards change
124289935 | other | Non-HFTD | Transmission | 2022-07-15 | 2024-07-15 | Level 3 | F | 2023-04-24 | 2027-07-15 | Level 3 | Standards change
124289975 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-01-25 | 2025-07-15 | Level 2 | Standards change
124290198 | insulator and brushing | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-03-02 | 2025-07-15 | Level 2 | Standards change
124291314 | insulator and brushing | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-03-08 | 2027-08-15 | Level 3 | Standards change
124291587 | other | HFTD Tier 3 | Transmission | 2022-07-16 | 2024-07-16 | Level 3 | F | 2024-04-06 | 2027-07-16 | Level 3 | Standards change
124291783 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-02-08 | 2025-08-15 | Level 2 | Standards change
124292020 | other | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-27 | 2025-07-18 | Level 2 | Standards change
124292123 | other | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2024-07-17 | 2027-07-21 | Level 3 | GO 165 Inspection
124292655 | other | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-12-27 | 2027-07-18 | Level 3 | Standards change
124293106 | other | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-02-28 | 2027-08-15 | Level 3 | Standards change
124293200 | other | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-02-02 | 2025-07-18 | Level 2 | Standards change
124293302 | anchor/guy | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2023-12-27 | 2027-07-18 | Level 3 | Standards change
124293437 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-12-05 | 2023-08-15 | Level 2 | Field Safety Reassessment
124293638 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-27 | 2027-07-18 | Level 3 | Standards change
124293711 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-04-06 | 2027-07-18 | Level 3 | Standards change
124293950 | other | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-01-04 | 2027-07-18 | Level 3 | Standards change
124294155 | pole | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2024-09-26 | 2025-08-12 | Level 2 | GO 165 Inspection
124294319 | other | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2024-10-25 | 2023-08-12 | Level 2 | GO 165 Inspection
124294451 | pole | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2024-10-25 | 2023-08-12 | Level 2 | GO 165 Inspection
124295159 | pole | Non-HFTD | Transmission | 2022-08-12 | 2024-08-12 | Level 3 | F | 2024-10-25 | 2027-08-12 | Level 3 | GO 165 Inspection
124295421 | anchor/guy | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-01-10 | 2027-07-18 | Level 3 | Standards change
124295650 | anchor/guy | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-02-27 | 2025-07-18 | Level 2 | Standards change
124295655 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2024-01-08 | 2025-07-18 | Level 2 | Standards change
124295846 | other | Non-HFTD | Transmission | 2022-07-18 | 2024-07-18 | Level 3 | F | 2024-12-10 | 2027-07-18 | Level 3 | GO 165 Inspection
124296517 | other | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-07 | 2025-08-03 | Level 2 | Standards change
124298099 | pole | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-02-08 | 2025-08-11 | Level 2 | Standards change
124298182 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-09-13 | 2025-08-15 | Level 2 | GO 165 Inspection
124298279 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2024-01-08 | 2025-07-19 | Level 2 | Standards change
124298473 | other | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-03-03 | 2027-08-11 | Level 3 | Standards change
124298629 | other | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-02-02 | 2025-08-01 | Level 2 | Standards change
124298635 | anchor/guy | Non-HFTD | Transmission | 2022-08-01 | 2024-08-01 | Level 3 | F | 2024-01-11 | 2027-08-01 | Level 3 | Standards change
124299205 | other | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-03-01 | 2025-07-25 | Level 2 | Standards change
124299339 | pole | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2024-01-08 | 2025-08-16 | Level 2 | Standards change
124299998 | insulator and brushing | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2024-10-18 | 2025-07-22 | Level 2 | GO 165 Inspection
124300043 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-02-15 | 2027-08-01 | Level 3 | Standards change
124300462 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2024-10-10 | 2025-08-16 | Level 2 | GO 165 Inspection
124300864 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-10-17 | 2027-08-01 | Level 3 | Standards change
124301028 | pole | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2024-11-13 | 2025-08-16 | Level 2 | GO 165 Inspection
124301204 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-08 | 2025-08-16 | Level 2 | Standards change
124301223 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-06-21 | 2025-08-16 | Level 2 | Field Safety Reassessment
124301329 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-06-21 | 2025-08-16 | Level 2 | Field Safety Reassessment
124301940 | anchor/guy | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-01-10 | 2027-07-20 | Level 3 | Standards change
124302034 | other | Non-HFTD | Transmission | 2022-08-01 | 2024-08-01 | Level 3 | F | 2024-04-06 | 2027-08-01 | Level 3 | Standards change
124302054 | pole | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-06-20 | 2025-08-11 | Level 2 | GO 165 Inspection
124302737 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-04-06 | 2027-08-10 | Level 3 | Standards change
124302770 | other | Non-HFTD | Transmission | 2022-08-16 | 2025-08-16 | Level 2 | E | 2024-11-12 | 2023-08-16 | Level 2 | GO 165 Inspection
124302852 | pole | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-07 | 2025-08-16 | Level 2 | Standards change
124303211 | other | Non-HFTD | Transmission | 2022-07-28 | 2023-07-28 | Level 2 | E | 2023-12-06 | 2023-07-28 | Level 2 | Standards change
124305648 | pole | Non-HFTD | Transmission | 2022-08-16 | 2024-08-16 | Level 3 | F | 2024-01-19 | 2027-08-16 | Level 3 | Standards change
124305724 | anchor/guy | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-10-15 | 2025-07-25 | Level 2 | GO 165 Inspection
124305879 | insulator and brushing | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-09-13 | 2025-07-20 | Level 2 | Standards change
124306432 | insulator and brushing | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2024-10-15 | 2025-08-17 | Level 2 | GO 165 Inspection
124307019 | insulator and brushing | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2024-02-02 | 2025-07-29 | Level 2 | Standards change
124307304 | insulator and brushing | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2023-02-28 | 2025-08-17 | Level 2 | Standards change
124307338 | insulator and brushing | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-07-24 | 2023-07-20 | Level 2 | GO 165 Inspection
124307545 | other | Non-HFTD | Transmission | 2022-07-29 | 2024-07-29 | Level 3 | F | 2024-04-06 | 2027-07-29 | Level 3 | Standards change
124307598 | other | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-07-25 | 2025-07-20 | Level 2 | GO 165 Inspection
124307620 | other | Non-HFTD | Transmission | 2022-08-05 | 2024-08-05 | Level 3 | F | 2024-04-06 | 2027-08-05 | Level 3 | Standards change
124308023 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124310432 | anchor/guy | Non-HFTD | Transmission | 2022-07-21 | 2024-07-21 | Level 3 | F | 2023-07-05 | 2027-07-21 | Level 3 | Standards change
124310730 | insulator and brushing | Non-HFTD | Transmission | 2022-07-28 | 2023-07-28 | Level 2 | E | 2024-08-12 | 2023-01-28 | Level 2 | GO 165 Inspection
124310743 | insulator and brushing | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2023-03-03 | 2025-08-17 | Level 2 | Standards change
124310782 | other | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-03-03 | 2027-08-11 | Level 3 | Standards change
124311550 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124312136 | insulator and brushing | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-04-11 | 2023-07-20 | Level 2 | GO 165 Inspection
124312489 | other | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2024-09-14 | 2027-07-22 | Level 3 | GO 165 Inspection
124314434 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2024-12-05 | 2023-08-18 | Level 2 | Field Safety Reassessment
124314762 | other | Non-HFTD | Transmission | 2022-07-20 | 2025-07-20 | Level 2 | E | 2024-07-26 | 2027-07-20 | Level 3 | GO 165 Inspection
124314973 | pole | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-08 | 2025-08-16 | Level 2 | Standards change
124315418 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-07-13 | 2025-08-18 | Level 2 | Standards change
124315529 | insulator and brushing | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-01-18 | 2025-07-21 | Level 2 | Standards change
124315756 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-04-06 | 2027-08-10 | Level 3 | Standards change
124315817 | insulator and brushing | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-04-26 | 2025-07-21 | Level 2 | Standards change
124316020 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-02-16 | 2025-08-18 | Level 2 | Standards change
124316163 | other | Non-HFTD | Transmission | 2022-07-29 | 2024-07-29 | Level 3 | F | 2024-04-06 | 2027-07-29 | Level 3 | Standards change
124316521 | pole | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-01-08 | 2025-07-26 | Level 2 | Standards change
124316616 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-01-09 | 2027-08-10 | Level 3 | Standards change
124316635 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-03-13 | 2027-08-18 | Level 3 | Standards change
124316972 | insulator and brushing | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-01-09 | 2027-08-18 | Level 3 | Standards change
124316984 | pole | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-11-22 | 2025-07-21 | Level 2 | Standards change
124317195 | insulator and brushing | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-01-10 | 2027-08-10 | Level 3 | Standards change
124317257 | insulator and brushing | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-07-25 | 2023-07-22 | Level 2 | Standards change
124317703 | other | Non-HFTD | Transmission | 2022-07-21 | 2024-07-21 | Level 3 | F | 2024-01-08 | 2027-07-21 | Level 3 | Standards change
124317789 | anchor/guy | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-07-17 | 2025-08-03 | Level 2 | Standards change
124318361 | other | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-08 | 2027-08-03 | Level 3 | Standards change
124318587 | insulator and brushing | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-11-18 | 2025-07-25 | Level 2 | GO 165 Inspection
124318766 | other | Non-HFTD | Transmission | 2022-08-18 | 2024-08-18 | Level 3 | F | 2024-04-06 | 2027-08-18 | Level 3 | Standards change
124318908 | insulator and brushing | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-07-07 | 2025-08-09 | Level 2 | Standards change
124319029 | pole | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-07-13 | 2025-07-25 | Level 2 | Standards change
124319975 | other | Non-HFTD | Transmission | 2022-07-29 | 2024-07-29 | Level 3 | F | 2024-04-06 | 2027-07-29 | Level 3 | Standards change
124320278 | pole | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2024-01-08 | 2025-07-25 | Level 2 | Standards change
124320464 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2024-01-08 | 2025-08-02 | Level 2 | Standards change
124320745 | anchor/guy | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-04-05 | 2027-07-21 | Level 3 | Standards change
124323038 | other | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2023-03-14 | 2025-07-21 | Level 2 | Standards change
124323046 | switch | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2024-12-09 | 2023-08-18 | Level 2 | Field Safety Reassessment
124323120 | insulator and brushing | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2024-01-30 | 2027-08-19 | Level 3 | Standards change
124323286 | other | Non-HFTD | Transmission | 2022-08-01 | 2024-08-01 | Level 3 | F | 2024-04-06 | 2027-08-01 | Level 3 | Standards change
124323440 | anchor/guy | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-03-03 | 2027-08-19 | Level 3 | Standards change
124323761 | insulator and brushing | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-11-06 | 2025-08-02 | Level 2 | GO 165 Inspection
124324624 | pole | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-03 | 2025-08-03 | Level 2 | Standards change
124325109 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-10-31 | 2025-08-19 | Level 2 | Standards change
124325359 | anchor/guy | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-02-10 | 2027-08-04 | Level 3 | Standards change
124326175 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-02-16 | 2025-08-18 | Level 2 | Standards change
124327147 | other | Non-HFTD | Transmission | 2022-07-25 | 2023-07-25 | Level 2 | E | 2023-02-14 | 2027-07-25 | Level 3 | Standards change
124327372 | pole | Non-HFTD | Transmission | 2022-07-25 | 2024-07-25 | Level 3 | F | 2023-02-14 | 2027-07-25 | Level 3 | Standards change
124327962 | pole | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-05-22 | 2025-08-01 | Level 2 | Field Safety Reassessment
124328007 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-14 | 2025-08-19 | Level 2 | Standards change
124328010 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2024-10-07 | 2025-08-19 | Level 2 | GO 165 Inspection
124328188 | pole | Non-HFTD | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-01-08 | 2025-07-26 | Level 2 | Standards change
124328249 | insulator and brushing | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-07-18 | 2025-07-22 | Level 2 | Standards change
124328631 | other | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-07 | 2025-08-16 | Level 2 | Standards change
124328639 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2027-08-16 | Level 3 | F |  | 2027-08-16 | Level 3
124329067 | other | Non-HFTD | Transmission | 2022-08-08 | 2024-08-08 | Level 3 | F | 2024-04-06 | 2027-08-08 | Level 3 | Standards change
124329094 | other | Non-HFTD | Transmission | 2022-08-03 | 2024-08-03 | Level 3 | F | 2024-04-06 | 2027-08-03 | Level 3 | Standards change
124329502 | insulator and brushing | Non-HFTD | Transmission | 2022-08-08 | 2023-08-08 | Level 2 | E | 2024-11-14 | 2027-08-08 | Level 3 | GO 165 Inspection
124329507 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-08-21 | 2025-08-05 | Level 2 | GO 165 Inspection
124329508 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-08-21 | 2025-08-05 | Level 2 | GO 165 Inspection
124329597 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124331074 | pole | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-08-08 | 2025-08-03 | Level 2 | GO 165 Inspection
124331672 | pole | Non-HFTD | Transmission | 2022-07-26 | 2024-07-26 | Level 3 | F | 2024-01-08 | 2027-07-26 | Level 3 | Standards change
124333134 | anchor/guy | Non-HFTD | Transmission | 2022-08-20 | 2024-08-20 | Level 3 | F | 2023-11-30 | 2027-08-20 | Level 3 | Standards change
124333529 | insulator and brushing | Non-HFTD | Transmission | 2022-08-20 | 2023-08-20 | Level 2 | E | 2023-02-14 | 2025-08-20 | Level 2 | Standards change
124333584 | other | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-08 | 2025-08-16 | Level 2 | Standards change
124334019 | insulator and brushing | Non-HFTD | Transmission | 2022-08-20 | 2023-08-20 | Level 2 | E | 2024-11-16 | 2025-08-20 | Level 2 | GO 165 Inspection
124334311 | other | Non-HFTD | Transmission | 2022-07-28 | 2023-07-28 | Level 2 | E | 2023-03-10 | 2025-07-28 | Level 2 | Standards change
124334927 | insulator and brushing | Non-HFTD | Transmission | 2022-08-21 | 2023-08-21 | Level 2 | E | 2023-09-25 | 2025-08-21 | Level 2 | Standards change
124334945 | pole | Non-HFTD | Transmission | 2022-07-21 | 2023-07-21 | Level 2 | E | 2024-07-02 | 2025-07-21 | Level 2 | GO 165 Inspection
124335341 | other | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-03-01 | 2027-08-04 | Level 3 | Standards change
124335404 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-04-06 | 2027-08-10 | Level 3 | Standards change
124335432 | other | Non-HFTD | Transmission | 2022-08-16 | 2025-08-16 | Level 2 | E | 2024-11-08 | 2023-08-16 | Level 2 | GO 165 Inspection
124335451 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-16 | 2025-08-19 | Level 2 | Standards change
124335746 | other | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2024-08-02 | 2027-07-27 | Level 3 | GO 165 Inspection
124336206 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2024-09-06 | 2025-08-16 | Level 2 | GO 165 Inspection
124336328 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-01-08 | 2025-08-05 | Level 2 | Standards change
124336493 | other | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-08-15 | 2027-08-15 | Level 3 | GO 165 Inspection
124336606 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-12-13 | 2023-08-15 | Level 2 | Field Safety Reassessment
124336700 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-01-09 | 2027-08-10 | Level 3 | Standards change
124337074 | other | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-02-14 | 2027-08-04 | Level 3 | Standards change
124337228 | other | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-24 | 2027-08-03 | Level 3 | Standards change
124338996 | insulator and brushing | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-31 | 2025-08-22 | Level 2 | Standards change
124340102 | insulator and brushing | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2024-01-30 | 2027-08-22 | Level 3 | Standards change
124340708 | crossarm | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-25 | 2025-08-04 | Level 2 | Standards change
124340834 | other | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-08-04 | 2025-08-09 | Level 2 | Standards change
124341113 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-06 | 2027-08-05 | Level 3 | Standards change
124342161 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-10-23 | 2025-08-15 | Level 2 | GO 165 Inspection
124342382 | other | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-26 | 2025-08-05 | Level 2 | Standards change
124342394 | pole | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-03-08 | 2025-08-22 | Level 2 | Standards change
124342802 | pole | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2023-11-30 | 2027-08-09 | Level 3 | Standards change
124342804 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-23 | 2025-08-04 | Level 2 | Standards change
124343043 | other | Non-HFTD | Transmission | 2022-08-04 | 2024-08-04 | Level 3 | F | 2024-04-06 | 2027-08-04 | Level 3 | Standards change
124343223 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124343265 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-26 | 2025-08-05 | Level 2 | Standards change
124343332 | other | Non-HFTD | Transmission | 2022-08-16 | 2024-08-16 | Level 3 | F | 2024-04-06 | 2027-08-16 | Level 3 | Standards change
124343416 | anchor/guy | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2023-04-24 | 2025-07-29 | Level 2 | Standards change
124343422 | pole | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-24 | 2025-08-03 | Level 2 | Standards change
124343424 | other | Non-HFTD | Transmission | 2022-08-02 | 2024-08-02 | Level 3 | F | 2024-04-06 | 2027-08-02 | Level 3 | Standards change
124343437 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124343525 | pole | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-24 | 2025-08-03 | Level 2 | Standards change
124343529 | other | Non-HFTD | Transmission | 2022-08-05 | 2024-08-05 | Level 3 | F | 2024-04-06 | 2027-08-05 | Level 3 | Standards change
124343706 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124343777 | insulator and brushing | Non-HFTD | Transmission | 2022-07-29 | 2023-07-29 | Level 2 | E | 2024-12-11 | 2023-07-29 | Level 2 | Field Safety Reassessment
124343877 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2024-09-05 | 2025-08-02 | Level 2 | GO 165 Inspection
124343892 | anchor/guy | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-07-25 | 2023-08-11 | Level 2 | Standards change
124343936 | insulator and brushing | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-02-17 | 2027-08-02 | Level 3 | Standards change
124344174 | insulator and brushing | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2023-02-14 | 2025-08-01 | Level 2 | Standards change
124344349 | other | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-03-09 | 2027-08-09 | Level 3 | Standards change
124344409 | other | Non-HFTD | Transmission | 2022-08-05 | 2024-08-05 | Level 3 | F | 2024-04-06 | 2027-08-05 | Level 3 | Standards change
124344423 | insulator and brushing | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-03-09 | 2025-08-09 | Level 2 | Standards change
124344431 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2023-11-30 | 2027-08-10 | Level 3 | Standards change
124344479 | pole | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2023-03-08 | 2025-08-12 | Level 2 | Standards change
124344525 | other | Non-HFTD | Transmission | 2022-08-03 | 2023-08-03 | Level 2 | E | 2023-03-24 | 2027-08-03 | Level 3 | Standards change
124344667 | anchor/guy | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-03-03 | 2027-08-23 | Level 3 | Standards change
124345034 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-03-02 | 2025-08-15 | Level 2 | Standards change
124345331 | pole | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2023-12-11 | 2027-08-12 | Level 3 | Standards change
124345488 | insulator and brushing | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-03-13 | 2025-08-23 | Level 2 | Standards change
124345503 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-03-09 | 2025-08-09 | Level 2 | Standards change
124346007 | other | Non-HFTD | Transmission | 2022-08-05 | 2024-08-05 | Level 3 | F | 2024-04-06 | 2027-08-05 | Level 3 | Standards change
124346371 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124346675 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2024-09-03 | 2025-08-05 | Level 2 | GO 165 Inspection
124346854 | other | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2024-04-06 | 2027-08-09 | Level 3 | Standards change
124346885 | other | Non-HFTD | Transmission | 2022-08-03 | 2024-08-03 | Level 3 | F | 2023-04-10 | 2027-08-03 | Level 3 | Standards change
124347002 | insulator and brushing | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2024-11-15 | 2025-08-23 | Level 2 | GO 165 Inspection
124347192 | anchor/guy | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-01-12 | 2027-08-15 | Level 3 | Standards change
124347327 | other | Non-HFTD | Transmission | 2022-08-18 | 2024-08-18 | Level 3 | F | 2024-04-06 | 2027-08-18 | Level 3 | Standards change
124347391 | pole | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2024-08-26 | 2025-08-17 | Level 2 | GO 165 Inspection
124347505 | other | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2024-08-26 | 2025-08-17 | Level 2 | GO 165 Inspection
124347731 | other | Non-HFTD | Transmission | 2022-08-04 | 2024-08-04 | Level 3 | F | 2024-01-09 | 2027-08-04 | Level 3 | Standards change
124348086 | other | Non-HFTD | Transmission | 2022-08-08 | 2024-08-08 | Level 3 | F | 2024-04-06 | 2027-08-08 | Level 3 | Standards change
124348195 | insulator and brushing | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2024-02-15 | 2025-08-23 | Level 2 | Standards change
124348815 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-06 | 2027-08-05 | Level 3 | Standards change
124348927 | other | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-02-14 | 2027-08-04 | Level 3 | Standards change
124348986 | other | Non-HFTD | Transmission | 2022-08-08 | 2024-08-08 | Level 3 | F | 2024-04-06 | 2027-08-08 | Level 3 | Standards change
124349148 | pole | Non-HFTD | Transmission | 2022-06-11 | 2023-06-11 | Level 2 | E | 2024-07-16 | 2025-06-11 | Level 2 | GO 165 Inspection
124349202 | pole | Non-HFTD | Transmission | 2022-06-23 | 2023-06-23 | Level 2 | E | 2023-03-14 | 2025-06-23 | Level 2 | Standards change
124349345 | other | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2024-08-27 | 2027-08-23 | Level 3 | GO 165 Inspection
124349528 | pole | Non-HFTD | Transmission | 2022-08-08 | 2023-08-08 | Level 2 | E | 2023-01-09 | 2025-08-08 | Level 2 | Standards change
124349940 | pole | Non-HFTD | Transmission | 2022-08-04 | 2023-08-04 | Level 2 | E | 2023-01-30 | 2025-08-04 | Level 2 | Standards change
124357793 | other | Non-HFTD | Transmission | 2022-08-08 | 2023-08-08 | Level 2 | E | 2023-01-26 | 2027-08-08 | Level 3 | Standards change
124357836 | other | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-03-01 | 2027-08-24 | Level 3 | Standards change
124357905 | other | Non-HFTD | Transmission | 2022-08-04 | 2024-08-04 | Level 3 | F | 2024-01-09 | 2027-08-04 | Level 3 | Standards change
124358349 | other | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-07-26 | 2025-08-11 | Level 2 | GO 165 Inspection
124358616 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-06 | 2025-08-05 | Level 2 | Standards change
124358916 | pole | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-04-26 | 2025-08-05 | Level 2 | Standards change
124359032 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2023-12-28 | 2027-08-10 | Level 3 | Standards change
124359315 | pole | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-26 | 2025-08-22 | Level 2 | Standards change
124359378 | anchor/guy | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-08-30 | 2027-08-24 | Level 3 | Standards change
124359788 | conductor | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-01-20 | 2025-08-24 | Level 2 | Standards change
124360163 | other | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-03-13 | 2025-08-24 | Level 2 | Standards change
124362869 | insulator and brushing | Non-HFTD | Transmission | 2022-08-08 | 2023-08-08 | Level 2 | E | 2024-08-05 | 2027-08-08 | Level 3 | GO 165 Inspection
124363071 | insulator and brushing | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-08-12 | 2025-08-11 | Level 2 | GO 165 Inspection
124363252 | pole | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2023-01-10 | 2025-08-12 | Level 2 | Standards change
124363254 | other | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2023-01-10 | 2027-08-12 | Level 3 | Standards change
124363859 | pole | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2023-11-30 | 2027-08-09 | Level 3 | Standards change
124364014 | insulator and brushing | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2024-09-09 | 2025-08-09 | Level 2 | GO 165 Inspection
124364067 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-04-06 | 2027-08-10 | Level 3 | Standards change
124364272 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-23 | 2025-08-19 | Level 2 | Standards change
124364449 | insulator and brushing | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2024-07-29 | 2025-08-10 | Level 2 | GO 165 Inspection
124364479 | insulator and brushing | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-12-11 | 2025-08-11 | Level 2 | Standards change
124364563 | other | Non-HFTD | Transmission | 2022-08-19 | 2024-08-19 | Level 3 | F | 2024-04-06 | 2027-08-19 | Level 3 | Standards change
124364576 | other | Non-HFTD | Transmission | 2022-08-09 | 2027-08-09 | Level 3 | F |  | 2027-08-09 | Level 3
124364585 | other | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2024-01-16 | 2027-08-18 | Level 3 | Standards change
124364589 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-17 | 2025-08-19 | Level 2 | Standards change
124364651 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-01-06 | 2027-08-10 | Level 3 | Standards change
124364653 | other | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-10-23 | 2025-08-11 | Level 2 | GO 165 Inspection
124364662 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-23 | 2025-08-19 | Level 2 | Standards change
124364664 | other | Non-HFTD | Transmission | 2022-08-19 | 2024-08-19 | Level 3 | F | 2024-04-06 | 2027-08-19 | Level 3 | Standards change
124364665 | pole | Non-HFTD | Transmission | 2022-08-09 | 2024-08-09 | Level 3 | F | 2023-11-30 | 2025-08-09 | Level 2 | Standards change
124364682 | other | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2024-11-18 | 2025-08-11 | Level 2 | GO 165 Inspection
124364695 | pole | Non-HFTD | Transmission | 2022-08-12 | 2024-08-12 | Level 3 | F | 2024-10-25 | 2027-08-12 | Level 3 | GO 165 Inspection
124364724 | pole | Non-HFTD | Transmission | 2022-08-18 | 2024-08-18 | Level 3 | F | 2024-01-16 | 2027-08-18 | Level 3 | Standards change
124364782 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-04-06 | 2027-08-10 | Level 3 | Standards change
124364786 | other | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-08-12 | 2027-08-15 | Level 3 | Standards change
124364885 | pole | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-01-24 | 2025-08-24 | Level 2 | Standards change
124365718 | insulator and brushing | Non-HFTD | Transmission | 2022-08-25 | 2022-11-25 | Level 2 | B | 2023-01-24 | 2025-08-25 | Level 2 | Standards change
124366020 | pole | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-08-15 | 2027-08-10 | Level 3 | GO 165 Inspection
124366137 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-17 | 2025-08-19 | Level 2 | Standards change
124366756 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2024-02-02 | 2027-08-10 | Level 3 | Standards change
124366768 | other | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-02-13 | 2025-08-22 | Level 2 | Standards change
124366775 | insulator and brushing | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-02-28 | 2025-08-25 | Level 2 | Standards change
124367328 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-01-09 | 2025-08-19 | Level 2 | Standards change
124367418 | conductor | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-23 | 2025-08-19 | Level 2 | Standards change
124367426 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-01-20 | 2025-08-25 | Level 2 | Standards change
124367655 | other | Non-HFTD | Transmission | 2022-08-25 | 2024-08-25 | Level 3 | F | 2023-12-21 | 2027-08-25 | Level 3 | Standards change
124367792 | insulator and brushing | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-05-10 | 2025-08-25 | Level 2 | Standards change
124367974 | other | Non-HFTD | Transmission | 2022-08-19 | 2024-08-19 | Level 3 | F | 2023-02-24 | 2027-08-19 | Level 3 | Standards change
124368239 | anchor/guy | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-01-10 | 2027-08-15 | Level 3 | Standards change
124368382 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-01-20 | 2025-08-25 | Level 2 | Standards change
124368402 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-02-07 | 2025-08-15 | Level 2 | Standards change
124369093 | other | Non-HFTD | Transmission | 2022-08-22 | 2024-08-22 | Level 3 | F | 2023-02-24 | 2027-08-22 | Level 3 | Standards change
124370067 | other | Non-HFTD | Transmission | 2022-08-10 | 2024-08-10 | Level 3 | F | 2023-12-28 | 2027-08-10 | Level 3 | Standards change
124371461 | other | Non-HFTD | Transmission | 2022-08-25 | 2025-08-25 | Level 2 | E | 2024-10-31 | 2027-08-25 | Level 3 | GO 165 Inspection
124371856 | insulator and brushing | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2024-01-29 | 2025-08-12 | Level 2 | Standards change
124372056 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-01-23 | 2025-08-25 | Level 2 | Standards change
124372105 | other | Non-HFTD | Transmission | 2022-08-11 | 2024-08-11 | Level 3 | F | 2024-06-20 | 2027-08-11 | Level 3 | GO 165 Inspection
124372253 | insulator and brushing | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-02-08 | 2025-08-11 | Level 2 | Standards change
124372848 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-01-20 | 2025-08-25 | Level 2 | Standards change
124373310 | other | Non-HFTD | Transmission | 2022-08-22 | 2024-08-22 | Level 3 | F | 2024-04-06 | 2027-08-22 | Level 3 | Standards change
124375192 | anchor/guy | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2023-01-20 | 2025-08-26 | Level 2 | Standards change
124375285 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2024-10-31 | 2025-08-15 | Level 2 | GO 165 Inspection
124375334 | other | Non-HFTD | Transmission | 2022-08-22 | 2024-08-22 | Level 3 | F | 2024-04-06 | 2027-08-22 | Level 3 | Standards change
124375517 | other | Non-HFTD | Transmission | 2022-08-15 | 2024-08-15 | Level 3 | F | 2024-04-06 | 2027-08-15 | Level 3 | Standards change
124375830 | other | Non-HFTD | Transmission | 2022-08-22 | 2024-08-22 | Level 3 | F | 2024-04-06 | 2027-08-22 | Level 3 | Standards change
124375918 | pole | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-26 | 2025-08-22 | Level 2 | Standards change
124376235 | insulator and brushing | Non-HFTD | Transmission | 2022-08-12 | 2023-08-12 | Level 2 | E | 2023-02-08 | 2025-08-12 | Level 2 | Standards change
124376446 | other | Non-HFTD | Transmission | 2022-08-12 | 2024-08-12 | Level 3 | F | 2024-04-06 | 2027-08-12 | Level 3 | Standards change
124376895 | other | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2023-10-06 | 2027-08-17 | Level 3 | Standards change
124376897 | pole | Non-HFTD | Transmission | 2022-08-15 | 2023-08-15 | Level 2 | E | 2023-07-12 | 2025-08-15 | Level 2 | Standards change
124377278 | insulator and brushing | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2024-09-06 | 2025-08-16 | Level 2 | GO 165 Inspection
124377402 | insulator and brushing | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2023-02-13 | 2025-08-26 | Level 2 | Standards change
124378135 | insulator and brushing | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2023-08-24 | 2025-08-17 | Level 2 | Standards change
124378406 | pole | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-07 | 2025-08-16 | Level 2 | Standards change
124378407 | other | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2024-10-23 | 2027-08-16 | Level 3 | GO 165 Inspection
124378519 | insulator and brushing | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2023-09-29 | 2025-08-17 | Level 2 | Standards change
124378855 | other | Non-HFTD | Transmission | 2022-08-16 | 2023-08-16 | Level 2 | E | 2023-02-08 | 2025-08-16 | Level 2 | Standards change
124379041 | other | Non-HFTD | Transmission | 2022-08-26 | 2024-08-26 | Level 3 | F | 2024-01-05 | 2027-08-26 | Level 3 | Standards change
124379051 | anchor/guy | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2024-01-05 | 2027-08-17 | Level 3 | Standards change
124379788 | pole | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2024-08-14 | 2027-08-26 | Level 3 | GO 165 Inspection
124380891 | insulator and brushing | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2024-09-20 | 2025-08-26 | Level 2 | GO 165 Inspection
124381161 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-03-07 | 2025-08-18 | Level 2 | Standards change
124381187 | anchor/guy | Non-HFTD | Transmission | 2022-08-27 | 2023-08-27 | Level 2 | E | 2023-01-25 | 2027-08-27 | Level 3 | Standards change
124381498 | anchor/guy | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-10 | 2027-08-22 | Level 3 | Standards change
124381600 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-02-01 | 2025-08-18 | Level 2 | Standards change
124381805 | insulator and brushing | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2024-08-27 | 2027-08-18 | Level 3 | GO 165 Inspection
124381808 | pole | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2023-03-07 | 2025-08-18 | Level 2 | Standards change
124381948 | other | Non-HFTD | Transmission | 2022-08-18 | 2024-08-18 | Level 3 | F | 2023-03-20 | 2027-08-18 | Level 3 | Standards change
124382046 | insulator and brushing | Non-HFTD | Transmission | 2022-08-18 | 2023-08-18 | Level 2 | E | 2024-02-01 | 2025-08-18 | Level 2 | Standards change
124382192 | other | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-03-09 | 2025-08-19 | Level 2 | Standards change
124382198 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-17 | 2025-08-19 | Level 2 | Standards change
124382273 | other | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-03-03 | 2027-08-22 | Level 3 | Standards change
124382275 | crossarm | Non-HFTD | Transmission | 2022-08-27 | 2023-08-27 | Level 2 | E | 2023-01-24 | 2025-08-27 | Level 2 | Standards change
124382369 | anchor/guy | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-10 | 2025-08-22 | Level 2 | Standards change
124382574 | pole | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-26 | 2025-08-22 | Level 2 | Standards change
124382682 | other | Non-HFTD | Transmission | 2022-08-27 | 2024-08-27 | Level 3 | F | 2024-01-02 | 2027-08-27 | Level 3 | Standards change
124382815 | other | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-01-19 | 2025-08-23 | Level 2 | Standards change
124382918 | crossarm | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-23 | 2025-08-19 | Level 2 | Standards change
124382967 | insulator and brushing | Non-HFTD | Transmission | 2022-08-27 | 2023-08-27 | Level 2 | E | 2024-01-09 | 2025-08-27 | Level 2 | Standards change
124383041 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-16 | 2025-08-19 | Level 2 | Standards change
124383048 | other | Non-HFTD | Transmission | 2022-08-19 | 2024-08-19 | Level 3 | F | 2024-04-06 | 2027-08-19 | Level 3 | Standards change
124383057 | pole | Non-HFTD | Transmission | 2022-08-27 | 2023-08-27 | Level 2 | E | 2024-01-18 | 2025-08-27 | Level 2 | Standards change
124383091 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-17 | 2025-08-19 | Level 2 | Standards change
124383099 | other | Non-HFTD | Transmission | 2022-08-19 | 2024-08-19 | Level 3 | F | 2024-04-06 | 2027-08-19 | Level 3 | Standards change
124383180 | pole | Non-HFTD | Transmission | 2022-08-19 | 2023-08-19 | Level 2 | E | 2023-02-23 | 2025-08-19 | Level 2 | Standards change
124383415 | other | Non-HFTD | Transmission | 2022-08-22 | 2024-08-22 | Level 3 | F | 2023-02-13 | 2027-08-22 | Level 3 | Standards change
124383501 | other | Non-HFTD | Transmission | 2022-08-23 | 2024-08-23 | Level 3 | F | 2024-04-06 | 2027-08-23 | Level 3 | Standards change
124383658 | anchor/guy | Non-HFTD | Transmission | 2022-08-27 | 2023-08-27 | Level 2 | E | 2024-08-24 | 2027-08-27 | Level 3 | GO 165 Inspection
124384444 | anchor/guy | Non-HFTD | Transmission | 2022-08-28 | 2023-08-28 | Level 2 | E | 2023-01-19 | 2025-08-28 | Level 2 | Standards change
124384527 | pole | Non-HFTD | Transmission | 2022-08-28 | 2023-08-28 | Level 2 | E | 2023-03-07 | 2025-08-28 | Level 2 | Standards change
124385915 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-07-13 | 2027-08-29 | Level 3 | Standards change
124386179 | other | Non-HFTD | Transmission | 2022-08-23 | 2024-08-23 | Level 3 | F | 2024-07-23 | 2027-08-23 | Level 3 | GO 165 Inspection
124386253 | other | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-03-01 | 2027-08-23 | Level 3 | Standards change
124386471 | insulator and brushing | Non-HFTD | Transmission | 2022-08-22 | 2023-08-22 | Level 2 | E | 2023-01-19 | 2027-08-22 | Level 3 | Standards change
124386559 | other | Non-HFTD | Transmission | 2022-08-24 | 2024-08-24 | Level 3 | F | 2024-04-06 | 2027-08-24 | Level 3 | Standards change
124386591 | other | Non-HFTD | Transmission | 2022-08-24 | 2024-08-24 | Level 3 | F | 2024-04-06 | 2027-08-24 | Level 3 | Standards change
124386722 | insulator and brushing | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-03-01 | 2025-08-23 | Level 2 | Standards change
124386945 | other | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-03-06 | 2027-08-23 | Level 3 | Standards change
124387096 | other | Non-HFTD | Transmission | 2022-08-23 | 2024-08-23 | Level 3 | F | 2024-01-29 | 2027-08-23 | Level 3 | Standards change
124387513 | other | Non-HFTD | Transmission | 2022-08-23 | 2027-08-23 | Level 3 | F |  | 2027-08-23 | Level 3
124387956 | other | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2024-01-04 | 2027-08-23 | Level 3 | Standards change
124388006 | insulator and brushing | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-03-01 | 2025-08-23 | Level 2 | Standards change
124388108 | pole | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2024-12-18 | 2023-08-24 | Level 2 | GO 165 Inspection
124388894 | other | Non-HFTD | Transmission | 2022-08-24 | 2024-08-24 | Level 3 | F | 2023-02-13 | 2027-08-24 | Level 3 | Standards change
124389776 | pole | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-01-23 | 2025-08-24 | Level 2 | Standards change
124389909 | other | Non-HFTD | Transmission | 2022-08-24 | 2024-08-24 | Level 3 | F | 2024-07-29 | 2027-08-24 | Level 3 | Field Safety Reassessment
124390028 | pole | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-02-20 | 2027-08-29 | Level 3 | Standards change
124390199 | other | Non-HFTD | Transmission | 2022-08-19 | 2024-08-19 | Level 3 | F | 2024-04-06 | 2027-08-19 | Level 3 | Standards change
124390251 | pole | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-02-13 | 2025-08-24 | Level 2 | Standards change
124390372 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-02-17 | 2027-08-29 | Level 3 | Standards change
124390376 | pole | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-11-14 | 2025-08-29 | Level 2 | GO 165 Inspection
124390605 | pole | Non-HFTD | Transmission | 2022-08-24 | 2023-08-24 | Level 2 | E | 2023-03-07 | 2025-08-24 | Level 2 | Standards change
124390821 | pole | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-03-24 | 2025-08-29 | Level 2 | Standards change
124391074 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-02-07 | 2025-08-29 | Level 2 | Standards change
124391123 | pole | Non-HFTD | Transmission | 2022-08-29 | 2024-08-29 | Level 3 | F | 2024-10-24 | 2027-08-29 | Level 3 | GO 165 Inspection
124391127 | anchor/guy | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-07-18 | 2025-08-29 | Level 2 | Standards change
124391361 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-07-16 | 2025-08-29 | Level 2 | GO 165 Inspection
124392542 | insulator and brushing | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-08 | 2025-08-30 | Level 2 | Standards change
124392658 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-03-07 | 2027-08-29 | Level 3 | Standards change
124392788 | insulator and brushing | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-06-27 | 2025-08-30 | Level 2 | GO 165 Inspection
124392961 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-08-14 | 2025-08-29 | Level 2 | GO 165 Inspection
124393073 | other | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-12-05 | 2025-08-25 | Level 2 | Standards change
124393127 | insulator and brushing | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-01-18 | 2025-08-25 | Level 2 | Standards change
124393226 | other | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-12-05 | 2027-08-25 | Level 3 | Standards change
124393846 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2024-11-14 | 2025-08-25 | Level 2 | GO 165 Inspection
124393896 | pole | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-01-24 | 2025-08-30 | Level 2 | Standards change
124394030 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2024-06-19 | 2025-08-25 | Level 2 | GO 165 Inspection
124396364 | other | Non-HFTD | Transmission | 2022-08-30 | 2024-08-30 | Level 3 | F | 2024-01-05 | 2027-08-30 | Level 3 | Standards change
124397429 | other | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2024-02-05 | 2027-08-25 | Level 3 | Standards change
124402824 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-14 | 2025-08-30 | Level 2 | Standards change
124404175 | pole | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-14 | 2025-08-30 | Level 2 | Standards change
124406799 | other | Non-HFTD | Transmission | 2022-08-25 | 2024-08-25 | Level 3 | F | 2024-04-06 | 2027-08-25 | Level 3 | Standards change
124407308 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-14 | 2025-08-30 | Level 2 | Standards change
124407353 | pole | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-14 | 2025-08-30 | Level 2 | Standards change
124408099 | other | Non-HFTD | Transmission | 2022-08-30 | 2024-08-30 | Level 3 | F | 2024-01-11 | 2025-08-30 | Level 2 | Standards change
124408603 | pole | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-14 | 2025-08-30 | Level 2 | Standards change
124408838 | other | Non-HFTD | Transmission | 2022-08-26 | 2024-08-26 | Level 3 | F | 2024-04-06 | 2027-08-26 | Level 3 | Standards change
124408885 | other | Non-HFTD | Transmission | 2022-08-26 | 2024-08-26 | Level 3 | F | 2023-12-28 | 2027-08-26 | Level 3 | Standards change
124412004 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-07-16 | 2027-08-30 | Level 3 | GO 165 Inspection
124412785 | pole | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-01-09 | 2025-08-30 | Level 2 | Standards change
124412860 | other | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2024-12-02 | 2025-08-25 | Level 2 | GO 165 Inspection
124414657 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-01-06 | 2027-08-31 | Level 3 | Standards change
124414680 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-01-06 | 2027-08-31 | Level 3 | Standards change
124414766 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-01-06 | 2027-08-31 | Level 3 | Standards change
124415805 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-01-06 | 2027-08-30 | Level 3 | Standards change
124416025 | other | Non-HFTD | Transmission | 2022-08-26 | 2024-08-26 | Level 3 | F | 2023-08-03 | 2027-08-26 | Level 3 | Standards change
124416479 | pole | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2024-06-27 | 2027-08-25 | Level 3 | GO 165 Inspection
124417241 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-02-08 | 2025-08-31 | Level 2 | GO 165 Inspection
124425762 | other | Non-HFTD | Transmission | 2022-08-31 | 2024-08-31 | Level 3 | F | 2024-11-12 | 2027-08-31 | Level 3 | GO 165 Inspection
124425845 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-03-08 | 2027-08-31 | Level 3 | Standards change
124426076 | pole | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-10-22 | 2025-08-31 | Level 2 | GO 165 Inspection
124426451 | insulator and brushing | Non-HFTD | Transmission | 2022-08-05 | 2023-08-05 | Level 2 | E | 2023-01-25 | 2025-08-05 | Level 2 | Standards change
124426623 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-01-02 | 2027-08-31 | Level 3 | Standards change
124426776 | pole | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-09-18 | 2025-08-31 | Level 2 | Standards change
124427275 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-08-29 | 2023-08-31 | Level 2 | GO 165 Inspection
124428015 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-10-31 | 2027-09-01 | Level 3 | GO 165 Inspection
124428918 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-08-02 | 2025-08-30 | Level 2 | GO 165 Inspection
124428972 | insulator and brushing | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2023-03-24 | 2025-08-25 | Level 2 | Standards change
124428976 | other | Non-HFTD | Transmission | 2022-08-25 | 2023-08-25 | Level 2 | E | 2024-09-04 | 2027-08-25 | Level 3 | GO 165 Inspection
124429302 | other | Non-HFTD | Transmission | 2022-08-31 | 2024-08-31 | Level 3 | F | 2024-11-19 | 2027-08-31 | Level 3 | GO 165 Inspection
124429972 | pole | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-11-19 | 2025-08-31 | Level 2 | GO 165 Inspection
124430506 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-07-08 | 2025-08-31 | Level 2 | GO 165 Inspection
124431244 | other | Non-HFTD | Transmission | 2022-09-01 | 2024-09-01 | Level 3 | F | 2024-04-06 | 2027-09-01 | Level 3 | Standards change
124432162 | anchor/guy | Non-HFTD | Transmission | 2022-08-26 | 2025-08-26 | Level 2 | E | 2024-11-13 | 2023-08-26 | Level 2 | GO 165 Inspection
124432422 | anchor/guy | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-01-10 | 2027-09-01 | Level 3 | Standards change
124433239 | anchor/guy | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-01-09 | 2025-09-01 | Level 2 | Standards change
124433656 | other | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2024-11-08 | 2027-08-26 | Level 3 | GO 165 Inspection
124433878 | other | Non-HFTD | Transmission | 2022-08-26 | 2024-08-26 | Level 3 | F | 2024-11-12 | 2027-08-26 | Level 3 | GO 165 Inspection
124433986 | insulator and brushing | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2023-02-13 | 2025-08-26 | Level 2 | Standards change
124434086 | other | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2024-11-08 | 2025-08-26 | Level 2 | GO 165 Inspection
124434715 | other | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2023-08-03 | 2027-08-26 | Level 3 | Standards change
124434716 | other | Non-HFTD | Transmission | 2022-08-26 | 2023-08-26 | Level 2 | E | 2023-08-03 | 2027-08-26 | Level 3 | Standards change
124437209 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-02-16 | 2025-09-01 | Level 2 | Standards change
124437274 | switch | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-02-16 | 2025-09-01 | Level 2 | Standards change
124437417 | anchor/guy | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-07-27 | 2027-09-02 | Level 3 | Standards change
124437427 | other | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-08-30 | 2025-09-01 | Level 2 | GO 165 Inspection
124438041 | insulator and brushing | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-02-07 | 2025-08-29 | Level 2 | Standards change
124438649 | pole | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-08-21 | 2025-08-29 | Level 2 | GO 165 Inspection
124438916 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-02-23 | 2025-09-02 | Level 2 | Standards change
124439074 | other | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-10-30 | 2025-09-01 | Level 2 | GO 165 Inspection
124439183 | other | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-08-14 | 2027-08-29 | Level 3 | GO 165 Inspection
124440474 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-14 | 2025-08-30 | Level 2 | Standards change
124441345 | other | Non-HFTD | Transmission | 2022-08-29 | 2024-08-29 | Level 3 | F | 2023-10-24 | 2027-08-29 | Level 3 | Standards change
124441401 | pole | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2024-08-14 | 2025-08-29 | Level 2 | GO 165 Inspection
124441610 | other | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-07-22 | 2027-09-02 | Level 3 | GO 165 Inspection
124441814 | pole | Non-HFTD | Transmission | 2022-08-29 | 2023-08-29 | Level 2 | E | 2023-03-08 | 2025-08-29 | Level 2 | Standards change
124442322 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-11-05 | 2025-09-02 | Level 2 | GO 165 Inspection
124442327 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-10-22 | 2025-09-02 | Level 2 | GO 165 Inspection
124443586 | anchor/guy | Non-HFTD | Transmission | 2022-09-03 | 2023-09-03 | Level 2 | E | 2023-02-07 | 2025-09-03 | Level 2 | Standards change
124444355 | other | Non-HFTD | Transmission | 2022-09-03 | 2024-09-03 | Level 3 | F | 2023-02-13 | 2027-09-03 | Level 3 | Standards change
124444673 | other | Non-HFTD | Transmission | 2022-09-03 | 2024-09-03 | Level 3 | F | 2023-07-20 | 2027-09-03 | Level 3 | Standards change
124446057 | pole | Non-HFTD | Transmission | 2022-09-04 | 2023-09-04 | Level 2 | E | 2023-03-08 | 2025-09-04 | Level 2 | Standards change
124447458 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-02-14 | 2025-09-02 | Level 2 | Standards change
124447611 | insulator and brushing | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-08-30 | 2025-09-02 | Level 2 | GO 165 Inspection
124447736 | insulator and brushing | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-10-30 | 2025-09-02 | Level 2 | GO 165 Inspection
124447840 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-10-31 | 2025-09-02 | Level 2 | GO 165 Inspection
124447847 | insulator and brushing | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-10-31 | 2025-09-02 | Level 2 | GO 165 Inspection
124448186 | other | Non-HFTD | Transmission | 2022-08-01 | 2024-08-01 | Level 3 | F | 2023-04-04 | 2027-08-01 | Level 3 | Standards change
124448299 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-03-08 | 2027-08-30 | Level 3 | Standards change
124448522 | pole | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-01-25 | 2025-08-30 | Level 2 | Standards change
124449152 | anchor/guy | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-03-08 | 2027-08-30 | Level 3 | Standards change
124449343 | anchor/guy | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-11-19 | 2025-08-30 | Level 2 | GO 165 Inspection
124449348 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-08-12 | 2027-08-30 | Level 3 | GO 165 Inspection
124449591 | insulator and brushing | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-03-10 | 2025-09-06 | Level 2 | Standards change
124450063 | other | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2024-08-01 | 2025-09-06 | Level 2 | GO 165 Inspection
124450921 | insulator and brushing | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-03-08 | 2025-09-06 | Level 2 | Standards change
124450998 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-02-15 | 2025-08-30 | Level 2 | Standards change
124452675 | insulator and brushing | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-01-31 | 2025-08-30 | Level 2 | Standards change
124452754 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-03-02 | 2027-08-30 | Level 3 | Standards change
124452879 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-01-09 | 2027-08-31 | Level 3 | Standards change
124453112 | other | Non-HFTD | Transmission | 2022-08-31 | 2024-08-31 | Level 3 | F | 2024-01-09 | 2027-08-31 | Level 3 | Standards change
124453152 | insulator and brushing | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2024-08-19 | 2027-08-30 | Level 3 | GO 165 Inspection
124453432 | other | Non-HFTD | Transmission | 2022-08-30 | 2023-08-30 | Level 2 | E | 2023-03-02 | 2027-08-30 | Level 3 | Standards change
124453436 | pole | Non-HFTD | Transmission | 2022-08-30 | 2024-08-30 | Level 3 | F | 2024-10-28 | 2027-08-30 | Level 3 | GO 165 Inspection
124453974 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-02-13 | 2025-08-31 | Level 2 | Standards change
124454746 | crossarm | Non-HFTD | Transmission | 2022-09-07 | 2023-09-07 | Level 2 | E | 2023-01-20 | 2025-09-07 | Level 2 | Standards change
124455222 | pole | Non-HFTD | Transmission | 2022-09-07 | 2023-09-07 | Level 2 | E | 2023-01-20 | 2025-09-07 | Level 2 | Standards change
124455638 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-07-18 | 2027-08-31 | Level 3 | Field Safety Reassessment
124455758 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-08-30 | 2025-08-31 | Level 2 | GO 165 Inspection
124455823 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-02-14 | 2025-08-31 | Level 2 | Standards change
124456067 | insulator and brushing | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-01-26 | 2025-08-31 | Level 2 | Standards change
124456105 | pole | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-01-23 | 2025-08-31 | Level 2 | Standards change
124456106 | other | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-02-15 | 2027-08-31 | Level 3 | Standards change
124456107 | anchor/guy | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-02-15 | 2027-08-31 | Level 3 | Standards change
124457161 | other | Non-HFTD | Transmission | 2022-08-31 | 2024-08-31 | Level 3 | F | 2023-12-20 | 2027-08-31 | Level 3 | Standards change
124457167 | other | Non-HFTD | Transmission | 2022-08-31 | 2024-08-31 | Level 3 | F | 2023-12-20 | 2027-08-31 | Level 3 | Standards change
124457180 | pole | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2023-03-02 | 2025-08-31 | Level 2 | Standards change
124458923 | insulator and brushing | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2024-11-15 | 2025-09-06 | Level 2 | GO 165 Inspection
124459091 | other | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-03-02 | 2027-09-01 | Level 3 | Standards change
124459370 | splice | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-02-03 | 2025-09-06 | Level 2 | Standards change
124459541 | other | Non-HFTD | Transmission | 2022-09-01 | 2024-09-01 | Level 3 | F | 2023-12-15 | 2027-09-01 | Level 3 | Standards change
124459581 | other | Non-HFTD | Transmission | 2022-09-08 | 2024-09-08 | Level 3 | F | 2023-02-14 | 2027-09-08 | Level 3 | Standards change
124459693 | other | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-12-21 | 2027-09-01 | Level 3 | Standards change
124460471 | other | Non-HFTD | Transmission | 2022-08-31 | 2024-08-31 | Level 3 | F | 2023-12-14 | 2027-08-31 | Level 3 | Standards change
124460546 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-12-11 | 2027-09-08 | Level 3 | Field Safety Reassessment
124460547 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-14 | 2027-09-08 | Level 3 | Standards change
124460736 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-14 | 2027-09-08 | Level 3 | Standards change
124461042 | other | HFTD Tier 3 | Transmission | 2022-09-08 | 2024-09-08 | Level 3 | F | 2024-05-06 | 2027-09-08 | Level 3 | GO 165 Inspection
124462498 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-02-14 | 2025-09-01 | Level 2 | Standards change
124462759 | insulator and brushing | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-02-03 | 2025-09-06 | Level 2 | Standards change
124462885 | pole | Non-HFTD | Transmission | 2022-09-06 | 2025-09-06 | Level 2 | E | 2024-11-15 | 2023-09-06 | Level 2 | GO 165 Inspection
124462888 | anchor/guy | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-03-09 | 2025-09-06 | Level 2 | Standards change
124463061 | other | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-03-02 | 2027-09-01 | Level 3 | Standards change
124464371 | pole | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-02-15 | 2025-09-01 | Level 2 | Standards change
124467227 | other | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-02-13 | 2025-09-06 | Level 2 | Standards change
124468076 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-02-01 | 2027-09-08 | Level 3 | Standards change
124468441 | pole | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-01-20 | 2025-09-09 | Level 2 | Standards change
124468588 | pole | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-03-13 | 2025-09-01 | Level 2 | Standards change
124468918 | other | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-02-02 | 2025-09-01 | Level 2 | Standards change
124468995 | other | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-02-14 | 2027-09-09 | Level 3 | Standards change
124469015 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-02-14 | 2025-09-01 | Level 2 | Standards change
124469026 | insulator and brushing | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-03-13 | 2025-09-09 | Level 2 | Standards change
124469294 | pole | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-01-20 | 2025-09-09 | Level 2 | Standards change
124469358 | pole | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2024-05-03 | 2025-09-09 | Level 2 | GO 165 Inspection
124470365 | insulator and brushing | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-28 | 2025-09-08 | Level 2 | Standards change
124470802 | insulator and brushing | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-02-14 | 2027-09-09 | Level 3 | Standards change
124470920 | crossarm | Non-HFTD | Transmission | 2022-09-08 | 2025-09-08 | Level 2 | E | 2024-10-28 | 2027-09-08 | Level 3 | GO 165 Inspection
124470923 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-10-28 | 2025-09-08 | Level 2 | GO 165 Inspection
124483883 | other | Non-HFTD | Transmission | 2022-09-10 | 2024-09-10 | Level 3 | F | 2023-02-13 | 2027-09-10 | Level 3 | Standards change
124484259 | anchor/guy | Non-HFTD | Transmission | 2022-09-10 | 2023-09-10 | Level 2 | E | 2023-02-17 | 2025-09-10 | Level 2 | Standards change
124484286 | pole | Non-HFTD | Transmission | 2022-09-10 | 2023-09-10 | Level 2 | E | 2023-02-14 | 2025-09-10 | Level 2 | Standards change
124485784 | other | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2023-02-28 | 2027-09-12 | Level 3 | Standards change
124486220 | anchor/guy | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2023-08-12 | 2027-09-12 | Level 3 | Standards change
124486290 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-12-05 | 2025-09-01 | Level 2 | Standards change
124487746 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-10-31 | 2025-09-01 | Level 2 | GO 165 Inspection
124488060 | other | Non-HFTD | Transmission | 2022-09-09 | 2024-09-09 | Level 3 | F | 2023-12-11 | 2027-09-09 | Level 3 | Standards change
124488619 | anchor/guy | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2024-01-08 | 2027-09-12 | Level 3 | Standards change
124491691 | other | Non-HFTD | Transmission | 2022-09-02 | 2025-09-02 | Level 2 | E | 2024-10-30 | 2023-09-02 | Level 2 | GO 165 Inspection
124491777 | other | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-08-27 | 2025-09-02 | Level 2 | GO 165 Inspection
124491779 | other | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-03-06 | 2025-09-09 | Level 2 | Standards change
124491863 | anchor/guy | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-12-26 | 2027-09-02 | Level 3 | Standards change
124491878 | pole | Non-HFTD | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-01-09 | 2025-08-31 | Level 2 | Standards change
124491972 | other | Non-HFTD | Transmission | 2022-09-01 | 2022-12-01 | Level 2 | B | 2024-10-23 | 2027-09-01 | Level 3 | GO 165 Inspection
124492296 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-02-14 | 2025-09-02 | Level 2 | Standards change
124492309 | other | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-12-09 | 2025-09-02 | Level 2 | Field Safety Reassessment
124492358 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-02-14 | 2025-09-01 | Level 2 | Standards change
124492366 | other | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-02-15 | 2025-09-02 | Level 2 | Standards change
124492372 | other | Non-HFTD | Transmission | 2022-09-02 | 2025-09-02 | Level 2 | E | 2024-10-31 | 2023-09-02 | Level 2 | GO 165 Inspection
124492390 | insulator and brushing | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-02-15 | 2025-09-02 | Level 2 | Standards change
124492393 | other | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-01-27 | 2025-09-02 | Level 2 | Standards change
124492448 | anchor/guy | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-09-26 | 2027-09-02 | Level 3 | Standards change
124492498 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-05-08 | 2025-09-08 | Level 2 | Standards change
124492513 | other | Non-HFTD | Transmission | 2022-09-02 | 2025-09-02 | Level 2 | E | 2024-11-05 | 2023-09-02 | Level 2 | GO 165 Inspection
124492521 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-01-09 | 2025-09-02 | Level 2 | Standards change
124493057 | pole | Non-HFTD | Transmission | 2022-06-24 | 2023-06-24 | Level 2 | E | 2024-01-10 | 2025-06-24 | Level 2 | Standards change
124493779 | anchor/guy | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-02-16 | 2025-09-13 | Level 2 | Standards change
124494021 | other | Non-HFTD | Transmission | 2022-09-02 | 2025-09-02 | Level 2 | E | 2024-11-19 | 2023-09-02 | Level 2 | GO 165 Inspection
124494505 | other | Non-HFTD | Transmission | 2022-09-01 | 2024-09-01 | Level 3 | F | 2023-12-20 | 2027-09-01 | Level 3 | Standards change
124495572 | insulator and brushing | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-02-14 | 2025-09-01 | Level 2 | Standards change
124496946 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-01-09 | 2027-09-13 | Level 3 | Standards change
124497032 | anchor/guy | Non-HFTD | Transmission | 2022-09-06 | 2027-09-06 | Level 3 | F | 2024-04-04 | 2025-09-06 | Level 2 | GO 165 Inspection
124497230 | insulator and brushing | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2024-01-10 | 2025-09-12 | Level 2 | Standards change
124497236 | pole | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-02-13 | 2025-09-13 | Level 2 | Standards change
124498731 | insulator and brushing | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-01-27 | 2027-09-02 | Level 3 | Standards change
124498734 | anchor/guy | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2023-03-13 | 2025-09-06 | Level 2 | Standards change
124500591 | other | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2023-02-13 | 2025-09-12 | Level 2 | Standards change
124501232 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-01-10 | 2025-09-13 | Level 2 | Standards change
124501608 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2023-01-17 | 2025-09-02 | Level 2 | Standards change
124501675 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-01-06 | 2025-09-08 | Level 2 | Standards change
124502244 | other | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2024-07-18 | 2025-09-06 | Level 2 | GO 165 Inspection
124502735 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-10-12 | 2025-09-02 | Level 2 | GO 165 Inspection
124502937 | pole | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2023-01-23 | 2025-09-14 | Level 2 | Standards change
124503038 | pole | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-10-28 | 2025-09-02 | Level 2 | GO 165 Inspection
124503971 | other | Non-HFTD | Transmission | 2022-09-06 | 2023-09-06 | Level 2 | E | 2024-11-15 | 2027-09-06 | Level 3 | GO 165 Inspection
124505569 | pole | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2024-11-20 | 2025-09-12 | Level 2 | GO 165 Inspection
124506473 | insulator and brushing | Non-HFTD | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-11-05 | 2025-09-02 | Level 2 | GO 165 Inspection
124508893 | switch | Non-HFTD | Transmission | 2022-09-14 | 2022-12-14 | Level 2 | B | 2024-08-02 | 2023-03-14 | Level 2 | Field Safety Reassessment
124509230 | insulator and brushing | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2023-08-07 | 2025-09-14 | Level 2 | Standards change
124509662 | pole | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-10-14 | 2025-09-13 | Level 2 | GO 165 Inspection
124509666 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-10-14 | 2025-09-13 | Level 2 | GO 165 Inspection
124509756 | pole | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2023-01-17 | 2025-09-12 | Level 2 | Standards change
124509794 | anchor/guy | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2023-03-13 | 2025-09-14 | Level 2 | Standards change
124509811 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-02-09 | 2025-09-13 | Level 2 | Standards change
124509985 | pole | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2024-10-23 | 2025-09-15 | Level 2 | GO 165 Inspection
124510494 | pole | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2024-01-10 | 2025-09-09 | Level 2 | Standards change
124510713 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2022-12-13 | 2027-09-15 | Level 3 | Standards change
124511692 | other | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2023-02-16 | 2027-09-15 | Level 3 | Standards change
124511981 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-01-03 | 2025-09-08 | Level 2 | Standards change
124513035 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2023-12-20 | 2027-09-15 | Level 3 | Standards change
124513048 | insulator and brushing | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2024-10-24 | 2025-09-15 | Level 2 | GO 165 Inspection
124513142 | other | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-03-01 | 2027-09-08 | Level 3 | Standards change
124513295 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-27 | 2025-09-08 | Level 2 | Standards change
124513482 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-27 | 2025-09-08 | Level 2 | Standards change
124516521 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-10-07 | 2025-09-13 | Level 2 | GO 165 Inspection
124517766 | anchor/guy | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2023-08-21 | 2025-09-14 | Level 2 | Standards change
124518052 | pole | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-11-15 | 2027-09-16 | Level 3 | GO 165 Inspection
124518204 | other | Non-HFTD | Transmission | 2022-09-14 | 2024-09-14 | Level 3 | F | 2024-08-13 | 2027-09-14 | Level 3 | GO 165 Inspection
124518205 | anchor/guy | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2024-08-13 | 2025-09-14 | Level 2 | GO 165 Inspection
124518390 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-15 | 2025-09-16 | Level 2 | GO 165 Inspection
124519125 | pole | Non-HFTD | Transmission | 2022-09-16 | 2025-09-16 | Level 2 | E | 2024-11-18 | 2023-09-16 | Level 2 | GO 165 Inspection
124519361 | insulator and brushing | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-16 | 2025-09-16 | Level 2 | GO 165 Inspection
124519766 | pole | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-11-14 | 2027-09-16 | Level 3 | GO 165 Inspection
124519930 | insulator and brushing | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-18 | 2025-09-16 | Level 2 | GO 165 Inspection
124520019 | insulator and brushing | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2024-10-04 | 2025-09-15 | Level 2 | GO 165 Inspection
124520358 | other | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-11-19 | 2027-09-16 | Level 3 | GO 165 Inspection
124520651 | insulator and brushing | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-18 | 2025-09-16 | Level 2 | GO 165 Inspection
124520976 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-16 | 2027-09-16 | Level 3 | GO 165 Inspection
124522283 | pole | Non-HFTD | Transmission | 2022-09-17 | 2023-09-17 | Level 2 | E | 2024-10-21 | 2025-09-17 | Level 2 | GO 165 Inspection
124522799 | other | Non-HFTD | Transmission | 2022-09-17 | 2023-09-17 | Level 2 | E | 2023-03-01 | 2027-09-17 | Level 3 | Standards change
124527203 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-02-12 | 2025-09-08 | Level 2 | GO 165 Inspection
124527582 | insulator and brushing | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-10-25 | 2025-09-19 | Level 2 | GO 165 Inspection
124527975 | pole | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-08-15 | 2025-09-19 | Level 2 | GO 165 Inspection
124529061 | pole | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2023-02-17 | 2025-09-19 | Level 2 | Standards change
124529873 | other | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-01-10 | 2025-09-19 | Level 2 | Standards change
124530324 | pole | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-10-09 | 2025-09-19 | Level 2 | GO 165 Inspection
124530662 | insulator and brushing | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-07-25 | 2025-09-08 | Level 2 | GO 165 Inspection
124532305 | anchor/guy | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-03-02 | 2025-09-08 | Level 2 | Standards change
124532402 | other | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-10-22 | 2025-09-08 | Level 2 | GO 165 Inspection
124532493 | insulator and brushing | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2024-07-24 | 2025-09-09 | Level 2 | GO 165 Inspection
124532779 | insulator and brushing | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2024-07-23 | 2025-09-09 | Level 2 | GO 165 Inspection
124532832 | insulator and brushing | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2024-01-19 | 2025-09-08 | Level 2 | Standards change
124532844 | pole | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-01-06 | 2027-09-09 | Level 3 | Standards change
124533435 | other | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-07-31 | 2027-09-20 | Level 3 | GO 165 Inspection
124533589 | other | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2024-01-31 | 2027-09-09 | Level 3 | Standards change
124533627 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-08-31 | 2027-09-20 | Level 3 | GO 165 Inspection
124534222 | other | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-01-13 | 2025-09-09 | Level 2 | Standards change
124535504 | other | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-02-13 | 2027-09-09 | Level 3 | Standards change
124536230 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-02-16 | 2025-09-20 | Level 2 | Standards change
124536763 | insulator and brushing | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E |  | 2023-09-16 | Level 2
124537739 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-28 | 2025-09-08 | Level 2 | Standards change
124538167 | pole | Non-HFTD | Transmission | 2022-09-08 | 2023-09-08 | Level 2 | E | 2023-02-15 | 2025-09-08 | Level 2 | Standards change
124538597 | pole | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-03-13 | 2025-09-13 | Level 2 | Standards change
124539010 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-11-13 | 2025-09-20 | Level 2 | Standards change
124539051 | insulator and brushing | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-11-14 | 2025-09-20 | Level 2 | Standards change
124539160 | other | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2024-08-20 | 2027-09-15 | Level 3 | GO 165 Inspection
124539247 | other | Non-HFTD | Transmission | 2022-09-12 | 2024-09-12 | Level 3 | F | 2024-08-31 | 2027-09-12 | Level 3 | GO 165 Inspection
124539568 | other | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2023-12-28 | 2027-09-16 | Level 3 | Standards change
124539627 | insulator and brushing | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2023-02-03 | 2025-09-12 | Level 2 | Standards change
124539661 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-01-11 | 2027-09-13 | Level 3 | Standards change
124539720 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-02-13 | 2027-09-13 | Level 3 | Standards change
124540510 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2025-09-13 | Level 2 | E | 2024-11-05 | 2023-09-13 | Level 2 | GO 165 Inspection
124540525 | insulator and brushing | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-03-03 | 2025-09-20 | Level 2 | Standards change
124540571 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-10-24 | 2025-09-20 | Level 2 | GO 165 Inspection
124540640 | switch | Non-HFTD | Transmission | 2022-09-20 | 2022-12-20 | Level 2 | B | 2023-01-26 | 2025-09-20 | Level 2 | Standards change
124541020 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-10-29 | 2025-09-21 | Level 2 | GO 165 Inspection
124541336 | insulator and brushing | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-07-19 | 2025-09-20 | Level 2 | GO 165 Inspection
124541915 | pole | Non-HFTD | Transmission | 2022-09-21 | 2022-12-21 | Level 2 | E | 2024-09-16 | 2022-12-21 | Level 2 | GO 165 Inspection
124542928 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-12-04 | 2023-09-21 | Level 2 | Field Safety Reassessment
124543285 | other | Non-HFTD | Transmission | 2022-09-09 | 2025-09-09 | Level 2 | E | 2024-09-05 | 2023-03-09 | Level 2 | GO 165 Inspection
124544253 | anchor/guy | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-09-12 | 2025-09-19 | Level 2 | GO 165 Inspection
124544878 | pole | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-10-10 | 2027-09-20 | Level 3 | GO 165 Inspection
124545160 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-04 | 2025-09-16 | Level 2 | GO 165 Inspection
124545542 | conductor | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-03-07 | 2025-09-21 | Level 2 | Standards change
124545544 | pole | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-03-01 | 2027-09-21 | Level 3 | Standards change
124547239 | insulator and brushing | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-11-27 | 2025-09-19 | Level 2 | GO 165 Inspection
124547557 | switch | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2024-12-06 | 2023-09-22 | Level 2 | Field Safety Reassessment
124547907 | other | Non-HFTD | Transmission | 2022-09-19 | 2024-09-19 | Level 3 | F | 2024-08-15 | 2027-09-19 | Level 3 | GO 165 Inspection
124548015 | other | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-07-18 | 2025-09-21 | Level 2 | GO 165 Inspection
124549333 | pole | Non-HFTD | Transmission | 2022-09-21 | 2024-09-21 | Level 3 | F | 2024-01-10 | 2027-09-21 | Level 3 | Standards change
124549346 | other | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-02-10 | 2025-09-09 | Level 2 | Standards change
124549468 | pole | Non-HFTD | Transmission | 2022-09-19 | 2024-09-19 | Level 3 | F | 2024-11-26 | 2027-09-19 | Level 3 | GO 165 Inspection
124549490 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2024-11-19 | 2025-09-22 | Level 2 | GO 165 Inspection
124550083 | other | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2024-11-18 | 2025-09-22 | Level 2 | GO 165 Inspection
124551194 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-08-28 | 2025-09-22 | Level 2 | Standards change
124553165 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-10-01 | 2025-09-20 | Level 2 | GO 165 Inspection
124553167 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-08-27 | 2025-09-20 | Level 2 | GO 165 Inspection
124553242 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-08-27 | 2027-09-20 | Level 3 | GO 165 Inspection
124553294 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-03-01 | 2027-09-22 | Level 3 | Standards change
124553297 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-03-01 | 2027-09-22 | Level 3 | Standards change
124553474 | anchor/guy | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-07-22 | 2027-09-13 | Level 3 | GO 165 Inspection
124553589 | pole | Non-HFTD | Transmission | 2022-09-09 | 2023-09-09 | Level 2 | E | 2023-03-09 | 2025-09-09 | Level 2 | Standards change
124553809 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-10-09 | 2025-09-13 | Level 2 | GO 165 Inspection
124553820 | pole | Non-HFTD | Transmission | 2022-09-09 | 2024-09-09 | Level 3 | F | 2023-01-19 | 2027-09-09 | Level 3 | Standards change
124553837 | other | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2023-02-28 | 2025-09-12 | Level 2 | Standards change
124553897 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-09-01 | 2025-09-13 | Level 2 | Standards change
124553962 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-08-14 | 2025-09-13 | Level 2 | GO 165 Inspection
124553964 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-08-14 | 2025-09-13 | Level 2 | GO 165 Inspection
124554052 | other | Non-HFTD | Transmission | 2022-09-12 | 2024-09-12 | Level 3 | F | 2024-01-10 | 2027-09-12 | Level 3 | Standards change
124554107 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-11-30 | 2025-09-13 | Level 2 | Standards change
124554211 | other | Non-HFTD | Transmission | 2022-09-14 | 2024-09-14 | Level 3 | F | 2024-04-06 | 2027-09-14 | Level 3 | Standards change
124554314 | other | Non-HFTD | Transmission | 2022-09-12 | 2024-09-12 | Level 3 | F | 2023-12-15 | 2027-09-12 | Level 3 | Standards change
124555817 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2023-12-29 | 2027-09-20 | Level 3 | Standards change
124556604 | insulator and brushing | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-03-08 | 2025-09-20 | Level 2 | Standards change
124557474 | pole | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2024-10-24 | 2025-09-14 | Level 2 | GO 165 Inspection
124558187 | anchor/guy | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2024-07-29 | 2025-09-14 | Level 2 | GO 165 Inspection
124558462 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2024-01-02 | 2027-09-15 | Level 3 | Standards change
124558603 | other | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2023-01-27 | 2025-09-15 | Level 2 | Standards change
124558806 | pole | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-11-16 | 2025-09-23 | Level 2 | GO 165 Inspection
124558909 | other | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-07-18 | 2025-09-20 | Level 2 | GO 165 Inspection
124559760 | pole | Non-HFTD | Transmission | 2022-09-12 | 2023-09-12 | Level 2 | E | 2024-08-22 | 2025-09-12 | Level 2 | GO 165 Inspection
124560309 | insulator and brushing | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-02-15 | 2027-09-23 | Level 3 | Standards change
124560389 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2024-01-02 | 2027-09-15 | Level 3 | Standards change
124560988 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-11-05 | 2025-09-16 | Level 2 | GO 165 Inspection
124561263 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2024-01-10 | 2027-09-15 | Level 3 | Standards change
124561298 | pole | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2024-01-10 | 2027-09-15 | Level 3 | Standards change
124561390 | other | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2023-01-27 | 2025-09-14 | Level 2 | Standards change
124561502 | other | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2024-08-15 | 2025-09-14 | Level 2 | GO 165 Inspection
124561523 | other | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2023-02-13 | 2027-09-13 | Level 3 | Standards change
124562449 | other | Non-HFTD | Transmission | 2022-09-24 | 2023-09-24 | Level 2 | E | 2024-11-16 | 2025-09-24 | Level 2 | GO 165 Inspection
124563211 | pole | Non-HFTD | Transmission | 2022-09-24 | 2023-09-24 | Level 2 | E | 2024-11-16 | 2025-09-24 | Level 2 | GO 165 Inspection
124565741 | insulator and brushing | Non-HFTD | Transmission | 2022-09-13 | 2023-09-13 | Level 2 | E | 2024-10-31 | 2025-09-13 | Level 2 | GO 165 Inspection
124565869 | anchor/guy | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-02-27 | 2025-09-26 | Level 2 | Standards change
124566266 | other | Non-HFTD | Transmission | 2022-09-26 | 2025-09-26 | Level 2 | E | 2024-11-18 | 2027-09-26 | Level 3 | GO 165 Inspection
124566651 | insulator and brushing | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2023-08-01 | 2025-09-15 | Level 2 | Field Safety Reassessment
124567582 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-09-24 | 2025-09-26 | Level 2 | GO 165 Inspection
124567686 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2023-11-30 | 2027-09-15 | Level 3 | Standards change
124567896 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-11-26 | 2025-09-26 | Level 2 | GO 165 Inspection
124567906 | other | Non-HFTD | Transmission | 2022-09-14 | 2025-09-14 | Level 2 | E | 2024-10-09 | 2023-09-14 | Level 2 | GO 165 Inspection
124567921 | other | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-11-18 | 2027-09-26 | Level 3 | GO 165 Inspection
124568697 | insulator and brushing | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2023-02-01 | 2027-09-14 | Level 3 | Standards change
124569257 | pole | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-02-28 | 2025-09-23 | Level 2 | Standards change
124569414 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-02-15 | 2027-09-26 | Level 3 | Standards change
124570204 | other | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2023-01-18 | 2025-09-16 | Level 2 | Standards change
124570373 | crossarm | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-03-08 | 2025-09-26 | Level 2 | Standards change
124571329 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2023-02-28 | 2025-09-16 | Level 2 | Standards change
124571357 | insulator and brushing | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-10-15 | 2023-09-23 | Level 2 | Field Safety Reassessment
124571620 | other | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-10-08 | 2027-09-16 | Level 3 | GO 165 Inspection
124573353 | insulator and brushing | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-07-25 | 2027-09-27 | Level 3 | GO 165 Inspection
124573406 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2023-02-13 | 2025-09-16 | Level 2 | Standards change
124573512 | other | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-01-03 | 2027-09-16 | Level 3 | Standards change
124574414 | other | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-04-06 | 2027-09-16 | Level 3 | Standards change
124574820 | insulator and brushing | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2023-03-10 | 2025-09-27 | Level 2 | Standards change
124575062 | insulator and brushing | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2023-02-15 | 2027-09-27 | Level 3 | Standards change
124575335 | anchor/guy | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2022-12-15 | 2027-09-27 | Level 3 | Standards change
124575621 | pole | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2023-01-09 | 2025-09-27 | Level 2 | Standards change
124576160 | pole | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-07-23 | 2025-09-27 | Level 2 | GO 165 Inspection
124577251 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-01-31 | 2025-09-26 | Level 2 | GO 165 Inspection
124577436 | insulator and brushing | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-02-06 | 2025-09-23 | Level 2 | Standards change
124578172 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2023-03-02 | 2025-09-16 | Level 2 | Standards change
124580082 | anchor/guy | Non-HFTD | Transmission | 2022-09-14 | 2023-09-14 | Level 2 | E | 2024-10-23 | 2025-09-14 | Level 2 | GO 165 Inspection
124581594 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-12-18 | 2023-03-26 | Level 2 | Field Safety Reassessment
124581664 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2024-09-28 | 2025-09-28 | Level 2 | GO 165 Inspection
124581785 | insulator and brushing | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2024-09-27 | 2025-09-22 | Level 2 | GO 165 Inspection
124582058 | other | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2024-11-18 | 2027-09-28 | Level 3 | GO 165 Inspection
124582310 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-02-14 | 2025-09-26 | Level 2 | Standards change
124582566 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2023-01-13 | 2025-09-28 | Level 2 | Standards change
124583890 | other | Non-HFTD | Transmission | 2022-09-28 | 2024-09-28 | Level 3 | F | 2024-04-06 | 2027-09-28 | Level 3 | Standards change
124584584 | other | Non-HFTD | Transmission | 2022-09-28 | 2024-09-28 | Level 3 | F | 2024-04-06 | 2027-09-28 | Level 3 | Standards change
124586563 | insulator and brushing | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-08-27 | 2025-09-23 | Level 2 | GO 165 Inspection
124586626 | other | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2024-09-05 | 2025-09-28 | Level 2 | GO 165 Inspection
124586838 | pole | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2024-01-10 | 2025-09-16 | Level 2 | Standards change
124588854 | pole | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-09-24 | 2025-09-23 | Level 2 | GO 165 Inspection
124588916 | pole | Non-HFTD | Transmission | 2022-09-28 | 2024-09-28 | Level 3 | F | 2024-10-21 | 2027-09-28 | Level 3 | GO 165 Inspection
124589065 | conductor | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-07-27 | 2025-09-26 | Level 2 | Field Safety Reassessment
124589111 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-11-09 | 2023-09-26 | Level 2 | Field Safety Reassessment
124589118 | other | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-01-10 | 2025-09-23 | Level 2 | Standards change
124589507 | other | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2023-02-27 | 2027-09-19 | Level 3 | Standards change
124589918 | other | Non-HFTD | Transmission | 2022-09-15 | 2024-09-15 | Level 3 | F | 2023-11-30 | 2027-09-15 | Level 3 | Standards change
124591330 | insulator and brushing | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-01-31 | 2025-09-26 | Level 2 | Standards change
124591394 | splice | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-11-30 | 2025-09-29 | Level 2 | Field Safety Reassessment
124592460 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-01-24 | 2025-09-29 | Level 2 | Standards change
124592660 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-07-28 | 2025-09-29 | Level 2 | Standards change
124592825 | insulator and brushing | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-09-03 | 2025-09-19 | Level 2 | GO 165 Inspection
124597341 | insulator and brushing | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2023-01-10 | 2025-09-19 | Level 2 | Standards change
124597427 | other | Non-HFTD | Transmission | 2022-09-19 | 2025-09-19 | Level 2 | E | 2024-11-04 | 2027-09-19 | Level 3 | GO 165 Inspection
124597565 | pole | Non-HFTD | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2024-07-19 | 2025-07-20 | Level 2 | GO 165 Inspection
124597693 | insulator and brushing | Non-HFTD | Transmission | 2022-09-19 | 2025-09-19 | Level 2 | E | 2024-06-11 | 2023-09-19 | Level 2 | GO 165 Inspection
124597695 | anchor/guy | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2024-06-11 | 2025-09-19 | Level 2 | GO 165 Inspection
124597722 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-11-05 | 2025-09-29 | Level 2 | GO 165 Inspection
124597929 | other | Non-HFTD | Transmission | 2022-09-19 | 2025-09-19 | Level 2 | E | 2024-10-28 | 2023-09-19 | Level 2 | GO 165 Inspection
124598282 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-02-02 | 2025-09-29 | Level 2 | Standards change
124598505 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-10-10 | 2027-09-20 | Level 3 | GO 165 Inspection
124598540 | insulator and brushing | Non-HFTD | Transmission | 2022-09-19 | 2023-09-19 | Level 2 | E | 2023-01-17 | 2025-09-19 | Level 2 | Standards change
124598620 | insulator and brushing | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2023-02-27 | 2027-09-30 | Level 3 | Standards change
124598743 | other | Non-HFTD | Transmission | 2022-09-16 | 2024-09-16 | Level 3 | F | 2024-04-06 | 2027-09-16 | Level 3 | Standards change
124598770 | pole | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2023-01-20 | 2025-09-30 | Level 2 | Standards change
124598796 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2023-12-29 | 2027-09-23 | Level 3 | Standards change
124598876 | insulator and brushing | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-09-28 | 2025-09-29 | Level 2 | GO 165 Inspection
124598982 | insulator and brushing | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-09-28 | 2025-09-29 | Level 2 | GO 165 Inspection
124599608 | pole | Non-HFTD | Transmission | 2022-09-21 | 2024-09-21 | Level 3 | F | 2024-01-10 | 2027-09-21 | Level 3 | Standards change
124599773 | other | Non-HFTD | Transmission | 2022-09-16 | 2023-09-16 | Level 2 | E | 2023-02-13 | 2025-09-16 | Level 2 | Standards change
124599834 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-10-28 | 2027-09-20 | Level 3 | GO 165 Inspection
124599871 | pole | Non-HFTD | Transmission | 2022-09-19 | 2024-09-19 | Level 3 | F | 2024-11-26 | 2027-09-19 | Level 3 | GO 165 Inspection
124600298 | pole | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2023-08-05 | 2027-09-20 | Level 3 | Standards change
124600731 | pole | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2023-01-26 | 2025-09-30 | Level 2 | Standards change
124600761 | anchor/guy | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-07-12 | 2025-09-30 | Level 2 | GO 165 Inspection
124601442 | insulator and brushing | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-10-24 | 2025-09-30 | Level 2 | GO 165 Inspection
124601501 | other | Non-HFTD | Transmission | 2022-09-29 | 2025-09-29 | Level 2 | E | 2024-10-25 | 2023-09-29 | Level 2 | GO 165 Inspection
124601781 | insulator and brushing | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-08-20 | 2025-09-27 | Level 2 | GO 165 Inspection
124601881 | other | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-08-20 | 2023-09-27 | Level 2 | GO 165 Inspection
124601984 | other | Non-HFTD | Transmission | 2022-09-29 | 2025-09-29 | Level 2 | E | 2024-10-09 | 2023-09-29 | Level 2 | GO 165 Inspection
124603210 | other | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-09-24 | 2023-09-30 | Level 2 | GO 165 Inspection
124609633 | pole | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-08-28 | 2025-09-27 | Level 2 | GO 165 Inspection
124610702 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-08-23 | 2025-09-21 | Level 2 | GO 165 Inspection
124610758 | other | Non-HFTD | Transmission | 2022-09-19 | 2024-09-19 | Level 3 | F | 2024-01-04 | 2027-09-19 | Level 3 | Standards change
124612695 | pole | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2023-02-06 | 2025-09-30 | Level 2 | Standards change
124613111 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-08-14 | 2027-09-29 | Level 3 | GO 165 Inspection
124613706 | switch | Non-HFTD | Transmission | 2022-09-30 | 2025-09-30 | Level 2 | E | 2024-10-07 | 2023-09-30 | Level 2 | GO 165 Inspection
124614645 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-09-27 | 2027-09-20 | Level 3 | GO 165 Inspection
124614830 | other | Non-HFTD | Transmission | 2022-09-20 | 2024-09-20 | Level 3 | F | 2024-09-27 | 2027-09-20 | Level 3 | GO 165 Inspection
124614963 | other | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-01-30 | 2027-09-20 | Level 3 | Standards change
124615187 | insulator and brushing | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-09-25 | 2025-09-20 | Level 2 | GO 165 Inspection
124615281 | pole | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-02-28 | 2025-09-23 | Level 2 | Standards change
124615355 | other | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-10-28 | 2027-09-23 | Level 3 | GO 165 Inspection
124615374 | anchor/guy | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-01-03 | 2027-09-20 | Level 3 | Standards change
124615461 | pole | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-01-12 | 2025-09-21 | Level 2 | Standards change
124615735 | insulator and brushing | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-01-10 | 2025-09-22 | Level 2 | Standards change
124615780 | other | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2023-11-06 | 2027-09-22 | Level 3 | Standards change
124615782 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-09-27 | 2027-09-20 | Level 3 | GO 165 Inspection
124615830 | pole | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-10-11 | 2025-09-21 | Level 2 | GO 165 Inspection
124615890 | other | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2024-10-10 | 2027-09-20 | Level 3 | GO 165 Inspection
124615980 | other | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2024-04-06 | 2027-09-22 | Level 3 | Standards change
124617145 | other | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-10-09 | 2025-09-30 | Level 2 | GO 165 Inspection
124617362 | pole | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2023-01-12 | 2025-09-30 | Level 2 | Standards change
124617550 | other | Non-HFTD | Transmission | 2022-09-29 | 2025-09-29 | Level 2 | E | 2024-11-18 | 2023-09-29 | Level 2 | GO 165 Inspection
124618001 | other | Non-HFTD | Transmission | 2022-10-04 | 2024-10-04 | Level 3 | F | 2024-01-04 | 2027-10-04 | Level 3 | Standards change
124618130 | other | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-08-22 | 2023-09-30 | Level 2 | GO 165 Inspection
124619003 | anchor/guy | Non-HFTD | Transmission | 2022-10-04 | 2024-10-04 | Level 3 | F | 2023-11-20 | 2027-10-04 | Level 3 | Standards change
124619740 | pole | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2023-03-02 | 2025-10-04 | Level 2 | Standards change
124621432 | anchor/guy | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2023-02-15 | 2025-10-04 | Level 2 | Standards change
124621969 | other | Non-HFTD | Transmission | 2022-09-30 | 2024-09-30 | Level 3 | F | 2024-09-05 | 2027-09-30 | Level 3 | GO 165 Inspection
124622005 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-02-01 | 2025-09-21 | Level 2 | Standards change
124622114 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2023-12-29 | 2027-09-23 | Level 3 | Standards change
124622476 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-01-30 | 2025-09-21 | Level 2 | Standards change
124622633 | other | Non-HFTD | Transmission | 2022-09-26 | 2024-09-26 | Level 3 | F | 2024-04-06 | 2027-09-26 | Level 3 | Standards change
124622777 | insulator and brushing | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-10-23 | 2025-09-23 | Level 2 | GO 165 Inspection
124622874 | other | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2024-01-10 | 2027-09-22 | Level 3 | Standards change
124622876 | insulator and brushing | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-08-01 | 2025-09-22 | Level 2 | Field Safety Reassessment
124622879 | insulator and brushing | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-08-01 | 2025-09-22 | Level 2 | Field Safety Reassessment
124622971 | insulator and brushing | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-01-11 | 2025-09-23 | Level 2 | Standards change
124623102 | pole | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-01-12 | 2025-09-21 | Level 2 | Standards change
124623151 | other | Non-HFTD | Transmission | 2022-09-21 | 2024-09-21 | Level 3 | F | 2024-04-06 | 2027-09-21 | Level 3 | Standards change
124623164 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2025-09-21 | Level 2 | E | 2024-08-23 | 2025-09-21 | Level 2 | GO 165 Inspection
124623241 | pole | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-08-23 | 2025-09-21 | Level 2 | GO 165 Inspection
124623305 | anchor/guy | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-02-16 | 2027-09-21 | Level 3 | Standards change
124623320 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2023-12-29 | 2027-09-23 | Level 3 | Standards change
124623355 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2023-01-10 | 2027-09-23 | Level 3 | Standards change
124623362 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2024-09-12 | 2025-09-22 | Level 2 | GO 165 Inspection
124623363 | other | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-02-14 | 2025-09-26 | Level 2 | Standards change
124623449 | other | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2024-01-10 | 2027-09-22 | Level 3 | Standards change
124623487 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-09-03 | 2023-09-21 | Level 2 | Field Safety Reassessment
124623566 | other | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-02-17 | 2025-09-26 | Level 2 | Standards change
124623636 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-01-10 | 2025-09-22 | Level 2 | Standards change
124623639 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2024-01-03 | 2027-09-23 | Level 3 | Standards change
124623715 | other | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2023-01-25 | 2027-09-21 | Level 3 | Standards change
124624414 | pole | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2023-01-10 | 2025-10-04 | Level 2 | Standards change
124624660 | insulator and brushing | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2024-08-30 | 2025-10-04 | Level 2 | GO 165 Inspection
124625039 | insulator and brushing | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-06-18 | 2025-09-21 | Level 2 | GO 165 Inspection
124625767 | other | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-01-19 | 2027-09-26 | Level 3 | Standards change
124627799 | other | Non-HFTD | Transmission | 2022-09-21 | 2023-09-21 | Level 2 | E | 2024-10-16 | 2025-09-21 | Level 2 | GO 165 Inspection
124627836 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2023-02-28 | 2025-10-05 | Level 2 | Standards change
124629531 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2024-01-10 | 2027-09-23 | Level 3 | Standards change
124631843 | switch | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2024-01-10 | 2025-10-06 | Level 2 | Standards change
124631914 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-10-09 | 2025-10-05 | Level 2 | GO 165 Inspection
124631972 | insulator and brushing | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-10-09 | 2025-10-05 | Level 2 | GO 165 Inspection
124632017 | other | Non-HFTD | Transmission | 2022-10-06 | 2024-10-06 | Level 3 | F | 2023-12-14 | 2027-10-06 | Level 3 | Standards change
124632107 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-11-04 | 2027-10-05 | Level 3 | GO 165 Inspection
124632250 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-10-29 | 2025-10-05 | Level 2 | GO 165 Inspection
124633036 | pole | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-03-14 | 2025-09-27 | Level 2 | GO 165 Inspection
124635314 | anchor/guy | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2023-06-10 | 2025-09-27 | Level 2 | Standards change
124635794 | pole | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2023-02-28 | 2025-10-06 | Level 2 | Standards change
124635822 | switch | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-01-10 | 2025-10-05 | Level 2 | Standards change
124636209 | other | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2024-07-29 | 2025-10-06 | Level 2 | GO 165 Inspection
124636953 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-10-16 | 2027-10-05 | Level 3 | GO 165 Inspection
124638224 | other | Non-HFTD | Transmission | 2022-09-23 | 2024-09-23 | Level 3 | F | 2024-01-02 | 2027-09-23 | Level 3 | Standards change
124638270 | other | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-10-23 | 2023-09-23 | Level 2 | GO 165 Inspection
124638275 | other | Non-HFTD | Transmission | 2022-09-29 | 2024-09-29 | Level 3 | F | 2024-04-06 | 2027-09-29 | Level 3 | Standards change
124638282 | other | Non-HFTD | Transmission | 2022-09-29 | 2024-09-29 | Level 3 | F |  | 2024-09-29 | Level 3
124638329 | other | Non-HFTD | Transmission | 2022-09-27 | 2024-09-27 | Level 3 | F | 2024-01-09 | 2027-09-27 | Level 3 | Standards change
124638368 | anchor/guy | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-07-24 | 2025-09-23 | Level 2 | Standards change
124638371 | pole | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-01-20 | 2025-09-26 | Level 2 | Standards change
124638443 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-01-24 | 2025-09-29 | Level 2 | Standards change
124638479 | other | Non-HFTD | Transmission | 2022-09-28 | 2024-09-28 | Level 3 | F | 2023-12-14 | 2027-09-28 | Level 3 | Standards change
124638534 | other | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-10-23 | 2025-09-23 | Level 2 | GO 165 Inspection
124638615 | pole | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-07-28 | 2025-09-26 | Level 2 | Standards change
124638664 | other | Non-HFTD | Transmission | 2022-09-26 | 2024-09-26 | Level 3 | F | 2023-12-28 | 2027-09-26 | Level 3 | Standards change
124641792 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2023-02-09 | 2025-09-28 | Level 2 | Standards change
124641820 | other | Non-HFTD | Transmission | 2022-09-28 | 2024-09-28 | Level 3 | F | 2023-02-09 | 2027-09-28 | Level 3 | Standards change
124642023 | other | Non-HFTD | Transmission | 2022-10-06 | 2024-10-06 | Level 3 | F | 2024-07-25 | 2027-10-06 | Level 3 | GO 165 Inspection
124653886 | other | Non-HFTD | Transmission | 2022-10-07 | 2023-10-07 | Level 2 | E | 2023-01-10 | 2027-10-07 | Level 3 | Standards change
124654551 | pole | Non-HFTD | Transmission | 2022-10-07 | 2023-10-07 | Level 2 | E | 2023-01-17 | 2025-10-07 | Level 2 | Standards change
124655084 | anchor/guy | Non-HFTD | Transmission | 2022-10-07 | 2023-10-07 | Level 2 | E | 2023-02-01 | 2027-10-07 | Level 3 | Standards change
124655235 | other | Non-HFTD | Transmission | 2022-10-07 | 2024-10-07 | Level 3 | F | 2024-04-06 | 2027-10-07 | Level 3 | Standards change
124655316 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2023-12-14 | 2027-10-05 | Level 3 | Standards change
124655448 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2024-09-27 | 2025-09-28 | Level 2 | GO 165 Inspection
124656539 | other | Non-HFTD | Transmission | 2022-10-04 | 2024-10-04 | Level 3 | F | 2024-01-04 | 2027-10-04 | Level 3 | Standards change
124656937 | anchor/guy | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2023-01-25 | 2025-09-27 | Level 2 | Standards change
124657054 | other | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2024-01-02 | 2027-09-22 | Level 3 | Standards change
124657116 | pole | Non-HFTD | Transmission | 2022-09-22 | 2023-09-22 | Level 2 | E | 2023-01-12 | 2025-09-22 | Level 2 | Standards change
124657263 | pole | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2024-08-16 | 2027-09-22 | Level 3 | GO 165 Inspection
124657582 | other | Non-HFTD | Transmission | 2022-09-22 | 2024-09-22 | Level 3 | F | 2024-08-23 | 2027-09-22 | Level 3 | GO 165 Inspection
124657869 | other | Non-HFTD | Transmission | 2022-10-08 | 2023-10-08 | Level 2 | E | 2023-01-10 | 2027-10-08 | Level 3 | Standards change
124658217 | other | Non-HFTD | Transmission | 2022-09-26 | 2024-09-26 | Level 3 | F | 2024-04-06 | 2027-09-26 | Level 3 | Standards change
124658467 | pole | Non-HFTD | Transmission | 2022-10-08 | 2023-10-08 | Level 2 | E | 2023-02-28 | 2025-10-08 | Level 2 | Standards change
124669113 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-11-04 | 2027-10-05 | Level 3 | GO 165 Inspection
124677014 | other | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-10-29 | 2023-01-05 | Level 2 | GO 165 Inspection
124677035 | pole | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-28 | 2025-10-10 | Level 2 | Standards change
124677649 | splice | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2023-02-13 | 2025-10-06 | Level 2 | Standards change
124678219 | pole | Non-HFTD | Transmission | 2022-09-12 | 2024-09-12 | Level 3 | F | 2024-11-13 | 2027-09-12 | Level 3 | GO 165 Inspection
124679247 | anchor/guy | Non-HFTD | Transmission | 2022-09-27 | 2023-09-27 | Level 2 | E | 2024-04-04 | 2025-09-27 | Level 2 | GO 165 Inspection
124680550 | other | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-28 | 2025-10-10 | Level 2 | Standards change
124680885 | insulator and brushing | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-28 | 2025-10-10 | Level 2 | Standards change
124681235 | other | HFTD Tier 2 | Transmission | 2022-10-03 | 2024-10-03 | Level 3 | F | 2023-03-14 | 2027-10-03 | Level 3 | Standards change
124683588 | other | Non-HFTD | Transmission | 2022-09-26 | 2024-09-26 | Level 3 | F | 2024-09-23 | 2027-09-26 | Level 3 | GO 165 Inspection
124686754 | other | Non-HFTD | Transmission | 2022-09-26 | 2024-09-26 | Level 3 | F | 2023-02-13 | 2027-09-26 | Level 3 | Standards change
124687918 | pole | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-14 | 2025-10-10 | Level 2 | Standards change
124690624 | pole | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2024-09-25 | 2027-09-23 | Level 3 | GO 165 Inspection
124691980 | pole | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2023-01-30 | 2025-10-11 | Level 2 | Standards change
124692141 | pole | Non-HFTD | Transmission | 2022-09-26 | 2024-09-26 | Level 3 | F | 2024-01-11 | 2027-09-26 | Level 3 | Standards change
124692153 | other | Non-HFTD | Transmission | 2022-10-04 | 2024-10-04 | Level 3 | F | 2024-10-16 | 2027-10-04 | Level 3 | GO 165 Inspection
124692280 | other | Non-HFTD | Transmission | 2022-10-03 | 2023-10-03 | Level 2 | E | 2024-11-19 | 2025-10-03 | Level 2 | GO 165 Inspection
124692459 | other | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-03-14 | 2025-07-18 | Level 2 | Standards change
124692561 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2024-10-01 | 2027-07-14 | Level 3 | GO 165 Inspection
124692566 | pole | Non-HFTD | Transmission | 2022-07-17 | 2023-07-17 | Level 2 | E | 2024-01-11 | 2025-07-17 | Level 2 | Standards change
124692608 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2024-09-05 | 2025-09-28 | Level 2 | GO 165 Inspection
124692730 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2023-03-08 | 2025-09-28 | Level 2 | Standards change
124692799 | other | Non-HFTD | Transmission | 2022-10-03 | 2024-10-03 | Level 3 | F | 2024-04-06 | 2027-10-03 | Level 3 | Standards change
124692801 | other | Non-HFTD | Transmission | 2022-10-04 | 2024-10-04 | Level 3 | F | 2024-09-23 | 2027-10-04 | Level 3 | GO 165 Inspection
124692905 | other | Non-HFTD | Transmission | 2022-09-29 | 2027-09-29 | Level 3 | F |  | 2027-09-29 | Level 3
124693021 | pole | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2024-01-11 | 2025-10-06 | Level 2 | Standards change
124693023 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-02-27 | 2025-09-29 | Level 2 | Standards change
124695091 | pole | Non-HFTD | Transmission | 2022-10-07 | 2024-10-07 | Level 3 | F | 2024-03-28 | 2027-10-07 | Level 3 | GO 165 Inspection
124695833 | anchor/guy | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2024-04-05 | 2027-10-12 | Level 3 | GO 165 Inspection
124696471 | insulator and brushing | Non-HFTD | Transmission | 2022-10-03 | 2025-10-03 | Level 2 | E | 2024-10-23 | 2023-10-03 | Level 2 | GO 165 Inspection
124696927 | pole | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-01-30 | 2025-10-12 | Level 2 | Standards change
124698126 | insulator and brushing | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-10-01 | 2025-10-11 | Level 2 | GO 165 Inspection
124699526 | insulator and brushing | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-01-06 | 2025-10-12 | Level 2 | Standards change
124699838 | conductor | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2024-09-04 | 2025-10-12 | Level 2 | GO 165 Inspection
124703012 | insulator and brushing | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-07-25 | 2025-10-10 | Level 2 | GO 165 Inspection
124703543 | insulator and brushing | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2024-11-19 | 2023-10-12 | Level 2 | Field Safety Reassessment
124704204 | anchor/guy | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-05-18 | 2025-10-12 | Level 2 | Standards change
124704570 | other | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-03-20 | 2025-10-13 | Level 2 | Standards change
124705026 | pole | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2022-12-09 | 2025-10-13 | Level 2 | Standards change
124705255 | anchor/guy | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-03-08 | 2025-10-13 | Level 2 | Standards change
124706041 | other | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2023-02-01 | 2025-09-28 | Level 2 | Standards change
124706788 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-03-20 | 2025-10-13 | Level 2 | Standards change
124706951 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2024-11-20 | 2025-10-13 | Level 2 | GO 165 Inspection
124706969 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-03-09 | 2025-10-13 | Level 2 | Standards change
124706996 | pole | Non-HFTD | Transmission | 2022-10-12 | 2024-10-12 | Level 3 | F | 2024-08-20 | 2027-10-12 | Level 3 | GO 165 Inspection
124707143 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-03-09 | 2025-10-13 | Level 2 | Standards change
124707435 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-01-12 | 2027-10-05 | Level 3 | Standards change
124707875 | insulator and brushing | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-10-07 | 2025-10-11 | Level 2 | GO 165 Inspection
124707956 | other | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2023-02-03 | 2027-10-11 | Level 3 | Standards change
124708163 | pole | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2023-11-30 | 2027-10-05 | Level 3 | Standards change
124708193 | other | Non-HFTD | Transmission | 2022-10-06 | 2024-10-06 | Level 3 | F | 2024-04-06 | 2027-10-06 | Level 3 | Standards change
124710788 | other | Non-HFTD | Transmission | 2022-10-10 | 2024-10-10 | Level 3 | F | 2023-02-13 | 2027-10-10 | Level 3 | Standards change
124711063 | insulator and brushing | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-02-09 | 2025-10-12 | Level 2 | Standards change
124711198 | other | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-02-16 | 2025-10-13 | Level 2 | Standards change
124711292 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-01-06 | 2027-09-29 | Level 3 | Standards change
124712793 | other | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2023-02-14 | 2025-09-26 | Level 2 | Standards change
124713072 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-11-26 | 2027-10-05 | Level 3 | GO 165 Inspection
124713459 | other | Non-HFTD | Transmission | 2022-09-30 | 2024-09-30 | Level 3 | F | 2024-11-19 | 2027-09-30 | Level 3 | GO 165 Inspection
124713662 | other | Non-HFTD | Transmission | 2022-09-30 | 2025-09-30 | Level 2 | E | 2024-11-18 | 2023-09-30 | Level 2 | GO 165 Inspection
124713887 | other | Non-HFTD | Transmission | 2022-09-29 | 2024-09-29 | Level 3 | F | 2024-04-06 | 2027-09-29 | Level 3 | Standards change
124713898 | other | Non-HFTD | Transmission | 2022-10-14 | 2024-10-14 | Level 3 | F | 2024-07-12 | 2027-10-14 | Level 3 | GO 165 Inspection
124713987 | other | Non-HFTD | Transmission | 2022-09-30 | 2024-09-30 | Level 3 | F | 2023-02-06 | 2027-09-30 | Level 3 | Standards change
124714544 | other | Non-HFTD | Transmission | 2022-09-30 | 2024-09-30 | Level 3 | F | 2023-12-29 | 2027-09-30 | Level 3 | Standards change
124716195 | anchor/guy | Non-HFTD | Transmission | 2022-10-06 | 2023-04-06 | Level 2 | E | 2024-07-12 | 2023-04-06 | Level 2 | GO 165 Inspection
124716408 | pole | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2023-02-27 | 2025-10-06 | Level 2 | Standards change
124719159 | pole | Non-HFTD | Transmission | 2022-10-15 | 2023-10-15 | Level 2 | E | 2023-01-10 | 2025-10-15 | Level 2 | Standards change
124719207 | insulator and brushing | Non-HFTD | Transmission | 2022-10-15 | 2023-10-15 | Level 2 | E | 2024-09-30 | 2025-10-15 | Level 2 | GO 165 Inspection
124719263 | insulator and brushing | Non-HFTD | Transmission | 2022-10-15 | 2023-10-15 | Level 2 | E | 2023-01-10 | 2025-10-15 | Level 2 | Standards change
124719264 | insulator and brushing | Non-HFTD | Transmission | 2022-10-15 | 2023-10-15 | Level 2 | E | 2023-01-10 | 2025-10-15 | Level 2 | Standards change
124720107 | insulator and brushing | Non-HFTD | Transmission | 2022-10-15 | 2023-10-15 | Level 2 | E | 2023-01-10 | 2025-10-15 | Level 2 | Standards change
124723310 | other | Non-HFTD | Transmission | 2022-10-17 | 2027-10-17 | Level 3 | F |  | 2027-10-17 | Level 3
124723510 | pole | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-11-08 | 2025-10-17 | Level 2 | GO 165 Inspection
124723693 | insulator and brushing | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2023-02-21 | 2025-10-14 | Level 2 | Standards change
124724571 | pole | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-11-06 | 2025-10-17 | Level 2 | GO 165 Inspection
124724715 | insulator and brushing | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2023-02-21 | 2025-10-14 | Level 2 | Standards change
124724843 | other | Non-HFTD | Transmission | 2022-10-10 | 2024-10-10 | Level 3 | F | 2024-04-06 | 2027-10-10 | Level 3 | Standards change
124724880 | insulator and brushing | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2023-02-21 | 2025-10-14 | Level 2 | Standards change
124724985 | other | Non-HFTD | Transmission | 2022-10-17 | 2024-10-17 | Level 3 | F | 2023-12-29 | 2027-10-17 | Level 3 | Standards change
124725275 | insulator and brushing | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-12-12 | 2025-09-29 | Level 2 | Standards change
124727054 | other | Non-HFTD | Transmission | 2022-10-14 | 2024-10-14 | Level 3 | F | 2024-01-05 | 2027-10-14 | Level 3 | Standards change
124727494 | other | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-01-10 | 2025-10-17 | Level 2 | Standards change
124727580 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-11-20 | 2025-09-29 | Level 2 | GO 165 Inspection
124727589 | other | Non-HFTD | Transmission | 2022-09-30 | 2025-09-30 | Level 2 | E | 2024-10-22 | 2023-09-30 | Level 2 | GO 165 Inspection
124728031 | pole | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2024-01-11 | 2025-10-17 | Level 2 | Standards change
124728548 | insulator and brushing | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-09-28 | 2025-09-29 | Level 2 | GO 165 Inspection
124729195 | other | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2023-02-06 | 2025-09-30 | Level 2 | Standards change
124729209 | insulator and brushing | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-11-18 | 2025-09-29 | Level 2 | GO 165 Inspection
124729600 | other | Non-HFTD | Transmission | 2022-10-03 | 2024-10-03 | Level 3 | F | 2023-12-07 | 2027-10-03 | Level 3 | Standards change
124729801 | insulator and brushing | Non-HFTD | Transmission | 2022-10-07 | 2023-10-07 | Level 2 | E | 2024-08-16 | 2025-10-07 | Level 2 | GO 165 Inspection
124729829 | pole | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2024-05-29 | 2025-10-06 | Level 2 | GO 165 Inspection
124729843 | pole | Non-HFTD | Transmission | 2022-10-03 | 2024-10-03 | Level 3 | F | 2024-01-11 | 2027-10-03 | Level 3 | Standards change
124729910 | insulator and brushing | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-10-25 | 2025-09-30 | Level 2 | GO 165 Inspection
124731557 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-03-29 | 2025-10-18 | Level 2 | Standards change
124731885 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-04-17 | 2025-10-18 | Level 2 | GO 165 Inspection
124732077 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-02-17 | 2025-10-13 | Level 2 | Standards change
124732560 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-10 | 2025-10-18 | Level 2 | Standards change
124733688 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-09-09 | 2025-10-18 | Level 2 | GO 165 Inspection
124733773 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-02-28 | 2025-10-18 | Level 2 | Standards change
124733978 | pole | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-01-05 | 2027-10-18 | Level 3 | Standards change
124734119 | other | Non-HFTD | Transmission | 2022-10-07 | 2024-10-07 | Level 3 | F | 2023-12-08 | 2027-10-07 | Level 3 | Standards change
124734310 | pole | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-01-05 | 2027-10-18 | Level 3 | Standards change
124734521 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-01-11 | 2025-10-18 | Level 2 | Standards change
124734552 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-11-19 | 2025-09-29 | Level 2 | GO 165 Inspection
124735568 | pole | Non-HFTD | Transmission | 2022-10-03 | 2024-10-03 | Level 3 | F | 2024-01-11 | 2027-10-03 | Level 3 | Standards change
124735918 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-10-30 | 2025-10-18 | Level 2 | GO 165 Inspection
124736046 | anchor/guy | Non-HFTD | Transmission | 2022-10-18 | 2025-10-18 | Level 2 | E | 2024-10-30 | 2023-10-18 | Level 2 | GO 165 Inspection
124736047 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-03-13 | 2025-10-18 | Level 2 | Standards change
124736049 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-03-13 | 2025-10-18 | Level 2 | Standards change
124736622 | other | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-03-08 | 2027-10-17 | Level 3 | Standards change
124737270 | conductor | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-05-01 | 2025-10-18 | Level 2 | GO 165 Inspection
124738361 | pole | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-01-05 | 2027-10-18 | Level 3 | Standards change
124738547 | other | Non-HFTD | Transmission | 2022-10-14 | 2024-10-14 | Level 3 | F | 2024-09-13 | 2027-10-14 | Level 3 | GO 165 Inspection
124739028 | pole | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2024-09-28 | 2025-10-19 | Level 2 | GO 165 Inspection
124739280 | pole | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2023-02-28 | 2025-10-19 | Level 2 | Standards change
124739908 | insulator and brushing | Non-HFTD | Transmission | 2022-10-19 | 2025-10-19 | Level 2 | E | 2024-07-12 | 2023-10-19 | Level 2 | GO 165 Inspection
124740151 | insulator and brushing | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2024-10-21 | 2025-10-17 | Level 2 | GO 165 Inspection
124740164 | insulator and brushing | Non-HFTD | Transmission | 2022-10-19 | 2025-10-19 | Level 2 | E | 2024-04-24 | 2023-01-19 | Level 2 | GO 165 Inspection
124741032 | insulator and brushing | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-07-25 | 2025-10-10 | Level 2 | GO 165 Inspection
124741417 | conductor | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2024-08-09 | 2025-10-19 | Level 2 | GO 165 Inspection
124742470 | insulator and brushing | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-12-05 | 2025-10-10 | Level 2 | Standards change
124743429 | other | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2023-02-17 | 2025-10-19 | Level 2 | Standards change
124743552 | pole | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2023-03-06 | 2025-10-19 | Level 2 | Standards change
124745664 | pole | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2024-09-05 | 2025-10-14 | Level 2 | GO 165 Inspection
124745722 | other | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2024-09-05 | 2027-10-14 | Level 3 | GO 165 Inspection
124746318 | other | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-07-25 | 2023-10-10 | Level 2 | GO 165 Inspection
124747027 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-10-22 | 2025-10-18 | Level 2 | GO 165 Inspection
124747100 | pole | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2023-12-12 | 2025-10-20 | Level 2 | Standards change
124747404 | pole | Non-HFTD | Transmission | 2022-10-03 | 2025-10-03 | Level 2 | E |  | 2025-10-03 | Level 2
124747460 | other | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2023-03-15 | 2027-10-20 | Level 3 | Standards change
124747593 | insulator and brushing | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-14 | 2025-10-10 | Level 2 | Standards change
124747786 | other | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-11-20 | 2025-10-18 | Level 2 | GO 165 Inspection
124748214 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-01-18 | Level 2 | B | 2024-11-14 | 2025-10-18 | Level 2 | GO 165 Inspection
124748259 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-12-13 | 2023-10-05 | Level 2 | Field Safety Reassessment
124748393 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-02-23 | 2027-10-05 | Level 3 | Standards change
124748786 | anchor/guy | Non-HFTD | Transmission | 2022-10-20 | 2025-10-20 | Level 2 | E | 2024-10-29 | 2023-10-20 | Level 2 | GO 165 Inspection
124749051 | other | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-11-20 | 2025-10-18 | Level 2 | GO 165 Inspection
124751094 | pole | Non-HFTD | Transmission | 2022-09-28 | 2025-09-28 | Level 2 | E | 2024-10-21 | 2023-09-28 | Level 2 | GO 165 Inspection
124752161 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-10-29 | 2027-10-05 | Level 3 | GO 165 Inspection
124752264 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-04-06 | 2027-10-05 | Level 3 | Standards change
124753135 | other | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-11-08 | 2025-10-10 | Level 2 | GO 165 Inspection
124753164 | other | Non-HFTD | Transmission | 2022-10-12 | 2024-10-12 | Level 3 | F | 2024-08-31 | 2027-10-12 | Level 3 | GO 165 Inspection
124753167 | other | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-08-30 | 2025-10-10 | Level 2 | GO 165 Inspection
124754642 | other | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2023-02-02 | 2025-10-04 | Level 2 | Standards change
124754694 | pole | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-01-11 | 2027-10-05 | Level 3 | Standards change
124754707 | pole | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-12-06 | 2025-10-10 | Level 2 | Standards change
124754730 | pole | Non-HFTD | Transmission | 2022-10-03 | 2023-10-03 | Level 2 | E | 2023-01-18 | 2025-10-03 | Level 2 | Standards change
124755108 | insulator and brushing | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2024-08-13 | 2025-10-04 | Level 2 | GO 165 Inspection
124755476 | insulator and brushing | Non-HFTD | Transmission | 2022-10-19 | 2027-10-19 | Level 2 | E | 2024-12-10 | 2023-10-19 | Level 2 | GO 165 Inspection
124755538 | other | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2023-03-01 | 2027-10-06 | Level 3 | Standards change
124755620 | other | Non-HFTD | Transmission | 2022-10-04 | 2023-10-04 | Level 2 | E | 2024-05-02 | 2027-10-04 | Level 3 | GO 165 Inspection
124756356 | anchor/guy | Non-HFTD | Transmission | 2022-10-07 | 2023-10-07 | Level 2 | E | 2023-01-06 | 2025-10-07 | Level 2 | Standards change
124756438 | other | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-01-12 | 2025-10-12 | Level 2 | Standards change
124756480 | switch | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-03-01 | 2025-10-12 | Level 2 | Standards change
124756560 | pole | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2023-08-12 | 2025-10-06 | Level 2 | Field Safety Reassessment
124756564 | crossarm | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2024-02-21 | 2025-10-06 | Level 2 | GO 165 Inspection
124756575 | pole | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2024-07-23 | 2025-10-12 | Level 2 | GO 165 Inspection
124756625 | other | Non-HFTD | Transmission | 2022-10-04 | 2024-10-04 | Level 3 | F | 2024-09-27 | 2027-10-04 | Level 3 | GO 165 Inspection
124756671 | other | Non-HFTD | Transmission | 2022-10-17 | 2024-10-17 | Level 3 | F | 2024-10-23 | 2027-10-17 | Level 3 | GO 165 Inspection
124757330 | anchor/guy | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-10-04 | 2025-10-05 | Level 2 | GO 165 Inspection
124757332 | anchor/guy | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2023-01-11 | 2025-10-05 | Level 2 | Standards change
124757336 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-10-04 | 2025-10-05 | Level 2 | GO 165 Inspection
124757369 | insulator and brushing | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2024-10-08 | 2025-10-17 | Level 2 | GO 165 Inspection
124757765 | crossarm | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2023-04-18 | 2027-10-11 | Level 3 | Standards change
124758331 | other | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-09-17 | 2027-10-21 | Level 3 | GO 165 Inspection
124758364 | other | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2023-03-07 | 2025-10-21 | Level 2 | Standards change
124759930 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2024-07-29 | 2027-10-13 | Level 3 | GO 165 Inspection
124761354 | insulator and brushing | Non-HFTD | Transmission | 2022-10-22 | 2023-10-22 | Level 2 | E | 2024-09-17 | 2025-10-22 | Level 2 | GO 165 Inspection
124761734 | anchor/guy | Non-HFTD | Transmission | 2022-10-22 | 2023-10-22 | Level 2 | E | 2024-08-15 | 2025-10-22 | Level 2 | GO 165 Inspection
124764384 | pole | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2023-02-23 | 2025-10-20 | Level 2 | Standards change
124765509 | switch | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2023-03-13 | 2025-10-24 | Level 2 | Standards change
124766086 | other | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-10-10 | 2027-10-21 | Level 3 | GO 165 Inspection
124766691 | conductor | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2024-10-11 | 2025-10-20 | Level 2 | GO 165 Inspection
124766923 | pole | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-10-15 | 2025-10-21 | Level 2 | GO 165 Inspection
124767702 | other | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-07-23 | 2027-10-18 | Level 3 | GO 165 Inspection
124768316 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124768319 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124770561 | insulator and brushing | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2023-01-20 | 2025-10-24 | Level 2 | Standards change
124771254 | pole | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-01-11 | 2025-10-13 | Level 2 | Standards change
124771598 | pole | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-01-11 | 2025-10-13 | Level 2 | Standards change
124773613 | pole | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-10-15 | 2027-10-24 | Level 3 | GO 165 Inspection
124774104 | other | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-10-15 | 2027-10-24 | Level 3 | GO 165 Inspection
124774729 | splice | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-03-17 | 2025-08-11 | Level 2 | Standards change
124774741 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-19 | 2025-10-18 | Level 2 | GO 165 Inspection
124775127 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124775372 | pole | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2024-01-11 | 2025-10-25 | Level 2 | Standards change
124775418 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124775649 | pole | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2023-12-06 | 2027-10-19 | Level 3 | Standards change
124777220 | other | Non-HFTD | Transmission | 2022-10-14 | 2024-10-14 | Level 3 | F | 2024-10-02 | 2027-10-14 | Level 3 | GO 165 Inspection
124777257 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124777975 | other | Non-HFTD | Transmission | 2022-10-25 | 2024-10-25 | Level 3 | F | 2024-09-24 | 2027-10-25 | Level 3 | GO 165 Inspection
124778526 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-02-01 | 2025-09-29 | Level 2 | Standards change
124778578 | pole | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2023-03-09 | 2025-10-26 | Level 2 | Standards change
124778702 | other | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2024-10-23 | 2025-10-17 | Level 2 | GO 165 Inspection
124778833 | other | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2024-08-16 | 2027-10-19 | Level 3 | GO 165 Inspection
124779189 | pole | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2023-02-02 | 2025-10-26 | Level 2 | Standards change
124779954 | pole | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2023-03-08 | 2025-10-26 | Level 2 | Standards change
124779988 | other | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2024-01-20 | 2025-10-06 | Level 2 | GO 165 Inspection
124780076 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-01-24 | 2025-09-29 | Level 2 | Standards change
124780436 | pole | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2023-11-20 | 2025-10-26 | Level 2 | Standards change
124780972 | pole | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2023-12-15 | 2027-10-26 | Level 3 | Standards change
124782284 | insulator and brushing | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-11-19 | 2025-09-30 | Level 2 | GO 165 Inspection
124782545 | insulator and brushing | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2024-09-16 | 2025-10-26 | Level 2 | GO 165 Inspection
124784312 | other | Non-HFTD | Transmission | 2022-10-25 | 2024-10-25 | Level 3 | F | 2024-07-10 | 2027-10-25 | Level 3 | Standards change
124784624 | pole | Non-HFTD | Transmission | 2022-10-27 | 2024-10-27 | Level 3 | F | 2024-09-06 | 2027-10-27 | Level 3 | GO 165 Inspection
124785042 | pole | Non-HFTD | Transmission | 2022-10-27 | 2023-10-27 | Level 2 | E | 2024-07-12 | 2023-10-27 | Level 2 | GO 165 Inspection
124785722 | other | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2024-09-27 | 2027-10-19 | Level 3 | GO 165 Inspection
124786927 | insulator and brushing | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2023-01-30 | 2025-10-11 | Level 2 | Standards change
124787678 | insulator and brushing | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2024-12-03 | 2025-10-20 | Level 2 | GO 165 Inspection
124788230 | insulator and brushing | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-12-12 | 2027-10-17 | Level 3 | Standards change
124796959 | insulator and brushing | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2024-09-17 | 2025-10-25 | Level 2 | GO 165 Inspection
124798457 | insulator and brushing | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-07-26 | 2025-10-11 | Level 2 | GO 165 Inspection
124799516 | pole | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2023-02-17 | 2025-10-11 | Level 2 | Standards change
124801129 | anchor/guy | Non-HFTD | Transmission | 2022-10-28 | 2023-10-28 | Level 2 | E | 2024-12-30 | 2023-10-28 | Level 2 | Field Safety Reassessment
124802887 | pole | Non-HFTD | Transmission | 2022-10-29 | 2023-10-29 | Level 2 | E | 2023-03-08 | 2025-10-29 | Level 2 | Standards change
124804964 | pole | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2024-09-17 | 2025-10-25 | Level 2 | GO 165 Inspection
124805022 | insulator and brushing | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2024-09-17 | 2025-10-25 | Level 2 | GO 165 Inspection
124805068 | other | Non-HFTD | Transmission | 2022-10-28 | 2023-10-28 | Level 2 | E | 2023-01-18 | 2027-10-28 | Level 3 | Standards change
124805846 | anchor/guy | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-01-25 | 2027-10-13 | Level 3 | Standards change
124806068 | pole | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-01-10 | 2025-10-12 | Level 2 | Standards change
124806452 | other | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-03-01 | 2025-10-12 | Level 2 | Standards change
124806504 | other | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2023-11-20 | 2027-10-24 | Level 3 | Standards change
124808101 | insulator and brushing | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 2 | E | 2024-10-23 | 2025-09-30 | Level 2 | GO 165 Inspection
124808702 | pole | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2023-12-19 | 2025-10-24 | Level 2 | Standards change
124808939 | pole | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-08-24 | 2025-10-24 | Level 2 | GO 165 Inspection
124809091 | insulator and brushing | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-09-11 | 2025-10-24 | Level 2 | GO 165 Inspection
124809096 | insulator and brushing | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-09-11 | 2025-10-24 | Level 2 | GO 165 Inspection
124809158 | insulator and brushing | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2024-10-09 | 2025-10-14 | Level 2 | GO 165 Inspection
124809277 | other | Non-HFTD | Transmission | 2022-10-14 | 2024-10-14 | Level 3 | F | 2024-10-02 | 2027-10-14 | Level 3 | GO 165 Inspection
124810565 | other | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-10-24 | 2027-10-31 | Level 3 | GO 165 Inspection
124810652 | pole | Non-HFTD | Transmission | 2022-10-31 | 2023-10-31 | Level 2 | E | 2024-10-17 | 2025-10-31 | Level 2 | GO 165 Inspection
124810954 | insulator and brushing | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2024-11-18 | 2027-10-14 | Level 3 | GO 165 Inspection
124811181 | pole | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-10-15 | 2025-10-24 | Level 2 | GO 165 Inspection
124812576 | other | Non-HFTD | Transmission | 2022-10-17 | 2024-10-17 | Level 3 | F | 2024-11-13 | 2027-10-17 | Level 3 | GO 165 Inspection
124813538 | other | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-03-01 | 2025-10-17 | Level 2 | Standards change
124814472 | other | Non-HFTD | Transmission | 2022-10-31 | 2025-10-31 | Level 2 | B | 2024-10-25 | 2023-01-31 | Level 2 | GO 165 Inspection
124814534 | other | Non-HFTD | Transmission | 2022-10-31 | 2023-10-31 | Level 2 | E | 2024-10-23 | 2025-10-31 | Level 2 | GO 165 Inspection
124814782 | other | Non-HFTD | Transmission | 2022-11-01 | 2023-11-01 | Level 2 | E | 2024-10-28 | 2027-11-01 | Level 3 | GO 165 Inspection
124816659 | other | Non-HFTD | Transmission | 2022-10-28 | 2024-10-28 | Level 3 | F | 2024-09-13 | 2027-10-28 | Level 3 | GO 165 Inspection
124817420 | insulator and brushing | Non-HFTD | Transmission | 2022-11-01 | 2023-11-01 | Level 2 | E | 2023-03-07 | 2025-11-01 | Level 2 | Standards change
124818104 | other | Non-HFTD | Transmission | 2022-10-31 | 2023-10-31 | Level 2 | E | 2024-10-23 | 2025-10-31 | Level 2 | GO 165 Inspection
124818634 | insulator and brushing | Non-HFTD | Transmission | 2022-11-01 | 2023-11-01 | Level 2 | E | 2024-09-11 | 2025-11-01 | Level 2 | GO 165 Inspection
124820583 | insulator and brushing | Non-HFTD | Transmission | 2022-11-02 | 2023-11-02 | Level 2 | E | 2023-02-23 | 2025-11-02 | Level 2 | Standards change
124821031 | other | Non-HFTD | Transmission | 2022-11-02 | 2024-11-02 | Level 3 | F | 2024-07-10 | 2027-11-02 | Level 3 | GO 165 Inspection
124821154 | other | Non-HFTD | Transmission | 2022-11-02 | 2023-11-02 | Level 2 | E | 2024-10-16 | 2025-11-02 | Level 2 | GO 165 Inspection
124821606 | other | Non-HFTD | Transmission | 2022-10-03 | 2023-10-03 | Level 2 | E | 2024-07-26 | 2025-10-03 | Level 2 | GO 165 Inspection
124823068 | other | Non-HFTD | Transmission | 2022-11-02 | 2023-11-02 | Level 2 | E | 2023-01-19 | 2025-11-02 | Level 2 | Standards change
124823251 | pole | Non-HFTD | Transmission | 2022-11-02 | 2023-11-02 | Level 2 | E | 2024-10-14 | 2025-11-02 | Level 2 | GO 165 Inspection
124823646 | other | Non-HFTD | Transmission | 2022-09-29 | 2024-09-29 | Level 3 | F | 2024-11-04 | 2025-09-29 | Level 2 | GO 165 Inspection
124824136 | pole | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2023-03-09 | 2025-11-03 | Level 2 | Standards change
124824710 | other | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2023-03-08 | 2025-11-03 | Level 2 | Standards change
124825396 | insulator and brushing | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2023-02-21 | 2025-11-03 | Level 2 | Standards change
124825563 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-03-03 | 2025-10-18 | Level 2 | Standards change
124825590 | insulator and brushing | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2024-10-10 | 2025-11-03 | Level 2 | GO 165 Inspection
124825600 | insulator and brushing | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2024-10-10 | 2025-11-03 | Level 2 | GO 165 Inspection
124825900 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124825905 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124825928 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-08-12 | 2025-10-18 | Level 2 | GO 165 Inspection
124826666 | pole | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-10-30 | 2027-10-31 | Level 3 | GO 165 Inspection
124826904 | pole | Non-HFTD | Transmission | 2022-10-28 | 2024-10-28 | Level 3 | F | 2024-09-11 | 2027-10-28 | Level 3 | GO 165 Inspection
124827286 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124827381 | other | Non-HFTD | Transmission | 2022-10-20 | 2024-10-20 | Level 3 | F | 2024-01-05 | 2027-10-20 | Level 3 | Standards change
124827389 | other | Non-HFTD | Transmission | 2022-10-27 | 2024-10-27 | Level 3 | F | 2024-04-06 | 2027-10-27 | Level 3 | Standards change
124831095 | other | Non-HFTD | Transmission | 2022-10-18 | 2025-10-18 | Level 2 | E | 2024-10-25 | 2023-10-18 | Level 2 | GO 165 Inspection
124831295 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-19 | 2025-10-18 | Level 2 | GO 165 Inspection
124832522 | other | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2024-10-21 | 2023-10-17 | Level 2 | GO 165 Inspection
124833508 | pole | Non-HFTD | Transmission | 2022-10-20 | 2024-10-20 | Level 3 | F | 2024-10-25 | 2027-10-20 | Level 3 | Field Safety Reassessment
124834609 | insulator and brushing | Non-HFTD | Transmission | 2022-10-03 | 2023-10-03 | Level 2 | E | 2024-08-12 | 2027-10-03 | Level 3 | GO 165 Inspection
124836501 | other | Non-HFTD | Transmission | 2022-11-05 | 2024-11-05 | Level 3 | F | 2024-10-15 | 2027-11-05 | Level 3 | GO 165 Inspection
124836861 | other | Non-HFTD | Transmission | 2022-11-05 | 2023-02-05 | Level 2 | E | 2024-10-15 | 2023-02-05 | Level 2 | GO 165 Inspection
124836902 | other | Non-HFTD | Transmission | 2022-11-05 | 2023-11-05 | Level 2 | E | 2024-10-15 | 2025-11-05 | Level 2 | GO 165 Inspection
124839552 | insulator and brushing | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2024-11-14 | 2025-11-04 | Level 2 | GO 165 Inspection
124840118 | other | Non-HFTD | Transmission | 2022-10-10 | 2024-10-10 | Level 3 | F | 2024-04-06 | 2027-10-10 | Level 3 | Standards change
124840267 | pole | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2023-01-12 | 2025-09-29 | Level 2 | Standards change
124840781 | pole | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2024-10-10 | 2025-10-20 | Level 2 | GO 165 Inspection
124840784 | pole | Non-HFTD | Transmission | 2022-11-07 | 2023-11-07 | Level 2 | E | 2023-02-01 | 2025-11-07 | Level 2 | Standards change
124841098 | pole | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2024-07-10 | 2027-11-07 | Level 3 | Field Safety Reassessment
124841388 | other | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2024-04-06 | 2027-11-07 | Level 3 | Standards change
124841471 | insulator and brushing | Non-HFTD | Transmission | 2022-11-07 | 2023-11-07 | Level 2 | E | 2023-02-09 | 2025-11-07 | Level 2 | Standards change
124842206 | other | Non-HFTD | Transmission | 2022-09-29 | 2024-09-29 | Level 3 | F | 2023-02-01 | 2027-09-29 | Level 3 | Standards change
124842747 | other | Non-HFTD | Transmission | 2022-09-29 | 2023-09-29 | Level 2 | E | 2024-11-18 | 2025-09-29 | Level 2 | GO 165 Inspection
124843241 | other | Non-HFTD | Transmission | 2022-10-04 | 2025-10-04 | Level 2 | E | 2024-11-19 | 2023-10-04 | Level 2 | GO 165 Inspection
124843470 | insulator and brushing | Non-HFTD | Transmission | 2022-09-30 | 2023-09-30 | Level 3 | F |  | 2027-09-30 | Level 3
124843719 | insulator and brushing | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-02 | 2025-10-10 | Level 2 | Standards change
124846790 | insulator and brushing | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2023-01-19 | 2025-11-08 | Level 2 | Standards change
124847282 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-11-04 | 2027-10-05 | Level 3 | GO 165 Inspection
124847333 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-11-04 | 2025-10-05 | Level 2 | GO 165 Inspection
124847613 | pole | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2023-01-30 | 2025-11-08 | Level 2 | Standards change
124847715 | insulator and brushing | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2023-01-09 | 2025-11-08 | Level 2 | Standards change
124847783 | pole | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2024-04-09 | 2025-11-08 | Level 2 | GO 165 Inspection
124847860 | other | Non-HFTD | Transmission | 2022-09-30 | 2024-09-30 | Level 3 | F | 2024-09-23 | 2027-09-30 | Level 3 | GO 165 Inspection
124848052 | other | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-02-21 | 2027-10-10 | Level 3 | Standards change
124848055 | other | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-09-12 | 2025-10-10 | Level 2 | GO 165 Inspection
124848277 | pole | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2023-01-30 | 2025-11-08 | Level 2 | Standards change
124849079 | other | Non-HFTD | Transmission | 2022-10-17 | 2024-10-17 | Level 3 | F | 2024-04-06 | 2027-10-17 | Level 3 | Standards change
124849615 | pole | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-11-14 | 2025-10-10 | Level 2 | GO 165 Inspection
124850081 | pole | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2023-01-30 | 2025-10-10 | Level 2 | Standards change
124850108 | pole | Non-HFTD | Transmission | 2022-08-17 | 2023-08-17 | Level 2 | E | 2024-11-15 | 2025-08-17 | Level 2 | Field Safety Reassessment
124850265 | other | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-08-23 | 2023-10-05 | Level 2 | GO 165 Inspection
124850340 | pole | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-08-23 | 2025-10-05 | Level 2 | GO 165 Inspection
124850970 | insulator and brushing | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2024-09-30 | 2025-11-08 | Level 2 | GO 165 Inspection
124851000 | other | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2023-01-12 | 2025-11-08 | Level 2 | Standards change
124851138 | insulator and brushing | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2024-01-17 | 2025-11-08 | Level 2 | Standards change
124852076 | insulator and brushing | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2023-09-12 | 2027-10-05 | Level 3 | Standards change
124852112 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-07-27 | 2025-07-15 | Level 2 | Standards change
124852243 | anchor/guy | Non-HFTD | Transmission | 2022-11-02 | 2023-11-02 | Level 2 | E | 2024-10-03 | 2025-11-02 | Level 2 | GO 165 Inspection
124852248 | pole | Non-HFTD | Transmission | 2022-07-17 | 2023-07-17 | Level 2 | E | 2023-02-28 | 2025-07-17 | Level 2 | Standards change
124852337 | other | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-10-14 | 2027-10-24 | Level 3 | GO 165 Inspection
124852338 | insulator and brushing | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2024-10-18 | 2025-11-04 | Level 2 | GO 165 Inspection
124852339 | other | Non-HFTD | Transmission | 2022-11-04 | 2024-11-04 | Level 3 | F | 2024-10-18 | 2027-11-04 | Level 3 | GO 165 Inspection
124853085 | insulator and brushing | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2024-10-16 | 2025-11-04 | Level 2 | GO 165 Inspection
124855091 | pole | Non-HFTD | Transmission | 2022-11-09 | 2024-11-09 | Level 3 | F | 2023-12-27 | 2027-11-09 | Level 3 | Standards change
124857128 | insulator and brushing | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-09-24 | 2025-10-05 | Level 2 | GO 165 Inspection
124857477 | other | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-09-10 | 2027-10-31 | Level 3 | GO 165 Inspection
124857479 | pole | Non-HFTD | Transmission | 2022-10-31 | 2023-10-31 | Level 2 | E | 2024-09-10 | 2025-10-31 | Level 2 | GO 165 Inspection
124858028 | anchor/guy | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-09-12 | 2025-10-05 | Level 2 | GO 165 Inspection
124858457 | other | Non-HFTD | Transmission | 2022-11-01 | 2024-11-01 | Level 3 | F | 2024-04-06 | 2027-11-01 | Level 3 | Standards change
124858501 | pole | Non-HFTD | Transmission | 2022-10-11 | 2024-10-11 | Level 3 | F | 2024-03-27 | 2027-10-11 | Level 3 | GO 165 Inspection
124858681 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-12 | 2025-10-18 | Level 2 | Standards change
124858771 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2023-12-14 | 2027-10-05 | Level 3 | Standards change
124858898 | pole | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-09-03 | 2025-10-11 | Level 2 | GO 165 Inspection
124858987 | other | Non-HFTD | Transmission | 2022-10-05 | 2024-10-05 | Level 3 | F | 2024-04-06 | 2027-10-05 | Level 3 | Standards change
124859172 | other | HFTD Tier 3 | Transmission | 2022-11-09 | 2024-11-09 | Level 3 | F | 2024-05-30 | 2027-11-09 | Level 3 | GO 165 Inspection
124859207 | other | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2023-03-23 | 2025-10-05 | Level 2 | Standards change
124865602 | insulator and brushing | Non-HFTD | Transmission | 2022-11-06 | 2025-11-06 | Level 2 | E | 2024-07-11 | 2023-02-06 | Level 2 | GO 165 Inspection
124866198 | insulator and brushing | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2024-07-23 | 2025-10-12 | Level 2 | GO 165 Inspection
124866521 | insulator and brushing | Non-HFTD | Transmission | 2022-11-05 | 2023-11-05 | Level 2 | E | 2024-12-10 | 2023-11-05 | Level 2 | Field Safety Reassessment
124868272 | other | Non-HFTD | Transmission | 2022-11-10 | 2023-11-10 | Level 2 | E | 2024-11-01 | 2025-11-10 | Level 2 | GO 165 Inspection
124868321 | other | Non-HFTD | Transmission | 2022-10-06 | 2024-10-06 | Level 3 | F | 2024-04-06 | 2027-10-06 | Level 3 | Standards change
124868654 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-02-17 | 2027-10-13 | Level 3 | Standards change
124869812 | other | Non-HFTD | Transmission | 2022-10-28 | 2024-10-28 | Level 3 | F | 2024-09-18 | 2027-10-28 | Level 3 | GO 165 Inspection
124869828 | other | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2024-04-06 | 2027-11-07 | Level 3 | Standards change
124877546 | anchor/guy | Non-HFTD | Transmission | 2022-11-11 | 2023-11-11 | Level 2 | E | 2023-03-09 | 2027-11-11 | Level 3 | Standards change
124883280 | conductor | Non-HFTD | Transmission | 2022-11-13 | 2023-11-13 | Level 2 | E | 2024-01-11 | 2025-11-13 | Level 2 | Standards change
124884308 | insulator and brushing | Non-HFTD | Transmission | 2022-10-28 | 2023-10-28 | Level 2 | E | 2024-08-29 | 2025-10-28 | Level 2 | GO 165 Inspection
124885107 | pole | Non-HFTD | Transmission | 2022-11-01 | 2024-11-01 | Level 3 | F | 2024-11-12 | 2027-11-01 | Level 3 | GO 165 Inspection
124885306 | pole | Non-HFTD | Transmission | 2022-11-14 | 2023-11-14 | Level 2 | E | 2023-03-09 | 2025-11-14 | Level 2 | Standards change
124886703 | other | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-08-01 | 2025-10-11 | Level 2 | GO 165 Inspection
124887000 | anchor/guy | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2023-03-02 | 2025-11-03 | Level 2 | Standards change
124887446 | pole | Non-HFTD | Transmission | 2022-10-31 | 2023-10-31 | Level 2 | E | 2024-08-21 | 2025-10-31 | Level 2 | GO 165 Inspection
124887585 | anchor/guy | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2023-02-27 | 2025-11-03 | Level 2 | Standards change
124889888 | insulator and brushing | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2024-02-02 | 2025-10-25 | Level 2 | Standards change
124890750 | other | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-07-22 | 2027-10-24 | Level 3 | GO 165 Inspection
124890756 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-12-06 | 2025-10-18 | Level 2 | Standards change
124891408 | insulator and brushing | Non-HFTD | Transmission | 2022-11-15 | 2023-11-15 | Level 2 | E | 2023-01-20 | 2025-11-15 | Level 2 | Standards change
124891744 | other | Non-HFTD | Transmission | 2022-11-04 | 2024-11-04 | Level 3 | F | 2024-04-06 | 2027-11-04 | Level 3 | Standards change
124891753 | pole | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2023-01-30 | 2025-11-04 | Level 2 | Standards change
124891947 | other | Non-HFTD | Transmission | 2022-10-21 | 2024-10-21 | Level 3 | F | 2022-12-16 | 2027-10-21 | Level 3 | Standards change
124893095 | pole | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2023-03-01 | 2025-11-04 | Level 2 | Standards change
124893333 | anchor/guy | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2023-01-13 | 2025-10-21 | Level 2 | Standards change
124893699 | other | Non-HFTD | Transmission | 2022-10-21 | 2024-10-21 | Level 3 | F | 2024-08-23 | 2027-10-21 | Level 3 | GO 165 Inspection
124893998 | pole | Non-HFTD | Transmission | 2022-10-06 | 2023-10-06 | Level 2 | E | 2023-02-27 | 2025-10-06 | Level 2 | Standards change
124896551 | pole | Non-HFTD | Transmission | 2022-11-16 | 2023-11-16 | Level 2 | E | 2023-02-27 | 2025-11-16 | Level 2 | Standards change
124896572 | other | Non-HFTD | Transmission | 2022-10-07 | 2023-10-07 | Level 2 | E | 2024-09-18 | 2025-10-07 | Level 2 | GO 165 Inspection
124906559 | other | Non-HFTD | Transmission | 2022-10-10 | 2024-10-10 | Level 3 | F | 2024-04-06 | 2027-10-10 | Level 3 | Standards change
124906731 | pole | Non-HFTD | Transmission | 2022-10-10 | 2023-10-10 | Level 2 | E | 2024-10-23 | 2025-10-10 | Level 2 | GO 165 Inspection
124907801 | insulator and brushing | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-11-24 | 2025-10-11 | Level 2 | GO 165 Inspection
124921271 | other | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-10-11 | 2025-10-18 | Level 2 | GO 165 Inspection
124921300 | pole | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2024-11-24 | 2025-10-11 | Level 2 | GO 165 Inspection
124921578 | other | Non-HFTD | Transmission | 2022-10-12 | 2024-10-12 | Level 3 | F | 2024-02-08 | 2027-10-12 | Level 3 | Standards change
124922166 | other | Non-HFTD | Transmission | 2022-10-11 | 2024-10-11 | Level 3 | F | 2023-01-30 | 2027-10-11 | Level 3 | Standards change
124922541 | other | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-01-20 | 2027-10-12 | Level 3 | Standards change
124922546 | other | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-01-20 | 2025-10-12 | Level 2 | Standards change
124922726 | other | Non-HFTD | Transmission | 2022-10-12 | 2024-10-12 | Level 3 | F | 2024-11-05 | 2027-10-12 | Level 3 | GO 165 Inspection
124922758 | pole | Non-HFTD | Transmission | 2022-11-21 | 2023-11-21 | Level 2 | E | 2022-12-19 | 2023-11-21 | Level 2 | Standards change
124922824 | pole | Non-HFTD | Transmission | 2022-11-21 | 2023-11-21 | Level 2 | E | 2022-12-19 | 2025-11-21 | Level 2 | Standards change
124923568 | pole | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2024-09-18 | 2027-10-13 | Level 3 | GO 165 Inspection
124924811 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2023-02-17 | 2027-10-13 | Level 3 | Standards change
124924819 | insulator and brushing | Non-HFTD | Transmission | 2022-10-13 | 2023-10-13 | Level 2 | E | 2024-07-29 | 2027-10-13 | Level 3 | GO 165 Inspection
124926634 | other | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2023-11-15 | 2025-10-14 | Level 2 | Standards change
124927498 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-02-14 | 2025-10-18 | Level 2 | Standards change
124928178 | other | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-11-15 | 2027-10-17 | Level 3 | Standards change
124929867 | other | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-11-15 | 2027-10-18 | Level 3 | GO 165 Inspection
124931801 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-11-20 | 2025-10-18 | Level 2 | GO 165 Inspection
124932302 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-10-09 | 2025-10-18 | Level 2 | GO 165 Inspection
124932871 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-18 | 2025-10-18 | Level 2 | GO 165 Inspection
124932875 | anchor/guy | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-18 | 2025-10-18 | Level 2 | GO 165 Inspection
124933082 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-11-15 | 2025-10-18 | Level 2 | Standards change
124933383 | other | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-07-17 | 2027-10-18 | Level 3 | GO 165 Inspection
124933388 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-17 | 2025-10-18 | Level 2 | GO 165 Inspection
124933505 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-19 | 2025-10-18 | Level 2 | GO 165 Inspection
124933507 | other | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-07-19 | 2027-10-18 | Level 3 | GO 165 Inspection
124933579 | other | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-07-19 | 2027-10-18 | Level 3 | GO 165 Inspection
124933632 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-19 | 2025-10-18 | Level 2 | GO 165 Inspection
124933634 | insulator and brushing | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-09-28 | 2025-10-18 | Level 2 | GO 165 Inspection
124934183 | other | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2024-07-19 | 2025-10-18 | Level 2 | GO 165 Inspection
124934187 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-01-27 | 2025-10-18 | Level 2 | Standards change
124941183 | other | Non-HFTD | Transmission | 2022-10-18 | 2024-10-18 | Level 3 | F | 2024-07-18 | 2027-10-18 | Level 3 | GO 165 Inspection
124941777 | other | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2024-11-08 | 2027-10-19 | Level 3 | GO 165 Inspection
124941932 | other | Non-HFTD | Transmission | 2022-11-28 | 2024-11-28 | Level 3 | F | 2022-12-20 | 2027-11-28 | Level 3 | Standards change
124941996 | other | Non-HFTD | Transmission | 2022-11-28 | 2024-11-28 | Level 3 | F | 2022-12-20 | 2027-11-28 | Level 3 | Standards change
124942202 | other | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2024-09-09 | 2025-10-19 | Level 2 | GO 165 Inspection
124942204 | insulator and brushing | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2024-09-09 | 2025-10-19 | Level 2 | GO 165 Inspection
124944459 | anchor/guy | Non-HFTD | Transmission | 2022-10-19 | 2023-10-19 | Level 2 | E | 2024-07-13 | 2023-04-19 | Level 2 | Field Safety Reassessment
124944555 | other | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2023-12-08 | 2027-10-19 | Level 3 | Standards change
124944623 | insulator and brushing | Non-HFTD | Transmission | 2022-10-11 | 2023-10-11 | Level 2 | E | 2023-02-03 | 2025-10-11 | Level 2 | Standards change
124947024 | insulator and brushing | Non-HFTD | Transmission | 2022-11-29 | 2023-11-29 | Level 2 | E | 2023-11-15 | 2025-11-29 | Level 2 | Standards change
124952394 | other | Non-HFTD | Transmission | 2022-11-30 | 2023-11-30 | Level 2 | E | 2022-12-22 | 2025-11-30 | Level 2 | Standards change
124953499 | pole | Non-HFTD | Transmission | 2022-11-30 | 2023-11-30 | Level 2 | E | 2023-08-14 | 2025-11-30 | Level 2 | GO 165 Inspection
124953597 | pole | Non-HFTD | Transmission | 2022-11-30 | 2023-11-30 | Level 2 | E | 2024-10-29 | 2023-11-30 | Level 2 | Field Safety Reassessment
124954109 | other | Non-HFTD | Transmission | 2022-10-20 | 2024-10-20 | Level 3 | F | 2024-10-10 | 2027-10-20 | Level 3 | GO 165 Inspection
124956039 | pole | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-09-10 | 2025-10-21 | Level 2 | GO 165 Inspection
124956379 | other | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2024-11-24 | 2027-10-19 | Level 3 | GO 165 Inspection
124956529 | other | Non-HFTD | Transmission | 2022-10-19 | 2024-10-19 | Level 3 | F | 2024-11-24 | 2027-10-19 | Level 3 | GO 165 Inspection
124957854 | pole | Non-HFTD | Transmission | 2022-10-20 | 2024-10-20 | Level 3 | F | 2024-10-10 | 2027-10-20 | Level 3 | GO 165 Inspection
124973892 | pole | Non-HFTD | Transmission | 2022-12-05 | 2024-12-05 | Level 3 | F | 2024-10-24 | 2027-12-05 | Level 3 | GO 165 Inspection
124974389 | pole | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2023-02-06 | 2025-10-20 | Level 2 | Standards change
124974492 | anchor/guy | Non-HFTD | Transmission | 2022-12-05 | 2023-12-05 | Level 2 | E | 2024-10-08 | 2025-12-05 | Level 2 | GO 165 Inspection
124975406 | insulator and brushing | Non-HFTD | Transmission | 2022-10-05 | 2023-10-05 | Level 2 | E | 2024-11-04 | 2025-10-05 | Level 2 | GO 165 Inspection
124978473 | other | Non-HFTD | Transmission | 2022-10-21 | 2024-10-21 | Level 3 | F | 2024-09-17 | 2027-10-21 | Level 3 | GO 165 Inspection
124979239 | pole | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2022-12-08 | 2025-10-21 | Level 2 | Standards change
124980648 | conductor | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-09-30 | 2025-10-21 | Level 2 | GO 165 Inspection
124980932 | other | Non-HFTD | Transmission | 2022-10-21 | 2024-10-21 | Level 3 | F | 2024-10-22 | 2027-10-21 | Level 3 | GO 165 Inspection
124981209 | pole | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-10-10 | 2025-10-21 | Level 2 | GO 165 Inspection
124981309 | other | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-10-08 | 2025-10-21 | Level 2 | GO 165 Inspection
124981912 | pole | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-09-06 | 2025-10-21 | Level 2 | GO 165 Inspection
124981970 | pole | Non-HFTD | Transmission | 2022-10-21 | 2024-10-21 | Level 3 | F | 2024-09-06 | 2027-10-21 | Level 3 | GO 165 Inspection
124981973 | pole | Non-HFTD | Transmission | 2022-10-21 | 2023-10-21 | Level 2 | E | 2024-09-06 | 2025-10-21 | Level 2 | GO 165 Inspection
124983501 | switch | Non-HFTD | Transmission | 2022-12-07 | 2023-03-07 | Level 2 | E | 2024-11-30 | 2023-03-07 | Level 2 | Field Safety Reassessment
124983547 | other | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-10-15 | 2027-10-24 | Level 3 | GO 165 Inspection
124983743 | pole | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-10-15 | 2025-10-24 | Level 2 | GO 165 Inspection
124983911 | pole | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-11-27 | 2027-10-24 | Level 3 | GO 165 Inspection
124984325 | pole | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-10-31 | 2027-10-24 | Level 3 | Field Safety Reassessment
124986170 | pole | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-08-17 | 2027-10-24 | Level 3 | GO 165 Inspection
124986264 | other | Non-HFTD | Transmission | 2022-12-07 | 2023-12-07 | Level 2 | E | 2022-12-30 | 2025-12-07 | Level 2 | Standards change
124986447 | other | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-10-15 | 2027-10-24 | Level 3 | GO 165 Inspection
124986719 | pole | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2024-10-15 | 2025-10-24 | Level 2 | GO 165 Inspection
124987297 | pole | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2022-12-09 | 2025-10-24 | Level 2 | Standards change
124987382 | insulator and brushing | Non-HFTD | Transmission | 2022-10-24 | 2023-10-24 | Level 2 | E | 2022-12-13 | 2025-10-24 | Level 2 | Standards change
124990156 | pole | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2024-10-09 | 2027-10-24 | Level 3 | GO 165 Inspection
124990393 | pole | Non-HFTD | Transmission | 2022-10-24 | 2024-10-24 | Level 3 | F | 2022-12-13 | 2027-10-24 | Level 3 | Standards change
124997843 | pole | Non-HFTD | Transmission | 2022-12-09 | 2023-12-09 | Level 2 | E | 2024-01-23 | 2023-12-09 | Level 2 | Field Safety Reassessment
125012294 | other | Non-HFTD | Transmission | 2022-10-26 | 2024-10-26 | Level 3 | F | 2024-10-31 | 2027-10-26 | Level 3 | GO 165 Inspection
125013119 | other | Non-HFTD | Transmission | 2022-10-25 | 2024-10-25 | Level 3 | F | 2022-12-14 | 2027-10-25 | Level 3 | Standards change
125014335 | pole | Non-HFTD | Transmission | 2022-10-20 | 2023-10-20 | Level 2 | E | 2023-08-14 | 2025-10-20 | Level 2 | GO 165 Inspection
125016286 | other | Non-HFTD | Transmission | 2022-10-25 | 2024-10-25 | Level 3 | F | 2024-08-15 | 2027-10-25 | Level 3 | GO 165 Inspection
125016797 | insulator and brushing | Non-HFTD | Transmission | 2022-11-21 | 2023-11-21 | Level 2 | E | 2022-12-19 | 2025-11-21 | Level 2 | Standards change
125018927 | other | Non-HFTD | Transmission | 2022-10-25 | 2024-10-25 | Level 3 | F | 2024-03-15 | 2027-10-25 | Level 3 | GO 165 Inspection
125022718 | insulator and brushing | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2024-10-18 | 2023-10-25 | Level 2 | GO 165 Inspection
125022739 | other | Non-HFTD | Transmission | 2022-10-26 | 2024-10-26 | Level 3 | F | 2024-09-17 | 2027-10-26 | Level 3 | GO 165 Inspection
125022829 | other | Non-HFTD | Transmission | 2022-11-14 | 2024-11-14 | Level 3 | F | 2022-12-15 | 2027-11-14 | Level 3 | Standards change
125022858 | other | Non-HFTD | Transmission | 2022-10-27 | 2024-10-27 | Level 3 | F | 2022-12-15 | 2027-10-27 | Level 3 | Standards change
125024670 | other | Non-HFTD | Transmission | 2022-10-26 | 2024-10-26 | Level 3 | F | 2024-07-31 | 2027-10-26 | Level 3 | GO 165 Inspection
125025281 | other | Non-HFTD | Transmission | 2022-12-13 | 2023-12-13 | Level 2 | E | 2024-12-03 | 2023-12-13 | Level 2 | Field Safety Reassessment
125027005 | pole | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2024-05-13 | 2027-11-07 | Level 3 | GO 165 Inspection
125027073 | other | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2024-05-13 | 2027-11-07 | Level 3 | GO 165 Inspection
125027441 | other | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2022-12-15 | 2027-11-07 | Level 3 | Standards change
125028079 | pole | Non-HFTD | Transmission | 2022-10-28 | 2023-10-28 | Level 2 | E | 2024-08-21 | 2025-10-28 | Level 2 | GO 165 Inspection
125031507 | anchor/guy | HFTD Tier 2 | Transmission | 2022-12-15 | 2024-12-15 | Level 3 | F | 2024-03-15 | 2027-12-15 | Level 3 | GO 165 Inspection
125032136 | switch | Non-HFTD | Transmission | 2022-12-15 | 2023-12-15 | Level 2 | E | 2023-07-06 | 2023-12-15 | Level 2 | Field Safety Reassessment
125057074 | crossarm | Non-HFTD | Transmission | 2022-12-15 | 2023-12-15 | Level 2 | E | 2023-12-11 | 2023-12-15 | Level 2 | Field Safety Reassessment
125071340 | other | Non-HFTD | Transmission | 2022-12-15 | 2024-12-15 | Level 3 | F | 2024-02-06 | 2027-12-15 | Level 3 | Field Safety Reassessment
125071361 | other | Non-HFTD | Transmission | 2022-12-15 | 2023-03-15 | Level 2 | E | 2024-09-13 | 2023-03-15 | Level 2 | GO 165 Inspection
125082754 | pole | Non-HFTD | Transmission | 2022-12-16 | 2024-12-16 | Level 3 | F | 2022-12-30 | 2027-12-16 | Level 3 | Standards change
125093259 | other | Non-HFTD | Transmission | 2022-12-16 | 2023-12-16 | Level 2 | E | 2022-12-30 | 2025-12-16 | Level 2 | Standards change
125093613 | other | Non-HFTD | Transmission | 2022-12-16 | 2024-12-16 | Level 3 | F | 2022-12-30 | 2027-12-16 | Level 3 | Standards change
125112244 | pole | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-10-10 | 2027-10-31 | Level 3 | GO 165 Inspection
125128897 | other | Non-HFTD | Transmission | 2022-10-28 | 2023-10-28 | Level 2 | E | 2022-12-21 | 2025-10-28 | Level 2 | Standards change
125128966 | other | Non-HFTD | Transmission | 2022-11-01 | 2024-11-01 | Level 3 | F | 2022-12-21 | 2027-11-01 | Level 3 | Standards change
125133490 | pole | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-10-29 | 2027-10-31 | Level 3 | GO 165 Inspection
125134654 | other | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2022-12-21 | 2027-11-07 | Level 3 | Standards change
125143892 | pole | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2022-12-21 | 2027-11-07 | Level 3 | Standards change
125146461 | pole | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-10-18 | 2027-10-31 | Level 3 | GO 165 Inspection
125148558 | other | HFTD Tier 2 | Transmission | 2022-12-20 | 2023-12-20 | Level 2 | E | 2024-04-03 | 2025-12-20 | Level 2 | GO 165 Inspection
125152217 | other | HFTD Tier 2 | Transmission | 2022-12-20 | 2024-12-20 | Level 3 | F | 2024-06-11 | 2027-12-20 | Level 3 | GO 165 Inspection
125155258 | other | Non-HFTD | Transmission | 2022-10-28 | 2024-10-28 | Level 3 | F | 2024-07-11 | 2027-10-28 | Level 3 | GO 165 Inspection
125159468 | other | Non-HFTD | Transmission | 2022-10-31 | 2024-10-31 | Level 3 | F | 2024-08-07 | 2027-10-31 | Level 3 | GO 165 Inspection
125170549 | pole | HFTD Tier 2 | Transmission | 2022-12-20 | 2023-12-20 | Level 2 | E | 2024-04-03 | 2025-12-20 | Level 2 | GO 165 Inspection
125174032 | other | Non-HFTD | Transmission | 2022-11-07 | 2024-11-07 | Level 3 | F | 2024-11-14 | 2027-11-07 | Level 3 | GO 165 Inspection
125175519 | insulator and brushing | Non-HFTD | Transmission | 2022-11-01 | 2023-11-01 | Level 2 | E | 2024-09-13 | 2025-11-01 | Level 2 | GO 165 Inspection
125175565 | anchor/guy | Non-HFTD | Transmission | 2022-11-06 | 2023-11-06 | Level 2 | E | 2024-07-12 | 2025-11-06 | Level 2 | GO 165 Inspection
125177028 | pole | Non-HFTD | Transmission | 2022-11-05 | 2023-11-05 | Level 2 | E | 2022-12-22 | 2025-11-05 | Level 2 | Standards change
125205933 | anchor/guy | Non-HFTD | Transmission | 2022-11-06 | 2023-11-06 | Level 2 | E | 2022-12-29 | 2025-11-06 | Level 2 | Standards change
125206368 | insulator and brushing | Non-HFTD | Transmission | 2022-11-05 | 2024-11-05 | Level 3 | F | 2024-08-23 | 2027-11-05 | Level 3 | GO 165 Inspection
125209787 | pole | Non-HFTD | Transmission | 2022-11-01 | 2024-11-01 | Level 3 | F | 2024-10-29 | 2027-11-01 | Level 3 | GO 165 Inspection
125223647 | other | Non-HFTD | Transmission | 2022-12-22 | 2023-12-22 | Level 2 | E | 2022-12-23 | 2025-12-22 | Level 2 | Standards change
125224599 | other | Non-HFTD | Transmission | 2022-12-22 | 2023-12-22 | Level 2 | E | 2022-12-23 | 2025-12-22 | Level 2 | Standards change
125226075 | insulator and brushing | Non-HFTD | Transmission | 2022-11-05 | 2023-11-05 | Level 2 | E | 2024-09-03 | 2025-11-05 | Level 2 | GO 165 Inspection
125229673 | other | Non-HFTD | Transmission | 2022-11-04 | 2024-11-04 | Level 3 | F | 2024-07-23 | 2027-11-04 | Level 3 | GO 165 Inspection
125229967 | anchor/guy | Non-HFTD | Transmission | 2022-11-04 | 2024-11-04 | Level 3 | F | 2022-12-23 | 2027-11-04 | Level 3 | Standards change
125230140 | other | Non-HFTD | Transmission | 2022-11-05 | 2024-11-05 | Level 3 | F | 2024-08-01 | 2027-11-05 | Level 3 | GO 165 Inspection
125254548 | other | Non-HFTD | Transmission | 2022-11-05 | 2023-11-05 | Level 2 | E | 2024-08-22 | 2025-11-05 | Level 2 | GO 165 Inspection
125254634 | pole | Non-HFTD | Transmission | 2022-11-03 | 2024-11-03 | Level 3 | F | 2024-10-15 | 2027-11-03 | Level 3 | GO 165 Inspection
125254686 | other | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2022-12-28 | 2025-11-04 | Level 2 | Standards change
125254940 | pole | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2024-10-16 | 2025-11-03 | Level 2 | GO 165 Inspection
125254992 | other | Non-HFTD | Transmission | 2022-11-03 | 2023-11-03 | Level 2 | E | 2024-09-17 | 2025-11-03 | Level 2 | GO 165 Inspection
125255177 | pole | Non-HFTD | Transmission | 2022-11-03 | 2024-11-03 | Level 3 | F | 2024-10-25 | 2027-11-03 | Level 3 | GO 165 Inspection
125255401 | anchor/guy | Non-HFTD | Transmission | 2022-11-04 | 2023-11-04 | Level 2 | E | 2023-03-26 | 2025-11-04 | Level 2 | GO 165 Inspection
125255572 | other | Non-HFTD | Transmission | 2022-12-27 | 2023-12-27 | Level 2 | E | 2023-01-04 | 2025-12-27 | Level 2 | Standards change
125258017 | other | Non-HFTD | Transmission | 2022-12-27 | 2023-12-27 | Level 2 | E | 2023-01-04 | 2025-12-27 | Level 2 | Standards change
125265548 | splice | Non-HFTD | Transmission | 2022-12-29 | 2023-12-29 | Level 2 | E | 2023-01-03 | 2025-12-29 | Level 2 | Standards change
125268949 | other | Non-HFTD | Transmission | 2022-12-30 | 2023-12-30 | Level 2 | E | 2024-08-30 | 2025-12-30 | Level 2 | GO 165 Inspection
125269143 | other | Non-HFTD | Transmission | 2022-12-30 | 2023-12-30 | Level 2 | E | 2024-07-18 | 2025-12-30 | Level 2 | GO 165 Inspection
125274683 | pole | Non-HFTD | Transmission | 2023-01-03 | 2026-01-03 | Level 2 | E |  | 2026-01-03 | Level 2
125277523 | pole | Non-HFTD | Transmission | 2023-01-04 | 2028-01-04 | Level 3 | F |  | 2028-01-04 | Level 3
125277531 | pole | Non-HFTD | Transmission | 2023-01-04 | 2028-01-04 | Level 3 | F |  | 2028-01-04 | Level 3
125324040 | anchor/guy | Non-HFTD | Transmission | 2023-01-10 | 2026-01-10 | Level 2 | E | 2023-09-19 | 2026-01-10 | Level 2 | GO 165 Inspection
125343810 | pole | Non-HFTD | Transmission | 2023-01-13 | 2026-01-13 | Level 2 | E | 2024-10-25 | 2023-07-13 | Level 2 | GO 165 Inspection
125364221 | pole | Non-HFTD | Transmission | 2022-11-29 | 2023-11-29 | Level 2 | E | 2024-08-26 | 2025-11-29 | Level 2 | GO 165 Inspection
125365481 | pole | Non-HFTD | Transmission | 2022-10-26 | 2023-10-26 | Level 2 | E | 2024-10-11 | 2025-10-26 | Level 2 | GO 165 Inspection
125365867 | pole | Non-HFTD | Transmission | 2022-09-20 | 2023-09-20 | Level 2 | E | 2023-11-15 | 2025-09-20 | Level 2 | Standards change
125366286 | pole | Non-HFTD | Transmission | 2022-09-15 | 2023-09-15 | Level 2 | E | 2024-08-19 | 2025-09-15 | Level 2 | GO 165 Inspection
125371661 | pole | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-11-07 | 2025-09-01 | Level 2 | GO 165 Inspection
125372135 | pole | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-10-08 | 2025-10-12 | Level 2 | GO 165 Inspection
125373084 | pole | Non-HFTD | Transmission | 2022-10-14 | 2023-10-14 | Level 2 | E | 2023-10-11 | 2025-10-14 | Level 2 | GO 165 Inspection
125373253 | pole | Non-HFTD | Transmission | 2022-09-23 | 2023-09-23 | Level 2 | E | 2023-10-05 | 2025-09-23 | Level 2 | GO 165 Inspection
125377843 | pole | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2024-04-17 | 2026-01-24 | Level 2 | GO 165 Inspection
125377901 | other | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2024-04-17 | 2026-01-24 | Level 2 | GO 165 Inspection
125379398 | pole | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2024-06-13 | 2026-01-24 | Level 2 | GO 165 Inspection
125379412 | pole | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2023-07-08 | 2026-01-24 | Level 2 | GO 165 Inspection
125379754 | pole | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2024-02-01 | 2026-01-24 | Level 2 | GO 165 Inspection
125381270 | pole | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2024-06-13 | 2026-01-24 | Level 2 | GO 165 Inspection
125381579 | pole | Non-HFTD | Transmission | 2023-01-24 | 2026-01-24 | Level 2 | E | 2024-06-14 | 2026-01-24 | Level 2 | GO 165 Inspection
125390296 | pole | Non-HFTD | Transmission | 2023-01-26 | 2026-01-26 | Level 2 | E | 2024-02-14 | 2026-01-26 | Level 2 | GO 165 Inspection
125390719 | anchor/guy | Non-HFTD | Transmission | 2023-01-26 | 2026-01-26 | Level 2 | E |  | 2026-01-26 | Level 2
125392158 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-01-26 | 2026-01-26 | Level 2 | E | 2024-06-03 | 2026-01-26 | Level 2 | GO 165 Inspection
125392265 | other | HFTD Tier 2 | Transmission | 2023-01-26 | 2028-01-26 | Level 3 | F |  | 2028-01-26 | Level 3
125394870 | other | Non-HFTD | Transmission | 2023-01-26 | 2026-01-26 | Level 2 | E | 2024-02-15 | 2026-01-26 | Level 2 | GO 165 Inspection
125408335 | anchor/guy | Non-HFTD | Transmission | 2023-01-30 | 2028-01-30 | Level 3 | F |  | 2028-01-30 | Level 3
125408710 | pole | Non-HFTD | Transmission | 2023-01-30 | 2026-01-30 | Level 2 | E | 2024-06-27 | 2026-01-30 | Level 2 | GO 165 Inspection
125409832 | pole | HFTD Tier 2 | Transmission | 2023-01-30 | 2026-01-30 | Level 2 | E | 2024-04-01 | 2026-01-30 | Level 2 | GO 165 Inspection
125409834 | pole | Non-HFTD | Transmission | 2023-01-30 | 2026-01-30 | Level 2 | E | 2024-02-15 | 2026-01-30 | Level 2 | GO 165 Inspection
125410785 | other | Non-HFTD | Transmission | 2023-01-27 | 2026-01-27 | Level 2 | E | 2024-07-09 | 2026-01-27 | Level 2 | GO 165 Inspection
125413097 | anchor/guy | Non-HFTD | Transmission | 2023-01-31 | 2026-01-31 | Level 2 | E | 2023-01-31 | 2026-01-31 | Level 2 | GO 165 Inspection
125413795 | other | Non-HFTD | Transmission | 2023-01-31 | 2028-01-31 | Level 3 | F | 2024-02-28 | 2028-01-31 | Level 3 | Field Safety Reassessment
125415465 | pole | Non-HFTD | Transmission | 2023-01-31 | 2026-01-31 | Level 2 | E | 2023-03-13 | 2026-01-31 | Level 2 | GO 165 Inspection
125419717 | pole | Non-HFTD | Transmission | 2023-02-01 | 2026-02-01 | Level 2 | E |  | 2026-02-01 | Level 2
125420191 | pole | Non-HFTD | Transmission | 2023-02-01 | 2026-02-01 | Level 2 | E | 2024-11-13 | 2026-02-01 | Level 2 | GO 165 Inspection
125420989 | other | Non-HFTD | Transmission | 2023-02-01 | 2026-02-01 | Level 2 | E |  | 2026-02-01 | Level 2
125422122 | pole | Non-HFTD | Transmission | 2023-02-01 | 2026-02-01 | Level 2 | E |  | 2026-02-01 | Level 2
125424821 | pole | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E |  | 2026-02-02 | Level 2
125425269 | other | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E |  | 2026-02-02 | Level 2
125425846 | pole | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E | 2024-01-31 | 2026-02-02 | Level 2 | GO 165 Inspection
125427058 | pole | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E |  | 2026-02-02 | Level 2
125427080 | pole | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E |  | 2026-02-02 | Level 2
125427385 | anchor/guy | Non-HFTD | Transmission | 2023-02-02 | 2028-02-02 | Level 3 | F |  | 2028-02-02 | Level 3
125428183 | other | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E |  | 2026-02-02 | Level 2
125428513 | anchor/guy | Non-HFTD | Transmission | 2023-02-02 | 2026-02-02 | Level 2 | E | 2024-03-20 | 2026-02-02 | Level 2 | GO 165 Inspection
125432167 | other | Non-HFTD | Transmission | 2023-02-03 | 2026-02-03 | Level 2 | E | 2024-06-13 | 2026-02-03 | Level 2 | GO 165 Inspection
125433017 | other | HFTD Tier 2 | Transmission | 2023-01-31 | 2028-01-31 | Level 3 | F | 2023-04-10 | 2028-01-31 | Level 3 | GO 165 Inspection
125433475 | pole | Non-HFTD | Transmission | 2023-02-03 | 2026-02-03 | Level 2 | E |  | 2026-02-03 | Level 2
125436053 | pole | Non-HFTD | Transmission | 2023-02-04 | 2026-02-04 | Level 2 | E | 2024-10-02 | 2026-02-04 | Level 2 | GO 165 Inspection
125439195 | other | HFTD Tier 2 | Transmission | 2023-01-31 | 2028-01-31 | Level 3 | F | 2024-02-01 | 2028-01-31 | Level 3 | GO 165 Inspection
125439285 | other | Non-HFTD | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F | 2024-09-05 | 2028-02-06 | Level 3 | GO 165 Inspection
125445069 | other | HFTD Tier 2 | Transmission | 2023-02-01 | 2028-02-01 | Level 3 | F | 2024-03-15 | 2028-02-01 | Level 3 | GO 165 Inspection
125445452 | pole | HFTD Tier 2 | Transmission | 2023-02-01 | 2028-02-01 | Level 3 | F | 2024-02-13 | 2028-02-01 | Level 3 | GO 165 Inspection
125445457 | other | HFTD Tier 2 | Transmission | 2023-02-01 | 2024-02-01 | Level 2 | E | 2024-08-08 | 2024-02-01 | Level 2 | Field Safety Reassessment
125446723 | other | HFTD Tier 2 | Transmission | 2023-02-02 | 2028-02-02 | Level 3 | F | 2023-05-17 | 2028-02-02 | Level 3 | GO 165 Inspection
125447176 | other | Non-HFTD | Transmission | 2023-02-07 | 2026-02-07 | Level 2 | E | 2024-01-30 | 2026-02-07 | Level 2 | GO 165 Inspection
125450307 | pole | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F | 2024-06-05 | 2028-02-08 | Level 3 | GO 165 Inspection
125450535 | pole | Non-HFTD | Transmission | 2023-02-08 | 2026-02-08 | Level 2 | E |  | 2026-02-08 | Level 2
125451266 | other | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125451321 | pole | Non-HFTD | Transmission | 2023-02-08 | 2026-02-08 | Level 2 | E |  | 2026-02-08 | Level 2
125451411 | pole | Non-HFTD | Transmission | 2023-02-08 | 2026-02-08 | Level 2 | E |  | 2026-02-08 | Level 2
125451782 | other | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125451844 | anchor/guy | Non-HFTD | Transmission | 2023-02-08 | 2026-02-08 | Level 2 | E |  | 2026-02-08 | Level 2
125452556 | other | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125453194 | pole | Non-HFTD | Transmission | 2023-02-08 | 2026-02-08 | Level 2 | E | 2024-01-30 | 2026-02-08 | Level 2 | GO 165 Inspection
125470288 | other | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125484463 | other | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125485078 | pole | Non-HFTD | Transmission | 2023-02-10 | 2026-02-10 | Level 2 | E | 2024-06-15 | 2026-02-10 | Level 2 | GO 165 Inspection
125485448 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125486111 | other | HFTD Tier 3 | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F |  | 2028-02-06 | Level 3
125486909 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F |  | 2028-02-06 | Level 3
125491444 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-06 | 2026-02-06 | Level 2 | E | 2023-04-05 | 2026-02-06 | Level 2 | GO 165 Inspection
125491492 | pole | Non-HFTD | Transmission | 2023-02-10 | 2026-02-10 | Level 2 | E | 2024-01-31 | 2026-02-10 | Level 2 | GO 165 Inspection
125491516 | other | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125491544 | other | Non-HFTD | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F | 2024-03-21 | 2028-02-06 | Level 3 | GO 165 Inspection
125491649 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F |  | 2028-02-06 | Level 3
125491718 | other | HFTD Tier 2 | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F |  | 2028-02-06 | Level 3
125492641 | other | HFTD Tier 2 | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F | 2024-06-04 | 2028-02-06 | Level 3 | GO 165 Inspection
125492644 | anchor/guy | HFTD Tier 3 | Transmission | 2023-02-06 | 2026-02-06 | Level 2 | E |  | 2026-02-06 | Level 2
125497654 | pole | HFTD Tier 2 | Transmission | 2023-02-06 | 2028-02-06 | Level 3 | F | 2023-05-31 | 2028-02-06 | Level 3 | GO 165 Inspection
125497838 | pole | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F | 2024-06-07 | 2028-02-14 | Level 3 | GO 165 Inspection
125498880 | pole | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F | 2024-06-05 | 2028-02-14 | Level 3 | GO 165 Inspection
125499212 | pole | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-01-31 | 2026-02-14 | Level 2 | GO 165 Inspection
125501443 | pole | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 2 | E | 2024-09-05 | 2024-02-14 | Level 2 | GO 165 Inspection
125502026 | other | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125504878 | pole | HFTD Tier 3 | Transmission | 2023-02-07 | 2028-02-07 | Level 3 | F | 2024-01-29 | 2028-02-07 | Level 3 | GO 165 Inspection
125507721 | other | HFTD Tier 2 | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F |  | 2028-02-15 | Level 3
125508891 | other | HFTD Tier 2 | Transmission | 2023-02-07 | 2028-02-07 | Level 3 | F |  | 2028-02-07 | Level 3
125508900 | other | HFTD Tier 2 | Transmission | 2023-02-15 | 2024-02-15 | Level 2 | E | 2024-06-08 | 2024-02-15 | Level 2 | GO 165 Inspection
125509114 | other | HFTD Tier 2 | Transmission | 2023-02-15 | 2028-02-15 | Level 2 | E | 2024-04-15 | 2024-02-15 | Level 2 | GO 165 Inspection
125509594 | other | Non-HFTD | Transmission | 2023-02-15 | 2024-02-15 | Level 2 | E |  | 2024-02-15 | Level 2
125511921 | other | HFTD Tier 2 | Transmission | 2023-02-07 | 2028-02-07 | Level 3 | F |  | 2028-02-07 | Level 3
125512272 | other | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F |  | 2028-02-08 | Level 3
125512750 | pole | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F | 2024-04-16 | 2028-02-08 | Level 3 | GO 165 Inspection
125513149 | pole | HFTD Tier 2 | Transmission | 2023-02-07 | 2026-02-07 | Level 2 | E | 2023-06-27 | 2026-02-07 | Level 2 | GO 165 Inspection
125513264 | other | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F | 2024-04-08 | 2028-02-08 | Level 3 | GO 165 Inspection
125514960 | insulator and brushing | Non-HFTD | Transmission | 2023-02-16 | 2026-02-16 | Level 2 | E | 2024-08-28 | 2026-02-16 | Level 2 | GO 165 Inspection
125516213 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125516609 | other | HFTD Tier 2 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F | 2023-06-23 | 2028-02-03 | Level 3 | GO 165 Inspection
125516658 | other | HFTD Tier 3 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125516691 | other | HFTD Tier 3 | Transmission | 2023-02-03 | 2028-02-03 | Level 3 | F |  | 2028-02-03 | Level 3
125516753 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-06 | 2026-02-06 | Level 2 | E | 2024-05-31 | 2026-02-06 | Level 2 | GO 165 Inspection
125520081 | other | HFTD Tier 2 | Transmission | 2023-02-07 | 2028-02-07 | Level 3 | F | 2023-05-23 | 2028-02-07 | Level 3 | GO 165 Inspection
125520250 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-07 | 2026-02-07 | Level 2 | E | 2023-06-27 | 2026-02-07 | Level 2 | GO 165 Inspection
125521731 | other | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F | 2024-05-28 | 2028-02-08 | Level 3 | GO 165 Inspection
125522081 | other | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F |  | 2028-02-08 | Level 3
125522226 | anchor/guy | Non-HFTD | Transmission | 2023-02-17 | 2024-02-17 | Level 2 | E | 2024-02-08 | 2024-02-17 | Level 2 | GO 165 Inspection
125522770 | other | HFTD Tier 2 | Transmission | 2023-02-07 | 2028-02-07 | Level 3 | F |  | 2028-02-07 | Level 3
125523304 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F |  | 2028-02-17 | Level 3
125524433 | other | HFTD Tier 3 | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F | 2024-03-15 | 2028-02-17 | Level 3 | GO 165 Inspection
125524572 | other | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F |  | 2028-02-09 | Level 3
125524761 | other | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F |  | 2028-02-09 | Level 3
125524795 | other | HFTD Tier 2 | Transmission | 2023-02-08 | 2028-02-08 | Level 3 | F |  | 2028-02-08 | Level 3
125525498 | pole | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F |  | 2028-02-09 | Level 3
125525624 | pole | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F |  | 2028-02-09 | Level 3
125525636 | other | HFTD Tier 2 | Transmission | 2023-02-09 | 2026-02-09 | Level 2 | E | 2024-05-20 | 2024-02-09 | Level 2 | GO 165 Inspection
125525816 | other | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F | 2024-05-21 | 2028-02-09 | Level 3 | GO 165 Inspection
125525961 | other | HFTD Tier 3 | Transmission | 2023-02-09 | 2026-02-09 | Level 2 | E |  | 2026-02-09 | Level 2
125528458 | anchor/guy | Non-HFTD | Transmission | 2023-02-19 | 2028-02-19 | Level 3 | F |  | 2028-02-19 | Level 3
125529488 | other | Non-HFTD | Transmission | 2023-02-18 | 2028-02-18 | Level 3 | F | 2024-08-16 | 2028-02-18 | Level 3 | GO 165 Inspection
125529812 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-20 | 2028-02-20 | Level 3 | F | 2024-03-29 | 2028-02-20 | Level 3 | GO 165 Inspection
125530549 | pole | HFTD Tier 2 | Transmission | 2023-02-20 | 2028-02-20 | Level 3 | F |  | 2028-02-20 | Level 3
125530716 | pole | HFTD Tier 3 | Transmission | 2023-02-20 | 2028-02-20 | Level 3 | F | 2024-04-29 | 2028-02-20 | Level 3 | GO 165 Inspection
125530907 | other | HFTD Tier 3 | Transmission | 2023-02-20 | 2026-02-20 | Level 2 | E |  | 2026-02-20 | Level 2
125531274 | pole | HFTD Tier 2 | Transmission | 2023-02-20 | 2026-02-20 | Level 2 | E | 2024-03-27 | 2026-02-20 | Level 2 | GO 165 Inspection
125532258 | other | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F |  | 2028-02-09 | Level 3
125534205 | other | HFTD Tier 2 | Transmission | 2023-02-09 | 2028-02-09 | Level 3 | F | 2024-05-29 | 2028-02-09 | Level 3 | GO 165 Inspection
125534384 | pole | HFTD Tier 3 | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-03-14 | 2028-02-21 | Level 3 | GO 165 Inspection
125534585 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125534717 | pole | HFTD Tier 2 | Transmission | 2023-02-10 | 2026-02-10 | Level 2 | E | 2023-03-27 | 2026-02-10 | Level 2 | GO 165 Inspection
125535749 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125535759 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125536075 | other | HFTD Tier 2 | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125536415 | pole | HFTD Tier 2 | Transmission | 2023-02-13 | 2024-02-13 | Level 2 | E | 2024-01-30 | 2024-02-13 | Level 2 | Field Safety Reassessment
125536466 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F | 2024-03-20 | 2028-02-13 | Level 3 | GO 165 Inspection
125536519 | other | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125536744 | other | HFTD Tier 2 | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125538585 | other | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125539470 | anchor/guy | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125540074 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-13 | 2026-02-13 | Level 2 | E | 2024-06-27 | 2026-02-13 | Level 2 | GO 165 Inspection
125540221 | anchor/guy | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2024-01-31 | 2026-02-22 | Level 2 | GO 165 Inspection
125540418 | pole | HFTD Tier 3 | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2024-06-06 | 2026-02-22 | Level 2 | GO 165 Inspection
125540699 | other | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125540714 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2024-01-31 | 2026-02-22 | Level 2 | GO 165 Inspection
125540975 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125541104 | other | HFTD Tier 3 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125541946 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125542308 | other | HFTD Tier 2 | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F | 2024-03-15 | 2028-02-22 | Level 3 | GO 165 Inspection
125542572 | other | HFTD Tier 2 | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125543347 | pole | HFTD Tier 3 | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F | 2024-05-13 | 2028-02-22 | Level 3 | GO 165 Inspection
125544921 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125545231 | other | HFTD Tier 3 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125546317 | pole | Non-HFTD | Transmission | 2023-02-23 | 2024-02-23 | Level 2 | E | 2024-10-05 | 2024-02-23 | Level 2 | GO 165 Inspection
125546648 | pole | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E | 2024-01-31 | 2026-02-23 | Level 2 | GO 165 Inspection
125546988 | insulator and brushing | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E | 2024-03-19 | 2026-02-23 | Level 2 | GO 165 Inspection
125551268 | other | HFTD Tier 2 | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2026-02-15 | Level 2
125551442 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125552427 | other | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125553099 | other | HFTD Tier 3 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125553255 | other | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125553448 | insulator and brushing | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2026-02-15 | Level 2
125553520 | pole | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-01-31 | 2026-02-15 | Level 2 | GO 165 Inspection
125553528 | other | Non-HFTD | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125553845 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-16 | 2026-02-16 | Level 2 | E | 2024-05-21 | 2026-02-16 | Level 2 | GO 165 Inspection
125554241 | pole | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 2 | E | 2024-05-23 | 2024-02-14 | Level 2 | GO 165 Inspection
125554637 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-13 | 2028-02-13 | Level 3 | F |  | 2028-02-13 | Level 3
125557234 | pole | Non-HFTD | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125557431 | other | HFTD Tier 2 | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F |  | 2028-02-15 | Level 3
125557567 | other | Non-HFTD | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125557610 | pole | HFTD Tier 3 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125557701 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125557880 | anchor/guy | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125557882 | other | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125561407 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F |  | 2028-02-27 | Level 3
125561415 | crossarm | Non-HFTD | Transmission | 2023-02-21 | 2024-02-21 | Level 2 | E | 2024-12-09 | 2024-02-21 | Level 2 | Field Safety Reassessment
125561598 | pole | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2024-06-08 | 2028-02-27 | Level 3 | GO 165 Inspection
125562006 | other | HFTD Tier 2 | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125562705 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125563090 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125563352 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125563486 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-27 | 2024-02-27 | Level 2 | E | 2023-05-25 | 2024-02-27 | Level 2 | GO 165 Inspection
125564637 | insulator and brushing | Non-HFTD | Transmission | 2023-02-16 | 2026-02-16 | Level 2 | E | 2024-07-12 | 2026-02-16 | Level 2 | GO 165 Inspection
125566306 | other | HFTD Tier 3 | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F |  | 2028-02-15 | Level 3
125566335 | other | HFTD Tier 2 | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F |  | 2028-02-15 | Level 3
125566640 | other | HFTD Tier 2 | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F | 2024-04-01 | 2028-02-17 | Level 3 | GO 165 Inspection
125566733 | other | HFTD Tier 3 | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F | 2024-04-18 | 2028-02-17 | Level 3 | Field Safety Reassessment
125568345 | other | HFTD Tier 2 | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F | 2024-03-21 | 2028-02-17 | Level 3 | GO 165 Inspection
125569626 | other | HFTD Tier 3 | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-05-21 | 2028-02-21 | Level 3 | GO 165 Inspection
125570477 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-24 | 2024-02-24 | Level 2 | E | 2024-12-03 | 2023-08-24 | Level 2 | Field Safety Reassessment
125570655 | pole | Non-HFTD | Transmission | 2023-02-21 | 2024-02-21 | Level 2 | E | 2024-12-09 | 2024-02-21 | Level 2 | Field Safety Reassessment
125570662 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125570698 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125570720 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125570724 | crossarm | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125570796 | other | HFTD Tier 3 | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125572106 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125572603 | other | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E | 2024-07-08 | 2026-02-21 | Level 2 | GO 165 Inspection
125573212 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2024-04-26 | 2028-02-27 | Level 3 | GO 165 Inspection
125574372 | insulator and brushing | Non-HFTD | Transmission | 2023-03-01 | 2026-03-01 | Level 2 | E | 2024-07-29 | 2026-03-01 | Level 2 | GO 165 Inspection
125575050 | anchor/guy | Non-HFTD | Transmission | 2023-03-01 | 2026-03-01 | Level 2 | E | 2024-05-07 | 2026-03-01 | Level 2 | GO 165 Inspection
125575293 | anchor/guy | Non-HFTD | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2024-08-21 | 2028-03-01 | Level 3 | GO 165 Inspection
125575323 | pole | Non-HFTD | Transmission | 2023-03-01 | 2026-03-01 | Level 2 | E |  | 2026-03-01 | Level 2
125575609 | splice | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125577414 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F |  | 2028-02-28 | Level 3
125577945 | pole | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-03-20 | 2028-03-02 | Level 3 | GO 165 Inspection
125577970 | pole | HFTD Tier 2 | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F | 2024-04-01 | 2028-02-16 | Level 3 | GO 165 Inspection
125579254 | pole | HFTD Tier 2 | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F | 2024-03-21 | 2028-02-17 | Level 3 | GO 165 Inspection
125579787 | pole | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125580443 | pole | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-08-21 | 2026-03-02 | Level 2 | GO 165 Inspection
125584361 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F | 2024-05-03 | 2028-02-16 | Level 3 | GO 165 Inspection
125584906 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-16 | 2024-02-16 | Level 2 | E | 2024-02-12 | 2024-02-16 | Level 2 | Field Safety Reassessment
125585138 | crossarm | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125585411 | pole | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E | 2024-05-04 | 2026-03-03 | Level 2 | GO 165 Inspection
125585670 | pole | HFTD Tier 2 | Transmission | 2023-02-21 | 2026-02-21 | Level 3 | F | 2024-04-05 | 2028-02-21 | Level 3 | GO 165 Inspection
125586316 | pole | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E |  | 2026-03-03 | Level 2
125586349 | pole | Non-HFTD | Transmission | 2023-03-03 | 2028-03-03 | Level 3 | F | 2024-05-04 | 2028-03-03 | Level 3 | GO 165 Inspection
125587669 | anchor/guy | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E | 2024-05-03 | 2026-03-03 | Level 2 | GO 165 Inspection
125588251 | anchor/guy | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E | 2024-05-03 | 2026-03-03 | Level 2 | GO 165 Inspection
125589681 | pole | HFTD Tier 2 | Transmission | 2023-03-01 | 2024-03-01 | Level 2 | E | 2024-04-01 | 2024-03-01 | Level 2 | Field Safety Reassessment
125591093 | pole | HFTD Tier 3 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125591287 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-03-26 | 2028-03-02 | Level 3 | GO 165 Inspection
125591376 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2024-02-22 | Level 2 | E | 2024-10-31 | 2026-02-22 | Level 2 | Field Safety Reassessment
125591896 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-06-10 | 2028-03-02 | Level 3 | GO 165 Inspection
125592041 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F | 2023-03-27 | 2028-02-23 | Level 3 | GO 165 Inspection
125592044 | pole | HFTD Tier 3 | Transmission | 2023-02-23 | 2023-08-23 | Level 2 | E | 2023-08-21 | 2023-08-23 | Level 2 | Field Safety Reassessment
125592090 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2023-10-18 | 2026-02-22 | Level 2 | GO 165 Inspection
125592163 | pole | Non-HFTD | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125592250 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-03 | 2024-03-03 | Level 2 | E | 2024-03-03 | 2024-03-03 | Level 2 | Field Safety Reassessment
125592335 | pole | HFTD Tier 2 | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125594810 | pole | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125594838 | other | HFTD Tier 2 | Transmission | 2023-03-06 | 2024-03-06 | Level 2 | E | 2024-05-13 | 2024-03-06 | Level 2 | GO 165 Inspection
125595894 | other | HFTD Tier 2 | Transmission | 2023-03-06 | 2024-03-06 | Level 2 | E | 2024-05-03 | 2023-09-06 | Level 2 | GO 165 Inspection
125596705 | anchor/guy | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-05-01 | 2024-03-06 | Level 2 | GO 165 Inspection
125597099 | other | HFTD Tier 3 | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E | 2024-03-22 | 2026-02-23 | Level 2 | GO 165 Inspection
125597254 | anchor/guy | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-04-30 | 2028-03-06 | Level 3 | GO 165 Inspection
125597778 | other | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-10-14 | 2026-03-06 | Level 2 | GO 165 Inspection
125597785 | pole | HFTD Tier 2 | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-06-03 | 2028-03-06 | Level 3 | GO 165 Inspection
125598234 | other | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125598551 | other | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125598696 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F | 2023-05-18 | 2028-02-23 | Level 3 | GO 165 Inspection
125598860 | other | Non-HFTD | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125598940 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-23 | 2024-02-23 | Level 2 | E | 2024-05-28 | 2024-02-23 | Level 2 | Field Safety Reassessment
125598968 | other | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2024-03-19 | 2028-02-24 | Level 3 | GO 165 Inspection
125599154 | pole | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2024-04-10 | 2028-02-24 | Level 3 | GO 165 Inspection
125600253 | pole | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125601079 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-24 | 2024-02-24 | Level 2 | E | 2024-04-10 | 2024-02-24 | Level 2 | GO 165 Inspection
125601240 | other | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2024-09-23 | 2026-03-07 | Level 2 | GO 165 Inspection
125601535 | other | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2024-03-19 | 2028-02-24 | Level 3 | GO 165 Inspection
125601541 | pole | HFTD Tier 2 | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F | 2024-07-02 | 2028-03-07 | Level 3 | GO 165 Inspection
125603042 | other | Non-HFTD | Transmission | 2023-03-07 | 2024-03-07 | Level 2 | E |  | 2024-03-07 | Level 2
125603290 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125603617 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125604077 | other | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2023-04-21 | 2028-02-24 | Level 3 | GO 165 Inspection
125605100 | other | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2023-04-17 | 2028-02-24 | Level 3 | GO 165 Inspection
125605307 | other | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2023-04-17 | 2028-02-24 | Level 3 | GO 165 Inspection
125605309 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-07-12 | 2028-03-06 | Level 3 | GO 165 Inspection
125605441 | conductor | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125606427 | pole | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2023-04-07 | 2028-02-24 | Level 3 | GO 165 Inspection
125607638 | pole | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2023-06-10 | 2028-02-24 | Level 3 | GO 165 Inspection
125608009 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125609049 | other | HFTD Tier 3 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125609382 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F | 2023-04-10 | 2028-02-24 | Level 3 | GO 165 Inspection
125609533 | pole | Non-HFTD | Transmission | 2023-03-08 | 2024-03-08 | Level 2 | E | 2024-04-16 | 2024-03-08 | Level 2 | GO 165 Inspection
125609609 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E | 2024-03-26 | 2026-03-08 | Level 2 | GO 165 Inspection
125609856 | other | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-10-10 | 2028-03-08 | Level 3 | GO 165 Inspection
125609878 | other | HFTD Tier 3 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-10-30 | 2028-03-08 | Level 3 | Field Safety Reassessment
125611797 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2023-04-11 | 2028-02-27 | Level 3 | GO 165 Inspection
125611910 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F |  | 2028-02-27 | Level 3
125612040 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2023-04-11 | 2028-02-27 | Level 3 | GO 165 Inspection
125612129 | anchor/guy | HFTD Tier 2 | Transmission | 2023-02-27 | 2026-02-27 | Level 2 | E | 2024-05-16 | 2026-02-27 | Level 2 | GO 165 Inspection
125612166 | pole | Non-HFTD | Transmission | 2023-03-08 | 2024-03-08 | Level 2 | E | 2024-11-21 | 2024-03-08 | Level 2 | Field Safety Reassessment
125612216 | splice | HFTD Tier 2 | Transmission | 2023-02-27 | 2024-02-27 | Level 2 | E |  | 2024-02-27 | Level 2
125612385 | pole | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E | 2024-11-01 | 2026-02-21 | Level 2 | GO 165 Inspection
125614753 | other | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125615005 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2023-04-27 | 2028-02-27 | Level 3 | GO 165 Inspection
125615194 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2023-04-27 | 2028-02-27 | Level 3 | GO 165 Inspection
125615268 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2023-04-27 | 2028-02-27 | Level 3 | GO 165 Inspection
125615428 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F |  | 2028-02-27 | Level 3
125615589 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F | 2024-02-27 | 2028-02-27 | Level 3 | GO 165 Inspection
125617205 | other | HFTD Tier 2 | Transmission | 2023-02-27 | 2028-02-27 | Level 3 | F |  | 2028-02-27 | Level 3
125619698 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F |  | 2028-02-28 | Level 3
125619897 | pole | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F |  | 2028-02-28 | Level 3
125620092 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2024-06-10 | 2028-02-28 | Level 3 | GO 165 Inspection
125620136 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2023-04-29 | 2028-02-28 | Level 3 | GO 165 Inspection
125620192 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F |  | 2028-02-28 | Level 3
125620363 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2024-03-19 | 2028-02-28 | Level 3 | GO 165 Inspection
125632644 | other | Non-HFTD | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F |  | 2028-02-14 | Level 3
125632674 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2024-05-17 | 2028-02-28 | Level 3 | GO 165 Inspection
125632830 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125632874 | other | Non-HFTD | Transmission | 2023-02-15 | 2024-02-15 | Level 2 | E | 2024-03-29 | 2024-02-15 | Level 2 | GO 165 Inspection
125632906 | other | Non-HFTD | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F | 2024-09-23 | 2028-02-14 | Level 3 | GO 165 Inspection
125632943 | other | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-03-29 | 2026-02-14 | Level 2 | GO 165 Inspection
125633035 | pole | HFTD Tier 3 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125633037 | pole | HFTD Tier 3 | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125633443 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2023-04-28 | 2028-02-28 | Level 3 | GO 165 Inspection
125633656 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F |  | 2028-02-28 | Level 3
125634313 | other | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-06-24 | 2024-02-14 | Level 2 | GO 165 Inspection
125634527 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 3 | F | 2024-09-23 | 2028-02-14 | Level 3 | GO 165 Inspection
125634581 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125634597 | insulator and brushing | Non-HFTD | Transmission | 2023-02-13 | 2026-02-13 | Level 2 | E |  | 2026-02-13 | Level 2
125634632 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-03-29 | 2026-02-14 | Level 2 | GO 165 Inspection
125634727 | other | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-09-06 | 2028-03-08 | Level 3 | GO 165 Inspection
125634729 | other | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-09-03 | 2028-03-08 | Level 3 | GO 165 Inspection
125634773 | insulator and brushing | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2026-02-15 | Level 2
125634885 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2024-05-16 | 2028-02-28 | Level 3 | GO 165 Inspection
125634931 | other | Non-HFTD | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F |  | 2028-02-15 | Level 3
125634970 | pole | HFTD Tier 2 | Transmission | 2023-02-28 | 2024-02-28 | Level 2 | E | 2024-05-29 | 2024-02-28 | Level 2 | Field Safety Reassessment
125634999 | other | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2026-02-15 | Level 2
125635072 | other | HFTD Tier 2 | Transmission | 2023-02-28 | 2028-02-28 | Level 3 | F | 2024-04-03 | 2028-02-28 | Level 3 | GO 165 Inspection
125635256 | other | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-09-24 | 2026-02-15 | Level 2 | GO 165 Inspection
125635755 | other | Non-HFTD | Transmission | 2023-02-14 | 2024-02-14 | Level 2 | E | 2024-04-11 | 2024-02-14 | Level 2 | GO 165 Inspection
125635757 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125635812 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125636112 | pole | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2026-02-15 | Level 2
125636639 | other | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2024-02-15 | Level 2
125636993 | other | Non-HFTD | Transmission | 2023-03-10 | 2026-03-10 | Level 2 | E |  | 2026-03-10 | Level 2
125637469 | anchor/guy | Non-HFTD | Transmission | 2023-02-13 | 2026-02-13 | Level 2 | E |  | 2026-02-13 | Level 2
125637537 | insulator and brushing | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-09-24 | 2026-02-15 | Level 2 | GO 165 Inspection
125637540 | insulator and brushing | Non-HFTD | Transmission | 2023-02-13 | 2026-02-13 | Level 2 | E |  | 2026-02-13 | Level 2
125637786 | other | Non-HFTD | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F | 2024-10-07 | 2028-02-15 | Level 3 | GO 165 Inspection
125637801 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125637877 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125637900 | splice | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125638151 | other | HFTD Tier 3 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125638222 | other | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F |  | 2028-03-10 | Level 3
125638261 | other | HFTD Tier 3 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2024-05-30 | 2028-03-01 | Level 3 | GO 165 Inspection
125638338 | pole | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2024-05-30 | 2028-03-01 | Level 3 | GO 165 Inspection
125638881 | other | Non-HFTD | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F | 2024-10-22 | 2028-02-15 | Level 3 | GO 165 Inspection
125638935 | other | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125638946 | anchor/guy | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F | 2024-06-15 | 2028-02-22 | Level 3 | GO 165 Inspection
125639129 | other | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2024-06-15 | 2028-03-01 | Level 3 | GO 165 Inspection
125639280 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2023-04-22 | 2028-03-01 | Level 3 | GO 165 Inspection
125639339 | splice | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E | 2023-07-10 | 2026-03-03 | Level 2 | GO 165 Inspection
125639399 | anchor/guy | Non-HFTD | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F | 2024-09-12 | 2028-02-15 | Level 3 | GO 165 Inspection
125639488 | pole | Non-HFTD | Transmission | 2023-03-03 | 2028-03-03 | Level 3 | F | 2023-07-06 | 2028-03-03 | Level 3 | GO 165 Inspection
125639517 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-06-25 | 2026-03-06 | Level 2 | GO 165 Inspection
125639590 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2024-06-28 | 2026-02-22 | Level 2 | GO 165 Inspection
125639636 | other | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125639908 | other | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125639948 | insulator and brushing | Non-HFTD | Transmission | 2023-02-15 | 2024-02-15 | Level 2 | E | 2024-10-04 | 2026-02-15 | Level 2 | GO 165 Inspection
125639980 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2023-04-21 | 2028-03-01 | Level 3 | GO 165 Inspection
125639985 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-01 | 2024-03-01 | Level 2 | E | 2024-04-01 | 2024-03-01 | Level 2 | GO 165 Inspection
125639987 | pole | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2024-04-01 | 2028-03-01 | Level 3 | GO 165 Inspection
125639998 | other | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-15 | 2026-03-06 | Level 2 | GO 165 Inspection
125640197 | other | Non-HFTD | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F | 2024-10-23 | 2028-02-15 | Level 3 | GO 165 Inspection
125640280 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F | 2024-05-16 | 2028-03-01 | Level 3 | GO 165 Inspection
125640444 | other | HFTD Tier 2 | Transmission | 2023-03-01 | 2028-03-01 | Level 3 | F |  | 2028-03-01 | Level 3
125640475 | other | Non-HFTD | Transmission | 2023-02-15 | 2028-02-15 | Level 3 | F | 2024-10-04 | 2028-02-15 | Level 3 | GO 165 Inspection
125640514 | pole | HFTD Tier 3 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-04-01 | 2028-03-02 | Level 3 | GO 165 Inspection
125640571 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F |  | 2028-03-02 | Level 3
125640616 | other | Non-HFTD | Transmission | 2023-03-11 | 2026-03-11 | Level 2 | E | 2024-09-25 | 2026-03-11 | Level 2 | GO 165 Inspection
125640710 | other | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-10-22 | 2026-02-15 | Level 2 | GO 165 Inspection
125640770 | pole | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-09-20 | 2026-02-15 | Level 2 | GO 165 Inspection
125640779 | other | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-10-03 | 2026-02-15 | Level 2 | GO 165 Inspection
125640814 | other | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E | 2024-10-23 | 2026-02-15 | Level 2 | GO 165 Inspection
125640818 | insulator and brushing | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-02-14 | 2026-02-14 | Level 2 | GO 165 Inspection
125640881 | other | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-02-14 | 2026-02-14 | Level 2 | GO 165 Inspection
125640936 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-04-01 | 2028-03-02 | Level 3 | GO 165 Inspection
125641498 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E |  | 2026-03-02 | Level 2
125641554 | anchor/guy | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E |  | 2026-03-02 | Level 2
125641570 | pole | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-04-15 | 2028-03-02 | Level 3 | GO 165 Inspection
125641575 | anchor/guy | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125641621 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125641668 | anchor/guy | Non-HFTD | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E |  | 2026-03-08 | Level 2
125641682 | crossarm | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125641740 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125641767 | other | Non-HFTD | Transmission | 2023-02-21 | 2024-02-21 | Level 2 | E | 2024-05-09 | 2023-05-21 | Level 2 | Field Safety Reassessment
125641822 | pole | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125641853 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125641855 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2024-06-28 | 2026-03-07 | Level 2 | GO 165 Inspection
125641857 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125641947 | insulator and brushing | Non-HFTD | Transmission | 2023-02-15 | 2026-02-15 | Level 2 | E |  | 2026-02-15 | Level 2
125641951 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125642000 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-11-13 | 2028-02-21 | Level 3 | Field Safety Reassessment
125642008 | other | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125642027 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125642230 | pole | Non-HFTD | Transmission | 2023-02-22 | 2023-05-22 | Level 2 | E | 2024-01-30 | 2023-05-22 | Level 2 | Field Safety Reassessment
125642291 | pole | Non-HFTD | Transmission | 2023-02-22 | 2024-02-22 | Level 2 | E | 2024-10-31 | 2024-02-22 | Level 2 | Field Safety Reassessment
125642312 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125642384 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2024-06-24 | 2026-03-07 | Level 2 | GO 165 Inspection
125642417 | splice | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-11 | 2026-03-06 | Level 2 | GO 165 Inspection
125642489 | insulator and brushing | Non-HFTD | Transmission | 2023-02-17 | 2026-02-17 | Level 2 | E | 2024-07-17 | 2026-02-17 | Level 2 | GO 165 Inspection
125642533 | splice | Non-HFTD | Transmission | 2023-02-17 | 2026-02-17 | Level 2 | E | 2024-07-16 | 2026-02-17 | Level 2 | GO 165 Inspection
125642577 | pole | HFTD Tier 2 | Transmission | 2023-02-17 | 2024-02-17 | Level 2 | E | 2024-03-18 | 2024-02-17 | Level 2 | GO 165 Inspection
125642646 | insulator and brushing | Non-HFTD | Transmission | 2023-02-16 | 2026-02-16 | Level 2 | E |  | 2026-02-16 | Level 2
125642670 | insulator and brushing | Non-HFTD | Transmission | 2023-02-16 | 2026-02-16 | Level 2 | E |  | 2026-02-16 | Level 2
125642704 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125642760 | anchor/guy | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E |  | 2026-02-14 | Level 2
125642767 | pole | Non-HFTD | Transmission | 2023-02-22 | 2024-02-22 | Level 2 | E | 2024-11-04 | 2024-02-22 | Level 2 | Field Safety Reassessment
125643302 | other | HFTD Tier 2 | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F | 2024-05-07 | 2028-03-13 | Level 3 | GO 165 Inspection
125644154 | other | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E |  | 2026-03-13 | Level 2
125645151 | anchor/guy | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E |  | 2026-03-13 | Level 2
125645338 | pole | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2023-10-31 | 2026-03-13 | Level 2 | GO 165 Inspection
125645435 | other | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2024-10-26 | 2026-03-13 | Level 2 | GO 165 Inspection
125645718 | other | Non-HFTD | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F | 2024-04-09 | 2028-03-13 | Level 3 | GO 165 Inspection
125645816 | splice | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E |  | 2026-03-13 | Level 2
125645944 | anchor/guy | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-10-15 | 2026-03-02 | Level 2 | GO 165 Inspection
125645952 | insulator and brushing | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2024-10-10 | 2026-03-13 | Level 2 | GO 165 Inspection
125646983 | other | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2024-09-25 | 2026-03-13 | Level 2 | GO 165 Inspection
125647432 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F |  | 2028-03-02 | Level 3
125647592 | other | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2023-03-16 | 2025-03-03 | Level 2 | Standards change
125647719 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125647839 | pole | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-06-14 | 2028-03-02 | Level 3 | GO 165 Inspection
125647929 | anchor/guy | Non-HFTD | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-09-26 | 2028-03-02 | Level 3 | GO 165 Inspection
125647948 | other | Non-HFTD | Transmission | 2023-03-03 | 2028-03-03 | Level 3 | F |  | 2028-03-03 | Level 3
125647980 | pole | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E | 2024-10-17 | 2026-03-03 | Level 2 | GO 165 Inspection
125647991 | pole | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-09-27 | 2026-03-02 | Level 2 | GO 165 Inspection
125648079 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125648173 | insulator and brushing | Non-HFTD | Transmission | 2022-03-03 | 2023-03-03 | Level 2 | E | 2024-06-24 | 2025-03-03 | Level 2 | GO 165 Inspection
125648208 | insulator and brushing | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-10-17 | 2026-03-02 | Level 2 | GO 165 Inspection
125648250 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125648280 | other | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E |  | 2026-03-03 | Level 2
125648284 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125648299 | insulator and brushing | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E |  | 2026-03-02 | Level 2
125648302 | other | HFTD Tier 2 | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-06-01 | 2028-03-02 | Level 3 | GO 165 Inspection
125648333 | anchor/guy | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-12-30 | 2026-03-02 | Level 2 | Field Safety Reassessment
125648460 | anchor/guy | Non-HFTD | Transmission | 2023-02-14 | 2028-02-14 | Level 3 | F | 2024-05-15 | 2028-02-14 | Level 3 | GO 165 Inspection
125648530 | other | Non-HFTD | Transmission | 2023-03-02 | 2028-03-02 | Level 3 | F | 2024-10-14 | 2028-03-02 | Level 3 | GO 165 Inspection
125648534 | other | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-10-14 | 2026-03-02 | Level 2 | GO 165 Inspection
125648538 | other | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-06-15 | 2026-03-02 | Level 2 | GO 165 Inspection
125648539 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125649264 | pole | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E | 2024-08-28 | 2026-03-14 | Level 2 | GO 165 Inspection
125649598 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125649908 | insulator and brushing | HFTD Tier 2 | Transmission | 2022-03-03 | 2024-03-03 | Level 3 | F | 2024-02-14 | 2027-03-03 | Level 3 | Standards change
125653154 | pole | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E | 2024-12-09 | 2026-03-14 | Level 2 | GO 165 Inspection
125654023 | other | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125654119 | other | HFTD Tier 2 | Transmission | 2023-03-14 | 2024-03-14 | Level 2 | E |  | 2024-03-14 | Level 2
125654336 | other | Non-HFTD | Transmission | 2023-03-14 | 2024-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125654550 | other | HFTD Tier 2 | Transmission | 2023-03-03 | 2028-03-03 | Level 3 | F |  | 2028-03-03 | Level 3
125654801 | anchor/guy | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-16 | 2026-03-06 | Level 2 | GO 165 Inspection
125654952 | switch | HFTD Tier 2 | Transmission | 2023-03-03 | 2024-03-03 | Level 2 | E | 2024-02-26 | 2024-03-03 | Level 2 | Field Safety Reassessment
125655117 | pole | Non-HFTD | Transmission | 2023-03-02 | 2026-03-02 | Level 2 | E | 2024-10-14 | 2026-03-02 | Level 2 | GO 165 Inspection
125655356 | pole | Non-HFTD | Transmission | 2023-03-03 | 2026-03-03 | Level 2 | E |  | 2026-03-03 | Level 2
125655705 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125655706 | other | HFTD Tier 2 | Transmission | 2023-03-03 | 2028-03-03 | Level 3 | F |  | 2028-03-03 | Level 3
125655708 | other | HFTD Tier 2 | Transmission | 2023-03-03 | 2028-03-03 | Level 3 | F |  | 2028-03-03 | Level 3
125655862 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-07-12 | 2028-03-06 | Level 3 | GO 165 Inspection
125655997 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F | 2024-10-30 | 2028-03-14 | Level 3 | GO 165 Inspection
125656011 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-16 | 2026-03-06 | Level 2 | GO 165 Inspection
125657364 | other | HFTD Tier 3 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2024-05-31 | 2028-03-15 | Level 3 | GO 165 Inspection
125657413 | other | HFTD Tier 3 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2024-05-31 | 2028-03-15 | Level 3 | GO 165 Inspection
125658698 | other | HFTD Tier 2 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2024-03-12 | 2028-03-15 | Level 3 | Field Safety Reassessment
125660793 | other | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125661871 | other | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-05-14 | 2026-03-06 | Level 2 | GO 165 Inspection
125662260 | other | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125662317 | other | Non-HFTD | Transmission | 2023-03-15 | 2024-03-15 | Level 2 | E |  | 2026-03-15 | Level 2
125662641 | anchor/guy | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E |  | 2026-03-15 | Level 2
125662809 | pole | HFTD Tier 2 | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-04-01 | 2028-03-06 | Level 3 | GO 165 Inspection
125662882 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125663128 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F | 2024-04-04 | 2028-03-10 | Level 3 | GO 165 Inspection
125663337 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-06 | 2024-03-06 | Level 2 | E | 2024-02-16 | 2024-03-06 | Level 2 | Field Safety Reassessment
125663410 | other | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F | 2024-03-27 | 2028-03-10 | Level 3 | GO 165 Inspection
125663463 | splice | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-11 | 2026-03-06 | Level 2 | GO 165 Inspection
125663467 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F | 2024-03-29 | 2028-03-10 | Level 3 | GO 165 Inspection
125663499 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125663533 | other | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F | 2024-03-27 | 2028-03-10 | Level 3 | GO 165 Inspection
125663660 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125663868 | splice | Non-HFTD | Transmission | 2023-02-17 | 2026-02-17 | Level 2 | E | 2024-07-11 | 2026-02-17 | Level 2 | GO 165 Inspection
125665031 | anchor/guy | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F |  | 2028-03-16 | Level 3
125667296 | pole | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125667363 | anchor/guy | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F |  | 2028-03-16 | Level 3
125667439 | anchor/guy | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125667592 | insulator and brushing | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F | 2024-07-17 | 2028-03-16 | Level 3 | GO 165 Inspection
125668650 | other | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F | 2024-07-01 | 2028-03-16 | Level 3 | GO 165 Inspection
125668894 | anchor/guy | Non-HFTD | Transmission | 2023-02-14 | 2026-02-14 | Level 2 | E | 2024-06-15 | 2026-02-14 | Level 2 | GO 165 Inspection
125669263 | pole | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125669461 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125669480 | pole | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125669560 | splice | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E | 2024-07-12 | 2026-02-21 | Level 2 | GO 165 Inspection
125669583 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669615 | conductor | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669781 | insulator and brushing | Non-HFTD | Transmission | 2023-03-16 | 2024-03-16 | Level 2 | E |  | 2024-03-16 | Level 2
125669815 | insulator and brushing | Non-HFTD | Transmission | 2023-02-16 | 2026-02-16 | Level 2 | E |  | 2026-02-16 | Level 2
125669817 | other | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125669873 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669907 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669943 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669954 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669963 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125669997 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125670047 | pole | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125670097 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125670180 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2024-02-22 | Level 2 | E | 2024-12-05 | 2024-02-22 | Level 2 | Field Safety Reassessment
125670217 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125670271 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125670335 | other | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125670357 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125672810 | insulator and brushing | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125672910 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2024-07-16 | 2026-03-07 | Level 2 | GO 165 Inspection
125673000 | pole | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E | 2024-07-16 | 2026-02-21 | Level 2 | GO 165 Inspection
125673217 | pole | Non-HFTD | Transmission | 2023-02-17 | 2026-02-17 | Level 2 | E | 2024-07-17 | 2026-02-17 | Level 2 | GO 165 Inspection
125673309 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125673405 | pole | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125673420 | other | Non-HFTD | Transmission | 2023-02-17 | 2028-02-17 | Level 3 | F | 2024-07-16 | 2028-02-17 | Level 3 | GO 165 Inspection
125673429 | pole | Non-HFTD | Transmission | 2023-02-17 | 2026-02-17 | Level 2 | E |  | 2026-02-17 | Level 2
125673468 | insulator and brushing | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E | 2024-04-03 | 2026-03-16 | Level 2 | GO 165 Inspection
125673545 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125673546 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-07-15 | 2028-02-21 | Level 3 | GO 165 Inspection
125673573 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125673625 | pole | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125673757 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125673859 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125673980 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125674063 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125674071 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125674092 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125674145 | other | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125674149 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125674219 | pole | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125674542 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125674632 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125674658 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125674695 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125674912 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125675043 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125675392 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-06-27 | 2028-02-21 | Level 3 | GO 165 Inspection
125675510 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125675684 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125675778 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125675862 | insulator and brushing | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F | 2024-08-19 | 2028-02-16 | Level 3 | GO 165 Inspection
125676123 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125676882 | splice | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125677239 | other | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125677476 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125677498 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125677711 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125677900 | insulator and brushing | Non-HFTD | Transmission | 2023-03-17 | 2026-03-17 | Level 2 | E | 2024-10-25 | 2026-03-17 | Level 2 | GO 165 Inspection
125678051 | other | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125678076 | pole | Non-HFTD | Transmission | 2023-02-22 | 2024-02-22 | Level 2 | E | 2024-10-31 | 2024-02-22 | Level 2 | Field Safety Reassessment
125678094 | insulator and brushing | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E | 2024-06-26 | 2026-03-15 | Level 2 | GO 165 Inspection
125678145 | splice | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125678212 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125678632 | pole | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125679105 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125679182 | insulator and brushing | Non-HFTD | Transmission | 2023-03-17 | 2026-03-17 | Level 2 | E | 2024-05-13 | 2026-03-17 | Level 2 | GO 165 Inspection
125679528 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125679608 | other | Non-HFTD | Transmission | 2023-02-16 | 2028-02-16 | Level 3 | F |  | 2028-02-16 | Level 3
125679738 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125679950 | other | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125679951 | crossarm | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125679985 | other | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125680214 | anchor/guy | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F | 2024-05-01 | 2028-03-16 | Level 3 | GO 165 Inspection
125680430 | other | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F | 2024-04-03 | 2028-03-16 | Level 3 | GO 165 Inspection
125681626 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681828 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681838 | splice | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E | 2024-07-12 | 2026-02-21 | Level 2 | GO 165 Inspection
125681850 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681867 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681882 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681883 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125681892 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-06-27 | 2028-02-21 | Level 3 | GO 165 Inspection
125681893 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681930 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681950 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125681962 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-07-08 | 2028-02-21 | Level 3 | GO 165 Inspection
125681971 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125681981 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682021 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682046 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682084 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682098 | other | HFTD Tier 2 | Transmission | 2023-03-18 | 2028-03-18 | Level 3 | F | 2024-05-21 | 2028-03-18 | Level 3 | GO 165 Inspection
125682120 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682121 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682130 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125682144 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682172 | pole | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125682174 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682176 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682216 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682243 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F | 2024-07-08 | 2028-02-21 | Level 3 | GO 165 Inspection
125682281 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125682284 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682291 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682322 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682324 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682339 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682448 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682492 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682518 | other | HFTD Tier 2 | Transmission | 2023-03-17 | 2028-03-17 | Level 3 | F |  | 2028-03-17 | Level 3
125682564 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125682626 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125682650 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2023-10-18 | 2026-02-22 | Level 2 | GO 165 Inspection
125682698 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682723 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125682727 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682769 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F | 2023-11-13 | 2028-02-22 | Level 3 | Field Safety Reassessment
125682852 | crossarm | HFTD Tier 2 | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E | 2023-05-01 | 2026-03-08 | Level 2 | GO 165 Inspection
125682900 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682902 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682936 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682937 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125682992 | anchor/guy | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125683019 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125683147 | other | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-03-14 | 2028-03-08 | Level 3 | GO 165 Inspection
125683217 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125683284 | pole | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125683315 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125683319 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125683389 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125683651 | pole | Non-HFTD | Transmission | 2023-03-18 | 2024-03-18 | Level 2 | E | 2024-04-29 | 2024-03-18 | Level 2 | Field Safety Reassessment
125683704 | other | Non-HFTD | Transmission | 2023-03-18 | 2028-03-18 | Level 3 | F |  | 2028-03-18 | Level 3
125683707 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125683710 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125683760 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125686660 | pole | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125687920 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125688918 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-05-30 | 2028-03-20 | Level 3 | GO 165 Inspection
125689178 | insulator and brushing | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E | 2024-10-24 | 2026-03-20 | Level 2 | GO 165 Inspection
125689684 | other | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E |  | 2026-03-20 | Level 2
125690081 | other | HFTD Tier 2 | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-04-29 | 2028-03-20 | Level 3 | GO 165 Inspection
125690420 | anchor/guy | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E |  | 2026-03-20 | Level 2
125690424 | pole | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E | 2024-05-28 | 2026-03-20 | Level 2 | GO 165 Inspection
125690429 | other | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E | 2024-10-30 | 2026-03-20 | Level 2 | GO 165 Inspection
125690635 | pole | Non-HFTD | Transmission | 2023-03-20 | 2024-03-20 | Level 2 | E | 2024-05-28 | 2023-09-20 | Level 2 | GO 165 Inspection
125695046 | other | Non-HFTD | Transmission | 2023-02-21 | 2028-02-21 | Level 3 | F |  | 2028-02-21 | Level 3
125696857 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2023-10-17 | 2026-02-22 | Level 2 | GO 165 Inspection
125697225 | other | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F | 2024-05-01 | 2028-03-16 | Level 3 | GO 165 Inspection
125697552 | anchor/guy | Non-HFTD | Transmission | 2023-03-17 | 2028-03-17 | Level 3 | F |  | 2028-03-17 | Level 3
125697594 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F | 2023-10-17 | 2028-02-22 | Level 3 | GO 165 Inspection
125697622 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125697668 | other | HFTD Tier 3 | Transmission | 2023-03-17 | 2028-03-17 | Level 3 | F | 2024-03-27 | 2028-03-17 | Level 3 | GO 165 Inspection
125697972 | insulator and brushing | Non-HFTD | Transmission | 2023-03-17 | 2026-03-17 | Level 2 | E | 2024-05-09 | 2026-03-17 | Level 2 | GO 165 Inspection
125698265 | pole | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E |  | 2026-03-20 | Level 2
125698268 | pole | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E | 2024-09-04 | 2026-03-20 | Level 2 | GO 165 Inspection
125700937 | other | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F | 2024-07-16 | 2028-03-21 | Level 3 | GO 165 Inspection
125701731 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E | 2024-07-15 | 2026-03-21 | Level 2 | GO 165 Inspection
125702103 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E | 2024-07-15 | 2026-03-21 | Level 2 | GO 165 Inspection
125705110 | other | Non-HFTD | Transmission | 2023-03-16 | 2028-03-16 | Level 3 | F | 2024-04-20 | 2028-03-16 | Level 3 | GO 165 Inspection
125705534 | other | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-03-14 | 2028-03-08 | Level 3 | GO 165 Inspection
125705694 | pole | HFTD Tier 2 | Transmission | 2023-03-20 | 2024-03-20 | Level 2 | E | 2024-03-10 | 2024-03-20 | Level 2 | Field Safety Reassessment
125705892 | other | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125705963 | other | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-03-14 | 2028-03-08 | Level 3 | GO 165 Inspection
125706041 | anchor/guy | HFTD Tier 3 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-03-15 | 2028-03-08 | Level 3 | GO 165 Inspection
125706153 | other | HFTD Tier 3 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125706185 | insulator and brushing | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125706246 | other | HFTD Tier 2 | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125706294 | anchor/guy | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125706298 | insulator and brushing | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125706443 | other | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125706518 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2024-07-10 | 2026-02-22 | Level 2 | GO 165 Inspection
125706541 | other | HFTD Tier 3 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-03-13 | 2028-03-08 | Level 3 | GO 165 Inspection
125706672 | other | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-03-14 | 2028-03-08 | Level 3 | GO 165 Inspection
125706717 | insulator and brushing | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125707888 | other | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E | 2024-03-22 | 2026-03-22 | Level 2 | GO 165 Inspection
125708208 | anchor/guy | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E |  | 2026-03-16 | Level 2
125709520 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125709718 | insulator and brushing | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E |  | 2026-02-21 | Level 2
125712186 | other | Non-HFTD | Transmission | 2023-03-22 | 2024-03-22 | Level 2 | E | 2024-04-02 | 2024-03-22 | Level 2 | GO 165 Inspection
125717066 | insulator and brushing | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125717105 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E | 2023-10-17 | 2026-02-22 | Level 2 | GO 165 Inspection
125718437 | pole | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-04-02 | 2026-03-23 | Level 2 | GO 165 Inspection
125720016 | anchor/guy | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-12-07 | 2026-03-23 | Level 2 | GO 165 Inspection
125720292 | pole | HFTD Tier 2 | Transmission | 2023-03-23 | 2024-03-23 | Level 2 | E | 2024-05-03 | 2024-03-23 | Level 2 | GO 165 Inspection
125720988 | other | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-05-22 | 2026-03-23 | Level 2 | GO 165 Inspection
125721229 | other | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2024-07-03 | 2026-03-13 | Level 2 | GO 165 Inspection
125721493 | other | HFTD Tier 2 | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F |  | 2028-03-13 | Level 3
125721519 | pole | Non-HFTD | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F | 2024-02-08 | 2028-03-13 | Level 3 | GO 165 Inspection
125721665 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-13 | 2024-03-13 | Level 2 | E | 2024-02-16 | 2024-03-13 | Level 2 | Field Safety Reassessment
125721880 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F |  | 2028-03-13 | Level 3
125722008 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125722028 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125722064 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125722253 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125722254 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125722256 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125723921 | other | HFTD Tier 2 | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F | 2023-05-22 | 2028-03-23 | Level 3 | GO 165 Inspection
125723990 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125724103 | other | Non-HFTD | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125724381 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125724437 | other | HFTD Tier 2 | Transmission | 2023-03-23 | 2024-03-23 | Level 2 | E | 2024-04-19 | 2024-03-23 | Level 2 | Field Safety Reassessment
125724551 | anchor/guy | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
125724565 | other | HFTD Tier 2 | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F |  | 2028-03-13 | Level 3
125724851 | other | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F |  | 2028-03-10 | Level 3
125724860 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125724891 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125724895 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-08-21 | 2028-03-06 | Level 3 | GO 165 Inspection
125724962 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125725106 | pole | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F | 2024-04-08 | 2028-03-23 | Level 3 | GO 165 Inspection
125725300 | other | Non-HFTD | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125725368 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125725598 | pole | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-05-14 | 2028-03-24 | Level 3 | GO 165 Inspection
125725619 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-11 | 2026-03-06 | Level 2 | GO 165 Inspection
125725945 | other | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E | 2024-06-27 | 2026-03-14 | Level 2 | GO 165 Inspection
125725958 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125725963 | pole | Non-HFTD | Transmission | 2023-02-24 | 2026-02-24 | Level 2 | E |  | 2026-02-24 | Level 2
125726016 | anchor/guy | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2024-07-03 | 2026-03-13 | Level 2 | GO 165 Inspection
125726235 | other | Non-HFTD | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125726254 | pole | Non-HFTD | Transmission | 2023-03-06 | 2024-03-06 | Level 2 | E | 2024-07-15 | 2024-03-06 | Level 2 | GO 165 Inspection
125726430 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-10 | 2026-03-06 | Level 2 | GO 165 Inspection
125726469 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-08-26 | 2028-03-06 | Level 3 | GO 165 Inspection
125726666 | other | HFTD Tier 2 | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125726722 | insulator and brushing | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E | 2024-06-26 | 2026-03-15 | Level 2 | GO 165 Inspection
125726746 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F | 2024-06-28 | 2028-03-07 | Level 3 | GO 165 Inspection
125726791 | other | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2024-06-17 | 2028-03-15 | Level 3 | GO 165 Inspection
125727005 | other | HFTD Tier 2 | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F | 2024-04-18 | 2028-03-14 | Level 3 | GO 165 Inspection
125727014 | pole | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-05-14 | 2028-03-24 | Level 3 | GO 165 Inspection
125727029 | other | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E | 2024-06-06 | 2026-03-24 | Level 2 | GO 165 Inspection
125727195 | pole | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-05-14 | 2028-03-24 | Level 3 | GO 165 Inspection
125727210 | other | HFTD Tier 2 | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-05-23 | 2028-03-24 | Level 3 | GO 165 Inspection
125727230 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-07-15 | 2028-03-06 | Level 3 | GO 165 Inspection
125727390 | insulator and brushing | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125727581 | pole | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-05-14 | 2028-03-24 | Level 3 | GO 165 Inspection
125727678 | splice | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125727780 | pole | Non-HFTD | Transmission | 2023-03-07 | 2024-03-07 | Level 2 | E | 2024-09-27 | 2024-03-07 | Level 2 | Field Safety Reassessment
125728027 | pole | Non-HFTD | Transmission | 2023-03-23 | 2024-03-23 | Level 2 | E | 2024-11-09 | 2024-03-23 | Level 2 | Field Safety Reassessment
125728407 | insulator and brushing | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E | 2024-09-05 | 2026-03-22 | Level 2 | GO 165 Inspection
125728461 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125728543 | other | HFTD Tier 3 | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125728602 | other | HFTD Tier 2 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2023-04-02 | 2028-03-15 | Level 3 | GO 165 Inspection
125728734 | other | Non-HFTD | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F |  | 2028-03-10 | Level 3
125728782 | other | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-09 | 2026-03-06 | Level 2 | GO 165 Inspection
125728857 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125728912 | other | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F |  | 2028-03-10 | Level 3
125728919 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F | 2024-03-13 | 2028-03-10 | Level 3 | GO 165 Inspection
125729284 | pole | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E |  | 2026-02-23 | Level 2
125729504 | pole | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E |  | 2026-02-23 | Level 2
125729595 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125729749 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125729824 | other | Non-HFTD | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125729932 | splice | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E |  | 2026-02-23 | Level 2
125729998 | other | Non-HFTD | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125730042 | other | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F | 2023-06-25 | 2028-03-21 | Level 3 | GO 165 Inspection
125730059 | other | Non-HFTD | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F | 2024-06-27 | 2028-03-13 | Level 3 | GO 165 Inspection
125730120 | other | Non-HFTD | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125730124 | other | Non-HFTD | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125730156 | other | Non-HFTD | Transmission | 2023-03-13 | 2026-03-13 | Level 2 | E | 2024-07-03 | 2026-03-13 | Level 2 | GO 165 Inspection
125730176 | other | HFTD Tier 2 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125730187 | other | HFTD Tier 2 | Transmission | 2023-03-13 | 2028-03-13 | Level 3 | F | 2024-03-14 | 2028-03-13 | Level 3 | GO 165 Inspection
125730813 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125730984 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125730986 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125731015 | other | HFTD Tier 2 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125731020 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731022 | insulator and brushing | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E |  | 2026-02-23 | Level 2
125731026 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731052 | insulator and brushing | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E |  | 2026-02-23 | Level 2
125731120 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125731246 | insulator and brushing | Non-HFTD | Transmission | 2023-02-23 | 2026-02-23 | Level 2 | E |  | 2026-02-23 | Level 2
125731248 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731266 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731299 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F | 2024-06-21 | 2028-03-07 | Level 3 | GO 165 Inspection
125731346 | other | Non-HFTD | Transmission | 2023-02-24 | 2028-02-24 | Level 3 | F |  | 2028-02-24 | Level 3
125731361 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731366 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125731451 | insulator and brushing | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
125731459 | switch | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-10-08 | 2026-03-23 | Level 2 | Field Safety Reassessment
125731468 | pole | HFTD Tier 2 | Transmission | 2023-03-25 | 2024-03-25 | Level 2 | E | 2024-04-03 | 2024-03-25 | Level 2 | GO 165 Inspection
125731487 | other | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125731524 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-07-15 | 2028-03-06 | Level 3 | GO 165 Inspection
125731714 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F | 2023-11-06 | 2028-03-07 | Level 3 | GO 165 Inspection
125731750 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731757 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731764 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-11 | 2026-03-06 | Level 2 | GO 165 Inspection
125731793 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2023-11-04 | 2026-03-07 | Level 2 | GO 165 Inspection
125731903 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125731946 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731965 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125731984 | other | HFTD Tier 3 | Transmission | 2023-03-25 | 2028-03-25 | Level 3 | F | 2024-03-06 | 2028-03-25 | Level 3 | GO 165 Inspection
125732052 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2023-11-04 | 2026-03-07 | Level 2 | GO 165 Inspection
125732072 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2024-06-25 | 2026-03-07 | Level 2 | GO 165 Inspection
125732136 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125732137 | splice | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125732175 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125732191 | pole | Non-HFTD | Transmission | 2023-02-22 | 2026-02-22 | Level 2 | E |  | 2026-02-22 | Level 2
125732193 | other | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125732194 | pole | Non-HFTD | Transmission | 2023-02-22 | 2028-02-22 | Level 3 | F |  | 2028-02-22 | Level 3
125732411 | other | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125732604 | other | Non-HFTD | Transmission | 2023-03-25 | 2028-03-25 | Level 3 | F | 2024-08-15 | 2028-03-25 | Level 3 | GO 165 Inspection
125732606 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125732621 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125732666 | pole | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125732717 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125732762 | other | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E | 2023-11-06 | 2026-03-07 | Level 2 | GO 165 Inspection
125732774 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125732835 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-15 | 2026-03-06 | Level 2 | GO 165 Inspection
125732885 | insulator and brushing | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-30 | 2026-03-06 | Level 2 | GO 165 Inspection
125732893 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-06-24 | 2026-03-06 | Level 2 | GO 165 Inspection
125732898 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125732918 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125732937 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125733061 | other | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125733105 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F |  | 2028-03-06 | Level 3
125733870 | other | HFTD Tier 3 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F | 2024-02-27 | 2028-03-26 | Level 3 | GO 165 Inspection
125733959 | other | HFTD Tier 2 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F |  | 2028-03-26 | Level 3
125734142 | other | HFTD Tier 2 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F |  | 2028-03-26 | Level 3
125734295 | pole | Non-HFTD | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F | 2024-10-16 | 2028-03-26 | Level 3 | GO 165 Inspection
125734434 | pole | HFTD Tier 2 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F |  | 2028-03-26 | Level 3
125734550 | pole | HFTD Tier 2 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F | 2024-05-28 | 2028-03-26 | Level 3 | GO 165 Inspection
125734596 | other | HFTD Tier 2 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F | 2024-03-27 | 2028-03-26 | Level 3 | GO 165 Inspection
125734671 | pole | HFTD Tier 2 | Transmission | 2023-03-26 | 2028-03-26 | Level 3 | F | 2024-03-13 | 2028-03-26 | Level 3 | GO 165 Inspection
125735585 | pole | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E |  | 2026-03-24 | Level 2
125737111 | other | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-03-05 | 2028-03-27 | Level 3 | GO 165 Inspection
125737222 | other | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-04-01 | 2028-03-27 | Level 3 | GO 165 Inspection
125737405 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
125737658 | other | HFTD Tier 3 | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125737686 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-27 | 2024-03-27 | Level 2 | E |  | 2024-03-27 | Level 2
125737758 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-27 | 2024-03-27 | Level 2 | E | 2024-03-26 | 2024-03-27 | Level 2 | GO 165 Inspection
125738436 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125738817 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125739106 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-09-11 | 2028-03-27 | Level 3 | GO 165 Inspection
125740082 | anchor/guy | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125740319 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125740459 | anchor/guy | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-10-07 | 2028-03-27 | Level 3 | GO 165 Inspection
125740500 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-04-19 | 2028-03-27 | Level 3 | GO 165 Inspection
125740735 | pole | HFTD Tier 2 | Transmission | 2023-03-27 | 2024-03-27 | Level 2 | E | 2024-03-06 | 2024-03-27 | Level 2 | Field Safety Reassessment
125742226 | splice | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E | 2024-02-18 | 2026-03-27 | Level 2 | Field Safety Reassessment
125742227 | pole | HFTD Tier 2 | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F | 2024-04-19 | 2028-03-14 | Level 3 | GO 165 Inspection
125742435 | other | HFTD Tier 2 | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2024-04-25 | 2028-03-15 | Level 3 | GO 165 Inspection
125742829 | other | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-23 | Level 3 | F |  | 2028-02-23 | Level 3
125742959 | pole | Non-HFTD | Transmission | 2023-03-06 | 2024-03-06 | Level 2 | E | 2024-07-11 | 2024-03-06 | Level 2 | GO 165 Inspection
125744374 | pole | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-10-22 | 2026-03-28 | Level 2 | GO 165 Inspection
125744875 | pole | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2023-07-03 | 2026-03-28 | Level 2 | GO 165 Inspection
125747992 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F | 2024-10-17 | 2028-03-22 | Level 3 | GO 165 Inspection
125748066 | other | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2023-04-02 | 2028-03-27 | Level 3 | GO 165 Inspection
125748140 | other | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2023-04-03 | 2028-03-27 | Level 3 | GO 165 Inspection
125748281 | pole | HFTD Tier 2 | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F | 2024-06-17 | 2028-03-23 | Level 3 | GO 165 Inspection
125748363 | anchor/guy | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F | 2024-10-17 | 2028-03-22 | Level 3 | GO 165 Inspection
125748365 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125748502 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125748514 | other | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E | 2024-11-19 | 2026-03-14 | Level 2 | GO 165 Inspection
125748518 | insulator and brushing | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E | 2024-11-19 | 2026-03-14 | Level 2 | GO 165 Inspection
125748650 | other | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E | 2024-07-02 | 2026-03-15 | Level 2 | GO 165 Inspection
125748769 | insulator and brushing | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E | 2024-07-02 | 2026-03-15 | Level 2 | GO 165 Inspection
125748771 | anchor/guy | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125753213 | pole | Non-HFTD | Transmission | 2023-03-17 | 2026-03-17 | Level 2 | E |  | 2026-03-17 | Level 2
125753702 | pole | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E |  | 2026-03-29 | Level 2
125753869 | insulator and brushing | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E |  | 2026-03-29 | Level 2
125753915 | other | Non-HFTD | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F | 2024-09-24 | 2028-03-29 | Level 3 | GO 165 Inspection
125755018 | pole | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-06-04 | 2028-03-27 | Level 3 | GO 165 Inspection
125756035 | pole | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125756073 | other | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E | 2024-11-19 | 2026-03-15 | Level 2 | GO 165 Inspection
125756369 | pole | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125756549 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-11-14 | 2028-03-24 | Level 3 | GO 165 Inspection
125756663 | other | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125756681 | other | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125756721 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-10-18 | 2028-03-24 | Level 3 | GO 165 Inspection
125756777 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F | 2023-05-22 | 2028-03-29 | Level 3 | GO 165 Inspection
125757090 | anchor/guy | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E |  | 2026-03-22 | Level 2
125757681 | other | Non-HFTD | Transmission | 2023-03-17 | 2028-03-17 | Level 3 | F | 2024-04-09 | 2028-03-17 | Level 3 | GO 165 Inspection
125757872 | anchor/guy | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E | 2024-08-08 | 2026-03-24 | Level 2 | GO 165 Inspection
125759426 | anchor/guy | HFTD Tier 2 | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-03-21 | 2028-03-20 | Level 3 | GO 165 Inspection
125760006 | other | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2024-05-30 | 2026-03-30 | Level 2 | GO 165 Inspection
125761116 | pole | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E |  | 2026-03-30 | Level 2
125761220 | pole | HFTD Tier 2 | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2024-04-29 | 2026-03-30 | Level 2 | GO 165 Inspection
125764312 | other | Non-HFTD | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F | 2024-09-17 | 2028-03-30 | Level 3 | GO 165 Inspection
125764497 | pole | HFTD Tier 2 | Transmission | 2023-03-30 | 2024-03-30 | Level 2 | E | 2024-03-11 | 2024-03-30 | Level 2 | Field Safety Reassessment
125764889 | pole | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125764957 | other | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125764975 | pole | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125765174 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-05-01 | 2028-03-20 | Level 3 | GO 165 Inspection
125765362 | pole | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-09-09 | 2028-03-28 | Level 3 | GO 165 Inspection
125765421 | anchor/guy | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E | 2024-10-17 | 2026-03-22 | Level 2 | GO 165 Inspection
125765428 | anchor/guy | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-04-22 | 2028-03-20 | Level 3 | GO 165 Inspection
125765587 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-11-14 | 2028-03-24 | Level 3 | GO 165 Inspection
125765673 | other | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E | 2024-11-19 | 2026-03-14 | Level 2 | GO 165 Inspection
125765677 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-07-16 | 2028-03-28 | Level 3 | GO 165 Inspection
125765679 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
125765835 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125765869 | insulator and brushing | Non-HFTD | Transmission | 2023-03-15 | 2026-03-15 | Level 2 | E | 2024-07-01 | 2026-03-15 | Level 2 | GO 165 Inspection
125766022 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-04-04 | 2028-03-20 | Level 3 | GO 165 Inspection
125766056 | other | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E | 2024-04-22 | 2026-03-20 | Level 2 | GO 165 Inspection
125766126 | pole | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E | 2024-04-10 | 2026-03-20 | Level 2 | GO 165 Inspection
125766157 | splice | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-15 | 2026-03-06 | Level 2 | GO 165 Inspection
125766226 | splice | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E | 2024-07-15 | 2026-03-06 | Level 2 | GO 165 Inspection
125766327 | anchor/guy | HFTD Tier 3 | Transmission | 2023-03-17 | 2026-03-17 | Level 2 | E | 2024-03-26 | 2026-03-17 | Level 2 | GO 165 Inspection
125768087 | insulator and brushing | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125768182 | anchor/guy | Non-HFTD | Transmission | 2023-03-07 | 2026-03-07 | Level 2 | E |  | 2026-03-07 | Level 2
125768210 | pole | HFTD Tier 2 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125768283 | anchor/guy | Non-HFTD | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E |  | 2026-03-08 | Level 2
125768287 | pole | Non-HFTD | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E |  | 2026-03-08 | Level 2
125768290 | other | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125768475 | insulator and brushing | Non-HFTD | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E |  | 2026-03-08 | Level 2
125768617 | other | Non-HFTD | Transmission | 2023-03-07 | 2028-03-07 | Level 3 | F |  | 2028-03-07 | Level 3
125768633 | anchor/guy | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125768693 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125768695 | anchor/guy | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125768908 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125768948 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125769167 | other | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F | 2024-08-13 | 2028-03-08 | Level 3 | GO 165 Inspection
125769749 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125769765 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125769946 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125770081 | pole | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-05-11 | 2028-03-27 | Level 3 | GO 165 Inspection
125770397 | other | HFTD Tier 2 | Transmission | 2023-03-31 | 2028-03-31 | Level 3 | F | 2024-05-19 | 2028-03-31 | Level 3 | GO 165 Inspection
125770515 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125770551 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
125770673 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125770736 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125770880 | other | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125771219 | other | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125771255 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125771262 | anchor/guy | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125771661 | crossarm | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125772120 | pole | Non-HFTD | Transmission | 2023-03-10 | 2026-03-10 | Level 2 | E |  | 2026-03-10 | Level 2
125772149 | pole | Non-HFTD | Transmission | 2023-03-20 | 2024-03-20 | Level 2 | E | 2024-06-24 | 2024-03-20 | Level 2 | GO 165 Inspection
125772336 | other | Non-HFTD | Transmission | 2023-03-08 | 2026-03-08 | Level 2 | E |  | 2026-03-08 | Level 2
125772802 | pole | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125772969 | insulator and brushing | Non-HFTD | Transmission | 2023-03-31 | 2026-03-31 | Level 2 | E |  | 2026-03-31 | Level 2
125772987 | pole | HFTD Tier 2 | Transmission | 2023-03-31 | 2024-03-31 | Level 2 | E | 2024-05-28 | 2024-03-31 | Level 2 | GO 165 Inspection
125773051 | other | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125773102 | other | HFTD Tier 3 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F | 2024-04-24 | 2028-03-30 | Level 3 | GO 165 Inspection
125773193 | other | HFTD Tier 3 | Transmission | 2023-03-31 | 2026-03-31 | Level 2 | E |  | 2026-03-31 | Level 2
125773292 | pole | HFTD Tier 2 | Transmission | 2023-03-31 | 2028-03-31 | Level 3 | F | 2024-03-22 | 2028-03-31 | Level 3 | GO 165 Inspection
125773448 | other | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125774102 | other | Non-HFTD | Transmission | 2023-03-31 | 2028-03-31 | Level 3 | F | 2024-08-01 | 2028-03-31 | Level 3 | GO 165 Inspection
125775000 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125775074 | anchor/guy | Non-HFTD | Transmission | 2023-03-31 | 2026-03-31 | Level 2 | E | 2024-08-20 | 2026-03-31 | Level 2 | GO 165 Inspection
125775208 | other | Non-HFTD | Transmission | 2023-03-10 | 2028-03-10 | Level 3 | F |  | 2028-03-10 | Level 3
125775241 | other | HFTD Tier 3 | Transmission | 2023-03-31 | 2028-03-30 | Level 3 | F | 2024-03-12 | 2028-03-30 | Level 3 | GO 165 Inspection
125776380 | insulator and brushing | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E |  | 2026-03-30 | Level 2
125776447 | anchor/guy | Non-HFTD | Transmission | 2023-03-10 | 2026-03-10 | Level 2 | E |  | 2026-03-10 | Level 2
125776538 | other | Non-HFTD | Transmission | 2023-03-09 | 2028-03-09 | Level 3 | F |  | 2028-03-09 | Level 3
125776737 | pole | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E | 2024-09-03 | 2026-03-16 | Level 2 | GO 165 Inspection
125776738 | other | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125776779 | insulator and brushing | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E |  | 2026-03-14 | Level 2
125776785 | other | Non-HFTD | Transmission | 2023-03-06 | 2028-03-06 | Level 3 | F | 2024-07-11 | 2028-03-06 | Level 3 | GO 165 Inspection
125776811 | insulator and brushing | Non-HFTD | Transmission | 2023-03-09 | 2026-03-09 | Level 2 | E |  | 2026-03-09 | Level 2
125776829 | other | Non-HFTD | Transmission | 2023-04-01 | 2028-04-01 | Level 3 | F | 2024-08-16 | 2028-04-01 | Level 3 | GO 165 Inspection
125776914 | splice | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
125776930 | crossarm | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E |  | 2026-03-14 | Level 2
125776931 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125776941 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125776951 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125776958 | splice | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2023-07-25 | 2026-03-23 | Level 2 | GO 165 Inspection
125777019 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125777036 | pole | HFTD Tier 2 | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F | 2024-04-24 | 2028-03-14 | Level 3 | GO 165 Inspection
125777053 | anchor/guy | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125777054 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125777090 | pole | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125777128 | other | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E |  | 2026-03-14 | Level 2
125777132 | anchor/guy | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125777214 | other | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125777225 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125777253 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125777295 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125777414 | anchor/guy | Non-HFTD | Transmission | 2023-03-08 | 2028-03-08 | Level 3 | F |  | 2028-03-08 | Level 3
125777507 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125777511 | anchor/guy | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F | 2023-11-07 | 2028-03-14 | Level 3 | GO 165 Inspection
125777563 | other | Non-HFTD | Transmission | 2023-04-01 | 2028-04-01 | Level 3 | F | 2024-08-16 | 2028-04-01 | Level 3 | GO 165 Inspection
125777585 | other | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125777607 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125777731 | other | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125777764 | pole | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125777946 | pole | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125778042 | other | HFTD Tier 2 | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F | 2024-05-18 | 2028-03-14 | Level 3 | GO 165 Inspection
125778230 | pole | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125778247 | conductor | Non-HFTD | Transmission | 2023-03-14 | 2026-03-14 | Level 2 | E |  | 2026-03-14 | Level 2
125778334 | pole | Non-HFTD | Transmission | 2023-03-21 | 2024-03-21 | Level 2 | E | 2024-12-10 | 2024-03-21 | Level 2 | Field Safety Reassessment
125778426 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125778471 | other | Non-HFTD | Transmission | 2023-03-17 | 2028-03-17 | Level 3 | F | 2024-08-26 | 2028-03-17 | Level 3 | GO 165 Inspection
125778575 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125778618 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125778626 | other | Non-HFTD | Transmission | 2023-04-01 | 2028-04-01 | Level 3 | F |  | 2028-04-01 | Level 3
125778680 | pole | HFTD Tier 2 | Transmission | 2023-04-01 | 2028-04-01 | Level 3 | F | 2024-05-07 | 2028-04-01 | Level 3 | GO 165 Inspection
125778737 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125778738 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125778829 | pole | HFTD Tier 2 | Transmission | 2023-04-01 | 2028-04-01 | Level 3 | F | 2024-02-14 | 2028-04-01 | Level 3 | GO 165 Inspection
125778860 | pole | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125778900 | other | Non-HFTD | Transmission | 2023-03-14 | 2028-03-14 | Level 3 | F |  | 2028-03-14 | Level 3
125779985 | pole | HFTD Tier 2 | Transmission | 2023-04-02 | 2024-04-02 | Level 2 | E | 2024-03-14 | 2024-04-02 | Level 2 | Field Safety Reassessment
125780012 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-02 | 2028-04-02 | Level 3 | F | 2024-03-27 | 2028-04-02 | Level 3 | GO 165 Inspection
125780227 | other | HFTD Tier 3 | Transmission | 2023-04-02 | 2028-04-02 | Level 3 | F | 2024-05-31 | 2028-04-02 | Level 3 | GO 165 Inspection
125780349 | other | HFTD Tier 2 | Transmission | 2023-04-02 | 2028-04-02 | Level 3 | F |  | 2028-04-02 | Level 3
125780513 | other | HFTD Tier 3 | Transmission | 2023-04-02 | 2028-04-02 | Level 3 | F | 2024-05-20 | 2028-04-02 | Level 3 | GO 165 Inspection
125780568 | other | HFTD Tier 3 | Transmission | 2023-04-02 | 2028-04-02 | Level 3 | F |  | 2028-04-02 | Level 3
125780731 | other | HFTD Tier 2 | Transmission | 2023-04-02 | 2028-04-02 | Level 3 | F | 2024-04-01 | 2028-04-02 | Level 3 | GO 165 Inspection
125781571 | other | Non-HFTD | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F | 2024-10-25 | 2028-03-29 | Level 3 | GO 165 Inspection
125782693 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F | 2024-04-19 | 2028-03-30 | Level 3 | GO 165 Inspection
125782731 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F |  | 2028-04-03 | Level 3
125783149 | other | Non-HFTD | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-05-22 | 2028-04-03 | Level 3 | GO 165 Inspection
125783355 | anchor/guy | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2023-06-15 | 2026-03-30 | Level 2 | GO 165 Inspection
125784071 | other | Non-HFTD | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-05-22 | 2028-04-03 | Level 3 | GO 165 Inspection
125785093 | pole | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
125785531 | other | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125785848 | other | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125785880 | other | Non-HFTD | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F | 2024-03-27 | 2028-03-30 | Level 3 | GO 165 Inspection
125786061 | other | Non-HFTD | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F | 2024-06-27 | 2028-03-29 | Level 3 | GO 165 Inspection
125786172 | other | HFTD Tier 3 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-04-29 | 2028-04-03 | Level 3 | GO 165 Inspection
125786404 | anchor/guy | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E | 2024-07-19 | 2026-03-29 | Level 2 | GO 165 Inspection
125786475 | insulator and brushing | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E | 2024-07-19 | 2026-03-29 | Level 2 | GO 165 Inspection
125786822 | conductor | HFTD Tier 3 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-05-21 | 2028-04-03 | Level 3 | GO 165 Inspection
125787702 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-31 | 2028-03-31 | Level 3 | F | 2024-05-10 | 2028-03-31 | Level 3 | GO 165 Inspection
125790590 | other | HFTD Tier 2 | Transmission | 2023-03-31 | 2026-03-31 | Level 2 | E | 2024-03-22 | 2026-03-31 | Level 2 | GO 165 Inspection
125792551 | pole | Non-HFTD | Transmission | 2023-04-04 | 2026-04-04 | Level 2 | E | 2024-10-22 | 2026-04-04 | Level 2 | GO 165 Inspection
125794084 | insulator and brushing | Non-HFTD | Transmission | 2023-04-03 | 2026-04-03 | Level 2 | E | 2024-03-28 | 2026-04-03 | Level 2 | GO 165 Inspection
125795396 | other | HFTD Tier 3 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F | 2024-03-08 | 2028-04-04 | Level 3 | GO 165 Inspection
125796050 | other | Non-HFTD | Transmission | 2023-03-31 | 2028-03-31 | Level 3 | F | 2024-05-13 | 2028-03-31 | Level 3 | GO 165 Inspection
125797284 | pole | Non-HFTD | Transmission | 2023-03-31 | 2026-03-31 | Level 2 | E | 2024-04-02 | 2026-03-31 | Level 2 | GO 165 Inspection
125798448 | insulator and brushing | Non-HFTD | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-04-02 | 2028-04-03 | Level 3 | GO 165 Inspection
125798486 | other | HFTD Tier 2 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-05-10 | 2028-04-03 | Level 3 | GO 165 Inspection
125799216 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-31 | 2028-03-31 | Level 3 | F | 2024-03-20 | 2028-03-31 | Level 3 | GO 165 Inspection
125799383 | pole | Non-HFTD | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125799770 | anchor/guy | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F |  | 2028-03-15 | Level 3
125799783 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125800555 | other | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125801036 | insulator and brushing | Non-HFTD | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125801207 | anchor/guy | Non-HFTD | Transmission | 2023-03-15 | 2028-03-15 | Level 3 | F | 2023-11-08 | 2028-03-15 | Level 3 | GO 165 Inspection
125801452 | pole | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E |  | 2026-04-05 | Level 2
125801538 | other | Non-HFTD | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125801958 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-05 | 2024-04-05 | Level 2 | E | 2024-05-14 | 2024-04-05 | Level 2 | GO 165 Inspection
125801970 | pole | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E |  | 2026-04-05 | Level 2
125802583 | other | HFTD Tier 2 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125802816 | pole | HFTD Tier 2 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-05-02 | 2028-04-05 | Level 3 | GO 165 Inspection
125803354 | pole | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E |  | 2026-04-05 | Level 2
125803356 | pole | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E | 2024-10-02 | 2026-04-05 | Level 2 | GO 165 Inspection
125803365 | pole | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E | 2024-08-05 | 2026-04-05 | Level 2 | GO 165 Inspection
125803824 | insulator and brushing | Non-HFTD | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125803996 | pole | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E |  | 2026-04-05 | Level 2
125805016 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125805178 | splice | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E |  | 2026-04-05 | Level 2
125805182 | other | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E |  | 2026-04-05 | Level 2
125806605 | pole | HFTD Tier 3 | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125807647 | other | Non-HFTD | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-03-18 | 2028-04-05 | Level 3 | GO 165 Inspection
125808431 | other | Non-HFTD | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E | 2024-05-22 | 2026-04-05 | Level 2 | GO 165 Inspection
125808471 | splice | Non-HFTD | Transmission | 2023-03-17 | 2026-03-17 | Level 2 | E |  | 2026-03-17 | Level 2
125808477 | insulator and brushing | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125808479 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2023-11-04 | 2028-03-27 | Level 3 | GO 165 Inspection
125808660 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125808745 | pole | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E | 2023-11-13 | 2026-03-27 | Level 2 | GO 165 Inspection
125809581 | pole | HFTD Tier 2 | Transmission | 2023-03-30 | 2024-03-30 | Level 2 | E | 2024-05-02 | 2024-03-30 | Level 2 | GO 165 Inspection
125810663 | pole | HFTD Tier 2 | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E | 2024-04-30 | 2026-04-06 | Level 2 | GO 165 Inspection
125810700 | pole | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125811387 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125812322 | insulator and brushing | Non-HFTD | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-05-29 | 2028-04-05 | Level 3 | GO 165 Inspection
125812549 | other | HFTD Tier 3 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-04-25 | 2028-04-06 | Level 3 | GO 165 Inspection
125813179 | pole | Non-HFTD | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E |  | 2026-04-06 | Level 2
125813378 | pole | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-06-15 | 2028-04-06 | Level 3 | GO 165 Inspection
125813805 | other | HFTD Tier 3 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F |  | 2028-04-06 | Level 3
125814000 | pole | HFTD Tier 3 | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125814559 | insulator and brushing | Non-HFTD | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E | 2024-04-19 | 2026-04-06 | Level 2 | GO 165 Inspection
125816321 | pole | HFTD Tier 2 | Transmission | 2023-04-03 | 2024-04-03 | Level 2 | E | 2024-05-10 | 2024-04-03 | Level 2 | GO 165 Inspection
125816434 | splice | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
125816437 | crossarm | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
125816462 | other | Non-HFTD | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E | 2024-06-27 | 2026-04-06 | Level 2 | GO 165 Inspection
125816774 | other | HFTD Tier 2 | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-04-16 | 2028-03-24 | Level 3 | GO 165 Inspection
125820062 | other | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-05-09 | 2028-03-27 | Level 3 | GO 165 Inspection
125820450 | other | HFTD Tier 2 | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F | 2023-06-01 | 2028-03-23 | Level 3 | GO 165 Inspection
125820555 | pole | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-06-06 | 2028-03-27 | Level 3 | GO 165 Inspection
125821297 | other | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125821879 | pole | HFTD Tier 2 | Transmission | 2023-03-23 | 2024-03-23 | Level 2 | E | 2024-05-14 | 2024-03-23 | Level 2 | Field Safety Reassessment
125822106 | other | HFTD Tier 2 | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F | 2023-05-15 | 2028-03-23 | Level 3 | GO 165 Inspection
125822135 | other | Non-HFTD | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-04-26 | 2028-04-06 | Level 3 | GO 165 Inspection
125822670 | other | HFTD Tier 3 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-01-30 | 2028-04-07 | Level 3 | GO 165 Inspection
125823614 | other | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-05-07 | 2028-04-05 | Level 3 | GO 165 Inspection
125823791 | other | HFTD Tier 2 | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F | 2024-04-12 | 2028-03-23 | Level 3 | GO 165 Inspection
125824651 | pole | Non-HFTD | Transmission | 2023-04-07 | 2024-04-07 | Level 2 | E | 2024-09-16 | 2024-04-07 | Level 2 | GO 165 Inspection
125825241 | other | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125826371 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-08 | 2028-04-07 | Level 3 | GO 165 Inspection
125826423 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-07-16 | 2028-03-28 | Level 3 | GO 165 Inspection
125826600 | anchor/guy | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E |  | 2026-03-20 | Level 2
125826628 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-07-16 | 2028-03-28 | Level 3 | GO 165 Inspection
125826671 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-07-16 | 2028-03-28 | Level 3 | GO 165 Inspection
125826737 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125826739 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2026-04-07 | Level 2 | E | 2024-04-30 | 2026-04-07 | Level 2 | GO 165 Inspection
125826863 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-11-20 | 2028-03-28 | Level 3 | GO 165 Inspection
125827064 | pole | Non-HFTD | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125829358 | other | HFTD Tier 3 | Transmission | 2023-04-08 | 2028-04-08 | Level 3 | F |  | 2028-04-08 | Level 3
125829645 | other | HFTD Tier 2 | Transmission | 2023-04-08 | 2024-04-08 | Level 2 | E | 2024-06-02 | 2024-04-08 | Level 2 | GO 165 Inspection
125830195 | other | Non-HFTD | Transmission | 2023-04-08 | 2028-04-08 | Level 3 | F | 2024-10-04 | 2028-04-08 | Level 3 | GO 165 Inspection
125844700 | insulator and brushing | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-03-04 | 2028-03-20 | Level 3 | GO 165 Inspection
125844976 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125845939 | pole | Non-HFTD | Transmission | 2023-03-06 | 2026-03-06 | Level 2 | E |  | 2026-03-06 | Level 2
125846094 | insulator and brushing | Non-HFTD | Transmission | 2023-04-10 | 2026-04-10 | Level 2 | E | 2024-08-14 | 2026-04-10 | Level 2 | GO 165 Inspection
125847029 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125847949 | anchor/guy | Non-HFTD | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-04-02 | 2028-04-10 | Level 3 | GO 165 Inspection
125848499 | anchor/guy | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-08-26 | 2026-03-28 | Level 2 | GO 165 Inspection
125849084 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125850005 | conductor | Non-HFTD | Transmission | 2023-04-10 | 2026-04-10 | Level 2 | E | 2024-10-07 | 2026-04-10 | Level 2 | GO 165 Inspection
125850380 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125851047 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-04-30 | 2028-04-10 | Level 3 | GO 165 Inspection
125851073 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-04-30 | 2028-04-10 | Level 3 | GO 165 Inspection
125852344 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-04-26 | 2028-04-10 | Level 3 | GO 165 Inspection
125852782 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
125852998 | anchor/guy | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125854304 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-03 | 2026-04-03 | Level 2 | E | 2024-03-15 | 2026-04-03 | Level 2 | GO 165 Inspection
125854360 | insulator and brushing | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125854596 | insulator and brushing | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-02-13 | 2028-03-20 | Level 3 | GO 165 Inspection
125855445 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-11 | 2024-04-11 | Level 2 | E | 2024-05-07 | 2024-04-11 | Level 2 | GO 165 Inspection
125855693 | anchor/guy | HFTD Tier 3 | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-05-07 | 2028-03-24 | Level 3 | GO 165 Inspection
125856246 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125856413 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
125856519 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-06-05 | 2028-04-11 | Level 3 | GO 165 Inspection
125856627 | other | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-06-17 | 2028-04-11 | Level 3 | GO 165 Inspection
125857741 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-06-17 | 2028-04-11 | Level 3 | GO 165 Inspection
125857901 | other | Non-HFTD | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-08-27 | 2028-04-11 | Level 3 | GO 165 Inspection
125859356 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2024-04-11 | Level 2 | E | 2024-06-04 | 2024-04-11 | Level 2 | GO 165 Inspection
125860957 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125861141 | anchor/guy | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
125861321 | other | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125861553 | other | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125861748 | pole | Non-HFTD | Transmission | 2023-04-11 | 2026-04-11 | Level 2 | E | 2024-05-13 | 2026-04-11 | Level 2 | GO 165 Inspection
125862762 | other | Non-HFTD | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-09-10 | 2028-04-11 | Level 3 | GO 165 Inspection
125863441 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-05-10 | 2028-04-11 | Level 3 | GO 165 Inspection
125863613 | other | HFTD Tier 2 | Transmission | 2023-04-11 | 2026-04-11 | Level 2 | E | 2024-04-26 | 2026-04-11 | Level 2 | GO 165 Inspection
125863614 | other | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-04-26 | 2028-04-11 | Level 3 | GO 165 Inspection
125864395 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F |  | 2028-03-20 | Level 3
125864399 | other | Non-HFTD | Transmission | 2023-03-20 | 2026-03-20 | Level 2 | E |  | 2024-03-20 | Level 2
125865838 | pole | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-04-22 | 2028-03-27 | Level 3 | GO 165 Inspection
125866230 | pole | HFTD Tier 3 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-05-03 | 2028-03-27 | Level 3 | GO 165 Inspection
125866272 | other | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-03-19 | 2028-04-06 | Level 3 | GO 165 Inspection
125866419 | other | HFTD Tier 2 | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-04-03 | 2028-03-28 | Level 3 | GO 165 Inspection
125866479 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125866553 | other | HFTD Tier 2 | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F | 2024-05-08 | 2028-03-28 | Level 3 | GO 165 Inspection
125866626 | other | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-04-20 | 2028-03-27 | Level 3 | GO 165 Inspection
125866928 | pole | HFTD Tier 2 | Transmission | 2023-03-27 | 2028-03-27 | Level 2 | E | 2024-05-11 | 2026-03-27 | Level 2 | GO 165 Inspection
125867033 | pole | HFTD Tier 2 | Transmission | 2023-03-24 | 2024-03-24 | Level 2 | E | 2024-10-30 | 2023-09-24 | Level 2 | Field Safety Reassessment
125867038 | pole | HFTD Tier 2 | Transmission | 2023-03-24 | 2024-03-24 | Level 2 | E | 2024-10-30 | 2023-09-24 | Level 2 | Field Safety Reassessment
125867217 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-29 | 2028-04-07 | Level 3 | GO 165 Inspection
125868665 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125869778 | other | Non-HFTD | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F |  | 2028-04-11 | Level 3
125870927 | other | Non-HFTD | Transmission | 2023-04-12 | 2026-04-12 | Level 2 | E |  | 2026-04-12 | Level 2
125871038 | pole | HFTD Tier 3 | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
125871622 | other | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125873045 | pole | Non-HFTD | Transmission | 2023-04-12 | 2026-04-12 | Level 2 | E |  | 2026-04-12 | Level 2
125873135 | pole | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125873494 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125873608 | other | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125873721 | other | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125874070 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125874316 | pole | Non-HFTD | Transmission | 2023-04-12 | 2026-04-12 | Level 2 | E |  | 2026-04-12 | Level 2
125875874 | other | Non-HFTD | Transmission | 2023-03-20 | 2028-03-20 | Level 3 | F | 2024-02-29 | 2028-03-20 | Level 3 | GO 165 Inspection
125876735 | pole | Non-HFTD | Transmission | 2023-03-21 | 2028-03-21 | Level 3 | F |  | 2028-03-21 | Level 3
125876824 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125877261 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125879551 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-04-26 | 2028-04-12 | Level 3 | GO 165 Inspection
125881692 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
125883050 | other | HFTD Tier 3 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-03-27 | 2028-04-12 | Level 3 | GO 165 Inspection
125883299 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125883696 | pole | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F | 2024-04-26 | 2028-03-29 | Level 3 | GO 165 Inspection
125883996 | other | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125884962 | anchor/guy | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E |  | 2026-03-30 | Level 2
125884984 | other | HFTD Tier 2 | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
125885400 | pole | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125892771 | anchor/guy | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
125892966 | insulator and brushing | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2023-11-04 | 2028-03-27 | Level 3 | GO 165 Inspection
125893084 | insulator and brushing | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125893189 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
125894329 | insulator and brushing | Non-HFTD | Transmission | 2023-03-30 | 2024-03-30 | Level 2 | E | 2024-08-23 | 2024-03-30 | Level 2 | GO 165 Inspection
125895146 | pole | Non-HFTD | Transmission | 2023-03-21 | 2024-03-21 | Level 2 | E | 2024-08-20 | 2024-03-21 | Level 2 | Field Safety Reassessment
125895289 | pole | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125896586 | insulator and brushing | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2024-08-23 | 2026-03-30 | Level 2 | GO 165 Inspection
125896710 | insulator and brushing | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2024-08-23 | 2026-03-30 | Level 2 | GO 165 Inspection
125896812 | other | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-05-07 | 2028-04-13 | Level 3 | GO 165 Inspection
125896813 | other | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2024-08-23 | 2024-03-30 | Level 2 | GO 165 Inspection
125896886 | other | Non-HFTD | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-06-04 | 2028-04-13 | Level 3 | GO 165 Inspection
125900330 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
125900417 | other | HFTD Tier 3 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-05-20 | 2028-04-13 | Level 3 | GO 165 Inspection
125901075 | other | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-06-10 | 2028-04-13 | Level 3 | GO 165 Inspection
125903526 | other | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
125903892 | other | HFTD Tier 3 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125903977 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125904009 | other | HFTD Tier 2 | Transmission | 2023-04-03 | 2024-04-03 | Level 2 | E | 2024-04-30 | 2024-04-03 | Level 2 | GO 165 Inspection
125904044 | pole | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125904222 | pole | HFTD Tier 2 | Transmission | 2023-04-03 | 2024-04-03 | Level 2 | E | 2024-06-11 | 2024-04-03 | Level 2 | Field Safety Reassessment
125904254 | pole | HFTD Tier 2 | Transmission | 2023-04-06 | 2024-04-06 | Level 2 | E | 2024-03-29 | 2024-04-06 | Level 2 | Field Safety Reassessment
125904660 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-29 | 2024-03-29 | Level 2 | E | 2024-05-02 | 2024-03-29 | Level 2 | GO 165 Inspection
125904857 | other | HFTD Tier 2 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-05-03 | 2028-04-05 | Level 3 | GO 165 Inspection
125905610 | other | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125905653 | pole | HFTD Tier 2 | Transmission | 2023-03-29 | 2024-03-29 | Level 2 | E | 2024-03-04 | 2024-03-29 | Level 2 | Field Safety Reassessment
125905672 | other | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-04-06 | 2028-04-06 | Level 3 | GO 165 Inspection
125908280 | other | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-04-25 | 2028-04-06 | Level 3 | GO 165 Inspection
125908330 | other | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125908337 | other | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-03-19 | 2028-04-05 | Level 3 | GO 165 Inspection
125908353 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125908435 | pole | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125908439 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125909017 | other | HFTD Tier 3 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F | 2024-03-20 | 2028-04-04 | Level 3 | GO 165 Inspection
125909346 | other | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-03-26 | 2028-04-05 | Level 3 | GO 165 Inspection
125909398 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125910298 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125910405 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125911102 | pole | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F | 2024-04-24 | 2028-03-30 | Level 3 | GO 165 Inspection
125911120 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125911272 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125912039 | other | Non-HFTD | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125912269 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125913179 | other | HFTD Tier 3 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
125913244 | other | HFTD Tier 2 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125913252 | other | HFTD Tier 2 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
125913310 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-04-11 | 2028-04-10 | Level 3 | GO 165 Inspection
125913348 | other | HFTD Tier 2 | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
125914398 | other | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F |  | 2028-04-05 | Level 3
125914875 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125915741 | anchor/guy | Non-HFTD | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F | 2024-11-20 | 2028-04-14 | Level 3 | GO 165 Inspection
125915742 | other | Non-HFTD | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F | 2024-11-20 | 2028-04-14 | Level 3 | GO 165 Inspection
125916159 | pole | HFTD Tier 3 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F | 2024-03-20 | 2028-04-04 | Level 3 | GO 165 Inspection
125916188 | other | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-03-20 | 2028-04-06 | Level 3 | GO 165 Inspection
125917339 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125919096 | pole | HFTD Tier 3 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-05-21 | 2028-04-03 | Level 3 | GO 165 Inspection
125919103 | pole | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-04-04 | 2028-04-07 | Level 3 | GO 165 Inspection
125919602 | other | HFTD Tier 2 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
125919788 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F |  | 2028-04-04 | Level 3
125920227 | pole | HFTD Tier 2 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F | 2024-05-17 | 2028-04-14 | Level 3 | GO 165 Inspection
125922263 | other | HFTD Tier 2 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F |  | 2028-04-03 | Level 3
125922296 | other | HFTD Tier 3 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F | 2024-03-20 | 2028-04-04 | Level 3 | GO 165 Inspection
125923090 | other | HFTD Tier 2 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F | 2024-04-26 | 2028-04-14 | Level 3 | GO 165 Inspection
125923200 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F | 2024-03-18 | 2028-04-04 | Level 3 | GO 165 Inspection
125923274 | other | HFTD Tier 2 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-07-01 | 2028-04-03 | Level 3 | GO 165 Inspection
125923644 | pole | HFTD Tier 2 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F |  | 2028-04-03 | Level 3
125923889 | splice | HFTD Tier 2 | Transmission | 2023-04-03 | 2026-04-03 | Level 2 | E |  | 2026-04-03 | Level 2
125924091 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125926740 | pole | HFTD Tier 3 | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E | 2023-06-06 | 2026-04-06 | Level 2 | GO 165 Inspection
125926762 | other | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-06-13 | 2028-04-06 | Level 3 | GO 165 Inspection
125926860 | pole | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-03-18 | 2028-04-06 | Level 3 | GO 165 Inspection
125926881 | other | HFTD Tier 3 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F | 2024-05-16 | 2028-04-03 | Level 3 | GO 165 Inspection
125926908 | other | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F |  | 2028-04-06 | Level 3
125927002 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125927390 | other | HFTD Tier 2 | Transmission | 2023-04-03 | 2028-04-03 | Level 3 | F |  | 2028-04-03 | Level 3
125927520 | other | HFTD Tier 2 | Transmission | 2023-04-04 | 2028-04-04 | Level 3 | F | 2024-06-04 | 2028-04-04 | Level 3 | GO 165 Inspection
125928013 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F |  | 2028-04-06 | Level 3
125928156 | pole | HFTD Tier 2 | Transmission | 2023-04-15 | 2028-04-15 | Level 3 | F | 2024-05-17 | 2028-04-15 | Level 3 | GO 165 Inspection
125928202 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-29 | 2028-04-07 | Level 3 | GO 165 Inspection
125928414 | pole | HFTD Tier 2 | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E | 2024-05-01 | 2026-04-06 | Level 2 | GO 165 Inspection
125928591 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125930325 | other | Non-HFTD | Transmission | 2023-04-14 | 2026-04-14 | Level 2 | E |  | 2026-04-14 | Level 2
125932179 | other | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E | 2024-07-09 | 2026-03-24 | Level 2 | GO 165 Inspection
125932933 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125932935 | anchor/guy | Non-HFTD | Transmission | 2023-04-04 | 2026-04-04 | Level 2 | E |  | 2026-04-04 | Level 2
125933244 | switch | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E | 2023-09-14 | 2026-03-22 | Level 2 | Field Safety Reassessment
125933413 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-17 | 2024-04-17 | Level 2 | E | 2024-04-03 | 2024-04-17 | Level 2 | Field Safety Reassessment
125934355 | other | HFTD Tier 2 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-05-20 | 2028-04-17 | Level 3 | GO 165 Inspection
125934428 | insulator and brushing | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E | 2024-09-05 | 2026-03-22 | Level 2 | GO 165 Inspection
125934455 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-05-17 | 2028-04-17 | Level 3 | GO 165 Inspection
125934551 | other | HFTD Tier 3 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-02-01 | 2028-04-17 | Level 3 | GO 165 Inspection
125935255 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E | 2024-04-24 | 2026-04-17 | Level 2 | GO 165 Inspection
125935539 | pole | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125935779 | splice | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-10-14 | 2026-03-23 | Level 2 | Field Safety Reassessment
125935851 | pole | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125936363 | anchor/guy | Non-HFTD | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-09-28 | 2028-04-17 | Level 3 | GO 165 Inspection
125936432 | anchor/guy | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E | 2024-10-03 | 2026-04-17 | Level 2 | GO 165 Inspection
125936961 | pole | Non-HFTD | Transmission | 2023-03-21 | 2026-03-21 | Level 2 | E |  | 2026-03-21 | Level 2
125937563 | insulator and brushing | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125937824 | conductor | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E |  | 2026-04-17 | Level 2
125938479 | pole | HFTD Tier 2 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F |  | 2028-04-17 | Level 3
125940532 | insulator and brushing | Non-HFTD | Transmission | 2023-04-17 | 2024-04-17 | Level 2 | E | 2024-05-29 | 2024-04-17 | Level 2 | GO 165 Inspection
125940643 | other | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E | 2024-04-22 | 2026-04-17 | Level 2 | GO 165 Inspection
125940728 | other | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E | 2024-05-29 | 2026-04-17 | Level 2 | GO 165 Inspection
125941087 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-02-13 | 2028-04-18 | Level 3 | GO 165 Inspection
125941531 | insulator and brushing | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E | 2024-05-29 | 2026-04-17 | Level 2 | GO 165 Inspection
125942274 | other | Non-HFTD | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-05-29 | 2028-04-17 | Level 3 | GO 165 Inspection
125943502 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F |  | 2028-04-18 | Level 3
125943573 | pole | Non-HFTD | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E |  | 2026-04-18 | Level 2
125943656 | other | Non-HFTD | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E |  | 2026-04-18 | Level 2
125943878 | pole | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E | 2024-05-31 | 2026-04-17 | Level 2 | GO 165 Inspection
125943948 | pole | HFTD Tier 2 | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E | 2024-05-02 | 2026-04-18 | Level 2 | GO 165 Inspection
125944249 | pole | HFTD Tier 2 | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E | 2024-05-02 | 2026-04-18 | Level 2 | GO 165 Inspection
125944290 | pole | Non-HFTD | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E |  | 2026-04-18 | Level 2
125944544 | other | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F |  | 2028-04-18 | Level 3
125944605 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
125944736 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-03-15 | 2028-04-05 | Level 3 | GO 165 Inspection
125944738 | pole | HFTD Tier 3 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-03-15 | 2028-04-05 | Level 3 | GO 165 Inspection
125945755 | other | Non-HFTD | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-10-01 | 2028-04-18 | Level 3 | GO 165 Inspection
125946397 | other | HFTD Tier 3 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F |  | 2028-04-18 | Level 3
125946398 | other | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-03-12 | 2028-04-18 | Level 3 | GO 165 Inspection
125946932 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-06-10 | 2028-04-18 | Level 3 | GO 165 Inspection
125947220 | other | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-04-18 | 2028-04-18 | Level 3 | GO 165 Inspection
125947345 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-04-18 | 2028-04-18 | Level 3 | GO 165 Inspection
125947566 | other | HFTD Tier 2 | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E | 2024-04-25 | 2026-04-05 | Level 2 | GO 165 Inspection
125947567 | pole | HFTD Tier 2 | Transmission | 2023-04-05 | 2026-04-05 | Level 2 | E | 2024-04-25 | 2026-04-05 | Level 2 | GO 165 Inspection
125947620 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-04-18 | 2028-04-18 | Level 3 | GO 165 Inspection
125947664 | other | Non-HFTD | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E | 2024-04-22 | 2026-04-18 | Level 2 | GO 165 Inspection
125948133 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-06-12 | 2028-04-19 | Level 3 | GO 165 Inspection
125948138 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-04-20 | 2028-04-18 | Level 3 | GO 165 Inspection
125950048 | pole | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E |  | 2026-04-19 | Level 2
125950650 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125950982 | other | HFTD Tier 2 | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F |  | 2028-04-19 | Level 3
125951221 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-19 | 2024-04-19 | Level 2 | E | 2024-04-22 | 2024-04-19 | Level 2 | GO 165 Inspection
125951445 | pole | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E |  | 2026-04-19 | Level 2
125951854 | pole | HFTD Tier 3 | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F |  | 2028-04-19 | Level 3
125952281 | pole | HFTD Tier 2 | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-02-21 | 2028-04-19 | Level 3 | GO 165 Inspection
125952701 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
125955070 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125955073 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125955272 | crossarm | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-06-15 | 2028-04-12 | Level 3 | GO 165 Inspection
125955503 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125955590 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125955648 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125955661 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125955718 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-05 | 2028-04-05 | Level 3 | F | 2024-05-22 | 2028-04-05 | Level 3 | GO 165 Inspection
125955722 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-29 | 2028-04-07 | Level 3 | GO 165 Inspection
125955724 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125955810 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E | 2024-03-28 | 2026-04-06 | Level 2 | GO 165 Inspection
125955814 | pole | HFTD Tier 2 | Transmission | 2023-04-06 | 2028-04-06 | Level 3 | F | 2024-06-04 | 2028-04-06 | Level 3 | GO 165 Inspection
125955838 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125957180 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-06-02 | 2028-04-20 | Level 3 | GO 165 Inspection
125958168 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-06-01 | 2028-04-20 | Level 3 | GO 165 Inspection
125958802 | other | Non-HFTD | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E | 2024-11-04 | 2026-04-18 | Level 2 | GO 165 Inspection
125959469 | other | Non-HFTD | Transmission | 2023-04-20 | 2026-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
125960261 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125960461 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125961485 | other | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E | 2024-04-11 | 2026-03-24 | Level 2 | GO 165 Inspection
125961573 | other | Non-HFTD | Transmission | 2023-03-22 | 2028-03-22 | Level 3 | F |  | 2028-03-22 | Level 3
125961750 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-05-23 | 2028-04-20 | Level 3 | GO 165 Inspection
125962176 | pole | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2023-06-19 | 2028-04-20 | Level 3 | GO 165 Inspection
125962472 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
125962491 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125963203 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125963224 | other | HFTD Tier 2 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-06-04 | 2028-04-17 | Level 3 | GO 165 Inspection
125963322 | pole | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-03-26 | 2028-04-07 | Level 3 | GO 165 Inspection
125963399 | pole | Non-HFTD | Transmission | 2023-04-06 | 2026-04-06 | Level 2 | E |  | 2026-04-06 | Level 2
125963518 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125963530 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125963537 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125963631 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125963663 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-24 | 2028-04-07 | Level 3 | GO 165 Inspection
125965012 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-12 | 2026-04-12 | Level 2 | E | 2024-05-22 | 2026-04-12 | Level 2 | GO 165 Inspection
125965411 | pole | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125965746 | pole | HFTD Tier 3 | Transmission | 2023-04-10 | 2026-04-10 | Level 2 | E | 2024-05-01 | 2026-04-10 | Level 2 | GO 165 Inspection
125966260 | pole | HFTD Tier 2 | Transmission | 2023-04-21 | 2026-04-21 | Level 2 | E | 2024-04-23 | 2026-04-21 | Level 2 | GO 165 Inspection
125966300 | other | HFTD Tier 3 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-05-28 | 2028-04-10 | Level 3 | GO 165 Inspection
125966889 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F | 2024-05-06 | 2028-04-10 | Level 3 | GO 165 Inspection
125967314 | other | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125967642 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F |  | 2028-04-11 | Level 3
125968073 | pole | HFTD Tier 2 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F |  | 2028-04-07 | Level 3
125968524 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125968802 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125969319 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125969326 | pole | Non-HFTD | Transmission | 2023-04-21 | 2026-04-21 | Level 2 | E | 2024-07-18 | 2026-04-21 | Level 2 | GO 165 Inspection
125969440 | pole | Non-HFTD | Transmission | 2023-04-21 | 2026-04-21 | Level 2 | E | 2024-05-28 | 2026-04-21 | Level 2 | GO 165 Inspection
125970301 | other | Non-HFTD | Transmission | 2023-04-18 | 2028-04-18 | Level 3 | F | 2024-04-24 | 2028-04-18 | Level 3 | GO 165 Inspection
125970499 | other | HFTD Tier 2 | Transmission | 2023-04-10 | 2028-04-10 | Level 3 | F |  | 2028-04-10 | Level 3
125970580 | other | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F |  | 2028-04-11 | Level 3
125971009 | other | Non-HFTD | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-12-10 | 2028-04-21 | Level 3 | GO 165 Inspection
125971243 | other | HFTD Tier 3 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-06-01 | 2028-04-21 | Level 3 | GO 165 Inspection
125971901 | other | HFTD Tier 3 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-05-08 | 2028-04-21 | Level 3 | GO 165 Inspection
125972029 | pole | HFTD Tier 3 | Transmission | 2023-04-07 | 2028-04-07 | Level 3 | F | 2024-05-21 | 2028-04-07 | Level 3 | GO 165 Inspection
125972883 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F |  | 2028-04-11 | Level 3
125972975 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-04-22 | 2028-04-12 | Level 3 | GO 165 Inspection
125973080 | pole | Non-HFTD | Transmission | 2023-04-13 | 2024-04-13 | Level 2 | E | 2024-09-02 | 2024-04-13 | Level 2 | Field Safety Reassessment
125973081 | pole | HFTD Tier 3 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
125973456 | insulator and brushing | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E |  | 2026-04-19 | Level 2
125973986 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F |  | 2028-04-11 | Level 3
125974137 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-05-21 | 2028-04-12 | Level 3 | GO 165 Inspection
125974225 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125974533 | other | HFTD Tier 2 | Transmission | 2023-04-22 | 2028-04-22 | Level 3 | F |  | 2028-04-22 | Level 3
125974672 | pole | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-06-05 | 2028-04-11 | Level 3 | GO 165 Inspection
125974674 | other | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-06-05 | 2028-04-11 | Level 3 | GO 165 Inspection
125974676 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-11 | 2028-04-11 | Level 3 | F | 2024-06-05 | 2028-04-11 | Level 3 | GO 165 Inspection
125975597 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-22 | 2028-04-22 | Level 3 | F |  | 2028-04-22 | Level 3
125978113 | anchor/guy | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
125978190 | pole | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
125979001 | pole | Non-HFTD | Transmission | 2023-04-24 | 2026-04-24 | Level 2 | E |  | 2026-04-24 | Level 2
125980631 | anchor/guy | Non-HFTD | Transmission | 2023-04-24 | 2026-04-24 | Level 2 | E | 2024-10-09 | 2026-04-24 | Level 2 | GO 165 Inspection
125980798 | other | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-05-03 | 2028-04-24 | Level 3 | GO 165 Inspection
125981088 | pole | HFTD Tier 2 | Transmission | 2023-04-24 | 2024-04-24 | Level 2 | E | 2024-05-31 | 2024-04-24 | Level 2 | GO 165 Inspection
125981163 | other | Non-HFTD | Transmission | 2023-04-24 | 2026-04-24 | Level 2 | E | 2024-05-03 | 2026-04-24 | Level 2 | GO 165 Inspection
125981199 | other | Non-HFTD | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
125981281 | pole | Non-HFTD | Transmission | 2023-04-24 | 2026-04-24 | Level 2 | E | 2024-08-13 | 2026-04-24 | Level 2 | GO 165 Inspection
125981318 | pole | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-05-22 | 2028-04-24 | Level 3 | GO 165 Inspection
125981327 | other | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-05-21 | 2028-04-24 | Level 3 | GO 165 Inspection
125981332 | other | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-05-21 | 2028-04-24 | Level 3 | GO 165 Inspection
125981464 | anchor/guy | Non-HFTD | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-10-07 | 2028-04-24 | Level 3 | GO 165 Inspection
125981520 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125981903 | other | HFTD Tier 3 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
125982724 | other | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2023-11-15 | 2026-03-30 | Level 2 | GO 165 Inspection
125983803 | pole | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125984247 | pole | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-05-08 | 2028-04-13 | Level 3 | GO 165 Inspection
125984521 | other | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-05-02 | 2028-04-12 | Level 3 | GO 165 Inspection
125984556 | pole | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F |  | 2028-04-12 | Level 3
125984775 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-03-19 | 2028-04-25 | Level 3 | GO 165 Inspection
125984805 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-05-22 | 2028-04-25 | Level 3 | GO 165 Inspection
125985024 | other | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
125985350 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F |  | 2028-04-25 | Level 3
125985772 | pole | Non-HFTD | Transmission | 2023-04-25 | 2026-04-25 | Level 2 | E |  | 2026-04-25 | Level 2
125986657 | insulator and brushing | Non-HFTD | Transmission | 2023-04-25 | 2026-04-25 | Level 2 | E |  | 2026-04-25 | Level 2
125987746 | other | Non-HFTD | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-08-17 | 2028-04-25 | Level 3 | GO 165 Inspection
125988076 | pole | Non-HFTD | Transmission | 2023-04-25 | 2026-04-25 | Level 2 | E |  | 2026-04-25 | Level 2
125988367 | other | Non-HFTD | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F |  | 2028-03-29 | Level 3
125988471 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
125989224 | splice | Non-HFTD | Transmission | 2023-04-25 | 2026-04-25 | Level 2 | E | 2024-10-02 | 2026-04-25 | Level 2 | GO 165 Inspection
125989743 | anchor/guy | HFTD Tier 3 | Transmission | 2023-04-25 | 2026-04-25 | Level 2 | E |  | 2026-04-25 | Level 2
125989797 | other | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-05-14 | 2028-04-25 | Level 3 | GO 165 Inspection
125991748 | other | HFTD Tier 3 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
125991993 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F |  | 2028-04-21 | Level 3
125992057 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-04-22 | 2028-04-20 | Level 3 | GO 165 Inspection
125992281 | pole | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-03-14 | 2028-04-21 | Level 3 | GO 165 Inspection
125993932 | pole | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E |  | 2026-04-26 | Level 2
125994177 | other | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125994325 | other | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125994611 | other | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125994785 | pole | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125995122 | anchor/guy | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E |  | 2026-04-26 | Level 2
125995154 | anchor/guy | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-06-20 | 2028-04-26 | Level 3 | GO 165 Inspection
125995189 | other | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E |  | 2026-04-26 | Level 2
125995576 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125995697 | insulator and brushing | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E | 2024-09-17 | 2026-04-26 | Level 2 | GO 165 Inspection
125995754 | pole | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E | 2024-07-05 | 2026-04-26 | Level 2 | GO 165 Inspection
125995794 | anchor/guy | Non-HFTD | Transmission | 2023-04-26 | 2024-04-26 | Level 2 | E | 2024-09-07 | 2024-04-26 | Level 2 | Field Safety Reassessment
125995814 | crossarm | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E |  | 2026-04-26 | Level 2
125996356 | anchor/guy | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125996527 | anchor/guy | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125996797 | other | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125997000 | pole | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E |  | 2026-04-26 | Level 2
125997441 | pole | HFTD Tier 3 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-05-08 | 2028-04-26 | Level 3 | GO 165 Inspection
125997445 | other | HFTD Tier 3 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-05-08 | 2028-04-26 | Level 3 | GO 165 Inspection
125997612 | other | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
125998191 | other | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E |  | 2026-04-26 | Level 2
125998589 | anchor/guy | Non-HFTD | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2023-07-08 | 2028-04-26 | Level 3 | GO 165 Inspection
125998709 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-04-25 | 2028-04-12 | Level 3 | GO 165 Inspection
125999737 | other | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-04-24 | 2028-04-26 | Level 3 | Field Safety Reassessment
125999949 | other | HFTD Tier 3 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
126000044 | pole | HFTD Tier 3 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-07-23 | 2028-04-17 | Level 3 | Field Safety Reassessment
126000105 | other | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-04-15 | 2028-04-26 | Level 3 | GO 165 Inspection
126000382 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-04-23 | 2028-04-26 | Level 3 | GO 165 Inspection
126001660 | other | Non-HFTD | Transmission | 2023-04-26 | 2026-04-26 | Level 2 | E | 2024-04-22 | 2026-04-26 | Level 2 | GO 165 Inspection
126002451 | other | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E |  | 2026-03-29 | Level 2
126003737 | pole | HFTD Tier 2 | Transmission | 2023-04-27 | 2024-04-27 | Level 2 | E | 2024-04-24 | 2024-04-27 | Level 2 | Field Safety Reassessment
126005650 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-05-31 | 2028-04-27 | Level 3 | GO 165 Inspection
126005798 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F |  | 2028-03-27 | Level 3
126006098 | pole | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
126006871 | other | Non-HFTD | Transmission | 2023-03-22 | 2026-03-22 | Level 2 | E |  | 2026-03-22 | Level 2
126006947 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2026-04-27 | Level 2 | E |  | 2026-04-27 | Level 2
126007290 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2026-04-27 | Level 2 | E |  | 2026-04-27 | Level 2
126007564 | pole | HFTD Tier 2 | Transmission | 2023-04-17 | 2028-04-17 | Level 3 | F | 2024-06-04 | 2028-04-17 | Level 3 | GO 165 Inspection
126007701 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-06-13 | 2028-04-19 | Level 3 | GO 165 Inspection
126007777 | other | HFTD Tier 3 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-05-23 | 2028-04-27 | Level 3 | GO 165 Inspection
126007887 | anchor/guy | Non-HFTD | Transmission | 2023-04-27 | 2026-04-27 | Level 2 | E | 2024-05-30 | 2026-04-27 | Level 2 | GO 165 Inspection
126007906 | other | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-05-14 | 2028-04-13 | Level 3 | GO 165 Inspection
126007998 | other | Non-HFTD | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-05-07 | 2028-04-27 | Level 3 | GO 165 Inspection
126008015 | pole | HFTD Tier 2 | Transmission | 2023-04-21 | 2024-04-21 | Level 2 | E | 2024-05-09 | 2024-04-21 | Level 2 | Field Safety Reassessment
126008103 | other | HFTD Tier 2 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
126008104 | pole | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-08-15 | 2028-04-19 | Level 3 | GO 165 Inspection
126008213 | other | HFTD Tier 3 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
126008216 | other | HFTD Tier 3 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
126009877 | other | HFTD Tier 3 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-04-17 | 2028-04-13 | Level 3 | GO 165 Inspection
126009957 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
126009976 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2023-05-11 | 2028-04-24 | Level 3 | GO 165 Inspection
126010065 | other | HFTD Tier 2 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
126010210 | other | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F |  | 2028-04-21 | Level 3
126010340 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F | 2024-05-06 | 2028-04-13 | Level 3 | GO 165 Inspection
126010374 | pole | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E |  | 2026-04-28 | Level 2
126010881 | pole | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E |  | 2026-04-28 | Level 2
126011840 | pole | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
126011841 | pole | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
126012025 | pole | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E |  | 2026-04-28 | Level 2
126012062 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-28 | 2024-04-28 | Level 2 | E | 2024-04-25 | 2024-04-28 | Level 2 | Field Safety Reassessment
126012166 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
126012739 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-04-10 | 2028-04-24 | Level 3 | GO 165 Inspection
126012996 | pole | Non-HFTD | Transmission | 2023-04-19 | 2024-04-19 | Level 2 | E | 2024-06-13 | 2024-04-19 | Level 2 | GO 165 Inspection
126013231 | pole | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F |  | 2028-04-25 | Level 3
126013294 | pole | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E |  | 2026-04-28 | Level 2
126013476 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-04-12 | 2028-04-21 | Level 3 | GO 165 Inspection
126013853 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E | 2024-05-30 | 2026-04-19 | Level 2 | GO 165 Inspection
126013952 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-06-13 | 2028-04-19 | Level 3 | GO 165 Inspection
126014055 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-02-12 | 2028-04-19 | Level 3 | GO 165 Inspection
126014242 | other | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E | 2024-10-18 | 2024-04-28 | Level 2 | GO 165 Inspection
126014610 | other | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E | 2024-09-12 | 2026-04-19 | Level 2 | GO 165 Inspection
126015111 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-05-01 | 2028-04-19 | Level 3 | GO 165 Inspection
126015244 | pole | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
126015337 | other | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-06-15 | 2028-04-21 | Level 3 | GO 165 Inspection
126015608 | pole | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
126015772 | other | HFTD Tier 3 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F | 2024-04-25 | 2028-04-28 | Level 3 | GO 165 Inspection
126015799 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
126015850 | other | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F | 2024-04-12 | 2028-04-21 | Level 3 | GO 165 Inspection
126015872 | other | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-06-05 | 2028-04-25 | Level 3 | GO 165 Inspection
126016420 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-05-15 | 2028-04-20 | Level 3 | GO 165 Inspection
126016536 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-05-25 | 2028-04-19 | Level 3 | GO 165 Inspection
126016546 | pole | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E |  | 2026-04-28 | Level 2
126016572 | pole | HFTD Tier 2 | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2023-06-05 | 2028-04-19 | Level 3 | GO 165 Inspection
126017078 | other | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-05-09 | 2028-04-24 | Level 3 | GO 165 Inspection
126017123 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-05-01 | 2028-04-20 | Level 3 | GO 165 Inspection
126017184 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-04-16 | 2028-04-20 | Level 3 | GO 165 Inspection
126017238 | other | HFTD Tier 3 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F |  | 2028-04-14 | Level 3
126017323 | other | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F |  | 2028-04-20 | Level 3
126017338 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F |  | 2028-04-25 | Level 3
126017424 | other | HFTD Tier 3 | Transmission | 2023-04-14 | 2028-04-14 | Level 3 | F | 2024-03-12 | 2028-04-14 | Level 3 | GO 165 Inspection
126017510 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F |  | 2028-04-26 | Level 3
126017710 | other | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F |  | 2028-04-25 | Level 3
126017730 | pole | HFTD Tier 2 | Transmission | 2023-04-20 | 2024-04-20 | Level 2 | E | 2024-05-09 | 2024-04-20 | Level 2 | Field Safety Reassessment
126017827 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-04-15 | 2028-04-20 | Level 3 | GO 165 Inspection
126017895 | other | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
126017961 | pole | Non-HFTD | Transmission | 2023-04-19 | 2024-04-19 | Level 2 | E | 2024-06-13 | 2024-04-19 | Level 2 | GO 165 Inspection
126017983 | pole | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F |  | 2028-04-21 | Level 3
126018001 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-20 | 2028-04-20 | Level 3 | F | 2024-04-17 | 2028-04-20 | Level 3 | GO 165 Inspection
126018043 | pole | HFTD Tier 2 | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F | 2024-04-25 | 2028-04-29 | Level 3 | GO 165 Inspection
126018573 | other | HFTD Tier 2 | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F |  | 2028-04-29 | Level 3
126018645 | other | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F |  | 2028-04-25 | Level 3
126018676 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
126018729 | other | Non-HFTD | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F | 2024-06-12 | 2028-04-29 | Level 3 | GO 165 Inspection
126019471 | insulator and brushing | Non-HFTD | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F | 2024-10-01 | 2028-04-29 | Level 3 | GO 165 Inspection
126019569 | pole | Non-HFTD | Transmission | 2023-04-29 | 2024-04-29 | Level 2 | E | 2024-06-17 | 2024-04-29 | Level 2 | GO 165 Inspection
126019943 | other | HFTD Tier 2 | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F | 2024-04-25 | 2028-04-29 | Level 3 | GO 165 Inspection
126020387 | other | HFTD Tier 2 | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F |  | 2028-04-29 | Level 3
126020480 | pole | HFTD Tier 2 | Transmission | 2023-04-29 | 2024-04-29 | Level 2 | E | 2024-05-30 | 2024-04-29 | Level 2 | GO 165 Inspection
126020495 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-29 | 2024-04-29 | Level 3 | F | 2024-05-31 | 2028-04-29 | Level 3 | GO 165 Inspection
126020650 | pole | HFTD Tier 2 | Transmission | 2023-04-29 | 2024-04-29 | Level 2 | E | 2024-04-11 | 2024-04-29 | Level 2 | Field Safety Reassessment
126020881 | anchor/guy | Non-HFTD | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F |  | 2028-04-29 | Level 3
126021020 | other | HFTD Tier 3 | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F | 2024-04-26 | 2028-04-29 | Level 3 | GO 165 Inspection
126021099 | other | HFTD Tier 2 | Transmission | 2023-04-29 | 2028-04-29 | Level 3 | F |  | 2028-04-29 | Level 3
126022511 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
126023326 | other | HFTD Tier 2 | Transmission | 2023-05-01 | 2028-05-01 | Level 3 | F |  | 2028-05-01 | Level 3
126024343 | pole | Non-HFTD | Transmission | 2023-05-01 | 2026-05-01 | Level 2 | E |  | 2026-05-01 | Level 2
126024661 | pole | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-06-14 | 2028-04-25 | Level 3 | GO 165 Inspection
126025570 | pole | Non-HFTD | Transmission | 2023-05-01 | 2026-05-01 | Level 2 | E | 2024-05-30 | 2024-05-01 | Level 2 | GO 165 Inspection
126025863 | other | Non-HFTD | Transmission | 2023-05-01 | 2026-05-01 | Level 2 | E | 2024-11-19 | 2026-05-01 | Level 2 | GO 165 Inspection
126026188 | pole | Non-HFTD | Transmission | 2023-05-01 | 2026-05-01 | Level 2 | E | 2024-06-26 | 2026-05-01 | Level 2 | GO 165 Inspection
126026764 | pole | Non-HFTD | Transmission | 2023-05-01 | 2026-05-01 | Level 2 | E |  | 2026-05-01 | Level 2
126027147 | pole | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E | 2024-10-08 | 2026-03-29 | Level 2 | GO 165 Inspection
126027543 | pole | HFTD Tier 3 | Transmission | 2023-05-01 | 2028-05-01 | Level 3 | F | 2024-03-12 | 2028-05-01 | Level 3 | GO 165 Inspection
126029820 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
126029850 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F | 2024-05-30 | 2028-04-19 | Level 3 | GO 165 Inspection
126030115 | pole | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126031444 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F | 2024-04-25 | 2028-04-24 | Level 3 | GO 165 Inspection
126032058 | pole | HFTD Tier 2 | Transmission | 2023-04-25 | 2026-04-25 | Level 2 | E | 2024-04-15 | 2026-04-25 | Level 2 | GO 165 Inspection
126032148 | other | HFTD Tier 3 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-05-23 | 2028-05-02 | Level 3 | GO 165 Inspection
126032522 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-05-22 | 2028-05-02 | Level 3 | GO 165 Inspection
126033015 | anchor/guy | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E | 2024-07-11 | 2026-03-27 | Level 2 | GO 165 Inspection
126033586 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
126033946 | other | Non-HFTD | Transmission | 2023-05-02 | 2024-05-02 | Level 2 | E | 2024-07-18 | 2024-05-02 | Level 2 | GO 165 Inspection
126034243 | other | Non-HFTD | Transmission | 2023-03-27 | 2028-03-27 | Level 3 | F | 2024-07-17 | 2028-03-27 | Level 3 | GO 165 Inspection
126035450 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-02 | 2024-05-02 | Level 3 | F | 2024-04-24 | 2028-05-02 | Level 3 | Field Safety Reassessment
126035865 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-02 | 2026-05-02 | Level 2 | E | 2024-04-15 | 2026-05-02 | Level 2 | GO 165 Inspection
126036075 | other | HFTD Tier 2 | Transmission | 2023-04-21 | 2028-04-21 | Level 3 | F |  | 2028-04-21 | Level 3
126036150 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126036267 | other | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-05-23 | 2028-04-26 | Level 3 | GO 165 Inspection
126036407 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-06-14 | 2028-04-27 | Level 3 | GO 165 Inspection
126036578 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126036609 | other | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F | 2024-04-23 | 2028-04-25 | Level 3 | GO 165 Inspection
126036641 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-27 | 2024-04-27 | Level 2 | E | 2024-04-09 | 2024-04-27 | Level 2 | Field Safety Reassessment
126036743 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-04-24 | 2028-04-24 | Level 3 | F |  | 2028-04-24 | Level 3
126036801 | other | HFTD Tier 2 | Transmission | 2023-04-26 | 2028-04-26 | Level 3 | F | 2024-04-16 | 2028-04-26 | Level 3 | GO 165 Inspection
126037286 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126038409 | other | HFTD Tier 3 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126038416 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-05-21 | 2028-04-27 | Level 3 | GO 165 Inspection
126038428 | pole | HFTD Tier 3 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-22 | 2028-05-03 | Level 3 | GO 165 Inspection
126039121 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-22 | 2028-05-03 | Level 3 | GO 165 Inspection
126039781 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-05-19 | 2028-04-27 | Level 3 | GO 165 Inspection
126040539 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-22 | 2028-05-03 | Level 3 | GO 165 Inspection
126041723 | pole | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126041726 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-06-04 | 2028-05-03 | Level 3 | GO 165 Inspection
126043338 | pole | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-04-16 | 2028-05-03 | Level 3 | GO 165 Inspection
126043352 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-03 | 2028-05-03 | Level 3 | GO 165 Inspection
126043427 | other | HFTD Tier 3 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-30 | 2028-05-03 | Level 3 | GO 165 Inspection
126043874 | pole | Non-HFTD | Transmission | 2023-05-03 | 2026-05-03 | Level 2 | E | 2024-06-18 | 2023-08-03 | Level 2 | GO 165 Inspection
126043894 | other | HFTD Tier 3 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-23 | 2028-05-03 | Level 3 | GO 165 Inspection
126044066 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126045233 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126045456 | other | HFTD Tier 2 | Transmission | 2023-04-25 | 2028-04-25 | Level 3 | F |  | 2028-04-25 | Level 3
126045478 | splice | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E | 2024-08-19 | 2026-04-28 | Level 2 | GO 165 Inspection
126045479 | insulator and brushing | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E | 2024-08-19 | 2026-04-28 | Level 2 | GO 165 Inspection
126045794 | other | HFTD Tier 2 | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E | 2023-06-06 | 2026-04-28 | Level 2 | GO 165 Inspection
126045813 | other | HFTD Tier 2 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F | 2024-06-11 | 2028-04-28 | Level 3 | GO 165 Inspection
126047925 | insulator and brushing | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E | 2024-12-07 | 2026-03-24 | Level 2 | GO 165 Inspection
126048081 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E |  | 2026-05-04 | Level 2
126048709 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-04-30 | 2028-05-04 | Level 3 | GO 165 Inspection
126049294 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-04-30 | 2028-05-04 | Level 3 | GO 165 Inspection
126049433 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-05-01 | 2028-05-04 | Level 3 | GO 165 Inspection
126049503 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F | 2024-05-19 | 2028-04-27 | Level 3 | GO 165 Inspection
126051267 | other | Non-HFTD | Transmission | 2023-03-23 | 2028-03-23 | Level 3 | F |  | 2028-03-23 | Level 3
126052003 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
126052122 | other | HFTD Tier 2 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F |  | 2028-04-28 | Level 3
126052637 | other | Non-HFTD | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-05-28 | 2028-05-04 | Level 3 | GO 165 Inspection
126052851 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-05-14 | 2028-05-04 | Level 3 | GO 165 Inspection
126053842 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-04-25 | 2028-05-04 | Level 3 | GO 165 Inspection
126053882 | pole | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126054056 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E | 2024-03-22 | 2026-05-04 | Level 2 | GO 165 Inspection
126054191 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E | 2024-03-25 | 2026-05-04 | Level 2 | GO 165 Inspection
126054296 | pole | HFTD Tier 2 | Transmission | 2023-05-01 | 2024-05-01 | Level 2 | E | 2024-04-24 | 2024-05-01 | Level 2 | Field Safety Reassessment
126054356 | other | HFTD Tier 2 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F |  | 2028-04-28 | Level 3
126054412 | other | HFTD Tier 2 | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126054567 | anchor/guy | HFTD Tier 2 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F | 2024-06-12 | 2028-04-28 | Level 3 | GO 165 Inspection
126056139 | other | Non-HFTD | Transmission | 2023-05-01 | 2028-05-01 | Level 3 | F |  | 2028-05-01 | Level 3
126056157 | other | HFTD Tier 2 | Transmission | 2023-05-01 | 2028-05-01 | Level 3 | F |  | 2028-05-01 | Level 3
126056352 | insulator and brushing | Non-HFTD | Transmission | 2023-03-24 | 2026-03-24 | Level 2 | E |  | 2026-03-24 | Level 2
126056560 | other | Non-HFTD | Transmission | 2023-05-01 | 2028-05-01 | Level 3 | F | 2024-05-01 | 2028-05-01 | Level 3 | GO 165 Inspection
126057008 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F |  | 2028-05-02 | Level 3
126057062 | pole | HFTD Tier 2 | Transmission | 2023-05-01 | 2024-05-01 | Level 2 | E | 2024-05-07 | 2024-05-01 | Level 2 | Field Safety Reassessment
126057442 | other | HFTD Tier 3 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F | 2024-05-17 | 2028-04-28 | Level 3 | GO 165 Inspection
126057943 | anchor/guy | Non-HFTD | Transmission | 2023-05-05 | 2024-05-05 | Level 2 | E | 2024-05-09 | 2024-05-05 | Level 2 | GO 165 Inspection
126057953 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2023-06-06 | 2028-05-02 | Level 3 | GO 165 Inspection
126058041 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-04-20 | 2028-05-02 | Level 3 | GO 165 Inspection
126058217 | pole | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F |  | 2028-05-02 | Level 3
126058254 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-02 | 2026-05-02 | Level 2 | E | 2024-05-18 | 2026-05-02 | Level 2 | GO 165 Inspection
126058349 | anchor/guy | Non-HFTD | Transmission | 2023-05-05 | 2026-05-05 | Level 2 | E | 2024-05-08 | 2026-05-05 | Level 2 | GO 165 Inspection
126058661 | anchor/guy | Non-HFTD | Transmission | 2023-05-05 | 2026-05-05 | Level 2 | E | 2024-05-09 | 2026-05-05 | Level 2 | GO 165 Inspection
126058707 | pole | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-06-07 | 2028-05-02 | Level 3 | GO 165 Inspection
126058862 | anchor/guy | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
126058872 | pole | HFTD Tier 3 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-05-15 | 2028-05-05 | Level 3 | GO 165 Inspection
126059737 | other | HFTD Tier 3 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-05-30 | 2028-05-05 | Level 3 | GO 165 Inspection
126059746 | pole | Non-HFTD | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126059830 | other | HFTD Tier 2 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-04-29 | 2028-05-05 | Level 3 | GO 165 Inspection
126059957 | other | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
126060797 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-04-16 | 2028-05-02 | Level 3 | GO 165 Inspection
126061227 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-04-01 | 2028-05-02 | Level 3 | GO 165 Inspection
126062085 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-05 | 2024-05-05 | Level 2 | E | 2024-04-24 | 2024-05-05 | Level 2 | Field Safety Reassessment
126062486 | other | HFTD Tier 2 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F |  | 2028-05-05 | Level 3
126062654 | other | Non-HFTD | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-04-26 | 2028-05-05 | Level 3 | GO 165 Inspection
126062768 | anchor/guy | Non-HFTD | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F |  | 2028-03-24 | Level 3
126062894 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F |  | 2028-05-02 | Level 3
126062922 | other | Non-HFTD | Transmission | 2023-03-27 | 2026-03-27 | Level 2 | E |  | 2026-03-27 | Level 2
126063887 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-04-24 | 2028-05-02 | Level 3 | GO 165 Inspection
126063895 | pole | HFTD Tier 3 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2024-04-06 | 2028-05-02 | Level 3 | GO 165 Inspection
126064029 | pole | HFTD Tier 2 | Transmission | 2023-05-02 | 2024-05-02 | Level 2 | E | 2024-05-14 | 2024-05-02 | Level 2 | Field Safety Reassessment
126064334 | other | HFTD Tier 2 | Transmission | 2023-05-02 | 2028-05-02 | Level 3 | F | 2023-05-12 | 2028-05-02 | Level 3 | GO 165 Inspection
126064343 | other | HFTD Tier 2 | Transmission | 2023-05-06 | 2028-05-06 | Level 3 | F | 2024-04-04 | 2028-05-06 | Level 3 | GO 165 Inspection
126064812 | pole | HFTD Tier 2 | Transmission | 2023-05-01 | 2024-05-01 | Level 2 | E | 2024-04-19 | 2024-05-01 | Level 2 | GO 165 Inspection
126065036 | pole | HFTD Tier 2 | Transmission | 2023-05-02 | 2024-05-02 | Level 2 | E | 2024-04-22 | 2024-05-02 | Level 2 | GO 165 Inspection
126065092 | splice | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
126065350 | pole | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126065357 | pole | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126065819 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-23 | 2028-05-03 | Level 3 | GO 165 Inspection
126065981 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2023-05-19 | 2028-05-03 | Level 3 | GO 165 Inspection
126066076 | pole | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-22 | 2028-05-03 | Level 3 | GO 165 Inspection
126066104 | other | Non-HFTD | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126066467 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-16 | 2028-05-03 | Level 3 | GO 165 Inspection
126066608 | other | HFTD Tier 3 | Transmission | 2023-05-03 | 2026-05-03 | Level 2 | E | 2024-04-06 | 2026-05-03 | Level 2 | GO 165 Inspection
126066644 | insulator and brushing | Non-HFTD | Transmission | 2023-05-06 | 2028-05-06 | Level 3 | F | 2024-03-13 | 2028-05-06 | Level 3 | GO 165 Inspection
126067068 | insulator and brushing | Non-HFTD | Transmission | 2023-05-06 | 2026-05-06 | Level 2 | E | 2024-04-10 | 2026-05-06 | Level 2 | GO 165 Inspection
126067292 | other | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F | 2024-05-19 | 2028-05-03 | Level 3 | GO 165 Inspection
126067297 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126069148 | anchor/guy | Non-HFTD | Transmission | 2023-05-08 | 2028-05-08 | Level 3 | F |  | 2028-05-08 | Level 3
126069261 | other | Non-HFTD | Transmission | 2023-05-08 | 2026-05-08 | Level 2 | E |  | 2026-05-08 | Level 2
126070031 | other | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-08-12 | 2026-03-28 | Level 2 | GO 165 Inspection
126070036 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-08-12 | 2026-03-28 | Level 2 | GO 165 Inspection
126071253 | other | HFTD Tier 2 | Transmission | 2023-05-08 | 2028-05-08 | Level 3 | F |  | 2028-05-08 | Level 3
126072192 | pole | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
126077160 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-07-17 | 2026-03-28 | Level 2 | GO 165 Inspection
126077289 | pole | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-07-17 | 2026-03-28 | Level 2 | GO 165 Inspection
126077591 | pole | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
126077663 | anchor/guy | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
126077785 | pole | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E | 2024-07-17 | 2026-03-28 | Level 2 | GO 165 Inspection
126078285 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126079569 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
126080337 | conductor | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
126080992 | insulator and brushing | Non-HFTD | Transmission | 2023-03-28 | 2026-03-28 | Level 2 | E |  | 2026-03-28 | Level 2
126081161 | insulator and brushing | Non-HFTD | Transmission | 2023-05-09 | 2026-05-09 | Level 2 | E | 2024-09-03 | 2026-05-09 | Level 2 | GO 165 Inspection
126082092 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126082466 | crossarm | Non-HFTD | Transmission | 2023-03-29 | 2024-03-29 | Level 2 | E | 2024-04-01 | 2024-03-29 | Level 2 | GO 165 Inspection
126082639 | pole | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E |  | 2026-03-29 | Level 2
126082880 | other | HFTD Tier 3 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126083573 | pole | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E |  | 2026-03-29 | Level 2
126084363 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-06-03 | 2028-05-04 | Level 3 | GO 165 Inspection
126084469 | other | Non-HFTD | Transmission | 2023-03-28 | 2028-03-28 | Level 3 | F |  | 2028-03-28 | Level 3
126084790 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-05-23 | 2028-05-04 | Level 3 | GO 165 Inspection
126085063 | pole | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-05-23 | 2028-05-04 | Level 3 | GO 165 Inspection
126085090 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126085186 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2024-05-02 | 2028-05-09 | Level 3 | GO 165 Inspection
126096931 | other | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-01-25 | 2028-05-10 | Level 3 | GO 165 Inspection
126097612 | other | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E | 2024-11-16 | 2026-03-29 | Level 2 | GO 165 Inspection
126097819 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-03-24 | 2028-03-24 | Level 3 | F | 2024-06-08 | 2028-03-24 | Level 3 | GO 165 Inspection
126098049 | other | Non-HFTD | Transmission | 2023-03-29 | 2028-03-29 | Level 3 | F | 2024-04-03 | 2028-03-29 | Level 3 | GO 165 Inspection
126099265 | switch | Non-HFTD | Transmission | 2023-05-10 | 2026-05-10 | Level 2 | E |  | 2026-05-10 | Level 2
126099401 | insulator and brushing | Non-HFTD | Transmission | 2023-05-10 | 2026-05-10 | Level 2 | E | 2024-06-25 | 2026-05-10 | Level 2 | GO 165 Inspection
126099419 | pole | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-16 | 2028-05-10 | Level 3 | GO 165 Inspection
126099475 | pole | Non-HFTD | Transmission | 2023-05-10 | 2026-05-10 | Level 2 | E |  | 2026-05-10 | Level 2
126099967 | other | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2023-11-15 | 2026-03-30 | Level 2 | GO 165 Inspection
126100301 | pole | Non-HFTD | Transmission | 2023-03-29 | 2026-03-29 | Level 2 | E |  | 2026-03-29 | Level 2
126100344 | pole | Non-HFTD | Transmission | 2023-05-10 | 2026-05-10 | Level 2 | E | 2024-10-18 | 2026-05-10 | Level 2 | GO 165 Inspection
126100556 | other | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-10 | 2028-05-10 | Level 3 | GO 165 Inspection
126100592 | pole | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126101571 | other | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126102918 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2024-05-29 | 2028-05-04 | Level 3 | GO 165 Inspection
126103134 | splice | Non-HFTD | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E |  | 2026-05-04 | Level 2
126103136 | pole | Non-HFTD | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F |  | 2028-05-04 | Level 3
126103157 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E | 2023-06-14 | 2026-05-04 | Level 2 | GO 165 Inspection
126103218 | other | HFTD Tier 3 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F |  | 2028-05-05 | Level 3
126103322 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2023-06-14 | 2028-05-04 | Level 3 | GO 165 Inspection
126103585 | other | HFTD Tier 3 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F |  | 2028-05-05 | Level 3
126103599 | other | HFTD Tier 2 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-05-01 | 2028-05-05 | Level 3 | GO 165 Inspection
126103603 | pole | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F |  | 2028-05-04 | Level 3
126103653 | pole | HFTD Tier 2 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E | 2024-05-07 | 2026-05-04 | Level 2 | GO 165 Inspection
126105556 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-02-01 | 2028-05-11 | Level 3 | GO 165 Inspection
126106010 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-02-01 | 2028-05-11 | Level 3 | GO 165 Inspection
126106572 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F |  | 2028-05-11 | Level 3
126106693 | anchor/guy | Non-HFTD | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
126107016 | anchor/guy | Non-HFTD | Transmission | 2023-03-30 | 2028-03-30 | Level 3 | F |  | 2028-03-30 | Level 3
126108136 | other | HFTD Tier 3 | Transmission | 2023-05-11 | 2026-05-11 | Level 2 | E | 2024-05-19 | 2026-05-11 | Level 2 | GO 165 Inspection
126108222 | other | HFTD Tier 3 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-03-20 | 2028-05-11 | Level 3 | GO 165 Inspection
126108374 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-05-23 | 2028-05-11 | Level 3 | GO 165 Inspection
126108409 | other | Non-HFTD | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-04-29 | 2028-05-11 | Level 3 | GO 165 Inspection
126108557 | other | HFTD Tier 3 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-05-19 | 2028-05-11 | Level 3 | GO 165 Inspection
126108773 | other | Non-HFTD | Transmission | 2023-03-30 | 2026-03-30 | Level 2 | E | 2023-11-15 | 2026-03-30 | Level 2 | GO 165 Inspection
126108944 | other | Non-HFTD | Transmission | 2023-05-11 | 2026-05-11 | Level 2 | E | 2024-04-22 | 2026-05-11 | Level 2 | GO 165 Inspection
126110278 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-05-23 | 2028-05-11 | Level 3 | GO 165 Inspection
126111002 | insulator and brushing | Non-HFTD | Transmission | 2023-05-11 | 2026-05-11 | Level 2 | E |  | 2026-05-11 | Level 2
126111898 | other | HFTD Tier 2 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2023-05-31 | 2028-05-05 | Level 3 | GO 165 Inspection
126111928 | other | HFTD Tier 3 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E | 2023-06-13 | 2026-05-04 | Level 2 | GO 165 Inspection
126111960 | pole | HFTD Tier 3 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2023-06-13 | 2028-05-04 | Level 3 | GO 165 Inspection
126112042 | crossarm | HFTD Tier 2 | Transmission | 2023-05-05 | 2024-05-05 | Level 2 | E | 2024-04-19 | 2024-05-05 | Level 2 | Field Safety Reassessment
126112302 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2026-05-04 | Level 2 | E | 2023-06-14 | 2026-05-04 | Level 2 | GO 165 Inspection
126112328 | pole | HFTD Tier 3 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2023-06-20 | 2028-05-05 | Level 3 | GO 165 Inspection
126112465 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-03-29 | 2028-05-11 | Level 3 | GO 165 Inspection
126113779 | other | HFTD Tier 2 | Transmission | 2023-05-08 | 2024-05-08 | Level 2 | E | 2024-04-30 | 2024-05-08 | Level 2 | Field Safety Reassessment
126113996 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-05-07 | 2028-05-05 | Level 3 | GO 165 Inspection
126114407 | crossarm | HFTD Tier 2 | Transmission | 2023-05-08 | 2024-05-08 | Level 2 | E | 2024-07-30 | 2024-05-08 | Level 2 | Field Safety Reassessment
126115965 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2024-03-19 | 2028-05-09 | Level 3 | GO 165 Inspection
126117091 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2023-05-16 | 2028-05-09 | Level 3 | GO 165 Inspection
126118558 | pole | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2023-05-22 | 2028-05-09 | Level 3 | GO 165 Inspection
126118873 | pole | HFTD Tier 2 | Transmission | 2023-05-12 | 2024-05-12 | Level 2 | E | 2024-05-13 | 2024-05-12 | Level 2 | GO 165 Inspection
126118964 | pole | HFTD Tier 2 | Transmission | 2023-05-12 | 2024-05-12 | Level 2 | E | 2024-05-06 | 2024-05-12 | Level 2 | Field Safety Reassessment
126119024 | other | HFTD Tier 2 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F |  | 2028-05-12 | Level 3
126119150 | pole | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126119839 | other | HFTD Tier 2 | Transmission | 2023-05-08 | 2023-08-08 | Level 2 | E |  | 2023-08-08 | Level 2
126119847 | other | HFTD Tier 2 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F |  | 2028-05-12 | Level 3
126120178 | pole | HFTD Tier 2 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F |  | 2028-05-12 | Level 3
126120190 | other | HFTD Tier 2 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F | 2024-03-13 | 2028-05-12 | Level 3 | GO 165 Inspection
126120627 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126120816 | other | Non-HFTD | Transmission | 2023-04-18 | 2026-04-18 | Level 2 | E |  | 2026-04-18 | Level 2
126121075 | other | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-06-15 | 2028-05-11 | Level 3 | GO 165 Inspection
126121376 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-05 | 2028-05-05 | Level 3 | F | 2024-04-20 | 2028-05-05 | Level 3 | GO 165 Inspection
126121752 | pole | HFTD Tier 2 | Transmission | 2023-05-08 | 2024-05-08 | Level 2 | E | 2024-04-01 | 2024-05-08 | Level 2 | GO 165 Inspection
126121955 | other | HFTD Tier 2 | Transmission | 2023-05-04 | 2028-05-04 | Level 3 | F | 2023-06-14 | 2028-05-04 | Level 3 | GO 165 Inspection
126121964 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-08 | 2028-05-08 | Level 3 | F |  | 2028-05-08 | Level 3
126122014 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2024-05-09 | 2028-05-09 | Level 3 | GO 165 Inspection
126122336 | other | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126122351 | other | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126122378 | pole | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126122992 | other | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-04-26 | 2028-05-10 | Level 3 | GO 165 Inspection
126123069 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126124772 | other | HFTD Tier 2 | Transmission | 2023-05-13 | 2028-05-13 | Level 3 | F |  | 2028-05-13 | Level 3
126124780 | other | HFTD Tier 3 | Transmission | 2023-05-13 | 2028-05-13 | Level 3 | F | 2024-05-15 | 2028-05-13 | Level 3 | GO 165 Inspection
126124793 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-13 | 2028-05-13 | Level 3 | F | 2024-04-11 | 2028-05-13 | Level 3 | GO 165 Inspection
126126400 | pole | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126126420 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126126444 | other | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-06 | 2028-05-10 | Level 3 | GO 165 Inspection
126126503 | pole | HFTD Tier 2 | Transmission | 2023-05-09 | 2024-05-09 | Level 3 | F | 2023-06-06 | 2028-05-09 | Level 3 | GO 165 Inspection
126126537 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2024-03-12 | 2028-05-09 | Level 3 | GO 165 Inspection
126126648 | other | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126126670 | other | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126126750 | pole | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-16 | 2028-05-10 | Level 3 | GO 165 Inspection
126126756 | pole | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-06 | 2028-05-10 | Level 3 | GO 165 Inspection
126126757 | other | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-06 | 2028-05-10 | Level 3 | GO 165 Inspection
126126849 | crossarm | HFTD Tier 2 | Transmission | 2023-05-08 | 2024-05-08 | Level 2 | E | 2024-07-30 | 2024-05-08 | Level 2 | Field Safety Reassessment
126126895 | pole | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-05-15 | 2028-05-10 | Level 3 | GO 165 Inspection
126126912 | other | HFTD Tier 2 | Transmission | 2023-05-08 | 2024-05-08 | Level 2 | E | 2024-03-12 | 2024-05-08 | Level 2 | GO 165 Inspection
126127000 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-04-25 | 2028-05-10 | Level 3 | GO 165 Inspection
126128109 | other | Non-HFTD | Transmission | 2023-04-12 | 2028-04-12 | Level 3 | F | 2024-05-02 | 2028-04-12 | Level 3 | GO 165 Inspection
126129039 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2023-09-07 | 2026-05-15 | Level 2 | GO 165 Inspection
126129295 | pole | Non-HFTD | Transmission | 2023-05-13 | 2028-05-13 | Level 3 | F | 2024-03-13 | 2028-05-13 | Level 3 | GO 165 Inspection
126129498 | pole | HFTD Tier 2 | Transmission | 2023-05-13 | 2024-05-13 | Level 2 | E | 2024-04-19 | 2024-05-13 | Level 2 | Field Safety Reassessment
126129511 | pole | HFTD Tier 3 | Transmission | 2023-05-13 | 2028-05-13 | Level 3 | F |  | 2028-05-13 | Level 3
126129823 | anchor/guy | Non-HFTD | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-08-12 | 2028-05-15 | Level 3 | GO 165 Inspection
126129983 | other | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E |  | 2026-04-19 | Level 2
126130036 | other | Non-HFTD | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F |  | 2028-05-15 | Level 3
126130323 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E |  | 2026-05-15 | Level 2
126130890 | pole | HFTD Tier 3 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-05-19 | 2028-05-15 | Level 3 | GO 165 Inspection
126131746 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-06-13 | 2028-05-15 | Level 3 | GO 165 Inspection
126131889 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-05-16 | 2028-05-15 | Level 3 | GO 165 Inspection
126132016 | pole | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F |  | 2028-05-15 | Level 3
126132047 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-15 | 2024-05-15 | Level 2 | E | 2024-05-13 | 2024-05-15 | Level 2 | GO 165 Inspection
126132076 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-15 | 2024-05-15 | Level 2 | E | 2024-05-13 | 2024-05-15 | Level 2 | GO 165 Inspection
126132089 | other | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E |  | 2026-05-15 | Level 2
126132240 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-04-09 | 2028-05-15 | Level 3 | GO 165 Inspection
126132387 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E |  | 2026-05-15 | Level 2
126132631 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E |  | 2026-05-15 | Level 2
126132736 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-04-09 | 2028-05-15 | Level 3 | GO 165 Inspection
126132823 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2024-09-18 | 2026-05-15 | Level 2 | GO 165 Inspection
126134522 | pole | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E |  | 2026-04-19 | Level 2
126134676 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2024-06-25 | 2026-05-15 | Level 2 | GO 165 Inspection
126135502 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-05-08 | 2028-05-15 | Level 3 | GO 165 Inspection
126136505 | other | Non-HFTD | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F |  | 2028-04-19 | Level 3
126136551 | anchor/guy | Non-HFTD | Transmission | 2023-04-13 | 2028-04-13 | Level 3 | F |  | 2028-04-13 | Level 3
126136661 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-03-20 | 2028-05-16 | Level 3 | GO 165 Inspection
126137480 | anchor/guy | Non-HFTD | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F |  | 2028-05-16 | Level 3
126137813 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-03-19 | 2028-05-16 | Level 3 | GO 165 Inspection
126138156 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-04-05 | 2028-05-16 | Level 3 | GO 165 Inspection
126138250 | other | Non-HFTD | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-07-29 | 2028-05-16 | Level 3 | GO 165 Inspection
126138452 | other | Non-HFTD | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-07-29 | 2028-05-16 | Level 3 | GO 165 Inspection
126139010 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2026-05-16 | Level 2 | E | 2024-05-23 | 2026-05-16 | Level 2 | GO 165 Inspection
126139330 | other | Non-HFTD | Transmission | 2023-05-16 | 2026-05-16 | Level 2 | E | 2024-04-22 | 2026-05-16 | Level 2 | GO 165 Inspection
126140260 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2024-06-25 | 2026-05-15 | Level 2 | GO 165 Inspection
126141309 | pole | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-06-10 | 2028-05-16 | Level 3 | GO 165 Inspection
126141700 | pole | Non-HFTD | Transmission | 2023-04-19 | 2026-04-19 | Level 2 | E | 2024-08-15 | 2026-04-19 | Level 2 | GO 165 Inspection
126143589 | other | Non-HFTD | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F |  | 2028-05-16 | Level 3
126145607 | anchor/guy | HFTD Tier 3 | Transmission | 2023-05-16 | 2026-05-16 | Level 2 | E | 2024-03-27 | 2026-05-16 | Level 2 | GO 165 Inspection
126146773 | other | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F |  | 2028-05-09 | Level 3
126146861 | anchor/guy | HFTD Tier 3 | Transmission | 2023-05-16 | 2026-05-16 | Level 2 | E |  | 2026-05-16 | Level 2
126147430 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-09 | 2028-05-09 | Level 3 | F | 2024-04-23 | 2028-05-09 | Level 3 | GO 165 Inspection
126147455 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-07-18 | 2028-05-16 | Level 3 | Field Safety Reassessment
126147955 | other | HFTD Tier 3 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-05-13 | 2028-05-16 | Level 3 | GO 165 Inspection
126147958 | pole | HFTD Tier 3 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-06-07 | 2028-05-16 | Level 3 | GO 165 Inspection
126148071 | pole | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F |  | 2028-05-16 | Level 3
126149849 | other | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-05-14 | 2028-05-17 | Level 3 | GO 165 Inspection
126150545 | pole | HFTD Tier 2 | Transmission | 2023-05-17 | 2024-05-17 | Level 2 | E | 2024-05-19 | 2024-05-17 | Level 2 | Field Safety Reassessment
126150547 | other | Non-HFTD | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F |  | 2028-05-17 | Level 3
126150835 | other | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F |  | 2028-05-10 | Level 3
126151526 | anchor/guy | Non-HFTD | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-01-30 | 2028-05-17 | Level 3 | GO 165 Inspection
126151747 | anchor/guy | Non-HFTD | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-01-30 | 2028-05-17 | Level 3 | GO 165 Inspection
126153059 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-06-01 | 2028-05-17 | Level 3 | GO 165 Inspection
126153316 | pole | Non-HFTD | Transmission | 2023-05-17 | 2026-05-17 | Level 2 | E | 2024-06-14 | 2026-05-17 | Level 2 | GO 165 Inspection
126153354 | insulator and brushing | Non-HFTD | Transmission | 2023-05-17 | 2026-05-17 | Level 2 | E |  | 2026-05-17 | Level 2
126154172 | other | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F |  | 2028-05-17 | Level 3
126154548 | other | HFTD Tier 2 | Transmission | 2023-04-19 | 2028-04-19 | Level 3 | F |  | 2028-04-19 | Level 3
126154580 | pole | HFTD Tier 2 | Transmission | 2023-05-17 | 2026-05-17 | Level 2 | E | 2024-06-13 | 2026-05-17 | Level 2 | GO 165 Inspection
126155231 | pole | Non-HFTD | Transmission | 2023-05-10 | 2026-05-10 | Level 2 | E | 2024-08-12 | 2026-05-10 | Level 2 | GO 165 Inspection
126155587 | other | Non-HFTD | Transmission | 2023-05-17 | 2026-05-17 | Level 2 | E | 2024-07-26 | 2026-05-17 | Level 2 | GO 165 Inspection
126155698 | other | Non-HFTD | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-07-26 | 2028-05-17 | Level 3 | GO 165 Inspection
126156309 | other | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F |  | 2028-05-17 | Level 3
126156716 | other | HFTD Tier 2 | Transmission | 2023-05-10 | 2028-05-10 | Level 3 | F | 2024-03-25 | 2028-05-10 | Level 3 | GO 165 Inspection
126156820 | other | HFTD Tier 3 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F |  | 2028-05-11 | Level 3
126156890 | pole | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F |  | 2028-05-11 | Level 3
126156908 | pole | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F |  | 2028-05-11 | Level 3
126156949 | pole | HFTD Tier 2 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-03-21 | 2028-05-11 | Level 3 | GO 165 Inspection
126158530 | anchor/guy | HFTD Tier 3 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-05-21 | 2028-05-17 | Level 3 | GO 165 Inspection
126159382 | other | HFTD Tier 3 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126160155 | other | Non-HFTD | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126160266 | other | HFTD Tier 3 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F |  | 2028-05-11 | Level 3
126161441 | other | HFTD Tier 3 | Transmission | 2023-05-11 | 2028-05-11 | Level 3 | F | 2024-04-01 | 2028-05-11 | Level 3 | GO 165 Inspection
126162041 | other | Non-HFTD | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126162474 | pole | HFTD Tier 2 | Transmission | 2023-05-18 | 2024-05-18 | Level 2 | E | 2024-06-10 | 2024-05-18 | Level 2 | GO 165 Inspection
126162892 | insulator and brushing | Non-HFTD | Transmission | 2023-05-18 | 2026-05-18 | Level 2 | E |  | 2026-05-18 | Level 2
126163048 | other | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-04-17 | 2028-05-18 | Level 3 | GO 165 Inspection
126163435 | insulator and brushing | Non-HFTD | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-04-25 | 2028-05-18 | Level 3 | GO 165 Inspection
126163643 | other | HFTD Tier 3 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126164161 | other | Non-HFTD | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126164246 | other | Non-HFTD | Transmission | 2023-05-18 | 2026-05-18 | Level 2 | E |  | 2026-05-18 | Level 2
126165045 | pole | Non-HFTD | Transmission | 2023-05-18 | 2026-05-18 | Level 2 | E |  | 2026-05-18 | Level 2
126165537 | other | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-04-20 | 2028-05-18 | Level 3 | GO 165 Inspection
126165919 | pole | HFTD Tier 2 | Transmission | 2023-05-08 | 2024-05-08 | Level 2 | E | 2024-05-03 | 2024-05-08 | Level 2 | Field Safety Reassessment
126165965 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-05-11 | 2023-11-11 | Level 2 | E | 2024-05-23 | 2023-11-11 | Level 2 | Field Safety Reassessment
126166162 | pole | Non-HFTD | Transmission | 2023-05-18 | 2023-08-18 | Level 2 | E | 2024-10-02 | 2023-08-18 | Level 2 | GO 165 Inspection
126173355 | pole | Non-HFTD | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F |  | 2028-05-12 | Level 3
126173538 | other | HFTD Tier 3 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F | 2024-04-01 | 2028-05-12 | Level 3 | GO 165 Inspection
126173826 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-03-21 | 2028-05-15 | Level 3 | GO 165 Inspection
126174684 | pole | HFTD Tier 3 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F |  | 2028-05-12 | Level 3
126174842 | pole | Non-HFTD | Transmission | 2023-05-19 | 2026-05-19 | Level 2 | E |  | 2026-05-19 | Level 2
126175035 | insulator and brushing | Non-HFTD | Transmission | 2023-05-19 | 2026-05-19 | Level 2 | E | 2024-10-07 | 2026-05-19 | Level 2 | GO 165 Inspection
126175151 | other | HFTD Tier 3 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-06-04 | 2028-05-18 | Level 3 | GO 165 Inspection
126175309 | pole | HFTD Tier 3 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F | 2024-04-01 | 2028-05-12 | Level 3 | GO 165 Inspection
126178599 | pole | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-03-20 | 2028-05-15 | Level 3 | GO 165 Inspection
126186602 | other | HFTD Tier 2 | Transmission | 2023-05-19 | 2028-05-19 | Level 3 | F | 2024-05-28 | 2028-05-19 | Level 3 | GO 165 Inspection
126187564 | other | HFTD Tier 2 | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F | 2024-06-11 | 2028-05-12 | Level 3 | GO 165 Inspection
126187642 | other | Non-HFTD | Transmission | 2023-05-19 | 2024-05-19 | Level 2 | E | 2024-07-10 | 2024-05-19 | Level 2 | GO 165 Inspection
126189617 | pole | HFTD Tier 3 | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2024-05-29 | 2026-05-15 | Level 2 | GO 165 Inspection
126190057 | other | HFTD Tier 3 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-03-28 | 2028-05-17 | Level 3 | GO 165 Inspection
126192125 | other | Non-HFTD | Transmission | 2023-05-20 | 2028-05-20 | Level 3 | F |  | 2028-05-20 | Level 3
126192186 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-20 | 2028-05-20 | Level 3 | F | 2024-05-30 | 2028-05-20 | Level 3 | GO 165 Inspection
126193810 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-20 | 2028-05-20 | Level 3 | F | 2024-05-18 | 2028-05-20 | Level 3 | GO 165 Inspection
126194990 | pole | HFTD Tier 2 | Transmission | 2023-05-20 | 2024-05-20 | Level 2 | E | 2024-05-02 | 2024-05-20 | Level 2 | Field Safety Reassessment
126198270 | pole | HFTD Tier 2 | Transmission | 2023-05-20 | 2024-05-20 | Level 2 | E | 2024-10-19 | 2024-05-20 | Level 2 | Field Safety Reassessment
126199049 | other | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F |  | 2028-05-22 | Level 3
126201242 | other | Non-HFTD | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2024-10-18 | 2028-05-22 | Level 3 | GO 165 Inspection
126202014 | other | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F |  | 2028-05-22 | Level 3
126202158 | other | Non-HFTD | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2023-07-24 | 2028-05-22 | Level 3 | Field Safety Reassessment
126202312 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 2 | E | 2024-05-28 | 2024-05-22 | Level 2 | GO 165 Inspection
126205211 | pole | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F |  | 2028-05-22 | Level 3
126205300 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2024-05-16 | Level 2 | E |  | 2023-08-16 | Level 2
126205730 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126205772 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126206214 | other | Non-HFTD | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-10-03 | 2028-05-23 | Level 3 | GO 165 Inspection
126206812 | other | Non-HFTD | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-10-01 | 2028-05-23 | Level 3 | GO 165 Inspection
126207619 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-15 | 2024-05-15 | Level 2 | E | 2024-05-20 | 2024-05-15 | Level 2 | GO 165 Inspection
126207824 | pole | Non-HFTD | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-24 | 2028-05-23 | Level 3 | GO 165 Inspection
126207826 | insulator and brushing | Non-HFTD | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-24 | 2028-05-23 | Level 3 | GO 165 Inspection
126209095 | pole | Non-HFTD | Transmission | 2023-05-23 | 2026-05-23 | Level 2 | E | 2024-07-30 | 2026-05-23 | Level 2 | GO 165 Inspection
126209309 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-06-05 | 2028-05-23 | Level 3 | GO 165 Inspection
126209408 | pole | Non-HFTD | Transmission | 2023-05-23 | 2026-05-23 | Level 2 | E | 2024-07-29 | 2026-05-23 | Level 2 | GO 165 Inspection
126209910 | anchor/guy | Non-HFTD | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-04-18 | 2028-05-15 | Level 3 | GO 165 Inspection
126209956 | other | Non-HFTD | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2023-09-12 | 2028-05-23 | Level 3 | GO 165 Inspection
126210131 | other | Non-HFTD | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-11-01 | 2028-05-23 | Level 3 | GO 165 Inspection
126210491 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-18 | 2028-05-23 | Level 3 | GO 165 Inspection
126210946 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-06-01 | 2028-05-23 | Level 3 | GO 165 Inspection
126211393 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E | 2024-05-14 | 2024-05-23 | Level 2 | Field Safety Reassessment
126212303 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126212843 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-04-22 | 2028-05-15 | Level 3 | GO 165 Inspection
126212895 | pole | HFTD Tier 2 | Transmission | 2023-05-16 | 2026-05-16 | Level 2 | E | 2024-05-28 | 2026-05-16 | Level 2 | GO 165 Inspection
126212898 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-05-28 | 2028-05-16 | Level 3 | GO 165 Inspection
126212968 | pole | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F |  | 2028-05-15 | Level 3
126213148 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F |  | 2028-05-15 | Level 3
126213321 | other | HFTD Tier 3 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-23 | 2028-05-23 | Level 3 | GO 165 Inspection
126214552 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F |  | 2028-05-15 | Level 3
126215587 | other | HFTD Tier 2 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2024-04-24 | 2028-05-24 | Level 3 | GO 165 Inspection
126215982 | pole | Non-HFTD | Transmission | 2023-05-24 | 2026-05-24 | Level 2 | E |  | 2026-05-24 | Level 2
126216175 | other | HFTD Tier 2 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2024-06-15 | 2028-05-24 | Level 3 | GO 165 Inspection
126216333 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F |  | 2028-05-16 | Level 3
126216423 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F |  | 2028-05-16 | Level 3
126216806 | pole | Non-HFTD | Transmission | 2023-05-24 | 2026-05-24 | Level 2 | E |  | 2026-05-24 | Level 2
126217086 | pole | Non-HFTD | Transmission | 2023-05-24 | 2024-05-24 | Level 2 | E | 2024-05-08 | 2024-05-24 | Level 2 | GO 165 Inspection
126218268 | pole | Non-HFTD | Transmission | 2023-05-24 | 2026-05-24 | Level 2 | E |  | 2026-05-24 | Level 2
126218758 | other | HFTD Tier 3 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2024-06-11 | 2028-05-24 | Level 3 | GO 165 Inspection
126220961 | crossarm | HFTD Tier 3 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-05-16 | 2028-05-17 | Level 3 | GO 165 Inspection
126221014 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E |  | 2026-05-15 | Level 2
126221178 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F | 2024-06-01 | 2028-05-16 | Level 3 | GO 165 Inspection
126221212 | other | HFTD Tier 2 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F |  | 2028-05-24 | Level 3
126221273 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-17 | 2024-05-17 | Level 2 | E | 2024-05-08 | 2024-05-17 | Level 2 | Field Safety Reassessment
126221284 | other | HFTD Tier 3 | Transmission | 2023-05-15 | 2028-05-15 | Level 3 | F | 2024-04-19 | 2028-05-15 | Level 3 | GO 165 Inspection
126221293 | other | Non-HFTD | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2024-05-23 | 2028-05-24 | Level 3 | GO 165 Inspection
126221410 | other | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F |  | 2028-05-17 | Level 3
126221733 | crossarm | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-04-12 | 2028-05-17 | Level 3 | GO 165 Inspection
126221734 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F |  | 2028-05-17 | Level 3
126221774 | other | HFTD Tier 2 | Transmission | 2023-05-17 | 2024-05-17 | Level 2 | E | 2024-04-23 | 2024-05-17 | Level 2 | GO 165 Inspection
126224244 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F | 2024-04-19 | 2028-05-25 | Level 3 | GO 165 Inspection
126224277 | other | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F | 2024-05-28 | 2028-05-25 | Level 3 | GO 165 Inspection
126224533 | other | Non-HFTD | Transmission | 2023-05-25 | 2026-05-25 | Level 2 | E |  | 2026-05-25 | Level 2
126224763 | other | HFTD Tier 3 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126227605 | pole | Non-HFTD | Transmission | 2023-03-16 | 2026-03-16 | Level 2 | E | 2024-08-12 | 2026-03-16 | Level 2 | GO 165 Inspection
126227637 | other | Non-HFTD | Transmission | 2023-05-25 | 2026-05-25 | Level 2 | E | 2024-11-01 | 2026-05-25 | Level 2 | GO 165 Inspection
126227678 | other | Non-HFTD | Transmission | 2023-04-27 | 2028-04-27 | Level 3 | F |  | 2028-04-27 | Level 3
126227724 | pole | Non-HFTD | Transmission | 2023-05-25 | 2026-05-25 | Level 2 | E | 2024-11-01 | 2026-05-25 | Level 2 | GO 165 Inspection
126227830 | other | Non-HFTD | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F |  | 2028-04-28 | Level 3
126228785 | other | Non-HFTD | Transmission | 2023-05-25 | 2026-05-25 | Level 3 | F | 2024-10-22 | 2028-05-25 | Level 3 | GO 165 Inspection
126228972 | other | Non-HFTD | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F |  | 2028-04-28 | Level 3
126229204 | pole | Non-HFTD | Transmission | 2023-04-28 | 2026-04-28 | Level 2 | E |  | 2026-04-28 | Level 2
126229653 | other | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126229842 | crossarm | Non-HFTD | Transmission | 2023-05-01 | 2026-05-01 | Level 2 | E |  | 2026-05-01 | Level 2
126229916 | pole | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F |  | 2028-05-17 | Level 3
126229968 | other | HFTD Tier 2 | Transmission | 2023-05-19 | 2028-05-19 | Level 3 | F | 2024-05-24 | 2028-05-19 | Level 3 | GO 165 Inspection
126230186 | pole | HFTD Tier 2 | Transmission | 2023-05-16 | 2024-05-16 | Level 2 | E | 2024-03-08 | 2024-05-16 | Level 2 | Field Safety Reassessment
126230220 | insulator and brushing | Non-HFTD | Transmission | 2023-05-03 | 2026-05-03 | Level 2 | E |  | 2026-05-03 | Level 2
126230325 | pole | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-02-01 | 2028-05-18 | Level 3 | GO 165 Inspection
126230346 | insulator and brushing | Non-HFTD | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126230462 | other | Non-HFTD | Transmission | 2023-05-03 | 2026-05-03 | Level 2 | E |  | 2026-05-03 | Level 2
126230538 | other | HFTD Tier 2 | Transmission | 2023-05-18 | 2024-05-18 | Level 2 | E | 2024-05-08 | 2024-05-18 | Level 2 | Field Safety Reassessment
126230554 | pole | Non-HFTD | Transmission | 2023-05-03 | 2028-05-03 | Level 3 | F |  | 2028-05-03 | Level 3
126230586 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-06-12 | 2028-05-18 | Level 3 | GO 165 Inspection
126230663 | pole | HFTD Tier 2 | Transmission | 2023-05-18 | 2024-05-18 | Level 2 | E | 2024-04-11 | 2024-05-18 | Level 2 | GO 165 Inspection
126232255 | other | HFTD Tier 2 | Transmission | 2023-05-19 | 2028-05-19 | Level 3 | F | 2024-05-30 | 2028-05-19 | Level 3 | GO 165 Inspection
126232319 | pole | HFTD Tier 3 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126232424 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126232941 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126233149 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F | 2024-07-26 | 2028-05-26 | Level 3 | GO 165 Inspection
126233362 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F | 2024-07-26 | 2028-05-26 | Level 3 | GO 165 Inspection
126233511 | other | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2024-02-13 | 2028-05-22 | Level 3 | GO 165 Inspection
126233668 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126234345 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F | 2024-05-22 | 2028-05-26 | Level 3 | GO 165 Inspection
126234529 | insulator and brushing | Non-HFTD | Transmission | 2023-05-05 | 2026-05-05 | Level 2 | E | 2024-05-29 | 2026-05-05 | Level 2 | GO 165 Inspection
126234571 | pole | Non-HFTD | Transmission | 2023-05-05 | 2026-05-05 | Level 2 | E | 2024-05-29 | 2026-05-05 | Level 2 | GO 165 Inspection
126234587 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126235022 | insulator and brushing | Non-HFTD | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E |  | 2026-05-26 | Level 2
126235275 | pole | HFTD Tier 3 | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E | 2024-06-05 | 2026-05-26 | Level 2 | GO 165 Inspection
126235461 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F |  | 2028-05-18 | Level 3
126235584 | other | HFTD Tier 2 | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F | 2024-06-15 | 2028-05-26 | Level 3 | GO 165 Inspection
126235696 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-04-24 | 2028-05-23 | Level 3 | GO 165 Inspection
126235972 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F | 2024-11-08 | 2028-05-26 | Level 3 | GO 165 Inspection
126236587 | other | HFTD Tier 2 | Transmission | 2023-05-16 | 2028-05-16 | Level 3 | F |  | 2028-05-16 | Level 3
126237296 | insulator and brushing | Non-HFTD | Transmission | 2023-05-12 | 2028-05-12 | Level 3 | F |  | 2028-05-12 | Level 3
126237322 | splice | HFTD Tier 3 | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E |  | 2026-05-26 | Level 2
126237583 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E | 2024-04-03 | 2024-05-23 | Level 2 | GO 165 Inspection
126237849 | crossarm | HFTD Tier 2 | Transmission | 2023-05-19 | 2024-05-19 | Level 2 | E | 2024-05-08 | 2024-05-19 | Level 2 | GO 165 Inspection
126238414 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-18 | 2024-05-18 | Level 2 | E | 2024-05-15 | 2024-05-18 | Level 2 | Field Safety Reassessment
126238418 | pole | HFTD Tier 2 | Transmission | 2023-05-18 | 2024-05-18 | Level 2 | E | 2024-06-15 | 2024-05-18 | Level 2 | GO 165 Inspection
126238560 | other | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2023-06-09 | 2028-05-22 | Level 3 | GO 165 Inspection
126238898 | other | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-04-24 | 2028-05-18 | Level 3 | GO 165 Inspection
126240183 | pole | HFTD Tier 2 | Transmission | 2023-05-18 | 2024-05-18 | Level 2 | E | 2024-04-10 | 2024-05-18 | Level 2 | GO 165 Inspection
126240210 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-18 | 2028-05-18 | Level 3 | F | 2024-06-12 | 2028-05-18 | Level 3 | GO 165 Inspection
126240258 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E |  | 2024-05-23 | Level 2
126240283 | pole | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2024-05-29 | 2028-05-22 | Level 3 | GO 165 Inspection
126240295 | conductor | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E |  | 2024-05-23 | Level 2
126240421 | other | HFTD Tier 3 | Transmission | 2023-05-18 | 2026-05-18 | Level 2 | E |  | 2026-05-18 | Level 2
126240435 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2023-06-12 | 2028-05-23 | Level 3 | GO 165 Inspection
126240467 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-22 | 2028-05-23 | Level 3 | GO 165 Inspection
126240545 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-19 | 2028-05-19 | Level 3 | F | 2023-06-19 | 2028-05-19 | Level 3 | GO 165 Inspection
126240925 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2023-06-16 | 2028-05-23 | Level 3 | GO 165 Inspection
126240978 | other | HFTD Tier 2 | Transmission | 2023-05-17 | 2028-05-17 | Level 3 | F | 2024-06-13 | 2028-05-17 | Level 3 | GO 165 Inspection
126241021 | other | HFTD Tier 3 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2024-05-16 | 2028-05-22 | Level 3 | GO 165 Inspection
126244144 | other | HFTD Tier 2 | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2024-05-20 | 2026-05-15 | Level 2 | GO 165 Inspection
126244866 | pole | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-04-19 | 2028-05-30 | Level 3 | GO 165 Inspection
126244906 | other | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126247341 | splice | HFTD Tier 3 | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E | 2024-05-07 | 2026-05-30 | Level 2 | GO 165 Inspection
126247645 | pole | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E | 2024-07-19 | 2026-05-30 | Level 2 | GO 165 Inspection
126247829 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-05-20 | 2028-05-30 | Level 3 | GO 165 Inspection
126248348 | other | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-04-30 | 2028-05-30 | Level 3 | GO 165 Inspection
126249475 | other | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126249501 | other | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126250709 | other | HFTD Tier 2 | Transmission | 2023-05-19 | 2028-05-19 | Level 3 | F |  | 2028-05-19 | Level 3
126251087 | switch | HFTD Tier 3 | Transmission | 2023-05-19 | 2023-11-19 | Level 2 | E | 2024-09-19 | 2023-11-19 | Level 2 | Field Safety Reassessment
126251249 | other | HFTD Tier 3 | Transmission | 2023-05-19 | 2028-05-19 | Level 3 | F |  | 2028-05-19 | Level 3
126251273 | other | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E |  | 2026-05-30 | Level 2
126251361 | other | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126251874 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-04-26 | 2028-05-23 | Level 3 | GO 165 Inspection
126252037 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-02-26 | 2028-05-23 | Level 3 | GO 165 Inspection
126252092 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2023-06-15 | 2028-05-23 | Level 3 | GO 165 Inspection
126252134 | other | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126252163 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E | 2024-06-18 | 2024-05-23 | Level 2 | GO 165 Inspection
126252164 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E | 2024-06-18 | 2024-05-23 | Level 2 | GO 165 Inspection
126252300 | other | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E |  | 2026-05-30 | Level 2
126252336 | other | HFTD Tier 2 | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E | 2024-04-26 | 2026-05-30 | Level 2 | GO 165 Inspection
126252873 | conductor | HFTD Tier 2 | Transmission | 2023-05-19 | 2024-05-19 | Level 2 | E | 2024-03-19 | 2024-05-19 | Level 2 | GO 165 Inspection
126252898 | pole | Non-HFTD | Transmission | 2023-04-17 | 2026-04-17 | Level 2 | E |  | 2026-04-17 | Level 2
126253494 | other | Non-HFTD | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-07-10 | 2028-05-31 | Level 3 | GO 165 Inspection
126254043 | pole | Non-HFTD | Transmission | 2023-05-09 | 2026-05-09 | Level 2 | E |  | 2026-05-09 | Level 2
126254457 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-04-27 | 2028-05-31 | Level 3 | GO 165 Inspection
126254485 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-18 | 2026-05-18 | Level 2 | E | 2024-04-12 | 2026-05-18 | Level 2 | GO 165 Inspection
126254693 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-05-31 | 2024-05-31 | Level 2 | E |  | 2024-05-31 | Level 2
126254854 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-04-27 | 2028-05-31 | Level 3 | GO 165 Inspection
126256605 | other | Non-HFTD | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126256634 | other | Non-HFTD | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126256780 | other | Non-HFTD | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126256878 | other | HFTD Tier 2 | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2024-04-11 | 2028-05-22 | Level 3 | GO 165 Inspection
126256881 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126257013 | other | Non-HFTD | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-07-18 | 2028-05-31 | Level 3 | GO 165 Inspection
126258202 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126258252 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126258406 | pole | HFTD Tier 2 | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E | 2024-05-23 | 2026-05-31 | Level 2 | GO 165 Inspection
126258524 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126259429 | other | Non-HFTD | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E |  | 2026-05-31 | Level 2
126259463 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2024-05-31 | Level 3 | F | 2024-03-18 | 2028-05-31 | Level 3 | GO 165 Inspection
126259466 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2024-05-31 | Level 2 | E | 2024-04-20 | 2024-05-31 | Level 2 | GO 165 Inspection
126262280 | other | HFTD Tier 3 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F |  | 2028-06-01 | Level 3
126263036 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-21 | 2028-05-23 | Level 3 | GO 165 Inspection
126263739 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-05-21 | 2028-05-23 | Level 3 | GO 165 Inspection
126265008 | pole | Non-HFTD | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F |  | 2028-05-31 | Level 3
126267185 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F |  | 2028-06-01 | Level 3
126267627 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-04-26 | 2028-06-01 | Level 3 | GO 165 Inspection
126267793 | anchor/guy | Non-HFTD | Transmission | 2023-05-22 | 2028-05-22 | Level 3 | F | 2024-05-28 | 2028-05-22 | Level 3 | GO 165 Inspection
126269934 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-13 | 2028-06-02 | Level 3 | GO 165 Inspection
126272059 | other | HFTD Tier 2 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2023-06-14 | 2028-05-24 | Level 3 | GO 165 Inspection
126276192 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F |  | 2028-06-02 | Level 3
126276249 | other | Non-HFTD | Transmission | 2023-06-02 | 2026-06-02 | Level 2 | E |  | 2026-06-02 | Level 2
126277581 | insulator and brushing | Non-HFTD | Transmission | 2023-05-25 | 2024-05-25 | Level 2 | E | 2024-07-17 | 2024-05-25 | Level 2 | GO 165 Inspection
126277744 | other | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F | 2023-06-07 | 2028-05-25 | Level 3 | GO 165 Inspection
126278197 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2024-06-02 | Level 2 | E | 2024-08-31 | 2024-06-02 | Level 2 | Field Safety Reassessment
126278637 | other | Non-HFTD | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F |  | 2028-06-02 | Level 3
126278834 | other | HFTD Tier 2 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2023-06-14 | 2028-05-24 | Level 3 | GO 165 Inspection
126279378 | anchor/guy | HFTD Tier 3 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-24 | 2028-06-02 | Level 3 | GO 165 Inspection
126280363 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F | 2023-06-14 | 2028-05-25 | Level 3 | GO 165 Inspection
126280829 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-30 | 2028-06-02 | Level 3 | GO 165 Inspection
126280867 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-29 | 2028-06-02 | Level 3 | GO 165 Inspection
126281511 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126281514 | crossarm | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F | 2024-04-30 | 2028-05-25 | Level 3 | GO 165 Inspection
126281775 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-04-17 | 2028-06-02 | Level 3 | GO 165 Inspection
126282181 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126282412 | other | HFTD Tier 3 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F |  | 2028-06-02 | Level 3
126282468 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-31 | 2028-06-02 | Level 3 | GO 165 Inspection
126282693 | other | Non-HFTD | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126283109 | crossarm | Non-HFTD | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2024-05-22 | 2028-05-24 | Level 3 | GO 165 Inspection
126283132 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126283289 | other | HFTD Tier 2 | Transmission | 2023-05-24 | 2028-05-24 | Level 3 | F | 2024-06-06 | 2028-05-24 | Level 3 | GO 165 Inspection
126283471 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126283584 | pole | HFTD Tier 2 | Transmission | 2023-05-25 | 2026-05-25 | Level 2 | E | 2024-05-14 | 2026-05-25 | Level 2 | GO 165 Inspection
126283730 | conductor | HFTD Tier 2 | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126284203 | pole | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F | 2024-03-06 | 2028-06-03 | Level 3 | GO 165 Inspection
126284330 | other | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-04-24 | 2028-05-23 | Level 3 | GO 165 Inspection
126284714 | other | HFTD Tier 3 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126284794 | pole | HFTD Tier 2 | Transmission | 2023-05-26 | 2024-05-26 | Level 2 | E | 2024-12-05 | 2024-05-26 | Level 2 | Field Safety Reassessment
126285090 | pole | Non-HFTD | Transmission | 2023-06-03 | 2026-06-03 | Level 2 | E | 2024-08-08 | 2026-06-03 | Level 2 | GO 165 Inspection
126285348 | pole | Non-HFTD | Transmission | 2023-06-03 | 2026-06-03 | Level 2 | E | 2024-08-20 | 2026-06-03 | Level 2 | GO 165 Inspection
126285677 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F |  | 2028-06-03 | Level 3
126285754 | pole | HFTD Tier 2 | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126286030 | other | Non-HFTD | Transmission | 2023-06-03 | 2026-06-03 | Level 2 | E | 2024-08-22 | 2026-06-03 | Level 2 | GO 165 Inspection
126286339 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F | 2024-03-13 | 2028-06-03 | Level 3 | GO 165 Inspection
126286810 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-03 | 2024-06-03 | Level 2 | E | 2024-05-08 | 2024-06-03 | Level 2 | GO 165 Inspection
126286811 | pole | HFTD Tier 2 | Transmission | 2023-06-03 | 2024-06-03 | Level 2 | E | 2024-05-10 | 2024-06-03 | Level 2 | GO 165 Inspection
126286815 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-03 | 2024-06-03 | Level 2 | E | 2024-05-10 | 2023-12-03 | Level 2 | GO 165 Inspection
126289234 | other | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-06-14 | 2028-06-05 | Level 3 | GO 165 Inspection
126291988 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F |  | 2028-05-23 | Level 3
126292119 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126292602 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2028-05-23 | Level 3 | F | 2024-04-24 | 2028-05-23 | Level 3 | GO 165 Inspection
126293051 | other | HFTD Tier 2 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F | 2023-06-10 | 2028-05-25 | Level 3 | GO 165 Inspection
126294497 | pole | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E |  | 2026-06-05 | Level 2
126295930 | pole | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E |  | 2026-06-05 | Level 2
126296164 | other | HFTD Tier 2 | Transmission | 2023-06-05 | 2024-06-05 | Level 3 | F | 2024-05-30 | 2028-06-05 | Level 3 | GO 165 Inspection
126296214 | insulator and brushing | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2024-09-19 | 2026-06-05 | Level 2 | GO 165 Inspection
126296638 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126296824 | other | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E |  | 2026-06-05 | Level 2
126296946 | other | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F |  | 2028-06-05 | Level 3
126297153 | pole | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-04-23 | 2028-06-05 | Level 3 | GO 165 Inspection
126297450 | other | HFTD Tier 3 | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E | 2024-04-29 | 2026-05-30 | Level 2 | GO 165 Inspection
126297540 | pole | Non-HFTD | Transmission | 2023-06-05 | 2028-06-05 | Level 2 | E | 2024-11-27 | 2026-06-05 | Level 2 | GO 165 Inspection
126297821 | pole | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E |  | 2026-06-05 | Level 2
126297850 | other | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-05-08 | 2028-06-05 | Level 3 | GO 165 Inspection
126298421 | anchor/guy | Non-HFTD | Transmission | 2023-06-05 | 2024-06-05 | Level 2 | E | 2024-07-19 | 2024-06-05 | Level 2 | GO 165 Inspection
126298729 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E | 2024-03-14 | 2026-05-26 | Level 2 | GO 165 Inspection
126298828 | pole | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126298986 | pole | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-05-23 | 2028-05-30 | Level 3 | GO 165 Inspection
126299016 | pole | HFTD Tier 2 | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126299677 | other | HFTD Tier 2 | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F | 2024-03-12 | 2028-06-06 | Level 3 | GO 165 Inspection
126299888 | other | Non-HFTD | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E |  | 2026-05-26 | Level 2
126300583 | pole | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E |  | 2026-06-06 | Level 2
126300714 | other | Non-HFTD | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126300717 | other | Non-HFTD | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126303019 | other | HFTD Tier 3 | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F |  | 2028-06-06 | Level 3
126303043 | insulator and brushing | Non-HFTD | Transmission | 2023-05-25 | 2026-05-25 | Level 2 | E |  | 2026-05-25 | Level 2
126303411 | other | Non-HFTD | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126303578 | splice | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-07-16 | 2026-06-06 | Level 2 | GO 165 Inspection
126303629 | other | Non-HFTD | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F | 2024-10-17 | 2028-06-06 | Level 3 | GO 165 Inspection
126304181 | pole | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E |  | 2026-06-06 | Level 2
126304410 | other | Non-HFTD | Transmission | 2023-06-06 | 2024-06-06 | Level 2 | E | 2024-04-20 | 2024-06-06 | Level 2 | GO 165 Inspection
126304411 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F | 2024-05-29 | 2028-06-06 | Level 3 | GO 165 Inspection
126305291 | pole | Non-HFTD | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E |  | 2026-05-26 | Level 2
126305620 | pole | Non-HFTD | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E |  | 2026-05-26 | Level 2
126305753 | insulator and brushing | Non-HFTD | Transmission | 2023-05-26 | 2026-05-26 | Level 2 | E |  | 2026-05-26 | Level 2
126305828 | insulator and brushing | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E |  | 2026-06-06 | Level 2
126305850 | anchor/guy | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E | 2024-11-13 | 2024-05-30 | Level 2 | GO 165 Inspection
126306141 | other | HFTD Tier 3 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-05-18 | 2028-05-30 | Level 3 | GO 165 Inspection
126306201 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-04-18 | 2028-05-31 | Level 3 | GO 165 Inspection
126306206 | other | HFTD Tier 2 | Transmission | 2023-05-26 | 2028-05-26 | Level 3 | F |  | 2028-05-26 | Level 3
126306309 | pole | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-06-19 | 2028-05-30 | Level 3 | GO 165 Inspection
126306355 | pole | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-11-05 | 2028-05-30 | Level 3 | GO 165 Inspection
126306511 | insulator and brushing | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E | 2024-11-04 | 2026-05-30 | Level 2 | GO 165 Inspection
126306784 | other | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-07-22 | 2028-05-30 | Level 3 | GO 165 Inspection
126306889 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E | 2024-06-07 | 2026-05-31 | Level 2 | GO 165 Inspection
126306900 | pole | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-11-14 | 2028-05-30 | Level 3 | GO 165 Inspection
126306933 | pole | HFTD Tier 3 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126307005 | other | HFTD Tier 3 | Transmission | 2023-05-30 | 2023-11-30 | Level 3 | F | 2024-04-29 | 2028-05-30 | Level 3 | GO 165 Inspection
126307063 | other | HFTD Tier 2 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-04-18 | 2028-05-30 | Level 3 | GO 165 Inspection
126307087 | pole | HFTD Tier 2 | Transmission | 2023-05-30 | 2024-05-30 | Level 2 | E | 2024-03-20 | 2024-05-30 | Level 2 | GO 165 Inspection
126307212 | other | HFTD Tier 3 | Transmission | 2023-05-25 | 2028-05-25 | Level 3 | F |  | 2028-05-25 | Level 3
126307873 | other | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-04-11 | 2028-06-07 | Level 3 | GO 165 Inspection
126308254 | other | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F |  | 2028-05-30 | Level 3
126308769 | other | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-04-17 | 2028-06-07 | Level 3 | GO 165 Inspection
126309789 | other | HFTD Tier 3 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-03-22 | 2028-06-07 | Level 3 | GO 165 Inspection
126310086 | other | HFTD Tier 3 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-02-21 | 2028-06-07 | Level 3 | GO 165 Inspection
126310365 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-07 | 2024-06-07 | Level 2 | E | 2024-05-20 | 2024-06-07 | Level 2 | GO 165 Inspection
126310519 | other | Non-HFTD | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E |  | 2026-06-01 | Level 2
126310654 | other | Non-HFTD | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E |  | 2026-06-01 | Level 2
126310740 | other | Non-HFTD | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E |  | 2026-06-01 | Level 2
126311050 | other | HFTD Tier 3 | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2024-03-19 | 2028-05-30 | Level 3 | GO 165 Inspection
126313446 | pole | Non-HFTD | Transmission | 2023-06-07 | 2026-06-07 | Level 2 | E |  | 2026-06-07 | Level 2
126314180 | other | HFTD Tier 2 | Transmission | 2023-06-05 | 2024-06-05 | Level 2 | E |  | 2024-06-05 | Level 2
126314285 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2024-05-31 | Level 2 | E | 2024-04-24 | 2024-05-31 | Level 2 | GO 165 Inspection
126314695 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-04-16 | 2028-05-31 | Level 3 | GO 165 Inspection
126314929 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-05-31 | 2028-05-31 | Level 3 | GO 165 Inspection
126315085 | pole | HFTD Tier 2 | Transmission | 2023-06-01 | 2024-06-01 | Level 2 | E |  | 2024-06-01 | Level 2
126315162 | other | HFTD Tier 3 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-04-09 | 2028-05-31 | Level 3 | GO 165 Inspection
126315173 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-04-16 | 2028-06-01 | Level 3 | GO 165 Inspection
126315223 | other | HFTD Tier 2 | Transmission | 2023-05-31 | 2028-05-31 | Level 3 | F | 2024-03-13 | 2028-05-31 | Level 3 | GO 165 Inspection
126315244 | other | HFTD Tier 2 | Transmission | 2023-05-30 | 2024-05-30 | Level 2 | E | 2024-04-26 | 2024-05-30 | Level 2 | GO 165 Inspection
126315347 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E |  | 2026-05-30 | Level 2
126315380 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-03-13 | 2028-06-01 | Level 3 | GO 165 Inspection
126316689 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126317981 | pole | Non-HFTD | Transmission | 2023-06-08 | 2024-06-08 | Level 2 | E |  | 2024-06-08 | Level 2
126318219 | pole | Non-HFTD | Transmission | 2023-06-08 | 2026-06-08 | Level 2 | E |  | 2026-06-08 | Level 2
126318870 | pole | HFTD Tier 2 | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E | 2024-04-17 | 2026-05-31 | Level 2 | GO 165 Inspection
126320043 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126320858 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126321195 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-06-06 | 2028-06-08 | Level 3 | GO 165 Inspection
126322082 | other | HFTD Tier 3 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F |  | 2028-06-01 | Level 3
126322289 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126322295 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E |  | 2026-06-01 | Level 2
126322455 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-08 | 2026-06-08 | Level 2 | E | 2024-07-20 | 2024-06-08 | Level 2 | Field Safety Reassessment
126322480 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-03-21 | 2028-06-01 | Level 3 | GO 165 Inspection
126322635 | pole | HFTD Tier 2 | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E | 2024-05-29 | 2026-05-31 | Level 2 | GO 165 Inspection
126322688 | other | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-07-18 | 2028-06-01 | Level 3 | GO 165 Inspection
126322713 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-01 | 2024-06-01 | Level 2 | E | 2024-03-20 | 2024-06-01 | Level 2 | GO 165 Inspection
126323002 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-08 | 2023-09-08 | Level 2 | E | 2024-07-08 | 2023-09-08 | Level 2 | Field Safety Reassessment
126324166 | anchor/guy | HFTD Tier 3 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F |  | 2028-06-03 | Level 3
126324346 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F |  | 2028-06-03 | Level 3
126324465 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-03-12 | 2028-06-01 | Level 3 | GO 165 Inspection
126324858 | other | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-03-15 | 2028-06-05 | Level 3 | GO 165 Inspection
126325345 | pole | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-03-18 | 2028-06-02 | Level 3 | GO 165 Inspection
126325566 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F |  | 2028-06-03 | Level 3
126325621 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-20 | 2028-06-02 | Level 3 | GO 165 Inspection
126325672 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-02-28 | 2028-06-02 | Level 3 | GO 165 Inspection
126326159 | other | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-04-26 | 2028-06-01 | Level 3 | GO 165 Inspection
126327583 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F | 2024-06-03 | 2028-06-03 | Level 3 | GO 165 Inspection
126327800 | pole | HFTD Tier 3 | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E | 2024-04-30 | 2026-06-01 | Level 2 | GO 165 Inspection
126327845 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126327881 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F |  | 2028-06-02 | Level 3
126328212 | other | Non-HFTD | Transmission | 2023-06-09 | 2026-06-09 | Level 2 | E | 2024-09-13 | 2026-06-09 | Level 2 | GO 165 Inspection
126328259 | pole | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-03-13 | 2028-06-01 | Level 3 | GO 165 Inspection
126328432 | other | HFTD Tier 3 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-06-06 | 2028-06-01 | Level 3 | GO 165 Inspection
126328433 | other | HFTD Tier 3 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-06-06 | 2028-06-01 | Level 3 | GO 165 Inspection
126328646 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F |  | 2028-06-03 | Level 3
126329099 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-02-26 | 2028-06-02 | Level 3 | GO 165 Inspection
126329226 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-03 | 2024-06-03 | Level 2 | E | 2024-05-29 | 2024-06-03 | Level 2 | Field Safety Reassessment
126329324 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-02-29 | 2028-06-05 | Level 3 | GO 165 Inspection
126329410 | pole | HFTD Tier 3 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F |  | 2028-06-05 | Level 3
126329597 | other | HFTD Tier 3 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126329940 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-03-25 | 2028-06-01 | Level 3 | GO 165 Inspection
126330232 | anchor/guy | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-10-24 | 2026-06-06 | Level 2 | GO 165 Inspection
126330800 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 2 | E | 2024-04-24 | 2026-06-03 | Level 2 | GO 165 Inspection
126330807 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F | 2023-06-17 | 2028-06-03 | Level 3 | GO 165 Inspection
126331371 | other | Non-HFTD | Transmission | 2023-06-09 | 2026-06-09 | Level 2 | E |  | 2026-06-09 | Level 2
126340916 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-02-28 | 2028-06-02 | Level 3 | GO 165 Inspection
126341247 | other | Non-HFTD | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-11-13 | 2028-06-05 | Level 3 | GO 165 Inspection
126341489 | other | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-06-03 | 2028-06-07 | Level 3 | GO 165 Inspection
126341631 | other | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-04-12 | 2028-06-07 | Level 3 | GO 165 Inspection
126341783 | other | HFTD Tier 2 | Transmission | 2023-06-03 | 2028-06-03 | Level 3 | F |  | 2028-06-03 | Level 3
126341972 | pole | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-05-17 | 2028-06-05 | Level 3 | GO 165 Inspection
126342354 | pole | HFTD Tier 2 | Transmission | 2023-06-02 | 2024-06-02 | Level 2 | E | 2024-03-22 | 2024-06-02 | Level 2 | GO 165 Inspection
126342418 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2023-06-13 | 2026-06-05 | Level 2 | GO 165 Inspection
126342668 | insulator and brushing | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-10-17 | 2026-06-06 | Level 2 | GO 165 Inspection
126342736 | other | Non-HFTD | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-11-01 | 2028-06-07 | Level 3 | GO 165 Inspection
126342753 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F |  | 2028-06-05 | Level 3
126343357 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F | 2024-06-14 | 2028-06-10 | Level 3 | GO 165 Inspection
126343372 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F |  | 2028-06-05 | Level 3
126343480 | other | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-04-11 | 2028-06-07 | Level 3 | GO 165 Inspection
126343680 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126343951 | other | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-10-16 | 2026-06-06 | Level 2 | GO 165 Inspection
126344387 | other | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F |  | 2028-06-07 | Level 3
126344740 | other | Non-HFTD | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126344951 | insulator and brushing | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2024-10-14 | 2026-06-05 | Level 2 | GO 165 Inspection
126345068 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F | 2024-03-18 | 2028-06-06 | Level 3 | GO 165 Inspection
126345184 | pole | HFTD Tier 2 | Transmission | 2023-06-10 | 2024-06-10 | Level 2 | E | 2024-03-19 | 2024-06-10 | Level 2 | GO 165 Inspection
126345606 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F | 2024-07-18 | 2028-06-10 | Level 3 | Field Safety Reassessment
126346106 | pole | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-04-19 | 2028-06-05 | Level 3 | GO 165 Inspection
126346122 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-08 | 2026-06-08 | Level 2 | E | 2024-04-17 | 2026-06-08 | Level 2 | GO 165 Inspection
126346126 | other | HFTD Tier 3 | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F | 2024-07-23 | 2028-06-06 | Level 3 | Field Safety Reassessment
126346296 | pole | HFTD Tier 2 | Transmission | 2023-06-05 | 2028-06-05 | Level 2 | E | 2024-04-05 | 2024-06-05 | Level 2 | GO 165 Inspection
126347043 | other | HFTD Tier 2 | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F |  | 2028-06-06 | Level 3
126347200 | pole | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-08 | 2028-06-08 | Level 3 | GO 165 Inspection
126347217 | other | Non-HFTD | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126347221 | other | HFTD Tier 3 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F | 2024-04-24 | 2028-06-09 | Level 3 | Field Safety Reassessment
126347228 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126347345 | pole | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-04-18 | 2028-06-08 | Level 3 | GO 165 Inspection
126347373 | pole | HFTD Tier 2 | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-06-12 | 2028-06-07 | Level 3 | GO 165 Inspection
126347378 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F | 2023-06-17 | 2028-06-09 | Level 3 | GO 165 Inspection
126347410 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F | 2024-06-05 | 2028-06-10 | Level 3 | GO 165 Inspection
126347522 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F | 2024-05-17 | 2028-06-02 | Level 3 | GO 165 Inspection
126347565 | pole | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126347672 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F | 2024-01-30 | 2028-06-09 | Level 3 | GO 165 Inspection
126347736 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-09 | 2028-06-08 | Level 3 | GO 165 Inspection
126347795 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-01 | 2028-06-08 | Level 3 | GO 165 Inspection
126347796 | pole | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-10 | 2028-06-08 | Level 3 | GO 165 Inspection
126347856 | other | HFTD Tier 3 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126347905 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126347931 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126348037 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-01 | 2028-06-08 | Level 3 | GO 165 Inspection
126348101 | pole | HFTD Tier 2 | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-03-12 | 2028-06-01 | Level 3 | GO 165 Inspection
126348599 | other | Non-HFTD | Transmission | 2023-06-11 | 2026-06-11 | Level 2 | E |  | 2026-06-11 | Level 2
126348787 | other | Non-HFTD | Transmission | 2023-06-11 | 2026-06-11 | Level 3 | F |  | 2028-06-11 | Level 3
126348809 | other | HFTD Tier 2 | Transmission | 2023-06-11 | 2024-06-11 | Level 3 | F |  | 2028-06-11 | Level 3
126348818 | other | Non-HFTD | Transmission | 2023-06-11 | 2026-06-11 | Level 3 | F |  | 2028-06-11 | Level 3
126350212 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126351133 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-01-30 | 2028-06-08 | Level 3 | GO 165 Inspection
126352962 | other | Non-HFTD | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126353045 | other | Non-HFTD | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126353577 | pole | Non-HFTD | Transmission | 2023-05-30 | 2026-05-30 | Level 2 | E |  | 2026-05-30 | Level 2
126354413 | other | Non-HFTD | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E |  | 2026-05-31 | Level 2
126354514 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126354570 | insulator and brushing | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-10-15 | 2026-06-06 | Level 2 | GO 165 Inspection
126354647 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-04 | 2028-06-12 | Level 3 | GO 165 Inspection
126355321 | pole | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126355639 | other | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-30 | 2028-06-12 | Level 3 | GO 165 Inspection
126357740 | other | Non-HFTD | Transmission | 2023-05-30 | 2028-05-30 | Level 3 | F | 2023-08-05 | 2028-05-30 | Level 3 | GO 165 Inspection
126357782 | insulator and brushing | Non-HFTD | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E | 2024-04-23 | 2026-06-01 | Level 2 | GO 165 Inspection
126361201 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126361356 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F | 2024-04-20 | 2028-06-13 | Level 3 | GO 165 Inspection
126361442 | insulator and brushing | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2024-10-08 | 2026-06-05 | Level 2 | GO 165 Inspection
126361829 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-12-09 | 2024-06-13 | Level 2 | Field Safety Reassessment
126362358 | other | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2024-10-24 | 2026-06-05 | Level 2 | GO 165 Inspection
126362547 | conductor | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E |  | 2024-06-13 | Level 2
126362798 | other | Non-HFTD | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E |  | 2026-06-01 | Level 2
126363587 | other | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2024-10-24 | 2026-06-05 | Level 2 | GO 165 Inspection
126364376 | other | Non-HFTD | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-09-09 | 2024-06-13 | Level 2 | GO 165 Inspection
126364566 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E | 2024-05-10 | 2026-06-13 | Level 2 | GO 165 Inspection
126365016 | other | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-01 | 2028-06-08 | Level 3 | GO 165 Inspection
126365023 | pole | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-23 | 2028-06-08 | Level 3 | GO 165 Inspection
126365240 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126365243 | pole | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F |  | 2028-06-08 | Level 3
126365350 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F | 2024-01-30 | 2028-06-09 | Level 3 | GO 165 Inspection
126365383 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126365478 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126365608 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126365641 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-08 | 2028-06-08 | Level 3 | F | 2024-05-31 | 2028-06-08 | Level 3 | GO 165 Inspection
126365691 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126365823 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126366908 | pole | Non-HFTD | Transmission | 2023-06-05 | 2026-06-05 | Level 2 | E | 2024-10-09 | 2026-06-05 | Level 2 | GO 165 Inspection
126369257 | pole | Non-HFTD | Transmission | 2023-06-14 | 2026-06-14 | Level 2 | E | 2024-07-26 | 2026-06-14 | Level 2 | GO 165 Inspection
126370676 | pole | Non-HFTD | Transmission | 2023-06-14 | 2024-06-14 | Level 2 | E | 2024-05-10 | 2024-06-14 | Level 2 | GO 165 Inspection
126370928 | other | Non-HFTD | Transmission | 2023-06-14 | 2023-09-14 | Level 2 | E |  | 2023-09-14 | Level 2
126371420 | anchor/guy | Non-HFTD | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-09-06 | 2028-06-14 | Level 3 | GO 165 Inspection
126372934 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F |  | 2028-06-14 | Level 3
126373284 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-05-21 | 2028-06-14 | Level 3 | GO 165 Inspection
126373700 | other | Non-HFTD | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-06-01 | 2028-06-14 | Level 3 | GO 165 Inspection
126374897 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126375467 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F | 2024-07-20 | 2028-06-09 | Level 3 | Field Safety Reassessment
126375480 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126375488 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126375545 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126375549 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126375640 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126375789 | other | HFTD Tier 2 | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126377106 | pole | HFTD Tier 2 | Transmission | 2023-05-23 | 2024-05-23 | Level 2 | E | 2024-03-18 | 2024-05-23 | Level 2 | GO 165 Inspection
126378447 | pole | Non-HFTD | Transmission | 2023-06-15 | 2024-06-15 | Level 2 | E | 2024-06-12 | 2024-06-15 | Level 2 | Field Safety Reassessment
126378594 | other | Non-HFTD | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F |  | 2028-06-15 | Level 3
126379570 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F | 2024-01-26 | 2028-06-15 | Level 3 | GO 165 Inspection
126381365 | pole | Non-HFTD | Transmission | 2023-06-15 | 2024-06-15 | Level 2 | E | 2024-11-06 | 2024-06-15 | Level 2 | Field Safety Reassessment
126381466 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F |  | 2028-06-15 | Level 3
126381682 | other | HFTD Tier 3 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F | 2024-04-09 | 2028-06-15 | Level 3 | GO 165 Inspection
126382721 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F |  | 2028-06-15 | Level 3
126383890 | other | Non-HFTD | Transmission | 2023-06-15 | 2026-06-15 | Level 3 | F |  | 2028-06-15 | Level 3
126384192 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126384330 | pole | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-06 | 2028-06-12 | Level 3 | GO 165 Inspection
126384435 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-09 | 2028-06-12 | Level 3 | GO 165 Inspection
126384490 | other | Non-HFTD | Transmission | 2023-06-12 | 2026-06-12 | Level 2 | E | 2024-10-30 | 2026-06-12 | Level 2 | GO 165 Inspection
126384549 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-03 | 2028-06-12 | Level 3 | GO 165 Inspection
126384580 | pole | Non-HFTD | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E |  | 2026-06-13 | Level 2
126384608 | other | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-08 | 2028-06-12 | Level 3 | GO 165 Inspection
126386783 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-03-27 | 2028-06-12 | Level 3 | GO 165 Inspection
126386976 | pole | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-05-23 | 2028-06-16 | Level 3 | GO 165 Inspection
126387031 | other | Non-HFTD | Transmission | 2023-06-16 | 2026-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126387580 | pole | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-05-20 | 2028-06-14 | Level 3 | GO 165 Inspection
126387652 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-08 | 2028-06-12 | Level 3 | GO 165 Inspection
126387653 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-08 | 2028-06-12 | Level 3 | GO 165 Inspection
126387846 | pole | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126388065 | other | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-10-08 | 2026-06-06 | Level 2 | GO 165 Inspection
126388392 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F |  | 2028-06-14 | Level 3
126388635 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-05-14 | 2028-06-16 | Level 3 | GO 165 Inspection
126388814 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F | 2024-04-10 | 2028-06-13 | Level 3 | GO 165 Inspection
126389185 | pole | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126389464 | other | Non-HFTD | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E |  | 2026-06-13 | Level 2
126390710 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126390742 | other | HFTD Tier 3 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126391321 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126391540 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F |  | 2028-06-15 | Level 3
126392294 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F |  | 2028-06-15 | Level 3
126392444 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126392445 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-11 | 2028-06-12 | Level 3 | GO 165 Inspection
126392959 | pole | Non-HFTD | Transmission | 2023-06-16 | 2024-06-16 | Level 2 | E | 2024-09-02 | 2024-06-16 | Level 2 | Field Safety Reassessment
126393147 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126393154 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126393436 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-16 | 2024-06-16 | Level 3 | F | 2024-04-29 | 2028-06-16 | Level 3 | GO 165 Inspection
126394054 | pole | HFTD Tier 2 | Transmission | 2023-06-12 | 2024-06-12 | Level 2 | E | 2024-03-27 | 2024-06-12 | Level 2 | GO 165 Inspection
126394214 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126394313 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-03-14 | 2028-06-16 | Level 3 | GO 165 Inspection
126394429 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126394821 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126394864 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F | 2024-05-16 | 2028-06-15 | Level 3 | GO 165 Inspection
126394895 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-04-02 | 2028-06-12 | Level 3 | GO 165 Inspection
126395020 | pole | HFTD Tier 2 | Transmission | 2023-06-14 | 2026-06-14 | Level 2 | E | 2024-05-17 | 2026-06-14 | Level 2 | GO 165 Inspection
126395142 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-04-15 | 2028-06-14 | Level 3 | GO 165 Inspection
126395226 | pole | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-03-27 | 2028-06-12 | Level 3 | GO 165 Inspection
126395563 | other | HFTD Tier 3 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F | 2024-06-04 | 2028-06-15 | Level 3 | GO 165 Inspection
126395639 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F | 2024-04-11 | 2028-06-13 | Level 3 | GO 165 Inspection
126396050 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-14 | 2024-06-14 | Level 2 | E | 2024-06-21 | 2024-06-14 | Level 2 | Field Safety Reassessment
126396092 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126396296 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F |  | 2028-06-14 | Level 3
126396360 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-11-10 | 2024-06-13 | Level 2 | Field Safety Reassessment
126396365 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E |  | 2026-06-13 | Level 2
126396520 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126396657 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2024-06-15 | Level 2 | E |  | 2024-06-15 | Level 2
126397024 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-05-17 | 2028-06-14 | Level 3 | GO 165 Inspection
126397028 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-15 | 2024-06-15 | Level 3 | F | 2024-06-04 | 2028-06-15 | Level 3 | Field Safety Reassessment
126397114 | pole | HFTD Tier 2 | Transmission | 2023-06-17 | 2024-06-17 | Level 2 | E |  | 2024-06-17 | Level 2
126397120 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-14 | 2026-06-14 | Level 2 | E |  | 2026-06-14 | Level 2
126397141 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-07-30 | 2024-06-13 | Level 2 | Field Safety Reassessment
126397145 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-07-30 | 2024-06-13 | Level 2 | Field Safety Reassessment
126397416 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E | 2024-05-31 | 2026-06-13 | Level 2 | GO 165 Inspection
126397572 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-11-10 | 2024-06-13 | Level 2 | Field Safety Reassessment
126397576 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2024-06-13 | Level 2 | E | 2024-05-09 | 2024-06-13 | Level 2 | GO 165 Inspection
126397715 | other | HFTD Tier 2 | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F |  | 2028-06-12 | Level 3
126397792 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2024-06-15 | Level 2 | E | 2024-07-02 | 2024-06-15 | Level 2 | Field Safety Reassessment
126397852 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-10 | 2028-06-10 | Level 3 | F |  | 2028-06-10 | Level 3
126398295 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-05-31 | 2028-06-14 | Level 3 | GO 165 Inspection
126398394 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-17 | 2024-06-17 | Level 2 | E | 2024-06-11 | 2024-06-17 | Level 2 | Field Safety Reassessment
126399029 | other | HFTD Tier 2 | Transmission | 2023-06-17 | 2028-06-17 | Level 3 | F | 2024-06-01 | 2028-06-17 | Level 3 | GO 165 Inspection
126399122 | other | HFTD Tier 2 | Transmission | 2023-06-17 | 2028-06-17 | Level 3 | F |  | 2028-06-17 | Level 3
126399130 | other | Non-HFTD | Transmission | 2023-06-17 | 2026-06-17 | Level 2 | E |  | 2026-06-17 | Level 2
126399192 | other | Non-HFTD | Transmission | 2023-06-17 | 2028-06-17 | Level 3 | F |  | 2028-06-17 | Level 3
126400334 | pole | Non-HFTD | Transmission | 2023-06-18 | 2024-06-18 | Level 2 | E | 2024-12-06 | 2024-06-18 | Level 2 | Field Safety Reassessment
126403036 | pole | Non-HFTD | Transmission | 2023-06-19 | 2028-06-19 | Level 3 | F | 2024-06-03 | 2028-06-19 | Level 3 | GO 165 Inspection
126405430 | other | HFTD Tier 2 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-06-05 | 2028-06-20 | Level 3 | GO 165 Inspection
126406035 | anchor/guy | Non-HFTD | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E | 2024-11-04 | 2026-06-13 | Level 2 | GO 165 Inspection
126406494 | anchor/guy | Non-HFTD | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126407218 | other | HFTD Tier 3 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126407237 | other | HFTD Tier 3 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F | 2024-05-31 | 2028-06-13 | Level 3 | GO 165 Inspection
126407325 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-20 | 2024-06-20 | Level 2 | E | 2024-03-15 | 2024-06-20 | Level 2 | GO 165 Inspection
126407479 | pole | Non-HFTD | Transmission | 2023-06-20 | 2024-06-20 | Level 2 | E | 2024-05-06 | 2024-06-20 | Level 2 | GO 165 Inspection
126407690 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126408114 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126408445 | insulator and brushing | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 2 | E | 2024-09-10 | 2026-06-20 | Level 2 | GO 165 Inspection
126408825 | pole | HFTD Tier 2 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-04-23 | 2028-06-20 | Level 3 | GO 165 Inspection
126408935 | pole | Non-HFTD | Transmission | 2023-05-06 | 2026-05-06 | Level 2 | E | 2023-11-04 | 2026-05-06 | Level 2 | GO 165 Inspection
126411999 | other | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-11-07 | 2026-06-06 | Level 2 | GO 165 Inspection
126412623 | insulator and brushing | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 2 | E | 2024-10-17 | 2026-06-20 | Level 2 | GO 165 Inspection
126412647 | other | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 2 | E | 2024-10-17 | 2026-06-20 | Level 2 | GO 165 Inspection
126413054 | other | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126414272 | other | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126416715 | insulator and brushing | Non-HFTD | Transmission | 2023-06-21 | 2024-06-21 | Level 2 | E | 2024-08-19 | 2026-06-21 | Level 2 | GO 165 Inspection
126416742 | insulator and brushing | Non-HFTD | Transmission | 2023-06-06 | 2026-06-06 | Level 2 | E | 2024-10-26 | 2026-06-06 | Level 2 | GO 165 Inspection
126417111 | anchor/guy | Non-HFTD | Transmission | 2023-06-21 | 2026-06-21 | Level 2 | E |  | 2026-06-21 | Level 2
126417660 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F |  | 2028-06-21 | Level 3
126418086 | pole | HFTD Tier 2 | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F | 2024-04-15 | 2028-06-21 | Level 3 | GO 165 Inspection
126418703 | insulator and brushing | Non-HFTD | Transmission | 2023-06-06 | 2028-06-06 | Level 3 | F | 2024-10-16 | 2028-06-06 | Level 3 | GO 165 Inspection
126419792 | pole | Non-HFTD | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F |  | 2028-06-21 | Level 3
126420377 | pole | Non-HFTD | Transmission | 2023-06-21 | 2026-06-21 | Level 2 | E |  | 2026-06-21 | Level 2
126421301 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-06-27 | 2028-06-16 | Level 3 | GO 165 Inspection
126421360 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-05-13 | 2028-06-14 | Level 3 | GO 165 Inspection
126421674 | pole | HFTD Tier 2 | Transmission | 2023-06-20 | 2024-06-20 | Level 2 | E | 2024-06-19 | 2024-06-20 | Level 2 | Field Safety Reassessment
126421737 | pole | HFTD Tier 2 | Transmission | 2023-06-13 | 2028-06-13 | Level 3 | F |  | 2028-06-13 | Level 3
126421770 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126424204 | other | Non-HFTD | Transmission | 2023-06-07 | 2026-06-07 | Level 2 | E | 2024-11-07 | 2026-06-07 | Level 2 | GO 165 Inspection
126425551 | other | Non-HFTD | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E | 2024-07-22 | 2026-06-22 | Level 2 | GO 165 Inspection
126426707 | conductor | HFTD Tier 2 | Transmission | 2023-06-22 | 2024-06-22 | Level 2 | E |  | 2024-06-22 | Level 2
126427185 | anchor/guy | Non-HFTD | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E | 2024-06-24 | 2026-06-22 | Level 2 | GO 165 Inspection
126427301 | other | Non-HFTD | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F |  | 2028-06-22 | Level 3
126427642 | insulator and brushing | Non-HFTD | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E |  | 2026-06-22 | Level 2
126428555 | other | Non-HFTD | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F |  | 2028-06-22 | Level 3
126428774 | pole | Non-HFTD | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E |  | 2026-06-22 | Level 2
126428987 | other | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-06-16 | 2028-06-22 | Level 3 | GO 165 Inspection
126430111 | pole | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-02-13 | 2028-06-22 | Level 3 | GO 165 Inspection
126430313 | pole | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 2 | E | 2024-05-01 | 2024-06-14 | Level 2 | GO 165 Inspection
126430376 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-06-17 | 2028-06-14 | Level 3 | GO 165 Inspection
126430585 | other | HFTD Tier 3 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-05-22 | 2028-06-20 | Level 3 | GO 165 Inspection
126430757 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F | 2024-06-06 | 2028-06-15 | Level 3 | GO 165 Inspection
126430791 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2024-06-14 | Level 2 | E | 2024-06-17 | 2024-06-14 | Level 2 | GO 165 Inspection
126430923 | other | Non-HFTD | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126430929 | other | HFTD Tier 2 | Transmission | 2023-06-14 | 2028-06-14 | Level 3 | F | 2024-04-09 | 2028-06-14 | Level 3 | GO 165 Inspection
126431167 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-22 | 2024-06-22 | Level 2 | E | 2024-10-29 | 2023-12-22 | Level 2 | Field Safety Reassessment
126431196 | pole | HFTD Tier 2 | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E |  | 2026-06-22 | Level 2
126432822 | other | HFTD Tier 2 | Transmission | 2023-06-15 | 2028-06-15 | Level 3 | F | 2024-04-08 | 2028-06-15 | Level 3 | GO 165 Inspection
126432823 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126432897 | pole | HFTD Tier 3 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-06-24 | 2028-06-20 | Level 3 | GO 165 Inspection
126433061 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F |  | 2028-06-21 | Level 3
126433445 | other | HFTD Tier 2 | Transmission | 2023-06-21 | 2028-06-21 | Level 2 | E | 2024-05-14 | 2024-06-21 | Level 2 | GO 165 Inspection
126433708 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-15 | 2026-06-15 | Level 2 | E | 2024-06-15 | 2024-06-15 | Level 2 | GO 165 Inspection
126434083 | pole | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-06-25 | 2028-06-16 | Level 3 | GO 165 Inspection
126434156 | anchor/guy | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 2 | E | 2024-11-12 | 2026-06-20 | Level 2 | GO 165 Inspection
126434169 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126434393 | pole | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-05-24 | 2028-06-22 | Level 3 | GO 165 Inspection
126434519 | other | HFTD Tier 2 | Transmission | 2023-06-22 | 2024-06-22 | Level 2 | E | 2024-05-20 | 2024-06-22 | Level 2 | GO 165 Inspection
126434606 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-05-10 | 2028-06-22 | Level 3 | GO 165 Inspection
126435869 | other | Non-HFTD | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-09-28 | 2028-06-23 | Level 3 | GO 165 Inspection
126435969 | pole | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-02-28 | 2028-06-23 | Level 3 | GO 165 Inspection
126436093 | other | HFTD Tier 2 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-05-31 | 2028-06-20 | Level 3 | GO 165 Inspection
126436120 | pole | HFTD Tier 2 | Transmission | 2023-06-20 | 2024-06-20 | Level 2 | E |  | 2024-06-20 | Level 2
126437748 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126437940 | pole | HFTD Tier 2 | Transmission | 2023-06-15 | 2024-06-15 | Level 2 | E | 2024-06-25 | 2024-06-15 | Level 2 | Field Safety Reassessment
126438092 | other | Non-HFTD | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-09-27 | 2028-06-23 | Level 3 | GO 165 Inspection
126438295 | other | HFTD Tier 3 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-06-24 | 2028-06-20 | Level 3 | GO 165 Inspection
126438311 | other | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F |  | 2028-06-16 | Level 3
126439661 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-06-06 | 2028-06-23 | Level 3 | GO 165 Inspection
126439909 | other | Non-HFTD | Transmission | 2023-06-23 | 2026-06-23 | Level 2 | E | 2024-08-09 | 2026-06-23 | Level 2 | GO 165 Inspection
126440426 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-06-13 | 2028-06-23 | Level 3 | GO 165 Inspection
126440459 | other | Non-HFTD | Transmission | 2023-06-07 | 2026-06-07 | Level 2 | E | 2024-11-07 | 2026-06-07 | Level 2 | GO 165 Inspection
126440700 | other | Non-HFTD | Transmission | 2023-06-07 | 2028-06-07 | Level 3 | F | 2024-11-14 | 2028-06-07 | Level 3 | GO 165 Inspection
126441450 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126441524 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126441686 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126442018 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126442149 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126442534 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126444760 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F | 2024-09-23 | 2028-06-24 | Level 3 | GO 165 Inspection
126444892 | other | Non-HFTD | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126445753 | other | Non-HFTD | Transmission | 2023-06-25 | 2028-06-25 | Level 3 | F |  | 2028-06-25 | Level 3
126446072 | other | HFTD Tier 2 | Transmission | 2023-06-25 | 2028-06-25 | Level 3 | F | 2024-06-10 | 2028-06-25 | Level 3 | GO 165 Inspection
126446754 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-25 | 2028-06-25 | Level 3 | F | 2024-06-12 | 2028-06-25 | Level 3 | GO 165 Inspection
126447572 | other | HFTD Tier 2 | Transmission | 2023-06-25 | 2028-06-25 | Level 3 | F | 2024-06-13 | 2028-06-25 | Level 3 | GO 165 Inspection
126448585 | pole | HFTD Tier 2 | Transmission | 2023-06-25 | 2024-06-25 | Level 2 | E | 2024-06-01 | 2024-06-25 | Level 2 | GO 165 Inspection
126450349 | pole | Non-HFTD | Transmission | 2023-05-08 | 2026-05-08 | Level 2 | E |  | 2026-05-08 | Level 2
126450633 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-24 | 2023-12-24 | Level 2 | E | 2023-12-18 | 2023-12-24 | Level 2 | Field Safety Reassessment
126452826 | pole | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-24 | 2028-06-26 | Level 3 | GO 165 Inspection
126452854 | switch | Non-HFTD | Transmission | 2023-06-26 | 2026-06-26 | Level 2 | E | 2024-10-05 | 2026-06-26 | Level 2 | GO 165 Inspection
126453310 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2024-09-20 | 2026-05-15 | Level 2 | GO 165 Inspection
126454705 | insulator and brushing | Non-HFTD | Transmission | 2023-05-25 | 2026-05-25 | Level 2 | E |  | 2026-05-25 | Level 2
126455033 | pole | Non-HFTD | Transmission | 2023-05-31 | 2026-05-31 | Level 2 | E |  | 2026-05-31 | Level 2
126456745 | insulator and brushing | Non-HFTD | Transmission | 2023-06-12 | 2026-06-12 | Level 2 | E |  | 2026-06-12 | Level 2
126456835 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-03-19 | 2028-06-20 | Level 3 | GO 165 Inspection
126456854 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-07-18 | 2028-06-26 | Level 3 | GO 165 Inspection
126456855 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126456953 | other | Non-HFTD | Transmission | 2023-06-12 | 2026-06-12 | Level 2 | E | 2024-11-14 | 2026-06-12 | Level 2 | GO 165 Inspection
126456992 | other | HFTD Tier 2 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126457050 | other | HFTD Tier 2 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-03-26 | 2028-06-20 | Level 3 | GO 165 Inspection
126457076 | pole | HFTD Tier 3 | Transmission | 2023-06-21 | 2026-06-21 | Level 2 | E |  | 2026-06-21 | Level 2
126457098 | insulator and brushing | Non-HFTD | Transmission | 2023-06-09 | 2028-06-09 | Level 3 | F |  | 2028-06-09 | Level 3
126457180 | pole | Non-HFTD | Transmission | 2023-06-10 | 2026-06-10 | Level 2 | E |  | 2026-06-10 | Level 2
126457228 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126457404 | pole | HFTD Tier 2 | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-03-22 | 2028-06-16 | Level 3 | GO 165 Inspection
126457423 | anchor/guy | Non-HFTD | Transmission | 2023-06-16 | 2028-06-16 | Level 3 | F | 2024-06-04 | 2028-06-16 | Level 3 | GO 165 Inspection
126457589 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F | 2024-03-14 | 2028-06-21 | Level 3 | GO 165 Inspection
126459132 | pole | Non-HFTD | Transmission | 2023-06-15 | 2024-06-15 | Level 2 | E | 2024-11-06 | 2024-06-15 | Level 2 | Field Safety Reassessment
126459636 | insulator and brushing | Non-HFTD | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126460210 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-13 | 2026-06-13 | Level 2 | E | 2024-06-06 | 2024-06-13 | Level 2 | GO 165 Inspection
126461335 | other | Non-HFTD | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-06-24 | 2028-06-12 | Level 3 | GO 165 Inspection
126462058 | other | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E | 2024-09-10 | 2026-06-27 | Level 2 | GO 165 Inspection
126463862 | anchor/guy | Non-HFTD | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-08-01 | 2028-06-27 | Level 3 | GO 165 Inspection
126464547 | other | Non-HFTD | Transmission | 2023-06-12 | 2028-06-12 | Level 3 | F | 2024-11-05 | 2028-06-12 | Level 3 | GO 165 Inspection
126465529 | insulator and brushing | Non-HFTD | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-07-11 | 2028-06-20 | Level 3 | GO 165 Inspection
126465679 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-09-09 | 2028-06-26 | Level 3 | GO 165 Inspection
126465920 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-21 | 2024-06-21 | Level 2 | E | 2024-06-07 | 2024-06-21 | Level 2 | GO 165 Inspection
126465923 | pole | HFTD Tier 3 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-05-18 | 2028-06-20 | Level 3 | GO 165 Inspection
126465960 | other | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E |  | 2026-06-27 | Level 2
126466249 | pole | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-02-13 | 2028-06-22 | Level 3 | GO 165 Inspection
126466305 | pole | HFTD Tier 3 | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F | 2024-05-21 | 2028-06-20 | Level 3 | GO 165 Inspection
126466317 | crossarm | HFTD Tier 2 | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F | 2024-06-05 | 2028-06-21 | Level 3 | GO 165 Inspection
126466368 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-16 | 2026-06-16 | Level 2 | E | 2024-05-30 | 2026-06-16 | Level 2 | GO 165 Inspection
126466416 | pole | HFTD Tier 2 | Transmission | 2023-06-21 | 2028-06-21 | Level 3 | F | 2024-03-27 | 2028-06-21 | Level 3 | GO 165 Inspection
126468452 | pole | Non-HFTD | Transmission | 2023-06-15 | 2026-06-15 | Level 2 | E | 2024-10-18 | 2026-06-15 | Level 2 | GO 165 Inspection
126469040 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-07-19 | 2026-06-28 | Level 2 | GO 165 Inspection
126469087 | insulator and brushing | Non-HFTD | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126469300 | pole | Non-HFTD | Transmission | 2023-06-19 | 2028-06-19 | Level 3 | F | 2024-07-08 | 2028-06-19 | Level 3 | GO 165 Inspection
126469309 | pole | Non-HFTD | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E | 2024-07-19 | 2026-06-22 | Level 2 | GO 165 Inspection
126469441 | other | Non-HFTD | Transmission | 2023-06-20 | 2028-06-20 | Level 3 | F |  | 2028-06-20 | Level 3
126469597 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-03-28 | 2028-06-28 | Level 3 | GO 165 Inspection
126469824 | anchor/guy | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126470480 | pole | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-07-24 | 2028-06-28 | Level 3 | GO 165 Inspection
126470786 | insulator and brushing | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 2 | E |  | 2026-06-20 | Level 2
126471488 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-07-19 | 2026-06-28 | Level 2 | GO 165 Inspection
126471819 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-10-17 | 2026-06-28 | Level 2 | GO 165 Inspection
126472063 | pole | HFTD Tier 2 | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E | 2024-06-05 | 2026-06-22 | Level 2 | GO 165 Inspection
126472704 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126472839 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-22 | 2024-06-22 | Level 2 | E |  | 2024-06-22 | Level 2
126472918 | anchor/guy | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-08-24 | 2028-06-28 | Level 3 | GO 165 Inspection
126473768 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-04-29 | 2028-06-23 | Level 3 | GO 165 Inspection
126474223 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2024-06-23 | Level 2 | E | 2024-04-29 | 2024-06-23 | Level 2 | GO 165 Inspection
126474532 | pole | HFTD Tier 2 | Transmission | 2023-06-23 | 2026-06-23 | Level 2 | E |  | 2026-06-23 | Level 2
126474756 | other | HFTD Tier 2 | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F | 2023-07-26 | 2028-06-24 | Level 3 | GO 165 Inspection
126475110 | other | Non-HFTD | Transmission | 2023-06-28 | 2024-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126477430 | pole | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E | 2024-07-17 | 2026-06-29 | Level 2 | GO 165 Inspection
126478063 | pole | HFTD Tier 2 | Transmission | 2023-06-29 | 2024-06-29 | Level 2 | E | 2024-06-24 | 2024-06-29 | Level 2 | GO 165 Inspection
126479672 | pole | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E | 2024-09-17 | 2026-06-29 | Level 2 | GO 165 Inspection
126480488 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-06-29 | 2028-06-23 | Level 3 | GO 165 Inspection
126481778 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-20 | 2028-06-26 | Level 3 | GO 165 Inspection
126482013 | pole | HFTD Tier 2 | Transmission | 2023-06-29 | 2024-06-29 | Level 2 | E | 2024-06-11 | 2024-06-29 | Level 2 | Field Safety Reassessment
126484108 | other | HFTD Tier 2 | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F | 2024-06-15 | 2028-06-30 | Level 3 | GO 165 Inspection
126484400 | pole | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-04-23 | 2028-06-22 | Level 3 | GO 165 Inspection
126485203 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126485456 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F |  | 2028-06-22 | Level 3
126486610 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F |  | 2028-06-23 | Level 3
126486659 | insulator and brushing | Non-HFTD | Transmission | 2023-06-30 | 2026-06-30 | Level 2 | E | 2024-08-26 | 2026-06-30 | Level 2 | GO 165 Inspection
126488251 | pole | HFTD Tier 3 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-03-22 | 2028-06-22 | Level 3 | GO 165 Inspection
126488501 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-20 | 2028-06-26 | Level 3 | GO 165 Inspection
126488521 | anchor/guy | Non-HFTD | Transmission | 2023-06-20 | 2026-06-20 | Level 2 | E | 2024-11-18 | 2026-06-20 | Level 2 | GO 165 Inspection
126488639 | pole | Non-HFTD | Transmission | 2023-06-30 | 2026-06-30 | Level 2 | E | 2024-08-15 | 2026-06-30 | Level 2 | GO 165 Inspection
126488965 | other | Non-HFTD | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F |  | 2028-06-30 | Level 3
126489726 | other | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F |  | 2028-06-22 | Level 3
126490694 | other | HFTD Tier 3 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-06-04 | 2028-06-23 | Level 3 | GO 165 Inspection
126491171 | pole | HFTD Tier 2 | Transmission | 2023-06-27 | 2024-06-27 | Level 2 | E | 2024-06-01 | 2024-06-27 | Level 2 | GO 165 Inspection
126491173 | pole | HFTD Tier 2 | Transmission | 2023-06-27 | 2024-06-27 | Level 2 | E | 2024-06-01 | 2024-06-27 | Level 2 | GO 165 Inspection
126491195 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-31 | 2028-06-26 | Level 3 | GO 165 Inspection
126491224 | pole | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E | 2023-07-25 | 2026-06-27 | Level 2 | GO 165 Inspection
126491271 | pole | HFTD Tier 3 | Transmission | 2023-06-22 | 2026-06-22 | Level 2 | E | 2024-04-11 | 2026-06-22 | Level 2 | GO 165 Inspection
126491388 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-15 | 2028-06-26 | Level 3 | GO 165 Inspection
126491421 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-31 | 2028-06-26 | Level 3 | GO 165 Inspection
126492026 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-10-30 | 2028-06-28 | Level 3 | GO 165 Inspection
126492084 | pole | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126492089 | insulator and brushing | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126492158 | anchor/guy | Non-HFTD | Transmission | 2023-07-01 | 2028-07-01 | Level 3 | F |  | 2028-07-01 | Level 3
126492367 | other | HFTD Tier 2 | Transmission | 2023-06-22 | 2028-06-22 | Level 3 | F | 2024-05-22 | 2028-06-22 | Level 3 | GO 165 Inspection
126492377 | pole | Non-HFTD | Transmission | 2023-07-01 | 2026-07-01 | Level 2 | E |  | 2026-07-01 | Level 2
126492674 | pole | HFTD Tier 2 | Transmission | 2023-06-24 | 2026-06-24 | Level 2 | E |  | 2026-06-24 | Level 2
126492892 | other | HFTD Tier 2 | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-05-29 | 2028-06-28 | Level 3 | GO 165 Inspection
126493075 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-05-31 | 2028-06-26 | Level 3 | GO 165 Inspection
126493187 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126493563 | other | Non-HFTD | Transmission | 2023-07-01 | 2028-07-01 | Level 3 | F |  | 2028-07-01 | Level 3
126493698 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F |  | 2028-06-23 | Level 3
126494174 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-24 | 2024-06-24 | Level 2 | E | 2024-06-05 | 2024-06-24 | Level 2 | GO 165 Inspection
126494178 | pole | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-05-24 | 2028-06-27 | Level 3 | GO 165 Inspection
126494270 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F |  | 2028-06-23 | Level 3
126494593 | other | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-06-07 | 2028-06-27 | Level 3 | GO 165 Inspection
126494627 | pole | Non-HFTD | Transmission | 2023-07-01 | 2026-07-01 | Level 2 | E | 2024-09-14 | 2026-07-01 | Level 2 | GO 165 Inspection
126494683 | pole | Non-HFTD | Transmission | 2023-06-28 | 2024-06-28 | Level 2 | E | 2024-08-14 | 2024-06-28 | Level 2 | Field Safety Reassessment
126495031 | splice | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E |  | 2026-06-27 | Level 2
126495111 | other | HFTD Tier 2 | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-04-16 | 2028-06-26 | Level 3 | GO 165 Inspection
126495741 | pole | Non-HFTD | Transmission | 2023-06-26 | 2024-06-26 | Level 2 | E | 2024-10-03 | 2024-06-26 | Level 2 | Field Safety Reassessment
126495792 | pole | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F | 2024-04-30 | 2028-06-23 | Level 3 | GO 165 Inspection
126496078 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F |  | 2028-06-23 | Level 3
126496170 | insulator and brushing | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-09-11 | 2026-06-28 | Level 2 | GO 165 Inspection
126496176 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-10-31 | 2028-06-28 | Level 3 | GO 165 Inspection
126498530 | other | Non-HFTD | Transmission | 2023-06-21 | 2026-06-21 | Level 2 | E | 2024-10-31 | 2026-06-21 | Level 2 | GO 165 Inspection
126498559 | anchor/guy | Non-HFTD | Transmission | 2023-06-26 | 2024-06-26 | Level 2 | E |  | 2024-06-26 | Level 2
126498820 | pole | Non-HFTD | Transmission | 2023-05-15 | 2026-05-15 | Level 2 | E | 2023-07-08 | 2026-05-15 | Level 2 | GO 165 Inspection
126499022 | other | HFTD Tier 3 | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126499969 | other | HFTD Tier 2 | Transmission | 2023-07-03 | 2024-07-03 | Level 2 | E | 2024-03-14 | 2024-07-03 | Level 2 | GO 165 Inspection
126500174 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126500233 | other | HFTD Tier 2 | Transmission | 2023-07-03 | 2024-07-03 | Level 3 | F | 2024-06-25 | 2028-07-03 | Level 3 | Field Safety Reassessment
126500236 | other | HFTD Tier 2 | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126500239 | other | HFTD Tier 2 | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126500248 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126500363 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 3 | F | 2024-07-24 | 2028-07-03 | Level 3 | GO 165 Inspection
126500413 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 3 | F | 2024-07-25 | 2028-07-03 | Level 3 | GO 165 Inspection
126500547 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E | 2023-08-22 | 2026-07-03 | Level 2 | GO 165 Inspection
126500806 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E | 2024-04-05 | 2026-07-03 | Level 2 | GO 165 Inspection
126500809 | other | Non-HFTD | Transmission | 2023-07-03 | 2024-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126500856 | pole | HFTD Tier 2 | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F |  | 2028-06-24 | Level 3
126501304 | other | HFTD Tier 2 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F |  | 2028-06-23 | Level 3
126501320 | anchor/guy | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E |  | 2026-06-29 | Level 2
126501370 | anchor/guy | HFTD Tier 3 | Transmission | 2023-06-23 | 2028-06-23 | Level 3 | F |  | 2028-06-23 | Level 3
126502541 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-07-02 | 2028-07-05 | Level 3 | GO 165 Inspection
126502548 | pole | HFTD Tier 2 | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-04-22 | 2028-06-28 | Level 3 | GO 165 Inspection
126502627 | pole | Non-HFTD | Transmission | 2023-06-26 | 2026-06-26 | Level 2 | E |  | 2026-06-26 | Level 2
126502628 | pole | Non-HFTD | Transmission | 2023-06-27 | 2024-06-27 | Level 2 | E | 2024-12-17 | 2024-06-27 | Level 2 | Field Safety Reassessment
126502662 | insulator and brushing | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E | 2024-12-17 | 2026-06-27 | Level 2 | Field Safety Reassessment
126503394 | pole | HFTD Tier 2 | Transmission | 2023-06-10 | 2024-06-10 | Level 2 | E | 2024-03-19 | 2024-06-10 | Level 2 | GO 165 Inspection
126504254 | other | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F |  | 2028-07-05 | Level 3
126504428 | pole | Non-HFTD | Transmission | 2023-05-21 | 2026-05-21 | Level 2 | E |  | 2026-05-21 | Level 2
126504471 | pole | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-07-22 | 2028-07-05 | Level 3 | GO 165 Inspection
126504566 | pole | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-07-22 | 2028-07-05 | Level 3 | GO 165 Inspection
126504845 | anchor/guy | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E | 2024-08-15 | 2026-06-27 | Level 2 | GO 165 Inspection
126505316 | other | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F |  | 2028-07-05 | Level 3
126505391 | pole | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-09-03 | 2028-07-05 | Level 3 | GO 165 Inspection
126505749 | anchor/guy | Non-HFTD | Transmission | 2023-07-05 | 2026-07-05 | Level 2 | E |  | 2026-07-05 | Level 2
126506384 | splice | Non-HFTD | Transmission | 2023-06-26 | 2026-06-26 | Level 2 | E |  | 2026-06-26 | Level 2
126506562 | pole | Non-HFTD | Transmission | 2023-06-27 | 2024-06-27 | Level 2 | E | 2024-12-16 | 2024-06-27 | Level 2 | Field Safety Reassessment
126506863 | insulator and brushing | Non-HFTD | Transmission | 2023-07-05 | 2024-07-05 | Level 2 | E | 2024-06-26 | 2024-07-05 | Level 2 | Field Safety Reassessment
126506866 | other | Non-HFTD | Transmission | 2023-07-05 | 2026-07-05 | Level 2 | E |  | 2026-07-05 | Level 2
126506897 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126507047 | other | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F |  | 2028-07-05 | Level 3
126507059 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126507755 | other | Non-HFTD | Transmission | 2023-07-05 | 2026-07-05 | Level 3 | F |  | 2028-07-05 | Level 3
126508067 | other | Non-HFTD | Transmission | 2023-07-05 | 2026-07-05 | Level 3 | F |  | 2028-07-05 | Level 3
126508376 | pole | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-06-11 | 2028-06-29 | Level 3 | GO 165 Inspection
126508846 | other | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-06-29 | 2028-06-29 | Level 3 | GO 165 Inspection
126508872 | other | Non-HFTD | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F |  | 2028-06-30 | Level 3
126508886 | pole | HFTD Tier 2 | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F |  | 2028-06-30 | Level 3
126508972 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126509065 | conductor | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-05-23 | 2028-06-29 | Level 3 | GO 165 Inspection
126509098 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126509106 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-04-22 | 2028-06-29 | Level 3 | GO 165 Inspection
126509108 | other | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126509198 | pole | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-05-29 | 2028-06-29 | Level 3 | GO 165 Inspection
126512299 | insulator and brushing | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E | 2024-12-02 | 2026-07-06 | Level 2 | GO 165 Inspection
126512470 | pole | Non-HFTD | Transmission | 2023-07-06 | 2024-07-06 | Level 2 | E | 2024-09-17 | 2024-07-06 | Level 2 | Field Safety Reassessment
126514437 | other | Non-HFTD | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F |  | 2028-06-27 | Level 3
126514714 | pole | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E | 2024-07-02 | 2026-07-06 | Level 2 | GO 165 Inspection
126515128 | other | HFTD Tier 2 | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F | 2024-06-12 | 2028-07-06 | Level 3 | GO 165 Inspection
126515340 | insulator and brushing | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E | 2024-09-17 | 2026-07-06 | Level 2 | GO 165 Inspection
126515472 | other | Non-HFTD | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F |  | 2028-06-27 | Level 3
126516399 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-07-21 | 2026-06-28 | Level 2 | GO 165 Inspection
126516688 | other | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F |  | 2028-06-27 | Level 3
126516812 | other | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-05-28 | 2028-06-27 | Level 3 | GO 165 Inspection
126516955 | switch | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E |  | 2026-07-06 | Level 2
126516969 | pole | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E | 2024-03-06 | 2026-07-06 | Level 2 | GO 165 Inspection
126517002 | other | HFTD Tier 2 | Transmission | 2023-06-27 | 2024-06-27 | Level 2 | E | 2024-10-19 | 2024-06-27 | Level 2 | Field Safety Reassessment
126517118 | other | HFTD Tier 2 | Transmission | 2023-06-24 | 2028-06-24 | Level 3 | F | 2023-09-21 | 2028-06-24 | Level 3 | Field Safety Reassessment
126517126 | other | Non-HFTD | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-09-12 | 2028-06-27 | Level 3 | GO 165 Inspection
126519597 | pole | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126519846 | other | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F |  | 2028-06-27 | Level 3
126519848 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F | 2024-06-08 | 2028-06-30 | Level 3 | GO 165 Inspection
126519934 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126520171 | other | HFTD Tier 2 | Transmission | 2023-07-07 | 2028-07-07 | Level 3 | F | 2024-06-03 | 2028-07-07 | Level 3 | GO 165 Inspection
126520453 | anchor/guy | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E |  | 2026-06-29 | Level 2
126520803 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-07-21 | 2028-06-28 | Level 3 | GO 165 Inspection
126520884 | other | Non-HFTD | Transmission | 2023-06-27 | 2026-06-27 | Level 2 | E | 2024-07-18 | 2026-06-27 | Level 2 | GO 165 Inspection
126521228 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126521253 | other | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 3 | F |  | 2028-07-07 | Level 3
126521270 | other | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 3 | F |  | 2028-07-07 | Level 3
126521325 | other | HFTD Tier 2 | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126521818 | anchor/guy | HFTD Tier 2 | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-06-06 | 2028-06-28 | Level 3 | GO 165 Inspection
126522143 | insulator and brushing | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E |  | 2026-07-07 | Level 2
126522510 | pole | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E | 2024-06-14 | 2026-07-07 | Level 2 | GO 165 Inspection
126522580 | other | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E |  | 2026-07-07 | Level 2
126522636 | pole | Non-HFTD | Transmission | 2023-07-07 | 2024-07-07 | Level 2 | E | 2024-06-20 | 2024-07-07 | Level 2 | GO 165 Inspection
126523165 | other | Non-HFTD | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F |  | 2028-06-27 | Level 3
126523314 | other | Non-HFTD | Transmission | 2023-07-07 | 2028-07-07 | Level 3 | F | 2024-03-04 | 2028-07-07 | Level 3 | GO 165 Inspection
126523541 | other | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-10-08 | 2028-06-27 | Level 3 | Field Safety Reassessment
126524091 | anchor/guy | Non-HFTD | Transmission | 2023-07-07 | 2028-07-07 | Level 3 | F | 2024-03-04 | 2028-07-07 | Level 3 | GO 165 Inspection
126524332 | other | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E | 2024-06-14 | 2026-07-07 | Level 2 | GO 165 Inspection
126524470 | splice | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E | 2024-07-16 | 2026-07-07 | Level 2 | GO 165 Inspection
126524517 | anchor/guy | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-10-04 | 2028-06-28 | Level 3 | GO 165 Inspection
126524740 | pole | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E | 2024-06-18 | 2026-07-07 | Level 2 | GO 165 Inspection
126525222 | insulator and brushing | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126525272 | other | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 3 | F |  | 2028-07-07 | Level 3
126525376 | conductor | HFTD Tier 2 | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F | 2024-06-11 | 2028-06-30 | Level 3 | GO 165 Inspection
126525950 | other | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126526019 | splice | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126526056 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-06-01 | 2028-06-29 | Level 3 | GO 165 Inspection
126526075 | other | Non-HFTD | Transmission | 2023-07-07 | 2028-07-07 | Level 3 | F |  | 2028-07-07 | Level 3
126526206 | other | Non-HFTD | Transmission | 2023-07-07 | 2028-07-07 | Level 3 | F |  | 2028-07-07 | Level 3
126526306 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126526411 | pole | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-05-25 | 2028-07-05 | Level 3 | GO 165 Inspection
126526865 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2023-10-05 | Level 2 | E | 2024-11-18 | 2023-10-05 | Level 2 | Field Safety Reassessment
126527151 | other | HFTD Tier 2 | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F | 2024-07-08 | 2028-07-06 | Level 3 | GO 165 Inspection
126527883 | pole | HFTD Tier 2 | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F | 2024-05-31 | 2028-06-30 | Level 3 | GO 165 Inspection
126528048 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-06-07 | 2028-06-28 | Level 3 | GO 165 Inspection
126528560 | other | HFTD Tier 3 | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126528709 | other | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126528936 | insulator and brushing | Non-HFTD | Transmission | 2023-07-08 | 2026-07-08 | Level 2 | E | 2024-08-27 | 2026-07-08 | Level 2 | GO 165 Inspection
126529216 | pole | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126529295 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126529331 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126529416 | pole | Non-HFTD | Transmission | 2023-07-08 | 2028-07-08 | Level 3 | F |  | 2028-07-08 | Level 3
126529554 | insulator and brushing | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-09-07 | 2028-06-28 | Level 3 | GO 165 Inspection
126529612 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126530308 | other | HFTD Tier 3 | Transmission | 2023-07-07 | 2024-01-07 | Level 2 | E |  | 2024-01-07 | Level 2
126530414 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-06-15 | 2028-07-05 | Level 3 | GO 165 Inspection
126530415 | pole | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-06-15 | 2028-07-05 | Level 3 | GO 165 Inspection
126531989 | pole | Non-HFTD | Transmission | 2023-07-08 | 2026-07-08 | Level 2 | E |  | 2026-07-08 | Level 2
126536200 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126536229 | other | Non-HFTD | Transmission | 2023-06-30 | 2028-06-30 | Level 3 | F |  | 2028-06-30 | Level 3
126536248 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-06-12 | 2028-07-05 | Level 3 | GO 165 Inspection
126536257 | splice | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126536395 | anchor/guy | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E | 2024-07-22 | 2026-06-29 | Level 2 | GO 165 Inspection
126536443 | insulator and brushing | Non-HFTD | Transmission | 2023-06-30 | 2024-06-30 | Level 2 | E | 2024-12-23 | 2024-06-30 | Level 2 | Field Safety Reassessment
126536575 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126536606 | pole | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126536614 | anchor/guy | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-08-19 | 2028-06-26 | Level 3 | GO 165 Inspection
126536640 | pole | Non-HFTD | Transmission | 2023-07-09 | 2026-07-09 | Level 2 | E |  | 2026-07-09 | Level 2
126536748 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126536854 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-08-10 | 2026-06-28 | Level 2 | GO 165 Inspection
126536856 | other | Non-HFTD | Transmission | 2023-06-26 | 2026-06-26 | Level 2 | E |  | 2026-06-26 | Level 2
126536904 | insulator and brushing | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F |  | 2028-06-26 | Level 3
126536909 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E | 2024-08-31 | 2026-06-28 | Level 2 | GO 165 Inspection
126537332 | insulator and brushing | Non-HFTD | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2023-08-04 | 2028-06-27 | Level 3 | Field Safety Reassessment
126537352 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-10-29 | 2028-06-28 | Level 3 | GO 165 Inspection
126537430 | insulator and brushing | Non-HFTD | Transmission | 2023-06-30 | 2026-06-30 | Level 2 | E |  | 2026-06-30 | Level 2
126537438 | splice | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E |  | 2026-06-29 | Level 2
126537527 | pole | Non-HFTD | Transmission | 2023-07-09 | 2026-07-09 | Level 2 | E |  | 2026-07-09 | Level 2
126537577 | pole | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E |  | 2026-06-29 | Level 2
126537677 | other | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F |  | 2028-06-29 | Level 3
126537812 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F | 2024-12-30 | 2028-06-28 | Level 3 | Field Safety Reassessment
126537967 | insulator and brushing | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126538282 | pole | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126538398 | insulator and brushing | Non-HFTD | Transmission | 2023-06-26 | 2024-06-26 | Level 2 | E | 2024-10-03 | 2024-06-26 | Level 2 | Field Safety Reassessment
126538490 | crossarm | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126538872 | other | Non-HFTD | Transmission | 2023-06-26 | 2028-06-26 | Level 3 | F | 2024-08-12 | 2028-06-26 | Level 3 | GO 165 Inspection
126539042 | anchor/guy | Non-HFTD | Transmission | 2023-06-29 | 2024-06-29 | Level 2 | E | 2024-12-19 | 2024-06-29 | Level 2 | Field Safety Reassessment
126539192 | pole | Non-HFTD | Transmission | 2023-06-28 | 2026-06-28 | Level 2 | E |  | 2026-06-28 | Level 2
126539667 | other | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126539678 | other | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126539702 | other | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126539704 | other | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126539712 | other | Non-HFTD | Transmission | 2023-07-09 | 2028-07-09 | Level 3 | F |  | 2028-07-09 | Level 3
126550847 | other | HFTD Tier 2 | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2024-05-21 | 2028-07-10 | Level 3 | GO 165 Inspection
126551183 | other | HFTD Tier 2 | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F |  | 2028-06-02 | Level 3
126551335 | other | Non-HFTD | Transmission | 2023-06-28 | 2028-06-28 | Level 3 | F |  | 2028-06-28 | Level 3
126551948 | pole | Non-HFTD | Transmission | 2023-07-10 | 2024-07-10 | Level 2 | E | 2024-05-30 | 2024-07-10 | Level 2 | GO 165 Inspection
126552097 | crossarm | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126552434 | other | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126552459 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126552747 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F |  | 2028-07-05 | Level 3
126552887 | pole | Non-HFTD | Transmission | 2023-07-05 | 2024-07-05 | Level 2 | E | 2024-12-16 | 2026-07-05 | Level 2 | Field Safety Reassessment
126553040 | other | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126553308 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126553944 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126554034 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126554324 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2024-06-07 | 2028-07-10 | Level 3 | GO 165 Inspection
126554553 | insulator and brushing | Non-HFTD | Transmission | 2023-06-29 | 2026-06-29 | Level 2 | E |  | 2026-06-29 | Level 2
126554801 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126555009 | pole | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2024-10-09 | 2028-07-10 | Level 3 | GO 165 Inspection
126555040 | insulator and brushing | Non-HFTD | Transmission | 2023-06-29 | 2028-06-29 | Level 3 | F | 2024-10-21 | 2028-06-29 | Level 3 | GO 165 Inspection
126555589 | pole | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E | 2024-10-21 | 2026-07-10 | Level 2 | GO 165 Inspection
126555613 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2023-10-03 | 2028-07-10 | Level 3 | Field Safety Reassessment
126555700 | other | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126555749 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2024-08-13 | 2028-07-10 | Level 3 | GO 165 Inspection
126555941 | splice | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126557341 | pole | HFTD Tier 2 | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E | 2024-05-02 | 2026-07-10 | Level 2 | GO 165 Inspection
126557498 | other | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126557678 | pole | HFTD Tier 3 | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2024-03-19 | 2028-07-10 | Level 3 | GO 165 Inspection
126559160 | splice | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E |  | 2026-07-03 | Level 2
126559296 | other | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126559648 | other | Non-HFTD | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-11-16 | 2028-07-05 | Level 3 | GO 165 Inspection
126560152 | pole | Non-HFTD | Transmission | 2023-06-30 | 2026-06-30 | Level 2 | E |  | 2026-06-30 | Level 2
126560416 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126560566 | other | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126560836 | anchor/guy | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126561646 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E |  | 2026-07-03 | Level 2
126561809 | pole | Non-HFTD | Transmission | 2023-07-05 | 2026-07-05 | Level 2 | E |  | 2026-07-05 | Level 2
126562353 | anchor/guy | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126563604 | pole | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126563882 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126564144 | pole | Non-HFTD | Transmission | 2023-07-05 | 2026-07-05 | Level 2 | E |  | 2026-07-05 | Level 2
126564426 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126564427 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126564662 | crossarm | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126564750 | pole | Non-HFTD | Transmission | 2023-07-11 | 2024-07-11 | Level 2 | E | 2024-10-28 | 2024-07-11 | Level 2 | Field Safety Reassessment
126564963 | insulator and brushing | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126565225 | other | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126565828 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E | 2024-08-27 | 2026-07-11 | Level 2 | GO 165 Inspection
126567542 | other | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126567645 | other | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126568320 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568343 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568410 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-14 | 2028-07-12 | Level 3 | GO 165 Inspection
126568453 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126568498 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-28 | 2028-07-12 | Level 3 | GO 165 Inspection
126568508 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568513 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568546 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568553 | pole | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-07-23 | 2028-07-12 | Level 3 | GO 165 Inspection
126568567 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568575 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568627 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568643 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-03-13 | 2028-07-12 | Level 3 | GO 165 Inspection
126568675 | pole | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-07-23 | 2028-07-12 | Level 3 | GO 165 Inspection
126568893 | pole | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-07-22 | 2028-07-12 | Level 3 | GO 165 Inspection
126569090 | pole | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-07-22 | 2028-07-12 | Level 3 | GO 165 Inspection
126569572 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126569949 | pole | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126570096 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126570243 | other | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126571055 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126571264 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126571464 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126572186 | other | Non-HFTD | Transmission | 2023-07-12 | 2024-07-12 | Level 2 | E | 2024-12-21 | 2024-07-12 | Level 2 | Field Safety Reassessment
126572190 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126572658 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126572674 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126572675 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126572824 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126572825 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126573030 | other | HFTD Tier 2 | Transmission | 2023-07-12 | 2024-07-12 | Level 3 | F | 2024-05-09 | 2028-07-12 | Level 3 | GO 165 Inspection
126574019 | anchor/guy | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126575913 | pole | HFTD Tier 2 | Transmission | 2023-06-27 | 2028-06-27 | Level 3 | F | 2024-05-23 | 2028-06-27 | Level 3 | GO 165 Inspection
126576200 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126576565 | insulator and brushing | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E | 2024-05-21 | 2026-07-13 | Level 2 | GO 165 Inspection
126576959 | anchor/guy | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126577181 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126577747 | pole | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E |  | 2026-07-03 | Level 2
126577817 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126577827 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126578686 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126579904 | anchor/guy | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126580588 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126581217 | pole | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E | 2024-08-12 | 2026-07-13 | Level 2 | GO 165 Inspection
126581345 | pole | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E | 2024-04-12 | 2026-07-13 | Level 2 | Field Safety Reassessment
126583480 | anchor/guy | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F | 2024-10-21 | 2028-07-13 | Level 3 | GO 165 Inspection
126585392 | splice | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E |  | 2026-07-13 | Level 2
126585756 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-06-15 | 2028-07-05 | Level 3 | GO 165 Inspection
126586149 | other | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126586622 | other | HFTD Tier 2 | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126586882 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-04-25 | 2028-07-12 | Level 3 | GO 165 Inspection
126587032 | other | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E | 2024-05-22 | 2026-07-14 | Level 2 | GO 165 Inspection
126587130 | other | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126587353 | pole | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126587493 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F | 2024-08-23 | 2028-07-14 | Level 3 | GO 165 Inspection
126587728 | pole | HFTD Tier 2 | Transmission | 2023-07-14 | 2024-07-14 | Level 2 | E | 2024-07-08 | 2024-07-14 | Level 2 | GO 165 Inspection
126588068 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F | 2024-08-22 | 2028-07-14 | Level 3 | GO 165 Inspection
126588069 | pole | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E | 2024-08-22 | 2026-07-14 | Level 2 | GO 165 Inspection
126588866 | other | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2023-07-19 | 2028-07-12 | Level 3 | GO 165 Inspection
126589039 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126589093 | insulator and brushing | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E | 2024-08-23 | 2026-07-14 | Level 2 | GO 165 Inspection
126589094 | insulator and brushing | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E | 2024-08-23 | 2026-07-14 | Level 2 | GO 165 Inspection
126589609 | anchor/guy | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126589690 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126589793 | pole | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E | 2024-07-24 | 2026-07-03 | Level 2 | GO 165 Inspection
126589850 | other | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F | 2024-07-24 | 2028-07-03 | Level 3 | GO 165 Inspection
126589890 | insulator and brushing | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E | 2024-09-12 | 2026-07-14 | Level 2 | GO 165 Inspection
126590230 | other | HFTD Tier 3 | Transmission | 2023-07-07 | 2028-07-07 | Level 3 | F |  | 2028-07-07 | Level 3
126590238 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126590283 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F | 2024-08-23 | 2028-07-14 | Level 3 | GO 165 Inspection
126590643 | other | HFTD Tier 2 | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F | 2024-06-16 | 2028-07-06 | Level 3 | GO 165 Inspection
126590750 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F | 2024-08-23 | 2028-07-14 | Level 3 | GO 165 Inspection
126591478 | other | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126591533 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126591756 | other | Non-HFTD | Transmission | 2023-07-03 | 2026-07-03 | Level 2 | E |  | 2026-07-03 | Level 2
126592065 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126592077 | other | HFTD Tier 2 | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F | 2024-06-15 | 2028-07-06 | Level 3 | GO 165 Inspection
126592238 | splice | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E | 2024-07-11 | 2026-07-14 | Level 2 | GO 165 Inspection
126592310 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-06-13 | 2028-07-05 | Level 3 | GO 165 Inspection
126592644 | anchor/guy | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126592681 | pole | HFTD Tier 2 | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126592773 | anchor/guy | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126592999 | anchor/guy | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126593041 | other | HFTD Tier 2 | Transmission | 2023-07-05 | 2028-07-05 | Level 3 | F | 2024-06-01 | 2028-07-05 | Level 3 | GO 165 Inspection
126593201 | pole | HFTD Tier 3 | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F | 2024-05-30 | 2028-07-11 | Level 3 | GO 165 Inspection
126593324 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126593336 | pole | Non-HFTD | Transmission | 2023-07-11 | 2024-07-11 | Level 2 | E |  | 2024-07-11 | Level 2
126593709 | other | Non-HFTD | Transmission | 2023-07-11 | 2024-07-11 | Level 2 | E | 2024-12-07 | 2024-07-11 | Level 2 | Field Safety Reassessment
126593793 | pole | HFTD Tier 2 | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2023-07-24 | 2028-07-12 | Level 3 | GO 165 Inspection
126593907 | pole | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126593964 | insulator and brushing | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126593970 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126594014 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126594130 | insulator and brushing | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E |  | 2026-07-06 | Level 2
126594203 | pole | Non-HFTD | Transmission | 2023-07-12 | 2024-07-12 | Level 2 | E | 2024-11-14 | 2026-07-12 | Level 2 | GO 165 Inspection
126594435 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126594465 | pole | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F | 2024-07-22 | 2028-07-06 | Level 3 | GO 165 Inspection
126594467 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126594469 | other | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126594480 | anchor/guy | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126594655 | insulator and brushing | Non-HFTD | Transmission | 2023-07-15 | 2026-07-15 | Level 2 | E |  | 2026-07-15 | Level 2
126594775 | other | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126595055 | pole | Non-HFTD | Transmission | 2023-07-03 | 2028-07-03 | Level 3 | F |  | 2028-07-03 | Level 3
126595258 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126595661 | pole | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126595807 | insulator and brushing | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E |  | 2026-07-07 | Level 2
126595809 | other | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E |  | 2026-07-07 | Level 2
126595876 | other | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E |  | 2026-07-13 | Level 2
126595878 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E | 2024-07-19 | 2026-07-10 | Level 2 | GO 165 Inspection
126595906 | other | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126595907 | pole | Non-HFTD | Transmission | 2023-07-15 | 2026-07-15 | Level 2 | E |  | 2026-07-15 | Level 2
126595953 | other | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126596070 | anchor/guy | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F | 2024-08-23 | 2028-07-12 | Level 3 | GO 165 Inspection
126596078 | other | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126596151 | insulator and brushing | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126596186 | anchor/guy | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126596198 | pole | Non-HFTD | Transmission | 2023-07-15 | 2026-07-15 | Level 2 | E |  | 2026-07-15 | Level 2
126596434 | anchor/guy | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126598261 | insulator and brushing | Non-HFTD | Transmission | 2023-07-15 | 2026-07-15 | Level 2 | E |  | 2026-07-15 | Level 2
126598337 | anchor/guy | Non-HFTD | Transmission | 2023-07-15 | 2028-07-15 | Level 3 | F |  | 2028-07-15 | Level 3
126604054 | other | HFTD Tier 2 | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F | 2024-05-13 | 2028-07-14 | Level 3 | GO 165 Inspection
126604513 | pole | Non-HFTD | Transmission | 2023-07-10 | 2024-07-10 | Level 2 | E | 2024-12-19 | 2024-07-10 | Level 2 | Field Safety Reassessment
126604819 | pole | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126604822 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F | 2024-11-27 | 2028-07-17 | Level 3 | GO 165 Inspection
126604868 | insulator and brushing | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126605155 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126605262 | other | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126605459 | other | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126606070 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126606092 | pole | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126606102 | pole | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126606146 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126606512 | anchor/guy | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126606620 | anchor/guy | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126606734 | crossarm | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126606755 | pole | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126607351 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126608377 | splice | HFTD Tier 3 | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126608442 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126608445 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126608448 | other | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126608540 | splice | HFTD Tier 3 | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126608783 | insulator and brushing | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E | 2024-09-05 | 2026-07-11 | Level 2 | GO 165 Inspection
126608853 | splice | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126608907 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126609091 | other | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E | 2024-09-07 | 2026-07-06 | Level 2 | GO 165 Inspection
126609095 | pole | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126609401 | splice | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E |  | 2026-07-06 | Level 2
126609578 | insulator and brushing | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126610079 | other | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F |  | 2028-07-06 | Level 3
126610275 | crossarm | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126610389 | insulator and brushing | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126612808 | pole | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126612936 | anchor/guy | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126614027 | pole | Non-HFTD | Transmission | 2023-07-18 | 2023-10-18 | Level 2 | E | 2024-12-30 | 2023-10-18 | Level 2 | Field Safety Reassessment
126614500 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126614914 | anchor/guy | Non-HFTD | Transmission | 2023-07-06 | 2026-07-06 | Level 2 | E |  | 2026-07-06 | Level 2
126615026 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126615064 | conductor | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126615421 | anchor/guy | Non-HFTD | Transmission | 2023-07-06 | 2028-07-06 | Level 3 | F | 2024-07-22 | 2028-07-06 | Level 3 | GO 165 Inspection
126615563 | pole | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126615567 | anchor/guy | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126615593 | anchor/guy | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126615845 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126616389 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126617126 | crossarm | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126617236 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126617237 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126617997 | splice | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E |  | 2026-07-13 | Level 2
126618325 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126618328 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126618734 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126618869 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126619215 | insulator and brushing | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126620094 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126620098 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126620216 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126620321 | pole | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E |  | 2026-07-13 | Level 2
126621853 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126621917 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126621939 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126622194 | insulator and brushing | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126622387 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126622453 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126623393 | anchor/guy | HFTD Tier 2 | Transmission | 2023-07-19 | 2024-07-19 | Level 2 | E |  | 2024-07-19 | Level 2
126623629 | other | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126623936 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126624149 | insulator and brushing | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126624257 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126624360 | insulator and brushing | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126624520 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126624590 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126624891 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126624896 | other | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126625070 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2024-07-19 | Level 2
126625156 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126625559 | anchor/guy | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126625562 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126625568 | crossarm | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E |  | 2026-07-13 | Level 2
126625631 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126625777 | pole | Non-HFTD | Transmission | 2023-07-07 | 2026-07-07 | Level 2 | E |  | 2026-07-07 | Level 2
126625836 | conductor | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F | 2024-10-10 | 2028-07-19 | Level 3 | GO 165 Inspection
126625951 | insulator and brushing | Non-HFTD | Transmission | 2023-07-19 | 2024-07-19 | Level 2 | E | 2024-05-07 | 2026-07-19 | Level 2 | Field Safety Reassessment
126626060 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126626258 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126626977 | splice | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126627052 | insulator and brushing | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126627151 | anchor/guy | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126627258 | anchor/guy | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126627784 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126627867 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126627932 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126628684 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126628791 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126628861 | pole | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126628919 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F | 2024-07-19 | 2028-07-10 | Level 3 | GO 165 Inspection
126628993 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126629027 | pole | HFTD Tier 2 | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126629035 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126629128 | insulator and brushing | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126629148 | other | HFTD Tier 2 | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126629165 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126629281 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126629303 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126629361 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126629371 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126629453 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126629537 | splice | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126629557 | other | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E | 2024-09-06 | 2026-07-17 | Level 2 | GO 165 Inspection
126630264 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F | 2024-08-19 | 2028-07-20 | Level 3 | GO 165 Inspection
126630400 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126631286 | other | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126631617 | pole | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126631769 | insulator and brushing | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126632203 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126632344 | other | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126632451 | insulator and brushing | Non-HFTD | Transmission | 2023-07-10 | 2026-07-10 | Level 2 | E |  | 2026-07-10 | Level 2
126632931 | insulator and brushing | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E | 2024-08-27 | 2026-07-20 | Level 2 | GO 165 Inspection
126632935 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126632995 | other | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126633005 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126633407 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126633616 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126634333 | splice | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E | 2024-08-26 | 2026-07-20 | Level 2 | GO 165 Inspection
126634539 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126634643 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126635196 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126635434 | anchor/guy | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126635436 | other | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126635555 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126635910 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126635999 | insulator and brushing | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126636070 | other | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126636132 | other | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126636423 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126636591 | anchor/guy | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126636599 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E | 2024-05-08 | 2026-07-11 | Level 2 | GO 165 Inspection
126636622 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126636626 | anchor/guy | Non-HFTD | Transmission | 2023-07-10 | 2028-07-10 | Level 3 | F |  | 2028-07-10 | Level 3
126636641 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126636685 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126636730 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126636771 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126636867 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126636875 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126636876 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126636935 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126636959 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E | 2024-05-30 | 2026-07-11 | Level 2 | GO 165 Inspection
126636983 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126636985 | crossarm | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126636996 | pole | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126637011 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126637050 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126637052 | pole | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126637071 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126637135 | splice | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126637152 | pole | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126637219 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126637280 | insulator and brushing | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E | 2024-09-26 | 2026-07-18 | Level 2 | GO 165 Inspection
126637288 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126637370 | splice | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126637384 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126637392 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126637393 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126637400 | pole | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126637430 | insulator and brushing | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126637442 | other | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126637447 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126637466 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126637468 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126637521 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 2 | E | 2024-09-13 | 2024-01-17 | Level 2 | GO 165 Inspection
126637525 | insulator and brushing | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126637544 | other | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126637567 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126637568 | insulator and brushing | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126637587 | other | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126637590 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126637645 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126637652 | crossarm | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126637680 | insulator and brushing | Non-HFTD | Transmission | 2023-07-18 | 2024-07-18 | Level 2 | E | 2024-12-19 | 2024-07-18 | Level 2 | Field Safety Reassessment
126637721 | pole | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126637729 | splice | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126637742 | pole | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126639535 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E | 2024-05-30 | 2026-07-11 | Level 2 | GO 165 Inspection
126639536 | insulator and brushing | Non-HFTD | Transmission | 2023-07-11 | 2028-07-11 | Level 3 | F |  | 2028-07-11 | Level 3
126639642 | anchor/guy | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2023-08-09 | 2025-03-02 | Level 2 | Standards change
126639649 | anchor/guy | Non-HFTD | Transmission | 2022-07-16 | 2023-07-16 | Level 2 | E | 2023-07-24 | 2025-07-16 | Level 2 | Standards change
126639751 | pole | Non-HFTD | Transmission | 2022-07-16 | 2023-07-16 | Level 2 | E | 2023-07-24 | 2025-07-16 | Level 2 | Standards change
126639757 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-07-25 | 2025-07-18 | Level 2 | Standards change
126639776 | pole | Non-HFTD | Transmission | 2022-04-18 | 2023-04-18 | Level 2 | E | 2024-01-20 | 2025-04-18 | Level 2 | GO 165 Inspection
126639779 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-07-25 | 2025-07-18 | Level 2 | Standards change
126639869 | pole | Non-HFTD | Transmission | 2022-10-17 | 2023-10-17 | Level 2 | E | 2023-09-02 | 2025-10-17 | Level 2 | GO 165 Inspection
126639975 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-07-24 | 2025-07-15 | Level 2 | Standards change
126640038 | pole | Non-HFTD | Transmission | 2022-08-23 | 2023-08-23 | Level 2 | E | 2023-07-26 | 2025-08-23 | Level 2 | Standards change
126640099 | pole | HFTD Tier 2 | Transmission | 2022-07-20 | 2023-07-20 | Level 2 | E | 2023-07-28 | 2023-07-20 | Level 2 | Standards change
126640104 | pole | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-07-24 | 2025-07-22 | Level 2 | Standards change
126640105 | pole | Non-HFTD | Transmission | 2023-07-11 | 2026-07-11 | Level 2 | E |  | 2026-07-11 | Level 2
126640191 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2024-09-03 | 2025-08-02 | Level 2 | GO 165 Inspection
126640241 | other | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126640280 | other | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126640325 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2023-08-10 | 2025-08-02 | Level 2 | Standards change
126640383 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-07-27 | 2025-07-13 | Level 2 | Standards change
126640428 | splice | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126640604 | anchor/guy | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-07-25 | 2025-08-11 | Level 2 | Standards change
126640860 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-07-24 | 2025-08-10 | Level 2 | Standards change
126640984 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-08-06 | 2025-07-19 | Level 2 | Standards change
126641141 | other | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126641396 | pole | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126641556 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126641908 | pole | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-06-06 | 2025-08-01 | Level 2 | GO 165 Inspection
126642039 | pole | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126642059 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-07-28 | 2025-08-09 | Level 2 | Standards change
126642106 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-07-24 | 2025-07-15 | Level 2 | Standards change
126642165 | pole | Non-HFTD | Transmission | 2022-08-02 | 2023-08-02 | Level 2 | E | 2024-08-28 | 2025-08-02 | Level 2 | GO 165 Inspection
126642254 | other | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126642294 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126642341 | pole | Non-HFTD | Transmission | 2022-11-22 | 2023-11-22 | Level 2 | E | 2024-09-09 | 2025-11-22 | Level 2 | GO 165 Inspection
126642348 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-07-27 | 2025-07-13 | Level 2 | Standards change
126642439 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126642637 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-07-27 | 2025-07-18 | Level 2 | Standards change
126642639 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-07-28 | 2025-08-09 | Level 2 | Standards change
126642756 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-07-25 | 2025-07-18 | Level 2 | Standards change
126642783 | pole | Non-HFTD | Transmission | 2023-07-13 | 2024-07-13 | Level 2 | E | 2024-05-21 | 2024-07-13 | Level 2 | Field Safety Reassessment
126643034 | insulator and brushing | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126643386 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126643494 | crossarm | Non-HFTD | Transmission | 2023-07-12 | 2028-07-12 | Level 3 | F |  | 2028-07-12 | Level 3
126643588 | other | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126644111 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126644202 | pole | Non-HFTD | Transmission | 2022-11-08 | 2023-11-08 | Level 2 | E | 2023-08-04 | 2025-11-08 | Level 2 | Standards change
126644277 | other | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126644484 | pole | Non-HFTD | Transmission | 2022-09-28 | 2023-09-28 | Level 2 | E | 2024-07-11 | 2025-09-28 | Level 2 | GO 165 Inspection
126644884 | insulator and brushing | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126644941 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126645074 | pole | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126645545 | anchor/guy | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126645625 | pole | HFTD Tier 2 | Transmission | 2022-07-26 | 2023-07-26 | Level 2 | E | 2024-03-18 | 2023-07-26 | Level 2 | GO 165 Inspection
126645857 | anchor/guy | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126645876 | pole | HFTD Tier 2 | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-04-25 | 2023-08-31 | Level 2 | GO 165 Inspection
126645956 | pole | HFTD Tier 2 | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-04-25 | 2023-08-31 | Level 2 | GO 165 Inspection
126645984 | pole | HFTD Tier 2 | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126646023 | pole | HFTD Tier 2 | Transmission | 2022-08-31 | 2023-08-31 | Level 2 | E | 2024-04-25 | 2023-08-31 | Level 2 | GO 165 Inspection
126646110 | pole | HFTD Tier 2 | Transmission | 2022-09-02 | 2023-09-02 | Level 2 | E | 2024-04-29 | 2023-09-02 | Level 2 | GO 165 Inspection
126646256 | pole | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-05-15 | 2025-09-01 | Level 2 | GO 165 Inspection
126646478 | pole | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2023-12-08 | 2025-03-07 | Level 2 | GO 165 Inspection
126646568 | pole | Non-HFTD | Transmission | 2023-07-12 | 2026-07-12 | Level 2 | E |  | 2026-07-12 | Level 2
126646597 | pole | Non-HFTD | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | E | 2023-07-25 | 2025-03-07 | Level 2 | Standards change
126646845 | pole | Non-HFTD | Transmission | 2023-07-13 | 2024-07-13 | Level 2 | E | 2024-08-29 | 2024-01-13 | Level 2 | Field Safety Reassessment
126646978 | pole | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2024-04-25 | 2025-09-01 | Level 2 | GO 165 Inspection
126647254 | pole | Non-HFTD | Transmission | 2022-08-11 | 2023-08-11 | Level 2 | E | 2023-07-25 | 2025-08-11 | Level 2 | Standards change
126647257 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126647391 | insulator and brushing | Non-HFTD | Transmission | 2023-07-19 | 2024-07-19 | Level 2 | E |  | 2024-07-19 | Level 2
126647478 | pole | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E | 2023-10-06 | 2026-07-13 | Level 2 | GO 165 Inspection
126647524 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126647525 | pole | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126647647 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126647664 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126647668 | pole | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-06-06 | 2025-08-01 | Level 2 | GO 165 Inspection
126647806 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E | 2024-09-18 | 2026-07-19 | Level 2 | GO 165 Inspection
126647844 | pole | Non-HFTD | Transmission | 2023-07-13 | 2026-07-13 | Level 2 | E |  | 2026-07-13 | Level 2
126647920 | pole | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126647944 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126647964 | other | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126647994 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126648327 | pole | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-08-13 | 2025-08-01 | Level 2 | GO 165 Inspection
126648466 | pole | Non-HFTD | Transmission | 2022-12-01 | 2023-12-01 | Level 2 | E | 2023-09-19 | 2025-12-01 | Level 2 | GO 165 Inspection
126648469 | anchor/guy | Non-HFTD | Transmission | 2022-12-01 | 2023-12-01 | Level 2 | E | 2023-09-19 | 2025-12-01 | Level 2 | GO 165 Inspection
126648704 | pole | Non-HFTD | Transmission | 2022-07-16 | 2023-07-16 | Level 2 | E | 2023-07-25 | 2025-07-16 | Level 2 | Standards change
126649079 | other | Non-HFTD | Transmission | 2023-07-22 | 2028-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
126649124 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126649126 | pole | Non-HFTD | Transmission | 2022-07-13 | 2023-07-13 | Level 2 | E | 2023-07-26 | 2025-07-13 | Level 2 | Standards change
126649130 | insulator and brushing | Non-HFTD | Transmission | 2023-07-22 | 2028-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
126649292 | insulator and brushing | Non-HFTD | Transmission | 2023-07-22 | 2028-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
126649472 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-07-24 | 2025-08-10 | Level 2 | Standards change
126649478 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-08-06 | 2025-07-19 | Level 2 | Standards change
126649787 | other | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126649883 | pole | Non-HFTD | Transmission | 2022-10-12 | 2023-10-12 | Level 2 | E | 2023-09-05 | 2025-10-12 | Level 2 | GO 165 Inspection
126649906 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126649936 | pole | Non-HFTD | Transmission | 2022-10-25 | 2023-10-25 | Level 2 | E | 2023-09-11 | 2025-10-25 | Level 2 | GO 165 Inspection
126649957 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-09-05 | 2025-10-18 | Level 2 | GO 165 Inspection
126650069 | pole | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126650227 | insulator and brushing | Non-HFTD | Transmission | 2023-07-13 | 2028-07-13 | Level 3 | F |  | 2028-07-13 | Level 3
126650231 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-07-25 | 2025-08-09 | Level 2 | Standards change
126650235 | pole | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2023-07-31 | 2025-07-27 | Level 2 | Standards change
126650414 | insulator and brushing | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126650463 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-07-24 | 2025-08-10 | Level 2 | Standards change
126650468 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126650546 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-07-24 | 2025-07-15 | Level 2 | Standards change
126650582 | pole | Non-HFTD | Transmission | 2022-07-22 | 2023-07-22 | Level 2 | E | 2023-07-24 | 2025-07-22 | Level 2 | Standards change
126650585 | pole | Non-HFTD | Transmission | 2023-07-22 | 2028-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
126650643 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-07-25 | 2025-07-18 | Level 2 | Standards change
126650648 | pole | Non-HFTD | Transmission | 2022-07-15 | 2023-07-15 | Level 2 | E | 2023-07-24 | 2025-07-15 | Level 2 | Standards change
126650804 | pole | Non-HFTD | Transmission | 2022-04-21 | 2023-04-21 | Level 2 | E | 2023-07-26 | 2025-04-21 | Level 2 | Standards change
126650896 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126650911 | pole | Non-HFTD | Transmission | 2022-08-10 | 2023-08-10 | Level 2 | E | 2023-07-24 | 2023-08-10 | Level 2 | Standards change
126651022 | anchor/guy | Non-HFTD | Transmission | 2023-07-22 | 2028-07-22 | Level 3 | F | 2024-05-13 | 2028-07-22 | Level 3 | GO 165 Inspection
126651041 | pole | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126651149 | crossarm | Non-HFTD | Transmission | 2023-07-14 | 2024-07-14 | Level 2 | E | 2024-12-17 | 2024-07-14 | Level 2 | Field Safety Reassessment
126651337 | pole | Non-HFTD | Transmission | 2023-07-22 | 2026-07-22 | Level 2 | E |  | 2026-07-22 | Level 2
126651514 | pole | Non-HFTD | Transmission | 2022-11-07 | 2023-11-07 | Level 2 | E | 2024-11-19 | 2025-11-07 | Level 2 | GO 165 Inspection
126651520 | pole | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126651686 | anchor/guy | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126651754 | pole | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126651815 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126652044 | insulator and brushing | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126652142 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126652147 | pole | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126652230 | other | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E | 2024-11-16 | 2026-07-20 | Level 2 | GO 165 Inspection
126652353 | insulator and brushing | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126652399 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126653011 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126653016 | pole | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126653131 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126653312 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126653395 | other | Non-HFTD | Transmission | 2023-07-14 | 2028-07-14 | Level 3 | F |  | 2028-07-14 | Level 3
126653434 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126653626 | pole | Non-HFTD | Transmission | 2023-07-22 | 2026-07-22 | Level 2 | E |  | 2026-07-22 | Level 2
126653633 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126653634 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126653638 | insulator and brushing | Non-HFTD | Transmission | 2023-07-14 | 2026-07-14 | Level 2 | E |  | 2026-07-14 | Level 2
126653658 | other | Non-HFTD | Transmission | 2023-07-22 | 2026-07-22 | Level 2 | E |  | 2026-07-22 | Level 2
126653797 | other | Non-HFTD | Transmission | 2023-07-22 | 2028-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
126653799 | other | Non-HFTD | Transmission | 2023-07-22 | 2026-07-22 | Level 2 | E |  | 2026-07-22 | Level 2
126653845 | insulator and brushing | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126653893 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126654020 | anchor/guy | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E | 2024-09-09 | 2026-07-21 | Level 2 | GO 165 Inspection
126654301 | pole | Non-HFTD | Transmission | 2022-11-07 | 2023-11-07 | Level 2 | E | 2024-11-19 | 2025-11-07 | Level 2 | GO 165 Inspection
126654344 | pole | Non-HFTD | Transmission | 2022-07-19 | 2023-07-19 | Level 2 | E | 2023-08-06 | 2025-07-19 | Level 2 | Standards change
126654347 | pole | Non-HFTD | Transmission | 2022-07-14 | 2023-07-14 | Level 2 | E | 2023-07-24 | 2025-07-14 | Level 2 | Standards change
126654349 | pole | Non-HFTD | Transmission | 2022-08-01 | 2023-08-01 | Level 2 | E | 2024-09-06 | 2025-08-01 | Level 2 | GO 165 Inspection
126654473 | pole | Non-HFTD | Transmission | 2022-09-26 | 2023-09-26 | Level 2 | E | 2024-09-25 | 2025-09-26 | Level 2 | GO 165 Inspection
126654586 | pole | Non-HFTD | Transmission | 2022-10-18 | 2023-10-18 | Level 2 | E | 2023-09-07 | 2025-10-18 | Level 2 | GO 165 Inspection
126655942 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126655995 | pole | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126656386 | other | Non-HFTD | Transmission | 2023-07-17 | 2028-07-17 | Level 3 | F |  | 2028-07-17 | Level 3
126656950 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126657050 | insulator and brushing | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126657210 | pole | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126657833 | other | HFTD Tier 2 | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126657965 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126658017 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126658218 | pole | Non-HFTD | Transmission | 2023-07-17 | 2026-07-17 | Level 2 | E |  | 2026-07-17 | Level 2
126658427 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126659839 | other | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126660199 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126660370 | splice | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126660527 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126660833 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126660999 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126661111 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126661817 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126662026 | anchor/guy | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126662042 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126662196 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126662246 | anchor/guy | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126662265 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126662276 | other | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126662283 | pole | Non-HFTD | Transmission | 2023-07-24 | 2024-07-24 | Level 2 | E | 2024-12-06 | 2024-07-24 | Level 2 | Field Safety Reassessment
126662404 | pole | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F | 2024-03-28 | 2028-07-24 | Level 3 | GO 165 Inspection
126663338 | conductor | HFTD Tier 3 | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126664585 | splice | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126664789 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126664795 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126664869 | other | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E | 2024-11-24 | 2026-07-24 | Level 2 | GO 165 Inspection
126664929 | pole | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126664962 | insulator and brushing | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126665034 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126665418 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E | 2024-07-24 | 2026-07-24 | Level 2 | GO 165 Inspection
126665438 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E | 2024-07-24 | 2026-07-24 | Level 2 | GO 165 Inspection
126666148 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126667457 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F | 2024-10-31 | 2028-07-24 | Level 3 | GO 165 Inspection
126667688 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126668459 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126668613 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F | 2024-10-15 | 2028-07-25 | Level 3 | GO 165 Inspection
126668664 | other | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126668742 | insulator and brushing | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E | 2024-09-12 | 2026-07-25 | Level 2 | GO 165 Inspection
126669113 | other | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126669273 | pole | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126670344 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126670372 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126671072 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126671103 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126671247 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126673356 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126673358 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126673438 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126673471 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126673501 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126673502 | pole | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126673604 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126673902 | pole | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126674629 | insulator and brushing | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126674661 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126674965 | other | Non-HFTD | Transmission | 2023-07-18 | 2028-07-18 | Level 3 | F |  | 2028-07-18 | Level 3
126675794 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126676418 | pole | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E | 2024-11-16 | 2026-07-19 | Level 2 | GO 165 Inspection
126676979 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E | 2024-09-24 | 2026-07-26 | Level 2 | GO 165 Inspection
126677020 | pole | Non-HFTD | Transmission | 2023-07-18 | 2026-07-18 | Level 2 | E |  | 2026-07-18 | Level 2
126677679 | pole | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126677861 | insulator and brushing | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E | 2024-07-23 | 2024-07-26 | Level 2 | GO 165 Inspection
126678103 | anchor/guy | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126679803 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126680121 | other | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126680198 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126680384 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126680392 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126680464 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126680522 | anchor/guy | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126680571 | other | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E | 2024-11-24 | 2026-07-24 | Level 2 | GO 165 Inspection
126680585 | insulator and brushing | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126680587 | other | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126680616 | pole | HFTD Tier 2 | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F | 2024-07-21 | 2028-07-26 | Level 3 | Field Safety Reassessment
126680674 | pole | Non-HFTD | Transmission | 2023-07-26 | 2024-01-26 | Level 2 | E | 2024-10-22 | 2024-01-26 | Level 2 | Field Safety Reassessment
126680696 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126680701 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126680706 | other | Non-HFTD | Transmission | 2023-07-19 | 2028-07-19 | Level 3 | F |  | 2028-07-19 | Level 3
126680714 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126680721 | anchor/guy | Non-HFTD | Transmission | 2023-07-19 | 2026-07-19 | Level 2 | E |  | 2026-07-19 | Level 2
126680760 | insulator and brushing | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126680769 | pole | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126680802 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126682262 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126682351 | pole | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E | 2024-06-07 | 2026-07-25 | Level 2 | GO 165 Inspection
126682546 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126683010 | conductor | HFTD Tier 2 | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126683057 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126683102 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126683633 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126684936 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126685298 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E | 2024-09-18 | 2026-07-27 | Level 2 | GO 165 Inspection
126685410 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126686536 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126688039 | pole | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126688041 | other | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E | 2024-09-04 | 2026-07-27 | Level 2 | GO 165 Inspection
126688261 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126688560 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126690973 | insulator and brushing | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126691065 | other | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126691083 | anchor/guy | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
126691162 | other | Non-HFTD | Transmission | 2023-07-20 | 2028-07-20 | Level 3 | F |  | 2028-07-20 | Level 3
126691250 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126691258 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126691450 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
126691469 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126691590 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126691594 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126691615 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126691649 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126691763 | anchor/guy | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126691924 | insulator and brushing | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E | 2023-10-19 | 2026-07-26 | Level 2 | Field Safety Reassessment
126692226 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126692494 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126692860 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126693068 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126693151 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126693194 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
126693270 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126693522 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126693640 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126693758 | pole | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126693928 | insulator and brushing | Non-HFTD | Transmission | 2023-07-21 | 2026-07-21 | Level 2 | E |  | 2026-07-21 | Level 2
126693935 | anchor/guy | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126694119 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126694131 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126694338 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
126694372 | splice | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126694531 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126694872 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126695247 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126695266 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E |  | 2026-07-24 | Level 2
126695709 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126695828 | other | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F | 2024-08-19 | 2028-07-24 | Level 3 | GO 165 Inspection
126696034 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126696231 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126696270 | splice | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126696334 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126696463 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126696483 | pole | Non-HFTD | Transmission | 2023-07-28 | 2024-07-28 | Level 2 | E |  | 2024-07-28 | Level 2
126696708 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126696787 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126697063 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126697928 | insulator and brushing | Non-HFTD | Transmission | 2023-07-28 | 2024-07-28 | Level 2 | E |  | 2024-07-28 | Level 2
126698197 | insulator and brushing | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E | 2024-08-28 | 2026-07-28 | Level 2 | GO 165 Inspection
126698202 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126698208 | pole | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F | 2024-07-29 | 2028-07-25 | Level 3 | GO 165 Inspection
126698236 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126698259 | insulator and brushing | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E | 2024-08-28 | 2026-07-28 | Level 2 | GO 165 Inspection
126698305 | pole | Non-HFTD | Transmission | 2023-07-24 | 2026-07-24 | Level 2 | E | 2024-09-26 | 2026-07-24 | Level 2 | GO 165 Inspection
126698371 | pole | Non-HFTD | Transmission | 2023-07-27 | 2024-07-27 | Level 2 | E | 2024-12-23 | 2024-07-27 | Level 2 | Field Safety Reassessment
126698720 | pole | Non-HFTD | Transmission | 2023-07-29 | 2024-07-29 | Level 2 | E | 2024-08-27 | 2024-07-29 | Level 2 | Field Safety Reassessment
126698945 | pole | Non-HFTD | Transmission | 2023-07-29 | 2024-07-29 | Level 2 | E | 2024-11-07 | 2024-07-29 | Level 2 | Field Safety Reassessment
126699252 | insulator and brushing | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
126699673 | pole | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E | 2024-10-21 | 2026-07-29 | Level 2 | GO 165 Inspection
126699832 | insulator and brushing | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
126699976 | splice | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
126700318 | pole | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
126700347 | anchor/guy | Non-HFTD | Transmission | 2023-07-29 | 2028-07-29 | Level 3 | F |  | 2028-07-29 | Level 3
126700702 | pole | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
126700713 | pole | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
126701266 | other | Non-HFTD | Transmission | 2023-07-29 | 2028-07-29 | Level 3 | F |  | 2028-07-29 | Level 3
126701295 | other | Non-HFTD | Transmission | 2023-07-29 | 2028-07-29 | Level 3 | F |  | 2028-07-29 | Level 3
126702027 | anchor/guy | Non-HFTD | Transmission | 2023-07-29 | 2028-07-29 | Level 3 | F |  | 2028-07-29 | Level 3
126706782 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126706828 | conductor | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126706878 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126707044 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126707049 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2024-07-31 | Level 2 | E | 2024-10-28 | 2024-07-31 | Level 2 | Field Safety Reassessment
126707567 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126707766 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126708061 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126708137 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126708450 | splice | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126708502 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126708940 | anchor/guy | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126709039 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126709094 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126709462 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126709673 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126709764 | other | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126709765 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126709818 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126709876 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126710167 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126710322 | splice | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126710745 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126710807 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126710873 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126711186 | pole | Non-HFTD | Transmission | 2023-07-27 | 2024-07-27 | Level 2 | E | 2024-07-30 | 2024-07-27 | Level 2 | Field Safety Reassessment
126711330 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126711869 | pole | HFTD Tier 2 | Transmission | 2023-07-31 | 2024-07-31 | Level 2 | E |  | 2024-07-31 | Level 2
126712087 | anchor/guy | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
126712373 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126712693 | other | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126712772 | switch | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126712934 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126712997 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126713068 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126713110 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126713114 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126713204 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126713205 | other | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126713209 | splice | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126713232 | anchor/guy | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126713239 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713241 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713247 | pole | Non-HFTD | Transmission | 2023-07-26 | 2024-07-26 | Level 2 | E | 2024-10-22 | 2024-01-26 | Level 2 | Field Safety Reassessment
126713257 | switch | Non-HFTD | Transmission | 2023-07-31 | 2024-07-31 | Level 2 | E |  | 2024-07-31 | Level 2
126713268 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126713309 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126713428 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126713465 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126713466 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713468 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713523 | other | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
126713574 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713583 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713587 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126713626 | other | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
126714773 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126714923 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126714959 | pole | Non-HFTD | Transmission | 2023-08-01 | 2024-08-01 | Level 2 | E | 2024-08-13 | 2024-08-01 | Level 2 | Field Safety Reassessment
126715008 | pole | Non-HFTD | Transmission | 2023-07-20 | 2024-07-20 | Level 2 | E | 2024-11-19 | 2024-07-20 | Level 2 | Field Safety Reassessment
126715252 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126715328 | insulator and brushing | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126715494 | other | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126716199 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126716496 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126716575 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126716617 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126717200 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126717492 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126717522 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126717633 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126717636 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126717701 | pole | Non-HFTD | Transmission | 2023-08-01 | 2024-08-01 | Level 2 | E | 2024-08-31 | 2024-08-01 | Level 2 | GO 165 Inspection
126717891 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126718033 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126718413 | insulator and brushing | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126718546 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126718619 | other | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E | 2024-11-19 | 2026-07-28 | Level 2 | GO 165 Inspection
126718888 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126719355 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126719706 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126720558 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126721268 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126721519 | insulator and brushing | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126721581 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126722652 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126722653 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126723335 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126723410 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126724460 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126724963 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126725360 | splice | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126725495 | anchor/guy | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126725696 | anchor/guy | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126726597 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126727003 | anchor/guy | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126727197 | insulator and brushing | Non-HFTD | Transmission | 2023-08-02 | 2024-08-02 | Level 2 | E | 2024-09-24 | 2024-08-02 | Level 2 | Field Safety Reassessment
126727251 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126727918 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126728038 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126728282 | pole | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126728301 | anchor/guy | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126728322 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126728503 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126728814 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126728992 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126729144 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126729307 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126729354 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126729358 | pole | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126729716 | pole | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126730005 | pole | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126730212 | splice | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126730217 | anchor/guy | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126730243 | crossarm | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126730306 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730324 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730371 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730411 | splice | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126730414 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126730496 | other | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126730551 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126730556 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730571 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126730583 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126730606 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730628 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730658 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126730671 | pole | Non-HFTD | Transmission | 2023-07-27 | 2024-07-27 | Level 2 | E | 2024-07-29 | 2024-07-27 | Level 2 | Field Safety Reassessment
126730680 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126730685 | anchor/guy | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F | 2024-02-06 | 2028-07-31 | Level 3 | GO 165 Inspection
126730701 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126730703 | splice | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126730710 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126730720 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126730766 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126730818 | crossarm | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126730830 | anchor/guy | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F | 2024-08-19 | 2028-07-31 | Level 3 | GO 165 Inspection
126730831 | other | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E | 2024-08-19 | 2026-07-31 | Level 2 | GO 165 Inspection
126730838 | insulator and brushing | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126731403 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126732627 | anchor/guy | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F | 2024-11-04 | 2028-08-03 | Level 3 | GO 165 Inspection
126732647 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126733037 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126733153 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126733606 | anchor/guy | HFTD Tier 2 | Transmission | 2023-08-03 | 2024-08-03 | Level 2 | E | 2024-07-30 | 2024-08-03 | Level 2 | Field Safety Reassessment
126733927 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126734168 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126734365 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F | 2024-07-29 | 2028-07-31 | Level 3 | GO 165 Inspection
126734942 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126734991 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126735133 | insulator and brushing | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126735160 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126735377 | splice | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126735432 | anchor/guy | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126735483 | splice | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126735564 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126735571 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126736216 | pole | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126736259 | pole | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126736513 | pole | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126736516 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126736557 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126737123 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126737168 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126737194 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126737196 | insulator and brushing | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126737751 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
126737754 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126737942 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126737952 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126738039 | pole | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126738721 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126738858 | insulator and brushing | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126739185 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126739250 | pole | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126739332 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126739426 | other | Non-HFTD | Transmission | 2023-07-21 | 2028-07-21 | Level 3 | F | 2024-02-22 | 2028-07-21 | Level 3 | GO 165 Inspection
126739438 | pole | Non-HFTD | Transmission | 2023-07-15 | 2026-07-15 | Level 2 | E | 2024-08-27 | 2026-07-15 | Level 2 | GO 165 Inspection
126740166 | other | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126741450 | anchor/guy | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126741466 | other | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126741486 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126741543 | splice | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126741551 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126741562 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126741602 | anchor/guy | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126741613 | conductor | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126741618 | insulator and brushing | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126741713 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126741912 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126742224 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126742344 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126742738 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126742767 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F | 2024-10-01 | 2028-08-02 | Level 3 | GO 165 Inspection
126742910 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126743310 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126743593 | insulator and brushing | Non-HFTD | Transmission | 2023-08-01 | 2024-02-01 | Level 2 | E | 2024-10-29 | 2024-02-01 | Level 2 | Field Safety Reassessment
126743621 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126744059 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126744445 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126744448 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126744617 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126744696 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126744733 | anchor/guy | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126744774 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126745472 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126745674 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126745820 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126745871 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126745882 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126746072 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126746193 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126746219 | anchor/guy | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126746252 | pole | Non-HFTD | Transmission | 2023-08-04 | 2024-08-04 | Level 2 | E | 2024-08-12 | 2024-08-04 | Level 2 | Field Safety Reassessment
126746519 | pole | Non-HFTD | Transmission | 2023-08-04 | 2024-08-04 | Level 2 | E | 2024-08-12 | 2024-08-04 | Level 2 | Field Safety Reassessment
126746678 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126746689 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126746790 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126746964 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126747211 | crossarm | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126747794 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126747829 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126747879 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126747885 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126748133 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126748151 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
126748152 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E | 2024-05-21 | 2026-08-01 | Level 2 | Field Safety Reassessment
126748415 | other | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126748480 | anchor/guy | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126748512 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126749109 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126749198 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126749330 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126749405 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126749483 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126749563 | conductor | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126749568 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126749629 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126749642 | pole | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126749649 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2023-11-03 | Level 2
126749772 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126750901 | anchor/guy | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126751065 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126751527 | pole | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126751668 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E | 2024-11-24 | 2026-08-05 | Level 2 | GO 165 Inspection
126751842 | pole | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126752034 | other | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126752200 | anchor/guy | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126752410 | anchor/guy | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126752765 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126753109 | other | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126753872 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126753998 | anchor/guy | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126754385 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 2 | E | 2024-09-17 | 2024-08-05 | Level 2 | GO 165 Inspection
126755135 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126755203 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126760709 | other | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126760804 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126760807 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126760985 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126761721 | pole | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126762218 | pole | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126762513 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126762821 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126762834 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126763578 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126763938 | pole | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126764001 | pole | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126764314 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F | 2024-11-12 | 2028-08-07 | Level 3 | GO 165 Inspection
126764837 | other | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126765631 | pole | Non-HFTD | Transmission | 2023-07-27 | 2026-07-27 | Level 2 | E |  | 2026-07-27 | Level 2
126766020 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126766339 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126766391 | pole | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126766461 | pole | Non-HFTD | Transmission | 2023-08-07 | 2024-08-07 | Level 2 | E | 2024-02-20 | 2024-08-07 | Level 2 | Field Safety Reassessment
126766513 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126766787 | other | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
126767615 | pole | Non-HFTD | Transmission | 2023-07-31 | 2026-07-31 | Level 2 | E |  | 2026-07-31 | Level 2
126767770 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126767823 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126767875 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126767980 | other | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126768009 | other | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E | 2024-09-05 | 2026-08-01 | Level 2 | GO 165 Inspection
126768014 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126768032 | insulator and brushing | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E | 2024-09-05 | 2026-08-01 | Level 2 | GO 165 Inspection
126768077 | crossarm | Non-HFTD | Transmission | 2023-08-04 | 2024-08-04 | Level 2 | E | 2024-07-31 | 2026-08-04 | Level 2 | Field Safety Reassessment
126768087 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126768106 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126768107 | other | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126768154 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126768237 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126769346 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126769899 | other | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126770202 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126770251 | pole | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126770494 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126770533 | other | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126770691 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126772119 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126772313 | pole | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E | 2024-11-12 | 2026-08-04 | Level 2 | GO 165 Inspection
126772507 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126772889 | pole | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126772923 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126773441 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126773448 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126773449 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126773498 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126773541 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126774038 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126774288 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126774727 | pole | HFTD Tier 2 | Transmission | 2023-08-08 | 2024-08-08 | Level 2 | E | 2024-08-05 | 2024-08-08 | Level 2 | Field Safety Reassessment
126774854 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126774995 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126775402 | anchor/guy | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126775814 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 2 | E | 2024-07-31 | 2024-02-05 | Level 2 | Field Safety Reassessment
126775872 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126775903 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126776107 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126776276 | other | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126776313 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126776341 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126776346 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126776380 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126776385 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126776395 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 2 | E | 2024-07-31 | 2024-08-05 | Level 2 | Field Safety Reassessment
126776408 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126776474 | insulator and brushing | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126776492 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126776547 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126776577 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126776683 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126776687 | conductor | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126776705 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126776735 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126776740 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126776818 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126776844 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126776903 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126776973 | other | Non-HFTD | Transmission | 2023-07-31 | 2028-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
126776989 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126777003 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 2 | E | 2024-07-31 | 2024-08-05 | Level 2 | Field Safety Reassessment
126777006 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126777083 | anchor/guy | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126777117 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126777126 | conductor | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126777141 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126777165 | pole | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126777182 | insulator and brushing | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126777192 | other | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126777194 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 2 | E | 2024-07-31 | 2024-02-05 | Level 2 | Field Safety Reassessment
126777203 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126777235 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126777254 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126777262 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126777332 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
126777335 | pole | Non-HFTD | Transmission | 2023-08-05 | 2026-08-05 | Level 2 | E |  | 2026-08-05 | Level 2
126777349 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E | 2024-10-21 | 2026-08-07 | Level 2 | GO 165 Inspection
126777393 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E | 2024-08-01 | 2026-08-08 | Level 2 | GO 165 Inspection
126777452 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126777876 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126779234 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126779303 | pole | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E | 2024-11-12 | 2026-08-07 | Level 2 | GO 165 Inspection
126779309 | other | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126779564 | insulator and brushing | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126780260 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126780368 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126780416 | insulator and brushing | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126780815 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126780998 | splice | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126782021 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F | 2024-09-26 | 2028-08-01 | Level 3 | GO 165 Inspection
126782058 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126782562 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E | 2024-07-09 | 2026-08-09 | Level 2 | GO 165 Inspection
126783069 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126783136 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126783260 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126783639 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126783907 | pole | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126784529 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126784738 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E | 2024-08-01 | 2026-08-08 | Level 2 | GO 165 Inspection
126784778 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126784809 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126784811 | other | Non-HFTD | Transmission | 2023-08-01 | 2028-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
126784915 | splice | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126784962 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126784972 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126785051 | insulator and brushing | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126785053 | splice | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126785183 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126785200 | splice | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126785208 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126785221 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126785223 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126785242 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126785289 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126785332 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126785340 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126785341 | other | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126785344 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126785346 | splice | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126785350 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126785423 | splice | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E | 2024-08-16 | 2026-08-09 | Level 2 | GO 165 Inspection
126796534 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126796541 | insulator and brushing | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126796727 | anchor/guy | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126796933 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126797011 | pole | Non-HFTD | Transmission | 2023-07-23 | 2026-07-23 | Level 2 | E |  | 2026-07-23 | Level 2
126798293 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126798411 | insulator and brushing | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126798776 | pole | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126798918 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126799302 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
126799629 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126799697 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126800674 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126800817 | insulator and brushing | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126800826 | insulator and brushing | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126800874 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126800977 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126801203 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126801349 | pole | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126801378 | pole | Non-HFTD | Transmission | 2023-08-10 | 2024-08-10 | Level 2 | E | 2024-08-26 | 2024-08-10 | Level 2 | GO 165 Inspection
126801449 | pole | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126801467 | insulator and brushing | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126802053 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F |  | 2028-08-04 | Level 3
126802057 | conductor | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126802058 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126802142 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126802245 | insulator and brushing | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126802486 | other | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126803356 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126803370 | pole | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126803413 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126803420 | pole | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126803449 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126803460 | other | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126803462 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126805012 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126805047 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126805132 | other | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126805138 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126805214 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126805250 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126805295 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126805301 | insulator and brushing | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126805437 | anchor/guy | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126805474 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126805478 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126805616 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126805638 | splice | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2026-08-07 | Level 2
126805651 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126805668 | pole | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126805701 | insulator and brushing | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F | 2023-09-05 | 2028-08-09 | Level 3 | GO 165 Inspection
126805724 | pole | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126806014 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126806080 | conductor | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126806481 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126806486 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126806790 | other | Non-HFTD | Transmission | 2023-08-10 | 2024-08-10 | Level 2 | E | 2024-08-30 | 2024-08-10 | Level 2 | GO 165 Inspection
126806807 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126806975 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F | 2024-10-01 | 2028-08-07 | Level 3 | GO 165 Inspection
126807287 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126807660 | insulator and brushing | Non-HFTD | Transmission | 2023-08-03 | 2024-08-03 | Level 2 | E | 2024-08-23 | 2024-08-03 | Level 2 | GO 165 Inspection
126807673 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126807809 | insulator and brushing | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126807942 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126808089 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126808150 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126808370 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126808395 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126808558 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126808792 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126808819 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126808871 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126809074 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126809106 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126809125 | other | Non-HFTD | Transmission | 2023-08-07 | 2028-08-07 | Level 3 | F |  | 2028-08-07 | Level 3
126809229 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2024-08-07 | Level 2 | E | 2024-12-03 | 2024-08-07 | Level 2 | Field Safety Reassessment
126809233 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126809269 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126809472 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126809694 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126809769 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126809803 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126809970 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126809971 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126810033 | pole | Non-HFTD | Transmission | 2023-08-03 | 2026-08-03 | Level 2 | E |  | 2026-08-03 | Level 2
126810077 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126810231 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E | 2024-08-26 | 2026-08-07 | Level 2 | GO 165 Inspection
126810232 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126810251 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126810332 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E | 2024-08-01 | 2026-08-08 | Level 2 | GO 165 Inspection
126810402 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126810449 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126810567 | splice | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126810585 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-08-26 | 2026-08-11 | Level 2 | GO 165 Inspection
126810665 | insulator and brushing | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126810687 | other | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E |  | 2024-08-07 | Level 2
126810720 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126810772 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126810950 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F |  | 2028-08-08 | Level 3
126811326 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126811607 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126811677 | insulator and brushing | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126811800 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126811947 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E | 2023-09-14 | 2026-08-09 | Level 2 | GO 165 Inspection
126812037 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126812302 | anchor/guy | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126812308 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126812378 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-09-24 | 2026-08-11 | Level 2 | GO 165 Inspection
126812404 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F | 2024-09-25 | 2028-08-11 | Level 3 | GO 165 Inspection
126812414 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 3 | F | 2024-09-25 | 2028-08-11 | Level 3 | GO 165 Inspection
126812416 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126812451 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F | 2024-08-20 | 2028-08-10 | Level 3 | GO 165 Inspection
126812491 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126812586 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126812588 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126812591 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E | 2024-08-21 | 2026-08-07 | Level 2 | GO 165 Inspection
126812632 | other | Non-HFTD | Transmission | 2023-08-03 | 2028-08-03 | Level 3 | F |  | 2028-08-03 | Level 3
126812648 | insulator and brushing | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E | 2024-10-22 | 2026-08-07 | Level 2 | GO 165 Inspection
126812854 | insulator and brushing | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F | 2024-09-11 | 2028-08-08 | Level 3 | GO 165 Inspection
126813126 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126813523 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126813744 | insulator and brushing | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E | 2024-08-20 | 2026-08-10 | Level 2 | GO 165 Inspection
126813842 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126813933 | crossarm | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126813941 | insulator and brushing | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126813942 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814073 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814082 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814237 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814339 | anchor/guy | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814500 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814577 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814594 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814759 | pole | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126814861 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126814877 | pole | Non-HFTD | Transmission | 2023-08-08 | 2026-08-08 | Level 2 | E |  | 2026-08-08 | Level 2
126814941 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126815043 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126815079 | insulator and brushing | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126815176 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815177 | pole | Non-HFTD | Transmission | 2023-08-12 | 2026-08-12 | Level 2 | E |  | 2026-08-12 | Level 2
126815295 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815359 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126815362 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815413 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126815424 | pole | Non-HFTD | Transmission | 2023-08-12 | 2026-08-12 | Level 2 | E |  | 2026-08-12 | Level 2
126815601 | other | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E | 2024-11-12 | 2026-08-09 | Level 2 | GO 165 Inspection
126815604 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815608 | other | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126815652 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126815655 | splice | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126815658 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815871 | insulator and brushing | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E |  | 2026-08-09 | Level 2
126815934 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815935 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126815938 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126816224 | other | Non-HFTD | Transmission | 2023-08-09 | 2026-08-09 | Level 2 | E | 2024-09-28 | 2026-08-09 | Level 2 | GO 165 Inspection
126816487 | other | Non-HFTD | Transmission | 2023-08-09 | 2028-08-09 | Level 3 | F |  | 2028-08-09 | Level 3
126816662 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126816669 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126816892 | anchor/guy | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126817028 | insulator and brushing | Non-HFTD | Transmission | 2023-08-12 | 2026-08-12 | Level 2 | E |  | 2026-08-12 | Level 2
126817073 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126817084 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F |  | 2028-08-12 | Level 3
126818410 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126818595 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126818629 | conductor | Non-HFTD | Transmission | 2023-08-02 | 2026-08-02 | Level 2 | E |  | 2026-08-02 | Level 2
126818841 | switch | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126819045 | pole | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126819063 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126819064 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126819356 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126819656 | pole | Non-HFTD | Transmission | 2023-08-10 | 2026-08-10 | Level 2 | E |  | 2026-08-10 | Level 2
126819919 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126820234 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126820238 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126820258 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126820433 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126821380 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2024-08-14 | Level 2 | E | 2024-09-17 | 2024-08-14 | Level 2 | GO 165 Inspection
126821914 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2024-08-14 | Level 2 | E | 2024-11-13 | 2024-08-14 | Level 2 | Field Safety Reassessment
126822062 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126822088 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126822876 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126823265 | splice | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126823275 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126823278 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126823279 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126823284 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126823307 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126823508 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E | 2023-10-17 | 2026-07-26 | Level 2 | GO 165 Inspection
126823571 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126823694 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E | 2024-06-13 | 2026-08-14 | Level 2 | GO 165 Inspection
126823705 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126823809 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126824060 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126824260 | splice | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126824649 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126824650 | splice | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126824671 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126824782 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F | 2024-09-25 | 2028-08-14 | Level 3 | GO 165 Inspection
126824784 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F | 2024-09-25 | 2028-08-14 | Level 3 | GO 165 Inspection
126824858 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126824916 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126826641 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126826864 | anchor/guy | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126826973 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126827081 | pole | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F | 2024-04-04 | 2028-08-14 | Level 3 | GO 165 Inspection
126827666 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126827748 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126827827 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126827828 | anchor/guy | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126827939 | other | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F |  | 2028-08-10 | Level 3
126828283 | pole | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126828348 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126828443 | insulator and brushing | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126828609 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126828627 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126828698 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126828724 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126828882 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126829034 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126829328 | anchor/guy | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126829907 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126829989 | pole | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126830491 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830499 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830574 | pole | Non-HFTD | Transmission | 2022-07-18 | 2023-07-18 | Level 2 | E | 2023-08-16 | 2025-07-18 | Level 2 | Standards change
126830661 | pole | Non-HFTD | Transmission | 2022-07-27 | 2023-07-27 | Level 2 | E | 2023-08-16 | 2025-07-27 | Level 2 | Standards change
126830663 | pole | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830753 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830756 | pole | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830807 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830808 | pole | Non-HFTD | Transmission | 2022-03-02 | 2023-03-02 | Level 2 | E | 2023-08-16 | 2025-03-02 | Level 2 | Standards change
126830889 | pole | Non-HFTD | Transmission | 2022-08-09 | 2023-08-09 | Level 2 | E | 2023-08-16 | 2025-08-09 | Level 2 | Standards change
126830893 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126830980 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126830984 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126831295 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126831428 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126831870 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126831912 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2024-08-15 | Level 2 | E | 2024-11-24 | 2024-08-15 | Level 2 | Field Safety Reassessment
126831944 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126831956 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F | 2024-10-01 | 2028-08-15 | Level 3 | GO 165 Inspection
126832456 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-11-13 | 2026-08-11 | Level 2 | GO 165 Inspection
126832571 | pole | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126832635 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126832642 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126832692 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E | 2024-10-01 | 2026-08-15 | Level 2 | GO 165 Inspection
126832835 | pole | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F | 2024-03-27 | 2028-08-15 | Level 3 | GO 165 Inspection
126832974 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126833105 | pole | Non-HFTD | Transmission | 2023-08-11 | 2024-08-11 | Level 2 | E | 2024-08-08 | 2024-08-11 | Level 2 | Field Safety Reassessment
126833141 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126833381 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126834060 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126834102 | pole | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126834234 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126834610 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126834703 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126834817 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2023-09-06 | 2026-08-11 | Level 2 | GO 165 Inspection
126834819 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126834863 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126834865 | pole | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126834867 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126834986 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F | 2024-10-01 | 2028-08-16 | Level 3 | GO 165 Inspection
126835018 | other | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126835049 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126835166 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F | 2024-10-01 | 2028-08-16 | Level 3 | GO 165 Inspection
126835187 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126835272 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126835365 | anchor/guy | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126835454 | insulator and brushing | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-11-20 | 2026-08-16 | Level 2 | GO 165 Inspection
126835597 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-04-11 | 2026-08-16 | Level 2 | GO 165 Inspection
126836090 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-10-01 | 2026-08-16 | Level 2 | GO 165 Inspection
126836339 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126836591 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126836703 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126836935 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126837054 | pole | Non-HFTD | Transmission | 2023-08-16 | 2024-02-16 | Level 2 | E | 2024-10-08 | 2024-02-16 | Level 2 | Field Safety Reassessment
126837059 | insulator and brushing | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126837552 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F | 2024-06-21 | 2028-08-11 | Level 3 | GO 165 Inspection
126837743 | pole | Non-HFTD | Transmission | 2023-08-11 | 2024-08-11 | Level 2 | E | 2024-11-15 | 2024-08-11 | Level 2 | Field Safety Reassessment
126837898 | pole | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126838071 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126838205 | pole | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126838545 | pole | Non-HFTD | Transmission | 2023-08-16 | 2024-08-16 | Level 2 | E | 2024-08-23 | 2024-08-16 | Level 2 | GO 165 Inspection
126838727 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126838734 | splice | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126838741 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126838745 | splice | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126838884 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126839647 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126839750 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 2 | E | 2024-08-14 | 2026-08-14 | Level 2 | GO 165 Inspection
126839830 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-07-23 | 2026-08-16 | Level 2 | GO 165 Inspection
126840528 | other | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126840553 | pole | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F | 2024-10-16 | 2028-08-16 | Level 3 | GO 165 Inspection
126840594 | pole | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F | 2024-08-15 | 2028-08-11 | Level 3 | GO 165 Inspection
126840595 | other | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-08-15 | 2026-08-11 | Level 2 | GO 165 Inspection
126840598 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F |  | 2028-08-11 | Level 3
126840618 | insulator and brushing | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-11-19 | 2024-08-16 | Level 2 | GO 165 Inspection
126840640 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-11-19 | 2026-08-16 | Level 2 | GO 165 Inspection
126841842 | other | HFTD Tier 2 | Transmission | 2023-08-16 | 2024-08-16 | Level 3 | F | 2024-02-13 | 2028-08-16 | Level 3 | GO 165 Inspection
126841874 | anchor/guy | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126841882 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126842649 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126843089 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E |  | 2026-08-11 | Level 2
126843141 | insulator and brushing | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126843261 | anchor/guy | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126843612 | splice | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126843778 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F | 2024-11-19 | 2028-08-17 | Level 3 | GO 165 Inspection
126843928 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126843949 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126844026 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126844325 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126844386 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126844614 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F | 2024-10-08 | 2028-08-17 | Level 3 | GO 165 Inspection
126844676 | switch | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-11-18 | 2026-08-17 | Level 2 | GO 165 Inspection
126844801 | other | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-08-14 | 2026-08-11 | Level 2 | GO 165 Inspection
126844805 | insulator and brushing | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-08-14 | 2026-08-11 | Level 2 | GO 165 Inspection
126845020 | anchor/guy | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126845634 | other | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E | 2024-08-05 | 2026-08-14 | Level 2 | GO 165 Inspection
126845686 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846258 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846264 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126846387 | other | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846399 | crossarm | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846406 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846410 | splice | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846413 | splice | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126846446 | insulator and brushing | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126846887 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F | 2024-08-14 | 2028-08-14 | Level 3 | GO 165 Inspection
126847914 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126848563 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126848976 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126851865 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-08-21 | 2026-08-17 | Level 2 | GO 165 Inspection
126852162 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126853152 | anchor/guy | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126856699 | anchor/guy | Non-HFTD | Transmission | 2023-08-14 | 2024-08-14 | Level 2 | E | 2024-08-12 | 2024-08-14 | Level 2 | GO 165 Inspection
126856775 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126856778 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126856869 | other | Non-HFTD | Transmission | 2022-08-14 | 2024-08-14 | Level 3 | F | 2024-07-26 | 2027-08-14 | Level 3 | GO 165 Inspection
126856903 | anchor/guy | Non-HFTD | Transmission | 2023-08-15 | 2024-08-15 | Level 2 | E | 2024-12-26 | 2024-08-15 | Level 2 | Field Safety Reassessment
126856905 | pole | Non-HFTD | Transmission | 2023-08-15 | 2023-11-15 | Level 2 | E | 2024-10-18 | 2023-11-15 | Level 2 | Field Safety Reassessment
126857056 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126857108 | other | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126857171 | splice | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126857341 | crossarm | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F | 2024-11-12 | 2028-08-15 | Level 3 | GO 165 Inspection
126857359 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126857643 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126858071 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126858171 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126858397 | anchor/guy | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126858510 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126858545 | pole | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126858771 | pole | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E | 2024-07-25 | 2026-08-15 | Level 2 | GO 165 Inspection
126859058 | splice | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126859174 | splice | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126859177 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126859351 | pole | HFTD Tier 2 | Transmission | 2023-08-18 | 2024-08-18 | Level 2 | E | 2024-04-11 | 2024-08-18 | Level 2 | GO 165 Inspection
126859384 | pole | HFTD Tier 2 | Transmission | 2023-08-18 | 2024-08-18 | Level 2 | E | 2024-04-11 | 2024-08-18 | Level 2 | GO 165 Inspection
126859390 | pole | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126859434 | splice | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E | 2024-06-20 | 2026-08-14 | Level 2 | GO 165 Inspection
126859438 | pole | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126859457 | anchor/guy | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E | 2024-08-16 | 2026-08-15 | Level 2 | GO 165 Inspection
126859459 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F | 2024-08-16 | 2028-08-15 | Level 3 | GO 165 Inspection
126859590 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126859900 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-06-25 | 2024-08-18 | Level 2 | GO 165 Inspection
126860193 | crossarm | Non-HFTD | Transmission | 2023-08-14 | 2026-08-14 | Level 2 | E |  | 2026-08-14 | Level 2
126860199 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126860240 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E | 2024-07-25 | 2026-08-15 | Level 2 | GO 165 Inspection
126860405 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126860711 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126860831 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-05-17 | 2026-08-18 | Level 2 | GO 165 Inspection
126860902 | pole | Non-HFTD | Transmission | 2023-08-18 | 2024-08-18 | Level 2 | E | 2024-08-09 | 2024-02-18 | Level 2 | Field Safety Reassessment
126861384 | anchor/guy | Non-HFTD | Transmission | 2023-08-18 | 2023-11-18 | Level 2 | E | 2024-08-01 | 2024-08-18 | Level 2 | Field Safety Reassessment
126861388 | other | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-11-08 | 2026-08-18 | Level 2 | GO 165 Inspection
126862061 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126862164 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126862266 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126862533 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126862653 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126862879 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126862936 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2024-08-23 | 2028-08-18 | Level 3 | GO 165 Inspection
126862984 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126863131 | anchor/guy | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F | 2024-10-22 | 2028-08-17 | Level 3 | GO 165 Inspection
126863418 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126863483 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-09-06 | 2026-08-17 | Level 2 | GO 165 Inspection
126863641 | other | Non-HFTD | Transmission | 2023-08-14 | 2028-08-14 | Level 3 | F |  | 2028-08-14 | Level 3
126863774 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-11-05 | 2026-08-18 | Level 2 | GO 165 Inspection
126864086 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126864120 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E | 2024-07-29 | 2026-08-15 | Level 2 | GO 165 Inspection
126864233 | pole | Non-HFTD | Transmission | 2023-08-15 | 2024-08-15 | Level 2 | E | 2024-11-20 | 2026-08-15 | Level 2 | Field Safety Reassessment
126864290 | pole | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126864729 | anchor/guy | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126864835 | anchor/guy | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126864998 | pole | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E | 2024-07-18 | 2026-08-19 | Level 2 | GO 165 Inspection
126865054 | pole | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E |  | 2026-08-19 | Level 2
126865252 | insulator and brushing | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E |  | 2026-08-19 | Level 2
126865511 | other | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126865963 | anchor/guy | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126866424 | anchor/guy | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126866909 | other | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126867010 | pole | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E |  | 2026-08-19 | Level 2
126867056 | other | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E |  | 2026-08-19 | Level 2
126867318 | pole | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E |  | 2026-08-19 | Level 2
126867332 | anchor/guy | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F | 2024-11-19 | 2028-08-19 | Level 3 | GO 165 Inspection
126867551 | other | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126867649 | other | Non-HFTD | Transmission | 2023-08-19 | 2026-08-19 | Level 2 | E | 2024-09-20 | 2026-08-19 | Level 2 | GO 165 Inspection
126867660 | anchor/guy | Non-HFTD | Transmission | 2023-08-19 | 2028-08-19 | Level 3 | F |  | 2028-08-19 | Level 3
126869845 | insulator and brushing | Non-HFTD | Transmission | 2023-08-20 | 2028-08-20 | Level 3 | F | 2024-10-14 | 2028-08-20 | Level 3 | GO 165 Inspection
126869870 | pole | Non-HFTD | Transmission | 2023-08-20 | 2026-08-20 | Level 2 | E |  | 2026-08-20 | Level 2
126870311 | pole | Non-HFTD | Transmission | 2023-08-20 | 2026-08-20 | Level 2 | E |  | 2026-08-20 | Level 2
126872739 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126872906 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126872957 | pole | HFTD Tier 2 | Transmission | 2023-08-08 | 2024-08-08 | Level 2 | E | 2024-08-05 | 2024-08-08 | Level 2 | Field Safety Reassessment
126873052 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126873262 | other | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126873312 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126873430 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126873435 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126873612 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126873730 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126874300 | insulator and brushing | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126874582 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E | 2024-07-24 | 2026-08-21 | Level 2 | GO 165 Inspection
126874596 | conductor | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126874684 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F | 2024-05-22 | 2028-08-21 | Level 3 | GO 165 Inspection
126874745 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E | 2024-07-29 | 2026-08-15 | Level 2 | GO 165 Inspection
126874831 | insulator and brushing | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126874834 | pole | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126874979 | pole | Non-HFTD | Transmission | 2022-04-25 | 2023-04-25 | Level 2 | E | 2023-11-15 | 2025-04-25 | Level 2 | Standards change
126875079 | other | Non-HFTD | Transmission | 2023-08-15 | 2028-08-15 | Level 3 | F |  | 2028-08-15 | Level 3
126875236 | pole | Non-HFTD | Transmission | 2023-08-15 | 2026-08-15 | Level 2 | E |  | 2026-08-15 | Level 2
126875453 | insulator and brushing | HFTD Tier 2 | Transmission | 2023-08-21 | 2024-08-21 | Level 2 | E | 2024-02-20 | 2024-08-21 | Level 2 | GO 165 Inspection
126875484 | conductor | HFTD Tier 2 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126875529 | splice | HFTD Tier 2 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-03-06 | 2024-03-23 | Level 2 | GO 165 Inspection
126875631 | conductor | HFTD Tier 2 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-04-25 | 2026-03-23 | Level 2 | GO 165 Inspection
126875660 | insulator and brushing | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E | 2024-04-04 | 2026-08-21 | Level 2 | GO 165 Inspection
126875992 | conductor | HFTD Tier 2 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-04-16 | 2026-03-23 | Level 2 | GO 165 Inspection
126876049 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126876375 | other | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126876547 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126876553 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F | 2024-10-10 | 2028-08-21 | Level 3 | GO 165 Inspection
126876617 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126876689 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F | 2024-10-22 | 2028-08-21 | Level 3 | GO 165 Inspection
126876808 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-03-26 | 2026-03-23 | Level 2 | GO 165 Inspection
126876833 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E | 2024-03-26 | 2026-03-23 | Level 2 | GO 165 Inspection
126876840 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126876898 | splice | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126877338 | pole | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126877340 | other | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126877423 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126877921 | other | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126877951 | pole | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126878078 | pole | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126878197 | insulator and brushing | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126878240 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126878458 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126879111 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126880575 | conductor | HFTD Tier 2 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880601 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880604 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880613 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880617 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880619 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880620 | conductor | HFTD Tier 3 | Transmission | 2023-03-23 | 2026-03-23 | Level 2 | E |  | 2026-03-23 | Level 2
126880625 | switch | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E | 2024-09-20 | 2026-08-21 | Level 2 | Field Safety Reassessment
126880901 | other | Non-HFTD | Transmission | 2023-08-18 | 2024-08-18 | Level 2 | E | 2024-10-28 | 2024-08-18 | Level 2 | GO 165 Inspection
126880967 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-10-28 | 2026-08-18 | Level 2 | GO 165 Inspection
126881567 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126881765 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126882174 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126882192 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E | 2024-10-30 | 2026-08-22 | Level 2 | GO 165 Inspection
126882262 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126882455 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126882459 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126882473 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126882524 | pole | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126882525 | anchor/guy | Non-HFTD | Transmission | 2023-08-16 | 2024-08-16 | Level 2 | E | 2024-09-26 | 2024-08-16 | Level 2 | Field Safety Reassessment
126882607 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126882984 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126883139 | insulator and brushing | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126883192 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126883197 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126883358 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126883363 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126883585 | pole | HFTD Tier 2 | Transmission | 2023-08-22 | 2024-08-22 | Level 2 | E | 2024-11-10 | 2024-08-22 | Level 2 | Field Safety Reassessment
126883948 | splice | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126883995 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126884151 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126884451 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126884728 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F | 2024-08-06 | 2028-08-16 | Level 3 | GO 165 Inspection
126885397 | other | Non-HFTD | Transmission | 2023-08-16 | 2028-08-16 | Level 3 | F |  | 2028-08-16 | Level 3
126887132 | insulator and brushing | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E |  | 2026-08-16 | Level 2
126887584 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126887603 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126887604 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126887906 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126887909 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126888209 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-08-15 | 2026-08-17 | Level 2 | GO 165 Inspection
126888214 | insulator and brushing | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F | 2024-11-18 | 2028-08-22 | Level 3 | GO 165 Inspection
126888397 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E | 2024-11-18 | 2026-08-22 | Level 2 | GO 165 Inspection
126888496 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126888501 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126888633 | pole | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E | 2024-10-05 | 2026-08-21 | Level 2 | GO 165 Inspection
126888645 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-08-19 | 2026-08-17 | Level 2 | GO 165 Inspection
126888733 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126888777 | insulator and brushing | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E | 2024-09-20 | 2026-08-21 | Level 2 | GO 165 Inspection
126888834 | pole | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F | 2024-08-20 | 2028-08-17 | Level 3 | GO 165 Inspection
126888869 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-08-16 | 2026-08-17 | Level 2 | GO 165 Inspection
126888872 | anchor/guy | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2024-09-20 | 2028-08-18 | Level 3 | GO 165 Inspection
126888927 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126888932 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126888941 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-08-16 | 2026-08-17 | Level 2 | GO 165 Inspection
126888984 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-08-15 | 2026-08-17 | Level 2 | GO 165 Inspection
126889006 | other | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-04-09 | 2026-08-17 | Level 2 | GO 165 Inspection
126889026 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E | 2024-11-18 | 2026-08-22 | Level 2 | GO 165 Inspection
126889161 | pole | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126889246 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-10-23 | 2026-08-17 | Level 2 | GO 165 Inspection
126889256 | anchor/guy | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F | 2023-09-15 | 2028-08-17 | Level 3 | GO 165 Inspection
126889276 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126889567 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126890012 | other | Non-HFTD | Transmission | 2023-08-16 | 2026-08-16 | Level 2 | E | 2024-09-27 | 2026-08-16 | Level 2 | GO 165 Inspection
126890996 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126891126 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-10-01 | 2026-08-23 | Level 2 | GO 165 Inspection
126891165 | pole | Non-HFTD | Transmission | 2023-08-23 | 2024-08-23 | Level 2 | E | 2024-10-30 | 2024-02-23 | Level 2 | GO 165 Inspection
126891565 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126891569 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126891803 | other | HFTD Tier 2 | Transmission | 2023-08-23 | 2024-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126891978 | other | HFTD Tier 3 | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F | 2024-04-01 | 2028-08-23 | Level 3 | GO 165 Inspection
126892201 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-12-09 | 2026-08-23 | Level 2 | Field Safety Reassessment
126892817 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126892909 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126892936 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126893238 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126893537 | other | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126893547 | splice | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126893935 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F | 2024-10-18 | 2028-08-23 | Level 3 | GO 165 Inspection
126894058 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-10-18 | 2026-08-23 | Level 2 | GO 165 Inspection
126894449 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 3 | F | 2024-07-24 | 2028-08-23 | Level 3 | GO 165 Inspection
126894586 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 3 | F | 2024-07-24 | 2028-08-23 | Level 3 | GO 165 Inspection
126894612 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126896171 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126896173 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126896911 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126897470 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126897499 | pole | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126897500 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126897632 | insulator and brushing | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126897684 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126897737 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2024-09-26 | 2028-08-18 | Level 3 | GO 165 Inspection
126897762 | other | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E | 2024-06-21 | 2026-08-17 | Level 2 | GO 165 Inspection
126897954 | pole | Non-HFTD | Transmission | 2023-08-18 | 2024-08-18 | Level 2 | E | 2024-11-26 | 2024-08-18 | Level 2 | Field Safety Reassessment
126898012 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126898029 | pole | Non-HFTD | Transmission | 2023-08-23 | 2024-08-23 | Level 2 | E | 2024-09-04 | 2024-08-23 | Level 2 | Field Safety Reassessment
126898044 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126898053 | pole | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126898104 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126898109 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F | 2024-08-19 | 2028-08-17 | Level 3 | GO 165 Inspection
126898112 | anchor/guy | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126898114 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126898126 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126898151 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126899563 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126899586 | conductor | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-10-29 | 2026-08-24 | Level 2 | GO 165 Inspection
126900249 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126900354 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-09-28 | 2026-08-18 | Level 2 | GO 165 Inspection
126900472 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126900618 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126900690 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2023-11-30 | 2028-08-18 | Level 3 | GO 165 Inspection
126900783 | other | Non-HFTD | Transmission | 2023-08-17 | 2028-08-17 | Level 3 | F |  | 2028-08-17 | Level 3
126901240 | pole | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E |  | 2026-08-24 | Level 2
126901517 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126903302 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-09-11 | 2026-08-18 | Level 2 | GO 165 Inspection
126903473 | pole | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-06-06 | 2028-08-24 | Level 3 | GO 165 Inspection
126903514 | pole | Non-HFTD | Transmission | 2022-09-01 | 2023-09-01 | Level 2 | E | 2023-11-15 | 2025-09-01 | Level 2 | Standards change
126903610 | anchor/guy | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-10-29 | 2028-08-24 | Level 3 | GO 165 Inspection
126903891 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2024-05-17 | 2028-08-18 | Level 3 | GO 165 Inspection
126903998 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126904266 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-10-25 | 2026-08-18 | Level 2 | GO 165 Inspection
126904346 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126904347 | anchor/guy | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126904417 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126904529 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126904595 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126904599 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
126904721 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2024-08-21 | 2028-08-18 | Level 3 | GO 165 Inspection
126905060 | other | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126905224 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126905237 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126905338 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126905416 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126905443 | pole | Non-HFTD | Transmission | 2023-08-17 | 2026-08-17 | Level 2 | E |  | 2026-08-17 | Level 2
126905492 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126905821 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126906168 | pole | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E |  | 2026-08-04 | Level 2
126906231 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126906421 | pole | Non-HFTD | Transmission | 2023-08-04 | 2026-08-04 | Level 2 | E | 2024-01-30 | 2026-08-04 | Level 2 | GO 165 Inspection
126906434 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126906436 | anchor/guy | HFTD Tier 2 | Transmission | 2023-08-24 | 2024-08-24 | Level 3 | F | 2024-05-30 | 2028-08-24 | Level 3 | GO 165 Inspection
126906477 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126906598 | switch | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126906849 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126906874 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126906917 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126906919 | anchor/guy | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126907015 | switch | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E | 2024-02-15 | 2026-08-18 | Level 2 | Field Safety Reassessment
126907070 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126907075 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126907086 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126907108 | anchor/guy | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F |  | 2028-08-18 | Level 3
126907132 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126907136 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126907193 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126907194 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2024-08-22 | Level 2 | E |  | 2024-08-22 | Level 2
126907230 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126907376 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126907396 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126907424 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126907524 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E |  | 2026-08-24 | Level 2
126907525 | pole | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2023-09-29 | 2026-08-24 | Level 2 | GO 165 Inspection
126909045 | pole | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E |  | 2026-08-24 | Level 2
126909053 | other | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126909069 | splice | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126909084 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126909088 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126909124 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126909125 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-11-19 | 2026-08-23 | Level 2 | GO 165 Inspection
126909242 | other | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126909262 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-06-20 | 2024-08-23 | Level 2 | GO 165 Inspection
126909283 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126909291 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126909295 | other | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126909375 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126909398 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126909440 | anchor/guy | Non-HFTD | Transmission | 2023-08-21 | 2028-08-21 | Level 3 | F |  | 2028-08-21 | Level 3
126909475 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126909564 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126909595 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126909683 | other | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126909754 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126909757 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126909860 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126909862 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-09-13 | 2028-08-24 | Level 3 | GO 165 Inspection
126909948 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126910010 | other | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126910016 | insulator and brushing | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126910100 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126910148 | anchor/guy | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126910227 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126910354 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-10-03 | 2026-08-23 | Level 2 | GO 165 Inspection
126910487 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126910492 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126910632 | anchor/guy | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126910696 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126910702 | crossarm | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-12-02 | 2026-08-23 | Level 2 | GO 165 Inspection
126910739 | anchor/guy | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126911008 | other | HFTD Tier 2 | Transmission | 2023-08-24 | 2024-08-24 | Level 2 | E | 2024-06-05 | 2024-08-24 | Level 2 | GO 165 Inspection
126911402 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126911560 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126911629 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126911682 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-10-03 | 2026-08-23 | Level 2 | GO 165 Inspection
126912035 | other | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126912604 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126912684 | other | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126912685 | anchor/guy | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126912708 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126912757 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126912788 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126913123 | insulator and brushing | Non-HFTD | Transmission | 2023-08-22 | 2028-08-22 | Level 3 | F |  | 2028-08-22 | Level 3
126913189 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126913344 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-11 | 2026-08-24 | Level 2 | GO 165 Inspection
126913426 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126913454 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-10-01 | 2026-08-25 | Level 2 | GO 165 Inspection
126913456 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-10-01 | 2026-08-25 | Level 2 | GO 165 Inspection
126913463 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126913502 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E |  | 2026-08-24 | Level 2
126913934 | other | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2023-10-03 | 2026-08-24 | Level 2 | GO 165 Inspection
126913975 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-10-07 | 2024-02-25 | Level 2 | GO 165 Inspection
126914049 | splice | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2023-09-19 | 2026-08-25 | Level 2 | GO 165 Inspection
126914604 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-08-27 | 2026-08-24 | Level 2 | GO 165 Inspection
126914631 | pole | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F | 2024-09-03 | 2028-08-25 | Level 3 | GO 165 Inspection
126914665 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126915292 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126915295 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F |  | 2028-08-25 | Level 3
126915465 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-11-04 | 2028-08-24 | Level 3 | GO 165 Inspection
126915544 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F | 2024-07-24 | 2028-08-25 | Level 3 | GO 165 Inspection
126916626 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-11-24 | 2026-08-25 | Level 2 | GO 165 Inspection
126917069 | other | HFTD Tier 2 | Transmission | 2023-08-26 | 2028-08-26 | Level 3 | F | 2024-05-10 | 2028-08-26 | Level 3 | GO 165 Inspection
126917162 | anchor/guy | Non-HFTD | Transmission | 2023-08-26 | 2028-08-26 | Level 3 | F | 2024-10-01 | 2028-08-26 | Level 3 | GO 165 Inspection
126917373 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-10-22 | 2026-08-26 | Level 2 | GO 165 Inspection
126917446 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-10-22 | 2026-08-26 | Level 2 | GO 165 Inspection
126917530 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E |  | 2026-08-26 | Level 2
126917767 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-11-20 | 2026-08-26 | Level 2 | GO 165 Inspection
126917946 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-07-24 | 2026-08-26 | Level 2 | GO 165 Inspection
126918034 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E |  | 2026-08-26 | Level 2
126918201 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E |  | 2026-08-26 | Level 2
126918259 | insulator and brushing | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-08-05 | 2026-08-26 | Level 2 | GO 165 Inspection
126918977 | insulator and brushing | Non-HFTD | Transmission | 2023-08-26 | 2028-08-26 | Level 3 | F |  | 2028-08-26 | Level 3
126919020 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E |  | 2026-08-26 | Level 2
126919027 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E |  | 2026-08-26 | Level 2
126919483 | other | Non-HFTD | Transmission | 2023-08-26 | 2028-08-26 | Level 3 | F |  | 2028-08-26 | Level 3
126919525 | other | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-11-02 | 2026-08-26 | Level 2 | GO 165 Inspection
126920355 | anchor/guy | Non-HFTD | Transmission | 2023-08-26 | 2028-08-26 | Level 3 | F | 2024-07-22 | 2028-08-26 | Level 3 | GO 165 Inspection
126920724 | pole | Non-HFTD | Transmission | 2023-08-26 | 2026-08-26 | Level 2 | E | 2024-11-13 | 2026-08-26 | Level 2 | GO 165 Inspection
126925216 | insulator and brushing | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126925360 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-10-22 | 2026-08-28 | Level 2 | GO 165 Inspection
126925701 | pole | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E |  | 2026-08-21 | Level 2
126925737 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-07-25 | 2026-08-28 | Level 2 | GO 165 Inspection
126925916 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126926162 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-09-26 | 2026-08-25 | Level 2 | GO 165 Inspection
126926566 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126926646 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F | 2024-08-20 | 2028-08-28 | Level 3 | GO 165 Inspection
126926665 | anchor/guy | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126926837 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-11-13 | 2026-08-23 | Level 2 | GO 165 Inspection
126927186 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F | 2024-06-20 | 2028-08-23 | Level 3 | GO 165 Inspection
126927374 | anchor/guy | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126927608 | conductor | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126927993 | other | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-07-12 | 2026-08-28 | Level 2 | GO 165 Inspection
126928030 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-07-17 | 2026-08-28 | Level 2 | GO 165 Inspection
126928488 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126930408 | anchor/guy | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126932925 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126933225 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126933765 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-07-24 | 2026-08-28 | Level 2 | GO 165 Inspection
126934787 | pole | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F | 2024-11-19 | 2028-08-23 | Level 3 | GO 165 Inspection
126934874 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F | 2024-07-24 | 2028-08-28 | Level 3 | GO 165 Inspection
126935619 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-11-15 | 2026-08-28 | Level 2 | GO 165 Inspection
126935632 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E |  | 2026-08-28 | Level 2
126935651 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-11-13 | 2026-08-28 | Level 2 | GO 165 Inspection
126936233 | anchor/guy | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126937274 | other | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126937275 | other | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E |  | 2026-08-28 | Level 2
126937926 | other | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-10-09 | 2026-08-29 | Level 2 | GO 165 Inspection
126938113 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F | 2024-08-27 | 2028-08-23 | Level 3 | GO 165 Inspection
126938194 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F | 2024-08-30 | 2028-08-23 | Level 3 | GO 165 Inspection
126938319 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-11 | 2026-08-24 | Level 2 | GO 165 Inspection
126939248 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126939604 | pole | Non-HFTD | Transmission | 2023-08-22 | 2026-08-22 | Level 2 | E |  | 2026-08-22 | Level 2
126939663 | other | HFTD Tier 2 | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F | 2024-05-02 | 2028-08-29 | Level 3 | GO 165 Inspection
126940178 | insulator and brushing | Non-HFTD | Transmission | 2023-08-29 | 2024-08-29 | Level 2 | E | 2024-08-30 | 2024-08-29 | Level 2 | Field Safety Reassessment
126940333 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-16 | 2026-08-24 | Level 2 | GO 165 Inspection
126940338 | pole | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-16 | 2026-08-24 | Level 2 | GO 165 Inspection
126940913 | pole | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E |  | 2026-08-24 | Level 2
126941773 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-11-27 | 2028-08-24 | Level 3 | GO 165 Inspection
126942416 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F | 2024-06-18 | 2028-08-29 | Level 3 | GO 165 Inspection
126942420 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F | 2024-10-24 | 2028-08-29 | Level 3 | GO 165 Inspection
126942593 | other | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 3 | F | 2024-05-07 | 2028-08-29 | Level 3 | Field Safety Reassessment
126942609 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-12-10 | 2028-08-24 | Level 3 | GO 165 Inspection
126942750 | pole | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-12 | 2026-08-24 | Level 2 | GO 165 Inspection
126942752 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-12 | 2026-08-24 | Level 2 | GO 165 Inspection
126943228 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126943279 | pole | Non-HFTD | Transmission | 2023-08-29 | 2024-08-29 | Level 2 | E | 2024-10-30 | 2023-11-29 | Level 2 | GO 165 Inspection
126943451 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F | 2024-09-06 | 2028-08-25 | Level 3 | GO 165 Inspection
126944203 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-08-31 | 2026-08-25 | Level 2 | GO 165 Inspection
126944357 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2024-08-24 | Level 2 | E | 2024-09-12 | 2023-11-24 | Level 2 | GO 165 Inspection
126944828 | pole | Non-HFTD | Transmission | 2023-08-25 | 2024-02-25 | Level 2 | E | 2024-11-20 | 2024-02-25 | Level 2 | GO 165 Inspection
126945704 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-07-22 | 2026-08-25 | Level 2 | GO 165 Inspection
126946396 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-08-31 | 2026-08-25 | Level 2 | GO 165 Inspection
126947357 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126949936 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126951452 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-09-06 | 2026-08-25 | Level 2 | GO 165 Inspection
126951573 | other | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126951815 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126951921 | insulator and brushing | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126952130 | other | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126952168 | other | HFTD Tier 2 | Transmission | 2023-08-30 | 2024-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126953081 | pole | HFTD Tier 2 | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126953086 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-09-16 | 2026-08-28 | Level 2 | GO 165 Inspection
126953250 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F | 2024-09-26 | 2028-08-28 | Level 3 | GO 165 Inspection
126953258 | pole | HFTD Tier 2 | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F |  | 2028-08-24 | Level 3
126953599 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126953626 | other | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-09-24 | 2026-08-25 | Level 2 | GO 165 Inspection
126953649 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126953701 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-11-08 | 2028-08-24 | Level 3 | GO 165 Inspection
126953797 | other | HFTD Tier 2 | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126953804 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F | 2024-11-12 | 2028-08-28 | Level 3 | Field Safety Reassessment
126953813 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126953940 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F | 2024-09-26 | 2028-08-25 | Level 3 | GO 165 Inspection
126953950 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F | 2024-09-26 | 2028-08-28 | Level 3 | GO 165 Inspection
126954067 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-11-05 | 2026-08-24 | Level 2 | GO 165 Inspection
126954089 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-09-13 | 2026-08-29 | Level 2 | GO 165 Inspection
126954112 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-06-20 | 2024-08-23 | Level 2 | GO 165 Inspection
126954210 | pole | Non-HFTD | Transmission | 2023-08-28 | 2024-08-28 | Level 2 | E | 2024-09-16 | 2026-08-28 | Level 2 | GO 165 Inspection
126954215 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-09-16 | 2026-08-28 | Level 2 | GO 165 Inspection
126954268 | other | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-09-26 | 2026-08-28 | Level 2 | GO 165 Inspection
126954416 | other | HFTD Tier 2 | Transmission | 2023-08-30 | 2024-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126954431 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126954810 | other | Non-HFTD | Transmission | 2023-08-23 | 2028-08-23 | Level 3 | F |  | 2028-08-23 | Level 3
126954878 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-11-13 | 2026-08-28 | Level 2 | GO 165 Inspection
126954918 | other | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E |  | 2026-08-23 | Level 2
126955029 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-08-31 | 2026-08-28 | Level 2 | GO 165 Inspection
126955196 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 2 | E | 2024-08-21 | 2024-08-05 | Level 2 | Field Safety Reassessment
126955400 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F | 2024-05-09 | 2028-08-05 | Level 3 | GO 165 Inspection
126955435 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-10-30 | 2028-08-24 | Level 3 | GO 165 Inspection
126955717 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2024-08-25 | Level 2 | E | 2024-11-18 | 2024-08-25 | Level 2 | GO 165 Inspection
126955718 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-11-18 | 2026-08-25 | Level 2 | GO 165 Inspection
126955917 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-11-18 | 2026-08-25 | Level 2 | GO 165 Inspection
126957371 | other | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-09-26 | 2026-08-28 | Level 2 | GO 165 Inspection
126958618 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-09-03 | 2026-08-28 | Level 2 | GO 165 Inspection
126959233 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-08-31 | 2026-08-28 | Level 2 | GO 165 Inspection
126959963 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126960201 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126960389 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-09-11 | 2026-08-24 | Level 2 | GO 165 Inspection
126960622 | pole | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2024-09-11 | 2028-08-24 | Level 3 | GO 165 Inspection
126961018 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126961169 | anchor/guy | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126961183 | other | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E | 2024-08-22 | 2026-08-30 | Level 2 | GO 165 Inspection
126961213 | anchor/guy | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126961321 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E | 2024-10-18 | 2026-08-30 | Level 2 | GO 165 Inspection
126961511 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126961533 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126961609 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126961679 | other | Non-HFTD | Transmission | 2023-08-24 | 2028-08-24 | Level 3 | F | 2023-09-29 | 2028-08-24 | Level 3 | GO 165 Inspection
126961695 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126961766 | other | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-10-21 | 2026-08-28 | Level 2 | GO 165 Inspection
126961771 | splice | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126961778 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126961807 | other | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126961945 | insulator and brushing | Non-HFTD | Transmission | 2023-08-24 | 2026-08-24 | Level 2 | E | 2024-06-20 | 2026-08-24 | Level 2 | GO 165 Inspection
126962021 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126962041 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126962125 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126962145 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126962201 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126964096 | other | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-09-13 | 2026-08-29 | Level 2 | GO 165 Inspection
126964101 | pole | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E |  | 2026-08-28 | Level 2
126964102 | anchor/guy | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126964129 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126964165 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-08-14 | 2026-08-29 | Level 2 | GO 165 Inspection
126964194 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126964207 | other | Non-HFTD | Transmission | 2023-08-25 | 2028-08-25 | Level 3 | F | 2024-09-26 | 2028-08-25 | Level 3 | GO 165 Inspection
126964208 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-09-16 | 2023-11-25 | Level 2 | GO 165 Inspection
126964210 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126964384 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126964404 | anchor/guy | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E | 2024-09-20 | 2026-08-30 | Level 2 | GO 165 Inspection
126964412 | other | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126964479 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126964500 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126964539 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126964663 | anchor/guy | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126964760 | other | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E |  | 2026-08-25 | Level 2
126965153 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126965179 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126965202 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126965334 | insulator and brushing | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-09-16 | 2026-08-25 | Level 2 | GO 165 Inspection
126965482 | pole | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2024-10-04 | 2026-08-25 | Level 2 | GO 165 Inspection
126965574 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-08-28 | 2026-08-29 | Level 2 | GO 165 Inspection
126965671 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126965744 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126965790 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F | 2024-09-26 | 2028-08-28 | Level 3 | GO 165 Inspection
126965805 | crossarm | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E | 2024-11-19 | 2026-09-01 | Level 2 | GO 165 Inspection
126965806 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126965844 | other | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126965967 | other | Non-HFTD | Transmission | 2023-08-25 | 2026-08-25 | Level 2 | E | 2023-09-20 | 2026-08-25 | Level 2 | GO 165 Inspection
126966076 | conductor | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-09-13 | 2026-08-29 | Level 2 | GO 165 Inspection
126966278 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126966307 | insulator and brushing | Non-HFTD | Transmission | 2023-08-28 | 2026-08-28 | Level 2 | E | 2024-09-13 | 2026-08-28 | Level 2 | GO 165 Inspection
126966732 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126966772 | conductor | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F | 2024-09-20 | 2028-08-30 | Level 3 | GO 165 Inspection
126967095 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967104 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126967107 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126967138 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126967220 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126967221 | insulator and brushing | Non-HFTD | Transmission | 2023-08-31 | 2024-08-31 | Level 2 | E | 2024-12-10 | 2024-08-31 | Level 2 | Field Safety Reassessment
126967228 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967307 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F | 2024-08-31 | 2028-08-30 | Level 3 | GO 165 Inspection
126967400 | insulator and brushing | Non-HFTD | Transmission | 2023-08-31 | 2024-08-31 | Level 2 | E | 2024-12-10 | 2024-08-31 | Level 2 | Field Safety Reassessment
126967482 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967625 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967734 | switch | Non-HFTD | Transmission | 2023-09-01 | 2024-09-01 | Level 2 | E |  | 2024-09-01 | Level 2
126967816 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967854 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126967884 | crossarm | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967885 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126967984 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126968144 | crossarm | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126968195 | other | Non-HFTD | Transmission | 2023-08-31 | 2024-08-31 | Level 2 | E | 2024-08-09 | 2024-08-31 | Level 2 | GO 165 Inspection
126968265 | other | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126968288 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126968441 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F | 2024-09-10 | 2028-08-30 | Level 3 | GO 165 Inspection
126968464 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F | 2024-07-25 | 2028-09-01 | Level 3 | GO 165 Inspection
126968476 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126968712 | conductor | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E | 2023-10-03 | 2026-08-31 | Level 2 | GO 165 Inspection
126968846 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126968996 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126969105 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126969441 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126971853 | pole | Non-HFTD | Transmission | 2023-09-02 | 2028-09-02 | Level 3 | F |  | 2028-09-02 | Level 3
126972859 | other | Non-HFTD | Transmission | 2023-09-02 | 2028-09-02 | Level 3 | F |  | 2028-09-02 | Level 3
126973178 | other | Non-HFTD | Transmission | 2023-09-02 | 2028-09-02 | Level 3 | F |  | 2028-09-02 | Level 3
126973362 | other | Non-HFTD | Transmission | 2023-09-02 | 2028-09-02 | Level 3 | F |  | 2028-09-02 | Level 3
126973527 | anchor/guy | Non-HFTD | Transmission | 2023-09-02 | 2028-09-02 | Level 3 | F |  | 2028-09-02 | Level 3
126973898 | other | Non-HFTD | Transmission | 2023-09-02 | 2028-09-02 | Level 3 | F |  | 2028-09-02 | Level 3
126974159 | pole | Non-HFTD | Transmission | 2023-09-02 | 2026-09-02 | Level 2 | E |  | 2026-09-02 | Level 2
126977710 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126977718 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126977925 | pole | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126978019 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126978021 | other | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E | 2024-10-05 | 2026-08-31 | Level 2 | GO 165 Inspection
126978026 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F | 2024-10-05 | 2028-08-31 | Level 3 | GO 165 Inspection
126978184 | other | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126978947 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126979209 | crossarm | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126979306 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F | 2023-10-03 | 2028-08-31 | Level 3 | GO 165 Inspection
126979396 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126979756 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126980569 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126980994 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126981108 | anchor/guy | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126981112 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126981117 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126981284 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E | 2023-10-03 | 2026-08-31 | Level 2 | GO 165 Inspection
126981369 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126981961 | anchor/guy | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126982085 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126982888 | pole | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126983085 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126983103 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126983529 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126983906 | pole | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F | 2024-08-23 | 2028-09-01 | Level 3 | GO 165 Inspection
126984029 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-30 | 2026-09-05 | Level 2 | GO 165 Inspection
126984093 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126984129 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
126984147 | pole | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126984182 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-23 | 2026-09-05 | Level 2 | GO 165 Inspection
126984191 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-07-29 | 2026-09-05 | Level 2 | GO 165 Inspection
126984196 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F | 2024-08-09 | 2028-09-05 | Level 3 | GO 165 Inspection
126984250 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126984263 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126984319 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F | 2024-07-23 | 2028-09-05 | Level 3 | GO 165 Inspection
126984423 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126984427 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126984430 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126984444 | pole | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126984475 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126984522 | pole | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126984526 | pole | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126984531 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126984536 | pole | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E |  | 2026-08-29 | Level 2
126984618 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126984692 | anchor/guy | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126986649 | anchor/guy | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-07-26 | 2026-09-05 | Level 2 | GO 165 Inspection
126987091 | other | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E | 2024-09-06 | 2026-09-06 | Level 2 | GO 165 Inspection
126987378 | other | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126987674 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126987773 | pole | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126988142 | anchor/guy | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126988341 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126989127 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E | 2024-09-30 | 2026-09-01 | Level 2 | GO 165 Inspection
126989158 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126989275 | crossarm | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126989346 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126989347 | splice | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126989496 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126989561 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126989770 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E | 2024-08-14 | 2026-08-30 | Level 2 | GO 165 Inspection
126989771 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126990058 | anchor/guy | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126990123 | conductor | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126990296 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126990481 | splice | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126990915 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126990917 | other | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E | 2024-07-24 | 2026-09-06 | Level 2 | GO 165 Inspection
126990950 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126991154 | other | Non-HFTD | Transmission | 2023-08-29 | 2028-08-29 | Level 3 | F |  | 2028-08-29 | Level 3
126991189 | crossarm | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126991452 | other | Non-HFTD | Transmission | 2023-08-29 | 2026-08-29 | Level 2 | E | 2024-07-23 | 2026-08-29 | Level 2 | GO 165 Inspection
126991584 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126991587 | pole | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126991821 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126992039 | crossarm | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126992060 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E | 2024-07-11 | 2026-09-01 | Level 2 | GO 165 Inspection
126992274 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126992290 | anchor/guy | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126992397 | anchor/guy | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126992609 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E | 2024-11-08 | 2026-09-06 | Level 2 | GO 165 Inspection
126992862 | crossarm | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126993188 | other | Non-HFTD | Transmission | 2023-09-06 | 2024-09-06 | Level 2 | E | 2024-08-09 | 2023-12-06 | Level 2 | GO 165 Inspection
126993662 | other | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E | 2024-10-28 | 2026-09-06 | Level 2 | GO 165 Inspection
126993761 | other | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
126993836 | insulator and brushing | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126993838 | insulator and brushing | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126993921 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
126993996 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126993997 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
126994085 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126994114 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F |  | 2028-08-30 | Level 3
126994119 | insulator and brushing | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126994174 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E | 2024-09-30 | 2026-09-01 | Level 2 | GO 165 Inspection
126994176 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E | 2024-09-30 | 2026-09-01 | Level 2 | GO 165 Inspection
126994179 | splice | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126994190 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F | 2023-10-03 | 2028-08-31 | Level 3 | GO 165 Inspection
126994204 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126994248 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126994254 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E | 2024-08-12 | 2026-08-30 | Level 2 | GO 165 Inspection
126994265 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E | 2024-08-22 | 2026-09-01 | Level 2 | GO 165 Inspection
126994306 | insulator and brushing | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E |  | 2026-08-30 | Level 2
126994320 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126994339 | other | Non-HFTD | Transmission | 2023-08-30 | 2028-08-30 | Level 3 | F | 2024-10-05 | 2028-08-30 | Level 3 | GO 165 Inspection
126994390 | pole | Non-HFTD | Transmission | 2023-08-30 | 2026-08-30 | Level 2 | E | 2024-10-05 | 2026-08-30 | Level 2 | GO 165 Inspection
126994905 | splice | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
126994979 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
126995017 | pole | Non-HFTD | Transmission | 2023-08-18 | 2026-08-18 | Level 2 | E |  | 2026-08-18 | Level 2
126995036 | anchor/guy | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
126995061 | pole | Non-HFTD | Transmission | 2023-08-23 | 2026-08-23 | Level 2 | E | 2024-04-08 | 2026-08-23 | Level 2 | GO 165 Inspection
126995141 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126995460 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
126996311 | crossarm | Non-HFTD | Transmission | 2023-09-07 | 2024-09-07 | Level 2 | E | 2024-11-15 | 2024-09-07 | Level 2 | Field Safety Reassessment
126996512 | anchor/guy | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126996728 | pole | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126996811 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
126996928 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126996935 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
126996999 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
126997059 | other | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E | 2023-10-03 | 2026-08-31 | Level 2 | GO 165 Inspection
126997226 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
126998216 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
126998376 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
126998595 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2023-10-30 | 2026-09-07 | Level 2 | Field Safety Reassessment
126998720 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126998946 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-10-29 | 2026-09-07 | Level 2 | GO 165 Inspection
126998995 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126999168 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126999383 | other | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
126999469 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-09-13 | 2026-09-07 | Level 2 | GO 165 Inspection
126999474 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
126999748 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127000037 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127000125 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127000131 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127000437 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-11-19 | 2026-09-07 | Level 2 | GO 165 Inspection
127000458 | pole | Non-HFTD | Transmission | 2023-08-31 | 2028-08-31 | Level 3 | F |  | 2028-08-31 | Level 3
127000842 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-08-21 | 2026-09-07 | Level 2 | GO 165 Inspection
127000845 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-08-21 | 2026-09-07 | Level 2 | GO 165 Inspection
127000848 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127000917 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2023-12-07 | Level 2 | E | 2024-10-16 | 2023-12-07 | Level 2 | Field Safety Reassessment
127001178 | other | HFTD Tier 2 | Transmission | 2023-09-07 | 2024-09-07 | Level 2 | E |  | 2024-09-07 | Level 2
127001309 | other | HFTD Tier 2 | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F | 2024-05-01 | 2028-09-07 | Level 3 | GO 165 Inspection
127001321 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127001512 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F | 2024-07-18 | 2028-09-01 | Level 3 | GO 165 Inspection
127003556 | pole | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F | 2024-09-18 | 2028-09-06 | Level 3 | GO 165 Inspection
127003558 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E | 2024-09-18 | 2026-09-06 | Level 2 | GO 165 Inspection
127003624 | other | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127003638 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127003651 | other | Non-HFTD | Transmission | 2023-09-05 | 2024-09-05 | Level 2 | E |  | 2024-09-05 | Level 2
127003710 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
127003730 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-07 | 2026-09-05 | Level 2 | GO 165 Inspection
127003770 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-11-12 | 2026-09-07 | Level 2 | GO 165 Inspection
127003771 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-11-12 | 2026-09-07 | Level 2 | GO 165 Inspection
127003949 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127004093 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127004100 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127004117 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
127004170 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-09-14 | 2026-09-05 | Level 2 | GO 165 Inspection
127004200 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
127004217 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
127004238 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
127004313 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127004326 | splice | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
127004353 | pole | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127004484 | crossarm | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127004520 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
127004533 | pole | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127004558 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
127004619 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127004631 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127004891 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127004896 | pole | Non-HFTD | Transmission | 2023-08-31 | 2026-08-31 | Level 2 | E |  | 2026-08-31 | Level 2
127004943 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2024-09-07 | Level 2 | E | 2024-12-11 | 2024-03-07 | Level 2 | GO 165 Inspection
127005092 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127005113 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127005186 | anchor/guy | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-30 | 2026-09-05 | Level 2 | GO 165 Inspection
127005208 | insulator and brushing | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127005226 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127005306 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F | 2024-08-23 | 2028-09-05 | Level 3 | GO 165 Inspection
127005342 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-24 | 2026-09-05 | Level 2 | GO 165 Inspection
127005472 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127005501 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-23 | 2026-09-05 | Level 2 | GO 165 Inspection
127005636 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-12-11 | 2026-09-07 | Level 2 | GO 165 Inspection
127005648 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127006336 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E | 2024-11-24 | 2026-09-08 | Level 2 | GO 165 Inspection
127006874 | other | Non-HFTD | Transmission | 2023-08-28 | 2028-08-28 | Level 3 | F |  | 2028-08-28 | Level 3
127006973 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127007221 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127007385 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127007566 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127007978 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E | 2024-09-30 | 2026-09-06 | Level 2 | GO 165 Inspection
127008168 | other | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127008243 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127008244 | anchor/guy | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127009207 | pole | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127009495 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127009504 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127009505 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127009507 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127009524 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127009542 | other | HFTD Tier 2 | Transmission | 2023-09-08 | 2024-09-08 | Level 3 | F | 2024-05-07 | 2028-09-08 | Level 3 | GO 165 Inspection
127009557 | other | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E | 2024-05-10 | 2026-09-08 | Level 2 | GO 165 Inspection
127010158 | pole | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F | 2024-11-16 | 2028-09-06 | Level 3 | GO 165 Inspection
127010655 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F | 2024-08-28 | 2028-09-05 | Level 3 | GO 165 Inspection
127010669 | other | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127010735 | other | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
127010780 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F | 2024-08-23 | 2028-09-06 | Level 3 | GO 165 Inspection
127011926 | pole | Non-HFTD | Transmission | 2023-09-09 | 2026-09-09 | Level 2 | E |  | 2026-09-09 | Level 2
127012066 | pole | Non-HFTD | Transmission | 2023-09-09 | 2026-09-09 | Level 2 | E |  | 2026-09-09 | Level 2
127012229 | other | Non-HFTD | Transmission | 2023-09-09 | 2028-09-09 | Level 3 | F |  | 2028-09-09 | Level 3
127013028 | crossarm | Non-HFTD | Transmission | 2023-09-09 | 2026-09-09 | Level 2 | E |  | 2026-09-09 | Level 2
127013238 | insulator and brushing | Non-HFTD | Transmission | 2023-09-09 | 2024-09-09 | Level 2 | E | 2024-10-25 | 2024-09-09 | Level 2 | Field Safety Reassessment
127013366 | pole | Non-HFTD | Transmission | 2023-09-09 | 2026-09-09 | Level 2 | E |  | 2026-09-09 | Level 2
127013627 | other | Non-HFTD | Transmission | 2023-09-09 | 2026-09-09 | Level 2 | E | 2024-11-19 | 2026-09-09 | Level 2 | GO 165 Inspection
127014208 | other | Non-HFTD | Transmission | 2023-09-09 | 2028-09-09 | Level 3 | F |  | 2028-09-09 | Level 3
127014335 | other | Non-HFTD | Transmission | 2023-09-09 | 2028-09-09 | Level 3 | F |  | 2028-09-09 | Level 3
127014424 | pole | Non-HFTD | Transmission | 2023-09-09 | 2026-09-09 | Level 2 | E |  | 2026-09-09 | Level 2
127026613 | splice | Non-HFTD | Transmission | 2023-09-10 | 2026-09-10 | Level 2 | E |  | 2026-09-10 | Level 2
127027489 | pole | Non-HFTD | Transmission | 2023-09-10 | 2024-09-10 | Level 2 | E | 2024-11-15 | 2024-09-10 | Level 2 | Field Safety Reassessment
127028929 | other | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
127028972 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127029024 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127029029 | pole | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127029265 | anchor/guy | Non-HFTD | Transmission | 2023-09-01 | 2028-09-01 | Level 3 | F |  | 2028-09-01 | Level 3
127029266 | splice | Non-HFTD | Transmission | 2023-09-01 | 2026-09-01 | Level 2 | E |  | 2026-09-01 | Level 2
127029502 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-07-24 | 2026-09-05 | Level 2 | GO 165 Inspection
127029825 | pole | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127030039 | pole | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
127030236 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127030545 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127031183 | other | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E |  | 2026-09-05 | Level 2
127031221 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127031302 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127031527 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127031608 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127031994 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127032237 | pole | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127032254 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127032342 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127032911 | other | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127032997 | splice | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-08-30 | 2026-09-05 | Level 2 | GO 165 Inspection
127033087 | pole | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2024-11-13 | 2026-09-11 | Level 2 | GO 165 Inspection
127033212 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F |  | 2028-09-05 | Level 3
127033371 | pole | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127033400 | pole | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127033480 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127033655 | conductor | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127033749 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127034033 | pole | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127034039 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127034274 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F | 2024-08-16 | 2028-09-05 | Level 3 | GO 165 Inspection
127034295 | anchor/guy | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127034377 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127034458 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127034502 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127034706 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127034759 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127034784 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127035063 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127035557 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127036636 | insulator and brushing | Non-HFTD | Transmission | 2023-09-08 | 2024-09-08 | Level 2 | E | 2024-08-12 | 2024-09-08 | Level 2 | GO 165 Inspection
127036844 | insulator and brushing | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127036941 | insulator and brushing | Non-HFTD | Transmission | 2023-09-12 | 2024-09-12 | Level 2 | E |  | 2024-09-12 | Level 2
127037082 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127037251 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127037504 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127038489 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127038582 | insulator and brushing | Non-HFTD | Transmission | 2023-09-05 | 2026-09-05 | Level 2 | E | 2024-07-25 | 2026-09-05 | Level 2 | GO 165 Inspection
127038796 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-08-12 | 2026-09-07 | Level 2 | GO 165 Inspection
127038798 | anchor/guy | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F | 2024-08-12 | 2028-09-07 | Level 3 | GO 165 Inspection
127038876 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127038891 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127039139 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127039277 | insulator and brushing | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127039424 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127039991 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F | 2024-10-22 | 2028-09-12 | Level 3 | GO 165 Inspection
127040298 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127040324 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127040468 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127040539 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127040959 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127041110 | pole | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127041161 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127041767 | other | HFTD Tier 2 | Transmission | 2023-09-12 | 2024-09-12 | Level 3 | F | 2024-05-02 | 2028-09-12 | Level 3 | GO 165 Inspection
127041822 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127042023 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-11-18 | 2026-09-07 | Level 2 | GO 165 Inspection
127042027 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127042032 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127042546 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127042754 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127042785 | other | HFTD Tier 2 | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F | 2024-05-30 | 2028-09-12 | Level 3 | GO 165 Inspection
127042786 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127042807 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127042815 | insulator and brushing | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127042996 | insulator and brushing | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127043084 | switch | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127044136 | insulator and brushing | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-11-24 | 2026-09-13 | Level 2 | GO 165 Inspection
127044183 | other | Non-HFTD | Transmission | 2023-09-05 | 2028-09-05 | Level 3 | F | 2024-08-09 | 2028-09-05 | Level 3 | GO 165 Inspection
127044396 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127044439 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127044478 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127044581 | pole | HFTD Tier 2 | Transmission | 2023-08-22 | 2024-08-22 | Level 2 | E | 2024-11-10 | 2024-08-22 | Level 2 | Field Safety Reassessment
127044727 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127044994 | other | Non-HFTD | Transmission | 2023-09-06 | 2026-09-06 | Level 2 | E |  | 2026-09-06 | Level 2
127045454 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127045640 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127045938 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127047355 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127047521 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127047686 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-10-31 | 2026-09-13 | Level 2 | GO 165 Inspection
127048045 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127048562 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127049020 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127049189 | insulator and brushing | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127050107 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127050201 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F | 2024-09-18 | 2028-09-13 | Level 3 | GO 165 Inspection
127050474 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-10-30 | 2026-09-13 | Level 2 | GO 165 Inspection
127051060 | other | HFTD Tier 2 | Transmission | 2023-09-13 | 2024-09-13 | Level 3 | F | 2024-05-20 | 2028-09-13 | Level 3 | GO 165 Inspection
127051149 | other | HFTD Tier 2 | Transmission | 2023-09-13 | 2024-09-13 | Level 3 | F | 2024-03-12 | 2028-09-13 | Level 3 | GO 165 Inspection
127052250 | conductor | Non-HFTD | Transmission | 2023-09-14 | 2024-09-14 | Level 2 | E | 2024-12-23 | 2024-09-14 | Level 2 | Field Safety Reassessment
127052336 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127052724 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F | 2024-11-19 | 2028-09-14 | Level 3 | GO 165 Inspection
127053437 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127054175 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F | 2024-10-30 | 2028-09-14 | Level 3 | GO 165 Inspection
127054195 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F | 2024-11-19 | 2028-09-14 | Level 3 | GO 165 Inspection
127054486 | splice | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E | 2024-09-18 | 2026-09-14 | Level 2 | GO 165 Inspection
127054576 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E | 2024-10-30 | 2026-09-14 | Level 2 | GO 165 Inspection
127055330 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127055457 | other | HFTD Tier 2 | Transmission | 2023-09-14 | 2024-09-14 | Level 2 | E |  | 2024-09-14 | Level 2
127055930 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E | 2024-10-30 | 2026-09-14 | Level 2 | GO 165 Inspection
127056383 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E | 2024-10-30 | 2026-09-14 | Level 2 | GO 165 Inspection
127056653 | anchor/guy | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F | 2024-11-15 | 2028-09-14 | Level 3 | GO 165 Inspection
127056797 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127057043 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F | 2024-09-18 | 2028-09-14 | Level 3 | GO 165 Inspection
127057407 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127057410 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127057420 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127057585 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127057637 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127058178 | pole | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127058268 | pole | Non-HFTD | Transmission | 2023-09-12 | 2024-09-12 | Level 2 | E | 2024-08-30 | 2024-09-12 | Level 2 | Field Safety Reassessment
127059069 | conductor | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E | 2024-09-18 | 2026-09-14 | Level 2 | GO 165 Inspection
127059167 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127059186 | anchor/guy | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127059210 | pole | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127059307 | other | HFTD Tier 2 | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F | 2024-05-03 | 2028-09-14 | Level 3 | GO 165 Inspection
127059473 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127060778 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127060824 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127060862 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127060941 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127060947 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127060975 | switch | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127061017 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127061022 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127061222 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127061255 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127061258 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127061259 | anchor/guy | Non-HFTD | Transmission | 2023-09-08 | 2024-09-08 | Level 2 | E | 2024-12-20 | 2024-09-08 | Level 2 | Field Safety Reassessment
127061558 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127061766 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E | 2024-11-19 | 2026-09-15 | Level 2 | GO 165 Inspection
127061988 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127062237 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127062291 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127062298 | pole | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127062333 | insulator and brushing | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E |  | 2026-09-15 | Level 2
127062372 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127062416 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127062616 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127062682 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127062738 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127063179 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F | 2024-11-18 | 2028-09-15 | Level 3 | GO 165 Inspection
127063216 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127063287 | other | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E | 2024-06-25 | 2026-09-08 | Level 2 | GO 165 Inspection
127063381 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127063808 | pole | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E |  | 2026-09-15 | Level 2
127063871 | splice | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E |  | 2026-09-15 | Level 2
127063935 | insulator and brushing | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127064339 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F | 2024-08-13 | 2028-09-08 | Level 3 | GO 165 Inspection
127064648 | insulator and brushing | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E | 2024-07-22 | 2026-09-08 | Level 2 | GO 165 Inspection
127064682 | other | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127064739 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127064954 | pole | Non-HFTD | Transmission | 2023-09-15 | 2024-09-15 | Level 2 | E | 2024-01-12 | 2024-09-15 | Level 2 | Field Safety Reassessment
127065056 | anchor/guy | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127065092 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127065404 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127065518 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127065861 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127066133 | insulator and brushing | Non-HFTD | Transmission | 2023-09-15 | 2024-09-15 | Level 2 | E | 2024-07-22 | 2024-09-15 | Level 2 | GO 165 Inspection
127066493 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2024-09-05 | 2026-09-11 | Level 2 | GO 165 Inspection
127066503 | pole | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127066578 | other | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2024-09-05 | 2026-09-11 | Level 2 | GO 165 Inspection
127066732 | insulator and brushing | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F | 2024-11-18 | 2028-09-15 | Level 3 | GO 165 Inspection
127066848 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127066921 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127067063 | other | Non-HFTD | Transmission | 2023-09-07 | 2024-09-07 | Level 2 | E | 2024-11-12 | 2023-12-07 | Level 2 | GO 165 Inspection
127067066 | insulator and brushing | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-11-12 | 2026-09-07 | Level 2 | GO 165 Inspection
127067069 | other | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127067110 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2024-06-14 | 2028-09-11 | Level 3 | GO 165 Inspection
127067212 | other | HFTD Tier 2 | Transmission | 2023-09-15 | 2024-09-15 | Level 3 | F | 2024-05-25 | 2028-09-15 | Level 3 | GO 165 Inspection
127067237 | other | HFTD Tier 2 | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F | 2024-03-15 | 2028-09-15 | Level 3 | GO 165 Inspection
127067392 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127067655 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127067658 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2024-08-16 | 2026-09-11 | Level 2 | GO 165 Inspection
127067697 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F | 2024-09-18 | 2028-09-08 | Level 3 | GO 165 Inspection
127067733 | conductor | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127067736 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127069030 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F | 2024-07-31 | 2028-09-16 | Level 3 | Field Safety Reassessment
127069197 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069385 | anchor/guy | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069545 | other | HFTD Tier 2 | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069634 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069639 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069662 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069743 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127069986 | anchor/guy | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127070089 | anchor/guy | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127070150 | other | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 2 | E | 2024-11-16 | 2026-09-16 | Level 2 | GO 165 Inspection
127070375 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127070519 | pole | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 2 | E |  | 2026-09-16 | Level 2
127070548 | anchor/guy | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 2 | E | 2024-10-17 | 2026-09-16 | Level 2 | GO 165 Inspection
127070553 | anchor/guy | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127070579 | pole | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 2 | E |  | 2026-09-16 | Level 2
127070932 | other | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127071054 | other | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127071070 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127071081 | other | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127071118 | insulator and brushing | Non-HFTD | Transmission | 2023-09-16 | 2026-09-16 | Level 2 | E |  | 2026-09-16 | Level 2
127071157 | other | HFTD Tier 2 | Transmission | 2023-09-16 | 2024-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127071174 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127071916 | other | Non-HFTD | Transmission | 2023-09-16 | 2028-09-16 | Level 3 | F |  | 2028-09-16 | Level 3
127073678 | other | Non-HFTD | Transmission | 2023-09-17 | 2028-09-17 | Level 3 | F | 2024-04-06 | 2028-09-17 | Level 3 | GO 165 Inspection
127073685 | other | HFTD Tier 2 | Transmission | 2023-09-17 | 2024-09-17 | Level 2 | E |  | 2024-09-17 | Level 2
127073787 | other | Non-HFTD | Transmission | 2023-09-17 | 2028-09-17 | Level 3 | F |  | 2028-09-17 | Level 3
127075945 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E |  | 2026-09-11 | Level 2
127075952 | pole | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F | 2024-08-19 | 2028-09-13 | Level 3 | GO 165 Inspection
127075991 | pole | Non-HFTD | Transmission | 2023-09-13 | 2024-09-13 | Level 2 | E | 2024-08-08 | 2024-09-13 | Level 2 | Field Safety Reassessment
127076130 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127076178 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E |  | 2026-09-15 | Level 2
127076893 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-09-27 | 2026-09-13 | Level 2 | GO 165 Inspection
127077143 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127077679 | anchor/guy | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127077826 | insulator and brushing | Non-HFTD | Transmission | 2023-08-18 | 2028-08-18 | Level 3 | F | 2024-11-18 | 2028-08-18 | Level 3 | GO 165 Inspection
127078211 | other | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127078243 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127079996 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127080547 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E | 2024-11-19 | 2026-09-18 | Level 2 | GO 165 Inspection
127080576 | anchor/guy | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127081005 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127081006 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127081397 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127081570 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127081644 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-01-29 | 2028-09-18 | Level 3 | GO 165 Inspection
127081661 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F | 2024-07-22 | 2028-09-15 | Level 3 | GO 165 Inspection
127084161 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127084230 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127084257 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F | 2024-10-29 | 2028-09-15 | Level 3 | GO 165 Inspection
127084479 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127084549 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127084606 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127085994 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-11-19 | 2026-09-19 | Level 2 | GO 165 Inspection
127086214 | other | Non-HFTD | Transmission | 2023-09-15 | 2024-09-15 | Level 2 | E | 2024-10-11 | 2024-09-15 | Level 2 | GO 165 Inspection
127086293 | insulator and brushing | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E | 2024-10-11 | 2026-09-15 | Level 2 | GO 165 Inspection
127086357 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127086379 | other | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E | 2024-10-11 | 2026-09-15 | Level 2 | GO 165 Inspection
127086787 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127086978 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127087294 | anchor/guy | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127087645 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127088433 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127088876 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F | 2023-10-11 | 2028-09-08 | Level 3 | Field Safety Reassessment
127088988 | pole | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E | 2024-10-21 | 2026-09-15 | Level 2 | GO 165 Inspection
127089072 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127089192 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-10-29 | 2026-09-13 | Level 2 | GO 165 Inspection
127089245 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127089425 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127089600 | other | HFTD Tier 2 | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F | 2024-04-29 | 2028-09-19 | Level 3 | GO 165 Inspection
127089662 | conductor | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127089683 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127089951 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127090641 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127090662 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127090780 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2023-11-22 | 2028-09-11 | Level 3 | GO 165 Inspection
127090795 | other | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E | 2024-12-10 | 2026-09-07 | Level 2 | GO 165 Inspection
127090827 | pole | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127090844 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127090872 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127090904 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127090933 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F | 2024-10-10 | 2028-09-12 | Level 3 | GO 165 Inspection
127090935 | insulator and brushing | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E | 2024-10-10 | 2026-09-12 | Level 2 | GO 165 Inspection
127090944 | splice | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E | 2024-08-19 | 2026-09-12 | Level 2 | GO 165 Inspection
127090949 | insulator and brushing | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F | 2024-06-27 | 2028-09-08 | Level 3 | GO 165 Inspection
127090970 | anchor/guy | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127091034 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127091038 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127091056 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127091057 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127091087 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127091094 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127091115 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127091133 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127091135 | anchor/guy | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 2 | E | 2024-06-12 | 2024-09-11 | Level 2 | GO 165 Inspection
127091151 | other | Non-HFTD | Transmission | 2023-09-06 | 2028-09-06 | Level 3 | F |  | 2028-09-06 | Level 3
127091159 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127091182 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2023-10-02 | 2028-09-11 | Level 3 | GO 165 Inspection
127091202 | pole | Non-HFTD | Transmission | 2023-09-07 | 2026-09-07 | Level 2 | E |  | 2026-09-07 | Level 2
127091217 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F |  | 2028-09-07 | Level 3
127091242 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2023-10-17 | 2028-09-11 | Level 3 | GO 165 Inspection
127091250 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E | 2024-09-07 | 2026-09-18 | Level 2 | GO 165 Inspection
127091252 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127091267 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127091325 | other | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2024-10-23 | 2026-09-11 | Level 2 | GO 165 Inspection
127091328 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2024-10-23 | 2026-09-11 | Level 2 | GO 165 Inspection
127091342 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127091381 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2024-09-12 | Level 2 | E | 2024-01-18 | 2024-09-12 | Level 2 | Field Safety Reassessment
127091419 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127091443 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127091445 | other | HFTD Tier 2 | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127092087 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-10-29 | 2026-09-20 | Level 2 | GO 165 Inspection
127092370 | insulator and brushing | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 3 | F |  | 2026-09-20 | Level 3
127092600 | splice | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127092882 | other | HFTD Tier 3 | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127093105 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-10-31 | 2026-09-19 | Level 2 | GO 165 Inspection
127093342 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127093377 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127093557 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127093558 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127093861 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-10-22 | 2026-09-19 | Level 2 | GO 165 Inspection
127094026 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127094148 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127094187 | other | HFTD Tier 2 | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127094256 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127094650 | splice | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127095357 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127095827 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127096081 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127096313 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127096874 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127097072 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127097155 | pole | Non-HFTD | Transmission | 2023-09-02 | 2026-09-02 | Level 2 | E |  | 2026-09-02 | Level 2
127098028 | other | HFTD Tier 2 | Transmission | 2023-09-20 | 2024-09-20 | Level 2 | E | 2024-03-14 | 2024-09-20 | Level 2 | GO 165 Inspection
127098297 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-10-31 | 2026-09-19 | Level 2 | GO 165 Inspection
127098311 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-10-31 | 2026-09-19 | Level 2 | GO 165 Inspection
127098315 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F | 2024-10-31 | 2028-09-19 | Level 3 | GO 165 Inspection
127098779 | other | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127098791 | other | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-05-03 | 2028-09-21 | Level 3 | GO 165 Inspection
127098921 | other | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 3 | F | 2024-09-28 | 2028-09-21 | Level 3 | GO 165 Inspection
127099011 | insulator and brushing | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127099257 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127099263 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127099379 | pole | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-11-19 | 2028-09-21 | Level 3 | GO 165 Inspection
127099746 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127099882 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127100101 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-11-19 | 2028-09-21 | Level 3 | GO 165 Inspection
127100625 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127101332 | splice | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127101704 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127101716 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127101717 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127102006 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127102590 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127103087 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-09-25 | 2026-09-19 | Level 2 | GO 165 Inspection
127103258 | anchor/guy | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-09-25 | 2026-09-19 | Level 2 | GO 165 Inspection
127104277 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127104568 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127104781 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127106084 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127106289 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127106296 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-10-11 | 2026-09-20 | Level 2 | GO 165 Inspection
127106926 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127107532 | conductor | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127107978 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127108053 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127108547 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127108769 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E | 2024-07-24 | 2026-09-08 | Level 2 | GO 165 Inspection
127108828 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2024-07-25 | 2028-09-11 | Level 3 | GO 165 Inspection
127108854 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127108930 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127109050 | other | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-09-25 | 2026-09-13 | Level 2 | GO 165 Inspection
127109069 | insulator and brushing | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127109241 | other | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E | 2024-10-07 | 2026-09-14 | Level 2 | GO 165 Inspection
127109271 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2024-07-24 | 2028-09-11 | Level 3 | GO 165 Inspection
127109315 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127109342 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127109350 | anchor/guy | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127109411 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127109414 | other | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127109417 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127109443 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127109541 | anchor/guy | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127109596 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127111115 | pole | Non-HFTD | Transmission | 2023-09-14 | 2026-09-14 | Level 2 | E |  | 2026-09-14 | Level 2
127111132 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2024-07-25 | 2028-09-11 | Level 3 | GO 165 Inspection
127111136 | anchor/guy | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127111138 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127111161 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127111173 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127111176 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127111221 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127111224 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127111242 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127111246 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2023-11-20 | 2026-09-11 | Level 2 | GO 165 Inspection
127111328 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127111350 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F |  | 2028-09-11 | Level 3
127111403 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F | 2024-08-14 | 2028-09-12 | Level 3 | Field Safety Reassessment
127111409 | other | Non-HFTD | Transmission | 2023-09-11 | 2028-09-11 | Level 3 | F | 2024-07-23 | 2028-09-11 | Level 3 | GO 165 Inspection
127111460 | anchor/guy | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127111468 | insulator and brushing | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127111485 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127111486 | other | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E |  | 2026-09-13 | Level 2
127111499 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127111583 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-11-06 | 2023-12-22 | Level 2 | Field Safety Reassessment
127111620 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127111625 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127111635 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127111804 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127111814 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127111824 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127112100 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127112115 | insulator and brushing | Non-HFTD | Transmission | 2023-09-11 | 2026-09-11 | Level 2 | E | 2023-10-18 | 2026-09-11 | Level 2 | GO 165 Inspection
127112192 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F | 2024-11-18 | 2028-09-07 | Level 3 | GO 165 Inspection
127112220 | other | Non-HFTD | Transmission | 2023-09-08 | 2028-09-08 | Level 3 | F |  | 2028-09-08 | Level 3
127112255 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127112320 | pole | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E |  | 2026-09-15 | Level 2
127112327 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127112358 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127112398 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-06-07 | 2028-09-20 | Level 3 | GO 165 Inspection
127112532 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127112592 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127112891 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127113114 | other | Non-HFTD | Transmission | 2023-09-07 | 2028-09-07 | Level 3 | F | 2024-07-25 | 2028-09-07 | Level 3 | GO 165 Inspection
127113127 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127113203 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127113260 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127113285 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-07-24 | 2028-09-20 | Level 3 | GO 165 Inspection
127113292 | anchor/guy | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-08-02 | 2028-09-18 | Level 3 | GO 165 Inspection
127113437 | insulator and brushing | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-10-02 | 2026-09-20 | Level 2 | GO 165 Inspection
127113540 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F | 2024-07-25 | 2028-09-12 | Level 3 | GO 165 Inspection
127113546 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E | 2024-09-25 | 2026-09-18 | Level 2 | GO 165 Inspection
127113604 | other | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127113607 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127113849 | pole | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F | 2024-03-14 | 2028-09-22 | Level 3 | GO 165 Inspection
127113887 | other | Non-HFTD | Transmission | 2023-09-22 | 2024-09-22 | Level 2 | E | 2024-10-05 | 2024-09-22 | Level 2 | GO 165 Inspection
127113912 | insulator and brushing | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127114044 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127114128 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-10-05 | 2026-09-22 | Level 2 | GO 165 Inspection
127114173 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127114258 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E | 2024-08-16 | 2026-09-21 | Level 2 | GO 165 Inspection
127114437 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127114542 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127114868 | pole | Non-HFTD | Transmission | 2023-09-22 | 2024-09-22 | Level 2 | E | 2024-08-19 | 2024-09-22 | Level 2 | Field Safety Reassessment
127114973 | other | Non-HFTD | Transmission | 2023-09-12 | 2028-09-12 | Level 3 | F |  | 2028-09-12 | Level 3
127115027 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127115198 | insulator and brushing | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127115452 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127115479 | other | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-10-05 | 2026-09-22 | Level 2 | GO 165 Inspection
127115966 | other | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-11-19 | 2026-09-22 | Level 2 | GO 165 Inspection
127116065 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-07-19 | 2028-09-18 | Level 3 | GO 165 Inspection
127116139 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127116573 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-11-29 | 2026-09-20 | Level 2 | GO 165 Inspection
127116747 | other | HFTD Tier 2 | Transmission | 2023-09-22 | 2024-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127116788 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127117077 | other | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127118378 | pole | Non-HFTD | Transmission | 2023-09-23 | 2024-09-23 | Level 2 | E | 2024-04-19 | 2024-09-23 | Level 2 | Field Safety Reassessment
127118629 | other | Non-HFTD | Transmission | 2023-09-23 | 2028-09-23 | Level 3 | F |  | 2028-09-23 | Level 3
127119376 | pole | Non-HFTD | Transmission | 2023-09-23 | 2026-09-23 | Level 2 | E |  | 2026-09-23 | Level 2
127119766 | pole | Non-HFTD | Transmission | 2023-09-23 | 2026-09-23 | Level 2 | E | 2024-07-21 | 2026-09-23 | Level 2 | GO 165 Inspection
127119850 | pole | Non-HFTD | Transmission | 2023-09-23 | 2024-09-23 | Level 2 | E | 2024-04-19 | 2024-09-23 | Level 2 | Field Safety Reassessment
127120433 | other | Non-HFTD | Transmission | 2023-09-23 | 2028-09-23 | Level 3 | F |  | 2028-09-23 | Level 3
127120444 | other | Non-HFTD | Transmission | 2023-09-23 | 2028-09-23 | Level 3 | F |  | 2028-09-23 | Level 3
127120729 | pole | Non-HFTD | Transmission | 2023-09-23 | 2026-09-23 | Level 2 | E |  | 2026-09-23 | Level 2
127120731 | splice | Non-HFTD | Transmission | 2023-09-23 | 2026-09-23 | Level 2 | E |  | 2026-09-23 | Level 2
127120962 | other | Non-HFTD | Transmission | 2023-09-23 | 2028-09-23 | Level 3 | F |  | 2028-09-23 | Level 3
127124487 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127125045 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127125289 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-10 | 2026-09-25 | Level 2 | GO 165 Inspection
127125394 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127125780 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127125963 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-10 | 2026-09-25 | Level 2 | GO 165 Inspection
127126172 | pole | Non-HFTD | Transmission | 2023-09-25 | 2024-09-25 | Level 2 | E | 2024-07-02 | 2024-09-25 | Level 2 | Field Safety Reassessment
127126261 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127126282 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127126295 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-09 | 2026-09-25 | Level 2 | GO 165 Inspection
127126745 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127126748 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127126871 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127126940 | crossarm | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E | 2024-10-22 | 2026-09-12 | Level 2 | GO 165 Inspection
127127065 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-09 | 2026-09-25 | Level 2 | GO 165 Inspection
127127469 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127127519 | pole | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127127523 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127127552 | pole | Non-HFTD | Transmission | 2023-09-12 | 2026-09-12 | Level 2 | E |  | 2026-09-12 | Level 2
127127573 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127127726 | pole | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-11-19 | 2028-09-25 | Level 3 | GO 165 Inspection
127128055 | pole | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-10-28 | 2028-09-25 | Level 3 | GO 165 Inspection
127128517 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127128575 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127128854 | crossarm | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127129195 | splice | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127129784 | crossarm | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-09-27 | 2026-09-25 | Level 2 | GO 165 Inspection
127130015 | other | HFTD Tier 2 | Transmission | 2023-09-20 | 2024-09-20 | Level 2 | E |  | 2024-09-20 | Level 2
127130126 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127130380 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127130827 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127130844 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127130916 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127131063 | pole | Non-HFTD | Transmission | 2023-09-25 | 2024-09-25 | Level 2 | E | 2024-01-29 | 2024-09-25 | Level 2 | Field Safety Reassessment
127131161 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127131699 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-10-25 | 2028-09-25 | Level 3 | GO 165 Inspection
127131730 | crossarm | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-25 | 2026-09-25 | Level 2 | GO 165 Inspection
127132806 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127132964 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127133048 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127133086 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127133148 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127133222 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127133232 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127133773 | pole | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127133851 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2028-09-26 | Level 3 | F | 2023-10-11 | 2028-09-26 | Level 3 | GO 165 Inspection
127134217 | other | Non-HFTD | Transmission | 2023-09-18 | 2024-09-18 | Level 2 | E | 2024-10-22 | 2024-09-18 | Level 2 | GO 165 Inspection
127134285 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127134310 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127134459 | other | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E | 2024-04-08 | 2026-09-26 | Level 2 | GO 165 Inspection
127134642 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-10-18 | 2028-09-26 | Level 3 | GO 165 Inspection
127134758 | conductor | HFTD Tier 2 | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127134805 | pole | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127134843 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127134955 | pole | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127136465 | pole | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127136519 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-09-27 | 2028-09-26 | Level 3 | GO 165 Inspection
127136710 | conductor | HFTD Tier 2 | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127136903 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127137063 | other | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127137166 | conductor | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127137283 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127137351 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127137621 | conductor | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127137700 | other | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-09-30 | 2026-09-25 | Level 2 | GO 165 Inspection
127138426 | pole | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127138735 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-11-19 | 2026-09-19 | Level 2 | GO 165 Inspection
127138737 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-11-19 | 2026-09-19 | Level 2 | GO 165 Inspection
127139017 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 2 | E | 2024-09-05 | 2026-09-26 | Level 2 | GO 165 Inspection
127139023 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127139272 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127139306 | pole | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127139732 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127139737 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127139944 | other | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127140083 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127140106 | pole | Non-HFTD | Transmission | 2023-09-08 | 2026-09-08 | Level 2 | E |  | 2026-09-08 | Level 2
127141307 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127141365 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127141799 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127142014 | conductor | HFTD Tier 2 | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127142289 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127142321 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127142504 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F | 2024-08-06 | 2028-09-27 | Level 3 | GO 165 Inspection
127142684 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2024-09-27 | Level 2 | E | 2024-12-23 | 2024-09-27 | Level 2 | Field Safety Reassessment
127142695 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127142846 | conductor | HFTD Tier 2 | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-05-28 | 2028-09-25 | Level 3 | GO 165 Inspection
127142885 | conductor | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127143005 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F | 2024-08-06 | 2028-09-27 | Level 3 | GO 165 Inspection
127143009 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F | 2024-10-04 | 2028-09-27 | Level 3 | GO 165 Inspection
127143334 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127143478 | pole | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127143567 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127143697 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127143848 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127143854 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127144392 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127144668 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E | 2024-10-11 | 2026-09-27 | Level 2 | GO 165 Inspection
127145226 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E | 2024-10-09 | 2026-09-27 | Level 2 | GO 165 Inspection
127145804 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127145875 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F | 2024-05-08 | 2028-09-27 | Level 3 | GO 165 Inspection
127145927 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127145966 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127146197 | pole | Non-HFTD | Transmission | 2023-09-20 | 2024-09-20 | Level 2 | E | 2024-10-17 | 2024-09-20 | Level 2 | Field Safety Reassessment
127146207 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127146235 | other | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F | 2024-04-18 | 2028-09-27 | Level 3 | GO 165 Inspection
127146377 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127146886 | anchor/guy | Non-HFTD | Transmission | 2023-09-27 | 2024-09-27 | Level 2 | E | 2024-09-07 | 2024-09-27 | Level 2 | GO 165 Inspection
127146972 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127147304 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E | 2024-10-09 | 2026-09-27 | Level 2 | GO 165 Inspection
127147329 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127147343 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127147345 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127147519 | other | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127147536 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127147697 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127147975 | anchor/guy | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127148070 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127148077 | insulator and brushing | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F | 2024-07-25 | 2028-09-13 | Level 3 | GO 165 Inspection
127148227 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2024-09-27 | Level 2 | E | 2024-11-01 | 2026-09-27 | Level 2 | GO 165 Inspection
127148246 | pole | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-10-31 | 2028-09-21 | Level 3 | GO 165 Inspection
127148392 | pole | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E | 2024-10-09 | 2026-09-27 | Level 2 | GO 165 Inspection
127148454 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-09-18 | 2028-09-21 | Level 3 | GO 165 Inspection
127148469 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127148513 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F | 2024-07-17 | 2028-09-22 | Level 3 | GO 165 Inspection
127148514 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127148539 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127148607 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127148643 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-05-01 | 2026-09-22 | Level 2 | GO 165 Inspection
127148666 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-11-19 | 2028-09-20 | Level 3 | GO 165 Inspection
127148706 | other | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127148719 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-11-19 | 2028-09-20 | Level 3 | GO 165 Inspection
127148727 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127148756 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F | 2024-08-06 | 2028-09-19 | Level 3 | GO 165 Inspection
127148833 | pole | Non-HFTD | Transmission | 2023-09-13 | 2026-09-13 | Level 2 | E | 2024-09-27 | 2026-09-13 | Level 2 | GO 165 Inspection
127148865 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2024-09-21 | Level 2 | E |  | 2024-09-21 | Level 2
127148867 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-11-19 | 2028-09-20 | Level 3 | GO 165 Inspection
127149001 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-11-19 | 2028-09-21 | Level 3 | GO 165 Inspection
127149041 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127149063 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127149084 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127149088 | insulator and brushing | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-10-08 | 2026-09-19 | Level 2 | GO 165 Inspection
127149110 | other | Non-HFTD | Transmission | 2023-09-14 | 2028-09-14 | Level 3 | F |  | 2028-09-14 | Level 3
127149140 | pole | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127149143 | anchor/guy | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127149201 | anchor/guy | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-09-25 | 2028-09-21 | Level 3 | GO 165 Inspection
127149209 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-09-25 | 2028-09-21 | Level 3 | GO 165 Inspection
127149448 | anchor/guy | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127149935 | conductor | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127150576 | other | HFTD Tier 3 | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F | 2024-05-03 | 2028-09-28 | Level 3 | GO 165 Inspection
127150577 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127150834 | insulator and brushing | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F | 2024-08-30 | 2028-09-13 | Level 3 | GO 165 Inspection
127151134 | pole | Non-HFTD | Transmission | 2023-09-28 | 2026-09-28 | Level 2 | E |  | 2026-09-28 | Level 2
127151237 | pole | Non-HFTD | Transmission | 2023-09-28 | 2026-09-28 | Level 2 | E |  | 2026-09-28 | Level 2
127151663 | insulator and brushing | Non-HFTD | Transmission | 2023-09-28 | 2026-09-28 | Level 2 | E |  | 2026-09-28 | Level 2
127151862 | insulator and brushing | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127152232 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127152365 | insulator and brushing | Non-HFTD | Transmission | 2023-09-28 | 2026-09-28 | Level 2 | E |  | 2026-09-28 | Level 2
127152537 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127152723 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-08-31 | 2026-09-25 | Level 2 | GO 165 Inspection
127152760 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2023-11-02 | 2026-09-25 | Level 2 | GO 165 Inspection
127152787 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-08-21 | 2028-09-21 | Level 3 | GO 165 Inspection
127153008 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-09-30 | 2026-09-20 | Level 2 | GO 165 Inspection
127153456 | pole | Non-HFTD | Transmission | 2023-09-28 | 2026-09-28 | Level 2 | E | 2024-11-14 | 2024-09-28 | Level 2 | GO 165 Inspection
127153586 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-11-19 | 2028-09-20 | Level 3 | GO 165 Inspection
127153677 | insulator and brushing | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F | 2024-08-05 | 2028-09-28 | Level 3 | GO 165 Inspection
127154153 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127154684 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2024-03-22 | Level 2 | E | 2024-10-03 | 2024-03-22 | Level 2 | GO 165 Inspection
127154687 | other | Non-HFTD | Transmission | 2023-09-13 | 2028-09-13 | Level 3 | F |  | 2028-09-13 | Level 3
127154711 | anchor/guy | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F | 2024-09-18 | 2028-09-28 | Level 3 | GO 165 Inspection
127154716 | splice | Non-HFTD | Transmission | 2023-09-28 | 2026-09-28 | Level 2 | E | 2024-09-18 | 2026-09-28 | Level 2 | GO 165 Inspection
127155050 | insulator and brushing | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127155132 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127155655 | other | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-11-19 | 2026-09-20 | Level 2 | GO 165 Inspection
127156181 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127156254 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-08-20 | 2028-09-18 | Level 3 | GO 165 Inspection
127156276 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127156402 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127156412 | other | Non-HFTD | Transmission | 2023-09-15 | 2028-09-15 | Level 3 | F |  | 2028-09-15 | Level 3
127156489 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127156527 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127156531 | insulator and brushing | Non-HFTD | Transmission | 2023-09-15 | 2026-09-15 | Level 2 | E | 2024-06-21 | 2026-09-15 | Level 2 | GO 165 Inspection
127156535 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127156604 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F |  | 2028-09-18 | Level 3
127156640 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127156671 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2023-10-11 | 2028-09-25 | Level 3 | GO 165 Inspection
127156799 | anchor/guy | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127156861 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127157305 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-11-18 | 2024-09-25 | Level 2 | GO 165 Inspection
127157306 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2024-09-25 | Level 2 | E | 2024-11-18 | 2024-09-25 | Level 2 | GO 165 Inspection
127158343 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-08-08 | 2028-09-18 | Level 3 | GO 165 Inspection
127158364 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127158370 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2023-11-02 | 2028-09-25 | Level 3 | GO 165 Inspection
127158390 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F | 2024-09-28 | 2028-09-19 | Level 3 | GO 165 Inspection
127158392 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127158408 | splice | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127158412 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127158413 | insulator and brushing | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127158540 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127158564 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127158614 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127158615 | pole | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127158768 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-08-02 | 2028-09-18 | Level 3 | GO 165 Inspection
127158887 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F | 2024-05-02 | 2028-09-22 | Level 3 | GO 165 Inspection
127158950 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-07-16 | 2028-09-26 | Level 3 | GO 165 Inspection
127159188 | other | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127159271 | anchor/guy | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127159392 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127159566 | pole | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127159575 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E | 2024-08-20 | 2026-09-18 | Level 2 | GO 165 Inspection
127159593 | anchor/guy | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127159617 | insulator and brushing | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127159763 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127159882 | insulator and brushing | Non-HFTD | Transmission | 2023-09-28 | 2024-09-28 | Level 2 | E | 2024-10-28 | 2024-09-28 | Level 2 | Field Safety Reassessment
127160002 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-06-27 | 2028-09-26 | Level 3 | GO 165 Inspection
127160007 | splice | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E | 2024-09-17 | 2026-09-19 | Level 2 | GO 165 Inspection
127160081 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127160159 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127160440 | conductor | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127160465 | anchor/guy | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F | 2024-11-19 | 2028-09-29 | Level 3 | GO 165 Inspection
127160537 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127160550 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-08-13 | 2026-09-25 | Level 2 | GO 165 Inspection
127160552 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-08-13 | 2028-09-25 | Level 3 | GO 165 Inspection
127160555 | other | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127160673 | pole | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127160726 | other | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-10-16 | 2026-09-29 | Level 2 | GO 165 Inspection
127160787 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127160853 | other | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127161104 | anchor/guy | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127161342 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127161499 | other | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127161544 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127161596 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-07-23 | 2028-09-26 | Level 3 | GO 165 Inspection
127161601 | splice | Non-HFTD | Transmission | 2023-09-19 | 2026-09-19 | Level 2 | E |  | 2026-09-19 | Level 2
127161954 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127162068 | other | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127162092 | pole | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E |  | 2026-09-29 | Level 2
127162133 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127162138 | other | Non-HFTD | Transmission | 2023-09-18 | 2028-09-18 | Level 3 | F | 2024-08-16 | 2028-09-18 | Level 3 | GO 165 Inspection
127162183 | other | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-10-28 | 2026-09-29 | Level 2 | GO 165 Inspection
127162373 | other | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-10-28 | 2026-09-29 | Level 2 | GO 165 Inspection
127162449 | insulator and brushing | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F |  | 2028-09-20 | Level 3
127162562 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-08-28 | 2026-09-20 | Level 2 | GO 165 Inspection
127162644 | insulator and brushing | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127162701 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127163025 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127163396 | pole | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-10-16 | 2023-12-29 | Level 2 | GO 165 Inspection
127165372 | pole | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E |  | 2026-09-29 | Level 2
127166108 | pole | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127169263 | insulator and brushing | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-08-19 | 2023-12-29 | Level 2 | GO 165 Inspection
127169301 | pole | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-07-16 | 2026-09-29 | Level 2 | GO 165 Inspection
127169308 | anchor/guy | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127169368 | splice | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-10-16 | 2026-09-29 | Level 2 | GO 165 Inspection
127169406 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127169425 | anchor/guy | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F | 2024-09-13 | 2028-09-22 | Level 3 | GO 165 Inspection
127169427 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127169429 | other | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-08-01 | 2028-09-20 | Level 3 | GO 165 Inspection
127169827 | other | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127169901 | splice | Non-HFTD | Transmission | 2023-09-30 | 2026-09-30 | Level 2 | E |  | 2026-09-30 | Level 2
127169907 | anchor/guy | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127170224 | other | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127170715 | insulator and brushing | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127171090 | other | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127172074 | other | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127172255 | insulator and brushing | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127172460 | pole | Non-HFTD | Transmission | 2023-09-30 | 2026-09-30 | Level 2 | E | 2024-09-17 | 2026-09-30 | Level 2 | GO 165 Inspection
127172501 | pole | Non-HFTD | Transmission | 2023-09-30 | 2026-09-30 | Level 2 | E |  | 2026-09-30 | Level 2
127173076 | other | Non-HFTD | Transmission | 2023-09-30 | 2028-09-30 | Level 3 | F |  | 2028-09-30 | Level 3
127173601 | other | Non-HFTD | Transmission | 2023-09-30 | 2026-09-30 | Level 2 | E | 2024-10-10 | 2026-09-30 | Level 2 | GO 165 Inspection
127175391 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E | 2024-09-19 | 2026-09-21 | Level 2 | GO 165 Inspection
127175714 | pole | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E | 2024-07-25 | 2026-09-18 | Level 2 | GO 165 Inspection
127175743 | anchor/guy | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F |  | 2028-10-02 | Level 3
127175854 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127175910 | insulator and brushing | Non-HFTD | Transmission | 2023-09-18 | 2026-09-18 | Level 2 | E |  | 2026-09-18 | Level 2
127175913 | pole | Non-HFTD | Transmission | 2023-10-02 | 2024-04-02 | Level 2 | E | 2024-10-28 | 2024-04-02 | Level 2 | GO 165 Inspection
127176059 | pole | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F |  | 2028-10-02 | Level 3
127176134 | other | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F |  | 2028-10-02 | Level 3
127176913 | other | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127176915 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127177038 | insulator and brushing | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127177355 | other | Non-HFTD | Transmission | 2023-09-19 | 2028-09-19 | Level 3 | F |  | 2028-09-19 | Level 3
127177582 | other | HFTD Tier 2 | Transmission | 2023-10-02 | 2024-10-02 | Level 2 | E | 2024-05-29 | 2024-10-02 | Level 2 | GO 165 Inspection
127178432 | pole | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127178595 | other | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F |  | 2028-10-02 | Level 3
127179495 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127179583 | other | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F |  | 2028-10-02 | Level 3
127179733 | pole | Non-HFTD | Transmission | 2023-10-02 | 2024-10-02 | Level 2 | E |  | 2024-10-02 | Level 2
127179735 | pole | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127179974 | other | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F |  | 2028-10-02 | Level 3
127180458 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127180720 | pole | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F | 2024-09-06 | 2028-10-02 | Level 3 | GO 165 Inspection
127181502 | pole | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127181655 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-11-19 | 2028-09-21 | Level 3 | GO 165 Inspection
127181731 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127181748 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127181792 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127181854 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127181910 | other | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E | 2024-11-19 | 2026-09-20 | Level 2 | GO 165 Inspection
127181924 | other | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127181939 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127181946 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-05 | 2026-09-25 | Level 2 | GO 165 Inspection
127181949 | splice | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127181957 | other | Non-HFTD | Transmission | 2023-08-21 | 2026-08-21 | Level 2 | E | 2024-11-26 | 2026-08-21 | Level 2 | GO 165 Inspection
127182152 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127182218 | insulator and brushing | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127182220 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2028-09-20 | Level 3 | F | 2024-05-30 | 2028-09-20 | Level 3 | GO 165 Inspection
127182226 | anchor/guy | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-11-19 | 2028-09-21 | Level 3 | GO 165 Inspection
127182240 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127182250 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F | 2024-11-19 | 2028-09-21 | Level 3 | GO 165 Inspection
127182259 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2026-09-20 | Level 2 | E |  | 2026-09-20 | Level 2
127182274 | anchor/guy | Non-HFTD | Transmission | 2023-09-20 | 2024-09-20 | Level 2 | E | 2024-11-19 | 2024-09-20 | Level 2 | GO 165 Inspection
127182300 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127182303 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E |  | 2026-09-21 | Level 2
127182309 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127182382 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127182394 | pole | Non-HFTD | Transmission | 2023-09-21 | 2026-09-21 | Level 2 | E | 2024-09-15 | 2026-09-21 | Level 2 | GO 165 Inspection
127182421 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127182440 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-10-01 | 2028-09-25 | Level 3 | GO 165 Inspection
127182464 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127183017 | insulator and brushing | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127183511 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127184053 | switch | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E |  | 2026-10-03 | Level 2
127184359 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127184404 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127184648 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127185127 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127186043 | anchor/guy | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127186046 | splice | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E |  | 2026-10-03 | Level 2
127186187 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127186740 | insulator and brushing | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E |  | 2026-10-03 | Level 2
127187531 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E | 2024-09-11 | 2026-10-03 | Level 2 | GO 165 Inspection
127187805 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127189170 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127189446 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127189979 | insulator and brushing | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127190171 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F | 2024-07-25 | 2028-09-28 | Level 3 | GO 165 Inspection
127190384 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127190532 | pole | Non-HFTD | Transmission | 2023-09-26 | 2024-09-26 | Level 2 | E | 2024-09-30 | 2026-09-26 | Level 2 | GO 165 Inspection
127190753 | switch | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127190759 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127190877 | pole | Non-HFTD | Transmission | 2023-09-29 | 2026-09-29 | Level 2 | E | 2024-11-08 | 2026-09-29 | Level 2 | GO 165 Inspection
127191011 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127191042 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127191068 | other | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E | 2024-11-18 | 2026-10-03 | Level 2 | GO 165 Inspection
127191765 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127191768 | pole | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127193673 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127194701 | other | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127194757 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127194822 | other | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E | 2024-09-16 | 2026-10-04 | Level 2 | GO 165 Inspection
127194879 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127194883 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E | 2024-09-18 | 2026-10-04 | Level 2 | GO 165 Inspection
127195194 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127195262 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127195429 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127195542 | conductor | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E | 2024-11-01 | 2026-10-04 | Level 2 | GO 165 Inspection
127195764 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-07-08 | 2028-10-04 | Level 3 | GO 165 Inspection
127196174 | other | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127196363 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F | 2024-10-02 | 2028-09-22 | Level 3 | GO 165 Inspection
127196681 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E | 2024-11-01 | 2026-10-04 | Level 2 | GO 165 Inspection
127197510 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2024-10-04 | Level 2 | E | 2024-11-18 | 2024-10-04 | Level 2 | GO 165 Inspection
127197742 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127197916 | insulator and brushing | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E |  | 2026-09-22 | Level 2
127198105 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127198222 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-08-28 | 2028-09-25 | Level 3 | GO 165 Inspection
127198267 | other | Non-HFTD | Transmission | 2023-09-22 | 2028-09-22 | Level 3 | F |  | 2028-09-22 | Level 3
127198329 | other | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127198416 | pole | Non-HFTD | Transmission | 2023-10-02 | 2028-10-02 | Level 3 | F | 2024-09-19 | 2028-10-02 | Level 3 | GO 165 Inspection
127198518 | splice | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127198520 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127198536 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-07-18 | 2026-09-22 | Level 2 | GO 165 Inspection
127198610 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127198677 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127198688 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-09-27 | 2028-09-25 | Level 3 | GO 165 Inspection
127198712 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127198718 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-09-28 | 2026-09-25 | Level 2 | GO 165 Inspection
127198719 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127198890 | switch | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127198913 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127198952 | pole | Non-HFTD | Transmission | 2023-09-22 | 2026-09-22 | Level 2 | E | 2024-10-05 | 2026-09-22 | Level 2 | GO 165 Inspection
127199015 | crossarm | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127199022 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127199065 | splice | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127199096 | other | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127199098 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127199148 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127199163 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-11-18 | 2026-09-25 | Level 2 | GO 165 Inspection
127199173 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127199199 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2024-08-28 | 2028-09-25 | Level 3 | Field Safety Reassessment
127199211 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127199312 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F | 2023-10-19 | 2028-09-25 | Level 3 | GO 165 Inspection
127200763 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127201418 | splice | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127203158 | splice | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127203159 | other | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127203606 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-07 | 2026-09-25 | Level 2 | GO 165 Inspection
127204018 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127204150 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127204327 | other | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127204336 | other | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127205173 | insulator and brushing | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127205225 | other | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E | 2024-09-25 | 2026-10-05 | Level 2 | GO 165 Inspection
127205320 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2023-11-03 | 2026-09-25 | Level 2 | GO 165 Inspection
127205352 | insulator and brushing | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127205592 | anchor/guy | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127205818 | anchor/guy | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127205827 | other | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127205996 | insulator and brushing | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127206036 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127206335 | other | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F | 2024-06-27 | 2028-10-05 | Level 3 | GO 165 Inspection
127206654 | pole | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E | 2024-10-02 | 2026-09-25 | Level 2 | GO 165 Inspection
127206720 | other | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F |  | 2028-10-05 | Level 3
127206751 | insulator and brushing | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127206784 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127207037 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F | 2024-03-04 | 2028-10-03 | Level 3 | GO 165 Inspection
127207914 | insulator and brushing | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E | 2024-10-01 | 2026-10-05 | Level 2 | GO 165 Inspection
127208194 | other | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E | 2024-10-17 | 2026-10-05 | Level 2 | GO 165 Inspection
127210514 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E | 2024-10-08 | 2026-09-26 | Level 2 | GO 165 Inspection
127210524 | other | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127210554 | anchor/guy | Non-HFTD | Transmission | 2023-09-25 | 2026-09-25 | Level 2 | E |  | 2026-09-25 | Level 2
127210567 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127210792 | other | Non-HFTD | Transmission | 2023-09-25 | 2028-09-25 | Level 3 | F |  | 2028-09-25 | Level 3
127210870 | other | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-05-21 | 2028-10-04 | Level 3 | GO 165 Inspection
127211373 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127211506 | pole | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127211716 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127211851 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-03-22 | 2028-10-04 | Level 3 | GO 165 Inspection
127211880 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E | 2024-09-10 | 2026-10-04 | Level 2 | GO 165 Inspection
127211981 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-11-01 | 2028-09-26 | Level 3 | GO 165 Inspection
127212034 | splice | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127212081 | insulator and brushing | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127212087 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2026-09-27 | Level 2 | E |  | 2026-09-27 | Level 2
127212151 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E | 2024-10-22 | 2026-10-06 | Level 2 | GO 165 Inspection
127212163 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E | 2024-08-19 | 2026-10-04 | Level 2 | GO 165 Inspection
127212246 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F |  | 2028-10-03 | Level 3
127212290 | other | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127212306 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F | 2024-05-21 | 2028-10-03 | Level 3 | GO 165 Inspection
127212349 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F | 2024-10-22 | 2028-10-06 | Level 3 | GO 165 Inspection
127212524 | other | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127212529 | conductor | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127212556 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127212789 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127212803 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127212805 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127212819 | other | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127212855 | other | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127212878 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127213070 | insulator and brushing | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127213076 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127213235 | other | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2023-10-16 | 2028-10-04 | Level 3 | GO 165 Inspection
127213254 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127213375 | other | Non-HFTD | Transmission | 2023-10-03 | 2028-10-03 | Level 3 | F | 2024-05-21 | 2028-10-03 | Level 3 | GO 165 Inspection
127213376 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E | 2024-05-21 | 2026-10-03 | Level 2 | GO 165 Inspection
127213567 | splice | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127213597 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127213668 | insulator and brushing | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E |  | 2026-09-26 | Level 2
127213839 | splice | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127213880 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127213974 | other | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F |  | 2028-09-26 | Level 3
127214007 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127214059 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127214088 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127214142 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127214156 | crossarm | Non-HFTD | Transmission | 2023-09-26 | 2026-09-26 | Level 2 | E | 2024-10-02 | 2026-09-26 | Level 2 | GO 165 Inspection
127214167 | anchor/guy | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F | 2024-09-18 | 2028-10-06 | Level 3 | GO 165 Inspection
127214179 | splice | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127214194 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-09-27 | 2028-10-04 | Level 3 | GO 165 Inspection
127214512 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127214785 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127214904 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127215180 | insulator and brushing | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E | 2024-03-22 | 2026-10-03 | Level 2 | GO 165 Inspection
127215209 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127215361 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127215481 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127215674 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127215745 | other | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127215842 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127216018 | splice | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127216084 | conductor | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E | 2024-10-08 | 2026-10-06 | Level 2 | GO 165 Inspection
127216344 | insulator and brushing | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
127216354 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127216551 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127217660 | other | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127217790 | conductor | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127217840 | conductor | HFTD Tier 2 | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127217950 | insulator and brushing | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E |  | 2026-10-07 | Level 2
127218775 | pole | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E | 2024-10-23 | 2026-10-07 | Level 2 | GO 165 Inspection
127219042 | pole | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E | 2024-10-23 | 2026-10-07 | Level 2 | GO 165 Inspection
127219119 | pole | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E | 2024-11-08 | 2026-10-07 | Level 2 | GO 165 Inspection
127219231 | other | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127219637 | other | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E | 2024-10-09 | 2026-10-07 | Level 2 | GO 165 Inspection
127219790 | splice | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E |  | 2026-10-07 | Level 2
127220171 | other | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127220386 | other | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F | 2024-11-27 | 2028-10-07 | Level 3 | GO 165 Inspection
127220393 | anchor/guy | Non-HFTD | Transmission | 2023-10-07 | 2026-10-07 | Level 2 | E |  | 2026-10-07 | Level 2
127220471 | other | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127220622 | other | Non-HFTD | Transmission | 2023-10-07 | 2028-10-07 | Level 3 | F |  | 2028-10-07 | Level 3
127221775 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127221839 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127222324 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127222358 | other | Non-HFTD | Transmission | 2023-10-08 | 2028-10-08 | Level 3 | F |  | 2028-10-08 | Level 3
127222474 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127222748 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127222775 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127222917 | pole | Non-HFTD | Transmission | 2023-10-08 | 2026-10-08 | Level 2 | E |  | 2026-10-08 | Level 2
127224208 | pole | Non-HFTD | Transmission | 2023-10-06 | 2024-10-06 | Level 2 | E | 2024-10-11 | 2024-10-06 | Level 2 | GO 165 Inspection
127224373 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
127224396 | insulator and brushing | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E | 2024-10-18 | 2026-10-06 | Level 2 | GO 165 Inspection
127224485 | pole | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E | 2024-10-23 | 2026-10-09 | Level 2 | GO 165 Inspection
127225174 | other | Non-HFTD | Transmission | 2023-10-09 | 2028-10-09 | Level 3 | F | 2024-09-27 | 2028-10-09 | Level 3 | GO 165 Inspection
127225561 | insulator and brushing | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127225563 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127225568 | other | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F | 2024-11-04 | 2028-09-27 | Level 3 | GO 165 Inspection
127225996 | anchor/guy | Non-HFTD | Transmission | 2023-09-27 | 2028-09-27 | Level 3 | F |  | 2028-09-27 | Level 3
127226077 | pole | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E |  | 2026-10-09 | Level 2
127226485 | insulator and brushing | Non-HFTD | Transmission | 2023-10-08 | 2024-10-08 | Level 2 | E | 2024-12-23 | 2024-10-08 | Level 2 | Field Safety Reassessment
127226568 | pole | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E |  | 2026-10-09 | Level 2
127226758 | pole | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E | 2024-11-08 | 2026-10-09 | Level 2 | GO 165 Inspection
127228086 | anchor/guy | Non-HFTD | Transmission | 2023-09-26 | 2028-09-26 | Level 3 | F | 2024-07-29 | 2028-09-26 | Level 3 | GO 165 Inspection
127228644 | anchor/guy | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127229292 | other | Non-HFTD | Transmission | 2023-10-09 | 2028-10-09 | Level 3 | F |  | 2028-10-09 | Level 3
127229304 | pole | Non-HFTD | Transmission | 2023-10-09 | 2024-10-09 | Level 2 | E | 2024-02-29 | 2024-10-09 | Level 2 | Field Safety Reassessment
127230127 | splice | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E | 2024-09-27 | 2026-10-09 | Level 2 | GO 165 Inspection
127230356 | splice | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E |  | 2026-10-09 | Level 2
127240065 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127240184 | insulator and brushing | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127240361 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E | 2024-11-08 | 2026-10-10 | Level 2 | GO 165 Inspection
127240806 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127241012 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127241016 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127241192 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127242231 | insulator and brushing | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127242399 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127242457 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127242476 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127242584 | other | Non-HFTD | Transmission | 2023-09-28 | 2028-09-28 | Level 3 | F |  | 2028-09-28 | Level 3
127242838 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127243114 | conductor | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127243115 | anchor/guy | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127243130 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127243433 | anchor/guy | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127243442 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2023-10-21 | 2028-10-04 | Level 3 | GO 165 Inspection
127243624 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127243707 | pole | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-03-22 | 2028-10-04 | Level 3 | GO 165 Inspection
127243747 | pole | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127244014 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127244101 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127244372 | insulator and brushing | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E | 2024-09-10 | 2026-10-10 | Level 2 | GO 165 Inspection
127244572 | insulator and brushing | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127244690 | anchor/guy | Non-HFTD | Transmission | 2023-10-10 | 2024-10-10 | Level 2 | E | 2024-12-20 | 2024-10-10 | Level 2 | Field Safety Reassessment
127244904 | other | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127245381 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127245530 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127245639 | anchor/guy | Non-HFTD | Transmission | 2023-09-29 | 2028-09-29 | Level 3 | F |  | 2028-09-29 | Level 3
127245679 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127245762 | conductor | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127245909 | insulator and brushing | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E | 2024-10-10 | 2026-10-06 | Level 2 | GO 165 Inspection
127245967 | pole | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127246003 | pole | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127246177 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127247442 | pole | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E | 2024-10-30 | 2026-10-10 | Level 2 | GO 165 Inspection
127247942 | other | HFTD Tier 2 | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127247989 | anchor/guy | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127248230 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127248239 | splice | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127248377 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127248500 | insulator and brushing | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127248825 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127249966 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127249974 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127249976 | other | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127249995 | insulator and brushing | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127250012 | anchor/guy | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127250248 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127250627 | insulator and brushing | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127250832 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127250926 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127251553 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127251792 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127251898 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127252734 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127252803 | pole | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E | 2024-07-30 | 2026-10-11 | Level 2 | GO 165 Inspection
127253369 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127254505 | splice | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127254628 | conductor | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127254629 | conductor | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F | 2024-02-09 | 2028-10-11 | Level 3 | GO 165 Inspection
127256381 | anchor/guy | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F |  | 2028-10-04 | Level 3
127256385 | insulator and brushing | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127256512 | pole | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F | 2024-10-10 | 2028-10-05 | Level 3 | GO 165 Inspection
127256536 | switch | Non-HFTD | Transmission | 2023-10-12 | 2024-01-12 | Level 2 | E | 2024-10-22 | 2024-01-12 | Level 2 | Field Safety Reassessment
127256726 | splice | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127257265 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2024-10-12 | Level 2
127257340 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127257370 | crossarm | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127257470 | splice | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E | 2024-07-12 | 2026-10-12 | Level 2 | GO 165 Inspection
127257515 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127257573 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127257627 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127257651 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127257761 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127257813 | crossarm | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127258135 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127258668 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127258857 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127259361 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127259589 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127259682 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127259688 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127259843 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127259852 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127261104 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127261204 | splice | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127261409 | pole | Non-HFTD | Transmission | 2023-10-12 | 2024-10-12 | Level 2 | E | 2024-11-17 | 2024-10-12 | Level 2 | Field Safety Reassessment
127261441 | anchor/guy | Non-HFTD | Transmission | 2023-10-12 | 2024-10-12 | Level 2 | E | 2024-11-17 | 2024-01-12 | Level 2 | Field Safety Reassessment
127262379 | conductor | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127262436 | splice | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127262904 | crossarm | HFTD Tier 3 | Transmission | 2023-10-12 | 2024-04-12 | Level 2 | E | 2024-04-04 | 2024-04-12 | Level 2 | Field Safety Reassessment
127264396 | pole | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E | 2024-10-07 | 2026-10-09 | Level 2 | GO 165 Inspection
127264537 | insulator and brushing | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E |  | 2026-10-09 | Level 2
127264681 | other | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127264710 | pole | Non-HFTD | Transmission | 2023-10-05 | 2028-10-05 | Level 3 | F | 2024-11-12 | 2028-10-05 | Level 3 | GO 165 Inspection
127264739 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127264793 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127265167 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F | 2024-09-30 | 2028-10-13 | Level 3 | GO 165 Inspection
127265168 | splice | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E | 2024-09-30 | 2026-10-13 | Level 2 | GO 165 Inspection
127265445 | splice | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127265856 | insulator and brushing | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127265878 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127266219 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127266243 | pole | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127266726 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127266812 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127266844 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127266851 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127266958 | insulator and brushing | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127266981 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127267000 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127267709 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127267751 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F | 2024-06-28 | 2028-10-13 | Level 3 | GO 165 Inspection
127268619 | pole | Non-HFTD | Transmission | 2023-10-13 | 2024-10-13 | Level 2 | E | 2024-09-27 | 2024-10-13 | Level 2 | Field Safety Reassessment
127268889 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127268902 | pole | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127269503 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127269515 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2024-10-13 | Level 2 | E | 2024-07-29 | 2024-10-13 | Level 2 | GO 165 Inspection
127269518 | other | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127269638 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E | 2024-09-06 | 2026-10-13 | Level 2 | GO 165 Inspection
127269816 | pole | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E | 2024-09-18 | 2026-10-13 | Level 2 | GO 165 Inspection
127270199 | pole | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E | 2024-08-15 | 2026-10-13 | Level 2 | GO 165 Inspection
127270220 | conductor | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127270466 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127270565 | conductor | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127270811 | other | HFTD Tier 3 | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127270914 | anchor/guy | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127270919 | conductor | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127270960 | other | HFTD Tier 3 | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127270963 | other | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127271002 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127271082 | splice | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E |  | 2026-10-10 | Level 2
127271160 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127272522 | pole | Non-HFTD | Transmission | 2023-10-14 | 2026-10-14 | Level 2 | E | 2024-08-27 | 2026-10-14 | Level 2 | GO 165 Inspection
127272574 | anchor/guy | Non-HFTD | Transmission | 2023-10-14 | 2028-10-14 | Level 3 | F |  | 2028-10-14 | Level 3
127272721 | other | Non-HFTD | Transmission | 2023-10-14 | 2028-10-14 | Level 3 | F |  | 2028-10-14 | Level 3
127273032 | anchor/guy | Non-HFTD | Transmission | 2023-10-14 | 2028-10-14 | Level 3 | F |  | 2028-10-14 | Level 3
127273038 | conductor | Non-HFTD | Transmission | 2023-10-14 | 2026-10-14 | Level 2 | E |  | 2026-10-14 | Level 2
127273216 | pole | Non-HFTD | Transmission | 2023-10-14 | 2026-10-14 | Level 2 | E |  | 2026-10-14 | Level 2
127273333 | insulator and brushing | Non-HFTD | Transmission | 2023-10-14 | 2026-10-14 | Level 2 | E |  | 2026-10-14 | Level 2
127274137 | pole | Non-HFTD | Transmission | 2023-10-14 | 2026-10-14 | Level 2 | E | 2024-08-30 | 2026-10-14 | Level 2 | GO 165 Inspection
127274522 | insulator and brushing | Non-HFTD | Transmission | 2023-10-14 | 2026-10-14 | Level 2 | E |  | 2026-10-14 | Level 2
127274546 | anchor/guy | Non-HFTD | Transmission | 2023-10-14 | 2028-10-14 | Level 3 | F |  | 2028-10-14 | Level 3
127274872 | anchor/guy | Non-HFTD | Transmission | 2023-10-14 | 2028-10-14 | Level 3 | F | 2024-09-30 | 2028-10-14 | Level 3 | GO 165 Inspection
127279642 | pole | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127279652 | insulator and brushing | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127279749 | anchor/guy | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127280973 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127281370 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F | 2024-07-09 | 2028-10-16 | Level 3 | GO 165 Inspection
127281472 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127282194 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127282320 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127283725 | other | HFTD Tier 2 | Transmission | 2023-10-16 | 2024-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127283729 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127284120 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2024-10-12 | Level 2 | E |  | 2024-10-12 | Level 2
127284309 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127284741 | other | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127284769 | anchor/guy | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127285711 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F | 2024-10-01 | 2028-10-16 | Level 3 | GO 165 Inspection
127285712 | other | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E | 2024-08-28 | 2026-10-16 | Level 2 | GO 165 Inspection
127286817 | insulator and brushing | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127286979 | splice | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127286987 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-07-08 | 2028-10-17 | Level 3 | GO 165 Inspection
127287548 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
127287962 | other | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F |  | 2028-10-10 | Level 3
127288092 | anchor/guy | Non-HFTD | Transmission | 2023-10-10 | 2028-10-10 | Level 3 | F | 2024-11-18 | 2028-10-10 | Level 3 | GO 165 Inspection
127288096 | splice | Non-HFTD | Transmission | 2023-10-10 | 2026-10-10 | Level 2 | E | 2024-11-18 | 2026-10-10 | Level 2 | GO 165 Inspection
127288835 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E | 2024-08-28 | 2026-10-16 | Level 2 | GO 165 Inspection
127288839 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E | 2024-08-28 | 2026-10-16 | Level 2 | GO 165 Inspection
127289045 | other | Non-HFTD | Transmission | 2023-10-16 | 2024-10-16 | Level 2 | E | 2024-08-28 | 2026-10-16 | Level 2 | GO 165 Inspection
127289224 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-09-25 | 2028-10-17 | Level 3 | GO 165 Inspection
127289469 | pole | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E |  | 2026-10-17 | Level 2
127290077 | pole | Non-HFTD | Transmission | 2023-10-17 | 2024-10-17 | Level 2 | E | 2024-10-08 | 2024-10-17 | Level 2 | Field Safety Reassessment
127290275 | pole | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-04-03 | 2028-10-17 | Level 3 | GO 165 Inspection
127290379 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127290522 | anchor/guy | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E | 2024-11-14 | 2026-10-16 | Level 2 | GO 165 Inspection
127290525 | splice | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127291922 | anchor/guy | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127292519 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2024-10-17 | Level 2 | E | 2024-09-16 | 2024-10-17 | Level 2 | GO 165 Inspection
127292598 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E | 2024-09-16 | 2026-10-17 | Level 2 | GO 165 Inspection
127292600 | anchor/guy | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-09-16 | 2028-10-17 | Level 3 | GO 165 Inspection
127292818 | splice | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E | 2024-09-16 | 2026-10-17 | Level 2 | GO 165 Inspection
127293921 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
127294046 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E | 2024-08-23 | 2026-10-17 | Level 2 | GO 165 Inspection
127294049 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-09-12 | 2028-10-17 | Level 3 | GO 165 Inspection
127294131 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E | 2024-09-16 | 2026-10-17 | Level 2 | GO 165 Inspection
127294299 | crossarm | Non-HFTD | Transmission | 2023-06-01 | 2023-12-01 | Level 2 | E | 2024-05-02 | 2023-12-01 | Level 2 | GO 165 Inspection
127294392 | crossarm | Non-HFTD | Transmission | 2023-06-01 | 2023-12-01 | Level 2 | E | 2024-04-10 | 2023-12-01 | Level 2 | Field Safety Reassessment
127294488 | other | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F |  | 2028-06-01 | Level 3
127294516 | crossarm | Non-HFTD | Transmission | 2023-06-05 | 2023-12-05 | Level 2 | E | 2024-04-10 | 2023-12-05 | Level 2 | Field Safety Reassessment
127294543 | other | Non-HFTD | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-07-31 | 2028-06-05 | Level 3 | GO 165 Inspection
127294545 | crossarm | Non-HFTD | Transmission | 2023-06-01 | 2023-12-01 | Level 2 | E | 2024-04-10 | 2023-12-01 | Level 2 | Field Safety Reassessment
127294546 | other | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-10-16 | 2028-06-01 | Level 3 | GO 165 Inspection
127294547 | pole | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-10-16 | 2028-06-01 | Level 3 | GO 165 Inspection
127294554 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127294555 | splice | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127294590 | pole | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F |  | 2028-06-01 | Level 3
127295818 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127296148 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127296155 | pole | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-09-04 | 2028-10-17 | Level 3 | GO 165 Inspection
127296157 | switch | Non-HFTD | Transmission | 2023-10-17 | 2024-10-17 | Level 2 | E |  | 2024-10-17 | Level 2
127296171 | pole | Non-HFTD | Transmission | 2023-10-18 | 2024-10-18 | Level 2 | E | 2024-10-30 | 2024-10-18 | Level 2 | GO 165 Inspection
127296212 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127296455 | insulator and brushing | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E | 2024-10-30 | 2026-10-18 | Level 2 | GO 165 Inspection
127296577 | pole | Non-HFTD | Transmission | 2023-10-17 | 2024-10-17 | Level 2 | E | 2024-11-15 | 2024-10-17 | Level 2 | Field Safety Reassessment
127296772 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E | 2024-10-18 | 2026-10-18 | Level 2 | GO 165 Inspection
127297286 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127297355 | insulator and brushing | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127297570 | insulator and brushing | Non-HFTD | Transmission | 2023-10-11 | 2026-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
127297787 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E | 2024-08-28 | 2026-10-17 | Level 2 | GO 165 Inspection
127297855 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127298249 | insulator and brushing | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127298268 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127298329 | anchor/guy | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127298404 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127298543 | other | Non-HFTD | Transmission | 2023-10-11 | 2028-10-11 | Level 3 | F |  | 2028-10-11 | Level 3
127298825 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127298991 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127299113 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127299197 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127300165 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127300303 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127300673 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127300793 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F | 2024-08-21 | 2028-10-18 | Level 3 | GO 165 Inspection
127300995 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127301251 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127301338 | pole | Non-HFTD | Transmission | 2023-06-01 | 2026-06-01 | Level 2 | E | 2024-10-15 | 2026-06-01 | Level 2 | GO 165 Inspection
127301377 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127301487 | pole | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-10-09 | 2028-06-01 | Level 3 | GO 165 Inspection
127301601 | pole | Non-HFTD | Transmission | 2023-06-03 | 2024-06-03 | Level 2 | E | 2024-09-03 | 2024-06-03 | Level 2 | GO 165 Inspection
127301624 | other | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-10-16 | 2028-06-01 | Level 3 | GO 165 Inspection
127301674 | other | Non-HFTD | Transmission | 2023-06-05 | 2028-06-05 | Level 3 | F | 2024-10-17 | 2028-06-05 | Level 3 | GO 165 Inspection
127301754 | pole | Non-HFTD | Transmission | 2023-05-31 | 2024-05-31 | Level 3 | F | 2024-10-09 | 2028-05-31 | Level 3 | GO 165 Inspection
127301866 | crossarm | Non-HFTD | Transmission | 2023-06-01 | 2023-12-01 | Level 2 | E | 2024-05-02 | 2023-12-01 | Level 2 | GO 165 Inspection
127301889 | pole | Non-HFTD | Transmission | 2023-06-01 | 2028-06-01 | Level 3 | F | 2024-10-16 | 2028-06-01 | Level 3 | GO 165 Inspection
127302774 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127302841 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F | 2024-04-30 | 2028-10-12 | Level 3 | GO 165 Inspection
127302907 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127302974 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-10-08 | 2028-10-19 | Level 3 | GO 165 Inspection
127302988 | pole | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127303133 | other | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127303160 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127303257 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F | 2024-04-30 | 2028-10-12 | Level 3 | GO 165 Inspection
127303261 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127303585 | anchor/guy | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127303729 | pole | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127303855 | pole | Non-HFTD | Transmission | 2023-10-19 | 2024-10-19 | Level 2 | E | 2024-01-26 | 2024-10-19 | Level 2 | Field Safety Reassessment
127303858 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127303952 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127304173 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127304482 | pole | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127304589 | pole | Non-HFTD | Transmission | 2023-10-19 | 2024-10-19 | Level 2 | E | 2024-03-18 | 2024-10-19 | Level 2 | Field Safety Reassessment
127304612 | insulator and brushing | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E | 2024-07-22 | 2026-10-12 | Level 2 | GO 165 Inspection
127304626 | other | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E | 2024-07-03 | 2026-10-19 | Level 2 | GO 165 Inspection
127305408 | pole | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127305473 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127305744 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127305886 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127306029 | splice | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127306184 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127306208 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127306415 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127306872 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127307069 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127307211 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127307290 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127307600 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127307933 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-08-02 | 2028-10-19 | Level 3 | GO 165 Inspection
127307971 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F | 2024-08-29 | 2028-10-13 | Level 3 | GO 165 Inspection
127308008 | pole | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E | 2024-09-28 | 2026-10-19 | Level 2 | GO 165 Inspection
127308102 | pole | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127308210 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127308275 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-11-08 | 2028-10-19 | Level 3 | GO 165 Inspection
127308499 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127308547 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E | 2024-09-28 | 2026-10-19 | Level 2 | GO 165 Inspection
127309044 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 2 | E | 2024-11-04 | 2024-10-19 | Level 2 | GO 165 Inspection
127309112 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-10-10 | 2028-10-19 | Level 3 | GO 165 Inspection
127310792 | pole | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E | 2024-11-01 | 2026-10-16 | Level 2 | GO 165 Inspection
127310798 | anchor/guy | Non-HFTD | Transmission | 2023-10-16 | 2024-04-16 | Level 2 | E | 2024-01-17 | 2024-04-16 | Level 2 | Field Safety Reassessment
127310817 | other | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127310824 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127310879 | conductor | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127310902 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127310957 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F | 2024-10-12 | 2028-10-16 | Level 3 | GO 165 Inspection
127311033 | insulator and brushing | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127311069 | anchor/guy | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127311120 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127311138 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127311147 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127311222 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127311232 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127311297 | splice | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E | 2024-08-29 | 2026-10-12 | Level 2 | GO 165 Inspection
127311318 | other | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
127311361 | pole | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127311438 | splice | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127311509 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
127311548 | insulator and brushing | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127311671 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127311777 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127311950 | pole | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127312593 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127312606 | pole | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127312621 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127312626 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127313523 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127314355 | anchor/guy | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127314465 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127314725 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127315035 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127315868 | other | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E |  | 2026-10-20 | Level 2
127315986 | anchor/guy | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127316317 | pole | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E | 2024-10-18 | 2026-10-20 | Level 2 | GO 165 Inspection
127317062 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E | 2024-10-28 | 2026-10-20 | Level 2 | GO 165 Inspection
127317130 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E | 2024-10-28 | 2026-10-20 | Level 2 | GO 165 Inspection
127317497 | other | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E |  | 2026-10-17 | Level 2
127317694 | other | Non-HFTD | Transmission | 2023-10-20 | 2024-10-20 | Level 2 | E | 2024-12-10 | 2024-10-20 | Level 2 | Field Safety Reassessment
127317792 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-10-15 | 2028-10-20 | Level 3 | GO 165 Inspection
127317863 | pole | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E | 2024-10-24 | 2026-10-20 | Level 2 | GO 165 Inspection
127317940 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127317948 | anchor/guy | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-11-19 | 2028-10-17 | Level 3 | GO 165 Inspection
127319461 | pole | Non-HFTD | Transmission | 2023-10-21 | 2026-10-21 | Level 2 | E |  | 2026-10-21 | Level 2
127319721 | pole | Non-HFTD | Transmission | 2023-10-21 | 2026-10-21 | Level 2 | E |  | 2026-10-21 | Level 2
127319862 | other | Non-HFTD | Transmission | 2023-10-21 | 2028-10-21 | Level 3 | F |  | 2028-10-21 | Level 3
127319863 | anchor/guy | Non-HFTD | Transmission | 2023-10-21 | 2028-10-21 | Level 3 | F |  | 2028-10-21 | Level 3
127321271 | conductor | Non-HFTD | Transmission | 2023-10-21 | 2026-10-21 | Level 2 | E | 2024-07-15 | 2026-10-21 | Level 2 | GO 165 Inspection
127322381 | pole | Non-HFTD | Transmission | 2023-10-22 | 2026-10-22 | Level 2 | E |  | 2026-10-22 | Level 2
127322816 | other | Non-HFTD | Transmission | 2023-10-22 | 2026-10-22 | Level 2 | E |  | 2026-10-22 | Level 2
127322865 | other | Non-HFTD | Transmission | 2023-10-22 | 2026-10-22 | Level 2 | E |  | 2026-10-22 | Level 2
127323371 | other | Non-HFTD | Transmission | 2023-10-22 | 2028-10-22 | Level 3 | F |  | 2028-10-22 | Level 3
127323501 | pole | Non-HFTD | Transmission | 2023-10-22 | 2026-10-22 | Level 2 | E |  | 2026-10-22 | Level 2
127325024 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127325145 | pole | Non-HFTD | Transmission | 2023-10-13 | 2026-10-13 | Level 2 | E |  | 2026-10-13 | Level 2
127325448 | other | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E |  | 2026-10-17 | Level 2
127325601 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127325702 | pole | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127326384 | pole | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127326791 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127326960 | insulator and brushing | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-08-16 | 2028-10-17 | Level 3 | GO 165 Inspection
127327090 | pole | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127327342 | anchor/guy | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127327367 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F |  | 2028-10-13 | Level 3
127327477 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127327616 | conductor | Non-HFTD | Transmission | 2023-10-13 | 2024-10-13 | Level 2 | E |  | 2024-10-13 | Level 2
127327719 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127327851 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127328070 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127328128 | pole | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F | 2024-10-21 | 2028-10-23 | Level 3 | GO 165 Inspection
127328219 | anchor/guy | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127328399 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127328553 | other | Non-HFTD | Transmission | 2023-10-23 | 2027-10-23 | Level 3 | F |  | 2027-10-23 | Level 3
127328821 | insulator and brushing | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F | 2024-02-22 | 2028-10-18 | Level 3 | Field Safety Reassessment
127328852 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127329120 | anchor/guy | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127329123 | anchor/guy | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E | 2024-11-08 | 2026-10-23 | Level 2 | GO 165 Inspection
127329131 | pole | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E | 2024-11-08 | 2026-10-23 | Level 2 | GO 165 Inspection
127329140 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2024-10-23 | Level 2 | E | 2024-11-08 | 2024-10-23 | Level 2 | GO 165 Inspection
127329295 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-10-28 | 2028-10-19 | Level 3 | GO 165 Inspection
127329329 | pole | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F | 2024-07-11 | 2028-10-06 | Level 3 | GO 165 Inspection
127329787 | other | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E | 2024-08-23 | 2026-10-16 | Level 2 | GO 165 Inspection
127330338 | pole | Non-HFTD | Transmission | 2023-10-09 | 2026-10-09 | Level 2 | E |  | 2026-10-09 | Level 2
127330592 | pole | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127330716 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127330767 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F | 2024-07-15 | 2028-10-23 | Level 3 | GO 165 Inspection
127330927 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127331690 | anchor/guy | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F | 2024-09-12 | 2028-10-18 | Level 3 | GO 165 Inspection
127331756 | crossarm | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E | 2024-09-06 | 2024-01-23 | Level 2 | GO 165 Inspection
127331809 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127331841 | switch | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127332479 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-07-31 | 2028-10-20 | Level 3 | GO 165 Inspection
127332816 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E | 2024-10-23 | 2026-10-23 | Level 2 | GO 165 Inspection
127332902 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F | 2024-10-10 | 2028-10-23 | Level 3 | GO 165 Inspection
127332931 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E | 2024-10-28 | 2026-10-23 | Level 2 | GO 165 Inspection
127333073 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F | 2023-11-06 | 2028-10-18 | Level 3 | GO 165 Inspection
127333596 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127335184 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127335636 | other | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F |  | 2028-10-24 | Level 3
127335655 | other | Non-HFTD | Transmission | 2023-10-13 | 2024-10-13 | Level 2 | E | 2024-09-04 | 2024-01-13 | Level 2 | GO 165 Inspection
127336152 | insulator and brushing | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127336360 | other | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127336559 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127336783 | other | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F |  | 2028-10-24 | Level 3
127336989 | anchor/guy | Non-HFTD | Transmission | 2023-10-16 | 2028-10-16 | Level 3 | F |  | 2028-10-16 | Level 3
127337112 | insulator and brushing | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E | 2024-09-28 | 2026-10-18 | Level 2 | GO 165 Inspection
127337126 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127337527 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-09-27 | 2028-10-19 | Level 3 | GO 165 Inspection
127338497 | pole | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F | 2024-04-01 | 2028-10-18 | Level 3 | GO 165 Inspection
127338566 | crossarm | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E |  | 2026-10-24 | Level 2
127338626 | anchor/guy | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F |  | 2028-10-24 | Level 3
127338938 | other | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F | 2024-08-10 | 2028-10-24 | Level 3 | GO 165 Inspection
127339055 | other | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E | 2024-10-24 | 2026-10-24 | Level 2 | GO 165 Inspection
127339057 | other | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F | 2024-10-24 | 2028-10-24 | Level 3 | GO 165 Inspection
127341499 | anchor/guy | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127341609 | other | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E | 2024-06-25 | 2026-10-17 | Level 2 | GO 165 Inspection
127341625 | pole | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E | 2024-08-15 | 2026-10-24 | Level 2 | GO 165 Inspection
127341861 | pole | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127342262 | insulator and brushing | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E | 2024-05-01 | 2026-10-24 | Level 2 | Field Safety Reassessment
127342608 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F | 2024-10-29 | 2028-10-17 | Level 3 | GO 165 Inspection
127342610 | conductor | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127342793 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E | 2024-09-11 | 2026-10-19 | Level 2 | GO 165 Inspection
127342796 | anchor/guy | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127342869 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127343051 | other | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127343281 | pole | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-07-30 | 2028-10-19 | Level 3 | GO 165 Inspection
127343339 | anchor/guy | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127343947 | other | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127343948 | other | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127344028 | other | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127344054 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-09-27 | 2028-10-19 | Level 3 | GO 165 Inspection
127344099 | anchor/guy | Non-HFTD | Transmission | 2023-10-16 | 2026-10-16 | Level 2 | E |  | 2026-10-16 | Level 2
127344703 | other | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127344870 | switch | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2024-10-25 | Level 2
127345023 | pole | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127345167 | insulator and brushing | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127345210 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E | 2024-07-17 | 2026-10-03 | Level 2 | GO 165 Inspection
127345296 | pole | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127345403 | pole | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127345665 | pole | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E |  | 2026-10-24 | Level 2
127346126 | other | Non-HFTD | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
127346632 | crossarm | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127347672 | insulator and brushing | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127347712 | insulator and brushing | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127347730 | pole | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127347738 | insulator and brushing | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E | 2024-10-24 | 2026-10-24 | Level 2 | GO 165 Inspection
127348047 | anchor/guy | Non-HFTD | Transmission | 2023-10-25 | 2024-10-25 | Level 2 | E | 2024-12-10 | 2024-10-25 | Level 2 | Field Safety Reassessment
127348088 | insulator and brushing | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127348090 | conductor | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-07-17 | 2026-10-26 | Level 2 | GO 165 Inspection
127348375 | conductor | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-07-17 | 2026-10-26 | Level 2 | GO 165 Inspection
127348522 | conductor | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-07-17 | 2026-10-26 | Level 2 | GO 165 Inspection
127348862 | anchor/guy | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127348872 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
127349374 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127349449 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127349729 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127350558 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
127350822 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127351154 | anchor/guy | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127352061 | insulator and brushing | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127352440 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E | 2024-08-12 | 2026-10-03 | Level 2 | GO 165 Inspection
127352596 | insulator and brushing | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E | 2024-08-21 | 2026-10-05 | Level 2 | GO 165 Inspection
127352825 | other | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-08-29 | 2026-10-26 | Level 2 | GO 165 Inspection
127352913 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-11-15 | 2028-10-26 | Level 3 | GO 165 Inspection
127353390 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127353483 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127353710 | insulator and brushing | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-02-22 | 2026-10-26 | Level 2 | Field Safety Reassessment
127353933 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127353944 | pole | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
127353953 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-09-05 | 2028-10-26 | Level 3 | GO 165 Inspection
127354135 | crossarm | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E |  | 2026-10-19 | Level 2
127354271 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-10-22 | 2028-10-26 | Level 3 | GO 165 Inspection
127356581 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F |  | 2028-10-27 | Level 3
127356609 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F | 2024-10-21 | 2028-10-23 | Level 3 | GO 165 Inspection
127356629 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127356687 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127356727 | anchor/guy | Non-HFTD | Transmission | 2023-10-17 | 2026-10-17 | Level 2 | E |  | 2026-10-17 | Level 2
127356753 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E | 2024-09-06 | 2026-10-19 | Level 2 | GO 165 Inspection
127356779 | anchor/guy | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E | 2024-04-04 | 2026-10-24 | Level 2 | GO 165 Inspection
127356809 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-10-15 | 2028-10-20 | Level 3 | GO 165 Inspection
127356926 | other | Non-HFTD | Transmission | 2023-10-18 | 2028-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
127356955 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F | 2024-07-06 | 2028-10-19 | Level 3 | GO 165 Inspection
127356961 | splice | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-11-01 | 2026-10-27 | Level 2 | GO 165 Inspection
127357163 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127357412 | insulator and brushing | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-09-18 | 2026-10-27 | Level 2 | GO 165 Inspection
127357471 | switch | Non-HFTD | Transmission | 2023-10-27 | 2024-10-27 | Level 2 | E | 2024-09-18 | 2024-10-27 | Level 2 | GO 165 Inspection
127357493 | splice | Non-HFTD | Transmission | 2023-10-18 | 2026-10-18 | Level 2 | E |  | 2026-10-18 | Level 2
127357774 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127358057 | pole | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E | 2024-10-30 | 2026-10-20 | Level 2 | GO 165 Inspection
127358130 | insulator and brushing | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127358348 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-07-15 | 2026-10-27 | Level 2 | GO 165 Inspection
127358403 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F |  | 2028-10-27 | Level 3
127358485 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-07-15 | 2026-10-27 | Level 2 | GO 165 Inspection
127358628 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-09-30 | 2028-10-20 | Level 3 | GO 165 Inspection
127358865 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-11-01 | 2028-10-27 | Level 3 | GO 165 Inspection
127358873 | insulator and brushing | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127358936 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F |  | 2028-10-27 | Level 3
127359218 | pole | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F | 2024-08-08 | 2028-10-24 | Level 3 | GO 165 Inspection
127359230 | pole | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-10-16 | 2028-10-27 | Level 3 | GO 165 Inspection
127359287 | splice | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-08-09 | 2026-10-27 | Level 2 | GO 165 Inspection
127359581 | pole | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-11-01 | 2028-10-27 | Level 3 | GO 165 Inspection
127359688 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-08-12 | 2028-10-27 | Level 3 | GO 165 Inspection
127359732 | insulator and brushing | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-08-12 | 2028-10-27 | Level 3 | GO 165 Inspection
127359803 | anchor/guy | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-08-09 | 2028-10-27 | Level 3 | GO 165 Inspection
127359933 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F |  | 2028-10-27 | Level 3
127359949 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-08-09 | 2028-10-27 | Level 3 | GO 165 Inspection
127360066 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F |  | 2028-10-27 | Level 3
127360437 | other | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E |  | 2026-10-27 | Level 2
127360455 | pole | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-10-04 | 2028-10-26 | Level 3 | GO 165 Inspection
127360538 | insulator and brushing | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E |  | 2026-10-27 | Level 2
127360888 | pole | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-10-30 | 2028-10-27 | Level 3 | GO 165 Inspection
127361701 | pole | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-10-23 | 2028-10-27 | Level 3 | Field Safety Reassessment
127361703 | conductor | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-10-10 | 2026-10-27 | Level 2 | GO 165 Inspection
127361709 | other | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-11-01 | 2028-10-26 | Level 3 | GO 165 Inspection
127362520 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-11-08 | 2026-10-27 | Level 2 | GO 165 Inspection
127362538 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F | 2024-11-08 | 2028-10-27 | Level 3 | GO 165 Inspection
127362855 | insulator and brushing | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-09-30 | 2028-10-20 | Level 3 | GO 165 Inspection
127362898 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127362910 | pole | Non-HFTD | Transmission | 2023-10-20 | 2026-10-20 | Level 2 | E | 2024-10-28 | 2026-10-20 | Level 2 | GO 165 Inspection
127362917 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127363312 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127363354 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127363384 | anchor/guy | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127363842 | insulator and brushing | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127364234 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127364445 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127364823 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F | 2024-07-18 | 2028-10-28 | Level 3 | GO 165 Inspection
127365332 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127365770 | other | Non-HFTD | Transmission | 2023-10-28 | 2026-10-28 | Level 2 | E |  | 2026-10-28 | Level 2
127365772 | insulator and brushing | Non-HFTD | Transmission | 2023-10-28 | 2026-10-28 | Level 2 | E |  | 2026-10-28 | Level 2
127366356 | other | Non-HFTD | Transmission | 2023-10-28 | 2028-10-28 | Level 3 | F |  | 2028-10-28 | Level 3
127371210 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127372301 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-10-09 | 2026-10-27 | Level 2 | GO 165 Inspection
127373347 | pole | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-08-19 | 2028-10-30 | Level 3 | GO 165 Inspection
127373647 | insulator and brushing | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-07-12 | 2028-10-30 | Level 3 | GO 165 Inspection
127374096 | switch | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127374561 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127374756 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127375492 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-10-09 | 2026-10-30 | Level 2 | GO 165 Inspection
127376654 | other | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127376969 | anchor/guy | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127377887 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127378317 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-08-02 | 2026-10-30 | Level 2 | GO 165 Inspection
127378375 | other | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127380295 | other | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127380582 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127381044 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-11-01 | 2028-10-30 | Level 3 | GO 165 Inspection
127382305 | insulator and brushing | Non-HFTD | Transmission | 2023-10-30 | 2024-10-30 | Level 2 | E | 2024-09-27 | 2024-10-30 | Level 2 | Field Safety Reassessment
127382364 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127382394 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
127382397 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127382413 | pole | Non-HFTD | Transmission | 2023-10-23 | 2026-10-23 | Level 2 | E |  | 2026-10-23 | Level 2
127382433 | anchor/guy | Non-HFTD | Transmission | 2023-10-25 | 2024-10-25 | Level 2 | E | 2024-11-01 | 2024-10-25 | Level 2 | GO 165 Inspection
127382546 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127382759 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-10-28 | 2028-10-20 | Level 3 | GO 165 Inspection
127382781 | other | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127382807 | other | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F |  | 2028-10-23 | Level 3
127382853 | anchor/guy | Non-HFTD | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
127383867 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F |  | 2028-10-31 | Level 3
127383874 | anchor/guy | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-10-23 | 2026-10-30 | Level 2 | GO 165 Inspection
127383903 | insulator and brushing | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 3 | F | 2024-07-11 | 2028-10-31 | Level 3 | GO 165 Inspection
127383914 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F | 2024-07-11 | 2028-10-31 | Level 3 | GO 165 Inspection
127384080 | switch | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127384285 | pole | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F | 2024-11-04 | 2028-10-31 | Level 3 | GO 165 Inspection
127384656 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F | 2024-10-29 | 2028-10-31 | Level 3 | GO 165 Inspection
127384706 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F |  | 2028-10-31 | Level 3
127384708 | pole | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127384710 | insulator and brushing | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F |  | 2028-10-31 | Level 3
127384957 | pole | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127385397 | pole | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E | 2024-11-04 | 2026-10-31 | Level 2 | GO 165 Inspection
127385559 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F | 2024-10-24 | 2028-10-31 | Level 3 | GO 165 Inspection
127385637 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F |  | 2028-10-31 | Level 3
127386124 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-11-08 | 2026-10-27 | Level 2 | GO 165 Inspection
127386186 | anchor/guy | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127386353 | pole | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127387272 | anchor/guy | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127388103 | other | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E | 2024-10-23 | 2026-10-31 | Level 2 | GO 165 Inspection
127388122 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-08-23 | 2028-10-20 | Level 3 | GO 165 Inspection
127388349 | other | Non-HFTD | Transmission | 2023-10-20 | 2028-10-20 | Level 3 | F | 2024-10-15 | 2028-10-20 | Level 3 | GO 165 Inspection
127390247 | pole | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E | 2024-09-28 | 2026-10-25 | Level 2 | GO 165 Inspection
127391975 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127392991 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127393008 | other | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E | 2024-10-04 | 2026-11-01 | Level 2 | Field Safety Reassessment
127393024 | other | Non-HFTD | Transmission | 2023-10-24 | 2026-10-24 | Level 2 | E | 2024-10-30 | 2026-10-24 | Level 2 | GO 165 Inspection
127393045 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127393266 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127393770 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127393998 | pole | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-10-15 | 2028-10-26 | Level 3 | GO 165 Inspection
127394929 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127395147 | crossarm | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
127395213 | insulator and brushing | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127395341 | insulator and brushing | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E |  | 2026-11-01 | Level 2
127395601 | anchor/guy | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127395864 | other | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127396000 | other | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127396004 | other | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E |  | 2026-11-01 | Level 2
127396049 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127396132 | pole | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F |  | 2028-10-24 | Level 3
127396169 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127396261 | other | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F |  | 2028-10-24 | Level 3
127396298 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-06-15 | 2028-11-01 | Level 3 | GO 165 Inspection
127396311 | other | Non-HFTD | Transmission | 2023-10-24 | 2028-10-24 | Level 3 | F |  | 2028-10-24 | Level 3
127396372 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127398313 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127398411 | anchor/guy | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127398746 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127398859 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127399053 | anchor/guy | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127399226 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127399384 | anchor/guy | Non-HFTD | Transmission | 2023-10-31 | 2024-02-01 | Level 2 | E | 2024-12-17 | 2024-01-31 | Level 2 | Field Safety Reassessment
127399606 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127400264 | insulator and brushing | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E | 2024-10-10 | 2026-11-01 | Level 2 | GO 165 Inspection
127400345 | pole | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E |  | 2026-11-01 | Level 2
127400669 | anchor/guy | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127400671 | anchor/guy | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127400673 | anchor/guy | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127400873 | insulator and brushing | Non-HFTD | Transmission | 2023-11-01 | 2024-02-01 | Level 2 | E | 2024-01-30 | 2024-02-01 | Level 2 | Field Safety Reassessment
127400956 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127401015 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127401958 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127402193 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127402527 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E | 2024-11-18 | 2026-11-02 | Level 2 | GO 165 Inspection
127402609 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127403184 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E | 2024-11-06 | 2026-11-02 | Level 2 | Field Safety Reassessment
127403410 | switch | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E |  | 2026-11-01 | Level 2
127403810 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E | 2024-11-18 | 2026-11-02 | Level 2 | GO 165 Inspection
127404841 | other | HFTD Tier 2 | Transmission | 2023-11-02 | 2024-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127404867 | other | HFTD Tier 2 | Transmission | 2023-11-02 | 2024-11-02 | Level 3 | F | 2024-03-26 | 2028-11-02 | Level 3 | GO 165 Inspection
127404917 | other | HFTD Tier 2 | Transmission | 2023-11-02 | 2024-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127406481 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127406510 | pole | Non-HFTD | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F | 2024-10-25 | 2028-10-26 | Level 3 | GO 165 Inspection
127406568 | other | Non-HFTD | Transmission | 2023-10-27 | 2028-10-27 | Level 3 | F |  | 2028-10-27 | Level 3
127406679 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-10-01 | 2024-05-03 | Level 2 | GO 165 Inspection
127406711 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127406765 | pole | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-10-23 | 2028-10-30 | Level 3 | Field Safety Reassessment
127406777 | splice | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-10-08 | 2026-10-26 | Level 2 | GO 165 Inspection
127406854 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2024-02-02 | Level 2 | E |  | 2024-02-02 | Level 2
127406910 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-10-10 | 2028-10-30 | Level 3 | GO 165 Inspection
127406937 | anchor/guy | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127406950 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-07-10 | 2028-10-30 | Level 3 | GO 165 Inspection
127406971 | anchor/guy | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-09-10 | 2026-10-26 | Level 2 | GO 165 Inspection
127406975 | insulator and brushing | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E |  | 2026-10-26 | Level 2
127407105 | anchor/guy | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127407120 | insulator and brushing | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-08-12 | 2026-10-27 | Level 2 | GO 165 Inspection
127407140 | other | Non-HFTD | Transmission | 2023-10-26 | 2026-10-26 | Level 2 | E | 2024-09-12 | 2026-10-26 | Level 2 | GO 165 Inspection
127407160 | pole | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127407309 | insulator and brushing | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-09-18 | 2026-10-27 | Level 2 | GO 165 Inspection
127407314 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-08-26 | 2026-10-30 | Level 2 | GO 165 Inspection
127407337 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127407709 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-07-11 | 2026-11-03 | Level 2 | GO 165 Inspection
127408081 | other | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E |  | 2026-10-27 | Level 2
127408178 | anchor/guy | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127408379 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-09-18 | 2026-10-27 | Level 2 | GO 165 Inspection
127408402 | anchor/guy | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E |  | 2026-10-27 | Level 2
127408611 | insulator and brushing | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E | 2024-09-18 | 2026-10-27 | Level 2 | GO 165 Inspection
127408931 | other | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E |  | 2026-10-27 | Level 2
127409064 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127409230 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127409231 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127409233 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-11-18 | 2026-11-03 | Level 2 | GO 165 Inspection
127409518 | insulator and brushing | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-09-03 | 2026-10-30 | Level 2 | GO 165 Inspection
127410017 | insulator and brushing | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F |  | 2028-10-31 | Level 3
127410262 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127410451 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127410466 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127410595 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127410638 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-10-10 | 2026-11-03 | Level 2 | GO 165 Inspection
127410743 | anchor/guy | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127410753 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F | 2024-10-10 | 2028-11-03 | Level 3 | GO 165 Inspection
127410755 | pole | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F | 2024-10-10 | 2028-11-03 | Level 3 | GO 165 Inspection
127411030 | pole | Non-HFTD | Transmission | 2023-10-12 | 2026-10-12 | Level 2 | E |  | 2026-10-12 | Level 2
127411256 | pole | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127411321 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127411453 | insulator and brushing | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127411904 | anchor/guy | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127412234 | splice | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127412703 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-09-18 | 2026-11-03 | Level 2 | GO 165 Inspection
127412809 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-11-18 | 2026-11-03 | Level 2 | GO 165 Inspection
127412840 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-11-18 | 2026-11-03 | Level 2 | GO 165 Inspection
127413320 | anchor/guy | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127413343 | other | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127413354 | other | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127413434 | other | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127413557 | insulator and brushing | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-11-18 | 2026-11-04 | Level 2 | GO 165 Inspection
127413558 | pole | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-06-19 | 2026-11-04 | Level 2 | GO 165 Inspection
127413571 | anchor/guy | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127413954 | insulator and brushing | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-11-18 | 2026-11-04 | Level 2 | GO 165 Inspection
127414051 | insulator and brushing | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E |  | 2026-11-04 | Level 2
127414052 | anchor/guy | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127414912 | anchor/guy | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127414952 | anchor/guy | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127415483 | other | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127417678 | other | Non-HFTD | Transmission | 2023-11-05 | 2028-11-05 | Level 3 | F | 2024-10-18 | 2028-11-05 | Level 3 | GO 165 Inspection
127417945 | other | Non-HFTD | Transmission | 2023-11-05 | 2026-11-05 | Level 2 | E |  | 2026-11-05 | Level 2
127418148 | other | Non-HFTD | Transmission | 2023-11-05 | 2028-11-05 | Level 3 | F | 2024-09-17 | 2028-11-05 | Level 3 | GO 165 Inspection
127418360 | other | Non-HFTD | Transmission | 2023-11-05 | 2028-11-05 | Level 3 | F |  | 2028-11-05 | Level 3
127419465 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127419550 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127419851 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127419927 | pole | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127420598 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-10-10 | 2026-11-03 | Level 2 | GO 165 Inspection
127420692 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-10-10 | 2026-11-03 | Level 2 | GO 165 Inspection
127420715 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127421055 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127421063 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127421851 | other | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-10-10 | 2026-11-03 | Level 2 | GO 165 Inspection
127421892 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127421913 | anchor/guy | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127422249 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127422720 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127423080 | pole | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-08-20 | 2028-11-06 | Level 3 | GO 165 Inspection
127423205 | anchor/guy | Non-HFTD | Transmission | 2023-02-21 | 2026-02-21 | Level 2 | E | 2024-02-07 | 2026-02-21 | Level 2 | GO 165 Inspection
127423314 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127423576 | anchor/guy | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-10-16 | 2026-11-06 | Level 2 | GO 165 Inspection
127424186 | other | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-10-10 | 2026-11-06 | Level 2 | GO 165 Inspection
127424222 | anchor/guy | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127424944 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-09-16 | 2028-11-06 | Level 3 | GO 165 Inspection
127425061 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-08 | 2028-11-06 | Level 3 | GO 165 Inspection
127425063 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-08 | 2028-11-06 | Level 3 | GO 165 Inspection
127425076 | other | Non-HFTD | Transmission | 2023-10-30 | 2024-10-30 | Level 2 | E |  | 2024-10-30 | Level 2
127425114 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127425142 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-09-06 | 2026-11-06 | Level 2 | GO 165 Inspection
127425149 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-08-23 | 2026-11-06 | Level 2 | GO 165 Inspection
127425162 | pole | Non-HFTD | Transmission | 2023-11-04 | 2024-11-04 | Level 2 | E | 2024-12-18 | 2024-11-04 | Level 2 | Field Safety Reassessment
127425167 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
127425195 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-08-30 | 2028-10-30 | Level 3 | GO 165 Inspection
127425317 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-03-18 | 2028-11-01 | Level 3 | Field Safety Reassessment
127425384 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-10-16 | 2028-11-01 | Level 3 | GO 165 Inspection
127425409 | other | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-09-18 | 2026-11-06 | Level 2 | GO 165 Inspection
127425422 | pole | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E |  | 2026-11-04 | Level 2
127425504 | anchor/guy | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F |  | 2028-10-31 | Level 3
127425581 | other | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127425629 | pole | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127425707 | anchor/guy | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127426240 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127426285 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127426345 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127427302 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127427305 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127427345 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-08-26 | 2026-11-06 | Level 2 | GO 165 Inspection
127427423 | splice | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127427643 | splice | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127427973 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127428149 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127428389 | pole | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
127428421 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127428660 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-08 | 2028-11-06 | Level 3 | GO 165 Inspection
127428662 | pole | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-08 | 2028-11-06 | Level 3 | GO 165 Inspection
127429955 | anchor/guy | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-09 | 2028-11-06 | Level 3 | GO 165 Inspection
127430198 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127430928 | anchor/guy | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127431279 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127431324 | insulator and brushing | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127432284 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127432611 | pole | HFTD Tier 3 | Transmission | 2023-11-07 | 2024-05-07 | Level 2 | E | 2024-05-03 | 2024-05-07 | Level 2 | Field Safety Reassessment
127432912 | other | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E | 2024-05-09 | 2026-11-01 | Level 2 | GO 165 Inspection
127435654 | switch | Non-HFTD | Transmission | 2023-11-07 | 2024-05-07 | Level 2 | E | 2024-08-23 | 2024-05-07 | Level 2 | Field Safety Reassessment
127435970 | anchor/guy | Non-HFTD | Transmission | 2023-11-08 | 2024-11-08 | Level 2 | E | 2024-10-23 | 2024-11-08 | Level 2 | GO 165 Inspection
127436364 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E | 2024-08-23 | 2026-11-07 | Level 2 | GO 165 Inspection
127436506 | conductor | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127436992 | other | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F | 2024-10-18 | 2028-10-31 | Level 3 | GO 165 Inspection
127437157 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127437822 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127438047 | splice | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127438253 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127438939 | switch | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127439446 | anchor/guy | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127439770 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-09-26 | 2028-11-01 | Level 3 | GO 165 Inspection
127440658 | pole | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E |  | 2026-11-01 | Level 2
127440768 | pole | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E |  | 2026-11-01 | Level 2
127440999 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F | 2024-10-01 | 2028-11-03 | Level 3 | GO 165 Inspection
127441151 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-08-07 | 2028-11-02 | Level 3 | GO 165 Inspection
127441160 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-08-07 | 2028-11-02 | Level 3 | GO 165 Inspection
127441174 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127441197 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127441266 | other | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E | 2024-10-18 | 2026-11-01 | Level 2 | GO 165 Inspection
127441340 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-07-17 | 2028-11-02 | Level 3 | GO 165 Inspection
127441347 | other | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-09-18 | 2026-11-03 | Level 2 | GO 165 Inspection
127441373 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127441444 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F | 2024-10-30 | 2028-11-03 | Level 3 | GO 165 Inspection
127441450 | insulator and brushing | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E | 2024-10-16 | 2026-11-01 | Level 2 | GO 165 Inspection
127441475 | conductor | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127441488 | switch | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127441554 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127441559 | other | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127441562 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127441566 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-09-26 | 2028-11-02 | Level 3 | GO 165 Inspection
127441575 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127441594 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E | 2024-08-06 | 2026-11-02 | Level 2 | GO 165 Inspection
127441619 | other | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127441622 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E | 2024-08-07 | 2026-11-03 | Level 2 | GO 165 Inspection
127441641 | conductor | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127441728 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E | 2024-09-12 | 2026-11-02 | Level 2 | GO 165 Inspection
127441735 | anchor/guy | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127441744 | anchor/guy | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127441748 | pole | Non-HFTD | Transmission | 2023-11-03 | 2024-11-03 | Level 2 | E | 2024-08-05 | 2024-11-03 | Level 2 | GO 165 Inspection
127441772 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127441784 | anchor/guy | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127441902 | switch | Non-HFTD | Transmission | 2023-11-03 | 2024-11-03 | Level 2 | E | 2024-10-25 | 2024-11-03 | Level 2 | Field Safety Reassessment
127447447 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E | 2024-07-15 | 2026-11-08 | Level 2 | GO 165 Inspection
127447497 | pole | Non-HFTD | Transmission | 2023-11-09 | 2024-11-09 | Level 2 | E | 2024-12-09 | 2024-11-09 | Level 2 | Field Safety Reassessment
127447699 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E | 2024-11-19 | 2026-11-08 | Level 2 | GO 165 Inspection
127447722 | other | HFTD Tier 3 | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-03-11 | 2028-10-30 | Level 3 | GO 165 Inspection
127447775 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F | 2024-11-19 | 2028-11-08 | Level 3 | GO 165 Inspection
127448673 | other | HFTD Tier 3 | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F | 2024-03-12 | 2028-10-30 | Level 3 | GO 165 Inspection
127448709 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127448857 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F | 2024-09-05 | 2028-11-09 | Level 3 | GO 165 Inspection
127449147 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127449423 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127450020 | pole | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127450205 | conductor | Non-HFTD | Transmission | 2023-11-08 | 2024-02-08 | Level 2 | E | 2024-12-09 | 2024-02-08 | Level 2 | Field Safety Reassessment
127451093 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127451098 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127451333 | anchor/guy | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127452325 | anchor/guy | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127452376 | other | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127455321 | pole | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-09-18 | 2028-11-06 | Level 3 | GO 165 Inspection
127456907 | pole | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-10-16 | 2026-11-04 | Level 2 | GO 165 Inspection
127456937 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F | 2024-08-08 | 2028-11-07 | Level 3 | GO 165 Inspection
127457625 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127457716 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127457721 | splice | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127457725 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-28 | 2028-11-06 | Level 3 | GO 165 Inspection
127457733 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F | 2024-08-01 | 2028-11-03 | Level 3 | GO 165 Inspection
127457818 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-10-18 | 2028-11-06 | Level 3 | GO 165 Inspection
127457994 | crossarm | Non-HFTD | Transmission | 2023-11-08 | 2024-11-08 | Level 2 | E | 2024-08-12 | 2024-11-08 | Level 2 | GO 165 Inspection
127458157 | pole | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127458221 | insulator and brushing | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127458246 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127458251 | other | Non-HFTD | Transmission | 2023-09-21 | 2028-09-21 | Level 3 | F |  | 2028-09-21 | Level 3
127458278 | anchor/guy | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F |  | 2028-11-03 | Level 3
127458282 | other | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E |  | 2026-11-04 | Level 2
127458300 | other | Non-HFTD | Transmission | 2023-11-04 | 2028-11-04 | Level 3 | F |  | 2028-11-04 | Level 3
127458311 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-09-03 | 2028-11-06 | Level 3 | GO 165 Inspection
127458359 | pole | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-07-18 | 2026-11-04 | Level 2 | GO 165 Inspection
127458408 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F | 2024-09-27 | 2028-11-06 | Level 3 | GO 165 Inspection
127458410 | insulator and brushing | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127458502 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
127458519 | insulator and brushing | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F | 2024-08-08 | 2028-11-07 | Level 3 | GO 165 Inspection
127458660 | anchor/guy | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127458698 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127460480 | pole | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127460686 | anchor/guy | Non-HFTD | Transmission | 2023-11-09 | 2024-11-09 | Level 2 | E | 2024-12-07 | 2024-11-09 | Level 2 | Field Safety Reassessment
127460990 | other | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127461068 | insulator and brushing | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E | 2024-10-11 | 2024-11-10 | Level 2 | GO 165 Inspection
127462567 | pole | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F | 2024-08-21 | 2028-11-08 | Level 3 | GO 165 Inspection
127462607 | anchor/guy | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F | 2024-11-20 | 2028-11-09 | Level 3 | GO 165 Inspection
127463845 | pole | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F | 2024-09-26 | 2028-11-09 | Level 3 | GO 165 Inspection
127464771 | pole | HFTD Tier 3 | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127465112 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F | 2024-10-22 | 2028-11-10 | Level 3 | GO 165 Inspection
127467725 | splice | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127468587 | crossarm | Non-HFTD | Transmission | 2023-11-12 | 2026-11-12 | Level 2 | E |  | 2026-11-12 | Level 2
127468654 | pole | Non-HFTD | Transmission | 2023-11-12 | 2026-11-12 | Level 2 | E |  | 2026-11-12 | Level 2
127469671 | other | HFTD Tier 2 | Transmission | 2023-11-12 | 2024-11-12 | Level 3 | F | 2024-04-26 | 2028-11-12 | Level 3 | GO 165 Inspection
127471628 | other | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E | 2024-10-28 | 2024-02-10 | Level 2 | GO 165 Inspection
127472035 | insulator and brushing | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127472105 | anchor/guy | Non-HFTD | Transmission | 2023-11-10 | 2024-11-10 | Level 2 | E | 2024-12-03 | 2024-11-10 | Level 2 | Field Safety Reassessment
127473021 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-08-06 | 2028-11-02 | Level 3 | GO 165 Inspection
127473280 | insulator and brushing | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127473538 | other | Non-HFTD | Transmission | 2023-11-11 | 2024-11-11 | Level 2 | E |  | 2024-11-11 | Level 2
127473623 | other | Non-HFTD | Transmission | 2023-11-11 | 2028-11-11 | Level 3 | F |  | 2028-11-11 | Level 3
127474428 | splice | Non-HFTD | Transmission | 2023-11-13 | 2026-11-13 | Level 2 | E |  | 2026-11-13 | Level 2
127475052 | insulator and brushing | Non-HFTD | Transmission | 2023-11-06 | 2024-11-06 | Level 2 | E | 2024-08-23 | 2024-11-06 | Level 2 | GO 165 Inspection
127475912 | insulator and brushing | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127475916 | anchor/guy | Non-HFTD | Transmission | 2023-11-11 | 2028-11-11 | Level 3 | F |  | 2028-11-11 | Level 3
127475919 | pole | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E | 2024-09-16 | 2026-11-09 | Level 2 | GO 165 Inspection
127476332 | insulator and brushing | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E | 2024-04-08 | 2026-11-11 | Level 2 | GO 165 Inspection
127476334 | conductor | Non-HFTD | Transmission | 2023-11-06 | 2024-05-06 | Level 2 | E | 2024-10-15 | 2024-05-06 | Level 2 | Field Safety Reassessment
127476425 | pole | Non-HFTD | Transmission | 2023-11-11 | 2024-11-11 | Level 2 | E | 2024-09-16 | 2024-02-11 | Level 2 | GO 165 Inspection
127476602 | pole | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-09-04 | 2026-11-04 | Level 2 | GO 165 Inspection
127476796 | other | Non-HFTD | Transmission | 2023-11-06 | 2028-11-06 | Level 3 | F |  | 2028-11-06 | Level 3
127476892 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127476983 | other | Non-HFTD | Transmission | 2023-11-13 | 2028-11-13 | Level 3 | F | 2024-09-26 | 2028-11-13 | Level 3 | GO 165 Inspection
127477041 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E | 2024-10-01 | 2026-11-07 | Level 2 | GO 165 Inspection
127477077 | conductor | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127477114 | crossarm | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127477261 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127477706 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127478037 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127479051 | other | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E |  | 2026-11-14 | Level 2
127479936 | other | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F |  | 2028-11-07 | Level 3
127479939 | anchor/guy | Non-HFTD | Transmission | 2023-11-07 | 2028-11-07 | Level 3 | F | 2024-09-16 | 2028-11-07 | Level 3 | GO 165 Inspection
127480561 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127480577 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2026-11-03 | Level 2 | E |  | 2026-11-03 | Level 2
127481036 | other | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E |  | 2026-11-14 | Level 2
127481336 | other | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E |  | 2026-11-14 | Level 2
127482303 | pole | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127482316 | other | HFTD Tier 2 | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F |  | 2028-11-14 | Level 3
127482364 | other | Non-HFTD | Transmission | 2023-11-08 | 2024-11-08 | Level 2 | E |  | 2024-11-08 | Level 2
127482395 | anchor/guy | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127482398 | insulator and brushing | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127482408 | insulator and brushing | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127482410 | other | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E | 2024-11-19 | 2026-11-07 | Level 2 | GO 165 Inspection
127482413 | crossarm | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127482614 | splice | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E | 2024-10-08 | 2026-11-08 | Level 2 | GO 165 Inspection
127482623 | other | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E | 2024-09-26 | 2026-11-09 | Level 2 | GO 165 Inspection
127482642 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127482649 | other | Non-HFTD | Transmission | 2023-11-09 | 2024-11-09 | Level 2 | E | 2024-02-21 | 2024-11-09 | Level 2 | Field Safety Reassessment
127482671 | insulator and brushing | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127482680 | conductor | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127482682 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127482711 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127483177 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127483433 | anchor/guy | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127483937 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127484360 | insulator and brushing | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F | 2024-10-22 | 2028-11-15 | Level 3 | GO 165 Inspection
127484378 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127484704 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F | 2023-11-24 | 2028-11-09 | Level 3 | GO 165 Inspection
127484950 | pole | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E |  | 2026-11-14 | Level 2
127485586 | pole | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127485652 | other | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127485922 | pole | Non-HFTD | Transmission | 2023-11-14 | 2024-05-15 | Level 2 | E | 2024-12-12 | 2024-02-15 | Level 2 | Field Safety Reassessment
127486197 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F |  | 2028-11-08 | Level 3
127486435 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127486783 | anchor/guy | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127487091 | pole | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127488171 | pole | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127488229 | crossarm | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127488414 | other | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127488475 | pole | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127490151 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127490756 | insulator and brushing | Non-HFTD | Transmission | 2023-11-09 | 2024-11-09 | Level 2 | E | 2024-09-07 | 2024-11-09 | Level 2 | GO 165 Inspection
127490840 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F |  | 2028-11-09 | Level 3
127490933 | other | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F | 2024-10-11 | 2028-11-09 | Level 3 | GO 165 Inspection
127491033 | insulator and brushing | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127491422 | crossarm | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127492191 | pole | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127492326 | pole | Non-HFTD | Transmission | 2023-11-09 | 2028-11-09 | Level 3 | F | 2024-11-05 | 2028-11-09 | Level 3 | Field Safety Reassessment
127492456 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F | 2024-07-26 | 2028-11-10 | Level 3 | GO 165 Inspection
127492459 | other | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E |  | 2026-11-10 | Level 2
127492540 | anchor/guy | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127492567 | splice | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E | 2024-09-17 | 2026-11-10 | Level 2 | GO 165 Inspection
127492576 | pole | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127492601 | anchor/guy | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127492653 | anchor/guy | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127492693 | pole | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E |  | 2026-11-10 | Level 2
127492741 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127492759 | anchor/guy | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E |  | 2026-11-10 | Level 2
127492809 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127492814 | anchor/guy | Non-HFTD | Transmission | 2023-11-13 | 2028-11-13 | Level 3 | F |  | 2028-11-13 | Level 3
127492822 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F |  | 2028-11-10 | Level 3
127492831 | pole | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127494240 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2024-11-17 | Level 2 | E |  | 2024-11-17 | Level 2
127494256 | insulator and brushing | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E |  | 2026-11-04 | Level 2
127494870 | other | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127495416 | insulator and brushing | Non-HFTD | Transmission | 2023-11-14 | 2024-11-14 | Level 2 | E | 2024-07-09 | 2024-11-14 | Level 2 | Field Safety Reassessment
127495437 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127496192 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127496195 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F | 2024-07-26 | 2028-11-10 | Level 3 | GO 165 Inspection
127496288 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-09-27 | 2028-11-17 | Level 3 | GO 165 Inspection
127496609 | pole | Non-HFTD | Transmission | 2023-11-10 | 2026-11-10 | Level 2 | E |  | 2026-11-10 | Level 2
127496768 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127496946 | anchor/guy | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127496947 | other | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127497108 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127497197 | pole | Non-HFTD | Transmission | 2023-11-16 | 2024-11-16 | Level 2 | E | 2024-12-09 | 2024-11-16 | Level 2 | GO 165 Inspection
127497198 | other | Non-HFTD | Transmission | 2023-11-16 | 2024-11-16 | Level 2 | E | 2024-12-09 | 2026-11-16 | Level 2 | GO 165 Inspection
127500489 | pole | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-12-02 | 2028-11-17 | Level 3 | GO 165 Inspection
127500549 | pole | Non-HFTD | Transmission | 2023-10-29 | 2026-10-29 | Level 2 | E |  | 2026-10-29 | Level 2
127500640 | pole | Non-HFTD | Transmission | 2023-10-29 | 2026-10-29 | Level 2 | E | 2024-07-31 | 2026-10-29 | Level 2 | GO 165 Inspection
127500722 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127500843 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127501026 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 2 | E | 2023-11-28 | 2024-11-16 | Level 2 | GO 165 Inspection
127501237 | other | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127501287 | other | Non-HFTD | Transmission | 2023-11-15 | 2024-11-15 | Level 2 | E | 2024-12-04 | 2024-11-15 | Level 2 | Field Safety Reassessment
127501362 | other | Non-HFTD | Transmission | 2023-11-15 | 2024-11-15 | Level 2 | E | 2024-12-04 | 2024-11-15 | Level 2 | Field Safety Reassessment
127501489 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F |  | 2028-11-20 | Level 3
127501671 | other | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127501711 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127501718 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127501867 | insulator and brushing | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E | 2024-10-08 | 2026-11-15 | Level 2 | GO 165 Inspection
127502066 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F | 2024-12-09 | 2028-11-16 | Level 3 | GO 165 Inspection
127502206 | other | HFTD Tier 2 | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-05-07 | 2028-11-20 | Level 3 | GO 165 Inspection
127502590 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2024-11-16 | Level 2 | E | 2024-12-30 | 2024-11-16 | Level 2 | Field Safety Reassessment
127502727 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2024-11-16 | Level 2 | E | 2024-10-08 | 2024-11-16 | Level 2 | Field Safety Reassessment
127502787 | other | Non-HFTD | Transmission | 2023-11-16 | 2024-11-16 | Level 2 | E |  | 2024-11-16 | Level 2
127502920 | other | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127502995 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127503075 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127503288 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127503919 | anchor/guy | Non-HFTD | Transmission | 2023-11-17 | 2024-11-17 | Level 2 | E | 2024-08-20 | 2024-11-17 | Level 2 | Field Safety Reassessment
127504077 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127504126 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127504905 | other | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F | 2024-07-25 | 2028-11-10 | Level 3 | GO 165 Inspection
127505947 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E | 2024-10-26 | 2026-11-21 | Level 2 | GO 165 Inspection
127506611 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-08-29 | 2028-11-17 | Level 3 | GO 165 Inspection
127506859 | pole | Non-HFTD | Transmission | 2023-11-10 | 2028-11-10 | Level 3 | F | 2024-10-28 | 2028-11-10 | Level 3 | GO 165 Inspection
127507799 | other | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E | 2024-10-23 | 2026-11-17 | Level 2 | GO 165 Inspection
127507908 | other | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E | 2024-11-24 | 2026-11-11 | Level 2 | GO 165 Inspection
127508274 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E | 2024-09-06 | 2026-11-18 | Level 2 | GO 165 Inspection
127508472 | other | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E | 2024-08-29 | 2026-11-17 | Level 2 | GO 165 Inspection
127508627 | anchor/guy | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127509081 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-10-23 | 2028-11-17 | Level 3 | GO 165 Inspection
127509398 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2024-05-17 | Level 2 | E | 2024-05-13 | 2024-05-17 | Level 2 | Field Safety Reassessment
127509724 | pole | Non-HFTD | Transmission | 2023-11-18 | 2024-11-22 | Level 2 | E | 2024-09-06 | 2024-11-22 | Level 2 | GO 165 Inspection
127509804 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E |  | 2026-10-30 | Level 2
127510043 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2024-11-18 | Level 2 | E | 2024-12-11 | 2024-11-18 | Level 2 | Field Safety Reassessment
127510153 | other | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E | 2024-01-17 | 2026-11-18 | Level 2 | Field Safety Reassessment
127510559 | pole | Non-HFTD | Transmission | 2023-11-13 | 2026-11-13 | Level 2 | E | 2024-11-19 | 2026-11-13 | Level 2 | GO 165 Inspection
127510735 | other | HFTD Tier 2 | Transmission | 2023-11-22 | 2028-11-22 | Level 3 | F |  | 2028-11-22 | Level 3
127514562 | anchor/guy | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127514622 | other | HFTD Tier 3 | Transmission | 2023-11-27 | 2028-11-27 | Level 3 | F |  | 2028-11-27 | Level 3
127515179 | other | Non-HFTD | Transmission | 2023-11-13 | 2028-11-13 | Level 3 | F | 2024-11-19 | 2028-11-13 | Level 3 | GO 165 Inspection
127515551 | insulator and brushing | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127515553 | pole | Non-HFTD | Transmission | 2023-11-11 | 2026-11-11 | Level 2 | E |  | 2026-11-11 | Level 2
127515558 | other | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-16 | 2026-11-14 | Level 2 | GO 165 Inspection
127515964 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127516221 | anchor/guy | Non-HFTD | Transmission | 2023-11-27 | 2028-11-27 | Level 3 | F |  | 2028-11-27 | Level 3
127516521 | other | Non-HFTD | Transmission | 2023-11-20 | 2024-02-20 | Level 2 | E |  | 2024-02-20 | Level 2
127516603 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127516949 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127517078 | pole | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-09-13 | 2026-11-20 | Level 2 | GO 165 Inspection
127517181 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127517448 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127517562 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127518044 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F | 2024-09-04 | 2028-11-18 | Level 3 | GO 165 Inspection
127518123 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E | 2024-08-23 | 2026-11-18 | Level 2 | GO 165 Inspection
127518182 | pole | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-12-11 | 2028-11-20 | Level 3 | Field Safety Reassessment
127518281 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2024-11-20 | Level 2 | E | 2024-10-09 | 2024-11-20 | Level 2 | GO 165 Inspection
127519016 | pole | Non-HFTD | Transmission | 2023-11-28 | 2028-11-28 | Level 3 | F | 2024-10-28 | 2028-11-28 | Level 3 | GO 165 Inspection
127519368 | pole | Non-HFTD | Transmission | 2023-11-28 | 2026-11-28 | Level 2 | E | 2024-08-13 | 2026-11-28 | Level 2 | GO 165 Inspection
127519451 | pole | Non-HFTD | Transmission | 2023-11-28 | 2026-11-28 | Level 2 | E | 2024-08-13 | 2026-11-28 | Level 2 | GO 165 Inspection
127520510 | other | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-09-17 | 2026-11-20 | Level 2 | GO 165 Inspection
127520658 | other | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-09-18 | 2026-11-20 | Level 2 | GO 165 Inspection
127521145 | pole | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E |  | 2026-10-02 | Level 2
127521173 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-11-01 | 2026-11-20 | Level 2 | GO 165 Inspection
127521185 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127521464 | conductor | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-10-17 | 2026-11-20 | Level 2 | GO 165 Inspection
127521695 | pole | Non-HFTD | Transmission | 2023-10-02 | 2026-10-02 | Level 2 | E | 2024-08-06 | 2026-10-02 | Level 2 | GO 165 Inspection
127521944 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E |  | 2026-10-03 | Level 2
127522112 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E |  | 2026-10-03 | Level 2
127522195 | pole | Non-HFTD | Transmission | 2023-10-03 | 2026-10-03 | Level 2 | E |  | 2026-10-03 | Level 2
127522250 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2024-11-21 | Level 2 | E | 2024-12-10 | 2024-11-21 | Level 2 | Field Safety Reassessment
127522900 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E | 2024-08-08 | 2026-11-21 | Level 2 | GO 165 Inspection
127522914 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127522970 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127522977 | pole | Non-HFTD | Transmission | 2023-10-04 | 2026-10-04 | Level 2 | E |  | 2026-10-04 | Level 2
127522979 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127523617 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127523670 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127523688 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127523735 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E |  | 2026-10-05 | Level 2
127523827 | anchor/guy | Non-HFTD | Transmission | 2023-11-22 | 2024-11-22 | Level 2 | E | 2024-12-17 | 2024-11-22 | Level 2 | Field Safety Reassessment
127523874 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2028-11-22 | Level 3 | F |  | 2028-11-22 | Level 3
127524014 | pole | Non-HFTD | Transmission | 2023-11-29 | 2026-11-29 | Level 2 | E | 2024-10-03 | 2026-11-29 | Level 2 | GO 165 Inspection
127524211 | anchor/guy | Non-HFTD | Transmission | 2023-11-29 | 2026-11-29 | Level 2 | E | 2024-10-24 | 2026-11-29 | Level 2 | GO 165 Inspection
127524218 | anchor/guy | Non-HFTD | Transmission | 2023-11-29 | 2028-11-29 | Level 3 | F |  | 2028-11-29 | Level 3
127524479 | pole | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F | 2024-09-10 | 2028-11-21 | Level 3 | GO 165 Inspection
127524764 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
127525557 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2024-11-21 | Level 2 | E | 2024-09-10 | 2026-11-21 | Level 2 | GO 165 Inspection
127526086 | insulator and brushing | Non-HFTD | Transmission | 2023-11-29 | 2026-11-29 | Level 2 | E | 2024-10-03 | 2026-11-29 | Level 2 | GO 165 Inspection
127526396 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E |  | 2026-11-22 | Level 2
127526555 | pole | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E |  | 2026-11-22 | Level 2
127526577 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E |  | 2026-11-22 | Level 2
127526580 | other | HFTD Tier 2 | Transmission | 2023-11-29 | 2028-11-29 | Level 3 | F |  | 2028-11-29 | Level 3
127526661 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E |  | 2026-11-22 | Level 2
127527875 | insulator and brushing | Non-HFTD | Transmission | 2023-11-29 | 2024-11-29 | Level 2 | E | 2024-08-21 | 2024-11-29 | Level 2 | Field Safety Reassessment
127529035 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
127529135 | pole | Non-HFTD | Transmission | 2023-11-29 | 2026-11-29 | Level 2 | E |  | 2026-11-29 | Level 2
127529158 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E | 2024-09-17 | 2026-11-22 | Level 2 | GO 165 Inspection
127529912 | pole | Non-HFTD | Transmission | 2023-11-30 | 2026-11-30 | Level 2 | E | 2024-08-16 | 2026-11-30 | Level 2 | GO 165 Inspection
127530476 | other | Non-HFTD | Transmission | 2023-11-13 | 2026-11-13 | Level 2 | E | 2024-11-18 | 2026-11-13 | Level 2 | GO 165 Inspection
127531566 | pole | Non-HFTD | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F | 2024-10-29 | 2028-11-14 | Level 3 | GO 165 Inspection
127532283 | other | Non-HFTD | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F | 2024-11-16 | 2028-11-14 | Level 3 | GO 165 Inspection
127534193 | other | Non-HFTD | Transmission | 2023-12-01 | 2028-12-01 | Level 3 | F |  | 2028-12-01 | Level 3
127534476 | other | Non-HFTD | Transmission | 2023-11-13 | 2028-11-13 | Level 3 | F | 2024-11-19 | 2028-11-13 | Level 3 | GO 165 Inspection
127534854 | insulator and brushing | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-26 | 2026-11-14 | Level 2 | GO 165 Inspection
127535497 | insulator and brushing | Non-HFTD | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F |  | 2028-11-14 | Level 3
127535586 | other | Non-HFTD | Transmission | 2023-12-01 | 2026-12-01 | Level 2 | E | 2024-09-16 | 2026-12-01 | Level 2 | GO 165 Inspection
127535941 | other | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-19 | 2026-11-14 | Level 2 | GO 165 Inspection
127536151 | other | Non-HFTD | Transmission | 2023-12-01 | 2026-12-01 | Level 2 | E | 2024-10-18 | 2026-12-01 | Level 2 | GO 165 Inspection
127536426 | pole | Non-HFTD | Transmission | 2023-10-05 | 2026-10-05 | Level 2 | E | 2024-07-25 | 2026-10-05 | Level 2 | GO 165 Inspection
127536438 | anchor/guy | Non-HFTD | Transmission | 2023-12-01 | 2028-12-01 | Level 3 | F |  | 2028-12-01 | Level 3
127536482 | other | Non-HFTD | Transmission | 2023-12-01 | 2028-12-01 | Level 3 | F |  | 2028-12-01 | Level 3
127537434 | pole | Non-HFTD | Transmission | 2023-12-03 | 2026-12-03 | Level 2 | E | 2024-10-29 | 2026-12-03 | Level 2 | GO 165 Inspection
127537729 | pole | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-12-02 | 2026-11-14 | Level 2 | GO 165 Inspection
127537775 | anchor/guy | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-11-29 | 2026-10-30 | Level 2 | GO 165 Inspection
127537892 | insulator and brushing | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-15 | 2026-11-14 | Level 2 | GO 165 Inspection
127538081 | other | Non-HFTD | Transmission | 2023-11-14 | 2024-11-14 | Level 2 | E | 2024-10-09 | 2024-11-14 | Level 2 | GO 165 Inspection
127538119 | other | Non-HFTD | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F |  | 2028-11-14 | Level 3
127538139 | other | Non-HFTD | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F | 2024-11-14 | 2028-11-14 | Level 3 | GO 165 Inspection
127538364 | insulator and brushing | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-13 | 2026-11-14 | Level 2 | GO 165 Inspection
127538819 | other | Non-HFTD | Transmission | 2023-12-04 | 2028-12-04 | Level 3 | F |  | 2028-12-04 | Level 3
127538863 | pole | HFTD Tier 2 | Transmission | 2023-10-11 | 2024-10-11 | Level 2 | E | 2024-03-12 | 2024-10-11 | Level 2 | GO 165 Inspection
127538955 | other | Non-HFTD | Transmission | 2023-12-04 | 2028-12-04 | Level 3 | F | 2024-11-26 | 2028-12-04 | Level 3 | GO 165 Inspection
127539361 | insulator and brushing | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-15 | 2026-11-14 | Level 2 | GO 165 Inspection
127539428 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127539568 | insulator and brushing | HFTD Tier 3 | Transmission | 2023-12-04 | 2024-06-04 | Level 2 | E |  | 2024-06-04 | Level 2
127539756 | other | Non-HFTD | Transmission | 2023-11-14 | 2028-11-14 | Level 3 | F | 2024-11-19 | 2028-11-14 | Level 3 | GO 165 Inspection
127540096 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127540213 | pole | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E |  | 2026-11-14 | Level 2
127540351 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127540757 | pole | Non-HFTD | Transmission | 2023-12-04 | 2026-12-04 | Level 2 | E |  | 2026-12-04 | Level 2
127541172 | other | Non-HFTD | Transmission | 2023-12-05 | 2028-12-05 | Level 3 | F |  | 2028-12-05 | Level 3
127541337 | pole | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E | 2024-11-04 | 2026-11-22 | Level 2 | GO 165 Inspection
127541453 | other | Non-HFTD | Transmission | 2023-12-05 | 2028-12-05 | Level 3 | F |  | 2028-12-05 | Level 3
127541775 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127541863 | other | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127542541 | pole | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-10-09 | 2026-11-20 | Level 2 | GO 165 Inspection
127542558 | other | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E | 2024-11-13 | 2026-11-14 | Level 2 | GO 165 Inspection
127542671 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127543336 | anchor/guy | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127543450 | splice | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127543569 | anchor/guy | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127544406 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127544471 | insulator and brushing | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127544476 | insulator and brushing | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127544580 | anchor/guy | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127544830 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127545028 | pole | HFTD Tier 3 | Transmission | 2023-12-06 | 2026-12-06 | Level 2 | E | 2024-04-29 | 2026-12-06 | Level 2 | GO 165 Inspection
127545362 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E |  | 2026-11-06 | Level 2
127547192 | insulator and brushing | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F | 2024-06-19 | 2028-11-15 | Level 3 | GO 165 Inspection
127547217 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
127547519 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127548466 | insulator and brushing | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F | 2024-09-04 | 2028-11-15 | Level 3 | GO 165 Inspection
127548469 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127548488 | insulator and brushing | Non-HFTD | Transmission | 2023-11-30 | 2026-11-30 | Level 2 | E | 2024-09-16 | 2026-11-30 | Level 2 | GO 165 Inspection
127548588 | pole | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F | 2024-11-19 | 2028-11-15 | Level 3 | GO 165 Inspection
127548695 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127548963 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F | 2024-11-19 | 2028-11-15 | Level 3 | GO 165 Inspection
127549520 | pole | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127549581 | anchor/guy | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127549584 | other | Non-HFTD | Transmission | 2023-11-15 | 2028-11-15 | Level 3 | F |  | 2028-11-15 | Level 3
127549741 | other | Non-HFTD | Transmission | 2023-12-07 | 2026-12-07 | Level 2 | E | 2024-11-04 | 2026-12-07 | Level 2 | GO 165 Inspection
127549948 | pole | Non-HFTD | Transmission | 2023-10-31 | 2026-10-31 | Level 2 | E |  | 2026-10-31 | Level 2
127550157 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127550351 | switch | Non-HFTD | Transmission | 2023-12-07 | 2024-06-07 | Level 2 | E | 2024-11-18 | 2024-06-07 | Level 2 | Field Safety Reassessment
127550476 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127550489 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127550572 | pole | HFTD Tier 3 | Transmission | 2023-09-25 | 2024-03-25 | Level 2 | E | 2024-07-30 | 2024-03-25 | Level 2 | Field Safety Reassessment
127550614 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127550634 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127550637 | pole | Non-HFTD | Transmission | 2023-11-07 | 2026-11-07 | Level 2 | E |  | 2026-11-07 | Level 2
127550665 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127550751 | pole | Non-HFTD | Transmission | 2023-11-08 | 2026-11-08 | Level 2 | E |  | 2026-11-08 | Level 2
127550812 | pole | Non-HFTD | Transmission | 2023-11-09 | 2026-11-09 | Level 2 | E |  | 2026-11-09 | Level 2
127550817 | pole | Non-HFTD | Transmission | 2023-11-04 | 2026-11-04 | Level 2 | E | 2024-08-26 | 2026-11-04 | Level 2 | GO 165 Inspection
127551328 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E | 2024-12-09 | 2026-11-16 | Level 2 | GO 165 Inspection
127551545 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551575 | pole | HFTD Tier 2 | Transmission | 2023-11-02 | 2024-11-02 | Level 2 | E |  | 2024-11-02 | Level 2
127551576 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551584 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551621 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127551663 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127551682 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127551706 | pole | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551711 | other | Non-HFTD | Transmission | 2023-11-16 | 2024-11-16 | Level 2 | E | 2024-12-31 | 2024-11-16 | Level 2 | Field Safety Reassessment
127551742 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551783 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127551785 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551802 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E | 2024-09-27 | 2026-11-16 | Level 2 | GO 165 Inspection
127551803 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E | 2024-09-27 | 2026-11-16 | Level 2 | GO 165 Inspection
127551841 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127551849 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551864 | other | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E | 2024-09-28 | 2026-11-17 | Level 2 | GO 165 Inspection
127551877 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F | 2024-08-06 | 2028-11-16 | Level 3 | GO 165 Inspection
127551893 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E | 2024-11-08 | 2026-11-17 | Level 2 | GO 165 Inspection
127551897 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127551913 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127551926 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551939 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127551943 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551950 | insulator and brushing | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127551954 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127552028 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127552036 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-10-15 | 2028-11-17 | Level 3 | GO 165 Inspection
127552055 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127552064 | anchor/guy | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127552073 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127552094 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127552101 | other | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
127552104 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2024-11-17 | Level 2 | E |  | 2024-11-17 | Level 2
127552139 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-10-18 | 2028-11-17 | Level 3 | GO 165 Inspection
127553296 | other | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-10-08 | 2028-11-20 | Level 3 | GO 165 Inspection
127553393 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
127553405 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E | 2024-10-24 | 2026-11-16 | Level 2 | GO 165 Inspection
127553870 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127554531 | other | Non-HFTD | Transmission | 2023-11-16 | 2028-11-16 | Level 3 | F |  | 2028-11-16 | Level 3
127555477 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E | 2024-10-09 | 2026-11-17 | Level 2 | GO 165 Inspection
127566198 | pole | Non-HFTD | Transmission | 2023-11-28 | 2026-11-28 | Level 2 | E | 2024-10-17 | 2026-11-28 | Level 2 | GO 165 Inspection
127568451 | pole | Non-HFTD | Transmission | 2023-11-12 | 2026-11-12 | Level 2 | E | 2024-08-09 | 2026-11-12 | Level 2 | GO 165 Inspection
127568480 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-11-15 | 2028-11-17 | Level 3 | GO 165 Inspection
127568821 | other | HFTD Tier 2 | Transmission | 2023-12-12 | 2024-12-12 | Level 3 | F | 2024-04-18 | 2028-12-12 | Level 3 | GO 165 Inspection
127568850 | other | HFTD Tier 2 | Transmission | 2023-12-12 | 2024-12-12 | Level 3 | F | 2024-04-15 | 2028-12-12 | Level 3 | GO 165 Inspection
127569532 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127570498 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127570568 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127570612 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
127570661 | other | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-06-15 | 2028-11-01 | Level 3 | GO 165 Inspection
127570815 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127574692 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127574849 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127574919 | other | Non-HFTD | Transmission | 2023-11-17 | 2024-11-17 | Level 2 | E |  | 2024-11-17 | Level 2
127575593 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F | 2024-09-05 | 2028-11-18 | Level 3 | GO 165 Inspection
127575725 | insulator and brushing | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E | 2024-11-12 | 2026-11-17 | Level 2 | GO 165 Inspection
127576155 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F | 2024-08-15 | 2028-11-17 | Level 3 | GO 165 Inspection
127576470 | anchor/guy | HFTD Tier 2 | Transmission | 2023-12-13 | 2024-12-13 | Level 2 | E | 2024-05-03 | 2024-12-13 | Level 2 | GO 165 Inspection
127576618 | other | Non-HFTD | Transmission | 2023-11-17 | 2028-11-17 | Level 3 | F |  | 2028-11-17 | Level 3
127576814 | other | Non-HFTD | Transmission | 2023-12-13 | 2028-12-13 | Level 3 | F |  | 2028-12-13 | Level 3
127576989 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127577241 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127577314 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127577421 | pole | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F | 2024-08-02 | 2028-11-18 | Level 3 | GO 165 Inspection
127577440 | anchor/guy | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127577483 | anchor/guy | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127577486 | other | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127577978 | pole | Non-HFTD | Transmission | 2023-11-01 | 2026-11-01 | Level 2 | E | 2024-04-05 | 2026-11-01 | Level 2 | GO 165 Inspection
127578307 | other | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127578390 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E | 2024-09-04 | 2026-11-18 | Level 2 | GO 165 Inspection
127578480 | pole | Non-HFTD | Transmission | 2023-11-02 | 2026-11-02 | Level 2 | E |  | 2026-11-02 | Level 2
127578495 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127578570 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127578599 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127578721 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2024-11-18 | Level 3 | F | 2024-11-26 | 2028-11-18 | Level 3 | GO 165 Inspection
127578729 | insulator and brushing | Non-HFTD | Transmission | 2023-11-18 | 2028-11-18 | Level 3 | F |  | 2028-11-18 | Level 3
127579797 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127579798 | pole | HFTD Tier 3 | Transmission | 2023-12-14 | 2024-06-14 | Level 2 | E | 2024-06-11 | 2024-06-14 | Level 2 | Field Safety Reassessment
127579839 | anchor/guy | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127580248 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127580562 | other | Non-HFTD | Transmission | 2023-12-14 | 2026-12-14 | Level 2 | E |  | 2026-12-14 | Level 2
127580700 | pole | Non-HFTD | Transmission | 2023-11-18 | 2026-11-18 | Level 2 | E |  | 2026-11-18 | Level 2
127581547 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-10-02 | 2026-11-20 | Level 2 | GO 165 Inspection
127581562 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F |  | 2028-11-20 | Level 3
127581622 | pole | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127581686 | pole | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127583350 | other | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F |  | 2028-11-20 | Level 3
127583354 | anchor/guy | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E |  | 2026-11-20 | Level 2
127584440 | other | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-10-18 | 2028-11-20 | Level 3 | GO 165 Inspection
127584479 | other | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F |  | 2028-11-20 | Level 3
127588774 | splice | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
127588788 | insulator and brushing | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-08-21 | 2026-11-20 | Level 2 | GO 165 Inspection
127588984 | pole | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-10-17 | 2028-11-20 | Level 3 | GO 165 Inspection
127596690 | pole | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-10-17 | 2028-11-20 | Level 3 | GO 165 Inspection
127600204 | pole | Non-HFTD | Transmission | 2023-10-19 | 2026-10-19 | Level 2 | E | 2024-04-29 | 2026-10-19 | Level 2 | GO 165 Inspection
127601629 | insulator and brushing | Non-HFTD | Transmission | 2023-12-18 | 2024-12-18 | Level 2 | E | 2024-03-29 | 2024-12-18 | Level 2 | GO 165 Inspection
127603700 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E | 2024-09-17 | 2026-11-21 | Level 2 | GO 165 Inspection
127607062 | insulator and brushing | Non-HFTD | Transmission | 2023-12-18 | 2026-12-18 | Level 2 | E |  | 2026-12-18 | Level 2
127609932 | insulator and brushing | Non-HFTD | Transmission | 2023-12-18 | 2026-12-18 | Level 2 | E | 2024-12-23 | 2026-12-18 | Level 2 | Field Safety Reassessment
127609948 | pole | Non-HFTD | Transmission | 2023-12-18 | 2024-12-18 | Level 2 | E | 2024-05-30 | 2024-12-18 | Level 2 | Field Safety Reassessment
127616189 | pole | HFTD Tier 2 | Transmission | 2023-10-23 | 2024-10-23 | Level 2 | E | 2024-04-04 | 2024-10-23 | Level 2 | GO 165 Inspection
127624639 | other | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-09-17 | 2024-02-20 | Level 2 | GO 165 Inspection
127626562 | other | Non-HFTD | Transmission | 2023-11-20 | 2028-11-20 | Level 3 | F | 2024-08-08 | 2028-11-20 | Level 3 | GO 165 Inspection
127629503 | other | HFTD Tier 3 | Transmission | 2023-12-18 | 2024-06-18 | Level 3 | F | 2024-04-16 | 2028-06-18 | Level 3 | GO 165 Inspection
127641422 | other | Non-HFTD | Transmission | 2023-11-20 | 2026-11-20 | Level 2 | E | 2024-10-23 | 2026-11-20 | Level 2 | GO 165 Inspection
127654778 | pole | Non-HFTD | Transmission | 2023-12-18 | 2026-12-18 | Level 2 | E | 2024-07-31 | 2026-12-18 | Level 2 | GO 165 Inspection
127654846 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
127654877 | other | Non-HFTD | Transmission | 2023-11-21 | 2024-11-21 | Level 2 | E | 2024-05-30 | 2024-11-21 | Level 2 | Field Safety Reassessment
127657320 | pole | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F | 2024-10-31 | 2028-11-21 | Level 3 | GO 165 Inspection
127665112 | other | Non-HFTD | Transmission | 2023-06-05 | 2024-06-05 | Level 2 | E | 2024-10-15 | 2024-06-05 | Level 2 | GO 165 Inspection
127666499 | pole | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F |  | 2028-11-21 | Level 3
127666500 | other | Non-HFTD | Transmission | 2023-06-02 | 2028-06-02 | Level 3 | F |  | 2028-06-02 | Level 3
127667325 | other | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F |  | 2028-11-21 | Level 3
127672675 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E | 2024-09-11 | 2026-11-21 | Level 2 | GO 165 Inspection
127675044 | other | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F |  | 2028-11-21 | Level 3
127686033 | other | Non-HFTD | Transmission | 2023-12-19 | 2024-12-19 | Level 2 | E | 2024-11-08 | 2024-12-19 | Level 2 | GO 165 Inspection
127689700 | other | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F | 2024-08-30 | 2028-11-21 | Level 3 | GO 165 Inspection
127689702 | other | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F | 2024-08-30 | 2028-11-21 | Level 3 | GO 165 Inspection
127689708 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F |  | 2028-11-21 | Level 3
127689815 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2028-11-22 | Level 3 | F |  | 2028-11-22 | Level 3
127690051 | insulator and brushing | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F |  | 2028-11-21 | Level 3
127693073 | insulator and brushing | Non-HFTD | Transmission | 2023-12-19 | 2026-12-19 | Level 2 | E |  | 2026-12-19 | Level 2
127700717 | pole | Non-HFTD | Transmission | 2023-12-19 | 2026-12-19 | Level 2 | E |  | 2026-12-19 | Level 2
127708577 | other | Non-HFTD | Transmission | 2023-12-19 | 2026-12-19 | Level 2 | E |  | 2026-12-19 | Level 2
127708595 | other | Non-HFTD | Transmission | 2023-12-19 | 2026-12-19 | Level 2 | E |  | 2026-12-19 | Level 2
127709017 | pole | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F | 2024-09-10 | 2028-11-21 | Level 3 | GO 165 Inspection
127709109 | pole | Non-HFTD | Transmission | 2023-11-21 | 2028-11-21 | Level 3 | F |  | 2028-11-21 | Level 3
127709120 | other | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
127709174 | other | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E | 2024-08-21 | 2026-11-22 | Level 2 | GO 165 Inspection
127709177 | insulator and brushing | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E | 2024-08-21 | 2026-11-22 | Level 2 | GO 165 Inspection
127709305 | other | Non-HFTD | Transmission | 2023-11-22 | 2028-11-22 | Level 3 | F | 2024-10-30 | 2028-11-22 | Level 3 | GO 165 Inspection
127709542 | pole | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E | 2024-10-10 | 2026-11-22 | Level 2 | GO 165 Inspection
127709715 | pole | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E |  | 2026-11-22 | Level 2
127709897 | other | Non-HFTD | Transmission | 2023-11-27 | 2026-11-27 | Level 2 | E |  | 2026-11-27 | Level 2
127722145 | other | Non-HFTD | Transmission | 2023-12-20 | 2026-12-20 | Level 2 | E |  | 2026-12-20 | Level 2
127727500 | other | Non-HFTD | Transmission | 2023-11-22 | 2028-11-22 | Level 3 | F |  | 2028-11-22 | Level 3
127727925 | other | HFTD Tier 3 | Transmission | 2023-11-22 | 2028-11-22 | Level 3 | F |  | 2028-11-22 | Level 3
127728057 | other | Non-HFTD | Transmission | 2022-11-22 | 2024-11-22 | Level 3 | F | 2024-07-06 | 2027-11-22 | Level 3 | GO 165 Inspection
127728170 | other | HFTD Tier 2 | Transmission | 2023-12-20 | 2024-12-20 | Level 2 | E | 2024-04-19 | 2024-12-20 | Level 2 | GO 165 Inspection
127728447 | other | Non-HFTD | Transmission | 2023-12-20 | 2024-03-20 | Level 2 | E | 2024-03-01 | 2024-03-20 | Level 2 | Field Safety Reassessment
127730849 | anchor/guy | Non-HFTD | Transmission | 2023-12-19 | 2026-12-19 | Level 2 | E |  | 2026-12-19 | Level 2
127731745 | other | HFTD Tier 2 | Transmission | 2023-12-21 | 2028-12-21 | Level 3 | F | 2024-03-29 | 2028-12-21 | Level 3 | GO 165 Inspection
127731795 | other | HFTD Tier 2 | Transmission | 2023-12-21 | 2028-12-21 | Level 3 | F | 2024-03-12 | 2028-12-21 | Level 3 | GO 165 Inspection
127753635 | pole | Non-HFTD | Transmission | 2023-12-22 | 2028-12-22 | Level 3 | F |  | 2028-12-22 | Level 3
127826638 | other | Non-HFTD | Transmission | 2023-12-26 | 2028-12-26 | Level 3 | F |  | 2028-12-26 | Level 3
127831735 | pole | Non-HFTD | Transmission | 2023-11-15 | 2026-11-15 | Level 2 | E |  | 2026-11-15 | Level 2
127832282 | pole | HFTD Tier 3 | Transmission | 2023-12-28 | 2024-06-28 | Level 2 | E | 2024-06-11 | 2024-06-28 | Level 2 | Field Safety Reassessment
127832528 | other | HFTD Tier 2 | Transmission | 2023-12-28 | 2024-12-28 | Level 2 | E | 2024-04-19 | 2024-12-28 | Level 2 | GO 165 Inspection
127992006 | other | Non-HFTD | Transmission | 2023-11-29 | 2028-11-29 | Level 3 | F | 2024-09-12 | 2028-11-29 | Level 3 | GO 165 Inspection
127992052 | insulator and brushing | Non-HFTD | Transmission | 2023-11-30 | 2028-11-30 | Level 3 | F |  | 2028-11-30 | Level 3
127992224 | other | Non-HFTD | Transmission | 2023-11-08 | 2028-11-08 | Level 3 | F | 2024-10-01 | 2028-11-08 | Level 3 | GO 165 Inspection
127992299 | other | Non-HFTD | Transmission | 2023-12-01 | 2028-12-01 | Level 3 | F |  | 2028-12-01 | Level 3
127992919 | other | Non-HFTD | Transmission | 2023-12-20 | 2028-12-20 | Level 3 | F |  | 2028-12-20 | Level 3
127993933 | other | HFTD Tier 3 | Transmission | 2023-12-20 | 2028-12-20 | Level 3 | F | 2024-04-20 | 2028-12-20 | Level 3 | GO 165 Inspection
127994365 | other | Non-HFTD | Transmission | 2024-01-02 | 2027-01-02 | Level 2 | E |  | 2027-01-02 | Level 2
127994424 | other | HFTD Tier 2 | Transmission | 2024-01-02 | 2025-01-02 | Level 3 | F | 2024-06-05 | 2029-01-02 | Level 3 | GO 165 Inspection
127994580 | other | HFTD Tier 2 | Transmission | 2024-01-02 | 2029-01-02 | Level 3 | F | 2024-05-17 | 2029-01-02 | Level 3 | GO 165 Inspection
127994598 | other | HFTD Tier 2 | Transmission | 2024-01-02 | 2029-01-02 | Level 3 | F | 2024-04-22 | 2029-01-02 | Level 3 | GO 165 Inspection
127997643 | other | Non-HFTD | Transmission | 2024-01-03 | 2029-01-03 | Level 3 | F |  | 2029-01-03 | Level 3
127998806 | other | HFTD Tier 2 | Transmission | 2024-01-03 | 2025-01-03 | Level 2 | E |  | 2025-01-03 | Level 2
127999953 | other | HFTD Tier 2 | Transmission | 2024-01-04 | 2029-01-04 | Level 3 | F | 2024-03-29 | 2029-01-04 | Level 3 | GO 165 Inspection
128000012 | other | Non-HFTD | Transmission | 2024-01-04 | 2027-01-04 | Level 3 | F |  | 2029-01-04 | Level 3
128000107 | other | HFTD Tier 2 | Transmission | 2024-01-04 | 2029-01-04 | Level 3 | F | 2024-03-12 | 2029-01-04 | Level 3 | GO 165 Inspection
128004814 | other | Non-HFTD | Transmission | 2024-01-04 | 2029-01-04 | Level 2 | E |  | 2027-01-04 | Level 2
128008600 | other | HFTD Tier 3 | Transmission | 2024-01-06 | 2024-07-06 | Level 3 | F |  | 2029-01-06 | Level 3
128008759 | other | Non-HFTD | Transmission | 2024-01-06 | 2027-01-06 | Level 3 | F |  | 2029-01-06 | Level 3
128008771 | other | Non-HFTD | Transmission | 2024-01-06 | 2027-01-06 | Level 3 | F |  | 2029-01-06 | Level 3
128009488 | pole | Non-HFTD | Transmission | 2023-11-13 | 2026-11-13 | Level 2 | E |  | 2026-11-13 | Level 2
128009546 | pole | Non-HFTD | Transmission | 2023-12-05 | 2026-12-05 | Level 2 | E |  | 2026-12-05 | Level 2
128009805 | pole | Non-HFTD | Transmission | 2023-11-16 | 2026-11-16 | Level 2 | E |  | 2026-11-16 | Level 2
128010174 | pole | Non-HFTD | Transmission | 2023-12-05 | 2026-12-05 | Level 2 | E |  | 2026-12-05 | Level 2
128010179 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E | 2024-08-07 | 2026-11-21 | Level 2 | GO 165 Inspection
128010311 | pole | Non-HFTD | Transmission | 2023-11-28 | 2026-11-28 | Level 2 | E |  | 2026-11-28 | Level 2
128010312 | pole | Non-HFTD | Transmission | 2023-11-22 | 2026-11-22 | Level 2 | E |  | 2026-11-22 | Level 2
128010375 | anchor/guy | Non-HFTD | Transmission | 2024-01-08 | 2024-07-08 | Level 2 | E | 2024-12-04 | 2024-04-08 | Level 2 | Field Safety Reassessment
128010847 | pole | Non-HFTD | Transmission | 2023-11-28 | 2026-11-28 | Level 2 | E |  | 2026-11-28 | Level 2
128011273 | pole | Non-HFTD | Transmission | 2024-01-08 | 2029-01-08 | Level 3 | F |  | 2029-01-08 | Level 3
128011332 | pole | Non-HFTD | Transmission | 2023-12-05 | 2026-12-05 | Level 2 | E |  | 2026-12-05 | Level 2
128011338 | pole | Non-HFTD | Transmission | 2023-11-17 | 2026-11-17 | Level 2 | E |  | 2026-11-17 | Level 2
128011365 | pole | Non-HFTD | Transmission | 2024-01-08 | 2029-01-08 | Level 3 | F |  | 2029-01-08 | Level 3
128011411 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E |  | 2026-11-21 | Level 2
128011416 | pole | Non-HFTD | Transmission | 2023-12-05 | 2026-12-05 | Level 2 | E |  | 2026-12-05 | Level 2
128011867 | pole | Non-HFTD | Transmission | 2024-01-08 | 2029-01-08 | Level 3 | F |  | 2029-01-08 | Level 3
128011880 | pole | Non-HFTD | Transmission | 2024-01-08 | 2029-01-08 | Level 3 | F |  | 2029-01-08 | Level 3
128011886 | pole | Non-HFTD | Transmission | 2024-01-08 | 2029-01-08 | Level 3 | F | 2024-05-15 | 2029-01-08 | Level 3 | GO 165 Inspection
128011902 | pole | Non-HFTD | Transmission | 2023-11-21 | 2026-11-21 | Level 2 | E | 2024-08-07 | 2026-11-21 | Level 2 | GO 165 Inspection
128011904 | pole | Non-HFTD | Transmission | 2023-12-05 | 2026-12-05 | Level 2 | E |  | 2026-12-05 | Level 2
128012066 | pole | Non-HFTD | Transmission | 2023-12-05 | 2026-12-05 | Level 2 | E |  | 2026-12-05 | Level 2
128012380 | pole | Non-HFTD | Transmission | 2023-11-14 | 2026-11-14 | Level 2 | E |  | 2026-11-14 | Level 2
128012439 | pole | Non-HFTD | Transmission | 2023-11-27 | 2026-11-27 | Level 2 | E |  | 2026-11-27 | Level 2
128012514 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-08-14 | 2026-11-06 | Level 2 | GO 165 Inspection
128013736 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-07-19 | 2026-11-06 | Level 2 | GO 165 Inspection
128013738 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-07-22 | 2026-11-06 | Level 2 | GO 165 Inspection
128013870 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-08-26 | 2026-11-06 | Level 2 | GO 165 Inspection
128014812 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-08-05 | 2026-11-06 | Level 2 | GO 165 Inspection
128014813 | pole | Non-HFTD | Transmission | 2023-11-06 | 2026-11-06 | Level 2 | E | 2024-08-06 | 2026-11-06 | Level 2 | GO 165 Inspection
128014865 | pole | Non-HFTD | Transmission | 2023-11-28 | 2026-11-28 | Level 2 | E |  | 2026-11-28 | Level 2
128015626 | other | HFTD Tier 3 | Transmission | 2024-01-09 | 2029-01-09 | Level 3 | F |  | 2029-01-09 | Level 3
128026409 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E | 2024-08-30 | 2025-01-07 | Level 2 | GO 165 Inspection
128026574 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E | 2024-08-29 | 2025-01-07 | Level 2 | GO 165 Inspection
128026590 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E | 2024-08-23 | 2025-01-07 | Level 2 | GO 165 Inspection
128026664 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E |  | 2025-01-07 | Level 2
128026832 | other | Non-HFTD | Transmission | 2024-01-10 | 2029-01-10 | Level 3 | F | 2024-10-24 | 2029-01-10 | Level 3 | GO 165 Inspection
128027615 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E |  | 2025-01-07 | Level 2
128027662 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E |  | 2025-01-07 | Level 2
128027937 | other | HFTD Tier 3 | Transmission | 2024-01-10 | 2029-01-10 | Level 3 | F |  | 2029-01-10 | Level 3
128027985 | other | HFTD Tier 3 | Transmission | 2024-01-10 | 2029-01-10 | Level 3 | F |  | 2029-01-10 | Level 3
128028042 | other | HFTD Tier 2 | Transmission | 2024-01-10 | 2025-01-10 | Level 3 | F | 2024-04-10 | 2029-01-10 | Level 3 | GO 165 Inspection
128028050 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-07 | Level 2 | E |  | 2025-01-07 | Level 2
128030119 | insulator and brushing | Non-HFTD | Transmission | 2024-01-11 | 2027-01-11 | Level 2 | E | 2024-09-05 | 2027-01-11 | Level 2 | GO 165 Inspection
128030430 | pole | HFTD Tier 2 | Transmission | 2024-01-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
128035667 | other | HFTD Tier 3 | Transmission | 2024-01-12 | 2024-07-12 | Level 2 | E | 2024-03-27 | 2024-07-12 | Level 2 | GO 165 Inspection
128037679 | anchor/guy | Non-HFTD | Transmission | 2024-01-12 | 2027-01-12 | Level 2 | E | 2024-09-05 | 2027-01-12 | Level 2 | GO 165 Inspection
128049421 | other | Non-HFTD | Transmission | 2024-01-17 | 2027-01-17 | Level 2 | E | 2024-06-17 | 2027-01-17 | Level 2 | GO 165 Inspection
128049802 | other | HFTD Tier 2 | Transmission | 2024-01-17 | 2025-01-17 | Level 2 | E | 2024-06-01 | 2025-01-17 | Level 2 | GO 165 Inspection
128063366 | other | Non-HFTD | Transmission | 2024-01-18 | 2029-01-18 | Level 3 | F |  | 2029-01-18 | Level 3
128070482 | other | Non-HFTD | Transmission | 2024-01-22 | 2027-01-22 | Level 3 | F |  | 2029-01-22 | Level 3
128070864 | pole | Non-HFTD | Transmission | 2024-01-22 | 2029-01-22 | Level 3 | F | 2024-09-03 | 2029-01-22 | Level 3 | GO 165 Inspection
128071199 | crossarm | HFTD Tier 2 | Transmission | 2024-01-22 | 2025-01-22 | Level 2 | E | 2024-03-28 | 2025-01-22 | Level 2 | GO 165 Inspection
128079020 | other | HFTD Tier 2 | Transmission | 2024-01-23 | 2029-01-23 | Level 3 | F | 2024-04-01 | 2029-01-23 | Level 3 | GO 165 Inspection
128080808 | anchor/guy | HFTD Tier 2 | Transmission | 2024-01-24 | 2024-04-24 | Level 2 | E | 2024-04-01 | 2025-01-24 | Level 2 | GO 165 Inspection
128082808 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-01-25 | 2029-01-25 | Level 3 | F |  | 2029-01-25 | Level 3
128084237 | other | HFTD Tier 3 | Transmission | 2024-01-25 | 2024-07-25 | Level 2 | E | 2024-05-16 | 2024-07-25 | Level 2 | GO 165 Inspection
128084633 | other | HFTD Tier 2 | Transmission | 2024-01-25 | 2029-01-25 | Level 3 | F | 2024-04-06 | 2029-01-25 | Level 3 | GO 165 Inspection
128084674 | other | HFTD Tier 2 | Transmission | 2024-01-25 | 2025-01-25 | Level 3 | F | 2024-05-07 | 2029-01-25 | Level 3 | GO 165 Inspection
128084738 | other | HFTD Tier 2 | Transmission | 2024-01-25 | 2029-01-25 | Level 3 | F | 2024-04-12 | 2029-01-25 | Level 3 | GO 165 Inspection
128084793 | other | HFTD Tier 2 | Transmission | 2024-01-25 | 2025-01-25 | Level 3 | F | 2024-04-12 | 2029-01-25 | Level 3 | GO 165 Inspection
128089368 | other | HFTD Tier 2 | Transmission | 2024-01-27 | 2029-01-27 | Level 3 | F | 2024-04-11 | 2029-01-27 | Level 3 | GO 165 Inspection
128089370 | other | HFTD Tier 2 | Transmission | 2024-01-27 | 2029-01-27 | Level 3 | F | 2024-04-01 | 2029-01-27 | Level 3 | GO 165 Inspection
128096405 | other | Non-HFTD | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F | 2024-10-01 | 2029-01-29 | Level 3 | GO 165 Inspection
128096634 | other | Non-HFTD | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F |  | 2029-01-29 | Level 3
128097488 | anchor/guy | Non-HFTD | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F |  | 2029-01-29 | Level 3
128097743 | other | HFTD Tier 3 | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F |  | 2029-01-29 | Level 3
128097884 | other | HFTD Tier 2 | Transmission | 2024-01-29 | 2025-01-29 | Level 2 | E | 2024-04-25 | 2025-01-29 | Level 2 | GO 165 Inspection
128099223 | other | HFTD Tier 2 | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E | 2024-03-27 | 2025-01-30 | Level 2 | GO 165 Inspection
128103564 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E |  | 2025-01-30 | Level 2
128103867 | pole | Non-HFTD | Transmission | 2024-01-30 | 2027-01-30 | Level 2 | E |  | 2027-01-30 | Level 2
128103958 | anchor/guy | HFTD Tier 2 | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E |  | 2025-01-30 | Level 2
128104297 | anchor/guy | Non-HFTD | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E | 2024-05-30 | 2025-01-30 | Level 2 | GO 165 Inspection
128113234 | pole | Non-HFTD | Transmission | 2024-01-30 | 2027-01-30 | Level 2 | E |  | 2027-01-30 | Level 2
128113369 | other | Non-HFTD | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128113490 | pole | HFTD Tier 2 | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E |  | 2025-01-30 | Level 2
128113556 | other | Non-HFTD | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F | 2024-03-27 | 2029-01-30 | Level 3 | GO 165 Inspection
128114558 | pole | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128115694 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-01-31 | 2025-01-31 | Level 2 | E |  | 2025-01-31 | Level 2
128116255 | other | HFTD Tier 2 | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128116895 | other | HFTD Tier 2 | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F | 2024-04-15 | 2029-01-31 | Level 3 | GO 165 Inspection
128116968 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128116983 | other | HFTD Tier 2 | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128117019 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128117119 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128117144 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128117145 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128117156 | other | HFTD Tier 2 | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128119046 | pole | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E | 2024-08-30 | 2027-02-01 | Level 2 | GO 165 Inspection
128119119 | switch | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128119232 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F | 2024-07-22 | 2029-02-01 | Level 3 | GO 165 Inspection
128120253 | pole | HFTD Tier 2 | Transmission | 2024-02-01 | 2025-02-01 | Level 2 | E |  | 2025-02-01 | Level 2
128120872 | pole | HFTD Tier 2 | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128121311 | other | HFTD Tier 2 | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F | 2024-03-21 | 2029-01-29 | Level 3 | GO 165 Inspection
128124216 | anchor/guy | HFTD Tier 2 | Transmission | 2024-01-29 | 2025-01-29 | Level 2 | E |  | 2025-01-29 | Level 2
128124486 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-02 | 2029-02-02 | Level 3 | F |  | 2029-02-02 | Level 3
128125549 | anchor/guy | HFTD Tier 2 | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E |  | 2025-01-30 | Level 2
128127398 | other | HFTD Tier 2 | Transmission | 2024-02-03 | 2029-02-03 | Level 3 | F |  | 2029-02-03 | Level 3
128127450 | other | HFTD Tier 2 | Transmission | 2024-02-03 | 2025-02-03 | Level 3 | F |  | 2029-02-03 | Level 3
128127513 | other | Non-HFTD | Transmission | 2024-02-03 | 2029-02-03 | Level 3 | F |  | 2029-02-03 | Level 3
128130063 | other | Non-HFTD | Transmission | 2024-02-05 | 2029-02-05 | Level 3 | F |  | 2029-02-05 | Level 3
128130069 | other | Non-HFTD | Transmission | 2024-02-05 | 2029-02-05 | Level 3 | F |  | 2029-02-05 | Level 3
128130179 | other | HFTD Tier 2 | Transmission | 2024-02-05 | 2029-02-05 | Level 3 | F | 2024-04-06 | 2029-02-05 | Level 3 | GO 165 Inspection
128130243 | other | HFTD Tier 2 | Transmission | 2024-01-25 | 2025-01-25 | Level 3 | F | 2024-05-07 | 2029-01-25 | Level 3 | GO 165 Inspection
128133494 | other | HFTD Tier 3 | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F |  | 2029-01-29 | Level 3
128137583 | other | HFTD Tier 2 | Transmission | 2024-02-06 | 2025-02-06 | Level 2 | E |  | 2025-02-06 | Level 2
128138025 | anchor/guy | HFTD Tier 2 | Transmission | 2024-01-29 | 2025-01-29 | Level 2 | E |  | 2025-01-29 | Level 2
128141744 | other | HFTD Tier 2 | Transmission | 2024-01-25 | 2025-01-25 | Level 2 | E |  | 2025-01-25 | Level 2
128141777 | other | Non-HFTD | Transmission | 2024-02-07 | 2029-02-07 | Level 3 | F |  | 2029-02-07 | Level 3
128142667 | other | HFTD Tier 2 | Transmission | 2024-01-29 | 2025-01-29 | Level 2 | E |  | 2025-01-29 | Level 2
128142668 | other | HFTD Tier 2 | Transmission | 2024-01-29 | 2025-01-29 | Level 2 | E |  | 2025-01-29 | Level 2
128142910 | other | HFTD Tier 2 | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128142955 | other | HFTD Tier 2 | Transmission | 2024-01-29 | 2029-01-29 | Level 3 | F |  | 2029-01-29 | Level 3
128143227 | pole | HFTD Tier 2 | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128143251 | pole | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128143253 | anchor/guy | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E | 2024-10-18 | 2027-02-01 | Level 2 | GO 165 Inspection
128143255 | pole | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128143428 | other | HFTD Tier 3 | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128144322 | other | HFTD Tier 2 | Transmission | 2024-02-08 | 2025-02-08 | Level 2 | E | 2024-03-22 | 2025-02-08 | Level 2 | GO 165 Inspection
128145203 | other | Non-HFTD | Transmission | 2024-02-08 | 2027-02-08 | Level 2 | E |  | 2027-02-08 | Level 2
128146129 | anchor/guy | Non-HFTD | Transmission | 2024-02-08 | 2027-02-08 | Level 2 | E | 2024-07-26 | 2027-02-08 | Level 2 | GO 165 Inspection
128146708 | anchor/guy | Non-HFTD | Transmission | 2024-02-08 | 2029-02-08 | Level 3 | F |  | 2029-02-08 | Level 3
128148110 | other | HFTD Tier 3 | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128148385 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-01-30 | 2025-01-30 | Level 2 | E |  | 2025-01-30 | Level 2
128148387 | other | HFTD Tier 2 | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128149614 | pole | HFTD Tier 2 | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F | 2024-04-03 | 2029-02-01 | Level 3 | GO 165 Inspection
128149617 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F | 2024-10-09 | 2029-02-01 | Level 3 | GO 165 Inspection
128149671 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F | 2024-03-20 | 2029-01-31 | Level 3 | GO 165 Inspection
128149679 | other | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128149726 | insulator and brushing | Non-HFTD | Transmission | 2024-01-30 | 2027-01-30 | Level 2 | E |  | 2027-01-30 | Level 2
128149822 | pole | Non-HFTD | Transmission | 2024-01-30 | 2027-01-30 | Level 2 | E |  | 2027-01-30 | Level 2
128149823 | insulator and brushing | Non-HFTD | Transmission | 2024-01-30 | 2027-01-30 | Level 2 | E |  | 2027-01-30 | Level 2
128150064 | other | Non-HFTD | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128150429 | other | HFTD Tier 2 | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128150509 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128150557 | other | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128150743 | other | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128150836 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128150871 | other | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128150873 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128150876 | other | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128150984 | anchor/guy | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128151278 | insulator and brushing | Non-HFTD | Transmission | 2024-01-30 | 2027-01-30 | Level 2 | E |  | 2027-01-30 | Level 2
128151434 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128151442 | other | Non-HFTD | Transmission | 2024-01-31 | 2027-01-31 | Level 2 | E |  | 2027-01-31 | Level 2
128151564 | other | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128151630 | pole | Non-HFTD | Transmission | 2024-01-30 | 2029-01-30 | Level 3 | F |  | 2029-01-30 | Level 3
128151714 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128151733 | insulator and brushing | Non-HFTD | Transmission | 2024-01-01 | 2027-01-01 | Level 2 | E | 2024-06-20 | 2027-01-01 | Level 2 | GO 165 Inspection
128152377 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128152798 | other | Non-HFTD | Transmission | 2024-02-07 | 2029-02-07 | Level 3 | F |  | 2029-02-07 | Level 3
128152851 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128152924 | anchor/guy | Non-HFTD | Transmission | 2024-02-01 | 2024-08-01 | Level 2 | E | 2024-07-24 | 2024-08-01 | Level 2 | Field Safety Reassessment
128152928 | pole | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162430 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128162433 | other | Non-HFTD | Transmission | 2024-02-07 | 2027-02-07 | Level 2 | E | 2024-06-24 | 2025-02-07 | Level 2 | GO 165 Inspection
128162434 | other | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162440 | pole | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F | 2024-08-01 | 2029-01-31 | Level 3 | GO 165 Inspection
128162455 | insulator and brushing | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162462 | crossarm | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162467 | other | HFTD Tier 2 | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128162487 | pole | HFTD Tier 2 | Transmission | 2023-04-28 | 2028-04-28 | Level 3 | F | 2024-05-18 | 2028-04-28 | Level 3 | GO 165 Inspection
128162497 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F |  | 2029-02-01 | Level 3
128162498 | other | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F | 2024-06-12 | 2029-02-01 | Level 3 | GO 165 Inspection
128162507 | other | Non-HFTD | Transmission | 2024-02-07 | 2027-02-07 | Level 2 | E |  | 2027-02-07 | Level 2
128162521 | insulator and brushing | Non-HFTD | Transmission | 2024-02-07 | 2027-02-07 | Level 2 | E |  | 2027-02-07 | Level 2
128162522 | other | Non-HFTD | Transmission | 2024-02-07 | 2027-02-07 | Level 2 | E |  | 2027-02-07 | Level 2
128162545 | other | Non-HFTD | Transmission | 2024-02-07 | 2029-02-07 | Level 3 | F |  | 2029-02-07 | Level 3
128162553 | conductor | Non-HFTD | Transmission | 2024-02-01 | 2025-02-01 | Level 2 | E |  | 2025-02-01 | Level 2
128162559 | other | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162574 | pole | Non-HFTD | Transmission | 2023-07-20 | 2026-07-20 | Level 2 | E |  | 2026-07-20 | Level 2
128162579 | other | Non-HFTD | Transmission | 2024-01-31 | 2029-01-31 | Level 3 | F |  | 2029-01-31 | Level 3
128162591 | pole | Non-HFTD | Transmission | 2023-07-29 | 2026-07-29 | Level 2 | E |  | 2026-07-29 | Level 2
128162604 | anchor/guy | Non-HFTD | Transmission | 2024-02-01 | 2029-02-01 | Level 3 | F | 2024-06-12 | 2029-02-01 | Level 3 | GO 165 Inspection
128162624 | other | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162625 | insulator and brushing | Non-HFTD | Transmission | 2024-02-01 | 2027-02-01 | Level 2 | E |  | 2027-02-01 | Level 2
128162935 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128162941 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F | 2024-03-15 | 2029-02-10 | Level 3 | GO 165 Inspection
128162965 | other | Non-HFTD | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128162985 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128163006 | other | Non-HFTD | Transmission | 2024-02-10 | 2027-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128163007 | other | Non-HFTD | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128163012 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F | 2024-05-07 | 2029-02-10 | Level 3 | GO 165 Inspection
128163013 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F | 2024-05-07 | 2029-02-10 | Level 3 | GO 165 Inspection
128163025 | other | Non-HFTD | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128163035 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2025-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128163040 | other | HFTD Tier 2 | Transmission | 2024-02-10 | 2029-02-10 | Level 3 | F |  | 2029-02-10 | Level 3
128163057 | other | Non-HFTD | Transmission | 2024-02-10 | 2027-02-10 | Level 2 | E |  | 2027-02-10 | Level 2
128166391 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-12 | 2025-02-12 | Level 2 | E |  | 2025-02-12 | Level 2
128166392 | other | HFTD Tier 2 | Transmission | 2024-02-12 | 2029-02-12 | Level 3 | F |  | 2029-02-12 | Level 3
128166411 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-12 | 2025-02-12 | Level 2 | E |  | 2025-02-12 | Level 2
128166493 | other | Non-HFTD | Transmission | 2024-02-12 | 2029-02-12 | Level 3 | F |  | 2029-02-12 | Level 3
128167090 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-12 | 2025-02-12 | Level 2 | E |  | 2025-02-12 | Level 2
128167349 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-12 | 2025-02-12 | Level 2 | E |  | 2025-02-12 | Level 2
128169046 | other | Non-HFTD | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F |  | 2029-02-13 | Level 3
128169495 | pole | HFTD Tier 2 | Transmission | 2023-07-21 | 2024-07-21 | Level 3 | F |  | 2028-07-21 | Level 3
128169994 | other | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 3 | F |  | 2029-02-13 | Level 3
128170344 | other | Non-HFTD | Transmission | 2022-07-21 | 2027-07-21 | Level 3 | F |  | 2027-07-21 | Level 3
128170531 | other | Non-HFTD | Transmission | 2022-07-21 | 2027-07-21 | Level 3 | F |  | 2027-07-21 | Level 3
128170538 | pole | HFTD Tier 2 | Transmission | 2023-07-22 | 2024-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
128170693 | pole | HFTD Tier 2 | Transmission | 2023-07-22 | 2024-07-22 | Level 2 | E | 2024-05-14 | 2024-07-22 | Level 2 | GO 165 Inspection
128170747 | pole | HFTD Tier 2 | Transmission | 2023-07-22 | 2023-07-22 | Level 3 | F |  | 2028-07-22 | Level 3
128170811 | pole | Non-HFTD | Transmission | 2023-07-24 | 2024-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
128170813 | pole | HFTD Tier 2 | Transmission | 2023-07-24 | 2024-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
128170952 | pole | Non-HFTD | Transmission | 2023-07-24 | 2024-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
128170956 | pole | Non-HFTD | Transmission | 2023-07-24 | 2024-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
128170981 | pole | Non-HFTD | Transmission | 2023-08-07 | 2026-08-07 | Level 2 | E | 2024-08-29 | 2026-08-07 | Level 2 | GO 165 Inspection
128171022 | pole | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
128171024 | pole | Non-HFTD | Transmission | 2023-07-28 | 2024-07-28 | Level 3 | F |  | 2028-07-24 | Level 3
128171031 | pole | HFTD Tier 2 | Transmission | 2023-07-24 | 2024-07-24 | Level 2 | E |  | 2024-07-24 | Level 2
128171060 | pole | Non-HFTD | Transmission | 2023-07-28 | 2028-07-28 | Level 3 | F |  | 2028-07-28 | Level 3
128171066 | pole | Non-HFTD | Transmission | 2023-07-27 | 2024-07-27 | Level 3 | F |  | 2028-07-24 | Level 3
128171106 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
128171107 | pole | Non-HFTD | Transmission | 2023-07-28 | 2026-07-28 | Level 2 | E |  | 2026-07-28 | Level 2
128171116 | other | Non-HFTD | Transmission | 2023-08-08 | 2028-08-08 | Level 3 | F | 2024-10-08 | 2028-08-08 | Level 3 | GO 165 Inspection
128171132 | pole | Non-HFTD | Transmission | 2023-07-24 | 2028-07-24 | Level 3 | F |  | 2028-07-24 | Level 3
128171137 | pole | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
128171156 | pole | Non-HFTD | Transmission | 2023-07-25 | 2026-07-25 | Level 2 | E |  | 2026-07-25 | Level 2
128171158 | pole | Non-HFTD | Transmission | 2023-07-25 | 2028-07-25 | Level 3 | F |  | 2028-07-25 | Level 3
128171175 | other | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F |  | 2028-07-27 | Level 3
128171178 | pole | Non-HFTD | Transmission | 2023-07-27 | 2028-07-27 | Level 3 | F | 2024-07-18 | 2028-07-27 | Level 3 | GO 165 Inspection
128171233 | pole | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
128171234 | pole | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
128171252 | pole | Non-HFTD | Transmission | 2023-07-26 | 2026-07-26 | Level 2 | E |  | 2026-07-26 | Level 2
128171257 | pole | Non-HFTD | Transmission | 2023-07-26 | 2028-07-26 | Level 3 | F |  | 2028-07-26 | Level 3
128171281 | pole | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F | 2024-11-01 | 2028-08-11 | Level 3 | GO 165 Inspection
128171284 | other | Non-HFTD | Transmission | 2023-08-11 | 2028-08-11 | Level 3 | F | 2024-12-02 | 2028-08-11 | Level 3 | GO 165 Inspection
128171300 | pole | Non-HFTD | Transmission | 2023-10-06 | 2026-10-06 | Level 2 | E |  | 2026-10-06 | Level 2
128171310 | pole | Non-HFTD | Transmission | 2023-08-10 | 2028-08-10 | Level 3 | F | 2024-10-31 | 2028-08-10 | Level 3 | GO 165 Inspection
128171589 | pole | Non-HFTD | Transmission | 2023-07-31 | 2024-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
128171591 | pole | Non-HFTD | Transmission | 2023-07-31 | 2024-07-31 | Level 3 | F |  | 2028-07-31 | Level 3
128171596 | pole | Non-HFTD | Transmission | 2023-08-01 | 2026-08-01 | Level 2 | E |  | 2026-08-01 | Level 2
128171611 | pole | Non-HFTD | Transmission | 2023-10-06 | 2024-10-06 | Level 2 | E |  | 2024-10-06 | Level 2
128171612 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
128171614 | other | Non-HFTD | Transmission | 2023-10-06 | 2028-10-06 | Level 3 | F |  | 2028-10-06 | Level 3
128171718 | other | Non-HFTD | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128171790 | other | Non-HFTD | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128172499 | other | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128172805 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128173557 | pole | Non-HFTD | Transmission | 2023-08-01 | 2024-08-01 | Level 3 | F |  | 2028-08-01 | Level 3
128173559 | pole | Non-HFTD | Transmission | 2023-08-01 | 2024-08-01 | Level 3 | F | 2024-08-30 | 2028-08-01 | Level 3 | GO 165 Inspection
128173634 | other | HFTD Tier 3 | Transmission | 2024-02-14 | 2024-08-14 | Level 2 | E |  | 2024-08-14 | Level 2
128173759 | other | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128173883 | other | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128173916 | other | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128173944 | other | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128174054 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
128174369 | pole | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128174523 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128174763 | pole | HFTD Tier 2 | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F |  | 2029-02-13 | Level 3
128176811 | pole | Non-HFTD | Transmission | 2023-10-11 | 2024-10-11 | Level 2 | E |  | 2026-10-11 | Level 2
128176818 | other | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F | 2024-04-24 | 2028-10-12 | Level 3 | GO 165 Inspection
128183433 | other | Non-HFTD | Transmission | 2023-10-13 | 2028-10-13 | Level 3 | F | 2024-10-29 | 2028-10-13 | Level 3 | GO 165 Inspection
128183756 | other | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
128183771 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
128183927 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
128184266 | other | HFTD Tier 2 | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F |  | 2029-02-13 | Level 3
128185425 | pole | HFTD Tier 2 | Transmission | 2024-02-15 | 2029-02-15 | Level 3 | F |  | 2029-02-15 | Level 3
128186495 | insulator and brushing | Non-HFTD | Transmission | 2024-02-15 | 2029-02-15 | Level 3 | F | 2024-03-19 | 2029-02-15 | Level 3 | GO 165 Inspection
128186737 | other | HFTD Tier 2 | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F |  | 2029-02-13 | Level 3
128186753 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F | 2024-09-27 | 2028-08-02 | Level 3 | GO 165 Inspection
128186755 | pole | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F | 2024-09-18 | 2028-08-02 | Level 3 | GO 165 Inspection
128186799 | pole | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
128186822 | pole | Non-HFTD | Transmission | 2023-08-03 | 2024-08-03 | Level 3 | F | 2024-10-28 | 2028-08-03 | Level 3 | GO 165 Inspection
128186856 | other | Non-HFTD | Transmission | 2023-10-17 | 2028-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
128186857 | pole | Non-HFTD | Transmission | 2023-10-17 | 2024-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
128186859 | pole | Non-HFTD | Transmission | 2023-10-17 | 2024-10-17 | Level 3 | F |  | 2028-10-17 | Level 3
128186868 | pole | Non-HFTD | Transmission | 2023-08-04 | 2024-08-04 | Level 3 | F | 2024-09-12 | 2028-08-04 | Level 3 | GO 165 Inspection
128186869 | other | Non-HFTD | Transmission | 2023-08-04 | 2028-08-04 | Level 3 | F | 2024-09-12 | 2028-08-04 | Level 3 | GO 165 Inspection
128186874 | other | HFTD Tier 2 | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F |  | 2029-02-13 | Level 3
128186886 | conductor | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
128186900 | pole | Non-HFTD | Transmission | 2023-08-05 | 2024-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
128186903 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
128186910 | pole | Non-HFTD | Transmission | 2023-10-18 | 2024-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
128186924 | other | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128186968 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-13 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
128186971 | pole | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128188336 | pole | Non-HFTD | Transmission | 2023-10-18 | 2024-10-18 | Level 2 | E |  | 2024-10-18 | Level 2
128188392 | pole | Non-HFTD | Transmission | 2023-10-18 | 2024-10-18 | Level 3 | F |  | 2028-10-18 | Level 3
128188482 | anchor/guy | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E | 2024-11-01 | 2027-02-13 | Level 2 | GO 165 Inspection
128188550 | other | HFTD Tier 3 | Transmission | 2023-10-19 | 2028-10-19 | Level 3 | F |  | 2028-10-19 | Level 3
128188559 | other | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E | 2024-11-01 | 2027-02-13 | Level 2 | GO 165 Inspection
128188593 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128188717 | pole | Non-HFTD | Transmission | 2023-10-20 | 2024-10-20 | Level 3 | F |  | 2028-10-20 | Level 3
128188816 | other | Non-HFTD | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F | 2024-06-27 | 2029-02-13 | Level 3 | GO 165 Inspection
128189115 | pole | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128189222 | other | Non-HFTD | Transmission | 2023-10-21 | 2028-10-21 | Level 3 | F |  | 2028-10-21 | Level 3
128189360 | other | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E | 2024-06-27 | 2027-02-13 | Level 2 | GO 165 Inspection
128189522 | pole | Non-HFTD | Transmission | 2023-10-12 | 2028-10-12 | Level 3 | F |  | 2028-10-12 | Level 3
128189538 | pole | Non-HFTD | Transmission | 2024-02-16 | 2029-02-16 | Level 2 | E | 2024-10-29 | 2027-02-16 | Level 2 | GO 165 Inspection
128189544 | pole | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E |  | 2027-02-13 | Level 2
128189545 | other | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E |  | 2027-02-13 | Level 2
128189614 | pole | Non-HFTD | Transmission | 2023-10-14 | 2028-10-14 | Level 3 | F | 2024-05-02 | 2028-10-14 | Level 3 | GO 165 Inspection
128189650 | other | Non-HFTD | Transmission | 2024-02-07 | 2029-02-07 | Level 3 | F | 2024-10-30 | 2029-02-07 | Level 3 | GO 165 Inspection
128189692 | pole | Non-HFTD | Transmission | 2024-02-16 | 2027-02-16 | Level 2 | E | 2024-08-16 | 2027-02-16 | Level 2 | GO 165 Inspection
128189761 | pole | Non-HFTD | Transmission | 2023-10-23 | 2028-10-23 | Level 3 | F | 2024-09-05 | 2028-10-23 | Level 3 | GO 165 Inspection
128190101 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128190193 | other | Non-HFTD | Transmission | 2024-02-16 | 2024-05-16 | Level 2 | E | 2024-11-20 | 2024-05-16 | Level 2 | GO 165 Inspection
128190275 | other | Non-HFTD | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F | 2024-10-28 | 2029-02-13 | Level 3 | GO 165 Inspection
128190276 | other | Non-HFTD | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F | 2024-11-01 | 2029-02-13 | Level 3 | GO 165 Inspection
128190335 | other | Non-HFTD | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
128190344 | other | HFTD Tier 3 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128190420 | pole | HFTD Tier 2 | Transmission | 2023-10-25 | 2028-10-25 | Level 3 | F |  | 2028-10-25 | Level 3
128190425 | pole | HFTD Tier 2 | Transmission | 2023-10-25 | 2026-10-25 | Level 2 | E |  | 2026-10-25 | Level 2
128190430 | other | Non-HFTD | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F | 2024-06-27 | 2029-02-13 | Level 3 | GO 165 Inspection
128190545 | other | Non-HFTD | Transmission | 2023-10-07 | 2024-04-07 | Level 2 | E | 2024-07-15 | 2024-04-07 | Level 2 | GO 165 Inspection
128190644 | pole | HFTD Tier 2 | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128190702 | anchor/guy | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E | 2024-11-01 | 2027-02-13 | Level 2 | GO 165 Inspection
128190828 | other | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E | 2024-10-25 | 2027-02-13 | Level 2 | GO 165 Inspection
128190829 | anchor/guy | Non-HFTD | Transmission | 2024-02-13 | 2027-02-13 | Level 2 | E | 2024-10-25 | 2027-02-13 | Level 2 | GO 165 Inspection
128190993 | pole | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128191061 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-14 | 2025-02-14 | Level 2 | E |  | 2025-02-14 | Level 2
128191109 | insulator and brushing | Non-HFTD | Transmission | 2024-02-14 | 2027-02-14 | Level 2 | E | 2024-07-09 | 2027-02-14 | Level 2 | GO 165 Inspection
128191294 | other | Non-HFTD | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F |  | 2029-02-14 | Level 3
128191338 | anchor/guy | Non-HFTD | Transmission | 2024-02-14 | 2027-02-14 | Level 2 | E | 2024-11-06 | 2027-02-14 | Level 2 | GO 165 Inspection
128191344 | pole | Non-HFTD | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F | 2024-06-27 | 2029-02-14 | Level 3 | GO 165 Inspection
128191529 | anchor/guy | Non-HFTD | Transmission | 2024-02-14 | 2027-02-14 | Level 2 | E |  | 2027-02-14 | Level 2
128191597 | other | Non-HFTD | Transmission | 2024-02-14 | 2029-02-14 | Level 3 | F | 2024-10-17 | 2029-02-14 | Level 3 | GO 165 Inspection
128191611 | insulator and brushing | Non-HFTD | Transmission | 2024-02-14 | 2027-02-14 | Level 2 | E | 2024-10-17 | 2027-02-14 | Level 2 | GO 165 Inspection
128192348 | other | Non-HFTD | Transmission | 2024-02-15 | 2029-02-15 | Level 3 | F |  | 2029-02-15 | Level 3
128192401 | other | Non-HFTD | Transmission | 2024-02-15 | 2029-02-15 | Level 3 | F |  | 2029-02-15 | Level 3
128192415 | insulator and brushing | Non-HFTD | Transmission | 2024-02-15 | 2029-02-15 | Level 3 | F |  | 2029-02-15 | Level 3
128192439 | pole | Non-HFTD | Transmission | 2024-02-02 | 2027-02-02 | Level 2 | E | 2024-06-25 | 2027-02-02 | Level 2 | GO 165 Inspection
128192451 | insulator and brushing | Non-HFTD | Transmission | 2024-02-15 | 2027-02-15 | Level 2 | E |  | 2027-02-15 | Level 2
128192454 | insulator and brushing | Non-HFTD | Transmission | 2024-02-15 | 2027-02-15 | Level 2 | E |  | 2027-02-15 | Level 2
128193416 | switch | HFTD Tier 2 | Transmission | 2024-02-16 | 2025-02-16 | Level 2 | E |  | 2025-02-16 | Level 2
128195522 | insulator and brushing | Non-HFTD | Transmission | 2024-02-15 | 2027-02-15 | Level 2 | E |  | 2027-02-15 | Level 2
128195690 | pole | Non-HFTD | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F |  | 2029-02-20 | Level 3
128196178 | insulator and brushing | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-10-28 | 2027-02-20 | Level 2 | GO 165 Inspection
128196916 | other | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128197110 | other | Non-HFTD | Transmission | 2023-08-05 | 2028-08-05 | Level 3 | F |  | 2028-08-05 | Level 3
128197113 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-11-01 | 2026-08-11 | Level 2 | GO 165 Inspection
128197121 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128197351 | pole | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128197538 | pole | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128197612 | other | HFTD Tier 2 | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F |  | 2029-02-20 | Level 3
128197694 | other | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-26 | Level 3 | F |  | 2028-10-26 | Level 3
128197781 | pole | Non-HFTD | Transmission | 2023-10-27 | 2026-10-27 | Level 2 | E |  | 2026-10-27 | Level 2
128198167 | pole | Non-HFTD | Transmission | 2023-08-11 | 2026-08-11 | Level 2 | E | 2024-11-01 | 2026-08-11 | Level 2 | GO 165 Inspection
128198244 | other | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F | 2024-10-16 | 2028-08-12 | Level 3 | GO 165 Inspection
128198245 | pole | Non-HFTD | Transmission | 2023-08-12 | 2028-08-12 | Level 3 | F | 2024-10-16 | 2028-08-12 | Level 3 | GO 165 Inspection
128198252 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-09-03 | 2028-11-01 | Level 3 | GO 165 Inspection
128198258 | pole | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-10-30 | 2028-10-04 | Level 3 | Field Safety Reassessment
128198274 | pole | Non-HFTD | Transmission | 2023-10-04 | 2028-10-04 | Level 3 | F | 2024-11-12 | 2028-10-04 | Level 3 | GO 165 Inspection
128198275 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F |  | 2028-11-02 | Level 3
128198295 | other | Non-HFTD | Transmission | 2023-10-03 | 2024-10-03 | Level 2 | E | 2024-05-20 | 2024-10-03 | Level 2 | Field Safety Reassessment
128198311 | other | Non-HFTD | Transmission | 2023-10-30 | 2024-10-30 | Level 2 | E | 2024-07-09 | 2024-10-30 | Level 2 | GO 165 Inspection
128198314 | pole | Non-HFTD | Transmission | 2023-10-30 | 2026-10-30 | Level 2 | E | 2024-07-09 | 2026-10-30 | Level 2 | GO 165 Inspection
128198317 | other | Non-HFTD | Transmission | 2023-10-30 | 2028-10-30 | Level 3 | F |  | 2028-10-30 | Level 3
128198336 | other | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-10-29 | 2028-11-02 | Level 3 | GO 165 Inspection
128198337 | pole | Non-HFTD | Transmission | 2023-11-02 | 2028-11-02 | Level 3 | F | 2024-10-29 | 2028-11-02 | Level 3 | GO 165 Inspection
128198344 | pole | Non-HFTD | Transmission | 2023-10-31 | 2028-10-31 | Level 3 | F | 2024-09-03 | 2028-10-31 | Level 3 | GO 165 Inspection
128198440 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
128198442 | pole | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F | 2024-11-13 | 2028-11-01 | Level 3 | GO 165 Inspection
128198444 | other | Non-HFTD | Transmission | 2023-11-01 | 2028-11-01 | Level 3 | F |  | 2028-11-01 | Level 3
128198502 | insulator and brushing | Non-HFTD | Transmission | 2023-11-03 | 2028-11-03 | Level 3 | F | 2024-06-19 | 2028-11-03 | Level 3 | GO 165 Inspection
128199618 | other | HFTD Tier 2 | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F |  | 2029-02-20 | Level 3
128199712 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
128199957 | other | HFTD Tier 2 | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
128200674 | anchor/guy | Non-HFTD | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F |  | 2029-02-21 | Level 3
128200695 | conductor | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E |  | 2027-02-21 | Level 2
128200957 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
128201081 | other | Non-HFTD | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F |  | 2029-02-21 | Level 3
128201446 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
128202303 | pole | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128202307 | pole | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128202387 | other | HFTD Tier 2 | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-05-28 | 2029-02-21 | Level 3 | GO 165 Inspection
128202404 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E | 2024-06-13 | 2025-02-20 | Level 2 | GO 165 Inspection
128202986 | other | Non-HFTD | Transmission | 2024-02-13 | 2029-02-13 | Level 3 | F | 2024-10-10 | 2029-02-13 | Level 3 | GO 165 Inspection
128203152 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-15 | 2025-02-15 | Level 2 | E |  | 2025-02-15 | Level 2
128203549 | pole | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E |  | 2027-02-22 | Level 2
128203582 | other | HFTD Tier 2 | Transmission | 2024-02-22 | 2025-02-22 | Level 2 | E |  | 2025-02-22 | Level 2
128204491 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128204640 | other | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E |  | 2027-02-22 | Level 2
128204748 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
128205113 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-22 | 2025-02-22 | Level 2 | E |  | 2025-02-22 | Level 2
128205314 | other | HFTD Tier 2 | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F | 2024-03-19 | 2029-02-22 | Level 3 | GO 165 Inspection
128205390 | pole | HFTD Tier 2 | Transmission | 2024-02-22 | 2025-02-22 | Level 2 | E |  | 2025-02-22 | Level 2
128205972 | anchor/guy | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E |  | 2027-02-22 | Level 2
128205974 | insulator and brushing | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-10-28 | 2027-02-22 | Level 2 | GO 165 Inspection
128205981 | other | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E | 2024-07-20 | 2025-02-20 | Level 2 | Field Safety Reassessment
128206039 | pole | HFTD Tier 2 | Transmission | 2024-02-20 | 2025-02-20 | Level 2 | E | 2024-05-30 | 2025-02-20 | Level 2 | GO 165 Inspection
128206056 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-07-20 | 2029-02-21 | Level 3 | Field Safety Reassessment
128206059 | pole | Non-HFTD | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F | 2024-06-26 | 2029-02-20 | Level 3 | GO 165 Inspection
128206082 | pole | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E | 2024-06-25 | 2027-02-21 | Level 2 | GO 165 Inspection
128206111 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
128206195 | pole | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 3 | F | 2024-07-25 | 2029-02-20 | Level 3 | GO 165 Inspection
128206221 | other | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-08-23 | 2027-02-20 | Level 2 | GO 165 Inspection
128206247 | pole | HFTD Tier 2 | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-05-29 | 2029-02-21 | Level 3 | GO 165 Inspection
128206298 | other | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E | 2024-07-23 | 2027-02-21 | Level 2 | GO 165 Inspection
128206305 | insulator and brushing | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E | 2024-07-23 | 2027-02-21 | Level 2 | GO 165 Inspection
128206310 | other | HFTD Tier 2 | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-05-28 | 2029-02-21 | Level 3 | GO 165 Inspection
128206323 | pole | HFTD Tier 2 | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-05-29 | 2029-02-21 | Level 3 | GO 165 Inspection
128207563 | pole | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-07-08 | 2027-02-20 | Level 2 | GO 165 Inspection
128207569 | anchor/guy | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-07-26 | 2027-02-20 | Level 2 | GO 165 Inspection
128207607 | other | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F |  | 2029-02-22 | Level 3
128207631 | pole | Non-HFTD | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F | 2024-07-26 | 2029-02-20 | Level 3 | GO 165 Inspection
128207636 | other | Non-HFTD | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F | 2024-08-23 | 2029-02-20 | Level 3 | GO 165 Inspection
128207689 | anchor/guy | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E | 2024-07-10 | 2027-02-21 | Level 2 | GO 165 Inspection
128207691 | other | Non-HFTD | Transmission | 2024-02-15 | 2029-02-15 | Level 3 | F |  | 2029-02-15 | Level 3
128207724 | insulator and brushing | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-07-22 | 2027-02-20 | Level 2 | GO 165 Inspection
128207728 | other | Non-HFTD | Transmission | 2024-02-20 | 2029-02-20 | Level 3 | F |  | 2029-02-20 | Level 3
128207735 | pole | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F |  | 2029-02-22 | Level 3
128207781 | insulator and brushing | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E |  | 2027-02-21 | Level 2
128207801 | pole | Non-HFTD | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E | 2024-06-26 | 2025-02-21 | Level 2 | GO 165 Inspection
128207850 | other | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 2 | E | 2024-07-12 | 2027-02-22 | Level 2 | GO 165 Inspection
128208141 | other | Non-HFTD | Transmission | 2024-02-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
128208592 | other | Non-HFTD | Transmission | 2024-02-21 | 2027-02-21 | Level 2 | E |  | 2027-02-21 | Level 2
128209563 | pole | HFTD Tier 2 | Transmission | 2024-02-23 | 2025-02-23 | Level 2 | E | 2024-05-03 | 2025-02-23 | Level 2 | GO 165 Inspection
128211885 | other | Non-HFTD | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128212185 | pole | Non-HFTD | Transmission | 2024-02-26 | 2027-02-26 | Level 2 | E |  | 2027-02-26 | Level 2
128212763 | switch | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128213342 | pole | Non-HFTD | Transmission | 2024-02-26 | 2027-02-26 | Level 2 | E |  | 2027-02-26 | Level 2
128213569 | other | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128213802 | other | Non-HFTD | Transmission | 2024-02-23 | 2027-02-23 | Level 2 | E |  | 2027-02-23 | Level 2
128213829 | anchor/guy | Non-HFTD | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128214205 | other | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128214209 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128214369 | other | Non-HFTD | Transmission | 2024-02-26 | 2027-02-26 | Level 2 | E |  | 2027-02-26 | Level 2
128214373 | insulator and brushing | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-07-16 | 2027-02-22 | Level 2 | GO 165 Inspection
128214439 | other | Non-HFTD | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128214665 | pole | Non-HFTD | Transmission | 2024-02-26 | 2027-02-26 | Level 2 | E |  | 2027-02-26 | Level 2
128214888 | other | Non-HFTD | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F |  | 2029-02-21 | Level 3
128214890 | other | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-07-11 | 2027-02-22 | Level 2 | GO 165 Inspection
128214891 | other | Non-HFTD | Transmission | 2024-02-22 | 2025-02-22 | Level 2 | E | 2024-07-11 | 2025-02-22 | Level 2 | GO 165 Inspection
128214915 | other | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128214972 | other | Non-HFTD | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-07-10 | 2029-02-21 | Level 3 | GO 165 Inspection
128214997 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128215038 | pole | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128215082 | pole | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128215162 | other | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-07-11 | 2027-02-22 | Level 2 | GO 165 Inspection
128215201 | other | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-07-08 | 2027-02-22 | Level 2 | GO 165 Inspection
128215210 | anchor/guy | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128215224 | pole | HFTD Tier 3 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128215269 | crossarm | HFTD Tier 3 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128215303 | switch | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128215322 | other | HFTD Tier 3 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128215335 | pole | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F | 2024-04-15 | 2029-02-26 | Level 3 | GO 165 Inspection
128215341 | other | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F | 2024-08-19 | 2029-02-22 | Level 3 | GO 165 Inspection
128216262 | pole | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F | 2024-04-15 | 2029-02-26 | Level 3 | GO 165 Inspection
128216766 | insulator and brushing | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F | 2024-07-19 | 2029-02-27 | Level 3 | GO 165 Inspection
128216968 | other | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128216969 | insulator and brushing | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128217469 | other | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128217518 | other | HFTD Tier 2 | Transmission | 2024-02-23 | 2025-02-23 | Level 2 | E | 2024-05-07 | 2025-02-23 | Level 2 | GO 165 Inspection
128217553 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E | 2024-06-05 | 2025-02-27 | Level 2 | GO 165 Inspection
128218091 | other | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128220551 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128221005 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
128221011 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128221364 | other | Non-HFTD | Transmission | 2024-02-27 | 2027-02-27 | Level 2 | E |  | 2027-02-27 | Level 2
128221423 | other | Non-HFTD | Transmission | 2024-02-27 | 2027-02-27 | Level 2 | E | 2024-10-24 | 2027-02-27 | Level 2 | GO 165 Inspection
128221557 | other | Non-HFTD | Transmission | 2024-02-27 | 2027-02-27 | Level 2 | E |  | 2027-02-27 | Level 2
128221574 | other | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128221586 | other | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128221630 | other | Non-HFTD | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128222868 | insulator and brushing | Non-HFTD | Transmission | 2024-02-28 | 2027-02-28 | Level 2 | E |  | 2027-02-28 | Level 2
128223154 | other | HFTD Tier 2 | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128223268 | other | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-05-22 | 2027-02-20 | Level 2 | GO 165 Inspection
128223269 | other | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-05-22 | 2027-02-20 | Level 2 | GO 165 Inspection
128223625 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-28 | 2025-02-28 | Level 2 | E | 2024-03-28 | 2025-02-28 | Level 2 | GO 165 Inspection
128224505 | other | Non-HFTD | Transmission | 2024-02-28 | 2027-02-28 | Level 2 | E | 2024-10-29 | 2027-02-28 | Level 2 | GO 165 Inspection
128224610 | other | Non-HFTD | Transmission | 2024-02-28 | 2027-02-28 | Level 2 | E |  | 2027-02-28 | Level 2
128225460 | pole | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128225547 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128225565 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F | 2024-04-17 | 2029-02-27 | Level 3 | GO 165 Inspection
128225585 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E | 2024-10-11 | 2025-01-08 | Level 2 | GO 165 Inspection
128225602 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128225630 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128225634 | pole | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E | 2024-04-03 | 2025-02-27 | Level 2 | GO 165 Inspection
128225637 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E | 2024-03-29 | 2025-02-27 | Level 2 | GO 165 Inspection
128225735 | other | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F |  | 2029-02-22 | Level 3
128225736 | other | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F | 2024-11-13 | 2029-02-22 | Level 3 | GO 165 Inspection
128225738 | pole | Non-HFTD | Transmission | 2024-02-22 | 2029-02-22 | Level 3 | F | 2024-08-19 | 2029-02-22 | Level 3 | GO 165 Inspection
128225739 | other | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-07-11 | 2027-02-22 | Level 2 | GO 165 Inspection
128225741 | other | HFTD Tier 3 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128225781 | other | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E | 2024-07-11 | 2027-02-22 | Level 2 | GO 165 Inspection
128225846 | other | HFTD Tier 3 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F |  | 2029-02-26 | Level 3
128226274 | other | Non-HFTD | Transmission | 2024-02-28 | 2027-02-28 | Level 2 | E |  | 2027-02-28 | Level 2
128227156 | other | Non-HFTD | Transmission | 2024-02-29 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128227852 | anchor/guy | Non-HFTD | Transmission | 2024-02-29 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128228022 | anchor/guy | Non-HFTD | Transmission | 2024-02-29 | 2027-02-28 | Level 2 | E |  | 2027-02-28 | Level 2
128228029 | other | Non-HFTD | Transmission | 2024-02-29 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128228188 | other | Non-HFTD | Transmission | 2024-02-29 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128228310 | pole | HFTD Tier 2 | Transmission | 2024-02-29 | 2025-02-28 | Level 2 | E |  | 2025-02-28 | Level 2
128229123 | anchor/guy | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128229309 | pole | HFTD Tier 3 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229564 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229589 | crossarm | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
128229620 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229637 | pole | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
128229669 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229717 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
128229725 | pole | HFTD Tier 2 | Transmission | 2024-02-26 | 2025-02-26 | Level 2 | E |  | 2025-02-26 | Level 2
128229732 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229735 | pole | HFTD Tier 2 | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128229772 | pole | Non-HFTD | Transmission | 2024-02-21 | 2029-02-21 | Level 3 | F | 2024-07-10 | 2029-02-21 | Level 3 | GO 165 Inspection
128229812 | other | HFTD Tier 3 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229816 | anchor/guy | HFTD Tier 3 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229839 | pole | HFTD Tier 3 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229852 | pole | Non-HFTD | Transmission | 2024-02-22 | 2027-02-22 | Level 2 | E |  | 2027-02-22 | Level 2
128229867 | pole | HFTD Tier 2 | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128229906 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-06-26 | 2029-02-28 | Level 3 | GO 165 Inspection
128229914 | other | HFTD Tier 2 | Transmission | 2024-02-26 | 2029-02-26 | Level 3 | F | 2024-05-24 | 2029-02-26 | Level 3 | GO 165 Inspection
128229932 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-28 | 2025-02-28 | Level 2 | E |  | 2025-02-28 | Level 2
128229943 | other | Non-HFTD | Transmission | 2024-01-08 | 2025-01-08 | Level 2 | E | 2024-10-11 | 2025-01-08 | Level 2 | GO 165 Inspection
128229952 | other | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229954 | crossarm | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128229955 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
128230009 | other | HFTD Tier 2 | Transmission | 2024-02-28 | 2025-02-28 | Level 2 | E |  | 2025-02-28 | Level 2
128230057 | crossarm | HFTD Tier 3 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128231676 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-06-25 | 2029-02-28 | Level 3 | GO 165 Inspection
128231704 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-06-24 | 2029-02-28 | Level 3 | GO 165 Inspection
128231706 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-07-25 | 2029-02-28 | Level 3 | GO 165 Inspection
128233836 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-01 | 2025-03-01 | Level 2 | E |  | 2025-03-01 | Level 2
128236876 | other | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
128237858 | other | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
128238353 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
128238420 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
128238439 | other | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E | 2024-03-11 | 2025-03-04 | Level 2 | GO 165 Inspection
128238591 | other | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 3 | F | 2024-04-01 | 2029-03-04 | Level 3 | GO 165 Inspection
128238599 | other | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
128238669 | other | Non-HFTD | Transmission | 2024-03-04 | 2027-03-04 | Level 2 | E |  | 2027-03-04 | Level 2
128238681 | pole | HFTD Tier 2 | Transmission | 2024-03-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
128238777 | other | Non-HFTD | Transmission | 2024-03-04 | 2029-03-04 | Level 3 | F |  | 2029-03-04 | Level 3
128238783 | other | HFTD Tier 2 | Transmission | 2024-03-04 | 2029-03-04 | Level 3 | F |  | 2029-03-04 | Level 3
128239560 | other | Non-HFTD | Transmission | 2024-03-05 | 2027-03-05 | Level 2 | E | 2024-06-12 | 2027-03-05 | Level 2 | GO 165 Inspection
128241551 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E |  | 2025-03-05 | Level 2
128241776 | other | Non-HFTD | Transmission | 2024-03-05 | 2027-03-05 | Level 2 | E |  | 2027-03-05 | Level 2
128242182 | insulator and brushing | Non-HFTD | Transmission | 2024-03-05 | 2027-03-05 | Level 2 | E |  | 2027-03-05 | Level 2
128243225 | pole | Non-HFTD | Transmission | 2024-03-05 | 2027-03-05 | Level 2 | E |  | 2027-03-05 | Level 2
128243636 | insulator and brushing | Non-HFTD | Transmission | 2024-03-05 | 2027-03-05 | Level 2 | E |  | 2027-03-05 | Level 2
128244329 | other | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E |  | 2025-03-05 | Level 2
128244834 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128245032 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-05-11 | 2029-03-06 | Level 3 | GO 165 Inspection
128245044 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-05-03 | 2029-03-06 | Level 3 | GO 165 Inspection
128245144 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2025-03-06 | Level 2 | E |  | 2025-03-06 | Level 2
128245356 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128245794 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128246078 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-06-17 | 2029-03-06 | Level 3 | GO 165 Inspection
128246615 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-03-27 | 2029-03-06 | Level 3 | GO 165 Inspection
128246743 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-03-18 | 2029-03-06 | Level 3 | GO 165 Inspection
128246888 | other | Non-HFTD | Transmission | 2023-08-02 | 2028-08-02 | Level 3 | F |  | 2028-08-02 | Level 3
128246897 | pole | Non-HFTD | Transmission | 2024-03-06 | 2027-03-06 | Level 2 | E |  | 2027-03-06 | Level 2
128247184 | anchor/guy | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F |  | 2029-02-27 | Level 3
128249938 | other | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F |  | 2029-03-07 | Level 3
128251168 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-07 | 2025-03-07 | Level 2 | E |  | 2025-03-07 | Level 2
128251505 | other | Non-HFTD | Transmission | 2024-03-07 | 2027-03-07 | Level 2 | E |  | 2027-03-07 | Level 2
128251842 | other | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F |  | 2029-03-07 | Level 3
128251955 | other | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F |  | 2029-03-07 | Level 3
128252130 | conductor | HFTD Tier 2 | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F | 2024-03-21 | 2029-03-07 | Level 3 | GO 165 Inspection
128252425 | anchor/guy | Non-HFTD | Transmission | 2024-03-07 | 2027-03-07 | Level 2 | E | 2024-05-07 | 2027-03-07 | Level 2 | GO 165 Inspection
128252440 | other | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F | 2024-05-01 | 2029-03-07 | Level 3 | GO 165 Inspection
128252480 | pole | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F | 2024-03-26 | 2029-03-07 | Level 3 | GO 165 Inspection
128252519 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-04-01 | 2029-03-06 | Level 3 | GO 165 Inspection
128252521 | other | Non-HFTD | Transmission | 2024-03-07 | 2027-03-07 | Level 2 | E | 2024-04-15 | 2027-03-07 | Level 2 | GO 165 Inspection
128252575 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2025-03-06 | Level 2 | E | 2024-06-03 | 2025-03-06 | Level 2 | GO 165 Inspection
128252578 | other | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F | 2024-05-02 | 2029-03-07 | Level 3 | GO 165 Inspection
128252740 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-04-04 | 2029-03-06 | Level 3 | GO 165 Inspection
128252741 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-06 | 2025-03-06 | Level 2 | E | 2024-04-04 | 2025-03-06 | Level 2 | GO 165 Inspection
128252783 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2025-03-06 | Level 2 | E | 2024-05-28 | 2025-03-06 | Level 2 | GO 165 Inspection
128252851 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-04-01 | 2029-03-06 | Level 3 | GO 165 Inspection
128254249 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-08-14 | 2029-02-28 | Level 3 | GO 165 Inspection
128254253 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-07-16 | 2029-02-28 | Level 3 | GO 165 Inspection
128254278 | other | Non-HFTD | Transmission | 2024-02-28 | 2027-02-28 | Level 2 | E | 2024-10-28 | 2027-02-28 | Level 2 | GO 165 Inspection
128254336 | pole | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-07-12 | 2029-02-28 | Level 3 | GO 165 Inspection
128254342 | other | HFTD Tier 2 | Transmission | 2024-02-28 | 2025-02-28 | Level 2 | E | 2024-05-07 | 2025-02-28 | Level 2 | GO 165 Inspection
128254350 | other | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-04-29 | 2025-03-05 | Level 2 | GO 165 Inspection
128254353 | other | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 3 | F | 2024-05-15 | 2029-03-05 | Level 3 | GO 165 Inspection
128254367 | other | HFTD Tier 3 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-04-03 | 2029-03-06 | Level 3 | GO 165 Inspection
128254486 | pole | Non-HFTD | Transmission | 2024-02-20 | 2027-02-20 | Level 2 | E | 2024-08-19 | 2027-02-20 | Level 2 | GO 165 Inspection
128254513 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F | 2024-05-15 | 2029-03-05 | Level 3 | GO 165 Inspection
128254517 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128254744 | insulator and brushing | Non-HFTD | Transmission | 2024-03-06 | 2027-03-06 | Level 2 | E | 2024-05-13 | 2027-03-06 | Level 2 | GO 165 Inspection
128254849 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-07-16 | 2029-02-28 | Level 3 | GO 165 Inspection
128254992 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-08-19 | 2029-03-06 | Level 3 | GO 165 Inspection
128255174 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128255176 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128255435 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128255853 | pole | HFTD Tier 2 | Transmission | 2024-03-06 | 2025-03-06 | Level 2 | E |  | 2025-03-06 | Level 2
128256018 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128256253 | pole | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128256852 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-10-18 | 2029-02-28 | Level 3 | GO 165 Inspection
128256987 | pole | Non-HFTD | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128257099 | pole | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E | 2024-03-14 | 2027-03-08 | Level 2 | GO 165 Inspection
128257540 | pole | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128258225 | pole | HFTD Tier 2 | Transmission | 2024-02-27 | 2029-02-27 | Level 3 | F | 2024-05-21 | 2029-02-27 | Level 3 | GO 165 Inspection
128258614 | other | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F | 2024-05-30 | 2029-03-08 | Level 3 | GO 165 Inspection
128258615 | other | HFTD Tier 2 | Transmission | 2024-03-09 | 2025-03-09 | Level 3 | F | 2024-04-25 | 2029-03-09 | Level 3 | GO 165 Inspection
128258616 | other | Non-HFTD | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F | 2024-06-01 | 2029-03-08 | Level 3 | GO 165 Inspection
128258630 | other | Non-HFTD | Transmission | 2024-03-08 | 2027-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128258645 | other | Non-HFTD | Transmission | 2024-03-09 | 2027-03-09 | Level 2 | E |  | 2027-03-09 | Level 2
128258678 | other | HFTD Tier 2 | Transmission | 2024-03-09 | 2029-03-09 | Level 3 | F |  | 2029-03-09 | Level 3
128259015 | other | Non-HFTD | Transmission | 2024-02-28 | 2027-02-28 | Level 2 | E | 2024-08-14 | 2027-02-28 | Level 2 | GO 165 Inspection
128269258 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-02-28 | 2025-02-28 | Level 2 | E |  | 2025-02-28 | Level 2
128269392 | insulator and brushing | Non-HFTD | Transmission | 2024-03-06 | 2027-03-06 | Level 2 | E |  | 2027-03-06 | Level 2
128271572 | insulator and brushing | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128271577 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128271582 | other | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E |  | 2027-03-11 | Level 2
128272053 | pole | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
128272174 | anchor/guy | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F | 2024-05-06 | 2029-03-07 | Level 3 | GO 165 Inspection
128272212 | pole | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128272260 | pole | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E |  | 2027-03-11 | Level 2
128272474 | anchor/guy | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128272676 | other | Non-HFTD | Transmission | 2024-03-07 | 2027-03-07 | Level 2 | E | 2024-05-08 | 2027-03-07 | Level 2 | GO 165 Inspection
128273700 | pole | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128274141 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128274142 | pole | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128274276 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-06-04 | 2029-03-11 | Level 3 | GO 165 Inspection
128276819 | pole | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128277181 | switch | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E | 2024-03-15 | 2025-03-11 | Level 2 | Field Safety Reassessment
128277288 | other | Non-HFTD | Transmission | 2024-03-07 | 2029-03-07 | Level 3 | F | 2024-04-01 | 2029-03-07 | Level 3 | GO 165 Inspection
128278981 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128279003 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128279271 | other | HFTD Tier 3 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F | 2024-03-28 | 2029-03-12 | Level 3 | GO 165 Inspection
128279274 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128279331 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128279407 | pole | Non-HFTD | Transmission | 2024-03-12 | 2027-03-12 | Level 2 | E |  | 2027-03-12 | Level 2
128279762 | other | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280281 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280372 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280378 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280379 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280411 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280412 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280417 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280418 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280431 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280439 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280506 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280523 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280527 | pole | Non-HFTD | Transmission | 2024-03-12 | 2027-03-12 | Level 3 | F |  | 2027-03-12 | Level 3
128280528 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280529 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280530 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280533 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280535 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280536 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280537 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280538 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280572 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280573 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280577 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280623 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128280630 | pole | Non-HFTD | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128281071 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128281144 | other | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128281188 | insulator and brushing | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-06-05 | 2027-03-11 | Level 2 | GO 165 Inspection
128281212 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128281472 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
128281621 | other | HFTD Tier 3 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-03-28 | 2029-03-13 | Level 3 | GO 165 Inspection
128281913 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282097 | other | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-03-20 | 2029-03-13 | Level 3 | GO 165 Inspection
128282126 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282381 | other | Non-HFTD | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128282407 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-06-27 | 2029-03-13 | Level 3 | GO 165 Inspection
128282586 | pole | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282598 | other | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282632 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282651 | other | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282785 | other | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282794 | other | Non-HFTD | Transmission | 2024-03-13 | 2027-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128282815 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128283532 | conductor | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128283535 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128283545 | pole | Non-HFTD | Transmission | 2024-03-13 | 2027-03-13 | Level 2 | E |  | 2027-03-13 | Level 2
128283714 | pole | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128283893 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F | 2024-04-22 | 2029-03-12 | Level 3 | GO 165 Inspection
128284024 | anchor/guy | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128284077 | other | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128284241 | pole | Non-HFTD | Transmission | 2024-03-12 | 2027-03-12 | Level 2 | E |  | 2027-03-12 | Level 2
128284419 | pole | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-03-27 | 2029-03-11 | Level 3 | GO 165 Inspection
128284481 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128284823 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128284919 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128285082 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128285114 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128285242 | pole | HFTD Tier 2 | Transmission | 2024-03-13 | 2024-09-13 | Level 2 | E | 2024-10-14 | 2024-09-13 | Level 2 | Field Safety Reassessment
128285285 | pole | Non-HFTD | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E | 2024-10-02 | 2025-03-13 | Level 2 | GO 165 Inspection
128285366 | conductor | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128286651 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F | 2024-04-20 | 2029-03-12 | Level 3 | GO 165 Inspection
128287242 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-05-10 | 2029-03-14 | Level 3 | GO 165 Inspection
128287380 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128287524 | pole | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E | 2024-04-30 | 2025-03-14 | Level 2 | GO 165 Inspection
128287531 | other | Non-HFTD | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128287687 | pole | Non-HFTD | Transmission | 2024-03-14 | 2027-03-14 | Level 2 | E |  | 2027-03-14 | Level 2
128287828 | insulator and brushing | Non-HFTD | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-09-05 | 2029-03-14 | Level 3 | GO 165 Inspection
128287976 | pole | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128288342 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128288532 | other | Non-HFTD | Transmission | 2024-03-14 | 2027-03-14 | Level 2 | E |  | 2027-03-14 | Level 2
128288603 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128288613 | pole | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128289521 | other | Non-HFTD | Transmission | 2024-03-14 | 2027-03-14 | Level 2 | E | 2024-04-16 | 2027-03-14 | Level 2 | GO 165 Inspection
128289546 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2027-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128289685 | pole | HFTD Tier 3 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128289921 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128290369 | pole | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128290408 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128290425 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F | 2024-04-12 | 2029-03-12 | Level 3 | GO 165 Inspection
128290499 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F | 2024-04-18 | 2029-03-12 | Level 3 | GO 165 Inspection
128290525 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128290576 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128290608 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128290620 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128290876 | pole | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128290890 | pole | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128290923 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F | 2024-04-09 | 2029-03-12 | Level 3 | GO 165 Inspection
128291052 | insulator and brushing | Non-HFTD | Transmission | 2024-03-13 | 2027-03-13 | Level 2 | E | 2024-05-22 | 2027-03-13 | Level 2 | GO 165 Inspection
128291122 | other | HFTD Tier 3 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128291169 | other | HFTD Tier 3 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128291182 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128291199 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-05-23 | 2029-03-13 | Level 3 | GO 165 Inspection
128291261 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128291276 | pole | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128291293 | pole | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128291311 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
128291325 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-06-25 | 2029-03-13 | Level 3 | GO 165 Inspection
128292798 | pole | Non-HFTD | Transmission | 2024-03-13 | 2027-03-13 | Level 2 | E | 2024-06-03 | 2027-03-13 | Level 2 | GO 165 Inspection
128292831 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128292866 | pole | Non-HFTD | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128292877 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E | 2024-05-29 | 2025-03-13 | Level 2 | GO 165 Inspection
128292895 | other | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-03-28 | 2029-03-11 | Level 3 | GO 165 Inspection
128292942 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-06-24 | 2029-03-13 | Level 3 | GO 165 Inspection
128292992 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128293024 | other | HFTD Tier 2 | Transmission | 2024-03-12 | 2029-03-12 | Level 3 | F |  | 2029-03-12 | Level 3
128293086 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F | 2024-05-21 | 2029-03-05 | Level 3 | GO 165 Inspection
128293118 | pole | Non-HFTD | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128293149 | pole | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E | 2024-06-04 | 2027-03-13 | Level 2 | GO 165 Inspection
128293246 | other | HFTD Tier 2 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F | 2024-05-07 | 2029-03-05 | Level 3 | GO 165 Inspection
128293294 | pole | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128293409 | pole | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128293440 | pole | HFTD Tier 2 | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F |  | 2029-02-28 | Level 3
128293484 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128293711 | other | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-05-07 | 2025-03-05 | Level 2 | GO 165 Inspection
128293863 | insulator and brushing | Non-HFTD | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128293941 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E | 2024-04-30 | 2025-03-15 | Level 2 | GO 165 Inspection
128294205 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-05-20 | 2025-03-05 | Level 2 | GO 165 Inspection
128294308 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128294408 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128294415 | other | HFTD Tier 3 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128294737 | other | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F | 2024-04-03 | 2029-03-08 | Level 3 | GO 165 Inspection
128295154 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128295216 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E | 2024-04-30 | 2025-03-15 | Level 2 | GO 165 Inspection
128295267 | anchor/guy | HFTD Tier 3 | Transmission | 2024-03-05 | 2027-03-05 | Level 2 | E |  | 2027-03-05 | Level 2
128295700 | anchor/guy | Non-HFTD | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E | 2024-06-10 | 2025-03-15 | Level 2 | GO 165 Inspection
128295814 | anchor/guy | HFTD Tier 3 | Transmission | 2024-03-15 | 2024-09-15 | Level 2 | E | 2024-05-31 | 2027-03-15 | Level 2 | GO 165 Inspection
128296141 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128296180 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F | 2024-05-15 | 2029-03-05 | Level 3 | GO 165 Inspection
128296185 | other | HFTD Tier 3 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-03-27 | 2029-03-13 | Level 3 | GO 165 Inspection
128296186 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-06-25 | 2029-03-13 | Level 3 | GO 165 Inspection
128296356 | conductor | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128296366 | pole | HFTD Tier 3 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-05-31 | 2029-03-15 | Level 3 | GO 165 Inspection
128296390 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-06-25 | 2029-03-13 | Level 3 | GO 165 Inspection
128296409 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-03-21 | 2029-03-15 | Level 3 | GO 165 Inspection
128296410 | other | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128296473 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128296480 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128296505 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128296519 | switch | Non-HFTD | Transmission | 2024-03-15 | 2027-03-15 | Level 2 | E |  | 2027-03-15 | Level 2
128296564 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-15 | 2027-03-15 | Level 2 | E |  | 2027-03-15 | Level 2
128297103 | other | Non-HFTD | Transmission | 2024-03-16 | 2029-03-16 | Level 3 | F | 2024-08-29 | 2029-03-16 | Level 3 | GO 165 Inspection
128298590 | switch | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128298698 | pole | HFTD Tier 3 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-04-04 | 2029-03-14 | Level 3 | GO 165 Inspection
128298745 | pole | HFTD Tier 3 | Transmission | 2024-03-14 | 2024-09-14 | Level 2 | E | 2024-04-04 | 2024-09-14 | Level 2 | GO 165 Inspection
128299002 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128299029 | pole | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128299206 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128299576 | insulator and brushing | Non-HFTD | Transmission | 2024-03-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
128299619 | pole | Non-HFTD | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-05-23 | 2029-03-13 | Level 3 | GO 165 Inspection
128299681 | other | HFTD Tier 3 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-04-09 | 2029-03-14 | Level 3 | GO 165 Inspection
128299768 | pole | HFTD Tier 2 | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E | 2024-03-26 | 2025-03-18 | Level 2 | GO 165 Inspection
128299888 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128299951 | pole | HFTD Tier 3 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F | 2024-05-10 | 2029-03-18 | Level 3 | GO 165 Inspection
128300181 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128300219 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128300224 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128300728 | pole | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128300770 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128300802 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128301030 | pole | HFTD Tier 2 | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E | 2024-03-26 | 2025-03-18 | Level 2 | GO 165 Inspection
128301037 | pole | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128301180 | pole | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F | 2024-03-26 | 2029-03-18 | Level 3 | GO 165 Inspection
128301373 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128301669 | other | HFTD Tier 3 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128301684 | pole | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128301780 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128301796 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128302834 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128303236 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128303260 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E |  | 2025-03-05 | Level 2
128303269 | pole | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128303270 | pole | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-04-20 | 2029-03-14 | Level 3 | GO 165 Inspection
128303281 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128303336 | pole | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128303459 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128303481 | crossarm | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
128303500 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128303528 | other | HFTD Tier 3 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128303605 | pole | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
128303609 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E | 2024-06-10 | 2025-03-14 | Level 2 | GO 165 Inspection
128303691 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-06-10 | 2029-03-14 | Level 3 | GO 165 Inspection
128303725 | other | HFTD Tier 2 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F | 2024-04-22 | 2029-03-05 | Level 3 | GO 165 Inspection
128303751 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-05-07 | 2029-03-11 | Level 3 | GO 165 Inspection
128303833 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128303914 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128303923 | other | HFTD Tier 3 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F |  | 2029-03-05 | Level 3
128303927 | other | HFTD Tier 3 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128303946 | other | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128303978 | other | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F | 2024-04-03 | 2029-03-08 | Level 3 | GO 165 Inspection
128303998 | crossarm | HFTD Tier 3 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128303999 | pole | HFTD Tier 3 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128304043 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-08 | 2024-09-08 | Level 2 | E | 2024-09-03 | 2024-09-08 | Level 2 | Field Safety Reassessment
128304088 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-18 | 2024-09-18 | Level 2 | E | 2024-08-30 | 2024-09-18 | Level 2 | Field Safety Reassessment
128304097 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-04-25 | 2025-03-05 | Level 2 | GO 165 Inspection
128304115 | other | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128304207 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128304803 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128305050 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E | 2024-11-27 | 2025-03-19 | Level 2 | GO 165 Inspection
128305086 | pole | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128305101 | conductor | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128305208 | pole | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128305261 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128305373 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128305423 | other | HFTD Tier 2 | Transmission | 2023-04-18 | 2025-03-19 | Level 2 | E |  | 2024-04-18 | Level 2
128305428 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128305715 | insulator and brushing | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E |  | 2027-03-19 | Level 2
128305818 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128305841 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128305904 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-05-21 | 2025-03-05 | Level 2 | GO 165 Inspection
128306329 | anchor/guy | HFTD Tier 3 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128306422 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-06 | 2025-03-06 | Level 2 | E |  | 2025-03-06 | Level 2
128306423 | crossarm | HFTD Tier 2 | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F |  | 2029-03-06 | Level 3
128306786 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128306833 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128306906 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128306918 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128307586 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128307752 | other | Non-HFTD | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128307755 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-06-19 | 2029-03-19 | Level 3 | GO 165 Inspection
128307791 | other | HFTD Tier 3 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128307793 | pole | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128307862 | insulator and brushing | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E |  | 2027-03-19 | Level 2
128308055 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-05-08 | 2029-03-19 | Level 3 | GO 165 Inspection
128308156 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128308806 | insulator and brushing | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E |  | 2027-03-19 | Level 2
128308849 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128308871 | anchor/guy | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E |  | 2027-03-19 | Level 2
128308963 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128309575 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128311358 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128312014 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128312045 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128312271 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128314043 | insulator and brushing | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128316269 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128318246 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128320004 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128320678 | other | HFTD Tier 3 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128320703 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128321240 | pole | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128321250 | other | Non-HFTD | Transmission | 2024-02-28 | 2029-02-28 | Level 3 | F | 2024-10-23 | 2029-02-28 | Level 3 | GO 165 Inspection
128322095 | other | HFTD Tier 2 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128322111 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2029-03-05 | Level 3 | F | 2024-04-25 | 2029-03-05 | Level 3 | GO 165 Inspection
128322119 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-04-01 | 2025-03-05 | Level 2 | GO 165 Inspection
128322157 | other | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-11-15 | 2027-03-11 | Level 2 | GO 165 Inspection
128322169 | conductor | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128322173 | other | Non-HFTD | Transmission | 2024-03-15 | 2027-03-15 | Level 2 | E | 2024-08-15 | 2027-03-15 | Level 2 | GO 165 Inspection
128322177 | other | Non-HFTD | Transmission | 2024-03-15 | 2027-03-15 | Level 2 | E | 2024-08-15 | 2027-03-15 | Level 2 | GO 165 Inspection
128322188 | pole | Non-HFTD | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128322233 | anchor/guy | Non-HFTD | Transmission | 2024-03-06 | 2027-03-06 | Level 2 | E | 2024-05-13 | 2027-03-06 | Level 2 | GO 165 Inspection
128322234 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-05-13 | 2029-03-06 | Level 3 | GO 165 Inspection
128322253 | other | HFTD Tier 3 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128322258 | other | HFTD Tier 3 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128322768 | other | Non-HFTD | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E |  | 2027-03-20 | Level 2
128323249 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128323276 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128323277 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128323284 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E | 2024-04-11 | 2025-03-20 | Level 2 | GO 165 Inspection
128323316 | other | Non-HFTD | Transmission | 2024-03-20 | 2027-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128323318 | other | Non-HFTD | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E |  | 2027-03-20 | Level 2
128323941 | other | HFTD Tier 3 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128324359 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128324491 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128324506 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128324573 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128324847 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128325159 | pole | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-05-06 | 2029-03-20 | Level 3 | GO 165 Inspection
128325278 | anchor/guy | Non-HFTD | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128325569 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128329262 | other | Non-HFTD | Transmission | 2024-03-20 | 2027-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128334045 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128334046 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128334080 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128334115 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128334315 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E | 2024-04-04 | 2025-03-20 | Level 2 | Field Safety Reassessment
128335597 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128335603 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128335781 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128335945 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128335985 | pole | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E |  | 2025-03-08 | Level 2
128336033 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128336074 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128336084 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128336092 | pole | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128336242 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-05 | 2025-03-05 | Level 2 | E | 2024-05-20 | 2025-03-05 | Level 2 | GO 165 Inspection
128336247 | other | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-09-09 | 2029-03-11 | Level 3 | GO 165 Inspection
128336252 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128336284 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128336286 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128336327 | other | Non-HFTD | Transmission | 2024-03-06 | 2029-03-06 | Level 3 | F | 2024-05-13 | 2029-03-06 | Level 3 | GO 165 Inspection
128336329 | other | Non-HFTD | Transmission | 2024-03-06 | 2027-03-06 | Level 2 | E | 2024-05-13 | 2027-03-06 | Level 2 | GO 165 Inspection
128336346 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128336347 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128336388 | other | HFTD Tier 2 | Transmission | 2024-03-08 | 2025-03-08 | Level 2 | E | 2024-07-09 | 2025-03-08 | Level 2 | GO 165 Inspection
128336400 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E | 2024-03-29 | 2025-03-11 | Level 2 | GO 165 Inspection
128336404 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128336413 | anchor/guy | Non-HFTD | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E | 2024-11-09 | 2027-03-18 | Level 2 | GO 165 Inspection
128336429 | other | Non-HFTD | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F | 2024-08-19 | 2029-03-08 | Level 3 | GO 165 Inspection
128336455 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F | 2024-04-09 | 2029-03-13 | Level 3 | GO 165 Inspection
128336466 | insulator and brushing | Non-HFTD | Transmission | 2024-03-06 | 2027-03-06 | Level 2 | E | 2024-07-16 | 2027-03-06 | Level 2 | GO 165 Inspection
128336477 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128337161 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128337200 | other | HFTD Tier 2 | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F |  | 2029-03-11 | Level 3
128337476 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128337530 | pole | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128337618 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128338222 | other | HFTD Tier 2 | Transmission | 2024-03-13 | 2029-03-13 | Level 3 | F |  | 2029-03-13 | Level 3
128338303 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128338309 | pole | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128338349 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128342232 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128342292 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F | 2024-07-20 | 2029-03-21 | Level 3 | Field Safety Reassessment
128342364 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E | 2024-06-04 | 2025-03-21 | Level 2 | GO 165 Inspection
128342395 | anchor/guy | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E | 2024-05-09 | 2027-03-21 | Level 2 | GO 165 Inspection
128342808 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128343191 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128343470 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128343524 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128343611 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344069 | other | Non-HFTD | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344094 | conductor | Non-HFTD | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128344204 | other | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344244 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344245 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344252 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128344295 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344309 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344334 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128344438 | pole | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344444 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128344460 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128344551 | pole | HFTD Tier 2 | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128344624 | insulator and brushing | Non-HFTD | Transmission | 2024-03-21 | 2024-09-21 | Level 2 | E | 2024-09-17 | 2024-09-21 | Level 2 | GO 165 Inspection
128346202 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128346270 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128346423 | other | HFTD Tier 3 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128346525 | pole | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128346616 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128347021 | pole | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F | 2024-04-02 | 2029-03-22 | Level 3 | GO 165 Inspection
128350385 | pole | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128350774 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128350858 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128350872 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128351102 | pole | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128351155 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128351609 | pole | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E | 2024-07-17 | 2025-03-22 | Level 2 | Field Safety Reassessment
128351769 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
128351967 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128352500 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128352539 | pole | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128352603 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128352666 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E | 2024-05-09 | 2025-03-22 | Level 2 | GO 165 Inspection
128352717 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F | 2024-05-30 | 2029-03-22 | Level 3 | GO 165 Inspection
128352781 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128352861 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128353072 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128353078 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128353157 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128353173 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-05-08 | 2029-03-14 | Level 3 | GO 165 Inspection
128353187 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128353193 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128353372 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128353419 | other | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-07-08 | 2027-03-11 | Level 2 | GO 165 Inspection
128353473 | other | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-06-25 | 2027-03-11 | Level 2 | GO 165 Inspection
128353474 | insulator and brushing | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-06-25 | 2027-03-11 | Level 2 | GO 165 Inspection
128353475 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128356524 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F |  | 2029-03-25 | Level 3
128356715 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E | 2024-05-08 | 2025-03-22 | Level 2 | GO 165 Inspection
128356896 | other | HFTD Tier 3 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F |  | 2029-03-25 | Level 3
128356922 | other | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-06-03 | 2029-03-25 | Level 3 | GO 165 Inspection
128357130 | insulator and brushing | Non-HFTD | Transmission | 2024-03-25 | 2027-03-25 | Level 2 | E | 2024-06-07 | 2027-03-25 | Level 2 | GO 165 Inspection
128357337 | insulator and brushing | Non-HFTD | Transmission | 2024-03-25 | 2027-03-25 | Level 2 | E |  | 2027-03-25 | Level 2
128358061 | pole | HFTD Tier 2 | Transmission | 2024-03-25 | 2025-03-25 | Level 2 | E |  | 2025-03-25 | Level 2
128358110 | insulator and brushing | Non-HFTD | Transmission | 2024-03-25 | 2024-06-25 | Level 2 | E | 2024-11-13 | 2024-06-25 | Level 2 | Field Safety Reassessment
128364404 | other | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-06-10 | 2029-03-25 | Level 3 | GO 165 Inspection
128364817 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-25 | 2025-03-25 | Level 2 | E | 2024-05-22 | 2025-03-25 | Level 2 | GO 165 Inspection
128365045 | pole | Non-HFTD | Transmission | 2024-03-25 | 2027-03-25 | Level 2 | E | 2024-11-08 | 2027-03-25 | Level 2 | GO 165 Inspection
128365274 | insulator and brushing | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-08-08 | 2029-03-25 | Level 3 | GO 165 Inspection
128366098 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128366111 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-04-02 | 2029-03-25 | Level 3 | GO 165 Inspection
128366181 | other | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-04-01 | 2029-03-25 | Level 3 | GO 165 Inspection
128366221 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128366354 | other | Non-HFTD | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128366439 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-05-09 | 2029-03-14 | Level 3 | GO 165 Inspection
128366446 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128366465 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128366516 | other | HFTD Tier 3 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128366554 | other | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E | 2024-05-08 | 2025-03-22 | Level 2 | GO 165 Inspection
128366573 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128366597 | crossarm | HFTD Tier 2 | Transmission | 2024-03-14 | 2025-03-14 | Level 2 | E |  | 2025-03-14 | Level 2
128366614 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128366698 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128366749 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128366802 | other | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128366803 | other | HFTD Tier 2 | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F |  | 2029-03-14 | Level 3
128366830 | crossarm | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128366957 | anchor/guy | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-09-09 | 2025-03-11 | Level 2 | GO 165 Inspection
128368358 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128368697 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128368782 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E | 2024-05-10 | 2025-03-26 | Level 2 | GO 165 Inspection
128368867 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128369355 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128369388 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E | 2024-06-05 | 2025-03-26 | Level 2 | GO 165 Inspection
128370981 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128371000 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128371482 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F | 2024-06-04 | 2029-03-26 | Level 3 | GO 165 Inspection
128372081 | other | HFTD Tier 3 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128372184 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F | 2024-06-04 | 2029-03-26 | Level 3 | GO 165 Inspection
128372444 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128372481 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128372545 | other | Non-HFTD | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F | 2024-10-21 | 2029-03-26 | Level 3 | GO 165 Inspection
128373147 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128373210 | pole | Non-HFTD | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128373485 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128373495 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128373770 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128375394 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128375556 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128376442 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F | 2024-04-19 | 2029-03-27 | Level 3 | GO 165 Inspection
128377122 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128377751 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128377858 | pole | Non-HFTD | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128379192 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128379214 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128379961 | other | Non-HFTD | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128380032 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2027-03-27 | Level 2 | E |  | 2025-03-27 | Level 2
128380033 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2025-03-27 | Level 2 | E |  | 2025-03-27 | Level 2
128380090 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2025-03-27 | Level 2 | E |  | 2025-03-27 | Level 2
128380116 | other | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-06-05 | 2029-03-25 | Level 3 | GO 165 Inspection
128380173 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-27 | 2025-03-27 | Level 2 | E |  | 2025-03-27 | Level 2
128380178 | other | Non-HFTD | Transmission | 2024-03-27 | 2027-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128380463 | anchor/guy | Non-HFTD | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128380573 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128380722 | other | Non-HFTD | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F | 2024-04-02 | 2029-03-26 | Level 3 | GO 165 Inspection
128380783 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128380800 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2027-03-26 | Level 2 | E |  | 2027-03-26 | Level 2
128380830 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F | 2024-06-04 | 2029-03-27 | Level 3 | GO 165 Inspection
128380839 | other | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-11-12 | 2029-03-11 | Level 3 | GO 165 Inspection
128380874 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128380962 | insulator and brushing | Non-HFTD | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F | 2024-11-24 | 2029-03-18 | Level 3 | GO 165 Inspection
128380992 | other | HFTD Tier 3 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128381052 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F |  | 2029-03-25 | Level 3
128381106 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128381142 | other | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-11-12 | 2029-03-11 | Level 3 | GO 165 Inspection
128381186 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128381213 | other | HFTD Tier 3 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128381230 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2027-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128381263 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128381295 | pole | HFTD Tier 2 | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E |  | 2025-03-15 | Level 2
128381319 | other | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-11-12 | 2027-03-11 | Level 2 | GO 165 Inspection
128381353 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128381359 | insulator and brushing | Non-HFTD | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E | 2024-08-08 | 2025-03-15 | Level 2 | GO 165 Inspection
128381367 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128381380 | other | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-09-09 | 2029-03-11 | Level 3 | GO 165 Inspection
128381388 | other | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128383074 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128383451 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128383609 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E | 2024-06-17 | 2025-03-28 | Level 2 | GO 165 Inspection
128383960 | pole | Non-HFTD | Transmission | 2024-03-28 | 2027-03-28 | Level 2 | E |  | 2027-03-28 | Level 2
128384066 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128384449 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F | 2024-07-21 | 2029-03-28 | Level 3 | Field Safety Reassessment
128384484 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E | 2024-06-14 | 2025-03-28 | Level 2 | GO 165 Inspection
128384849 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-26 | 2024-09-26 | Level 2 | E |  | 2024-09-26 | Level 2
128385241 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128385246 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128385415 | other | HFTD Tier 3 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128385420 | other | Non-HFTD | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E | 2024-05-17 | 2025-03-28 | Level 2 | GO 165 Inspection
128385432 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128385481 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128385729 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128385740 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128385754 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128385888 | pole | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128385980 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128386002 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128386173 | other | HFTD Tier 3 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128386313 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128386448 | other | Non-HFTD | Transmission | 2024-03-25 | 2027-03-25 | Level 2 | E | 2024-10-09 | 2027-03-25 | Level 2 | GO 165 Inspection
128386459 | pole | Non-HFTD | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-10-28 | 2029-03-15 | Level 3 | GO 165 Inspection
128386475 | other | Non-HFTD | Transmission | 2024-03-15 | 2027-03-15 | Level 2 | E | 2024-06-25 | 2027-03-15 | Level 2 | GO 165 Inspection
128386529 | pole | Non-HFTD | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-10-30 | 2029-03-15 | Level 3 | GO 165 Inspection
128386568 | other | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E | 2024-10-25 | 2027-03-19 | Level 2 | GO 165 Inspection
128386605 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F |  | 2029-03-25 | Level 3
128386629 | other | Non-HFTD | Transmission | 2024-03-11 | 2027-03-11 | Level 2 | E | 2024-09-18 | 2027-03-11 | Level 2 | GO 165 Inspection
128386655 | other | Non-HFTD | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-08-15 | 2029-03-15 | Level 3 | GO 165 Inspection
128386673 | other | HFTD Tier 3 | Transmission | 2024-03-25 | 2024-09-25 | Level 2 | E | 2024-12-27 | 2024-09-25 | Level 2 | Field Safety Reassessment
128386675 | other | HFTD Tier 3 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-04-30 | 2029-03-25 | Level 3 | GO 165 Inspection
128386748 | crossarm | HFTD Tier 3 | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E |  | 2027-03-19 | Level 2
128386760 | pole | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128386860 | insulator and brushing | Non-HFTD | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-10-28 | 2029-03-15 | Level 3 | GO 165 Inspection
128386862 | other | Non-HFTD | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-10-28 | 2029-03-15 | Level 3 | GO 165 Inspection
128386863 | insulator and brushing | Non-HFTD | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E | 2024-05-14 | 2025-03-18 | Level 2 | GO 165 Inspection
128386951 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128386955 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128386960 | anchor/guy | Non-HFTD | Transmission | 2024-03-15 | 2025-03-15 | Level 2 | E | 2024-08-09 | 2025-03-15 | Level 2 | GO 165 Inspection
128386964 | pole | Non-HFTD | Transmission | 2024-03-15 | 2027-03-15 | Level 2 | E | 2024-08-09 | 2027-03-15 | Level 2 | GO 165 Inspection
128387010 | other | Non-HFTD | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F | 2024-08-19 | 2029-03-18 | Level 3 | GO 165 Inspection
128387012 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E | 2024-04-10 | 2025-03-19 | Level 2 | GO 165 Inspection
128387017 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-04-10 | 2029-03-19 | Level 3 | GO 165 Inspection
128387055 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-04-11 | 2029-03-19 | Level 3 | GO 165 Inspection
128387066 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E | 2024-04-09 | 2025-03-19 | Level 2 | GO 165 Inspection
128388505 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128388717 | other | HFTD Tier 3 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128388914 | pole | HFTD Tier 3 | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F |  | 2029-03-29 | Level 3
128389321 | other | Non-HFTD | Transmission | 2024-03-11 | 2029-03-11 | Level 3 | F | 2024-09-09 | 2029-03-11 | Level 3 | GO 165 Inspection
128389407 | pole | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E | 2024-10-26 | 2027-03-21 | Level 2 | GO 165 Inspection
128389422 | other | Non-HFTD | Transmission | 2024-03-12 | 2027-03-12 | Level 2 | E | 2024-07-10 | 2027-03-12 | Level 2 | GO 165 Inspection
128389495 | other | HFTD Tier 3 | Transmission | 2024-03-08 | 2029-03-08 | Level 3 | F |  | 2029-03-08 | Level 3
128389496 | other | Non-HFTD | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128389748 | other | Non-HFTD | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F | 2024-10-28 | 2029-03-15 | Level 3 | GO 165 Inspection
128390866 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-10-24 | 2029-03-19 | Level 3 | GO 165 Inspection
128390931 | other | Non-HFTD | Transmission | 2024-03-14 | 2029-03-14 | Level 3 | F | 2024-05-08 | 2029-03-14 | Level 3 | GO 165 Inspection
128392563 | pole | HFTD Tier 2 | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F |  | 2029-03-29 | Level 3
128392724 | anchor/guy | HFTD Tier 3 | Transmission | 2024-03-29 | 2024-09-29 | Level 2 | E | 2024-10-29 | 2024-09-29 | Level 2 | Field Safety Reassessment
128393050 | other | Non-HFTD | Transmission | 2024-03-29 | 2025-03-29 | Level 2 | E |  | 2025-03-29 | Level 2
128393079 | pole | Non-HFTD | Transmission | 2024-03-11 | 2025-03-11 | Level 2 | E | 2024-09-09 | 2025-03-11 | Level 2 | GO 165 Inspection
128393080 | insulator and brushing | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-05-23 | 2027-03-29 | Level 2 | GO 165 Inspection
128393081 | anchor/guy | Non-HFTD | Transmission | 2024-03-29 | 2025-03-29 | Level 2 | E |  | 2025-03-29 | Level 2
128393160 | other | Non-HFTD | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E | 2024-07-09 | 2027-03-18 | Level 2 | GO 165 Inspection
128393161 | other | Non-HFTD | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E | 2024-07-09 | 2027-03-18 | Level 2 | GO 165 Inspection
128393195 | other | Non-HFTD | Transmission | 2024-03-29 | 2025-03-29 | Level 2 | E |  | 2025-03-29 | Level 2
128393255 | other | HFTD Tier 2 | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F |  | 2029-03-29 | Level 3
128393307 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-29 | 2025-03-29 | Level 2 | E |  | 2025-03-29 | Level 2
128393554 | other | HFTD Tier 2 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128393574 | other | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-05-02 | 2027-03-29 | Level 2 | GO 165 Inspection
128393641 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-06-13 | 2029-03-20 | Level 3 | GO 165 Inspection
128393676 | switch | Non-HFTD | Transmission | 2024-03-29 | 2025-03-29 | Level 2 | E |  | 2025-03-29 | Level 2
128393807 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-18 | 2024-09-18 | Level 2 | E | 2024-09-03 | 2024-09-18 | Level 2 | Field Safety Reassessment
128393909 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-10-07 | 2029-03-19 | Level 3 | GO 165 Inspection
128394286 | other | HFTD Tier 3 | Transmission | 2024-03-18 | 2029-03-18 | Level 3 | F |  | 2029-03-18 | Level 3
128394320 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-10-26 | 2029-03-19 | Level 3 | GO 165 Inspection
128394898 | pole | Non-HFTD | Transmission | 2024-03-30 | 2027-03-30 | Level 2 | E | 2024-10-18 | 2027-03-30 | Level 2 | GO 165 Inspection
128395044 | pole | Non-HFTD | Transmission | 2024-03-30 | 2027-03-30 | Level 2 | E | 2024-08-28 | 2027-03-30 | Level 2 | GO 165 Inspection
128395210 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395280 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128395312 | insulator and brushing | Non-HFTD | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128395313 | other | Non-HFTD | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E | 2024-11-09 | 2027-03-20 | Level 2 | GO 165 Inspection
128395318 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-11-09 | 2029-03-20 | Level 3 | GO 165 Inspection
128395332 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128395334 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395338 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395340 | other | HFTD Tier 3 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395346 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395348 | other | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395520 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128395534 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128395578 | pole | Non-HFTD | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F | 2024-08-13 | 2029-03-29 | Level 3 | GO 165 Inspection
128395580 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-11-07 | 2029-03-20 | Level 3 | GO 165 Inspection
128395594 | insulator and brushing | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E | 2024-08-19 | 2027-03-19 | Level 2 | GO 165 Inspection
128395608 | pole | HFTD Tier 2 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128395624 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128395667 | pole | Non-HFTD | Transmission | 2024-03-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
128397064 | other | Non-HFTD | Transmission | 2024-04-01 | 2027-04-01 | Level 2 | E |  | 2027-04-01 | Level 2
128397067 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-05-10 | 2025-04-01 | Level 2 | GO 165 Inspection
128397139 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128397845 | other | Non-HFTD | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-08-12 | 2025-04-01 | Level 2 | GO 165 Inspection
128401658 | switch | Non-HFTD | Transmission | 2024-04-01 | 2024-07-01 | Level 2 | E | 2024-11-26 | 2024-07-01 | Level 2 | Field Safety Reassessment
128403634 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F | 2024-06-04 | 2029-04-01 | Level 3 | GO 165 Inspection
128403660 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-06-04 | 2025-04-01 | Level 2 | GO 165 Inspection
128404071 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128410216 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-05-28 | 2025-04-01 | Level 2 | GO 165 Inspection
128410466 | pole | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128410472 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128412001 | other | Non-HFTD | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128414081 | pole | Non-HFTD | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128414551 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128414576 | pole | Non-HFTD | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-06-19 | 2025-04-01 | Level 2 | GO 165 Inspection
128414828 | other | HFTD Tier 3 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128415275 | pole | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-05-16 | 2025-04-01 | Level 2 | GO 165 Inspection
128415393 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128415438 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128415479 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128415482 | pole | Non-HFTD | Transmission | 2024-04-01 | 2027-04-01 | Level 2 | E |  | 2027-04-01 | Level 2
128415745 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128415824 | pole | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128415924 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128415929 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128415930 | other | Non-HFTD | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F | 2024-11-18 | 2029-03-21 | Level 3 | GO 165 Inspection
128415968 | other | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128415989 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128416005 | pole | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E | 2024-09-03 | 2027-03-21 | Level 2 | GO 165 Inspection
128416015 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128416068 | other | Non-HFTD | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128416154 | pole | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128416172 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-21 | 2025-03-21 | Level 2 | E |  | 2025-03-21 | Level 2
128416176 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128416206 | other | HFTD Tier 3 | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F |  | 2029-03-19 | Level 3
128416273 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128416275 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128416338 | switch | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128416404 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-08-13 | 2029-03-20 | Level 3 | GO 165 Inspection
128416461 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128416643 | other | Non-HFTD | Transmission | 2024-03-19 | 2029-03-19 | Level 3 | F | 2024-10-22 | 2029-03-19 | Level 3 | GO 165 Inspection
128416681 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-10-25 | 2029-03-20 | Level 3 | GO 165 Inspection
128416711 | other | Non-HFTD | Transmission | 2024-03-20 | 2027-03-20 | Level 2 | E | 2024-08-12 | 2027-03-20 | Level 2 | GO 165 Inspection
128416772 | pole | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F | 2024-06-26 | 2029-03-20 | Level 3 | GO 165 Inspection
128416775 | other | Non-HFTD | Transmission | 2024-03-20 | 2029-03-20 | Level 3 | F |  | 2029-03-20 | Level 3
128416795 | insulator and brushing | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E | 2024-10-26 | 2027-03-19 | Level 2 | GO 165 Inspection
128418107 | pole | Non-HFTD | Transmission | 2024-03-19 | 2024-06-19 | Level 2 | E | 2024-10-24 | 2024-06-19 | Level 2 | GO 165 Inspection
128418110 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-10-18 | 2027-04-02 | Level 2 | GO 165 Inspection
128418351 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128418524 | pole | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128418783 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128418833 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128418851 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128419147 | other | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128419487 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128419670 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128419719 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-10-31 | 2027-04-02 | Level 2 | GO 165 Inspection
128419764 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128419856 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128419955 | pole | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128419978 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128420135 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128420186 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E | 2024-07-20 | 2025-04-02 | Level 2 | Field Safety Reassessment
128420460 | pole | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128420531 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128420745 | pole | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-06-18 | 2027-04-02 | Level 2 | GO 165 Inspection
128420933 | other | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128421611 | other | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128423841 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F | 2024-07-08 | 2029-04-02 | Level 3 | GO 165 Inspection
128423847 | pole | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E | 2024-06-08 | 2025-04-02 | Level 2 | GO 165 Inspection
128424384 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128424393 | pole | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-07-08 | 2027-04-02 | Level 2 | GO 165 Inspection
128427690 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128428098 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F | 2024-07-20 | 2029-04-02 | Level 3 | Field Safety Reassessment
128429132 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128429177 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-04-19 | 2025-04-01 | Level 2 | GO 165 Inspection
128429442 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128429456 | other | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E | 2024-12-09 | 2024-06-20 | Level 2 | Field Safety Reassessment
128429902 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128429918 | other | HFTD Tier 2 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128429927 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128429947 | pole | Non-HFTD | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F | 2024-11-07 | 2029-03-21 | Level 3 | GO 165 Inspection
128429953 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128429987 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128429998 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128430088 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-22 | 2024-09-22 | Level 2 | E | 2024-09-19 | 2025-03-22 | Level 2 | Field Safety Reassessment
128430089 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
128430120 | insulator and brushing | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E |  | 2027-03-29 | Level 2
128430130 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-22 | 2025-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128430157 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128430249 | crossarm | HFTD Tier 3 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F | 2024-04-20 | 2029-04-01 | Level 3 | GO 165 Inspection
128430275 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-21 | 2024-09-21 | Level 2 | E | 2024-08-29 | 2024-09-21 | Level 2 | Field Safety Reassessment
128430282 | other | Non-HFTD | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128430292 | other | Non-HFTD | Transmission | 2024-03-19 | 2027-03-19 | Level 2 | E | 2024-10-26 | 2027-03-19 | Level 2 | GO 165 Inspection
128430295 | insulator and brushing | Non-HFTD | Transmission | 2024-03-15 | 2025-03-15 | Level 3 | F | 2024-09-11 | 2029-03-15 | Level 3 | GO 165 Inspection
128430304 | other | HFTD Tier 3 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128430321 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128430325 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128430354 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F |  | 2029-03-25 | Level 3
128430362 | pole | Non-HFTD | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128430385 | other | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128430431 | pole | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E | 2024-09-03 | 2027-03-21 | Level 2 | GO 165 Inspection
128430471 | anchor/guy | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-08-16 | 2027-04-02 | Level 2 | GO 165 Inspection
128430475 | other | Non-HFTD | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F | 2024-05-21 | 2029-03-22 | Level 3 | GO 165 Inspection
128430485 | other | HFTD Tier 3 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128430491 | other | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128430542 | anchor/guy | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128430606 | pole | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128433779 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128433823 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128433890 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
128433947 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128435840 | other | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F | 2024-04-30 | 2029-04-03 | Level 3 | GO 165 Inspection
128435935 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128435938 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128436445 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128437926 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128437985 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128438134 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128438222 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128438537 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128438764 | other | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128438966 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128439512 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439583 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128439592 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128439668 | anchor/guy | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439674 | other | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439689 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439700 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439760 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439834 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128439870 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128439889 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128440007 | other | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128440009 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128440047 | other | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F | 2024-06-22 | 2029-04-03 | Level 3 | GO 165 Inspection
128440049 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128442617 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128442731 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128442815 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128442987 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128443018 | other | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128443071 | other | HFTD Tier 3 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F |  | 2029-03-25 | Level 3
128443072 | other | HFTD Tier 3 | Transmission | 2024-03-21 | 2029-03-21 | Level 3 | F |  | 2029-03-21 | Level 3
128443204 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128443230 | other | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E | 2024-11-06 | 2027-03-21 | Level 2 | GO 165 Inspection
128443235 | insulator and brushing | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E | 2024-11-06 | 2027-03-21 | Level 2 | GO 165 Inspection
128443255 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128443265 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-25 | 2024-09-25 | Level 2 | E | 2024-08-30 | 2024-09-25 | Level 2 | Field Safety Reassessment
128443269 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128443278 | other | HFTD Tier 3 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128443319 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128443321 | other | Non-HFTD | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F |  | 2029-03-22 | Level 3
128443372 | anchor/guy | Non-HFTD | Transmission | 2024-03-21 | 2027-03-21 | Level 2 | E |  | 2027-03-21 | Level 2
128443375 | other | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-10-08 | 2029-03-25 | Level 3 | GO 165 Inspection
128443420 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-06-03 | 2029-03-25 | Level 3 | GO 165 Inspection
128443429 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F | 2024-05-23 | 2029-03-26 | Level 3 | GO 165 Inspection
128443431 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128443478 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128443482 | pole | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128443501 | insulator and brushing | Non-HFTD | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E | 2024-09-11 | 2027-03-18 | Level 2 | GO 165 Inspection
128443517 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2024-09-26 | Level 2 | E | 2024-10-04 | 2024-09-26 | Level 2 | Field Safety Reassessment
128443601 | insulator and brushing | Non-HFTD | Transmission | 2024-03-25 | 2027-03-25 | Level 2 | E | 2024-08-19 | 2027-03-25 | Level 2 | GO 165 Inspection
128443602 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-05-30 | 2029-03-25 | Level 3 | GO 165 Inspection
128443612 | insulator and brushing | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-08-12 | 2027-03-29 | Level 2 | GO 165 Inspection
128443624 | anchor/guy | Non-HFTD | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128443661 | other | Non-HFTD | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-08-19 | 2029-03-25 | Level 3 | GO 165 Inspection
128443744 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E | 2024-09-09 | 2027-04-03 | Level 2 | GO 165 Inspection
128443745 | pole | Non-HFTD | Transmission | 2024-03-22 | 2029-03-22 | Level 3 | F | 2024-10-10 | 2029-03-22 | Level 3 | GO 165 Inspection
128443746 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E | 2024-09-10 | 2027-04-03 | Level 2 | GO 165 Inspection
128443748 | other | Non-HFTD | Transmission | 2024-03-25 | 2027-03-25 | Level 2 | E | 2024-10-09 | 2027-03-25 | Level 2 | GO 165 Inspection
128443752 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128443766 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128443812 | other | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128443821 | pole | Non-HFTD | Transmission | 2024-03-22 | 2027-03-22 | Level 2 | E |  | 2025-03-22 | Level 2
128443843 | anchor/guy | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128443851 | pole | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128443867 | other | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128443983 | other | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128444309 | other | HFTD Tier 2 | Transmission | 2024-03-15 | 2029-03-15 | Level 3 | F |  | 2029-03-15 | Level 3
128444435 | other | Non-HFTD | Transmission | 2024-03-18 | 2027-03-18 | Level 2 | E |  | 2027-03-18 | Level 2
128444782 | other | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128444808 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128444984 | pole | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128445155 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128445545 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128447710 | crossarm | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128447732 | other | HFTD Tier 3 | Transmission | 2024-04-04 | 2024-10-04 | Level 2 | E |  | 2024-10-04 | Level 2
128447744 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128447848 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128448008 | other | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-04-24 | 2027-04-04 | Level 2 | GO 165 Inspection
128448138 | anchor/guy | Non-HFTD | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F | 2024-07-12 | 2029-04-04 | Level 3 | GO 165 Inspection
128448589 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E | 2024-05-28 | 2025-04-04 | Level 2 | GO 165 Inspection
128448615 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128448721 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128448844 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-07-11 | 2027-04-04 | Level 2 | GO 165 Inspection
128448847 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128448848 | pole | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128448939 | other | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-04-24 | 2027-04-04 | Level 2 | GO 165 Inspection
128448966 | pole | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128449689 | pole | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-04-23 | 2027-04-04 | Level 2 | GO 165 Inspection
128449761 | pole | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-05-30 | 2029-03-25 | Level 3 | GO 165 Inspection
128449765 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-03-25 | 2029-03-25 | Level 3 | F | 2024-05-30 | 2029-03-25 | Level 3 | GO 165 Inspection
128449767 | other | HFTD Tier 2 | Transmission | 2024-03-25 | 2025-03-25 | Level 2 | E | 2024-05-30 | 2025-03-25 | Level 2 | GO 165 Inspection
128451621 | pole | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-05-23 | 2025-04-04 | Level 2 | GO 165 Inspection
128451633 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128451720 | other | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128451927 | other | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128451954 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128452045 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128452210 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128454161 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128454207 | other | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128454261 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E | 2024-05-24 | 2025-04-04 | Level 2 | GO 165 Inspection
128454266 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E | 2024-05-21 | 2025-04-04 | Level 2 | GO 165 Inspection
128454338 | pole | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E | 2024-05-18 | 2025-04-04 | Level 2 | GO 165 Inspection
128454388 | pole | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-09-06 | 2027-04-04 | Level 2 | GO 165 Inspection
128454458 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128456881 | other | HFTD Tier 3 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128457009 | pole | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E | 2024-04-23 | 2027-04-05 | Level 2 | GO 165 Inspection
128457446 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128457527 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F | 2024-05-02 | 2029-03-26 | Level 3 | GO 165 Inspection
128457617 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128457688 | other | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128457796 | pole | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
128457833 | anchor/guy | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E | 2024-05-31 | 2027-04-05 | Level 2 | GO 165 Inspection
128459889 | crossarm | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128459936 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128461140 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128461508 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F | 2024-05-07 | 2029-03-27 | Level 3 | GO 165 Inspection
128461809 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2024-09-26 | Level 2 | E |  | 2024-09-26 | Level 2
128462086 | other | HFTD Tier 3 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128462231 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128462269 | anchor/guy | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E | 2024-04-17 | 2027-04-05 | Level 2 | GO 165 Inspection
128462960 | anchor/guy | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E | 2024-04-22 | 2027-04-05 | Level 2 | GO 165 Inspection
128463573 | other | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128463994 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128464035 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128464039 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128464139 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128464169 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2027-03-26 | Level 2 | E |  | 2027-03-26 | Level 2
128464264 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-03-27 | 2024-09-27 | Level 2 | E | 2024-08-30 | 2024-09-27 | Level 2 | Field Safety Reassessment
128464461 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2027-03-26 | Level 2 | E | 2024-05-29 | 2025-03-26 | Level 2 | GO 165 Inspection
128464840 | other | Non-HFTD | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128464843 | other | HFTD Tier 2 | Transmission | 2024-03-26 | 2029-03-26 | Level 3 | F |  | 2029-03-26 | Level 3
128464847 | other | Non-HFTD | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128465198 | pole | HFTD Tier 3 | Transmission | 2024-03-26 | 2024-09-26 | Level 2 | E | 2024-09-02 | 2024-09-26 | Level 2 | Field Safety Reassessment
128465279 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128465595 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128465632 | other | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128465695 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128465850 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128466329 | other | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F | 2024-05-29 | 2029-04-05 | Level 3 | GO 165 Inspection
128466341 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128466345 | pole | Non-HFTD | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F | 2024-10-28 | 2029-04-04 | Level 3 | GO 165 Inspection
128466584 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128466649 | other | Non-HFTD | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128466692 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128466779 | pole | HFTD Tier 3 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128466794 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128466962 | other | Non-HFTD | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128467126 | other | HFTD Tier 3 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128467128 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128467129 | pole | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128467192 | other | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128467262 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-05 | 2024-10-05 | Level 2 | E | 2024-12-20 | 2024-10-05 | Level 2 | Field Safety Reassessment
128467271 | pole | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128467314 | other | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F | 2024-05-07 | 2029-03-27 | Level 3 | GO 165 Inspection
128468719 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F |  | 2029-04-06 | Level 3
128468816 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F |  | 2029-04-06 | Level 3
128468827 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F |  | 2029-04-06 | Level 3
128468830 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128468858 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128468859 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128468881 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2027-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469003 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469030 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469082 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F | 2024-06-03 | 2029-04-06 | Level 3 | GO 165 Inspection
128469101 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E | 2024-06-03 | 2025-04-06 | Level 2 | GO 165 Inspection
128469104 | other | Non-HFTD | Transmission | 2024-04-06 | 2027-04-06 | Level 2 | E | 2024-04-22 | 2027-04-06 | Level 2 | GO 165 Inspection
128469113 | other | Non-HFTD | Transmission | 2024-04-06 | 2027-04-06 | Level 2 | E | 2024-04-17 | 2027-04-06 | Level 2 | GO 165 Inspection
128469139 | other | Non-HFTD | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F | 2024-04-22 | 2029-04-06 | Level 3 | GO 165 Inspection
128469156 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F | 2024-06-03 | 2029-04-06 | Level 3 | GO 165 Inspection
128469242 | anchor/guy | Non-HFTD | Transmission | 2024-04-06 | 2027-04-06 | Level 2 | E | 2024-04-17 | 2027-04-06 | Level 2 | GO 165 Inspection
128469254 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469262 | pole | HFTD Tier 3 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F | 2024-07-21 | 2029-04-06 | Level 3 | Field Safety Reassessment
128469298 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E | 2024-06-04 | 2025-04-06 | Level 2 | GO 165 Inspection
128469365 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F |  | 2029-04-06 | Level 3
128469459 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469496 | pole | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469587 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F |  | 2029-04-06 | Level 3
128469644 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2029-04-06 | Level 3 | F |  | 2029-04-06 | Level 3
128469660 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 2 | E |  | 2025-04-06 | Level 2
128469781 | other | HFTD Tier 2 | Transmission | 2024-04-06 | 2025-04-06 | Level 3 | F | 2024-05-23 | 2029-04-06 | Level 3 | GO 165 Inspection
128470259 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128471074 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128471078 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
128471219 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128471619 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128471658 | pole | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128471785 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128471860 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E | 2024-05-21 | 2025-04-08 | Level 2 | GO 165 Inspection
128472409 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128472543 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-09-09 | 2029-04-08 | Level 3 | GO 165 Inspection
128472551 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E | 2024-09-09 | 2027-04-08 | Level 2 | GO 165 Inspection
128472683 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128473617 | anchor/guy | Non-HFTD | Transmission | 2024-04-08 | 2025-04-08 | Level 3 | F | 2024-09-09 | 2029-04-08 | Level 3 | GO 165 Inspection
128473688 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-06-04 | 2029-04-08 | Level 3 | GO 165 Inspection
128473699 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128473730 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128473912 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128473960 | pole | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E | 2024-05-30 | 2027-04-08 | Level 2 | GO 165 Inspection
128474063 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E | 2024-07-20 | 2025-04-08 | Level 2 | Field Safety Reassessment
128474084 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128474085 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128474248 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128474313 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128474363 | anchor/guy | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E | 2024-05-30 | 2027-04-08 | Level 2 | GO 165 Inspection
128474420 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128474464 | pole | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E | 2024-09-09 | 2027-04-08 | Level 2 | GO 165 Inspection
128474629 | pole | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128474682 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-06-05 | 2029-04-08 | Level 3 | GO 165 Inspection
128474687 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-05-09 | 2029-04-08 | Level 3 | GO 165 Inspection
128475637 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128477663 | pole | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128477665 | pole | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E | 2024-09-06 | 2027-04-08 | Level 2 | GO 165 Inspection
128479109 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-09-06 | 2029-04-08 | Level 3 | GO 165 Inspection
128482228 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128484308 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128484543 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128485452 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128486501 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E | 2024-04-25 | 2025-04-08 | Level 2 | GO 165 Inspection
128487604 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-27 | 2025-03-27 | Level 2 | E |  | 2025-03-27 | Level 2
128488463 | other | HFTD Tier 3 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128491817 | insulator and brushing | Non-HFTD | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F | 2024-09-12 | 2029-03-29 | Level 3 | GO 165 Inspection
128492365 | pole | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128492427 | anchor/guy | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-11-04 | 2027-03-29 | Level 2 | GO 165 Inspection
128492428 | other | Non-HFTD | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F | 2024-07-09 | 2029-03-29 | Level 3 | GO 165 Inspection
128492492 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128492527 | anchor/guy | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-11-04 | 2027-03-29 | Level 2 | GO 165 Inspection
128492553 | anchor/guy | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-11-04 | 2027-03-29 | Level 2 | GO 165 Inspection
128492617 | pole | HFTD Tier 3 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128492735 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128493463 | other | Non-HFTD | Transmission | 2024-03-27 | 2025-03-27 | Level 2 | E |  | 2025-03-27 | Level 2
128493538 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128493572 | other | Non-HFTD | Transmission | 2024-03-28 | 2027-03-28 | Level 2 | E | 2024-10-26 | 2027-03-28 | Level 2 | GO 165 Inspection
128493596 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128494477 | anchor/guy | HFTD Tier 2 | Transmission | 2024-03-27 | 2029-03-27 | Level 3 | F |  | 2029-03-27 | Level 3
128496929 | other | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E |  | 2027-04-09 | Level 2
128497164 | anchor/guy | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E | 2024-05-31 | 2027-04-09 | Level 2 | GO 165 Inspection
128497239 | anchor/guy | Non-HFTD | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-09-09 | 2025-04-09 | Level 2 | GO 165 Inspection
128497250 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E | 2024-09-12 | 2025-04-09 | Level 2 | GO 165 Inspection
128497324 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128497466 | crossarm | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128497602 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128497686 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-09-09 | 2029-04-09 | Level 3 | GO 165 Inspection
128497689 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128497814 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-05-16 | 2025-04-09 | Level 2 | GO 165 Inspection
128498020 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128498154 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-06-04 | 2029-04-09 | Level 3 | GO 165 Inspection
128498184 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-06-04 | 2025-04-09 | Level 2 | GO 165 Inspection
128498243 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128498289 | anchor/guy | Non-HFTD | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-06-05 | 2025-04-09 | Level 2 | GO 165 Inspection
128498378 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128498386 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128498601 | anchor/guy | Non-HFTD | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-09-09 | 2025-04-09 | Level 2 | GO 165 Inspection
128498602 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-09-09 | 2029-04-09 | Level 3 | GO 165 Inspection
128498810 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128499171 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128499267 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-04-23 | 2029-04-09 | Level 3 | GO 165 Inspection
128499498 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128499569 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128499725 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128499787 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128499835 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E | 2024-09-12 | 2027-04-09 | Level 2 | GO 165 Inspection
128499886 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128499897 | pole | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E |  | 2027-04-09 | Level 2
128500048 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128500114 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128500118 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128500154 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128500189 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128500195 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-05-01 | 2029-04-09 | Level 3 | GO 165 Inspection
128500217 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-05-29 | 2025-04-09 | Level 2 | GO 165 Inspection
128500311 | pole | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-04-30 | 2025-04-01 | Level 2 | GO 165 Inspection
128500355 | pole | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-04-23 | 2025-04-01 | Level 2 | GO 165 Inspection
128500362 | anchor/guy | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E |  | 2027-03-29 | Level 2
128500371 | other | HFTD Tier 3 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128500384 | other | Non-HFTD | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128500397 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F | 2024-04-23 | 2029-04-01 | Level 3 | GO 165 Inspection
128500495 | other | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-10-11 | 2027-03-29 | Level 2 | GO 165 Inspection
128500504 | other | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E | 2024-04-23 | 2025-04-01 | Level 2 | GO 165 Inspection
128500518 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128500525 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128500602 | pole | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128500613 | other | Non-HFTD | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F | 2024-10-18 | 2029-03-29 | Level 3 | GO 165 Inspection
128500622 | other | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-10-25 | 2027-03-29 | Level 2 | GO 165 Inspection
128500662 | other | Non-HFTD | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128500663 | other | Non-HFTD | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F | 2024-10-18 | 2029-03-29 | Level 3 | GO 165 Inspection
128500666 | other | Non-HFTD | Transmission | 2024-03-29 | 2029-03-29 | Level 3 | F | 2024-10-25 | 2029-03-29 | Level 3 | GO 165 Inspection
128500669 | other | Non-HFTD | Transmission | 2024-03-29 | 2027-03-29 | Level 2 | E | 2024-08-13 | 2027-03-29 | Level 2 | GO 165 Inspection
128510224 | other | HFTD Tier 2 | Transmission | 2024-03-29 | 2025-03-29 | Level 2 | E | 2024-04-30 | 2025-03-29 | Level 2 | GO 165 Inspection
128510239 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128510402 | pole | HFTD Tier 2 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F | 2024-04-30 | 2029-04-01 | Level 3 | GO 165 Inspection
128510856 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E | 2024-06-05 | 2025-04-10 | Level 2 | GO 165 Inspection
128510910 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128510912 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128511056 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128511182 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128511541 | pole | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-05-15 | 2027-04-10 | Level 2 | GO 165 Inspection
128511783 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128511812 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128511823 | other | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128511914 | other | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128512111 | other | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F | 2024-09-12 | 2029-04-10 | Level 3 | GO 165 Inspection
128512168 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F | 2024-05-22 | 2029-04-10 | Level 3 | GO 165 Inspection
128512555 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128512556 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128512557 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128512681 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128515032 | pole | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-09-10 | 2025-04-10 | Level 2 | GO 165 Inspection
128515134 | insulator and brushing | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-10-11 | 2027-04-10 | Level 2 | GO 165 Inspection
128515279 | anchor/guy | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F | 2024-06-28 | 2029-04-10 | Level 3 | GO 165 Inspection
128517232 | insulator and brushing | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-09-12 | 2027-04-10 | Level 2 | GO 165 Inspection
128517597 | other | HFTD Tier 3 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128518829 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128518847 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128518860 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128519070 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128519132 | insulator and brushing | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-05-20 | 2027-04-10 | Level 2 | GO 165 Inspection
128519203 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128519358 | insulator and brushing | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-05-30 | 2027-04-10 | Level 2 | GO 165 Inspection
128519396 | other | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F | 2024-06-26 | 2029-04-10 | Level 3 | GO 165 Inspection
128519503 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128519527 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128519550 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128519634 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128519698 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128520000 | crossarm | HFTD Tier 2 | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128520002 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128520054 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128520058 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128520111 | other | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F | 2024-05-29 | 2029-04-10 | Level 3 | GO 165 Inspection
128525419 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128525501 | pole | Non-HFTD | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128525742 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128526398 | other | HFTD Tier 3 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128528059 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E | 2024-05-21 | 2025-04-11 | Level 2 | GO 165 Inspection
128528332 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E | 2024-10-24 | 2024-10-10 | Level 2 | Field Safety Reassessment
128528884 | other | HFTD Tier 3 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128529117 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128529800 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128529824 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128530274 | other | Non-HFTD | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128531619 | other | Non-HFTD | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128531974 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128532371 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F | 2024-07-20 | 2029-04-11 | Level 3 | Field Safety Reassessment
128532568 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F | 2024-07-20 | 2029-04-11 | Level 3 | Field Safety Reassessment
128532684 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128532781 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128532856 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128533195 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128533371 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E | 2024-05-21 | 2025-04-10 | Level 2 | GO 165 Inspection
128533434 | other | Non-HFTD | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128533507 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128534278 | other | Non-HFTD | Transmission | 2024-04-11 | 2027-04-11 | Level 2 | E |  | 2027-04-11 | Level 2
128534666 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F | 2024-05-02 | 2029-04-11 | Level 3 | GO 165 Inspection
128534722 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E | 2024-05-06 | 2025-04-11 | Level 2 | GO 165 Inspection
128534759 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128534776 | crossarm | HFTD Tier 3 | Transmission | 2024-04-02 | 2024-10-02 | Level 2 | E | 2024-09-30 | 2024-10-02 | Level 2 | Field Safety Reassessment
128534900 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128534904 | pole | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128534966 | anchor/guy | Non-HFTD | Transmission | 2024-04-01 | 2027-04-01 | Level 2 | E |  | 2027-04-01 | Level 2
128534982 | other | HFTD Tier 3 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128535001 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128535042 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2027-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128535100 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128535125 | pole | HFTD Tier 3 | Transmission | 2024-04-02 | 2024-10-02 | Level 2 | E |  | 2024-10-02 | Level 2
128535171 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128535193 | other | Non-HFTD | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128535197 | anchor/guy | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128535204 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128535241 | other | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F | 2024-04-19 | 2029-04-02 | Level 3 | GO 165 Inspection
128535258 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128535347 | other | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128535348 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128535355 | other | HFTD Tier 3 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128535401 | other | HFTD Tier 3 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128535402 | pole | HFTD Tier 3 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128535487 | other | Non-HFTD | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F | 2024-11-01 | 2029-04-01 | Level 3 | GO 165 Inspection
128535574 | anchor/guy | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128535578 | other | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-08-07 | 2027-04-02 | Level 2 | GO 165 Inspection
128535589 | other | HFTD Tier 3 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128535631 | other | HFTD Tier 3 | Transmission | 2024-04-01 | 2029-04-01 | Level 3 | F |  | 2029-04-01 | Level 3
128535660 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128535689 | anchor/guy | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-10-31 | 2027-04-02 | Level 2 | GO 165 Inspection
128535701 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128535704 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
128535777 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128536069 | crossarm | HFTD Tier 2 | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128536201 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128536281 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-09-16 | 2027-04-02 | Level 2 | GO 165 Inspection
128537121 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128537165 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128537333 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128537522 | other | Non-HFTD | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128537579 | pole | HFTD Tier 2 | Transmission | 2024-04-12 | 2027-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128537878 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128537946 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E | 2024-04-20 | 2025-04-12 | Level 2 | GO 165 Inspection
128538123 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128538243 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128538383 | pole | HFTD Tier 3 | Transmission | 2024-04-02 | 2024-10-02 | Level 2 | E | 2024-10-11 | 2024-10-02 | Level 2 | Field Safety Reassessment
128538384 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-02 | 2024-07-02 | Level 2 | E |  | 2024-07-02 | Level 2
128538385 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-02 | 2024-10-02 | Level 2 | E |  | 2024-10-02 | Level 2
128538589 | pole | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128538608 | pole | HFTD Tier 2 | Transmission | 2024-04-12 | 2027-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128538618 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128538770 | other | HFTD Tier 3 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128538799 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128538974 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F | 2024-07-20 | 2029-04-12 | Level 3 | Field Safety Reassessment
128539317 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128539348 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128539407 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E |  | 2027-04-02 | Level 2
128539725 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128539754 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2027-04-12 | Level 2 | E | 2024-10-31 | 2025-04-12 | Level 2 | GO 165 Inspection
128540054 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128540218 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128540315 | pole | HFTD Tier 2 | Transmission | 2024-04-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
128540432 | anchor/guy | Non-HFTD | Transmission | 2024-04-12 | 2027-04-12 | Level 2 | E | 2024-05-29 | 2027-04-12 | Level 2 | GO 165 Inspection
128540479 | anchor/guy | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F | 2024-09-05 | 2029-04-03 | Level 3 | GO 165 Inspection
128540501 | pole | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E | 2024-10-09 | 2027-04-09 | Level 2 | GO 165 Inspection
128540657 | pole | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128540802 | anchor/guy | Non-HFTD | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128540844 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128540941 | pole | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128540981 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128541290 | pole | Non-HFTD | Transmission | 2024-03-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
128541331 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128541381 | other | Non-HFTD | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128541440 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E |  | 2027-04-09 | Level 2
128541446 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128541449 | other | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128541455 | other | Non-HFTD | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128541468 | pole | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E |  | 2025-04-12 | Level 2
128541491 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128541551 | pole | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128541553 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128541560 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128541619 | other | Non-HFTD | Transmission | 2024-04-12 | 2027-04-12 | Level 2 | E | 2024-09-17 | 2027-04-12 | Level 2 | GO 165 Inspection
128541632 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128541887 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-12 | 2025-04-12 | Level 2 | E | 2024-07-20 | 2025-04-12 | Level 2 | Field Safety Reassessment
128541919 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128541923 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128541936 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128541939 | other | Non-HFTD | Transmission | 2024-04-12 | 2027-04-12 | Level 2 | E | 2024-05-29 | 2027-04-12 | Level 2 | GO 165 Inspection
128541971 | anchor/guy | Non-HFTD | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128541974 | other | HFTD Tier 3 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128542064 | other | HFTD Tier 3 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128542078 | pole | Non-HFTD | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128542126 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128542128 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-07-01 | 2029-04-08 | Level 3 | GO 165 Inspection
128542133 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128542136 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128542203 | other | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-10-15 | 2027-04-02 | Level 2 | GO 165 Inspection
128542210 | other | HFTD Tier 3 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128544194 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128544232 | other | HFTD Tier 2 | Transmission | 2024-04-12 | 2029-04-12 | Level 3 | F |  | 2029-04-12 | Level 3
128544907 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128544993 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128545351 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128545449 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128545483 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128545489 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128545607 | other | HFTD Tier 3 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128545686 | other | HFTD Tier 3 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128546113 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128546117 | insulator and brushing | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128546180 | pole | Non-HFTD | Transmission | 2022-11-29 | 2023-11-29 | Level 2 | E | 2024-05-05 | 2025-11-29 | Level 2 | Standards change
128546411 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128546570 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128546571 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128546818 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128546838 | other | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128546916 | other | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128546936 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128546957 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128547121 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128547251 | other | Non-HFTD | Transmission | 2024-04-15 | 2027-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548033 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128548163 | pole | HFTD Tier 3 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128548171 | pole | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548248 | insulator and brushing | Non-HFTD | Transmission | 2024-04-15 | 2027-04-15 | Level 2 | E | 2024-08-20 | 2027-04-15 | Level 2 | GO 165 Inspection
128548333 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548390 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128548399 | other | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F | 2024-08-28 | 2029-04-15 | Level 3 | GO 165 Inspection
128548407 | anchor/guy | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128548437 | other | HFTD Tier 3 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128548443 | other | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548476 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128548518 | pole | HFTD Tier 2 | Transmission | 2024-04-03 | 2025-04-03 | Level 2 | E |  | 2025-04-03 | Level 2
128548530 | other | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128548560 | pole | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128548571 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548619 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548674 | pole | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128548678 | switch | HFTD Tier 2 | Transmission | 2024-04-05 | 2024-10-05 | Level 2 | E | 2024-08-29 | 2024-10-05 | Level 2 | Field Safety Reassessment
128548686 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128548695 | pole | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548696 | pole | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128548706 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128548715 | other | Non-HFTD | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128548815 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128548827 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-05 | 2024-10-05 | Level 2 | E | 2024-10-01 | 2024-10-05 | Level 2 | Field Safety Reassessment
128548878 | other | HFTD Tier 3 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128548894 | pole | HFTD Tier 3 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128548914 | other | HFTD Tier 3 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128548942 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128548991 | pole | HFTD Tier 2 | Transmission | 2024-04-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
128549015 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F | 2024-08-15 | 2029-04-02 | Level 3 | GO 165 Inspection
128549021 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128549037 | other | HFTD Tier 2 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128549076 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128549085 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128549102 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128549115 | other | HFTD Tier 3 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128549122 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128549165 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-04 | 2024-10-04 | Level 2 | E | 2024-10-01 | 2025-04-04 | Level 2 | Field Safety Reassessment
128549192 | pole | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F |  | 2029-04-02 | Level 3
128549198 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128549264 | other | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128549273 | pole | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128549469 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128549483 | anchor/guy | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128549502 | other | Non-HFTD | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128549525 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2024-06-10 | Level 2 | E |  | 2024-06-10 | Level 2
128549528 | other | HFTD Tier 2 | Transmission | 2023-06-10 | 2024-06-10 | Level 2 | E |  | 2024-06-10 | Level 2
128549571 | insulator and brushing | Non-HFTD | Transmission | 2024-04-16 | 2027-04-16 | Level 2 | E |  | 2027-04-16 | Level 2
128549575 | switch | Non-HFTD | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128549979 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128550147 | anchor/guy | Non-HFTD | Transmission | 2024-04-16 | 2024-04-16 | Level 2 | E |  | 2027-04-16 | Level 2
128550167 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128550483 | other | Non-HFTD | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F | 2024-08-20 | 2029-04-16 | Level 3 | GO 165 Inspection
128550582 | other | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128550967 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128551013 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128552024 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128553427 | pole | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128553639 | insulator and brushing | Non-HFTD | Transmission | 2024-04-16 | 2027-04-16 | Level 2 | E |  | 2027-04-16 | Level 2
128553706 | other | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128553794 | other | Non-HFTD | Transmission | 2024-04-16 | 2027-04-16 | Level 2 | E |  | 2027-04-16 | Level 2
128554192 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128554214 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128554221 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128554230 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128554410 | pole | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128554457 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128554655 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128555034 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E | 2024-05-17 | 2025-04-16 | Level 2 | GO 165 Inspection
128555056 | other | Non-HFTD | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128555105 | anchor/guy | Non-HFTD | Transmission | 2024-04-16 | 2027-04-16 | Level 2 | E |  | 2027-04-16 | Level 2
128555159 | pole | HFTD Tier 3 | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128555308 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128555316 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128555318 | other | HFTD Tier 3 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128555391 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-08-28 | 2029-04-09 | Level 3 | GO 165 Inspection
128555395 | pole | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128555419 | anchor/guy | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E | 2024-06-24 | 2027-04-05 | Level 2 | GO 165 Inspection
128555421 | other | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E |  | 2027-04-09 | Level 2
128555425 | other | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E |  | 2027-04-09 | Level 2
128555471 | other | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128555477 | other | HFTD Tier 3 | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128555498 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128555517 | other | HFTD Tier 3 | Transmission | 2024-04-05 | 2029-10-05 | Level 3 | F |  | 2029-04-05 | Level 3
128555521 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E | 2024-10-03 | 2027-04-09 | Level 2 | GO 165 Inspection
128555654 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-07-12 | 2029-04-09 | Level 3 | GO 165 Inspection
128555682 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128555690 | anchor/guy | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E | 2024-10-28 | 2027-04-04 | Level 2 | GO 165 Inspection
128555724 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128555741 | conductor | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128555785 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128555797 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128555821 | other | Non-HFTD | Transmission | 2024-04-09 | 2027-04-09 | Level 2 | E | 2024-10-14 | 2027-04-09 | Level 2 | GO 165 Inspection
128555822 | insulator and brushing | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-10-14 | 2029-04-09 | Level 3 | GO 165 Inspection
128555831 | other | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128555848 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128555860 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128555875 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128555877 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128555901 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128555903 | pole | Non-HFTD | Transmission | 2024-04-03 | 2029-04-03 | Level 3 | F |  | 2029-04-03 | Level 3
128555907 | other | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128555930 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2027-04-04 | Level 2 | E |  | 2027-04-04 | Level 2
128555933 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128555944 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128555950 | switch | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128556270 | pole | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128556603 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128556604 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128556633 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128556667 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128556692 | other | Non-HFTD | Transmission | 2024-04-17 | 2027-04-17 | Level 2 | E |  | 2027-04-17 | Level 2
128556700 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128556721 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128556837 | other | Non-HFTD | Transmission | 2024-04-17 | 2027-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128556893 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128556897 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128558478 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128559976 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128560836 | pole | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128561004 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128561013 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128561093 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128566722 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128566844 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128566980 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128567022 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128567028 | other | HFTD Tier 2 | Transmission | 2024-03-28 | 2029-03-28 | Level 3 | F |  | 2029-03-28 | Level 3
128567456 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567535 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567536 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567595 | anchor/guy | Non-HFTD | Transmission | 2024-04-17 | 2027-04-17 | Level 2 | E |  | 2027-04-17 | Level 2
128567655 | conductor | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128567662 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128567709 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E | 2024-05-18 | 2025-04-17 | Level 2 | GO 165 Inspection
128567757 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128567759 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128567762 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128567763 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128567765 | other | HFTD Tier 2 | Transmission | 2024-04-05 | 2025-04-05 | Level 2 | E |  | 2025-04-05 | Level 2
128567769 | other | Non-HFTD | Transmission | 2024-04-02 | 2029-04-02 | Level 3 | F | 2024-08-28 | 2029-04-02 | Level 3 | GO 165 Inspection
128567780 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E | 2024-05-18 | 2025-04-17 | Level 2 | GO 165 Inspection
128567834 | other | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128567844 | insulator and brushing | Non-HFTD | Transmission | 2024-04-02 | 2027-04-02 | Level 2 | E | 2024-08-28 | 2027-04-02 | Level 2 | GO 165 Inspection
128567853 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567898 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567900 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F |  | 2029-04-09 | Level 3
128567906 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128567907 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567923 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128567941 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128567945 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128567948 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128567961 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128567990 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128568036 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128568038 | insulator and brushing | Non-HFTD | Transmission | 2024-04-03 | 2027-04-03 | Level 2 | E |  | 2027-04-03 | Level 2
128568118 | insulator and brushing | Non-HFTD | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F |  | 2029-04-04 | Level 3
128568162 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128568178 | other | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128568194 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128568211 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-06-13 | 2029-04-09 | Level 3 | GO 165 Inspection
128568304 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E | 2024-10-18 | 2027-04-05 | Level 2 | GO 165 Inspection
128568343 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128568346 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128568362 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128568488 | other | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128568522 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128569027 | pole | Non-HFTD | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
128569033 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128569058 | other | Non-HFTD | Transmission | 2024-04-09 | 2024-07-09 | Level 2 | E | 2024-10-02 | 2024-07-09 | Level 2 | Field Safety Reassessment
128569062 | insulator and brushing | Non-HFTD | Transmission | 2024-04-05 | 2027-04-05 | Level 2 | E |  | 2027-04-05 | Level 2
128569301 | pole | Non-HFTD | Transmission | 2024-04-09 | 2024-10-09 | Level 2 | E |  | 2024-10-09 | Level 2
128569752 | switch | Non-HFTD | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128569826 | anchor/guy | Non-HFTD | Transmission | 2024-04-17 | 2027-04-17 | Level 2 | E | 2024-06-25 | 2027-04-17 | Level 2 | GO 165 Inspection
128569964 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128570001 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128570210 | other | Non-HFTD | Transmission | 2024-04-18 | 2027-04-18 | Level 2 | E |  | 2027-04-18 | Level 2
128571127 | other | Non-HFTD | Transmission | 2024-04-18 | 2027-04-18 | Level 2 | E |  | 2027-04-18 | Level 2
128571200 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128571537 | pole | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128571830 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128571935 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128572669 | anchor/guy | Non-HFTD | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F | 2024-05-13 | 2029-04-18 | Level 3 | GO 165 Inspection
128572707 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128572801 | other | Non-HFTD | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128573928 | other | Non-HFTD | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128575472 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128575742 | pole | HFTD Tier 3 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128575871 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128576467 | other | Non-HFTD | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128577216 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128577458 | anchor/guy | Non-HFTD | Transmission | 2024-04-11 | 2027-04-11 | Level 2 | E | 2024-09-10 | 2027-04-11 | Level 2 | GO 165 Inspection
128577527 | other | Non-HFTD | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F | 2024-09-10 | 2029-04-11 | Level 3 | GO 165 Inspection
128577683 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128577798 | other | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128577809 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E | 2024-05-19 | 2025-04-18 | Level 2 | GO 165 Inspection
128577810 | other | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128577833 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128577838 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E | 2024-05-07 | 2025-04-11 | Level 2 | GO 165 Inspection
128577850 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E | 2024-05-19 | 2025-04-18 | Level 2 | GO 165 Inspection
128577888 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128578000 | anchor/guy | Non-HFTD | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128578008 | other | Non-HFTD | Transmission | 2024-04-09 | 2029-04-09 | Level 3 | F | 2024-06-26 | 2029-04-09 | Level 3 | GO 165 Inspection
128578076 | other | HFTD Tier 3 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578113 | other | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578193 | pole | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128578202 | crossarm | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578206 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128578207 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578254 | anchor/guy | Non-HFTD | Transmission | 2024-04-10 | 2027-04-10 | Level 2 | E | 2024-04-23 | 2027-04-10 | Level 2 | GO 165 Inspection
128578270 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E | 2024-06-20 | 2025-04-08 | Level 2 | GO 165 Inspection
128578272 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578325 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128578350 | other | Non-HFTD | Transmission | 2024-04-11 | 2027-04-11 | Level 2 | E |  | 2027-04-11 | Level 2
128578357 | conductor | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128578358 | other | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F |  | 2029-04-08 | Level 3
128578379 | other | Non-HFTD | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F | 2024-06-06 | 2029-04-10 | Level 3 | GO 165 Inspection
128578380 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578401 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128578472 | pole | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578474 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578476 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578496 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128578524 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2025-04-10 | Level 2 | E |  | 2025-04-10 | Level 2
128578525 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578588 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128578591 | other | HFTD Tier 2 | Transmission | 2024-04-10 | 2029-04-10 | Level 3 | F |  | 2029-04-10 | Level 3
128580824 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128581063 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E |  | 2025-04-18 | Level 2
128581350 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128581470 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128581503 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128581592 | pole | HFTD Tier 3 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128581871 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128581872 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128581903 | insulator and brushing | Non-HFTD | Transmission | 2024-04-19 | 2027-04-19 | Level 2 | E |  | 2027-04-19 | Level 2
128581923 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128581929 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128582003 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128582011 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 3 | F | 2024-06-07 | 2029-04-19 | Level 3 | GO 165 Inspection
128582093 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2024-07-17 | Level 2 | E | 2024-10-16 | 2024-07-17 | Level 2 | Field Safety Reassessment
128582110 | other | Non-HFTD | Transmission | 2024-04-19 | 2027-04-19 | Level 2 | E |  | 2027-04-19 | Level 2
128582169 | other | Non-HFTD | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128582214 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2024-10-16 | Level 2 | E |  | 2024-07-16 | Level 2
128582264 | crossarm | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128582307 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
128582385 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128582612 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128582679 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128582680 | other | HFTD Tier 3 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128582695 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128582760 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F | 2024-05-07 | 2029-04-11 | Level 3 | GO 165 Inspection
128582765 | pole | HFTD Tier 3 | Transmission | 2024-04-16 | 2024-10-16 | Level 2 | E | 2024-10-31 | 2024-10-16 | Level 2 | Field Safety Reassessment
128583040 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128583110 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128583170 | pole | HFTD Tier 3 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128583245 | pole | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128583259 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128583390 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128583432 | pole | HFTD Tier 3 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128583477 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F | 2024-06-15 | 2029-04-17 | Level 3 | GO 165 Inspection
128583500 | other | HFTD Tier 3 | Transmission | 2024-04-11 | 2029-04-11 | Level 3 | F |  | 2029-04-11 | Level 3
128583509 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128583620 | pole | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128583822 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-15 | 2025-04-15 | Level 2 | E | 2024-05-17 | 2025-04-15 | Level 2 | GO 165 Inspection
128583876 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128583911 | other | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128583959 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128583965 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128583968 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128584032 | other | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E | 2024-05-02 | 2025-04-11 | Level 2 | GO 165 Inspection
128584041 | other | Non-HFTD | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128584047 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584059 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584070 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584072 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584080 | other | HFTD Tier 2 | Transmission | 2024-04-15 | 2029-04-15 | Level 3 | F |  | 2029-04-15 | Level 3
128584131 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128584183 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128584187 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128584189 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F | 2024-06-17 | 2029-04-16 | Level 3 | GO 165 Inspection
128584351 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128584362 | other | Non-HFTD | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584365 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F | 2024-06-15 | 2029-04-17 | Level 3 | GO 165 Inspection
128584388 | pole | HFTD Tier 2 | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128584402 | other | Non-HFTD | Transmission | 2024-04-19 | 2027-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584471 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128584673 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128584829 | other | Non-HFTD | Transmission | 2024-04-11 | 2025-04-11 | Level 2 | E |  | 2025-04-11 | Level 2
128584887 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128584910 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E | 2024-05-19 | 2025-04-18 | Level 2 | GO 165 Inspection
128584913 | pole | HFTD Tier 3 | Transmission | 2024-04-16 | 2024-10-16 | Level 2 | E | 2024-10-31 | 2024-10-16 | Level 2 | Field Safety Reassessment
128584944 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584948 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128584971 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128585072 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E | 2024-10-18 | 2024-10-16 | Level 2 | Field Safety Reassessment
128585100 | pole | HFTD Tier 2 | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128585120 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128585179 | other | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128585266 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128585350 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128585376 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128585381 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2027-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128585394 | other | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128585402 | pole | Non-HFTD | Transmission | 2024-04-19 | 2027-04-19 | Level 2 | E |  | 2027-04-19 | Level 2
128585814 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128587849 | other | Non-HFTD | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128590859 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128593364 | pole | HFTD Tier 3 | Transmission | 2024-04-16 | 2029-04-16 | Level 3 | F |  | 2029-04-16 | Level 3
128596118 | pole | HFTD Tier 3 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128596119 | other | Non-HFTD | Transmission | 2024-04-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
128598507 | other | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128599305 | other | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128599307 | pole | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128600354 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128601002 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F |  | 2029-04-05 | Level 3
128601867 | other | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128601868 | pole | HFTD Tier 3 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128607628 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128607647 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128607660 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128608053 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128608266 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128608298 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128608398 | other | Non-HFTD | Transmission | 2024-04-20 | 2024-07-20 | Level 2 | E |  | 2024-07-20 | Level 2
128608766 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-20 | 2029-10-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609106 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609192 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F | 2024-05-19 | 2029-04-20 | Level 3 | GO 165 Inspection
128609215 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F | 2024-05-19 | 2029-04-20 | Level 3 | GO 165 Inspection
128609268 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128609285 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609358 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609366 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128609384 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128609432 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609436 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609442 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609447 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609448 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609457 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609472 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609473 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609475 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609477 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128609482 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128609550 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128609571 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128609670 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128610911 | pole | Non-HFTD | Transmission | 2024-04-19 | 2027-04-19 | Level 2 | E |  | 2027-04-19 | Level 2
128611010 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128611241 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128611368 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128611388 | pole | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128611528 | pole | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128611902 | pole | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128612228 | pole | HFTD Tier 2 | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E | 2024-10-02 | 2025-04-22 | Level 2 | GO 165 Inspection
128613947 | pole | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128614012 | insulator and brushing | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E |  | 2027-04-22 | Level 2
128614052 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128616042 | pole | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128616137 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128616528 | pole | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128616606 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128617017 | anchor/guy | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E |  | 2027-04-22 | Level 2
128617242 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E |  | 2025-04-22 | Level 2
128617309 | anchor/guy | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E |  | 2027-04-22 | Level 2
128617379 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2025-04-22 | Level 3 | F | 2024-05-07 | 2029-04-22 | Level 3 | GO 165 Inspection
128617627 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128617634 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2025-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128617737 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E |  | 2025-04-22 | Level 2
128617833 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E | 2024-05-19 | 2025-04-19 | Level 2 | GO 165 Inspection
128617835 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F | 2024-05-19 | 2029-04-19 | Level 3 | GO 165 Inspection
128617965 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-22 | 2024-07-22 | Level 3 | F | 2024-05-20 | 2029-04-22 | Level 3 | GO 165 Inspection
128617970 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F | 2024-05-20 | 2029-04-22 | Level 3 | GO 165 Inspection
128617985 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128617989 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128617992 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128618042 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-17 | 2029-04-17 | Level 3 | F |  | 2029-04-17 | Level 3
128618137 | other | HFTD Tier 3 | Transmission | 2024-04-20 | 2024-10-20 | Level 2 | E |  | 2024-10-20 | Level 2
128618191 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F | 2024-05-18 | 2029-04-18 | Level 3 | GO 165 Inspection
128618197 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E |  | 2025-04-19 | Level 2
128618233 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128618281 | other | HFTD Tier 3 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128618303 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128618305 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128618341 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128618501 | other | HFTD Tier 3 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128618525 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E | 2024-05-20 | 2025-04-19 | Level 2 | GO 165 Inspection
128618527 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128618529 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2024-07-20 | Level 2 | E | 2024-12-27 | 2024-07-20 | Level 2 | Field Safety Reassessment
128618530 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E | 2024-05-19 | 2025-04-18 | Level 2 | GO 165 Inspection
128618539 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-18 | 2025-04-18 | Level 2 | E | 2024-05-18 | 2025-04-18 | Level 2 | GO 165 Inspection
128618635 | other | HFTD Tier 3 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F | 2024-05-17 | 2029-04-19 | Level 3 | GO 165 Inspection
128618793 | other | HFTD Tier 3 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128618809 | pole | HFTD Tier 3 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F |  | 2029-04-19 | Level 3
128618864 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F | 2024-05-21 | 2029-04-19 | Level 3 | GO 165 Inspection
128618871 | other | HFTD Tier 2 | Transmission | 2024-04-19 | 2029-04-19 | Level 3 | F | 2024-05-20 | 2029-04-19 | Level 3 | GO 165 Inspection
128618893 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F | 2024-05-18 | 2029-04-18 | Level 3 | GO 165 Inspection
128618965 | other | Non-HFTD | Transmission | 2024-04-04 | 2029-04-04 | Level 3 | F | 2024-08-01 | 2029-04-04 | Level 3 | GO 165 Inspection
128618971 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128618987 | insulator and brushing | Non-HFTD | Transmission | 2024-04-17 | 2025-04-17 | Level 2 | E |  | 2025-04-17 | Level 2
128618988 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128618989 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128619034 | other | HFTD Tier 2 | Transmission | 2024-04-18 | 2029-04-18 | Level 3 | F |  | 2029-04-18 | Level 3
128622186 | other | Non-HFTD | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128622245 | other | HFTD Tier 2 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128622368 | other | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128622546 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128622876 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128623735 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-06-08 | 2029-04-23 | Level 3 | GO 165 Inspection
128623802 | other | Non-HFTD | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128624082 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128624141 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128624262 | other | HFTD Tier 3 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128624303 | pole | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 2 | E |  | 2027-04-23 | Level 2
128624533 | other | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128624832 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128625046 | other | Non-HFTD | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-08-28 | 2029-04-23 | Level 3 | GO 165 Inspection
128625060 | anchor/guy | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F | 2024-06-19 | 2029-04-22 | Level 3 | GO 165 Inspection
128625269 | other | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 2 | E |  | 2027-04-23 | Level 2
128625338 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128625398 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128625479 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128625483 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128625521 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2024-10-23 | Level 2 | E | 2024-09-17 | 2024-10-23 | Level 2 | Field Safety Reassessment
128625533 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128625578 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128625652 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128627489 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128627543 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128627778 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-23 | 2024-07-23 | Level 2 | E |  | 2024-07-23 | Level 2
128627825 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128627833 | other | Non-HFTD | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E | 2024-05-29 | 2025-04-22 | Level 2 | GO 165 Inspection
128627853 | other | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 2 | E | 2024-08-20 | 2027-04-23 | Level 2 | GO 165 Inspection
128627958 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628231 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628249 | other | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E |  | 2027-04-22 | Level 2
128628337 | crossarm | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628421 | anchor/guy | Non-HFTD | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E | 2024-05-29 | 2025-04-22 | Level 2 | GO 165 Inspection
128628423 | anchor/guy | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F | 2024-05-31 | 2029-04-22 | Level 3 | GO 165 Inspection
128628511 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628518 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628572 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628634 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628642 | anchor/guy | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F | 2024-05-31 | 2029-04-22 | Level 3 | GO 165 Inspection
128628643 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-05-22 | 2029-04-23 | Level 3 | GO 165 Inspection
128628644 | other | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E |  | 2027-04-22 | Level 2
128628672 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628681 | insulator and brushing | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 2 | E |  | 2027-04-23 | Level 2
128628720 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628728 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628731 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628732 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128628735 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628738 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128628820 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128628826 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128628893 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128629996 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128631109 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128631129 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128635722 | pole | Non-HFTD | Transmission | 2024-04-24 | 2027-04-24 | Level 2 | E | 2024-08-19 | 2027-04-24 | Level 2 | GO 165 Inspection
128639900 | other | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128644347 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128645312 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128646805 | other | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128647206 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128647260 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128647427 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128648800 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128648818 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128649090 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128649829 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128650066 | other | Non-HFTD | Transmission | 2024-04-22 | 2024-07-22 | Level 2 | E | 2024-07-12 | 2024-07-22 | Level 2 | Field Safety Reassessment
128650307 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128650501 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128650587 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E | 2024-05-20 | 2025-04-24 | Level 2 | GO 165 Inspection
128650590 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128650609 | other | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E | 2024-05-02 | 2027-04-22 | Level 2 | GO 165 Inspection
128650711 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F | 2024-05-31 | 2029-04-24 | Level 3 | GO 165 Inspection
128650736 | other | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128650738 | other | Non-HFTD | Transmission | 2024-04-22 | 2027-04-22 | Level 2 | E |  | 2027-04-22 | Level 2
128650778 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128650835 | insulator and brushing | Non-HFTD | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E |  | 2025-04-22 | Level 2
128650837 | other | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128650938 | other | Non-HFTD | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128650993 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128651123 | other | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128651191 | pole | HFTD Tier 3 | Transmission | 2024-04-20 | 2024-10-20 | Level 2 | E | 2024-12-23 | 2024-10-20 | Level 2 | Field Safety Reassessment
128651194 | other | HFTD Tier 3 | Transmission | 2024-04-20 | 2024-10-20 | Level 2 | E | 2024-12-23 | 2024-10-20 | Level 2 | Field Safety Reassessment
128651205 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2024-07-24 | Level 2 | E |  | 2025-04-24 | Level 2
128651226 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128651298 | anchor/guy | Non-HFTD | Transmission | 2024-04-24 | 2027-04-24 | Level 2 | E |  | 2027-04-24 | Level 2
128652321 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128652477 | other | Non-HFTD | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F | 2024-09-13 | 2029-04-24 | Level 3 | GO 165 Inspection
128652883 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128653675 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128653847 | other | Non-HFTD | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F | 2024-06-20 | 2029-04-25 | Level 3 | GO 165 Inspection
128654246 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128654324 | other | Non-HFTD | Transmission | 2024-04-25 | 2027-04-25 | Level 2 | E | 2024-06-21 | 2027-04-25 | Level 2 | GO 165 Inspection
128654933 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128655193 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128655194 | anchor/guy | Non-HFTD | Transmission | 2024-04-25 | 2027-04-25 | Level 2 | E | 2024-06-20 | 2027-04-25 | Level 2 | GO 165 Inspection
128655392 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128656796 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128656833 | other | Non-HFTD | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128656878 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E | 2024-06-01 | 2025-04-25 | Level 2 | GO 165 Inspection
128657014 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128657035 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128657131 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128657261 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128657429 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128657562 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128657775 | pole | Non-HFTD | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128657790 | pole | Non-HFTD | Transmission | 2024-04-25 | 2027-04-25 | Level 2 | E |  | 2027-04-25 | Level 2
128658048 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E | 2024-05-07 | 2025-04-25 | Level 2 | GO 165 Inspection
128658071 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128658250 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128659522 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128659637 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128659644 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128660156 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128660957 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128661185 | other | Non-HFTD | Transmission | 2024-04-26 | 2027-04-26 | Level 2 | E | 2024-08-30 | 2027-04-26 | Level 2 | GO 165 Inspection
128661469 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128661501 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128661931 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2024-07-24 | Level 2 | E | 2024-07-22 | 2024-07-24 | Level 2 | Field Safety Reassessment
128662243 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128662342 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128662349 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128662372 | other | Non-HFTD | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-05-30 | 2029-04-23 | Level 3 | GO 165 Inspection
128662602 | other | HFTD Tier 3 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128662613 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128662636 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128662663 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128662774 | other | HFTD Tier 3 | Transmission | 2024-04-26 | 2024-10-26 | Level 3 | F |  | 2029-04-26 | Level 3
128662817 | other | HFTD Tier 3 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128662818 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128662903 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128663478 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F | 2024-05-09 | 2029-04-26 | Level 3 | GO 165 Inspection
128663590 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128663672 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128664023 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E | 2024-05-10 | 2025-04-26 | Level 2 | GO 165 Inspection
128664038 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F | 2024-05-17 | 2029-04-26 | Level 3 | GO 165 Inspection
128664046 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F | 2024-05-10 | 2029-04-26 | Level 3 | GO 165 Inspection
128664353 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128667265 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128667312 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128668144 | other | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128668215 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-28 | 2029-04-28 | Level 3 | F |  | 2029-04-28 | Level 3
128668489 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128671026 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128671505 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128671616 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128671677 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128672056 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128672182 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128672212 | pole | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F | 2024-10-17 | 2029-04-29 | Level 3 | GO 165 Inspection
128674828 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128676533 | insulator and brushing | Non-HFTD | Transmission | 2024-04-29 | 2027-04-29 | Level 2 | E |  | 2027-04-29 | Level 2
128678049 | other | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128678383 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128678390 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128678686 | other | Non-HFTD | Transmission | 2024-04-29 | 2027-04-29 | Level 2 | E |  | 2027-04-29 | Level 2
128678821 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E | 2024-05-20 | 2025-04-23 | Level 2 | GO 165 Inspection
128678912 | other | Non-HFTD | Transmission | 2024-04-29 | 2027-04-29 | Level 2 | E |  | 2027-04-29 | Level 2
128679006 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128679024 | other | HFTD Tier 3 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128679087 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128679145 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128679216 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128679220 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2024-10-29 | Level 2 | E |  | 2024-10-29 | Level 2
128679253 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128679259 | other | HFTD Tier 3 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128679273 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128679369 | other | HFTD Tier 3 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-06-24 | 2029-04-23 | Level 3 | GO 165 Inspection
128679394 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128679416 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128679417 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E | 2024-06-16 | 2025-04-23 | Level 2 | GO 165 Inspection
128679467 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-20 | 2024-10-20 | Level 2 | E |  | 2024-10-20 | Level 2
128679478 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128679501 | other | HFTD Tier 3 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-05-17 | 2029-04-23 | Level 3 | GO 165 Inspection
128679554 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128679559 | other | Non-HFTD | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128679608 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128679616 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128679635 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2027-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128679638 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-22 | 2025-04-22 | Level 2 | E |  | 2025-04-22 | Level 2
128679679 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128679721 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128679739 | anchor/guy | Non-HFTD | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128679767 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-06-25 | 2029-04-23 | Level 3 | GO 165 Inspection
128679771 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128679805 | other | Non-HFTD | Transmission | 2024-04-22 | 2029-04-22 | Level 3 | F |  | 2029-04-22 | Level 3
128679810 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128679811 | conductor | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128679824 | pole | HFTD Tier 2 | Transmission | 2024-04-20 | 2024-10-20 | Level 2 | E |  | 2025-04-20 | Level 2
128679840 | other | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 2 | E |  | 2027-04-23 | Level 2
128679860 | other | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128680258 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128680338 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128680386 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128680651 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128681779 | pole | Non-HFTD | Transmission | 2024-04-29 | 2027-04-29 | Level 2 | E |  | 2027-04-29 | Level 2
128682157 | anchor/guy | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128682616 | other | Non-HFTD | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F | 2024-08-29 | 2029-04-30 | Level 3 | GO 165 Inspection
128683021 | other | Non-HFTD | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F | 2024-09-10 | 2029-04-30 | Level 3 | GO 165 Inspection
128683285 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128683346 | pole | HFTD Tier 3 | Transmission | 2024-04-30 | 2024-10-30 | Level 2 | E | 2024-12-27 | 2024-10-30 | Level 2 | Field Safety Reassessment
128683434 | other | Non-HFTD | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F | 2024-10-14 | 2029-04-30 | Level 3 | GO 165 Inspection
128683625 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128683802 | other | Non-HFTD | Transmission | 2024-04-30 | 2027-04-30 | Level 2 | E |  | 2027-04-30 | Level 2
128683882 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128684209 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128684233 | pole | Non-HFTD | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128684237 | insulator and brushing | Non-HFTD | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128684262 | insulator and brushing | Non-HFTD | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128684293 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128684537 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128684868 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128684882 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128685184 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128685455 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128685512 | pole | Non-HFTD | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128685580 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128685596 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128689403 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128690132 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F | 2024-06-07 | 2029-04-30 | Level 3 | GO 165 Inspection
128691760 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128691815 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128691934 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128691938 | other | HFTD Tier 3 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128691964 | other | HFTD Tier 3 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128692091 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128692337 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128692777 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128692842 | other | Non-HFTD | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E | 2024-10-17 | 2025-05-01 | Level 2 | GO 165 Inspection
128693078 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128693111 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128693245 | pole | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E | 2024-09-30 | 2027-05-01 | Level 2 | GO 165 Inspection
128693260 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128693360 | other | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E |  | 2027-05-01 | Level 2
128693558 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128693664 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128693959 | pole | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E | 2024-10-25 | 2027-05-01 | Level 2 | GO 165 Inspection
128694945 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-06-08 | 2025-04-09 | Level 2 | GO 165 Inspection
128695622 | pole | Non-HFTD | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128696894 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128696923 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128696943 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128696953 | pole | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E | 2024-10-24 | 2027-05-01 | Level 2 | GO 165 Inspection
128697257 | other | Non-HFTD | Transmission | 2024-04-05 | 2029-04-05 | Level 3 | F | 2024-07-01 | 2029-04-05 | Level 3 | GO 165 Inspection
128697351 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128697443 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128697499 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128697671 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E | 2024-06-18 | 2025-05-01 | Level 2 | GO 165 Inspection
128697759 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F | 2024-10-30 | 2029-05-01 | Level 3 | GO 165 Inspection
128697798 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128697874 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698273 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128698368 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E | 2024-06-24 | 2025-05-01 | Level 2 | GO 165 Inspection
128698369 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E | 2024-06-13 | 2025-05-01 | Level 2 | GO 165 Inspection
128698375 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698448 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2024-07-25 | Level 2 | E |  | 2024-07-25 | Level 2
128698461 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128698463 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698468 | anchor/guy | Non-HFTD | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128698472 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698475 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128698483 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128698574 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F | 2024-05-25 | 2029-04-20 | Level 3 | GO 165 Inspection
128698597 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128698632 | other | HFTD Tier 3 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F | 2024-05-07 | 2029-04-20 | Level 3 | GO 165 Inspection
128698659 | other | Non-HFTD | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128698675 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128698699 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128698713 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698735 | pole | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-19 | Level 2 | E | 2024-05-18 | 2025-04-19 | Level 2 | GO 165 Inspection
128698738 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128698748 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128698791 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128698795 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128698830 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698869 | other | Non-HFTD | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128698879 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128698991 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128699018 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128699049 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-20 | 2025-04-20 | Level 2 | E |  | 2025-04-20 | Level 2
128699054 | pole | Non-HFTD | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128699056 | pole | Non-HFTD | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128699073 | other | HFTD Tier 2 | Transmission | 2024-04-27 | 2025-04-27 | Level 2 | E | 2024-05-17 | 2025-04-27 | Level 2 | GO 165 Inspection
128699112 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128699135 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128699147 | pole | HFTD Tier 3 | Transmission | 2024-05-01 | 2024-11-01 | Level 2 | E | 2024-10-30 | 2024-11-01 | Level 2 | Field Safety Reassessment
128699163 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-27 | 2025-04-27 | Level 2 | E | 2024-05-17 | 2025-04-27 | Level 2 | GO 165 Inspection
128699260 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128700405 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128700432 | pole | HFTD Tier 2 | Transmission | 2024-04-09 | 2025-04-09 | Level 2 | E | 2024-06-08 | 2025-04-09 | Level 2 | GO 165 Inspection
128700686 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128700976 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128701312 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128701382 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128701448 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128701512 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128701572 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128701615 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128701635 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128701909 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-02 | 2024-11-02 | Level 2 | E | 2024-09-26 | 2024-11-02 | Level 2 | Field Safety Reassessment
128701971 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128702131 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128702292 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128702358 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128702450 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128702492 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128702524 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703163 | pole | HFTD Tier 3 | Transmission | 2024-05-02 | 2024-11-02 | Level 2 | E | 2024-11-19 | 2024-11-02 | Level 2 | Field Safety Reassessment
128703167 | pole | HFTD Tier 3 | Transmission | 2024-05-02 | 2024-11-02 | Level 2 | E | 2024-11-19 | 2024-11-02 | Level 2 | Field Safety Reassessment
128703306 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703455 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703567 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128703588 | splice | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703651 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128703654 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128703706 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703757 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128703818 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703909 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128703989 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128704138 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128704151 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128704425 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128705921 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2027-04-08 | Level 2 | E |  | 2027-04-08 | Level 2
128706069 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128706121 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128706130 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128706277 | other | Non-HFTD | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128706311 | pole | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128706323 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128707077 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128707129 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128707178 | pole | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128707191 | pole | Non-HFTD | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E | 2024-06-17 | 2027-05-01 | Level 2 | GO 165 Inspection
128707231 | insulator and brushing | Non-HFTD | Transmission | 2024-04-08 | 2029-04-08 | Level 3 | F | 2024-07-01 | 2029-04-08 | Level 3 | GO 165 Inspection
128707274 | other | Non-HFTD | Transmission | 2024-05-02 | 2027-05-02 | Level 2 | E |  | 2027-05-02 | Level 2
128707509 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-11-03 | Level 3 | F |  | 2029-05-03 | Level 3
128707610 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128707618 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F | 2024-06-24 | 2029-05-01 | Level 3 | GO 165 Inspection
128707757 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F | 2024-06-21 | 2029-05-01 | Level 3 | GO 165 Inspection
128707839 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128708219 | other | Non-HFTD | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E | 2024-08-20 | 2027-05-03 | Level 2 | GO 165 Inspection
128708237 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-11-21 | 2029-05-02 | Level 3 | GO 165 Inspection
128708250 | pole | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128708285 | pole | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128708288 | pole | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708422 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-27 | 2025-04-27 | Level 2 | E |  | 2025-04-27 | Level 2
128708445 | conductor | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708502 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128708509 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128708515 | other | Non-HFTD | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128708523 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128708574 | other | HFTD Tier 2 | Transmission | 2024-04-16 | 2024-07-16 | Level 2 | E |  | 2024-07-16 | Level 2
128708578 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128708618 | other | Non-HFTD | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128708645 | other | Non-HFTD | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E |  | 2027-05-03 | Level 2
128708751 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-11-01 | 2029-05-02 | Level 3 | GO 165 Inspection
128708766 | insulator and brushing | Non-HFTD | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708778 | other | HFTD Tier 2 | Transmission | 2024-04-27 | 2025-04-27 | Level 2 | E |  | 2025-04-27 | Level 2
128708804 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708862 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708912 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708913 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708914 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128708925 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128708943 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-10-30 | 2029-05-02 | Level 3 | GO 165 Inspection
128709048 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F | 2024-10-22 | 2029-05-01 | Level 3 | GO 165 Inspection
128709117 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128709142 | other | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E | 2024-10-22 | 2027-05-01 | Level 2 | GO 165 Inspection
128709211 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-11-21 | 2029-05-02 | Level 3 | GO 165 Inspection
128709353 | other | Non-HFTD | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F | 2024-06-20 | 2029-05-03 | Level 3 | GO 165 Inspection
128709372 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128709377 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128709417 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128709424 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128709442 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128709562 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128710058 | pole | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128710207 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128710695 | other | HFTD Tier 2 | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128710795 | other | HFTD Tier 2 | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128710841 | other | Non-HFTD | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128710844 | other | HFTD Tier 2 | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128710854 | other | Non-HFTD | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F | 2024-08-16 | 2029-05-04 | Level 3 | GO 165 Inspection
128710905 | other | HFTD Tier 2 | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128710919 | other | HFTD Tier 2 | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128710932 | other | HFTD Tier 2 | Transmission | 2024-05-04 | 2029-05-04 | Level 3 | F |  | 2029-05-04 | Level 3
128711779 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128712241 | insulator and brushing | Non-HFTD | Transmission | 2024-05-06 | 2027-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128712817 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128712890 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128712951 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128713296 | pole | HFTD Tier 3 | Transmission | 2024-05-06 | 2024-11-06 | Level 2 | E |  | 2024-11-06 | Level 2
128713529 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128713771 | pole | HFTD Tier 3 | Transmission | 2024-05-06 | 2024-11-06 | Level 2 | E | 2024-10-12 | 2024-11-06 | Level 2 | Field Safety Reassessment
128713785 | other | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F | 2024-09-05 | 2029-05-06 | Level 3 | GO 165 Inspection
128713838 | insulator and brushing | Non-HFTD | Transmission | 2024-05-06 | 2027-05-06 | Level 2 | E |  | 2027-05-06 | Level 2
128714317 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128714782 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128714882 | pole | Non-HFTD | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128715003 | other | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F | 2024-08-27 | 2029-05-06 | Level 3 | GO 165 Inspection
128715161 | other | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F | 2024-08-29 | 2029-05-06 | Level 3 | GO 165 Inspection
128715482 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716228 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716303 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716325 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716327 | other | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716330 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716336 | other | HFTD Tier 3 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716349 | other | HFTD Tier 3 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716350 | other | HFTD Tier 3 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716416 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F | 2024-10-30 | 2029-05-01 | Level 3 | GO 165 Inspection
128716423 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128716446 | insulator and brushing | Non-HFTD | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128716447 | pole | Non-HFTD | Transmission | 2024-05-02 | 2027-05-02 | Level 2 | E | 2024-11-01 | 2027-05-02 | Level 2 | GO 165 Inspection
128716482 | pole | Non-HFTD | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128716536 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716551 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128716553 | pole | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-10-23 | 2029-05-02 | Level 3 | GO 165 Inspection
128716563 | pole | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-10-22 | 2029-05-02 | Level 3 | GO 165 Inspection
128716567 | other | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E |  | 2027-05-01 | Level 2
128716569 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128716576 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128716592 | other | HFTD Tier 3 | Transmission | 2024-05-02 | 2029-11-02 | Level 3 | F |  | 2029-05-02 | Level 3
128716593 | conductor | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E | 2024-11-08 | 2027-05-01 | Level 2 | GO 165 Inspection
128716616 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128716632 | pole | Non-HFTD | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128716651 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2025-05-02 | Level 2 | E |  | 2025-05-02 | Level 2
128716691 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128716694 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128716711 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716729 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-06-07 | 2029-04-23 | Level 3 | GO 165 Inspection
128716784 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128716809 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128716837 | other | HFTD Tier 2 | Transmission | 2024-04-20 | 2029-04-20 | Level 3 | F |  | 2029-04-20 | Level 3
128716851 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-10-23 | 2029-05-02 | Level 3 | GO 165 Inspection
128716858 | other | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-10-30 | 2029-05-02 | Level 3 | GO 165 Inspection
128716908 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128716935 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2024-08-03 | Level 2 | E |  | 2024-08-03 | Level 2
128716942 | pole | HFTD Tier 3 | Transmission | 2024-04-30 | 2024-10-30 | Level 2 | E |  | 2024-10-30 | Level 2
128716977 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128716980 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128717022 | pole | HFTD Tier 2 | Transmission | 2024-04-27 | 2029-04-27 | Level 3 | F |  | 2029-04-27 | Level 3
128717066 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128717092 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128717110 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128717119 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128717125 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128717184 | pole | Non-HFTD | Transmission | 2024-05-01 | 2027-05-01 | Level 2 | E | 2024-11-04 | 2027-05-01 | Level 2 | GO 165 Inspection
128717645 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2027-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128717657 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128717670 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128717676 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128717684 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2024-10-29 | Level 2 | E |  | 2025-04-29 | Level 2
128717704 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128717709 | other | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F | 2024-06-20 | 2029-05-06 | Level 3 | GO 165 Inspection
128717713 | insulator and brushing | Non-HFTD | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128717715 | anchor/guy | Non-HFTD | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128717722 | pole | Non-HFTD | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F | 2024-10-23 | 2029-05-02 | Level 3 | GO 165 Inspection
128718361 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128718883 | other | Non-HFTD | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128718910 | pole | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2027-05-07 | Level 2
128719231 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128719328 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128719350 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2024-11-07 | Level 2 | E | 2024-11-04 | 2024-11-07 | Level 2 | Field Safety Reassessment
128719380 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128719388 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2024-11-07 | Level 2 | E | 2024-12-20 | 2024-11-07 | Level 2 | Field Safety Reassessment
128719540 | anchor/guy | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E | 2024-09-10 | 2027-05-07 | Level 2 | GO 165 Inspection
128719552 | other | Non-HFTD | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128719661 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128719714 | anchor/guy | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E | 2024-09-10 | 2027-05-07 | Level 2 | GO 165 Inspection
128719957 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128720224 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128720727 | anchor/guy | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2027-05-07 | Level 2
128721090 | other | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128721185 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128721309 | pole | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2027-05-07 | Level 2
128721348 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128721391 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128721599 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128721968 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722056 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128722262 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128722263 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128722367 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722368 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722381 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128722430 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722450 | other | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722508 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722526 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128722545 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722548 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722563 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722607 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722692 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128722795 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128722978 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128723030 | pole | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2027-05-07 | Level 2
128723100 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128723134 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128723139 | other | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128723241 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128723243 | conductor | HFTD Tier 2 | Transmission | 2024-05-07 | 2024-11-07 | Level 2 | E | 2024-10-18 | 2024-08-07 | Level 2 | Field Safety Reassessment
128723420 | crossarm | Non-HFTD | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128723783 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2024-11-07 | Level 2 | E | 2024-10-12 | 2024-11-07 | Level 2 | Field Safety Reassessment
128723837 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128723897 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128723935 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128723939 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128723950 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128724092 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128724149 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128724913 | pole | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128725362 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128725446 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128725447 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128725502 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128725900 | pole | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128726247 | other | Non-HFTD | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128726593 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128726766 | insulator and brushing | Non-HFTD | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E |  | 2027-05-08 | Level 2
128727143 | other | Non-HFTD | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E | 2024-09-11 | 2027-05-08 | Level 2 | GO 165 Inspection
128727230 | conductor | Non-HFTD | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E |  | 2027-05-08 | Level 2
128727657 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128727833 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128727896 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128727920 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728420 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728456 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728488 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-08 | 2024-11-08 | Level 2 | E | 2024-11-04 | 2024-11-08 | Level 2 | Field Safety Reassessment
128728520 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728530 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728553 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728560 | pole | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128728582 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128728879 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128729079 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128729402 | pole | Non-HFTD | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E | 2024-07-12 | 2027-05-08 | Level 2 | GO 165 Inspection
128729781 | other | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128729949 | other | Non-HFTD | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F | 2024-05-23 | 2029-05-07 | Level 3 | GO 165 Inspection
128730067 | other | HFTD Tier 3 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128730412 | other | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128730540 | anchor/guy | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128731689 | insulator and brushing | Non-HFTD | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128731816 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128731907 | anchor/guy | Non-HFTD | Transmission | 2024-05-09 | 2027-05-09 | Level 2 | E | 2024-07-19 | 2027-05-09 | Level 2 | GO 165 Inspection
128731924 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128731988 | anchor/guy | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128732044 | pole | Non-HFTD | Transmission | 2024-05-09 | 2027-05-09 | Level 2 | E |  | 2027-05-09 | Level 2
128732179 | other | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F | 2024-11-13 | 2029-05-09 | Level 3 | GO 165 Inspection
128732365 | insulator and brushing | Non-HFTD | Transmission | 2024-05-09 | 2027-05-09 | Level 2 | E |  | 2027-05-09 | Level 2
128732499 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128732962 | other | Non-HFTD | Transmission | 2024-05-09 | 2027-05-09 | Level 2 | E |  | 2027-05-09 | Level 2
128732987 | other | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733003 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733029 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128733163 | pole | HFTD Tier 3 | Transmission | 2024-05-09 | 2024-11-09 | Level 2 | E | 2024-10-12 | 2024-11-09 | Level 2 | Field Safety Reassessment
128733169 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-09 | 2024-11-09 | Level 2 | E | 2024-11-08 | 2024-11-09 | Level 2 | Field Safety Reassessment
128733260 | anchor/guy | HFTD Tier 3 | Transmission | 2024-05-09 | 2024-11-09 | Level 2 | E | 2024-11-08 | 2024-11-09 | Level 2 | Field Safety Reassessment
128733311 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733327 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733334 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733360 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-09 | 2024-08-09 | Level 2 | E |  | 2024-08-09 | Level 2
128733375 | crossarm | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128733385 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128733424 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733515 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128733532 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128742960 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128743441 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128743952 | pole | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E |  | 2027-05-10 | Level 2
128744269 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F | 2024-08-14 | 2029-05-10 | Level 3 | GO 165 Inspection
128744281 | other | HFTD Tier 3 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128744295 | pole | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E |  | 2027-05-10 | Level 2
128744758 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128744797 | other | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128744874 | pole | HFTD Tier 3 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128744887 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128745007 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128745024 | other | Non-HFTD | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128745050 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128745141 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128745174 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128745365 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-06-20 | 2029-04-23 | Level 3 | GO 165 Inspection
128745369 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128745833 | other | HFTD Tier 3 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128745914 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128745915 | other | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F | 2024-07-17 | 2029-04-24 | Level 3 | GO 165 Inspection
128745921 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2024-08-07 | Level 2 | E |  | 2025-05-07 | Level 2
128745940 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128746025 | other | HFTD Tier 3 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128746072 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128746103 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128746116 | pole | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128746118 | pole | Non-HFTD | Transmission | 2024-04-23 | 2027-04-23 | Level 2 | E |  | 2027-04-23 | Level 2
128746147 | other | HFTD Tier 3 | Transmission | 2024-04-23 | 2024-10-23 | Level 2 | E | 2024-12-27 | 2024-10-23 | Level 2 | Field Safety Reassessment
128746160 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2027-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128746201 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E | 2024-05-20 | 2025-04-23 | Level 2 | GO 165 Inspection
128746297 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E | 2024-05-20 | 2025-04-23 | Level 2 | GO 165 Inspection
128746320 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128746384 | other | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F | 2024-06-04 | 2029-05-10 | Level 3 | GO 165 Inspection
128746390 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128746466 | other | HFTD Tier 3 | Transmission | 2024-05-09 | 2024-08-09 | Level 2 | E | 2024-11-14 | 2024-08-09 | Level 2 | Field Safety Reassessment
128746503 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128746507 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F | 2024-05-20 | 2029-04-23 | Level 3 | GO 165 Inspection
128746537 | other | Non-HFTD | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128746555 | other | HFTD Tier 3 | Transmission | 2024-04-23 | 2024-10-23 | Level 2 | E | 2024-12-27 | 2024-10-23 | Level 2 | Field Safety Reassessment
128746559 | anchor/guy | HFTD Tier 3 | Transmission | 2024-04-23 | 2024-10-23 | Level 2 | E | 2024-12-27 | 2024-10-23 | Level 2 | Field Safety Reassessment
128746564 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128746583 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128746587 | pole | HFTD Tier 3 | Transmission | 2024-04-23 | 2024-10-23 | Level 2 | E | 2024-06-24 | 2024-10-23 | Level 2 | GO 165 Inspection
128746604 | other | HFTD Tier 3 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128746613 | other | HFTD Tier 2 | Transmission | 2024-04-23 | 2029-04-23 | Level 3 | F |  | 2029-04-23 | Level 3
128746728 | pole | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128746793 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128746794 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128746810 | other | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E | 2024-06-24 | 2025-05-10 | Level 2 | GO 165 Inspection
128746813 | pole | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128746992 | pole | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128747005 | other | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128747071 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128747073 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128747078 | other | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128747088 | other | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128747135 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128747242 | anchor/guy | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E |  | 2027-05-10 | Level 2
128747321 | other | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128747324 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128748978 | crossarm | Non-HFTD | Transmission | 2024-05-11 | 2029-05-11 | Level 3 | F |  | 2029-05-11 | Level 3
128749277 | pole | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128751148 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128751812 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128752150 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E | 2024-09-03 | 2025-05-13 | Level 2 | Field Safety Reassessment
128752689 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-13 | 2024-11-13 | Level 2 | E | 2024-11-13 | 2024-11-13 | Level 2 | Field Safety Reassessment
128753077 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128753393 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128753528 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128753629 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128754375 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128754624 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128754750 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128759433 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E | 2024-05-21 | 2025-05-13 | Level 2 | GO 165 Inspection
128759570 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 3 | F | 2024-07-20 | 2029-05-13 | Level 3 | Field Safety Reassessment
128761462 | pole | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128761467 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128762149 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128762857 | other | HFTD Tier 3 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128763344 | pole | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128764748 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128765358 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F | 2024-05-20 | 2029-05-03 | Level 3 | GO 165 Inspection
128765635 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128767240 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128768366 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128768388 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128768416 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128768472 | other | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128768500 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128768501 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128768502 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128768504 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128768550 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128768606 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128768611 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128768612 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128768618 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128768620 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128768628 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128768638 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-10-24 | Level 3 | F |  | 2029-04-24 | Level 3
128768716 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2027-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128768718 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128768720 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128768728 | anchor/guy | Non-HFTD | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128768783 | insulator and brushing | Non-HFTD | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128768803 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128768836 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128768852 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128768857 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128768859 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128768868 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128768927 | anchor/guy | Non-HFTD | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128768947 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128768957 | pole | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128769027 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128769056 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128769059 | anchor/guy | Non-HFTD | Transmission | 2024-04-24 | 2025-04-24 | Level 2 | E |  | 2025-04-24 | Level 2
128769348 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769374 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128769376 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-13 | 2027-05-13 | Level 2 | E | 2024-07-20 | 2025-05-13 | Level 2 | Field Safety Reassessment
128769397 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769433 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128769438 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769439 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769441 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769445 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769450 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128769461 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128769969 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128770263 | switch | HFTD Tier 3 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128770676 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128770725 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128770731 | other | Non-HFTD | Transmission | 2024-05-14 | 2027-05-14 | Level 2 | E |  | 2027-05-14 | Level 2
128771255 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128771630 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128771967 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128772474 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128773007 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128773297 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128773353 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128773453 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128773468 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128773607 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128773624 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128773767 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128773866 | other | HFTD Tier 3 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128773936 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128774056 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128774092 | pole | Non-HFTD | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E | 2024-06-11 | 2025-05-06 | Level 2 | GO 165 Inspection
128774093 | insulator and brushing | Non-HFTD | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E | 2024-06-11 | 2025-05-03 | Level 2 | GO 165 Inspection
128774142 | anchor/guy | Non-HFTD | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128774189 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128774200 | other | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128774203 | anchor/guy | Non-HFTD | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128774218 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F | 2024-05-17 | 2029-04-29 | Level 3 | GO 165 Inspection
128774219 | other | Non-HFTD | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128774224 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F | 2024-06-11 | 2029-04-25 | Level 3 | GO 165 Inspection
128774229 | other | HFTD Tier 3 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128774231 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F | 2024-05-20 | 2029-04-25 | Level 3 | GO 165 Inspection
128774232 | conductor | Non-HFTD | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128774265 | other | Non-HFTD | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128774281 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128774291 | pole | HFTD Tier 2 | Transmission | 2024-04-24 | 2029-04-24 | Level 3 | F |  | 2029-04-24 | Level 3
128774594 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128774745 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128774918 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128774929 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128775279 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128775380 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128775433 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128776084 | switch | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2027-05-15 | Level 2
128776459 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128776775 | pole | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2027-05-15 | Level 2
128777064 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128777667 | pole | HFTD Tier 2 | Transmission | 2024-04-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
128777721 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128777769 | pole | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2027-05-15 | Level 2
128777841 | pole | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2027-05-15 | Level 2
128778286 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128778540 | pole | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2027-05-15 | Level 2
128779179 | other | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128779253 | crossarm | Non-HFTD | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128779597 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128779599 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128779743 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128779749 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128779795 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128779811 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128779819 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128779877 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128779878 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128779895 | other | HFTD Tier 3 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128779915 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128779945 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128779974 | crossarm | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E | 2024-11-15 | 2025-05-01 | Level 2 | GO 165 Inspection
128780027 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128780030 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128780046 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128780066 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128780083 | other | Non-HFTD | Transmission | 2024-05-06 | 2027-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128780149 | other | HFTD Tier 2 | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128780156 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128780157 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128780204 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128780207 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128780234 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128780237 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128780239 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128780242 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128780245 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128780249 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128780251 | anchor/guy | Non-HFTD | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128780272 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128780277 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128780311 | other | Non-HFTD | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128780312 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128780752 | other | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E | 2024-09-03 | 2027-05-15 | Level 2 | GO 165 Inspection
128780753 | other | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E | 2024-09-03 | 2027-05-15 | Level 2 | GO 165 Inspection
128780768 | pole | Non-HFTD | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F | 2024-09-03 | 2029-05-15 | Level 3 | GO 165 Inspection
128781293 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128782408 | pole | Non-HFTD | Transmission | 2024-05-10 | 2024-11-10 | Level 2 | E |  | 2024-11-10 | Level 2
128782546 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-23 | 2025-04-23 | Level 2 | E |  | 2025-04-23 | Level 2
128782689 | pole | Non-HFTD | Transmission | 2024-05-16 | 2027-05-16 | Level 2 | E |  | 2027-05-16 | Level 2
128782931 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128783113 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
128783232 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128785093 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128785575 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
128785576 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128787117 | other | Non-HFTD | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
128787631 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128791352 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
128792597 | pole | Non-HFTD | Transmission | 2024-05-17 | 2027-05-17 | Level 2 | E |  | 2027-05-17 | Level 2
128799391 | pole | Non-HFTD | Transmission | 2024-05-17 | 2027-05-17 | Level 2 | E |  | 2027-05-17 | Level 2
128799568 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128799682 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128799759 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128799774 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128799786 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128799827 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128799837 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
128799881 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128799931 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128799996 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128800056 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128800071 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128800076 | anchor/guy | Non-HFTD | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128800096 | pole | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128800105 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
128800111 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-26 | Level 2 | E |  | 2025-04-26 | Level 2
128800121 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128800152 | other | Non-HFTD | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128800162 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128800211 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128800213 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128800227 | other | Non-HFTD | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128800234 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E | 2024-05-29 | 2025-05-16 | Level 2 | GO 165 Inspection
128800285 | other | Non-HFTD | Transmission | 2024-04-25 | 2029-04-25 | Level 3 | F |  | 2029-04-25 | Level 3
128800327 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128800417 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
128800494 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128800503 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128800637 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128800655 | other | HFTD Tier 2 | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128800665 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128800752 | other | Non-HFTD | Transmission | 2024-04-26 | 2029-04-26 | Level 3 | F |  | 2029-04-26 | Level 3
128800791 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128800816 | other | HFTD Tier 3 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128800884 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128800928 | other | HFTD Tier 3 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128800973 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
128801088 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
128801109 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
128801147 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
128801209 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
128801901 | conductor | HFTD Tier 2 | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128802077 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-18 | 2025-05-18 | Level 2 | E |  | 2025-05-18 | Level 2
128802764 | insulator and brushing | Non-HFTD | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128802765 | pole | Non-HFTD | Transmission | 2024-05-18 | 2027-05-18 | Level 2 | E |  | 2027-05-18 | Level 2
128802767 | other | Non-HFTD | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128802807 | pole | Non-HFTD | Transmission | 2024-05-18 | 2027-05-18 | Level 2 | E |  | 2027-05-18 | Level 2
128802825 | pole | Non-HFTD | Transmission | 2024-05-18 | 2027-05-18 | Level 2 | E |  | 2025-05-18 | Level 2
128802989 | pole | Non-HFTD | Transmission | 2024-05-18 | 2027-05-18 | Level 2 | E |  | 2027-05-18 | Level 2
128802999 | other | HFTD Tier 2 | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128803048 | other | HFTD Tier 2 | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128803222 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128803649 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
128803674 | pole | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
128803693 | other | Non-HFTD | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
128803803 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
128803872 | other | HFTD Tier 3 | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128803875 | other | HFTD Tier 2 | Transmission | 2024-05-18 | 2029-05-18 | Level 3 | F |  | 2029-05-18 | Level 3
128805542 | pole | Non-HFTD | Transmission | 2024-05-15 | 2027-05-15 | Level 2 | E |  | 2027-05-15 | Level 2
128805722 | other | Non-HFTD | Transmission | 2024-05-20 | 2027-05-20 | Level 2 | E |  | 2027-05-20 | Level 2
128806275 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128806560 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128806661 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128807015 | pole | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128807219 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128811556 | pole | Non-HFTD | Transmission | 2024-05-20 | 2027-05-20 | Level 2 | E |  | 2027-05-20 | Level 2
128811581 | pole | HFTD Tier 2 | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128811827 | pole | Non-HFTD | Transmission | 2024-05-20 | 2027-05-20 | Level 2 | E |  | 2027-05-20 | Level 2
128817632 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128817655 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128818055 | pole | HFTD Tier 3 | Transmission | 2024-04-30 | 2027-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128818289 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128818374 | pole | Non-HFTD | Transmission | 2024-05-20 | 2027-05-20 | Level 2 | E |  | 2027-05-20 | Level 2
128818676 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128818727 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2027-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128818839 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128818862 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128818879 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128818880 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128818887 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128818992 | other | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128819053 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128819056 | pole | Non-HFTD | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128819080 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128819149 | pole | HFTD Tier 2 | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128819156 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
128819181 | crossarm | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
128819187 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128819198 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128819220 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128819264 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
128819270 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128819293 | anchor/guy | Non-HFTD | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128819319 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128819327 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128819367 | pole | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128819379 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2029-04-29 | Level 3 | F |  | 2029-04-29 | Level 3
128819385 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128819388 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128819411 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-20 | 2024-11-20 | Level 2 | E | 2024-09-24 | 2024-11-20 | Level 2 | Field Safety Reassessment
128819421 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F | 2024-11-12 | 2029-05-20 | Level 3 | GO 165 Inspection
128819436 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128819488 | anchor/guy | Non-HFTD | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F | 2024-07-24 | 2029-05-03 | Level 3 | GO 165 Inspection
128819500 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-20 | 2024-11-20 | Level 2 | E | 2024-12-27 | 2024-11-20 | Level 2 | Field Safety Reassessment
128819502 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
128819506 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2024-08-20 | Level 2
128819520 | pole | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-29 | Level 2 | E |  | 2025-04-29 | Level 2
128819863 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128820005 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128822237 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128824844 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128827340 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128830495 | pole | Non-HFTD | Transmission | 2024-05-21 | 2027-05-21 | Level 2 | E | 2024-09-13 | 2027-05-21 | Level 2 | GO 165 Inspection
128832838 | anchor/guy | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128833865 | pole | Non-HFTD | Transmission | 2024-05-21 | 2027-05-21 | Level 2 | E | 2024-09-13 | 2027-05-21 | Level 2 | GO 165 Inspection
128833910 | other | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128834007 | pole | Non-HFTD | Transmission | 2024-05-21 | 2027-05-21 | Level 2 | E |  | 2027-05-21 | Level 2
128834120 | pole | Non-HFTD | Transmission | 2024-05-21 | 2027-05-21 | Level 2 | E | 2024-09-12 | 2027-05-21 | Level 2 | GO 165 Inspection
128834488 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128834841 | pole | Non-HFTD | Transmission | 2024-05-21 | 2027-05-21 | Level 2 | E | 2024-09-12 | 2027-05-21 | Level 2 | GO 165 Inspection
128835285 | anchor/guy | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128835511 | other | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128835514 | other | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128835629 | anchor/guy | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128835856 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128836591 | pole | HFTD Tier 3 | Transmission | 2024-05-21 | 2024-11-21 | Level 2 | E | 2024-11-18 | 2024-11-21 | Level 2 | Field Safety Reassessment
128836784 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128836788 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128836880 | pole | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128836896 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128836902 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128836906 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128836909 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128836932 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128837033 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128837034 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
128837086 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128837108 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128837152 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128837192 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128837260 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
128837274 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128837275 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128837279 | pole | HFTD Tier 3 | Transmission | 2024-05-21 | 2024-11-21 | Level 2 | E |  | 2024-11-21 | Level 2
128837306 | other | Non-HFTD | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E | 2024-08-16 | 2027-05-03 | Level 2 | GO 165 Inspection
128837406 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128837408 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128837444 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2024-11-07 | Level 2 | E |  | 2024-11-07 | Level 2
128837447 | anchor/guy | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128837450 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128837557 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128837592 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128837833 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
128838727 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128838751 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128838993 | pole | Non-HFTD | Transmission | 2024-05-22 | 2027-05-22 | Level 2 | E |  | 2027-05-22 | Level 2
128839134 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2024-08-22 | Level 2 | E | 2024-11-05 | 2024-08-22 | Level 2 | Field Safety Reassessment
128839166 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128839219 | anchor/guy | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128839488 | pole | Non-HFTD | Transmission | 2024-05-22 | 2027-05-22 | Level 2 | E |  | 2027-05-22 | Level 2
128839729 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2024-08-22 | Level 2 | E |  | 2024-08-22 | Level 2
128839972 | pole | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128840209 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
128840399 | insulator and brushing | Non-HFTD | Transmission | 2024-05-22 | 2027-05-22 | Level 2 | E |  | 2027-05-22 | Level 2
128840600 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128840646 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128840689 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
128840836 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128840880 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128840996 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128841136 | pole | Non-HFTD | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
128841757 | insulator and brushing | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128841792 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
128842188 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128842365 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
128842671 | other | Non-HFTD | Transmission | 2024-05-22 | 2027-05-22 | Level 2 | E | 2024-09-13 | 2027-05-22 | Level 2 | GO 165 Inspection
128842948 | other | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128851515 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128852413 | pole | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-25 | Level 2 | E |  | 2025-04-25 | Level 2
128856251 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
128858696 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128867262 | insulator and brushing | Non-HFTD | Transmission | 2024-05-23 | 2027-05-23 | Level 2 | E |  | 2027-05-23 | Level 2
128881980 | pole | Non-HFTD | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128882067 | pole | Non-HFTD | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128883377 | pole | Non-HFTD | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128883655 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128883658 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
128883721 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
128883943 | other | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128884031 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128884065 | other | Non-HFTD | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
128885733 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-23 | 2024-11-23 | Level 2 | E |  | 2024-11-23 | Level 2
128885945 | other | Non-HFTD | Transmission | 2024-05-24 | 2024-11-24 | Level 2 | E |  | 2024-11-24 | Level 2
128886845 | anchor/guy | Non-HFTD | Transmission | 2024-05-23 | 2027-05-23 | Level 2 | E |  | 2027-05-23 | Level 2
128886848 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128887024 | other | HFTD Tier 3 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128887051 | crossarm | Non-HFTD | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
128887062 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128887078 | pole | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128887201 | pole | HFTD Tier 3 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128887368 | pole | HFTD Tier 3 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128887400 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128887503 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128887567 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128887606 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128887642 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E | 2024-06-01 | 2025-05-06 | Level 2 | GO 165 Inspection
128887652 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128887653 | other | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128887738 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-22 | 2024-11-22 | Level 2 | E |  | 2024-11-22 | Level 2
128887762 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128887892 | pole | HFTD Tier 2 | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128887982 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128887989 | other | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128888231 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128888308 | anchor/guy | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128888371 | other | HFTD Tier 3 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128888378 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | Level 2 | E |  | 2025-04-30 | Level 2
128888397 | other | HFTD Tier 3 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128888401 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128888501 | pole | Non-HFTD | Transmission | 2024-05-24 | 2027-05-24 | Level 2 | E |  | 2027-05-24 | Level 2
128888539 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128888547 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128888576 | conductor | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128888604 | anchor/guy | Non-HFTD | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128888615 | conductor | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128888646 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128888689 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128888866 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
128888954 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F | 2024-06-10 | 2029-05-22 | Level 3 | GO 165 Inspection
128889015 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128889126 | pole | HFTD Tier 3 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128889147 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128889197 | anchor/guy | Non-HFTD | Transmission | 2024-05-24 | 2027-05-24 | Level 2 | E |  | 2027-05-24 | Level 2
128889200 | anchor/guy | Non-HFTD | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128889236 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128889337 | other | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128889348 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128889462 | pole | HFTD Tier 2 | Transmission | 2024-04-30 | 2029-04-30 | Level 3 | F |  | 2029-04-30 | Level 3
128889470 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128889501 | insulator and brushing | Non-HFTD | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128889573 | anchor/guy | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128889613 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128889615 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128889619 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128889650 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128889671 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128890632 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128890645 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128890662 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128890668 | other | HFTD Tier 3 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128890684 | pole | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128890865 | anchor/guy | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E | 2024-08-31 | 2027-05-10 | Level 2 | GO 165 Inspection
128890867 | insulator and brushing | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E | 2024-08-31 | 2027-05-10 | Level 2 | GO 165 Inspection
128890869 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128890932 | other | Non-HFTD | Transmission | 2024-05-07 | 2027-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128890940 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128891013 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
128891048 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128891117 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128891459 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-25 | 2025-05-25 | Level 2 | E |  | 2025-05-25 | Level 2
128891509 | anchor/guy | Non-HFTD | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
128891806 | pole | Non-HFTD | Transmission | 2024-05-25 | 2025-05-25 | Level 2 | E |  | 2025-05-25 | Level 2
128891826 | other | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
128896241 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
128896242 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2024-08-28 | Level 2
128896332 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128897880 | insulator and brushing | Non-HFTD | Transmission | 2024-05-28 | 2027-05-28 | Level 2 | E |  | 2027-05-28 | Level 2
128897885 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
128897949 | insulator and brushing | Non-HFTD | Transmission | 2024-05-28 | 2027-05-28 | Level 2 | E |  | 2027-05-28 | Level 2
128899489 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128899497 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
128899701 | pole | Non-HFTD | Transmission | 2024-05-28 | 2027-05-28 | Level 2 | E |  | 2027-05-28 | Level 2
128899857 | other | Non-HFTD | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128900596 | other | Non-HFTD | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128900598 | conductor | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128901699 | pole | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128901711 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128901774 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128901825 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128901828 | anchor/guy | Non-HFTD | Transmission | 2024-05-06 | 2025-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128901850 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F | 2024-07-17 | 2029-05-13 | Level 3 | GO 165 Inspection
128901910 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
128902002 | pole | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
128902008 | other | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
128902028 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128902070 | other | Non-HFTD | Transmission | 2024-05-01 | 2029-05-01 | Level 3 | F |  | 2029-05-01 | Level 3
128902076 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128902103 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128902111 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
128902133 | pole | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
128902167 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-25 | 2025-05-25 | Level 2 | E |  | 2025-05-25 | Level 2
128902183 | other | HFTD Tier 3 | Transmission | 2024-05-11 | 2029-05-11 | Level 3 | F |  | 2029-05-11 | Level 3
128902190 | other | HFTD Tier 3 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128902195 | other | HFTD Tier 3 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128902237 | pole | Non-HFTD | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2027-05-13 | Level 2
128902238 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
128902250 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128902261 | pole | HFTD Tier 3 | Transmission | 2024-05-08 | 2024-11-08 | Level 2 | E |  | 2024-11-08 | Level 2
128902268 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
128902276 | pole | HFTD Tier 2 | Transmission | 2024-05-01 | 2025-05-01 | Level 2 | E |  | 2025-05-01 | Level 2
128902313 | pole | Non-HFTD | Transmission | 2024-05-28 | 2027-05-28 | Level 2 | E |  | 2027-05-28 | Level 2
128902479 | other | HFTD Tier 2 | Transmission | 2024-05-02 | 2029-05-02 | Level 3 | F |  | 2029-05-02 | Level 3
128902498 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128902499 | pole | HFTD Tier 2 | Transmission | 2024-05-10 | 2025-05-10 | Level 2 | E |  | 2025-05-10 | Level 2
128902621 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128902637 | other | HFTD Tier 2 | Transmission | 2024-05-03 | 2025-05-03 | Level 2 | E |  | 2025-05-03 | Level 2
128902652 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128902659 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128902670 | pole | HFTD Tier 2 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128902680 | anchor/guy | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128902695 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128902699 | pole | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E | 2024-08-30 | 2027-05-10 | Level 2 | GO 165 Inspection
128902708 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128902721 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F | 2024-08-30 | 2029-05-10 | Level 3 | GO 165 Inspection
128902725 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2027-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128902734 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128902745 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-25 | 2025-05-25 | Level 2 | E |  | 2025-05-25 | Level 2
128902760 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2024-08-28 | Level 2 | E |  | 2025-05-28 | Level 2
128902766 | pole | HFTD Tier 3 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128902801 | other | HFTD Tier 3 | Transmission | 2024-05-03 | 2029-05-03 | Level 3 | F |  | 2029-05-03 | Level 3
128902802 | other | HFTD Tier 2 | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128902871 | other | Non-HFTD | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128902934 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128902949 | insulator and brushing | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128902984 | crossarm | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128904909 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
128905693 | other | Non-HFTD | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F | 2024-09-04 | 2029-05-29 | Level 3 | GO 165 Inspection
128906056 | anchor/guy | Non-HFTD | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F | 2024-09-04 | 2029-05-29 | Level 3 | GO 165 Inspection
128906465 | other | Non-HFTD | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128906650 | conductor | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128907049 | conductor | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128907691 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128908521 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128909263 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128909452 | pole | Non-HFTD | Transmission | 2024-05-29 | 2027-05-29 | Level 2 | E |  | 2027-05-29 | Level 2
128909650 | other | Non-HFTD | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128909689 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128909764 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128909772 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128909808 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128909829 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128909880 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128910012 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128910015 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128910032 | other | HFTD Tier 3 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128910038 | other | Non-HFTD | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F | 2024-06-20 | 2029-05-08 | Level 3 | GO 165 Inspection
128910062 | crossarm | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
128910197 | other | HFTD Tier 3 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128910201 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128910281 | anchor/guy | Non-HFTD | Transmission | 2024-05-03 | 2027-05-03 | Level 2 | E | 2024-10-24 | 2027-05-03 | Level 2 | GO 165 Inspection
128910295 | pole | HFTD Tier 3 | Transmission | 2024-05-14 | 2024-11-14 | Level 2 | E |  | 2024-11-14 | Level 2
128910471 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128910476 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128910479 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128910502 | pole | Non-HFTD | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128910515 | pole | Non-HFTD | Transmission | 2024-05-09 | 2027-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128910534 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
128912147 | other | Non-HFTD | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F | 2024-09-17 | 2029-05-29 | Level 3 | GO 165 Inspection
128912398 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128913943 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128914885 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128915371 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128916556 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128921701 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128921882 | pole | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128924751 | pole | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128924984 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128929825 | pole | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128932929 | pole | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128933894 | other | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128933897 | insulator and brushing | Non-HFTD | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128935478 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128935523 | splice | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128935526 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128935537 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F | 2024-07-21 | 2029-05-30 | Level 3 | Field Safety Reassessment
128935683 | splice | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128935726 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128935750 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E | 2024-06-10 | 2025-05-30 | Level 2 | GO 165 Inspection
128935851 | pole | Non-HFTD | Transmission | 2024-05-30 | 2027-05-30 | Level 2 | E |  | 2027-05-30 | Level 2
128935912 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128935948 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128937716 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128937730 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128937735 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128937739 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128938222 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128938232 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128938272 | pole | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128944159 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128947331 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128954439 | pole | Non-HFTD | Transmission | 2024-05-31 | 2024-08-31 | Level 2 | E | 2024-09-19 | 2024-08-31 | Level 2 | Field Safety Reassessment
128954805 | other | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128956149 | pole | Non-HFTD | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128956300 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128956301 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-11-29 | Level 2 | E |  | 2025-05-29 | Level 2
128956599 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
128957599 | pole | Non-HFTD | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128957607 | other | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128958102 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128958293 | other | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128958855 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
128959546 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
128959571 | pole | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E | 2024-08-28 | 2027-05-10 | Level 2 | GO 165 Inspection
128960186 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128960390 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128960723 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128960754 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128960936 | pole | HFTD Tier 3 | Transmission | 2024-05-30 | 2024-11-30 | Level 2 | E |  | 2024-11-30 | Level 2
128961147 | pole | Non-HFTD | Transmission | 2024-05-06 | 2027-05-06 | Level 2 | E |  | 2025-05-06 | Level 2
128961174 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
128961195 | pole | HFTD Tier 3 | Transmission | 2024-05-30 | 2024-11-30 | Level 2 | E | 2024-10-24 | 2024-11-30 | Level 2 | Field Safety Reassessment
128961208 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
128961294 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128961395 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
128961448 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128961564 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128961615 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128961622 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128961721 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
128961911 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128961931 | other | Non-HFTD | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128961954 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128962041 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128962050 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128962102 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128962167 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-31 | 2024-11-30 | Level 2 | E | 2024-11-20 | 2024-11-30 | Level 2 | Field Safety Reassessment
128962192 | other | Non-HFTD | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128962403 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
128962414 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128962417 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128962421 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128962462 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128962470 | other | Non-HFTD | Transmission | 2024-05-08 | 2027-05-08 | Level 2 | E | 2024-09-10 | 2027-05-08 | Level 2 | GO 165 Inspection
128962717 | conductor | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128962955 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128963020 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128963114 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128963135 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128963695 | other | HFTD Tier 3 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964062 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964078 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964084 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128964128 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964132 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964150 | other | HFTD Tier 3 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964155 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128964169 | pole | HFTD Tier 2 | Transmission | 2024-05-07 | 2025-05-07 | Level 2 | E |  | 2025-05-07 | Level 2
128964177 | other | Non-HFTD | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964184 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128964186 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
128964195 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128964202 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
128964220 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128964252 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964266 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
128964270 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128964281 | other | HFTD Tier 2 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128964285 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128964290 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964297 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964324 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964342 | other | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128964381 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E | 2024-06-13 | 2025-05-31 | Level 2 | GO 165 Inspection
128964384 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128964417 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128964428 | anchor/guy | Non-HFTD | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128964435 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964436 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964438 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964440 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
128964468 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128964496 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
128964513 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
128964535 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
128964562 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2029-05-07 | Level 3 | F |  | 2029-05-07 | Level 3
128964568 | pole | HFTD Tier 3 | Transmission | 2024-05-07 | 2024-11-07 | Level 2 | E | 2024-10-09 | 2024-08-07 | Level 2 | Field Safety Reassessment
128964605 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128964607 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
128964652 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
128964659 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
128964887 | pole | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
128965146 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
128965335 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
128965376 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
128965380 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
128965649 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F | 2024-07-20 | 2029-06-01 | Level 3 | Field Safety Reassessment
128965653 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E | 2024-07-20 | 2025-06-01 | Level 2 | Field Safety Reassessment
128965742 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
128965762 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
128965774 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
128966483 | switch | Non-HFTD | Transmission | 2024-06-02 | 2027-06-02 | Level 2 | E |  | 2027-06-02 | Level 2
128974545 | pole | Non-HFTD | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E |  | 2027-06-03 | Level 2
128980536 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128980538 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
128996586 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
128997339 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
128999021 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129002447 | pole | Non-HFTD | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E |  | 2027-06-03 | Level 2
129002781 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129002787 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129003166 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129003168 | anchor/guy | Non-HFTD | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E | 2024-09-23 | 2027-06-03 | Level 2 | GO 165 Inspection
129003273 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129003668 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129008428 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129010325 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129014494 | other | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129015080 | other | HFTD Tier 3 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129015167 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129015281 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E | 2024-06-06 | 2025-06-03 | Level 2 | GO 165 Inspection
129015417 | other | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129015757 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129015775 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129015776 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129015791 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129015796 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129015799 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129015822 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129015870 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129015871 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129015873 | anchor/guy | Non-HFTD | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129016007 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129016011 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129016022 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129016102 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129016176 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129016431 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129017797 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129018097 | insulator and brushing | Non-HFTD | Transmission | 2024-06-04 | 2027-06-04 | Level 2 | E |  | 2027-06-04 | Level 2
129018240 | pole | Non-HFTD | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129018862 | pole | HFTD Tier 3 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129018996 | other | Non-HFTD | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129019140 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129019157 | insulator and brushing | Non-HFTD | Transmission | 2024-06-04 | 2027-06-04 | Level 2 | E |  | 2027-06-04 | Level 2
129019312 | insulator and brushing | Non-HFTD | Transmission | 2024-06-04 | 2027-06-04 | Level 2 | E |  | 2027-06-04 | Level 2
129020073 | pole | Non-HFTD | Transmission | 2024-06-04 | 2024-09-04 | Level 2 | E |  | 2024-09-04 | Level 2
129021121 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129021183 | other | Non-HFTD | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129021248 | anchor/guy | Non-HFTD | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129021249 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129021289 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129021308 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129021369 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129021451 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129021463 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129021464 | other | HFTD Tier 3 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129021515 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2025-06-02 | Level 2 | E |  | 2025-06-02 | Level 2
129021586 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129021596 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129021705 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129021707 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2025-06-02 | Level 3 | F | 2024-06-13 | 2029-06-02 | Level 3 | GO 165 Inspection
129021727 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129021750 | other | HFTD Tier 3 | Transmission | 2024-05-15 | 2024-11-15 | Level 2 | E |  | 2024-11-15 | Level 2
129021753 | pole | HFTD Tier 3 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129021754 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129021816 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129021827 | anchor/guy | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
129021862 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129021878 | switch | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
129021884 | pole | Non-HFTD | Transmission | 2024-06-04 | 2027-06-04 | Level 2 | E |  | 2027-06-04 | Level 2
129021912 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129021919 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
129021924 | other | HFTD Tier 3 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129021960 | anchor/guy | Non-HFTD | Transmission | 2024-05-08 | 2025-05-08 | Level 2 | E |  | 2025-05-08 | Level 2
129021969 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129021986 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129022004 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129022039 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-02 | 2025-06-02 | Level 2 | E |  | 2025-06-02 | Level 2
129022079 | other | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
129022092 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129022093 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129022096 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129022116 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129022151 | anchor/guy | HFTD Tier 3 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
129022160 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129022192 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129022201 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129022207 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129022227 | insulator and brushing | Non-HFTD | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
129022231 | other | HFTD Tier 3 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129022233 | pole | HFTD Tier 3 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129022235 | other | HFTD Tier 3 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129022255 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129022279 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2024-12-03 | Level 2 | E |  | 2024-12-03 | Level 2
129022305 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129022313 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2027-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129022377 | other | HFTD Tier 3 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129022421 | crossarm | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129023001 | pole | Non-HFTD | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E |  | 2027-06-03 | Level 2
129023236 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129023522 | insulator and brushing | Non-HFTD | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129023628 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129023664 | pole | Non-HFTD | Transmission | 2024-06-05 | 2027-06-05 | Level 2 | E | 2024-09-19 | 2027-06-05 | Level 2 | GO 165 Inspection
129024194 | anchor/guy | Non-HFTD | Transmission | 2024-06-05 | 2027-06-05 | Level 2 | E | 2024-09-19 | 2027-06-05 | Level 2 | GO 165 Inspection
129024682 | other | HFTD Tier 3 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129024946 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129025155 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129025695 | other | HFTD Tier 3 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129025925 | pole | HFTD Tier 3 | Transmission | 2024-06-05 | 2024-12-05 | Level 2 | E |  | 2024-12-05 | Level 2
129025994 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129026002 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129026003 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129026088 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129026156 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129026183 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129026222 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129026250 | anchor/guy | Non-HFTD | Transmission | 2024-05-09 | 2025-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
129026293 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129026297 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129026340 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129026341 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129026347 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
129026348 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129026419 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129026429 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129026462 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129026491 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129026492 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129026495 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129026511 | other | HFTD Tier 3 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129026546 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129026549 | other | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
129026634 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129026643 | pole | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129026653 | insulator and brushing | Non-HFTD | Transmission | 2024-05-09 | 2027-05-09 | Level 2 | E |  | 2025-05-09 | Level 2
129026691 | anchor/guy | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F |  | 2029-05-10 | Level 3
129026693 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129026700 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2027-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129026703 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129026705 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129026732 | other | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129026761 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129026766 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129026770 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129026784 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129026785 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129026810 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129026811 | other | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129026814 | insulator and brushing | Non-HFTD | Transmission | 2024-05-17 | 2027-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129026816 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129026874 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129026879 | pole | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129026910 | pole | HFTD Tier 3 | Transmission | 2024-05-17 | 2024-11-17 | Level 2 | E |  | 2024-11-17 | Level 2
129026933 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129026934 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129026947 | insulator and brushing | Non-HFTD | Transmission | 2024-05-10 | 2029-05-10 | Level 3 | F | 2024-08-28 | 2029-05-10 | Level 3 | GO 165 Inspection
129026959 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129026972 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129027003 | pole | HFTD Tier 3 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129027008 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129027070 | pole | HFTD Tier 2 | Transmission | 2024-05-09 | 2029-05-09 | Level 3 | F |  | 2029-05-09 | Level 3
129027326 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129027417 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129028063 | insulator and brushing | Non-HFTD | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129028097 | other | Non-HFTD | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129029324 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129030225 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129030549 | other | Non-HFTD | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129030586 | anchor/guy | Non-HFTD | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129030640 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129030673 | insulator and brushing | Non-HFTD | Transmission | 2024-06-06 | 2027-06-06 | Level 2 | E |  | 2027-06-06 | Level 2
129030798 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129031169 | insulator and brushing | Non-HFTD | Transmission | 2024-06-06 | 2027-06-06 | Level 2 | E |  | 2027-06-06 | Level 2
129031508 | other | HFTD Tier 3 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129031524 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129031567 | pole | HFTD Tier 3 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129031600 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129031617 | other | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129031641 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129031645 | pole | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129031649 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129031665 | other | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129031678 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129031681 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129031811 | other | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129031845 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129031873 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129031891 | other | HFTD Tier 3 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129031913 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129031915 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2029-05-13 | Level 3 | F |  | 2029-05-13 | Level 3
129031921 | pole | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129031924 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129032033 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129032131 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129032137 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129032150 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129032152 | pole | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129032180 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129032199 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129032209 | other | HFTD Tier 3 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129032256 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129032270 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129032295 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129032296 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129032297 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129032510 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129032592 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129032683 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129032687 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129033287 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129033794 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129034575 | anchor/guy | Non-HFTD | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E | 2024-11-13 | 2025-06-07 | Level 2 | GO 165 Inspection
129035243 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129035327 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2024-11-16 | Level 2 | E |  | 2024-11-16 | Level 2
129035494 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129035551 | pole | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129035554 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129035556 | pole | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129035557 | other | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E | 2024-08-20 | 2027-05-10 | Level 2 | GO 165 Inspection
129035570 | insulator and brushing | Non-HFTD | Transmission | 2024-06-07 | 2027-06-07 | Level 2 | E |  | 2027-06-07 | Level 2
129035617 | other | Non-HFTD | Transmission | 2024-05-10 | 2027-05-10 | Level 2 | E | 2024-08-20 | 2027-05-10 | Level 2 | GO 165 Inspection
129035619 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129035661 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2024-12-06 | Level 2 | E | 2024-12-23 | 2024-12-06 | Level 2 | Field Safety Reassessment
129035681 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129035684 | other | HFTD Tier 3 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129035686 | other | HFTD Tier 3 | Transmission | 2024-06-06 | 2024-12-06 | Level 2 | E | 2024-12-18 | 2024-12-06 | Level 2 | Field Safety Reassessment
129035688 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129035733 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129035808 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129035833 | other | Non-HFTD | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129035917 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129035972 | pole | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129035977 | insulator and brushing | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129036092 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129036187 | anchor/guy | Non-HFTD | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129036188 | insulator and brushing | Non-HFTD | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129036274 | pole | HFTD Tier 2 | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
129036278 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F | 2024-06-16 | 2029-06-06 | Level 3 | GO 165 Inspection
129036283 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E | 2024-06-16 | 2025-06-06 | Level 2 | GO 165 Inspection
129036337 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129036339 | other | HFTD Tier 2 | Transmission | 2024-05-06 | 2029-05-06 | Level 3 | F |  | 2029-05-06 | Level 3
129036421 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129036513 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129036566 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129036619 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129036624 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129036683 | other | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129036749 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129036773 | anchor/guy | Non-HFTD | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129036910 | crossarm | HFTD Tier 3 | Transmission | 2024-05-21 | 2024-11-21 | Level 3 | F |  | 2029-05-21 | Level 3
129036914 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129036938 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129036964 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129036970 | other | Non-HFTD | Transmission | 2024-05-13 | 2025-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
129037094 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129037132 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129037243 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129037253 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129037273 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129037484 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129037533 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129037827 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129037881 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129038135 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129038352 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129038362 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 3 | F | 2024-10-30 | 2029-06-08 | Level 3 | Field Safety Reassessment
129038392 | other | Non-HFTD | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129038460 | anchor/guy | Non-HFTD | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129038601 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129049881 | insulator and brushing | Non-HFTD | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129050076 | insulator and brushing | Non-HFTD | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129051399 | insulator and brushing | Non-HFTD | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129051992 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129052079 | anchor/guy | Non-HFTD | Transmission | 2024-06-10 | 2027-06-10 | Level 2 | E |  | 2027-06-10 | Level 2
129052124 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129052214 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129052280 | other | HFTD Tier 3 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129052912 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129053021 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129053730 | pole | Non-HFTD | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129053792 | conductor | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129054249 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129054410 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129054455 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129054540 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E | 2024-12-23 | 2024-09-07 | Level 2 | Field Safety Reassessment
129054547 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129054548 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129054549 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129054590 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129054619 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129054631 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129054634 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129054673 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129054680 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129054686 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129054758 | pole | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129054786 | pole | HFTD Tier 3 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129054843 | other | HFTD Tier 3 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129054856 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129054916 | insulator and brushing | Non-HFTD | Transmission | 2024-05-31 | 2027-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129054933 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129054984 | other | HFTD Tier 2 | Transmission | 2024-05-13 | 2027-05-13 | Level 2 | E |  | 2025-05-13 | Level 2
129055036 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129055185 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129055192 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129055211 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129055240 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129055252 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129055898 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129056803 | other | HFTD Tier 3 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129057595 | other | HFTD Tier 3 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129057902 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129058243 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129058323 | conductor | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129058660 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129058885 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129059063 | pole | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E |  | 2027-06-11 | Level 2
129059144 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E | 2024-10-29 | 2024-09-11 | Level 2 | Field Safety Reassessment
129059148 | pole | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129060319 | other | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E | 2024-10-29 | 2027-06-11 | Level 2 | GO 165 Inspection
129060820 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129061044 | pole | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E | 2024-08-22 | 2027-06-11 | Level 2 | GO 165 Inspection
129061093 | other | Non-HFTD | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E | 2024-06-20 | 2025-06-08 | Level 2 | GO 165 Inspection
129061191 | pole | HFTD Tier 3 | Transmission | 2024-05-22 | 2024-11-22 | Level 2 | E |  | 2024-11-22 | Level 2
129061216 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129061222 | pole | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129061356 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
129061365 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129061377 | pole | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
129061385 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-11 | 2024-12-11 | Level 2 | E | 2024-12-09 | 2024-12-11 | Level 2 | Field Safety Reassessment
129061410 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-11 | 2024-12-11 | Level 2 | E | 2024-12-30 | 2024-12-11 | Level 2 | Field Safety Reassessment
129061424 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129061427 | pole | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129061430 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2025-05-14 | Level 2 | E |  | 2025-05-14 | Level 2
129061434 | pole | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
129061476 | pole | HFTD Tier 3 | Transmission | 2024-06-10 | 2027-06-10 | Level 2 | E |  | 2027-06-10 | Level 2
129061478 | other | HFTD Tier 3 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129061512 | switch | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129061521 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129061563 | pole | HFTD Tier 3 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129061601 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129061653 | other | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129061666 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129061709 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129061731 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129061802 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129061928 | pole | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129061929 | other | Non-HFTD | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129062000 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129063277 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129064613 | other | Non-HFTD | Transmission | 2024-06-12 | 2027-06-12 | Level 2 | E |  | 2025-06-12 | Level 2
129064966 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129065220 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129065923 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129065930 | pole | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-09-16 | 2029-06-12 | Level 3 | GO 165 Inspection
129066310 | pole | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129066329 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2025-06-12 | Level 2 | E |  | 2025-06-12 | Level 2
129066436 | other | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129067214 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129067270 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129067280 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129067283 | other | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129067300 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2024-09-12 | Level 2 | E | 2024-12-23 | 2024-09-12 | Level 2 | Field Safety Reassessment
129067304 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2025-06-12 | Level 2 | E |  | 2025-06-12 | Level 2
129067433 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129067440 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129067460 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129067475 | pole | HFTD Tier 2 | Transmission | 2024-05-14 | 2029-05-14 | Level 3 | F |  | 2029-05-14 | Level 3
129067528 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129067603 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129067605 | other | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129067641 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129067647 | pole | HFTD Tier 3 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129067660 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129067687 | pole | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129067726 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2024-09-12 | Level 2 | E | 2024-12-23 | 2024-09-12 | Level 2 | Field Safety Reassessment
129067744 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129067760 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129067785 | pole | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129067830 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129067854 | anchor/guy | Non-HFTD | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129067902 | other | Non-HFTD | Transmission | 2024-06-12 | 2027-06-12 | Level 2 | E | 2024-09-09 | 2027-06-12 | Level 2 | GO 165 Inspection
129069584 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2024-12-06 | Level 2 | E | 2024-11-21 | 2024-12-06 | Level 2 | Field Safety Reassessment
129069928 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 3 | F | 2024-07-17 | 2029-05-28 | Level 3 | GO 165 Inspection
129070159 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129070204 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129071510 | conductor | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E |  | 2027-06-13 | Level 2
129071993 | insulator and brushing | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F | 2024-09-19 | 2029-06-13 | Level 3 | GO 165 Inspection
129072003 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129072196 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129072458 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129072919 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129072929 | insulator and brushing | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E | 2024-09-30 | 2027-06-13 | Level 2 | GO 165 Inspection
129072938 | other | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E | 2024-09-30 | 2027-06-13 | Level 2 | GO 165 Inspection
129073405 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129073424 | pole | Non-HFTD | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129073738 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129073895 | pole | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129073898 | conductor | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129075421 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129076408 | pole | HFTD Tier 2 | Transmission | 2024-06-14 | 2025-06-14 | Level 2 | E |  | 2025-06-14 | Level 2
129076673 | other | HFTD Tier 2 | Transmission | 2024-05-15 | 2025-05-15 | Level 2 | E |  | 2025-05-15 | Level 2
129076737 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129076830 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-12 | 2024-12-12 | Level 2 | E | 2024-11-20 | 2024-09-12 | Level 2 | Field Safety Reassessment
129076853 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129076946 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129077005 | pole | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129077064 | other | HFTD Tier 2 | Transmission | 2024-05-16 | 2025-05-16 | Level 2 | E |  | 2025-05-16 | Level 2
129077067 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129077068 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-17 | 2025-05-17 | Level 2 | E |  | 2025-05-17 | Level 2
129077114 | pole | HFTD Tier 2 | Transmission | 2024-05-25 | 2025-05-25 | Level 2 | E |  | 2025-05-25 | Level 2
129077169 | other | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129077215 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129077233 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-12 | 2024-12-12 | Level 2 | E | 2024-11-20 | 2024-09-12 | Level 2 | Field Safety Reassessment
129077331 | pole | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129077334 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129077383 | crossarm | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129077450 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129077453 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129077467 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129077554 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129077584 | pole | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129077604 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129077684 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129077725 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129077763 | other | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129077819 | pole | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129077889 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129077936 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129078022 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129078130 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129078179 | other | HFTD Tier 3 | Transmission | 2024-05-17 | 2029-05-17 | Level 3 | F |  | 2029-05-17 | Level 3
129078340 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129078391 | other | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129078496 | other | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129078542 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129078558 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129078611 | insulator and brushing | Non-HFTD | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E | 2024-06-17 | 2025-06-13 | Level 2 | GO 165 Inspection
129078686 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129078694 | other | Non-HFTD | Transmission | 2024-05-15 | 2029-05-15 | Level 3 | F |  | 2029-05-15 | Level 3
129078697 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129078775 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129078971 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129079086 | pole | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
129079172 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129079173 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129079679 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129079730 | insulator and brushing | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129080123 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129080156 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129080734 | other | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129080777 | other | HFTD Tier 2 | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129080818 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129080877 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129081070 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129081190 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129081556 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129081604 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129083166 | pole | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129083259 | other | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129083658 | pole | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129083709 | anchor/guy | Non-HFTD | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E | 2024-11-14 | 2025-06-17 | Level 2 | GO 165 Inspection
129083810 | other | HFTD Tier 2 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129083822 | insulator and brushing | Non-HFTD | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129084380 | anchor/guy | Non-HFTD | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E | 2024-11-14 | 2025-06-17 | Level 2 | GO 165 Inspection
129084728 | other | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129084926 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129084962 | other | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129085158 | insulator and brushing | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129085567 | other | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129085597 | pole | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2027-06-17 | Level 2
129085762 | pole | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E | 2024-11-19 | 2027-06-17 | Level 2 | GO 165 Inspection
129085905 | pole | HFTD Tier 2 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129085956 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129086078 | pole | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2027-06-17 | Level 2
129086451 | pole | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F | 2024-11-20 | 2029-06-17 | Level 3 | GO 165 Inspection
129086509 | insulator and brushing | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2027-06-17 | Level 2
129086621 | pole | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129087192 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129087264 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129087320 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129087362 | insulator and brushing | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2027-06-17 | Level 2
129087419 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129087460 | other | Non-HFTD | Transmission | 2024-05-16 | 2029-05-16 | Level 3 | F |  | 2029-05-16 | Level 3
129087464 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129087526 | insulator and brushing | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E | 2024-10-17 | 2027-06-17 | Level 2 | GO 165 Inspection
129087540 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129087542 | pole | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129087596 | other | HFTD Tier 3 | Transmission | 2024-05-21 | 2024-08-21 | Level 2 | E | 2024-09-18 | 2024-11-21 | Level 2 | Field Safety Reassessment
129087662 | pole | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129087676 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129087689 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129087708 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129087746 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129087752 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129087759 | insulator and brushing | Non-HFTD | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129087784 | other | HFTD Tier 3 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129087787 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129087821 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129087823 | anchor/guy | HFTD Tier 3 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129087833 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129087853 | pole | HFTD Tier 3 | Transmission | 2024-06-13 | 2024-12-13 | Level 2 | E |  | 2024-12-13 | Level 2
129087895 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129087896 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129087933 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129087961 | pole | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
129087973 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129088019 | pole | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129088022 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-14 | 2025-06-14 | Level 2 | E |  | 2025-06-14 | Level 2
129088037 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129088111 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129088154 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129088178 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129088187 | other | HFTD Tier 2 | Transmission | 2024-05-19 | 2025-05-19 | Level 2 | E |  | 2025-05-19 | Level 2
129088287 | pole | HFTD Tier 3 | Transmission | 2024-05-19 | 2024-11-19 | Level 2 | E | 2024-09-26 | 2024-11-19 | Level 2 | Field Safety Reassessment
129088288 | pole | HFTD Tier 3 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129088301 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129088334 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129088374 | pole | HFTD Tier 3 | Transmission | 2024-05-19 | 2029-05-19 | Level 3 | F |  | 2029-05-19 | Level 3
129088395 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129088398 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129088505 | pole | HFTD Tier 3 | Transmission | 2024-05-23 | 2024-11-23 | Level 2 | E |  | 2024-11-23 | Level 2
129090119 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2025-06-14 | Level 2 | E |  | 2025-06-14 | Level 2
129090544 | pole | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129090644 | pole | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129090812 | anchor/guy | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129091288 | pole | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129092559 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E |  | 2025-06-18 | Level 2
129093395 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129093596 | other | HFTD Tier 2 | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129093691 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E |  | 2025-06-18 | Level 2
129094119 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129094164 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129094166 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129094238 | other | Non-HFTD | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129094272 | pole | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129094277 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129094435 | other | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2027-06-17 | Level 2
129094443 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129094453 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129094537 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129094598 | pole | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129094675 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129094677 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129094682 | other | HFTD Tier 2 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129094719 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129094722 | crossarm | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129094804 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129094805 | conductor | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129094855 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129094881 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129094927 | pole | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129095111 | pole | HFTD Tier 3 | Transmission | 2024-05-20 | 2029-05-20 | Level 3 | F |  | 2029-05-20 | Level 3
129095175 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2025-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129095191 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129095211 | pole | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129095305 | anchor/guy | HFTD Tier 3 | Transmission | 2024-05-22 | 2024-11-22 | Level 2 | E | 2024-11-05 | 2024-11-22 | Level 2 | Field Safety Reassessment
129095306 | switch | HFTD Tier 3 | Transmission | 2024-06-14 | 2024-12-14 | Level 2 | E | 2024-11-29 | 2024-12-14 | Level 2 | Field Safety Reassessment
129095361 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-20 | 2025-05-20 | Level 2 | E |  | 2025-05-20 | Level 2
129095363 | other | Non-HFTD | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129095435 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129097421 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129097439 | pole | Non-HFTD | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E |  | 2025-06-18 | Level 2
129097528 | pole | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129097599 | other | Non-HFTD | Transmission | 2024-06-19 | 2027-06-19 | Level 2 | E | 2024-06-27 | 2027-06-19 | Level 2 | GO 165 Inspection
129097617 | pole | Non-HFTD | Transmission | 2024-06-19 | 2027-06-19 | Level 2 | E |  | 2027-06-19 | Level 2
129097797 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129097850 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129097943 | pole | HFTD Tier 2 | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129098086 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129098156 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129098250 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129099191 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129099517 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129099661 | other | Non-HFTD | Transmission | 2024-06-19 | 2029-06-19 | Level 3 | F |  | 2029-06-19 | Level 3
129100694 | other | Non-HFTD | Transmission | 2024-06-20 | 2025-06-20 | Level 2 | E |  | 2025-06-20 | Level 2
129100957 | pole | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129101228 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129102101 | pole | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129103652 | insulator and brushing | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129103655 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129103738 | pole | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2025-06-20 | Level 2
129103846 | pole | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129103898 | insulator and brushing | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129103997 | conductor | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129104044 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129104176 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129104219 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129104360 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2025-06-20 | Level 2
129104882 | pole | Non-HFTD | Transmission | 2024-06-20 | 2025-06-20 | Level 2 | E |  | 2025-06-20 | Level 2
129104948 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129104955 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129105077 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129105244 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129105310 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129105323 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129105395 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129105396 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129105404 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129105422 | other | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129105453 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E |  | 2025-06-18 | Level 2
129105493 | pole | HFTD Tier 3 | Transmission | 2024-05-21 | 2024-11-21 | Level 2 | E | 2024-11-19 | 2024-11-21 | Level 2 | Field Safety Reassessment
129105496 | anchor/guy | HFTD Tier 3 | Transmission | 2024-05-21 | 2024-11-21 | Level 2 | E | 2024-11-19 | 2024-11-21 | Level 2 | Field Safety Reassessment
129105533 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F | 2024-09-27 | 2029-06-20 | Level 3 | GO 165 Inspection
129105545 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129105566 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2027-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129105571 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129105572 | other | HFTD Tier 3 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129105579 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129105638 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129105662 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129105722 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129105738 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129105754 | other | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129105766 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129108375 | anchor/guy | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129108482 | pole | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E | 2024-11-15 | 2027-06-21 | Level 2 | GO 165 Inspection
129108918 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F | 2024-09-28 | 2029-06-21 | Level 3 | GO 165 Inspection
129109004 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129109308 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129109347 | conductor | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E | 2024-09-24 | 2027-06-20 | Level 2 | GO 165 Inspection
129109524 | pole | Non-HFTD | Transmission | 2024-06-21 | 2025-06-21 | Level 2 | E |  | 2025-06-21 | Level 2
129109829 | conductor | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129109899 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129110013 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129110601 | other | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129110698 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-21 | 2024-12-21 | Level 2 | E |  | 2024-12-21 | Level 2
129110707 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-21 | 2025-06-21 | Level 2 | E |  | 2025-06-21 | Level 2
129110769 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129110829 | pole | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129110860 | insulator and brushing | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129111020 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129112281 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129112517 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129112577 | pole | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129112842 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F | 2024-09-18 | 2029-06-21 | Level 3 | GO 165 Inspection
129113001 | insulator and brushing | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129115318 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-21 | 2025-06-21 | Level 2 | E |  | 2025-06-21 | Level 2
129115392 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-21 | 2025-06-21 | Level 2 | E |  | 2025-06-21 | Level 2
129115736 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129116282 | pole | HFTD Tier 2 | Transmission | 2024-06-20 | 2025-06-20 | Level 2 | E |  | 2025-06-20 | Level 2
129116525 | pole | HFTD Tier 2 | Transmission | 2023-05-17 | 2024-05-17 | Level 2 | E |  | 2024-05-17 | Level 2
129117599 | pole | Non-HFTD | Transmission | 2024-05-21 | 2027-05-21 | Level 2 | E |  | 2027-05-21 | Level 2
129118071 | other | HFTD Tier 2 | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129118601 | switch | Non-HFTD | Transmission | 2024-06-24 | 2025-06-24 | Level 2 | E |  | 2025-06-24 | Level 2
129118796 | anchor/guy | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E |  | 2027-06-24 | Level 2
129118811 | anchor/guy | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E |  | 2027-06-24 | Level 2
129118936 | insulator and brushing | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-13 | 2027-06-24 | Level 2 | GO 165 Inspection
129118961 | other | Non-HFTD | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129119198 | other | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E |  | 2027-06-24 | Level 2
129119301 | other | Non-HFTD | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129119553 | other | Non-HFTD | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129119747 | insulator and brushing | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-13 | 2027-06-24 | Level 2 | GO 165 Inspection
129119764 | insulator and brushing | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-13 | 2027-06-24 | Level 2 | GO 165 Inspection
129119903 | conductor | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129120051 | insulator and brushing | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-17 | 2024-12-24 | Level 2 | GO 165 Inspection
129120148 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129120223 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129120231 | conductor | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129120240 | pole | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E |  | 2027-06-24 | Level 2
129120253 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129120323 | pole | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129120384 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120393 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120398 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120401 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129120460 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129120473 | other | Non-HFTD | Transmission | 2024-05-22 | 2027-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129120474 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129120505 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129120509 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129120550 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129120634 | other | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129120643 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129120675 | other | HFTD Tier 2 | Transmission | 2024-05-21 | 2029-05-21 | Level 3 | F |  | 2029-05-21 | Level 3
129120691 | pole | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129120695 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120728 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129120775 | pole | HFTD Tier 3 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129120779 | pole | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120808 | pole | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129120836 | other | Non-HFTD | Transmission | 2024-05-22 | 2027-05-22 | Level 2 | E |  | 2025-05-22 | Level 2
129120837 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129120925 | other | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129120929 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120975 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129120976 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | E |  | 2025-05-21 | Level 2
129120991 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129121019 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129121085 | other | HFTD Tier 2 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129121133 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129121175 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129121201 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129121253 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129121256 | other | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129121806 | crossarm | HFTD Tier 2 | Transmission | 2024-06-25 | 2025-06-25 | Level 2 | E |  | 2025-06-25 | Level 2
129121959 | pole | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129122092 | pole | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129122346 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129122364 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F | 2024-09-06 | 2029-06-25 | Level 3 | GO 165 Inspection
129122980 | pole | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129123504 | pole | Non-HFTD | Transmission | 2024-06-25 | 2025-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129123820 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129124388 | insulator and brushing | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129124419 | pole | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129124754 | insulator and brushing | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129125996 | other | HFTD Tier 2 | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129126210 | pole | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129126413 | insulator and brushing | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129126838 | other | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129126914 | conductor | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129126915 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129126988 | other | HFTD Tier 3 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129126991 | crossarm | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129126994 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129127053 | insulator and brushing | Non-HFTD | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129127094 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2024-08-28 | Level 2 | E |  | 2027-05-28 | Level 2
129127096 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129127161 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129127163 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129127166 | other | Non-HFTD | Transmission | 2024-05-29 | 2027-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129127181 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129127214 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129127218 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129127234 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129127260 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129127261 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129127262 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129127282 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129128240 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129128250 | pole | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129128901 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E | 2024-11-05 | 2027-06-26 | Level 2 | GO 165 Inspection
129129197 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129129477 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129129604 | other | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129130423 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129130887 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129131399 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129131531 | anchor/guy | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 2 | E | 2024-09-28 | 2027-06-26 | Level 2 | GO 165 Inspection
129132232 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129132441 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129132448 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E | 2024-09-27 | 2027-06-26 | Level 2 | GO 165 Inspection
129132699 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129133769 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129133840 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129134055 | pole | HFTD Tier 2 | Transmission | 2024-06-26 | 2025-06-26 | Level 2 | E |  | 2025-06-26 | Level 2
129134127 | other | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129134323 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129134325 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129134379 | pole | HFTD Tier 3 | Transmission | 2024-05-31 | 2024-11-30 | Level 2 | E | 2024-09-26 | 2024-11-30 | Level 2 | Field Safety Reassessment
129134395 | pole | HFTD Tier 3 | Transmission | 2024-05-23 | 2024-11-23 | Level 2 | E |  | 2024-11-23 | Level 2
129134437 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134457 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129134460 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129134461 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129134466 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129134470 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129134490 | other | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129134499 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134503 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134506 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129134509 | other | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129134520 | pole | HFTD Tier 2 | Transmission | 2024-05-23 | 2025-05-23 | Level 2 | E |  | 2025-05-23 | Level 2
129134579 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129134588 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134600 | other | HFTD Tier 3 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129134646 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134672 | pole | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134681 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134712 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129134716 | pole | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129134735 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-25 | 2024-06-25 | Level 2 | E |  | 2025-06-25 | Level 2
129134751 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129134770 | other | HFTD Tier 3 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129134781 | other | Non-HFTD | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129134794 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129134864 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F | 2024-07-17 | 2029-05-29 | Level 3 | GO 165 Inspection
129134885 | other | HFTD Tier 2 | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129134907 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-26 | 2025-06-26 | Level 2 | E |  | 2025-06-26 | Level 2
129134908 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-26 | 2025-06-26 | Level 2 | E |  | 2025-06-26 | Level 2
129135430 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129135441 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129135442 | insulator and brushing | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129135449 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129135481 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129135612 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129135825 | conductor | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E |  | 2027-06-21 | Level 2
129135987 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129137024 | pole | HFTD Tier 2 | Transmission | 2024-06-27 | 2025-06-27 | Level 2 | E |  | 2025-06-27 | Level 2
129137286 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129137334 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129137356 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129137448 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129137798 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129138206 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129138356 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129138403 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129138613 | insulator and brushing | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129138663 | anchor/guy | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129138669 | insulator and brushing | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E | 2024-11-24 | 2027-06-26 | Level 2 | GO 165 Inspection
129138847 | other | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129138955 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129138957 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-27 | 2025-06-27 | Level 2 | E |  | 2025-06-27 | Level 2
129138972 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129139032 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129140584 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129141023 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129141048 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129141059 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129141078 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129141081 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129141095 | pole | HFTD Tier 3 | Transmission | 2024-05-31 | 2024-11-30 | Level 2 | E | 2024-10-22 | 2024-11-30 | Level 2 | Field Safety Reassessment
129141152 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129141165 | pole | HFTD Tier 3 | Transmission | 2024-05-24 | 2024-11-24 | Level 2 | E |  | 2024-11-24 | Level 2
129141214 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129141219 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129141224 | crossarm | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129141244 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129141256 | insulator and brushing | Non-HFTD | Transmission | 2024-06-28 | 2027-06-28 | Level 2 | E |  | 2027-06-28 | Level 2
129141287 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F | 2024-07-20 | 2029-05-30 | Level 3 | Field Safety Reassessment
129141345 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129141347 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129141361 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129141363 | other | HFTD Tier 3 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129141383 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129141409 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129141410 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129141439 | insulator and brushing | Non-HFTD | Transmission | 2024-06-28 | 2027-06-28 | Level 2 | E |  | 2027-06-28 | Level 2
129141628 | pole | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129141661 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129141662 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129141719 | other | HFTD Tier 2 | Transmission | 2024-05-08 | 2029-05-08 | Level 3 | F |  | 2029-05-08 | Level 3
129141742 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129141762 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129141813 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129141823 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129141870 | other | HFTD Tier 2 | Transmission | 2024-05-24 | 2029-05-24 | Level 3 | F |  | 2029-05-24 | Level 3
129141876 | pole | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129141989 | pole | HFTD Tier 3 | Transmission | 2024-06-01 | 2024-12-01 | Level 2 | E |  | 2024-12-01 | Level 2
129142023 | pole | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129142169 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129142255 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129142358 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129142433 | other | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129142442 | other | Non-HFTD | Transmission | 2024-06-28 | 2027-06-28 | Level 2 | E |  | 2027-06-28 | Level 2
129142447 | other | HFTD Tier 3 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129142617 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129142800 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129143089 | anchor/guy | Non-HFTD | Transmission | 2024-06-28 | 2025-06-28 | Level 2 | E |  | 2025-06-28 | Level 2
129143229 | insulator and brushing | Non-HFTD | Transmission | 2024-06-28 | 2027-06-28 | Level 2 | E |  | 2027-06-28 | Level 2
129144211 | crossarm | HFTD Tier 2 | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129144239 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129144443 | other | HFTD Tier 2 | Transmission | 2024-06-28 | 2025-06-28 | Level 2 | E |  | 2025-06-28 | Level 2
129144501 | other | HFTD Tier 2 | Transmission | 2024-06-28 | 2025-06-28 | Level 2 | E |  | 2025-06-28 | Level 2
129145913 | other | Non-HFTD | Transmission | 2024-06-29 | 2029-06-29 | Level 3 | F |  | 2029-06-29 | Level 3
129145915 | other | Non-HFTD | Transmission | 2024-06-29 | 2029-06-29 | Level 3 | F |  | 2029-06-29 | Level 3
129145917 | anchor/guy | Non-HFTD | Transmission | 2024-06-29 | 2029-06-29 | Level 3 | F |  | 2029-06-29 | Level 3
129146176 | crossarm | HFTD Tier 2 | Transmission | 2024-06-29 | 2029-06-29 | Level 3 | F |  | 2029-06-29 | Level 3
129146181 | other | HFTD Tier 2 | Transmission | 2024-06-29 | 2029-06-29 | Level 3 | F |  | 2029-06-29 | Level 3
129146238 | pole | HFTD Tier 2 | Transmission | 2024-06-29 | 2025-06-29 | Level 2 | E |  | 2025-06-29 | Level 2
129150703 | anchor/guy | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129150822 | anchor/guy | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129151017 | pole | HFTD Tier 2 | Transmission | 2024-07-01 | 2025-07-01 | Level 2 | E |  | 2025-07-01 | Level 2
129151381 | other | HFTD Tier 2 | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129151722 | pole | Non-HFTD | Transmission | 2024-07-01 | 2027-07-01 | Level 2 | E |  | 2027-07-01 | Level 2
129151876 | other | HFTD Tier 2 | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129152042 | pole | Non-HFTD | Transmission | 2024-07-01 | 2025-07-01 | Level 2 | E |  | 2025-07-01 | Level 2
129152072 | other | Non-HFTD | Transmission | 2024-07-01 | 2027-07-01 | Level 2 | E |  | 2027-07-01 | Level 2
129152224 | other | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129152388 | other | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129152409 | pole | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 2 | E |  | 2027-07-01 | Level 2
129152455 | pole | HFTD Tier 2 | Transmission | 2024-06-29 | 2025-06-29 | Level 2 | E |  | 2025-06-29 | Level 2
129152527 | pole | Non-HFTD | Transmission | 2024-07-01 | 2027-07-01 | Level 2 | E | 2024-09-13 | 2027-07-01 | Level 2 | GO 165 Inspection
129152594 | pole | Non-HFTD | Transmission | 2024-07-01 | 2027-07-01 | Level 2 | E |  | 2027-07-01 | Level 2
129152794 | anchor/guy | Non-HFTD | Transmission | 2024-07-01 | 2025-07-01 | Level 2 | E |  | 2025-07-01 | Level 2
129152873 | other | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129153029 | pole | HFTD Tier 2 | Transmission | 2024-07-01 | 2025-07-01 | Level 2 | E |  | 2025-07-01 | Level 2
129153564 | other | Non-HFTD | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129153639 | insulator and brushing | Non-HFTD | Transmission | 2024-07-01 | 2027-07-01 | Level 2 | E |  | 2027-07-01 | Level 2
129153715 | other | HFTD Tier 2 | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129153812 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129153815 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129153828 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129153834 | other | HFTD Tier 2 | Transmission | 2024-07-01 | 2029-07-01 | Level 3 | F |  | 2029-07-01 | Level 3
129153855 | insulator and brushing | Non-HFTD | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129153869 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129153961 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-28 | 2025-06-28 | Level 2 | E |  | 2025-06-28 | Level 2
129153970 | other | Non-HFTD | Transmission | 2024-07-01 | 2027-07-01 | Level 2 | E |  | 2027-07-01 | Level 2
129153988 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129154010 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129154092 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129155495 | other | Non-HFTD | Transmission | 2024-07-02 | 2029-07-02 | Level 3 | F |  | 2029-07-02 | Level 3
129155568 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129155942 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129156673 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129156929 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-24 | Level 2 | E |  | 2025-05-24 | Level 2
129156931 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129156940 | insulator and brushing | Non-HFTD | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129157427 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-02 | 2025-07-02 | Level 2 | E |  | 2025-07-02 | Level 2
129157992 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129158329 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129158450 | other | Non-HFTD | Transmission | 2024-07-02 | 2029-07-02 | Level 3 | F |  | 2029-07-02 | Level 3
129158681 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129158773 | other | Non-HFTD | Transmission | 2024-07-02 | 2029-07-02 | Level 3 | F |  | 2029-07-02 | Level 3
129158815 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2024-09-04 | Level 2 | E |  | 2024-09-04 | Level 2
129158870 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E | 2024-12-26 | 2027-07-02 | Level 2 | Field Safety Reassessment
129158986 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129159474 | pole | Non-HFTD | Transmission | 2024-07-02 | 2027-07-02 | Level 2 | E |  | 2027-07-02 | Level 2
129159506 | pole | HFTD Tier 3 | Transmission | 2024-05-22 | 2029-05-22 | Level 3 | F |  | 2029-05-22 | Level 3
129159606 | insulator and brushing | Non-HFTD | Transmission | 2024-07-02 | 2029-07-02 | Level 3 | F |  | 2029-07-02 | Level 3
129159652 | other | HFTD Tier 2 | Transmission | 2024-07-02 | 2025-07-02 | Level 2 | E |  | 2025-07-02 | Level 2
129159654 | other | HFTD Tier 2 | Transmission | 2024-07-02 | 2025-07-02 | Level 2 | E |  | 2025-07-02 | Level 2
129162002 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-03 | 2025-07-03 | Level 2 | E |  | 2025-07-03 | Level 2
129163130 | anchor/guy | Non-HFTD | Transmission | 2024-07-03 | 2029-07-03 | Level 3 | F |  | 2029-07-03 | Level 3
129163276 | other | HFTD Tier 2 | Transmission | 2024-07-03 | 2029-07-03 | Level 3 | F |  | 2029-07-03 | Level 3
129163314 | pole | Non-HFTD | Transmission | 2024-07-03 | 2027-07-03 | Level 2 | E |  | 2027-07-03 | Level 2
129166491 | pole | Non-HFTD | Transmission | 2024-07-03 | 2027-07-03 | Level 2 | E |  | 2027-07-03 | Level 2
129166700 | pole | Non-HFTD | Transmission | 2024-07-03 | 2027-07-03 | Level 2 | E |  | 2027-07-03 | Level 2
129167090 | pole | HFTD Tier 2 | Transmission | 2024-07-03 | 2025-07-03 | Level 2 | E |  | 2025-07-03 | Level 2
129169887 | other | Non-HFTD | Transmission | 2024-07-04 | 2027-07-04 | Level 2 | E |  | 2027-07-04 | Level 2
129169996 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129170010 | pole | Non-HFTD | Transmission | 2024-07-04 | 2027-07-04 | Level 2 | E |  | 2027-07-04 | Level 2
129172636 | insulator and brushing | Non-HFTD | Transmission | 2024-07-05 | 2029-07-05 | Level 3 | F |  | 2029-07-05 | Level 3
129172669 | other | Non-HFTD | Transmission | 2024-07-05 | 2029-07-05 | Level 3 | F |  | 2029-07-05 | Level 3
129172790 | other | Non-HFTD | Transmission | 2024-07-05 | 2029-07-05 | Level 3 | F |  | 2029-07-05 | Level 3
129173172 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-05 | 2029-07-05 | Level 3 | F |  | 2029-07-05 | Level 3
129177056 | anchor/guy | Non-HFTD | Transmission | 2024-07-06 | 2029-07-06 | Level 3 | F |  | 2029-07-06 | Level 3
129177135 | pole | Non-HFTD | Transmission | 2024-07-06 | 2027-07-06 | Level 2 | E |  | 2027-07-06 | Level 2
129177154 | other | Non-HFTD | Transmission | 2024-07-06 | 2029-07-06 | Level 3 | F |  | 2029-07-06 | Level 3
129177155 | pole | Non-HFTD | Transmission | 2024-07-06 | 2027-07-06 | Level 2 | E |  | 2027-07-06 | Level 2
129177201 | insulator and brushing | Non-HFTD | Transmission | 2024-07-06 | 2027-07-06 | Level 2 | E |  | 2027-07-06 | Level 2
129178769 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129178787 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129178814 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129179053 | pole | HFTD Tier 2 | Transmission | 2024-07-03 | 2025-07-03 | Level 2 | E |  | 2025-07-03 | Level 2
129179457 | other | Non-HFTD | Transmission | 2024-07-08 | 2027-07-08 | Level 2 | E |  | 2027-07-08 | Level 2
129179670 | pole | Non-HFTD | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129180003 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129180287 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129181112 | other | Non-HFTD | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129185599 | pole | HFTD Tier 2 | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129185690 | pole | HFTD Tier 2 | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129185693 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129185744 | pole | Non-HFTD | Transmission | 2024-07-08 | 2027-07-08 | Level 2 | E |  | 2027-07-08 | Level 2
129185901 | pole | Non-HFTD | Transmission | 2024-07-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
129186147 | crossarm | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129186392 | pole | Non-HFTD | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129186923 | pole | Non-HFTD | Transmission | 2024-07-08 | 2027-07-08 | Level 2 | E |  | 2027-07-08 | Level 2
129186940 | insulator and brushing | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129187005 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129187117 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-04 | 2025-07-04 | Level 2 | E |  | 2025-07-04 | Level 2
129187160 | insulator and brushing | Non-HFTD | Transmission | 2024-07-08 | 2027-07-08 | Level 2 | E |  | 2027-07-08 | Level 2
129187194 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187237 | pole | HFTD Tier 2 | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129187243 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187254 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187256 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129187278 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129187294 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129187368 | other | HFTD Tier 3 | Transmission | 2024-07-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
129187448 | pole | Non-HFTD | Transmission | 2024-07-04 | 2027-07-04 | Level 2 | E |  | 2027-07-04 | Level 2
129187462 | other | HFTD Tier 3 | Transmission | 2024-07-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
129187529 | pole | HFTD Tier 3 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129187539 | other | HFTD Tier 2 | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129187555 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187567 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187659 | anchor/guy | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187682 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129187701 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129187741 | anchor/guy | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187753 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187763 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129187811 | other | HFTD Tier 3 | Transmission | 2024-07-08 | 2025-01-08 | Level 2 | E |  | 2025-01-08 | Level 2
129187815 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129187819 | crossarm | Non-HFTD | Transmission | 2024-07-04 | 2027-07-04 | Level 2 | E |  | 2027-07-04 | Level 2
129187821 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129187854 | anchor/guy | Non-HFTD | Transmission | 2024-07-04 | 2027-07-04 | Level 2 | E |  | 2027-07-04 | Level 2
129187864 | switch | Non-HFTD | Transmission | 2024-07-04 | 2025-07-04 | Level 2 | E |  | 2025-07-04 | Level 2
129187874 | insulator and brushing | Non-HFTD | Transmission | 2024-07-04 | 2027-07-04 | Level 2 | E |  | 2027-07-04 | Level 2
129187905 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187915 | insulator and brushing | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187941 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187962 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187972 | conductor | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129187984 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129188011 | insulator and brushing | Non-HFTD | Transmission | 2024-07-04 | 2025-07-04 | Level 2 | E |  | 2025-07-04 | Level 2
129188290 | other | Non-HFTD | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129188319 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129188600 | other | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129189812 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129189892 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129190102 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129190120 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129190183 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129190295 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129190344 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129190469 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129190491 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129190588 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129190939 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129191148 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129191175 | pole | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129191308 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129191344 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129191377 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129191556 | anchor/guy | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129191781 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129191914 | pole | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129191955 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129191962 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129192072 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129192192 | pole | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129192210 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129192340 | pole | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129192413 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129192595 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129192701 | other | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129192708 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129192709 | pole | Non-HFTD | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129192763 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129192793 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129192999 | other | HFTD Tier 3 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129193238 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129193272 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129193276 | other | HFTD Tier 2 | Transmission | 2024-05-25 | 2029-05-25 | Level 3 | F |  | 2029-05-25 | Level 3
129193299 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129193331 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129193366 | pole | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129193369 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2024-10-09 | Level 2 | E | 2024-10-08 | 2024-10-08 | Level 2 | Field Safety Reassessment
129193444 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129193456 | other | HFTD Tier 2 | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129193526 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-28 | 2025-05-28 | Level 2 | E |  | 2025-05-28 | Level 2
129193636 | other | HFTD Tier 3 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129193639 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129193658 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2025-06-02 | Level 2 | E |  | 2025-06-02 | Level 2
129193659 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129193683 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129193688 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129193697 | pole | HFTD Tier 3 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129193700 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129193730 | pole | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129193737 | pole | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129193766 | other | HFTD Tier 3 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129193789 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F |  | 2029-07-04 | Level 3
129193808 | pole | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129193851 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129193872 | other | Non-HFTD | Transmission | 2024-07-04 | 2029-07-04 | Level 3 | F | 2024-08-20 | 2029-07-04 | Level 3 | GO 165 Inspection
129193875 | conductor | Non-HFTD | Transmission | 2024-07-04 | 2025-07-04 | Level 2 | E |  | 2025-07-04 | Level 2
129202797 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129202815 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129202846 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129203615 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129203699 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129203755 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129203772 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129203896 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129203899 | anchor/guy | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129204753 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129204758 | other | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129205030 | other | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129205062 | other | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129205581 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129205618 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129205705 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129205764 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129206048 | insulator and brushing | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129206162 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129206756 | other | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129208097 | insulator and brushing | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129208215 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129208660 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129209274 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129209753 | other | Non-HFTD | Transmission | 2024-07-11 | 2025-07-11 | Level 2 | E |  | 2025-07-11 | Level 2
129209757 | insulator and brushing | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129209928 | pole | HFTD Tier 3 | Transmission | 2024-07-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129210292 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129210299 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129210417 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129210523 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129210613 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129211206 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129211207 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129211220 | crossarm | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129211640 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129211641 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129213244 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129213250 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129213254 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129213277 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129213318 | insulator and brushing | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129213345 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129213348 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129213352 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129213368 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129213375 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129213537 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E | 2024-12-30 | 2025-05-31 | Level 2 | Field Safety Reassessment
129213563 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129213586 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129213609 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129213635 | other | Non-HFTD | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129213666 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129213677 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129213741 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129213745 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E | 2024-09-13 | 2024-08-30 | Level 2 | Field Safety Reassessment
129213777 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129213785 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129213853 | conductor | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129213868 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129213963 | pole | HFTD Tier 3 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129213984 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129213986 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129214029 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129214232 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129214330 | pole | HFTD Tier 3 | Transmission | 2024-05-29 | 2024-11-29 | Level 2 | E |  | 2024-11-29 | Level 2
129214367 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129214375 | pole | HFTD Tier 3 | Transmission | 2024-05-31 | 2024-11-30 | Level 2 | E |  | 2024-11-30 | Level 2
129214449 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129214501 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129214641 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129214684 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129214724 | pole | HFTD Tier 3 | Transmission | 2024-05-28 | 2024-11-28 | Level 2 | E |  | 2024-11-28 | Level 2
129214728 | other | HFTD Tier 3 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129214835 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129214880 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129214911 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129214920 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129214928 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129214980 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129214988 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129215126 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129215179 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129215181 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129215207 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129215220 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129215268 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129215327 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129215337 | other | HFTD Tier 2 | Transmission | 2024-05-28 | 2029-05-28 | Level 3 | F |  | 2029-05-28 | Level 3
129215379 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129215388 | crossarm | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129215409 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129215416 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2025-07-12 | Level 2 | E |  | 2025-07-12 | Level 2
129215417 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129215592 | switch | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129215777 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129215784 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129215788 | crossarm | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129216000 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129216084 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129216110 | anchor/guy | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129216168 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129216251 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129216364 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129216418 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129216916 | other | Non-HFTD | Transmission | 2024-07-12 | 2025-07-12 | Level 2 | E |  | 2025-07-12 | Level 2
129217736 | other | Non-HFTD | Transmission | 2024-07-13 | 2029-07-13 | Level 3 | F |  | 2029-07-13 | Level 3
129219078 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129219097 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129220202 | pole | HFTD Tier 2 | Transmission | 2024-07-15 | 2025-07-15 | Level 2 | E |  | 2025-07-15 | Level 2
129221322 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129221620 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129221668 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129222091 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129222215 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129222242 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129222725 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129222735 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129222807 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129222944 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129223020 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129223111 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129223302 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129223446 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129223857 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129223882 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F | 2024-10-01 | 2029-07-15 | Level 3 | GO 165 Inspection
129223945 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129224036 | other | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129224044 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129224081 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129224084 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129224160 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129224165 | other | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129224197 | pole | Non-HFTD | Transmission | 2024-07-12 | 2025-07-12 | Level 2 | E |  | 2025-07-12 | Level 2
129224234 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129224269 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129224290 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129224297 | other | Non-HFTD | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129224319 | pole | HFTD Tier 2 | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129224356 | other | HFTD Tier 3 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129224367 | crossarm | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129224400 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129224442 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129224447 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129224468 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-02 | 2025-06-02 | Level 2 | E |  | 2025-06-02 | Level 2
129224491 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129224512 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129224527 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129224540 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129224544 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129224545 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129224562 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129224563 | other | Non-HFTD | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129224585 | other | Non-HFTD | Transmission | 2024-07-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129224599 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129224612 | other | HFTD Tier 2 | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129224655 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129224683 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129224700 | other | Non-HFTD | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129224718 | other | HFTD Tier 3 | Transmission | 2024-06-04 | 2024-12-04 | Level 2 | E | 2024-12-23 | 2024-12-04 | Level 2 | Field Safety Reassessment
129224721 | anchor/guy | Non-HFTD | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129224735 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2025-06-12 | Level 2 | E |  | 2024-12-12 | Level 2
129224740 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129224909 | conductor | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129225232 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E | 2024-10-02 | 2027-07-16 | Level 2 | GO 165 Inspection
129225252 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129225354 | other | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129225629 | anchor/guy | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129225750 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-15 | 2025-07-15 | Level 2 | E |  | 2025-07-15 | Level 2
129226328 | anchor/guy | Non-HFTD | Transmission | 2024-07-16 | 2025-07-16 | Level 2 | E | 2024-10-11 | 2025-07-16 | Level 2 | GO 165 Inspection
129226788 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129227334 | other | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129227661 | insulator and brushing | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129227695 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129227733 | pole | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129228629 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129228658 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129228830 | insulator and brushing | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129228867 | pole | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229165 | anchor/guy | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229466 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129229467 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129229530 | insulator and brushing | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229605 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229665 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229675 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229737 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129229746 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229747 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229792 | anchor/guy | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129229980 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129229985 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129229989 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129230014 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-14 | 2025-06-14 | Level 2 | E |  | 2025-06-14 | Level 2
129230083 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129230087 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129230090 | anchor/guy | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129230092 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129230093 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129230096 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129230098 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129230112 | pole | HFTD Tier 2 | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129230115 | pole | HFTD Tier 2 | Transmission | 2024-07-08 | 2025-07-08 | Level 2 | E |  | 2025-07-08 | Level 2
129230157 | other | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129230189 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129230198 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129230212 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129230213 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129230270 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129230281 | conductor | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129230334 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129230336 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129230370 | other | HFTD Tier 2 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129230421 | other | Non-HFTD | Transmission | 2024-07-16 | 2025-07-16 | Level 2 | E |  | 2025-07-16 | Level 2
129230428 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129230455 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129230484 | pole | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129230487 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129230491 | other | HFTD Tier 3 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129230940 | other | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129230975 | crossarm | Non-HFTD | Transmission | 2024-07-16 | 2024-07-16 | Level 2 | E |  | 2025-07-16 | Level 2
129231143 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129231958 | anchor/guy | Non-HFTD | Transmission | 2024-07-17 | 2027-07-17 | Level 2 | E | 2024-10-14 | 2027-07-17 | Level 2 | GO 165 Inspection
129232527 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129232540 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129232810 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129232860 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233095 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233184 | insulator and brushing | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233185 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233186 | anchor/guy | Non-HFTD | Transmission | 2024-07-17 | 2027-07-17 | Level 2 | E |  | 2027-07-17 | Level 2
129233216 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233382 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233441 | anchor/guy | Non-HFTD | Transmission | 2024-07-17 | 2025-07-17 | Level 2 | E |  | 2025-07-17 | Level 2
129233459 | insulator and brushing | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129233922 | other | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129234215 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129234590 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129234646 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129234954 | pole | Non-HFTD | Transmission | 2024-07-17 | 2027-07-17 | Level 2 | E |  | 2027-07-17 | Level 2
129235753 | pole | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129235824 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129235828 | crossarm | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129235867 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129235919 | other | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129235920 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129235937 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129235945 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129235952 | pole | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129236055 | anchor/guy | Non-HFTD | Transmission | 2024-07-17 | 2025-07-17 | Level 2 | E |  | 2025-07-17 | Level 2
129236056 | other | Non-HFTD | Transmission | 2024-07-17 | 2024-10-17 | Level 2 | E | 2024-10-20 | 2024-10-17 | Level 2 | Field Safety Reassessment
129236149 | other | HFTD Tier 2 | Transmission | 2024-06-24 | 2025-06-24 | Level 2 | E |  | 2025-06-24 | Level 2
129236164 | pole | HFTD Tier 2 | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129236214 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129236629 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129236691 | conductor | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129236705 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129236918 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129236988 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129237258 | other | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129237340 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129237707 | other | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129239024 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129239111 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129240534 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-18 | 2025-07-18 | Level 2 | E |  | 2025-07-18 | Level 2
129240874 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129241735 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129241813 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129241982 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129242163 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129242244 | pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129242288 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129242326 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129242692 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2025-07-18 | Level 2 | E |  | 2025-07-18 | Level 2
129243256 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129243275 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129243624 | other | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129245193 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F | 2024-11-13 | 2029-07-17 | Level 3 | GO 165 Inspection
129245194 | pole | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F | 2024-11-12 | 2029-07-17 | Level 3 | GO 165 Inspection
129245246 | pole | HFTD Tier 3 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129245262 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129245284 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F | 2024-10-17 | 2029-07-17 | Level 3 | GO 165 Inspection
129245412 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129245419 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129245421 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129245425 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129245427 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129245530 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129246110 | pole | HFTD Tier 3 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129246743 | other | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129246942 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129246960 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129246986 | pole | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129247020 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129247103 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129247255 | switch | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129247311 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129247318 | pole | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129247327 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129247340 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129247400 | pole | HFTD Tier 3 | Transmission | 2024-07-08 | 2029-07-08 | Level 3 | F |  | 2029-07-08 | Level 3
129247413 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129247513 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129247518 | other | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129247903 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129248244 | other | HFTD Tier 3 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129248954 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E | 2024-11-01 | 2024-09-07 | Level 2 | Field Safety Reassessment
129249652 | pole | HFTD Tier 3 | Transmission | 2024-06-07 | 2024-12-07 | Level 2 | E |  | 2024-12-07 | Level 2
129249936 | pole | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129249946 | other | Non-HFTD | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129250012 | pole | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129250027 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129250096 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2025-07-19 | Level 2
129250113 | insulator and brushing | Non-HFTD | Transmission | 2024-07-11 | 2025-07-11 | Level 2 | E |  | 2025-07-11 | Level 2
129250116 | other | Non-HFTD | Transmission | 2024-07-11 | 2025-07-11 | Level 2 | E |  | 2025-07-11 | Level 2
129250118 | pole | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129250127 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129250245 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129250425 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129250426 | other | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129250452 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129250588 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129250701 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129250840 | anchor/guy | Non-HFTD | Transmission | 2024-07-19 | 2025-01-19 | Level 2 | E |  | 2025-01-19 | Level 2
129250888 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129252190 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129253413 | pole | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F | 2024-12-10 | 2029-07-19 | Level 3 | GO 165 Inspection
129254277 | anchor/guy | Non-HFTD | Transmission | 2024-07-20 | 2027-07-20 | Level 2 | E | 2024-10-03 | 2027-07-20 | Level 2 | GO 165 Inspection
129256402 | other | HFTD Tier 2 | Transmission | 2024-07-20 | 2025-07-20 | Level 2 | E |  | 2025-07-20 | Level 2
129257015 | pole | Non-HFTD | Transmission | 2024-07-21 | 2027-07-21 | Level 2 | E |  | 2027-07-21 | Level 2
129257061 | other | Non-HFTD | Transmission | 2024-07-21 | 2029-07-21 | Level 3 | F |  | 2029-07-21 | Level 3
129257066 | insulator and brushing | Non-HFTD | Transmission | 2024-07-21 | 2025-07-21 | Level 2 | E |  | 2025-07-21 | Level 2
129257373 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129257384 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F | 2024-09-25 | 2029-07-22 | Level 3 | GO 165 Inspection
129257432 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129257488 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129257492 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129260682 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F | 2024-11-04 | 2029-07-22 | Level 3 | GO 165 Inspection
129260993 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129261099 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129261144 | pole | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129264199 | pole | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129264283 | pole | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129264314 | anchor/guy | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129264319 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129264591 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129264634 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129267456 | anchor/guy | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129269633 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129271693 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129271882 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2025-07-22 | Level 2
129272330 | anchor/guy | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129273299 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129273472 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129273475 | pole | Non-HFTD | Transmission | 2024-07-19 | 2024-10-19 | Level 2 | E | 2024-11-26 | 2025-07-19 | Level 2 | Field Safety Reassessment
129273505 | conductor | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129273623 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129274246 | conductor | Non-HFTD | Transmission | 2024-07-19 | 2025-07-19 | Level 2 | E |  | 2025-07-19 | Level 2
129274249 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129274420 | conductor | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129274434 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129274445 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129274453 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129274549 | anchor/guy | Non-HFTD | Transmission | 2024-07-19 | 2025-07-19 | Level 2 | E |  | 2025-07-19 | Level 2
129274595 | anchor/guy | Non-HFTD | Transmission | 2024-07-20 | 2025-01-20 | Level 2 | E | 2024-08-01 | 2025-01-20 | Level 2 | GO 165 Inspection
129274605 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-08 | 2024-12-08 | Level 2 | E |  | 2024-12-08 | Level 2
129274650 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129274670 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129274677 | switch | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129274682 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129274686 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129274690 | other | Non-HFTD | Transmission | 2024-07-20 | 2029-07-20 | Level 3 | F |  | 2029-07-20 | Level 3
129274695 | other | Non-HFTD | Transmission | 2024-07-20 | 2029-07-20 | Level 3 | F |  | 2029-07-20 | Level 3
129274708 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129274766 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129274768 | anchor/guy | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129274783 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129274818 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129274820 | anchor/guy | Non-HFTD | Transmission | 2024-07-20 | 2027-07-20 | Level 2 | E |  | 2027-07-20 | Level 2
129274857 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2025-01-19 | Level 2 | E |  | 2025-01-19 | Level 2
129274900 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129274919 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129275034 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F | 2024-11-27 | 2029-07-22 | Level 3 | GO 165 Inspection
129275037 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E | 2024-12-02 | 2027-07-19 | Level 2 | GO 165 Inspection
129275192 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F | 2024-10-11 | 2029-07-22 | Level 3 | GO 165 Inspection
129275194 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129275200 | other | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129275212 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F | 2024-10-11 | 2029-07-19 | Level 3 | GO 165 Inspection
129275221 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129275272 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129275582 | other | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129276336 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129276607 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129276834 | other | HFTD Tier 2 | Transmission | 2024-07-23 | 2025-07-23 | Level 2 | E |  | 2025-07-23 | Level 2
129277464 | other | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129277644 | other | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129277921 | anchor/guy | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129278171 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129278326 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129278328 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129278489 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129278695 | pole | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129278696 | insulator and brushing | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129278869 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129279374 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F | 2024-10-16 | 2029-07-23 | Level 3 | GO 165 Inspection
129279895 | pole | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129279911 | other | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129279992 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129280053 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129280072 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129280254 | other | Non-HFTD | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129280257 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129280293 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129280299 | other | HFTD Tier 3 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129280314 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129280329 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129280348 | anchor/guy | Non-HFTD | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129280411 | other | Non-HFTD | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129281008 | insulator and brushing | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129281438 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129281746 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129281895 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129282015 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129282472 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129282546 | other | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129282636 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129282642 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129282890 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129282960 | insulator and brushing | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129282978 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129283081 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129283513 | anchor/guy | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129283590 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129283753 | anchor/guy | HFTD Tier 2 | Transmission | 2024-07-24 | 2025-07-24 | Level 2 | E |  | 2025-07-24 | Level 2
129284179 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F | 2024-10-14 | 2029-07-24 | Level 3 | GO 165 Inspection
129284290 | other | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E | 2024-10-11 | 2027-07-24 | Level 2 | GO 165 Inspection
129284365 | other | Non-HFTD | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129284431 | other | Non-HFTD | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F | 2024-09-24 | 2029-06-11 | Level 3 | GO 165 Inspection
129284475 | other | Non-HFTD | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129284508 | other | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-08-29 | 2029-06-12 | Level 3 | GO 165 Inspection
129284522 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129284569 | other | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E | 2024-09-23 | 2027-06-11 | Level 2 | GO 165 Inspection
129284581 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129284590 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129284599 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129284608 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F | 2024-08-26 | 2029-06-13 | Level 3 | GO 165 Inspection
129284632 | other | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-08-27 | 2029-06-12 | Level 3 | GO 165 Inspection
129284638 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129284668 | other | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E |  | 2027-06-11 | Level 2
129284738 | pole | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129284770 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129284795 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2025-06-02 | Level 2 | E |  | 2025-06-02 | Level 2
129284816 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129284826 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129284829 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129284840 | insulator and brushing | Non-HFTD | Transmission | 2024-07-16 | 2024-10-19 | Level 2 | E | 2024-10-09 | 2025-07-16 | Level 2 | Field Safety Reassessment
129284879 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129284894 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-10 | 2024-12-10 | Level 2 | E | 2024-12-05 | 2024-12-10 | Level 2 | Field Safety Reassessment
129284910 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129284999 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129285816 | other | Non-HFTD | Transmission | 2024-07-24 | 2025-07-24 | Level 2 | E |  | 2025-07-24 | Level 2
129286177 | anchor/guy | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129286301 | anchor/guy | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129287079 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2025-07-25 | Level 2 | E |  | 2025-07-25 | Level 2
129287675 | pole | HFTD Tier 3 | Transmission | 2023-09-15 | 2024-03-15 | Level 2 | E |  | 2024-03-15 | Level 2
129288160 | conductor | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129288231 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129288312 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129288805 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129288955 | anchor/guy | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129289014 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F | 2024-11-07 | 2029-07-25 | Level 3 | GO 165 Inspection
129289167 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129289539 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2025-01-25 | Level 2 | E |  | 2025-01-25 | Level 2
129289689 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129289704 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129289730 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129290117 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129290176 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F | 2024-12-02 | 2029-07-25 | Level 3 | GO 165 Inspection
129290177 | anchor/guy | Non-HFTD | Transmission | 2024-07-25 | 2025-01-25 | Level 2 | E | 2024-12-02 | 2025-01-25 | Level 2 | GO 165 Inspection
129290313 | pole | Non-HFTD | Transmission | 2024-07-25 | 2025-01-25 | Level 2 | E |  | 2025-01-25 | Level 2
129290487 | anchor/guy | HFTD Tier 2 | Transmission | 2024-07-25 | 2025-07-25 | Level 2 | E |  | 2025-07-25 | Level 2
129292804 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129292838 | other | HFTD Tier 2 | Transmission | 2024-07-18 | 2025-07-18 | Level 2 | E |  | 2024-10-18 | Level 2
129292854 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129292860 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129292937 | other | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-08-30 | 2029-06-12 | Level 3 | GO 165 Inspection
129292994 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-03 | 2024-12-03 | Level 2 | E |  | 2024-12-03 | Level 2
129293074 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129293137 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129293139 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129293303 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129293391 | other | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F | 2024-09-13 | 2029-06-15 | Level 3 | GO 165 Inspection
129293633 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129293983 | anchor/guy | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F | 2024-08-28 | 2029-06-13 | Level 3 | GO 165 Inspection
129293988 | anchor/guy | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129294060 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E | 2024-09-10 | 2025-06-13 | Level 2 | Field Safety Reassessment
129294061 | pole | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129294430 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129295082 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129295086 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129295088 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129295174 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-08-29 | 2029-06-14 | Level 3 | GO 165 Inspection
129295228 | pole | HFTD Tier 2 | Transmission | 2024-06-14 | 2025-06-14 | Level 2 | E |  | 2025-06-14 | Level 2
129295230 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129295268 | other | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-08-27 | 2029-06-12 | Level 3 | GO 165 Inspection
129295286 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129295397 | pole | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129295492 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129295526 | pole | HFTD Tier 3 | Transmission | 2024-06-14 | 2024-12-14 | Level 2 | E | 2024-10-17 | 2024-12-14 | Level 2 | Field Safety Reassessment
129295530 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129295567 | other | Non-HFTD | Transmission | 2024-07-22 | 2025-07-22 | Level 2 | E |  | 2025-07-22 | Level 2
129295681 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129295688 | conductor | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129295748 | conductor | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129295872 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129295923 | insulator and brushing | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129296077 | insulator and brushing | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129296105 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2025-07-18 | Level 2 | E |  | 2025-07-18 | Level 2
129296110 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F | 2024-11-06 | 2029-07-22 | Level 3 | GO 165 Inspection
129296127 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E | 2024-10-29 | 2027-07-26 | Level 2 | GO 165 Inspection
129296170 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2025-07-18 | Level 2 | E |  | 2025-07-18 | Level 2
129296184 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129296270 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129296272 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129296462 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129296613 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129296738 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129296761 | pole | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129296892 | other | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129297237 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129297279 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129297313 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129297356 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129297357 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129299023 | other | Non-HFTD | Transmission | 2024-07-27 | 2029-07-27 | Level 3 | F |  | 2029-07-27 | Level 3
129301111 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-24 | 2025-07-24 | Level 2 | E |  | 2025-07-24 | Level 2
129301836 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129302286 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129302366 | insulator and brushing | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129302504 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129302799 | anchor/guy | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129302884 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E | 2024-09-06 | 2027-07-29 | Level 2 | GO 165 Inspection
129303032 | pole | Non-HFTD | Transmission | 2024-07-27 | 2027-07-27 | Level 2 | E |  | 2027-07-27 | Level 2
129303226 | anchor/guy | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129303227 | other | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129303619 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129303670 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129303865 | other | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E | 2024-11-06 | 2027-07-29 | Level 2 | GO 165 Inspection
129303970 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129304549 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129304593 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129304930 | other | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129305005 | pole | Non-HFTD | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E |  | 2027-06-03 | Level 2
129305103 | pole | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129305139 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129305150 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129305425 | conductor | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129305653 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129305927 | insulator and brushing | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F | 2024-10-01 | 2029-06-20 | Level 3 | GO 165 Inspection
129305929 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-09-13 | 2029-06-14 | Level 3 | GO 165 Inspection
129306165 | other | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E | 2024-09-26 | 2027-06-18 | Level 2 | GO 165 Inspection
129306449 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-09-13 | 2029-06-14 | Level 3 | GO 165 Inspection
129306472 | insulator and brushing | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129306477 | other | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129306491 | pole | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129306492 | other | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129306527 | other | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129306543 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F | 2024-10-18 | 2029-06-20 | Level 3 | GO 165 Inspection
129306566 | other | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129306586 | pole | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129306592 | anchor/guy | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129306598 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129306600 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-09-11 | 2029-06-14 | Level 3 | GO 165 Inspection
129306603 | other | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E | 2024-09-16 | 2027-06-20 | Level 2 | GO 165 Inspection
129306606 | pole | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129306607 | anchor/guy | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129306610 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-29 | Level 2 | E |  | 2025-05-29 | Level 2
129306612 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129306614 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F | 2024-10-21 | 2029-06-21 | Level 3 | GO 165 Inspection
129306633 | other | Non-HFTD | Transmission | 2024-06-12 | 2027-06-12 | Level 2 | E | 2024-09-09 | 2027-06-12 | Level 2 | GO 165 Inspection
129306641 | other | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129306643 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129306674 | other | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129306682 | pole | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129306686 | other | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129306689 | pole | HFTD Tier 3 | Transmission | 2024-05-30 | 2024-11-30 | Level 2 | E |  | 2024-11-30 | Level 2
129306694 | other | Non-HFTD | Transmission | 2024-06-14 | 2027-06-14 | Level 2 | E |  | 2027-06-14 | Level 2
129306716 | other | Non-HFTD | Transmission | 2024-06-15 | 2027-06-15 | Level 2 | E |  | 2027-06-15 | Level 2
129306756 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129306759 | pole | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129306797 | other | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129307305 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129307676 | other | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2025-07-30 | Level 2
129308290 | other | HFTD Tier 2 | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129308585 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E | 2024-09-06 | 2027-07-30 | Level 2 | GO 165 Inspection
129308778 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129309381 | other | Non-HFTD | Transmission | 2024-07-30 | 2025-07-30 | Level 2 | E |  | 2025-07-30 | Level 2
129310501 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129310750 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F | 2024-09-06 | 2029-07-30 | Level 3 | GO 165 Inspection
129310991 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129311038 | anchor/guy | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129311544 | pole | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E |  | 2025-06-18 | Level 2
129311561 | anchor/guy | Non-HFTD | Transmission | 2024-07-29 | 2025-07-29 | Level 2 | E |  | 2025-07-29 | Level 2
129311570 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129311572 | pole | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129311577 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129311587 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E |  | 2025-06-18 | Level 2
129311616 | other | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E |  | 2027-06-24 | Level 2
129311634 | other | Non-HFTD | Transmission | 2024-06-15 | 2027-06-15 | Level 2 | E | 2024-08-06 | 2027-06-15 | Level 2 | GO 165 Inspection
129311667 | other | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129311686 | other | HFTD Tier 3 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129311706 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129311738 | other | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129311773 | other | HFTD Tier 2 | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129311805 | other | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129311807 | insulator and brushing | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129311854 | other | HFTD Tier 3 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129311864 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129311906 | other | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-17 | 2027-06-24 | Level 2 | GO 165 Inspection
129311929 | anchor/guy | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-05 | 2027-06-24 | Level 2 | GO 165 Inspection
129311944 | pole | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129311980 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129312015 | other | Non-HFTD | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129312017 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129312080 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129313405 | insulator and brushing | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129313619 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129313623 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129313741 | anchor/guy | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129313923 | anchor/guy | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129314765 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129314772 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129314862 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129314890 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F | 2024-10-17 | 2029-07-31 | Level 3 | GO 165 Inspection
129314920 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129314950 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315264 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129315667 | anchor/guy | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315674 | anchor/guy | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315675 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315966 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315968 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315973 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129315982 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129316211 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129316249 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F | 2024-09-06 | 2029-07-31 | Level 3 | GO 165 Inspection
129316281 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129316295 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F | 2024-10-22 | 2029-07-31 | Level 3 | GO 165 Inspection
129316464 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-18 | Level 2 | E | 2024-11-20 | 2024-12-18 | Level 2 | Field Safety Reassessment
129316496 | pole | HFTD Tier 3 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129316497 | pole | HFTD Tier 3 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129316648 | other | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129316699 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129316715 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129316734 | anchor/guy | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129316739 | pole | Non-HFTD | Transmission | 2024-07-29 | 2025-07-29 | Level 2 | E |  | 2025-07-29 | Level 2
129316760 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129316766 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129316823 | other | HFTD Tier 3 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129316869 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129316881 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129316935 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-17 | 2024-12-17 | Level 2 | E |  | 2024-12-17 | Level 2
129316947 | pole | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129316974 | pole | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129316996 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-31 | 2025-07-31 | Level 2 | E |  | 2025-07-31 | Level 2
129316997 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-31 | 2025-07-31 | Level 2 | E |  | 2025-07-31 | Level 2
129316999 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129317009 | pole | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129317010 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129317039 | pole | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129317060 | pole | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129318293 | other | Non-HFTD | Transmission | 2024-08-01 | 2025-02-01 | Level 2 | E |  | 2025-02-01 | Level 2
129318537 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129319140 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129319938 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129320166 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2025-08-01 | Level 2 | E |  | 2025-08-01 | Level 2
129320500 | pole | HFTD Tier 2 | Transmission | 2024-08-01 | 2025-08-01 | Level 2 | E |  | 2025-08-01 | Level 2
129320623 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129321346 | other | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129321348 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129321368 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129321369 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129321426 | anchor/guy | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129321644 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129321795 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129321867 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129322019 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129322032 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129322098 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129323766 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2025-08-01 | Level 2 | E | 2024-10-15 | 2025-08-01 | Level 2 | GO 165 Inspection
129323788 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129323840 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129323941 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129323974 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129323977 | anchor/guy | Non-HFTD | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129323991 | pole | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129324044 | other | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129324150 | other | Non-HFTD | Transmission | 2024-06-17 | 2027-06-17 | Level 2 | E |  | 2027-06-17 | Level 2
129324151 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129324156 | other | HFTD Tier 3 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129324165 | pole | Non-HFTD | Transmission | 2024-06-03 | 2024-12-03 | Level 2 | E | 2024-12-09 | 2024-12-03 | Level 2 | Field Safety Reassessment
129324194 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129324209 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129324232 | other | HFTD Tier 2 | Transmission | 2024-05-31 | 2029-05-31 | Level 3 | F |  | 2029-05-31 | Level 3
129324324 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129324445 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129324485 | other | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E |  | 2027-06-18 | Level 2
129324526 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E | 2024-09-04 | 2025-07-09 | Level 2 | GO 165 Inspection
129324560 | other | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129324574 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129324592 | anchor/guy | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129324636 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129324684 | anchor/guy | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129324694 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129324906 | other | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129324929 | other | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129325122 | insulator and brushing | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129325127 | anchor/guy | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129325196 | anchor/guy | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129325230 | other | Non-HFTD | Transmission | 2024-05-31 | 2027-05-31 | Level 2 | E |  | 2027-05-31 | Level 2
129325356 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E | 2024-11-04 | 2027-08-02 | Level 2 | GO 165 Inspection
129325625 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129325712 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129326078 | pole | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129326244 | anchor/guy | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E | 2024-10-25 | 2027-08-02 | Level 2 | GO 165 Inspection
129326684 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129326688 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129327118 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129327189 | pole | Non-HFTD | Transmission | 2024-08-02 | 2025-08-02 | Level 2 | E | 2024-11-08 | 2025-08-02 | Level 2 | GO 165 Inspection
129327722 | pole | Non-HFTD | Transmission | 2024-08-03 | 2027-08-03 | Level 2 | E |  | 2027-08-03 | Level 2
129327873 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129327929 | anchor/guy | Non-HFTD | Transmission | 2024-08-03 | 2029-08-03 | Level 3 | F |  | 2029-08-03 | Level 3
129328503 | other | Non-HFTD | Transmission | 2024-08-04 | 2029-08-04 | Level 3 | F |  | 2029-08-04 | Level 3
129328611 | insulator and brushing | Non-HFTD | Transmission | 2024-08-04 | 2029-08-04 | Level 3 | F |  | 2029-08-04 | Level 3
129328847 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129329269 | other | Non-HFTD | Transmission | 2024-08-05 | 2025-08-05 | Level 2 | E |  | 2025-08-05 | Level 2
129330057 | other | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E | 2024-10-16 | 2027-08-05 | Level 2 | GO 165 Inspection
129331649 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E | 2024-09-27 | 2027-08-05 | Level 2 | GO 165 Inspection
129331859 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129331960 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129332921 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129332928 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129333084 | pole | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129333323 | insulator and brushing | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129333567 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F | 2024-11-27 | 2029-08-05 | Level 3 | GO 165 Inspection
129333633 | pole | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129333833 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129333869 | pole | HFTD Tier 3 | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129333892 | other | HFTD Tier 2 | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129333961 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129334074 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F |  | 2029-06-21 | Level 3
129334090 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E | 2024-12-20 | 2025-05-30 | Level 2 | Field Safety Reassessment
129334169 | pole | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129334222 | pole | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129334226 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129334266 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129334270 | pole | HFTD Tier 3 | Transmission | 2024-06-17 | 2024-12-17 | Level 2 | E |  | 2024-12-17 | Level 2
129334288 | other | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129334302 | other | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129334339 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129334424 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129334513 | other | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129334533 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129334538 | other | HFTD Tier 3 | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129334546 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129334557 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F | 2024-09-10 | 2029-07-17 | Level 3 | GO 165 Inspection
129334574 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-30 | Level 2 | E |  | 2025-05-30 | Level 2
129334582 | other | Non-HFTD | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129335396 | anchor/guy | Non-HFTD | Transmission | 2024-08-03 | 2029-08-03 | Level 3 | F |  | 2029-08-03 | Level 3
129335410 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129335413 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129335723 | insulator and brushing | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129336622 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129337099 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129337191 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129337464 | insulator and brushing | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129337498 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129337661 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129337858 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129338255 | anchor/guy | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129338256 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129338355 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129338712 | insulator and brushing | Non-HFTD | Transmission | 2024-08-06 | 2025-08-06 | Level 2 | E |  | 2025-08-06 | Level 2
129338837 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129338851 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129338853 | crossarm | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129338856 | crossarm | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129338871 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129338878 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129338896 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129338937 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129339317 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129339319 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129339361 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129339390 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129339400 | anchor/guy | Non-HFTD | Transmission | 2024-06-01 | 2027-06-01 | Level 2 | E |  | 2027-06-01 | Level 2
129339457 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129339526 | other | HFTD Tier 2 | Transmission | 2024-05-30 | 2029-05-30 | Level 3 | F |  | 2029-05-30 | Level 3
129339542 | insulator and brushing | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129339543 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F | 2024-10-11 | 2029-08-06 | Level 3 | GO 165 Inspection
129339567 | insulator and brushing | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129339614 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129339992 | anchor/guy | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129339998 | other | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129340041 | anchor/guy | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-31 | Level 2 | E |  | 2025-05-31 | Level 2
129340120 | insulator and brushing | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129340123 | insulator and brushing | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129340128 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129340139 | anchor/guy | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E | 2024-11-04 | 2027-08-02 | Level 2 | GO 165 Inspection
129340141 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129340143 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129340156 | pole | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129340169 | pole | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129340177 | other | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129340178 | pole | HFTD Tier 2 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129340183 | anchor/guy | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129340185 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129340192 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129340196 | other | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129340210 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129340225 | insulator and brushing | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129340259 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129340263 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129340267 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129340268 | pole | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129340279 | anchor/guy | Non-HFTD | Transmission | 2024-08-05 | 2025-08-05 | Level 2 | E | 2024-11-02 | 2025-08-05 | Level 2 | GO 165 Inspection
129340312 | pole | HFTD Tier 3 | Transmission | 2024-06-01 | 2024-12-01 | Level 2 | E |  | 2024-12-01 | Level 2
129340333 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129340340 | other | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E | 2024-11-02 | 2027-08-02 | Level 2 | GO 165 Inspection
129340342 | pole | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E | 2024-11-02 | 2027-08-02 | Level 2 | GO 165 Inspection
129342106 | anchor/guy | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129342229 | anchor/guy | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129342486 | other | HFTD Tier 2 | Transmission | 2024-08-01 | 2025-08-01 | Level 2 | E |  | 2025-08-01 | Level 2
129344007 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129344181 | other | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E | 2024-09-16 | 2027-08-07 | Level 2 | GO 165 Inspection
129344671 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F | 2024-11-15 | 2029-08-07 | Level 3 | GO 165 Inspection
129344912 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129345107 | pole | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E |  | 2027-08-07 | Level 2
129345290 | insulator and brushing | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E | 2024-11-15 | 2027-08-07 | Level 2 | GO 165 Inspection
129345311 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129345551 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129345837 | other | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E | 2024-11-19 | 2027-08-07 | Level 2 | GO 165 Inspection
129345914 | insulator and brushing | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E |  | 2027-08-07 | Level 2
129346084 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129346122 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129346132 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129346153 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129346155 | pole | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E |  | 2027-08-07 | Level 2
129346172 | anchor/guy | Non-HFTD | Transmission | 2024-08-07 | 2025-02-07 | Level 2 | E |  | 2025-02-07 | Level 2
129346190 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129346227 | pole | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E |  | 2027-08-07 | Level 2
129346473 | pole | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F | 2024-11-19 | 2029-08-07 | Level 3 | GO 165 Inspection
129346482 | insulator and brushing | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E | 2024-11-19 | 2027-08-07 | Level 2 | GO 165 Inspection
129346655 | insulator and brushing | Non-HFTD | Transmission | 2024-08-07 | 2025-08-07 | Level 2 | E |  | 2025-08-07 | Level 2
129346874 | other | Non-HFTD | Transmission | 2024-08-07 | 2025-02-07 | Level 2 | E |  | 2025-02-07 | Level 2
129346944 | pole | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E | 2024-10-30 | 2027-08-07 | Level 2 | GO 165 Inspection
129347107 | other | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E |  | 2027-08-07 | Level 2
129347196 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129347216 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129347343 | anchor/guy | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129347351 | pole | Non-HFTD | Transmission | 2024-06-03 | 2024-12-03 | Level 2 | E |  | 2024-12-03 | Level 2
129347354 | pole | Non-HFTD | Transmission | 2024-06-03 | 2024-12-03 | Level 2 | E |  | 2024-12-03 | Level 2
129347360 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129347444 | insulator and brushing | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129347459 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129347470 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129347500 | other | HFTD Tier 3 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129347506 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129347545 | insulator and brushing | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129347555 | crossarm | HFTD Tier 2 | Transmission | 2024-06-01 | 2025-06-01 | Level 2 | E |  | 2025-06-01 | Level 2
129347563 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129347577 | insulator and brushing | Non-HFTD | Transmission | 2024-07-10 | 2025-07-10 | Level 2 | E |  | 2025-07-10 | Level 2
129347581 | insulator and brushing | Non-HFTD | Transmission | 2024-06-14 | 2027-06-14 | Level 2 | E |  | 2027-06-14 | Level 2
129347610 | anchor/guy | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E | 2024-10-14 | 2027-07-18 | Level 2 | GO 165 Inspection
129347676 | other | HFTD Tier 2 | Transmission | 2024-07-24 | 2024-10-24 | Level 2 | E |  | 2024-10-24 | Level 2
129347677 | pole | HFTD Tier 2 | Transmission | 2024-07-24 | 2025-07-24 | Level 2 | E |  | 2025-07-24 | Level 2
129347678 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129347710 | anchor/guy | Non-HFTD | Transmission | 2024-06-01 | 2027-06-01 | Level 2 | E |  | 2027-06-01 | Level 2
129347721 | other | Non-HFTD | Transmission | 2024-06-15 | 2027-06-15 | Level 2 | E |  | 2027-06-15 | Level 2
129347731 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129347736 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129348050 | other | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129348198 | pole | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129348461 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129348897 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129348902 | insulator and brushing | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E | 2024-11-13 | 2027-08-07 | Level 2 | GO 165 Inspection
129349069 | pole | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129349234 | insulator and brushing | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129349528 | insulator and brushing | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129349691 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129349698 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129351346 | other | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E | 2024-10-28 | 2027-08-08 | Level 2 | GO 165 Inspection
129351909 | pole | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129351978 | pole | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129351979 | pole | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129351980 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129352385 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129352712 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129353105 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129353134 | pole | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129353429 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129353453 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129353544 | insulator and brushing | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129353545 | anchor/guy | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129353553 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129353572 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129353613 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E |  | 2025-06-05 | Level 2
129353614 | pole | HFTD Tier 3 | Transmission | 2024-06-01 | 2029-06-01 | Level 3 | F |  | 2029-06-01 | Level 3
129353619 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129353660 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129353702 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E | 2024-08-16 | 2027-07-29 | Level 2 | GO 165 Inspection
129353708 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129353709 | pole | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129353736 | other | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129353742 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129353775 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129353784 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129353787 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129353793 | other | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129353796 | other | Non-HFTD | Transmission | 2024-06-03 | 2029-06-03 | Level 3 | F |  | 2029-06-03 | Level 3
129353831 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129353860 | pole | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129354074 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129354077 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129354080 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129354098 | insulator and brushing | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129354099 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129354141 | anchor/guy | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129354142 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129354144 | insulator and brushing | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E | 2024-11-12 | 2027-07-29 | Level 2 | GO 165 Inspection
129354145 | other | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E | 2024-11-12 | 2027-07-29 | Level 2 | GO 165 Inspection
129354159 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129354351 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129354470 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129354475 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129355978 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129355995 | pole | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F | 2024-10-28 | 2029-08-08 | Level 3 | GO 165 Inspection
129356326 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129356402 | pole | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129356470 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129356621 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129356647 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129356716 | pole | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129356852 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129357337 | insulator and brushing | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129357425 | other | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129357662 | pole | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129358079 | other | Non-HFTD | Transmission | 2024-08-09 | 2025-08-09 | Level 2 | E |  | 2025-08-09 | Level 2
129358116 | insulator and brushing | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129358869 | anchor/guy | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129358890 | anchor/guy | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129369224 | insulator and brushing | Non-HFTD | Transmission | 2024-08-10 | 2025-08-10 | Level 2 | E |  | 2025-08-10 | Level 2
129369261 | other | Non-HFTD | Transmission | 2024-08-10 | 2029-08-10 | Level 3 | F |  | 2029-08-10 | Level 3
129369827 | other | Non-HFTD | Transmission | 2024-08-11 | 2029-08-11 | Level 3 | F |  | 2029-08-11 | Level 3
129370802 | pole | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E | 2024-10-29 | 2027-08-09 | Level 2 | GO 165 Inspection
129371080 | pole | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129371661 | anchor/guy | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129371805 | pole | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129372240 | pole | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129373336 | pole | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129373338 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F | 2024-11-24 | 2029-08-12 | Level 3 | GO 165 Inspection
129373775 | other | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129373917 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F | 2024-11-24 | 2029-08-12 | Level 3 | GO 165 Inspection
129373983 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129374008 | other | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129374164 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F | 2024-09-17 | 2029-08-12 | Level 3 | GO 165 Inspection
129374581 | other | Non-HFTD | Transmission | 2024-08-12 | 2025-08-12 | Level 2 | E | 2024-10-15 | 2025-08-12 | Level 2 | GO 165 Inspection
129374850 | anchor/guy | Non-HFTD | Transmission | 2024-08-12 | 2025-08-12 | Level 2 | E |  | 2025-08-12 | Level 2
129375170 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375267 | anchor/guy | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375359 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375498 | anchor/guy | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375553 | insulator and brushing | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375560 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375564 | insulator and brushing | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375565 | anchor/guy | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375568 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375569 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129375916 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129375976 | pole | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129376066 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129376075 | pole | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129376081 | crossarm | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129376131 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2025-07-31 | Level 2 | E |  | 2025-07-31 | Level 2
129376154 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129376165 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129376182 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129376235 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129376277 | insulator and brushing | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129376296 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129376322 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129376327 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129376350 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129376355 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129376365 | insulator and brushing | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129376367 | pole | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129376391 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129376393 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129376415 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129376430 | pole | HFTD Tier 2 | Transmission | 2024-06-03 | 2027-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129376445 | anchor/guy | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129376453 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129376463 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129376471 | other | HFTD Tier 2 | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129376857 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129377223 | anchor/guy | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F | 2024-09-04 | 2029-07-31 | Level 3 | GO 165 Inspection
129377306 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129379247 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129379392 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129379394 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129379475 | insulator and brushing | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129379514 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129380254 | other | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129380480 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-08-13 | 2025-08-13 | Level 2 | E |  | 2025-08-13 | Level 2
129380575 | other | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129381065 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E | 2024-10-31 | 2027-08-13 | Level 2 | GO 165 Inspection
129381248 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129381264 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129381276 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129381423 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129381582 | insulator and brushing | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129381626 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129381653 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129381667 | pole | Non-HFTD | Transmission | 2024-08-03 | 2027-08-03 | Level 2 | E | 2024-11-08 | 2027-08-03 | Level 2 | GO 165 Inspection
129381675 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129381688 | anchor/guy | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129381832 | pole | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E | 2024-09-18 | 2027-08-09 | Level 2 | GO 165 Inspection
129381912 | pole | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129382202 | anchor/guy | Non-HFTD | Transmission | 2024-06-03 | 2025-06-03 | Level 2 | E |  | 2025-06-03 | Level 2
129382250 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129382251 | other | Non-HFTD | Transmission | 2024-08-12 | 2025-02-13 | Level 2 | E |  | 2025-02-13 | Level 2
129382254 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129382304 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129382309 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129382340 | pole | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E | 2024-10-02 | 2027-08-12 | Level 2 | GO 165 Inspection
129382374 | crossarm | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129382385 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129382388 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129382395 | pole | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129382399 | other | Non-HFTD | Transmission | 2024-07-30 | 2025-07-30 | Level 2 | E |  | 2025-07-30 | Level 2
129382421 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129382423 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129382426 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129382492 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129382520 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129382530 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129382535 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129382546 | pole | HFTD Tier 3 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129382561 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-12 | Level 2 | E |  | 2025-06-04 | Level 2
129382571 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F | 2024-12-05 | 2029-06-05 | Level 3 | GO 165 Inspection
129382574 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129382615 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129382616 | pole | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129382621 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129382639 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129382644 | other | HFTD Tier 2 | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129382652 | crossarm | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129382664 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129382710 | anchor/guy | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129382733 | pole | HFTD Tier 3 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129382766 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-05 | Level 2 | E | 2024-12-05 | 2025-06-05 | Level 2 | GO 165 Inspection
129383081 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129383231 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129383449 | pole | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129383525 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129383657 | insulator and brushing | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129383658 | insulator and brushing | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129383807 | other | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129384472 | anchor/guy | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129384738 | anchor/guy | Non-HFTD | Transmission | 2024-08-14 | 2025-08-14 | Level 2 | E |  | 2025-08-14 | Level 2
129384838 | insulator and brushing | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129385833 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129385972 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129385987 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129386095 | pole | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129386397 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129386426 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129386567 | insulator and brushing | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129387948 | pole | Non-HFTD | Transmission | 2024-08-14 | 2025-08-14 | Level 2 | E |  | 2025-08-14 | Level 2
129389291 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129389609 | anchor/guy | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E | 2024-10-26 | 2027-08-14 | Level 2 | GO 165 Inspection
129389807 | insulator and brushing | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129390848 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129391208 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129391444 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2024-12-06 | Level 2 | E |  | 2024-12-06 | Level 2
129391539 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129391813 | pole | Non-HFTD | Transmission | 2024-08-15 | 2025-08-15 | Level 2 | E | 2024-10-10 | 2025-08-15 | Level 2 | GO 165 Inspection
129392701 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F | 2024-10-09 | 2029-08-15 | Level 3 | GO 165 Inspection
129392707 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129392708 | pole | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129392740 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129392776 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F | 2024-10-09 | 2029-08-15 | Level 3 | GO 165 Inspection
129393251 | pole | HFTD Tier 3 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129393278 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129393343 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129393404 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129393410 | pole | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129393412 | other | HFTD Tier 2 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129393541 | pole | HFTD Tier 3 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129393543 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129393549 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129393621 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129393672 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129393693 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129393734 | pole | HFTD Tier 3 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129393740 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129393779 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129393783 | other | HFTD Tier 2 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129393881 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129393883 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129393894 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129393943 | pole | HFTD Tier 2 | Transmission | 2024-06-04 | 2025-06-04 | Level 2 | E |  | 2025-06-04 | Level 2
129393949 | other | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129393969 | anchor/guy | Non-HFTD | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129394017 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394041 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129394057 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129394104 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129394128 | pole | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129394140 | other | HFTD Tier 3 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394194 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129394243 | pole | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129394248 | crossarm | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129394260 | pole | HFTD Tier 2 | Transmission | 2024-06-10 | 2025-06-10 | Level 2 | E |  | 2025-06-10 | Level 2
129394288 | other | HFTD Tier 3 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129394310 | pole | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394327 | pole | HFTD Tier 3 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394333 | other | HFTD Tier 3 | Transmission | 2024-06-06 | 2029-06-06 | Level 3 | F |  | 2029-06-06 | Level 3
129394336 | pole | HFTD Tier 3 | Transmission | 2024-06-06 | 2024-12-06 | Level 2 | E | 2024-10-24 | 2024-12-06 | Level 2 | Field Safety Reassessment
129394337 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129394369 | pole | HFTD Tier 3 | Transmission | 2024-06-08 | 2024-12-08 | Level 2 | E |  | 2024-12-08 | Level 2
129394374 | pole | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394409 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394422 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129394783 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129394974 | other | HFTD Tier 2 | Transmission | 2024-06-08 | 2029-06-08 | Level 3 | F |  | 2029-06-08 | Level 3
129394985 | pole | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129394986 | other | Non-HFTD | Transmission | 2024-08-13 | 2024-11-13 | Level 2 | E | 2024-12-23 | 2024-11-13 | Level 2 | Field Safety Reassessment
129394991 | other | Non-HFTD | Transmission | 2024-06-07 | 2025-06-07 | Level 2 | E |  | 2025-06-07 | Level 2
129395170 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129395183 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129395771 | insulator and brushing | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129395773 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129395774 | anchor/guy | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129395776 | anchor/guy | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129395780 | insulator and brushing | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129396218 | anchor/guy | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129396410 | anchor/guy | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129397582 | other | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129398441 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129398572 | insulator and brushing | Non-HFTD | Transmission | 2024-08-16 | 2025-08-16 | Level 2 | E |  | 2025-08-16 | Level 2
129398827 | insulator and brushing | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129399871 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129399876 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129399883 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129399886 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129401134 | insulator and brushing | Non-HFTD | Transmission | 2024-08-17 | 2027-08-17 | Level 2 | E |  | 2027-08-17 | Level 2
129401142 | pole | Non-HFTD | Transmission | 2024-08-17 | 2025-08-17 | Level 2 | E |  | 2025-08-17 | Level 2
129401151 | anchor/guy | Non-HFTD | Transmission | 2024-08-17 | 2029-08-17 | Level 3 | F |  | 2029-08-17 | Level 3
129401476 | other | Non-HFTD | Transmission | 2024-08-17 | 2029-08-17 | Level 3 | F |  | 2029-08-17 | Level 3
129401602 | insulator and brushing | Non-HFTD | Transmission | 2024-08-17 | 2027-08-17 | Level 2 | E |  | 2027-08-17 | Level 2
129401612 | other | Non-HFTD | Transmission | 2024-08-17 | 2029-08-17 | Level 3 | F |  | 2029-08-17 | Level 3
129401631 | insulator and brushing | Non-HFTD | Transmission | 2024-08-17 | 2027-08-17 | Level 2 | E |  | 2027-08-17 | Level 2
129404747 | anchor/guy | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129404748 | other | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129404912 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129404937 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129405180 | pole | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129405661 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129405669 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129405760 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129405901 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129406028 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129406335 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129406459 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129406548 | pole | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E | 2024-09-24 | 2027-08-14 | Level 2 | GO 165 Inspection
129406941 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129407104 | other | Non-HFTD | Transmission | 2024-08-17 | 2029-08-17 | Level 3 | F |  | 2029-08-17 | Level 3
129407155 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129407196 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129407385 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129407392 | insulator and brushing | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129407427 | pole | Non-HFTD | Transmission | 2024-08-19 | 2025-08-19 | Level 2 | E | 2024-10-21 | 2025-08-19 | Level 2 | GO 165 Inspection
129407442 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129407601 | anchor/guy | Non-HFTD | Transmission | 2024-08-19 | 2025-02-19 | Level 2 | E |  | 2025-02-19 | Level 2
129407636 | anchor/guy | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F | 2024-10-22 | 2029-08-19 | Level 3 | GO 165 Inspection
129408004 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129408020 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129408225 | insulator and brushing | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129408535 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129408657 | conductor | Non-HFTD | Transmission | 2024-08-19 | 2025-02-19 | Level 2 | E |  | 2025-02-19 | Level 2
129408723 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129408724 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129408729 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129408809 | anchor/guy | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129408818 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129408820 | anchor/guy | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129408839 | pole | Non-HFTD | Transmission | 2024-08-19 | 2025-08-19 | Level 2 | E |  | 2025-08-19 | Level 2
129408840 | insulator and brushing | Non-HFTD | Transmission | 2024-08-19 | 2024-11-19 | Level 2 | E | 2024-12-29 | 2024-11-19 | Level 2 | Field Safety Reassessment
129408859 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129408918 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129408950 | anchor/guy | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129408954 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129408980 | pole | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129408994 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129409012 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129409017 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129409057 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129409068 | pole | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129409070 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-06 | 2025-06-06 | Level 2 | E |  | 2025-06-06 | Level 2
129409084 | other | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129409088 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-12 | 2025-06-12 | Level 2 | E |  | 2025-06-12 | Level 2
129409139 | other | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129409177 | other | HFTD Tier 3 | Transmission | 2024-06-02 | 2029-06-02 | Level 3 | F |  | 2029-06-02 | Level 3
129409188 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129409189 | other | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E | 2024-09-06 | 2027-06-13 | Level 2 | GO 165 Inspection
129409205 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129409221 | other | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E | 2024-09-18 | 2027-06-11 | Level 2 | GO 165 Inspection
129409239 | other | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129409260 | other | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E | 2024-09-06 | 2027-06-13 | Level 2 | GO 165 Inspection
129409261 | other | HFTD Tier 3 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129409266 | pole | HFTD Tier 2 | Transmission | 2024-06-12 | 2025-06-12 | Level 2 | E |  | 2025-06-12 | Level 2
129409267 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129409292 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F | 2024-09-05 | 2029-06-13 | Level 3 | GO 165 Inspection
129409322 | crossarm | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129409331 | other | Non-HFTD | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129409332 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129409371 | anchor/guy | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-08-29 | 2029-06-12 | Level 3 | GO 165 Inspection
129409374 | other | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E |  | 2027-06-11 | Level 2
129409379 | other | Non-HFTD | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129409390 | other | HFTD Tier 3 | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129409393 | other | HFTD Tier 2 | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129409407 | anchor/guy | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F | 2024-08-29 | 2029-06-12 | Level 3 | GO 165 Inspection
129409409 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129409436 | insulator and brushing | Non-HFTD | Transmission | 2024-06-12 | 2027-06-12 | Level 2 | E | 2024-08-29 | 2027-06-12 | Level 2 | GO 165 Inspection
129409467 | pole | HFTD Tier 2 | Transmission | 2024-06-14 | 2024-12-14 | Level 2 | E |  | 2024-12-14 | Level 2
129409472 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129409475 | other | HFTD Tier 3 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129409483 | pole | Non-HFTD | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129409487 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E |  | 2025-06-13 | Level 2
129409502 | other | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 2 | E | 2024-09-06 | 2025-06-13 | Level 2 | GO 165 Inspection
129409506 | other | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E | 2024-09-06 | 2027-06-13 | Level 2 | GO 165 Inspection
129409521 | other | Non-HFTD | Transmission | 2024-06-12 | 2027-06-12 | Level 2 | E | 2024-08-29 | 2027-06-12 | Level 2 | GO 165 Inspection
129409533 | anchor/guy | Non-HFTD | Transmission | 2024-06-14 | 2027-06-14 | Level 2 | E | 2024-08-27 | 2027-06-14 | Level 2 | GO 165 Inspection
129409550 | other | HFTD Tier 2 | Transmission | 2024-06-07 | 2029-06-07 | Level 3 | F |  | 2029-06-07 | Level 3
129409554 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-11 | 2025-06-11 | Level 2 | E |  | 2025-06-11 | Level 2
129409560 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-14 | 2025-06-14 | Level 2 | E |  | 2025-06-14 | Level 2
129409567 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129409609 | insulator and brushing | Non-HFTD | Transmission | 2024-06-13 | 2025-06-13 | Level 2 | E | 2024-08-26 | 2025-06-13 | Level 2 | GO 165 Inspection
129409639 | other | Non-HFTD | Transmission | 2024-06-13 | 2027-06-13 | Level 2 | E | 2024-08-29 | 2027-06-13 | Level 2 | GO 165 Inspection
129409714 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129409732 | other | Non-HFTD | Transmission | 2024-08-19 | 2025-08-19 | Level 2 | E |  | 2025-08-19 | Level 2
129409978 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F | 2024-10-23 | 2029-08-19 | Level 3 | GO 165 Inspection
129410296 | other | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E |  | 2025-08-20 | Level 2
129411382 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129411515 | anchor/guy | Non-HFTD | Transmission | 2024-08-20 | 2025-02-20 | Level 2 | E |  | 2025-02-20 | Level 2
129411554 | pole | Non-HFTD | Transmission | 2024-08-17 | 2027-08-17 | Level 2 | E | 2024-10-30 | 2027-08-17 | Level 2 | GO 165 Inspection
129411580 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F | 2024-09-24 | 2029-08-20 | Level 3 | GO 165 Inspection
129411892 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129411921 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129412044 | pole | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129412734 | anchor/guy | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E | 2024-10-25 | 2025-08-20 | Level 2 | GO 165 Inspection
129413131 | pole | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129413558 | pole | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129413751 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129413781 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129414459 | other | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E |  | 2025-08-20 | Level 2
129415010 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129415097 | anchor/guy | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129415507 | insulator and brushing | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129415543 | pole | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129416721 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129417263 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129417650 | pole | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129417759 | pole | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129417847 | pole | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F | 2024-11-22 | 2029-08-21 | Level 3 | GO 165 Inspection
129418109 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129418154 | pole | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129418427 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129418572 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129418584 | pole | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E | 2024-10-16 | 2027-08-21 | Level 2 | GO 165 Inspection
129418713 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129419035 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129419038 | insulator and brushing | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129419361 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129419474 | other | Non-HFTD | Transmission | 2024-08-21 | 2025-02-21 | Level 2 | E |  | 2025-02-21 | Level 2
129419516 | pole | HFTD Tier 3 | Transmission | 2024-06-17 | 2024-12-17 | Level 2 | E | 2024-10-15 | 2024-12-17 | Level 2 | Field Safety Reassessment
129419537 | other | HFTD Tier 3 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129419609 | other | HFTD Tier 3 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129419796 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129419803 | pole | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129419849 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-09-11 | 2029-06-14 | Level 3 | GO 165 Inspection
129419853 | other | Non-HFTD | Transmission | 2024-06-12 | 2027-06-12 | Level 2 | E | 2024-08-28 | 2027-06-12 | Level 2 | GO 165 Inspection
129419858 | anchor/guy | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129419859 | pole | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E | 2024-10-23 | 2027-08-21 | Level 2 | GO 165 Inspection
129419972 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129419976 | other | HFTD Tier 2 | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129419988 | pole | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F | 2024-09-30 | 2029-06-20 | Level 3 | GO 165 Inspection
129420026 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-09-13 | 2029-06-14 | Level 3 | GO 165 Inspection
129420084 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F | 2024-10-16 | 2029-06-21 | Level 3 | GO 165 Inspection
129420100 | other | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E | 2024-09-04 | 2027-06-18 | Level 2 | GO 165 Inspection
129420107 | pole | HFTD Tier 2 | Transmission | 2024-06-17 | 2025-06-17 | Level 2 | E |  | 2025-06-17 | Level 2
129420122 | other | Non-HFTD | Transmission | 2024-06-21 | 2029-06-21 | Level 3 | F | 2024-10-21 | 2029-06-21 | Level 3 | GO 165 Inspection
129420160 | other | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E | 2024-09-04 | 2027-06-20 | Level 2 | GO 165 Inspection
129420181 | other | Non-HFTD | Transmission | 2024-06-21 | 2027-06-21 | Level 2 | E | 2024-09-05 | 2027-06-21 | Level 2 | GO 165 Inspection
129420202 | other | Non-HFTD | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F | 2024-09-11 | 2029-06-15 | Level 3 | GO 165 Inspection
129420229 | other | Non-HFTD | Transmission | 2024-08-16 | 2025-08-16 | Level 2 | E |  | 2025-08-16 | Level 2
129420253 | anchor/guy | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129420320 | other | Non-HFTD | Transmission | 2024-06-24 | 2027-06-24 | Level 2 | E | 2024-09-04 | 2027-06-24 | Level 2 | GO 165 Inspection
129420337 | pole | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129420381 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129420382 | pole | Non-HFTD | Transmission | 2024-08-19 | 2025-08-19 | Level 2 | E |  | 2025-08-19 | Level 2
129420408 | pole | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129420419 | other | Non-HFTD | Transmission | 2024-06-20 | 2027-06-20 | Level 2 | E |  | 2027-06-20 | Level 2
129420469 | other | HFTD Tier 2 | Transmission | 2024-06-15 | 2029-06-15 | Level 3 | F |  | 2029-06-15 | Level 3
129420482 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129420496 | other | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129420507 | anchor/guy | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129420509 | other | Non-HFTD | Transmission | 2024-08-16 | 2024-11-16 | Level 2 | E | 2024-10-29 | 2025-08-16 | Level 2 | Field Safety Reassessment
129420512 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129420514 | other | HFTD Tier 3 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129421923 | pole | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129422075 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129422733 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129422782 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129422800 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129422852 | other | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129423013 | anchor/guy | HFTD Tier 2 | Transmission | 2024-08-22 | 2025-02-22 | Level 2 | E |  | 2025-02-22 | Level 2
129423035 | other | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129423087 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129423352 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129423432 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129423658 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129423746 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E | 2024-10-28 | 2027-08-22 | Level 2 | GO 165 Inspection
129424064 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129424122 | pole | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129424185 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2025-08-22 | Level 2 | E |  | 2025-08-22 | Level 2
129424586 | pole | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129424656 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129424702 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129424787 | pole | HFTD Tier 2 | Transmission | 2024-06-15 | 2025-06-15 | Level 2 | E |  | 2025-06-15 | Level 2
129424854 | other | HFTD Tier 2 | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129425002 | pole | HFTD Tier 2 | Transmission | 2024-06-21 | 2024-12-21 | Level 2 | E |  | 2024-12-21 | Level 2
129425074 | other | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F | 2024-09-06 | 2029-06-14 | Level 3 | GO 165 Inspection
129425076 | pole | Non-HFTD | Transmission | 2024-06-14 | 2027-06-14 | Level 2 | E | 2024-09-06 | 2027-06-14 | Level 2 | GO 165 Inspection
129425147 | pole | Non-HFTD | Transmission | 2024-06-14 | 2029-06-14 | Level 3 | F |  | 2029-06-14 | Level 3
129425149 | insulator and brushing | Non-HFTD | Transmission | 2024-06-14 | 2027-06-14 | Level 2 | E |  | 2027-06-14 | Level 2
129425166 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129425419 | other | Non-HFTD | Transmission | 2024-08-19 | 2024-11-19 | Level 2 | E | 2024-12-02 | 2024-11-19 | Level 2 | Field Safety Reassessment
129425500 | other | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129425580 | crossarm | Non-HFTD | Transmission | 2024-08-21 | 2024-11-21 | Level 2 | E |  | 2024-11-21 | Level 2
129425616 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129425633 | other | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F | 2024-09-25 | 2029-06-17 | Level 3 | GO 165 Inspection
129425639 | other | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F | 2024-09-20 | 2029-06-17 | Level 3 | GO 165 Inspection
129425675 | pole | Non-HFTD | Transmission | 2024-06-18 | 2027-06-18 | Level 2 | E | 2024-09-12 | 2027-06-18 | Level 2 | GO 165 Inspection
129425763 | pole | HFTD Tier 2 | Transmission | 2024-06-08 | 2025-06-08 | Level 2 | E |  | 2025-06-08 | Level 2
129425776 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129427770 | anchor/guy | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129427923 | conductor | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2025-08-23 | Level 2
129428184 | pole | Non-HFTD | Transmission | 2024-08-23 | 2025-08-23 | Level 2 | E |  | 2025-08-23 | Level 2
129428245 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129428342 | insulator and brushing | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129429011 | anchor/guy | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129429123 | pole | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129429542 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129429587 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129429643 | pole | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129429962 | anchor/guy | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129430274 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129430433 | insulator and brushing | Non-HFTD | Transmission | 2024-08-23 | 2025-08-23 | Level 2 | E |  | 2025-08-23 | Level 2
129430710 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F | 2024-10-15 | 2029-08-23 | Level 3 | GO 165 Inspection
129431815 | insulator and brushing | Non-HFTD | Transmission | 2024-08-24 | 2027-08-24 | Level 2 | E |  | 2027-08-24 | Level 2
129433738 | anchor/guy | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E | 2024-10-23 | 2027-08-23 | Level 2 | GO 165 Inspection
129434381 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129435118 | anchor/guy | HFTD Tier 3 | Transmission | 2024-08-12 | 2025-02-12 | Level 2 | E |  | 2025-02-12 | Level 2
129435437 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129435609 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129435652 | other | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E | 2024-10-09 | 2027-08-16 | Level 2 | GO 165 Inspection
129436046 | other | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E | 2024-10-10 | 2027-08-16 | Level 2 | GO 165 Inspection
129436084 | switch | HFTD Tier 2 | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129436259 | other | HFTD Tier 2 | Transmission | 2024-08-26 | 2024-11-26 | Level 2 | E |  | 2024-11-26 | Level 2
129436498 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129436516 | pole | HFTD Tier 2 | Transmission | 2024-08-26 | 2025-08-26 | Level 2 | E |  | 2025-08-26 | Level 2
129436529 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129436534 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129436997 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129437109 | other | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129437303 | pole | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129437408 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129437567 | other | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129437893 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129437905 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129437936 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129437959 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129437961 | anchor/guy | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E |  | 2025-08-20 | Level 2
129438049 | pole | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129438092 | pole | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129438181 | other | HFTD Tier 2 | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129438193 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E |  | 2025-08-20 | Level 2
129438601 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129439416 | pole | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E |  | 2025-08-20 | Level 2
129439517 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129440246 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129440255 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129440598 | pole | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129440608 | crossarm | Non-HFTD | Transmission | 2024-08-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
129441238 | pole | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129441840 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129441884 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129442429 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129442448 | pole | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129443088 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129443165 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129444274 | other | Non-HFTD | Transmission | 2024-06-24 | 2029-06-24 | Level 3 | F |  | 2029-06-24 | Level 3
129444579 | other | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E |  | 2027-07-09 | Level 2
129444601 | pole | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129444627 | pole | HFTD Tier 2 | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129444743 | anchor/guy | Non-HFTD | Transmission | 2024-06-24 | 2025-06-24 | Level 2 | E |  | 2025-06-24 | Level 2
129444764 | pole | HFTD Tier 3 | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129444825 | pole | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129444848 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129444944 | pole | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129444949 | crossarm | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129444974 | pole | Non-HFTD | Transmission | 2024-08-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
129444984 | insulator and brushing | Non-HFTD | Transmission | 2024-06-27 | 2027-06-27 | Level 2 | E |  | 2027-06-27 | Level 2
129445010 | other | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129445019 | other | Non-HFTD | Transmission | 2024-06-26 | 2027-06-26 | Level 2 | E |  | 2027-06-26 | Level 2
129445025 | pole | HFTD Tier 2 | Transmission | 2024-07-09 | 2025-07-09 | Level 2 | E |  | 2025-07-09 | Level 2
129445028 | other | HFTD Tier 2 | Transmission | 2024-07-09 | 2029-07-09 | Level 3 | F |  | 2029-07-09 | Level 3
129445088 | other | Non-HFTD | Transmission | 2024-08-23 | 2024-11-23 | Level 2 | E |  | 2024-11-23 | Level 2
129445099 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129445101 | other | Non-HFTD | Transmission | 2024-06-25 | 2027-06-25 | Level 2 | E |  | 2027-06-25 | Level 2
129445112 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129445117 | pole | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129445118 | anchor/guy | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129445128 | other | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129445175 | other | Non-HFTD | Transmission | 2024-06-25 | 2029-06-25 | Level 3 | F |  | 2029-06-25 | Level 3
129445177 | insulator and brushing | Non-HFTD | Transmission | 2024-06-25 | 2025-06-25 | Level 2 | E |  | 2025-06-25 | Level 2
129445179 | anchor/guy | Non-HFTD | Transmission | 2024-06-25 | 2025-06-25 | Level 2 | E |  | 2025-06-25 | Level 2
129445182 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129445208 | other | Non-HFTD | Transmission | 2024-06-28 | 2029-06-28 | Level 3 | F |  | 2029-06-28 | Level 3
129445227 | other | Non-HFTD | Transmission | 2024-06-28 | 2027-06-28 | Level 2 | E | 2024-09-12 | 2027-06-28 | Level 2 | GO 165 Inspection
129445237 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129445562 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129445873 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129445990 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129446242 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129446369 | other | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129446474 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129447064 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129447402 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129447408 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129448158 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129448866 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129449084 | other | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129449235 | switch | Non-HFTD | Transmission | 2024-08-28 | 2024-11-28 | Level 2 | E |  | 2024-11-28 | Level 2
129449303 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129449544 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129449955 | conductor | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129450268 | other | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129450361 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129450364 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129450373 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129450448 | other | Non-HFTD | Transmission | 2024-08-27 | 2024-11-27 | Level 2 | E | 2024-12-20 | 2024-11-27 | Level 2 | Field Safety Reassessment
129450546 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129450569 | pole | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129450616 | pole | HFTD Tier 2 | Transmission | 2024-07-11 | 2025-07-11 | Level 2 | E |  | 2025-07-11 | Level 2
129450688 | other | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129450693 | insulator and brushing | Non-HFTD | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | E | 2024-09-04 | 2027-07-09 | Level 2 | GO 165 Inspection
129450763 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129450775 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129450815 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129450818 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129450824 | anchor/guy | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129450860 | insulator and brushing | Non-HFTD | Transmission | 2024-07-11 | 2027-07-11 | Level 2 | E |  | 2027-07-11 | Level 2
129452330 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2025-08-29 | Level 2 | E |  | 2025-08-29 | Level 2
129452610 | pole | HFTD Tier 2 | Transmission | 2024-08-26 | 2025-08-26 | Level 2 | E |  | 2025-08-26 | Level 2
129452804 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129452827 | pole | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129452894 | pole | HFTD Tier 2 | Transmission | 2024-08-26 | 2025-08-26 | Level 2 | E |  | 2025-08-26 | Level 2
129453636 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129453750 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129453933 | pole | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455071 | anchor/guy | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455194 | pole | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129455195 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455198 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455398 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455444 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455467 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455469 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129455470 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129456673 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2025-02-28 | Level 2 | E |  | 2027-08-29 | Level 2
129456742 | pole | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129456895 | anchor/guy | Non-HFTD | Transmission | 2024-07-10 | 2029-07-10 | Level 3 | F |  | 2029-07-10 | Level 3
129456899 | anchor/guy | Non-HFTD | Transmission | 2024-07-10 | 2025-07-10 | Level 2 | E |  | 2025-07-10 | Level 2
129457092 | pole | Non-HFTD | Transmission | 2024-07-10 | 2027-07-10 | Level 2 | E |  | 2027-07-10 | Level 2
129457119 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129457160 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129457234 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129457375 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129457377 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2025-07-11 | Level 2 | E |  | 2025-07-11 | Level 2
129457404 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129457442 | other | Non-HFTD | Transmission | 2024-07-11 | 2029-07-11 | Level 3 | F |  | 2029-07-11 | Level 3
129457470 | anchor/guy | Non-HFTD | Transmission | 2024-07-11 | 2025-07-11 | Level 2 | E |  | 2025-07-11 | Level 2
129457501 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129457522 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129457529 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129457563 | anchor/guy | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129457564 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129457568 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129457575 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129457576 | pole | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129457792 | other | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129458863 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129458865 | insulator and brushing | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129458879 | other | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129459299 | other | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129459328 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129460019 | pole | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129460108 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129460347 | pole | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129461012 | insulator and brushing | Non-HFTD | Transmission | 2024-08-30 | 2025-08-30 | Level 2 | E |  | 2025-08-30 | Level 2
129461013 | anchor/guy | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129461090 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129461262 | pole | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129462173 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129462176 | pole | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129462178 | other | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129462554 | pole | Non-HFTD | Transmission | 2024-08-31 | 2025-08-31 | Level 2 | E |  | 2025-08-31 | Level 2
129463214 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129466059 | anchor/guy | HFTD Tier 2 | Transmission | 2023-05-19 | 2024-05-19 | Level 2 | E |  | 2024-05-19 | Level 2
129466676 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129466956 | anchor/guy | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129467051 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129467098 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129468974 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129468997 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129469030 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129469041 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129469168 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129469179 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129469352 | other | HFTD Tier 2 | Transmission | 2024-09-03 | 2025-09-03 | Level 2 | E |  | 2025-09-03 | Level 2
129469387 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129469415 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129469499 | other | HFTD Tier 2 | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129469647 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129469752 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F | 2024-10-11 | 2029-08-31 | Level 3 | GO 165 Inspection
129469759 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129469793 | other | Non-HFTD | Transmission | 2024-07-16 | 2025-07-16 | Level 2 | E |  | 2025-07-16 | Level 2
129469798 | other | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129469826 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129469854 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129469872 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129469880 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129469882 | pole | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129469904 | anchor/guy | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129469927 | pole | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129469939 | pole | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129469950 | insulator and brushing | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129469959 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129469967 | pole | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129469981 | other | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129469983 | switch | Non-HFTD | Transmission | 2024-09-03 | 2025-09-03 | Level 2 | E |  | 2025-09-03 | Level 2
129470007 | pole | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129470040 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129470052 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129470087 | anchor/guy | Non-HFTD | Transmission | 2024-07-16 | 2025-01-16 | Level 2 | E |  | 2025-01-16 | Level 2
129470123 | other | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129470141 | other | Non-HFTD | Transmission | 2024-07-15 | 2025-07-15 | Level 2 | E |  | 2025-07-15 | Level 2
129470161 | pole | Non-HFTD | Transmission | 2024-07-12 | 2029-07-12 | Level 3 | F |  | 2029-07-12 | Level 3
129470163 | anchor/guy | Non-HFTD | Transmission | 2024-07-12 | 2027-07-12 | Level 2 | E |  | 2027-07-12 | Level 2
129470170 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129470176 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129470207 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129470242 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129470273 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129470787 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129471025 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129471026 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129471192 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129471308 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129471435 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129471634 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129471760 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129471765 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129471960 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129472044 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129472969 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129474169 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129474185 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129474471 | other | Non-HFTD | Transmission | 2024-09-03 | 2024-12-03 | Level 2 | E |  | 2024-12-03 | Level 2
129474598 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129474762 | pole | Non-HFTD | Transmission | 2024-07-16 | 2027-07-16 | Level 2 | E |  | 2027-07-16 | Level 2
129474768 | insulator and brushing | Non-HFTD | Transmission | 2024-07-17 | 2029-07-17 | Level 3 | F |  | 2029-07-17 | Level 3
129475598 | anchor/guy | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129475651 | pole | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129475664 | other | HFTD Tier 2 | Transmission | 2024-07-17 | 2025-07-17 | Level 2 | E |  | 2025-07-17 | Level 2
129475676 | pole | Non-HFTD | Transmission | 2024-07-17 | 2027-07-17 | Level 2 | E |  | 2027-07-17 | Level 2
129475679 | other | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129475734 | pole | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129475743 | pole | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F | 2024-11-16 | 2029-09-04 | Level 3 | GO 165 Inspection
129475762 | pole | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129475807 | pole | Non-HFTD | Transmission | 2024-09-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
129475825 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129475830 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129475840 | other | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129475873 | switch | Non-HFTD | Transmission | 2024-08-30 | 2025-08-30 | Level 2 | E |  | 2025-08-30 | Level 2
129475881 | other | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129475888 | pole | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129475930 | pole | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129475936 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129476003 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2025-08-22 | Level 2 | E |  | 2025-08-22 | Level 2
129476005 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129476006 | anchor/guy | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129476472 | anchor/guy | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129476611 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129476808 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129477695 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129477857 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129477912 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129477962 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129477995 | anchor/guy | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129478230 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129478417 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129478773 | anchor/guy | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129479150 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129479158 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129479516 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129480109 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E | 2024-11-19 | 2027-09-04 | Level 2 | GO 165 Inspection
129480142 | other | Non-HFTD | Transmission | 2024-09-03 | 2024-12-03 | Level 2 | E |  | 2025-09-03 | Level 2
129480186 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129480187 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129480188 | other | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129480192 | insulator and brushing | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E | 2024-11-18 | 2027-08-21 | Level 2 | GO 165 Inspection
129480199 | other | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 3 | F | 2024-11-18 | 2029-08-23 | Level 3 | GO 165 Inspection
129480314 | other | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E | 2024-11-13 | 2027-08-14 | Level 2 | GO 165 Inspection
129480315 | pole | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F | 2024-11-13 | 2029-08-14 | Level 3 | GO 165 Inspection
129480317 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F | 2024-11-17 | 2029-08-21 | Level 3 | GO 165 Inspection
129480319 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F | 2024-11-17 | 2029-08-21 | Level 3 | GO 165 Inspection
129480342 | other | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E | 2024-11-14 | 2025-08-22 | Level 2 | GO 165 Inspection
129480353 | pole | Non-HFTD | Transmission | 2024-08-23 | 2025-08-23 | Level 2 | E | 2024-10-23 | 2025-08-23 | Level 2 | GO 165 Inspection
129480365 | pole | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F | 2024-11-15 | 2029-09-04 | Level 3 | GO 165 Inspection
129480369 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E | 2024-11-15 | 2027-09-04 | Level 2 | GO 165 Inspection
129480391 | anchor/guy | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129480411 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E | 2024-12-12 | 2027-09-04 | Level 2 | GO 165 Inspection
129480415 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E | 2024-12-12 | 2027-09-04 | Level 2 | GO 165 Inspection
129480427 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E | 2024-12-10 | 2027-09-04 | Level 2 | GO 165 Inspection
129480461 | other | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129480477 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129480528 | other | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E | 2024-11-13 | 2027-08-15 | Level 2 | GO 165 Inspection
129480545 | crossarm | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129480561 | pole | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129480563 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129480564 | switch | Non-HFTD | Transmission | 2024-09-04 | 2025-09-04 | Level 2 | E |  | 2025-09-04 | Level 2
129480585 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2024-11-26 | Level 2 | E | 2024-09-20 | 2024-11-26 | Level 2 | GO 165 Inspection
129480621 | other | Non-HFTD | Transmission | 2024-08-13 | 2024-11-13 | Level 2 | E |  | 2024-11-13 | Level 2
129480623 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F | 2024-10-02 | 2029-08-14 | Level 3 | GO 165 Inspection
129480636 | insulator and brushing | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E | 2024-11-14 | 2027-08-21 | Level 2 | GO 165 Inspection
129480647 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2025-09-03 | Level 2 | E |  | 2025-09-03 | Level 2
129480664 | other | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E | 2024-11-13 | 2027-08-14 | Level 2 | GO 165 Inspection
129480667 | other | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E | 2024-12-10 | 2027-08-31 | Level 2 | GO 165 Inspection
129480675 | switch | Non-HFTD | Transmission | 2024-08-12 | 2025-08-12 | Level 2 | E |  | 2025-08-12 | Level 2
129480680 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129480683 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129480684 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129480689 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129480829 | pole | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F | 2024-12-10 | 2029-08-31 | Level 3 | GO 165 Inspection
129480919 | insulator and brushing | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E | 2024-11-12 | 2027-08-15 | Level 2 | GO 165 Inspection
129481188 | other | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F | 2024-11-18 | 2029-08-21 | Level 3 | GO 165 Inspection
129481273 | other | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E | 2024-11-14 | 2025-09-03 | Level 2 | GO 165 Inspection
129482049 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129482064 | pole | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129482103 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129482181 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129482466 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129482781 | anchor/guy | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129482889 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129483071 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129483226 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129483502 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129483785 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129484581 | anchor/guy | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485103 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485105 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485148 | anchor/guy | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485160 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485456 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485458 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129485467 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485502 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129485503 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129486105 | pole | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129487380 | pole | Non-HFTD | Transmission | 2024-09-07 | 2027-09-07 | Level 2 | E |  | 2027-09-07 | Level 2
129487824 | other | Non-HFTD | Transmission | 2024-09-07 | 2029-09-07 | Level 3 | F |  | 2029-09-07 | Level 3
129487825 | pole | Non-HFTD | Transmission | 2024-09-07 | 2027-09-07 | Level 2 | E |  | 2027-09-07 | Level 2
129488979 | other | Non-HFTD | Transmission | 2024-09-08 | 2029-09-08 | Level 3 | F |  | 2029-09-08 | Level 3
129488987 | anchor/guy | Non-HFTD | Transmission | 2024-09-08 | 2029-09-08 | Level 3 | F |  | 2029-09-08 | Level 3
129488996 | other | Non-HFTD | Transmission | 2024-09-08 | 2029-09-08 | Level 3 | F |  | 2029-09-08 | Level 3
129489593 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129489600 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129490189 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129490253 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129490400 | other | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129490410 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129490431 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129490568 | crossarm | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129490856 | crossarm | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129490858 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129490931 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129492047 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129492386 | pole | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129492575 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129492686 | pole | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E | 2024-12-10 | 2027-09-09 | Level 2 | GO 165 Inspection
129492841 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129492918 | pole | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129492986 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494018 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494081 | other | Non-HFTD | Transmission | 2024-08-31 | 2025-08-31 | Level 2 | E | 2024-11-14 | 2025-08-31 | Level 2 | GO 165 Inspection
129494088 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 3 | F | 2024-11-14 | 2029-09-03 | Level 3 | GO 165 Inspection
129494239 | other | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129494254 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129494270 | pole | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F | 2024-11-15 | 2029-08-31 | Level 3 | GO 165 Inspection
129494295 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129494331 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129494333 | pole | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129494350 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129494355 | other | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129494383 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F | 2024-09-19 | 2029-09-06 | Level 3 | GO 165 Inspection
129494436 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129494437 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129494473 | insulator and brushing | Non-HFTD | Transmission | 2024-07-18 | 2027-07-18 | Level 2 | E |  | 2027-07-18 | Level 2
129494484 | other | Non-HFTD | Transmission | 2024-07-18 | 2029-07-18 | Level 3 | F |  | 2029-07-18 | Level 3
129494490 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129494517 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129494546 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494554 | pole | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129494556 | insulator and brushing | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129494560 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129494575 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129494603 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494620 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129494645 | pole | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129494649 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E | 2024-09-19 | 2025-09-05 | Level 2 | GO 165 Inspection
129494659 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494665 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129494667 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129494670 | pole | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129494675 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129494694 | other | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129494721 | insulator and brushing | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129494729 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129494730 | pole | Non-HFTD | Transmission | 2024-09-05 | 2024-12-05 | Level 2 | E |  | 2024-12-05 | Level 2
129494735 | other | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129494754 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129494755 | insulator and brushing | Non-HFTD | Transmission | 2024-07-22 | 2029-07-22 | Level 3 | F |  | 2029-07-22 | Level 3
129494772 | other | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129494774 | pole | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129494794 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129494796 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129494811 | pole | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129494819 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129494831 | insulator and brushing | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129494842 | pole | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129494845 | insulator and brushing | Non-HFTD | Transmission | 2024-07-15 | 2027-07-15 | Level 2 | E |  | 2027-07-15 | Level 2
129494854 | pole | Non-HFTD | Transmission | 2024-07-22 | 2027-07-22 | Level 2 | E |  | 2027-07-22 | Level 2
129494863 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129494866 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129494868 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2024-12-09 | Level 2 | E |  | 2024-12-09 | Level 2
129494875 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129494881 | pole | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129494926 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129494932 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494941 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129494970 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129495015 | pole | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129495045 | anchor/guy | Non-HFTD | Transmission | 2024-07-24 | 2025-07-24 | Level 2 | E |  | 2025-07-24 | Level 2
129495057 | switch | Non-HFTD | Transmission | 2024-07-19 | 2027-07-19 | Level 2 | E |  | 2027-07-19 | Level 2
129495110 | other | Non-HFTD | Transmission | 2024-07-23 | 2029-07-23 | Level 3 | F |  | 2029-07-23 | Level 3
129495113 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129495125 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129495126 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129495152 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129495156 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129495161 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129495192 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129506079 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129506259 | anchor/guy | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129506588 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129507018 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129507659 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129507723 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129507789 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129507857 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129507932 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129507938 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129507972 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508068 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508147 | anchor/guy | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508227 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129508240 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508494 | anchor/guy | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508601 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508667 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2025-09-10 | Level 2 | E |  | 2025-09-10 | Level 2
129508753 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129508964 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509053 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509079 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509194 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509326 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509367 | other | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509639 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509746 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509798 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509804 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129509819 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509944 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509945 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509952 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129509953 | switch | Non-HFTD | Transmission | 2024-09-10 | 2025-09-10 | Level 2 | E |  | 2025-09-10 | Level 2
129509965 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129510275 | anchor/guy | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129510315 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129510356 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129510357 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129510431 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129510433 | insulator and brushing | Non-HFTD | Transmission | 2024-07-26 | 2025-07-26 | Level 2 | E |  | 2025-07-26 | Level 2
129510478 | insulator and brushing | Non-HFTD | Transmission | 2024-07-26 | 2024-10-26 | Level 2 | E |  | 2024-10-26 | Level 2
129510484 | anchor/guy | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129510502 | other | Non-HFTD | Transmission | 2024-07-23 | 2025-07-23 | Level 2 | E |  | 2025-07-23 | Level 2
129510504 | pole | Non-HFTD | Transmission | 2024-07-23 | 2025-07-23 | Level 2 | E |  | 2025-07-23 | Level 2
129510517 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129510526 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129510528 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129510529 | other | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129510554 | pole | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129510559 | other | Non-HFTD | Transmission | 2024-09-06 | 2024-12-06 | Level 2 | E |  | 2024-12-06 | Level 2
129510561 | other | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129510625 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129510675 | other | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129510707 | other | Non-HFTD | Transmission | 2024-09-09 | 2025-09-09 | Level 2 | E |  | 2025-09-09 | Level 2
129510741 | other | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129510766 | insulator and brushing | Non-HFTD | Transmission | 2024-07-26 | 2027-07-26 | Level 2 | E |  | 2027-07-26 | Level 2
129510874 | pole | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129510876 | other | Non-HFTD | Transmission | 2024-07-23 | 2025-07-23 | Level 2 | E |  | 2025-07-23 | Level 2
129510882 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129510886 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129510887 | other | Non-HFTD | Transmission | 2024-09-06 | 2024-12-06 | Level 2 | E |  | 2024-12-06 | Level 2
129510898 | switch | Non-HFTD | Transmission | 2024-07-25 | 2025-07-25 | Level 2 | E |  | 2025-07-25 | Level 2
129510913 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129510916 | anchor/guy | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129510937 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129510941 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F | 2024-11-08 | 2029-07-29 | Level 3 | GO 165 Inspection
129510944 | pole | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F | 2024-11-08 | 2029-07-29 | Level 3 | GO 165 Inspection
129510950 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129510981 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2025-09-09 | Level 2 | E |  | 2025-09-09 | Level 2
129510988 | pole | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129511047 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129511087 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129511104 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129511111 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129511121 | splice | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129511124 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129511137 | switch | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129511139 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129511153 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129511159 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129511160 | pole | Non-HFTD | Transmission | 2024-07-29 | 2027-07-29 | Level 2 | E |  | 2027-07-29 | Level 2
129511176 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129511185 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129511189 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129511218 | pole | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129511220 | crossarm | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129511254 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129511258 | other | Non-HFTD | Transmission | 2024-07-29 | 2029-07-29 | Level 3 | F |  | 2029-07-29 | Level 3
129511260 | pole | Non-HFTD | Transmission | 2024-07-26 | 2025-07-26 | Level 2 | E |  | 2025-07-26 | Level 2
129511268 | pole | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129511270 | anchor/guy | Non-HFTD | Transmission | 2024-09-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
129511271 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129511286 | pole | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129511303 | pole | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129511307 | other | Non-HFTD | Transmission | 2024-07-24 | 2027-07-24 | Level 2 | E |  | 2027-07-24 | Level 2
129511332 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129511335 | insulator and brushing | Non-HFTD | Transmission | 2024-07-30 | 2027-07-30 | Level 2 | E |  | 2027-07-30 | Level 2
129511343 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129511348 | anchor/guy | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129511350 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129511357 | other | Non-HFTD | Transmission | 2024-07-19 | 2029-07-19 | Level 3 | F |  | 2029-07-19 | Level 3
129511359 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129511381 | pole | Non-HFTD | Transmission | 2024-09-10 | 2024-12-10 | Level 2 | E |  | 2024-12-10 | Level 2
129511405 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129511416 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129511463 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129511468 | other | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129512463 | other | Non-HFTD | Transmission | 2024-07-25 | 2029-07-25 | Level 3 | F |  | 2029-07-25 | Level 3
129512505 | pole | Non-HFTD | Transmission | 2024-09-05 | 2024-12-05 | Level 2 | E |  | 2024-12-05 | Level 2
129515953 | other | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129516210 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129516738 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129516896 | anchor/guy | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129516975 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129517062 | anchor/guy | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129517110 | pole | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129517396 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129517437 | anchor/guy | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129517711 | anchor/guy | Non-HFTD | Transmission | 2024-09-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
129517833 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129517886 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129518043 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129518125 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129518132 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129518139 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129518197 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
129518415 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129518507 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2024-12-10 | Level 2 | E |  | 2024-12-10 | Level 2
129518554 | pole | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129518583 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129518619 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129518620 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129518642 | other | Non-HFTD | Transmission | 2024-09-06 | 2024-12-06 | Level 2 | E |  | 2024-12-06 | Level 2
129518643 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129518648 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129518786 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129518787 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129518799 | other | Non-HFTD | Transmission | 2024-07-26 | 2029-07-26 | Level 3 | F |  | 2029-07-26 | Level 3
129518856 | other | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129518953 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129518958 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129518963 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129518995 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129519002 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129519009 | pole | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129519046 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129519060 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129519070 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129519083 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129519148 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129519573 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129519688 | other | Non-HFTD | Transmission | 2024-07-30 | 2029-07-30 | Level 3 | F |  | 2029-07-30 | Level 3
129520127 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129520129 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129520174 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129520404 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129520408 | insulator and brushing | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129520647 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129520688 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129520713 | other | Non-HFTD | Transmission | 2024-07-22 | 2025-07-22 | Level 2 | E |  | 2025-07-22 | Level 2
129520716 | insulator and brushing | Non-HFTD | Transmission | 2024-07-31 | 2027-07-31 | Level 2 | E |  | 2027-07-31 | Level 2
129520780 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129520820 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129520827 | pole | Non-HFTD | Transmission | 2024-07-24 | 2025-07-24 | Level 2 | E |  | 2025-07-24 | Level 2
129520850 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129520900 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129520902 | other | Non-HFTD | Transmission | 2024-07-31 | 2029-07-31 | Level 3 | F |  | 2029-07-31 | Level 3
129520941 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129520945 | pole | Non-HFTD | Transmission | 2024-08-05 | 2025-08-05 | Level 2 | E |  | 2025-08-05 | Level 2
129520972 | other | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129520985 | other | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129520989 | conductor | Non-HFTD | Transmission | 2024-07-24 | 2029-07-24 | Level 3 | F |  | 2029-07-24 | Level 3
129521022 | anchor/guy | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129521064 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129521546 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129521861 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
129521863 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129521870 | pole | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129522203 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129522540 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129523776 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129523878 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129524093 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129524768 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129524827 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129524910 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129524984 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129525042 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2024-12-12 | Level 2 | E |  | 2024-12-12 | Level 2
129525090 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129525098 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129525123 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129525134 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129525297 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129525307 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129525317 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129525345 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129525348 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129525551 | pole | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129525996 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526435 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129526440 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129526442 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129526458 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129526494 | pole | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129526520 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129526572 | insulator and brushing | Non-HFTD | Transmission | 2024-07-25 | 2027-07-25 | Level 2 | E |  | 2027-07-25 | Level 2
129526578 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526579 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526603 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129526619 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129526652 | crossarm | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129526662 | pole | Non-HFTD | Transmission | 2024-07-26 | 2025-07-26 | Level 2 | E |  | 2025-07-26 | Level 2
129526684 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129526717 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526740 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526762 | insulator and brushing | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129526800 | pole | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129526824 | insulator and brushing | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129526825 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129526870 | pole | Non-HFTD | Transmission | 2024-07-29 | 2025-01-29 | Level 2 | E |  | 2025-01-29 | Level 2
129526876 | pole | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129526887 | pole | Non-HFTD | Transmission | 2024-08-01 | 2027-08-01 | Level 2 | E |  | 2027-08-01 | Level 2
129526906 | other | Non-HFTD | Transmission | 2024-08-05 | 2029-08-05 | Level 3 | F |  | 2029-08-05 | Level 3
129526969 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526970 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129526978 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129527001 | pole | Non-HFTD | Transmission | 2024-08-02 | 2027-08-02 | Level 2 | E |  | 2027-08-02 | Level 2
129527008 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129527042 | other | Non-HFTD | Transmission | 2024-08-02 | 2029-08-02 | Level 3 | F |  | 2029-08-02 | Level 3
129527095 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129527105 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129528312 | anchor/guy | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129528412 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528415 | anchor/guy | Non-HFTD | Transmission | 2024-08-06 | 2025-08-06 | Level 2 | E |  | 2025-08-06 | Level 2
129528417 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129528482 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129528501 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528522 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129528530 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129528641 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129528645 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129528654 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528655 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528656 | insulator and brushing | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129528657 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528670 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528727 | anchor/guy | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528729 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129528760 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129528785 | pole | Non-HFTD | Transmission | 2024-09-11 | 2024-12-11 | Level 2 | E |  | 2024-12-11 | Level 2
129528837 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129528858 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129529110 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129529200 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F | 2024-10-16 | 2029-08-07 | Level 3 | GO 165 Inspection
129529207 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129529208 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129529209 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129529268 | other | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129529273 | pole | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129529307 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129529535 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129529683 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129529746 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129529773 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129529774 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129529778 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129529806 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530086 | pole | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129530372 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530378 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530434 | pole | Non-HFTD | Transmission | 2024-08-07 | 2027-08-07 | Level 2 | E |  | 2027-08-07 | Level 2
129530444 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129530560 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530584 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530615 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530776 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129530801 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129530869 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129530895 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129530927 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129530929 | pole | Non-HFTD | Transmission | 2024-08-08 | 2027-08-08 | Level 2 | E |  | 2027-08-08 | Level 2
129530935 | pole | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129530958 | pole | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129530964 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129530968 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129531001 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531006 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129531039 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129531063 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531175 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129531192 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129531195 | other | Non-HFTD | Transmission | 2024-09-12 | 2025-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129531256 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531270 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531273 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531279 | other | Non-HFTD | Transmission | 2024-08-07 | 2029-08-07 | Level 3 | F |  | 2029-08-07 | Level 3
129531366 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129531375 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531403 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531438 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129531447 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129531451 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531454 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531691 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531771 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129531791 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129531814 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129531844 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129531893 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129531949 | pole | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129531951 | other | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129531959 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129532051 | anchor/guy | Non-HFTD | Transmission | 2024-08-06 | 2029-08-06 | Level 3 | F |  | 2029-08-06 | Level 3
129532214 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129532302 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129532309 | insulator and brushing | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129532383 | insulator and brushing | Non-HFTD | Transmission | 2024-08-06 | 2027-08-06 | Level 2 | E |  | 2027-08-06 | Level 2
129532521 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129532760 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129532794 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129532823 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129532824 | pole | Non-HFTD | Transmission | 2024-08-09 | 2025-08-09 | Level 2 | E |  | 2025-08-09 | Level 2
129532827 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129532968 | other | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129532980 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2025-09-12 | Level 2 | E |  | 2025-09-12 | Level 2
129532981 | other | Non-HFTD | Transmission | 2024-09-08 | 2029-09-08 | Level 3 | F |  | 2029-09-08 | Level 3
129532982 | pole | Non-HFTD | Transmission | 2024-09-08 | 2027-09-08 | Level 2 | E |  | 2027-09-08 | Level 2
129532996 | switch | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129532999 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129533006 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2025-09-13 | Level 2 | E |  | 2025-09-13 | Level 2
129533047 | insulator and brushing | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129533067 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129533158 | insulator and brushing | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129533161 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129533180 | other | Non-HFTD | Transmission | 2024-08-08 | 2029-08-08 | Level 3 | F |  | 2029-08-08 | Level 3
129533206 | insulator and brushing | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129533262 | anchor/guy | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129533264 | anchor/guy | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129533304 | conductor | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129533320 | pole | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129533385 | anchor/guy | Non-HFTD | Transmission | 2024-08-09 | 2025-08-09 | Level 2 | E |  | 2025-08-09 | Level 2
129533785 | anchor/guy | HFTD Tier 2 | Transmission | 2024-09-14 | 2025-09-14 | Level 2 | E |  | 2025-09-14 | Level 2
129534164 | pole | Non-HFTD | Transmission | 2024-09-14 | 2027-09-14 | Level 2 | E |  | 2027-09-14 | Level 2
129534298 | insulator and brushing | Non-HFTD | Transmission | 2024-09-14 | 2029-09-14 | Level 3 | F |  | 2029-09-14 | Level 3
129534312 | insulator and brushing | Non-HFTD | Transmission | 2024-09-14 | 2027-09-14 | Level 2 | E |  | 2027-09-14 | Level 2
129534697 | anchor/guy | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129534744 | anchor/guy | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129534754 | insulator and brushing | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129534849 | other | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129534853 | anchor/guy | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129534872 | other | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129534929 | pole | Non-HFTD | Transmission | 2024-09-15 | 2027-09-15 | Level 2 | E |  | 2027-09-15 | Level 2
129534959 | anchor/guy | Non-HFTD | Transmission | 2024-09-15 | 2027-09-15 | Level 2 | E |  | 2025-09-15 | Level 2
129534988 | insulator and brushing | Non-HFTD | Transmission | 2024-09-15 | 2025-09-15 | Level 2 | E |  | 2025-09-15 | Level 2
129535801 | insulator and brushing | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129535804 | insulator and brushing | Non-HFTD | Transmission | 2024-09-15 | 2029-09-15 | Level 3 | F |  | 2029-09-15 | Level 3
129536193 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129536219 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129536629 | pole | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129537510 | anchor/guy | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129537511 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129537878 | other | Non-HFTD | Transmission | 2024-08-01 | 2029-08-01 | Level 3 | F |  | 2029-08-01 | Level 3
129539228 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129539229 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129539337 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129539338 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129539402 | other | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129539558 | other | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129539865 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129540123 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129540285 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129540290 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129540405 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129540463 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129540544 | other | Non-HFTD | Transmission | 2024-08-12 | 2025-02-12 | Level 2 | E |  | 2025-02-12 | Level 2
129540570 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129540709 | pole | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129540803 | other | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E | 2024-10-16 | 2027-08-13 | Level 2 | GO 165 Inspection
129540816 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129540817 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129540857 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129540869 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129540897 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129540936 | insulator and brushing | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129540967 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541001 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129541013 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541021 | pole | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129541061 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541068 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541084 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129541092 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541115 | anchor/guy | Non-HFTD | Transmission | 2024-08-09 | 2027-08-09 | Level 2 | E |  | 2027-08-09 | Level 2
129541122 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541123 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129541147 | insulator and brushing | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129541188 | pole | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129541232 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129541251 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129541280 | insulator and brushing | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E | 2024-10-16 | 2027-08-12 | Level 2 | GO 165 Inspection
129541289 | pole | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129541295 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129541331 | insulator and brushing | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129541339 | insulator and brushing | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129541380 | anchor/guy | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129541393 | pole | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129541402 | other | Non-HFTD | Transmission | 2024-08-09 | 2029-08-09 | Level 3 | F |  | 2029-08-09 | Level 3
129541407 | other | Non-HFTD | Transmission | 2024-08-12 | 2029-08-12 | Level 3 | F |  | 2029-08-12 | Level 3
129541409 | other | Non-HFTD | Transmission | 2024-08-09 | 2025-08-09 | Level 2 | E |  | 2025-08-09 | Level 2
129541426 | insulator and brushing | Non-HFTD | Transmission | 2024-08-09 | 2025-08-09 | Level 2 | E |  | 2025-08-09 | Level 2
129541451 | insulator and brushing | Non-HFTD | Transmission | 2024-08-13 | 2027-08-13 | Level 2 | E |  | 2027-08-13 | Level 2
129542338 | switch | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129543264 | other | Non-HFTD | Transmission | 2024-09-17 | 2024-12-17 | Level 2 | E |  | 2027-09-17 | Level 2
129543617 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129543680 | anchor/guy | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129544009 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129544200 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129544255 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129544981 | other | HFTD Tier 2 | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129544984 | other | HFTD Tier 2 | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129545003 | pole | Non-HFTD | Transmission | 2024-08-15 | 2025-02-15 | Level 2 | E |  | 2025-02-15 | Level 2
129545100 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129545118 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129545136 | insulator and brushing | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129545219 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F | 2024-10-22 | 2029-09-17 | Level 3 | GO 165 Inspection
129545442 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F | 2024-10-22 | 2029-09-17 | Level 3 | GO 165 Inspection
129545483 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129545668 | insulator and brushing | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129545716 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129545896 | pole | Non-HFTD | Transmission | 2024-09-16 | 2025-09-16 | Level 2 | E |  | 2025-09-16 | Level 2
129546179 | insulator and brushing | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129546207 | other | Non-HFTD | Transmission | 2024-09-17 | 2024-12-17 | Level 2 | E |  | 2024-12-17 | Level 2
129546218 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129546289 | pole | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129546358 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129546383 | pole | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129546388 | pole | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129546405 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129546407 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129546445 | other | Non-HFTD | Transmission | 2024-09-10 | 2024-12-10 | Level 2 | E |  | 2025-09-10 | Level 2
129546544 | anchor/guy | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129546672 | pole | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129546694 | anchor/guy | Non-HFTD | Transmission | 2024-08-15 | 2025-08-15 | Level 2 | E |  | 2025-08-15 | Level 2
129546749 | other | Non-HFTD | Transmission | 2024-08-13 | 2024-11-13 | Level 2 | E |  | 2024-11-13 | Level 2
129546771 | pole | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129546801 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129546893 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129546903 | other | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129546911 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129548851 | crossarm | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129548892 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129548895 | anchor/guy | Non-HFTD | Transmission | 2024-09-17 | 2025-03-17 | Level 2 | E |  | 2025-03-17 | Level 2
129548974 | pole | Non-HFTD | Transmission | 2024-08-12 | 2027-08-12 | Level 2 | E |  | 2027-08-12 | Level 2
129549441 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129549452 | insulator and brushing | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129549480 | pole | Non-HFTD | Transmission | 2024-09-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
129549672 | other | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129549821 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129550014 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129550317 | insulator and brushing | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129550322 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129550328 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129550418 | insulator and brushing | Non-HFTD | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | E |  | 2025-09-18 | Level 2
129550802 | anchor/guy | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129551300 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129551347 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129551444 | pole | Non-HFTD | Transmission | 2024-08-27 | 2025-08-27 | Level 2 | E | 2024-10-09 | 2025-08-27 | Level 2 | GO 165 Inspection
129551489 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129551533 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129551571 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129551754 | anchor/guy | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129551778 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129552047 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129552326 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129552327 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129552331 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129552335 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129552341 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129552690 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129552727 | other | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129552754 | other | Non-HFTD | Transmission | 2024-09-17 | 2024-12-17 | Level 2 | E |  | 2025-09-17 | Level 2
129552794 | pole | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129552819 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129552875 | other | Non-HFTD | Transmission | 2024-08-13 | 2029-08-13 | Level 3 | F |  | 2029-08-13 | Level 3
129552876 | pole | Non-HFTD | Transmission | 2024-08-14 | 2029-08-14 | Level 3 | F |  | 2029-08-14 | Level 3
129552988 | pole | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129553040 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129553178 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129553213 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129553520 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F | 2024-10-26 | 2029-08-16 | Level 3 | GO 165 Inspection
129553555 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129553834 | anchor/guy | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F | 2024-11-14 | 2029-08-16 | Level 3 | GO 165 Inspection
129554013 | other | Non-HFTD | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | E |  | 2025-09-18 | Level 2
129554037 | pole | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129554045 | anchor/guy | Non-HFTD | Transmission | 2024-08-14 | 2025-08-14 | Level 2 | E |  | 2025-08-14 | Level 2
129554064 | pole | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129554076 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129554080 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129554096 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129554102 | other | Non-HFTD | Transmission | 2024-08-14 | 2024-11-14 | Level 2 | E |  | 2024-11-14 | Level 2
129554119 | pole | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129554127 | pole | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129554128 | pole | Non-HFTD | Transmission | 2024-08-16 | 2027-08-16 | Level 2 | E |  | 2027-08-16 | Level 2
129554137 | pole | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129554144 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129554156 | other | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129554161 | other | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129554167 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129554173 | pole | Non-HFTD | Transmission | 2024-09-18 | 2025-03-18 | Level 2 | E |  | 2025-03-18 | Level 2
129554192 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129554195 | anchor/guy | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129554201 | other | Non-HFTD | Transmission | 2024-08-19 | 2029-08-19 | Level 3 | F |  | 2029-08-19 | Level 3
129554269 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129554287 | insulator and brushing | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129554289 | crossarm | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129554317 | other | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129554370 | pole | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129554373 | pole | Non-HFTD | Transmission | 2024-08-15 | 2029-08-15 | Level 3 | F |  | 2029-08-15 | Level 3
129554376 | anchor/guy | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E | 2024-10-15 | 2027-08-15 | Level 2 | GO 165 Inspection
129557063 | insulator and brushing | Non-HFTD | Transmission | 2024-08-14 | 2027-08-14 | Level 2 | E |  | 2027-08-14 | Level 2
129557226 | pole | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129557649 | anchor/guy | Non-HFTD | Transmission | 2024-09-11 | 2025-03-11 | Level 2 | E |  | 2025-03-11 | Level 2
129557842 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129557847 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558026 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129558056 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558141 | insulator and brushing | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129558444 | anchor/guy | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E | 2024-10-15 | 2025-08-20 | Level 2 | GO 165 Inspection
129558544 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558577 | anchor/guy | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129558605 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558607 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129558626 | pole | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129558627 | insulator and brushing | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129558637 | other | Non-HFTD | Transmission | 2024-08-15 | 2027-08-15 | Level 2 | E |  | 2027-08-15 | Level 2
129558660 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558713 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558728 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129558729 | other | Non-HFTD | Transmission | 2024-08-19 | 2027-08-19 | Level 2 | E |  | 2027-08-19 | Level 2
129558731 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129558766 | other | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129558812 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129558876 | anchor/guy | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129558996 | insulator and brushing | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129559018 | other | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129559019 | other | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129559024 | other | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 2 | E |  | 2025-08-20 | Level 2
129559025 | pole | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129559032 | anchor/guy | Non-HFTD | Transmission | 2024-08-16 | 2029-08-16 | Level 3 | F |  | 2029-08-16 | Level 3
129559064 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129559078 | pole | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129559210 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129559214 | other | Non-HFTD | Transmission | 2024-08-20 | 2027-08-20 | Level 2 | E |  | 2027-08-20 | Level 2
129559820 | pole | Non-HFTD | Transmission | 2024-08-19 | 2025-02-19 | Level 2 | E |  | 2025-02-19 | Level 2
129561768 | other | Non-HFTD | Transmission | 2024-08-21 | 2025-08-21 | Level 2 | E |  | 2025-08-21 | Level 2
129561850 | conductor | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E |  | 2027-09-20 | Level 2
129561882 | insulator and brushing | Non-HFTD | Transmission | 2024-08-21 | 2027-08-21 | Level 2 | E |  | 2027-08-21 | Level 2
129561931 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F | 2024-11-08 | 2029-08-20 | Level 3 | GO 165 Inspection
129562134 | pole | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129562140 | pole | Non-HFTD | Transmission | 2024-08-20 | 2029-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129563543 | pole | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E |  | 2027-09-20 | Level 2
129563594 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129563976 | insulator and brushing | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E |  | 2027-09-20 | Level 2
129564281 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129564682 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129566329 | other | Non-HFTD | Transmission | 2024-09-21 | 2029-09-21 | Level 3 | F |  | 2029-09-21 | Level 3
129566662 | other | Non-HFTD | Transmission | 2024-09-21 | 2029-09-21 | Level 3 | F |  | 2029-09-21 | Level 3
129572248 | pole | Non-HFTD | Transmission | 2024-09-23 | 2025-09-23 | Level 2 | E | 2024-10-28 | 2025-09-23 | Level 2 | GO 165 Inspection
129572594 | pole | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129573375 | insulator and brushing | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129573932 | insulator and brushing | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129574181 | other | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129574182 | insulator and brushing | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129574622 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-09-23 | 2025-09-23 | Level 2 | E |  | 2025-09-23 | Level 2
129574695 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2025-08-22 | Level 2 | E |  | 2025-08-22 | Level 2
129574698 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129574776 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129574784 | pole | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129574844 | pole | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129574931 | insulator and brushing | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129574989 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575177 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129575186 | pole | HFTD Tier 3 | Transmission | 2024-09-23 | 2025-03-23 | Level 2 | E |  | 2025-03-23 | Level 2
129575245 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575307 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575384 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575405 | other | Non-HFTD | Transmission | 2024-08-20 | 2025-08-20 | Level 3 | F |  | 2029-08-20 | Level 3
129575437 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575474 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575480 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575504 | pole | Non-HFTD | Transmission | 2024-08-21 | 2029-08-21 | Level 3 | F |  | 2029-08-21 | Level 3
129575507 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575523 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575525 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575578 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575620 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575625 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575641 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575672 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575676 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575710 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575750 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129575819 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129575837 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575846 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575852 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575853 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129575862 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575865 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575869 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129575874 | other | Non-HFTD | Transmission | 2024-08-21 | 2025-08-21 | Level 2 | E |  | 2025-08-21 | Level 2
129575883 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129575890 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575896 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575902 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129575904 | switch | Non-HFTD | Transmission | 2024-09-19 | 2024-12-19 | Level 2 | E | 2024-10-15 | 2024-12-19 | Level 2 | GO 165 Inspection
129575905 | other | Non-HFTD | Transmission | 2024-09-19 | 2025-09-19 | Level 2 | E | 2024-10-15 | 2025-09-19 | Level 2 | GO 165 Inspection
129575941 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129575949 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129576022 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129576023 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129576030 | pole | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129577974 | pole | HFTD Tier 2 | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129578603 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129578886 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129579219 | conductor | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129579793 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129579812 | insulator and brushing | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129580309 | other | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129580425 | other | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129580449 | pole | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129580528 | anchor/guy | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129580564 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129580787 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581047 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129581075 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581085 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581088 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129581095 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129581099 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581118 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581126 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581134 | pole | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129581176 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581223 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581232 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129581247 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129581248 | other | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129581285 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E | 2024-10-09 | 2027-08-28 | Level 2 | GO 165 Inspection
129581298 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581310 | anchor/guy | Non-HFTD | Transmission | 2024-08-22 | 2029-08-22 | Level 3 | F |  | 2029-08-22 | Level 3
129581348 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581411 | insulator and brushing | Non-HFTD | Transmission | 2024-08-22 | 2027-08-22 | Level 2 | E |  | 2027-08-22 | Level 2
129581440 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581444 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581447 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129581463 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581481 | pole | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581506 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581508 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129581543 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129581650 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581713 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129581717 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129581720 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581721 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129581789 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129581906 | pole | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129581954 | pole | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129581978 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129582011 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2025-02-27 | Level 2 | E |  | 2025-02-27 | Level 2
129582016 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129582020 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129582094 | pole | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129582095 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129582178 | other | Non-HFTD | Transmission | 2024-08-23 | 2029-08-23 | Level 3 | F |  | 2029-08-23 | Level 3
129582255 | insulator and brushing | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129582495 | pole | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129583763 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129583764 | insulator and brushing | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129583773 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129584688 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129584778 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129585793 | anchor/guy | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129585797 | anchor/guy | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129586133 | anchor/guy | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129586137 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129586763 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129586812 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587228 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129587279 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587288 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129587313 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587359 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587439 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587460 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587464 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587473 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129587482 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587565 | other | Non-HFTD | Transmission | 2024-09-25 | 2025-09-25 | Level 2 | E |  | 2025-09-25 | Level 2
129587675 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129587741 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2025-09-25 | Level 2 | E |  | 2025-09-25 | Level 2
129588000 | pole | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129588014 | other | Non-HFTD | Transmission | 2024-08-29 | 2025-08-29 | Level 2 | E |  | 2025-08-29 | Level 2
129588026 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129588048 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129588067 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129588093 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129588140 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129588146 | pole | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129588228 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129588231 | other | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129588241 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129588247 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129588291 | other | Non-HFTD | Transmission | 2024-08-27 | 2027-08-27 | Level 2 | E |  | 2027-08-27 | Level 2
129588313 | pole | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129588325 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129588378 | other | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129588393 | pole | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129588395 | insulator and brushing | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129588398 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129588421 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129588434 | insulator and brushing | Non-HFTD | Transmission | 2024-08-26 | 2027-08-26 | Level 2 | E |  | 2027-08-26 | Level 2
129588481 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129588503 | pole | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129588509 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129588522 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129590963 | insulator and brushing | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129591017 | anchor/guy | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129591094 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129591230 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129591454 | other | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129591620 | insulator and brushing | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129592236 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129592462 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129592483 | insulator and brushing | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129592742 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129592834 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129592846 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129592866 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129592872 | other | Non-HFTD | Transmission | 2024-09-26 | 2027-09-29 | Level 3 | F |  | 2029-09-26 | Level 3
129592877 | insulator and brushing | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129593344 | pole | Non-HFTD | Transmission | 2024-08-31 | 2025-03-03 | Level 2 | E |  | 2025-03-03 | Level 2
129593412 | insulator and brushing | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129593442 | other | Non-HFTD | Transmission | 2024-09-26 | 2024-12-26 | Level 2 | E |  | 2024-12-26 | Level 2
129593470 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129593536 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129593560 | pole | Non-HFTD | Transmission | 2024-08-29 | 2025-08-29 | Level 2 | E |  | 2025-08-29 | Level 2
129593638 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129593643 | switch | Non-HFTD | Transmission | 2024-09-26 | 2025-03-26 | Level 2 | E |  | 2025-03-26 | Level 2
129593880 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129593924 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129593925 | pole | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129593926 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129593938 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129593944 | other | Non-HFTD | Transmission | 2024-08-26 | 2029-08-26 | Level 3 | F |  | 2029-08-26 | Level 3
129594086 | insulator and brushing | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129594087 | anchor/guy | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129594147 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129594191 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129594193 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129594270 | conductor | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129594320 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129594330 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129594353 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129594356 | insulator and brushing | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129594367 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129594376 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2024-12-25 | Level 2 | E |  | 2024-12-25 | Level 2
129594380 | insulator and brushing | Non-HFTD | Transmission | 2024-08-23 | 2027-08-23 | Level 2 | E |  | 2027-08-23 | Level 2
129594384 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129594390 | anchor/guy | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129594391 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129594416 | pole | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129594428 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129596271 | pole | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129596274 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129596309 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129596341 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129596350 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129596361 | other | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129596362 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129596369 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2024-12-25 | Level 2 | E |  | 2024-12-25 | Level 2
129596502 | anchor/guy | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129596592 | pole | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129596609 | other | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129596655 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129596671 | other | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129596862 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129596898 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129596954 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129596963 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129597070 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129597075 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129597159 | pole | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129597306 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129597429 | other | HFTD Tier 2 | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129597507 | pole | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129597566 | pole | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129597590 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129597673 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129597772 | other | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129597821 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129597880 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129597921 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129598035 | anchor/guy | Non-HFTD | Transmission | 2024-08-30 | 2025-08-30 | Level 2 | E |  | 2025-08-30 | Level 2
129598067 | other | Non-HFTD | Transmission | 2024-08-30 | 2025-08-30 | Level 2 | E |  | 2025-08-30 | Level 2
129598156 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129598241 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F | 2024-10-11 | 2029-09-03 | Level 3 | GO 165 Inspection
129598342 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129598489 | other | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129598670 | insulator and brushing | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129598799 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129598832 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129598842 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129598873 | pole | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129599144 | other | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129599295 | pole | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129599325 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129599336 | insulator and brushing | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129599345 | insulator and brushing | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129599387 | pole | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129599544 | anchor/guy | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129599585 | insulator and brushing | Non-HFTD | Transmission | 2024-08-30 | 2025-08-30 | Level 2 | E |  | 2025-08-30 | Level 2
129599587 | other | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129599629 | anchor/guy | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129599638 | pole | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129599805 | other | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129599945 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129600581 | pole | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129601817 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129601943 | other | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129601953 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2024-12-26 | Level 2 | E |  | 2024-12-05 | Level 2
129601962 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129601987 | other | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129601990 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129601999 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129602031 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129602039 | pole | Non-HFTD | Transmission | 2024-09-27 | 2025-09-27 | Level 2 | E |  | 2025-09-27 | Level 2
129602128 | other | Non-HFTD | Transmission | 2024-09-27 | 2025-09-27 | Level 2 | E |  | 2025-09-27 | Level 2
129602284 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129602327 | pole | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129602366 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129602372 | pole | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129602422 | conductor | Non-HFTD | Transmission | 2024-08-30 | 2027-08-30 | Level 2 | E |  | 2027-08-30 | Level 2
129602428 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129602429 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129602471 | pole | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129602472 | other | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129602501 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129602502 | other | Non-HFTD | Transmission | 2024-09-09 | 2025-09-09 | Level 2 | E |  | 2025-09-09 | Level 2
129602504 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129602542 | pole | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129602556 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129602795 | pole | Non-HFTD | Transmission | 2024-09-03 | 2025-03-03 | Level 2 | E |  | 2025-03-03 | Level 2
129602796 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129602797 | pole | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129603003 | insulator and brushing | Non-HFTD | Transmission | 2024-09-28 | 2027-09-28 | Level 2 | E | 2024-11-18 | 2027-09-28 | Level 2 | GO 165 Inspection
129603005 | switch | Non-HFTD | Transmission | 2024-09-27 | 2025-09-27 | Level 2 | E |  | 2025-09-27 | Level 2
129603080 | other | Non-HFTD | Transmission | 2024-08-27 | 2029-08-27 | Level 3 | F |  | 2029-08-27 | Level 3
129603487 | insulator and brushing | Non-HFTD | Transmission | 2024-09-29 | 2027-09-29 | Level 2 | E |  | 2027-09-29 | Level 2
129604109 | insulator and brushing | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129604341 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129604342 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129604377 | other | Non-HFTD | Transmission | 2024-09-30 | 2027-09-30 | Level 2 | E |  | 2027-09-30 | Level 2
129604383 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129604619 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2025-03-30 | Level 2 | E |  | 2025-03-30 | Level 2
129604656 | pole | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129604657 | crossarm | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129604665 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129604929 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129605377 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129605529 | insulator and brushing | Non-HFTD | Transmission | 2024-09-30 | 2024-12-30 | Level 2 | E |  | 2024-12-30 | Level 2
129605609 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129605694 | other | HFTD Tier 3 | Transmission | 2024-09-30 | 2025-03-30 | Level 2 | E |  | 2025-03-30 | Level 2
129605779 | insulator and brushing | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129605947 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 2 | E |  | 2027-09-30 | Level 2
129606120 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2025-03-30 | Level 2 | E |  | 2025-03-30 | Level 2
129606268 | conductor | Non-HFTD | Transmission | 2024-09-30 | 2025-03-30 | Level 2 | E |  | 2025-03-30 | Level 2
129606922 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129607338 | other | Non-HFTD | Transmission | 2024-09-30 | 2027-09-30 | Level 2 | E |  | 2027-09-30 | Level 2
129607344 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129607346 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129607362 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129607407 | other | Non-HFTD | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129607564 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129607768 | switch | HFTD Tier 2 | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129607937 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129607979 | other | HFTD Tier 2 | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129608159 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129608171 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129608172 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129608263 | pole | HFTD Tier 2 | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129608269 | pole | Non-HFTD | Transmission | 2024-09-30 | 2027-09-30 | Level 2 | E |  | 2027-09-30 | Level 2
129608284 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129608318 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129608319 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2027-08-28 | Level 2 | E |  | 2027-08-28 | Level 2
129608329 | insulator and brushing | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129608353 | other | HFTD Tier 2 | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129608379 | insulator and brushing | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129608463 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129608480 | crossarm | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129608490 | insulator and brushing | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129608555 | other | Non-HFTD | Transmission | 2024-08-28 | 2029-08-28 | Level 3 | F |  | 2029-08-28 | Level 3
129608557 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129608565 | insulator and brushing | Non-HFTD | Transmission | 2024-08-28 | 2025-08-28 | Level 2 | E |  | 2025-08-28 | Level 2
129608569 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129608596 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129608605 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129608644 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129608702 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129609561 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129610201 | other | Non-HFTD | Transmission | 2024-09-30 | 2025-03-30 | Level 2 | E |  | 2025-03-30 | Level 2
129610475 | pole | HFTD Tier 2 | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129610777 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129610978 | other | HFTD Tier 2 | Transmission | 2023-11-02 | 2025-02-02 | Level 2 | E |  | 2024-11-02 | Level 2
129611591 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129612154 | pole | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129612163 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129612194 | anchor/guy | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129612238 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129612350 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129612520 | anchor/guy | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129612954 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129612956 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129612971 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129612982 | other | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129613073 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129613282 | anchor/guy | Non-HFTD | Transmission | 2024-10-01 | 2025-04-01 | Level 2 | E |  | 2025-04-01 | Level 2
129613517 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129613589 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129613626 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129613799 | anchor/guy | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129613870 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129613873 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129613879 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129613943 | other | Non-HFTD | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129613959 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129614005 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129614091 | other | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129614096 | other | HFTD Tier 2 | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129614123 | pole | Non-HFTD | Transmission | 2024-05-23 | 2029-05-23 | Level 3 | F |  | 2029-05-23 | Level 3
129614125 | pole | Non-HFTD | Transmission | 2024-06-05 | 2029-06-05 | Level 3 | F |  | 2029-06-05 | Level 3
129614129 | other | Non-HFTD | Transmission | 2024-07-23 | 2027-07-23 | Level 2 | E |  | 2027-07-23 | Level 2
129614136 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129614145 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129614175 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129614176 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129614177 | splice | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129614184 | pole | HFTD Tier 2 | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129614191 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129614199 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129614216 | pole | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129614223 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129614228 | pole | HFTD Tier 2 | Transmission | 2024-09-27 | 2025-09-27 | Level 2 | E |  | 2025-09-27 | Level 2
129614289 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129614316 | pole | HFTD Tier 2 | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129614341 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129614344 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129614379 | pole | Non-HFTD | Transmission | 2024-06-28 | 2027-06-28 | Level 2 | E |  | 2027-06-28 | Level 2
129614380 | other | HFTD Tier 2 | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129614381 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129614400 | anchor/guy | Non-HFTD | Transmission | 2024-08-29 | 2029-08-29 | Level 3 | F |  | 2029-08-29 | Level 3
129614479 | pole | Non-HFTD | Transmission | 2024-07-16 | 2029-07-16 | Level 3 | F |  | 2029-07-16 | Level 3
129614505 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129614529 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129614588 | anchor/guy | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129614595 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129614596 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2025-09-03 | Level 2 | E |  | 2025-09-03 | Level 2
129614623 | conductor | HFTD Tier 2 | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129614627 | pole | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129614648 | anchor/guy | Non-HFTD | Transmission | 2024-09-06 | 2025-03-06 | Level 2 | E |  | 2025-03-06 | Level 2
129614655 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129614662 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129614704 | pole | Non-HFTD | Transmission | 2024-05-23 | 2027-05-23 | Level 2 | E |  | 2027-05-23 | Level 2
129614707 | pole | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129614756 | pole | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129614770 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129614788 | pole | Non-HFTD | Transmission | 2024-06-18 | 2029-06-18 | Level 3 | F |  | 2029-06-18 | Level 3
129614806 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129614850 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129614851 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129614852 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129614853 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129614859 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129614876 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129614880 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129614882 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129614895 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129614976 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129614977 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129614978 | pole | Non-HFTD | Transmission | 2024-06-11 | 2029-06-11 | Level 3 | F |  | 2029-06-11 | Level 3
129614986 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129615004 | other | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129615006 | pole | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129615007 | pole | Non-HFTD | Transmission | 2024-06-17 | 2029-06-17 | Level 3 | F |  | 2029-06-17 | Level 3
129615013 | anchor/guy | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129615035 | pole | Non-HFTD | Transmission | 2024-06-13 | 2029-06-13 | Level 3 | F |  | 2029-06-13 | Level 3
129615040 | pole | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129615055 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129615056 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129615057 | other | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129615084 | other | Non-HFTD | Transmission | 2024-08-30 | 2029-08-30 | Level 3 | F |  | 2029-08-30 | Level 3
129617201 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129617350 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129617464 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129618031 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129618272 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129619559 | pole | Non-HFTD | Transmission | 2024-10-02 | 2025-10-02 | Level 2 | E |  | 2025-10-02 | Level 2
129619883 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129620082 | other | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129620115 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129621153 | anchor/guy | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129621155 | other | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129621379 | anchor/guy | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129621457 | other | Non-HFTD | Transmission | 2024-10-02 | 2025-01-02 | Level 2 | E |  | 2025-01-02 | Level 2
129621577 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129621627 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129621696 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129621709 | insulator and brushing | Non-HFTD | Transmission | 2024-08-29 | 2027-08-29 | Level 2 | E |  | 2027-08-29 | Level 2
129621786 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129621795 | pole | Non-HFTD | Transmission | 2024-05-29 | 2029-05-29 | Level 3 | F |  | 2029-05-29 | Level 3
129621844 | pole | Non-HFTD | Transmission | 2024-06-10 | 2027-06-10 | Level 2 | E |  | 2027-06-10 | Level 2
129621849 | other | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129621853 | anchor/guy | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129621855 | pole | Non-HFTD | Transmission | 2024-08-31 | 2027-08-31 | Level 2 | E |  | 2027-08-31 | Level 2
129621858 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129621871 | pole | Non-HFTD | Transmission | 2024-06-10 | 2029-06-10 | Level 3 | F |  | 2029-06-10 | Level 3
129621890 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129621891 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129621896 | other | Non-HFTD | Transmission | 2024-09-04 | 2025-09-04 | Level 2 | E |  | 2025-09-04 | Level 2
129621897 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129621944 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129621945 | pole | Non-HFTD | Transmission | 2024-06-20 | 2029-06-20 | Level 3 | F |  | 2029-06-20 | Level 3
129621998 | other | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129622001 | switch | Non-HFTD | Transmission | 2024-09-04 | 2025-03-04 | Level 2 | E |  | 2025-03-04 | Level 2
129622004 | pole | Non-HFTD | Transmission | 2024-06-26 | 2029-06-26 | Level 3 | F |  | 2029-06-26 | Level 3
129622034 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129622071 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129622077 | other | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129622099 | pole | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129622117 | other | Non-HFTD | Transmission | 2024-06-27 | 2029-06-27 | Level 3 | F |  | 2029-06-27 | Level 3
129622132 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129622134 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129622195 | pole | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129622198 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129622219 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129622236 | pole | Non-HFTD | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129622238 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129622247 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129622252 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129622271 | pole | Non-HFTD | Transmission | 2024-06-04 | 2029-06-04 | Level 3 | F |  | 2029-06-04 | Level 3
129622274 | pole | Non-HFTD | Transmission | 2024-06-12 | 2029-06-12 | Level 3 | F |  | 2029-06-12 | Level 3
129622277 | other | Non-HFTD | Transmission | 2024-06-11 | 2027-06-11 | Level 2 | E |  | 2027-06-11 | Level 2
129622319 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129622344 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129622364 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129622376 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129622379 | switch | Non-HFTD | Transmission | 2024-09-04 | 2025-09-04 | Level 2 | E |  | 2025-09-04 | Level 2
129622389 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129622403 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129622415 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129622418 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129622427 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129622428 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129622438 | anchor/guy | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129622455 | anchor/guy | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129624455 | pole | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129625253 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129625536 | anchor/guy | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129625664 | other | HFTD Tier 3 | Transmission | 2023-06-07 | 2023-12-07 | Level 2 | E |  | 2023-12-07 | Level 2
129625960 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129626304 | pole | HFTD Tier 2 | Transmission | 2024-08-26 | 2025-08-26 | Level 2 | E |  | 2025-08-26 | Level 2
129626432 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129626464 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129626540 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129626648 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129627369 | other | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129627614 | other | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129627654 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129628214 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129628215 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129628255 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129628262 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129628505 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129628508 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129628625 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129628626 | pole | Non-HFTD | Transmission | 2024-08-05 | 2027-08-05 | Level 2 | E |  | 2027-08-05 | Level 2
129628671 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129628678 | other | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129628729 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129628764 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129628769 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129628832 | other | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129628947 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129628971 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129628974 | other | Non-HFTD | Transmission | 2024-07-15 | 2029-07-15 | Level 3 | F |  | 2029-07-15 | Level 3
129629004 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129629026 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129629034 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129629055 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129629082 | other | Non-HFTD | Transmission | 2024-09-05 | 2029-09-05 | Level 3 | F |  | 2029-09-05 | Level 3
129629088 | other | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129629144 | other | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129629151 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129629160 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2025-09-05 | Level 2 | E |  | 2025-09-05 | Level 2
129629164 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129629230 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129629236 | other | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129629323 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129629348 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2024-12-06 | Level 2 | E |  | 2024-12-06 | Level 2
129629362 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129629372 | insulator and brushing | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129629378 | other | Non-HFTD | Transmission | 2024-08-31 | 2029-08-31 | Level 3 | F |  | 2029-08-31 | Level 3
129629388 | pole | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129629399 | pole | Non-HFTD | Transmission | 2024-09-04 | 2027-09-04 | Level 2 | E |  | 2027-09-04 | Level 2
129629445 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129629691 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129629697 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129629922 | other | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129630157 | anchor/guy | Non-HFTD | Transmission | 2024-09-10 | 2029-09-10 | Level 3 | F |  | 2029-09-10 | Level 3
129630321 | pole | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129631979 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129632046 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129632104 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129632106 | other | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129632107 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129632121 | other | Non-HFTD | Transmission | 2024-09-10 | 2025-09-10 | Level 2 | E |  | 2025-09-10 | Level 2
129632185 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129632240 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-09-10 | 2025-09-10 | Level 2 | E |  | 2025-09-10 | Level 2
129632244 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129632262 | pole | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129632279 | other | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129632385 | pole | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129632432 | insulator and brushing | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129632449 | pole | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129632539 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129632689 | other | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129632697 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129632752 | other | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129632757 | pole | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129632884 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129632994 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129633053 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129633123 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129633124 | pole | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129633128 | insulator and brushing | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129633288 | insulator and brushing | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129633291 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129633340 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129633353 | other | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129633378 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129633432 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129633764 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129633792 | pole | Non-HFTD | Transmission | 2024-09-17 | 2025-03-17 | Level 2 | E |  | 2025-03-17 | Level 2
129633808 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129634067 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129634153 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129634199 | other | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129634312 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129634470 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129634488 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129634497 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129634555 | pole | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129634561 | anchor/guy | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129634635 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129634641 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129634699 | anchor/guy | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129634703 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F | 2024-11-30 | 2029-09-11 | Level 3 | GO 165 Inspection
129634801 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129634809 | pole | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129634818 | crossarm | Non-HFTD | Transmission | 2024-10-04 | 2025-10-04 | Level 2 | E |  | 2025-10-04 | Level 2
129634871 | anchor/guy | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129634879 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129635012 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129635224 | crossarm | Non-HFTD | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129635279 | pole | Non-HFTD | Transmission | 2024-09-09 | 2029-09-09 | Level 3 | F |  | 2029-09-09 | Level 3
129635316 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129635329 | anchor/guy | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635344 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635346 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635413 | other | Non-HFTD | Transmission | 2024-09-12 | 2024-12-12 | Level 2 | E | 2024-12-12 | 2024-12-12 | Level 2 | Field Safety Reassessment
129635418 | other | Non-HFTD | Transmission | 2024-09-12 | 2024-12-12 | Level 2 | E | 2024-12-12 | 2024-12-12 | Level 2 | Field Safety Reassessment
129635467 | pole | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129635532 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129635654 | other | Non-HFTD | Transmission | 2024-09-12 | 2024-12-12 | Level 2 | E |  | 2024-12-12 | Level 2
129635663 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2025-01-02 | Level 2 | E |  | 2025-01-02 | Level 2
129635701 | other | Non-HFTD | Transmission | 2024-09-12 | 2024-12-12 | Level 2 | E |  | 2024-12-12 | Level 2
129635748 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129635757 | conductor | Non-HFTD | Transmission | 2024-10-04 | 2025-01-04 | Level 2 | E | 2024-12-24 | 2025-01-04 | Level 2 | Field Safety Reassessment
129635795 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635799 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635808 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635813 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635817 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129635831 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129636028 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129636223 | anchor/guy | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129636430 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129636431 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129636464 | other | Non-HFTD | Transmission | 2024-09-06 | 2024-12-06 | Level 2 | E | 2024-10-24 | 2024-12-06 | Level 2 | GO 165 Inspection
129636477 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129636537 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129636574 | pole | Non-HFTD | Transmission | 2024-09-05 | 2027-09-05 | Level 2 | E |  | 2027-09-05 | Level 2
129636604 | insulator and brushing | Non-HFTD | Transmission | 2024-09-09 | 2027-09-09 | Level 2 | E |  | 2027-09-09 | Level 2
129636609 | other | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129636620 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129638124 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129638151 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129638186 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129638189 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129638197 | other | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129638227 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2025-03-16 | Level 2 | E |  | 2025-03-16 | Level 2
129638232 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129638234 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129638287 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129638311 | other | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129638321 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129638323 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129638342 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129638344 | pole | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129638348 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129638385 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129638386 | pole | Non-HFTD | Transmission | 2024-09-17 | 2024-12-17 | Level 2 | E |  | 2024-12-17 | Level 2
129638398 | pole | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129638402 | insulator and brushing | Non-HFTD | Transmission | 2024-09-06 | 2027-09-06 | Level 2 | E |  | 2027-09-06 | Level 2
129638430 | other | Non-HFTD | Transmission | 2024-09-06 | 2025-09-06 | Level 2 | E |  | 2025-09-06 | Level 2
129638443 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129638491 | pole | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129638508 | pole | Non-HFTD | Transmission | 2024-09-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
129638519 | other | Non-HFTD | Transmission | 2024-09-06 | 2029-09-06 | Level 3 | F |  | 2029-09-06 | Level 3
129638552 | pole | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F | 2024-12-11 | 2029-10-04 | Level 3 | GO 165 Inspection
129638568 | anchor/guy | Non-HFTD | Transmission | 2024-10-03 | 2025-10-03 | Level 2 | E |  | 2025-10-03 | Level 2
129638573 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129638641 | pole | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129638648 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129638650 | insulator and brushing | Non-HFTD | Transmission | 2024-10-03 | 2025-10-03 | Level 2 | E |  | 2025-10-03 | Level 2
129638743 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129638781 | pole | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129638785 | other | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129638788 | anchor/guy | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129638791 | other | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129638822 | other | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129638841 | pole | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129638865 | pole | Non-HFTD | Transmission | 2024-09-09 | 2024-12-09 | Level 2 | E |  | 2024-12-09 | Level 2
129638868 | other | Non-HFTD | Transmission | 2024-09-11 | 2029-09-11 | Level 3 | F |  | 2029-09-11 | Level 3
129638891 | other | Non-HFTD | Transmission | 2024-01-08 | 2024-12-31 | Level 3 | F |  | 2029-01-08 | Level 3
129638979 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129639011 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129639055 | insulator and brushing | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129639170 | other | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129639179 | pole | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129639192 | anchor/guy | Non-HFTD | Transmission | 2024-10-03 | 2025-10-03 | Level 2 | E |  | 2025-10-03 | Level 2
129639234 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129639256 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129639302 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129639339 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129639377 | switch | Non-HFTD | Transmission | 2024-09-18 | 2027-09-18 | Level 2 | E |  | 2027-09-18 | Level 2
129639379 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129639413 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129639440 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2025-01-02 | Level 2 | E |  | 2025-01-02 | Level 2
129639523 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129639561 | pole | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129639595 | anchor/guy | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129639637 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129639658 | switch | Non-HFTD | Transmission | 2024-09-16 | 2024-12-16 | Level 2 | E |  | 2024-12-16 | Level 2
129639836 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129639857 | pole | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129639883 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129639889 | other | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129639901 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129639907 | insulator and brushing | Non-HFTD | Transmission | 2024-10-03 | 2025-01-03 | Level 2 | E |  | 2025-01-03 | Level 2
129639908 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129639925 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129639930 | switch | Non-HFTD | Transmission | 2024-09-16 | 2025-09-16 | Level 2 | E |  | 2025-09-16 | Level 2
129639935 | insulator and brushing | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129640037 | other | Non-HFTD | Transmission | 2024-09-19 | 2025-09-19 | Level 2 | E |  | 2025-09-19 | Level 2
129641338 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129641339 | pole | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129641340 | pole | Non-HFTD | Transmission | 2024-09-03 | 2029-09-03 | Level 3 | F |  | 2029-09-03 | Level 3
129641353 | pole | Non-HFTD | Transmission | 2024-09-19 | 2024-12-19 | Level 2 | E |  | 2024-12-19 | Level 2
129641357 | anchor/guy | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129641363 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129641390 | pole | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E | 2024-12-02 | 2027-10-05 | Level 2 | GO 165 Inspection
129641409 | pole | Non-HFTD | Transmission | 2024-09-16 | 2025-03-16 | Level 2 | E |  | 2025-03-16 | Level 2
129641415 | pole | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129641424 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129641436 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129641527 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129641560 | pole | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129641568 | other | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129641591 | pole | Non-HFTD | Transmission | 2024-09-16 | 2025-03-16 | Level 2 | E |  | 2025-03-16 | Level 2
129641592 | insulator and brushing | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129641620 | insulator and brushing | Non-HFTD | Transmission | 2024-09-16 | 2027-09-16 | Level 2 | E |  | 2027-09-16 | Level 2
129641626 | insulator and brushing | Non-HFTD | Transmission | 2024-09-11 | 2027-09-11 | Level 2 | E |  | 2027-09-11 | Level 2
129641632 | anchor/guy | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129641663 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129641670 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129641682 | pole | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129641693 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2025-01-04 | Level 2 | E |  | 2025-01-04 | Level 2
129641700 | pole | Non-HFTD | Transmission | 2024-09-10 | 2027-09-10 | Level 2 | E |  | 2027-09-10 | Level 2
129641716 | pole | Non-HFTD | Transmission | 2024-09-13 | 2025-03-13 | Level 2 | E |  | 2025-03-13 | Level 2
129641723 | switch | Non-HFTD | Transmission | 2024-09-17 | 2025-09-17 | Level 2 | E |  | 2025-09-17 | Level 2
129641729 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129641746 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129641851 | insulator and brushing | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129641853 | pole | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129641881 | other | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E |  | 2027-09-20 | Level 2
129641883 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129641968 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F | 2024-11-19 | 2029-09-20 | Level 3 | GO 165 Inspection
129641977 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129642006 | anchor/guy | Non-HFTD | Transmission | 2024-09-12 | 2029-09-12 | Level 3 | F |  | 2029-09-12 | Level 3
129642021 | anchor/guy | Non-HFTD | Transmission | 2024-09-16 | 2025-09-16 | Level 2 | E |  | 2025-09-16 | Level 2
129642024 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F | 2024-10-24 | 2029-10-04 | Level 3 | GO 165 Inspection
129642028 | anchor/guy | Non-HFTD | Transmission | 2024-10-04 | 2025-04-04 | Level 2 | E | 2024-10-24 | 2025-04-04 | Level 2 | GO 165 Inspection
129642105 | pole | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129642113 | pole | Non-HFTD | Transmission | 2024-09-13 | 2027-09-13 | Level 2 | E |  | 2027-09-13 | Level 2
129642134 | insulator and brushing | Non-HFTD | Transmission | 2024-09-17 | 2025-09-17 | Level 2 | E |  | 2025-09-17 | Level 2
129642179 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129642238 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F | 2024-11-09 | 2029-09-24 | Level 3 | GO 165 Inspection
129642239 | other | Non-HFTD | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | E |  | 2025-09-18 | Level 2
129642245 | pole | Non-HFTD | Transmission | 2024-10-04 | 2025-01-04 | Level 2 | E |  | 2025-01-04 | Level 2
129642276 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129642305 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129642311 | pole | Non-HFTD | Transmission | 2024-09-12 | 2025-03-12 | Level 2 | E |  | 2025-03-12 | Level 2
129642315 | anchor/guy | Non-HFTD | Transmission | 2024-09-13 | 2029-09-13 | Level 3 | F |  | 2029-09-13 | Level 3
129642339 | pole | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E | 2024-11-12 | 2027-09-24 | Level 2 | GO 165 Inspection
129642367 | pole | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129642386 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129642411 | pole | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129642495 | other | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129642496 | pole | Non-HFTD | Transmission | 2024-09-24 | 2025-03-24 | Level 2 | E | 2024-11-16 | 2025-03-24 | Level 2 | GO 165 Inspection
129646386 | insulator and brushing | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E | 2024-12-10 | 2027-10-05 | Level 2 | GO 165 Inspection
129647698 | insulator and brushing | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E | 2024-12-11 | 2027-10-05 | Level 2 | GO 165 Inspection
129647699 | other | Non-HFTD | Transmission | 2024-10-05 | 2025-10-05 | Level 2 | E | 2024-12-11 | 2025-10-05 | Level 2 | GO 165 Inspection
129647724 | insulator and brushing | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E | 2024-12-11 | 2027-10-05 | Level 2 | GO 165 Inspection
129648891 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129649277 | anchor/guy | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129649920 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E | 2024-11-13 | 2027-10-07 | Level 2 | GO 165 Inspection
129650195 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129650437 | other | Non-HFTD | Transmission | 2024-09-12 | 2024-12-12 | Level 2 | E |  | 2024-12-12 | Level 2
129650890 | crossarm | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129650892 | crossarm | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129650976 | switch | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129650977 | switch | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129651247 | other | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E | 2024-11-14 | 2027-10-07 | Level 2 | GO 165 Inspection
129651406 | anchor/guy | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129651430 | pole | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E |  | 2027-10-07 | Level 2
129651439 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E | 2024-11-14 | 2027-10-07 | Level 2 | GO 165 Inspection
129651494 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E | 2024-11-14 | 2027-10-07 | Level 2 | GO 165 Inspection
129651608 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129651621 | conductor | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E |  | 2027-10-05 | Level 2
129651652 | pole | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129651668 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129651716 | pole | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129651745 | pole | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129651786 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129651838 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129651843 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129651851 | insulator and brushing | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129651852 | insulator and brushing | Non-HFTD | Transmission | 2024-10-05 | 2025-01-05 | Level 2 | E |  | 2025-01-05 | Level 2
129651889 | other | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129651891 | other | Non-HFTD | Transmission | 2024-09-18 | 2024-12-18 | Level 2 | E | 2024-11-18 | 2024-12-18 | Level 2 | GO 165 Inspection
129651899 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129651902 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F |  | 2029-09-23 | Level 3
129651905 | pole | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129651935 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129653969 | pole | Non-HFTD | Transmission | 2024-09-16 | 2029-09-16 | Level 3 | F |  | 2029-09-16 | Level 3
129654249 | anchor/guy | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129654386 | switch | Non-HFTD | Transmission | 2024-10-08 | 2025-04-08 | Level 2 | E |  | 2025-04-08 | Level 2
129655216 | other | HFTD Tier 3 | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129656456 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129656679 | anchor/guy | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129656703 | pole | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129656704 | pole | Non-HFTD | Transmission | 2024-10-08 | 2027-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129656722 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129656822 | pole | Non-HFTD | Transmission | 2024-10-08 | 2027-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129656826 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129656938 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F | 2024-11-06 | 2029-09-20 | Level 3 | GO 165 Inspection
129656967 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129657021 | pole | Non-HFTD | Transmission | 2024-09-19 | 2025-03-19 | Level 2 | E |  | 2025-03-19 | Level 2
129657023 | other | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129657061 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129657080 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F | 2024-11-04 | 2029-09-25 | Level 3 | GO 165 Inspection
129657094 | crossarm | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129657096 | pole | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129657122 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129657127 | pole | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129657155 | splice | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129657165 | switch | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129657185 | other | Non-HFTD | Transmission | 2024-10-07 | 2025-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129657225 | anchor/guy | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129657251 | crossarm | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129657283 | pole | Non-HFTD | Transmission | 2024-09-18 | 2029-09-18 | Level 3 | F |  | 2029-09-18 | Level 3
129657292 | pole | Non-HFTD | Transmission | 2024-10-08 | 2027-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129657306 | other | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129657308 | pole | Non-HFTD | Transmission | 2024-09-17 | 2029-09-17 | Level 3 | F |  | 2029-09-17 | Level 3
129657311 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129657321 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129657327 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F | 2024-11-06 | 2029-09-20 | Level 3 | GO 165 Inspection
129657332 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129657363 | anchor/guy | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129657377 | conductor | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129657391 | other | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129657397 | insulator and brushing | Non-HFTD | Transmission | 2024-09-17 | 2025-09-17 | Level 2 | E |  | 2025-09-17 | Level 2
129657436 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129657491 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129657503 | anchor/guy | Non-HFTD | Transmission | 2024-10-08 | 2025-04-08 | Level 2 | E |  | 2025-10-08 | Level 2
129657504 | insulator and brushing | Non-HFTD | Transmission | 2024-10-08 | 2025-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129657787 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129658245 | anchor/guy | HFTD Tier 3 | Transmission | 2024-10-09 | 2025-04-09 | Level 2 | E |  | 2025-04-09 | Level 2
129658591 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129659183 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129659439 | insulator and brushing | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129659478 | anchor/guy | Non-HFTD | Transmission | 2024-10-09 | 2025-10-09 | Level 2 | E |  | 2025-10-09 | Level 2
129659549 | pole | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129659679 | conductor | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129659796 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129659909 | pole | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129660030 | switch | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129660142 | pole | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129660236 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129660421 | insulator and brushing | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129660465 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129660875 | other | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129661316 | other | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129661379 | pole | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129661426 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129661438 | insulator and brushing | Non-HFTD | Transmission | 2024-10-08 | 2025-10-08 | Level 2 | E |  | 2025-10-08 | Level 2
129661529 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129661589 | pole | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129661606 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129661659 | pole | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129661699 | anchor/guy | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129661731 | insulator and brushing | Non-HFTD | Transmission | 2024-09-17 | 2027-09-17 | Level 2 | E |  | 2027-09-17 | Level 2
129661741 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129661748 | insulator and brushing | Non-HFTD | Transmission | 2024-09-19 | 2027-09-19 | Level 2 | E |  | 2027-09-19 | Level 2
129661829 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129661854 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129661904 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129661923 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129661926 | insulator and brushing | Non-HFTD | Transmission | 2024-09-20 | 2025-03-20 | Level 2 | E |  | 2025-03-20 | Level 2
129661927 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F | 2024-11-06 | 2029-09-20 | Level 3 | GO 165 Inspection
129661942 | other | Non-HFTD | Transmission | 2024-09-19 | 2029-09-19 | Level 3 | F |  | 2029-09-19 | Level 3
129661944 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129661949 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129661962 | insulator and brushing | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E | 2024-11-24 | 2025-09-20 | Level 2 | GO 165 Inspection
129661991 | pole | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129662008 | splice | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129669288 | pole | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129669300 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129669399 | other | Non-HFTD | Transmission | 2024-10-10 | 2025-01-10 | Level 2 | E |  | 2025-01-10 | Level 2
129669514 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129669675 | anchor/guy | Non-HFTD | Transmission | 2024-10-10 | 2025-10-10 | Level 2 | E |  | 2025-10-10 | Level 2
129669676 | pole | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129669684 | insulator and brushing | Non-HFTD | Transmission | 2024-09-03 | 2027-09-03 | Level 2 | E |  | 2027-09-03 | Level 2
129669829 | insulator and brushing | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129669965 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670004 | insulator and brushing | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670062 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670075 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670189 | pole | Non-HFTD | Transmission | 2024-10-10 | 2025-10-10 | Level 2 | E |  | 2025-10-10 | Level 2
129670245 | pole | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129670259 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670316 | pole | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129670328 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670399 | crossarm | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129670571 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129670860 | pole | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129670951 | insulator and brushing | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129671258 | anchor/guy | Non-HFTD | Transmission | 2024-10-10 | 2025-01-10 | Level 2 | E |  | 2025-01-10 | Level 2
129671307 | anchor/guy | Non-HFTD | Transmission | 2024-10-10 | 2025-01-10 | Level 2 | E |  | 2025-01-10 | Level 2
129671308 | anchor/guy | Non-HFTD | Transmission | 2024-10-10 | 2025-01-10 | Level 2 | E |  | 2025-01-10 | Level 2
129671476 | other | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F | 2024-10-21 | 2029-09-20 | Level 3 | GO 165 Inspection
129671487 | pole | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E | 2024-10-18 | 2027-09-20 | Level 2 | GO 165 Inspection
129671506 | pole | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129671575 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129671592 | other | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E |  | 2027-09-20 | Level 2
129671657 | pole | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129671740 | other | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E |  | 2027-09-23 | Level 2
129671744 | other | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129671748 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129671775 | insulator and brushing | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129671790 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129671888 | other | Non-HFTD | Transmission | 2024-09-23 | 2029-09-23 | Level 3 | F | 2024-10-18 | 2029-09-23 | Level 3 | GO 165 Inspection
129671950 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129671956 | other | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129671972 | pole | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129672031 | other | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129672032 | other | Non-HFTD | Transmission | 2024-09-20 | 2027-09-20 | Level 2 | E |  | 2027-09-20 | Level 2
129672035 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129672046 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129672065 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129672115 | other | Non-HFTD | Transmission | 2024-10-09 | 2027-10-09 | Level 2 | E |  | 2027-10-09 | Level 2
129672119 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129672142 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129672224 | splice | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129672554 | insulator and brushing | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129672556 | insulator and brushing | Non-HFTD | Transmission | 2024-09-24 | 2027-09-24 | Level 2 | E |  | 2027-09-24 | Level 2
129673011 | pole | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E | 2024-11-19 | 2027-09-26 | Level 2 | GO 165 Inspection
129673533 | pole | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129673707 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129673749 | other | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129673922 | insulator and brushing | Non-HFTD | Transmission | 2024-10-10 | 2027-10-10 | Level 2 | E |  | 2027-10-10 | Level 2
129673949 | pole | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129674071 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129674174 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129674255 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129674475 | other | Non-HFTD | Transmission | 2024-09-26 | 2025-09-26 | Level 2 | E |  | 2025-09-26 | Level 2
129674476 | other | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129674477 | pole | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129674601 | pole | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129674673 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129674720 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129674773 | other | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129674847 | pole | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129675136 | anchor/guy | Non-HFTD | Transmission | 2024-10-11 | 2025-10-11 | Level 2 | E |  | 2025-10-11 | Level 2
129675274 | pole | Non-HFTD | Transmission | 2024-09-23 | 2027-09-23 | Level 2 | E | 2024-10-18 | 2027-09-23 | Level 2 | GO 165 Inspection
129675278 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F | 2024-11-25 | 2029-09-25 | Level 3 | GO 165 Inspection
129675481 | pole | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129675600 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129675606 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129675660 | other | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129675847 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129675884 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129676001 | anchor/guy | Non-HFTD | Transmission | 2024-09-25 | 2025-09-25 | Level 2 | E |  | 2025-09-25 | Level 2
129676104 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129676153 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129676890 | other | Non-HFTD | Transmission | 2024-10-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129676891 | insulator and brushing | Non-HFTD | Transmission | 2024-10-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129677196 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129677199 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129677215 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129677221 | insulator and brushing | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129677401 | insulator and brushing | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129677489 | anchor/guy | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129677905 | anchor/guy | Non-HFTD | Transmission | 2024-10-11 | 2025-10-11 | Level 2 | E |  | 2025-10-11 | Level 2
129678716 | anchor/guy | Non-HFTD | Transmission | 2024-10-12 | 2027-10-12 | Level 2 | E |  | 2027-10-12 | Level 2
129680376 | pole | Non-HFTD | Transmission | 2024-09-20 | 2029-09-20 | Level 3 | F |  | 2029-09-20 | Level 3
129680407 | switch | Non-HFTD | Transmission | 2024-10-14 | 2025-10-14 | Level 2 | E |  | 2025-10-14 | Level 2
129684092 | insulator and brushing | HFTD Tier 3 | Transmission | 2024-10-14 | 2025-04-14 | Level 2 | E |  | 2025-04-14 | Level 2
129686514 | other | Non-HFTD | Transmission | 2024-10-14 | 2029-10-14 | Level 3 | F |  | 2029-10-14 | Level 3
129686624 | other | Non-HFTD | Transmission | 2024-10-14 | 2029-10-14 | Level 3 | F |  | 2029-10-14 | Level 3
129686640 | insulator and brushing | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129686652 | insulator and brushing | Non-HFTD | Transmission | 2024-10-14 | 2027-10-14 | Level 2 | E |  | 2027-10-14 | Level 2
129686661 | other | Non-HFTD | Transmission | 2024-10-14 | 2029-10-14 | Level 3 | F |  | 2029-10-14 | Level 3
129686669 | insulator and brushing | Non-HFTD | Transmission | 2024-10-14 | 2027-10-14 | Level 2 | E |  | 2027-10-14 | Level 2
129686724 | other | Non-HFTD | Transmission | 2024-09-28 | 2025-03-28 | Level 2 | E |  | 2025-03-28 | Level 2
129686763 | other | Non-HFTD | Transmission | 2024-09-26 | 2027-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129686813 | switch | Non-HFTD | Transmission | 2024-10-14 | 2025-01-14 | Level 2 | E |  | 2025-01-14 | Level 2
129686814 | other | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129686882 | other | Non-HFTD | Transmission | 2024-10-14 | 2027-10-14 | Level 2 | E |  | 2027-10-14 | Level 2
129686888 | insulator and brushing | Non-HFTD | Transmission | 2024-09-25 | 2027-09-25 | Level 2 | E |  | 2027-09-25 | Level 2
129686901 | pole | Non-HFTD | Transmission | 2024-10-14 | 2029-10-14 | Level 3 | F |  | 2029-10-14 | Level 3
129686914 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129686948 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129686965 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129686983 | insulator and brushing | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129686986 | insulator and brushing | Non-HFTD | Transmission | 2024-10-14 | 2025-10-14 | Level 2 | E |  | 2025-10-14 | Level 2
129687020 | pole | Non-HFTD | Transmission | 2024-09-27 | 2025-09-27 | Level 2 | E |  | 2025-09-27 | Level 2
129687130 | insulator and brushing | Non-HFTD | Transmission | 2024-10-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129687190 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129687209 | other | Non-HFTD | Transmission | 2024-09-24 | 2029-09-24 | Level 3 | F |  | 2029-09-24 | Level 3
129687221 | other | Non-HFTD | Transmission | 2024-09-26 | 2025-09-26 | Level 2 | E |  | 2027-09-26 | Level 2
129687251 | other | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F |  | 2029-09-27 | Level 3
129687287 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129687292 | pole | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129687298 | other | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129687323 | pole | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129687342 | other | Non-HFTD | Transmission | 2024-09-25 | 2029-09-25 | Level 3 | F |  | 2029-09-25 | Level 3
129687350 | other | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129687366 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129687370 | insulator and brushing | Non-HFTD | Transmission | 2024-09-28 | 2025-09-28 | Level 2 | E |  | 2025-09-28 | Level 2
129687381 | insulator and brushing | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129688649 | pole | Non-HFTD | Transmission | 2024-10-14 | 2027-10-14 | Level 2 | E |  | 2027-10-14 | Level 2
129688791 | insulator and brushing | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129688973 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129689055 | insulator and brushing | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129689154 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129689762 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129690145 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129690449 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129690595 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129690701 | anchor/guy | Non-HFTD | Transmission | 2024-10-15 | 2025-04-15 | Level 2 | E |  | 2025-04-15 | Level 2
129690834 | other | Non-HFTD | Transmission | 2024-10-15 | 2027-10-15 | Level 2 | E |  | 2027-10-15 | Level 2
129690858 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129691058 | other | Non-HFTD | Transmission | 2024-10-15 | 2027-10-15 | Level 2 | E |  | 2027-10-15 | Level 2
129691749 | insulator and brushing | Non-HFTD | Transmission | 2024-10-10 | 2025-01-10 | Level 2 | E |  | 2025-01-10 | Level 2
129691790 | insulator and brushing | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129691808 | pole | Non-HFTD | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129691857 | other | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129691879 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2025-04-02 | Level 2 | E |  | 2025-04-02 | Level 2
129691882 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129691926 | other | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129691938 | pole | Non-HFTD | Transmission | 2024-09-27 | 2029-09-27 | Level 3 | F | 2024-10-18 | 2029-09-27 | Level 3 | GO 165 Inspection
129691943 | other | Non-HFTD | Transmission | 2024-09-26 | 2025-09-26 | Level 2 | E |  | 2025-09-26 | Level 2
129691960 | insulator and brushing | Non-HFTD | Transmission | 2024-09-27 | 2024-12-27 | Level 2 | E | 2024-10-18 | 2025-09-27 | Level 2 | GO 165 Inspection
129692029 | insulator and brushing | Non-HFTD | Transmission | 2024-10-11 | 2025-01-11 | Level 2 | E |  | 2025-01-11 | Level 2
129692031 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129692033 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129692041 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129692046 | other | Non-HFTD | Transmission | 2024-09-28 | 2027-09-28 | Level 2 | E |  | 2027-09-28 | Level 2
129692065 | insulator and brushing | Non-HFTD | Transmission | 2024-10-14 | 2027-10-14 | Level 2 | E |  | 2027-10-14 | Level 2
129692088 | insulator and brushing | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129692150 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129692155 | switch | Non-HFTD | Transmission | 2024-09-30 | 2027-09-30 | Level 2 | E |  | 2027-09-30 | Level 2
129692159 | pole | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129692169 | other | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129692185 | other | Non-HFTD | Transmission | 2024-09-28 | 2025-09-28 | Level 2 | E |  | 2025-09-28 | Level 2
129692220 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129692236 | other | Non-HFTD | Transmission | 2024-09-26 | 2029-09-26 | Level 3 | F |  | 2029-09-26 | Level 3
129692283 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129692304 | pole | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129692345 | switch | Non-HFTD | Transmission | 2024-09-27 | 2025-09-27 | Level 2 | E |  | 2025-09-27 | Level 2
129692363 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129692426 | switch | Non-HFTD | Transmission | 2024-09-27 | 2027-09-27 | Level 2 | E |  | 2027-09-27 | Level 2
129692428 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129692455 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129692467 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129692474 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129692499 | insulator and brushing | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129692501 | other | HFTD Tier 2 | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129692522 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129692554 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129692557 | anchor/guy | Non-HFTD | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129692561 | other | Non-HFTD | Transmission | 2024-09-30 | 2029-09-30 | Level 3 | F |  | 2029-09-30 | Level 3
129692593 | pole | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129693859 | other | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129694930 | other | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129695156 | insulator and brushing | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129695167 | crossarm | Non-HFTD | Transmission | 2024-09-04 | 2029-09-04 | Level 3 | F |  | 2029-09-04 | Level 3
129695577 | other | HFTD Tier 2 | Transmission | 2024-10-16 | 2025-04-16 | Level 2 | E |  | 2025-04-16 | Level 2
129695634 | anchor/guy | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129696412 | pole | Non-HFTD | Transmission | 2024-09-12 | 2027-09-12 | Level 2 | E |  | 2027-09-12 | Level 2
129696453 | splice | Non-HFTD | Transmission | 2024-10-16 | 2027-10-16 | Level 2 | E |  | 2027-10-16 | Level 2
129696741 | pole | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F | 2024-11-18 | 2029-10-16 | Level 3 | GO 165 Inspection
129696815 | other | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129697053 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697076 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697097 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697117 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697120 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697124 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697132 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2025-03-30 | Level 2 | E |  | 2025-03-30 | Level 2
129697138 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697158 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697217 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697224 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697267 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129697280 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697297 | insulator and brushing | Non-HFTD | Transmission | 2024-10-15 | 2025-01-15 | Level 2 | E |  | 2025-10-15 | Level 2
129697335 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697345 | pole | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129697370 | insulator and brushing | Non-HFTD | Transmission | 2024-09-28 | 2027-09-28 | Level 2 | E |  | 2027-09-28 | Level 2
129697376 | other | Non-HFTD | Transmission | 2024-09-28 | 2029-09-28 | Level 3 | F |  | 2029-09-28 | Level 3
129697377 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697393 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697395 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697401 | pole | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129697409 | pole | Non-HFTD | Transmission | 2024-10-15 | 2029-10-15 | Level 3 | F |  | 2029-10-15 | Level 3
129697418 | insulator and brushing | Non-HFTD | Transmission | 2024-09-30 | 2024-12-30 | Level 2 | E |  | 2024-12-30 | Level 2
129697464 | pole | Non-HFTD | Transmission | 2024-10-14 | 2029-10-14 | Level 3 | F |  | 2029-10-14 | Level 3
129697484 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697489 | pole | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129697506 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697619 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697628 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697641 | insulator and brushing | Non-HFTD | Transmission | 2024-10-01 | 2027-10-01 | Level 2 | E |  | 2027-10-01 | Level 2
129697657 | insulator and brushing | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129697683 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697685 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697688 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697706 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697708 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697716 | pole | Non-HFTD | Transmission | 2024-09-30 | 2025-09-30 | Level 2 | E |  | 2025-09-30 | Level 2
129697718 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697743 | anchor/guy | Non-HFTD | Transmission | 2024-09-30 | 2027-09-30 | Level 2 | E |  | 2027-09-30 | Level 2
129697744 | pole | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697753 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697774 | insulator and brushing | Non-HFTD | Transmission | 2024-10-15 | 2025-01-15 | Level 2 | E |  | 2025-01-15 | Level 2
129697775 | pole | Non-HFTD | Transmission | 2024-10-16 | 2027-10-16 | Level 2 | E |  | 2027-10-16 | Level 2
129697786 | pole | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129697798 | anchor/guy | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697835 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697850 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129697861 | other | Non-HFTD | Transmission | 2024-10-15 | 2025-10-15 | Level 2 | E |  | 2025-10-15 | Level 2
129699189 | other | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E | 2024-11-14 | 2027-10-07 | Level 2 | GO 165 Inspection
129699659 | other | Non-HFTD | Transmission | 2024-10-17 | 2029-10-17 | Level 3 | F |  | 2029-10-17 | Level 3
129699945 | other | Non-HFTD | Transmission | 2024-10-17 | 2029-10-17 | Level 3 | F |  | 2029-10-17 | Level 3
129700252 | other | Non-HFTD | Transmission | 2024-10-17 | 2029-10-17 | Level 3 | F |  | 2029-10-17 | Level 3
129700407 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700408 | insulator and brushing | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129700421 | other | Non-HFTD | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129700423 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129700439 | insulator and brushing | Non-HFTD | Transmission | 2024-10-16 | 2027-10-16 | Level 2 | E |  | 2027-10-16 | Level 2
129700452 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700487 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129700571 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129700577 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700591 | pole | Non-HFTD | Transmission | 2024-10-17 | 2027-10-17 | Level 2 | E |  | 2027-10-17 | Level 2
129700593 | other | Non-HFTD | Transmission | 2024-10-17 | 2027-10-17 | Level 2 | E |  | 2027-10-17 | Level 2
129700594 | insulator and brushing | Non-HFTD | Transmission | 2024-10-17 | 2027-10-17 | Level 2 | E |  | 2027-10-17 | Level 2
129700610 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700622 | pole | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129700631 | other | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129700637 | pole | Non-HFTD | Transmission | 2024-10-08 | 2027-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129700647 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700648 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700656 | other | Non-HFTD | Transmission | 2024-10-03 | 2025-10-03 | Level 2 | E |  | 2025-10-03 | Level 2
129700664 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700665 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700683 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700689 | pole | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129700690 | other | Non-HFTD | Transmission | 2024-10-17 | 2029-10-17 | Level 3 | F |  | 2029-10-17 | Level 3
129700742 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700746 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129700773 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129700778 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700785 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129700803 | insulator and brushing | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700816 | pole | Non-HFTD | Transmission | 2024-10-02 | 2027-10-02 | Level 2 | E |  | 2027-10-02 | Level 2
129700847 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129700856 | pole | Non-HFTD | Transmission | 2024-10-01 | 2025-10-01 | Level 2 | E |  | 2025-10-01 | Level 2
129700872 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700884 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129700926 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700927 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700929 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700933 | anchor/guy | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700940 | anchor/guy | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700941 | pole | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129700954 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700955 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129700959 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700975 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129700993 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129701004 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129701015 | insulator and brushing | Non-HFTD | Transmission | 2024-10-17 | 2025-10-17 | Level 2 | E |  | 2025-10-17 | Level 2
129701036 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129701039 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129701047 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129701052 | other | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129701198 | other | Non-HFTD | Transmission | 2024-10-01 | 2029-10-01 | Level 3 | F |  | 2029-10-01 | Level 3
129701435 | other | Non-HFTD | Transmission | 2024-10-04 | 2025-10-04 | Level 2 | E |  | 2025-10-04 | Level 2
129701438 | insulator and brushing | Non-HFTD | Transmission | 2024-10-02 | 2029-10-02 | Level 3 | F |  | 2029-10-02 | Level 3
129702873 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129702923 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129702952 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129702979 | pole | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E |  | 2027-10-07 | Level 2
129702986 | pole | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129702993 | other | Non-HFTD | Transmission | 2024-10-18 | 2029-10-18 | Level 3 | F |  | 2029-10-18 | Level 3
129703029 | other | Non-HFTD | Transmission | 2024-10-18 | 2029-10-18 | Level 3 | F |  | 2029-10-18 | Level 3
129703061 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129703070 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129703072 | pole | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129703101 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129703116 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129703210 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129703221 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129703278 | other | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129703483 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129703485 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129703607 | pole | Non-HFTD | Transmission | 2024-10-07 | 2025-10-07 | Level 2 | E |  | 2025-10-07 | Level 2
129703662 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129703677 | pole | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129703783 | pole | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129703805 | pole | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129703967 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129704032 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129704034 | other | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129704042 | pole | Non-HFTD | Transmission | 2024-10-18 | 2029-10-18 | Level 3 | F |  | 2029-10-18 | Level 3
129704066 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129704306 | pole | Non-HFTD | Transmission | 2024-10-18 | 2025-01-18 | Level 2 | E |  | 2027-10-18 | Level 2
129704327 | pole | Non-HFTD | Transmission | 2024-10-18 | 2025-01-18 | Level 2 | E |  | 2027-10-18 | Level 2
129704679 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129704683 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129704738 | pole | Non-HFTD | Transmission | 2024-10-04 | 2025-01-04 | Level 2 | E |  | 2025-01-04 | Level 2
129704777 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129704860 | pole | Non-HFTD | Transmission | 2024-10-04 | 2025-10-04 | Level 2 | E |  | 2025-10-04 | Level 2
129705091 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129705092 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129705157 | other | Non-HFTD | Transmission | 2024-10-18 | 2029-10-18 | Level 3 | F |  | 2029-10-18 | Level 3
129705200 | pole | Non-HFTD | Transmission | 2024-10-18 | 2029-10-18 | Level 3 | F |  | 2029-10-18 | Level 3
129705209 | pole | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129705432 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2027-10-04 | Level 2 | E |  | 2027-10-04 | Level 2
129705499 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2025-10-07 | Level 2 | E |  | 2025-10-07 | Level 2
129705566 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129705782 | pole | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E |  | 2027-10-05 | Level 2
129706048 | other | Non-HFTD | Transmission | 2024-10-15 | 2025-10-15 | Level 2 | E |  | 2025-10-15 | Level 2
129706154 | pole | Non-HFTD | Transmission | 2024-10-07 | 2025-10-07 | Level 2 | E |  | 2025-10-07 | Level 2
129706237 | anchor/guy | Non-HFTD | Transmission | 2024-10-03 | 2029-10-03 | Level 3 | F |  | 2029-10-03 | Level 3
129706298 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129706637 | anchor/guy | Non-HFTD | Transmission | 2024-10-18 | 2027-10-18 | Level 2 | E |  | 2027-10-18 | Level 2
129706711 | other | Non-HFTD | Transmission | 2024-10-18 | 2029-10-18 | Level 3 | F |  | 2029-10-18 | Level 3
129706712 | other | Non-HFTD | Transmission | 2024-10-10 | 2029-10-10 | Level 3 | F |  | 2029-10-10 | Level 3
129706965 | pole | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129706969 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129707078 | pole | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129707161 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129707191 | pole | Non-HFTD | Transmission | 2024-10-04 | 2025-04-04 | Level 2 | E |  | 2025-04-04 | Level 2
129707257 | other | Non-HFTD | Transmission | 2024-10-04 | 2029-10-04 | Level 3 | F |  | 2029-10-04 | Level 3
129707351 | pole | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129707356 | insulator and brushing | Non-HFTD | Transmission | 2024-10-04 | 2025-10-04 | Level 2 | E |  | 2025-10-04 | Level 2
129707359 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129708921 | other | Non-HFTD | Transmission | 2024-10-21 | 2029-10-21 | Level 3 | F |  | 2029-10-21 | Level 3
129709681 | pole | Non-HFTD | Transmission | 2022-05-27 | 2023-05-27 | Level 2 | E | 2024-10-31 | 2023-05-27 | Level 2 | Standards change
129709689 | insulator and brushing | Non-HFTD | Transmission | 2024-10-03 | 2027-10-03 | Level 2 | E |  | 2027-10-03 | Level 2
129710203 | pole | HFTD Tier 2 | Transmission | 2021-04-24 | 2022-04-24 | Level 2 | E |  | 2022-04-24 | Level 2
129711064 | insulator and brushing | Non-HFTD | Transmission | 2024-10-21 | 2025-10-21 | Level 2 | E |  | 2025-10-21 | Level 2
129711274 | other | Non-HFTD | Transmission | 2024-10-21 | 2029-10-21 | Level 3 | F |  | 2029-10-21 | Level 3
129711492 | other | Non-HFTD | Transmission | 2024-10-21 | 2029-10-21 | Level 3 | F |  | 2029-10-21 | Level 3
129711680 | other | HFTD Tier 2 | Transmission | 2024-10-21 | 2025-10-21 | Level 2 | E |  | 2025-10-21 | Level 2
129711778 | switch | Non-HFTD | Transmission | 2024-10-21 | 2027-10-21 | Level 2 | E |  | 2027-10-21 | Level 2
129712390 | other | Non-HFTD | Transmission | 2024-10-21 | 2025-10-21 | Level 2 | E |  | 2025-10-21 | Level 2
129712509 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F | 2024-10-30 | 2029-10-09 | Level 3 | GO 165 Inspection
129712539 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129712599 | other | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129712626 | pole | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E |  | 2027-10-07 | Level 2
129712640 | other | Non-HFTD | Transmission | 2024-10-07 | 2025-10-07 | Level 2 | E |  | 2025-10-07 | Level 2
129712671 | pole | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129712697 | anchor/guy | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712703 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712728 | insulator and brushing | Non-HFTD | Transmission | 2024-10-18 | 2025-10-18 | Level 2 | E |  | 2025-10-18 | Level 2
129712758 | pole | Non-HFTD | Transmission | 2024-10-07 | 2027-10-07 | Level 2 | E |  | 2027-10-07 | Level 2
129712763 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712764 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712784 | pole | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712824 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712826 | insulator and brushing | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712834 | insulator and brushing | HFTD Tier 2 | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712852 | other | Non-HFTD | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712857 | other | HFTD Tier 2 | Transmission | 2024-10-07 | 2029-10-07 | Level 3 | F |  | 2029-10-07 | Level 3
129712897 | other | Non-HFTD | Transmission | 2024-10-21 | 2029-10-21 | Level 3 | F |  | 2029-10-21 | Level 3
129712917 | other | Non-HFTD | Transmission | 2024-10-08 | 2025-10-08 | Level 2 | E |  | 2025-10-08 | Level 2
129712942 | other | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129712960 | other | Non-HFTD | Transmission | 2024-10-09 | 2025-10-09 | Level 2 | E |  | 2025-10-09 | Level 2
129712972 | pole | Non-HFTD | Transmission | 2024-10-05 | 2029-10-05 | Level 3 | F |  | 2029-10-05 | Level 3
129713012 | other | Non-HFTD | Transmission | 2024-10-09 | 2025-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129713029 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129713040 | other | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129713074 | other | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129713290 | insulator and brushing | Non-HFTD | Transmission | 2024-10-22 | 2025-10-22 | Level 2 | E |  | 2025-10-22 | Level 2
129713556 | switch | Non-HFTD | Transmission | 2024-10-22 | 2025-04-22 | Level 2 | E |  | 2025-04-22 | Level 2
129713558 | switch | Non-HFTD | Transmission | 2024-10-22 | 2025-04-22 | Level 2 | E |  | 2025-04-22 | Level 2
129713727 | anchor/guy | Non-HFTD | Transmission | 2024-10-22 | 2029-10-22 | Level 3 | F |  | 2029-10-22 | Level 3
129714786 | other | Non-HFTD | Transmission | 2024-10-22 | 2027-10-22 | Level 2 | E |  | 2027-10-22 | Level 2
129715742 | insulator and brushing | Non-HFTD | Transmission | 2024-10-22 | 2029-10-22 | Level 3 | F |  | 2029-10-22 | Level 3
129716257 | insulator and brushing | Non-HFTD | Transmission | 2024-10-22 | 2025-01-22 | Level 2 | E |  | 2025-01-22 | Level 2
129716349 | other | Non-HFTD | Transmission | 2024-10-22 | 2029-10-22 | Level 3 | F |  | 2029-10-22 | Level 3
129716377 | insulator and brushing | Non-HFTD | Transmission | 2024-10-22 | 2029-10-22 | Level 3 | F |  | 2029-10-22 | Level 3
129716399 | anchor/guy | Non-HFTD | Transmission | 2024-10-22 | 2029-10-22 | Level 3 | F |  | 2029-10-22 | Level 3
129717004 | other | Non-HFTD | Transmission | 2024-10-22 | 2029-10-22 | Level 3 | F |  | 2029-10-22 | Level 3
129717070 | pole | Non-HFTD | Transmission | 2024-10-22 | 2027-10-22 | Level 2 | E |  | 2027-10-22 | Level 2
129717079 | pole | Non-HFTD | Transmission | 2024-10-09 | 2029-10-09 | Level 3 | F |  | 2029-10-09 | Level 3
129717128 | other | Non-HFTD | Transmission | 2024-10-18 | 2025-01-18 | Level 2 | E |  | 2027-10-18 | Level 2
129717136 | pole | Non-HFTD | Transmission | 2024-10-11 | 2029-10-11 | Level 3 | F |  | 2029-10-11 | Level 3
129717140 | switch | Non-HFTD | Transmission | 2024-10-05 | 2027-10-05 | Level 2 | E |  | 2027-10-05 | Level 2
129717169 | other | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129717187 | pole | Non-HFTD | Transmission | 2024-10-08 | 2027-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129717210 | other | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3
129717216 | other | Non-HFTD | Transmission | 2024-10-14 | 2029-10-14 | Level 3 | F |  | 2029-10-14 | Level 3
129717223 | other | Non-HFTD | Transmission | 2024-10-09 | 2025-01-09 | Level 2 | E |  | 2025-01-09 | Level 2
129717264 | pole | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129717281 | pole | Non-HFTD | Transmission | 2024-10-08 | 2027-10-08 | Level 2 | E |  | 2027-10-08 | Level 2
129717291 | pole | Non-HFTD | Transmission | 2024-10-08 | 2029-10-08 | Level 3 | F |  | 2029-10-08 | Level 3
129717299 | pole | Non-HFTD | Transmission | 2024-10-11 | 2027-10-11 | Level 2 | E |  | 2027-10-11 | Level 2
129717300 | other | Non-HFTD | Transmission | 2024-10-16 | 2029-10-16 | Level 3 | F |  | 2029-10-16 | Level 3