## 2023 Expense Summary
Expense 2023 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiative Name | 2023 Planned Budget (as reported in the WMP in 1,000s) | 2023 Actual Expenditure (in 1,000s) | Variance | Met Threshold for Variance Explanation (greater than 10%) | Detailed explanation of the reason for the discrepancy
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | 15292 | 15425.0242 | 133.0242 | No
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program | 0 | 7431.7979 | 7431.7979 | Yes | The cost of the distribution aerial pilot was not included in the expenditure forecast provided in the original 2023-2025 WMP.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 31707.4614 | 32947.1747 | 1239.7133 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 3366.0178 | 4532.06 | 1166.0422 | Yes | Execution resources were allocated to storm response in the 1st quarter leading to a compressed timeline for execution prior to fire season resulting increased overtime and double-time costs.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | 1822.9832 | 2908.94 | 1085.9568 | Yes | Original forecast was based on unit cost data from early 2022 and did not account for changes in the methods of infrared inspection.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | 55665.1346 | 65428.3223 | 9763.1877 | Yes | Execution resources were allocated to storm response in the 1st quarter leading to a compressed timeline for execution resulting increased overtime and double-time costs. Furthermore, the expanded use of contractors to complete inspections required increased support from inspection review specialists.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | 2826.0332 | 1083.5342 | -1742.499 | Yes | Technology updates allowed us to become more efficiency and not have to utilize as many contractors in order to complete inspections.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | 2633 | 1778.4617 | -854.5383 | Yes | Technology updates allowed us to become more efficiency and not have to utilize as many contractors in order to complete inspections.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 1181.6663 | 744.5437 | -437.1225 | Yes | Costs significantly lower than planned, due to internal resource replacing contractor. Enhanced switchyard inspections lower than planned attributed to System Inspection’s ability to inspect more efficiently requiring less hours from System Inspection and Hydro O&M resources.
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | No
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | PCC Costs | PCC Costs | - | No
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | PCC Costs | PCC Costs | - | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | PCC Costs | PCC Costs | - | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | PCC Costs | PCC Costs | - | No
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | PCC Costs | PCC Costs | - | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | 0 | 0 | 0 | No
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | - | - | - | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | 2944 | 8483.0784 | 5539.0784 | Yes | GM-01 was updated during through the Revision Notice resulting increased scope and additional cost.
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | PCC Costs | PCC Costs | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.8.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | - | - | - | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | 0 | 0 | 0 | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | 23500 | 32182.4431 | 8682.443 | Yes | Target GM-09 was created through the Revision Notice process and increased the scope of the program resulting in higher costs.
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | 0 | 0 | 0 | No
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 15249 | 15134 | -115 | No
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 2612 | 2699 | 87 | No
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 413 | 470.03 | 57.03 | Yes | Driven by additional scope for Meteorology IT associated with AWS migration
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | 0 | 0 | 0 | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | 0 | 0 | 0 | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | - | - | - | No
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | - | - | - | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | 10163 | 8575 | -1588 | Yes | PG&E's original 2023 financial forecast for LiDAR included the total projected cost for the vendor contract, which sought to do additional LiDAR inspections above and beyond the VM-01 target. The $8.6 million actual expenditure represents the cost of PG&E completing the VM-01 target.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | 31000 | 27877.22 | -3122.78 | Yes | Decrease primarily the result of a delay in completing 1254C work
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | 83418 | 12088.7764 | -71329.2236 | Yes | FTI's original forecast was based on high level estimates as the scope of the program was being developed. The actual costs in FTI stem from completing 266.6 circuit miles, while future years will 1,500 circuit miles.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | 160357 | 34947.3955 | -125409.6045 | Yes | TRI unit cost assumptions for the budget were based on historical EVM unit pricing. Actual unit pricing and units came in lower than planned.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 2521.7317 | 5442.7722 | 2921.0405 | Yes | Increased precipitation in 2023 resulted in increase vegetation growth requiring crews to conduct brush clearing multiple times at the same location to maintain adequate defensible space.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 407.602 | 2799.6811 | 2392.0791 | Yes | Increased precipitation in 2023 resulted in increase vegetation growth requiring crews to conduct brush clearing multiple times at the same location to maintain adequate defensible space.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 1906.6667 | 1694.2942 | -212.3724 | Yes | Budget forecasts are based on best available information, and vegetation growth varies annually based on weather and enviromental conditions. As a result the amount of vegetation work needed varies from year to year. Also, PMO costs significantly lower than planned due to internal resources replacing contractors.
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | 5970 | 13295.0074 | 7325.0074 | Yes | Primarily increase due to the original reported $ did not include Transmission Work (TO B/A) and the team did additional QA work and we included into the territoriy costs.
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | 21727.6 | 23798 | 2070.4 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | 1000 | 4210.26 | 3210.26 | Yes | The initial 2023 forecasts for transmission second patrol used a high level forecast based on helicopter based patrols in 2022. The actual expenditures reflect PG&E's use of additional patrol technology (e.g. LiDAR) and increased volume of inspections.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | 12679.2 | 9253 | -3426.2 | Yes | PG&E was able to achieve a lower unit cost for IVM related work than previously forecasted while completing the unit target.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | 711944.189 | 785445.7701 | 73501.5811 | Yes | Driven by an increased average cost per unit as the program incurred additional T&M costs related to contractor change-outs and additional support costs (increased SVMI headcount, training/assessment yards and constraint resolution), partly offset by decreased volume of tree work due to efforts to maintain 2023 costs to the Veg Management budget.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | 100616.61 | 127440.4547 | 26823.8447 | Yes | Primarily attributable to more additional tree work identified based on revised inspection procedure to include non-dead and dying units.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | 23455 | 13279.9317 | -10175.0683 | Yes | VMOM achieved a lower unit cost than originally planned, as well as a lower number of trees to mitigate were identified during the inspections than originally planned.
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 18000 | 35300.1363 | 17300.1363 | Yes | Variance is attributable to increased requirements and demand, which included increasing demand on O&M support including Live Help Desk, additional licenses purchased for end users of Routine/2nd Patrol, implementation of VC Pole Clearing Program to meet regulatory commitments, requirements and user story writing in addition to the PMO and Focus Tree Inspection enhancements. The costs associated with completing the VM-20 and VM-21 objectives have been captured here as part of the development costs of the overall One VM application.
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | 0 | 0 | 0 | No
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | 0 | 0 | 0 | No
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | 5006 | 25828.3124 | 20822.3124 | Yes | Primarily increase due to the original reported $ did not include the work performed in Dist. Routine and Pole Clearing, and additional expenses actualized in Jan’25 due to defer expense was being recognized after accounting and regulatory review.
Total | [5 empty] | 1349384.8959 | 1322524.4222 | -26860.4737

## 2023 Capital Summary
Capital 2023 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiative Name | 2023 Planned Budget (as reported in the WMP in 1,000s) | 2023 Actual Expenditure (in 1,000s) | Variance | Met Threshold for Variance Explanation (greater than 10%) | Detailed explanation of the reason for the discrepancy
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | - | - | - | No
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | - | - | - | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | - | - | - | No
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | No
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | - | - | - | No
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | - | - | - | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | 0 | 0 | 0 | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | - | - | - | No
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | - | - | - | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | 0 | 0 | 0 | No
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | 67504.2203 | 125029 | 57524.7797 | Yes | Increased volume of overhead miles completed 144.8 miles compared to the original plan of 140 miles coupled with higher units cost led to overall expenditures. *The GH-01 target includes both overhead and underground miles. To prevent double counting costs, the expenditures related to underground work are shown in GH-04.
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | 1233980.7283 | 1151452 | -82528.7283 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | 14134.1732 | 17282 | 3147.8268 | Yes | Costs for transmission hardening increased over the original forecast due to three major drivers: -Access roads needed improvement requiring civil construction work such as grading and/or gravel. -Increased use of helicopter required to continue construction due to inclement weather and wet access roads. -Clearance cancellations due to inclement weather resulted in extra mobilizations.
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | 5000 | 2673 | -2327 | Yes | Reduced costs by collaboratively identifying efficiencies working with tag crews and leveraging existing clearances.
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | 12679.2 | 12151.24 | -527.96 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | 3796.5281 | 5190 | 1393.4719 | Yes | Additional 2023 expenditures due to higher unit cost driven by transitioning to new regional vendors.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 3169.8 | 1809.29 | -1360.51 | Yes | PG&E was able to achieve operational efficiencies. There were some scope changes from replacement to removal only, which the cost is lower due to not replacing with SCADA enable devices.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | 27962.0933 | 18258 | -9704.0933 | Yes | Was able to achieve execution efficiencies by bundling fuse replacements with other projects, reducing the overall cost while completing the targeted units.
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | - | - | - | No
Target | Grid Design, Operations and Maintenance | 8.1.8.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | 15901.3824 | 12743 | -3158.3824 | Yes | Updated Activity from Grid Settings to reduce Wildifire Risk to Other grid topology improvements to minimize risk of ignitions. Less units completed than planned.
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | 0 | 0 | 0 | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | - | - | - | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | 0 | 0 | 0 | No
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | - | - | - | No
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | - | - | - | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 3008 | 3008 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 1061 | 904.3723 | -156.6277 | Yes | Driven by slightly lower scope of work to develop AWS pipelines dan tools.
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | 0 | 0 | 0 | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | 0 | 0 | - | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | 999.92 | 180 | -819.92 | Yes | 2023 budget was based on a high level forecast developed as the program was stood up. PG&E completed its WMP target units at a lower cost than expected, partially due to pre-construction and engineering being completed in 2022.
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | 999.6568 | 644 | -355.6568 | Yes | 2023 budget was based on a high level forecast developed as the program was stood up. PG&E completed its WMP target units at a lower cost than expected, partially due to pre-construction and engineering being completed in 2022.
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | - | - | - | No
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | - | - | - | No
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | - | - | - | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | - | - | - | No
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | - | - | - | No
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | 0 | - | - | No
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | - | - | - | No
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | - | - | - | No
Total | [5 empty] | 1390196.7024 | 1351323.9023 | -38872.8001

## Template (hidden)
[5 empty] | OPEX HFTD | #VALUE! | #VALUE!
[5 empty] | CAPEX HFTD | #VALUE! | #VALUE!
2023-2025 WMP Forecast vs Actual Overview
| Financials are shown in $ Thousands |  |  |  |  | #VALUE!
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiatve Name | 2023 Planned Budget (as reported in the WMP Errata in 1,000s) | 2023 Actual Expenditure HFTD (in 1,000s) | Variance | . | Threshold for change (greater than 10%) | .. | Detailed explanation of the reason for the discrepancy
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | 14931.7992 | 11326.7317 | -3605.0675 | Yes | meet
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | 11834.5776 | 11580.847 | -253.7306 | Yes | not met
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | 23346.5806 | 9547.3863 | -13799.1943 | Yes | meet
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | 3496.1115 | 3404.964 | -91.1475 | Yes | not met
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | 8700 | 7493.0565 | -1206.9435 | Yes | meet
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | 4119 | 10850.7744 | 6731.7744 | Yes | meet
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | PCC Costs | PCC Costs |  | No (PCC Costs)
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | 10177.4132 | 9168.7073 | -1008.7059 | Yes | not met
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program | 2297.8178 | 3382.2149 | 1084.397 | Yes (1:1) | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 16913.4639 | 16894.164 | -19.2999 | Yes | not met
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 1438 | 4532.0562 | 3094.0561 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | 1100 | 2908.9432 | 1808.9432 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | 23422.894 | 31626.4497 | 8203.5557 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | 2826.0332 | 1083.5342 | -1742.499 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | 2596.8896 | 1605.8621 | -991.0275 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 1181.6663 | 7.3612 | -1174.3051 | Yes | meet
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | Yes
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | 67504.2203 | 125029 | 57524.7797 | Yes | meet
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | 1233980.7283 | 1128010 | -105970.7283 | Yes | not met
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | 14134.1732 | 17282 | 3147.8268 | Yes | meet
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | 5000 | 2673 | -2327 | Yes | meet
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | 12679.2 | 12151.24 | -527.96 | Yes (49A work) | not met
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | 3796.5281 | 5190 | 1393.4719 | Yes (2AR work) | meet | -10222.2785
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 3169.8 | 1809.29 | -1360.51 | Yes | meet | -10222.2785
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | 27962.0933 | 18258 | -9704.0933 | Yes | meet | -10222.2785
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | 1873.5091 | 4847 | 2973.4909 | Yes | meet | 16914.605
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | 1442.7149 | 1538.7305 | 96.0157 | Yes | not met | 211.6761
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 1737.8944 | 1853.5548 | 115.6605 | Yes | not met | 211.6761
Target | Grid Design, Operations and Maintenance | 8.1.2.10.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | 41301.1159 | 35571 | -5730.1159 | Yes | meet
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | 8783.8859 | 22725 | 13941.1141 | Yes | meet | 16914.605
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 10800 | 10610.0236 | -189.9764 | Yes | not met
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 6412.6448 | 6153.0575 | -259.5874 | Yes | not met
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 7798.5822 | 3008 | -4790.5822 | Yes | meet
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 1976.0114 | 1880.6446 | -95.3668 | Yes | not met
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | 999.92 | 180 | -819.92 | Yes | meet
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | 999.6568 | 644 | -355.6568 | Yes | meet | -6453.0511
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | PCC Costs | PCC Costs |  | No (PCC Costs)
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | 10163 | 8575.303 | -1587.697 | Yes | meet |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | 17049.5 | 16818.3226 | -231.1774 | Yes | not met
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | 0 | 0 | 0 | Yes
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | 160356.7372 | 64936.3512 | -95420.386 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 2521.7317 | 3374.6762 | 852.9445 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 407.602 | 695 | 287.398 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 1906.6667 | 1321.5244 | -585.1423 | Yes | meet
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | Reached out to LOB for allocation from VM-22 | Reached out to LOB for allocation from VM-22 |  | Yes
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | 0 | 0 | 0 | Yes
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | Reached out to LOB for info | Reached out to LOB for info |  | Yes |  |  | Reached out to LOB Nicole de la Torre for info
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | Reached out to LOB for info | Reached out to LOB for info |  | Yes |  |  | Reached out to LOB Nicole de la Torre for info
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | Reached out to LOB for info | Reached out to LOB for info |  | Yes |  |  | Reached out to LOB Nicole de la Torre for info
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | 21727 | 23798.349 | 2071.349 | Yes | not met |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | 1000 | 4210.26 | 3210.26 | Yes | meet |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | 12679 | 963.908 | -11715.092 | Yes | meet |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | 354500 | 235600 | -118900 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | 87200 | 71300 | -15900 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | See Note | See Note |  | Yes |  |  | Initiative 8.2.2.2 for 2023 included only Routine and Second Patrol. VMOM and all the other transitional programs were embedded within Fall-In Mitigation (8.2.3.4).
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 18000 | 35300.1363 | 17300.1363 | Yes | meet |  | Since modifications related to VM-19 thru VM-21 were part of a revision process that occurred the second half of 2023, the definitions of spend or tracking mechanisms were not modified accordingly. This focus has really been specific to the start of this year. All that said, for VM-19 & VM-20, there was a minimal amount of time and effort in completing the ask so any costs would be immaterial and already embedded within what has been reported.
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | See Note | See Note |  | Yes |  |  | Since modifications related to VM-19 thru VM-21 were part of a revision process that occurred the second half of 2023, the definitions of spend or tracking mechanisms were not modified accordingly. This focus has really been specific to the start of this year. All that said, for VM-19 & VM-20, there was a minimal amount of time and effort in completing the ask so any costs would be immaterial and already embedded within what has been reported.
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | See Note | See Note |  | Yes |  |  | Since modifications related to VM-19 thru VM-21 were part of a revision process that occurred the second half of 2023, the definitions of spend or tracking mechanisms were not modified accordingly. This focus has really been specific to the start of this year. All that said, for VM-19 & VM-20, there was a minimal amount of time and effort in completing the ask so any costs would be immaterial and already embedded within what has been reported.
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | 11029.6955 | 34362.5828 | 23332.8873 | Yes | meet
Total | [5 empty] | 2279275.8588 | 2026083.0072 | -253192.8515 |  |  |  | 11
[6 empty] | #VALUE! | #VALUE!
[5 empty] | Total | 2279275.8588 | 2026083.0072 | -253192.8515
Note on G42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAPEX only
Note on G55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both CAPEX & OPEX Totals
Note on G56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAPEX Only
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OPEX Only
Note on I43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both CAPEX & OPEX
Note on I55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both CAPEX & OPEX
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Free text variance explanation where difference between the actual expenditure and planned budget is more than 10% (no dollar threshold)