## 2023 DaD NullWorkDate_ARC_1,665
ProjType | PrescripID | PrescripFieldCreatedDate(PI Date) | PrescripStatus | WOLIStatus | WOLITreeWorkDate | PrescripDeadDying | HFTD | ConstraintTypes | PrescripLat | PrescripLong | Updated Notification (data as of 3/20/2025) | Updated Work Date (data as of 3/20/2025) | Updated TrimCode (data as of 3/20/2025) | Updated ITS Constraint (data as of 3/20/2025) | Updated ITS Status (data as of 3/20/2025) | Due Date Per Compliance (data as of 3/20/2025) | Notes on Resolving Constraints (data as of 3/20/2025) | VMDR-4056 Updated Notification as of 8/1/2025 | VMDR-4056 Updated Work Date as of 8/1/2025 | VMDR-4056 Updated TrimCode worked as of 8/1/2025 | VMDR-4056 Updated ITS Constraint as of 8/1/2025 | VMDR-4056 Updated ITS Status as of 8/1/2025 | VMDR-4056 Notes on Resolving Constraints as of 8/1/2025
CEMA | RX-00764026 | 2023-09-11 10:13 | Constrained | Not Completed | NULL | TRUE | Tier 2 | NULL | 39.2034 | -121.1339 | Constrained |  |  |  | NEW | 2024-03-11 | #N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-01140631 | 2023-11-13 14:23 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 39.2729 | -121.0805 | Constrained |  |  |  |  | 2024-05-13 | #N/A | Constrained |  |  |  |  | N/A
CEMA | RX-00932512 | 2023-10-06 09:38 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 37.0581 | -122.2256 | Constrained |  |  | Coastal Constraint |  | 2024-04-03 | Coastal Constraint | Completed | 2025-04-29 | 022-Major Dismantle R4 36-47.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01068605 | 2023-10-27 13:43 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.2673 | -121.0588 | Constrained |  |  | Clearance Request | Resolved | 2025-02-05 | Constraint resolved 3/18/24 but still shows prescription status of constrained, A newer constraint was added 4/22/24 | Completed | 2025-05-12 | 022-Major Dismantle R4 36-47.99 in | Debris | Closed | Tree Work Complete
CEMA | RX-01133363 | 2023-11-09 11:30 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5308 | -121.6393 | Constrained |  |  | Clearance Request | NEW | 2024-05-07 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01190169 | 2023-12-04 13:37 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 38.0337 | -122.6752 | Constrained |  |  | Clearance Request | NEW | 2024-06-03 | N/A | Constrained |  | 028-Targeted Prune R5 greater than 48 in | Primary | NEW | N/A
CEMA | RX-00161269 | 2023-05-05 09:39 | Constrained | NULL | NULL | TRUE | Tier 3 | Primary | 39.424 | -123.406 | Constrained |  |  | Clearance Request | NEW | 2023-11-01 | N/A | Inspected, No Work |  | NW - No Work | Primary | Closed | Constraint Resolved/Closed
CEMA | RX-01133373 | 2023-11-09 11:51 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5312 | -121.6387 | Constrained |  |  | Clearance Request | NEW | 2024-05-07 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01111993 | 2023-11-06 10:03 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5298 | -121.665 | Constrained |  |  | Clearance Request | NEW | 2024-05-06 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Primary | OPEN | N/A
CEMA | RX-01086728 | 2023-10-31 10:34 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5243 | -121.6779 | Constrained |  |  | Clearance Request | NEW | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Primary | OPEN | N/A
CEMA | RX-00773458 | 2023-09-12 10:41 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 38.499 | -122.9037 | Constrained |  |  | Clearance Request | NEW | 2024-03-11 | N/A | Completed | 2025-04-07 10:00 | 021-Major Dismantle R3 24-35.99 in | Primary | Closed | Constraint Resolved/Closed
CEMA | RX-01133374 | 2023-11-09 11:59 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5314 | -121.6383 | Constrained |  |  | Clearance Request | NEW | 2024-05-07 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Primary | OPEN | N/A
CEMA | RX-00658082 | 2023-08-23 14:13 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary, Primary | 38.5102 | -122.9266 | Constrained |  |  | Clearance Request | NEW | 2024-02-20 | N/A | Inspected, No Work |  | NW - No Work | Primary | Closed | Constraint Resolved/Closed
CEMA | RX-01041685 | 2023-10-24 12:56 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 38.0837 | -120.1482 | Constrained |  |  | Clearance Request | In Progress | 2024-04-22 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Primary | OPEN | N/A
CEMA | RX-01133364 | 2023-11-09 11:32 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5308 | -121.6393 | Constrained |  |  | Clearance Request | NEW | 2024-05-07 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01133420 | 2023-11-09 13:23 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5326 | -121.6347 | Constrained |  |  | Clearance Request | NEW | 2024-05-07 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Primary | OPEN | N/A
CEMA | RX-00748661 | 2023-09-07 15:54 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Secondary | 40.7205 | -122.3308 | Constrained |  |  | Clearance Request | In Progress | 2024-03-05 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00914254 | 2023-10-03 13:31 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 38.8025 | -123.1747 | Constrained |  |  | Clearance Request | NEW | 2024-04-01 | N/A | Completed | 2025-03-26 | 021-Major Dismantle R3 24-35.99 in | Primary | Closed | Tree Work Complete
CEMA | RX-00769319 | 2023-09-12 11:00 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 38.5054 | -122.9244 | Constrained |  |  | Clearance Request | NEW | 2024-03-11 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Primary | OPEN | N/A
CEMA | RX-00902752 | 2023-10-03 10:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 38.8042 | -123.1575 | Constrained |  |  | Clearance Request | NEW | 2024-04-01 | N/A | Completed | 2025-03-25 | 021-Major Dismantle R3 24-35.99 in | Primary | Closed | Tree Work Complete
CEMA | RX-01232826 | 2023-12-29 10:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.0631 | -124.1431 | Constrained |  |  | Agency Managed Lands | New | 2025-01-02 | Constraint Created | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | In Environmental Review
CEMA | RX-01229564 | 2023-12-28 13:29 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.1274 | -124.1583 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-01229478 | 2023-12-28 12:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.1346 | -124.1516 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-01074450 | 2023-10-30 13:12 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9527 | -122.5881 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Completed | 2025-06-20 | 026-Targeted Prune R3 24-35.99 in | Utility/Water Districts | Resolved | Tree Work Complete
CEMA | RX-01075397 | 2023-10-30 13:55 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9534 | -122.5907 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Completed | 2025-06-24 | 020-Major Dismantle R2 12-23.99 in | Utility/Water Districts | Resolved | Tree Work Complete
CEMA | RX-01082037 | 2023-10-31 11:04 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9567 | -122.5872 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Completed | 2025-06-12 | 025-Targeted Prune R2 12-23.99 in | Utility/Water Districts | Resolved | Tree Work Complete
CEMA | RX-01229477 | 2023-12-28 12:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.135 | -124.1512 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-01117048 | 2023-11-07 10:04 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 38.3772 | -120.555 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01117862 | 2023-11-07 09:21 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4927 | -121.882 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01148964 | 2023-11-15 13:06 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4873 | -121.888 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01141540 | 2023-11-14 09:36 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans, CalTrans | 38.3788 | -120.5432 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Constraint Created | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01227170 | 2023-12-27 11:19 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3466 | -121.6032 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-24 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-00209707 | 2023-05-18 10:15 | Constrained | NULL | NULL | TRUE | Tier 3 | City/County | 38.0052 | -122.6268 | Constrained |  |  | Agency Managed Lands | In Progress | 2023-11-14 | Constraint Created | Inspected, No Work |  | NW - No Work | Open Space/Regional Parks | Closed | Constraint Resolved/Closed
CEMA | RX-01110680 | 2023-11-06 10:52 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9307 | -120.7092 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-01229473 | 2023-12-28 10:06 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.146 | -124.1387 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-01228225 | 2023-12-28 09:55 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.1477 | -124.1373 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-01228201 | 2023-12-28 09:50 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.1477 | -124.1372 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-01228170 | 2023-12-28 09:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 41.1476 | -124.1379 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-27 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-00614926 | 2023-08-16 09:31 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.8506 | -122.4911 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Constraint Created | Completed | 2025-07-15 | 025-Targeted Prune R2 12-23.99 in | NPS | Resolved | Tree Work Complete
CEMA | RX-01032743 | 2023-10-23 12:04 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4781 | -121.8607 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-22 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01048401 | 2023-10-25 10:43 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9355 | -120.7269 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-01074337 | 2023-10-30 13:04 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9525 | -122.5871 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Utility/Water Districts | NEW | Constraint Created
CEMA | RX-01049867 | 2023-10-25 11:13 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9376 | -120.7269 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-01114984 | 2023-11-06 12:46 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.5185 | -121.9155 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01139482 | 2023-11-13 14:01 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 38.3789 | -120.543 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01116830 | 2023-11-07 09:53 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 38.3772 | -120.5553 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01218995 | 2023-12-14 13:00 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3464 | -121.5982 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-11 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01086527 | 2023-10-31 13:53 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.958 | -122.573 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Utility/Water Districts | NEW | Constraint Created
CEMA | RX-01100554 | 2023-11-02 13:15 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.5331 | -121.7301 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01116671 | 2023-11-07 09:44 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 38.3771 | -120.5554 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01146868 | 2023-11-15 09:21 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4872 | -121.8903 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01229511 | 2023-12-28 13:59 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3485 | -121.5998 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-25 | Constraint Created | Constrained |  | 025-Targeted Prune R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-00194557 | 2023-05-15 12:29 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 37.2363 | -122.1471 | Scheduled |  |  | Veg Point Refusals | Closed | 2025-03-07 |  | Completed | 2025-06-30 | 022-Major Dismantle R4 36-47.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01229515 | 2023-12-28 14:13 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3483 | -121.6001 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-25 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-00231239 | 2023-05-23 15:03 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 40.3653 | -122.2157 | Approved |  |  | Veg Point Refusals | Resolved | 2025-03-17 |  | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-01045626 | 2023-10-24 15:19 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4961 | -121.8462 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-22 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01082350 | 2023-10-31 11:18 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.434 | -121.8146 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-29 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01086529 | 2023-10-31 13:57 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9579 | -122.573 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Scheduled |  | 020-Major Dismantle R2 12-23.99 in | Utility/Water Districts | Resolved | Constraint Resolved/Closed
CEMA | RX-01180122 | 2023-11-29 11:40 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused, USFS | 40.3445 | -121.6254 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-28 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | OPEN | N/A
CEMA | RX-01229510 | 2023-12-28 13:57 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3485 | -121.5998 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-25 | Constraint Created | Constrained |  | 025-Targeted Prune R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01190640 | 2023-12-04 10:43 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3506 | -121.5837 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-03 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01086526 | 2023-10-31 13:47 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9579 | -122.5732 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Utility/Water Districts | NEW | Constraint Created
CEMA | RX-01061771 | 2023-10-26 13:20 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4915 | -121.8706 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-23 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01061868 | 2023-10-26 10:21 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9349 | -120.7269 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-01131840 | 2023-11-09 11:36 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.515 | -121.9332 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-07 | Constraint Created | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01163527 | 2023-11-21 10:53 | Constrained | NULL | NULL | TRUE | Tier 2 | Utility/water districts | 39.0633 | -121.018 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-20 | Constraint Created | Completed | 2025-07-08 | 026-Targeted Prune R3 24-35.99 in | Utility/Water Districts | Closed | Tree Work Complete
CEMA | RX-01179943 | 2023-11-29 11:24 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.3546 | -121.5774 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-28 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-01180129 | 2023-11-29 12:02 | Constrained | Not Completed | NULL | TRUE | Tier 2 | USFS, Work_Refused | 40.3444 | -121.625 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-28 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | N/A
CEMA | RX-00838962 | 2023-09-22 11:21 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 39.4473 | -121.2059 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-03-20 | Constraint Created | Inspected, No Work |  | NW - No Work | Open Space/Regional Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00965210 | 2023-10-11 11:13 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9203 | -120.6927 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00714284 | 2023-08-31 14:08 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 39.9576 | -121.6385 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-27 | Constraint Created | Completed | 2025-05-05 | 021-Major Dismantle R3 24-35.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00884562 | 2023-09-29 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 38.8762 | -123.1074 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | Constraint Created | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CALTRANS | NEW | N/A
CEMA | RX-00965216 | 2023-10-11 12:06 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9206 | -120.6935 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00936255 | 2023-10-07 11:29 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9365 | -120.7139 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-04 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00949694 | 2023-10-10 10:28 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 40.5624 | -122.2865 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-08 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Constraint Created
CEMA | RX-00966268 | 2023-10-11 13:50 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9555 | -122.5777 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Utility/Water Districts | NEW | Constraint Created
CEMA | RX-00967479 | 2023-10-11 12:03 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9205 | -120.6934 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00967480 | 2023-10-11 12:06 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9204 | -120.6933 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00944081 | 2023-10-09 14:08 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9364 | -120.7136 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Inspected, No Work |  | NW - No Work | Riparian-No water-in TOB, >6in cuts | Closed | Constraint Resolved/Closed
CEMA | RX-00970466 | 2023-10-12 10:51 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Tribal | 38.3979 | -120.5172 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Constraint Created | Scheduled |  | 019-Major Dismantle R1 4-11.99 in | Extra Work Needed | Closed | Constraint Resolved/Closed
CEMA | RX-00967475 | 2023-10-11 11:23 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9206 | -120.6943 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00936280 | 2023-10-07 11:43 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9375 | -120.7141 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-04 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00965214 | 2023-10-11 11:43 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9208 | -120.6954 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00977293 | 2023-10-12 13:11 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9568 | -122.5748 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | Constraint Created | Inspected, No Work |  | NW - No Work | Utility/Water Districts | Resolved | Constraint Resolved/Closed
CEMA | RX-00965218 | 2023-10-11 12:11 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9206 | -120.6932 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00967476 | 2023-10-11 11:30 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 38.9207 | -120.6951 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00947143 | 2023-10-07 11:57 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.9377 | -120.7139 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Constraint Created | Inspected, No Work |  | NW - No Work | Other Agency | Resolved | Constraint Resolved/Closed
CEMA | RX-00973742 | 2023-10-12 13:08 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9567 | -122.5748 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Utility/Water Districts | NEW | Constraint Created
CEMA | RX-00163487 | 2023-05-08 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.427 | -123.7798 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Constraint resolved 10/9/23 but still shows prescription status of constrained, Another constraint was added 10/9/24 | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01051895 | 2023-10-25 13:46 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.4754 | -123.0185 | Approved |  |  | Environmental Review | Resolved | 2025-03-10 |  | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | N/A
CEMA | RX-00921880 | 2023-10-04 11:47 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 41.3018 | -123.5401 | Constrained |  |  | Agency Managed Lands | Closed | 2024-12-19 | Constraint resolved 11/19/24 but still shows prescription status of constrained | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00173752 | 2023-05-09 13:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.428 | -123.7761 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Constraint resolved 2/12/25 but still shows prescription status of constrained | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01109026 | 2023-11-06 08:50 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 38.4947 | -122.9617 | Constrained |  |  | Agency Managed Lands | Resolved | 2024-05-06 | Constraint resolved 3/18/24 but still shows prescription status of constrained, A newer constraint was added 4/22/24 | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Primary | NEW | N/A
CEMA | RX-00128624 | 2023-04-27 10:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4213 | -123.7912 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-24 | Constraint resolved 4/19/24 but still shows prescription status of constrained, A newer constraint was added 5/17/24 | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00121580 | 2023-04-25 15:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3986 | -123.8085 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-23 | Constraint resolved 8/14/24 but still shows prescription status of constrained, A newer constraint was added 8/23/24 | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00851269 | 2023-09-25 10:17 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 39.6522 | -121.042 | Constrained |  |  | Agency Managed Lands | Resolved | 2024-09-13 | Constraint resolved 8/14/24 but still shows prescription status of constrained, A newer constraint was added 8/23/24 | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Primary | NEW | N/A
CEMA | RX-00091209 | 2023-04-14 10:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4068 | -123.7931 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-11 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01206357 | 2023-12-11 09:07 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 37.7135 | -122.1206 | Constrained |  |  | Agency Managed Lands | NEW | 2024-12-10 | Constraint Created | Completed | 2025-03-18 | 021-Major Dismantle R3 24-35.99 in | City/County | Closed | Tree Work Complete
CEMA | RX-00099486 | 2023-04-18 12:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3943 | -123.8009 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00108515 | 2023-04-20 14:39 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3874 | -123.8 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01000681 | 2023-10-17 13:56 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7965 | -123.565 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-05-28 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00092316 | 2023-04-14 13:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4012 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-11 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00099418 | 2023-04-18 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4086 | -123.7942 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00993981 | 2023-10-16 11:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7914 | -123.5527 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00319877 | 2023-06-13 10:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5066 | -123.7498 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01017756 | 2023-10-19 11:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.9265 | -123.6497 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01019442 | 2023-10-19 10:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8942 | -123.6283 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Completed | 2025-06-10 16:03 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01033439 | 2023-10-23 10:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8993 | -123.6415 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Completed | 2025-06-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01019439 | 2023-10-19 09:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8945 | -123.6271 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Completed | 2025-06-10 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01019448 | 2023-10-19 10:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8942 | -123.629 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Completed | 2025-06-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01044748 | 2023-10-24 11:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8877 | -123.6674 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Completed | 2025-06-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01079527 | 2023-10-31 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5581 | -123.3082 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00093019 | 2023-04-14 15:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3911 | -123.8008 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-11 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00125112 | 2023-04-26 12:52 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.4171 | -123.7946 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-23 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00125114 | 2023-04-26 12:52 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.4169 | -123.7938 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-23 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00101278 | 2023-04-19 07:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3957 | -123.7941 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00133374 | 2023-04-28 10:11 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4241 | -123.7871 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00990389 | 2023-10-16 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8898 | -123.6427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-06-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01000676 | 2023-10-17 13:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8019 | -123.5627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00229838 | 2023-05-23 10:17 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5407 | -123.7444 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01057111 | 2023-10-26 10:26 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.4753 | -123.0181 | Approved |  |  | Environmental Review | Resolved | 2025-03-10 |  | Constrained |  | 023-Major Dismantle R5 greater than 48 in | CALTRANS | NEW | N/A
CEMA | RX-01080217 | 2023-10-31 10:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5573 | -123.3071 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01093868 | 2023-11-01 12:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8486 | -123.6442 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-17 | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01069005 | 2023-10-27 11:44 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5399 | -123.002 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01101485 | 2023-11-02 13:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8399 | -123.5689 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01105955 | 2023-11-03 11:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.839 | -123.5752 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00101277 | 2023-04-19 07:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3957 | -123.7941 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00126536 | 2023-04-26 15:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4175 | -123.7913 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-23 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00102515 | 2023-04-19 11:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4021 | -123.7939 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00173751 | 2023-05-09 13:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4283 | -123.776 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00998247 | 2023-10-17 11:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7813 | -123.5467 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01093850 | 2023-11-01 11:03 | Constrained | NULL | NULL | TRUE | Tier 2 | GGNRA | 38.848 | -123.6446 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-12 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01114325 | 2023-11-06 12:02 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.9153 | -123.6534 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-09 17:30 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01118968 | 2023-11-07 11:39 | Constrained | NULL | NULL | TRUE | Tier 3 | BLM | 38.3599 | -120.5705 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | In Environmental Review | Completed | 2025-06-10 | 021-Major Dismantle R3 24-35.99 in | BLM | Closed | Tree Work Complete
CEMA | RX-01127669 | 2023-11-08 10:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.9161 | -123.6535 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-09 17:28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01120994 | 2023-11-07 10:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.9166 | -123.6497 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-17 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01222765 | 2023-12-19 11:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.163 | -123.7112 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01222767 | 2023-12-19 11:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.163 | -123.711 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00099425 | 2023-04-18 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4075 | -123.7926 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00105234 | 2023-04-20 07:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4117 | -123.7978 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-17 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00990384 | 2023-10-16 11:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.889 | -123.6382 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-06-09 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00235066 | 2023-05-24 12:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7381 | -123.8219 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | N/A
CEMA | RX-01030024 | 2023-10-23 08:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8967 | -123.6429 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Completed | 2025-06-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01044746 | 2023-10-24 10:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8877 | -123.6674 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Completed | 2025-06-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01079079 | 2023-10-31 09:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.558 | -123.3084 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01085377 | 2023-10-31 11:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5568 | -123.3047 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01086356 | 2023-10-31 13:43 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.8917 | -123.6206 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01093855 | 2023-11-01 11:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.848 | -123.6446 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-12 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01093863 | 2023-11-01 12:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8485 | -123.6443 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-17 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01009608 | 2023-10-18 10:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8926 | -123.6437 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-06-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01009625 | 2023-10-18 12:53 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.888 | -123.6308 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00088939 | 2023-04-13 12:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.399 | -123.8063 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-10 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00099423 | 2023-04-18 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4074 | -123.7925 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-16 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00105235 | 2023-04-20 07:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4117 | -123.7978 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-17 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00111249 | 2023-04-21 12:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.385 | -123.7972 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00111250 | 2023-04-21 12:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.3851 | -123.7969 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01009592 | 2023-10-18 13:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7929 | -123.5614 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-05-28 09:55 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00131719 | 2023-04-27 15:09 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4201 | -123.7887 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-24 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00133042 | 2023-04-28 09:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4214 | -123.7874 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00133046 | 2023-04-28 09:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4241 | -123.7874 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01153759 | 2023-11-16 10:22 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Open Space/Regional Parks | 37.9948 | -122.9765 | Constrained |  |  | Agency Managed Lands | NEW | 2024-11-15 | Submitted to AML/VegPermits | Constrained |  | 019-Major Dismantle R1 4-11.99 in | NPS | NEW | N/A
CEMA | RX-01145841 | 2023-11-14 13:48 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.0422 | -122.7909 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-11-13 | Returned to LOB | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | Submitted to Agency
CEMA | RX-00990391 | 2023-10-16 12:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8898 | -123.6427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-06-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00990399 | 2023-10-16 12:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission, Coastal Commission | 38.8911 | -123.645 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Completed | 2025-06-10 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01069008 | 2023-10-27 11:54 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5399 | -123.002 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01121012 | 2023-11-07 12:28 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.9141 | -123.6403 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01122809 | 2023-11-07 10:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8369 | -123.571 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01172191 | 2023-11-27 13:09 | Constrained | Not Completed | NULL | TRUE | Tier 3 | BLM | 38.3606 | -120.5875 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-28 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | BLM | Closed | Tree Work Complete
CEMA | RX-00773670 | 2023-09-12 13:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7257 | -123.4645 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01066789 | 2023-10-27 10:14 | Constrained | NULL | NULL | TRUE | Tier 3 | BLM | 38.4166 | -120.5548 | Approved |  |  | Agency Managed Lands | Closed | 2025-03-28 |  | Completed | 2025-03-20 | 021-Major Dismantle R3 24-35.99 in | BLM | Closed | Tree Work Complete
CEMA | RX-00773671 | 2023-09-12 14:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7257 | -123.4644 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00774037 | 2023-09-12 16:28 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7223 | -123.4599 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00775161 | 2023-09-13 07:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7612 | -123.5199 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776316 | 2023-09-13 10:17 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7177 | -123.4557 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776307 | 2023-09-13 10:17 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5596 | -123.3127 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776849 | 2023-09-13 10:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7654 | -123.5206 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-21 10:45 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00777072 | 2023-09-13 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5601 | -123.3121 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00753011 | 2023-09-08 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5632 | -123.3129 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00780828 | 2023-09-13 13:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8318 | -123.6209 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00783283 | 2023-09-14 08:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7072 | -123.4427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00784287 | 2023-09-14 09:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, CalTrans | 38.5605 | -123.3121 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-07-09 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00784478 | 2023-09-14 10:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5432 | -123.2816 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00786415 | 2023-09-14 11:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5649 | -123.315 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-29 | 029-Fell Tree R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00786995 | 2023-09-14 12:37 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5649 | -123.3153 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 032-Fell Tree R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00761872 | 2023-09-11 13:06 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5644 | -123.3143 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00763891 | 2023-09-11 12:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5336 | -123.2745 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00793579 | 2023-09-15 10:37 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.5436 | -123.2802 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00769796 | 2023-09-12 11:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5589 | -123.313 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00800789 | 2023-09-18 10:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5677 | -123.3186 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00800856 | 2023-09-18 10:21 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5678 | -123.3186 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-06-04 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01135392 | 2023-11-10 14:15 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 39.1345 | -121.0688 | Constrained |  |  | Veg Point Refusals | NEW | 2024-11-12 | Customer Interference Process Being Followed | Completed | 2025-04-03 | 026-Targeted Prune R3 24-35.99 in | Debris | Closed | Tree Work Complete
CEMA | RX-00801573 | 2023-09-18 11:04 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5681 | -123.3194 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | In Environmental Review
CEMA | RX-00805904 | 2023-09-18 13:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8395 | -123.63 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00807105 | 2023-09-18 13:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7948 | -123.5278 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00810863 | 2023-09-19 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5705 | -123.3241 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00810943 | 2023-09-19 11:25 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5706 | -123.3243 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00811446 | 2023-09-19 11:59 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5707 | -123.3255 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00811712 | 2023-09-19 12:16 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5709 | -123.3277 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00839176 | 2023-09-22 11:36 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5901 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00812039 | 2023-09-19 12:35 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5708 | -123.3281 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-04-28 | 029-Fell Tree R1 4-11.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00839071 | 2023-09-22 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5901 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-07-02 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839774 | 2023-09-22 12:29 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-04-28 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839913 | 2023-09-22 12:48 | Constrained | Not Completed | NULL | TRUE | Tier 2 | State Parks, Coastal Commission | 38.6066 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00841533 | 2023-09-22 11:53 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5316 | -123.2677 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00814460 | 2023-09-19 12:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5272 | -123.2618 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00814461 | 2023-09-19 12:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5271 | -123.2618 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00842175 | 2023-09-22 12:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8234 | -123.5798 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00843474 | 2023-09-23 10:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.533 | -123.2718 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01152264 | 2023-11-16 09:35 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.4974 | -122.969 | Approved |  |  | Environmental Review | Resolved | 2025-03-26 |  | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00817528 | 2023-09-19 11:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5388 | -123.2753 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00818504 | 2023-09-20 09:48 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5708 | -123.3286 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00818912 | 2023-09-20 10:14 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5713 | -123.3299 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01115155 | 2023-11-06 14:58 | Constrained | NULL | NULL | TRUE | Non-HFTD | NPS | 37.9211 | -122.7234 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-11-05 | Returned to LOB | Constrained |  | 020-Major Dismantle R2 12-23.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-00845789 | 2023-09-25 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6066 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00819295 | 2023-09-20 10:36 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5713 | -123.3303 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01115153 | 2023-11-06 14:54 | Constrained | NULL | NULL | TRUE | Non-HFTD | NPS | 37.921 | -122.7233 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-11-05 | Returned to LOB | Constrained |  | 021-Major Dismantle R3 24-35.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-00819449 | 2023-09-20 10:41 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5714 | -123.3303 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820303 | 2023-09-20 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5716 | -123.3308 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820564 | 2023-09-20 11:40 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5717 | -123.3309 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00847429 | 2023-09-25 11:17 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.607 | -123.3629 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00848108 | 2023-09-25 11:54 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3424 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00848783 | 2023-09-25 12:36 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5909 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00823062 | 2023-09-20 12:55 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.769 | -123.5154 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-08 | 020-Major Dismantle R2 12-23.99 in | Primary | Closed | Tree Work Complete
CEMA | RX-00823864 | 2023-09-20 10:30 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5367 | -123.2769 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00824088 | 2023-09-20 11:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5292 | -123.2661 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00855735 | 2023-09-26 10:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5915 | -123.3426 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 019-Major Dismantle R1 4-11.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00856525 | 2023-09-26 11:03 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5911 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00856772 | 2023-09-26 11:14 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5912 | -123.3428 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00864897 | 2023-09-27 10:04 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5921 | -123.3428 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00865409 | 2023-09-27 10:35 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans, State Parks | 38.5929 | -123.3434 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00866582 | 2023-09-27 11:44 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5941 | -123.345 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00867039 | 2023-09-27 09:51 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6124 | -123.3652 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867726 | 2023-09-27 13:05 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5963 | -123.3477 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01213911 | 2023-12-13 10:29 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3141 | -120.4505 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-05 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00869297 | 2023-09-27 10:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8149 | -123.5666 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-22 14:08 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00875697 | 2023-09-28 11:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6165 | -123.3712 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00879063 | 2023-09-28 12:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6141 | -123.367 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01223027 | 2023-12-20 10:20 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 39.3147 | -120.4594 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-07 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00905975 | 2023-10-03 11:59 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6811 | -123.422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00907866 | 2023-10-03 15:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6797 | -123.4218 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00908067 | 2023-10-03 16:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7966 | -123.5584 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-21 11:47 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00887030 | 2023-09-29 13:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8333 | -123.5849 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00915425 | 2023-10-04 14:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.821 | -123.5571 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:18 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00915497 | 2023-10-04 14:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.821 | -123.5572 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:18 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00916735 | 2023-10-04 15:11 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.82 | -123.5577 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:13 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01037058 | 2023-10-24 09:02 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 40.5187 | -122.2354 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-23 | Customer Interference Process Being Followed | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | OPEN | N/A
CEMA | RX-00894112 | 2023-10-02 10:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8228 | -123.6043 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894142 | 2023-10-02 12:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8211 | -123.6027 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Riparian-No water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-01218364 | 2023-12-14 12:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.1707 | -123.7202 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01222770 | 2023-12-19 12:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.1627 | -123.7108 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01093857 | 2023-11-01 11:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8481 | -123.6445 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-12 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01222760 | 2023-12-19 10:39 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.1671 | -123.7158 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01075389 | 2023-10-30 10:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8582 | -123.6164 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01079574 | 2023-10-31 09:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5579 | -123.3082 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01079832 | 2023-10-31 10:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5577 | -123.3077 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01085367 | 2023-10-31 10:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5573 | -123.3064 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00699372 | 2023-08-30 11:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5911 | -123.3151 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00745177 | 2023-09-07 12:34 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5617 | -123.3116 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-05 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00773679 | 2023-09-12 16:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7229 | -123.4604 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776741 | 2023-09-13 11:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7172 | -123.4558 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776360 | 2023-09-13 10:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5595 | -123.3127 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776470 | 2023-09-13 10:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5597 | -123.3124 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00752408 | 2023-09-08 11:38 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5628 | -123.3125 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00753026 | 2023-09-08 12:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5634 | -123.3131 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | In Environmental Review | Completed | 2025-04-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00779921 | 2023-09-13 12:40 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5203 | -123.2547 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00998261 | 2023-10-17 12:52 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.7791 | -123.5448 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-16 | In Environmental Review | Completed | 2025-05-22 13:48 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00998259 | 2023-10-17 12:28 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.7796 | -123.5442 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-16 | In Environmental Review | Constrained |  | 035-OFFC - Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00756966 | 2023-09-09 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5337 | -123.2763 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00756950 | 2023-09-09 11:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5335 | -123.275 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00786029 | 2023-09-14 11:31 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5646 | -123.315 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00787244 | 2023-09-14 12:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8299 | -123.6181 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01040176 | 2023-10-24 11:26 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.475 | -123.0177 | Approved |  |  | Environmental Review | Resolved | 2025-03-10 |  | Constrained |  | 023-Major Dismantle R5 greater than 48 in | CALTRANS | NEW | N/A
CEMA | RX-00789059 | 2023-09-14 11:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5391 | -123.2825 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | N/A
CEMA | RX-01051642 | 2023-10-25 13:36 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.4754 | -123.0184 | Approved |  |  | Environmental Review | Resolved | 2025-03-10 |  | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-00765654 | 2023-09-11 16:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7341 | -123.477 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00766393 | 2023-09-12 08:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7437 | -123.4966 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00767322 | 2023-09-12 09:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7471 | -123.5033 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00768299 | 2023-09-12 10:44 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.559 | -123.314 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00768328 | 2023-09-12 10:45 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.559 | -123.314 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00794402 | 2023-09-15 11:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5435 | -123.2803 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00769420 | 2023-09-12 09:21 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5345 | -123.2752 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00795391 | 2023-09-15 13:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5441 | -123.2797 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00797038 | 2023-09-15 12:31 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.552 | -123.3007 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00797110 | 2023-09-15 11:38 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans, Coastal Commission | 38.8323 | -123.6229 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01107832 | 2023-11-03 10:18 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.8814 | -123.6102 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01140802 | 2023-11-13 11:40 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.9292 | -122.7363 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01118429 | 2023-11-07 11:11 | Constrained | NULL | NULL | TRUE | Tier 3 | BLM | 38.3599 | -120.5714 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | In Environmental Review | Completed | 2025-06-18 | 020-Major Dismantle R2 12-23.99 in | BLM | Closed | Tree Work Complete
CEMA | RX-00774294 | 2023-09-12 16:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7258 | -123.4644 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776861 | 2023-09-13 11:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7173 | -123.4555 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00777563 | 2023-09-13 12:02 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, CalTrans | 38.5604 | -123.312 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-07-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00752878 | 2023-09-08 11:53 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5628 | -123.3126 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | In Environmental Review | Completed | 2025-04-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00753028 | 2023-09-08 12:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5634 | -123.313 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00780839 | 2023-09-13 13:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8324 | -123.6216 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-22 | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00785096 | 2023-09-14 10:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5437 | -123.2818 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00785831 | 2023-09-14 11:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5646 | -123.315 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00976533 | 2023-10-12 13:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8017 | -123.5753 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-11 | In Environmental Review | Completed | 2025-06-10 | 022-Major Dismantle R4 36-47.99 in | Tree Crew Access | Closed | Tree Work Complete
CEMA | RX-00759628 | 2023-09-11 09:38 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5145 | -123.2325 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-04-24 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00760789 | 2023-09-11 11:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5335 | -123.2749 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01077272 | 2023-10-30 13:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8781 | -123.6353 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-17 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00974344 | 2023-10-12 10:04 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, CalTrans | 38.7776 | -123.5408 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01077384 | 2023-10-30 13:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8966 | -123.6255 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00775611 | 2023-09-13 09:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7192 | -123.4575 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776637 | 2023-09-13 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7173 | -123.4557 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00777120 | 2023-09-13 11:31 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5441 | -123.2757 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00781339 | 2023-09-13 15:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7136 | -123.4488 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00783992 | 2023-09-14 09:38 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5603 | -123.3123 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-07-10 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00786251 | 2023-09-14 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5648 | -123.3149 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-29 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00761020 | 2023-09-11 12:10 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5636 | -123.3135 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-28 | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00761407 | 2023-09-11 12:37 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.564 | -123.3139 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00789054 | 2023-09-14 10:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5391 | -123.2823 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00970990 | 2023-10-12 08:38 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.5621 | -122.8229 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-11 | Released by ERTC/Permit | Approved |  | 038-OFFC - Major Dismantle R5 greater than 48 in | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00790054 | 2023-09-14 12:11 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5218 | -123.2594 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00793883 | 2023-09-15 10:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5665 | -123.3169 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Completed | 2025-06-05 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00970981 | 2023-10-12 08:31 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.562 | -122.8229 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-11 | Released by ERTC/Permit | Approved |  | 023-Major Dismantle R5 greater than 48 in | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00794356 | 2023-09-15 11:33 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5669 | -123.3178 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00794964 | 2023-09-15 12:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5435 | -123.2802 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00799062 | 2023-09-15 12:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.552 | -123.301 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00802166 | 2023-09-18 11:37 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5689 | -123.3201 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00967303 | 2023-10-11 17:06 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 38.6869 | -122.9432 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | Preparing Permit Application | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00964277 | 2023-10-11 13:45 | Constrained | NULL | NULL | TRUE | Non-HFTD | CalTrans | 38.7773 | -123.5406 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | Submitted to AML/VegPermits | Constrained |  | 025-Targeted Prune R2 12-23.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00805882 | 2023-09-18 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8349 | -123.6265 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00964276 | 2023-10-11 13:39 | Constrained | NULL | NULL | TRUE | Non-HFTD | CalTrans | 38.7774 | -123.5406 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00837326 | 2023-09-22 09:26 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5817 | -123.3341 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 019-Major Dismantle R1 4-11.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00837422 | 2023-09-22 09:31 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5817 | -123.3343 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00840840 | 2023-09-22 13:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00814423 | 2023-09-19 11:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5273 | -123.2625 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00814465 | 2023-09-19 12:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.527 | -123.2618 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00964273 | 2023-10-11 13:30 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.7773 | -123.5406 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00959941 | 2023-10-11 09:37 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | NULL | 38.4904 | -122.7399 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | Constraint Created | Scheduled |  | 020-Major Dismantle R2 12-23.99 in | City/County | Resolved | Constraint Resolved/Closed
CEMA | RX-00958462 | 2023-10-11 09:14 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | NULL | 38.4906 | -122.7402 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | Constraint Created | Scheduled |  | 021-Major Dismantle R3 24-35.99 in | City/County | Resolved | Constraint Resolved/Closed
CEMA | RX-00958455 | 2023-10-11 08:56 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | NULL | 38.4909 | -122.7406 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-10 | Constraint Created | Scheduled |  | 022-Major Dismantle R4 36-47.99 in | City/County | Resolved | Constraint Resolved/Closed
CEMA | RX-00841538 | 2023-09-22 12:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5326 | -123.2676 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00815641 | 2023-09-19 13:21 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8415 | -123.6335 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00815647 | 2023-09-19 13:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8419 | -123.6342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00951941 | 2023-10-10 12:02 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8848 | -121.7243 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Completed | 2025-04-09 | 021-Major Dismantle R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00951838 | 2023-10-10 11:57 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8847 | -121.7244 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Completed | 2025-04-09 | 022-Major Dismantle R4 36-47.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00818696 | 2023-09-20 10:02 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5708 | -123.3294 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00819809 | 2023-09-20 11:01 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5714 | -123.3305 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00951533 | 2023-10-10 11:43 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8847 | -121.7247 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00847663 | 2023-09-25 11:26 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6072 | -123.363 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00847693 | 2023-09-25 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5906 | -123.3425 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 030-Fell Tree R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00849029 | 2023-09-25 12:54 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6069 | -123.363 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00951367 | 2023-10-10 11:36 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8846 | -121.7246 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00822503 | 2023-09-20 09:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.843 | -123.6344 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00822524 | 2023-09-20 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8456 | -123.6397 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00848827 | 2023-09-25 12:38 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6072 | -123.3631 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00849329 | 2023-09-25 13:09 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | N/A
CEMA | RX-00824015 | 2023-09-20 13:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.537 | -123.2777 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00951274 | 2023-10-10 11:31 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8846 | -121.7246 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00951141 | 2023-10-10 11:25 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8846 | -121.7246 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00855793 | 2023-09-26 10:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5915 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00950857 | 2023-10-10 11:15 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 36.8845 | -121.7246 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-10-09 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00856425 | 2023-09-26 10:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5911 | -123.3423 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00948857 | 2023-10-10 09:30 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.4319 | -122.7065 | Constrained |  |  | Veg Point Refusals | NEW | 2024-10-09 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | N/A
CEMA | RX-00857816 | 2023-09-26 12:07 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5915 | -123.343 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00948178 | 2023-10-10 09:17 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.4319 | -122.7069 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-09 | Preparing Permit Application | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00947778 | 2023-10-10 08:53 | Constrained | NULL | NULL | TRUE | Non-HFTD | Min. Clearance Requested | 38.5158 | -122.8214 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-09 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Customer Interference | NEW | N/A
CEMA | RX-00858274 | 2023-09-26 12:36 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5921 | -123.343 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00857935 | 2023-09-26 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5917 | -123.3426 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00865574 | 2023-09-27 10:46 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5929 | -123.3436 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00933489 | 2023-10-06 13:47 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 38.4411 | -122.6941 | Constrained |  |  | Veg Point Refusals | NEW | 2024-10-07 | Customer Interference Process Being Followed | Constrained |  | 037-OFFC- Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00866691 | 2023-09-27 11:48 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.594 | -123.345 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00867481 | 2023-09-27 12:39 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6124 | -123.3651 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867700 | 2023-09-27 13:03 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5963 | -123.3477 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00933452 | 2023-10-06 13:45 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 38.4411 | -122.6941 | Constrained |  |  | Veg Point Refusals | NEW | 2024-10-07 | Customer Interference Process Being Followed | Constrained |  | 036-OFFC - Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00933368 | 2023-10-06 13:37 | Scheduled | Pending | NULL | TRUE | Non-HFTD | NULL | 38.4411 | -122.694 | Constrained |  |  | Veg Point Refusals | NEW | 2024-10-07 | Customer Interference Process Being Followed | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00869272 | 2023-09-27 10:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8146 | -123.5658 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-22 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00901895 | 2023-10-03 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.681 | -123.422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00875625 | 2023-09-28 11:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission, State Parks | 38.6045 | -123.36 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00875901 | 2023-09-28 11:55 | Constrained | Not Completed | NULL | TRUE | Tier 2 | State Parks, Coastal Commission | 38.6046 | -123.3601 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01085374 | 2023-10-31 11:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5573 | -123.3061 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01060622 | 2023-10-26 12:23 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5366 | -123.0021 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01062795 | 2023-10-26 13:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8715 | -123.6537 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Completed | 2025-06-11 | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01067516 | 2023-10-27 13:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8613 | -123.6271 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | In Environmental Review | Completed | 2025-06-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01093852 | 2023-11-01 11:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.848 | -123.6443 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Completed | 2025-06-12 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01069022 | 2023-10-27 12:02 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5397 | -123.002 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01105952 | 2023-11-03 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8389 | -123.5737 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | In Environmental Review | Completed | 2025-06-16 11:18 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01121004 | 2023-11-07 11:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.9157 | -123.6419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-09 17:30 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00937067 | 2023-10-06 12:47 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.7757 | -123.5394 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-08 | In Environmental Review | Completed | 2025-05-22 13:50 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01121013 | 2023-11-07 12:37 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.9135 | -123.6403 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01219140 | 2023-12-14 14:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.1676 | -123.7159 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01127671 | 2023-11-08 10:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.9162 | -123.653 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-09 17:29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01222768 | 2023-12-19 12:07 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.163 | -123.7112 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00931061 | 2023-10-06 10:55 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Primary | 40.4881 | -122.2326 | Constrained |  |  | Clearance Request | In Progress | 2024-10-07 | N/A | Constrained |  | 026-Targeted Prune R3 24-35.99 in | Primary | OPEN | N/A
CEMA | RX-01079166 | 2023-10-31 09:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.558 | -123.3084 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01053970 | 2023-10-25 10:59 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8843 | -123.6147 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Completed | 2025-06-16 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01114324 | 2023-11-06 11:56 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.9153 | -123.6535 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | In Environmental Review | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00921653 | 2023-10-05 10:19 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8077 | -123.591 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Completed | 2025-05-29 09:52 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00698485 | 2023-08-30 10:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5917 | -123.3209 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00743683 | 2023-09-07 10:56 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5466 | -123.2431 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-05 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776053 | 2023-09-13 09:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5593 | -123.3125 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00776233 | 2023-09-13 10:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5596 | -123.3126 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921649 | 2023-10-05 10:18 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8077 | -123.591 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Completed | 2025-05-29 09:51 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00921648 | 2023-10-05 10:12 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8078 | -123.5906 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921644 | 2023-10-05 10:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8079 | -123.5907 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921642 | 2023-10-05 10:07 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8078 | -123.5908 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921639 | 2023-10-05 09:32 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8074 | -123.5905 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00919509 | 2023-10-05 09:24 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 38.6804 | -122.9508 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00779905 | 2023-09-13 10:49 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5189 | -123.2512 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00779914 | 2023-09-13 11:14 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.519 | -123.2514 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00921637 | 2023-10-05 09:21 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.807 | -123.5901 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921635 | 2023-10-05 09:17 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8069 | -123.5901 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00781328 | 2023-09-13 13:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7151 | -123.4499 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921634 | 2023-10-05 09:14 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.807 | -123.59 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921632 | 2023-10-05 09:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8068 | -123.5899 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00783118 | 2023-09-14 08:16 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5211 | -123.2564 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00921631 | 2023-10-05 09:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8068 | -123.5898 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921628 | 2023-10-05 09:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8068 | -123.5899 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921623 | 2023-10-05 08:59 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8067 | -123.5899 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-04 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00918323 | 2023-10-04 15:42 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 38.6889 | -122.9458 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | Preparing Permit Application | Completed | 2025-03-28 | 020-Major Dismantle R2 12-23.99 in | City/County | Resolved | Tree Work Complete
CEMA | RX-00915970 | 2023-10-04 14:37 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.6717 | -123.416 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00917997 | 2023-10-04 13:42 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8039 | -123.5803 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00913260 | 2023-10-04 12:17 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8062 | -123.5892 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00913259 | 2023-10-04 12:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8062 | -123.5892 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00913255 | 2023-10-04 12:02 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.806 | -123.5888 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00911507 | 2023-10-04 10:28 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.8048 | -123.5888 | Constrained |  |  | Agency Managed Lands | NEW | 2024-10-03 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00908007 | 2023-10-03 15:13 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7111 | -122.9725 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:31 | 019-Major Dismantle R1 4-11.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00786058 | 2023-09-14 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5646 | -123.315 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-29 | 030-Fell Tree R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00760915 | 2023-09-11 12:04 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5637 | -123.3135 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00787028 | 2023-09-14 12:39 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.565 | -123.3154 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Completed | 2025-05-29 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00761127 | 2023-09-11 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5635 | -123.3136 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00761296 | 2023-09-11 12:25 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5638 | -123.3137 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-28 | 029-Fell Tree R1 4-11.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00790084 | 2023-09-14 13:38 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5214 | -123.2583 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00908005 | 2023-10-03 15:09 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7111 | -122.9725 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:30 | 019-Major Dismantle R1 4-11.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00908004 | 2023-10-03 15:00 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7111 | -122.9724 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:30 | 020-Major Dismantle R2 12-23.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00765653 | 2023-09-11 16:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7343 | -123.4769 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00908003 | 2023-10-03 14:53 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7111 | -122.9724 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:31 | 020-Major Dismantle R2 12-23.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-01200810 | 2023-12-07 10:12 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.4769 | -123.0217 | Approved |  |  | Environmental Review | Resolved | 2025-03-10 |  | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-00908002 | 2023-10-03 14:43 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7111 | -122.9724 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:30 | 019-Major Dismantle R1 4-11.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00766419 | 2023-09-12 08:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission, Coastal Commission | 38.7421 | -123.4935 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | N/A
CEMA | RX-01213979 | 2023-12-13 10:38 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3149 | -120.4505 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-06 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00793844 | 2023-09-15 10:56 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5435 | -123.2803 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00908000 | 2023-10-03 13:28 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7108 | -122.9722 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:30 | 020-Major Dismantle R2 12-23.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00907999 | 2023-10-03 11:48 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | ERTC/Permit Required | 38.7108 | -122.972 | Constrained |  |  | Environmental Review | NEW | 2024-10-02 | Released by ERTC/Permit | Completed | 2025-05-12 15:30 | 019-Major Dismantle R1 4-11.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00897225 | 2023-10-02 11:58 | Constrained | NULL | NULL | TRUE | Non-HFTD | NULL | 38.7205 | -122.9947 | Constrained |  |  | Environmental Review | NEW | 2024-10-01 | Constraint Created | Constrained |  | 035-OFFC - Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Released by ERTC/Permit
CEMA | RX-00875976 | 2023-09-28 12:00 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 38.4305 | -122.716 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-27 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | City/County | NEW | Constraint Created
CEMA | RX-01220922 | 2023-12-16 10:43 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 37.8162 | -122.1761 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-21 |  | Completed | 2025-03-19 | 022-Major Dismantle R4 36-47.99 in | Open Space/Regional Parks | Closed | Tree Work Complete
CEMA | RX-01223145 | 2023-12-20 11:14 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3149 | -120.4608 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-06 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01223208 | 2023-12-20 11:44 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3149 | -120.4617 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-07 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00875836 | 2023-09-28 11:52 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.616 | -123.3708 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-27 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00875739 | 2023-09-28 11:48 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 38.4304 | -122.7159 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-27 | Constraint Created | Constrained |  | 023-Major Dismantle R5 greater than 48 in | City/County | NEW | Constraint Created
CEMA | RX-00837952 | 2023-09-22 10:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 38.5853 | -123.339 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-23 | In Environmental Review | Completed | 2025-06-30 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00837925 | 2023-09-22 10:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 38.5853 | -123.3389 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-23 | In Environmental Review | Completed | 2025-06-30 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00830302 | 2023-09-21 11:44 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.8003 | -122.3118 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-09-20 | Customer Interference Process Being Followed | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00769987 | 2023-09-12 10:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5461 | -123.2762 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00829077 | 2023-09-21 09:50 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 38.5781 | -123.335 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-20 | In Environmental Review | Completed | 2025-07-02 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00817511 | 2023-09-19 14:08 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.7508 | -122.3213 | Constrained |  |  | Veg Point Refusals | NEW | 2024-09-19 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00812489 | 2023-09-19 12:59 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks | 38.5677 | -123.3293 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-18 | In Environmental Review | Completed | 2025-07-14 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00802692 | 2023-09-18 12:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | CalTrans | 38.6451 | -122.7772 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-09-17 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-00798441 | 2023-09-16 09:41 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.5781 | -122.4133 | Constrained |  |  | Veg Point Refusals | NEW | 2024-09-16 | Customer Interference Process Being Followed | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00798440 | 2023-09-16 09:40 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.578 | -122.4133 | Constrained |  |  | Veg Point Refusals | NEW | 2024-09-16 | Customer Interference Process Being Followed | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00755175 | 2023-09-08 15:25 | Constrained | NULL | NULL | TRUE | Non-HFTD | Riparian-No water-in TOB, >6in cuts, Request For Delay | 36.6047 | -121.8956 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-09 | Constraint Created | Scheduled |  | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00745136 | 2023-09-07 11:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.5527 | -123.3011 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-06 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00797036 | 2023-09-15 12:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5518 | -123.3005 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00736865 | 2023-09-06 13:45 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.2527 | -122.671 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-09-05 | Customer Interference Process Being Followed | Completed | 2025-04-05 | 023-Major Dismantle R5 greater than 48 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00730740 | 2023-09-05 17:08 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.2556 | -122.6518 | Constrained |  |  | Agency Managed Lands | NEW | 2024-09-04 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | City/County | NEW | N/A
CEMA | RX-00797108 | 2023-09-15 11:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8321 | -123.6223 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00771883 | 2023-09-12 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.559 | -123.3128 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00809103 | 2023-09-19 09:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5396 | -123.2754 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00837790 | 2023-09-22 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5487 | -123.2834 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00839314 | 2023-09-22 11:46 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5902 | -123.3421 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 023-Major Dismantle R5 greater than 48 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00840612 | 2023-09-22 13:39 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-26 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00841365 | 2023-09-22 14:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5907 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-25 | 023-Major Dismantle R5 greater than 48 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00814420 | 2023-09-19 11:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5273 | -123.2627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00843291 | 2023-09-23 10:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.543 | -123.2895 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00843471 | 2023-09-23 10:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5329 | -123.2716 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00843468 | 2023-09-23 09:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5322 | -123.2703 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00817525 | 2023-09-19 10:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5405 | -123.2749 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00817523 | 2023-09-19 10:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5399 | -123.2749 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00817524 | 2023-09-19 10:11 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5401 | -123.2753 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00817527 | 2023-09-19 11:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5388 | -123.2753 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00819191 | 2023-09-20 10:29 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5712 | -123.3302 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00819418 | 2023-09-20 10:39 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5714 | -123.3303 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820694 | 2023-09-20 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5718 | -123.331 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00847933 | 2023-09-25 11:41 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3424 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-26 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00847396 | 2023-09-25 11:16 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5907 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00848937 | 2023-09-25 12:47 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5909 | -123.3421 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00848621 | 2023-09-25 12:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00849326 | 2023-09-25 12:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00824011 | 2023-09-20 11:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5361 | -123.2756 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00825166 | 2023-09-20 08:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6955 | -123.4253 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00831881 | 2023-09-21 13:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.821 | -123.5833 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-19 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00861982 | 2023-09-26 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8073 | -123.5678 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-28 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00867042 | 2023-09-27 09:56 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6124 | -123.3651 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867053 | 2023-09-27 10:23 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.613 | -123.3652 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867472 | 2023-09-27 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6118 | -123.3649 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867863 | 2023-09-27 13:12 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5963 | -123.3476 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00869293 | 2023-09-27 10:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8149 | -123.5666 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-22 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00869320 | 2023-09-27 13:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8126 | -123.5699 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-22 14:23 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00875175 | 2023-09-28 11:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7993 | -123.5354 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Completed | 2025-05-21 | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00875698 | 2023-09-28 11:45 | Constrained | Not Completed | NULL | TRUE | Tier 2 | State Parks, Coastal Commission | 38.6045 | -123.36 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00901837 | 2023-10-03 09:59 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6835 | -123.4253 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00879070 | 2023-09-28 12:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6141 | -123.3669 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00879077 | 2023-09-28 12:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6142 | -123.3672 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00905996 | 2023-10-03 13:31 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6806 | -123.422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00906000 | 2023-10-03 14:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.68 | -123.4219 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00907868 | 2023-10-03 15:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.679 | -123.4218 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00887032 | 2023-09-29 13:11 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8332 | -123.5847 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00800731 | 2023-09-18 10:10 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5677 | -123.3185 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00801578 | 2023-09-18 11:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5409 | -123.2761 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00801973 | 2023-09-18 11:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5403 | -123.2764 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00802815 | 2023-09-18 12:09 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5696 | -123.3216 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00803162 | 2023-09-18 12:36 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5699 | -123.3222 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00808812 | 2023-09-19 09:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5395 | -123.2749 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00810176 | 2023-09-19 10:41 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5704 | -123.3236 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00837510 | 2023-09-22 09:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5439 | -123.2835 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00810708 | 2023-09-19 11:12 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5705 | -123.3239 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00810750 | 2023-09-19 11:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5705 | -123.324 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00811039 | 2023-09-19 09:54 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.5399 | -123.2749 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00838488 | 2023-09-22 09:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5487 | -123.2833 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00841125 | 2023-09-22 14:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5906 | -123.3421 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-25 | 021-Major Dismantle R3 24-35.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00839975 | 2023-09-22 12:56 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission, State Parks | 38.6066 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00841245 | 2023-09-22 14:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5906 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00840981 | 2023-09-22 14:04 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5905 | -123.3421 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00842178 | 2023-09-22 13:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8249 | -123.5755 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00815635 | 2023-09-19 10:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8384 | -123.6303 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00818960 | 2023-09-20 10:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5373 | -123.2761 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00846329 | 2023-09-25 10:21 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6067 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00846773 | 2023-09-25 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6068 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00820168 | 2023-09-20 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5715 | -123.3308 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820393 | 2023-09-20 11:31 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5717 | -123.3307 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820884 | 2023-09-20 11:54 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.572 | -123.3313 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820469 | 2023-09-20 11:34 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5717 | -123.3308 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00847217 | 2023-09-25 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6069 | -123.3628 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00822518 | 2023-09-20 11:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8443 | -123.6368 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00849526 | 2023-09-25 13:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3426 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00824013 | 2023-09-20 11:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.536 | -123.2756 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00824072 | 2023-09-20 10:07 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5282 | -123.2631 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00825170 | 2023-09-20 09:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6951 | -123.425 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00825176 | 2023-09-20 09:39 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6951 | -123.4251 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00855216 | 2023-09-26 10:00 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5911 | -123.3423 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00728414 | 2023-09-05 14:42 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.4922 | -122.319 | Constrained |  |  | Veg Point Refusals | NEW | 2024-09-04 | Customer Interference Process Being Followed | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00857006 | 2023-09-26 11:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.591 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-23 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00858471 | 2023-09-26 12:46 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5922 | -123.343 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 022-Major Dismantle R4 36-47.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00867071 | 2023-09-27 12:16 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5945 | -123.3455 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00867110 | 2023-09-27 12:19 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5945 | -123.3455 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00867479 | 2023-09-27 12:31 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.612 | -123.3651 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00708242 | 2023-08-31 10:59 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 40.3867 | -122.2584 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-08-30 | Customer Interference Process Being Followed | Completed | 2025-04-15 | 025-Targeted Prune R2 12-23.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00867948 | 2023-09-27 13:17 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5962 | -123.3477 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00690330 | 2023-08-29 10:07 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 40.3875 | -122.2587 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-08-28 | Customer Interference Process Being Followed | Completed | 2025-04-17 | 020-Major Dismantle R2 12-23.99 in | Riparian-No water-out TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00869696 | 2023-09-27 14:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7755 | -123.537 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-22 10:51 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00683919 | 2023-08-28 14:09 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 36.9709 | -121.9035 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-08-27 | Submitted to AML/VegPermits | Completed | 2025-06-03 | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00870035 | 2023-09-27 11:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.799 | -123.5307 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-21 11:49 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00898994 | 2023-10-03 09:25 | Constrained | NULL | NULL | TRUE | Tier 3 | Coastal Commission | 37.02 | -122.1271 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | Submitted to AML/VegPermits
CEMA | RX-00698452 | 2023-08-30 10:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5916 | -123.3212 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00707194 | 2023-08-31 09:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5907 | -123.3111 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-27 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00745272 | 2023-09-07 12:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.548 | -123.2427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00775838 | 2023-09-13 09:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5591 | -123.3126 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00683650 | 2023-08-28 13:53 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 36.9707 | -121.9026 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-08-27 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | OPEN | Submitted to Agency
CEMA | RX-00776613 | 2023-09-13 10:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5598 | -123.3122 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00663560 | 2023-08-24 10:20 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.388 | -122.2989 | Constrained |  |  | Veg Point Refusals | NEW | 2024-08-23 | Customer Interference Process Being Followed | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00632281 | 2023-08-18 10:23 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.3883 | -122.4237 | Constrained |  |  | Veg Point Refusals | NEW | 2024-08-19 | Customer Interference Process Being Followed | Constrained |  | 026-Targeted Prune R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00752880 | 2023-09-08 12:00 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5629 | -123.3127 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01223153 | 2023-12-20 11:17 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3149 | -120.4607 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-06 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00779919 | 2023-09-13 12:17 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5201 | -123.2535 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00577739 | 2023-08-09 08:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | Riparian-Water-out TOB, >6in cuts | 38.3972 | -122.871 | Constrained |  |  | Environmental Review | NEW | 2024-08-08 | Constraint Created | Constrained |  | 037-OFFC- Major Dismantle R4 36-47.99 in | Riparian | NEW | In-Hand with CMT Fielding and Bio
CEMA | RX-00568412 | 2023-08-07 14:35 | Constrained | NULL | NULL | TRUE | Non-HFTD | Riparian-Water-in TOB, >6in cuts | 38.3936 | -122.8761 | Constrained |  |  | Environmental Review | NEW | 2024-08-06 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Riparian | NEW | Released by ERTC/Permit
CEMA | RX-00756949 | 2023-09-09 11:21 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5335 | -123.2745 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00565315 | 2023-08-07 11:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5701 | -121.9298 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-12 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00549419 | 2023-08-02 15:35 | Constrained | NULL | NULL | TRUE | Non-HFTD | Riparian-Water-in TOB, >6in cuts | 38.3947 | -122.8725 | Constrained |  |  | Environmental Review | NEW | 2024-08-01 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Riparian | NEW | In-Hand with CMT Fielding and Bio
CEMA | RX-00761365 | 2023-09-11 12:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.564 | -123.3138 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-28 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00617022 | 2023-08-16 11:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.9693 | -121.8755 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-31 |  | Completed | 2025-03-17 | 027-Targeted Prune R4 36-47.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00624821 | 2023-08-17 11:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5786 | -121.949 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00790075 | 2023-09-14 13:28 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5215 | -123.2579 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00790087 | 2023-09-14 13:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5215 | -123.2582 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00794737 | 2023-09-15 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5434 | -123.2804 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00769840 | 2023-09-12 11:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7276 | -123.4683 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00769871 | 2023-09-12 12:13 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.559 | -123.3128 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00803282 | 2023-09-18 12:49 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5699 | -123.3225 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 022-Major Dismantle R4 36-47.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00805884 | 2023-09-18 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.835 | -123.6265 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00806707 | 2023-09-18 14:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7009 | -123.437 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00809255 | 2023-09-19 09:43 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5702 | -123.3232 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00837243 | 2023-09-22 09:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5817 | -123.3342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00810678 | 2023-09-19 11:09 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5705 | -123.3239 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00811748 | 2023-09-19 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5709 | -123.3277 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00811582 | 2023-09-19 12:09 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5709 | -123.3274 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00838444 | 2023-09-22 10:46 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.59 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-07-02 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839435 | 2023-09-22 11:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5902 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839628 | 2023-09-22 12:11 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5903 | -123.3418 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-07-02 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839731 | 2023-09-22 12:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00549501 | 2023-08-02 11:03 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.4215 | -122.8404 | Constrained |  |  | Veg Point Refusals | NEW | 2024-08-01 | Customer Interference Process Being Followed | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-00839667 | 2023-09-22 12:16 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5903 | -123.3418 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839813 | 2023-09-22 12:34 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00839869 | 2023-09-22 12:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | N/A
CEMA | RX-00840685 | 2023-09-22 13:45 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00538184 | 2023-08-01 10:42 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 39.0548 | -122.9398 | Constrained |  |  | Veg Point Refusals | Closed | 2024-12-16 | Customer Interference Process Being Followed | Completed | 2025-07-23 | 021-Major Dismantle R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01057204 | 2023-10-26 10:31 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.4753 | -123.0182 | Approved |  |  | Environmental Review | Resolved | 2025-03-10 |  | Constrained |  | 023-Major Dismantle R5 greater than 48 in | CALTRANS | NEW | N/A
CEMA | RX-00815638 | 2023-09-19 12:59 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8407 | -123.6327 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00815632 | 2023-09-19 10:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8385 | -123.6301 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00819111 | 2023-09-20 10:25 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5713 | -123.3301 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00819251 | 2023-09-20 10:33 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5713 | -123.3301 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820059 | 2023-09-20 11:16 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5715 | -123.3307 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820222 | 2023-09-20 11:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5715 | -123.3308 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00846983 | 2023-09-25 10:53 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6069 | -123.3628 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00847974 | 2023-09-25 11:43 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission, State Parks | 38.6072 | -123.3629 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00848048 | 2023-09-25 11:49 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3424 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00848710 | 2023-09-25 12:30 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00849549 | 2023-09-25 13:26 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3426 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-04-28 | 021-Major Dismantle R3 24-35.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00855125 | 2023-09-26 09:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.591 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00856034 | 2023-09-26 10:39 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5915 | -123.3428 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-23 | 021-Major Dismantle R3 24-35.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00830190 | 2023-09-21 10:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6968 | -123.4232 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-19 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00857127 | 2023-09-26 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5909 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-23 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00858351 | 2023-09-26 12:40 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5921 | -123.343 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00857846 | 2023-09-26 12:10 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5916 | -123.3426 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-23 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00513590 | 2023-07-26 10:30 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.6753 | -122.831 | Constrained |  |  | Agency Managed Lands | NEW | 2024-07-25 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00513525 | 2023-07-26 10:25 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.6753 | -122.8309 | Constrained |  |  | Agency Managed Lands | NEW | 2024-07-25 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00864606 | 2023-09-27 09:43 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5917 | -123.3428 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00513196 | 2023-07-26 10:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | CalTrans | 38.6743 | -122.8297 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-07-25 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00864956 | 2023-09-27 10:08 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.592 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 022-Major Dismantle R4 36-47.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00865732 | 2023-09-27 10:56 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5929 | -123.3439 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00865641 | 2023-09-27 10:51 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5931 | -123.3438 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00866195 | 2023-09-27 11:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5937 | -123.3444 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00866381 | 2023-09-27 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5941 | -123.3449 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00867476 | 2023-09-27 12:25 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.612 | -123.365 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00869170 | 2023-09-27 14:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7756 | -123.5369 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-21 10:58 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00870059 | 2023-09-27 14:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8044 | -123.5341 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-21 11:52 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00903279 | 2023-10-03 11:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.807 | -123.5476 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-21 11:53 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00905998 | 2023-10-03 14:09 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6803 | -123.4217 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00881240 | 2023-09-28 14:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.551 | -123.2851 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00908386 | 2023-10-03 09:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 37.1069 | -122.2722 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00886083 | 2023-09-29 10:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5415 | -123.2879 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00917225 | 2023-10-04 15:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8196 | -123.5582 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00894106 | 2023-10-02 10:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8226 | -123.6042 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894137 | 2023-10-02 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8216 | -123.6032 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00896125 | 2023-10-02 15:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8208 | -123.5518 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Approved |  | 020-Major Dismantle R2 12-23.99 in | Customer Interference | Closed | Constraint Resolved/Closed
CEMA | RX-00512730 | 2023-07-26 09:02 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 38.6727 | -122.8274 | Constrained |  |  | Agency Managed Lands | NEW | 2024-07-25 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00934659 | 2023-10-06 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8134 | -123.5955 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-03 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00961885 | 2023-10-11 09:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8147 | -123.5976 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 16:38 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00765639 | 2023-09-11 15:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7346 | -123.4776 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00765643 | 2023-09-11 16:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7346 | -123.4771 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00766763 | 2023-09-12 08:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7342 | -123.4767 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00512346 | 2023-07-24 12:47 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Debris | 36.5976 | -121.9538 | Scheduled |  |  | Veg Point Refusals | Closed | 2025-03-17 |  | Completed | 2025-03-13 | 021-Major Dismantle R3 24-35.99 in | Debris | Closed | Tree Work Complete
CEMA | RX-00792805 | 2023-09-15 09:33 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5655 | -123.3157 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00793020 | 2023-09-15 09:52 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5656 | -123.3159 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00793463 | 2023-09-15 10:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5659 | -123.3163 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00794481 | 2023-09-15 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.567 | -123.3179 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Completed | 2025-06-04 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00769170 | 2023-09-12 11:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5588 | -123.313 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01206771 | 2023-12-11 10:25 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Riparian-No water-out TOB, >6in cuts | 39.3382 | -121.0453 | Scheduled |  |  | Environmental Review | Resolved | 2025-03-21 |  | Inspected, No Work |  | NW - No Work | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-01185552 | 2023-11-30 12:16 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-Water-in TOB, >6in cuts | 38.4949 | -122.9905 | Approved |  |  | Environmental Review | Resolved | 2025-03-20 |  | Completed | 2025-03-19 | 020-Major Dismantle R2 12-23.99 in | Riparian | Resolved | Tree Work Complete
CEMA | RX-00769011 | 2023-09-12 11:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5588 | -123.3131 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00795307 | 2023-09-15 13:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.544 | -123.2797 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00796528 | 2023-09-15 10:56 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5399 | -123.284 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01223137 | 2023-12-20 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3147 | -120.4602 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-06 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01224028 | 2023-12-21 09:38 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3184 | -120.4316 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-05 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01224029 | 2023-12-21 09:41 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3183 | -120.4317 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-05 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00773672 | 2023-09-12 14:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.725 | -123.4621 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00798621 | 2023-09-16 10:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5436 | -123.2757 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-14 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00800989 | 2023-09-18 10:29 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.568 | -123.3186 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00802239 | 2023-09-18 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5689 | -123.3202 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00801807 | 2023-09-18 11:18 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5686 | -123.3196 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00802741 | 2023-09-18 12:04 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5697 | -123.3215 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00803682 | 2023-09-18 13:21 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5391 | -123.276 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00837726 | 2023-09-22 09:39 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.548 | -123.283 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00811273 | 2023-09-19 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5706 | -123.3252 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00839221 | 2023-09-22 11:39 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5901 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-30 | 030-Fell Tree R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839475 | 2023-09-22 11:58 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5902 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-26 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00839553 | 2023-09-22 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5903 | -123.3419 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Completed | 2025-06-26 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00840739 | 2023-09-22 13:50 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.342 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00814463 | 2023-09-19 12:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5271 | -123.2619 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00841528 | 2023-09-22 11:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.531 | -123.2669 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01067268 | 2023-10-27 13:07 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.1248 | -123.8397 | Scheduled |  |  | Agency Managed Lands | Closed | 2025-03-28 |  | Completed | 2025-03-05 | 023-Major Dismantle R5 greater than 48 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00457180 | 2023-07-13 12:40 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 37.4835 | -122.4466 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-07-12 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | In Environmental Review
CEMA | RX-00457079 | 2023-07-13 12:33 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 37.4835 | -122.4466 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-07-12 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | In Environmental Review
CEMA | RX-00815636 | 2023-09-19 12:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8407 | -123.6327 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00843470 | 2023-09-23 09:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5322 | -123.2709 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00843467 | 2023-09-23 09:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5311 | -123.2694 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00819788 | 2023-09-20 10:59 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5714 | -123.3305 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00717040 | 2023-09-01 09:21 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 38.5106 | -122.9415 | Scheduled |  |  | Veg Point Refusals | Resolved | 2025-03-10 |  | Completed | 2025-04-07 | 020-Major Dismantle R2 12-23.99 in | Delayed Approval | Closed | Tree Work Complete
CEMA | RX-00819748 | 2023-09-20 10:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5714 | -123.3304 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00821185 | 2023-09-20 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5724 | -123.3324 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00848312 | 2023-09-25 12:08 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3424 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00849394 | 2023-09-25 13:14 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3428 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | N/A
CEMA | RX-00825179 | 2023-09-20 09:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.695 | -123.4252 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00855445 | 2023-09-26 10:12 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5913 | -123.3424 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 021-Major Dismantle R3 24-35.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00858152 | 2023-09-26 12:28 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5921 | -123.343 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 022-Major Dismantle R4 36-47.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00861984 | 2023-09-26 11:55 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8079 | -123.5677 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00865038 | 2023-09-27 10:14 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5923 | -123.3432 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00865908 | 2023-09-27 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5936 | -123.3442 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00865828 | 2023-09-27 11:02 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5934 | -123.3441 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00866774 | 2023-09-27 11:54 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5939 | -123.345 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00867051 | 2023-09-27 10:01 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6123 | -123.3651 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867418 | 2023-09-27 12:45 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5966 | -123.3479 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-04-28 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00867469 | 2023-09-27 11:59 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.611 | -123.3648 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00869300 | 2023-09-27 11:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8141 | -123.5681 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-05-27 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00875731 | 2023-09-28 10:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8095 | -123.5818 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Completed | 2025-05-30 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00901921 | 2023-10-03 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6812 | -123.422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00879068 | 2023-09-28 12:28 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6141 | -123.367 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00879187 | 2023-09-28 12:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8153 | -123.5777 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Completed | 2025-05-30 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00905982 | 2023-10-03 12:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6811 | -123.4221 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00880007 | 2023-09-28 13:13 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8323 | -123.5911 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00880009 | 2023-09-28 13:18 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.8323 | -123.5911 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00880013 | 2023-09-28 13:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8318 | -123.5909 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00881241 | 2023-09-28 14:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5511 | -123.2851 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00909223 | 2023-10-04 08:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.794 | -123.56 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-21 11:47 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00915428 | 2023-10-04 13:01 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.814 | -123.5887 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00915826 | 2023-10-04 14:30 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8209 | -123.5572 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:15 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00917998 | 2023-10-04 13:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.804 | -123.5803 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00918646 | 2023-10-05 07:59 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8167 | -123.5604 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-22 11:18 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00918784 | 2023-10-05 08:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8172 | -123.5596 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-21 11:51 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00918836 | 2023-10-05 08:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8171 | -123.5593 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-22 10:26 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00894151 | 2023-10-02 13:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8224 | -123.6013 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00894108 | 2023-10-02 10:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8228 | -123.6042 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894115 | 2023-10-02 10:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8228 | -123.6043 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00931416 | 2023-10-06 11:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8136 | -123.5957 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-03 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00961892 | 2023-10-11 09:22 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8148 | -123.5984 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00961897 | 2023-10-11 09:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8141 | -123.5985 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 16:41 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00961900 | 2023-10-11 09:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.814 | -123.5987 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-29 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00937066 | 2023-10-06 11:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7897 | -123.5398 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-22 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00942394 | 2023-10-09 11:40 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.819 | -123.5989 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 16:36 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01222761 | 2023-12-19 10:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.1668 | -123.7157 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01222764 | 2023-12-19 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.1634 | -123.7116 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00683100 | 2023-08-28 13:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5915 | -123.3168 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-26 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00773667 | 2023-09-12 12:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7338 | -123.4783 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00773673 | 2023-09-12 15:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7247 | -123.4625 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00781322 | 2023-09-13 11:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7173 | -123.4553 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00758381 | 2023-09-09 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5337 | -123.2762 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00785797 | 2023-09-14 11:21 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5223 | -123.2605 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00761200 | 2023-09-11 12:19 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5636 | -123.3136 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Completed | 2025-05-28 | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00761461 | 2023-09-11 12:40 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.564 | -123.3139 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 029-Fell Tree R1 4-11.99 in | State Parks | NEW | N/A
CEMA | RX-00789061 | 2023-09-14 11:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5392 | -123.2824 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00763890 | 2023-09-11 12:09 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5335 | -123.2743 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00790057 | 2023-09-14 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5217 | -123.2593 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00719395 | 2023-09-01 11:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.5632 | -123.281 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-10 |  | Completed | 2025-03-10 | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00790061 | 2023-09-14 12:59 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5211 | -123.2565 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00790069 | 2023-09-14 13:13 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5214 | -123.2573 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00790073 | 2023-09-14 13:23 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5213 | -123.2579 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00790080 | 2023-09-14 13:36 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5214 | -123.258 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00790077 | 2023-09-14 13:33 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5214 | -123.258 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00765635 | 2023-09-11 15:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7343 | -123.4772 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00794846 | 2023-09-15 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5434 | -123.2804 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00797116 | 2023-09-15 12:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8336 | -123.623 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-13 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00799061 | 2023-09-15 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.552 | -123.3008 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00801099 | 2023-09-18 10:35 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5679 | -123.3186 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-06-04 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00802182 | 2023-09-18 11:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5403 | -123.2764 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00803214 | 2023-09-18 12:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.57 | -123.3222 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-07-02 | 029-Fell Tree R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00807271 | 2023-09-18 16:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6959 | -123.4306 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00432718 | 2023-07-08 10:05 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 37.6783 | -122.3959 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-07-08 | Customer Interference Process Being Followed | Completed | 2025-04-03 | 023-Major Dismantle R5 greater than 48 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00392546 | 2023-06-28 12:12 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | CalTrans | 40.4913 | -123.6246 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-27 | Preparing Permit Application | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-00371710 | 2023-06-23 15:05 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.4539 | -122.3175 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-24 | Customer Interference Process Being Followed | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00837874 | 2023-09-22 10:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5462 | -123.276 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00811831 | 2023-09-19 12:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5709 | -123.3278 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00839805 | 2023-09-22 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6065 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-20 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00815628 | 2023-09-19 10:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8377 | -123.6293 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 036-OFFC - Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00815645 | 2023-09-19 13:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8414 | -123.6336 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00343032 | 2023-06-20 09:10 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.3653 | -122.7864 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-20 | Customer Interference Process Being Followed | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00843279 | 2023-09-23 09:59 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5428 | -123.2894 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00843477 | 2023-09-23 10:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5333 | -123.2734 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00819003 | 2023-09-20 10:19 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5711 | -123.3301 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00334604 | 2023-06-15 13:53 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.337 | -122.9826 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-14 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00819659 | 2023-09-20 10:52 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5713 | -123.3304 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00845902 | 2023-09-25 09:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6066 | -123.3627 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00312906 | 2023-06-12 14:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.336 | -122.9941 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00312865 | 2023-06-12 14:26 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3359 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312593 | 2023-06-12 14:21 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3359 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312482 | 2023-06-12 14:17 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3359 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00312411 | 2023-06-12 14:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.336 | -122.9939 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312344 | 2023-06-12 14:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.336 | -122.9939 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312305 | 2023-06-12 14:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.336 | -122.9939 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312271 | 2023-06-12 14:04 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3361 | -122.9939 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312226 | 2023-06-12 14:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3361 | -122.9939 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312190 | 2023-06-12 13:58 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3361 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00312106 | 2023-06-12 13:55 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3361 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00820264 | 2023-09-20 11:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5715 | -123.3309 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00537304 | 2023-08-01 09:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5768 | -121.9446 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-07 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00543949 | 2023-08-02 09:55 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.578 | -121.9498 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-10 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00820802 | 2023-09-20 11:51 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.572 | -123.3313 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00820918 | 2023-09-20 11:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.572 | -123.3313 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00312060 | 2023-06-12 13:51 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3361 | -122.9941 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00624765 | 2023-08-17 11:30 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5785 | -121.949 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00848227 | 2023-09-25 12:02 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5904 | -123.3425 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-26 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00847775 | 2023-09-25 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6072 | -123.3629 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00311978 | 2023-06-12 13:47 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3361 | -122.9942 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00822511 | 2023-09-20 10:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8451 | -123.63 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00822504 | 2023-09-20 09:40 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.843 | -123.6344 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00822515 | 2023-09-20 10:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8432 | -123.6316 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00849222 | 2023-09-25 13:02 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6068 | -123.363 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00848889 | 2023-09-25 12:43 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5909 | -123.3422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-24 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00849472 | 2023-09-25 13:20 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5908 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | N/A
CEMA | RX-00824087 | 2023-09-20 11:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5296 | -123.2665 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00824084 | 2023-09-20 11:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5297 | -123.2667 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00855160 | 2023-09-26 09:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6078 | -123.3633 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00829683 | 2023-09-21 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5417 | -123.2712 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-19 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00311914 | 2023-06-12 13:43 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3362 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00856603 | 2023-09-26 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5913 | -123.3424 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | N/A
CEMA | RX-00857357 | 2023-09-26 11:43 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5909 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-23 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00311880 | 2023-06-12 13:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3362 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00856929 | 2023-09-26 11:21 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.591 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-23 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00857524 | 2023-09-26 11:51 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5909 | -123.3427 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00865496 | 2023-09-27 10:41 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, CalTrans | 38.5929 | -123.3435 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Submitted to Agency
CEMA | RX-00866290 | 2023-09-27 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.594 | -123.3447 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-18 | 022-Major Dismantle R4 36-47.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00866454 | 2023-09-27 11:35 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5942 | -123.3449 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00866521 | 2023-09-27 11:40 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5941 | -123.345 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-00867027 | 2023-09-27 09:37 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6128 | -123.3655 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00867466 | 2023-09-27 12:50 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5966 | -123.348 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-17 | 021-Major Dismantle R3 24-35.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00867468 | 2023-09-27 10:58 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.6129 | -123.3652 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00872890 | 2023-09-28 09:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.693 | -123.4249 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00901874 | 2023-10-03 10:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6809 | -123.422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00876237 | 2023-09-28 12:15 | Constrained | Not Completed | NULL | TRUE | Tier 2 | State Parks, Coastal Commission | 38.6043 | -123.3599 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00906884 | 2023-10-03 11:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8128 | -123.5867 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-30 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00909348 | 2023-10-04 08:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.678 | -123.4217 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00885569 | 2023-09-29 10:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8172 | -123.58 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00912318 | 2023-10-04 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8061 | -123.588 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00915301 | 2023-10-04 14:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.821 | -123.5571 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:17 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00917142 | 2023-10-04 15:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8196 | -123.5583 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 10:26 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00893461 | 2023-10-02 12:29 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5612 | -123.3109 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00894138 | 2023-10-02 11:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8218 | -123.603 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00894146 | 2023-10-02 12:22 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8206 | -123.6019 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00921869 | 2023-10-05 10:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6616 | -123.3974 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00921662 | 2023-10-05 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8082 | -123.5903 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-29 09:50 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00903280 | 2023-10-03 12:11 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8062 | -123.5487 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00905971 | 2023-10-03 11:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6811 | -123.4221 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00881239 | 2023-09-28 14:13 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5509 | -123.2851 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-26 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00907871 | 2023-10-03 16:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6788 | -123.4217 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00909346 | 2023-10-04 08:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.678 | -123.4217 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00909413 | 2023-10-04 09:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6785 | -123.4217 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00911689 | 2023-10-04 10:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6775 | -123.4215 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00912291 | 2023-10-04 11:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8061 | -123.588 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00916166 | 2023-10-04 14:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8202 | -123.5579 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:12 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00915732 | 2023-10-04 14:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.821 | -123.5572 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:17 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00916329 | 2023-10-04 14:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.82 | -123.5577 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:14 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00920471 | 2023-10-05 10:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8209 | -123.5591 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-22 10:44 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00894119 | 2023-10-02 10:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8228 | -123.6043 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00923195 | 2023-10-05 11:12 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.8163 | -123.5883 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-29 16:13 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00896550 | 2023-10-02 13:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8167 | -123.5844 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-29 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00961901 | 2023-10-11 09:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.814 | -123.5987 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-29 09:48 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00963342 | 2023-10-10 13:31 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5536 | -123.2735 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00966385 | 2023-10-11 13:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8021 | -123.5758 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00942413 | 2023-10-09 12:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8181 | -123.6006 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00942411 | 2023-10-09 12:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8181 | -123.6006 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00974360 | 2023-10-12 13:22 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans, Coastal Commission | 38.7794 | -123.543 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00982470 | 2023-10-13 13:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.791 | -123.5573 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00983353 | 2023-10-13 09:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8838 | -123.6402 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-06-09 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00983363 | 2023-10-13 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission, Coastal Commission | 38.8859 | -123.6353 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00983596 | 2023-10-13 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7979 | -123.5702 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-05-28 14:29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00883173 | 2023-09-29 10:30 | Constrained | Not Completed | NULL | TRUE | Tier 2 | State Parks, Coastal Commission | 38.6022 | -123.3567 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00887026 | 2023-09-29 12:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8338 | -123.5851 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00887037 | 2023-09-29 13:40 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8306 | -123.5819 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-27 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00913903 | 2023-10-04 12:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.816 | -123.5546 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-21 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00893683 | 2023-10-02 12:46 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.5604 | -123.3098 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00919876 | 2023-10-05 09:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8198 | -123.5584 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-22 09:26 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00311825 | 2023-06-12 13:36 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3363 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00311791 | 2023-06-12 13:34 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3363 | -122.994 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894111 | 2023-10-02 10:17 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8227 | -123.6043 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894132 | 2023-10-02 11:39 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8216 | -123.6032 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-27 17:17 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00311537 | 2023-06-12 13:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3366 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00931411 | 2023-10-06 10:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8114 | -123.5944 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-03 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00937062 | 2023-10-06 10:09 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7829 | -123.5409 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-22 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00963339 | 2023-10-10 13:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5495 | -123.2751 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00942395 | 2023-10-09 12:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8187 | -123.5985 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00916070 | 2023-10-04 14:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8205 | -123.5577 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:13 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00916976 | 2023-10-04 15:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8197 | -123.5582 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-22 09:25 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00894129 | 2023-10-02 11:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8244 | -123.607 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00919753 | 2023-10-05 09:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8195 | -123.5584 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | In Environmental Review | Completed | 2025-05-22 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00894124 | 2023-10-02 10:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8233 | -123.6046 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894107 | 2023-10-02 10:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8228 | -123.6042 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01062798 | 2023-10-26 11:37 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.1294 | -123.8188 | Scheduled |  |  | Agency Managed Lands | Closed | 2025-03-28 |  | Completed | 2025-03-04 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00894126 | 2023-10-02 10:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8235 | -123.6049 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894131 | 2023-10-02 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8225 | -123.6041 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00894150 | 2023-10-02 12:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8229 | -123.6019 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | In Environmental Review | Completed | 2025-05-27 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00961904 | 2023-10-11 09:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8139 | -123.5987 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-29 09:49 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01066738 | 2023-10-27 12:11 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.127 | -123.8419 | Scheduled |  |  | Agency Managed Lands | Closed | 2025-03-28 |  | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | Constraint Created
CEMA | RX-00966382 | 2023-10-11 13:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8021 | -123.5758 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00942398 | 2023-10-09 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8183 | -123.5981 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00957498 | 2023-10-10 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8148 | -123.5972 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00982471 | 2023-10-13 13:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7911 | -123.5572 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-05-27 | 035-OFFC - Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00958037 | 2023-10-10 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5489 | -123.2752 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00983358 | 2023-10-13 09:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8841 | -123.6396 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00983365 | 2023-10-13 10:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission, Coastal Commission | 38.8861 | -123.6351 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-06-09 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00931406 | 2023-10-06 10:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8109 | -123.5948 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-03 | In Environmental Review | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00961887 | 2023-10-11 09:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8147 | -123.5977 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 16:39 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00942392 | 2023-10-09 11:31 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.819 | -123.599 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 16:37 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00972455 | 2023-10-12 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8221 | -123.6014 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00952167 | 2023-10-10 11:28 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6604 | -123.3995 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00982450 | 2023-10-13 10:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7907 | -123.5605 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00311465 | 2023-06-12 13:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3366 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00983348 | 2023-10-13 08:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8822 | -123.6422 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00969171 | 2023-10-12 09:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5469 | -123.2755 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00310317 | 2023-06-12 11:37 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3367 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00952127 | 2023-10-10 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6601 | -123.4 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00310297 | 2023-06-12 11:35 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3367 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00310253 | 2023-06-12 11:31 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3367 | -122.9942 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00951907 | 2023-10-10 11:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5494 | -123.2751 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00978449 | 2023-10-13 08:28 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission, Tribal | 38.6284 | -123.3817 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Tribal Lands | NEW | Submitted to AML/VegPermits
CEMA | RX-00961895 | 2023-10-11 09:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8142 | -123.5986 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 16:40 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00952174 | 2023-10-10 11:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6605 | -123.399 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00310235 | 2023-06-12 11:29 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3367 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00982468 | 2023-10-13 13:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.791 | -123.5573 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | In Environmental Review | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00310203 | 2023-06-12 11:27 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3367 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00966380 | 2023-10-11 13:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8021 | -123.5758 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00942396 | 2023-10-09 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.8188 | -123.5984 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Completed | 2025-05-28 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00310159 | 2023-06-12 11:24 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3367 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00310131 | 2023-06-12 11:23 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3367 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00310076 | 2023-06-12 11:20 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3368 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00310042 | 2023-06-12 11:17 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3368 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00309984 | 2023-06-12 11:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3368 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00309899 | 2023-06-12 11:06 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3368 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00952139 | 2023-10-10 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6604 | -123.3992 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00410675 | 2023-07-03 13:00 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 40.4652 | -123.653 | Constrained |  |  | Agency Managed Lands | NEW | 2024-01-02 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | N/A
CEMA | RX-01007954 | 2023-10-18 13:58 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 38.4723 | -123.0063 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | Preparing Permit Application | Completed | 2025-03-27 | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Resolved | Tree Work Complete
CEMA | RX-01214363 | 2023-12-13 10:48 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3149 | -120.4504 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-06 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01189561 | 2023-12-04 10:50 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 37.3887 | -122.2765 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-03 | Preparing Permit Application | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | OPEN | Submitted to Agency
CEMA | RX-00309581 | 2023-06-12 10:48 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3368 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00309526 | 2023-06-12 10:44 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3369 | -122.9943 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00309485 | 2023-06-12 10:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3369 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01220950 | 2023-12-16 11:53 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 37.8158 | -122.1753 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-21 |  | Completed | 2025-03-19 07:16 | 025-Targeted Prune R2 12-23.99 in | Open Space/Regional Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00309448 | 2023-06-12 10:39 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3368 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00309346 | 2023-06-12 10:33 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3369 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00309265 | 2023-06-12 10:28 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.337 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00309044 | 2023-06-12 10:14 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3371 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00308983 | 2023-06-12 10:11 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3371 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00676423 | 2023-08-25 10:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9785 | -121.6396 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-21 | Preparing Permit Application | Completed | 2025-06-09 | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00702651 | 2023-08-30 10:11 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 39.9255 | -121.6485 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-26 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00308916 | 2023-06-12 10:07 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3371 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00308892 | 2023-06-12 10:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3371 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00702662 | 2023-08-30 12:01 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 39.9259 | -121.6487 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-26 | Preparing Permit Application | Completed | 2025-07-22 | 021-Major Dismantle R3 24-35.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00830868 | 2023-09-21 09:48 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 37.3747 | -122.2589 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-03-19 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | OPEN | Submitted to Agency
CEMA | RX-00902925 | 2023-10-03 11:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9926 | -121.6326 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-10 | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00914881 | 2023-10-04 11:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 40.0029 | -121.6314 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-11 | 021-Major Dismantle R3 24-35.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00393204 | 2023-06-28 12:34 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 40.4554 | -123.6943 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-26 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-01080419 | 2023-10-31 10:33 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans, Coastal Commission | 38.5573 | -123.307 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | In Environmental Review
CEMA | RX-00693915 | 2023-08-29 13:05 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 39.9252 | -121.6487 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-26 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00308525 | 2023-06-12 09:43 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3371 | -122.9944 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00789052 | 2023-09-14 10:08 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 38.5383 | -123.2806 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00676276 | 2023-08-25 10:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9787 | -121.6396 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-21 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-01209348 | 2023-12-11 12:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Riparian-No water-in TOB, >6in cuts, USFS | 39.3179 | -120.4167 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-06-06 | 020-Major Dismantle R2 12-23.99 in | Riparian | Closed | Tree Work Complete
CEMA | RX-01213885 | 2023-12-13 10:26 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3139 | -120.4503 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-05 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00308415 | 2023-06-12 09:35 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3373 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00308362 | 2023-06-12 09:32 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3373 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00308325 | 2023-06-12 09:30 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3373 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00613162 | 2023-08-15 14:07 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 39.8248 | -123.6719 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Preparing Permit Application | Completed | 2025-03-25 15:34 | 021-Major Dismantle R3 24-35.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00308193 | 2023-06-12 09:25 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3373 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00308124 | 2023-06-12 09:21 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3374 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-11 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00305088 | 2023-06-09 12:48 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.5019 | -122.338 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-10 | Constraint Created | Constrained |  | 030-Fell Tree R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00300142 | 2023-06-08 13:59 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3374 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00616887 | 2023-08-16 11:05 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.8423 | -123.6899 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | N/A
CEMA | RX-00300006 | 2023-06-08 13:55 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3374 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00299934 | 2023-06-08 13:51 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3374 | -122.9945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00299901 | 2023-06-08 13:49 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3374 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00299870 | 2023-06-08 13:48 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3374 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00299842 | 2023-06-08 13:46 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3374 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00299772 | 2023-06-08 13:42 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3375 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00564279 | 2023-08-07 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5723 | -121.9296 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-12 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00676274 | 2023-08-25 09:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9787 | -121.6396 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-21 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | No Work Review Req'd | Closed | Constraint Resolved/Closed
CEMA | RX-00676422 | 2023-08-25 10:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9787 | -121.6396 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-21 | Preparing Permit Application | Completed | 2025-06-06 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00594412 | 2023-08-11 10:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5783 | -121.9205 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-10 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-01185670 | 2023-11-30 14:09 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 37.3892 | -122.2684 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-29 | Preparing Permit Application | Constrained |  | 025-Targeted Prune R2 12-23.99 in | CALTRANS | OPEN | Submitted to Agency
CEMA | RX-00616885 | 2023-08-16 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.8419 | -123.6901 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Preparing Permit Application | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00676432 | 2023-08-25 10:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9783 | -121.6398 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-21 | Preparing Permit Application | Completed | 2025-06-06 15:41 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-01185671 | 2023-11-30 14:17 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 37.3888 | -122.2677 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-29 | Preparing Permit Application | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CALTRANS | OPEN | Submitted to Agency
CEMA | RX-00720417 | 2023-09-01 14:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9772 | -121.64 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-28 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00758486 | 2023-09-11 09:23 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 38.8163 | -122.7143 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Preparing Permit Application | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Constraint Created
CEMA | RX-00790340 | 2023-09-14 12:53 | Constrained | NULL | NULL | TRUE | Tier 3 | CalTrans | 37.3804 | -122.265 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-03-12 | Preparing Permit Application | Scheduled |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Resolved | Constraint Resolved/Closed
CEMA | RX-00907722 | 2023-10-03 13:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 40.0069 | -121.6329 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-09 15:02 | 021-Major Dismantle R3 24-35.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00912707 | 2023-10-04 11:03 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9788 | -121.6395 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-06 | 020-Major Dismantle R2 12-23.99 in | Riparian-No water-out TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00720404 | 2023-09-01 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9776 | -121.6399 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-28 | Preparing Permit Application | Completed | 2025-07-21 | 022-Major Dismantle R4 36-47.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00726633 | 2023-09-05 09:57 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.9305 | -121.6477 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-03-04 | Preparing Permit Application | Completed | 2025-07-22 | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00788976 | 2023-09-14 09:57 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 38.5382 | -123.2803 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-12 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00905578 | 2023-10-03 13:26 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9936 | -121.6325 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00803413 | 2023-09-18 13:01 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 38.57 | -123.3228 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | N/A
CEMA | RX-00921899 | 2023-10-04 14:05 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 41.3016 | -123.5407 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-02 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | N/A
CEMA | RX-00616888 | 2023-08-16 11:08 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.8422 | -123.6899 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-00720418 | 2023-09-01 14:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9781 | -121.6399 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-28 | Preparing Permit Application | Completed | 2025-06-06 15:40 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00693917 | 2023-08-29 13:23 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 39.9258 | -121.6485 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-26 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00702663 | 2023-08-30 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 39.9259 | -121.6487 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-02-26 | Preparing Permit Application | Completed | 2025-07-22 | 021-Major Dismantle R3 24-35.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00843469 | 2023-09-23 09:50 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 38.532 | -123.2703 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-21 | Preparing Permit Application | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-00908044 | 2023-10-03 13:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9802 | -121.639 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-10 | 019-Major Dismantle R1 4-11.99 in | Riparian-No water-out TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00908047 | 2023-10-03 14:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9798 | -121.6392 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | Riparian-No water-out TOB, >6in cuts | Closed | Constraint Resolved/Closed
CEMA | RX-00905579 | 2023-10-03 13:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9912 | -121.6327 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-11 14:18 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00907541 | 2023-10-03 12:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9983 | -121.6306 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00907727 | 2023-10-03 14:53 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 40.0081 | -121.6309 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-09 15:02 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00958606 | 2023-10-11 09:36 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 38.6404 | -122.7658 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-08 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Preparing Permit Application
CEMA | RX-00902927 | 2023-10-03 11:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9925 | -121.6325 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-10 15:11 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00298031 | 2023-06-08 11:37 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3375 | -122.9947 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00913699 | 2023-10-04 12:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9883 | -121.634 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-01 | Preparing Permit Application | Completed | 2025-06-11 14:23 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00950545 | 2023-10-10 10:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 39.9971 | -121.6309 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-08 | Preparing Permit Application | Completed | 2025-06-10 | 019-Major Dismantle R1 4-11.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-00193600 | 2023-05-15 12:55 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 39.0679 | -123.4526 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Released by ERTC/Permit | Completed | 2025-04-29 | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-01073142 | 2023-10-30 10:41 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5485 | -123.0013 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01076509 | 2023-10-30 12:00 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2925 | -123.8822 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01107811 | 2023-11-03 14:32 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.4987 | -122.9719 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-00297979 | 2023-06-08 11:33 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3376 | -122.9946 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01088906 | 2023-11-01 10:45 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5506 | -122.998 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01093253 | 2023-11-01 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2804 | -123.8725 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01105535 | 2023-11-03 12:07 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.4993 | -122.972 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-00293586 | 2023-06-07 13:39 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 39.7901 | -123.5434 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Released by ERTC/Permit
CEMA | RX-01216637 | 2023-12-13 11:56 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 36.2544 | -121.7875 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Released by ERTC/Permit | Completed | 2025-06-26 | 026-Targeted Prune R3 24-35.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00114567 | 2023-04-24 11:41 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.4111 | -123.7482 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-23 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | Released by ERTC/Permit
CEMA | RX-01081011 | 2023-10-31 11:03 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.283 | -123.8584 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01086007 | 2023-10-31 13:42 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5508 | -122.9981 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01088069 | 2023-11-01 09:56 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5509 | -122.9998 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00297891 | 2023-06-08 11:29 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3376 | -122.9947 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00297810 | 2023-06-08 11:24 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3376 | -122.9949 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00177451 | 2023-05-10 13:38 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 39.7401 | -123.8175 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | Riparian-Water-out TOB, >6in cuts | Closed | Constraint Resolved/Closed
CEMA | RX-00297753 | 2023-06-08 11:21 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3377 | -122.9947 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00297722 | 2023-06-08 11:19 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3377 | -122.9947 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-01069024 | 2023-10-27 12:18 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5398 | -123.0017 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01105083 | 2023-11-03 10:19 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2432 | -123.8169 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01107089 | 2023-11-03 12:59 | Constrained | Not Completed | NULL | TRUE | Tier 3 | BOR | 38.4989 | -122.9719 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | BOR | NEW | N/A
CEMA | RX-01113192 | 2023-11-06 12:16 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.4977 | -122.9697 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-01218893 | 2023-12-14 14:01 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 36.2515 | -121.7875 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-11 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00765344 | 2023-09-11 15:22 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5017 | -122.9038 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-00297652 | 2023-06-08 11:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3376 | -122.9948 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01041438 | 2023-10-24 12:39 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 40.2197 | -123.8159 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Released by ERTC/Permit | Completed | 2025-04-07 | 020-Major Dismantle R2 12-23.99 in | CALTRANS | Resolved | Tree Work Complete
CEMA | RX-01076649 | 2023-10-30 11:51 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5525 | -123.003 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 023-Major Dismantle R5 greater than 48 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01086001 | 2023-10-31 12:59 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5497 | -123.0015 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01059578 | 2023-10-26 09:50 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2488 | -123.8326 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01213893 | 2023-12-13 10:27 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3139 | -120.4503 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-05 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01063897 | 2023-10-26 11:07 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.3065 | -123.9006 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01193177 | 2023-12-05 10:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5104 | -121.9382 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-03 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-01213260 | 2023-12-11 13:37 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 36.2482 | -121.7824 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-06-10 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | Submitted to AML/VegPermits
CEMA | RX-00297618 | 2023-06-08 11:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3376 | -122.9948 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-01076653 | 2023-10-30 12:29 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5541 | -123.0031 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01060621 | 2023-10-26 11:28 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5377 | -123.0019 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00765325 | 2023-09-11 15:46 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5013 | -122.9044 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-01069001 | 2023-10-27 11:23 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5401 | -123.0018 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01069003 | 2023-10-27 11:33 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5402 | -123.0017 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01148554 | 2023-11-15 12:13 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.4993 | -122.972 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-13 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CALTRANS | NEW | N/A
CEMA | RX-01076663 | 2023-10-30 12:58 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5546 | -123.003 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00765345 | 2023-09-11 15:27 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5017 | -122.9038 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-01048667 | 2023-10-25 10:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2523 | -123.8335 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Released by ERTC/Permit | Constrained |  | 024-Targeted Prune R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01076655 | 2023-10-30 12:51 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5544 | -123.0028 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01093249 | 2023-11-01 11:40 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2805 | -123.8725 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01069026 | 2023-10-27 13:05 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5455 | -123.004 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01068958 | 2023-10-27 10:25 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.3112 | -123.9015 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01096085 | 2023-11-02 10:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.4994 | -122.9814 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-01100118 | 2023-11-02 14:10 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.4992 | -122.9769 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-01213258 | 2023-12-11 11:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.2416 | -121.7917 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-01053449 | 2023-10-25 13:10 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5335 | -123.0027 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01061225 | 2023-10-26 13:48 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 38.5001 | -122.985 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-01065173 | 2023-10-27 10:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.3114 | -123.9015 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01093261 | 2023-11-01 11:57 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2782 | -123.8723 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01097543 | 2023-11-02 11:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2264 | -123.7913 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01104755 | 2023-11-03 11:07 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5542 | -123.0025 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01105094 | 2023-11-03 10:30 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.2417 | -123.8164 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01107394 | 2023-11-03 12:59 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.3338 | -123.9163 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01213259 | 2023-12-11 13:27 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 36.2482 | -121.7823 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Released by ERTC/Permit | Constrained |  | 027-Targeted Prune R4 36-47.99 in | Tree Crew Access | NEW | Submitted to AML/VegPermits
CEMA | RX-00773699 | 2023-09-12 12:30 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 41.247 | -123.6508 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | USFS | NEW | Released by ERTC/Permit
CEMA | RX-00765318 | 2023-09-11 15:19 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5016 | -122.904 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-00818775 | 2023-09-20 10:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Tribal | 38.6939 | -122.8557 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-03-18 | Released by ERTC/Permit | Completed | 2025-03-27 15:30 | 022-Major Dismantle R4 36-47.99 in | Tribal Lands | Resolved | Constraint Resolved/Closed
CEMA | RX-00765339 | 2023-09-11 14:49 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5015 | -122.9043 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 036-OFFC - Major Dismantle R3 24-35.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-00765347 | 2023-09-11 15:44 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5013 | -122.9045 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-00297555 | 2023-06-08 11:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3377 | -122.9948 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00765337 | 2023-09-11 14:36 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5014 | -122.9041 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-00765319 | 2023-09-11 15:23 | Constrained | NULL | NULL | TRUE | Tier 3 | State Parks | 38.5017 | -122.9038 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CDFW | NEW | Released by ERTC/Permit
CEMA | RX-00812261 | 2023-09-19 12:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Tribal | 38.6995 | -122.8558 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-03-18 | Released by ERTC/Permit | Completed | 2025-03-18 | 022-Major Dismantle R4 36-47.99 in | Tribal Lands | Resolved | Tree Work Complete
CEMA | RX-00909368 | 2023-10-04 09:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.6781 | -123.4213 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-01 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00978647 | 2023-10-13 09:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Tribal, Coastal Commission | 38.6269 | -123.3805 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | Released by ERTC/Permit | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00975834 | 2023-10-12 14:59 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 40.1431 | -123.8053 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-09 | Released by ERTC/Permit | Completed | 2025-05-29 | 023-Major Dismantle R5 greater than 48 in | CALTRANS | Resolved | Tree Work Complete
CEMA | RX-01121947 | 2023-11-07 14:38 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.1372 | -122.9032 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Inspected, No Work |  | NW - No Work | NPS | Resolved | Constraint Resolved/Closed
CEMA | RX-01148891 | 2023-11-15 09:00 | Constrained | NULL | NULL | TRUE | Tier 3 | NPS, NPS | 37.997 | -122.7546 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Returned to LOB | Constrained |  | 023-Major Dismantle R5 greater than 48 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01121550 | 2023-11-07 14:18 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.136 | -122.9049 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Constrained |  | 021-Major Dismantle R3 24-35.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01121114 | 2023-11-07 13:51 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.1377 | -122.9026 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Inspected, No Work |  | NW - No Work | NPS | Closed | Constraint Resolved/Closed
CEMA | RX-01140803 | 2023-11-13 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.9292 | -122.7363 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Returned to LOB | Constrained |  | 019-Major Dismantle R1 4-11.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01121178 | 2023-11-07 13:54 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.1377 | -122.9026 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Inspected, No Work |  | NW - No Work | NPS | Closed | Constraint Resolved/Closed
CEMA | RX-01148893 | 2023-11-15 09:09 | Constrained | NULL | NULL | TRUE | Tier 3 | NPS, NPS | 37.997 | -122.7546 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Returned to LOB | Constrained |  | 023-Major Dismantle R5 greater than 48 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01158292 | 2023-11-17 14:10 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.9219 | -122.7046 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-15 | Returned to LOB | Constrained |  | 020-Major Dismantle R2 12-23.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01121297 | 2023-11-07 14:00 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.1375 | -122.9024 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Constrained |  | 021-Major Dismantle R3 24-35.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01122185 | 2023-11-07 14:47 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.1373 | -122.9028 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Constrained |  | 020-Major Dismantle R2 12-23.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01121642 | 2023-11-07 14:23 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.1359 | -122.9049 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | Returned to LOB | Constrained |  | 020-Major Dismantle R2 12-23.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01148842 | 2023-11-15 08:35 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.9985 | -122.7568 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Returned to LOB | Inspected, No Work |  | NW - No Work | NPS | Resolved | Constraint Resolved/Closed
CEMA | RX-01140804 | 2023-11-13 11:45 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.9292 | -122.7363 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Returned to LOB | Constrained |  | 019-Major Dismantle R1 4-11.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01143677 | 2023-11-14 10:11 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 38.0017 | -122.7622 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-13 | Returned to LOB | Constrained |  | 023-Major Dismantle R5 greater than 48 in | NPS | OPEN | Submitted to Agency
CEMA | RX-01157695 | 2023-11-17 13:03 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.9226 | -122.7041 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-15 | Returned to LOB | Constrained |  | 022-Major Dismantle R4 36-47.99 in | NPS | OPEN | Submitted to Agency
CEMA | RX-00164044 | 2023-05-08 11:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6989 | -123.8003 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00164159 | 2023-05-08 11:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6991 | -123.8003 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00164177 | 2023-05-08 11:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6991 | -123.8003 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00229835 | 2023-05-23 10:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5407 | -123.7445 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00270680 | 2023-06-01 12:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5268 | -123.7279 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00272314 | 2023-06-02 10:56 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6846 | -123.7894 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00272816 | 2023-06-02 10:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5254 | -123.7264 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00251790 | 2023-05-30 10:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6849 | -123.7858 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00211759 | 2023-05-18 12:55 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5504 | -123.7629 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-14 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00229843 | 2023-05-23 10:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5409 | -123.7445 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00242613 | 2023-05-25 12:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5339 | -123.7571 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-21 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00270668 | 2023-06-01 10:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.525 | -123.7304 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00270679 | 2023-06-01 12:22 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5268 | -123.7279 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00279371 | 2023-06-05 13:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6796 | -123.7837 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00324235 | 2023-06-14 10:53 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7049 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00325451 | 2023-06-14 11:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.707 | -123.8035 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00319882 | 2023-06-13 10:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5067 | -123.7498 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00321227 | 2023-06-13 11:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6999 | -123.8011 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00324238 | 2023-06-14 11:02 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7047 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00324552 | 2023-06-14 11:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.706 | -123.803 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00325452 | 2023-06-14 11:49 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.707 | -123.8034 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00333866 | 2023-06-15 13:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7107 | -123.8044 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-12 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00316727 | 2023-06-13 10:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.701 | -123.802 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00164142 | 2023-05-08 11:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.699 | -123.8003 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00173291 | 2023-05-09 13:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6792 | -123.7876 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00297240 | 2023-06-08 10:52 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3377 | -122.9948 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00229841 | 2023-05-23 10:40 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5407 | -123.7443 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00269430 | 2023-06-01 11:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6774 | -123.7874 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-28 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00270682 | 2023-06-01 12:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5268 | -123.7278 | Constrained |  |  | Agency Managed Lands | In Progress | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | OPEN | In Environmental Review
CEMA | RX-00270687 | 2023-06-01 14:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.524 | -123.7254 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00251805 | 2023-05-30 10:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6849 | -123.7858 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00278414 | 2023-06-05 12:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4916 | -123.784 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00283749 | 2023-06-06 10:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4963 | -123.7832 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00173282 | 2023-05-09 11:31 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6792 | -123.7876 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00229284 | 2023-05-23 09:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5407 | -123.7446 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00265182 | 2023-06-01 10:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.559 | -123.7251 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-28 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00240962 | 2023-05-25 11:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.535 | -123.7559 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-21 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00270652 | 2023-05-31 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5271 | -123.7366 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00272998 | 2023-06-02 11:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5514 | -123.7257 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00272810 | 2023-06-02 10:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5254 | -123.7265 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00252848 | 2023-05-30 10:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5219 | -123.7593 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00297217 | 2023-06-08 10:50 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3377 | -122.9948 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00255353 | 2023-05-30 13:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5277 | -123.7385 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00257862 | 2023-05-31 09:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6948 | -123.7967 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00283743 | 2023-06-06 10:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4961 | -123.7832 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00432430 | 2023-07-07 11:39 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS, Coastal Commission | 38.0565 | -122.8379 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-01-03 | Submitted to Agency | Inspected, Prescribed |  | 025-Targeted Prune R2 12-23.99 in | NPS | Resolved | Constraint Resolved/Closed
CEMA | RX-00293032 | 2023-06-07 13:27 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.496 | -123.787 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00293062 | 2023-06-07 14:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4934 | -123.7865 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00294258 | 2023-06-07 13:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6859 | -123.7899 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00323811 | 2023-06-14 10:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7054 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00301524 | 2023-06-08 10:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5129 | -123.7592 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-05 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00305393 | 2023-06-09 12:37 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5626 | -123.7202 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00306829 | 2023-06-09 09:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4926 | -123.7741 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00317433 | 2023-06-13 11:38 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6991 | -123.8005 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00296776 | 2023-06-08 10:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4967 | -123.7872 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-05 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00325453 | 2023-06-14 11:52 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7069 | -123.8034 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00326720 | 2023-06-14 13:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7081 | -123.8039 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00306861 | 2023-06-09 12:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4964 | -123.7759 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00333865 | 2023-06-15 13:12 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7106 | -123.8044 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-12 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00316942 | 2023-06-13 10:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7009 | -123.8019 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00321230 | 2023-06-13 12:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6978 | -123.7997 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00321239 | 2023-06-13 12:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6977 | -123.7995 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01209200 | 2023-12-11 10:10 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3164 | -120.4382 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Submitted to Agency | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | Released by ERTC/Permit
CEMA | RX-00127135 | 2023-04-26 15:57 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4355 | -123.7818 | Constrained |  |  | Agency Managed Lands | NEW | 2023-10-23 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00164171 | 2023-05-08 11:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6929 | -123.7958 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00173292 | 2023-05-09 13:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6792 | -123.7876 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00204753 | 2023-05-17 11:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6336 | -123.7803 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00240380 | 2023-05-25 10:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.48 | -123.7961 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-21 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00269421 | 2023-06-01 11:07 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6774 | -123.7874 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-28 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00270660 | 2023-05-31 13:36 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.526 | -123.7278 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00251789 | 2023-05-30 10:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6849 | -123.7858 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00277456 | 2023-06-05 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5187 | -123.7584 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00260181 | 2023-05-31 09:58 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5207 | -123.7618 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00321222 | 2023-06-13 10:53 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7012 | -123.8021 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00201762 | 2023-05-16 13:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6598 | -123.7807 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Submitted to Agency | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00201764 | 2023-05-16 13:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6599 | -123.7833 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00297154 | 2023-06-08 10:46 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3377 | -122.9947 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00297002 | 2023-06-08 10:36 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3378 | -122.9949 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00571502 | 2023-08-08 10:22 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 36.5673 | -121.9303 | Scheduled |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-11 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00296867 | 2023-06-08 10:29 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3379 | -122.9949 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00296803 | 2023-06-08 10:25 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3379 | -122.9949 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00296721 | 2023-06-08 10:21 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3379 | -122.9949 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00204977 | 2023-05-17 12:07 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6341 | -123.7801 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00185542 | 2023-05-11 11:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7383 | -123.8211 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-07 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00185544 | 2023-05-11 11:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7381 | -123.8216 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-07 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00185545 | 2023-05-11 12:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.738 | -123.8218 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-07 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00221079 | 2023-05-22 11:00 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4739 | -123.7977 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00234260 | 2023-05-24 11:19 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4765 | -123.7993 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00241129 | 2023-05-25 11:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5351 | -123.7558 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-21 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00269433 | 2023-06-01 12:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6774 | -123.7874 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-28 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00246422 | 2023-05-26 10:09 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4832 | -123.7926 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-22 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00252635 | 2023-05-30 10:46 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6849 | -123.7858 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00254700 | 2023-05-30 12:18 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.522 | -123.7581 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00260183 | 2023-05-31 11:07 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5177 | -123.7598 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 030-Fell Tree R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00163916 | 2023-05-08 11:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6989 | -123.8003 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00163997 | 2023-05-08 11:29 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6989 | -123.8003 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00296623 | 2023-06-08 10:17 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3379 | -122.995 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00774634 | 2023-09-12 17:05 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.7919 | -123.5068 | Inspected, Prescribed |  |  | Veg Point Refusals | Closed | 2025-04-02 |  | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Nest | NEW | N/A
CEMA | RX-00175817 | 2023-05-10 11:10 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6852 | -123.7897 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-06 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00201765 | 2023-05-16 13:44 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6599 | -123.7834 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Submitted to Agency | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00201760 | 2023-05-16 10:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6618 | -123.7838 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-13 | Submitted to Agency | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00185543 | 2023-05-11 11:48 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7383 | -123.8211 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-07 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00229844 | 2023-05-23 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5409 | -123.7445 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-20 | Submitted to Agency | Constrained |  | 031-Fell Tree R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00246492 | 2023-05-26 10:16 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4832 | -123.7926 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-22 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00246631 | 2023-05-26 10:28 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4832 | -123.7926 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-22 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00272812 | 2023-06-02 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5253 | -123.7264 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-29 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00277454 | 2023-06-05 10:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5186 | -123.7584 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00256286 | 2023-05-30 14:22 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4863 | -123.7889 | Constrained |  |  | Agency Managed Lands | NEW | 2023-11-27 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00286612 | 2023-06-06 12:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6846 | -123.789 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00287965 | 2023-06-06 12:56 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5252 | -123.727 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00297233 | 2023-06-08 10:51 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.738 | -123.8219 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-05 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00306832 | 2023-06-09 10:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4936 | -123.7725 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-06 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00296545 | 2023-06-08 10:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.338 | -122.995 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00321237 | 2023-06-13 12:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6979 | -123.7996 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01209194 | 2023-12-11 10:06 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3165 | -120.4376 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | Released by ERTC/Permit
CEMA | RX-00286613 | 2023-06-06 12:33 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6846 | -123.789 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00293020 | 2023-06-07 13:23 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4959 | -123.787 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-04 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00296774 | 2023-06-08 10:13 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.497 | -123.7871 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-05 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00324241 | 2023-06-14 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.7047 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00301549 | 2023-06-08 11:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.5119 | -123.7571 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-05 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00321226 | 2023-06-13 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6999 | -123.8011 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00321244 | 2023-06-13 12:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.698 | -123.7996 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-11 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00298310 | 2023-06-08 10:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.6845 | -123.7894 | Constrained |  |  | Agency Managed Lands | NEW | 2023-12-05 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01209154 | 2023-12-11 10:04 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3166 | -120.4377 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Submitted to Agency | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | Released by ERTC/Permit
CEMA | RX-00296481 | 2023-06-08 10:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.338 | -122.9951 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01209130 | 2023-12-11 10:02 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3165 | -120.4377 | Constrained |  |  | Agency Managed Lands | NEW | 2024-06-10 | Submitted to Agency | Constrained |  | 008-Brush Clear to Ground | CALTRANS | NEW | Released by ERTC/Permit
CEMA | RX-00838516 | 2023-09-22 10:53 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Coastal Commission | 38.5548 | -123.2637 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-10 |  | Completed | 2025-03-10 | 019-Major Dismantle R1 4-11.99 in | Delayed Approval | Closed | Tree Work Complete
CEMA | RX-00615600 | 2023-08-16 10:21 | Constrained | NULL | NULL | TRUE | Tier 2 | NPS | 37.8507 | -122.4908 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Submitted to Agency | Completed | 2025-07-16 | 025-Targeted Prune R2 12-23.99 in | NPS | Resolved | Tree Work Complete
CEMA | RX-00993978 | 2023-10-16 10:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7908 | -123.5581 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | Submitted to AML/VegPermits | Completed | 2025-05-27 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01066618 | 2023-10-27 10:24 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.8771 | -123.722 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Submitted to AML/VegPermits | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00993979 | 2023-10-16 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7908 | -123.5582 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | Submitted to AML/VegPermits | Completed | 2025-05-27 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01128699 | 2023-11-08 12:42 | Constrained | NULL | NULL | TRUE | Tier 3 | NPS | 37.9922 | -122.743 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-06 | Submitted to AML/VegPermits | Completed | 2025-04-02 | 028-Targeted Prune R5 greater than 48 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00460582 | 2023-07-13 10:43 | Constrained | NULL | NULL | TRUE | Tier 2 | City/County | 39.0055 | -123.4058 | Constrained |  |  | Agency Managed Lands | NEW | 2024-01-09 | Submitted to AML/VegPermits | Completed | 2025-04-09 | 025-Targeted Prune R2 12-23.99 in | City/County | Closed | Tree Work Complete
CEMA | RX-00726097 | 2023-09-05 12:28 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks, Coastal Commission | 38.0025 | -122.6553 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00726300 | 2023-09-05 12:43 | Constrained | NULL | NULL | TRUE | Tier 3 | Coastal Commission, Open Space/Regional Parks | 38.0013 | -122.6555 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00452769 | 2023-07-12 15:32 | Constrained | NULL | NULL | TRUE | Tier 2 | City/County | 39.0057 | -123.4054 | Constrained |  |  | Agency Managed Lands | NEW | 2024-01-08 | Submitted to AML/VegPermits | Completed | 2025-04-09 | 020-Major Dismantle R2 12-23.99 in | City/County | Closed | Tree Work Complete
CEMA | RX-00296449 | 2023-06-08 10:06 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.338 | -122.9952 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-07 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01038034 | 2023-10-24 09:36 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Other | 38.4693 | -123.0077 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-01105913 | 2023-11-03 12:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Open Space/Regional Parks | 38.0803 | -122.8663 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | NPS | NEW | N/A
CEMA | RX-01025166 | 2023-10-20 13:44 | Constrained | NULL | NULL | TRUE | Tier 2 | USFS | 41.3921 | -123.4944 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-17 | Submitted to AML/VegPermits | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Tribal Lands | NEW | Submitted to AML/VegPermits
CEMA | RX-00735603 | 2023-09-06 11:04 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5057 | -123.1905 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Completed | 2025-06-20 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00749550 | 2023-09-07 15:42 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9571 | -122.6089 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-05 | Submitted to AML/VegPermits | Scheduled |  | 023-Major Dismantle R5 greater than 48 in | Utility/Water Districts | Resolved | Constraint Resolved/Closed
CEMA | RX-00752484 | 2023-09-08 11:50 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5494 | -123.2447 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | Submitted to AML/VegPermits | Completed | 2025-07-14 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-01038033 | 2023-10-24 09:32 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Other | 38.4693 | -123.0077 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00749540 | 2023-09-07 13:59 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9558 | -122.6187 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-05 | Submitted to AML/VegPermits | Completed | 2025-06-26 | 026-Targeted Prune R3 24-35.99 in | Utility/Water Districts | Resolved | Tree Work Complete
CEMA | RX-00805319 | 2023-09-18 09:35 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5056 | -123.191 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | Submitted to AML/VegPermits | Completed | 2025-06-20 14:30 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01085369 | 2023-10-31 10:54 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5573 | -123.3063 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-29 | Submitted to AML/VegPermits | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-00452773 | 2023-07-12 16:02 | Constrained | NULL | NULL | TRUE | Tier 2 | City/County | 39.0056 | -123.4059 | Constrained |  |  | Agency Managed Lands | NEW | 2024-01-08 | Submitted to AML/VegPermits | Completed | 2025-04-09 | 025-Targeted Prune R2 12-23.99 in | City/County | Closed | Tree Work Complete
CEMA | RX-00620379 | 2023-08-16 15:45 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4625 | -123.7905 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-01107569 | 2023-11-03 12:41 | Constrained | NULL | NULL | TRUE | Tier 3 | NPS | 38.0171 | -122.7655 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Submitted to AML/VegPermits | Completed | 2025-04-02 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01107571 | 2023-11-03 12:43 | Constrained | NULL | NULL | TRUE | Tier 3 | NPS | 38.0171 | -122.7656 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Submitted to AML/VegPermits | Completed | 2025-04-02 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01148888 | 2023-11-15 08:49 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 37.9987 | -122.7556 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-13 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | NPS | NEW | N/A
CEMA | RX-00725702 | 2023-09-05 12:00 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks, Coastal Commission | 38.0029 | -122.6553 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00749544 | 2023-09-07 14:21 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts, Utility/water districts | 37.9558 | -122.6167 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-05 | Submitted to AML/VegPermits | Completed | 2025-06-17 | 019-Major Dismantle R1 4-11.99 in | Utility/Water Districts | Resolved | Tree Work Complete
CEMA | RX-00756076 | 2023-09-08 14:11 | Constrained | NULL | NULL | TRUE | Tier 3 | Utility/water districts | 37.9515 | -122.5985 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-06 | Submitted to AML/VegPermits | Completed | 2025-06-24 | 020-Major Dismantle R2 12-23.99 in | Utility/Water Districts | Resolved | Tree Work Complete
CEMA | RX-00815910 | 2023-09-19 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.7029 | -123.4271 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00618064 | 2023-08-16 13:07 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 38.0025 | -122.6553 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00620198 | 2023-08-16 15:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 39.4626 | -123.7905 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00715649 | 2023-09-01 09:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5078 | -123.1932 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-28 | Submitted to AML/VegPermits | Completed | 2025-06-17 | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-00723820 | 2023-09-05 10:13 | Constrained | NULL | NULL | TRUE | Tier 3 | Coastal Commission, Open Space/Regional Parks | 38.0086 | -122.6548 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00726353 | 2023-09-05 12:47 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks, Coastal Commission | 38.0013 | -122.6555 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00735503 | 2023-09-06 12:30 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.5462 | -123.239 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-04 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00799988 | 2023-09-16 13:24 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission | 38.547 | -123.231 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-18 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00617913 | 2023-08-16 13:02 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 38.0029 | -122.6553 | Constrained |  |  | Agency Managed Lands | NEW | 2024-02-12 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Open Space/Regional Parks | NEW | N/A
CEMA | RX-00780834 | 2023-09-13 13:16 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 38.8319 | -123.6215 | Constrained |  |  | Agency Managed Lands | NEW | 2024-03-11 | Submitted to AML/VegPermits | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | Submitted to Agency
CEMA | RX-01067626 | 2023-10-27 11:31 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9962 | -123.927 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-24 | #N/A | Completed | 2025-03-06 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102199 | 2023-11-02 10:32 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9922 | -123.9247 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01108014 | 2023-11-03 13:00 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0198 | -123.9338 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01108019 | 2023-11-03 13:12 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0198 | -123.9338 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01108017 | 2023-11-03 13:04 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0198 | -123.9338 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01094158 | 2023-11-01 13:31 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9914 | -123.9249 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-29 | #N/A | Completed | 2025-03-06 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102200 | 2023-11-02 11:01 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9939 | -123.9243 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102205 | 2023-11-02 15:02 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0077 | -123.9285 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01108007 | 2023-11-03 12:15 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.02 | -123.9365 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 035-OFFC - Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01112573 | 2023-11-06 11:44 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0197 | -123.9338 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | #N/A | Completed | 2025-03-05 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102206 | 2023-11-02 15:11 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0075 | -123.9285 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01107915 | 2023-11-03 11:20 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0201 | -123.9374 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 14:00 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01107921 | 2023-11-03 11:28 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0201 | -123.9374 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 14:01 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01108010 | 2023-11-03 12:52 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0198 | -123.934 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102197 | 2023-11-02 10:17 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9924 | -123.9248 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 14:30 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01102196 | 2023-11-02 10:00 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9922 | -123.9247 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102201 | 2023-11-02 11:13 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9939 | -123.9242 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 025-Targeted Prune R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01108009 | 2023-11-03 12:19 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.02 | -123.9364 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01108012 | 2023-11-03 12:55 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0198 | -123.934 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-01 | #N/A | Completed | 2025-03-05 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01067620 | 2023-10-27 10:47 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9975 | -123.9276 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-24 | #N/A | Completed | 2025-03-06 | 029-Fell Tree R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102203 | 2023-11-02 12:21 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0063 | -123.9292 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 008-Brush Clear to Ground | State Parks | Resolved | Tree Work Complete
CEMA | RX-01102204 | 2023-11-02 14:42 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0073 | -123.9285 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01067623 | 2023-10-27 11:14 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9953 | -123.9265 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-24 | #N/A | Completed | 2025-03-06 14:33 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Constraint Resolved/Closed
CEMA | RX-01102198 | 2023-11-02 10:25 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 39.9922 | -123.9247 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-04-30 | #N/A | Completed | 2025-03-06 | 020-Major Dismantle R2 12-23.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-01112586 | 2023-11-06 12:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks | 40.0185 | -123.933 | Constrained |  |  | Agency Managed Lands | In Progress | 2024-05-06 | #N/A | Completed | 2025-03-05 | 019-Major Dismantle R1 4-11.99 in | State Parks | Resolved | Tree Work Complete
CEMA | RX-00980028 | 2023-10-13 10:39 | Constrained | Not Completed | NULL | TRUE | Tier 3 | CalTrans | 39.4847 | -121.0399 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-10 | #N/A | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-01031952 | 2023-10-23 11:25 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required | 39.2372 | -121.0672 | Constrained |  |  | Environmental Review | NEW | 2024-04-22 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01039048 | 2023-10-24 09:31 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required | 39.2443 | -121.0661 | Constrained |  |  | Environmental Review | NEW | 2024-04-22 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00084301 | 2023-04-12 10:46 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required | 39.2166 | -121.0821 | Constrained |  |  | Environmental Review | NEW | 2023-10-09 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00083406 | 2023-04-12 07:44 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required | 39.2141 | -121.0869 | Constrained |  |  | Environmental Review | NEW | 2023-10-09 | Constraint Created | Inspected, No Work |  | NW - No Work | Riparian-Water-in TOB, <6in cuts | Closed | Constraint Resolved/Closed
CEMA | RX-01157076 | 2023-11-17 10:53 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 39.3704 | -121.0402 | Constrained |  |  | Environmental Review | NEW | 2024-05-15 | Constraint Created | Inspected, No Work |  | NW - No Work | Site-Specific ERTC | Closed | Constraint Resolved/Closed
CEMA | RX-01157077 | 2023-11-17 10:55 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required, ERTC/Permit Required | 39.3704 | -121.0402 | Constrained |  |  | Environmental Review | NEW | 2024-05-15 | Constraint Created | Inspected, No Work |  | NW - No Work | Site-Specific ERTC | Closed | Constraint Resolved/Closed
CEMA | RX-00708922 | 2023-08-31 11:49 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-Water-in TOB, >6in cuts | 38.5447 | -123.0886 | Constrained |  |  | Environmental Review | NEW | 2024-02-27 | Constraint Created | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Riparian | NEW | N/A
CEMA | RX-01039051 | 2023-10-24 09:34 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required | 39.2443 | -121.0661 | Constrained |  |  | Environmental Review | NEW | 2024-04-22 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01158733 | 2023-11-17 14:16 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 39.3754 | -121.0759 | Constrained |  |  | Environmental Review | NEW | 2024-05-15 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01158727 | 2023-11-17 13:48 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 39.3753 | -121.0756 | Constrained |  |  | Environmental Review | NEW | 2024-05-15 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01178306 | 2023-11-29 09:54 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 39.3519 | -121.0675 | Constrained |  |  | Environmental Review | NEW | 2024-05-28 | Constraint Created | Inspected, No Work |  | NW - No Work | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-01069492 | 2023-10-27 13:08 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required, ERTC/Permit Required | 39.2806 | -121.0976 | Constrained |  |  | Environmental Review | NEW | 2024-04-24 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00828250 | 2023-09-21 09:48 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required | 39.2311 | -121.152 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01173692 | 2023-11-27 12:39 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 39.3683 | -121.0821 | Constrained |  |  | Environmental Review | NEW | 2024-05-28 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01197496 | 2023-12-05 09:58 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 39.5262 | -121.0076 | Constrained |  |  | Environmental Review | NEW | 2024-06-03 | Constraint Created | Completed | 2025-04-30 | 023-Major Dismantle R5 greater than 48 in | Riparian-Water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00886524 | 2023-09-29 10:13 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-No water-in TOB, >6in cuts | 37.0214 | -122.1299 | Constrained |  |  | Environmental Review | In Progress | 2024-03-27 | Constraint Created | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Riparian | OPEN | In-Hand with CMT Fielding and Bio
CEMA | RX-00908359 | 2023-10-03 11:14 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-Water-in TOB, >6in cuts, Coastal Commission | 37.0232 | -122.1327 | Constrained |  |  | Environmental Review | In Progress | 2024-04-01 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00996967 | 2023-10-17 09:47 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6841 | -123.1064 | Constrained |  |  | Environmental Review | NEW | 2024-04-15 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00982878 | 2023-10-13 12:43 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6829 | -123.1073 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00982883 | 2023-10-13 13:25 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6838 | -123.1065 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00996969 | 2023-10-17 09:53 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6842 | -123.1064 | Constrained |  |  | Environmental Review | NEW | 2024-04-15 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00982886 | 2023-10-13 13:35 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.684 | -123.1065 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00982882 | 2023-10-13 13:22 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6838 | -123.1065 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00996968 | 2023-10-17 09:50 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6842 | -123.1064 | Constrained |  |  | Environmental Review | NEW | 2024-04-15 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00982881 | 2023-10-13 13:15 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6837 | -123.1066 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00287581 | 2023-06-06 15:16 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3383 | -122.995 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00982884 | 2023-10-13 13:29 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.684 | -123.1065 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00982885 | 2023-10-13 13:32 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6839 | -123.1065 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00996966 | 2023-10-17 09:40 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.684 | -123.1064 | Constrained |  |  | Environmental Review | NEW | 2024-04-15 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00982888 | 2023-10-13 13:43 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6835 | -123.1065 | Constrained |  |  | Environmental Review | NEW | 2024-04-10 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-00996971 | 2023-10-17 10:04 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.6843 | -123.1063 | Constrained |  |  | Environmental Review | NEW | 2024-04-15 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Site-Specific ERTC | NEW | Constraint Created
CEMA | RX-01093894 | 2023-11-01 12:37 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 40.5055 | -121.6702 | Constrained |  |  | Environmental Review | Closed | 2024-05-20 | Constraint resolved 4/19/24 but still shows prescription status of constrained, A newer constraint was added 5/17/24 | Constrained |  | 022-Major Dismantle R4 36-47.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00725983 | 2023-09-05 12:18 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 38.5271 | -122.9536 | Constrained |  |  | Environmental Review | Resolved | 2024-03-04 | Constraint resolved 9/25/23 but still shows prescription status of constrained, A newer constraint was added 2/28/24 | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Primary | NEW | N/A
CEMA | RX-01085396 | 2023-10-31 12:34 | Constrained | NULL | NULL | TRUE | Tier 2 | Riparian-No water-out TOB, >6in cuts, Coastal Commission | 38.5564 | -123.3039 | Constrained |  |  | Environmental Review | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Riparian | NEW | In Environmental Review
CEMA | RX-00829818 | 2023-09-21 11:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Nest-Raptor- Adjacent to identified worked | 38.5804 | -123.3344 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | In Environmental Review | Completed | 2025-07-02 | 020-Major Dismantle R2 12-23.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00886536 | 2023-09-29 11:18 | Constrained | NULL | NULL | TRUE | Tier 3 | Coastal Commission | 37.021 | -122.1298 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-03-12 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00865213 | 2023-09-27 10:22 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, Riparian-No water-out TOB, <6in cuts | 38.5924 | -123.3435 | Constrained |  |  | Environmental Review | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 030-Fell Tree R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-01085391 | 2023-10-31 12:21 | Constrained | NULL | NULL | TRUE | Tier 2 | Riparian-No water-in TOB, >6in cuts, Coastal Commission | 38.5564 | -123.3041 | Constrained |  |  | Environmental Review | NEW | 2024-04-29 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00865298 | 2023-09-27 10:28 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, Riparian-Water-out TOB, >6in cuts | 38.5927 | -123.3433 | Constrained |  |  | Environmental Review | NEW | 2024-03-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00848382 | 2023-09-25 12:14 | Constrained | NULL | NULL | TRUE | Tier 2 | Riparian-No water-out TOB, >6in cuts | 38.5905 | -123.3425 | Constrained |  |  | Environmental Review | NEW | 2024-03-25 | In Environmental Review | Completed | 2025-06-25 | 020-Major Dismantle R2 12-23.99 in | Riparian | Resolved | Tree Work Complete
CEMA | RX-00829078 | 2023-09-21 09:56 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, Riparian-Water-out TOB, >6in cuts | 38.5787 | -123.3347 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Riparian | NEW | Released by ERTC/Permit
CEMA | RX-00830267 | 2023-09-21 11:41 | Constrained | NULL | NULL | TRUE | Tier 2 | Nest-Raptor- Adjacent to identified worked | 38.5808 | -123.3343 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | In Environmental Review | Completed | 2025-07-02 | 021-Major Dismantle R3 24-35.99 in | State Parks | Closed | Tree Work Complete
CEMA | RX-00205942 | 2023-05-17 13:21 | Constrained | NULL | NULL | TRUE | Tier 3 | Nest-Raptor- Adjacent to identified worked | 38.3612 | -122.9804 | Constrained |  |  | Environmental Review | NEW | 2023-11-13 | In-Hand with CMT Fielding and Bio | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Nest | NEW | In-Hand with CMT Fielding and Bio
CEMA | RX-01085381 | 2023-10-31 11:53 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans, Coastal Commission, Riparian-No water-out TOB, >6in cuts | 38.5565 | -123.3043 | Constrained |  |  | Environmental Review | NEW | 2024-04-29 | Preparing Permit Application | Constrained |  | 021-Major Dismantle R3 24-35.99 in | CALTRANS | NEW | In Environmental Review
CEMA | RX-01085385 | 2023-10-31 12:05 | Constrained | NULL | NULL | TRUE | Tier 2 | Coastal Commission, CalTrans, Riparian-No water-out TOB, >6in cuts | 38.5564 | -123.3042 | Constrained |  |  | Environmental Review | NEW | 2024-04-29 | Preparing Permit Application | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01013859 | 2023-10-19 10:36 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-No water-out TOB, >6in cuts | 38.4708 | -123.0157 | Constrained |  |  | Environmental Review | NEW | 2024-04-16 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | CALTRANS | NEW | N/A
CEMA | RX-00521986 | 2023-07-27 12:16 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Nest-Raptor | 38.5501 | -122.5237 | Constrained |  |  | Environmental Review | NEW | 2024-01-23 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00287532 | 2023-06-06 15:12 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3382 | -122.9953 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00287480 | 2023-06-06 15:09 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3382 | -122.9953 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00287453 | 2023-06-06 15:07 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3382 | -122.9953 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00287405 | 2023-06-06 15:03 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3383 | -122.9953 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00287077 | 2023-06-06 14:37 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.491 | -122.3247 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00287064 | 2023-06-06 14:36 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3385 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00522135 | 2023-07-27 12:43 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Nest-Raptor | 38.55 | -122.5237 | Constrained |  |  | Environmental Review | NEW | 2024-01-23 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00522061 | 2023-07-27 12:27 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Nest-Raptor | 38.55 | -122.5238 | Constrained |  |  | Environmental Review | NEW | 2024-01-23 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00522086 | 2023-07-27 12:33 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Nest-Raptor | 38.55 | -122.5237 | Constrained |  |  | Environmental Review | NEW | 2024-01-23 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00601830 | 2023-08-14 11:59 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Riparian-Water-in TOB, <6in cuts | 38.3909 | -122.8826 | Constrained |  |  | Environmental Review | NEW | 2024-02-12 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | Site-Specific ERTC | Resolved | Constraint Resolved/Closed
CEMA | RX-00829521 | 2023-09-21 10:58 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, Nest-Raptor- Adjacent to identified worked | 38.5801 | -123.3345 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00601630 | 2023-08-14 11:43 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Riparian-Water-in TOB, >6in cuts | 38.3909 | -122.8826 | Constrained |  |  | Environmental Review | NEW | 2024-02-12 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | Site-Specific ERTC | Resolved | Constraint Resolved/Closed
CEMA | RX-00522095 | 2023-07-27 12:36 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Nest-Raptor | 38.55 | -122.5237 | Constrained |  |  | Environmental Review | NEW | 2024-01-23 | Released by ERTC/Permit | Inspected, No Work |  | NW - No Work | State Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00829125 | 2023-09-21 10:38 | Constrained | NULL | NULL | TRUE | Tier 2 | State Parks, Nest-Raptor- Adjacent to identified worked | 38.5799 | -123.3346 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | State Parks | NEW | Released by ERTC/Permit
CEMA | RX-00830008 | 2023-09-21 11:06 | Constrained | NULL | NULL | TRUE | Tier 2 | Nest-Active- Nest removed (non raptor), Coastal Commission | 38.5478 | -123.2832 | Constrained |  |  | Environmental Review | NEW | 2024-03-19 | Submitted to Agency | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00286973 | 2023-06-06 14:29 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3386 | -122.9955 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01076916 | 2023-10-30 12:07 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-No water-out TOB, <6in cuts | 38.5164 | -123.1024 | Constrained |  |  | Environmental Review | NEW | 2024-04-29 | Submitted to AML/VegPermits | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Other Agency | NEW | N/A
CEMA | RX-00286669 | 2023-06-06 14:17 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3392 | -122.9956 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00286543 | 2023-06-06 14:11 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3391 | -122.9953 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00286472 | 2023-06-06 14:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3391 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01069662 | 2023-10-29 20:36 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.5288 | -123.1611 | Constrained |  |  | Environmental Review | NEW | 2024-04-26 | Submitted to AML/VegPermits | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00718996 | 2023-09-01 10:54 | Constrained | Not Completed | NULL | TRUE | Tier 2 | ERTC/Permit Required, Riparian-Water-in TOB, >6in cuts | 38.5307 | -123.1884 | Constrained |  |  | Environmental Review | NEW | 2024-02-28 | Submitted to AML/VegPermits | Inspected, No Work |  | NW - No Work | Delayed Approval | Closed | Constraint Resolved/Closed
CEMA | RX-01224027 | 2023-12-21 09:30 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 39.3185 | -120.4313 | Approved |  |  | Agency Managed Lands | Resolved | 2025-03-17 |  | Completed | 2025-05-05 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00286397 | 2023-06-06 14:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.339 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00286347 | 2023-06-06 13:58 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.339 | -122.9955 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00719698 | 2023-09-01 13:06 | Constrained | Not Completed | NULL | TRUE | Tier 3 | ERTC/Permit Required | 38.5549 | -123.1464 | Constrained |  |  | Environmental Review | NEW | 2024-02-28 | Submitted to AML/VegPermits | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-00286300 | 2023-06-06 13:55 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.339 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00286116 | 2023-06-06 13:48 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.339 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00286061 | 2023-06-06 13:43 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.339 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00286002 | 2023-06-06 13:39 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3389 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00285922 | 2023-06-06 13:35 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3389 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00285784 | 2023-06-06 13:26 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3389 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00285696 | 2023-06-06 13:19 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3388 | -122.9955 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00277138 | 2023-06-05 10:56 | Constrained | NULL | NULL | TRUE | Tier 3 | BLM | 39.2774 | -120.9836 | Constrained |  |  | Veg Point Refusals | NEW | 2023-12-04 | Constraint Created | Inspected, No Work |  | NW - No Work | No Work Review Req'd | Closed | Constraint Resolved/Closed
CEMA | RX-00285578 | 2023-06-06 13:14 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3386 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00285510 | 2023-06-06 13:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3386 | -122.9954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00285482 | 2023-06-06 13:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3386 | -122.9953 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | Constraint Created | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01073936 | 2023-10-30 10:09 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5181 | -121.6773 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | Constraint Created | Constrained |  | 030-Fell Tree R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01098774 | 2023-11-01 15:08 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5019 | -121.8278 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-30 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01010238 | 2023-10-18 12:12 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4601 | -121.8673 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Constraint Created | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00281103 | 2023-06-05 16:11 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.2772 | -122.6237 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-04 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Work_Refused | Resolved | Constraint Resolved/Closed
CEMA | RX-00282228 | 2023-06-05 15:23 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3388 | -122.9838 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00282227 | 2023-06-05 15:04 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3387 | -122.9837 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-01194386 | 2023-12-05 10:34 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 39.4663 | -120.9924 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-03 | Constraint Created | Inspected, No Work |  | NW - No Work | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00282225 | 2023-06-05 15:01 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3386 | -122.9836 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-01194384 | 2023-12-05 10:16 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 39.4688 | -120.9925 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-03 | Constraint Created | Inspected, No Work |  | NW - No Work | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-01032719 | 2023-10-23 09:51 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4784 | -121.8607 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00276536 | 2023-06-05 10:14 | Constrained | NULL | NULL | TRUE | Tier 3 | BLM | 39.2774 | -120.9833 | Constrained |  |  | Veg Point Refusals | NEW | 2023-12-04 | Constraint Created | Inspected, No Work |  | NW - No Work | No Work Review Req'd | Closed | Constraint Resolved/Closed
CEMA | RX-01109765 | 2023-11-06 10:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4953 | -121.8736 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00282224 | 2023-06-05 14:51 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3383 | -122.9834 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-00779895 | 2023-09-13 14:32 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.7299 | -122.3239 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-11 | Constraint Created | Constrained |  | 029-Fell Tree R1 4-11.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01098773 | 2023-11-01 15:05 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.502 | -121.8278 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-30 | Constraint Created | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00620860 | 2023-08-16 15:15 | Constrained | NULL | NULL | TRUE | Tier 2 | Work_Refused, GGNRA | 40.3966 | -122.3208 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-02-12 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00818076 | 2023-09-20 09:16 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4988 | -122.3734 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00853389 | 2023-09-25 10:59 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 39.4303 | -121.1999 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-25 | Constraint Created | Inspected, No Work |  | NW - No Work | Open Space/Regional Parks | Closed | Constraint Resolved/Closed
CEMA | RX-01064632 | 2023-10-25 14:55 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.888 | -122.296 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-24 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01092982 | 2023-11-01 12:05 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Coastal Commission | 40.4884 | -121.8837 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01194389 | 2023-12-05 10:48 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS, USFS | 39.4655 | -120.9926 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-03 | Constraint Created | Completed | 2025-04-24 10:00 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00853390 | 2023-09-25 12:10 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 39.4362 | -121.2022 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-25 | Constraint Created | Inspected, No Work |  | NW - No Work | Open Space/Regional Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00888062 | 2023-09-30 09:56 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.8451 | -122.3364 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-28 | Constraint Created | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | Constraint Created
CEMA | RX-00861807 | 2023-09-26 09:58 | Constrained | NULL | NULL | TRUE | Tier 3 | Open Space/Regional Parks | 39.438 | -121.2028 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-25 | Constraint Created | Inspected, No Work |  | NW - No Work | Open Space/Regional Parks | Closed | Constraint Resolved/Closed
CEMA | RX-00948436 | 2023-10-10 09:32 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.6387 | -122.3688 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-08 | Constraint Created | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00918326 | 2023-10-04 11:57 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 40.0188 | -121.6285 | Constrained |  |  | Veg Point Refusals | Resolved | 2025-02-27 | Constraint resolved 1/28/25 but still shows prescription status of constrained | Inspected, No Work |  | NW - No Work | CALTRANS | Closed | Constraint Resolved/Closed
CEMA | RX-00738883 | 2023-09-06 12:48 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Primary | 38.7586 | -123.3553 | Constrained |  |  | Veg Point Refusals | Closed | 2024-03-04 | Constraint resolved 10/9/23 but still shows prescription status of constrained, Another constraint was added 10/9/24 | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Primary | OPEN | N/A
CEMA | RX-00178110 | 2023-05-10 14:28 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.3429 | -123.0024 | Constrained |  |  | Veg Point Refusals | NEW | 2023-11-06 | Constraint resolved 11/19/24 but still shows prescription status of constrained | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00103014 | 2023-04-19 12:08 | Constrained | NULL | NULL | TRUE | Tier 2 | Work_Refused | 39.2131 | -121.0247 | Constrained |  |  | Veg Point Refusals | Closed | 2025-01-02 | Constraint Resolved 12/3/24 but still shows prescription status of constrained | Inspected, No Work |  | NW - No Work | Debris | Closed | Constraint Resolved/Closed
CEMA | RX-01097721 | 2023-11-02 11:33 | Constrained | NULL | NULL | TRUE | Tier 3 | USFS | 38.1857 | -119.9996 | Constrained |  |  | Veg Point Refusals | Closed | 2025-01-06 | Constraint resolved 12/5/24 but still shows prescription status of constrained, A newer constraint was added 1/6/25 | Completed | 2025-05-17 | 022-Major Dismantle R4 36-47.99 in | USFS | Closed | Tree Work Complete
CEMA | RX-01215893 | 2023-12-13 10:20 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.3008 | -120.4176 | Constrained |  |  | Veg Point Refusals | Resolved | 2025-03-14 | Constraint resolved 2/12/25 but still shows prescription status of constrained | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Tree Crew Access | NEW | N/A
CEMA | RX-00936215 | 2023-10-07 11:11 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Primary | 39.5087 | -121.3378 | Constrained |  |  | Veg Point Refusals | Closed | 2024-07-05 | Constraint resolved 6/5/24 but still shows prescription status of constrained, Another constraint was added 2/28/24 | Completed | 2025-03-21 | 021-Major Dismantle R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00990277 | 2023-10-16 09:36 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5196 | -122.7135 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | N/A | Constrained |  | 035-OFFC - Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00993319 | 2023-10-16 14:29 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5201 | -121.906 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-15 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282223 | 2023-06-05 14:45 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3383 | -122.9834 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-01017120 | 2023-10-19 12:18 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5135 | -121.955 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-16 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01025164 | 2023-10-20 13:44 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4657 | -123.0153 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-17 | N/A | Constrained |  | 036-OFFC - Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-01033031 | 2023-10-23 11:38 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4978 | -122.991 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 019-Major Dismantle R1 4-11.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-00400396 | 2023-06-29 13:32 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.2442 | -121.0104 | Constrained |  |  | Veg Point Refusals | In Progress | 2023-12-26 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-01037823 | 2023-10-24 09:44 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.7115 | -120.7508 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Resolved | Constraint Resolved/Closed
CEMA | RX-01045933 | 2023-10-24 15:05 | Constrained | NULL | NULL | TRUE | Tier 3 | Work_Refused | 38.436 | -122.5502 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Completed | 2025-04-23 | 022-Major Dismantle R4 36-47.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01053367 | 2023-10-25 11:38 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4979 | -122.9911 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 020-Major Dismantle R2 12-23.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-00193963 | 2023-05-15 13:25 | Constrained | NULL | NULL | TRUE | Tier 2 | Work_Refused | 39.2414 | -121.0301 | Constrained |  |  | Veg Point Refusals | In Progress | 2023-11-13 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Debris | OPEN | N/A
CEMA | RX-01053372 | 2023-10-25 13:29 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4972 | -122.9908 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 002-Radial 12' or greater | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-01053361 | 2023-10-25 11:12 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4978 | -122.9911 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 020-Major Dismantle R2 12-23.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-01061138 | 2023-10-26 13:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.519 | -121.9401 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-23 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01061140 | 2023-10-26 13:08 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.519 | -121.9404 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-23 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094627 | 2023-11-01 15:41 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.8897 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01095385 | 2023-11-02 09:17 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4982 | -123.0156 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-30 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-01102004 | 2023-11-02 14:28 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4877 | -121.8851 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-30 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01134247 | 2023-11-09 14:32 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.565 | -121.715 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-07 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01010340 | 2023-10-18 13:33 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4358 | -122.5499 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | N/A | Completed | 2025-04-24 | 023-Major Dismantle R5 greater than 48 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01061135 | 2023-10-26 12:56 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5188 | -121.9397 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-23 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094610 | 2023-11-01 14:48 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4691 | -121.8899 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01094611 | 2023-11-01 14:50 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4691 | -121.8899 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094617 | 2023-11-01 15:06 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4689 | -121.89 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094612 | 2023-11-01 14:54 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.8901 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094613 | 2023-11-01 14:56 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.89 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094621 | 2023-11-01 15:19 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.89 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01134245 | 2023-11-09 13:59 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5656 | -121.7197 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-07 | N/A | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01138101 | 2023-11-13 12:38 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 40.502 | -121.8311 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-13 | N/A | Completed | 2025-04-16 | 022-Major Dismantle R4 36-47.99 in | Riparian-Water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-01110418 | 2023-11-06 10:37 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.639 | -120.6338 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-04-21 07:16 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-01135362 | 2023-11-10 13:44 | Scheduled | Pending | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5016 | -121.8492 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-08 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01125473 | 2023-11-08 10:58 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.6111 | -120.5858 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-03-25 | 020-Major Dismantle R2 12-23.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01125549 | 2023-11-08 11:03 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.611 | -120.5858 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-03-25 | 020-Major Dismantle R2 12-23.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01127491 | 2023-11-08 09:59 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5079 | -121.8151 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01017113 | 2023-10-19 12:16 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5135 | -121.9551 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-16 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00393478 | 2023-06-28 14:11 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.9102 | -123.2345 | Constrained |  |  | Veg Point Refusals | NEW | 2023-12-26 | N/A | Constrained |  | 025-Targeted Prune R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-01115278 | 2023-11-06 11:05 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6404 | -120.6334 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-05-28 16:36 | 022-Major Dismantle R4 36-47.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-01143915 | 2023-11-14 09:33 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 40.5024 | -121.8316 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-13 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149510 | 2023-11-15 12:41 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5135 | -121.9089 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01126777 | 2023-11-08 12:29 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6214 | -120.5827 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-04-21 07:15 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00282222 | 2023-06-05 14:36 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3384 | -122.9834 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-01010493 | 2023-10-18 12:36 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.8802 | -122.2873 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-15 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00080388 | 2023-04-11 09:24 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 39.2047 | -121.0032 | Constrained |  |  | Veg Point Refusals | NEW | 2023-10-09 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | OPEN | N/A
CEMA | RX-00991076 | 2023-10-16 14:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.5085 | -122.7512 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00993317 | 2023-10-16 14:24 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.52 | -121.9058 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-15 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00278547 | 2023-06-05 12:23 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 39.2777 | -120.9825 | Constrained |  |  | Veg Point Refusals | In Progress | 2023-12-04 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | OPEN | N/A
CEMA | RX-01019162 | 2023-10-19 09:18 | Constrained | NULL | NULL | TRUE | Tier 3 | Hire Own Contractor | 38.5083 | -123.0726 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-16 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Hire Own Contractor | NEW | N/A
CEMA | RX-01053369 | 2023-10-25 13:14 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4979 | -122.9912 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 020-Major Dismantle R2 12-23.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-01067120 | 2023-10-27 12:52 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.541 | -122.9579 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-24 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-01094618 | 2023-11-01 15:09 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4689 | -121.89 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094622 | 2023-11-01 15:22 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4688 | -121.8899 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094624 | 2023-11-01 15:30 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4689 | -121.8898 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094625 | 2023-11-01 15:32 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4688 | -121.8898 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00181024 | 2023-05-11 10:00 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.3446 | -123.0027 | Constrained |  |  | Veg Point Refusals | NEW | 2023-11-07 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00993705 | 2023-10-16 14:44 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.6568 | -122.9608 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00194070 | 2023-05-15 13:32 | Constrained | NULL | NULL | TRUE | Tier 2 | Work_Refused | 39.2414 | -121.03 | Constrained |  |  | Veg Point Refusals | In Progress | 2023-11-13 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Debris | OPEN | N/A
CEMA | RX-01143577 | 2023-11-14 09:30 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 40.5025 | -121.8316 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-13 | N/A | Completed | 2025-04-15 | 022-Major Dismantle R4 36-47.99 in | Riparian-Water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-01149712 | 2023-11-15 14:09 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5132 | -121.9139 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282220 | 2023-06-05 14:32 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3385 | -122.9833 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01149518 | 2023-11-15 13:46 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5137 | -121.9098 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149538 | 2023-11-14 12:06 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 40.3311 | -121.9298 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-00278242 | 2023-06-05 12:12 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 39.2776 | -120.9826 | Constrained |  |  | Veg Point Refusals | In Progress | 2023-12-04 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | OPEN | N/A
CEMA | RX-01131158 | 2023-11-09 11:06 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6289 | -120.6243 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-07 | N/A | Completed | 2025-05-29 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-01190551 | 2023-12-04 13:45 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 37.1398 | -122.1521 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-03 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00686257 | 2023-08-28 16:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.7282 | -122.9094 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-26 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00902147 | 2023-10-03 11:22 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.6813 | -122.593 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00637482 | 2023-08-21 08:29 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.3765 | -122.8948 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Completed | 2025-04-18 | 021-Major Dismantle R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00637674 | 2023-08-21 10:26 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.3763 | -122.8955 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Resolved | Constraint Resolved/Closed
CEMA | RX-01017105 | 2023-10-19 12:10 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5136 | -121.9563 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-16 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01019089 | 2023-10-19 13:16 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5281 | -123.0874 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-16 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-01024567 | 2023-10-20 12:57 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5492 | -122.9709 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-17 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Request for Delay | NEW | N/A
CEMA | RX-01033033 | 2023-10-23 11:47 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4978 | -122.991 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 019-Major Dismantle R1 4-11.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-01033034 | 2023-10-23 12:10 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4978 | -122.991 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 019-Major Dismantle R1 4-11.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-01048940 | 2023-10-25 10:23 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5245 | -121.9499 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-22 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282219 | 2023-06-05 14:30 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3384 | -122.9833 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01080733 | 2023-10-31 10:50 | Constrained | NULL | NULL | TRUE | Tier 3 | Work_Refused | 38.3626 | -122.5745 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-01089751 | 2023-11-01 11:09 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5359 | -121.7371 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01067011 | 2023-10-27 12:42 | Constrained | NULL | NULL | TRUE | Tier 2 | Work_Refused | 39.1178 | -121.0854 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-24 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Debris | OPEN | N/A
CEMA | RX-01094626 | 2023-11-01 15:38 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.8897 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01125525 | 2023-11-08 11:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.6109 | -120.5857 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-03-25 | 020-Major Dismantle R2 12-23.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01149511 | 2023-11-15 12:44 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5132 | -121.909 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149513 | 2023-11-15 12:49 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.513 | -121.9089 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282217 | 2023-06-05 14:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3381 | -122.9831 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Work_Refused | NEW | N/A
CEMA | RX-00282215 | 2023-06-05 14:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3381 | -122.9831 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Work_Refused | NEW | N/A
CEMA | RX-01129248 | 2023-11-08 09:22 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5272 | -121.8331 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282213 | 2023-06-05 14:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3381 | -122.9833 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-01167520 | 2023-11-22 10:52 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.0591 | -121.0135 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-20 | N/A | Completed | 2025-04-15 | 020-Major Dismantle R2 12-23.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01174479 | 2023-11-28 10:12 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.5098 | -123.0952 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-28 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-01017148 | 2023-10-19 12:32 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5156 | -121.9493 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-16 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01017140 | 2023-10-19 12:25 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5141 | -121.9519 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-16 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00382499 | 2023-06-27 10:05 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.9145 | -123.2714 | Constrained |  |  | Veg Point Refusals | NEW | 2023-12-26 | N/A | Completed | 2025-05-29 | 026-Targeted Prune R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01051134 | 2023-10-25 13:11 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.8084 | -122.3478 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-22 | N/A | Constrained |  | 029-Fell Tree R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01053364 | 2023-10-25 11:29 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4979 | -122.9911 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 019-Major Dismantle R1 4-11.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-01064619 | 2023-10-25 12:01 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.884 | -122.2932 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-24 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00625842 | 2023-08-17 11:47 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4027 | -122.3214 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282212 | 2023-06-05 14:07 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Work_Refused | 38.3379 | -122.9834 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-01094608 | 2023-11-01 14:35 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4701 | -121.8909 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094616 | 2023-11-01 15:04 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.8901 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00282209 | 2023-06-05 14:04 | Constrained | NULL | NULL | TRUE | Non-HFTD | Work_Refused, Coastal Commission | 38.3378 | -122.9834 | Constrained |  |  | Veg Point Refusals | NEW | 2024-06-05 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-01094628 | 2023-11-01 16:02 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4704 | -121.8914 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-29 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01134246 | 2023-11-09 14:27 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5653 | -121.7153 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-07 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01114129 | 2023-11-06 14:34 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.6455 | -120.6419 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Resolved | Constraint Resolved/Closed
CEMA | RX-01115280 | 2023-11-06 12:13 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6469 | -120.6306 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Resolved | Constraint Resolved/Closed
CEMA | RX-00656988 | 2023-08-23 11:52 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.3691 | -122.8966 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Completed | 2025-06-27 13:28 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Resolved | Constraint Resolved/Closed
CEMA | RX-00269856 | 2023-06-01 12:23 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3189 | -122.9211 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-31 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00323717 | 2023-06-13 13:31 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.678 | -123.4946 | Constrained |  |  | Veg Point Refusals | NEW | 2023-12-11 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Work_Refused | NEW | N/A
CEMA | RX-01017098 | 2023-10-19 12:03 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5148 | -121.9578 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-16 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01030505 | 2023-10-23 11:06 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4979 | -122.9911 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 020-Major Dismantle R2 12-23.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-00625840 | 2023-08-17 11:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4027 | -122.3215 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-13 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00269851 | 2023-06-01 12:18 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3195 | -122.9216 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-31 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00637496 | 2023-08-21 10:15 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.3765 | -122.8956 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Resolved | Constraint Resolved/Closed
CEMA | RX-00647176 | 2023-08-22 09:50 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay, Request For Delay | 38.8407 | -122.5512 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | OPEN | N/A
CEMA | RX-00721566 | 2023-09-02 11:38 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.6582 | -122.3945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-29 | N/A | Constrained |  | 024-Targeted Prune R1 4-11.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00844050 | 2023-09-23 14:41 | Constrained | Not Completed | NULL | TRUE | Tier 2 | NULL | 38.5894 | -123.1181 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-21 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00901607 | 2023-10-03 11:13 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused, Work_Refused | 38.6811 | -122.5925 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | N/A | Inspected, Prescribed |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-01032903 | 2023-10-23 13:19 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.6889 | -122.0216 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-22 | N/A | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01036838 | 2023-10-24 08:36 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.7115 | -120.7529 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Resolved | Constraint Resolved/Closed
CEMA | RX-01052323 | 2023-10-25 14:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.922 | -120.8418 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-22 | N/A | Completed | 2025-05-09 | 021-Major Dismantle R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01058072 | 2023-10-26 11:10 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.7987 | -122.3486 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-23 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00260718 | 2023-05-31 13:22 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3336 | -122.9699 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01089444 | 2023-11-01 11:14 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5918 | -122.2453 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-29 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01068083 | 2023-10-27 11:10 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-No water-out TOB, >6in cuts | 38.5414 | -122.634 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-24 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Request for Delay | NEW | N/A
CEMA | RX-01094619 | 2023-11-01 15:12 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.8899 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094614 | 2023-11-01 14:58 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.4691 | -121.8901 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01069995 | 2023-10-30 08:39 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6203 | -120.6001 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Completed | 2025-04-14 12:14 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00260581 | 2023-05-31 13:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3336 | -122.9699 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00260491 | 2023-05-31 13:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3336 | -122.9701 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01070088 | 2023-10-30 08:51 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6208 | -120.5988 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Resolved | Constraint Resolved/Closed
CEMA | RX-01111308 | 2023-11-06 10:58 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5019 | -121.7417 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-06 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01141947 | 2023-11-14 09:26 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 40.5026 | -121.8316 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-13 | N/A | Completed | 2025-06-04 | 022-Major Dismantle R4 36-47.99 in | Riparian-Water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-01149517 | 2023-11-15 13:19 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5135 | -121.9094 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149526 | 2023-11-15 13:52 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5136 | -121.9101 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00454588 | 2023-07-13 09:37 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4346 | -122.3926 | Constrained |  |  | Veg Point Refusals | NEW | 2024-01-09 | N/A | Constrained |  | 002-Radial 12' or greater | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149512 | 2023-11-15 12:46 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.513 | -121.9089 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149520 | 2023-11-15 13:49 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5136 | -121.91 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00260458 | 2023-05-31 13:08 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3336 | -122.9701 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01161032 | 2023-11-20 10:20 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6336 | -120.5508 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-20 | N/A | Completed | 2025-04-21 07:16 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-01161035 | 2023-11-20 10:22 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6336 | -120.5508 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-20 | N/A | Completed | 2025-04-21 07:16 | 019-Major Dismantle R1 4-11.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00260408 | 2023-05-31 13:05 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3336 | -122.9701 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01181739 | 2023-11-29 11:14 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.0483 | -121.0466 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-28 | N/A | Completed | 2025-07-15 | 020-Major Dismantle R2 12-23.99 in | Debris | Closed | Tree Work Complete
CEMA | RX-00628958 | 2023-08-17 12:13 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.3839 | -122.8898 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-13 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-00637757 | 2023-08-21 10:32 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.377 | -122.8956 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Resolved | Constraint Resolved/Closed
CEMA | RX-00954318 | 2023-10-10 11:06 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 36.3881 | -121.869 | Scheduled |  |  | Veg Point Refusals | Closed | 2025-03-17 |  | Completed | 2025-03-13 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-01053368 | 2023-10-25 11:53 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.4975 | -122.9908 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-22 | N/A | Inspected, Prescribed |  | 021-Major Dismantle R3 24-35.99 in | Min. Clearance Requested | Closed | Constraint Resolved/Closed
CEMA | RX-00260263 | 2023-05-31 12:59 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3337 | -122.9702 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01087198 | 2023-11-01 07:51 | Constrained | NULL | NULL | TRUE | Tier 3 | Riparian-No water-in TOB, <6in cuts | 38.5397 | -122.6239 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Inspected, No Work |  | NW - No Work | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-01061145 | 2023-10-26 13:21 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5193 | -121.9393 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-23 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01066596 | 2023-10-27 08:55 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.5095 | -121.9522 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-24 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00260206 | 2023-05-31 12:54 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3337 | -122.9703 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01094620 | 2023-11-01 15:16 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.8898 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01094615 | 2023-11-01 15:01 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.469 | -121.89 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-29 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01111301 | 2023-11-06 10:45 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5018 | -121.7417 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-06 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-01149523 | 2023-11-14 12:02 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 40.3313 | -121.9295 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Closed | Constraint Resolved/Closed
CEMA | RX-01125944 | 2023-11-08 11:26 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.6212 | -120.5836 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Completed | 2025-04-21 07:16 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-01150050 | 2023-11-15 13:19 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Extra Work Needed | 37.1399 | -122.1506 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-13 | N/A | Completed | 2025-03-18 | 022-Major Dismantle R4 36-47.99 in | Extra Work Needed | Closed | Tree Work Complete
CEMA | RX-01129002 | 2023-11-08 14:14 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Delayed Approval | 39.1011 | -121.1647 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Inspected, No Work |  | NW - No Work | Riparian | Closed | Constraint Resolved/Closed
CEMA | RX-01174883 | 2023-11-28 10:55 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.5303 | -123.0954 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-28 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Work_Refused | NEW | N/A
CEMA | RX-00746014 | 2023-09-07 12:55 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.6165 | -122.4861 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-05 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00764019 | 2023-09-11 09:42 | Constrained | Not Completed | NULL | TRUE | Tier 2 | NULL | 39.2025 | -121.1343 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-11 | N/A | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Work_Refused | NEW | N/A
CEMA | RX-00799718 | 2023-09-18 08:58 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4983 | -122.3726 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00839291 | 2023-09-22 11:43 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.7472 | -122.8518 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-20 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00845443 | 2023-09-25 09:23 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5503 | -122.2222 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-25 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00800171 | 2023-09-18 09:31 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4982 | -122.3725 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00803633 | 2023-09-18 13:18 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.6254 | -122.4138 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 026-Targeted Prune R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00258303 | 2023-05-31 10:34 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3187 | -122.9831 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00258261 | 2023-05-31 10:32 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3187 | -122.9833 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-30 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00625848 | 2023-08-17 11:54 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4026 | -122.3214 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-13 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00645868 | 2023-08-22 10:49 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.3944 | -122.8945 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | N/A | Completed | 2025-04-17 | 021-Major Dismantle R3 24-35.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00799588 | 2023-09-18 08:44 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.4983 | -122.3727 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 025-Targeted Prune R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00811022 | 2023-09-19 11:32 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.6389 | -122.8521 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-00903805 | 2023-10-03 13:02 | Constrained | NULL | NULL | TRUE | Tier 3 | Hire Own Contractor | 38.763 | -122.8918 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Hire Own Contractor | NEW | N/A
CEMA | RX-00256758 | 2023-05-30 15:31 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3065 | -122.9211 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-29 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00256757 | 2023-05-30 15:06 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3194 | -122.9202 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-29 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00245029 | 2023-05-25 15:44 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Delayed Approval | 38.2791 | -122.6198 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-24 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Delayed Approval | Closed | Constraint Resolved/Closed
CEMA | RX-00245028 | 2023-05-25 15:41 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Delayed Approval | 38.2791 | -122.6198 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-24 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Delayed Approval | Closed | Constraint Resolved/Closed
CEMA | RX-00245025 | 2023-05-25 15:37 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Delayed Approval | 38.2791 | -122.6198 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-24 | Customer Interference Process Being Followed | Inspected, No Work |  | NW - No Work | Delayed Approval | Closed | Constraint Resolved/Closed
CEMA | RX-00818865 | 2023-09-20 10:11 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5112 | -122.3918 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00898067 | 2023-10-03 08:17 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4658 | -122.6903 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00913072 | 2023-10-04 12:01 | Constrained | NULL | NULL | TRUE | Tier 2 | Work_Refused | 38.7258 | -122.979 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-04-01 | N/A | Completed | 2025-07-07 10:46 | 020-Major Dismantle R2 12-23.99 in | Riparian | Resolved | Constraint Resolved/Closed
CEMA | RX-00938329 | 2023-10-05 08:50 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4661 | -122.6838 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-08 | N/A | Constrained |  | 035-OFFC - Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00446000 | 2023-07-11 09:23 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.2873 | -122.5603 | Constrained |  |  | Veg Point Refusals | NEW | 2024-01-08 | N/A | Inspected, No Work |  | NW - No Work | Work_Refused | Resolved | Constraint Resolved/Closed
CEMA | RX-00611649 | 2023-08-15 14:17 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.3853 | -122.8819 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-12 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00808511 | 2023-09-19 08:53 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.6341 | -122.8582 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-00852167 | 2023-09-25 15:41 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.8111 | -122.319 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-03-25 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | OPEN | N/A
CEMA | RX-00878454 | 2023-09-28 14:25 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.4839 | -122.6765 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-26 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00955065 | 2023-10-10 11:17 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 36.3882 | -121.8694 | Scheduled |  |  | Veg Point Refusals | Closed | 2025-03-17 |  | Completed | 2025-03-13 | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00913159 | 2023-10-04 12:20 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Min. Clearance Requested | 38.7948 | -123.0371 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00938352 | 2023-10-05 09:28 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4631 | -122.684 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-08 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00934163 | 2023-10-06 11:47 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4682 | -122.6889 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-03 | N/A | Constrained |  | 036-OFFC - Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00934169 | 2023-10-06 12:29 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.468 | -122.6888 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-03 | N/A | Constrained |  | 036-OFFC - Major Dismantle R3 24-35.99 in | Request for Delay | NEW | N/A
CEMA | RX-00952362 | 2023-10-10 12:29 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.8318 | -122.9979 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-08 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Work_Refused | NEW | N/A
CEMA | RX-00979593 | 2023-10-13 10:52 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.5034 | -122.7377 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-10 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Work_Refused | NEW | N/A
CEMA | RX-00969303 | 2023-10-12 10:04 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.6214 | -122.7547 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-09 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00930904 | 2023-10-06 10:45 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.412 | -122.6495 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-03 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Request for Delay | NEW | N/A
CEMA | RX-00241110 | 2023-05-25 09:53 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 40.3955 | -122.2321 | Constrained |  |  | Veg Point Refusals | In Progress | 2025-01-15 | Constraint Created | Constrained |  | NW - No Work | No Work Review Req'd | OPEN | N/A
CEMA | RX-00971775 | 2023-10-12 11:51 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 38.5501 | -123.2441 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-09 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00970354 | 2023-10-12 10:45 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.5838 | -122.3026 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-09 | N/A | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00971065 | 2023-10-12 11:15 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Work_Refused | 38.8373 | -122.9968 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-09 | N/A | Completed | 2025-06-18 | 022-Major Dismantle R4 36-47.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-00980784 | 2023-10-13 12:08 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.4966 | -122.695 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-10 | N/A | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-01066017 | 2023-10-27 09:40 | Inspected, Prescribed | Not Completed | NULL | TRUE | Tier 3 | NULL | 38.4212 | -122.9506 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-24 | N/A | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00711540 | 2023-08-31 12:35 | Scheduled | Pending | NULL | TRUE | Tier 3 | NULL | 38.544 | -123.0885 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-27 | N/A | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Site-Specific ERTC | NEW | N/A
CEMA | RX-01111900 | 2023-11-06 12:13 | Constrained | Not Completed | NULL | TRUE | Tier 3 | NULL | 37.0621 | -121.9871 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | N/A | Inspected, No Work |  | NW - No Work | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-01008282 | 2023-10-18 14:10 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.775 | -122.3115 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00955069 | 2023-10-10 11:21 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Delayed Approval | 36.3881 | -121.8693 | Scheduled |  |  | Veg Point Refusals | Closed | 2025-03-17 |  | Completed | 2025-03-13 | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | Closed | Tree Work Complete
CEMA | RX-00989865 | 2023-10-16 13:01 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.9162 | -122.4344 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00991545 | 2023-10-16 14:21 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.9163 | -122.4347 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00990488 | 2023-10-16 13:35 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.9163 | -122.4349 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-01008501 | 2023-10-18 14:19 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.775 | -122.311 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00817522 | 2023-09-19 16:11 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.7488 | -122.3204 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-18 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00883241 | 2023-09-29 10:35 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.7336 | -122.3669 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-27 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00860961 | 2023-09-26 14:11 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.7474 | -122.2372 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-25 | Released by ERTC/Permit | Constrained |  | 019-Major Dismantle R1 4-11.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00850702 | 2023-09-25 14:23 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.84 | -122.3598 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-25 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00877524 | 2023-09-28 13:35 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.8953 | -122.3719 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-26 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00883300 | 2023-09-29 10:39 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.7338 | -122.3668 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-27 | Released by ERTC/Permit | Constrained |  | 021-Major Dismantle R3 24-35.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00909804 | 2023-10-04 09:53 | Constrained | NULL | NULL | TRUE | Tier 2 | CalTrans | 36.5705 | -121.7654 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | Released by ERTC/Permit | Completed | 2025-07-10 | 002-Radial 12' or greater | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00888058 | 2023-09-30 09:55 | Constrained | Not Completed | NULL | TRUE | Tier 3 | No Work Review Reqd | 40.845 | -122.3362 | Constrained |  |  | Veg Point Refusals | NEW | 2024-03-28 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00963157 | 2023-10-11 13:09 | Constrained | Not Completed | NULL | TRUE | Tier 2 | No Work Review Reqd | 40.8128 | -122.297 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-08 | Released by ERTC/Permit | Constrained |  | 020-Major Dismantle R2 12-23.99 in | No Work Review Req'd | NEW | N/A
CEMA | RX-00219965 | 2023-05-22 09:49 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 40.6787 | -124.2287 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-21 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00215145 | 2023-05-19 09:52 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 40.6578 | -124.2086 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-20 | Submitted to AML/VegPermits | Completed | 2025-06-17 14:31 | 019-Major Dismantle R1 4-11.99 in | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00210575 | 2023-05-18 11:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 40.6611 | -124.2196 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-17 | Submitted to Agency | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00194264 | 2023-05-15 12:18 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 37.2363 | -122.1472 | Constrained |  |  | Veg Point Refusals | NEW | 2023-11-13 | Submitted to Agency | Completed | 2025-06-11 | 023-Major Dismantle R5 greater than 48 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00202716 | 2023-05-17 09:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 40.7027 | -124.2047 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-16 | Submitted to Agency | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | Released by ERTC/Permit
CEMA | RX-00194262 | 2023-05-15 11:58 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 37.2364 | -122.1472 | Constrained |  |  | Veg Point Refusals | NEW | 2023-11-13 | Submitted to Agency | Completed | 2025-06-10 | 023-Major Dismantle R5 greater than 48 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00195945 | 2023-05-15 15:59 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3492 | -123.0619 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-14 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00195812 | 2023-05-15 15:48 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.349 | -123.0617 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-14 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00194555 | 2023-05-15 12:23 | Constrained | Not Completed | NULL | TRUE | Tier 2 | CalTrans | 37.2364 | -122.1472 | Constrained |  |  | Veg Point Refusals | NEW | 2023-11-13 | Submitted to Agency | Completed | 2025-06-17 | 022-Major Dismantle R4 36-47.99 in | Request for Delay | Closed | Tree Work Complete
CEMA | RX-00182448 | 2023-05-11 12:00 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4012 | -123.8025 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-10 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00173011 | 2023-05-09 15:12 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 38.447 | -122.8903 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-08 | Customer Interference Process Being Followed | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Work_Refused | NEW | N/A
CEMA | RX-00173004 | 2023-05-09 15:09 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | No Work Review Reqd | 38.4469 | -122.8903 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-08 | Constraint resolved 1/28/25 but still shows prescription status of constrained | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Work_Refused | NEW | N/A
CEMA | RX-00145099 | 2023-05-02 13:09 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 39.2702 | -123.2056 | Constrained |  |  | Agency Managed Lands | NEW | 2024-05-01 | Submitted to AML/VegPermits | Completed | 2025-04-16 | 021-Major Dismantle R3 24-35.99 in | City/County | Closed | Tree Work Complete
CEMA | RX-00103732 | 2023-04-19 13:35 | Scheduled | Not Completed | NULL | TRUE | Tier 3 | NULL | 37.1083 | -122.1137 | Constrained |  |  | Veg Point Refusals | NEW | 2023-10-16 | Submitted to Agency | Completed | 2025-05-21 | 027-Targeted Prune R4 36-47.99 in | CALTRANS | Closed | Tree Work Complete
CEMA | RX-01019078 | 2023-10-19 12:04 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5237 | -123.0889 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-16 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00141645 | 2023-05-01 16:00 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3682 | -123.0644 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | In Environmental Review | Scheduled |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00139141 | 2023-05-01 12:15 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.4383 | -122.8527 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-30 | Customer Interference Process Being Followed | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00138427 | 2023-05-01 11:15 | Constrained | NULL | NULL | TRUE | Non-HFTD | City/County | 37.6125 | -122.4773 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | Constraint Created | Completed | 2025-06-11 | 021-Major Dismantle R3 24-35.99 in | Riparian-Water-out TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00138200 | 2023-05-01 10:52 | Constrained | NULL | NULL | TRUE | Non-HFTD | Nest-Raptor- Adjacent to identified worked, Coastal Commission | 38.3395 | -123.0493 | Constrained |  |  | Environmental Review | NEW | 2024-04-30 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-01133376 | 2023-11-09 12:05 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 40.5317 | -121.6381 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-07 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-00137235 | 2023-05-01 09:27 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3222 | -123.0358 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-30 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01076158 | 2023-10-30 10:40 | Constrained | NULL | NULL | TRUE | Tier 3 | NULL | 38.5072 | -123.1313 | Approved |  |  | Contact | Resolved | 2025-03-10 |  | Completed | 2025-03-10 | 021-Major Dismantle R3 24-35.99 in | Customer Communication | Closed | Tree Work Complete
CEMA | RX-00126614 | 2023-04-26 15:16 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Coastal Commission | 39.3849 | -123.8128 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-25 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | N/A
CEMA | RX-00125289 | 2023-04-26 13:11 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3367 | -123.0493 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00124969 | 2023-04-26 12:34 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Coastal Commission | 39.3901 | -123.8141 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00990722 | 2023-10-16 13:19 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Other | 38.5266 | -123.0871 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00124894 | 2023-04-26 12:28 | Constrained | NULL | NULL | TRUE | Non-HFTD | Nest-Raptor- Adjacent to identified worked, Coastal Commission | 38.3372 | -123.0506 | Constrained |  |  | Environmental Review | NEW | 2024-04-25 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Resolved | Constraint Resolved/Closed
CEMA | RX-00124593 | 2023-04-26 11:54 | Constrained | NULL | NULL | TRUE | Non-HFTD | Nest-Raptor- Adjacent to identified worked, Coastal Commission | 38.3367 | -123.0486 | Constrained |  |  | Environmental Review | NEW | 2024-04-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Nest | NEW | N/A
CEMA | RX-00870425 | 2023-09-27 12:24 | Inspected, Prescribed | Not Completed | NULL | TRUE | Tier 2 | NULL | 40.5438 | -122.232 | Scheduled |  |  | Veg Point Refusals | Resolved | 2025-03-17 |  | Completed | 2025-03-26 | 025-Targeted Prune R2 12-23.99 in | Work_Refused | Closed | Tree Work Complete
CEMA | RX-01009707 | 2023-10-18 10:41 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5262 | -123.0903 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Submitted to AML/VegPermits | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Request for Delay | NEW | N/A
CEMA | RX-00124584 | 2023-04-26 11:53 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission, Nest-Active- Nest removed (non raptor) | 38.3367 | -123.0486 | Constrained |  |  | Environmental Review | NEW | 2024-04-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Nest | NEW | N/A
CEMA | RX-00124472 | 2023-04-26 11:44 | Constrained | NULL | NULL | TRUE | Non-HFTD | Riparian-Water-in TOB, >6in cuts, Nest-Raptor- Adjacent to identified worked, Coastal Commission | 38.3368 | -123.0486 | Constrained |  |  | Environmental Review | NEW | 2024-04-25 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00990764 | 2023-10-16 13:44 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Other | 38.5267 | -123.0888 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Request for Delay | NEW | N/A
CEMA | RX-00122326 | 2023-04-26 06:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3421 | -123.0457 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-25 | In Environmental Review | Completed | 2025-07-11 | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | Resolved | Tree Work Complete
CEMA | RX-01071330 | 2023-10-30 10:14 | Constrained | NULL | NULL | TRUE | Tier 2 | NULL | 38.5054 | -123.1316 | Approved |  |  | Contact | Resolved | 2025-03-10 |  | Completed | 2025-03-10 | 020-Major Dismantle R2 12-23.99 in | Customer Communication | Closed | Tree Work Complete
CEMA | RX-00122325 | 2023-04-26 06:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3412 | -123.0489 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-25 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-01009658 | 2023-10-18 10:24 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5262 | -123.0911 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-15 | Submitted to AML/VegPermits | Constrained |  | 037-OFFC- Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00121567 | 2023-04-25 15:19 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4044 | -123.8069 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01076160 | 2023-10-30 10:48 | Constrained | NULL | NULL | TRUE | Tier 3 | NULL | 38.5068 | -123.1311 | Approved |  |  | Contact | Resolved | 2025-03-10 |  | Completed | 2025-03-10 | 021-Major Dismantle R3 24-35.99 in | Customer Communication | Closed | Tree Work Complete
CEMA | RX-00119767 | 2023-04-25 12:37 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.3934 | -123.8138 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Constraint resolved 12/5/24 but still shows prescription status of constrained, A newer constraint was added 1/6/25 | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00119766 | 2023-04-25 12:37 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.3932 | -123.8137 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-24 | Constraint resolved 3/18/24 but still shows prescription status of constrained, A newer constraint was added 4/22/24 | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00118542 | 2023-04-25 10:38 | Constrained | NULL | NULL | TRUE | Non-HFTD | Nest-Raptor- Adjacent to identified worked, Coastal Commission | 38.3389 | -123.0546 | Constrained |  |  | Environmental Review | NEW | 2024-04-24 | In Environmental Review | Constrained |  | 019-Major Dismantle R1 4-11.99 in | Nest | NEW | N/A
CEMA | RX-00116526 | 2023-04-24 15:12 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.3957 | -123.8127 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00116515 | 2023-04-24 15:10 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Coastal Commission | 39.401 | -123.8199 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00116514 | 2023-04-24 15:10 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4011 | -123.8193 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00116511 | 2023-04-24 15:10 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4011 | -123.8193 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | N/A
CEMA | RX-00116510 | 2023-04-24 15:10 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4011 | -123.8193 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00114209 | 2023-04-24 11:00 | Constrained | NULL | NULL | TRUE | Non-HFTD | State Parks, Coastal Commission | 38.3443 | -123.0533 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00113932 | 2023-04-24 10:33 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3475 | -123.0543 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-23 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00112374 | 2023-04-21 15:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4051 | -123.8144 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00112373 | 2023-04-21 15:13 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4052 | -123.8139 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-22 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00108389 | 2023-04-20 14:29 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3263 | -123.0566 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-19 | Constraint resolved 9/25/23 but still shows prescription status of constrained, A newer constraint was added 2/28/24 | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Nest | NEW | Constraint Created
CEMA | RX-00107253 | 2023-04-20 12:30 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4085 | -123.8069 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-19 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00106770 | 2023-04-20 11:21 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4098 | -123.8129 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-19 | In Environmental Review | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01133366 | 2023-11-09 11:37 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 40.531 | -121.6391 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-07 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | CALTRANS | NEW | N/A
CEMA | RX-01019075 | 2023-10-19 11:58 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Request For Delay | 38.5238 | -123.0891 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-16 | Submitted to AML/VegPermits | Constrained |  | 022-Major Dismantle R4 36-47.99 in | Request for Delay | NEW | N/A
CEMA | RX-00104573 | 2023-04-19 15:11 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4146 | -123.8054 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00104552 | 2023-04-19 15:07 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4148 | -123.8056 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-18 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00104520 | 2023-04-19 15:02 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4147 | -123.8054 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-18 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00103993 | 2023-04-19 14:00 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 38.3492 | -123.0538 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-18 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00100678 | 2023-04-18 14:59 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4155 | -123.8092 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-17 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00099268 | 2023-04-18 12:11 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4194 | -123.8125 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-17 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00096363 | 2023-04-17 14:42 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4072 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00095223 | 2023-04-17 12:39 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.3959 | -123.8124 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01026375 | 2023-10-20 10:42 | Constrained | Not Completed | NULL | TRUE | Tier 3 | Other | 38.5288 | -123.087 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-17 | Submitted to AML/VegPermits | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Request for Delay | NEW | N/A
CEMA | RX-00094956 | 2023-04-17 11:50 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4054 | -123.8019 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00093839 | 2023-04-17 09:46 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4072 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01133368 | 2023-11-09 11:40 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 40.5311 | -121.6391 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-07 | Submitted to AML/VegPermits | Constrained |  | 020-Major Dismantle R2 12-23.99 in | CALTRANS | NEW | N/A
CEMA | RX-01129212 | 2023-11-08 15:28 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 40.5176 | -121.6955 | Constrained |  |  | Veg Point Refusals | NEW | 2024-05-06 | Submitted to AML/VegPermits | Constrained |  | 023-Major Dismantle R5 greater than 48 in | CALTRANS | NEW | N/A
CEMA | RX-01135226 | 2023-11-10 09:18 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.101 | -121.1503 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-08 | #N/A | Completed | 2025-03-07 | 021-Major Dismantle R3 24-35.99 in | Riparian-Water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00093802 | 2023-04-17 09:41 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4072 | -123.8029 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-01135227 | 2023-11-10 09:20 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Work_Refused | 39.101 | -121.1503 | Constrained |  |  | Veg Point Refusals | In Progress | 2024-05-08 | #N/A | Completed | 2025-03-07 | 021-Major Dismantle R3 24-35.99 in | Riparian-Water-in TOB, >6in cuts | Closed | Tree Work Complete
CEMA | RX-00658495 | 2023-08-23 14:00 | Constrained | NULL | NULL | TRUE | Tier 3 | CDFW | 37.0561 | -122.142 | Constrained |  |  | Veg Point Refusals | NEW | 2024-02-20 | #N/A | Completed | 2025-03-26 11:31 | 020-Major Dismantle R2 12-23.99 in | Request for Delay | Closed | Constraint Resolved/Closed
CEMA | RX-00093576 | 2023-04-17 09:11 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4066 | -123.803 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-16 | In Environmental Review | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00090636 | 2023-04-14 08:47 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.4093 | -123.799 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-15 | In Environmental Review | Inspected, No Work |  | NW - No Work | Coastal Commission | Closed | Constraint Resolved/Closed
CEMA | RX-00089593 | 2023-04-13 14:24 | Constrained | NULL | NULL | TRUE | Non-HFTD | Coastal Commission | 39.403 | -123.8028 | Constrained |  |  | Agency Managed Lands | NEW | 2024-04-12 | In Environmental Review | Constrained |  | 021-Major Dismantle R3 24-35.99 in | Coastal Commission | NEW | In Environmental Review
CEMA | RX-00088638 | 2023-04-13 11:57 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.3569 | -122.7836 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-12 | Customer Interference Process Being Followed | Constrained |  | 023-Major Dismantle R5 greater than 48 in | Work_Refused | NEW | N/A
CEMA | RX-00069982 | 2023-04-05 09:58 | Constrained | Not Completed | NULL | TRUE | Non-HFTD | Work_Refused | 38.4165 | -122.8333 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-04 | Customer Interference Process Being Followed | Constrained |  | 020-Major Dismantle R2 12-23.99 in | Work_Refused | NEW | N/A
CEMA | RX-00893169 | 2023-10-02 12:05 | Constrained | Not Completed | NULL | TRUE | Tier 2 | Request For Delay | 38.7885 | -123.1206 | Constrained |  |  | Veg Point Refusals | NEW | 2024-04-01 | #N/A | Completed | 2025-03-27 | 021-Major Dismantle R3 24-35.99 in | Request for Delay | Closed | Tree Work Complete